## Sheet1
ID | TaskType | Label | PlannedStart | PlannedEnd | ActualStart | ActualEnd | Float | Status
303 | TT_TASK | MSFT Issue DRB #1 for Review | Tue May 26 07:00:00 IDT 2020 | Mon Jun 01 17:00:00 IDT 2020 | Tue May 19 00:00:00 IDT 2020 | Mon Jul 20 00:00:00 IDT 2020 |  | COMPLETED
306 | TT_TASK | Lead Time for PEMB | Wed Feb 19 08:00:00 IST 2020 | Thu Jun 18 17:00:00 IDT 2020 | Mon Feb 24 00:00:00 IST 2020 | Thu Jun 18 00:00:00 IDT 2020 |  | COMPLETED
307 | TT_TASK | Lead Time for Rebar (Footings & Walls) | Mon Apr 27 08:00:00 IDT 2020 | Sun May 31 17:00:00 IDT 2020 | Mon Mar 30 00:00:00 IDT 2020 | Tue Apr 21 00:00:00 IDT 2020 |  | COMPLETED
308 | TT_TASK | Lead Time for COLO 1 Structural Interior Steel | Mon Aug 10 08:00:00 IDT 2020 | Sat Oct 31 17:00:00 IST 2020 | Tue Jun 30 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
309 | TT_TASK | Lead Time for Wall & Roof Metal Panels | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Mon Jun 29 00:00:00 IDT 2020 |  | COMPLETED
310 | TT_TASK | Lead Time for Admin/COLO 1 Yard Steel | Mon Aug 31 08:00:00 IDT 2020 | Sun Oct 18 17:00:00 IDT 2020 | Tue Jun 30 00:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 |  | COMPLETED
311 | TT_TASK | Lead Time for HM Ext. frames | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
312 | TT_TASK | Lead time for Drywall/Framing | Mon Aug 10 08:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Mon Aug 10 08:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
592 | TT_TASK | MV Ductbanks Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | Mon Sep 14 08:00:00 IDT 2020 | Sun Sep 20 17:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 | Sun Sep 06 00:00:00 IDT 2020 |  | COMPLETED
593 | TT_TASK | MV Wire Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | Wed Aug 12 08:00:00 IDT 2020 | Tue Nov 03 17:00:00 IST 2020 | Tue Aug 04 00:00:00 IDT 2020 | Mon Oct 26 00:00:00 IST 2020 |  | COMPLETED
594 | TT_TASK | UMS Vault Procurement DRB#1 | Mon Sep 28 08:00:00 IDT 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
595 | TT_TASK | DRB#1 BIM Modeling & Coordination DRB#1 JAZ to UMS/URS & UPM to UMS | Mon Aug 10 08:00:00 IDT 2020 | Sun Aug 23 17:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
596 | TT_TASK | Site- Neher Mcgrath Study DRB#1 JAZ to UMS/URS & UPM to UMS | Tue Aug 11 08:00:00 IDT 2020 | Mon Aug 24 17:00:00 IDT 2020 | Tue Aug 04 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
597 | TT_TASK | JAZ Riser Support DRB#1 Procurement/ Jaz Foundations/Construction | Mon Aug 10 08:00:00 IDT 2020 | Sun Oct 18 17:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
598 | TT_TASK | UPM to UMS Vaults Procurement DRB#1 | Tue Sep 08 08:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
600 | TT_TASK | MV Ductbanks Procurement | Wed Aug 12 08:00:00 IDT 2020 | Thu Aug 20 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
601 | TT_TASK | Telecom DuctBank / Vaults Procurement | Thu May 14 08:00:00 IDT 2020 | Mon May 18 17:00:00 IDT 2020 | Wed May 06 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
602 | TT_TASK | MV Wire Procurement | Wed Aug 12 08:00:00 IDT 2020 | Tue Nov 03 17:00:00 IST 2020 | Tue Jul 21 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
603 | TT_TASK | Off-Site BIM Modeling & Coordination | Mon Apr 27 08:00:00 IDT 2020 | Sun May 24 17:00:00 IDT 2020 | Tue Apr 14 00:00:00 IDT 2020 | Tue May 05 00:00:00 IDT 2020 |  | COMPLETED
604 | TT_TASK | Neher Mcgrath Study | Thu Jul 02 08:00:00 IDT 2020 | Thu Aug 06 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Fri Jul 24 00:00:00 IDT 2020 |  | COMPLETED
605 | TT_TASK | URS Vault Procurement | Mon Sep 28 08:00:00 IDT 2020 | Wed Nov 11 17:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
607 | TT_TASK | Site Temp Power Procurement & Infrastructure | Mon Jun 29 08:00:00 IDT 2020 | Mon Aug 31 08:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
609 | TT_TASK | Underground Grounding Procurement | Mon Apr 27 08:00:00 IDT 2020 | Sun May 17 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Tue Apr 28 00:00:00 IDT 2020 |  | COMPLETED
610 | TT_TASK | BIM Modeling (Under ground) | Tue May 05 08:00:00 IDT 2020 | Mon Jun 08 17:00:00 IDT 2020 | Tue May 05 08:00:00 IDT 2020 | Mon Jun 08 00:00:00 IDT 2020 |  | COMPLETED
611 | TT_TASK | Electrical Long Lead Equipment Procurement (Cablebus, Panel Boards) | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Mon Apr 27 08:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
612 | TT_TASK | BIM Modeling (Above ground) | Sun Aug 02 08:00:00 IDT 2020 | Wed Sep 30 17:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
615 | TT_TASK | Design / Lead Time for Electrical/Telecom (OFCI Telecom BOM Materials) | Mon Aug 10 08:00:00 IDT 2020 | Sat Nov 07 17:00:00 IST 2020 | Wed Jul 01 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
616 | TT_TASK | Design / Lead Time for Busway (OFCI Starline BOM Materials) | Thu Nov 26 08:00:00 IST 2020 | Thu Jan 14 17:00:00 IST 2021 | Mon Sep 21 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
619 | TT_TASK | Water treatment Skids Procurement ( sourcing materials and Materail approval only) | Mon Apr 27 08:00:00 IDT 2020 | Fri Nov 06 12:00:00 IST 2020 | Tue Apr 07 00:00:00 IDT 2020 | Mon Jul 06 00:00:00 IDT 2020 |  | COMPLETED
620 | TT_TASK | Design / Lead Time for M&P overhead | Mon Jun 29 08:00:00 IDT 2020 | Tue Jul 28 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
621 | TT_TASK | Design / Lead Time for Fire Protection | Mon Aug 31 08:00:00 IDT 2020 | Tue Sep 29 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
622 | TT_TASK | Design / Lead Time for Fire Alarm | Mon Jun 29 08:00:00 IDT 2020 | Thu Aug 27 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
628 | TT_TASK | URS/UMS Concrete Anchor and Vault Design | Mon Aug 10 07:00:00 IDT 2020 | Wed Aug 26 17:00:00 IDT 2020 | Wed Aug 05 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
629 | TT_TASK | URS/UMS Vault Submiital Review by EOR | Mon Sep 14 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Fri Sep 25 00:00:00 IDT 2020 |  | COMPLETED
632 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-2 PSR(10/13) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sat Dec 12 17:00:00 IST 2020 | Tue Oct 13 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
633 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-3 PSR(9/28) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Mon Dec 28 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
634 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-4 PSR (10/28) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Fri Nov 27 16:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
635 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-1 PSR (9/19) to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Tue Dec 15 17:00:00 IST 2020 | Sat Sep 19 00:00:00 IDT 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
637 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-1 11/25 to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Fri Oct 09 17:00:00 IDT 2020 | Wed Nov 25 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
638 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-2 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sun Nov 15 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
639 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-4 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Fri Nov 06 16:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
640 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-3 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sun Nov 15 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
642 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-1 PSR 11/23 to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Wed Oct 14 17:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
643 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-2 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
644 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-4 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Wed Nov 11 16:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Sun Jan 03 00:00:00 IST 2021 |  | COMPLETED
645 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-3 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Sun Jan 03 00:00:00 IST 2021 |  | COMPLETED
647 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-1 12/7 to MSFT delivery) | Sat Jan 09 08:00:00 IST 2021 | Sat Jan 09 08:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
648 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-2 12/7 to MSFT delivery) | Tue Jan 05 08:00:00 IST 2021 | Tue Jan 05 08:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
649 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-4 12/18 to MSFT delivery) | Sat Jan 09 08:00:00 IST 2021 | Sat Jan 09 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
650 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-3 12/18 to MSFT delivery) | Thu Jan 14 08:00:00 IST 2021 | Thu Jan 14 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
653 | TT_TASK | Review Fluid Cooler wiring and devices buyout with Stetner | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Wed Sep 23 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
654 | TT_TASK | Change order release for fluid cooler wiring devices | Mon Oct 19 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 | Mon Oct 26 00:00:00 IST 2020 |  | COMPLETED
657 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
658 | TT_TASK | Fluid Cooler RI in place | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
659 | TT_TASK | Fluid Cooler Wire install and Term | Fri Mar 05 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
661 | TT_TASK | Fluid Cooler Panel installation | Tue Mar 23 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
662 | TT_TASK | Fluid Cooler RI in place | Thu Mar 18 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
663 | TT_TASK | Fluid Cooler Wire install and Term | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 |  | COMPLETED
665 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 15 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
666 | TT_TASK | Fluid Cooler RI in place | Fri Feb 19 07:00:00 IST 2021 | Thu Feb 25 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
667 | TT_TASK | Fluid Cooler Wire install and Term | Thu Mar 18 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
669 | TT_TASK | Fluid Cooler Panel installation | Thu Mar 18 07:00:00 IST 2021 | Mon Mar 22 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
670 | TT_TASK | Fluid Cooler RI in place | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
671 | TT_TASK | Fluid Cooler Wire install and Term | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
674 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 29 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
675 | TT_TASK | Fluid Cooler RI in place | Thu Mar 25 07:00:00 IST 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
676 | TT_TASK | Fluid Cooler Wire install and Term | Thu Apr 01 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
678 | TT_TASK | Fluid Cooler Panel installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
679 | TT_TASK | Fluid Cooler RI in place | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
680 | TT_TASK | Fluid Cooler Wire install and Term | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
682 | TT_TASK | Fluid Cooler Panel installation | Thu Apr 01 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Sat Mar 27 00:00:00 IDT 2021 |  | COMPLETED
683 | TT_TASK | Fluid Cooler RI in place | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
684 | TT_TASK | Fluid Cooler Wire install and Term | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
687 | TT_TASK | Fluid Cooler Panel installation | Tue May 04 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
688 | TT_TASK | Fluid Cooler RI in place | Fri May 07 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
689 | TT_TASK | Fluid Cooler Wire install and Term | Fri May 14 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
691 | TT_TASK | Fluid Cooler Panel installation | Mon May 17 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
692 | TT_TASK | Fluid Cooler RI in place | Thu May 20 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
693 | TT_TASK | Fluid Cooler Wire install and Term | Fri May 28 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
695 | TT_TASK | Fluid Cooler Panel installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
696 | TT_TASK | Fluid Cooler RI in place | Fri Jun 04 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
697 | TT_TASK | Fluid Cooler Wire install and Term | Fri Jun 11 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
700 | TT_TASK | Fluid Cooler Panel installation | Tue Jun 08 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
701 | TT_TASK | Fluid Cooler RI in place | Fri Jun 11 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
702 | TT_TASK | Fluid Cooler Wire install and Term | Sat Jun 19 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
704 | TT_TASK | Fluid Cooler Panel installation | Fri Jun 11 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
705 | TT_TASK | Fluid Cooler RI in place | Sat Jun 19 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
706 | TT_TASK | Fluid Cooler Wire install and Term | Sat Jun 26 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
708 | TT_TASK | Fluid Cooler Panel installation | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
709 | TT_TASK | Fluid Cooler RI in place | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
710 | TT_TASK | Fluid Cooler Wire install and Term | Tue Jul 13 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
712 | TT_TASK | Fluid Cooler Panel installation | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
713 | TT_TASK | Fluid Cooler RI in place | Tue Jul 13 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
714 | TT_TASK | Fluid Cooler Wire install and Term | Tue Jul 20 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
718 | TT_TASK | ADMIN Overhead Rough-in (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
719 | TT_TASK | ADMIN Electrical Room Build out (DRB#2) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
720 | TT_TASK | ADMIN Lighting installation (DRB#2) | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
742 | TT_TASK | Water Treatmant Skid Fabrication | Mon Sep 14 08:00:00 IDT 2020 | Mon Dec 07 17:00:00 IST 2020 | Tue Aug 25 00:00:00 IDT 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
743 | TT_TASK | L&I approval process | Mon Sep 14 08:00:00 IDT 2020 | Tue Oct 13 17:00:00 IDT 2020 | Tue Aug 25 00:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 |  | COMPLETED
745 | TT_TASK | Water treatment delivery COLO-1 | Mon Dec 21 08:00:00 IST 2020 | Sun Dec 27 17:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
750 | TT_TASK | Submit and approve Shop drawings for UPM junstion box | Mon Oct 19 08:00:00 IDT 2020 | Sun Nov 08 17:00:00 IST 2020 | Fri Oct 09 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
751 | TT_TASK | Lead time for junction box | Mon Nov 02 08:00:00 IST 2020 | Sun Dec 13 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
752 | TT_TASK | Fabrication and Delivery of PEMB pentrations support steel | Mon Nov 09 08:00:00 IST 2020 | Fri Nov 13 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
756 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
757 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Tue Dec 15 00:00:00 IST 2020 |  | COMPLETED
758 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
760 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
761 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
762 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Feb 13 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
763 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
764 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Mar 05 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
765 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
768 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
769 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
770 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Feb 08 08:00:00 IST 2021 | Thu Feb 11 08:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
772 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
773 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
774 | TT_TASK | Install additional Cable bus (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
775 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
776 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Mar 02 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
777 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
780 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
781 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Tue Dec 15 00:00:00 IST 2020 |  | COMPLETED
782 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
784 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
785 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
786 | TT_TASK | Install additional Cable bus (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
787 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
788 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
789 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
792 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Dec 04 07:00:00 IST 2020 | Wed Dec 09 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
793 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
794 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
796 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
797 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
798 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 03 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
799 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
800 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Thu Mar 04 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
801 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
803 | TT_TASK | COLO-1 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon Mar 22 07:00:00 IST 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
804 | TT_TASK | COLO-1 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon Apr 05 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
805 | TT_TASK | COLO-1 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
806 | TT_TASK | COLO-1 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
810 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Sat Jan 02 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
811 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
812 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
814 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
815 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
816 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
817 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
818 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
819 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
822 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
823 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Thu Feb 11 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
824 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Mar 26 07:00:00 IDT 2021 | Mon Mar 29 17:00:00 IDT 2021 | Sat Feb 27 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
826 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
827 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
828 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
829 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
830 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
831 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
834 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
835 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
836 | TT_TASK | Install added DRB#3 Tray and conduit | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
838 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Sat Mar 27 00:00:00 IDT 2021 |  | COMPLETED
839 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 |  | COMPLETED
840 | TT_TASK | Install additional Cable bus (DRB#3) | Mon May 03 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
841 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
842 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue May 04 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
843 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
846 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
847 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Thu Feb 11 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
848 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 02 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
850 | TT_TASK | Install MER Supply duct | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
851 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri May 07 07:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
852 | TT_TASK | Install additional Cable bus (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
853 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue May 04 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
854 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
855 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 |  | COMPLETED
857 | TT_TASK | COLO-2 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Fri Apr 30 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
858 | TT_TASK | COLO-2 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
859 | TT_TASK | COLO-2 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 03 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
860 | TT_TASK | COLO-2 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
864 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
865 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
866 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
868 | TT_TASK | Install MER Supply duct | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
869 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
870 | TT_TASK | Install Roxtec block sealing and Install added tray cable (DRB#3) | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
871 | TT_TASK | Install additional Cable bus (DRB#3) | Tue May 18 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
872 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
873 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
876 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
877 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
878 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
880 | TT_TASK | Install MER Supply duct | Mon May 24 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
881 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
882 | TT_TASK | Install additional Cable bus (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
883 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 |  | COMPLETED
884 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Sat Aug 14 07:00:00 IDT 2021 | Sat Aug 14 17:00:00 IDT 2021 |  | COMPLETED
885 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Fri Sep 03 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Thu Aug 26 00:00:00 IDT 2021 |  | COMPLETED
888 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
889 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 |  | COMPLETED
890 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
892 | TT_TASK | Install MER Supply duct | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
893 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 |  | COMPLETED
894 | TT_TASK | Install additional Cable bus (DRB#3) | Sat May 29 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
895 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
896 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 |  | COMPLETED
897 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Mon Aug 09 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
900 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
901 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
902 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
904 | TT_TASK | Install MER Supply duct | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
905 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
906 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jun 05 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
907 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
908 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
909 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
911 | TT_TASK | COLO-3 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
912 | TT_TASK | COLO-3 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 |  | COMPLETED
913 | TT_TASK | COLO-3 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
914 | TT_TASK | COLO-3 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
918 | TT_TASK | Sure steel - PEMB MER penetration framing | Thu Feb 11 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
919 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
920 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
922 | TT_TASK | Install MER Supply duct | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
923 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Thu Jul 08 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
924 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
925 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
926 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
927 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
930 | TT_TASK | Sure steel - PEMB MER penetration framing | Tue Feb 16 07:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
931 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
932 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
934 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
935 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
936 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
937 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Fri Sep 03 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 |  |  | 400.0 | NOT_STARTED
938 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
939 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Sat Oct 02 07:00:00 IDT 2021 | Fri Oct 08 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
942 | TT_TASK | Sure steel - PEMB MER penetration framing | Thu Feb 11 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
943 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
944 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
946 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
947 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Thu Jul 08 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 |  | COMPLETED
948 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Jul 28 00:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 |  | COMPLETED
949 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
950 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
951 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
954 | TT_TASK | Sure steel - PEMB MER penetration framing | Tue Feb 16 07:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
955 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
956 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 00:00:00 IDT 2021 |  | COMPLETED
958 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
959 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
960 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
961 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
962 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
963 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
965 | TT_TASK | COLO-4 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Thu Sep 09 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
966 | TT_TASK | COLO-4 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Wed Aug 18 00:00:00 IDT 2021 |  |  | IN_PROGRESS
967 | TT_TASK | COLO-4 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
968 | TT_TASK | COLO-4 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
970 | TT_TASK | Site Shut Down - 9/9/2020 | Mon Sep 14 07:00:00 IDT 2020 | Mon Sep 14 17:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 |  | COMPLETED
971 | TT_TASK | Site Shut Down - 9/10/2020 | Tue Sep 15 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Thu Sep 10 00:00:00 IDT 2020 | Thu Sep 10 00:00:00 IDT 2020 |  | COMPLETED
972 | TT_TASK | Site Shut Down - 9/11/2020 | Wed Sep 16 07:00:00 IDT 2020 | Wed Sep 16 17:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
973 | TT_TASK | Site Shut Down - 9/12/2020 | Thu Sep 17 07:00:00 IDT 2020 | Thu Sep 17 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
974 | TT_TASK | Site Shut Down - 9/14/2020 | Mon Sep 28 07:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 |  | COMPLETED
975 | TT_TASK | Site Shut Down - 9/15/2020 | Tue Sep 29 07:00:00 IDT 2020 | Tue Sep 29 17:00:00 IDT 2020 | Tue Sep 15 00:00:00 IDT 2020 | Tue Sep 15 00:00:00 IDT 2020 |  | COMPLETED
976 | TT_TASK | Site Shut Down - 9/16/2020 | Wed Sep 30 07:00:00 IDT 2020 | Wed Sep 30 17:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 |  | COMPLETED
979 | TT_TASK | Complete Remaining IWW piping to tie-in point | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 29 17:00:00 IST 2020 | Mon Sep 21 00:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
980 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
982 | TT_TASK | Complete Remaining Sanitary piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
983 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
985 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
986 | TT_TASK | Complete Remaining Fire Main piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
988 | TT_TASK | Complete Remaining ITW piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
989 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
991 | TT_TASK | Complete Remaining Telecom Duct Back (excluding Tie-in) | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
992 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
995 | TT_TASK | Delay in COLO-1- Cell-1 MER Delivery (Duration = COLO1 Cell-1 PSR(11/6/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sat Jan 30 17:00:00 IST 2021 | Fri Nov 06 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
996 | TT_TASK | Delay in COLO-1- Cell-2 MER Delivery (Duration = COLO1 Cell-2 PSR(11/13/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Fri Jan 29 17:00:00 IST 2021 | Fri Nov 13 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
997 | TT_TASK | Delay in COLO-1- Cell-3 MER Delivery (Duration = COLO1 Cell-3 PSR(11/20/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Feb 04 17:00:00 IST 2021 | Fri Nov 20 00:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 |  | COMPLETED
998 | TT_TASK | Delay in COLO-1- Cell-4 MER Delivery (Duration = COLO1 Cell-4 PSR(11/30/20) to MSFT delivery) | Mon Feb 01 08:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1000 | TT_TASK | Delay in COLO-2- Cell-1 MER Delivery (Duration = Colo1 Cell-1 PSR(12/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Feb 11 10:00:00 IST 2021 | Tue Dec 15 00:00:00 IST 2020 | Wed Feb 03 00:00:00 IST 2021 |  | COMPLETED
1001 | TT_TASK | Delay in COLO-2- Cell-2 MER Delivery (Duration = COLO 2 Cell-2 PSR(12/22/20) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1002 | TT_TASK | Delay in COLO-2- Cell-3 MER Delivery (Duration = COLO 2- Cell-3 PSR(12/28/20) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1003 | TT_TASK | Delay in COLO-2- Cell-4 MER Delivery (Duration = COLO 2- Cell-4 PSR(1/5/21) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Jan 05 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1005 | TT_TASK | Delay in COLO-3- Cell-1 MER Delivery (Duration = COLO-3 Cell-1 PSR(1/29/21) to MSFT delivery) | Sun Jan 31 08:00:00 IST 2021 | Sat Apr 03 17:00:00 IDT 2021 | Fri Jan 29 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1006 | TT_TASK | Delay in COLO-3- Cell-2 MER Delivery (Duration = COLO-3 Cell-2 PSR(2/5/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 05 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1007 | TT_TASK | Delay in COLO-3 Cell-3 MER Delivery (Duration = COLO-3 Cell-3 PSR(2/12/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Feb 12 00:00:00 IST 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1008 | TT_TASK | Delay in COLO-3 Cell-4 MER Delivery (Duration = COLO-3 Cell-4 PSR(2/19/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Thu Apr 22 00:00:00 IDT 2021 |  | COMPLETED
1010 | TT_TASK | Delay in COLO-4- Cell-1 MER Delivery (Duration= COLO-4 Cell-1 PSR(3/12/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Mar 12 00:00:00 IST 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
1011 | TT_TASK | Delay in COLO-4- Cell-2 MER Delivery (Duration = COLO-4 Cell-2 PSR(3/19/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1012 | TT_TASK | Delay in COLO-4- Cell-3 MER Delivery (Duration = COLO-4 Cell-3 PSR(3/26/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1013 | TT_TASK | Delay in COLO-4- Cell-4 MER Delivery (Duration = COLO-4 Cell-4 PSR(4/2/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 | Sun May 09 00:00:00 IDT 2021 |  | COMPLETED
1015 | TT_TASK | Wire Mesh Procurement | Mon Nov 16 08:00:00 IST 2020 | Wed Dec 23 12:00:00 IST 2020 | Thu Sep 24 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
1016 | TT_TASK | Wire Mesh Submittal Approval | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Wed Sep 16 00:00:00 IDT 2020 | Wed Sep 23 00:00:00 IDT 2020 |  | COMPLETED
1017 | TT_TASK | Wire Mesh Procurement Delay | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Sat Oct 24 00:00:00 IDT 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1019 | TT_TASK | Complete Remaining Telecom Duct Back tie-in Install to MWH02 | Mon Dec 21 07:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1020 | TT_TASK | Clayco waiting on MSOW Approval | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Tue Dec 01 00:00:00 IST 2020 |  | COMPLETED
1021 | TT_TASK | Clayco MSOW Submited for approval | Mon Nov 16 07:00:00 IST 2020 | Tue Nov 17 17:00:00 IST 2020 | Fri Oct 16 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
1022 | TT_TASK | MSFT Stand down/ Additional Hydro excavation | Mon Dec 21 07:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
1024 | TT_TASK | Delay in UMS delivery (Duration = (9/19) to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Thu Nov 19 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
1027 | TT_TASK | Delay In COLO-1 Cell-1 Generator (Duration= COLO-1 Cell-1 PSR(9/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Tue Jan 19 17:00:00 IST 2021 | Tue Sep 15 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1028 | TT_TASK | Delay In COLO-1 Cell-2 Generator (Duration= COLO-1 Cell-2 PSR(9/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sat Feb 06 17:00:00 IST 2021 | Tue Sep 15 00:00:00 IDT 2020 | Mon Nov 02 00:00:00 IST 2020 |  | COMPLETED
1029 | TT_TASK | Delay In COLO-1 Cell-4 Generator (Duration= COLO-1 Cell-4 PSR(9/29/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Sep 29 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1030 | TT_TASK | Delay In COLO-1 Cell-3 Generator (Duration= COLO-1 Cell-3 PSR(9/29/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Wed Feb 03 17:00:00 IST 2021 | Tue Sep 29 00:00:00 IDT 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1032 | TT_TASK | Delay In COLO-2 Cell-1 Generator (Duration= COLO-2 Cell-1 PSR(10/12/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sun Mar 07 17:00:00 IST 2021 | Mon Oct 12 00:00:00 IDT 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1033 | TT_TASK | Delay In COLO-2 Cell-2 Generator (Duration= COLO-2 Cell-2 PSR(11/6/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sun Feb 21 17:00:00 IST 2021 | Fri Nov 06 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
1034 | TT_TASK | Delay In COLO-2 Cell-4 Generator (Duration= COLO-2 Cell-4 PSR(11/21/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Fri Feb 19 17:00:00 IST 2021 | Sat Nov 21 00:00:00 IST 2020 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
1035 | TT_TASK | Delay In COLO-2 Cell-3 Generator (Duration= COLO-2 Cell-3 PSR(10/22/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Mar 18 17:00:00 IST 2021 | Thu Oct 22 00:00:00 IDT 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1037 | TT_TASK | 6.1.39.1- COLO-3 CEll-1 GEN Belly tank Failed pressure test | Mon Mar 15 07:00:00 IST 2021 | Fri Apr 09 17:00:00 IDT 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
1038 | TT_TASK | 6.1.39.2- COLO-3 Cell-1 Replace Belly Tank and Set GEN | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1039 | TT_TASK | Delay In COLO-3 Cell-1 Generator (Duration= COLO-3 Cell-1 PSR(10/12/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Sat May 08 17:00:00 IDT 2021 | Mon Nov 09 00:00:00 IST 2020 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1040 | TT_TASK | Delay In COLO-3 Cell-2 Generator (Duration= COLO-3 Cell-2 PSR(11/6/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Tue Mar 30 17:00:00 IDT 2021 | Sat Nov 21 00:00:00 IST 2020 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
1041 | TT_TASK | Delay In COLO-3 Cell-4 Generator (Duration= COLO-3 Cell-4 PSR(11/21/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Mar 18 17:00:00 IST 2021 | Wed Dec 09 00:00:00 IST 2020 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
1042 | TT_TASK | Delay In COLO-3 Cell-3 Generator (Duration= COLO-3 Cell-3 PSR(10/22/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Apr 29 17:00:00 IDT 2021 | Thu Nov 05 00:00:00 IST 2020 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1044 | TT_TASK | Delay In COLO-4 Cell-1 Generator (Duration= COLO-4 Cell-1 PSR(10/12/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Sat Jun 05 17:00:00 IDT 2021 | Mon Nov 09 00:00:00 IST 2020 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
1045 | TT_TASK | Delay In COLO-4 Cell-2 Generator (Duration= COLO-4 Cell-2 PSR(11/6/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Apr 01 17:00:00 IDT 2021 | Wed Dec 09 00:00:00 IST 2020 | Thu Mar 11 00:00:00 IST 2021 |  | COMPLETED
1046 | TT_TASK | Delay In COLO-4 Cell-4 Generator (Duration= COLO-4 Cell-4 PSR(11/21/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Wed Apr 14 17:00:00 IDT 2021 | Mon Nov 30 00:00:00 IST 2020 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
1047 | TT_TASK | Delay In COLO-4 Cell-3 Generator (Duration= COLO-4 Cell-3 PSR(10/22/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Tue May 11 17:00:00 IDT 2021 | Fri Nov 20 00:00:00 IST 2020 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1050 | TT_TASK | COLO1 CELL1 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1051 | TT_TASK | COLO1 CELL3 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
1052 | TT_TASK | COLO1 CELL2 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1053 | TT_TASK | COLO1 CELL4 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
1058 | TT_TASK | COLO-1 Cell-1 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1059 | TT_TASK | COLO1 CELL1 Interior MER conduit installation utility side | Fri Mar 05 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1060 | TT_TASK | COLO-1 Cell-1 Interior MER conduit installation building side Complete March1st (MER discovery Corrections & Signoff) | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1063 | TT_TASK | COLO-1 CELL3 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1064 | TT_TASK | COLO1 CELL3 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1065 | TT_TASK | COLO-1 CELL3 Interior MER conduit installation building side | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
1068 | TT_TASK | COLO-1 CELL2 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1069 | TT_TASK | COLO1 CELL2 Interior MER conduit installation utility side | Sat Mar 06 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1070 | TT_TASK | COLO-1 CELL2 Interior MER conduit installation building side | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1073 | TT_TASK | COLO-1 CELL4 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1074 | TT_TASK | COLO1 CELL4 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1075 | TT_TASK | COLO-1 CELL4 Interior MER conduit installation building side | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
1079 | TT_TASK | COLO-2 Cell-1 Rearrange Roxtec blocks per coordination layout | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1080 | TT_TASK | COLO2 CELL1 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1081 | TT_TASK | COLO-2 Cell-1 Interior MER conduit installation building side | Mon Apr 05 07:00:00 IDT 2021 | Mon Apr 19 17:00:00 IDT 2021 | Fri Mar 05 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1089 | TT_TASK | COLO-1 Cell-1 MER Flex Conduit fixes | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1090 | TT_TASK | COLO-1 Cell-3 MER Flex Conduit fixes | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1091 | TT_TASK | COLO-1 Cell-2 MER Flex Conduit fixes | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1092 | TT_TASK | COLO-1 Cell-4 MER Flex Conduit fixes | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1095 | TT_TASK | Safety Stop work due to failed Starline Hangers | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 01 07:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
1096 | TT_TASK | Lead time for replacement hangers from Starline | Mon Feb 01 08:00:00 IST 2021 | Sun Feb 07 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
1097 | TT_TASK | COLO-1 Cell-1 Remove/ Replace busway & hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1098 | TT_TASK | COLO-1 Cell-3 Remove/ Replace busway & hangers | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1099 | TT_TASK | COLO-1 Cell-2 Remove/ Replace busway & hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1100 | TT_TASK | COLO-1 Cell-4 Remove/ Replace busway & hangers | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1101 | TT_TASK | Determined Startline hanger Design Issue & Approve replacement hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
1102 | TT_TASK | COLO-2 Cell-1 Remove/ Replace busway & hangers | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1103 | TT_TASK | COLO-2 Cell-2 Remove/ Replace busway & hangers | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1105 | TT_TASK | Lead time for missing Admin Gen Bussing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 |  | COMPLETED
1106 | TT_TASK | Admin Gen Bussing Install | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1107 | TT_TASK | Awaiting DCE approval of Non NEMA standard Lugs | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1108 | TT_TASK | Awaiting Phase conductor lugs from NC power as per RFI#412 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1109 | TT_TASK | 6.1.41 - Incorrect Lugs for Admin Gen Main Bussing | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1112 | TT_TASK | COLO-1 Cell-4 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
1113 | TT_TASK | COLO-1 Cell-3 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Thu Mar 11 00:00:00 IST 2021 |  | COMPLETED
1114 | TT_TASK | COLO-1 Cell-2 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1115 | TT_TASK | COLO-1 Cell-1 SE Install UPS batteries in cabinet | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1117 | TT_TASK | COLO-2 Cell-1 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
1118 | TT_TASK | COLO-2 Cell-2 SE Install UPS batteries in cabinet | Fri Apr 30 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
1119 | TT_TASK | COLO-2 Cell-3 SE Install UPS batteries in cabinet | Sat May 08 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1120 | TT_TASK | COLO-2 Cell-4 SE Install UPS batteries in cabinet | Sat May 15 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
1122 | TT_TASK | COLO-3 Cell-1 SE Install UPS batteries in cabinet | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1123 | TT_TASK | COLO-3 Cell-2 SE Install UPS batteries in cabinet | Tue May 25 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1124 | TT_TASK | COLO-3 Cell-3 SE Install UPS batteries in cabinet | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1125 | TT_TASK | COLO-3 Cell-4 SE Install UPS batteries in cabinet | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1127 | TT_TASK | COLO-4 Cell-1 SE Install UPS batteries in cabinet | Tue Sep 14 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1128 | TT_TASK | COLO-4 Cell-2 SE Install UPS batteries in cabinet | Wed Sep 29 07:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  | 320.0 | IN_PROGRESS
1129 | TT_TASK | COLO-4 Cell-3 SE Install UPS batteries in cabinet | Tue Sep 07 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
1130 | TT_TASK | COLO-4 Cell-4 SE Install UPS batteries in cabinet | Tue Sep 21 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
1132 | TT_TASK | COLO-2 CEll-2 Awaiting SE Revised tool Come along for MER Lift & Set | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
1133 | TT_TASK | COLO-2 CEll-3 Awaiting SE Revised tool Come along for MER Lift & Set | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1134 | TT_TASK | MER shipping split connection Safety Standown & RCA Review | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1137 | TT_TASK | COLO-2 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1138 | TT_TASK | RFI#432 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
1139 | TT_TASK | Lead time for tube steel | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
1140 | TT_TASK | COLO-2 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1141 | TT_TASK | COLO-2 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Thu Apr 01 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1142 | TT_TASK | COLO-2 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1144 | TT_TASK | COLO-3 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Fri May 07 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 |  | COMPLETED
1145 | TT_TASK | COLO-3 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Wed May 19 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed May 19 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 |  | COMPLETED
1146 | TT_TASK | COLO-3 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Thu May 13 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Thu May 13 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 |  | COMPLETED
1147 | TT_TASK | COLO-3 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Wed May 26 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Wed May 26 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 |  | COMPLETED
1149 | TT_TASK | COLO-4 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1150 | TT_TASK | COLO-4 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1151 | TT_TASK | COLO-4 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1152 | TT_TASK | COLO-4 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Mon Jun 14 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1154 | TT_TASK | All Construction activities -Safety Standown due to Admin Gen unplanned Energization | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
1156 | TT_TASK | COLO-1 Cell-1 Field Modification of tray | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1157 | TT_TASK | COLO-1 Cell-2 Field Modification of tray | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Jan 21 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1160 | TT_TASK | #3. Snow- 1/27/2021(one full day) | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 |  | COMPLETED
1161 | TT_TASK | #4. Extreme Heat - 6/28/21- 7/2/21(Effecting COLO-4 Yard work) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
1162 | TT_TASK | #5 Extreme heat -production loss in Yards 7/1/21 through 7/14/21 (11 half days of loss) | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 09 00:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
1163 | TT_TASK | #6 Extreme heat - Production loss in Yards 7/15/21 through 7/31/21 (3 half days) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
1164 | TT_TASK | #1. Rain And High Winds- 10/13/2020(half day only) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Tue Oct 13 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1165 | TT_TASK | #2. Snow -12/30/20 (one full day) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Wed Dec 30 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
1168 | TT_TASK | COLO-1 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Mon Jan 11 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
1169 | TT_TASK | COLO-1 CELL-3 WA State L&I onsite inspection & Approval to Connect to MER | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1170 | TT_TASK | COLO-1 CELL-2 WA State L&I onsite inspection & Approval to Connect to MER | Sat Jan 23 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1171 | TT_TASK | COLO-1 CELL-4 WA State L&I onsite inspection & Approval to Connect to MER | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1173 | TT_TASK | COLO-2 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Fri Mar 12 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1174 | TT_TASK | COLO-2 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Tue Mar 23 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1175 | TT_TASK | COLO-2 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
1176 | TT_TASK | COLO-2 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Fri Apr 09 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1178 | TT_TASK | COLO-3 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Sat May 08 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1179 | TT_TASK | COLO-3 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Fri May 14 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1180 | TT_TASK | COLO-3 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1181 | TT_TASK | COLO-3 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1183 | TT_TASK | COLO-4 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 |  | COMPLETED
1184 | TT_TASK | COLO-4 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Sat Jun 19 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1185 | TT_TASK | COLO-4 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
1186 | TT_TASK | COLO-4 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 |  | COMPLETED
1189 | TT_TASK | 6.1.36 Rework for Addtional circuits for UMS URS Battery charger feed upsize | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1190 | TT_TASK | 6.1.34.1 COLO-1 Cell-1 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1191 | TT_TASK | 6.1.34.2 COLO-1 Cell-2 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1192 | TT_TASK | 6.1.34.3 COLO-1 Cell-3 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 |  | COMPLETED
1193 | TT_TASK | 6.1.34.4 COLO-1 Cell-4 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 |  | COMPLETED
1194 | TT_TASK | 6.1.01.0 Awaiting MER 10A HRG's (lead time= 8 weeks from 2/2/2021) | Mon Mar 01 07:00:00 IST 2021 | Mon Apr 12 17:00:00 IDT 2021 | Tue Feb 02 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
1195 | TT_TASK | 6.1.09 Awaiting Rev-D for Coordination study (DRB3/SCCS/ Submittal Breaker verification) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1196 | TT_TASK | 6.1.26.1 L2/L3 Scripts SE MER overall Script | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
1197 | TT_TASK | 6.1.33 URS UMS Ground Buss hole Pattern | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1198 | TT_TASK | 6.1.35 UPS battery IR Scanning | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1199 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-1 Cell-1 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1200 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-1 Cell-4 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1201 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-1 Cell-3 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1202 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-1 Cell-2 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1203 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-2 Cell-1 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1204 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-2 Cell-2 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1205 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-2 Cell-3 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1206 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-2 Cell-4 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue Jul 13 00:00:00 IDT 2021 | Mon Jul 19 00:00:00 IDT 2021 |  | COMPLETED
1207 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-3 Cell-1 | Tue Aug 31 07:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
1208 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-3 Cell-4 | Tue Sep 07 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  |  | 10.0 | NOT_STARTED
1209 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-3 Cell-3 | Tue Sep 07 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  |  | 10.0 | NOT_STARTED
1210 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-3 Cell-2 | Thu Sep 09 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1211 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-4 Cell-1 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1212 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-4 Cell-4 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1213 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-4 Cell-3 | Mon Oct 18 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1214 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-4 Cell-2 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1216 | TT_TASK | 6.1.37- 6.2.01- Ground Fault setting on COLO-2 Gen MCB01 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Wed Apr 28 17:00:00 IDT 2021 |  | COMPLETED
1218 | TT_TASK | 6.1.38 PDU MCB01 LOTO Provisions | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1220 | TT_TASK | 6.1.11 Awaiting BAS Backplanes from Siemens to VECA for Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
1221 | TT_TASK | 6.1.26.2 L2/L3 Scripts Siemens BAS SAT Scripts | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1222 | TT_TASK | 6.1.11 Awaiting Liftstation #3 BAS Backplanes from Siemens to VECA for Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1223 | TT_TASK | 6.1.11 Liftstation #3 BAS Install / Pull wire / term Backplanes | Mon May 17 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 |  | COMPLETED
1226 | TT_TASK | COLO-2 Cell-1 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Dec 29 00:00:00 IST 2020 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1227 | TT_TASK | COLO-2 Cell-2 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sun Jan 10 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1228 | TT_TASK | COLO-2 Cell-3 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Jan 20 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1229 | TT_TASK | COLO-2 Cell-4 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sat Jan 23 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1231 | TT_TASK | COLO-3 Cell-1 Install Missing Raceway & Bussing within generator | Mon Apr 26 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1232 | TT_TASK | COLO-3 Cell-2 Install Missing Raceway & Bussing within generator | Thu Apr 29 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1233 | TT_TASK | COLO-3 Cell-3 Install Missing Raceway & Bussing within generator | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
1234 | TT_TASK | COLO-3 Cell-4 Install Missing Raceway & Bussing within generator | Tue May 04 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1236 | TT_TASK | COLO-4 Cell-1 Install Missing Raceway & Bussing within generator | Tue May 25 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
1237 | TT_TASK | COLO-4 Cell-2 Install Missing Raceway & Bussing within generator | Tue May 11 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1238 | TT_TASK | COLO-4 Cell-3 Install Missing Raceway & Bussing within generator | Thu May 20 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1239 | TT_TASK | COLO-4 Cell-4 Install Missing Raceway & Bussing within generator | Mon May 17 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
1242 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1243 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 2weeks- fab and ship | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Mon Apr 05 00:00:00 IDT 2021 |  | COMPLETED
1244 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 1 week to install | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
1245 | TT_TASK | 6.1.44- MER Battery Monitoring Software Â– Constraint to EPMS checkouts/Point Â– Point(needed by 4/23) | Mon Mar 15 07:00:00 IST 2021 | Mon Jun 07 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Aug 07 07:00:00 IDT 2021 |  | COMPLETED
1246 | TT_TASK | 6.1.46- Site UPM Inspections | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
1247 | TT_TASK | 6.1.47- COLO-1 Cell-2 UPS01- Factory Test thermal event | Mon Mar 15 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
1249 | TT_TASK | 6.1.40- 480V house power to Gen Enclousure is Fed OH vs UG | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1254 | TT_TASK | Downtime awaiting solution for safety space constraint | Mon Apr 26 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1256 | TT_TASK | NOPC-18 Remove COLO-1 Cell-1 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1257 | TT_TASK | Rubicon MSB inspection complete (ready for transformer reinstall) | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Mon Apr 26 07:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1258 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-1 transformer | Tue May 25 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1260 | TT_TASK | NOPC-18 Remove COLO-1 Cell-2 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
1261 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1262 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-2 transformer | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1264 | TT_TASK | NOPC-18 Remove COLO-1 Cell-3 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 |  | COMPLETED
1265 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1266 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-3 transformer | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1268 | TT_TASK | NOPC-18 Remove COLO-1 Cell-4 transformer | Mon May 17 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1269 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1270 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-4 transformer | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1273 | TT_TASK | NOPC-18 Remove COLO-2 Cell-1 transformer | Tue Jun 01 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue Jun 08 00:00:00 IDT 2021 |  | COMPLETED
1274 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-1 transformer | Thu Jul 22 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1276 | TT_TASK | NOPC-18 Remove COLO-2 Cell-2 transformer | Wed Jun 02 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
1277 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-2 transformer | Fri Jul 23 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
1279 | TT_TASK | NOPC-18 Remove COLO-2 Cell-3 transformer | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 |  | COMPLETED
1280 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-3 transformer | Thu Jul 29 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1282 | TT_TASK | NOPC-18 Remove COLO-2 Cell-4 transformer | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1283 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-4 transformer | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Jul 09 00:00:00 IDT 2021 | Mon Jul 12 00:00:00 IDT 2021 |  | COMPLETED
1286 | TT_TASK | NOPC-18 Remove COLO-3 Cell-1 transformer | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
1287 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-1 transformer | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 22 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1289 | TT_TASK | NOPC-18 Remove COLO-3 Cell-2 transformer | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jul 24 07:00:00 IDT 2021 | Sat Jul 24 17:00:00 IDT 2021 |  | COMPLETED
1290 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-2 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
1292 | TT_TASK | NOPC-18 Remove COLO-3 Cell-3 transformer | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Thu Aug 19 07:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1293 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-3 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1295 | TT_TASK | NOPC-18 Remove COLO-3 Cell-4 transformer | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1296 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-4 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1299 | TT_TASK | NOPC-18 Remove COLO-4 Cell-1 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1300 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-1 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1302 | TT_TASK | NOPC-18 Remove COLO-4 Cell-2 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1303 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-2 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1305 | TT_TASK | NOPC-18 Remove COLO-4 Cell-3 transformer | Wed Sep 29 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1306 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-3 transformer | Sat Oct 09 07:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1308 | TT_TASK | NOPC-18 Remove COLO-4 Cell-4 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1309 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-4 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1311 | TT_TASK | PDU termination crew downtime due to COVID-19 | Sat Apr 24 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Sat Apr 24 07:00:00 IDT 2021 |  | COMPLETED
1314 | TT_TASK | 6.2.03- Replace ADP01 faulty trip units | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1315 | TT_TASK | 6.1.51-COLO-1 Cell-1,2 Factory conductors not terminated per drawings | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1316 | TT_TASK | 6.1.49 - COLO-1 Cell-1 Awaiting Ground Lug solution, procurement, installation of labelling ATS 01-06 | Fri Apr 30 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
1317 | TT_TASK | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
1318 | TT_TASK | 6.1.53-COLO-1 Cell-1,2 UPS01, PNL01 awaiting missing breakers | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1319 | TT_TASK | 6.1.53-COLO-1 Cell-1,2,3,4 UPS01, PNL01 Install/ term Missing breakers | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1320 | TT_TASK | 6.1.59 (6.1.51 carryover) -COLO-1 Cell-1,2 Factory conductors exertherm corrections | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
1321 | TT_TASK | 6.1.50- SCCS Revision#10 (RFI-540) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1325 | TT_TASK | 6.1.54- TCM Awaiting Admin Siemens Break tank parts | Mon May 17 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1326 | TT_TASK | 6.1.54- Install Breaktank parts | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1328 | TT_TASK | 6.2.03- Replace Damaged UPM in COLO-4 Cell-4 | Thu May 06 07:00:00 IDT 2021 | Sat May 08 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1330 | TT_TASK | 6.1.55-COLO-1 - FC Factoy Re-wire (RFI-502) | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1331 | TT_TASK | 6.1.55-COLO-2 - FC Factoy Re-wire (RFI-502) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1332 | TT_TASK | 6.1.55-COLO-3 - FC Factoy Re-wire (RFI-502) | Sat Jun 05 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1333 | TT_TASK | 6.1.55-COLO-4 - FC Factoy Re-wire (RFI-502) | Thu Jun 10 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1335 | TT_TASK | 6.1.57 -Awaiting revised coordination study #9 | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
1336 | TT_TASK | Reprint revised panel 3,4 Arc flash labels | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1337 | TT_TASK | Print new DC Arc flash labels for Admin ELP | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1340 | TT_TASK | 6.1.58-RFI-528- COLO-1 - SF/RF Circuitry & terminal block rework | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
1341 | TT_TASK | 6.1.63- COLO1-UPS01-PNL01 Compass Issues Constraining L3Â’s | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
1342 | TT_TASK | 6.1.56 - COLO-1 Awaiting MSB/ADP Ground Lug replacements, Installation of labelling | Fri Apr 30 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
1349 | TT_TASK | All trades stand down | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
1350 | TT_TASK | Veca standown | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
1353 | TT_TASK | COLO-1 Cell-1 MER-UPS Battery Disconnect modifications rework | Wed Jun 16 07:00:00 IDT 2021 | Sat Jun 19 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1354 | TT_TASK | COLO-1 Cell-2 MER-UPS Battery Disconnect modifications rework | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1355 | TT_TASK | COLO-1 Cell-3 MER-UPS Battery Disconnect modifications rework | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
1356 | TT_TASK | COLO-1 Cell-4 MER-UPS Battery Disconnect modifications rework | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
1357 | TT_TASK | RFI-548 COLO MSB to UPS Battery disconnect solution approval | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1358 | TT_TASK | ADMIN-UPS Battery Disconnect modifications rework | Wed Jun 16 07:00:00 IDT 2021 | Sat Jun 19 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1359 | TT_TASK | RFI-552 Admin MSB to UPS Battery disconnect solution approval | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
1361 | TT_TASK | COLO-2 Cell-2 MER-UPS Battery Disconnect modifications rework | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 |  | COMPLETED
1362 | TT_TASK | COLO-2 Cell-1 MER-UPS Battery Disconnect modifications rework | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  | COMPLETED
1363 | TT_TASK | COLO-2 Cell-3 MER-UPS Battery Disconnect modifications rework | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  | COMPLETED
1364 | TT_TASK | COLO-2 Cell-4 MER-UPS Battery Disconnect modifications rework | Fri Jul 02 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 23 07:00:00 IDT 2021 |  | COMPLETED
1366 | TT_TASK | COLO-3 Cell-1 MER-UPS Battery Disconnect modifications rework | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 |  | COMPLETED
1367 | TT_TASK | COLO-3 Cell-2 MER-UPS Battery Disconnect modifications rework | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1368 | TT_TASK | COLO-3 Cell-3 MER-UPS Battery Disconnect modifications rework | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
1369 | TT_TASK | COLO-3 Cell-4 MER-UPS Battery Disconnect modifications rework | Sat Sep 11 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Mon Aug 16 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1371 | TT_TASK | COLO-4 Cell-1 MER-UPS Battery Disconnect modifications rework | Thu Sep 16 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
1372 | TT_TASK | COLO-4 Cell-2 MER-UPS Battery Disconnect modifications rework | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
1373 | TT_TASK | COLO-4 Cell-3 MER-UPS Battery Disconnect modifications rework | Mon Sep 27 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1374 | TT_TASK | COLO-4 Cell-4 MER-UPS Battery Disconnect modifications rework | Fri Sep 03 07:00:00 IDT 2021 | Thu Sep 09 17:00:00 IDT 2021 |  |  | 270.0 | NOT_STARTED
1377 | TT_TASK | COLO-3 Cell-3 Remove inaccessible tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 |  | COMPLETED
1378 | TT_TASK | COLO-3 CEll-3 Reinstall tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
1379 | TT_TASK | COLO-3 Cell-4 Remove inaccessible tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Sat Jun 12 00:00:00 IDT 2021 |  | COMPLETED
1380 | TT_TASK | COLO-3 Cell-4 Reinstall tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1381 | TT_TASK | COLO-4 Cell-1 Remove inaccessible tray in MER | Mon Jul 12 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Sat Jun 12 00:00:00 IDT 2021 |  | COMPLETED
1382 | TT_TASK | COLO-4 Cell-1 Reinstall tray in MER | Tue Aug 03 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
1383 | TT_TASK | COLO-4 Cell-2 Remove inaccessible tray in MER | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
1384 | TT_TASK | COLO-4 Cell-2 Reinstall tray in MER | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1385 | TT_TASK | COLO-4 Cell-3 Remove inaccessible tray in MER | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Thu Jul 15 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
1386 | TT_TASK | COLO-4 Cell-3 Reinstall tray in MER | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
1387 | TT_TASK | COLO-4 Cell-4 Remove inaccessible tray in MER4 | Wed Aug 04 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
1388 | TT_TASK | COLO-4 Cell-4 Reinstall tray in MER | Fri Sep 03 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Mon Aug 09 07:00:00 IDT 2021 | Thu Aug 12 00:00:00 IDT 2021 |  | COMPLETED
1389 | TT_TASK | COLO-3 Cell-1 Remove inaccessible tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
1390 | TT_TASK | COLO-3 CEll-1 Reinstall tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 |  | COMPLETED
1391 | TT_TASK | COLO-3 Cell-2 Remove inaccessible tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1392 | TT_TASK | COLO-3 Cell-2 Reinstall tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1395 | TT_TASK | COLO-3 Cell-3 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 14 00:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1397 | TT_TASK | COLO-4 Cell-1 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Fri Jul 23 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1398 | TT_TASK | COLO-4 Cell-2 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
1399 | TT_TASK | COLO-4 Cell-3 Conduit rework | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 |  | COMPLETED
1400 | TT_TASK | COLO-4 Cell-4 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1404 | TT_TASK | 6.1-88 COLO-1 MER awaiting updated UPS L3 test script approval | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 31 07:00:00 IDT 2021 |  | COMPLETED
1405 | TT_TASK | 6.1-89 RFI574- COLO-1 Relocating MSB EPMS device to different cabinet | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1406 | TT_TASK | 6.1-92 COLO-1 SF/ RF startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
1407 | TT_TASK | 6.1-93 COLO-1 HVAC minisplits startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1409 | TT_TASK | 6.2-08 COLO-2 Cell- 1,2 MER equipment Phenolic labelling | Wed Jul 14 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
1410 | TT_TASK | 6.2-08 COLO-2 Cell- 3,4 MER equipment Phenolic labelling | Wed Jul 14 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Mon Aug 02 00:00:00 IDT 2021 |  | COMPLETED
1411 | TT_TASK | 6.2-12 COLO-2 All Cells- Factory connection Torque verification | Wed Jul 14 07:00:00 IDT 2021 | Wed Jul 21 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
1413 | TT_TASK | 6.1-95 COLO-1 ATS's L3 startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  | COMPLETED
1415 | TT_TASK | 6.1-96 COLO-1 PDU - EPMS L3 startup delay (vendor schedule availability) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Mon Aug 02 07:00:00 IDT 2021 |  | COMPLETED
1420 | TT_TASK | COLO-2 Cell-1 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1421 | TT_TASK | COLO-2 Cell-2 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1422 | TT_TASK | COLO-2 Cell-3 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1423 | TT_TASK | COLO-2 Cell-4 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 00:00:00 IDT 2021 |  | COMPLETED
1429 | TT_TASK | 6.1-98 Admin/COLO-1 ASCO EPMS Connectivity Issues | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1430 | TT_TASK | 6.1-88 Admin/ COLO-1 MER/ADMIN UPS L3 Testing (includes shutdown to move PQM's & PQM data post proccessing) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 31 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1431 | TT_TASK | 6.1-106 COLO-1 Cell-2 UPS01 Power module failure | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1433 | TT_TASK | COLO-2 Cell-1 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1434 | TT_TASK | COLO-2 Cell-3 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1435 | TT_TASK | COLO-2 Cell-4 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1437 | TT_TASK | COLO-3 Delay in SE uploading QC Checkilst | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Fri Aug 06 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1439 | TT_TASK | COLO-2 Cell-2 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1442 | TT_TASK | Mobilization | Mon Apr 27 07:00:00 IDT 2020 | Wed May 20 17:00:00 IDT 2020 | Mon Apr 06 00:00:00 IDT 2020 | Sat May 02 17:00:00 IDT 2020 |  | COMPLETED
1444 | TT_TASK | Establish Access Roads / Laydown / Craft Parking / Temp Utilities | Thu May 14 07:00:00 IDT 2020 | Fri Jun 19 17:00:00 IDT 2020 | Fri Apr 24 00:00:00 IDT 2020 | Sat May 23 00:00:00 IDT 2020 |  | COMPLETED
1446 | TT_TASK | Site Sanitary | Mon May 11 07:00:00 IDT 2020 | Fri Jul 24 17:00:00 IDT 2020 | Tue May 05 00:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 |  | COMPLETED
1447 | TT_TASK | Remaining Site Sanitary | Mon May 11 07:00:00 IDT 2020 | Fri Jul 24 17:00:00 IDT 2020 | Tue Aug 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
1448 | TT_TASK | IWW System | Tue May 26 07:00:00 IDT 2020 | Sat Aug 08 17:00:00 IDT 2020 | Mon May 18 00:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 |  | COMPLETED
1449 | TT_TASK | Remaining IWW System | Tue May 26 07:00:00 IDT 2020 | Sat Aug 08 17:00:00 IDT 2020 | Tue Aug 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
1450 | TT_TASK | Site Water / Fire Loop | Fri Jul 24 07:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1451 | TT_TASK | Site Storm | Mon Jun 29 07:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
1454 | TT_TASK | Telecom-Communications Site Loop/Ductbank | Mon Jun 29 08:00:00 IDT 2020 | Thu Oct 01 08:00:00 IDT 2020 | Thu Jun 25 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1455 | TT_TASK | Telecom-RNG Fiber Underground installation | Mon Feb 01 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
1456 | TT_TASK | Telecom-RNG Fiber CNR buildout | Mon Oct 05 07:00:00 IDT 2020 | Tue Dec 08 17:00:00 IST 2020 | Mon Oct 05 07:00:00 IDT 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
1461 | TT_TASK | Temp Power/ Telecom duct bank | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Thu Aug 27 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1462 | TT_TASK | Vault- set 1st Vault Along UMS Duct bank run | Thu Sep 03 07:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1463 | TT_TASK | Vault- Set 2nd vault Along UMS Duct Run near COLO-2 | Tue Sep 08 07:00:00 IDT 2020 | Thu Sep 10 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1464 | TT_TASK | Vault- Set vault along URS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1465 | TT_TASK | Vault- Set vault along UMS to JAZ run | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1466 | TT_TASK | Set URS Vault | Mon Nov 16 08:00:00 IST 2020 | Wed Nov 25 08:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1467 | TT_TASK | Set UMS vault | Wed Nov 25 08:00:00 IST 2020 | Tue Dec 08 08:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1469 | TT_TASK | Vault- Set North vault- Along UPM to Vault | Fri Oct 09 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1470 | TT_TASK | Vault - Set North Vault Along Vault to URS run | Fri Oct 23 07:00:00 IDT 2020 | Tue Oct 27 17:00:00 IST 2020 | Thu Aug 20 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1471 | TT_TASK | Vault - Set South Vault Along Vault to URS run | Sat Nov 07 07:00:00 IST 2020 | Tue Nov 10 17:00:00 IST 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1472 | TT_TASK | Vault - Set South Vault along UPM to Vault | Mon Nov 23 07:00:00 IST 2020 | Wed Nov 25 17:00:00 IST 2020 | Thu Aug 20 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1475 | TT_TASK | Duct bank- COLO-1 UPM to north vault | Mon Oct 19 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Fri Oct 02 00:00:00 IDT 2020 | Mon Oct 05 00:00:00 IDT 2020 |  | COMPLETED
1476 | TT_TASK | Duct bank- COLO-2 UPM to north Valut | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Mon Oct 05 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1477 | TT_TASK | Duct Bank- Building to URS - 1st Half | Sat Sep 26 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 07:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
1478 | TT_TASK | Duct Bank- Building to URS(upto horse shoe) - 2nd Half | Wed Sep 30 07:00:00 IDT 2020 | Thu Oct 08 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
1479 | TT_TASK | Duct Bank - JAZ to vault- UMS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Thu Oct 29 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1480 | TT_TASK | Duct Bank - Vault to Vault along UMS duct Run - horseshoe | Mon Oct 26 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
1481 | TT_TASK | Duct Bank - COLO-3 UPM to Vault UMS Run | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1482 | TT_TASK | Duct Bank - URS to vault - URS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1483 | TT_TASK | Duct Bank - Vault To JAZ - URS to JAZ run | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 09 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1484 | TT_TASK | Duct Bank - Vault to UMS- UMS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1485 | TT_TASK | Duct Bank - south vault (along UMS duct run) to UMS | Sat Nov 21 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1486 | TT_TASK | Duct Bank - COLO-4 UPM to UMS | Mon Nov 23 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
1488 | TT_TASK | Duct Bank - COLO1- UPM to UPM | Mon Aug 10 07:00:00 IDT 2020 | Thu Aug 13 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1489 | TT_TASK | Duct Bank - COLO2- UPM to UPM | Mon Aug 31 07:00:00 IDT 2020 | Thu Sep 03 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
1490 | TT_TASK | Duct Bank - North Crossover (URS to west Vault Run) | Mon Sep 14 07:00:00 IDT 2020 | Sat Sep 26 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
1491 | TT_TASK | Duct Bank - South Cross over (URS to west Vault Run) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
1492 | TT_TASK | Duct Bank - COLO-3 UPM to UPM | Fri Nov 06 07:00:00 IST 2020 | Tue Nov 10 17:00:00 IST 2020 | Sat Oct 10 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1493 | TT_TASK | Duct Bank - COLO-4 UPM to UPM | Wed Nov 25 07:00:00 IST 2020 | Wed Dec 02 17:00:00 IST 2020 | Sat Oct 10 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1495 | TT_TASK | Duct Bank Admin UPM to COLO-1 UPM | Thu Sep 24 07:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1496 | TT_TASK | Duct Back- Admin UPM to Vault | Fri Oct 23 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Mon Aug 24 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
1497 | TT_TASK | Duct Bank COLO-2 UPM to Vault | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Mon Sep 28 00:00:00 IDT 2020 | Thu Oct 01 00:00:00 IDT 2020 |  | COMPLETED
1498 | TT_TASK | Duct Bank - Building to North Vault URS run | Fri Oct 23 07:00:00 IDT 2020 | Sat Oct 31 17:00:00 IST 2020 | Fri Oct 02 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1499 | TT_TASK | Duct Bank - Builing to South Vault- URS Run | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 09 17:00:00 IST 2020 | Fri Oct 02 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1500 | TT_TASK | Duct Bank - Vault to COLO-3 UPM | Tue Nov 10 07:00:00 IST 2020 | Fri Nov 13 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1501 | TT_TASK | Duct Bank - Vault to COLO-4 UPM | Mon Nov 16 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1503 | TT_TASK | Set MV Gear (URS) | Mon Nov 23 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1504 | TT_TASK | Set MV Gear (UMS) | Mon Dec 21 07:00:00 IST 2020 | Mon Dec 28 17:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
1506 | TT_TASK | Pull UPM to UPM COLO-1 - CELL-1 to Cell-3 | Tue Jan 05 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1507 | TT_TASK | Pul UPM to UPM COLO-2- CELL-1 to Cell-3 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Sat Jan 02 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
1508 | TT_TASK | Pull UPM to UPM COLO-3 - CELL-1 to Cell-3 | Fri Jan 15 07:00:00 IST 2021 | Mon Jan 18 17:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1509 | TT_TASK | Pull UPM to UPM COLO-4 - CELL-1 to Cell-3 | Wed Feb 03 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
1511 | TT_TASK | Pull UPM to UPM Admin to COLO-1 Cell -2 | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1512 | TT_TASK | Pull UPM to UPM COLO-1 Cell 2- Cell - 4 | Thu Jan 07 07:00:00 IST 2021 | Fri Jan 08 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1513 | TT_TASK | Pull UPM to UPM COLO-2 Cell 2- Cell - 4 | Wed Feb 03 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1514 | TT_TASK | Pull UPM to UPM COLO-3 Cell 2- Cell - 4 | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1515 | TT_TASK | Pull UPM to UPM COLO-4 Cell 2- Cell - 4 | Thu Feb 11 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1517 | TT_TASK | Pull Cross Overs- COLO-1 CELL-3 to CELL-4 | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1518 | TT_TASK | Pull Cross Overs- COLO-2 CELL-3 to CELL-4 | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1519 | TT_TASK | Pull Cross Overs- COLO-3 CELL-3 to CELL-4 | Tue Feb 09 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1520 | TT_TASK | Pull Cross Overs- COLO-4 CELL-3 to CELL-4 | Sat Feb 13 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1522 | TT_TASK | PULL- URS to Admin | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Sat Dec 05 00:00:00 IST 2020 |  | COMPLETED
1523 | TT_TASK | PULL- URS to COLO-2 | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
1524 | TT_TASK | PULL- URS to COLO-3 | Tue Jan 12 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1525 | TT_TASK | PULL- URS to COLO-4 | Mon Jan 18 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1527 | TT_TASK | Pull- UMS to COLO-1,2,3 | Tue Jan 12 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Jan 11 17:00:00 IST 2021 |  | COMPLETED
1528 | TT_TASK | Pull- UMS to COLO-4 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 |  | COMPLETED
1530 | TT_TASK | Pull - JAZ to URS | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
1531 | TT_TASK | Pull - JAZ to UMS | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1534 | TT_TASK | Term COLO -1 Cell-3 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1535 | TT_TASK | Term COLO -2 Cell-3 UPM | Thu Mar 04 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1536 | TT_TASK | Term COLO -3 Cell-3 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 |  | COMPLETED
1537 | TT_TASK | Term COLO -4 Cell-3 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1538 | TT_TASK | Term COLO -1 Cell-1 UPM | Wed Feb 10 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1539 | TT_TASK | Term COLO -2 Cell-1 UPM | Sat Feb 13 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1540 | TT_TASK | Term COLO -3 Cell-1 UPM | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1541 | TT_TASK | Term COLO -4 Cell-1 UPM | Thu Mar 11 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1543 | TT_TASK | Term COLO -1 Cell-4 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
1544 | TT_TASK | Term COLO -2 Cell-4 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1545 | TT_TASK | Term COLO -3 Cell-4 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1546 | TT_TASK | Term COLO -4 Cell-4 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1547 | TT_TASK | Term Admin - UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1548 | TT_TASK | Term COLO -1 Cell-2 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
1549 | TT_TASK | Term COLO -2 Cell-2 UPM | Fri Feb 05 07:00:00 IST 2021 | Tue Feb 09 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1550 | TT_TASK | Term COLO -3 Cell-2 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1551 | TT_TASK | Term COLO -4 Cell-2 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1553 | TT_TASK | Battery Station Yellow tagging / EPMS Checkouts | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1554 | TT_TASK | GCPUD NORTH Mobile substation maintance & Mobile Sub re-energization 4/1 Â– 4/3 | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1555 | TT_TASK | GCPUD SOUTH Mobile substation maintance & Mobile Sub re-energization 4/1 Â– 4/3 | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1556 | TT_TASK | Term- UMS- Line Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1557 | TT_TASK | Term- JAZ to Structure- (Incl Stress Cones) from ums | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1558 | TT_TASK | Term- UMS- Load side | Wed Feb 10 07:00:00 IST 2021 | Tue Feb 23 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1559 | TT_TASK | Yellow Tagging for UMS (includes GC, vendor Lvl-2) | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
1560 | TT_TASK | UMS Control Power Available CYT | Wed Feb 10 07:00:00 IST 2021 | Wed Feb 17 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
1562 | TT_TASK | Term URS- Line Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
1563 | TT_TASK | Term- JAS to URS- (Incl Stress Cones) | Wed Feb 03 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1564 | TT_TASK | TERM- URS- Load Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1565 | TT_TASK | Yellow Tagging for URS | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
1566 | TT_TASK | URS Control Power Available CYT | Wed Feb 10 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
1568 | TT_TASK | Aggregate Road Base | Mon Oct 19 07:00:00 IDT 2020 | Tue Nov 24 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
1569 | TT_TASK | Plant shutdown for winter | Mon Nov 30 07:00:00 IST 2020 | Tue Apr 06 17:00:00 IDT 2021 | Mon Nov 23 00:00:00 IST 2020 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
1570 | TT_TASK | Curb & Gutter | Mon Nov 30 07:00:00 IST 2020 | Sat Jan 09 17:00:00 IST 2021 | Mon Nov 02 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1571 | TT_TASK | Pave HMA | Mon Apr 05 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Sat Nov 07 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1572 | TT_TASK | Site Lighting | Mon May 03 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 |  | 120.0 | IN_PROGRESS
1575 | TT_TASK | Landscape and Site Specialties | Mon May 17 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1581 | TT_TASK | Perimeter Foundations - Excavate/FRP | Mon Apr 27 07:00:00 IDT 2020 | Thu May 14 17:00:00 IDT 2020 | Wed Apr 22 00:00:00 IDT 2020 | Wed May 20 00:00:00 IDT 2020 |  | COMPLETED
1582 | TT_TASK | Perimeter Foundations - Waterproof/Backfill | Mon Jun 01 07:00:00 IDT 2020 | Thu Jun 04 17:00:00 IDT 2020 | Wed May 27 00:00:00 IDT 2020 | Fri Jun 05 00:00:00 IDT 2020 |  | COMPLETED
1583 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Fri Jun 05 07:00:00 IDT 2020 | Tue Jun 16 17:00:00 IDT 2020 | Tue Jun 02 00:00:00 IDT 2020 | Fri Jun 12 00:00:00 IDT 2020 |  | COMPLETED
1585 | TT_TASK | Erect PEMB Steel | Mon Jun 29 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 |  | COMPLETED
1586 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Thu Jul 02 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
1588 | TT_TASK | MEP Undeground Rough-In (Interior) | Tue Aug 18 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1589 | TT_TASK | Aggregate Base Course | Mon Aug 31 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 |  | COMPLETED
1590 | TT_TASK | Slab on Grade | Mon Sep 14 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1592 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Aug 18 07:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 |  | COMPLETED
1593 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Tue Jul 14 00:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 |  | COMPLETED
1594 | TT_TASK | Downspouts & Gutters | Tue Aug 18 07:00:00 IDT 2020 | Sat Aug 29 17:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
1604 | TT_TASK | Perimeter Foundations - Excavate/FRP | Fri May 15 07:00:00 IDT 2020 | Wed Jun 03 17:00:00 IDT 2020 | Mon May 04 00:00:00 IDT 2020 | Fri May 15 00:00:00 IDT 2020 |  | COMPLETED
1605 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Sat Jun 13 07:00:00 IDT 2020 | Thu Jun 25 17:00:00 IDT 2020 | Tue Jun 02 00:00:00 IDT 2020 | Fri Jun 12 00:00:00 IDT 2020 |  | COMPLETED
1606 | TT_TASK | Perimeter Foundations - Waterproof Backfill | Tue May 26 07:00:00 IDT 2020 | Sat Jun 06 17:00:00 IDT 2020 | Tue May 26 07:00:00 IDT 2020 | Wed Jun 17 00:00:00 IDT 2020 |  | COMPLETED
1608 | TT_TASK | Erect PEMB Steel | Mon Jun 29 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Fri Jun 26 00:00:00 IDT 2020 | Mon Jul 06 00:00:00 IDT 2020 |  | COMPLETED
1609 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 |  | COMPLETED
1610 | TT_TASK | Erect Interior Structural Steel | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
1612 | TT_TASK | MEP Undeground Rough-In (Interior) | Fri Aug 14 07:00:00 IDT 2020 | Tue Sep 01 17:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1613 | TT_TASK | Aggregate Base Course | Sat Sep 05 07:00:00 IDT 2020 | Fri Sep 11 17:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 |  | COMPLETED
1614 | TT_TASK | Slab on Grade | Mon Sep 14 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1618 | TT_TASK | Exterior Insulated Metal Panels Installation - East Elevation | Tue Aug 18 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Mon Jul 13 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1621 | TT_TASK | Exterior Insulated Metal Panels Installation - West Elevation | Tue Aug 18 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Mon Jul 13 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1623 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 |  | COMPLETED
1624 | TT_TASK | Downspouts & Gutters | Tue Aug 18 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Wed Aug 12 00:00:00 IDT 2020 |  | COMPLETED
1629 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jun 22 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Mon May 11 00:00:00 IDT 2020 | Tue Jun 16 00:00:00 IDT 2020 |  | COMPLETED
1630 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Wed Jul 08 07:00:00 IDT 2020 | Mon Jul 20 17:00:00 IDT 2020 | Tue Jun 09 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
1632 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Tue Jul 07 00:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 |  | COMPLETED
1633 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 | Tue Aug 04 00:00:00 IDT 2020 |  | COMPLETED
1634 | TT_TASK | Erect Interior Structural Steel | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1636 | TT_TASK | MEP Undeground Rough-In (Interior) | Mon Aug 31 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 |  | COMPLETED
1637 | TT_TASK | Aggregate Base Course | Mon Oct 19 07:00:00 IDT 2020 | Mon Oct 26 17:00:00 IST 2020 | Thu Oct 01 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1638 | TT_TASK | Slab on Grade | Mon Oct 19 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1640 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Aug 18 07:00:00 IDT 2020 | Tue Sep 01 17:00:00 IDT 2020 | Fri Jul 31 00:00:00 IDT 2020 | Thu Aug 13 00:00:00 IDT 2020 |  | COMPLETED
1641 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Wed Aug 26 17:00:00 IDT 2020 | Fri Jul 31 00:00:00 IDT 2020 | Fri Aug 14 00:00:00 IDT 2020 |  | COMPLETED
1642 | TT_TASK | Downspouts & Gutters | Sat Sep 05 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 |  | COMPLETED
1647 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Wed Jul 08 07:00:00 IDT 2020 | Mon Jul 20 17:00:00 IDT 2020 | Wed Jun 24 00:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 |  | COMPLETED
1648 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jun 22 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Tue Jun 16 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1650 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 |  | COMPLETED
1651 | TT_TASK | Secondary Steel | Mon Aug 31 07:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 |  | COMPLETED
1652 | TT_TASK | Erect Interior Structural Steel | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1654 | TT_TASK | MEP Undeground Rough-In (Interior) | Mon Oct 19 07:00:00 IDT 2020 | Thu Nov 05 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1655 | TT_TASK | Aggregate Base Course | Fri Nov 06 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1656 | TT_TASK | Slab on Grade | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
1658 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Sep 08 07:00:00 IDT 2020 | Tue Sep 22 17:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1659 | TT_TASK | Roof Panels Installation | Tue Sep 08 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 | Tue Sep 01 00:00:00 IDT 2020 |  | COMPLETED
1660 | TT_TASK | Downspouts & Gutters | Wed Sep 16 07:00:00 IDT 2020 | Tue Sep 22 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
1670 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jul 06 07:00:00 IDT 2020 | Thu Jul 23 17:00:00 IDT 2020 | Tue Jun 23 00:00:00 IDT 2020 | Thu Jul 30 00:00:00 IDT 2020 |  | COMPLETED
1671 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Sat Aug 29 07:00:00 IDT 2020 | Thu Sep 10 17:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 |  | COMPLETED
1673 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Sat Aug 08 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
1674 | TT_TASK | Secondary Steel | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 08 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1675 | TT_TASK | Erect Interior Structural Steel | Mon Dec 21 07:00:00 IST 2020 | Tue Dec 29 17:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
1677 | TT_TASK | MEP Undeground Rough-In (Interior) | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1678 | TT_TASK | Aggregate Base Course | Wed Nov 11 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
1679 | TT_TASK | Slab on Grade | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1681 | TT_TASK | Exterior Insulated Metal Panels Installation | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Sep 30 00:00:00 IDT 2020 |  | COMPLETED
1682 | TT_TASK | Roof Panels Installation | Thu Sep 03 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Thu Aug 27 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1683 | TT_TASK | Downspouts & Gutters | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Sep 07 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1693 | TT_TASK | Hang Wall Partitions | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1694 | TT_TASK | Hang Wall Partitions- Early Walls | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1695 | TT_TASK | MEP Rough-In / Wall & Ceiling | Mon Oct 19 07:00:00 IDT 2020 | Mon Nov 02 17:00:00 IST 2020 | Thu Oct 01 00:00:00 IDT 2020 | Tue Nov 17 00:00:00 IST 2020 |  | COMPLETED
1697 | TT_TASK | Early Room - Finishes | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1699 | TT_TASK | Loading Dock Equipment & Dock Doors | Wed May 05 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
1700 | TT_TASK | MEP Overhead | Mon Oct 19 07:00:00 IDT 2020 | Tue Nov 17 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1701 | TT_TASK | Ceilings / Ligthing / FA Devices | Mon Mar 01 07:00:00 IST 2021 | Tue Apr 13 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
1702 | TT_TASK | Concrete Floor Sealing/Epoxy | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1706 | TT_TASK | Generator Term | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
1707 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 | Fri Sep 25 00:00:00 IDT 2020 |  | COMPLETED
1708 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Fri Sep 18 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
1709 | TT_TASK | Set Exterior Electrical OFCI Equipment | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1710 | TT_TASK | Admin -Electrical Underground Rough-In | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 31 17:00:00 IDT 2020 | Fri Aug 07 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
1711 | TT_TASK | Generator & Utility Power Pull-Test | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1712 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Jan 18 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1713 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1715 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Oct 19 07:00:00 IDT 2020 | Mon Nov 02 17:00:00 IST 2020 | Fri Oct 09 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1716 | TT_TASK | Set Exterior Mechanical CFCI Equipment (remaning mini splits) | Fri Nov 06 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1717 | TT_TASK | Mechanical Underground Rough-In | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 31 17:00:00 IDT 2020 | Sat Aug 08 00:00:00 IDT 2020 | Tue Aug 25 00:00:00 IDT 2020 |  | COMPLETED
1718 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1721 | TT_TASK | Fire Alarm Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1722 | TT_TASK | Controls Installation | Tue Feb 16 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
1724 | TT_TASK | Set Electrical Equipment incl. OH raceways | Mon Nov 23 07:00:00 IST 2020 | Wed Jan 13 17:00:00 IST 2021 | Mon Nov 16 00:00:00 IST 2020 | Tue Dec 29 00:00:00 IST 2020 |  | COMPLETED
1725 | TT_TASK | Electrical Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1727 | TT_TASK | Domestic Water Piping | Mon Nov 23 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1728 | TT_TASK | Plumbing Devices & Trim | Mon Jul 26 15:00:00 IDT 2021 | Tue Aug 17 15:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
1730 | TT_TASK | Security Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
1732 | TT_TASK | Mechanical Ductwork Installation | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1733 | TT_TASK | Set Mechanical Equipment | Mon Nov 23 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
1734 | TT_TASK | Mechanical Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1739 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1740 | TT_TASK | Overhead MEPFP Rough-In | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 11 17:00:00 IST 2020 | Wed Oct 14 00:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
1741 | TT_TASK | Early Topout | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1743 | TT_TASK | Sprinkler Test | Mon Dec 21 07:00:00 IST 2020 | Tue Dec 22 17:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1744 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1747 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1748 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1749 | TT_TASK | Early Topout | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Tue Nov 10 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1751 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Nov 30 07:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1754 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 |  | COMPLETED
1755 | TT_TASK | Overhead MEPFP Rough-In | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 11 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 |  | COMPLETED
1756 | TT_TASK | Early Topout | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1758 | TT_TASK | Datahall Finishes- Ceiling Grid | Thu Dec 03 07:00:00 IST 2020 | Tue Dec 15 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1761 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1762 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1763 | TT_TASK | Early Topout | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Tue Nov 10 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1765 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1768 | TT_TASK | Remaining MER raceway across Mech chase | Tue Dec 01 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1769 | TT_TASK | Electrical OH Below Mechanical Piping | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1770 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1771 | TT_TASK | OverHead MEPFP Rough-In ( Add TCM Cross over piping HRA Level-3) | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1772 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1774 | TT_TASK | Mechanical Corridor Finishes | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1777 | TT_TASK | Remaining MER raceway across Mech chase | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1778 | TT_TASK | Electrical OH Below Mechanical Piping | Wed Jan 20 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1779 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 11 00:00:00 IST 2020 |  | COMPLETED
1780 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1781 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1783 | TT_TASK | Mechanical Corridor Finishes | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1786 | TT_TASK | Remaining MER raceway across Mech chase | Tue Dec 01 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1787 | TT_TASK | Electrical OH Below Mechanical Piping | Mon Jan 04 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1788 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1789 | TT_TASK | OverHead MEPFP Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1790 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1792 | TT_TASK | Mechanical Corridor Finishes | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1795 | TT_TASK | Remaining MER raceway across Mech chase | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1796 | TT_TASK | Electrical OH Below Mechanical Piping | Wed Jan 20 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1797 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 11 00:00:00 IST 2020 |  | COMPLETED
1798 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1799 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1801 | TT_TASK | Mechanical Corridor Finishes | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Tue Nov 17 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1805 | TT_TASK | Generator & Utility Power Term | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1806 | TT_TASK | Remaining Mechanical Equipment (ADP01) Termimations | Thu Mar 18 07:00:00 IST 2021 | Tue Mar 23 17:00:00 IST 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1807 | TT_TASK | Electrical Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 14 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1808 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1809 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1810 | TT_TASK | Exterior Equipment Pads - Electrical | Thu Sep 03 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1811 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Oct 12 07:00:00 IDT 2020 | Mon Oct 26 17:00:00 IST 2020 | Mon Oct 12 07:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1812 | TT_TASK | Lift & Set MER in Place | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Wed Dec 16 00:00:00 IST 2020 | Wed Dec 16 17:00:00 IST 2020 |  | COMPLETED
1813 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
1814 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 13 17:00:00 IST 2021 | Thu Dec 17 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1815 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Jan 11 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Tue Jan 05 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1816 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1817 | TT_TASK | Generator & Utility Power Pull | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1819 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1820 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1821 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1822 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1823 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Sat Dec 05 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1824 | TT_TASK | Mechanical Equipment Piping Connections | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1825 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
1828 | TT_TASK | Fire Alarm Installation | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1829 | TT_TASK | Controls Installation | Fri Mar 05 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1832 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 22 07:00:00 IST 2021 | Tue Mar 30 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1833 | TT_TASK | Electrical Underground Rough-In | Thu Sep 03 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1834 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1835 | TT_TASK | Set Electrical Equipment-UPM Cell -3 | Fri Dec 11 07:00:00 IST 2020 | Tue Dec 15 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1836 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
1837 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1838 | TT_TASK | Lift & Set MER in Place | Mon Jan 11 08:00:00 IST 2021 | Mon Jan 18 08:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1839 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 18 08:00:00 IST 2021 | Fri Jan 22 08:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1840 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
1841 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1842 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
1843 | TT_TASK | Generator & Utility Power Pull | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1845 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1846 | TT_TASK | Exterior Equipment Pads - Mechanical | Fri Oct 16 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Sat Sep 19 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
1847 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1848 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1849 | TT_TASK | Set Exterior Water Treatment equipment | Mon Dec 07 07:00:00 IST 2020 | Tue Dec 08 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1850 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1851 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 15 07:00:00 IST 2021 | Mon Mar 22 17:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
1854 | TT_TASK | Fire Alarm Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1855 | TT_TASK | Controls Installation | Tue Mar 09 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1858 | TT_TASK | Generator & Utility Power Pull | Tue Feb 02 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Feb 26 07:00:00 IST 2021 |  | COMPLETED
1859 | TT_TASK | Remaining Mechanical Equipment (ADP01) Termimations | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1860 | TT_TASK | Electrical Underground Rough-In | Fri Aug 14 07:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1861 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 05 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1862 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1863 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Sep 05 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Fri Oct 02 00:00:00 IDT 2020 |  | COMPLETED
1864 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Oct 26 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1865 | TT_TASK | Lift & Set MER in Place | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
1866 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 11 08:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1867 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1868 | TT_TASK | GEN & UPM to MER Cable Bus Install | Wed Jan 20 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1869 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1870 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1872 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1873 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Oct 05 07:00:00 IDT 2020 | Sat Oct 17 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
1874 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1875 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1876 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1877 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1878 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 08 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1881 | TT_TASK | Fire Alarm Installation | Thu Feb 18 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1882 | TT_TASK | Controls Installation | Sat Mar 06 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
1885 | TT_TASK | Generator & Utility Power Pull | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1886 | TT_TASK | Electrical Underground Rough-In | Sat Sep 05 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1887 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1888 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1889 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1890 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1891 | TT_TASK | Lift & Set MER in Place | Mon Jan 11 08:00:00 IST 2021 | Mon Jan 18 08:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1892 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 11 08:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Jan 11 08:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1893 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1894 | TT_TASK | GEN & UPM to MER Cable Bus Install | Thu Feb 04 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1895 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Wed Apr 07 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
1896 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 15 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
1898 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Sep 14 07:00:00 IDT 2020 | Sat Sep 26 17:00:00 IDT 2020 | Mon Sep 14 07:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1899 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1900 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1901 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1902 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1903 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1904 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
1907 | TT_TASK | Fire Alarm Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1908 | TT_TASK | Controls Installation | Thu Apr 15 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1911 | TT_TASK | VFD'S Installation & wirepull | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1912 | TT_TASK | Ligthing Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 |  | COMPLETED
1914 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Thu Nov 26 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
1915 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1917 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1919 | TT_TASK | Fire Riser Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1920 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1921 | TT_TASK | Controls Installation | Fri Mar 26 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1924 | TT_TASK | VFD'S Installation & Wiring | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
1925 | TT_TASK | Ligthing Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1927 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
1928 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1930 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1932 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1933 | TT_TASK | Controls Installation | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1936 | TT_TASK | VFD'S Installation & Wiring | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1937 | TT_TASK | Ligthing Installation | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1939 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
1940 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1942 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1944 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1945 | TT_TASK | Controls Installation | Tue Apr 13 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1948 | TT_TASK | VFD'S Installation & Wiring | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
1949 | TT_TASK | Ligthing Installation | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jul 29 00:00:00 IDT 2021 |  | COMPLETED
1951 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
1952 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1954 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1956 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1957 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1961 | TT_TASK | HAC Installation | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
1962 | TT_TASK | Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1963 | TT_TASK | Power Bus Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1964 | TT_TASK | PDU's Installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1965 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Apr 05 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1966 | TT_TASK | Light Fixtures Installation | Wed May 05 07:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
1967 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
1969 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
1970 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1971 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1972 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1974 | TT_TASK | Security Devices & Trim | Mon May 17 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
1975 | TT_TASK | Controls Installation | Fri Mar 26 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1976 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1979 | TT_TASK | HAC Installation | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1980 | TT_TASK | Cable Tray Installation | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
1981 | TT_TASK | Power Bus Installation | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1982 | TT_TASK | PDU's Installation | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
1983 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Apr 26 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1984 | TT_TASK | Light Fixtures Installation | Wed May 12 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1985 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Apr 26 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
1987 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
1988 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1989 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1990 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Thu Jul 01 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1992 | TT_TASK | Security Devices & Trim | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
1993 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1994 | TT_TASK | Fire Alarm System | Tue May 04 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1997 | TT_TASK | HAC Installation | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1998 | TT_TASK | Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1999 | TT_TASK | Power Bus Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
2000 | TT_TASK | PDU's Installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
2001 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Apr 01 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2002 | TT_TASK | Light Fixtures Installation | Tue May 11 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
2003 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 23 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
2005 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2006 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2007 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2008 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed May 19 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2010 | TT_TASK | Security Devices & Trim | Mon May 17 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2011 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2012 | TT_TASK | Fire Alarm System | Thu May 06 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2015 | TT_TASK | HAC Installation | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2016 | TT_TASK | Cable Tray Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2017 | TT_TASK | Power Bus Installation | Fri Mar 12 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2018 | TT_TASK | PDU's Installation | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2019 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon May 03 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
2020 | TT_TASK | Light Fixtures Installation | Fri May 21 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2021 | TT_TASK | Pull/term/Test PDU to Power bus | Mon May 03 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2023 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2024 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2025 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2026 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed May 19 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2028 | TT_TASK | Security Devices & Trim | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 |  | COMPLETED
2029 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2030 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2036 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2037 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
2038 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2040 | TT_TASK | Datahall Finishes - Ceiling Grid | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2043 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2044 | TT_TASK | Overhead MEPFP Rough-In | Fri Nov 06 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2045 | TT_TASK | Hang drywall / Mud / Tape | Wed Jan 06 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2047 | TT_TASK | Datahall Finishes - Ceiling Grid | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2050 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2051 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
2052 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2054 | TT_TASK | Datahall Finishes - Ceiling Grid | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2057 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2058 | TT_TASK | Overhead MEPFP Rough-In | Fri Nov 06 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2059 | TT_TASK | Hang drywall / Mud / Tape | Wed Jan 06 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2061 | TT_TASK | Datahall Finishes - Ceiling Grid | Mon Jan 11 07:00:00 IST 2021 | Wed Jan 20 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2064 | TT_TASK | Remaining Post MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2065 | TT_TASK | Frame & Top out | Mon Nov 23 07:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2066 | TT_TASK | OverHead MEPFP Rough-In | Thu Nov 19 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2067 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Dec 12 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2069 | TT_TASK | Mechanical Corridor Finishes | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2072 | TT_TASK | Remaining MER raceway across Mech chase | Thu Mar 25 07:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2073 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2074 | TT_TASK | OverHead MEPFP Rough-In | Tue Dec 08 07:00:00 IST 2020 | Mon Dec 21 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2075 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Dec 14 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2077 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2080 | TT_TASK | Remaining MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 |  | COMPLETED
2081 | TT_TASK | Frame & Top out | Mon Nov 30 07:00:00 IST 2020 | Wed Dec 09 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2082 | TT_TASK | OverHead MEPFP Rough-In | Sat Dec 19 07:00:00 IST 2020 | Thu Jan 07 17:00:00 IST 2021 | Mon Oct 26 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2083 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Dec 12 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2085 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2088 | TT_TASK | Remaining MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Mar 12 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2089 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2090 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2091 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 30 07:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
2093 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2097 | TT_TASK | Generator & Utility Power Pull | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
2098 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
2099 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2100 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
2101 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Dec 14 07:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 |  | COMPLETED
2102 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Tue Dec 29 00:00:00 IST 2020 |  | COMPLETED
2103 | TT_TASK | Lift & Set MER in Place | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2104 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 |  | COMPLETED
2105 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
2106 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Mar 22 07:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Fri Mar 05 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
2107 | TT_TASK | Generator & Utility Power Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2108 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2110 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
2111 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 08 17:00:00 IST 2021 | Mon Nov 02 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
2112 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2113 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2114 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2115 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2116 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2119 | TT_TASK | Fire Alarm Installation | Tue May 11 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2120 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2123 | TT_TASK | Generator & Utility Power Pull | Tue May 11 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
2124 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 21 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2125 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2126 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Wed Dec 16 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2127 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Dec 14 07:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2128 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2129 | TT_TASK | Lift & Set MER in Place | Tue Mar 23 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
2130 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Mar 29 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2131 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Mar 29 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2132 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Fri Apr 16 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
2133 | TT_TASK | Generator & Utility Power Test-Term | Thu May 06 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2134 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
2136 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2137 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 08 17:00:00 IST 2021 | Mon Nov 16 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2138 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2139 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2140 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2141 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2142 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
2145 | TT_TASK | Fire Alarm Installation | Wed May 26 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2146 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2149 | TT_TASK | Generator & Utility Power Pull | Fri Mar 26 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
2150 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2151 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
2152 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Wed Nov 04 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2153 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Tue Nov 03 00:00:00 IST 2020 |  | COMPLETED
2154 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
2155 | TT_TASK | Lift & Set MER in Place | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2156 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Mar 27 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2157 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Mar 27 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2158 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Thu Mar 25 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
2159 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2160 | TT_TASK | Generator & Utility Power Test-Term | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Tue Apr 06 07:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2162 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2163 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2164 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2165 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2166 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Fri Jan 15 07:00:00 IST 2021 | Fri Jan 29 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2167 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
2168 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
2171 | TT_TASK | Fire Alarm Installation | Tue May 11 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2172 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2175 | TT_TASK | Generator & Utility Power Pull | Thu May 13 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2176 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2177 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2178 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2179 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2180 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
2181 | TT_TASK | Lift & Set MER in Place | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
2182 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Mar 27 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2183 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Mar 27 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
2184 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Thu Apr 15 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
2185 | TT_TASK | Generator & Utility Power Test-Term | Tue May 18 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2186 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2188 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2189 | TT_TASK | Set Gen Stack / Exhaust duct | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2192 | TT_TASK | Fire Alarm Installation | Wed May 12 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2193 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2196 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 |  | COMPLETED
2197 | TT_TASK | Ligthing Installation | Fri Jul 23 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2199 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2200 | TT_TASK | Hydronic Piping Installation | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2202 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2203 | TT_TASK | Toilet Piping Installation / DW | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2205 | TT_TASK | Fire Riser Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2206 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2207 | TT_TASK | Controls Installation | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue Jun 08 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2210 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2211 | TT_TASK | Ligthing Installation | Sat Aug 07 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2213 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
2214 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2216 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2217 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2219 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2220 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
2223 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2224 | TT_TASK | Ligthing Installation | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2226 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
2227 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2229 | TT_TASK | Toilet Piping Installation / DW | Mon May 03 07:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2230 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2232 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2233 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri Jul 09 08:12:00 IDT 2021 |  | COMPLETED
2236 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2237 | TT_TASK | Ligthing Installation | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2239 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
2240 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2242 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2243 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2245 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2246 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2249 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2250 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2251 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
2252 | TT_TASK | Power Bus Installation | Fri Mar 26 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2253 | TT_TASK | PDU's Installation | Fri Mar 26 07:00:00 IDT 2021 | Mon Mar 29 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
2254 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2255 | TT_TASK | Light Fixtures Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2256 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 23 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
2258 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Jun 10 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2259 | TT_TASK | BMS Pull Wire / Term / Test | Thu Jun 10 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2260 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Jul 23 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2262 | TT_TASK | Fire Alarm System | Tue May 04 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2263 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2266 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2267 | TT_TASK | HAC Installation | Wed Feb 03 07:00:00 IST 2021 | Wed Feb 17 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Wed Feb 03 00:00:00 IST 2021 |  | COMPLETED
2268 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
2269 | TT_TASK | Power Bus Installation | Mon Mar 22 07:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2270 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2271 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Tue Jun 08 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2272 | TT_TASK | Light Fixtures Installation | Wed Jun 23 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
2273 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2275 | TT_TASK | EPMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 |  | COMPLETED
2276 | TT_TASK | BMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 |  | COMPLETED
2277 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon Aug 09 07:00:00 IDT 2021 | Wed Sep 01 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2279 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2280 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2283 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2284 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2285 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
2286 | TT_TASK | Power Bus Installation | Fri Mar 26 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2287 | TT_TASK | PDU's Installation | Mon Mar 22 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2288 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2289 | TT_TASK | Light Fixtures Installation | Fri Jun 18 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Jun 18 07:00:00 IDT 2021 | Thu Jul 01 00:00:00 IDT 2021 |  | COMPLETED
2290 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 02 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
2292 | TT_TASK | EPMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2293 | TT_TASK | BMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2294 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Jul 30 07:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2296 | TT_TASK | Fire Alarm System | Mon May 10 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon May 10 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 |  | COMPLETED
2297 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2300 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Thu Apr 22 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2301 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
2302 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2303 | TT_TASK | Power Bus Installation | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2304 | TT_TASK | PDU's Installation | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2305 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Jun 09 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2306 | TT_TASK | Light Fixtures Installation | Wed Jun 23 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2307 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2309 | TT_TASK | EPMS Pull Wire / Term / Test | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2310 | TT_TASK | BMS Pull Wire / Term / Test | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2311 | TT_TASK | ` | Tue Aug 24 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2313 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2314 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2319 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2320 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
2321 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2323 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2326 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
2327 | TT_TASK | Overhead MEPFP Rough-In | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 |  | COMPLETED
2328 | TT_TASK | Hang drywall / Mud / Tape | Thu Jan 14 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2330 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2333 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2334 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2335 | TT_TASK | Hang drywall / Mud / Tape | Fri Jan 08 07:00:00 IST 2021 | Mon Jan 18 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2337 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2340 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
2341 | TT_TASK | Overhead MEPFP Rough-In | Fri Jan 15 07:00:00 IST 2021 | Wed Jan 27 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2342 | TT_TASK | Hang drywall / Mud / Tape | Thu Jan 14 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2344 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2347 | TT_TASK | Remaining MER raceway across Mech chase | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2348 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
2349 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2350 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Thu Jan 21 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Thu Jan 21 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 |  | COMPLETED
2352 | TT_TASK | Mechanical Corridor Finishes | Fri Mar 05 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2355 | TT_TASK | Remaining MER raceway across Mech chase | Thu Jun 17 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2356 | TT_TASK | Frame & Top out | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2357 | TT_TASK | OverHead MEPFP Rough-In | Wed Jan 13 07:00:00 IST 2021 | Wed Jan 27 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2358 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
2360 | TT_TASK | Mechanical Corridor Finishes | Wed Feb 03 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2363 | TT_TASK | Remaining MER raceway across Mech chase | Mon May 03 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2364 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
2365 | TT_TASK | OverHead MEPFP Rough-In | Tue Jan 12 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2366 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2368 | TT_TASK | Mechanical Corridor Finishes | Tue Feb 02 07:00:00 IST 2021 | Tue Feb 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2371 | TT_TASK | Remaining MER raceway across Mech chase | Thu Jun 17 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
2372 | TT_TASK | Frame & Top out | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2373 | TT_TASK | OverHead MEPFP Rough-In | Fri Jan 08 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2374 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2376 | TT_TASK | Mechanical Corridor Finishes | Tue Feb 23 07:00:00 IST 2021 | Tue Mar 16 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2380 | TT_TASK | Generator & Utility Power Pull | Wed May 19 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2381 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
2382 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2383 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 29 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
2384 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 07:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
2385 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2386 | TT_TASK | Lift & Set MER in Place | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
2387 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
2388 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon May 03 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2389 | TT_TASK | GEN & UPM to MER Cable Bus Install | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2390 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2391 | TT_TASK | Generator & Utility Power Test-Term | Wed Jun 02 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
2393 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
2394 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2395 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
2396 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2397 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2398 | TT_TASK | Set Exterior Water Treatment equipment | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 01 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2399 | TT_TASK | Mechanical Equipment Piping Connections | Fri Apr 30 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2402 | TT_TASK | Fire Alarm Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2403 | TT_TASK | Controls Installation | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2406 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2407 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
2408 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2409 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2410 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 02 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2411 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 15 08:00:00 IST 2021 | Mon Mar 22 08:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2412 | TT_TASK | Lift & Set MER in Place | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2413 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2414 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Fri May 07 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2415 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2416 | TT_TASK | Generator & Utility Power Test-Term | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2417 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Jun 08 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Tue Jun 08 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2419 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
2420 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
2423 | TT_TASK | Fire Alarm Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 15 07:00:00 IDT 2021 |  | COMPLETED
2424 | TT_TASK | Controls Installation | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 29 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2427 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2428 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2429 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2430 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 08:00:00 IST 2021 | Tue Jan 12 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2431 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Fri Nov 27 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2432 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
2433 | TT_TASK | Lift & Set MER in Place | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
2434 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2435 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon May 03 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
2436 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Mon May 17 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 |  | COMPLETED
2437 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Thu Jun 10 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2438 | TT_TASK | Generator & Utility Power Test-Term | Thu Jun 03 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
2440 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2441 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2442 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2443 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Apr 26 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2444 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 |  | COMPLETED
2445 | TT_TASK | Set Exterior Water Treatment equipment | Mon Apr 26 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2446 | TT_TASK | Mechanical Equipment Piping Connections | Mon May 03 07:00:00 IDT 2021 | Sat May 08 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2449 | TT_TASK | Fire Alarm Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2450 | TT_TASK | Controls Installation | Fri Jun 25 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2453 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2454 | TT_TASK | Electrical Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2455 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Fri Dec 04 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2456 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2457 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 02 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2458 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
2459 | TT_TASK | Lift & Set MER in Place | Fri May 07 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2460 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2461 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2462 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2463 | TT_TASK | Generator & Utility Power Test-Term | Tue Jul 06 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 | Thu Jul 15 12:00:00 IDT 2021 |  | COMPLETED
2464 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2466 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Fri Dec 04 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2467 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2468 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2469 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2470 | TT_TASK | Set Exterior Water Treatment equipment | Fri Apr 30 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2471 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
2472 | TT_TASK | Mechanical Equipment Piping Connections | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2475 | TT_TASK | Fire Alarm Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jul 07 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2476 | TT_TASK | Controls Installation | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
2479 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2480 | TT_TASK | Ligthing Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2482 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
2483 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2485 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 00:00:00 IDT 2021 |  | COMPLETED
2486 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2488 | TT_TASK | Fire Riser Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2489 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2490 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2493 | TT_TASK | VFD'S Installation & Wiring | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2494 | TT_TASK | Ligthing Installation | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
2496 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
2497 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2499 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2500 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2502 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2503 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2506 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2507 | TT_TASK | Ligthing Installation | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
2509 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
2510 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2512 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2513 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2515 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2516 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
2519 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
2520 | TT_TASK | Ligthing Installation | Mon Aug 30 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2522 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
2523 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2525 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2526 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2528 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2529 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2532 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 |  | COMPLETED
2533 | TT_TASK | HAC Installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2534 | TT_TASK | Cable Tray Installation | Sat Apr 03 07:00:00 IDT 2021 | Sat Apr 17 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
2535 | TT_TASK | Power Bus Installation | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2536 | TT_TASK | PDU's Installation | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2537 | TT_TASK | Pull/term/Test PDU to Power bus | Sat Jun 19 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2538 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2539 | TT_TASK | Light Fixtures Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
2541 | TT_TASK | EPMS Pull Wire / Term / Test | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2542 | TT_TASK | BMS Pull Wire / Term / Test | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2543 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Aug 20 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Jul 07 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2545 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2546 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
2549 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2550 | TT_TASK | HAC Installation | Wed Apr 07 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2551 | TT_TASK | Cable Tray Installation | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2552 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
2553 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
2554 | TT_TASK | Pull/term/Test PDU to Power bus | Fri Jul 02 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
2555 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Aug 16 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Thu Jul 08 00:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2556 | TT_TASK | Light Fixtures Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2558 | TT_TASK | EPMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2559 | TT_TASK | BMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2560 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2562 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2563 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2566 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 |  | COMPLETED
2567 | TT_TASK | HAC Installation | Sat Apr 03 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2568 | TT_TASK | Cable Tray Installation | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2569 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 |  | COMPLETED
2570 | TT_TASK | PDU's Installation | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2571 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Sat Jul 24 00:00:00 IDT 2021 |  | COMPLETED
2572 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 23 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2573 | TT_TASK | Light Fixtures Installation | Wed Jul 21 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2575 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2576 | TT_TASK | BMS Pull Wire / Term / Test | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2577 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Aug 20 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2579 | TT_TASK | Fire Alarm System | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2580 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2583 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2584 | TT_TASK | HAC Installation | Mon Apr 12 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2585 | TT_TASK | Cable Tray Installation | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2586 | TT_TASK | Power Bus Installation | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
2587 | TT_TASK | PDU's Installation | Mon Jun 14 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
2588 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
2589 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2590 | TT_TASK | Light Fixtures Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2592 | TT_TASK | EPMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2593 | TT_TASK | BMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2594 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed Sep 15 07:00:00 IDT 2021 | Fri Oct 08 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2596 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2597 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2602 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2603 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2604 | TT_TASK | Early Topout | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2606 | TT_TASK | Datahall Finishes | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
2609 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Jan 18 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2610 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2611 | TT_TASK | Early Topout | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
2613 | TT_TASK | Datahall Finishes | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2616 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2617 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2618 | TT_TASK | Early Topout | Tue Feb 09 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2620 | TT_TASK | Datahall Finishes | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
2623 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Jan 18 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2624 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2625 | TT_TASK | Early Topout | Mon Feb 08 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2627 | TT_TASK | Datahall Finishes | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2630 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2631 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2632 | TT_TASK | OverHead MEPFP Rough-In | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
2633 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 15 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
2635 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Sat Jan 09 00:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 |  | COMPLETED
2638 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2639 | TT_TASK | Frame & Top out | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Sat Jan 09 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
2640 | TT_TASK | OverHead MEPFP Rough-In | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2641 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Tue Mar 30 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2643 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 29 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Thu Jan 21 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
2646 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 |  | COMPLETED
2647 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
2648 | TT_TASK | OverHead MEPFP Rough-In | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Feb 05 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2649 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 15 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2651 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
2654 | TT_TASK | Remaining MER raceway across Mech chase | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
2655 | TT_TASK | Frame & Top out | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
2656 | TT_TASK | OverHead MEPFP Rough-In | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2657 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Tue Mar 30 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Fri Feb 12 00:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
2659 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 29 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2663 | TT_TASK | Generator & Utility Power Pull | Wed Jul 28 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2664 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2665 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2666 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Wed Dec 30 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2667 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2668 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Apr 26 08:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2669 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
2670 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2671 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2672 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 |  | COMPLETED
2673 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2674 | TT_TASK | Generator & Utility Power Test-Term | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
2676 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2677 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2678 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2679 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2680 | TT_TASK | Set Exterior Water Treatment equipment | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 01 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2681 | TT_TASK | Mechanical Equipment Piping Connections | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2682 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2685 | TT_TASK | Fire Alarm Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
2686 | TT_TASK | Controls Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2689 | TT_TASK | Generator & Utility Power Pull | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 19 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2690 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2691 | TT_TASK | Exterior Equipment Pads - for UPM's | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2692 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2693 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2694 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Apr 26 08:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2695 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2696 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2697 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
2698 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jul 10 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2699 | TT_TASK | Generator & Utility Power Test-Term | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Sat Aug 07 17:00:00 IDT 2021 |  | COMPLETED
2700 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2702 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2703 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2704 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2705 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2706 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2707 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2708 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2711 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
2712 | TT_TASK | Controls Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
2715 | TT_TASK | Generator & Utility Power Pull | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 | Thu Aug 05 09:30:00 IDT 2021 |  | COMPLETED
2716 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2717 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2718 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2719 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2720 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2721 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2722 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2723 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2724 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jul 15 00:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2725 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2726 | TT_TASK | Generator & Utility Power Test-Term | Fri Sep 03 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
2728 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 09 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2729 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2730 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2731 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2732 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2733 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2734 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
2737 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2738 | TT_TASK | Controls Installation | Wed Sep 01 07:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Thu Aug 26 07:00:00 IDT 2021 |  | 1210.0 | IN_PROGRESS
2741 | TT_TASK | Generator & Utility Power Pull | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Thu Jul 29 00:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
2742 | TT_TASK | Electrical Underground Rough-In | Sat Nov 07 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2743 | TT_TASK | Exterior Equipment Pads - for UPM's | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2744 | TT_TASK | Set Electrical Equipment-UPM | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2745 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Jan 18 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2746 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2747 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2748 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2749 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
2750 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2751 | TT_TASK | Generator & Utility Power Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2752 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2754 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2755 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2756 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2757 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2758 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2759 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2760 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2763 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
2764 | TT_TASK | Controls Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
2767 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2768 | TT_TASK | Ligthing Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2770 | TT_TASK | AHU/DOAS Equipment Setting | Sat May 15 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2771 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2773 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2774 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2776 | TT_TASK | Fire Riser Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed May 19 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2777 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2778 | TT_TASK | Controls Installation | Sat Jul 31 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2781 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
2782 | TT_TASK | Ligthing Installation | Thu Sep 16 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
2784 | TT_TASK | AHU/DOAS Equipment Setting | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2785 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2787 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2788 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2790 | TT_TASK | Fire Alarm System | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2791 | TT_TASK | Controls Installation | Mon Aug 23 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2794 | TT_TASK | VFD'S Installation & Wiring | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2795 | TT_TASK | Lighting Installation | Sat Sep 11 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
2797 | TT_TASK | AHU/DOAS Equipment Setting | Sat May 15 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2798 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2800 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2801 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2803 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2804 | TT_TASK | Controls Installation | Mon Aug 16 07:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 |  | COMPLETED
2807 | TT_TASK | VFD'S Installation & Wiring | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2808 | TT_TASK | Ligthing Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
2810 | TT_TASK | AHU/DOAS Equipment Setting | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2811 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2813 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2814 | TT_TASK | Toilet Piping Installation / DW | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
2816 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2817 | TT_TASK | Controls Installation | Wed Sep 08 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2820 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 09 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2821 | TT_TASK | HAC Installation | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2822 | TT_TASK | Cable Tray Installation | Tue May 04 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2823 | TT_TASK | Power Bus Installation | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2824 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2825 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 27 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2826 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Aug 25 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2827 | TT_TASK | Light Fixtures Installation | Sat Aug 21 07:00:00 IDT 2021 | Fri Aug 27 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
2829 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2830 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
2831 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon Sep 27 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2833 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2834 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2837 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 16 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2838 | TT_TASK | HAC Installation | Thu Apr 29 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2839 | TT_TASK | Cable Tray Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2840 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 |  | COMPLETED
2841 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2842 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Fri Sep 03 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2843 | TT_TASK | Pull/term/Test PDU to Power bus | Fri Sep 03 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  | 210.0 | NOT_STARTED
2844 | TT_TASK | Light Fixtures Installation | Fri Oct 01 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2846 | TT_TASK | EPMS Pull Wire / Term / Test | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2847 | TT_TASK | BMS Pull Wire / Term / Test | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
2848 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Thu Oct 21 07:00:00 IDT 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  | 801.0 | NOT_STARTED
2850 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2851 | TT_TASK | Controls Installation | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2854 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 16 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2855 | TT_TASK | HAC Installation | Thu Apr 29 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2856 | TT_TASK | Cable Tray Installation | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2857 | TT_TASK | Power Bus Installation | Mon Jun 14 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2858 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2859 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Sep 01 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2860 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Aug 25 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2861 | TT_TASK | Light Fixtures Installation | Mon Aug 30 07:00:00 IDT 2021 | Tue Sep 07 08:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  | 89.0 | IN_PROGRESS
2863 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2864 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 170.0 | NOT_STARTED
2865 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Sat Oct 09 07:00:00 IDT 2021 | Tue Nov 02 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2867 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2868 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2871 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 23 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2872 | TT_TASK | HAC Installation | Fri May 07 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2873 | TT_TASK | Cable Tray Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2874 | TT_TASK | Power Bus Installation | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Thu Jun 24 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2875 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed Jul 14 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2876 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Sep 01 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 25 00:00:00 IDT 2021 |  |  | IN_PROGRESS
2877 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 22 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2878 | TT_TASK | Light Fixtures Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2880 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2881 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 300.0 | NOT_STARTED
2882 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed Nov 03 07:00:00 IST 2021 | Tue Nov 30 17:00:00 IST 2021 |  |  | 691.0 | NOT_STARTED
2884 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2885 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jul 27 00:00:00 IDT 2021 | Tue Aug 24 13:00:00 IDT 2021 |  | COMPLETED
2889 | TT_TASK | ATS Equipment Yellow Tagging (S2 from MER) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2890 | TT_TASK | Control Power Available | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Fri Apr 30 07:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
2891 | TT_TASK | Power available for Start up | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2892 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2893 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 |  | COMPLETED
2895 | TT_TASK | Admin - NETA test validation Inpections- VECA-EPS-RTS Admin | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Mar 11 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
2896 | TT_TASK | Electrical Equipment Yellow Tagging | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2897 | TT_TASK | Admin/Colo-1 Network Startup | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2898 | TT_TASK | EPMS Checkout / Point to Point | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2902 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2903 | TT_TASK | UPM Yellow tagging - Admin & COLO-1 CELL-1 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2904 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
2905 | TT_TASK | SE- Completed L2 QC Checklist | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
2906 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-1 | Sat Apr 17 07:00:00 IDT 2021 | Tue Apr 20 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2907 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2908 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2909 | TT_TASK | Network Startup | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
2910 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2911 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2912 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2914 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2915 | TT_TASK | Power available for Start up | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2916 | TT_TASK | SE- Completed L2 QC Checklist | Mon Jun 14 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
2917 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Jul 13 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2918 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-3 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2919 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-3 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2920 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Thu Jun 10 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2921 | TT_TASK | Network Startup | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 |  | COMPLETED
2922 | TT_TASK | EPMS Checkout / Point to Point | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jul 06 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2923 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2924 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2926 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2927 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2928 | TT_TASK | SE- Completed L2 QC Checklist | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2929 | TT_TASK | Mechanical Equipment Yellow Tag | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 |  | COMPLETED
2930 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-2 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2931 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-2 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2932 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2933 | TT_TASK | Network Startup | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2934 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2935 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2936 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 20 15:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2938 | TT_TASK | Control Power Available | Tue Jun 22 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue Jun 22 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2939 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2940 | TT_TASK | SE- Completed L2 QC Checklist | Mon Jun 14 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
2941 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Jul 02 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2942 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-4 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2943 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-4 | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
2944 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Jul 07 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2945 | TT_TASK | Network Startup | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2946 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2947 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2948 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2950 | TT_TASK | GEN SCR testing and Burnins | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jul 14 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2951 | TT_TASK | Admin GEN SCR testing and Burnins | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2952 | TT_TASK | ATS- Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 |  | 100.0 | IN_PROGRESS
2953 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Tue Jul 13 11:00:00 IDT 2021 | Wed Jul 28 11:00:00 IDT 2021 | Tue Jul 13 11:00:00 IDT 2021 | Wed Jul 28 11:00:00 IDT 2021 |  | COMPLETED
2954 | TT_TASK | Cooling Automation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2955 | TT_TASK | BAS Prefunctional Testing on Construction Server | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Sat Aug 28 00:00:00 IDT 2021 |  | COMPLETED
2956 | TT_TASK | Additional Go-Back loadbanking (ASCO) | Fri Sep 10 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2957 | TT_TASK | Load Bank & IR Scan | Wed Sep 15 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2958 | TT_TASK | Level 3 Cx - ADMIN AND COLO1 | Fri Sep 17 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2959 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Sat Oct 02 07:00:00 IDT 2021 | Sat Oct 02 07:00:00 IDT 2021 |  |  |  | NOT_STARTED
2961 | TT_TASK | COLO 1 Level 4 & Level 5 IST | Sat Oct 02 08:00:00 IDT 2021 | Fri Oct 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2962 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Sat Oct 30 08:00:00 IDT 2021 | Mon Nov 08 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2963 | TT_TASK | Security Commissioning (level3 DCPS) | Tue Nov 09 08:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2964 | TT_TASK | Punch List - Admin/COLO 1 | Sat Oct 30 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2965 | TT_TASK | MST Ready for Network Install | Sat Oct 02 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2966 | TT_TASK | Final Clean/ ready for lock down | Sat Nov 13 07:00:00 IST 2021 | Mon Nov 22 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2970 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 18 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2971 | TT_TASK | Power available for Start up | Sat Sep 11 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2972 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2973 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  | 20.0 | IN_PROGRESS
2974 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-1 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2975 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-1 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2976 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Aug 04 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2977 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2978 | TT_TASK | EPMS Checkout / Point to Point | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 200.0 | NOT_STARTED
2979 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Thu Sep 16 07:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 |  |  | 20.0 | NOT_STARTED
2980 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Thu Sep 16 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  | 50.0 | NOT_STARTED
2982 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2983 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2984 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2985 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2986 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-3 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2987 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-3 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2988 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2989 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2990 | TT_TASK | EPMS Checkout / Point to Point | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
2991 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2992 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2994 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2995 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2996 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2997 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2998 | TT_TASK | UPM Yellow tagging - COLO-2 CELL-2 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2999 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-2 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
3000 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jul 13 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3001 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3002 | TT_TASK | EPMS Checkout / Point to Point | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3003 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3004 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3006 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3007 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3008 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
3009 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3010 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-4 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
3011 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-4 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
3012 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Aug 18 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3013 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3014 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3015 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3016 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  | 30.0 | NOT_STARTED
3018 | TT_TASK | GEN SCR testing and Burnins | Sat Sep 18 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  | 150.0 | NOT_STARTED
3019 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Mon Sep 27 07:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3020 | TT_TASK | Cooling Automation | Mon Oct 11 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3021 | TT_TASK | BAS Prefunctional Testing on Construction Server | Thu Oct 07 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3022 | TT_TASK | Load Bank & IR Scan | Tue Oct 26 07:00:00 IDT 2021 | Tue Nov 16 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3023 | TT_TASK | Level 3 Cx- COLO-2 | Wed Nov 17 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3024 | TT_TASK | Weather (5 Days) - 0 remaining Check Delay #14 for updates | Sat Dec 04 07:00:00 IST 2021 | Sat Dec 04 07:00:00 IST 2021 |  |  |  | NOT_STARTED
3026 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Mon Dec 27 07:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3027 | TT_TASK | Security Commissioning (level3 DCPS) | Tue Jan 11 07:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3028 | TT_TASK | COLO 2 Level 4 & Level 5 IST | Sat Dec 04 08:00:00 IST 2021 | Fri Dec 24 17:00:00 IST 2021 |  |  | 16.0 | NOT_STARTED
3029 | TT_TASK | Punch List COLO-2 | Mon Dec 27 08:00:00 IST 2021 | Sun Jan 09 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3030 | TT_TASK | MST Ready for Network Install | Sat Dec 04 07:00:00 IST 2021 | Thu Dec 09 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3031 | TT_TASK | Final Clean/ ready for lock down | Mon Jan 10 08:00:00 IST 2022 | Fri Jan 21 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3035 | TT_TASK | Control Power Available | Thu Sep 09 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3036 | TT_TASK | Power available for Start up | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3037 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3038 | TT_TASK | Mechanical Equipment Yellow Tag | Wed Sep 22 07:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3039 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-1 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3040 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-1 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3041 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3042 | TT_TASK | Network Startup | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3043 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3044 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3045 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Tue Oct 05 07:00:00 IDT 2021 | Tue Oct 19 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3047 | TT_TASK | Control Power Available | Tue Sep 21 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3048 | TT_TASK | Power available for Start up | Mon Oct 04 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3049 | TT_TASK | SE- Completed L2 QC Checklist | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3050 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Oct 05 07:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3051 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-3 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 160.0 | NOT_STARTED
3052 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-3 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3053 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3054 | TT_TASK | Network Startup | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3055 | TT_TASK | EPMS Checkout / Point to Point | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3056 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3057 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Oct 18 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3059 | TT_TASK | Control Power Available | Thu Sep 09 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3060 | TT_TASK | Power available for Start up | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3061 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3062 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3063 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-2 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3064 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-2 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3065 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Fri Aug 13 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3066 | TT_TASK | Network Startup | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3067 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3068 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3069 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  |  | 170.0 | NOT_STARTED
3071 | TT_TASK | Control Power Available | Tue Sep 21 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3072 | TT_TASK | Power available for Start up | Mon Oct 04 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3073 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3074 | TT_TASK | Mechanical Equipment Yellow Tag | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3075 | TT_TASK | UPM Yellow tagging COLO-3 CELL-4 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 160.0 | NOT_STARTED
3076 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-4 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
3077 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3078 | TT_TASK | Network Startup | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3079 | TT_TASK | EPMS Checkout / Point to Point | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3080 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3081 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  |  | 70.0 | NOT_STARTED
3083 | TT_TASK | GEN SCR testing and Burnins | Fri Oct 08 07:00:00 IDT 2021 | Tue Oct 26 17:00:00 IDT 2021 |  |  | 320.0 | NOT_STARTED
3084 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Fri Oct 22 07:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3085 | TT_TASK | Cooling Automation | Fri Nov 05 07:00:00 IST 2021 | Fri Nov 19 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3086 | TT_TASK | BAS Prefunctional Testing on Construction Server | Mon Nov 01 07:00:00 IST 2021 | Wed Nov 24 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3087 | TT_TASK | Load Bank & IR Scan | Wed Dec 08 07:00:00 IST 2021 | Mon Jan 03 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3088 | TT_TASK | Level 3 Cx- COLO-3 | Tue Jan 04 07:00:00 IST 2022 | Tue Jan 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3089 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Wed Jan 19 07:00:00 IST 2022 | Wed Jan 19 07:00:00 IST 2022 |  |  |  | NOT_STARTED
3091 | TT_TASK | COLO 3 Level 4 & Level 5 IST | Wed Jan 19 08:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3092 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Wed Feb 09 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3093 | TT_TASK | Security Commissioning (level3 DCPS) | Sat Feb 19 08:00:00 IST 2022 | Wed Feb 23 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3094 | TT_TASK | Punch List COLO-3 | Wed Feb 09 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3095 | TT_TASK | MST Ready for Network Install | Wed Jan 19 08:00:00 IST 2022 | Tue Jan 25 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3096 | TT_TASK | Final Clean/ ready for lock down | Wed Feb 23 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3100 | TT_TASK | Control Power Available | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3101 | TT_TASK | Power available for Start up | Tue Nov 02 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3102 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3103 | TT_TASK | Mechanical Equipment Yellow Tag | Mon Oct 18 07:00:00 IDT 2021 | Thu Oct 28 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3104 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-1 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
3105 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-1 | Fri Sep 17 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
3106 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3107 | TT_TASK | Network Startup | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3108 | TT_TASK | EPMS Checkout / Point to Point | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  | 40.0 | NOT_STARTED
3109 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3110 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3112 | TT_TASK | Control Power Available | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3113 | TT_TASK | Power available for Start up | Mon Nov 15 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3114 | TT_TASK | SE- Completed L2 QC Checklist | Sat Oct 23 07:00:00 IDT 2021 | Wed Nov 03 17:00:00 IST 2021 |  |  | 20.0 | NOT_STARTED
3115 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Oct 29 07:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 |  |  | 70.0 | NOT_STARTED
3116 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-3 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Mon Aug 16 00:00:00 IDT 2021 |  | COMPLETED
3117 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-3 | Tue Sep 28 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  | 200.0 | NOT_STARTED
3118 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3119 | TT_TASK | Network Startup | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3120 | TT_TASK | EPMS Checkout / Point to Point | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3121 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3122 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3124 | TT_TASK | Control Power Available | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3125 | TT_TASK | Power available for Start up | Tue Nov 02 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3126 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3127 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3128 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-2 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3129 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-2 | Fri Sep 17 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
3130 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3131 | TT_TASK | Network Startup | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3132 | TT_TASK | EPMS Checkout / Point to Point | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3133 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3134 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3136 | TT_TASK | Control Power Available | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3137 | TT_TASK | Power available for Start up | Mon Nov 15 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3138 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3139 | TT_TASK | Mechanical Equipment Yellow Tag | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  | 140.0 | NOT_STARTED
3140 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-4 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3141 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-4 | Sat Sep 18 07:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 |  |  | 270.0 | NOT_STARTED
3142 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3143 | TT_TASK | Network Startup | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3144 | TT_TASK | EPMS Checkout / Point to Point | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3145 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3146 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3148 | TT_TASK | GEN SCR testing and Burnins | Fri Nov 19 07:00:00 IST 2021 | Thu Dec 09 17:00:00 IST 2021 |  |  | 310.0 | NOT_STARTED
3149 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Tue Nov 30 07:00:00 IST 2021 | Mon Dec 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3150 | TT_TASK | Cooling Automation | Tue Dec 14 07:00:00 IST 2021 | Thu Dec 30 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3151 | TT_TASK | BAS Prefunctional Testing on Construction Server | Tue Dec 07 07:00:00 IST 2021 | Tue Jan 04 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3152 | TT_TASK | Load Bank & IR Scan | Sat Jan 22 07:00:00 IST 2022 | Sat Feb 12 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3153 | TT_TASK | Level 3 Cx - COLO-4 | Mon Feb 14 07:00:00 IST 2022 | Sat Feb 26 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3154 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Mon Feb 28 07:00:00 IST 2022 | Mon Feb 28 07:00:00 IST 2022 |  |  |  | NOT_STARTED
3156 | TT_TASK | COLO 4 Level 4 & Level 5 IST | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 20 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3157 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Mon Mar 21 08:00:00 IST 2022 | Wed Mar 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3158 | TT_TASK | Security Commissioning (level3 DCPS) | Thu Mar 31 08:00:00 IDT 2022 | Mon Apr 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3159 | TT_TASK | Punch List COLO-4 | Mon Mar 21 08:00:00 IST 2022 | Sat Apr 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3160 | TT_TASK | MST Ready for Network Install | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3161 | TT_TASK | Final Clean/ ready for lock down | Sun Apr 03 08:00:00 IDT 2022 | Wed Apr 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3163 | TT_TASK | CSA Punchlist - COLO-1 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  | COMPLETED
3164 | TT_TASK | CSA Punchlist - COLO-2 | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 220.0 | NOT_STARTED
3165 | TT_TASK | CSA Punchlist - COLO-3 | Mon Nov 01 07:00:00 IST 2021 | Fri Nov 12 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3166 | TT_TASK | CSA Punchlist - COLO-4 | Sat Dec 11 07:00:00 IST 2021 | Thu Dec 23 17:00:00 IST 2021 |  |  | 380.0 | NOT_STARTED
3167 | TT_TASK | MEP Punchlist - COLO-1 | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 110.0 | NOT_STARTED
3168 | TT_TASK | MEP Punchlist - COLO-2 | Wed Nov 17 07:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 |  |  | 20.0 | NOT_STARTED
3169 | TT_TASK | MEP Punchlist - COLO-3 | Tue Jan 04 07:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  |  | 20.0 | NOT_STARTED
3170 | TT_TASK | MEP Punchlist - COLO-4 | Mon Feb 14 07:00:00 IST 2022 | Thu Feb 24 17:00:00 IST 2022 |  |  | 20.0 | NOT_STARTED
3171 | TT_TASK | AE/Owner Punchlist - COLO-1 | Sat Oct 30 07:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  |  | 60.0 | NOT_STARTED
3172 | TT_TASK | AE/Owner Punchlist - COLO-2 | Mon Dec 27 07:00:00 IST 2021 | Mon Jan 03 17:00:00 IST 2022 |  |  | 41.0 | NOT_STARTED
3173 | TT_TASK | AE/Owner Punchlist - COLO-3 | Wed Feb 09 07:00:00 IST 2022 | Mon Feb 14 17:00:00 IST 2022 |  |  | 71.0 | NOT_STARTED
3174 | TT_TASK | AE/Owner Punchlist - COLO-4 | Mon Mar 21 07:00:00 IST 2022 | Fri Mar 25 17:00:00 IDT 2022 |  |  | 70.0 | NOT_STARTED
3182 | TT_TASK | UMS - ROJ COLO-2 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3183 | TT_TASK | UMS - ROJ COLO-3 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3184 | TT_TASK | UMS - ROJ COLO-4 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3185 | TT_TASK | MSFT Delivery -UMS -COLO 4 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3186 | TT_TASK | MSFT Delivery -UMS -COLO 3 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3187 | TT_TASK | MSFT Delivery -UMS -COLO 2 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3190 | TT_TASK | TCO COLO 2 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3191 | TT_TASK | Weather Tight | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3192 | TT_TASK | Duct Bank - UMS01 to UPM COLO-1 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3193 | TT_TASK | Duct Bank - UMS02 to UPM COLO-2 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3194 | TT_TASK | Duct Bank - UMS03 to UPM COLO-3 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3195 | TT_TASK | Duct Bank - UMS04 to UPM COLO-4 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3196 | TT_TASK | PAD- COLO-1 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3197 | TT_TASK | PAD- COLO-2 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3198 | TT_TASK | PAD- COLO-3 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3199 | TT_TASK | PAD- COLO-4 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3200 | TT_TASK | Pull- UMS01- UPM COLO-1 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3201 | TT_TASK | Pull- UMS02- UPM COLO-2 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3202 | TT_TASK | Pull- UMS03- UPM COLO-3 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3203 | TT_TASK | Pull- UMS04- UPM COLO-4 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3204 | TT_TASK | Set- COLO-1 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3205 | TT_TASK | Set- COLO-2 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3206 | TT_TASK | Set- COLO-3 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3207 | TT_TASK | Set- COLO-4 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3208 | TT_TASK | Term Admin - UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3209 | TT_TASK | Term COLO -1 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3210 | TT_TASK | Term COLO -1 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3211 | TT_TASK | Term COLO -2 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3212 | TT_TASK | Term COLO -2 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3213 | TT_TASK | Term COLO -3 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3214 | TT_TASK | Term COLO -3 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3215 | TT_TASK | Term COLO -4 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3216 | TT_TASK | Term COLO -4 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3217 | TT_TASK | Term- UMS01- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3218 | TT_TASK | Term- UMS02- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3219 | TT_TASK | Term- UMS03- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3220 | TT_TASK | Term- UMS04- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3221 | TT_TASK | Yellow Tagging for UMS01 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3222 | TT_TASK | Yellow Tagging for UMS02 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3223 | TT_TASK | Yellow Tagging for UMS03 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3224 | TT_TASK | Yellow Tagging for UMS04 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3225 | TT_TASK | URS Vault design and Approval | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3227 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Thu Oct 22 07:00:00 IDT 2020 | Thu Oct 22 07:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3228 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3229 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jan 23 07:00:00 IST 2021 | Sat Jan 23 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3230 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Thu Oct 22 07:00:00 IDT 2020 | Thu Oct 22 07:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3231 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3232 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jan 23 07:00:00 IST 2021 | Sat Jan 23 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3233 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Nov 04 07:00:00 IST 2020 | Wed Nov 04 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3234 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3235 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Feb 04 07:00:00 IST 2021 | Thu Feb 04 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3236 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Nov 04 07:00:00 IST 2020 | Wed Nov 04 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3237 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3238 | TT_TASK | COLO Lighting installation (DRB#2) | Mon Feb 08 07:00:00 IST 2021 | Mon Feb 08 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3239 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3240 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Dec 02 07:00:00 IST 2020 | Wed Dec 02 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3241 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Mar 11 07:00:00 IST 2021 | Thu Mar 11 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3242 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Tue Dec 29 07:00:00 IST 2020 | Tue Dec 29 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3243 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Dec 02 07:00:00 IST 2020 | Wed Dec 02 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3244 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Mar 11 07:00:00 IST 2021 | Thu Mar 11 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3245 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Dec 18 07:00:00 IST 2020 | Fri Dec 18 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3246 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Dec 15 07:00:00 IST 2020 | Tue Dec 15 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3247 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Mar 26 07:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3248 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Dec 15 07:00:00 IST 2020 | Tue Dec 15 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3249 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Mar 26 07:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3250 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Jan 07 07:00:00 IST 2021 | Thu Jan 07 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3251 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3252 | TT_TASK | COLO Lighting installation (DRB#2) | Tue Apr 27 07:00:00 IDT 2021 | Tue Apr 27 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3253 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Jan 14 07:00:00 IST 2021 | Thu Jan 14 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3254 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3255 | TT_TASK | COLO Lighting installation (DRB#2) | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3256 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Fri Feb 12 07:00:00 IST 2021 | Fri Feb 12 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3257 | TT_TASK | COLO Lighting installation (DRB#2) | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3258 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Jan 29 07:00:00 IST 2021 | Fri Jan 29 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3259 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Fri Feb 12 07:00:00 IST 2021 | Fri Feb 12 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3260 | TT_TASK | COLO Lighting installation (DRB#2) | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3261 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3262 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Mar 09 07:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3263 | TT_TASK | COLO Lighting installation (DRB#2) | Wed Jun 09 07:00:00 IDT 2021 | Wed Jun 09 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3264 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3265 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Mar 09 07:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3266 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Jun 04 07:00:00 IDT 2021 | Fri Jun 04 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3267 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Sat Feb 20 07:00:00 IST 2021 | Sat Feb 20 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3268 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Mon Mar 22 07:00:00 IST 2021 | Mon Mar 22 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3269 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jun 19 07:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3270 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Sat Feb 20 07:00:00 IST 2021 | Sat Feb 20 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3271 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Mon Mar 22 07:00:00 IST 2021 | Mon Mar 22 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3272 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jun 19 07:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3273 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3274 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3275 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3276 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3277 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3278 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3279 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3280 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3281 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3282 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3283 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3284 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3285 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3286 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3287 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3288 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3290 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 05 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3291 | TT_TASK | Mechanical Equipment Piping Connections | Tue Nov 03 07:00:00 IST 2020 | Tue Nov 17 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3292 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3293 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3294 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3295 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3296 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3297 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3298 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3299 | TT_TASK | Fluid Cooler RI prefabrication | Thu Dec 10 07:00:00 IST 2020 | Wed Dec 16 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3300 | TT_TASK | Fluid Cooler RI prefabrication | Wed Dec 16 07:00:00 IST 2020 | Tue Dec 22 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3301 | TT_TASK | Fluid Cooler RI prefabrication | Wed Dec 23 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3302 | TT_TASK | Fluid Cooler RI prefabrication | Thu Jan 07 07:00:00 IST 2021 | Wed Jan 13 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3303 | TT_TASK | Fluid Cooler RI prefabrication | Thu Jan 14 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3304 | TT_TASK | Fluid Cooler RI prefabrication | Fri Jan 22 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3305 | TT_TASK | Fluid Cooler RI prefabrication | Tue Jan 26 07:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3306 | TT_TASK | Submit and approve shop drawing for PEMB penetrations | Mon Oct 19 08:00:00 IDT 2020 | Sun Nov 08 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3308 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3309 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3310 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3311 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3312 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3313 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3314 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3315 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3316 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3317 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3318 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3319 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3321 | TT_TASK | Yellow Tagging for COLO-2 UPM's | Fri Jan 29 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3322 | TT_TASK | Yellow Tagging for COLO-3 UPM's | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 |  | COMPLETED
3323 | TT_TASK | Yellow Tagging for COLO-4 UPM's | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 |  | COMPLETED
3324 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 11 07:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3326 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3327 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3328 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Mar 10 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3329 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 08 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3330 | TT_TASK | Fluid Cooler QAQC and Cx | Thu Mar 18 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3331 | TT_TASK | Fluid Cooler QAQC and Cx | Fri Apr 02 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3332 | TT_TASK | Fluid Cooler QAQC and Cx | Fri Mar 26 07:00:00 IDT 2021 | Sat Mar 27 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3333 | TT_TASK | Fluid Cooler QAQC and Cx | Tue Apr 06 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3334 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 14 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3335 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 21 07:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3336 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 14 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3337 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 28 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3338 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 21 07:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3339 | TT_TASK | Fluid Cooler QAQC and Cx | Thu May 06 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3341 | TT_TASK | COLO-2 CELL3 Rearrange Roxtec blocks per coordination layout | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3342 | TT_TASK | COLO2 CELL3 Interior MER conduit installation utility side | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 06 07:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3343 | TT_TASK | COLO-2 CELL3 Interior MER conduit installation building side | Tue Apr 20 07:00:00 IDT 2021 | Tue Apr 20 07:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3345 | TT_TASK | COLO-2 Cell-4 Rearrange Roxtec blocks per coordination layout | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3346 | TT_TASK | COLO2 CELL4 Interior MER conduit installation utility side | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3347 | TT_TASK | COLO2 CELL4 Interior MER conduit installation building side | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3350 | TT_TASK | COLO-2 Cell-1 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3351 | TT_TASK | COLO-2 Cell-2 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3352 | TT_TASK | COLO-2 Cell-3 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3353 | TT_TASK | COLO-2 Cell-4 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3354 | TT_TASK | COLO2 CELL1 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3355 | TT_TASK | COLO2 CELL2 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3356 | TT_TASK | COLO2 CELL3 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3357 | TT_TASK | COLO2 CELL4 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3360 | TT_TASK | Concrete interior - Create Punch list | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
3361 | TT_TASK | Concrete interior - Complete Punch List | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
3362 | TT_TASK | Garco Steel (Mezz steel, Yard) - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3363 | TT_TASK | Garco Steel (Mezz steel, Yard) - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3364 | TT_TASK | Sure Steel (Building, Mezz, Ceiling) - Create Punch list | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
3365 | TT_TASK | Sure Steel (Building, Mezz, Ceiling) - Complete Punch List | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
3366 | TT_TASK | Advantage - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3367 | TT_TASK | Advantage - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3368 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3369 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3370 | TT_TASK | VECA - Create Punch list | Tue Sep 07 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3371 | TT_TASK | VECA - Complete Punch List | Thu Sep 09 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3372 | TT_TASK | LINX - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3373 | TT_TASK | LINX - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3374 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3375 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3376 | TT_TASK | TCM- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3377 | TT_TASK | TCM - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3378 | TT_TASK | Cascade- Create Punch list | Mon Apr 26 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
3379 | TT_TASK | Cascade - Complete Punch List | Wed Apr 28 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3380 | TT_TASK | Submit GC Punch List to A/E | Tue Sep 21 07:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3381 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3382 | TT_TASK | Complete A/E Punchlist | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3383 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3384 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3385 | TT_TASK | VECA - Create Punch list | Fri Oct 29 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3386 | TT_TASK | VECA - Complete Punch List | Mon Nov 01 07:00:00 IST 2021 | Mon Nov 08 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3387 | TT_TASK | LINX - Create Punch list | Mon Aug 16 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3388 | TT_TASK | LINX - Complete Punch List | Wed Aug 18 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3389 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3390 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3391 | TT_TASK | TCM- Create Punch list | Wed Sep 22 07:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3392 | TT_TASK | TCM - Complete Punch List | Fri Sep 24 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3393 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3394 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3395 | TT_TASK | Submit GC Punch List to A/E | Tue Nov 09 07:00:00 IST 2021 | Tue Nov 09 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3396 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Nov 10 07:00:00 IST 2021 | Tue Nov 16 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3397 | TT_TASK | Complete A/E Punchlist | Wed Nov 17 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3398 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3399 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3400 | TT_TASK | VECA - Create Punch list | Tue Dec 14 07:00:00 IST 2021 | Wed Dec 15 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3401 | TT_TASK | VECA - Complete Punch List | Thu Dec 16 07:00:00 IST 2021 | Thu Dec 23 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3402 | TT_TASK | LINX - Create Punch list | Wed Oct 13 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3403 | TT_TASK | LINX - Complete Punch List | Fri Oct 15 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3404 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3405 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3406 | TT_TASK | TCM- Create Punch list | Wed Sep 22 07:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3407 | TT_TASK | TCM - Complete Punch List | Fri Sep 24 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3408 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3409 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3410 | TT_TASK | Submit GC Punch List to A/E | Mon Dec 27 07:00:00 IST 2021 | Mon Dec 27 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3411 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Tue Dec 28 07:00:00 IST 2021 | Wed Jan 05 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3412 | TT_TASK | Complete A/E Punchlist | Thu Jan 06 07:00:00 IST 2022 | Thu Jan 20 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3413 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3414 | TT_TASK | PCI - Complete Punch List | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3415 | TT_TASK | VECA - Create Punch list | Fri Jan 28 07:00:00 IST 2022 | Mon Jan 31 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3416 | TT_TASK | VECA - Complete Punch List | Tue Feb 01 07:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3417 | TT_TASK | LINX - Create Punch list | Fri Nov 19 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3418 | TT_TASK | LINX - Complete Punch List | Mon Nov 22 07:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3419 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3420 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3421 | TT_TASK | TCM- Create Punch list | Thu Nov 04 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3422 | TT_TASK | TCM - Complete Punch List | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3423 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3424 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3425 | TT_TASK | Submit GC Punch List to A/E | Tue Feb 08 07:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3426 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Feb 09 07:00:00 IST 2022 | Tue Feb 15 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3427 | TT_TASK | Complete A/E Punchlist | Wed Feb 16 07:00:00 IST 2022 | Tue Mar 01 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3428 | TT_TASK | COLO-2 Cell2 Rearrange Roxtec blocks per coordination layout (delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
3429 | TT_TASK | COLO2 CELL2 Interior MER conduit installation utility side(delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
3430 | TT_TASK | COLO-2 CELL2 Interior MER conduit installation building (delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
3432 | TT_TASK | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change(delete) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
3433 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3434 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3435 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3436 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
303 | TT_TASK | MSFT Issue DRB #1 for Review | Tue May 26 07:00:00 IDT 2020 | Mon Jun 01 17:00:00 IDT 2020 | Tue May 19 00:00:00 IDT 2020 | Mon Jul 20 00:00:00 IDT 2020 |  | COMPLETED
306 | TT_TASK | Lead Time for PEMB | Wed Feb 19 08:00:00 IST 2020 | Thu Jun 18 17:00:00 IDT 2020 | Mon Feb 24 00:00:00 IST 2020 | Thu Jun 18 00:00:00 IDT 2020 |  | COMPLETED
307 | TT_TASK | Lead Time for Rebar (Footings & Walls) | Mon Apr 27 08:00:00 IDT 2020 | Sun May 31 17:00:00 IDT 2020 | Mon Mar 30 00:00:00 IDT 2020 | Tue Apr 21 00:00:00 IDT 2020 |  | COMPLETED
308 | TT_TASK | Lead Time for COLO 1 Structural Interior Steel | Mon Aug 10 08:00:00 IDT 2020 | Sat Oct 31 17:00:00 IST 2020 | Tue Jun 30 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
309 | TT_TASK | Lead Time for Wall & Roof Metal Panels | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Mon Jun 29 00:00:00 IDT 2020 |  | COMPLETED
310 | TT_TASK | Lead Time for Admin/COLO 1 Yard Steel | Mon Aug 31 08:00:00 IDT 2020 | Sun Oct 18 17:00:00 IDT 2020 | Tue Jun 30 00:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 |  | COMPLETED
311 | TT_TASK | Lead Time for HM Ext. frames | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
312 | TT_TASK | Lead time for Drywall/Framing | Mon Aug 10 08:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Mon Aug 10 08:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
592 | TT_TASK | MV Ductbanks Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | Mon Sep 14 08:00:00 IDT 2020 | Sun Sep 20 17:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 | Sun Sep 06 00:00:00 IDT 2020 |  | COMPLETED
593 | TT_TASK | MV Wire Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | Wed Aug 12 08:00:00 IDT 2020 | Tue Nov 03 17:00:00 IST 2020 | Tue Aug 04 00:00:00 IDT 2020 | Mon Oct 26 00:00:00 IST 2020 |  | COMPLETED
594 | TT_TASK | UMS Vault Procurement DRB#1 | Mon Sep 28 08:00:00 IDT 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
595 | TT_TASK | DRB#1 BIM Modeling & Coordination DRB#1 JAZ to UMS/URS & UPM to UMS | Mon Aug 10 08:00:00 IDT 2020 | Sun Aug 23 17:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
596 | TT_TASK | Site- Neher Mcgrath Study DRB#1 JAZ to UMS/URS & UPM to UMS | Tue Aug 11 08:00:00 IDT 2020 | Mon Aug 24 17:00:00 IDT 2020 | Tue Aug 04 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
597 | TT_TASK | JAZ Riser Support DRB#1 Procurement/ Jaz Foundations/Construction | Mon Aug 10 08:00:00 IDT 2020 | Sun Oct 18 17:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
598 | TT_TASK | UPM to UMS Vaults Procurement DRB#1 | Tue Sep 08 08:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
600 | TT_TASK | MV Ductbanks Procurement | Wed Aug 12 08:00:00 IDT 2020 | Thu Aug 20 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
601 | TT_TASK | Telecom DuctBank / Vaults Procurement | Thu May 14 08:00:00 IDT 2020 | Mon May 18 17:00:00 IDT 2020 | Wed May 06 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
602 | TT_TASK | MV Wire Procurement | Wed Aug 12 08:00:00 IDT 2020 | Tue Nov 03 17:00:00 IST 2020 | Tue Jul 21 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
603 | TT_TASK | Off-Site BIM Modeling & Coordination | Mon Apr 27 08:00:00 IDT 2020 | Sun May 24 17:00:00 IDT 2020 | Tue Apr 14 00:00:00 IDT 2020 | Tue May 05 00:00:00 IDT 2020 |  | COMPLETED
604 | TT_TASK | Neher Mcgrath Study | Thu Jul 02 08:00:00 IDT 2020 | Thu Aug 06 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Fri Jul 24 00:00:00 IDT 2020 |  | COMPLETED
605 | TT_TASK | URS Vault Procurement | Mon Sep 28 08:00:00 IDT 2020 | Wed Nov 11 17:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
607 | TT_TASK | Site Temp Power Procurement & Infrastructure | Mon Jun 29 08:00:00 IDT 2020 | Mon Aug 31 08:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
609 | TT_TASK | Underground Grounding Procurement | Mon Apr 27 08:00:00 IDT 2020 | Sun May 17 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Tue Apr 28 00:00:00 IDT 2020 |  | COMPLETED
610 | TT_TASK | BIM Modeling (Under ground) | Tue May 05 08:00:00 IDT 2020 | Mon Jun 08 17:00:00 IDT 2020 | Tue May 05 08:00:00 IDT 2020 | Mon Jun 08 00:00:00 IDT 2020 |  | COMPLETED
611 | TT_TASK | Electrical Long Lead Equipment Procurement (Cablebus, Panel Boards) | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Mon Apr 27 08:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
612 | TT_TASK | BIM Modeling (Above ground) | Sun Aug 02 08:00:00 IDT 2020 | Wed Sep 30 17:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
615 | TT_TASK | Design / Lead Time for Electrical/Telecom (OFCI Telecom BOM Materials) | Mon Aug 10 08:00:00 IDT 2020 | Sat Nov 07 17:00:00 IST 2020 | Wed Jul 01 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
616 | TT_TASK | Design / Lead Time for Busway (OFCI Starline BOM Materials) | Thu Nov 26 08:00:00 IST 2020 | Thu Jan 14 17:00:00 IST 2021 | Mon Sep 21 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
619 | TT_TASK | Water treatment Skids Procurement ( sourcing materials and Materail approval only) | Mon Apr 27 08:00:00 IDT 2020 | Fri Nov 06 12:00:00 IST 2020 | Tue Apr 07 00:00:00 IDT 2020 | Mon Jul 06 00:00:00 IDT 2020 |  | COMPLETED
620 | TT_TASK | Design / Lead Time for M&P overhead | Mon Jun 29 08:00:00 IDT 2020 | Tue Jul 28 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
621 | TT_TASK | Design / Lead Time for Fire Protection | Mon Aug 31 08:00:00 IDT 2020 | Tue Sep 29 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
622 | TT_TASK | Design / Lead Time for Fire Alarm | Mon Jun 29 08:00:00 IDT 2020 | Thu Aug 27 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
628 | TT_TASK | URS/UMS Concrete Anchor and Vault Design | Mon Aug 10 07:00:00 IDT 2020 | Wed Aug 26 17:00:00 IDT 2020 | Wed Aug 05 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
629 | TT_TASK | URS/UMS Vault Submiital Review by EOR | Mon Sep 14 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Fri Sep 25 00:00:00 IDT 2020 |  | COMPLETED
632 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-2 PSR(10/13) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sat Dec 12 17:00:00 IST 2020 | Tue Oct 13 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
633 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-3 PSR(9/28) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Mon Dec 28 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
634 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-4 PSR (10/28) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Fri Nov 27 16:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
635 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-1 PSR (9/19) to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Tue Dec 15 17:00:00 IST 2020 | Sat Sep 19 00:00:00 IDT 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
637 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-1 11/25 to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Fri Oct 09 17:00:00 IDT 2020 | Wed Nov 25 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
638 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-2 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sun Nov 15 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
639 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-4 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Fri Nov 06 16:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
640 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-3 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sun Nov 15 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
642 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-1 PSR 11/23 to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Wed Oct 14 17:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
643 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-2 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
644 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-4 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Wed Nov 11 16:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Sun Jan 03 00:00:00 IST 2021 |  | COMPLETED
645 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-3 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Sun Jan 03 00:00:00 IST 2021 |  | COMPLETED
647 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-1 12/7 to MSFT delivery) | Sat Jan 09 08:00:00 IST 2021 | Sat Jan 09 08:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
648 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-2 12/7 to MSFT delivery) | Tue Jan 05 08:00:00 IST 2021 | Tue Jan 05 08:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
649 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-4 12/18 to MSFT delivery) | Sat Jan 09 08:00:00 IST 2021 | Sat Jan 09 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
650 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-3 12/18 to MSFT delivery) | Thu Jan 14 08:00:00 IST 2021 | Thu Jan 14 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
653 | TT_TASK | Review Fluid Cooler wiring and devices buyout with Stetner | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Wed Sep 23 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
654 | TT_TASK | Change order release for fluid cooler wiring devices | Mon Oct 19 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 | Mon Oct 26 00:00:00 IST 2020 |  | COMPLETED
657 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
658 | TT_TASK | Fluid Cooler RI in place | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
659 | TT_TASK | Fluid Cooler Wire install and Term | Fri Mar 05 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
661 | TT_TASK | Fluid Cooler Panel installation | Tue Mar 23 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
662 | TT_TASK | Fluid Cooler RI in place | Thu Mar 18 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
663 | TT_TASK | Fluid Cooler Wire install and Term | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 |  | COMPLETED
665 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 15 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
666 | TT_TASK | Fluid Cooler RI in place | Fri Feb 19 07:00:00 IST 2021 | Thu Feb 25 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
667 | TT_TASK | Fluid Cooler Wire install and Term | Thu Mar 18 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
669 | TT_TASK | Fluid Cooler Panel installation | Thu Mar 18 07:00:00 IST 2021 | Mon Mar 22 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
670 | TT_TASK | Fluid Cooler RI in place | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
671 | TT_TASK | Fluid Cooler Wire install and Term | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
674 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 29 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
675 | TT_TASK | Fluid Cooler RI in place | Thu Mar 25 07:00:00 IST 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
676 | TT_TASK | Fluid Cooler Wire install and Term | Thu Apr 01 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
678 | TT_TASK | Fluid Cooler Panel installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
679 | TT_TASK | Fluid Cooler RI in place | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
680 | TT_TASK | Fluid Cooler Wire install and Term | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
682 | TT_TASK | Fluid Cooler Panel installation | Thu Apr 01 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Sat Mar 27 00:00:00 IDT 2021 |  | COMPLETED
683 | TT_TASK | Fluid Cooler RI in place | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
684 | TT_TASK | Fluid Cooler Wire install and Term | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
687 | TT_TASK | Fluid Cooler Panel installation | Tue May 04 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
688 | TT_TASK | Fluid Cooler RI in place | Fri May 07 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
689 | TT_TASK | Fluid Cooler Wire install and Term | Fri May 14 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
691 | TT_TASK | Fluid Cooler Panel installation | Mon May 17 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
692 | TT_TASK | Fluid Cooler RI in place | Thu May 20 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
693 | TT_TASK | Fluid Cooler Wire install and Term | Fri May 28 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
695 | TT_TASK | Fluid Cooler Panel installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
696 | TT_TASK | Fluid Cooler RI in place | Fri Jun 04 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
697 | TT_TASK | Fluid Cooler Wire install and Term | Fri Jun 11 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
700 | TT_TASK | Fluid Cooler Panel installation | Tue Jun 08 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
701 | TT_TASK | Fluid Cooler RI in place | Fri Jun 11 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
702 | TT_TASK | Fluid Cooler Wire install and Term | Sat Jun 19 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
704 | TT_TASK | Fluid Cooler Panel installation | Fri Jun 11 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
705 | TT_TASK | Fluid Cooler RI in place | Sat Jun 19 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
706 | TT_TASK | Fluid Cooler Wire install and Term | Sat Jun 26 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
708 | TT_TASK | Fluid Cooler Panel installation | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
709 | TT_TASK | Fluid Cooler RI in place | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
710 | TT_TASK | Fluid Cooler Wire install and Term | Tue Jul 13 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
712 | TT_TASK | Fluid Cooler Panel installation | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
713 | TT_TASK | Fluid Cooler RI in place | Tue Jul 13 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
714 | TT_TASK | Fluid Cooler Wire install and Term | Tue Jul 20 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
718 | TT_TASK | ADMIN Overhead Rough-in (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
719 | TT_TASK | ADMIN Electrical Room Build out (DRB#2) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
720 | TT_TASK | ADMIN Lighting installation (DRB#2) | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
742 | TT_TASK | Water Treatmant Skid Fabrication | Mon Sep 14 08:00:00 IDT 2020 | Mon Dec 07 17:00:00 IST 2020 | Tue Aug 25 00:00:00 IDT 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
743 | TT_TASK | L&I approval process | Mon Sep 14 08:00:00 IDT 2020 | Tue Oct 13 17:00:00 IDT 2020 | Tue Aug 25 00:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 |  | COMPLETED
745 | TT_TASK | Water treatment delivery COLO-1 | Mon Dec 21 08:00:00 IST 2020 | Sun Dec 27 17:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
750 | TT_TASK | Submit and approve Shop drawings for UPM junstion box | Mon Oct 19 08:00:00 IDT 2020 | Sun Nov 08 17:00:00 IST 2020 | Fri Oct 09 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
751 | TT_TASK | Lead time for junction box | Mon Nov 02 08:00:00 IST 2020 | Sun Dec 13 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
752 | TT_TASK | Fabrication and Delivery of PEMB pentrations support steel | Mon Nov 09 08:00:00 IST 2020 | Fri Nov 13 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
756 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
757 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Tue Dec 15 00:00:00 IST 2020 |  | COMPLETED
758 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
760 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
761 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
762 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Feb 13 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
763 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
764 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Mar 05 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
765 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
768 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
769 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
770 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Feb 08 08:00:00 IST 2021 | Thu Feb 11 08:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
772 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
773 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
774 | TT_TASK | Install additional Cable bus (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
775 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
776 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Mar 02 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
777 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
780 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
781 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Tue Dec 15 00:00:00 IST 2020 |  | COMPLETED
782 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
784 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
785 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
786 | TT_TASK | Install additional Cable bus (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
787 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
788 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
789 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
792 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Dec 04 07:00:00 IST 2020 | Wed Dec 09 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
793 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
794 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
796 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
797 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
798 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 03 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
799 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
800 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Thu Mar 04 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
801 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
803 | TT_TASK | COLO-1 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon Mar 22 07:00:00 IST 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
804 | TT_TASK | COLO-1 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon Apr 05 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
805 | TT_TASK | COLO-1 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
806 | TT_TASK | COLO-1 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
810 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Sat Jan 02 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
811 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
812 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
814 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
815 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
816 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
817 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
818 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
819 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
822 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
823 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Thu Feb 11 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
824 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Mar 26 07:00:00 IDT 2021 | Mon Mar 29 17:00:00 IDT 2021 | Sat Feb 27 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
826 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
827 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
828 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
829 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
830 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
831 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
834 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
835 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
836 | TT_TASK | Install added DRB#3 Tray and conduit | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
838 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Sat Mar 27 00:00:00 IDT 2021 |  | COMPLETED
839 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 |  | COMPLETED
840 | TT_TASK | Install additional Cable bus (DRB#3) | Mon May 03 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
841 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
842 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue May 04 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
843 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
846 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
847 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Thu Feb 11 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
848 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 02 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
850 | TT_TASK | Install MER Supply duct | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
851 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri May 07 07:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
852 | TT_TASK | Install additional Cable bus (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
853 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue May 04 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
854 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
855 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 |  | COMPLETED
857 | TT_TASK | COLO-2 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Fri Apr 30 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
858 | TT_TASK | COLO-2 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
859 | TT_TASK | COLO-2 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 03 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
860 | TT_TASK | COLO-2 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
864 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
865 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
866 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
868 | TT_TASK | Install MER Supply duct | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
869 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
870 | TT_TASK | Install Roxtec block sealing and Install added tray cable (DRB#3) | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
871 | TT_TASK | Install additional Cable bus (DRB#3) | Tue May 18 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
872 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
873 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
876 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
877 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
878 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
880 | TT_TASK | Install MER Supply duct | Mon May 24 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
881 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
882 | TT_TASK | Install additional Cable bus (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
883 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 |  | COMPLETED
884 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Sat Aug 14 07:00:00 IDT 2021 | Sat Aug 14 17:00:00 IDT 2021 |  | COMPLETED
885 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Fri Sep 03 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Thu Aug 26 00:00:00 IDT 2021 |  | COMPLETED
888 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
889 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 |  | COMPLETED
890 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
892 | TT_TASK | Install MER Supply duct | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
893 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 |  | COMPLETED
894 | TT_TASK | Install additional Cable bus (DRB#3) | Sat May 29 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
895 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
896 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 |  | COMPLETED
897 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Mon Aug 09 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
900 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
901 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
902 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
904 | TT_TASK | Install MER Supply duct | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
905 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
906 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jun 05 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
907 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
908 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
909 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
911 | TT_TASK | COLO-3 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
912 | TT_TASK | COLO-3 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 |  | COMPLETED
913 | TT_TASK | COLO-3 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
914 | TT_TASK | COLO-3 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
918 | TT_TASK | Sure steel - PEMB MER penetration framing | Thu Feb 11 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
919 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
920 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
922 | TT_TASK | Install MER Supply duct | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
923 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Thu Jul 08 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
924 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
925 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
926 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
927 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
930 | TT_TASK | Sure steel - PEMB MER penetration framing | Tue Feb 16 07:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
931 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
932 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
934 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
935 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
936 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
937 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Fri Sep 03 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 |  |  | 400.0 | NOT_STARTED
938 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
939 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Sat Oct 02 07:00:00 IDT 2021 | Fri Oct 08 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
942 | TT_TASK | Sure steel - PEMB MER penetration framing | Thu Feb 11 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
943 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
944 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
946 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
947 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Thu Jul 08 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 |  | COMPLETED
948 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Jul 28 00:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 |  | COMPLETED
949 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
950 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
951 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
954 | TT_TASK | Sure steel - PEMB MER penetration framing | Tue Feb 16 07:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
955 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
956 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 00:00:00 IDT 2021 |  | COMPLETED
958 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
959 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
960 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
961 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
962 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
963 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
965 | TT_TASK | COLO-4 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Thu Sep 09 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
966 | TT_TASK | COLO-4 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Wed Aug 18 00:00:00 IDT 2021 |  |  | IN_PROGRESS
967 | TT_TASK | COLO-4 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
968 | TT_TASK | COLO-4 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
970 | TT_TASK | Site Shut Down - 9/9/2020 | Mon Sep 14 07:00:00 IDT 2020 | Mon Sep 14 17:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 |  | COMPLETED
971 | TT_TASK | Site Shut Down - 9/10/2020 | Tue Sep 15 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Thu Sep 10 00:00:00 IDT 2020 | Thu Sep 10 00:00:00 IDT 2020 |  | COMPLETED
972 | TT_TASK | Site Shut Down - 9/11/2020 | Wed Sep 16 07:00:00 IDT 2020 | Wed Sep 16 17:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
973 | TT_TASK | Site Shut Down - 9/12/2020 | Thu Sep 17 07:00:00 IDT 2020 | Thu Sep 17 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
974 | TT_TASK | Site Shut Down - 9/14/2020 | Mon Sep 28 07:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 |  | COMPLETED
975 | TT_TASK | Site Shut Down - 9/15/2020 | Tue Sep 29 07:00:00 IDT 2020 | Tue Sep 29 17:00:00 IDT 2020 | Tue Sep 15 00:00:00 IDT 2020 | Tue Sep 15 00:00:00 IDT 2020 |  | COMPLETED
976 | TT_TASK | Site Shut Down - 9/16/2020 | Wed Sep 30 07:00:00 IDT 2020 | Wed Sep 30 17:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 |  | COMPLETED
979 | TT_TASK | Complete Remaining IWW piping to tie-in point | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 29 17:00:00 IST 2020 | Mon Sep 21 00:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
980 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
982 | TT_TASK | Complete Remaining Sanitary piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
983 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
985 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
986 | TT_TASK | Complete Remaining Fire Main piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
988 | TT_TASK | Complete Remaining ITW piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
989 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
991 | TT_TASK | Complete Remaining Telecom Duct Back (excluding Tie-in) | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
992 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
995 | TT_TASK | Delay in COLO-1- Cell-1 MER Delivery (Duration = COLO1 Cell-1 PSR(11/6/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sat Jan 30 17:00:00 IST 2021 | Fri Nov 06 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
996 | TT_TASK | Delay in COLO-1- Cell-2 MER Delivery (Duration = COLO1 Cell-2 PSR(11/13/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Fri Jan 29 17:00:00 IST 2021 | Fri Nov 13 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
997 | TT_TASK | Delay in COLO-1- Cell-3 MER Delivery (Duration = COLO1 Cell-3 PSR(11/20/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Feb 04 17:00:00 IST 2021 | Fri Nov 20 00:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 |  | COMPLETED
998 | TT_TASK | Delay in COLO-1- Cell-4 MER Delivery (Duration = COLO1 Cell-4 PSR(11/30/20) to MSFT delivery) | Mon Feb 01 08:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1000 | TT_TASK | Delay in COLO-2- Cell-1 MER Delivery (Duration = Colo1 Cell-1 PSR(12/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Feb 11 10:00:00 IST 2021 | Tue Dec 15 00:00:00 IST 2020 | Wed Feb 03 00:00:00 IST 2021 |  | COMPLETED
1001 | TT_TASK | Delay in COLO-2- Cell-2 MER Delivery (Duration = COLO 2 Cell-2 PSR(12/22/20) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1002 | TT_TASK | Delay in COLO-2- Cell-3 MER Delivery (Duration = COLO 2- Cell-3 PSR(12/28/20) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1003 | TT_TASK | Delay in COLO-2- Cell-4 MER Delivery (Duration = COLO 2- Cell-4 PSR(1/5/21) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Jan 05 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1005 | TT_TASK | Delay in COLO-3- Cell-1 MER Delivery (Duration = COLO-3 Cell-1 PSR(1/29/21) to MSFT delivery) | Sun Jan 31 08:00:00 IST 2021 | Sat Apr 03 17:00:00 IDT 2021 | Fri Jan 29 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1006 | TT_TASK | Delay in COLO-3- Cell-2 MER Delivery (Duration = COLO-3 Cell-2 PSR(2/5/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 05 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1007 | TT_TASK | Delay in COLO-3 Cell-3 MER Delivery (Duration = COLO-3 Cell-3 PSR(2/12/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Feb 12 00:00:00 IST 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1008 | TT_TASK | Delay in COLO-3 Cell-4 MER Delivery (Duration = COLO-3 Cell-4 PSR(2/19/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Thu Apr 22 00:00:00 IDT 2021 |  | COMPLETED
1010 | TT_TASK | Delay in COLO-4- Cell-1 MER Delivery (Duration= COLO-4 Cell-1 PSR(3/12/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Mar 12 00:00:00 IST 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
1011 | TT_TASK | Delay in COLO-4- Cell-2 MER Delivery (Duration = COLO-4 Cell-2 PSR(3/19/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1012 | TT_TASK | Delay in COLO-4- Cell-3 MER Delivery (Duration = COLO-4 Cell-3 PSR(3/26/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1013 | TT_TASK | Delay in COLO-4- Cell-4 MER Delivery (Duration = COLO-4 Cell-4 PSR(4/2/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 | Sun May 09 00:00:00 IDT 2021 |  | COMPLETED
1015 | TT_TASK | Wire Mesh Procurement | Mon Nov 16 08:00:00 IST 2020 | Wed Dec 23 12:00:00 IST 2020 | Thu Sep 24 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
1016 | TT_TASK | Wire Mesh Submittal Approval | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Wed Sep 16 00:00:00 IDT 2020 | Wed Sep 23 00:00:00 IDT 2020 |  | COMPLETED
1017 | TT_TASK | Wire Mesh Procurement Delay | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Sat Oct 24 00:00:00 IDT 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1019 | TT_TASK | Complete Remaining Telecom Duct Back tie-in Install to MWH02 | Mon Dec 21 07:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1020 | TT_TASK | Clayco waiting on MSOW Approval | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Tue Dec 01 00:00:00 IST 2020 |  | COMPLETED
1021 | TT_TASK | Clayco MSOW Submited for approval | Mon Nov 16 07:00:00 IST 2020 | Tue Nov 17 17:00:00 IST 2020 | Fri Oct 16 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
1022 | TT_TASK | MSFT Stand down/ Additional Hydro excavation | Mon Dec 21 07:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
1024 | TT_TASK | Delay in UMS delivery (Duration = (9/19) to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Thu Nov 19 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
1027 | TT_TASK | Delay In COLO-1 Cell-1 Generator (Duration= COLO-1 Cell-1 PSR(9/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Tue Jan 19 17:00:00 IST 2021 | Tue Sep 15 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1028 | TT_TASK | Delay In COLO-1 Cell-2 Generator (Duration= COLO-1 Cell-2 PSR(9/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sat Feb 06 17:00:00 IST 2021 | Tue Sep 15 00:00:00 IDT 2020 | Mon Nov 02 00:00:00 IST 2020 |  | COMPLETED
1029 | TT_TASK | Delay In COLO-1 Cell-4 Generator (Duration= COLO-1 Cell-4 PSR(9/29/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Sep 29 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1030 | TT_TASK | Delay In COLO-1 Cell-3 Generator (Duration= COLO-1 Cell-3 PSR(9/29/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Wed Feb 03 17:00:00 IST 2021 | Tue Sep 29 00:00:00 IDT 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1032 | TT_TASK | Delay In COLO-2 Cell-1 Generator (Duration= COLO-2 Cell-1 PSR(10/12/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sun Mar 07 17:00:00 IST 2021 | Mon Oct 12 00:00:00 IDT 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1033 | TT_TASK | Delay In COLO-2 Cell-2 Generator (Duration= COLO-2 Cell-2 PSR(11/6/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sun Feb 21 17:00:00 IST 2021 | Fri Nov 06 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
1034 | TT_TASK | Delay In COLO-2 Cell-4 Generator (Duration= COLO-2 Cell-4 PSR(11/21/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Fri Feb 19 17:00:00 IST 2021 | Sat Nov 21 00:00:00 IST 2020 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
1035 | TT_TASK | Delay In COLO-2 Cell-3 Generator (Duration= COLO-2 Cell-3 PSR(10/22/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Mar 18 17:00:00 IST 2021 | Thu Oct 22 00:00:00 IDT 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1037 | TT_TASK | 6.1.39.1- COLO-3 CEll-1 GEN Belly tank Failed pressure test | Mon Mar 15 07:00:00 IST 2021 | Fri Apr 09 17:00:00 IDT 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
1038 | TT_TASK | 6.1.39.2- COLO-3 Cell-1 Replace Belly Tank and Set GEN | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1039 | TT_TASK | Delay In COLO-3 Cell-1 Generator (Duration= COLO-3 Cell-1 PSR(10/12/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Sat May 08 17:00:00 IDT 2021 | Mon Nov 09 00:00:00 IST 2020 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1040 | TT_TASK | Delay In COLO-3 Cell-2 Generator (Duration= COLO-3 Cell-2 PSR(11/6/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Tue Mar 30 17:00:00 IDT 2021 | Sat Nov 21 00:00:00 IST 2020 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
1041 | TT_TASK | Delay In COLO-3 Cell-4 Generator (Duration= COLO-3 Cell-4 PSR(11/21/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Mar 18 17:00:00 IST 2021 | Wed Dec 09 00:00:00 IST 2020 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
1042 | TT_TASK | Delay In COLO-3 Cell-3 Generator (Duration= COLO-3 Cell-3 PSR(10/22/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Apr 29 17:00:00 IDT 2021 | Thu Nov 05 00:00:00 IST 2020 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1044 | TT_TASK | Delay In COLO-4 Cell-1 Generator (Duration= COLO-4 Cell-1 PSR(10/12/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Sat Jun 05 17:00:00 IDT 2021 | Mon Nov 09 00:00:00 IST 2020 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
1045 | TT_TASK | Delay In COLO-4 Cell-2 Generator (Duration= COLO-4 Cell-2 PSR(11/6/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Apr 01 17:00:00 IDT 2021 | Wed Dec 09 00:00:00 IST 2020 | Thu Mar 11 00:00:00 IST 2021 |  | COMPLETED
1046 | TT_TASK | Delay In COLO-4 Cell-4 Generator (Duration= COLO-4 Cell-4 PSR(11/21/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Wed Apr 14 17:00:00 IDT 2021 | Mon Nov 30 00:00:00 IST 2020 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
1047 | TT_TASK | Delay In COLO-4 Cell-3 Generator (Duration= COLO-4 Cell-3 PSR(10/22/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Tue May 11 17:00:00 IDT 2021 | Fri Nov 20 00:00:00 IST 2020 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1050 | TT_TASK | COLO1 CELL1 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1051 | TT_TASK | COLO1 CELL3 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
1052 | TT_TASK | COLO1 CELL2 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1053 | TT_TASK | COLO1 CELL4 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
1058 | TT_TASK | COLO-1 Cell-1 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1059 | TT_TASK | COLO1 CELL1 Interior MER conduit installation utility side | Fri Mar 05 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1060 | TT_TASK | COLO-1 Cell-1 Interior MER conduit installation building side Complete March1st (MER discovery Corrections & Signoff) | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1063 | TT_TASK | COLO-1 CELL3 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1064 | TT_TASK | COLO1 CELL3 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1065 | TT_TASK | COLO-1 CELL3 Interior MER conduit installation building side | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
1068 | TT_TASK | COLO-1 CELL2 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1069 | TT_TASK | COLO1 CELL2 Interior MER conduit installation utility side | Sat Mar 06 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1070 | TT_TASK | COLO-1 CELL2 Interior MER conduit installation building side | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1073 | TT_TASK | COLO-1 CELL4 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1074 | TT_TASK | COLO1 CELL4 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1075 | TT_TASK | COLO-1 CELL4 Interior MER conduit installation building side | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
1079 | TT_TASK | COLO-2 Cell-1 Rearrange Roxtec blocks per coordination layout | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1080 | TT_TASK | COLO2 CELL1 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1081 | TT_TASK | COLO-2 Cell-1 Interior MER conduit installation building side | Mon Apr 05 07:00:00 IDT 2021 | Mon Apr 19 17:00:00 IDT 2021 | Fri Mar 05 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1089 | TT_TASK | COLO-1 Cell-1 MER Flex Conduit fixes | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1090 | TT_TASK | COLO-1 Cell-3 MER Flex Conduit fixes | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1091 | TT_TASK | COLO-1 Cell-2 MER Flex Conduit fixes | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1092 | TT_TASK | COLO-1 Cell-4 MER Flex Conduit fixes | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1095 | TT_TASK | Safety Stop work due to failed Starline Hangers | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 01 07:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
1096 | TT_TASK | Lead time for replacement hangers from Starline | Mon Feb 01 08:00:00 IST 2021 | Sun Feb 07 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
1097 | TT_TASK | COLO-1 Cell-1 Remove/ Replace busway & hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1098 | TT_TASK | COLO-1 Cell-3 Remove/ Replace busway & hangers | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1099 | TT_TASK | COLO-1 Cell-2 Remove/ Replace busway & hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1100 | TT_TASK | COLO-1 Cell-4 Remove/ Replace busway & hangers | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1101 | TT_TASK | Determined Startline hanger Design Issue & Approve replacement hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
1102 | TT_TASK | COLO-2 Cell-1 Remove/ Replace busway & hangers | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1103 | TT_TASK | COLO-2 Cell-2 Remove/ Replace busway & hangers | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1105 | TT_TASK | Lead time for missing Admin Gen Bussing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 |  | COMPLETED
1106 | TT_TASK | Admin Gen Bussing Install | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1107 | TT_TASK | Awaiting DCE approval of Non NEMA standard Lugs | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1108 | TT_TASK | Awaiting Phase conductor lugs from NC power as per RFI#412 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1109 | TT_TASK | 6.1.41 - Incorrect Lugs for Admin Gen Main Bussing | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1112 | TT_TASK | COLO-1 Cell-4 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
1113 | TT_TASK | COLO-1 Cell-3 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Thu Mar 11 00:00:00 IST 2021 |  | COMPLETED
1114 | TT_TASK | COLO-1 Cell-2 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1115 | TT_TASK | COLO-1 Cell-1 SE Install UPS batteries in cabinet | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1117 | TT_TASK | COLO-2 Cell-1 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
1118 | TT_TASK | COLO-2 Cell-2 SE Install UPS batteries in cabinet | Fri Apr 30 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
1119 | TT_TASK | COLO-2 Cell-3 SE Install UPS batteries in cabinet | Sat May 08 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1120 | TT_TASK | COLO-2 Cell-4 SE Install UPS batteries in cabinet | Sat May 15 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
1122 | TT_TASK | COLO-3 Cell-1 SE Install UPS batteries in cabinet | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1123 | TT_TASK | COLO-3 Cell-2 SE Install UPS batteries in cabinet | Tue May 25 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1124 | TT_TASK | COLO-3 Cell-3 SE Install UPS batteries in cabinet | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1125 | TT_TASK | COLO-3 Cell-4 SE Install UPS batteries in cabinet | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1127 | TT_TASK | COLO-4 Cell-1 SE Install UPS batteries in cabinet | Tue Sep 14 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1128 | TT_TASK | COLO-4 Cell-2 SE Install UPS batteries in cabinet | Wed Sep 29 07:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  | 320.0 | IN_PROGRESS
1129 | TT_TASK | COLO-4 Cell-3 SE Install UPS batteries in cabinet | Tue Sep 07 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
1130 | TT_TASK | COLO-4 Cell-4 SE Install UPS batteries in cabinet | Tue Sep 21 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
1132 | TT_TASK | COLO-2 CEll-2 Awaiting SE Revised tool Come along for MER Lift & Set | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
1133 | TT_TASK | COLO-2 CEll-3 Awaiting SE Revised tool Come along for MER Lift & Set | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1134 | TT_TASK | MER shipping split connection Safety Standown & RCA Review | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1137 | TT_TASK | COLO-2 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1138 | TT_TASK | RFI#432 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
1139 | TT_TASK | Lead time for tube steel | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
1140 | TT_TASK | COLO-2 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1141 | TT_TASK | COLO-2 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Thu Apr 01 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1142 | TT_TASK | COLO-2 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1144 | TT_TASK | COLO-3 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Fri May 07 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 |  | COMPLETED
1145 | TT_TASK | COLO-3 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Wed May 19 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed May 19 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 |  | COMPLETED
1146 | TT_TASK | COLO-3 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Thu May 13 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Thu May 13 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 |  | COMPLETED
1147 | TT_TASK | COLO-3 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Wed May 26 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Wed May 26 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 |  | COMPLETED
1149 | TT_TASK | COLO-4 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1150 | TT_TASK | COLO-4 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1151 | TT_TASK | COLO-4 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1152 | TT_TASK | COLO-4 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Mon Jun 14 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1154 | TT_TASK | All Construction activities -Safety Standown due to Admin Gen unplanned Energization | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
1156 | TT_TASK | COLO-1 Cell-1 Field Modification of tray | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1157 | TT_TASK | COLO-1 Cell-2 Field Modification of tray | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Jan 21 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1160 | TT_TASK | #3. Snow- 1/27/2021(one full day) | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 |  | COMPLETED
1161 | TT_TASK | #4. Extreme Heat - 6/28/21- 7/2/21(Effecting COLO-4 Yard work) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
1162 | TT_TASK | #5 Extreme heat -production loss in Yards 7/1/21 through 7/14/21 (11 half days of loss) | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 09 00:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
1163 | TT_TASK | #6 Extreme heat - Production loss in Yards 7/15/21 through 7/31/21 (3 half days) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
1164 | TT_TASK | #1. Rain And High Winds- 10/13/2020(half day only) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Tue Oct 13 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1165 | TT_TASK | #2. Snow -12/30/20 (one full day) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Wed Dec 30 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
1168 | TT_TASK | COLO-1 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Mon Jan 11 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
1169 | TT_TASK | COLO-1 CELL-3 WA State L&I onsite inspection & Approval to Connect to MER | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1170 | TT_TASK | COLO-1 CELL-2 WA State L&I onsite inspection & Approval to Connect to MER | Sat Jan 23 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1171 | TT_TASK | COLO-1 CELL-4 WA State L&I onsite inspection & Approval to Connect to MER | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1173 | TT_TASK | COLO-2 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Fri Mar 12 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1174 | TT_TASK | COLO-2 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Tue Mar 23 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1175 | TT_TASK | COLO-2 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
1176 | TT_TASK | COLO-2 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Fri Apr 09 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1178 | TT_TASK | COLO-3 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Sat May 08 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1179 | TT_TASK | COLO-3 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Fri May 14 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1180 | TT_TASK | COLO-3 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1181 | TT_TASK | COLO-3 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1183 | TT_TASK | COLO-4 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 |  | COMPLETED
1184 | TT_TASK | COLO-4 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Sat Jun 19 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1185 | TT_TASK | COLO-4 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
1186 | TT_TASK | COLO-4 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 |  | COMPLETED
1189 | TT_TASK | 6.1.36 Rework for Addtional circuits for UMS URS Battery charger feed upsize | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1190 | TT_TASK | 6.1.34.1 COLO-1 Cell-1 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1191 | TT_TASK | 6.1.34.2 COLO-1 Cell-2 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1192 | TT_TASK | 6.1.34.3 COLO-1 Cell-3 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 |  | COMPLETED
1193 | TT_TASK | 6.1.34.4 COLO-1 Cell-4 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 |  | COMPLETED
1194 | TT_TASK | 6.1.01.0 Awaiting MER 10A HRG's (lead time= 8 weeks from 2/2/2021) | Mon Mar 01 07:00:00 IST 2021 | Mon Apr 12 17:00:00 IDT 2021 | Tue Feb 02 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
1195 | TT_TASK | 6.1.09 Awaiting Rev-D for Coordination study (DRB3/SCCS/ Submittal Breaker verification) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1196 | TT_TASK | 6.1.26.1 L2/L3 Scripts SE MER overall Script | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
1197 | TT_TASK | 6.1.33 URS UMS Ground Buss hole Pattern | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1198 | TT_TASK | 6.1.35 UPS battery IR Scanning | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1199 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-1 Cell-1 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1200 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-1 Cell-4 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1201 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-1 Cell-3 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1202 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-1 Cell-2 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1203 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-2 Cell-1 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1204 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-2 Cell-2 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1205 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-2 Cell-3 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1206 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-2 Cell-4 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue Jul 13 00:00:00 IDT 2021 | Mon Jul 19 00:00:00 IDT 2021 |  | COMPLETED
1207 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-3 Cell-1 | Tue Aug 31 07:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
1208 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-3 Cell-4 | Tue Sep 07 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  |  | 10.0 | NOT_STARTED
1209 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-3 Cell-3 | Tue Sep 07 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  |  | 10.0 | NOT_STARTED
1210 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-3 Cell-2 | Thu Sep 09 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1211 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-4 Cell-1 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1212 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-4 Cell-4 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1213 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-4 Cell-3 | Mon Oct 18 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1214 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-4 Cell-2 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1216 | TT_TASK | 6.1.37- 6.2.01- Ground Fault setting on COLO-2 Gen MCB01 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Wed Apr 28 17:00:00 IDT 2021 |  | COMPLETED
1218 | TT_TASK | 6.1.38 PDU MCB01 LOTO Provisions | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1220 | TT_TASK | 6.1.11 Awaiting BAS Backplanes from Siemens to VECA for Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
1221 | TT_TASK | 6.1.26.2 L2/L3 Scripts Siemens BAS SAT Scripts | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1222 | TT_TASK | 6.1.11 Awaiting Liftstation #3 BAS Backplanes from Siemens to VECA for Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1223 | TT_TASK | 6.1.11 Liftstation #3 BAS Install / Pull wire / term Backplanes | Mon May 17 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 |  | COMPLETED
1226 | TT_TASK | COLO-2 Cell-1 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Dec 29 00:00:00 IST 2020 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1227 | TT_TASK | COLO-2 Cell-2 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sun Jan 10 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1228 | TT_TASK | COLO-2 Cell-3 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Jan 20 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1229 | TT_TASK | COLO-2 Cell-4 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sat Jan 23 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1231 | TT_TASK | COLO-3 Cell-1 Install Missing Raceway & Bussing within generator | Mon Apr 26 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1232 | TT_TASK | COLO-3 Cell-2 Install Missing Raceway & Bussing within generator | Thu Apr 29 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1233 | TT_TASK | COLO-3 Cell-3 Install Missing Raceway & Bussing within generator | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
1234 | TT_TASK | COLO-3 Cell-4 Install Missing Raceway & Bussing within generator | Tue May 04 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1236 | TT_TASK | COLO-4 Cell-1 Install Missing Raceway & Bussing within generator | Tue May 25 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
1237 | TT_TASK | COLO-4 Cell-2 Install Missing Raceway & Bussing within generator | Tue May 11 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1238 | TT_TASK | COLO-4 Cell-3 Install Missing Raceway & Bussing within generator | Thu May 20 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1239 | TT_TASK | COLO-4 Cell-4 Install Missing Raceway & Bussing within generator | Mon May 17 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
1242 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1243 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 2weeks- fab and ship | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Mon Apr 05 00:00:00 IDT 2021 |  | COMPLETED
1244 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 1 week to install | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
1245 | TT_TASK | 6.1.44- MER Battery Monitoring Software Â– Constraint to EPMS checkouts/Point Â– Point(needed by 4/23) | Mon Mar 15 07:00:00 IST 2021 | Mon Jun 07 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Aug 07 07:00:00 IDT 2021 |  | COMPLETED
1246 | TT_TASK | 6.1.46- Site UPM Inspections | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
1247 | TT_TASK | 6.1.47- COLO-1 Cell-2 UPS01- Factory Test thermal event | Mon Mar 15 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
1249 | TT_TASK | 6.1.40- 480V house power to Gen Enclousure is Fed OH vs UG | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1254 | TT_TASK | Downtime awaiting solution for safety space constraint | Mon Apr 26 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1256 | TT_TASK | NOPC-18 Remove COLO-1 Cell-1 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1257 | TT_TASK | Rubicon MSB inspection complete (ready for transformer reinstall) | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Mon Apr 26 07:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1258 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-1 transformer | Tue May 25 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1260 | TT_TASK | NOPC-18 Remove COLO-1 Cell-2 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
1261 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1262 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-2 transformer | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1264 | TT_TASK | NOPC-18 Remove COLO-1 Cell-3 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 |  | COMPLETED
1265 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1266 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-3 transformer | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1268 | TT_TASK | NOPC-18 Remove COLO-1 Cell-4 transformer | Mon May 17 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1269 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1270 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-4 transformer | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1273 | TT_TASK | NOPC-18 Remove COLO-2 Cell-1 transformer | Tue Jun 01 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue Jun 08 00:00:00 IDT 2021 |  | COMPLETED
1274 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-1 transformer | Thu Jul 22 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1276 | TT_TASK | NOPC-18 Remove COLO-2 Cell-2 transformer | Wed Jun 02 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
1277 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-2 transformer | Fri Jul 23 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
1279 | TT_TASK | NOPC-18 Remove COLO-2 Cell-3 transformer | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 |  | COMPLETED
1280 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-3 transformer | Thu Jul 29 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1282 | TT_TASK | NOPC-18 Remove COLO-2 Cell-4 transformer | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1283 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-4 transformer | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Jul 09 00:00:00 IDT 2021 | Mon Jul 12 00:00:00 IDT 2021 |  | COMPLETED
1286 | TT_TASK | NOPC-18 Remove COLO-3 Cell-1 transformer | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
1287 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-1 transformer | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 22 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1289 | TT_TASK | NOPC-18 Remove COLO-3 Cell-2 transformer | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jul 24 07:00:00 IDT 2021 | Sat Jul 24 17:00:00 IDT 2021 |  | COMPLETED
1290 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-2 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
1292 | TT_TASK | NOPC-18 Remove COLO-3 Cell-3 transformer | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Thu Aug 19 07:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1293 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-3 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1295 | TT_TASK | NOPC-18 Remove COLO-3 Cell-4 transformer | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1296 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-4 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1299 | TT_TASK | NOPC-18 Remove COLO-4 Cell-1 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1300 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-1 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1302 | TT_TASK | NOPC-18 Remove COLO-4 Cell-2 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1303 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-2 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1305 | TT_TASK | NOPC-18 Remove COLO-4 Cell-3 transformer | Wed Sep 29 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1306 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-3 transformer | Sat Oct 09 07:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1308 | TT_TASK | NOPC-18 Remove COLO-4 Cell-4 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1309 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-4 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1311 | TT_TASK | PDU termination crew downtime due to COVID-19 | Sat Apr 24 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Sat Apr 24 07:00:00 IDT 2021 |  | COMPLETED
1314 | TT_TASK | 6.2.03- Replace ADP01 faulty trip units | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1315 | TT_TASK | 6.1.51-COLO-1 Cell-1,2 Factory conductors not terminated per drawings | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1316 | TT_TASK | 6.1.49 - COLO-1 Cell-1 Awaiting Ground Lug solution, procurement, installation of labelling ATS 01-06 | Fri Apr 30 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
1317 | TT_TASK | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
1318 | TT_TASK | 6.1.53-COLO-1 Cell-1,2 UPS01, PNL01 awaiting missing breakers | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1319 | TT_TASK | 6.1.53-COLO-1 Cell-1,2,3,4 UPS01, PNL01 Install/ term Missing breakers | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1320 | TT_TASK | 6.1.59 (6.1.51 carryover) -COLO-1 Cell-1,2 Factory conductors exertherm corrections | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
1321 | TT_TASK | 6.1.50- SCCS Revision#10 (RFI-540) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1325 | TT_TASK | 6.1.54- TCM Awaiting Admin Siemens Break tank parts | Mon May 17 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1326 | TT_TASK | 6.1.54- Install Breaktank parts | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1328 | TT_TASK | 6.2.03- Replace Damaged UPM in COLO-4 Cell-4 | Thu May 06 07:00:00 IDT 2021 | Sat May 08 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1330 | TT_TASK | 6.1.55-COLO-1 - FC Factoy Re-wire (RFI-502) | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1331 | TT_TASK | 6.1.55-COLO-2 - FC Factoy Re-wire (RFI-502) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1332 | TT_TASK | 6.1.55-COLO-3 - FC Factoy Re-wire (RFI-502) | Sat Jun 05 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1333 | TT_TASK | 6.1.55-COLO-4 - FC Factoy Re-wire (RFI-502) | Thu Jun 10 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1335 | TT_TASK | 6.1.57 -Awaiting revised coordination study #9 | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
1336 | TT_TASK | Reprint revised panel 3,4 Arc flash labels | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1337 | TT_TASK | Print new DC Arc flash labels for Admin ELP | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1340 | TT_TASK | 6.1.58-RFI-528- COLO-1 - SF/RF Circuitry & terminal block rework | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
1341 | TT_TASK | 6.1.63- COLO1-UPS01-PNL01 Compass Issues Constraining L3Â’s | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
1342 | TT_TASK | 6.1.56 - COLO-1 Awaiting MSB/ADP Ground Lug replacements, Installation of labelling | Fri Apr 30 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
1349 | TT_TASK | All trades stand down | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
1350 | TT_TASK | Veca standown | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
1353 | TT_TASK | COLO-1 Cell-1 MER-UPS Battery Disconnect modifications rework | Wed Jun 16 07:00:00 IDT 2021 | Sat Jun 19 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1354 | TT_TASK | COLO-1 Cell-2 MER-UPS Battery Disconnect modifications rework | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1355 | TT_TASK | COLO-1 Cell-3 MER-UPS Battery Disconnect modifications rework | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
1356 | TT_TASK | COLO-1 Cell-4 MER-UPS Battery Disconnect modifications rework | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
1357 | TT_TASK | RFI-548 COLO MSB to UPS Battery disconnect solution approval | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1358 | TT_TASK | ADMIN-UPS Battery Disconnect modifications rework | Wed Jun 16 07:00:00 IDT 2021 | Sat Jun 19 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1359 | TT_TASK | RFI-552 Admin MSB to UPS Battery disconnect solution approval | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
1361 | TT_TASK | COLO-2 Cell-2 MER-UPS Battery Disconnect modifications rework | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 |  | COMPLETED
1362 | TT_TASK | COLO-2 Cell-1 MER-UPS Battery Disconnect modifications rework | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  | COMPLETED
1363 | TT_TASK | COLO-2 Cell-3 MER-UPS Battery Disconnect modifications rework | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  | COMPLETED
1364 | TT_TASK | COLO-2 Cell-4 MER-UPS Battery Disconnect modifications rework | Fri Jul 02 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 23 07:00:00 IDT 2021 |  | COMPLETED
1366 | TT_TASK | COLO-3 Cell-1 MER-UPS Battery Disconnect modifications rework | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 |  | COMPLETED
1367 | TT_TASK | COLO-3 Cell-2 MER-UPS Battery Disconnect modifications rework | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1368 | TT_TASK | COLO-3 Cell-3 MER-UPS Battery Disconnect modifications rework | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
1369 | TT_TASK | COLO-3 Cell-4 MER-UPS Battery Disconnect modifications rework | Sat Sep 11 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Mon Aug 16 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1371 | TT_TASK | COLO-4 Cell-1 MER-UPS Battery Disconnect modifications rework | Thu Sep 16 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
1372 | TT_TASK | COLO-4 Cell-2 MER-UPS Battery Disconnect modifications rework | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
1373 | TT_TASK | COLO-4 Cell-3 MER-UPS Battery Disconnect modifications rework | Mon Sep 27 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1374 | TT_TASK | COLO-4 Cell-4 MER-UPS Battery Disconnect modifications rework | Fri Sep 03 07:00:00 IDT 2021 | Thu Sep 09 17:00:00 IDT 2021 |  |  | 270.0 | NOT_STARTED
1377 | TT_TASK | COLO-3 Cell-3 Remove inaccessible tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 |  | COMPLETED
1378 | TT_TASK | COLO-3 CEll-3 Reinstall tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
1379 | TT_TASK | COLO-3 Cell-4 Remove inaccessible tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Sat Jun 12 00:00:00 IDT 2021 |  | COMPLETED
1380 | TT_TASK | COLO-3 Cell-4 Reinstall tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1381 | TT_TASK | COLO-4 Cell-1 Remove inaccessible tray in MER | Mon Jul 12 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Sat Jun 12 00:00:00 IDT 2021 |  | COMPLETED
1382 | TT_TASK | COLO-4 Cell-1 Reinstall tray in MER | Tue Aug 03 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
1383 | TT_TASK | COLO-4 Cell-2 Remove inaccessible tray in MER | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
1384 | TT_TASK | COLO-4 Cell-2 Reinstall tray in MER | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1385 | TT_TASK | COLO-4 Cell-3 Remove inaccessible tray in MER | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Thu Jul 15 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
1386 | TT_TASK | COLO-4 Cell-3 Reinstall tray in MER | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
1387 | TT_TASK | COLO-4 Cell-4 Remove inaccessible tray in MER4 | Wed Aug 04 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
1388 | TT_TASK | COLO-4 Cell-4 Reinstall tray in MER | Fri Sep 03 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Mon Aug 09 07:00:00 IDT 2021 | Thu Aug 12 00:00:00 IDT 2021 |  | COMPLETED
1389 | TT_TASK | COLO-3 Cell-1 Remove inaccessible tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
1390 | TT_TASK | COLO-3 CEll-1 Reinstall tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 |  | COMPLETED
1391 | TT_TASK | COLO-3 Cell-2 Remove inaccessible tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1392 | TT_TASK | COLO-3 Cell-2 Reinstall tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1395 | TT_TASK | COLO-3 Cell-3 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 14 00:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1397 | TT_TASK | COLO-4 Cell-1 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Fri Jul 23 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1398 | TT_TASK | COLO-4 Cell-2 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
1399 | TT_TASK | COLO-4 Cell-3 Conduit rework | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 |  | COMPLETED
1400 | TT_TASK | COLO-4 Cell-4 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1404 | TT_TASK | 6.1-88 COLO-1 MER awaiting updated UPS L3 test script approval | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 31 07:00:00 IDT 2021 |  | COMPLETED
1405 | TT_TASK | 6.1-89 RFI574- COLO-1 Relocating MSB EPMS device to different cabinet | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1406 | TT_TASK | 6.1-92 COLO-1 SF/ RF startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
1407 | TT_TASK | 6.1-93 COLO-1 HVAC minisplits startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1409 | TT_TASK | 6.2-08 COLO-2 Cell- 1,2 MER equipment Phenolic labelling | Wed Jul 14 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
1410 | TT_TASK | 6.2-08 COLO-2 Cell- 3,4 MER equipment Phenolic labelling | Wed Jul 14 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Mon Aug 02 00:00:00 IDT 2021 |  | COMPLETED
1411 | TT_TASK | 6.2-12 COLO-2 All Cells- Factory connection Torque verification | Wed Jul 14 07:00:00 IDT 2021 | Wed Jul 21 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
1413 | TT_TASK | 6.1-95 COLO-1 ATS's L3 startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  | COMPLETED
1415 | TT_TASK | 6.1-96 COLO-1 PDU - EPMS L3 startup delay (vendor schedule availability) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Mon Aug 02 07:00:00 IDT 2021 |  | COMPLETED
1420 | TT_TASK | COLO-2 Cell-1 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1421 | TT_TASK | COLO-2 Cell-2 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1422 | TT_TASK | COLO-2 Cell-3 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1423 | TT_TASK | COLO-2 Cell-4 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 00:00:00 IDT 2021 |  | COMPLETED
1429 | TT_TASK | 6.1-98 Admin/COLO-1 ASCO EPMS Connectivity Issues | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1430 | TT_TASK | 6.1-88 Admin/ COLO-1 MER/ADMIN UPS L3 Testing (includes shutdown to move PQM's & PQM data post proccessing) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 31 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1431 | TT_TASK | 6.1-106 COLO-1 Cell-2 UPS01 Power module failure | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1433 | TT_TASK | COLO-2 Cell-1 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1434 | TT_TASK | COLO-2 Cell-3 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1435 | TT_TASK | COLO-2 Cell-4 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1437 | TT_TASK | COLO-3 Delay in SE uploading QC Checkilst | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Fri Aug 06 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1439 | TT_TASK | COLO-2 Cell-2 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1442 | TT_TASK | Mobilization | Mon Apr 27 07:00:00 IDT 2020 | Wed May 20 17:00:00 IDT 2020 | Mon Apr 06 00:00:00 IDT 2020 | Sat May 02 17:00:00 IDT 2020 |  | COMPLETED
1444 | TT_TASK | Establish Access Roads / Laydown / Craft Parking / Temp Utilities | Thu May 14 07:00:00 IDT 2020 | Fri Jun 19 17:00:00 IDT 2020 | Fri Apr 24 00:00:00 IDT 2020 | Sat May 23 00:00:00 IDT 2020 |  | COMPLETED
1446 | TT_TASK | Site Sanitary | Mon May 11 07:00:00 IDT 2020 | Fri Jul 24 17:00:00 IDT 2020 | Tue May 05 00:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 |  | COMPLETED
1447 | TT_TASK | Remaining Site Sanitary | Mon May 11 07:00:00 IDT 2020 | Fri Jul 24 17:00:00 IDT 2020 | Tue Aug 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
1448 | TT_TASK | IWW System | Tue May 26 07:00:00 IDT 2020 | Sat Aug 08 17:00:00 IDT 2020 | Mon May 18 00:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 |  | COMPLETED
1449 | TT_TASK | Remaining IWW System | Tue May 26 07:00:00 IDT 2020 | Sat Aug 08 17:00:00 IDT 2020 | Tue Aug 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
1450 | TT_TASK | Site Water / Fire Loop | Fri Jul 24 07:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1451 | TT_TASK | Site Storm | Mon Jun 29 07:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
1454 | TT_TASK | Telecom-Communications Site Loop/Ductbank | Mon Jun 29 08:00:00 IDT 2020 | Thu Oct 01 08:00:00 IDT 2020 | Thu Jun 25 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1455 | TT_TASK | Telecom-RNG Fiber Underground installation | Mon Feb 01 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
1456 | TT_TASK | Telecom-RNG Fiber CNR buildout | Mon Oct 05 07:00:00 IDT 2020 | Tue Dec 08 17:00:00 IST 2020 | Mon Oct 05 07:00:00 IDT 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
1461 | TT_TASK | Temp Power/ Telecom duct bank | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Thu Aug 27 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1462 | TT_TASK | Vault- set 1st Vault Along UMS Duct bank run | Thu Sep 03 07:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1463 | TT_TASK | Vault- Set 2nd vault Along UMS Duct Run near COLO-2 | Tue Sep 08 07:00:00 IDT 2020 | Thu Sep 10 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1464 | TT_TASK | Vault- Set vault along URS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1465 | TT_TASK | Vault- Set vault along UMS to JAZ run | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1466 | TT_TASK | Set URS Vault | Mon Nov 16 08:00:00 IST 2020 | Wed Nov 25 08:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1467 | TT_TASK | Set UMS vault | Wed Nov 25 08:00:00 IST 2020 | Tue Dec 08 08:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1469 | TT_TASK | Vault- Set North vault- Along UPM to Vault | Fri Oct 09 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1470 | TT_TASK | Vault - Set North Vault Along Vault to URS run | Fri Oct 23 07:00:00 IDT 2020 | Tue Oct 27 17:00:00 IST 2020 | Thu Aug 20 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1471 | TT_TASK | Vault - Set South Vault Along Vault to URS run | Sat Nov 07 07:00:00 IST 2020 | Tue Nov 10 17:00:00 IST 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1472 | TT_TASK | Vault - Set South Vault along UPM to Vault | Mon Nov 23 07:00:00 IST 2020 | Wed Nov 25 17:00:00 IST 2020 | Thu Aug 20 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1475 | TT_TASK | Duct bank- COLO-1 UPM to north vault | Mon Oct 19 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Fri Oct 02 00:00:00 IDT 2020 | Mon Oct 05 00:00:00 IDT 2020 |  | COMPLETED
1476 | TT_TASK | Duct bank- COLO-2 UPM to north Valut | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Mon Oct 05 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1477 | TT_TASK | Duct Bank- Building to URS - 1st Half | Sat Sep 26 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 07:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
1478 | TT_TASK | Duct Bank- Building to URS(upto horse shoe) - 2nd Half | Wed Sep 30 07:00:00 IDT 2020 | Thu Oct 08 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
1479 | TT_TASK | Duct Bank - JAZ to vault- UMS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Thu Oct 29 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1480 | TT_TASK | Duct Bank - Vault to Vault along UMS duct Run - horseshoe | Mon Oct 26 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
1481 | TT_TASK | Duct Bank - COLO-3 UPM to Vault UMS Run | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1482 | TT_TASK | Duct Bank - URS to vault - URS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1483 | TT_TASK | Duct Bank - Vault To JAZ - URS to JAZ run | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 09 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1484 | TT_TASK | Duct Bank - Vault to UMS- UMS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1485 | TT_TASK | Duct Bank - south vault (along UMS duct run) to UMS | Sat Nov 21 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1486 | TT_TASK | Duct Bank - COLO-4 UPM to UMS | Mon Nov 23 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
1488 | TT_TASK | Duct Bank - COLO1- UPM to UPM | Mon Aug 10 07:00:00 IDT 2020 | Thu Aug 13 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1489 | TT_TASK | Duct Bank - COLO2- UPM to UPM | Mon Aug 31 07:00:00 IDT 2020 | Thu Sep 03 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
1490 | TT_TASK | Duct Bank - North Crossover (URS to west Vault Run) | Mon Sep 14 07:00:00 IDT 2020 | Sat Sep 26 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
1491 | TT_TASK | Duct Bank - South Cross over (URS to west Vault Run) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
1492 | TT_TASK | Duct Bank - COLO-3 UPM to UPM | Fri Nov 06 07:00:00 IST 2020 | Tue Nov 10 17:00:00 IST 2020 | Sat Oct 10 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1493 | TT_TASK | Duct Bank - COLO-4 UPM to UPM | Wed Nov 25 07:00:00 IST 2020 | Wed Dec 02 17:00:00 IST 2020 | Sat Oct 10 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1495 | TT_TASK | Duct Bank Admin UPM to COLO-1 UPM | Thu Sep 24 07:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1496 | TT_TASK | Duct Back- Admin UPM to Vault | Fri Oct 23 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Mon Aug 24 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
1497 | TT_TASK | Duct Bank COLO-2 UPM to Vault | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Mon Sep 28 00:00:00 IDT 2020 | Thu Oct 01 00:00:00 IDT 2020 |  | COMPLETED
1498 | TT_TASK | Duct Bank - Building to North Vault URS run | Fri Oct 23 07:00:00 IDT 2020 | Sat Oct 31 17:00:00 IST 2020 | Fri Oct 02 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1499 | TT_TASK | Duct Bank - Builing to South Vault- URS Run | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 09 17:00:00 IST 2020 | Fri Oct 02 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1500 | TT_TASK | Duct Bank - Vault to COLO-3 UPM | Tue Nov 10 07:00:00 IST 2020 | Fri Nov 13 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1501 | TT_TASK | Duct Bank - Vault to COLO-4 UPM | Mon Nov 16 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1503 | TT_TASK | Set MV Gear (URS) | Mon Nov 23 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1504 | TT_TASK | Set MV Gear (UMS) | Mon Dec 21 07:00:00 IST 2020 | Mon Dec 28 17:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
1506 | TT_TASK | Pull UPM to UPM COLO-1 - CELL-1 to Cell-3 | Tue Jan 05 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1507 | TT_TASK | Pul UPM to UPM COLO-2- CELL-1 to Cell-3 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Sat Jan 02 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
1508 | TT_TASK | Pull UPM to UPM COLO-3 - CELL-1 to Cell-3 | Fri Jan 15 07:00:00 IST 2021 | Mon Jan 18 17:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1509 | TT_TASK | Pull UPM to UPM COLO-4 - CELL-1 to Cell-3 | Wed Feb 03 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
1511 | TT_TASK | Pull UPM to UPM Admin to COLO-1 Cell -2 | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1512 | TT_TASK | Pull UPM to UPM COLO-1 Cell 2- Cell - 4 | Thu Jan 07 07:00:00 IST 2021 | Fri Jan 08 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1513 | TT_TASK | Pull UPM to UPM COLO-2 Cell 2- Cell - 4 | Wed Feb 03 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1514 | TT_TASK | Pull UPM to UPM COLO-3 Cell 2- Cell - 4 | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1515 | TT_TASK | Pull UPM to UPM COLO-4 Cell 2- Cell - 4 | Thu Feb 11 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1517 | TT_TASK | Pull Cross Overs- COLO-1 CELL-3 to CELL-4 | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1518 | TT_TASK | Pull Cross Overs- COLO-2 CELL-3 to CELL-4 | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1519 | TT_TASK | Pull Cross Overs- COLO-3 CELL-3 to CELL-4 | Tue Feb 09 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1520 | TT_TASK | Pull Cross Overs- COLO-4 CELL-3 to CELL-4 | Sat Feb 13 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1522 | TT_TASK | PULL- URS to Admin | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Sat Dec 05 00:00:00 IST 2020 |  | COMPLETED
1523 | TT_TASK | PULL- URS to COLO-2 | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
1524 | TT_TASK | PULL- URS to COLO-3 | Tue Jan 12 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1525 | TT_TASK | PULL- URS to COLO-4 | Mon Jan 18 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1527 | TT_TASK | Pull- UMS to COLO-1,2,3 | Tue Jan 12 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Jan 11 17:00:00 IST 2021 |  | COMPLETED
1528 | TT_TASK | Pull- UMS to COLO-4 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 |  | COMPLETED
1530 | TT_TASK | Pull - JAZ to URS | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
1531 | TT_TASK | Pull - JAZ to UMS | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1534 | TT_TASK | Term COLO -1 Cell-3 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1535 | TT_TASK | Term COLO -2 Cell-3 UPM | Thu Mar 04 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1536 | TT_TASK | Term COLO -3 Cell-3 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 |  | COMPLETED
1537 | TT_TASK | Term COLO -4 Cell-3 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1538 | TT_TASK | Term COLO -1 Cell-1 UPM | Wed Feb 10 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1539 | TT_TASK | Term COLO -2 Cell-1 UPM | Sat Feb 13 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1540 | TT_TASK | Term COLO -3 Cell-1 UPM | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1541 | TT_TASK | Term COLO -4 Cell-1 UPM | Thu Mar 11 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1543 | TT_TASK | Term COLO -1 Cell-4 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
1544 | TT_TASK | Term COLO -2 Cell-4 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1545 | TT_TASK | Term COLO -3 Cell-4 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1546 | TT_TASK | Term COLO -4 Cell-4 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1547 | TT_TASK | Term Admin - UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1548 | TT_TASK | Term COLO -1 Cell-2 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
1549 | TT_TASK | Term COLO -2 Cell-2 UPM | Fri Feb 05 07:00:00 IST 2021 | Tue Feb 09 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1550 | TT_TASK | Term COLO -3 Cell-2 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1551 | TT_TASK | Term COLO -4 Cell-2 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1553 | TT_TASK | Battery Station Yellow tagging / EPMS Checkouts | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1554 | TT_TASK | GCPUD NORTH Mobile substation maintance & Mobile Sub re-energization 4/1 Â– 4/3 | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1555 | TT_TASK | GCPUD SOUTH Mobile substation maintance & Mobile Sub re-energization 4/1 Â– 4/3 | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1556 | TT_TASK | Term- UMS- Line Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1557 | TT_TASK | Term- JAZ to Structure- (Incl Stress Cones) from ums | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1558 | TT_TASK | Term- UMS- Load side | Wed Feb 10 07:00:00 IST 2021 | Tue Feb 23 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1559 | TT_TASK | Yellow Tagging for UMS (includes GC, vendor Lvl-2) | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
1560 | TT_TASK | UMS Control Power Available CYT | Wed Feb 10 07:00:00 IST 2021 | Wed Feb 17 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
1562 | TT_TASK | Term URS- Line Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
1563 | TT_TASK | Term- JAS to URS- (Incl Stress Cones) | Wed Feb 03 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1564 | TT_TASK | TERM- URS- Load Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1565 | TT_TASK | Yellow Tagging for URS | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
1566 | TT_TASK | URS Control Power Available CYT | Wed Feb 10 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
1568 | TT_TASK | Aggregate Road Base | Mon Oct 19 07:00:00 IDT 2020 | Tue Nov 24 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
1569 | TT_TASK | Plant shutdown for winter | Mon Nov 30 07:00:00 IST 2020 | Tue Apr 06 17:00:00 IDT 2021 | Mon Nov 23 00:00:00 IST 2020 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
1570 | TT_TASK | Curb & Gutter | Mon Nov 30 07:00:00 IST 2020 | Sat Jan 09 17:00:00 IST 2021 | Mon Nov 02 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1571 | TT_TASK | Pave HMA | Mon Apr 05 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Sat Nov 07 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1572 | TT_TASK | Site Lighting | Mon May 03 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 |  | 120.0 | IN_PROGRESS
1575 | TT_TASK | Landscape and Site Specialties | Mon May 17 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1581 | TT_TASK | Perimeter Foundations - Excavate/FRP | Mon Apr 27 07:00:00 IDT 2020 | Thu May 14 17:00:00 IDT 2020 | Wed Apr 22 00:00:00 IDT 2020 | Wed May 20 00:00:00 IDT 2020 |  | COMPLETED
1582 | TT_TASK | Perimeter Foundations - Waterproof/Backfill | Mon Jun 01 07:00:00 IDT 2020 | Thu Jun 04 17:00:00 IDT 2020 | Wed May 27 00:00:00 IDT 2020 | Fri Jun 05 00:00:00 IDT 2020 |  | COMPLETED
1583 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Fri Jun 05 07:00:00 IDT 2020 | Tue Jun 16 17:00:00 IDT 2020 | Tue Jun 02 00:00:00 IDT 2020 | Fri Jun 12 00:00:00 IDT 2020 |  | COMPLETED
1585 | TT_TASK | Erect PEMB Steel | Mon Jun 29 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 |  | COMPLETED
1586 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Thu Jul 02 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
1588 | TT_TASK | MEP Undeground Rough-In (Interior) | Tue Aug 18 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1589 | TT_TASK | Aggregate Base Course | Mon Aug 31 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 |  | COMPLETED
1590 | TT_TASK | Slab on Grade | Mon Sep 14 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1592 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Aug 18 07:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 |  | COMPLETED
1593 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Tue Jul 14 00:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 |  | COMPLETED
1594 | TT_TASK | Downspouts & Gutters | Tue Aug 18 07:00:00 IDT 2020 | Sat Aug 29 17:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
1604 | TT_TASK | Perimeter Foundations - Excavate/FRP | Fri May 15 07:00:00 IDT 2020 | Wed Jun 03 17:00:00 IDT 2020 | Mon May 04 00:00:00 IDT 2020 | Fri May 15 00:00:00 IDT 2020 |  | COMPLETED
1605 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Sat Jun 13 07:00:00 IDT 2020 | Thu Jun 25 17:00:00 IDT 2020 | Tue Jun 02 00:00:00 IDT 2020 | Fri Jun 12 00:00:00 IDT 2020 |  | COMPLETED
1606 | TT_TASK | Perimeter Foundations - Waterproof Backfill | Tue May 26 07:00:00 IDT 2020 | Sat Jun 06 17:00:00 IDT 2020 | Tue May 26 07:00:00 IDT 2020 | Wed Jun 17 00:00:00 IDT 2020 |  | COMPLETED
1608 | TT_TASK | Erect PEMB Steel | Mon Jun 29 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Fri Jun 26 00:00:00 IDT 2020 | Mon Jul 06 00:00:00 IDT 2020 |  | COMPLETED
1609 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 |  | COMPLETED
1610 | TT_TASK | Erect Interior Structural Steel | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
1612 | TT_TASK | MEP Undeground Rough-In (Interior) | Fri Aug 14 07:00:00 IDT 2020 | Tue Sep 01 17:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1613 | TT_TASK | Aggregate Base Course | Sat Sep 05 07:00:00 IDT 2020 | Fri Sep 11 17:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 |  | COMPLETED
1614 | TT_TASK | Slab on Grade | Mon Sep 14 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1618 | TT_TASK | Exterior Insulated Metal Panels Installation - East Elevation | Tue Aug 18 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Mon Jul 13 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1621 | TT_TASK | Exterior Insulated Metal Panels Installation - West Elevation | Tue Aug 18 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Mon Jul 13 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1623 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 |  | COMPLETED
1624 | TT_TASK | Downspouts & Gutters | Tue Aug 18 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Wed Aug 12 00:00:00 IDT 2020 |  | COMPLETED
1629 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jun 22 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Mon May 11 00:00:00 IDT 2020 | Tue Jun 16 00:00:00 IDT 2020 |  | COMPLETED
1630 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Wed Jul 08 07:00:00 IDT 2020 | Mon Jul 20 17:00:00 IDT 2020 | Tue Jun 09 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
1632 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Tue Jul 07 00:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 |  | COMPLETED
1633 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 | Tue Aug 04 00:00:00 IDT 2020 |  | COMPLETED
1634 | TT_TASK | Erect Interior Structural Steel | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1636 | TT_TASK | MEP Undeground Rough-In (Interior) | Mon Aug 31 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 |  | COMPLETED
1637 | TT_TASK | Aggregate Base Course | Mon Oct 19 07:00:00 IDT 2020 | Mon Oct 26 17:00:00 IST 2020 | Thu Oct 01 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1638 | TT_TASK | Slab on Grade | Mon Oct 19 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1640 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Aug 18 07:00:00 IDT 2020 | Tue Sep 01 17:00:00 IDT 2020 | Fri Jul 31 00:00:00 IDT 2020 | Thu Aug 13 00:00:00 IDT 2020 |  | COMPLETED
1641 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Wed Aug 26 17:00:00 IDT 2020 | Fri Jul 31 00:00:00 IDT 2020 | Fri Aug 14 00:00:00 IDT 2020 |  | COMPLETED
1642 | TT_TASK | Downspouts & Gutters | Sat Sep 05 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 |  | COMPLETED
1647 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Wed Jul 08 07:00:00 IDT 2020 | Mon Jul 20 17:00:00 IDT 2020 | Wed Jun 24 00:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 |  | COMPLETED
1648 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jun 22 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Tue Jun 16 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1650 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 |  | COMPLETED
1651 | TT_TASK | Secondary Steel | Mon Aug 31 07:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 |  | COMPLETED
1652 | TT_TASK | Erect Interior Structural Steel | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1654 | TT_TASK | MEP Undeground Rough-In (Interior) | Mon Oct 19 07:00:00 IDT 2020 | Thu Nov 05 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1655 | TT_TASK | Aggregate Base Course | Fri Nov 06 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1656 | TT_TASK | Slab on Grade | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
1658 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Sep 08 07:00:00 IDT 2020 | Tue Sep 22 17:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1659 | TT_TASK | Roof Panels Installation | Tue Sep 08 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 | Tue Sep 01 00:00:00 IDT 2020 |  | COMPLETED
1660 | TT_TASK | Downspouts & Gutters | Wed Sep 16 07:00:00 IDT 2020 | Tue Sep 22 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
1670 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jul 06 07:00:00 IDT 2020 | Thu Jul 23 17:00:00 IDT 2020 | Tue Jun 23 00:00:00 IDT 2020 | Thu Jul 30 00:00:00 IDT 2020 |  | COMPLETED
1671 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Sat Aug 29 07:00:00 IDT 2020 | Thu Sep 10 17:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 |  | COMPLETED
1673 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Sat Aug 08 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
1674 | TT_TASK | Secondary Steel | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 08 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1675 | TT_TASK | Erect Interior Structural Steel | Mon Dec 21 07:00:00 IST 2020 | Tue Dec 29 17:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
1677 | TT_TASK | MEP Undeground Rough-In (Interior) | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1678 | TT_TASK | Aggregate Base Course | Wed Nov 11 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
1679 | TT_TASK | Slab on Grade | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1681 | TT_TASK | Exterior Insulated Metal Panels Installation | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Sep 30 00:00:00 IDT 2020 |  | COMPLETED
1682 | TT_TASK | Roof Panels Installation | Thu Sep 03 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Thu Aug 27 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1683 | TT_TASK | Downspouts & Gutters | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Sep 07 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1693 | TT_TASK | Hang Wall Partitions | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1694 | TT_TASK | Hang Wall Partitions- Early Walls | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1695 | TT_TASK | MEP Rough-In / Wall & Ceiling | Mon Oct 19 07:00:00 IDT 2020 | Mon Nov 02 17:00:00 IST 2020 | Thu Oct 01 00:00:00 IDT 2020 | Tue Nov 17 00:00:00 IST 2020 |  | COMPLETED
1697 | TT_TASK | Early Room - Finishes | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1699 | TT_TASK | Loading Dock Equipment & Dock Doors | Wed May 05 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
1700 | TT_TASK | MEP Overhead | Mon Oct 19 07:00:00 IDT 2020 | Tue Nov 17 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1701 | TT_TASK | Ceilings / Ligthing / FA Devices | Mon Mar 01 07:00:00 IST 2021 | Tue Apr 13 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
1702 | TT_TASK | Concrete Floor Sealing/Epoxy | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1706 | TT_TASK | Generator Term | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
1707 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 | Fri Sep 25 00:00:00 IDT 2020 |  | COMPLETED
1708 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Fri Sep 18 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
1709 | TT_TASK | Set Exterior Electrical OFCI Equipment | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1710 | TT_TASK | Admin -Electrical Underground Rough-In | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 31 17:00:00 IDT 2020 | Fri Aug 07 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
1711 | TT_TASK | Generator & Utility Power Pull-Test | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1712 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Jan 18 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1713 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1715 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Oct 19 07:00:00 IDT 2020 | Mon Nov 02 17:00:00 IST 2020 | Fri Oct 09 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1716 | TT_TASK | Set Exterior Mechanical CFCI Equipment (remaning mini splits) | Fri Nov 06 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1717 | TT_TASK | Mechanical Underground Rough-In | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 31 17:00:00 IDT 2020 | Sat Aug 08 00:00:00 IDT 2020 | Tue Aug 25 00:00:00 IDT 2020 |  | COMPLETED
1718 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1721 | TT_TASK | Fire Alarm Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1722 | TT_TASK | Controls Installation | Tue Feb 16 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
1724 | TT_TASK | Set Electrical Equipment incl. OH raceways | Mon Nov 23 07:00:00 IST 2020 | Wed Jan 13 17:00:00 IST 2021 | Mon Nov 16 00:00:00 IST 2020 | Tue Dec 29 00:00:00 IST 2020 |  | COMPLETED
1725 | TT_TASK | Electrical Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1727 | TT_TASK | Domestic Water Piping | Mon Nov 23 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1728 | TT_TASK | Plumbing Devices & Trim | Mon Jul 26 15:00:00 IDT 2021 | Tue Aug 17 15:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
1730 | TT_TASK | Security Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
1732 | TT_TASK | Mechanical Ductwork Installation | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1733 | TT_TASK | Set Mechanical Equipment | Mon Nov 23 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
1734 | TT_TASK | Mechanical Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1739 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1740 | TT_TASK | Overhead MEPFP Rough-In | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 11 17:00:00 IST 2020 | Wed Oct 14 00:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
1741 | TT_TASK | Early Topout | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1743 | TT_TASK | Sprinkler Test | Mon Dec 21 07:00:00 IST 2020 | Tue Dec 22 17:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1744 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1747 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1748 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1749 | TT_TASK | Early Topout | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Tue Nov 10 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1751 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Nov 30 07:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1754 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 |  | COMPLETED
1755 | TT_TASK | Overhead MEPFP Rough-In | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 11 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 |  | COMPLETED
1756 | TT_TASK | Early Topout | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1758 | TT_TASK | Datahall Finishes- Ceiling Grid | Thu Dec 03 07:00:00 IST 2020 | Tue Dec 15 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1761 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1762 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1763 | TT_TASK | Early Topout | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Tue Nov 10 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1765 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1768 | TT_TASK | Remaining MER raceway across Mech chase | Tue Dec 01 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1769 | TT_TASK | Electrical OH Below Mechanical Piping | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1770 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1771 | TT_TASK | OverHead MEPFP Rough-In ( Add TCM Cross over piping HRA Level-3) | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1772 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1774 | TT_TASK | Mechanical Corridor Finishes | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1777 | TT_TASK | Remaining MER raceway across Mech chase | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1778 | TT_TASK | Electrical OH Below Mechanical Piping | Wed Jan 20 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1779 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 11 00:00:00 IST 2020 |  | COMPLETED
1780 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1781 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1783 | TT_TASK | Mechanical Corridor Finishes | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1786 | TT_TASK | Remaining MER raceway across Mech chase | Tue Dec 01 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1787 | TT_TASK | Electrical OH Below Mechanical Piping | Mon Jan 04 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1788 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1789 | TT_TASK | OverHead MEPFP Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1790 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1792 | TT_TASK | Mechanical Corridor Finishes | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1795 | TT_TASK | Remaining MER raceway across Mech chase | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1796 | TT_TASK | Electrical OH Below Mechanical Piping | Wed Jan 20 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1797 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 11 00:00:00 IST 2020 |  | COMPLETED
1798 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1799 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1801 | TT_TASK | Mechanical Corridor Finishes | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Tue Nov 17 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1805 | TT_TASK | Generator & Utility Power Term | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1806 | TT_TASK | Remaining Mechanical Equipment (ADP01) Termimations | Thu Mar 18 07:00:00 IST 2021 | Tue Mar 23 17:00:00 IST 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1807 | TT_TASK | Electrical Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 14 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1808 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1809 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1810 | TT_TASK | Exterior Equipment Pads - Electrical | Thu Sep 03 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1811 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Oct 12 07:00:00 IDT 2020 | Mon Oct 26 17:00:00 IST 2020 | Mon Oct 12 07:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1812 | TT_TASK | Lift & Set MER in Place | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Wed Dec 16 00:00:00 IST 2020 | Wed Dec 16 17:00:00 IST 2020 |  | COMPLETED
1813 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
1814 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 13 17:00:00 IST 2021 | Thu Dec 17 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1815 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Jan 11 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Tue Jan 05 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1816 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1817 | TT_TASK | Generator & Utility Power Pull | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1819 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1820 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1821 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1822 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1823 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Sat Dec 05 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1824 | TT_TASK | Mechanical Equipment Piping Connections | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1825 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
1828 | TT_TASK | Fire Alarm Installation | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1829 | TT_TASK | Controls Installation | Fri Mar 05 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1832 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 22 07:00:00 IST 2021 | Tue Mar 30 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1833 | TT_TASK | Electrical Underground Rough-In | Thu Sep 03 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1834 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1835 | TT_TASK | Set Electrical Equipment-UPM Cell -3 | Fri Dec 11 07:00:00 IST 2020 | Tue Dec 15 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1836 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
1837 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1838 | TT_TASK | Lift & Set MER in Place | Mon Jan 11 08:00:00 IST 2021 | Mon Jan 18 08:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1839 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 18 08:00:00 IST 2021 | Fri Jan 22 08:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1840 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
1841 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1842 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
1843 | TT_TASK | Generator & Utility Power Pull | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1845 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1846 | TT_TASK | Exterior Equipment Pads - Mechanical | Fri Oct 16 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Sat Sep 19 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
1847 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1848 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1849 | TT_TASK | Set Exterior Water Treatment equipment | Mon Dec 07 07:00:00 IST 2020 | Tue Dec 08 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1850 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1851 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 15 07:00:00 IST 2021 | Mon Mar 22 17:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
1854 | TT_TASK | Fire Alarm Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1855 | TT_TASK | Controls Installation | Tue Mar 09 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1858 | TT_TASK | Generator & Utility Power Pull | Tue Feb 02 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Feb 26 07:00:00 IST 2021 |  | COMPLETED
1859 | TT_TASK | Remaining Mechanical Equipment (ADP01) Termimations | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1860 | TT_TASK | Electrical Underground Rough-In | Fri Aug 14 07:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1861 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 05 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1862 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1863 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Sep 05 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Fri Oct 02 00:00:00 IDT 2020 |  | COMPLETED
1864 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Oct 26 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1865 | TT_TASK | Lift & Set MER in Place | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
1866 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 11 08:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1867 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1868 | TT_TASK | GEN & UPM to MER Cable Bus Install | Wed Jan 20 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1869 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1870 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1872 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1873 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Oct 05 07:00:00 IDT 2020 | Sat Oct 17 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
1874 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1875 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1876 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1877 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1878 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 08 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1881 | TT_TASK | Fire Alarm Installation | Thu Feb 18 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1882 | TT_TASK | Controls Installation | Sat Mar 06 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
1885 | TT_TASK | Generator & Utility Power Pull | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1886 | TT_TASK | Electrical Underground Rough-In | Sat Sep 05 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1887 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1888 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1889 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1890 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1891 | TT_TASK | Lift & Set MER in Place | Mon Jan 11 08:00:00 IST 2021 | Mon Jan 18 08:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1892 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 11 08:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Jan 11 08:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1893 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1894 | TT_TASK | GEN & UPM to MER Cable Bus Install | Thu Feb 04 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1895 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Wed Apr 07 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
1896 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 15 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
1898 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Sep 14 07:00:00 IDT 2020 | Sat Sep 26 17:00:00 IDT 2020 | Mon Sep 14 07:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1899 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1900 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1901 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1902 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1903 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1904 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
1907 | TT_TASK | Fire Alarm Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1908 | TT_TASK | Controls Installation | Thu Apr 15 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1911 | TT_TASK | VFD'S Installation & wirepull | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1912 | TT_TASK | Ligthing Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 |  | COMPLETED
1914 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Thu Nov 26 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
1915 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1917 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1919 | TT_TASK | Fire Riser Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1920 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1921 | TT_TASK | Controls Installation | Fri Mar 26 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1924 | TT_TASK | VFD'S Installation & Wiring | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
1925 | TT_TASK | Ligthing Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1927 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
1928 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1930 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1932 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1933 | TT_TASK | Controls Installation | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1936 | TT_TASK | VFD'S Installation & Wiring | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1937 | TT_TASK | Ligthing Installation | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1939 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
1940 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1942 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1944 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1945 | TT_TASK | Controls Installation | Tue Apr 13 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1948 | TT_TASK | VFD'S Installation & Wiring | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
1949 | TT_TASK | Ligthing Installation | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jul 29 00:00:00 IDT 2021 |  | COMPLETED
1951 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
1952 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1954 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1956 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1957 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1961 | TT_TASK | HAC Installation | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
1962 | TT_TASK | Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1963 | TT_TASK | Power Bus Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1964 | TT_TASK | PDU's Installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1965 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Apr 05 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1966 | TT_TASK | Light Fixtures Installation | Wed May 05 07:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
1967 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
1969 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
1970 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1971 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1972 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1974 | TT_TASK | Security Devices & Trim | Mon May 17 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
1975 | TT_TASK | Controls Installation | Fri Mar 26 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1976 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1979 | TT_TASK | HAC Installation | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1980 | TT_TASK | Cable Tray Installation | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
1981 | TT_TASK | Power Bus Installation | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1982 | TT_TASK | PDU's Installation | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
1983 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Apr 26 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1984 | TT_TASK | Light Fixtures Installation | Wed May 12 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1985 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Apr 26 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
1987 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
1988 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1989 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1990 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Thu Jul 01 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1992 | TT_TASK | Security Devices & Trim | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
1993 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1994 | TT_TASK | Fire Alarm System | Tue May 04 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1997 | TT_TASK | HAC Installation | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1998 | TT_TASK | Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1999 | TT_TASK | Power Bus Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
2000 | TT_TASK | PDU's Installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
2001 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Apr 01 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2002 | TT_TASK | Light Fixtures Installation | Tue May 11 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
2003 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 23 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
2005 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2006 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2007 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2008 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed May 19 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2010 | TT_TASK | Security Devices & Trim | Mon May 17 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2011 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2012 | TT_TASK | Fire Alarm System | Thu May 06 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2015 | TT_TASK | HAC Installation | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2016 | TT_TASK | Cable Tray Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2017 | TT_TASK | Power Bus Installation | Fri Mar 12 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2018 | TT_TASK | PDU's Installation | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2019 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon May 03 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
2020 | TT_TASK | Light Fixtures Installation | Fri May 21 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2021 | TT_TASK | Pull/term/Test PDU to Power bus | Mon May 03 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2023 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2024 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2025 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2026 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed May 19 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2028 | TT_TASK | Security Devices & Trim | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 |  | COMPLETED
2029 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2030 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2036 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2037 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
2038 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2040 | TT_TASK | Datahall Finishes - Ceiling Grid | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2043 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2044 | TT_TASK | Overhead MEPFP Rough-In | Fri Nov 06 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2045 | TT_TASK | Hang drywall / Mud / Tape | Wed Jan 06 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2047 | TT_TASK | Datahall Finishes - Ceiling Grid | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2050 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2051 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
2052 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2054 | TT_TASK | Datahall Finishes - Ceiling Grid | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2057 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2058 | TT_TASK | Overhead MEPFP Rough-In | Fri Nov 06 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2059 | TT_TASK | Hang drywall / Mud / Tape | Wed Jan 06 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2061 | TT_TASK | Datahall Finishes - Ceiling Grid | Mon Jan 11 07:00:00 IST 2021 | Wed Jan 20 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2064 | TT_TASK | Remaining Post MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2065 | TT_TASK | Frame & Top out | Mon Nov 23 07:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2066 | TT_TASK | OverHead MEPFP Rough-In | Thu Nov 19 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2067 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Dec 12 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2069 | TT_TASK | Mechanical Corridor Finishes | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2072 | TT_TASK | Remaining MER raceway across Mech chase | Thu Mar 25 07:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2073 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2074 | TT_TASK | OverHead MEPFP Rough-In | Tue Dec 08 07:00:00 IST 2020 | Mon Dec 21 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2075 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Dec 14 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2077 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2080 | TT_TASK | Remaining MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 |  | COMPLETED
2081 | TT_TASK | Frame & Top out | Mon Nov 30 07:00:00 IST 2020 | Wed Dec 09 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2082 | TT_TASK | OverHead MEPFP Rough-In | Sat Dec 19 07:00:00 IST 2020 | Thu Jan 07 17:00:00 IST 2021 | Mon Oct 26 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2083 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Dec 12 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2085 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2088 | TT_TASK | Remaining MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Mar 12 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2089 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2090 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2091 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 30 07:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
2093 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2097 | TT_TASK | Generator & Utility Power Pull | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
2098 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
2099 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2100 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
2101 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Dec 14 07:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 |  | COMPLETED
2102 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Tue Dec 29 00:00:00 IST 2020 |  | COMPLETED
2103 | TT_TASK | Lift & Set MER in Place | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2104 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 |  | COMPLETED
2105 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
2106 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Mar 22 07:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Fri Mar 05 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
2107 | TT_TASK | Generator & Utility Power Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2108 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2110 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
2111 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 08 17:00:00 IST 2021 | Mon Nov 02 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
2112 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2113 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2114 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2115 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2116 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2119 | TT_TASK | Fire Alarm Installation | Tue May 11 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2120 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2123 | TT_TASK | Generator & Utility Power Pull | Tue May 11 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
2124 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 21 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2125 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2126 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Wed Dec 16 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2127 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Dec 14 07:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2128 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2129 | TT_TASK | Lift & Set MER in Place | Tue Mar 23 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
2130 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Mar 29 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2131 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Mar 29 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2132 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Fri Apr 16 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
2133 | TT_TASK | Generator & Utility Power Test-Term | Thu May 06 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2134 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
2136 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2137 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 08 17:00:00 IST 2021 | Mon Nov 16 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2138 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2139 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2140 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2141 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2142 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
2145 | TT_TASK | Fire Alarm Installation | Wed May 26 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2146 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2149 | TT_TASK | Generator & Utility Power Pull | Fri Mar 26 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
2150 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2151 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
2152 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Wed Nov 04 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2153 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Tue Nov 03 00:00:00 IST 2020 |  | COMPLETED
2154 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
2155 | TT_TASK | Lift & Set MER in Place | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2156 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Mar 27 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2157 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Mar 27 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2158 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Thu Mar 25 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
2159 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2160 | TT_TASK | Generator & Utility Power Test-Term | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Tue Apr 06 07:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2162 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2163 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2164 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2165 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2166 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Fri Jan 15 07:00:00 IST 2021 | Fri Jan 29 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2167 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
2168 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
2171 | TT_TASK | Fire Alarm Installation | Tue May 11 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2172 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2175 | TT_TASK | Generator & Utility Power Pull | Thu May 13 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2176 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2177 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2178 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2179 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2180 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
2181 | TT_TASK | Lift & Set MER in Place | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
2182 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Mar 27 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2183 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Mar 27 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
2184 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Thu Apr 15 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
2185 | TT_TASK | Generator & Utility Power Test-Term | Tue May 18 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2186 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2188 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2189 | TT_TASK | Set Gen Stack / Exhaust duct | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2192 | TT_TASK | Fire Alarm Installation | Wed May 12 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2193 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2196 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 |  | COMPLETED
2197 | TT_TASK | Ligthing Installation | Fri Jul 23 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2199 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2200 | TT_TASK | Hydronic Piping Installation | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2202 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2203 | TT_TASK | Toilet Piping Installation / DW | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2205 | TT_TASK | Fire Riser Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2206 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2207 | TT_TASK | Controls Installation | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue Jun 08 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2210 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2211 | TT_TASK | Ligthing Installation | Sat Aug 07 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2213 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
2214 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2216 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2217 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2219 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2220 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
2223 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2224 | TT_TASK | Ligthing Installation | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2226 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
2227 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2229 | TT_TASK | Toilet Piping Installation / DW | Mon May 03 07:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2230 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2232 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2233 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri Jul 09 08:12:00 IDT 2021 |  | COMPLETED
2236 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2237 | TT_TASK | Ligthing Installation | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2239 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
2240 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2242 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2243 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2245 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2246 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2249 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2250 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2251 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
2252 | TT_TASK | Power Bus Installation | Fri Mar 26 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2253 | TT_TASK | PDU's Installation | Fri Mar 26 07:00:00 IDT 2021 | Mon Mar 29 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
2254 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2255 | TT_TASK | Light Fixtures Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2256 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 23 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
2258 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Jun 10 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2259 | TT_TASK | BMS Pull Wire / Term / Test | Thu Jun 10 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2260 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Jul 23 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2262 | TT_TASK | Fire Alarm System | Tue May 04 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2263 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2266 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2267 | TT_TASK | HAC Installation | Wed Feb 03 07:00:00 IST 2021 | Wed Feb 17 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Wed Feb 03 00:00:00 IST 2021 |  | COMPLETED
2268 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
2269 | TT_TASK | Power Bus Installation | Mon Mar 22 07:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2270 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2271 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Tue Jun 08 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2272 | TT_TASK | Light Fixtures Installation | Wed Jun 23 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
2273 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2275 | TT_TASK | EPMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 |  | COMPLETED
2276 | TT_TASK | BMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 |  | COMPLETED
2277 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon Aug 09 07:00:00 IDT 2021 | Wed Sep 01 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2279 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2280 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2283 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2284 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2285 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
2286 | TT_TASK | Power Bus Installation | Fri Mar 26 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2287 | TT_TASK | PDU's Installation | Mon Mar 22 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2288 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2289 | TT_TASK | Light Fixtures Installation | Fri Jun 18 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Jun 18 07:00:00 IDT 2021 | Thu Jul 01 00:00:00 IDT 2021 |  | COMPLETED
2290 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 02 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
2292 | TT_TASK | EPMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2293 | TT_TASK | BMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2294 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Jul 30 07:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2296 | TT_TASK | Fire Alarm System | Mon May 10 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon May 10 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 |  | COMPLETED
2297 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2300 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Thu Apr 22 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2301 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
2302 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2303 | TT_TASK | Power Bus Installation | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2304 | TT_TASK | PDU's Installation | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2305 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Jun 09 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2306 | TT_TASK | Light Fixtures Installation | Wed Jun 23 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2307 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2309 | TT_TASK | EPMS Pull Wire / Term / Test | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2310 | TT_TASK | BMS Pull Wire / Term / Test | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2311 | TT_TASK | ` | Tue Aug 24 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2313 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2314 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2319 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2320 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
2321 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2323 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2326 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
2327 | TT_TASK | Overhead MEPFP Rough-In | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 |  | COMPLETED
2328 | TT_TASK | Hang drywall / Mud / Tape | Thu Jan 14 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2330 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2333 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2334 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2335 | TT_TASK | Hang drywall / Mud / Tape | Fri Jan 08 07:00:00 IST 2021 | Mon Jan 18 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2337 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2340 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
2341 | TT_TASK | Overhead MEPFP Rough-In | Fri Jan 15 07:00:00 IST 2021 | Wed Jan 27 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2342 | TT_TASK | Hang drywall / Mud / Tape | Thu Jan 14 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2344 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2347 | TT_TASK | Remaining MER raceway across Mech chase | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2348 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
2349 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2350 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Thu Jan 21 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Thu Jan 21 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 |  | COMPLETED
2352 | TT_TASK | Mechanical Corridor Finishes | Fri Mar 05 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2355 | TT_TASK | Remaining MER raceway across Mech chase | Thu Jun 17 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2356 | TT_TASK | Frame & Top out | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2357 | TT_TASK | OverHead MEPFP Rough-In | Wed Jan 13 07:00:00 IST 2021 | Wed Jan 27 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2358 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
2360 | TT_TASK | Mechanical Corridor Finishes | Wed Feb 03 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2363 | TT_TASK | Remaining MER raceway across Mech chase | Mon May 03 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2364 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
2365 | TT_TASK | OverHead MEPFP Rough-In | Tue Jan 12 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2366 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2368 | TT_TASK | Mechanical Corridor Finishes | Tue Feb 02 07:00:00 IST 2021 | Tue Feb 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2371 | TT_TASK | Remaining MER raceway across Mech chase | Thu Jun 17 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
2372 | TT_TASK | Frame & Top out | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2373 | TT_TASK | OverHead MEPFP Rough-In | Fri Jan 08 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2374 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2376 | TT_TASK | Mechanical Corridor Finishes | Tue Feb 23 07:00:00 IST 2021 | Tue Mar 16 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2380 | TT_TASK | Generator & Utility Power Pull | Wed May 19 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2381 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
2382 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2383 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 29 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
2384 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 07:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
2385 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2386 | TT_TASK | Lift & Set MER in Place | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
2387 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
2388 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon May 03 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2389 | TT_TASK | GEN & UPM to MER Cable Bus Install | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2390 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2391 | TT_TASK | Generator & Utility Power Test-Term | Wed Jun 02 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
2393 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
2394 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2395 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
2396 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2397 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2398 | TT_TASK | Set Exterior Water Treatment equipment | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 01 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2399 | TT_TASK | Mechanical Equipment Piping Connections | Fri Apr 30 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2402 | TT_TASK | Fire Alarm Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2403 | TT_TASK | Controls Installation | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2406 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2407 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
2408 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2409 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2410 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 02 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2411 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 15 08:00:00 IST 2021 | Mon Mar 22 08:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2412 | TT_TASK | Lift & Set MER in Place | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2413 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2414 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Fri May 07 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2415 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2416 | TT_TASK | Generator & Utility Power Test-Term | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2417 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Jun 08 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Tue Jun 08 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2419 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
2420 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
2423 | TT_TASK | Fire Alarm Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 15 07:00:00 IDT 2021 |  | COMPLETED
2424 | TT_TASK | Controls Installation | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 29 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2427 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2428 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2429 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2430 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 08:00:00 IST 2021 | Tue Jan 12 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2431 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Fri Nov 27 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2432 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
2433 | TT_TASK | Lift & Set MER in Place | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
2434 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2435 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon May 03 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
2436 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Mon May 17 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 |  | COMPLETED
2437 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Thu Jun 10 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2438 | TT_TASK | Generator & Utility Power Test-Term | Thu Jun 03 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
2440 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2441 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2442 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2443 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Apr 26 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2444 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 |  | COMPLETED
2445 | TT_TASK | Set Exterior Water Treatment equipment | Mon Apr 26 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2446 | TT_TASK | Mechanical Equipment Piping Connections | Mon May 03 07:00:00 IDT 2021 | Sat May 08 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2449 | TT_TASK | Fire Alarm Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2450 | TT_TASK | Controls Installation | Fri Jun 25 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2453 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2454 | TT_TASK | Electrical Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2455 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Fri Dec 04 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2456 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2457 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 02 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2458 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
2459 | TT_TASK | Lift & Set MER in Place | Fri May 07 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2460 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2461 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2462 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2463 | TT_TASK | Generator & Utility Power Test-Term | Tue Jul 06 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 | Thu Jul 15 12:00:00 IDT 2021 |  | COMPLETED
2464 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2466 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Fri Dec 04 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2467 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2468 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2469 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2470 | TT_TASK | Set Exterior Water Treatment equipment | Fri Apr 30 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2471 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
2472 | TT_TASK | Mechanical Equipment Piping Connections | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2475 | TT_TASK | Fire Alarm Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jul 07 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2476 | TT_TASK | Controls Installation | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
2479 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2480 | TT_TASK | Ligthing Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2482 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
2483 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2485 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 00:00:00 IDT 2021 |  | COMPLETED
2486 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2488 | TT_TASK | Fire Riser Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2489 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2490 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2493 | TT_TASK | VFD'S Installation & Wiring | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2494 | TT_TASK | Ligthing Installation | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
2496 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
2497 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2499 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2500 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2502 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2503 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2506 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2507 | TT_TASK | Ligthing Installation | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
2509 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
2510 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2512 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2513 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2515 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2516 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
2519 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
2520 | TT_TASK | Ligthing Installation | Mon Aug 30 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2522 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
2523 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2525 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2526 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2528 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2529 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2532 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 |  | COMPLETED
2533 | TT_TASK | HAC Installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2534 | TT_TASK | Cable Tray Installation | Sat Apr 03 07:00:00 IDT 2021 | Sat Apr 17 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
2535 | TT_TASK | Power Bus Installation | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2536 | TT_TASK | PDU's Installation | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2537 | TT_TASK | Pull/term/Test PDU to Power bus | Sat Jun 19 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2538 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2539 | TT_TASK | Light Fixtures Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
2541 | TT_TASK | EPMS Pull Wire / Term / Test | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2542 | TT_TASK | BMS Pull Wire / Term / Test | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2543 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Aug 20 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Jul 07 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2545 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2546 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
2549 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2550 | TT_TASK | HAC Installation | Wed Apr 07 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2551 | TT_TASK | Cable Tray Installation | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2552 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
2553 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
2554 | TT_TASK | Pull/term/Test PDU to Power bus | Fri Jul 02 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
2555 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Aug 16 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Thu Jul 08 00:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2556 | TT_TASK | Light Fixtures Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2558 | TT_TASK | EPMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2559 | TT_TASK | BMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2560 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2562 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2563 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2566 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 |  | COMPLETED
2567 | TT_TASK | HAC Installation | Sat Apr 03 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2568 | TT_TASK | Cable Tray Installation | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2569 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 |  | COMPLETED
2570 | TT_TASK | PDU's Installation | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2571 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Sat Jul 24 00:00:00 IDT 2021 |  | COMPLETED
2572 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 23 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2573 | TT_TASK | Light Fixtures Installation | Wed Jul 21 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2575 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2576 | TT_TASK | BMS Pull Wire / Term / Test | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2577 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Aug 20 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2579 | TT_TASK | Fire Alarm System | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2580 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2583 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2584 | TT_TASK | HAC Installation | Mon Apr 12 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2585 | TT_TASK | Cable Tray Installation | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2586 | TT_TASK | Power Bus Installation | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
2587 | TT_TASK | PDU's Installation | Mon Jun 14 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
2588 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
2589 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2590 | TT_TASK | Light Fixtures Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2592 | TT_TASK | EPMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2593 | TT_TASK | BMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2594 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed Sep 15 07:00:00 IDT 2021 | Fri Oct 08 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2596 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2597 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2602 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2603 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2604 | TT_TASK | Early Topout | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2606 | TT_TASK | Datahall Finishes | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
2609 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Jan 18 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2610 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2611 | TT_TASK | Early Topout | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
2613 | TT_TASK | Datahall Finishes | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2616 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2617 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2618 | TT_TASK | Early Topout | Tue Feb 09 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2620 | TT_TASK | Datahall Finishes | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
2623 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Jan 18 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2624 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2625 | TT_TASK | Early Topout | Mon Feb 08 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2627 | TT_TASK | Datahall Finishes | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2630 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2631 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2632 | TT_TASK | OverHead MEPFP Rough-In | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
2633 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 15 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
2635 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Sat Jan 09 00:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 |  | COMPLETED
2638 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2639 | TT_TASK | Frame & Top out | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Sat Jan 09 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
2640 | TT_TASK | OverHead MEPFP Rough-In | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2641 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Tue Mar 30 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2643 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 29 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Thu Jan 21 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
2646 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 |  | COMPLETED
2647 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
2648 | TT_TASK | OverHead MEPFP Rough-In | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Feb 05 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2649 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 15 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2651 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
2654 | TT_TASK | Remaining MER raceway across Mech chase | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
2655 | TT_TASK | Frame & Top out | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
2656 | TT_TASK | OverHead MEPFP Rough-In | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2657 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Tue Mar 30 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Fri Feb 12 00:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
2659 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 29 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2663 | TT_TASK | Generator & Utility Power Pull | Wed Jul 28 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2664 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2665 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2666 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Wed Dec 30 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2667 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2668 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Apr 26 08:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2669 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
2670 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2671 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2672 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 |  | COMPLETED
2673 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2674 | TT_TASK | Generator & Utility Power Test-Term | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
2676 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2677 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2678 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2679 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2680 | TT_TASK | Set Exterior Water Treatment equipment | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 01 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2681 | TT_TASK | Mechanical Equipment Piping Connections | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2682 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2685 | TT_TASK | Fire Alarm Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
2686 | TT_TASK | Controls Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2689 | TT_TASK | Generator & Utility Power Pull | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 19 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2690 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2691 | TT_TASK | Exterior Equipment Pads - for UPM's | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2692 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2693 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2694 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Apr 26 08:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2695 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2696 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2697 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
2698 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jul 10 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2699 | TT_TASK | Generator & Utility Power Test-Term | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Sat Aug 07 17:00:00 IDT 2021 |  | COMPLETED
2700 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2702 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2703 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2704 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2705 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2706 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2707 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2708 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2711 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
2712 | TT_TASK | Controls Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
2715 | TT_TASK | Generator & Utility Power Pull | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 | Thu Aug 05 09:30:00 IDT 2021 |  | COMPLETED
2716 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2717 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2718 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2719 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2720 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2721 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2722 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2723 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2724 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jul 15 00:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2725 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2726 | TT_TASK | Generator & Utility Power Test-Term | Fri Sep 03 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
2728 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 09 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2729 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2730 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2731 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2732 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2733 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2734 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
2737 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2738 | TT_TASK | Controls Installation | Wed Sep 01 07:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Thu Aug 26 07:00:00 IDT 2021 |  | 1210.0 | IN_PROGRESS
2741 | TT_TASK | Generator & Utility Power Pull | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Thu Jul 29 00:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
2742 | TT_TASK | Electrical Underground Rough-In | Sat Nov 07 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2743 | TT_TASK | Exterior Equipment Pads - for UPM's | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2744 | TT_TASK | Set Electrical Equipment-UPM | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2745 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Jan 18 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2746 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2747 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2748 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2749 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
2750 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2751 | TT_TASK | Generator & Utility Power Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2752 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2754 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2755 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2756 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2757 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2758 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2759 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2760 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2763 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
2764 | TT_TASK | Controls Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
2767 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2768 | TT_TASK | Ligthing Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2770 | TT_TASK | AHU/DOAS Equipment Setting | Sat May 15 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2771 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2773 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2774 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2776 | TT_TASK | Fire Riser Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed May 19 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2777 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2778 | TT_TASK | Controls Installation | Sat Jul 31 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2781 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
2782 | TT_TASK | Ligthing Installation | Thu Sep 16 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
2784 | TT_TASK | AHU/DOAS Equipment Setting | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2785 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2787 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2788 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2790 | TT_TASK | Fire Alarm System | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2791 | TT_TASK | Controls Installation | Mon Aug 23 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2794 | TT_TASK | VFD'S Installation & Wiring | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2795 | TT_TASK | Lighting Installation | Sat Sep 11 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
2797 | TT_TASK | AHU/DOAS Equipment Setting | Sat May 15 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2798 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2800 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2801 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2803 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2804 | TT_TASK | Controls Installation | Mon Aug 16 07:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 |  | COMPLETED
2807 | TT_TASK | VFD'S Installation & Wiring | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2808 | TT_TASK | Ligthing Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
2810 | TT_TASK | AHU/DOAS Equipment Setting | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2811 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2813 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2814 | TT_TASK | Toilet Piping Installation / DW | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
2816 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2817 | TT_TASK | Controls Installation | Wed Sep 08 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2820 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 09 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2821 | TT_TASK | HAC Installation | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2822 | TT_TASK | Cable Tray Installation | Tue May 04 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2823 | TT_TASK | Power Bus Installation | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2824 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2825 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 27 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2826 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Aug 25 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2827 | TT_TASK | Light Fixtures Installation | Sat Aug 21 07:00:00 IDT 2021 | Fri Aug 27 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
2829 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2830 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
2831 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon Sep 27 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2833 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2834 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2837 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 16 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2838 | TT_TASK | HAC Installation | Thu Apr 29 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2839 | TT_TASK | Cable Tray Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2840 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 |  | COMPLETED
2841 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2842 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Fri Sep 03 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2843 | TT_TASK | Pull/term/Test PDU to Power bus | Fri Sep 03 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  | 210.0 | NOT_STARTED
2844 | TT_TASK | Light Fixtures Installation | Fri Oct 01 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2846 | TT_TASK | EPMS Pull Wire / Term / Test | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2847 | TT_TASK | BMS Pull Wire / Term / Test | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
2848 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Thu Oct 21 07:00:00 IDT 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  | 801.0 | NOT_STARTED
2850 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2851 | TT_TASK | Controls Installation | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2854 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 16 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2855 | TT_TASK | HAC Installation | Thu Apr 29 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2856 | TT_TASK | Cable Tray Installation | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2857 | TT_TASK | Power Bus Installation | Mon Jun 14 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2858 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2859 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Sep 01 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2860 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Aug 25 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2861 | TT_TASK | Light Fixtures Installation | Mon Aug 30 07:00:00 IDT 2021 | Tue Sep 07 08:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  | 89.0 | IN_PROGRESS
2863 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2864 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 170.0 | NOT_STARTED
2865 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Sat Oct 09 07:00:00 IDT 2021 | Tue Nov 02 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2867 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2868 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2871 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 23 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2872 | TT_TASK | HAC Installation | Fri May 07 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2873 | TT_TASK | Cable Tray Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2874 | TT_TASK | Power Bus Installation | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Thu Jun 24 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2875 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed Jul 14 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2876 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Sep 01 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 25 00:00:00 IDT 2021 |  |  | IN_PROGRESS
2877 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 22 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2878 | TT_TASK | Light Fixtures Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2880 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2881 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 300.0 | NOT_STARTED
2882 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed Nov 03 07:00:00 IST 2021 | Tue Nov 30 17:00:00 IST 2021 |  |  | 691.0 | NOT_STARTED
2884 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2885 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jul 27 00:00:00 IDT 2021 | Tue Aug 24 13:00:00 IDT 2021 |  | COMPLETED
2889 | TT_TASK | ATS Equipment Yellow Tagging (S2 from MER) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2890 | TT_TASK | Control Power Available | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Fri Apr 30 07:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
2891 | TT_TASK | Power available for Start up | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2892 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2893 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 |  | COMPLETED
2895 | TT_TASK | Admin - NETA test validation Inpections- VECA-EPS-RTS Admin | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Mar 11 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
2896 | TT_TASK | Electrical Equipment Yellow Tagging | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2897 | TT_TASK | Admin/Colo-1 Network Startup | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2898 | TT_TASK | EPMS Checkout / Point to Point | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2902 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2903 | TT_TASK | UPM Yellow tagging - Admin & COLO-1 CELL-1 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2904 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
2905 | TT_TASK | SE- Completed L2 QC Checklist | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
2906 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-1 | Sat Apr 17 07:00:00 IDT 2021 | Tue Apr 20 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2907 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2908 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2909 | TT_TASK | Network Startup | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
2910 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2911 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2912 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2914 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2915 | TT_TASK | Power available for Start up | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2916 | TT_TASK | SE- Completed L2 QC Checklist | Mon Jun 14 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
2917 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Jul 13 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2918 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-3 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2919 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-3 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2920 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Thu Jun 10 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2921 | TT_TASK | Network Startup | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 |  | COMPLETED
2922 | TT_TASK | EPMS Checkout / Point to Point | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jul 06 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2923 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2924 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2926 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2927 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2928 | TT_TASK | SE- Completed L2 QC Checklist | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2929 | TT_TASK | Mechanical Equipment Yellow Tag | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 |  | COMPLETED
2930 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-2 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2931 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-2 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2932 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2933 | TT_TASK | Network Startup | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2934 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2935 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2936 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 20 15:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2938 | TT_TASK | Control Power Available | Tue Jun 22 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue Jun 22 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2939 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2940 | TT_TASK | SE- Completed L2 QC Checklist | Mon Jun 14 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
2941 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Jul 02 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2942 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-4 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2943 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-4 | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
2944 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Jul 07 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2945 | TT_TASK | Network Startup | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2946 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2947 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2948 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2950 | TT_TASK | GEN SCR testing and Burnins | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jul 14 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2951 | TT_TASK | Admin GEN SCR testing and Burnins | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2952 | TT_TASK | ATS- Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 |  | 100.0 | IN_PROGRESS
2953 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Tue Jul 13 11:00:00 IDT 2021 | Wed Jul 28 11:00:00 IDT 2021 | Tue Jul 13 11:00:00 IDT 2021 | Wed Jul 28 11:00:00 IDT 2021 |  | COMPLETED
2954 | TT_TASK | Cooling Automation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2955 | TT_TASK | BAS Prefunctional Testing on Construction Server | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Sat Aug 28 00:00:00 IDT 2021 |  | COMPLETED
2956 | TT_TASK | Additional Go-Back loadbanking (ASCO) | Fri Sep 10 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2957 | TT_TASK | Load Bank & IR Scan | Wed Sep 15 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2958 | TT_TASK | Level 3 Cx - ADMIN AND COLO1 | Fri Sep 17 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2959 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Sat Oct 02 07:00:00 IDT 2021 | Sat Oct 02 07:00:00 IDT 2021 |  |  |  | NOT_STARTED
2961 | TT_TASK | COLO 1 Level 4 & Level 5 IST | Sat Oct 02 08:00:00 IDT 2021 | Fri Oct 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2962 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Sat Oct 30 08:00:00 IDT 2021 | Mon Nov 08 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2963 | TT_TASK | Security Commissioning (level3 DCPS) | Tue Nov 09 08:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2964 | TT_TASK | Punch List - Admin/COLO 1 | Sat Oct 30 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2965 | TT_TASK | MST Ready for Network Install | Sat Oct 02 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2966 | TT_TASK | Final Clean/ ready for lock down | Sat Nov 13 07:00:00 IST 2021 | Mon Nov 22 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2970 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 18 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2971 | TT_TASK | Power available for Start up | Sat Sep 11 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2972 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2973 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  | 20.0 | IN_PROGRESS
2974 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-1 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2975 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-1 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2976 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Aug 04 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2977 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2978 | TT_TASK | EPMS Checkout / Point to Point | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 200.0 | NOT_STARTED
2979 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Thu Sep 16 07:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 |  |  | 20.0 | NOT_STARTED
2980 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Thu Sep 16 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  | 50.0 | NOT_STARTED
2982 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2983 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2984 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2985 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2986 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-3 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2987 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-3 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2988 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2989 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2990 | TT_TASK | EPMS Checkout / Point to Point | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
2991 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2992 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2994 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2995 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2996 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2997 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2998 | TT_TASK | UPM Yellow tagging - COLO-2 CELL-2 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2999 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-2 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
3000 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jul 13 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3001 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3002 | TT_TASK | EPMS Checkout / Point to Point | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3003 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3004 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3006 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3007 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3008 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
3009 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3010 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-4 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
3011 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-4 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
3012 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Aug 18 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3013 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3014 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3015 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3016 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  | 30.0 | NOT_STARTED
3018 | TT_TASK | GEN SCR testing and Burnins | Sat Sep 18 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  | 150.0 | NOT_STARTED
3019 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Mon Sep 27 07:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3020 | TT_TASK | Cooling Automation | Mon Oct 11 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3021 | TT_TASK | BAS Prefunctional Testing on Construction Server | Thu Oct 07 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3022 | TT_TASK | Load Bank & IR Scan | Tue Oct 26 07:00:00 IDT 2021 | Tue Nov 16 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3023 | TT_TASK | Level 3 Cx- COLO-2 | Wed Nov 17 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3024 | TT_TASK | Weather (5 Days) - 0 remaining Check Delay #14 for updates | Sat Dec 04 07:00:00 IST 2021 | Sat Dec 04 07:00:00 IST 2021 |  |  |  | NOT_STARTED
3026 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Mon Dec 27 07:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3027 | TT_TASK | Security Commissioning (level3 DCPS) | Tue Jan 11 07:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3028 | TT_TASK | COLO 2 Level 4 & Level 5 IST | Sat Dec 04 08:00:00 IST 2021 | Fri Dec 24 17:00:00 IST 2021 |  |  | 16.0 | NOT_STARTED
3029 | TT_TASK | Punch List COLO-2 | Mon Dec 27 08:00:00 IST 2021 | Sun Jan 09 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3030 | TT_TASK | MST Ready for Network Install | Sat Dec 04 07:00:00 IST 2021 | Thu Dec 09 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3031 | TT_TASK | Final Clean/ ready for lock down | Mon Jan 10 08:00:00 IST 2022 | Fri Jan 21 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3035 | TT_TASK | Control Power Available | Thu Sep 09 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3036 | TT_TASK | Power available for Start up | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3037 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3038 | TT_TASK | Mechanical Equipment Yellow Tag | Wed Sep 22 07:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3039 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-1 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3040 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-1 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3041 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3042 | TT_TASK | Network Startup | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3043 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3044 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3045 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Tue Oct 05 07:00:00 IDT 2021 | Tue Oct 19 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3047 | TT_TASK | Control Power Available | Tue Sep 21 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3048 | TT_TASK | Power available for Start up | Mon Oct 04 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3049 | TT_TASK | SE- Completed L2 QC Checklist | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3050 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Oct 05 07:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3051 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-3 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 160.0 | NOT_STARTED
3052 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-3 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3053 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3054 | TT_TASK | Network Startup | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3055 | TT_TASK | EPMS Checkout / Point to Point | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3056 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3057 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Oct 18 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3059 | TT_TASK | Control Power Available | Thu Sep 09 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3060 | TT_TASK | Power available for Start up | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3061 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3062 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3063 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-2 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3064 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-2 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3065 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Fri Aug 13 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3066 | TT_TASK | Network Startup | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3067 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3068 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3069 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  |  | 170.0 | NOT_STARTED
3071 | TT_TASK | Control Power Available | Tue Sep 21 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3072 | TT_TASK | Power available for Start up | Mon Oct 04 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3073 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3074 | TT_TASK | Mechanical Equipment Yellow Tag | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3075 | TT_TASK | UPM Yellow tagging COLO-3 CELL-4 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 160.0 | NOT_STARTED
3076 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-4 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
3077 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3078 | TT_TASK | Network Startup | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3079 | TT_TASK | EPMS Checkout / Point to Point | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3080 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3081 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  |  | 70.0 | NOT_STARTED
3083 | TT_TASK | GEN SCR testing and Burnins | Fri Oct 08 07:00:00 IDT 2021 | Tue Oct 26 17:00:00 IDT 2021 |  |  | 320.0 | NOT_STARTED
3084 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Fri Oct 22 07:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3085 | TT_TASK | Cooling Automation | Fri Nov 05 07:00:00 IST 2021 | Fri Nov 19 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3086 | TT_TASK | BAS Prefunctional Testing on Construction Server | Mon Nov 01 07:00:00 IST 2021 | Wed Nov 24 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3087 | TT_TASK | Load Bank & IR Scan | Wed Dec 08 07:00:00 IST 2021 | Mon Jan 03 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3088 | TT_TASK | Level 3 Cx- COLO-3 | Tue Jan 04 07:00:00 IST 2022 | Tue Jan 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3089 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Wed Jan 19 07:00:00 IST 2022 | Wed Jan 19 07:00:00 IST 2022 |  |  |  | NOT_STARTED
3091 | TT_TASK | COLO 3 Level 4 & Level 5 IST | Wed Jan 19 08:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3092 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Wed Feb 09 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3093 | TT_TASK | Security Commissioning (level3 DCPS) | Sat Feb 19 08:00:00 IST 2022 | Wed Feb 23 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3094 | TT_TASK | Punch List COLO-3 | Wed Feb 09 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3095 | TT_TASK | MST Ready for Network Install | Wed Jan 19 08:00:00 IST 2022 | Tue Jan 25 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3096 | TT_TASK | Final Clean/ ready for lock down | Wed Feb 23 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3100 | TT_TASK | Control Power Available | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3101 | TT_TASK | Power available for Start up | Tue Nov 02 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3102 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3103 | TT_TASK | Mechanical Equipment Yellow Tag | Mon Oct 18 07:00:00 IDT 2021 | Thu Oct 28 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3104 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-1 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
3105 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-1 | Fri Sep 17 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
3106 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3107 | TT_TASK | Network Startup | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3108 | TT_TASK | EPMS Checkout / Point to Point | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  | 40.0 | NOT_STARTED
3109 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3110 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3112 | TT_TASK | Control Power Available | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3113 | TT_TASK | Power available for Start up | Mon Nov 15 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3114 | TT_TASK | SE- Completed L2 QC Checklist | Sat Oct 23 07:00:00 IDT 2021 | Wed Nov 03 17:00:00 IST 2021 |  |  | 20.0 | NOT_STARTED
3115 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Oct 29 07:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 |  |  | 70.0 | NOT_STARTED
3116 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-3 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Mon Aug 16 00:00:00 IDT 2021 |  | COMPLETED
3117 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-3 | Tue Sep 28 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  | 200.0 | NOT_STARTED
3118 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3119 | TT_TASK | Network Startup | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3120 | TT_TASK | EPMS Checkout / Point to Point | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3121 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3122 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3124 | TT_TASK | Control Power Available | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3125 | TT_TASK | Power available for Start up | Tue Nov 02 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3126 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3127 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3128 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-2 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3129 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-2 | Fri Sep 17 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
3130 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3131 | TT_TASK | Network Startup | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3132 | TT_TASK | EPMS Checkout / Point to Point | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3133 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3134 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3136 | TT_TASK | Control Power Available | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3137 | TT_TASK | Power available for Start up | Mon Nov 15 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3138 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3139 | TT_TASK | Mechanical Equipment Yellow Tag | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  | 140.0 | NOT_STARTED
3140 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-4 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3141 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-4 | Sat Sep 18 07:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 |  |  | 270.0 | NOT_STARTED
3142 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3143 | TT_TASK | Network Startup | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3144 | TT_TASK | EPMS Checkout / Point to Point | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3145 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3146 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3148 | TT_TASK | GEN SCR testing and Burnins | Fri Nov 19 07:00:00 IST 2021 | Thu Dec 09 17:00:00 IST 2021 |  |  | 310.0 | NOT_STARTED
3149 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Tue Nov 30 07:00:00 IST 2021 | Mon Dec 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3150 | TT_TASK | Cooling Automation | Tue Dec 14 07:00:00 IST 2021 | Thu Dec 30 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3151 | TT_TASK | BAS Prefunctional Testing on Construction Server | Tue Dec 07 07:00:00 IST 2021 | Tue Jan 04 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3152 | TT_TASK | Load Bank & IR Scan | Sat Jan 22 07:00:00 IST 2022 | Sat Feb 12 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3153 | TT_TASK | Level 3 Cx - COLO-4 | Mon Feb 14 07:00:00 IST 2022 | Sat Feb 26 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3154 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Mon Feb 28 07:00:00 IST 2022 | Mon Feb 28 07:00:00 IST 2022 |  |  |  | NOT_STARTED
3156 | TT_TASK | COLO 4 Level 4 & Level 5 IST | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 20 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3157 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Mon Mar 21 08:00:00 IST 2022 | Wed Mar 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3158 | TT_TASK | Security Commissioning (level3 DCPS) | Thu Mar 31 08:00:00 IDT 2022 | Mon Apr 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3159 | TT_TASK | Punch List COLO-4 | Mon Mar 21 08:00:00 IST 2022 | Sat Apr 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3160 | TT_TASK | MST Ready for Network Install | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3161 | TT_TASK | Final Clean/ ready for lock down | Sun Apr 03 08:00:00 IDT 2022 | Wed Apr 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3163 | TT_TASK | CSA Punchlist - COLO-1 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  | COMPLETED
3164 | TT_TASK | CSA Punchlist - COLO-2 | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 220.0 | NOT_STARTED
3165 | TT_TASK | CSA Punchlist - COLO-3 | Mon Nov 01 07:00:00 IST 2021 | Fri Nov 12 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3166 | TT_TASK | CSA Punchlist - COLO-4 | Sat Dec 11 07:00:00 IST 2021 | Thu Dec 23 17:00:00 IST 2021 |  |  | 380.0 | NOT_STARTED
3167 | TT_TASK | MEP Punchlist - COLO-1 | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 110.0 | NOT_STARTED
3168 | TT_TASK | MEP Punchlist - COLO-2 | Wed Nov 17 07:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 |  |  | 20.0 | NOT_STARTED
3169 | TT_TASK | MEP Punchlist - COLO-3 | Tue Jan 04 07:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  |  | 20.0 | NOT_STARTED
3170 | TT_TASK | MEP Punchlist - COLO-4 | Mon Feb 14 07:00:00 IST 2022 | Thu Feb 24 17:00:00 IST 2022 |  |  | 20.0 | NOT_STARTED
3171 | TT_TASK | AE/Owner Punchlist - COLO-1 | Sat Oct 30 07:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  |  | 60.0 | NOT_STARTED
3172 | TT_TASK | AE/Owner Punchlist - COLO-2 | Mon Dec 27 07:00:00 IST 2021 | Mon Jan 03 17:00:00 IST 2022 |  |  | 41.0 | NOT_STARTED
3173 | TT_TASK | AE/Owner Punchlist - COLO-3 | Wed Feb 09 07:00:00 IST 2022 | Mon Feb 14 17:00:00 IST 2022 |  |  | 71.0 | NOT_STARTED
3174 | TT_TASK | AE/Owner Punchlist - COLO-4 | Mon Mar 21 07:00:00 IST 2022 | Fri Mar 25 17:00:00 IDT 2022 |  |  | 70.0 | NOT_STARTED
3182 | TT_TASK | UMS - ROJ COLO-2 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3183 | TT_TASK | UMS - ROJ COLO-3 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3184 | TT_TASK | UMS - ROJ COLO-4 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3185 | TT_TASK | MSFT Delivery -UMS -COLO 4 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3186 | TT_TASK | MSFT Delivery -UMS -COLO 3 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3187 | TT_TASK | MSFT Delivery -UMS -COLO 2 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3190 | TT_TASK | TCO COLO 2 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3191 | TT_TASK | Weather Tight | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3192 | TT_TASK | Duct Bank - UMS01 to UPM COLO-1 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3193 | TT_TASK | Duct Bank - UMS02 to UPM COLO-2 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3194 | TT_TASK | Duct Bank - UMS03 to UPM COLO-3 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3195 | TT_TASK | Duct Bank - UMS04 to UPM COLO-4 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3196 | TT_TASK | PAD- COLO-1 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3197 | TT_TASK | PAD- COLO-2 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3198 | TT_TASK | PAD- COLO-3 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3199 | TT_TASK | PAD- COLO-4 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3200 | TT_TASK | Pull- UMS01- UPM COLO-1 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3201 | TT_TASK | Pull- UMS02- UPM COLO-2 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3202 | TT_TASK | Pull- UMS03- UPM COLO-3 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3203 | TT_TASK | Pull- UMS04- UPM COLO-4 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3204 | TT_TASK | Set- COLO-1 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3205 | TT_TASK | Set- COLO-2 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3206 | TT_TASK | Set- COLO-3 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3207 | TT_TASK | Set- COLO-4 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3208 | TT_TASK | Term Admin - UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3209 | TT_TASK | Term COLO -1 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3210 | TT_TASK | Term COLO -1 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3211 | TT_TASK | Term COLO -2 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3212 | TT_TASK | Term COLO -2 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3213 | TT_TASK | Term COLO -3 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3214 | TT_TASK | Term COLO -3 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3215 | TT_TASK | Term COLO -4 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3216 | TT_TASK | Term COLO -4 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3217 | TT_TASK | Term- UMS01- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3218 | TT_TASK | Term- UMS02- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3219 | TT_TASK | Term- UMS03- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3220 | TT_TASK | Term- UMS04- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3221 | TT_TASK | Yellow Tagging for UMS01 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3222 | TT_TASK | Yellow Tagging for UMS02 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3223 | TT_TASK | Yellow Tagging for UMS03 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3224 | TT_TASK | Yellow Tagging for UMS04 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3225 | TT_TASK | URS Vault design and Approval | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3227 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Thu Oct 22 07:00:00 IDT 2020 | Thu Oct 22 07:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3228 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3229 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jan 23 07:00:00 IST 2021 | Sat Jan 23 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3230 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Thu Oct 22 07:00:00 IDT 2020 | Thu Oct 22 07:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3231 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3232 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jan 23 07:00:00 IST 2021 | Sat Jan 23 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3233 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Nov 04 07:00:00 IST 2020 | Wed Nov 04 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3234 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3235 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Feb 04 07:00:00 IST 2021 | Thu Feb 04 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3236 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Nov 04 07:00:00 IST 2020 | Wed Nov 04 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3237 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3238 | TT_TASK | COLO Lighting installation (DRB#2) | Mon Feb 08 07:00:00 IST 2021 | Mon Feb 08 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3239 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3240 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Dec 02 07:00:00 IST 2020 | Wed Dec 02 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3241 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Mar 11 07:00:00 IST 2021 | Thu Mar 11 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3242 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Tue Dec 29 07:00:00 IST 2020 | Tue Dec 29 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3243 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Dec 02 07:00:00 IST 2020 | Wed Dec 02 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3244 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Mar 11 07:00:00 IST 2021 | Thu Mar 11 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3245 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Dec 18 07:00:00 IST 2020 | Fri Dec 18 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3246 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Dec 15 07:00:00 IST 2020 | Tue Dec 15 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3247 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Mar 26 07:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3248 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Dec 15 07:00:00 IST 2020 | Tue Dec 15 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3249 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Mar 26 07:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3250 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Jan 07 07:00:00 IST 2021 | Thu Jan 07 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3251 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3252 | TT_TASK | COLO Lighting installation (DRB#2) | Tue Apr 27 07:00:00 IDT 2021 | Tue Apr 27 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3253 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Jan 14 07:00:00 IST 2021 | Thu Jan 14 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3254 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3255 | TT_TASK | COLO Lighting installation (DRB#2) | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3256 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Fri Feb 12 07:00:00 IST 2021 | Fri Feb 12 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3257 | TT_TASK | COLO Lighting installation (DRB#2) | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3258 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Jan 29 07:00:00 IST 2021 | Fri Jan 29 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3259 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Fri Feb 12 07:00:00 IST 2021 | Fri Feb 12 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3260 | TT_TASK | COLO Lighting installation (DRB#2) | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3261 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3262 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Mar 09 07:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3263 | TT_TASK | COLO Lighting installation (DRB#2) | Wed Jun 09 07:00:00 IDT 2021 | Wed Jun 09 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3264 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3265 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Mar 09 07:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3266 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Jun 04 07:00:00 IDT 2021 | Fri Jun 04 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3267 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Sat Feb 20 07:00:00 IST 2021 | Sat Feb 20 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3268 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Mon Mar 22 07:00:00 IST 2021 | Mon Mar 22 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3269 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jun 19 07:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3270 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Sat Feb 20 07:00:00 IST 2021 | Sat Feb 20 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3271 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Mon Mar 22 07:00:00 IST 2021 | Mon Mar 22 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3272 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jun 19 07:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3273 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3274 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3275 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3276 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3277 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3278 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3279 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3280 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3281 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3282 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3283 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3284 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3285 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3286 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3287 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3288 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3290 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 05 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3291 | TT_TASK | Mechanical Equipment Piping Connections | Tue Nov 03 07:00:00 IST 2020 | Tue Nov 17 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3292 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3293 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3294 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3295 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3296 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3297 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3298 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3299 | TT_TASK | Fluid Cooler RI prefabrication | Thu Dec 10 07:00:00 IST 2020 | Wed Dec 16 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3300 | TT_TASK | Fluid Cooler RI prefabrication | Wed Dec 16 07:00:00 IST 2020 | Tue Dec 22 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3301 | TT_TASK | Fluid Cooler RI prefabrication | Wed Dec 23 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3302 | TT_TASK | Fluid Cooler RI prefabrication | Thu Jan 07 07:00:00 IST 2021 | Wed Jan 13 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3303 | TT_TASK | Fluid Cooler RI prefabrication | Thu Jan 14 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3304 | TT_TASK | Fluid Cooler RI prefabrication | Fri Jan 22 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3305 | TT_TASK | Fluid Cooler RI prefabrication | Tue Jan 26 07:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3306 | TT_TASK | Submit and approve shop drawing for PEMB penetrations | Mon Oct 19 08:00:00 IDT 2020 | Sun Nov 08 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3308 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3309 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3310 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3311 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3312 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3313 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3314 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3315 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3316 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3317 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3318 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3319 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3321 | TT_TASK | Yellow Tagging for COLO-2 UPM's | Fri Jan 29 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3322 | TT_TASK | Yellow Tagging for COLO-3 UPM's | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 |  | COMPLETED
3323 | TT_TASK | Yellow Tagging for COLO-4 UPM's | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 |  | COMPLETED
3324 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 11 07:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3326 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3327 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3328 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Mar 10 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3329 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 08 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3330 | TT_TASK | Fluid Cooler QAQC and Cx | Thu Mar 18 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3331 | TT_TASK | Fluid Cooler QAQC and Cx | Fri Apr 02 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3332 | TT_TASK | Fluid Cooler QAQC and Cx | Fri Mar 26 07:00:00 IDT 2021 | Sat Mar 27 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3333 | TT_TASK | Fluid Cooler QAQC and Cx | Tue Apr 06 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3334 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 14 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3335 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 21 07:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3336 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 14 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3337 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 28 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3338 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 21 07:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3339 | TT_TASK | Fluid Cooler QAQC and Cx | Thu May 06 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3341 | TT_TASK | COLO-2 CELL3 Rearrange Roxtec blocks per coordination layout | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3342 | TT_TASK | COLO2 CELL3 Interior MER conduit installation utility side | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 06 07:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3343 | TT_TASK | COLO-2 CELL3 Interior MER conduit installation building side | Tue Apr 20 07:00:00 IDT 2021 | Tue Apr 20 07:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3345 | TT_TASK | COLO-2 Cell-4 Rearrange Roxtec blocks per coordination layout | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3346 | TT_TASK | COLO2 CELL4 Interior MER conduit installation utility side | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3347 | TT_TASK | COLO2 CELL4 Interior MER conduit installation building side | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3350 | TT_TASK | COLO-2 Cell-1 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3351 | TT_TASK | COLO-2 Cell-2 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3352 | TT_TASK | COLO-2 Cell-3 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3353 | TT_TASK | COLO-2 Cell-4 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3354 | TT_TASK | COLO2 CELL1 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3355 | TT_TASK | COLO2 CELL2 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3356 | TT_TASK | COLO2 CELL3 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3357 | TT_TASK | COLO2 CELL4 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3360 | TT_TASK | Concrete interior - Create Punch list | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
3361 | TT_TASK | Concrete interior - Complete Punch List | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
3362 | TT_TASK | Garco Steel (Mezz steel, Yard) - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3363 | TT_TASK | Garco Steel (Mezz steel, Yard) - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3364 | TT_TASK | Sure Steel (Building, Mezz, Ceiling) - Create Punch list | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
3365 | TT_TASK | Sure Steel (Building, Mezz, Ceiling) - Complete Punch List | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
3366 | TT_TASK | Advantage - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3367 | TT_TASK | Advantage - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3368 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3369 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3370 | TT_TASK | VECA - Create Punch list | Tue Sep 07 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3371 | TT_TASK | VECA - Complete Punch List | Thu Sep 09 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3372 | TT_TASK | LINX - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3373 | TT_TASK | LINX - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3374 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3375 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3376 | TT_TASK | TCM- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3377 | TT_TASK | TCM - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3378 | TT_TASK | Cascade- Create Punch list | Mon Apr 26 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
3379 | TT_TASK | Cascade - Complete Punch List | Wed Apr 28 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3380 | TT_TASK | Submit GC Punch List to A/E | Tue Sep 21 07:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3381 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3382 | TT_TASK | Complete A/E Punchlist | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3383 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3384 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3385 | TT_TASK | VECA - Create Punch list | Fri Oct 29 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3386 | TT_TASK | VECA - Complete Punch List | Mon Nov 01 07:00:00 IST 2021 | Mon Nov 08 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3387 | TT_TASK | LINX - Create Punch list | Mon Aug 16 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3388 | TT_TASK | LINX - Complete Punch List | Wed Aug 18 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3389 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3390 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3391 | TT_TASK | TCM- Create Punch list | Wed Sep 22 07:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3392 | TT_TASK | TCM - Complete Punch List | Fri Sep 24 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3393 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3394 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3395 | TT_TASK | Submit GC Punch List to A/E | Tue Nov 09 07:00:00 IST 2021 | Tue Nov 09 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3396 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Nov 10 07:00:00 IST 2021 | Tue Nov 16 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3397 | TT_TASK | Complete A/E Punchlist | Wed Nov 17 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3398 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3399 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3400 | TT_TASK | VECA - Create Punch list | Tue Dec 14 07:00:00 IST 2021 | Wed Dec 15 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3401 | TT_TASK | VECA - Complete Punch List | Thu Dec 16 07:00:00 IST 2021 | Thu Dec 23 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3402 | TT_TASK | LINX - Create Punch list | Wed Oct 13 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3403 | TT_TASK | LINX - Complete Punch List | Fri Oct 15 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3404 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3405 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3406 | TT_TASK | TCM- Create Punch list | Wed Sep 22 07:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3407 | TT_TASK | TCM - Complete Punch List | Fri Sep 24 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3408 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3409 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3410 | TT_TASK | Submit GC Punch List to A/E | Mon Dec 27 07:00:00 IST 2021 | Mon Dec 27 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3411 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Tue Dec 28 07:00:00 IST 2021 | Wed Jan 05 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3412 | TT_TASK | Complete A/E Punchlist | Thu Jan 06 07:00:00 IST 2022 | Thu Jan 20 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3413 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3414 | TT_TASK | PCI - Complete Punch List | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3415 | TT_TASK | VECA - Create Punch list | Fri Jan 28 07:00:00 IST 2022 | Mon Jan 31 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3416 | TT_TASK | VECA - Complete Punch List | Tue Feb 01 07:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3417 | TT_TASK | LINX - Create Punch list | Fri Nov 19 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3418 | TT_TASK | LINX - Complete Punch List | Mon Nov 22 07:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3419 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3420 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3421 | TT_TASK | TCM- Create Punch list | Thu Nov 04 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3422 | TT_TASK | TCM - Complete Punch List | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3423 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3424 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3425 | TT_TASK | Submit GC Punch List to A/E | Tue Feb 08 07:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3426 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Feb 09 07:00:00 IST 2022 | Tue Feb 15 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3427 | TT_TASK | Complete A/E Punchlist | Wed Feb 16 07:00:00 IST 2022 | Tue Mar 01 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3428 | TT_TASK | COLO-2 Cell2 Rearrange Roxtec blocks per coordination layout (delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
3429 | TT_TASK | COLO2 CELL2 Interior MER conduit installation utility side(delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
3430 | TT_TASK | COLO-2 CELL2 Interior MER conduit installation building (delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
3432 | TT_TASK | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change(delete) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
3433 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3434 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3435 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3436 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
303 | TT_TASK | MSFT Issue DRB #1 for Review | Tue May 26 07:00:00 IDT 2020 | Mon Jun 01 17:00:00 IDT 2020 | Tue May 19 00:00:00 IDT 2020 | Mon Jul 20 00:00:00 IDT 2020 |  | COMPLETED
306 | TT_TASK | Lead Time for PEMB | Wed Feb 19 08:00:00 IST 2020 | Thu Jun 18 17:00:00 IDT 2020 | Mon Feb 24 00:00:00 IST 2020 | Thu Jun 18 00:00:00 IDT 2020 |  | COMPLETED
307 | TT_TASK | Lead Time for Rebar (Footings & Walls) | Mon Apr 27 08:00:00 IDT 2020 | Sun May 31 17:00:00 IDT 2020 | Mon Mar 30 00:00:00 IDT 2020 | Tue Apr 21 00:00:00 IDT 2020 |  | COMPLETED
308 | TT_TASK | Lead Time for COLO 1 Structural Interior Steel | Mon Aug 10 08:00:00 IDT 2020 | Sat Oct 31 17:00:00 IST 2020 | Tue Jun 30 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
309 | TT_TASK | Lead Time for Wall & Roof Metal Panels | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Mon Jun 29 00:00:00 IDT 2020 |  | COMPLETED
310 | TT_TASK | Lead Time for Admin/COLO 1 Yard Steel | Mon Aug 31 08:00:00 IDT 2020 | Sun Oct 18 17:00:00 IDT 2020 | Tue Jun 30 00:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 |  | COMPLETED
311 | TT_TASK | Lead Time for HM Ext. frames | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
312 | TT_TASK | Lead time for Drywall/Framing | Mon Aug 10 08:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Mon Aug 10 08:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
592 | TT_TASK | MV Ductbanks Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | Mon Sep 14 08:00:00 IDT 2020 | Sun Sep 20 17:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 | Sun Sep 06 00:00:00 IDT 2020 |  | COMPLETED
593 | TT_TASK | MV Wire Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | Wed Aug 12 08:00:00 IDT 2020 | Tue Nov 03 17:00:00 IST 2020 | Tue Aug 04 00:00:00 IDT 2020 | Mon Oct 26 00:00:00 IST 2020 |  | COMPLETED
594 | TT_TASK | UMS Vault Procurement DRB#1 | Mon Sep 28 08:00:00 IDT 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
595 | TT_TASK | DRB#1 BIM Modeling & Coordination DRB#1 JAZ to UMS/URS & UPM to UMS | Mon Aug 10 08:00:00 IDT 2020 | Sun Aug 23 17:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
596 | TT_TASK | Site- Neher Mcgrath Study DRB#1 JAZ to UMS/URS & UPM to UMS | Tue Aug 11 08:00:00 IDT 2020 | Mon Aug 24 17:00:00 IDT 2020 | Tue Aug 04 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
597 | TT_TASK | JAZ Riser Support DRB#1 Procurement/ Jaz Foundations/Construction | Mon Aug 10 08:00:00 IDT 2020 | Sun Oct 18 17:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
598 | TT_TASK | UPM to UMS Vaults Procurement DRB#1 | Tue Sep 08 08:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
600 | TT_TASK | MV Ductbanks Procurement | Wed Aug 12 08:00:00 IDT 2020 | Thu Aug 20 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
601 | TT_TASK | Telecom DuctBank / Vaults Procurement | Thu May 14 08:00:00 IDT 2020 | Mon May 18 17:00:00 IDT 2020 | Wed May 06 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
602 | TT_TASK | MV Wire Procurement | Wed Aug 12 08:00:00 IDT 2020 | Tue Nov 03 17:00:00 IST 2020 | Tue Jul 21 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
603 | TT_TASK | Off-Site BIM Modeling & Coordination | Mon Apr 27 08:00:00 IDT 2020 | Sun May 24 17:00:00 IDT 2020 | Tue Apr 14 00:00:00 IDT 2020 | Tue May 05 00:00:00 IDT 2020 |  | COMPLETED
604 | TT_TASK | Neher Mcgrath Study | Thu Jul 02 08:00:00 IDT 2020 | Thu Aug 06 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Fri Jul 24 00:00:00 IDT 2020 |  | COMPLETED
605 | TT_TASK | URS Vault Procurement | Mon Sep 28 08:00:00 IDT 2020 | Wed Nov 11 17:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
607 | TT_TASK | Site Temp Power Procurement & Infrastructure | Mon Jun 29 08:00:00 IDT 2020 | Mon Aug 31 08:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
609 | TT_TASK | Underground Grounding Procurement | Mon Apr 27 08:00:00 IDT 2020 | Sun May 17 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Tue Apr 28 00:00:00 IDT 2020 |  | COMPLETED
610 | TT_TASK | BIM Modeling (Under ground) | Tue May 05 08:00:00 IDT 2020 | Mon Jun 08 17:00:00 IDT 2020 | Tue May 05 08:00:00 IDT 2020 | Mon Jun 08 00:00:00 IDT 2020 |  | COMPLETED
611 | TT_TASK | Electrical Long Lead Equipment Procurement (Cablebus, Panel Boards) | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Mon Apr 27 08:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
612 | TT_TASK | BIM Modeling (Above ground) | Sun Aug 02 08:00:00 IDT 2020 | Wed Sep 30 17:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
615 | TT_TASK | Design / Lead Time for Electrical/Telecom (OFCI Telecom BOM Materials) | Mon Aug 10 08:00:00 IDT 2020 | Sat Nov 07 17:00:00 IST 2020 | Wed Jul 01 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
616 | TT_TASK | Design / Lead Time for Busway (OFCI Starline BOM Materials) | Thu Nov 26 08:00:00 IST 2020 | Thu Jan 14 17:00:00 IST 2021 | Mon Sep 21 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
619 | TT_TASK | Water treatment Skids Procurement ( sourcing materials and Materail approval only) | Mon Apr 27 08:00:00 IDT 2020 | Fri Nov 06 12:00:00 IST 2020 | Tue Apr 07 00:00:00 IDT 2020 | Mon Jul 06 00:00:00 IDT 2020 |  | COMPLETED
620 | TT_TASK | Design / Lead Time for M&P overhead | Mon Jun 29 08:00:00 IDT 2020 | Tue Jul 28 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
621 | TT_TASK | Design / Lead Time for Fire Protection | Mon Aug 31 08:00:00 IDT 2020 | Tue Sep 29 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
622 | TT_TASK | Design / Lead Time for Fire Alarm | Mon Jun 29 08:00:00 IDT 2020 | Thu Aug 27 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
628 | TT_TASK | URS/UMS Concrete Anchor and Vault Design | Mon Aug 10 07:00:00 IDT 2020 | Wed Aug 26 17:00:00 IDT 2020 | Wed Aug 05 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
629 | TT_TASK | URS/UMS Vault Submiital Review by EOR | Mon Sep 14 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Fri Sep 25 00:00:00 IDT 2020 |  | COMPLETED
632 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-2 PSR(10/13) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sat Dec 12 17:00:00 IST 2020 | Tue Oct 13 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
633 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-3 PSR(9/28) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Mon Dec 28 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
634 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-4 PSR (10/28) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Fri Nov 27 16:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
635 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-1 PSR (9/19) to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Tue Dec 15 17:00:00 IST 2020 | Sat Sep 19 00:00:00 IDT 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
637 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-1 11/25 to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Fri Oct 09 17:00:00 IDT 2020 | Wed Nov 25 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
638 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-2 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sun Nov 15 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
639 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-4 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Fri Nov 06 16:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
640 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-3 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sun Nov 15 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
642 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-1 PSR 11/23 to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Wed Oct 14 17:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
643 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-2 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
644 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-4 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Wed Nov 11 16:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Sun Jan 03 00:00:00 IST 2021 |  | COMPLETED
645 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-3 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Sun Jan 03 00:00:00 IST 2021 |  | COMPLETED
647 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-1 12/7 to MSFT delivery) | Sat Jan 09 08:00:00 IST 2021 | Sat Jan 09 08:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
648 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-2 12/7 to MSFT delivery) | Tue Jan 05 08:00:00 IST 2021 | Tue Jan 05 08:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
649 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-4 12/18 to MSFT delivery) | Sat Jan 09 08:00:00 IST 2021 | Sat Jan 09 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
650 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-3 12/18 to MSFT delivery) | Thu Jan 14 08:00:00 IST 2021 | Thu Jan 14 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
653 | TT_TASK | Review Fluid Cooler wiring and devices buyout with Stetner | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Wed Sep 23 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
654 | TT_TASK | Change order release for fluid cooler wiring devices | Mon Oct 19 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 | Mon Oct 26 00:00:00 IST 2020 |  | COMPLETED
657 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
658 | TT_TASK | Fluid Cooler RI in place | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
659 | TT_TASK | Fluid Cooler Wire install and Term | Fri Mar 05 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
661 | TT_TASK | Fluid Cooler Panel installation | Tue Mar 23 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
662 | TT_TASK | Fluid Cooler RI in place | Thu Mar 18 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
663 | TT_TASK | Fluid Cooler Wire install and Term | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 |  | COMPLETED
665 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 15 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
666 | TT_TASK | Fluid Cooler RI in place | Fri Feb 19 07:00:00 IST 2021 | Thu Feb 25 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
667 | TT_TASK | Fluid Cooler Wire install and Term | Thu Mar 18 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
669 | TT_TASK | Fluid Cooler Panel installation | Thu Mar 18 07:00:00 IST 2021 | Mon Mar 22 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
670 | TT_TASK | Fluid Cooler RI in place | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
671 | TT_TASK | Fluid Cooler Wire install and Term | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
674 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 29 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
675 | TT_TASK | Fluid Cooler RI in place | Thu Mar 25 07:00:00 IST 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
676 | TT_TASK | Fluid Cooler Wire install and Term | Thu Apr 01 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
678 | TT_TASK | Fluid Cooler Panel installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
679 | TT_TASK | Fluid Cooler RI in place | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
680 | TT_TASK | Fluid Cooler Wire install and Term | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
682 | TT_TASK | Fluid Cooler Panel installation | Thu Apr 01 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Sat Mar 27 00:00:00 IDT 2021 |  | COMPLETED
683 | TT_TASK | Fluid Cooler RI in place | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
684 | TT_TASK | Fluid Cooler Wire install and Term | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
687 | TT_TASK | Fluid Cooler Panel installation | Tue May 04 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
688 | TT_TASK | Fluid Cooler RI in place | Fri May 07 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
689 | TT_TASK | Fluid Cooler Wire install and Term | Fri May 14 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
691 | TT_TASK | Fluid Cooler Panel installation | Mon May 17 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
692 | TT_TASK | Fluid Cooler RI in place | Thu May 20 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
693 | TT_TASK | Fluid Cooler Wire install and Term | Fri May 28 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
695 | TT_TASK | Fluid Cooler Panel installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
696 | TT_TASK | Fluid Cooler RI in place | Fri Jun 04 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
697 | TT_TASK | Fluid Cooler Wire install and Term | Fri Jun 11 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
700 | TT_TASK | Fluid Cooler Panel installation | Tue Jun 08 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
701 | TT_TASK | Fluid Cooler RI in place | Fri Jun 11 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
702 | TT_TASK | Fluid Cooler Wire install and Term | Sat Jun 19 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
704 | TT_TASK | Fluid Cooler Panel installation | Fri Jun 11 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
705 | TT_TASK | Fluid Cooler RI in place | Sat Jun 19 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
706 | TT_TASK | Fluid Cooler Wire install and Term | Sat Jun 26 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
708 | TT_TASK | Fluid Cooler Panel installation | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
709 | TT_TASK | Fluid Cooler RI in place | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
710 | TT_TASK | Fluid Cooler Wire install and Term | Tue Jul 13 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
712 | TT_TASK | Fluid Cooler Panel installation | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
713 | TT_TASK | Fluid Cooler RI in place | Tue Jul 13 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
714 | TT_TASK | Fluid Cooler Wire install and Term | Tue Jul 20 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
718 | TT_TASK | ADMIN Overhead Rough-in (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
719 | TT_TASK | ADMIN Electrical Room Build out (DRB#2) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
720 | TT_TASK | ADMIN Lighting installation (DRB#2) | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
742 | TT_TASK | Water Treatmant Skid Fabrication | Mon Sep 14 08:00:00 IDT 2020 | Mon Dec 07 17:00:00 IST 2020 | Tue Aug 25 00:00:00 IDT 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
743 | TT_TASK | L&I approval process | Mon Sep 14 08:00:00 IDT 2020 | Tue Oct 13 17:00:00 IDT 2020 | Tue Aug 25 00:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 |  | COMPLETED
745 | TT_TASK | Water treatment delivery COLO-1 | Mon Dec 21 08:00:00 IST 2020 | Sun Dec 27 17:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
750 | TT_TASK | Submit and approve Shop drawings for UPM junstion box | Mon Oct 19 08:00:00 IDT 2020 | Sun Nov 08 17:00:00 IST 2020 | Fri Oct 09 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
751 | TT_TASK | Lead time for junction box | Mon Nov 02 08:00:00 IST 2020 | Sun Dec 13 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
752 | TT_TASK | Fabrication and Delivery of PEMB pentrations support steel | Mon Nov 09 08:00:00 IST 2020 | Fri Nov 13 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
756 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
757 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Tue Dec 15 00:00:00 IST 2020 |  | COMPLETED
758 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
760 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
761 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
762 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Feb 13 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
763 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
764 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Mar 05 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
765 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
768 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
769 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
770 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Feb 08 08:00:00 IST 2021 | Thu Feb 11 08:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
772 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
773 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
774 | TT_TASK | Install additional Cable bus (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
775 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
776 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Mar 02 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
777 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
780 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
781 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Tue Dec 15 00:00:00 IST 2020 |  | COMPLETED
782 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
784 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
785 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
786 | TT_TASK | Install additional Cable bus (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
787 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
788 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
789 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
792 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Dec 04 07:00:00 IST 2020 | Wed Dec 09 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
793 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
794 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
796 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
797 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
798 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 03 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
799 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
800 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Thu Mar 04 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
801 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
803 | TT_TASK | COLO-1 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon Mar 22 07:00:00 IST 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
804 | TT_TASK | COLO-1 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon Apr 05 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
805 | TT_TASK | COLO-1 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
806 | TT_TASK | COLO-1 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
810 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Sat Jan 02 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
811 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
812 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
814 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
815 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
816 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
817 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
818 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
819 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
822 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
823 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Thu Feb 11 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
824 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Mar 26 07:00:00 IDT 2021 | Mon Mar 29 17:00:00 IDT 2021 | Sat Feb 27 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
826 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
827 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
828 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
829 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
830 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
831 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
834 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
835 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
836 | TT_TASK | Install added DRB#3 Tray and conduit | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
838 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Sat Mar 27 00:00:00 IDT 2021 |  | COMPLETED
839 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 |  | COMPLETED
840 | TT_TASK | Install additional Cable bus (DRB#3) | Mon May 03 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
841 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
842 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue May 04 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
843 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
846 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
847 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Thu Feb 11 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
848 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 02 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
850 | TT_TASK | Install MER Supply duct | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
851 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri May 07 07:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
852 | TT_TASK | Install additional Cable bus (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
853 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue May 04 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
854 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
855 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 |  | COMPLETED
857 | TT_TASK | COLO-2 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Fri Apr 30 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
858 | TT_TASK | COLO-2 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
859 | TT_TASK | COLO-2 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 03 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
860 | TT_TASK | COLO-2 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
864 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
865 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
866 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
868 | TT_TASK | Install MER Supply duct | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
869 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
870 | TT_TASK | Install Roxtec block sealing and Install added tray cable (DRB#3) | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
871 | TT_TASK | Install additional Cable bus (DRB#3) | Tue May 18 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
872 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
873 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
876 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
877 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
878 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
880 | TT_TASK | Install MER Supply duct | Mon May 24 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
881 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
882 | TT_TASK | Install additional Cable bus (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
883 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 |  | COMPLETED
884 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Sat Aug 14 07:00:00 IDT 2021 | Sat Aug 14 17:00:00 IDT 2021 |  | COMPLETED
885 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Fri Sep 03 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Thu Aug 26 00:00:00 IDT 2021 |  | COMPLETED
888 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
889 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 |  | COMPLETED
890 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
892 | TT_TASK | Install MER Supply duct | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
893 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 |  | COMPLETED
894 | TT_TASK | Install additional Cable bus (DRB#3) | Sat May 29 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
895 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
896 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 |  | COMPLETED
897 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Mon Aug 09 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
900 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
901 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
902 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
904 | TT_TASK | Install MER Supply duct | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
905 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
906 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jun 05 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
907 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
908 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
909 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
911 | TT_TASK | COLO-3 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
912 | TT_TASK | COLO-3 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 |  | COMPLETED
913 | TT_TASK | COLO-3 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
914 | TT_TASK | COLO-3 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
918 | TT_TASK | Sure steel - PEMB MER penetration framing | Thu Feb 11 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
919 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
920 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
922 | TT_TASK | Install MER Supply duct | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
923 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Thu Jul 08 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
924 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
925 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
926 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
927 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
930 | TT_TASK | Sure steel - PEMB MER penetration framing | Tue Feb 16 07:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
931 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
932 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
934 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
935 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
936 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
937 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Fri Sep 03 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 |  |  | 400.0 | NOT_STARTED
938 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
939 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Sat Oct 02 07:00:00 IDT 2021 | Fri Oct 08 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
942 | TT_TASK | Sure steel - PEMB MER penetration framing | Thu Feb 11 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
943 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
944 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
946 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
947 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Thu Jul 08 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 |  | COMPLETED
948 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Jul 28 00:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 |  | COMPLETED
949 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
950 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
951 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
954 | TT_TASK | Sure steel - PEMB MER penetration framing | Tue Feb 16 07:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
955 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
956 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 00:00:00 IDT 2021 |  | COMPLETED
958 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
959 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
960 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
961 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
962 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
963 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
965 | TT_TASK | COLO-4 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Thu Sep 09 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
966 | TT_TASK | COLO-4 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Wed Aug 18 00:00:00 IDT 2021 |  |  | IN_PROGRESS
967 | TT_TASK | COLO-4 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
968 | TT_TASK | COLO-4 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
970 | TT_TASK | Site Shut Down - 9/9/2020 | Mon Sep 14 07:00:00 IDT 2020 | Mon Sep 14 17:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 |  | COMPLETED
971 | TT_TASK | Site Shut Down - 9/10/2020 | Tue Sep 15 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Thu Sep 10 00:00:00 IDT 2020 | Thu Sep 10 00:00:00 IDT 2020 |  | COMPLETED
972 | TT_TASK | Site Shut Down - 9/11/2020 | Wed Sep 16 07:00:00 IDT 2020 | Wed Sep 16 17:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
973 | TT_TASK | Site Shut Down - 9/12/2020 | Thu Sep 17 07:00:00 IDT 2020 | Thu Sep 17 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
974 | TT_TASK | Site Shut Down - 9/14/2020 | Mon Sep 28 07:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 |  | COMPLETED
975 | TT_TASK | Site Shut Down - 9/15/2020 | Tue Sep 29 07:00:00 IDT 2020 | Tue Sep 29 17:00:00 IDT 2020 | Tue Sep 15 00:00:00 IDT 2020 | Tue Sep 15 00:00:00 IDT 2020 |  | COMPLETED
976 | TT_TASK | Site Shut Down - 9/16/2020 | Wed Sep 30 07:00:00 IDT 2020 | Wed Sep 30 17:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 |  | COMPLETED
979 | TT_TASK | Complete Remaining IWW piping to tie-in point | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 29 17:00:00 IST 2020 | Mon Sep 21 00:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
980 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
982 | TT_TASK | Complete Remaining Sanitary piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
983 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
985 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
986 | TT_TASK | Complete Remaining Fire Main piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
988 | TT_TASK | Complete Remaining ITW piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
989 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
991 | TT_TASK | Complete Remaining Telecom Duct Back (excluding Tie-in) | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
992 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
995 | TT_TASK | Delay in COLO-1- Cell-1 MER Delivery (Duration = COLO1 Cell-1 PSR(11/6/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sat Jan 30 17:00:00 IST 2021 | Fri Nov 06 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
996 | TT_TASK | Delay in COLO-1- Cell-2 MER Delivery (Duration = COLO1 Cell-2 PSR(11/13/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Fri Jan 29 17:00:00 IST 2021 | Fri Nov 13 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
997 | TT_TASK | Delay in COLO-1- Cell-3 MER Delivery (Duration = COLO1 Cell-3 PSR(11/20/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Feb 04 17:00:00 IST 2021 | Fri Nov 20 00:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 |  | COMPLETED
998 | TT_TASK | Delay in COLO-1- Cell-4 MER Delivery (Duration = COLO1 Cell-4 PSR(11/30/20) to MSFT delivery) | Mon Feb 01 08:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1000 | TT_TASK | Delay in COLO-2- Cell-1 MER Delivery (Duration = Colo1 Cell-1 PSR(12/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Feb 11 10:00:00 IST 2021 | Tue Dec 15 00:00:00 IST 2020 | Wed Feb 03 00:00:00 IST 2021 |  | COMPLETED
1001 | TT_TASK | Delay in COLO-2- Cell-2 MER Delivery (Duration = COLO 2 Cell-2 PSR(12/22/20) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1002 | TT_TASK | Delay in COLO-2- Cell-3 MER Delivery (Duration = COLO 2- Cell-3 PSR(12/28/20) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1003 | TT_TASK | Delay in COLO-2- Cell-4 MER Delivery (Duration = COLO 2- Cell-4 PSR(1/5/21) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Jan 05 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1005 | TT_TASK | Delay in COLO-3- Cell-1 MER Delivery (Duration = COLO-3 Cell-1 PSR(1/29/21) to MSFT delivery) | Sun Jan 31 08:00:00 IST 2021 | Sat Apr 03 17:00:00 IDT 2021 | Fri Jan 29 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1006 | TT_TASK | Delay in COLO-3- Cell-2 MER Delivery (Duration = COLO-3 Cell-2 PSR(2/5/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 05 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1007 | TT_TASK | Delay in COLO-3 Cell-3 MER Delivery (Duration = COLO-3 Cell-3 PSR(2/12/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Feb 12 00:00:00 IST 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1008 | TT_TASK | Delay in COLO-3 Cell-4 MER Delivery (Duration = COLO-3 Cell-4 PSR(2/19/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Thu Apr 22 00:00:00 IDT 2021 |  | COMPLETED
1010 | TT_TASK | Delay in COLO-4- Cell-1 MER Delivery (Duration= COLO-4 Cell-1 PSR(3/12/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Mar 12 00:00:00 IST 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
1011 | TT_TASK | Delay in COLO-4- Cell-2 MER Delivery (Duration = COLO-4 Cell-2 PSR(3/19/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1012 | TT_TASK | Delay in COLO-4- Cell-3 MER Delivery (Duration = COLO-4 Cell-3 PSR(3/26/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1013 | TT_TASK | Delay in COLO-4- Cell-4 MER Delivery (Duration = COLO-4 Cell-4 PSR(4/2/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 | Sun May 09 00:00:00 IDT 2021 |  | COMPLETED
1015 | TT_TASK | Wire Mesh Procurement | Mon Nov 16 08:00:00 IST 2020 | Wed Dec 23 12:00:00 IST 2020 | Thu Sep 24 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
1016 | TT_TASK | Wire Mesh Submittal Approval | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Wed Sep 16 00:00:00 IDT 2020 | Wed Sep 23 00:00:00 IDT 2020 |  | COMPLETED
1017 | TT_TASK | Wire Mesh Procurement Delay | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Sat Oct 24 00:00:00 IDT 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1019 | TT_TASK | Complete Remaining Telecom Duct Back tie-in Install to MWH02 | Mon Dec 21 07:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1020 | TT_TASK | Clayco waiting on MSOW Approval | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Tue Dec 01 00:00:00 IST 2020 |  | COMPLETED
1021 | TT_TASK | Clayco MSOW Submited for approval | Mon Nov 16 07:00:00 IST 2020 | Tue Nov 17 17:00:00 IST 2020 | Fri Oct 16 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
1022 | TT_TASK | MSFT Stand down/ Additional Hydro excavation | Mon Dec 21 07:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
1024 | TT_TASK | Delay in UMS delivery (Duration = (9/19) to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Thu Nov 19 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
1027 | TT_TASK | Delay In COLO-1 Cell-1 Generator (Duration= COLO-1 Cell-1 PSR(9/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Tue Jan 19 17:00:00 IST 2021 | Tue Sep 15 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1028 | TT_TASK | Delay In COLO-1 Cell-2 Generator (Duration= COLO-1 Cell-2 PSR(9/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sat Feb 06 17:00:00 IST 2021 | Tue Sep 15 00:00:00 IDT 2020 | Mon Nov 02 00:00:00 IST 2020 |  | COMPLETED
1029 | TT_TASK | Delay In COLO-1 Cell-4 Generator (Duration= COLO-1 Cell-4 PSR(9/29/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Sep 29 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1030 | TT_TASK | Delay In COLO-1 Cell-3 Generator (Duration= COLO-1 Cell-3 PSR(9/29/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Wed Feb 03 17:00:00 IST 2021 | Tue Sep 29 00:00:00 IDT 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1032 | TT_TASK | Delay In COLO-2 Cell-1 Generator (Duration= COLO-2 Cell-1 PSR(10/12/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sun Mar 07 17:00:00 IST 2021 | Mon Oct 12 00:00:00 IDT 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1033 | TT_TASK | Delay In COLO-2 Cell-2 Generator (Duration= COLO-2 Cell-2 PSR(11/6/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sun Feb 21 17:00:00 IST 2021 | Fri Nov 06 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
1034 | TT_TASK | Delay In COLO-2 Cell-4 Generator (Duration= COLO-2 Cell-4 PSR(11/21/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Fri Feb 19 17:00:00 IST 2021 | Sat Nov 21 00:00:00 IST 2020 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
1035 | TT_TASK | Delay In COLO-2 Cell-3 Generator (Duration= COLO-2 Cell-3 PSR(10/22/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Mar 18 17:00:00 IST 2021 | Thu Oct 22 00:00:00 IDT 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1037 | TT_TASK | 6.1.39.1- COLO-3 CEll-1 GEN Belly tank Failed pressure test | Mon Mar 15 07:00:00 IST 2021 | Fri Apr 09 17:00:00 IDT 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
1038 | TT_TASK | 6.1.39.2- COLO-3 Cell-1 Replace Belly Tank and Set GEN | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1039 | TT_TASK | Delay In COLO-3 Cell-1 Generator (Duration= COLO-3 Cell-1 PSR(10/12/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Sat May 08 17:00:00 IDT 2021 | Mon Nov 09 00:00:00 IST 2020 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1040 | TT_TASK | Delay In COLO-3 Cell-2 Generator (Duration= COLO-3 Cell-2 PSR(11/6/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Tue Mar 30 17:00:00 IDT 2021 | Sat Nov 21 00:00:00 IST 2020 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
1041 | TT_TASK | Delay In COLO-3 Cell-4 Generator (Duration= COLO-3 Cell-4 PSR(11/21/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Mar 18 17:00:00 IST 2021 | Wed Dec 09 00:00:00 IST 2020 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
1042 | TT_TASK | Delay In COLO-3 Cell-3 Generator (Duration= COLO-3 Cell-3 PSR(10/22/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Apr 29 17:00:00 IDT 2021 | Thu Nov 05 00:00:00 IST 2020 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1044 | TT_TASK | Delay In COLO-4 Cell-1 Generator (Duration= COLO-4 Cell-1 PSR(10/12/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Sat Jun 05 17:00:00 IDT 2021 | Mon Nov 09 00:00:00 IST 2020 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
1045 | TT_TASK | Delay In COLO-4 Cell-2 Generator (Duration= COLO-4 Cell-2 PSR(11/6/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Apr 01 17:00:00 IDT 2021 | Wed Dec 09 00:00:00 IST 2020 | Thu Mar 11 00:00:00 IST 2021 |  | COMPLETED
1046 | TT_TASK | Delay In COLO-4 Cell-4 Generator (Duration= COLO-4 Cell-4 PSR(11/21/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Wed Apr 14 17:00:00 IDT 2021 | Mon Nov 30 00:00:00 IST 2020 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
1047 | TT_TASK | Delay In COLO-4 Cell-3 Generator (Duration= COLO-4 Cell-3 PSR(10/22/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Tue May 11 17:00:00 IDT 2021 | Fri Nov 20 00:00:00 IST 2020 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1050 | TT_TASK | COLO1 CELL1 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1051 | TT_TASK | COLO1 CELL3 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
1052 | TT_TASK | COLO1 CELL2 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1053 | TT_TASK | COLO1 CELL4 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
1058 | TT_TASK | COLO-1 Cell-1 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1059 | TT_TASK | COLO1 CELL1 Interior MER conduit installation utility side | Fri Mar 05 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1060 | TT_TASK | COLO-1 Cell-1 Interior MER conduit installation building side Complete March1st (MER discovery Corrections & Signoff) | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1063 | TT_TASK | COLO-1 CELL3 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1064 | TT_TASK | COLO1 CELL3 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1065 | TT_TASK | COLO-1 CELL3 Interior MER conduit installation building side | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
1068 | TT_TASK | COLO-1 CELL2 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1069 | TT_TASK | COLO1 CELL2 Interior MER conduit installation utility side | Sat Mar 06 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1070 | TT_TASK | COLO-1 CELL2 Interior MER conduit installation building side | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1073 | TT_TASK | COLO-1 CELL4 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1074 | TT_TASK | COLO1 CELL4 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1075 | TT_TASK | COLO-1 CELL4 Interior MER conduit installation building side | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
1079 | TT_TASK | COLO-2 Cell-1 Rearrange Roxtec blocks per coordination layout | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1080 | TT_TASK | COLO2 CELL1 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1081 | TT_TASK | COLO-2 Cell-1 Interior MER conduit installation building side | Mon Apr 05 07:00:00 IDT 2021 | Mon Apr 19 17:00:00 IDT 2021 | Fri Mar 05 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1089 | TT_TASK | COLO-1 Cell-1 MER Flex Conduit fixes | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1090 | TT_TASK | COLO-1 Cell-3 MER Flex Conduit fixes | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1091 | TT_TASK | COLO-1 Cell-2 MER Flex Conduit fixes | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1092 | TT_TASK | COLO-1 Cell-4 MER Flex Conduit fixes | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1095 | TT_TASK | Safety Stop work due to failed Starline Hangers | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 01 07:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
1096 | TT_TASK | Lead time for replacement hangers from Starline | Mon Feb 01 08:00:00 IST 2021 | Sun Feb 07 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
1097 | TT_TASK | COLO-1 Cell-1 Remove/ Replace busway & hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1098 | TT_TASK | COLO-1 Cell-3 Remove/ Replace busway & hangers | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1099 | TT_TASK | COLO-1 Cell-2 Remove/ Replace busway & hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1100 | TT_TASK | COLO-1 Cell-4 Remove/ Replace busway & hangers | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1101 | TT_TASK | Determined Startline hanger Design Issue & Approve replacement hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
1102 | TT_TASK | COLO-2 Cell-1 Remove/ Replace busway & hangers | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1103 | TT_TASK | COLO-2 Cell-2 Remove/ Replace busway & hangers | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1105 | TT_TASK | Lead time for missing Admin Gen Bussing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 |  | COMPLETED
1106 | TT_TASK | Admin Gen Bussing Install | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1107 | TT_TASK | Awaiting DCE approval of Non NEMA standard Lugs | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1108 | TT_TASK | Awaiting Phase conductor lugs from NC power as per RFI#412 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1109 | TT_TASK | 6.1.41 - Incorrect Lugs for Admin Gen Main Bussing | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1112 | TT_TASK | COLO-1 Cell-4 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
1113 | TT_TASK | COLO-1 Cell-3 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Thu Mar 11 00:00:00 IST 2021 |  | COMPLETED
1114 | TT_TASK | COLO-1 Cell-2 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1115 | TT_TASK | COLO-1 Cell-1 SE Install UPS batteries in cabinet | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1117 | TT_TASK | COLO-2 Cell-1 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
1118 | TT_TASK | COLO-2 Cell-2 SE Install UPS batteries in cabinet | Fri Apr 30 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
1119 | TT_TASK | COLO-2 Cell-3 SE Install UPS batteries in cabinet | Sat May 08 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1120 | TT_TASK | COLO-2 Cell-4 SE Install UPS batteries in cabinet | Sat May 15 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
1122 | TT_TASK | COLO-3 Cell-1 SE Install UPS batteries in cabinet | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1123 | TT_TASK | COLO-3 Cell-2 SE Install UPS batteries in cabinet | Tue May 25 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1124 | TT_TASK | COLO-3 Cell-3 SE Install UPS batteries in cabinet | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1125 | TT_TASK | COLO-3 Cell-4 SE Install UPS batteries in cabinet | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1127 | TT_TASK | COLO-4 Cell-1 SE Install UPS batteries in cabinet | Tue Sep 14 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1128 | TT_TASK | COLO-4 Cell-2 SE Install UPS batteries in cabinet | Wed Sep 29 07:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  | 320.0 | IN_PROGRESS
1129 | TT_TASK | COLO-4 Cell-3 SE Install UPS batteries in cabinet | Tue Sep 07 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
1130 | TT_TASK | COLO-4 Cell-4 SE Install UPS batteries in cabinet | Tue Sep 21 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
1132 | TT_TASK | COLO-2 CEll-2 Awaiting SE Revised tool Come along for MER Lift & Set | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
1133 | TT_TASK | COLO-2 CEll-3 Awaiting SE Revised tool Come along for MER Lift & Set | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1134 | TT_TASK | MER shipping split connection Safety Standown & RCA Review | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1137 | TT_TASK | COLO-2 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1138 | TT_TASK | RFI#432 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
1139 | TT_TASK | Lead time for tube steel | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
1140 | TT_TASK | COLO-2 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1141 | TT_TASK | COLO-2 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Thu Apr 01 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1142 | TT_TASK | COLO-2 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1144 | TT_TASK | COLO-3 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Fri May 07 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 |  | COMPLETED
1145 | TT_TASK | COLO-3 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Wed May 19 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed May 19 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 |  | COMPLETED
1146 | TT_TASK | COLO-3 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Thu May 13 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Thu May 13 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 |  | COMPLETED
1147 | TT_TASK | COLO-3 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Wed May 26 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Wed May 26 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 |  | COMPLETED
1149 | TT_TASK | COLO-4 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1150 | TT_TASK | COLO-4 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1151 | TT_TASK | COLO-4 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1152 | TT_TASK | COLO-4 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Mon Jun 14 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1154 | TT_TASK | All Construction activities -Safety Standown due to Admin Gen unplanned Energization | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
1156 | TT_TASK | COLO-1 Cell-1 Field Modification of tray | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1157 | TT_TASK | COLO-1 Cell-2 Field Modification of tray | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Jan 21 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1160 | TT_TASK | #3. Snow- 1/27/2021(one full day) | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 |  | COMPLETED
1161 | TT_TASK | #4. Extreme Heat - 6/28/21- 7/2/21(Effecting COLO-4 Yard work) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
1162 | TT_TASK | #5 Extreme heat -production loss in Yards 7/1/21 through 7/14/21 (11 half days of loss) | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 09 00:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
1163 | TT_TASK | #6 Extreme heat - Production loss in Yards 7/15/21 through 7/31/21 (3 half days) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
1164 | TT_TASK | #1. Rain And High Winds- 10/13/2020(half day only) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Tue Oct 13 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1165 | TT_TASK | #2. Snow -12/30/20 (one full day) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Wed Dec 30 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
1168 | TT_TASK | COLO-1 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Mon Jan 11 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
1169 | TT_TASK | COLO-1 CELL-3 WA State L&I onsite inspection & Approval to Connect to MER | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1170 | TT_TASK | COLO-1 CELL-2 WA State L&I onsite inspection & Approval to Connect to MER | Sat Jan 23 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1171 | TT_TASK | COLO-1 CELL-4 WA State L&I onsite inspection & Approval to Connect to MER | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1173 | TT_TASK | COLO-2 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Fri Mar 12 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1174 | TT_TASK | COLO-2 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Tue Mar 23 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1175 | TT_TASK | COLO-2 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
1176 | TT_TASK | COLO-2 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Fri Apr 09 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1178 | TT_TASK | COLO-3 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Sat May 08 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1179 | TT_TASK | COLO-3 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Fri May 14 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1180 | TT_TASK | COLO-3 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1181 | TT_TASK | COLO-3 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1183 | TT_TASK | COLO-4 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 |  | COMPLETED
1184 | TT_TASK | COLO-4 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Sat Jun 19 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1185 | TT_TASK | COLO-4 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
1186 | TT_TASK | COLO-4 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 |  | COMPLETED
1189 | TT_TASK | 6.1.36 Rework for Addtional circuits for UMS URS Battery charger feed upsize | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1190 | TT_TASK | 6.1.34.1 COLO-1 Cell-1 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1191 | TT_TASK | 6.1.34.2 COLO-1 Cell-2 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1192 | TT_TASK | 6.1.34.3 COLO-1 Cell-3 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 |  | COMPLETED
1193 | TT_TASK | 6.1.34.4 COLO-1 Cell-4 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 |  | COMPLETED
1194 | TT_TASK | 6.1.01.0 Awaiting MER 10A HRG's (lead time= 8 weeks from 2/2/2021) | Mon Mar 01 07:00:00 IST 2021 | Mon Apr 12 17:00:00 IDT 2021 | Tue Feb 02 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
1195 | TT_TASK | 6.1.09 Awaiting Rev-D for Coordination study (DRB3/SCCS/ Submittal Breaker verification) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1196 | TT_TASK | 6.1.26.1 L2/L3 Scripts SE MER overall Script | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
1197 | TT_TASK | 6.1.33 URS UMS Ground Buss hole Pattern | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1198 | TT_TASK | 6.1.35 UPS battery IR Scanning | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1199 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-1 Cell-1 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1200 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-1 Cell-4 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1201 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-1 Cell-3 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1202 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-1 Cell-2 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1203 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-2 Cell-1 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1204 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-2 Cell-2 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1205 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-2 Cell-3 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1206 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-2 Cell-4 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue Jul 13 00:00:00 IDT 2021 | Mon Jul 19 00:00:00 IDT 2021 |  | COMPLETED
1207 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-3 Cell-1 | Tue Aug 31 07:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
1208 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-3 Cell-4 | Tue Sep 07 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  |  | 10.0 | NOT_STARTED
1209 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-3 Cell-3 | Tue Sep 07 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  |  | 10.0 | NOT_STARTED
1210 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-3 Cell-2 | Thu Sep 09 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1211 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-4 Cell-1 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1212 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-4 Cell-4 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1213 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-4 Cell-3 | Mon Oct 18 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1214 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-4 Cell-2 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1216 | TT_TASK | 6.1.37- 6.2.01- Ground Fault setting on COLO-2 Gen MCB01 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Wed Apr 28 17:00:00 IDT 2021 |  | COMPLETED
1218 | TT_TASK | 6.1.38 PDU MCB01 LOTO Provisions | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1220 | TT_TASK | 6.1.11 Awaiting BAS Backplanes from Siemens to VECA for Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
1221 | TT_TASK | 6.1.26.2 L2/L3 Scripts Siemens BAS SAT Scripts | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1222 | TT_TASK | 6.1.11 Awaiting Liftstation #3 BAS Backplanes from Siemens to VECA for Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1223 | TT_TASK | 6.1.11 Liftstation #3 BAS Install / Pull wire / term Backplanes | Mon May 17 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 |  | COMPLETED
1226 | TT_TASK | COLO-2 Cell-1 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Dec 29 00:00:00 IST 2020 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1227 | TT_TASK | COLO-2 Cell-2 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sun Jan 10 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1228 | TT_TASK | COLO-2 Cell-3 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Jan 20 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1229 | TT_TASK | COLO-2 Cell-4 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sat Jan 23 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1231 | TT_TASK | COLO-3 Cell-1 Install Missing Raceway & Bussing within generator | Mon Apr 26 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1232 | TT_TASK | COLO-3 Cell-2 Install Missing Raceway & Bussing within generator | Thu Apr 29 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1233 | TT_TASK | COLO-3 Cell-3 Install Missing Raceway & Bussing within generator | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
1234 | TT_TASK | COLO-3 Cell-4 Install Missing Raceway & Bussing within generator | Tue May 04 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1236 | TT_TASK | COLO-4 Cell-1 Install Missing Raceway & Bussing within generator | Tue May 25 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
1237 | TT_TASK | COLO-4 Cell-2 Install Missing Raceway & Bussing within generator | Tue May 11 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1238 | TT_TASK | COLO-4 Cell-3 Install Missing Raceway & Bussing within generator | Thu May 20 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1239 | TT_TASK | COLO-4 Cell-4 Install Missing Raceway & Bussing within generator | Mon May 17 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
1242 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1243 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 2weeks- fab and ship | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Mon Apr 05 00:00:00 IDT 2021 |  | COMPLETED
1244 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 1 week to install | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
1245 | TT_TASK | 6.1.44- MER Battery Monitoring Software Â– Constraint to EPMS checkouts/Point Â– Point(needed by 4/23) | Mon Mar 15 07:00:00 IST 2021 | Mon Jun 07 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Aug 07 07:00:00 IDT 2021 |  | COMPLETED
1246 | TT_TASK | 6.1.46- Site UPM Inspections | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
1247 | TT_TASK | 6.1.47- COLO-1 Cell-2 UPS01- Factory Test thermal event | Mon Mar 15 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
1249 | TT_TASK | 6.1.40- 480V house power to Gen Enclousure is Fed OH vs UG | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1254 | TT_TASK | Downtime awaiting solution for safety space constraint | Mon Apr 26 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1256 | TT_TASK | NOPC-18 Remove COLO-1 Cell-1 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1257 | TT_TASK | Rubicon MSB inspection complete (ready for transformer reinstall) | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Mon Apr 26 07:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1258 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-1 transformer | Tue May 25 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1260 | TT_TASK | NOPC-18 Remove COLO-1 Cell-2 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
1261 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1262 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-2 transformer | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1264 | TT_TASK | NOPC-18 Remove COLO-1 Cell-3 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 |  | COMPLETED
1265 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1266 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-3 transformer | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1268 | TT_TASK | NOPC-18 Remove COLO-1 Cell-4 transformer | Mon May 17 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1269 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1270 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-4 transformer | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1273 | TT_TASK | NOPC-18 Remove COLO-2 Cell-1 transformer | Tue Jun 01 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue Jun 08 00:00:00 IDT 2021 |  | COMPLETED
1274 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-1 transformer | Thu Jul 22 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1276 | TT_TASK | NOPC-18 Remove COLO-2 Cell-2 transformer | Wed Jun 02 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
1277 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-2 transformer | Fri Jul 23 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
1279 | TT_TASK | NOPC-18 Remove COLO-2 Cell-3 transformer | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 |  | COMPLETED
1280 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-3 transformer | Thu Jul 29 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1282 | TT_TASK | NOPC-18 Remove COLO-2 Cell-4 transformer | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1283 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-4 transformer | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Jul 09 00:00:00 IDT 2021 | Mon Jul 12 00:00:00 IDT 2021 |  | COMPLETED
1286 | TT_TASK | NOPC-18 Remove COLO-3 Cell-1 transformer | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
1287 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-1 transformer | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 22 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1289 | TT_TASK | NOPC-18 Remove COLO-3 Cell-2 transformer | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jul 24 07:00:00 IDT 2021 | Sat Jul 24 17:00:00 IDT 2021 |  | COMPLETED
1290 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-2 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
1292 | TT_TASK | NOPC-18 Remove COLO-3 Cell-3 transformer | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Thu Aug 19 07:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1293 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-3 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1295 | TT_TASK | NOPC-18 Remove COLO-3 Cell-4 transformer | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1296 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-4 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1299 | TT_TASK | NOPC-18 Remove COLO-4 Cell-1 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1300 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-1 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1302 | TT_TASK | NOPC-18 Remove COLO-4 Cell-2 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1303 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-2 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1305 | TT_TASK | NOPC-18 Remove COLO-4 Cell-3 transformer | Wed Sep 29 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1306 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-3 transformer | Sat Oct 09 07:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1308 | TT_TASK | NOPC-18 Remove COLO-4 Cell-4 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1309 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-4 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1311 | TT_TASK | PDU termination crew downtime due to COVID-19 | Sat Apr 24 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Sat Apr 24 07:00:00 IDT 2021 |  | COMPLETED
1314 | TT_TASK | 6.2.03- Replace ADP01 faulty trip units | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1315 | TT_TASK | 6.1.51-COLO-1 Cell-1,2 Factory conductors not terminated per drawings | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1316 | TT_TASK | 6.1.49 - COLO-1 Cell-1 Awaiting Ground Lug solution, procurement, installation of labelling ATS 01-06 | Fri Apr 30 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
1317 | TT_TASK | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
1318 | TT_TASK | 6.1.53-COLO-1 Cell-1,2 UPS01, PNL01 awaiting missing breakers | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1319 | TT_TASK | 6.1.53-COLO-1 Cell-1,2,3,4 UPS01, PNL01 Install/ term Missing breakers | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1320 | TT_TASK | 6.1.59 (6.1.51 carryover) -COLO-1 Cell-1,2 Factory conductors exertherm corrections | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
1321 | TT_TASK | 6.1.50- SCCS Revision#10 (RFI-540) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1325 | TT_TASK | 6.1.54- TCM Awaiting Admin Siemens Break tank parts | Mon May 17 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1326 | TT_TASK | 6.1.54- Install Breaktank parts | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1328 | TT_TASK | 6.2.03- Replace Damaged UPM in COLO-4 Cell-4 | Thu May 06 07:00:00 IDT 2021 | Sat May 08 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1330 | TT_TASK | 6.1.55-COLO-1 - FC Factoy Re-wire (RFI-502) | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1331 | TT_TASK | 6.1.55-COLO-2 - FC Factoy Re-wire (RFI-502) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1332 | TT_TASK | 6.1.55-COLO-3 - FC Factoy Re-wire (RFI-502) | Sat Jun 05 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1333 | TT_TASK | 6.1.55-COLO-4 - FC Factoy Re-wire (RFI-502) | Thu Jun 10 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1335 | TT_TASK | 6.1.57 -Awaiting revised coordination study #9 | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
1336 | TT_TASK | Reprint revised panel 3,4 Arc flash labels | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1337 | TT_TASK | Print new DC Arc flash labels for Admin ELP | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1340 | TT_TASK | 6.1.58-RFI-528- COLO-1 - SF/RF Circuitry & terminal block rework | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
1341 | TT_TASK | 6.1.63- COLO1-UPS01-PNL01 Compass Issues Constraining L3Â’s | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
1342 | TT_TASK | 6.1.56 - COLO-1 Awaiting MSB/ADP Ground Lug replacements, Installation of labelling | Fri Apr 30 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
1349 | TT_TASK | All trades stand down | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
1350 | TT_TASK | Veca standown | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
1353 | TT_TASK | COLO-1 Cell-1 MER-UPS Battery Disconnect modifications rework | Wed Jun 16 07:00:00 IDT 2021 | Sat Jun 19 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1354 | TT_TASK | COLO-1 Cell-2 MER-UPS Battery Disconnect modifications rework | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1355 | TT_TASK | COLO-1 Cell-3 MER-UPS Battery Disconnect modifications rework | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
1356 | TT_TASK | COLO-1 Cell-4 MER-UPS Battery Disconnect modifications rework | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
1357 | TT_TASK | RFI-548 COLO MSB to UPS Battery disconnect solution approval | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1358 | TT_TASK | ADMIN-UPS Battery Disconnect modifications rework | Wed Jun 16 07:00:00 IDT 2021 | Sat Jun 19 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1359 | TT_TASK | RFI-552 Admin MSB to UPS Battery disconnect solution approval | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
1361 | TT_TASK | COLO-2 Cell-2 MER-UPS Battery Disconnect modifications rework | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 |  | COMPLETED
1362 | TT_TASK | COLO-2 Cell-1 MER-UPS Battery Disconnect modifications rework | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  | COMPLETED
1363 | TT_TASK | COLO-2 Cell-3 MER-UPS Battery Disconnect modifications rework | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  | COMPLETED
1364 | TT_TASK | COLO-2 Cell-4 MER-UPS Battery Disconnect modifications rework | Fri Jul 02 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 23 07:00:00 IDT 2021 |  | COMPLETED
1366 | TT_TASK | COLO-3 Cell-1 MER-UPS Battery Disconnect modifications rework | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 |  | COMPLETED
1367 | TT_TASK | COLO-3 Cell-2 MER-UPS Battery Disconnect modifications rework | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1368 | TT_TASK | COLO-3 Cell-3 MER-UPS Battery Disconnect modifications rework | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
1369 | TT_TASK | COLO-3 Cell-4 MER-UPS Battery Disconnect modifications rework | Sat Sep 11 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Mon Aug 16 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1371 | TT_TASK | COLO-4 Cell-1 MER-UPS Battery Disconnect modifications rework | Thu Sep 16 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
1372 | TT_TASK | COLO-4 Cell-2 MER-UPS Battery Disconnect modifications rework | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
1373 | TT_TASK | COLO-4 Cell-3 MER-UPS Battery Disconnect modifications rework | Mon Sep 27 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1374 | TT_TASK | COLO-4 Cell-4 MER-UPS Battery Disconnect modifications rework | Fri Sep 03 07:00:00 IDT 2021 | Thu Sep 09 17:00:00 IDT 2021 |  |  | 270.0 | NOT_STARTED
1377 | TT_TASK | COLO-3 Cell-3 Remove inaccessible tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 |  | COMPLETED
1378 | TT_TASK | COLO-3 CEll-3 Reinstall tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
1379 | TT_TASK | COLO-3 Cell-4 Remove inaccessible tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Sat Jun 12 00:00:00 IDT 2021 |  | COMPLETED
1380 | TT_TASK | COLO-3 Cell-4 Reinstall tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1381 | TT_TASK | COLO-4 Cell-1 Remove inaccessible tray in MER | Mon Jul 12 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Sat Jun 12 00:00:00 IDT 2021 |  | COMPLETED
1382 | TT_TASK | COLO-4 Cell-1 Reinstall tray in MER | Tue Aug 03 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
1383 | TT_TASK | COLO-4 Cell-2 Remove inaccessible tray in MER | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
1384 | TT_TASK | COLO-4 Cell-2 Reinstall tray in MER | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1385 | TT_TASK | COLO-4 Cell-3 Remove inaccessible tray in MER | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Thu Jul 15 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
1386 | TT_TASK | COLO-4 Cell-3 Reinstall tray in MER | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
1387 | TT_TASK | COLO-4 Cell-4 Remove inaccessible tray in MER4 | Wed Aug 04 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
1388 | TT_TASK | COLO-4 Cell-4 Reinstall tray in MER | Fri Sep 03 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Mon Aug 09 07:00:00 IDT 2021 | Thu Aug 12 00:00:00 IDT 2021 |  | COMPLETED
1389 | TT_TASK | COLO-3 Cell-1 Remove inaccessible tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
1390 | TT_TASK | COLO-3 CEll-1 Reinstall tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 |  | COMPLETED
1391 | TT_TASK | COLO-3 Cell-2 Remove inaccessible tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1392 | TT_TASK | COLO-3 Cell-2 Reinstall tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1395 | TT_TASK | COLO-3 Cell-3 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 14 00:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1397 | TT_TASK | COLO-4 Cell-1 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Fri Jul 23 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1398 | TT_TASK | COLO-4 Cell-2 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
1399 | TT_TASK | COLO-4 Cell-3 Conduit rework | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 |  | COMPLETED
1400 | TT_TASK | COLO-4 Cell-4 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1404 | TT_TASK | 6.1-88 COLO-1 MER awaiting updated UPS L3 test script approval | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 31 07:00:00 IDT 2021 |  | COMPLETED
1405 | TT_TASK | 6.1-89 RFI574- COLO-1 Relocating MSB EPMS device to different cabinet | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1406 | TT_TASK | 6.1-92 COLO-1 SF/ RF startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
1407 | TT_TASK | 6.1-93 COLO-1 HVAC minisplits startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1409 | TT_TASK | 6.2-08 COLO-2 Cell- 1,2 MER equipment Phenolic labelling | Wed Jul 14 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
1410 | TT_TASK | 6.2-08 COLO-2 Cell- 3,4 MER equipment Phenolic labelling | Wed Jul 14 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Mon Aug 02 00:00:00 IDT 2021 |  | COMPLETED
1411 | TT_TASK | 6.2-12 COLO-2 All Cells- Factory connection Torque verification | Wed Jul 14 07:00:00 IDT 2021 | Wed Jul 21 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
1413 | TT_TASK | 6.1-95 COLO-1 ATS's L3 startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  | COMPLETED
1415 | TT_TASK | 6.1-96 COLO-1 PDU - EPMS L3 startup delay (vendor schedule availability) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Mon Aug 02 07:00:00 IDT 2021 |  | COMPLETED
1420 | TT_TASK | COLO-2 Cell-1 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1421 | TT_TASK | COLO-2 Cell-2 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1422 | TT_TASK | COLO-2 Cell-3 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1423 | TT_TASK | COLO-2 Cell-4 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 00:00:00 IDT 2021 |  | COMPLETED
1429 | TT_TASK | 6.1-98 Admin/COLO-1 ASCO EPMS Connectivity Issues | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1430 | TT_TASK | 6.1-88 Admin/ COLO-1 MER/ADMIN UPS L3 Testing (includes shutdown to move PQM's & PQM data post proccessing) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 31 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1431 | TT_TASK | 6.1-106 COLO-1 Cell-2 UPS01 Power module failure | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1433 | TT_TASK | COLO-2 Cell-1 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1434 | TT_TASK | COLO-2 Cell-3 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1435 | TT_TASK | COLO-2 Cell-4 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1437 | TT_TASK | COLO-3 Delay in SE uploading QC Checkilst | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Fri Aug 06 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1439 | TT_TASK | COLO-2 Cell-2 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1442 | TT_TASK | Mobilization | Mon Apr 27 07:00:00 IDT 2020 | Wed May 20 17:00:00 IDT 2020 | Mon Apr 06 00:00:00 IDT 2020 | Sat May 02 17:00:00 IDT 2020 |  | COMPLETED
1444 | TT_TASK | Establish Access Roads / Laydown / Craft Parking / Temp Utilities | Thu May 14 07:00:00 IDT 2020 | Fri Jun 19 17:00:00 IDT 2020 | Fri Apr 24 00:00:00 IDT 2020 | Sat May 23 00:00:00 IDT 2020 |  | COMPLETED
1446 | TT_TASK | Site Sanitary | Mon May 11 07:00:00 IDT 2020 | Fri Jul 24 17:00:00 IDT 2020 | Tue May 05 00:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 |  | COMPLETED
1447 | TT_TASK | Remaining Site Sanitary | Mon May 11 07:00:00 IDT 2020 | Fri Jul 24 17:00:00 IDT 2020 | Tue Aug 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
1448 | TT_TASK | IWW System | Tue May 26 07:00:00 IDT 2020 | Sat Aug 08 17:00:00 IDT 2020 | Mon May 18 00:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 |  | COMPLETED
1449 | TT_TASK | Remaining IWW System | Tue May 26 07:00:00 IDT 2020 | Sat Aug 08 17:00:00 IDT 2020 | Tue Aug 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
1450 | TT_TASK | Site Water / Fire Loop | Fri Jul 24 07:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1451 | TT_TASK | Site Storm | Mon Jun 29 07:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
1454 | TT_TASK | Telecom-Communications Site Loop/Ductbank | Mon Jun 29 08:00:00 IDT 2020 | Thu Oct 01 08:00:00 IDT 2020 | Thu Jun 25 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1455 | TT_TASK | Telecom-RNG Fiber Underground installation | Mon Feb 01 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
1456 | TT_TASK | Telecom-RNG Fiber CNR buildout | Mon Oct 05 07:00:00 IDT 2020 | Tue Dec 08 17:00:00 IST 2020 | Mon Oct 05 07:00:00 IDT 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
1461 | TT_TASK | Temp Power/ Telecom duct bank | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Thu Aug 27 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1462 | TT_TASK | Vault- set 1st Vault Along UMS Duct bank run | Thu Sep 03 07:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1463 | TT_TASK | Vault- Set 2nd vault Along UMS Duct Run near COLO-2 | Tue Sep 08 07:00:00 IDT 2020 | Thu Sep 10 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1464 | TT_TASK | Vault- Set vault along URS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1465 | TT_TASK | Vault- Set vault along UMS to JAZ run | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1466 | TT_TASK | Set URS Vault | Mon Nov 16 08:00:00 IST 2020 | Wed Nov 25 08:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1467 | TT_TASK | Set UMS vault | Wed Nov 25 08:00:00 IST 2020 | Tue Dec 08 08:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1469 | TT_TASK | Vault- Set North vault- Along UPM to Vault | Fri Oct 09 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1470 | TT_TASK | Vault - Set North Vault Along Vault to URS run | Fri Oct 23 07:00:00 IDT 2020 | Tue Oct 27 17:00:00 IST 2020 | Thu Aug 20 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1471 | TT_TASK | Vault - Set South Vault Along Vault to URS run | Sat Nov 07 07:00:00 IST 2020 | Tue Nov 10 17:00:00 IST 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1472 | TT_TASK | Vault - Set South Vault along UPM to Vault | Mon Nov 23 07:00:00 IST 2020 | Wed Nov 25 17:00:00 IST 2020 | Thu Aug 20 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1475 | TT_TASK | Duct bank- COLO-1 UPM to north vault | Mon Oct 19 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Fri Oct 02 00:00:00 IDT 2020 | Mon Oct 05 00:00:00 IDT 2020 |  | COMPLETED
1476 | TT_TASK | Duct bank- COLO-2 UPM to north Valut | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Mon Oct 05 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1477 | TT_TASK | Duct Bank- Building to URS - 1st Half | Sat Sep 26 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 07:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
1478 | TT_TASK | Duct Bank- Building to URS(upto horse shoe) - 2nd Half | Wed Sep 30 07:00:00 IDT 2020 | Thu Oct 08 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
1479 | TT_TASK | Duct Bank - JAZ to vault- UMS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Thu Oct 29 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1480 | TT_TASK | Duct Bank - Vault to Vault along UMS duct Run - horseshoe | Mon Oct 26 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
1481 | TT_TASK | Duct Bank - COLO-3 UPM to Vault UMS Run | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1482 | TT_TASK | Duct Bank - URS to vault - URS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1483 | TT_TASK | Duct Bank - Vault To JAZ - URS to JAZ run | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 09 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1484 | TT_TASK | Duct Bank - Vault to UMS- UMS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1485 | TT_TASK | Duct Bank - south vault (along UMS duct run) to UMS | Sat Nov 21 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1486 | TT_TASK | Duct Bank - COLO-4 UPM to UMS | Mon Nov 23 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
1488 | TT_TASK | Duct Bank - COLO1- UPM to UPM | Mon Aug 10 07:00:00 IDT 2020 | Thu Aug 13 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1489 | TT_TASK | Duct Bank - COLO2- UPM to UPM | Mon Aug 31 07:00:00 IDT 2020 | Thu Sep 03 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
1490 | TT_TASK | Duct Bank - North Crossover (URS to west Vault Run) | Mon Sep 14 07:00:00 IDT 2020 | Sat Sep 26 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
1491 | TT_TASK | Duct Bank - South Cross over (URS to west Vault Run) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
1492 | TT_TASK | Duct Bank - COLO-3 UPM to UPM | Fri Nov 06 07:00:00 IST 2020 | Tue Nov 10 17:00:00 IST 2020 | Sat Oct 10 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1493 | TT_TASK | Duct Bank - COLO-4 UPM to UPM | Wed Nov 25 07:00:00 IST 2020 | Wed Dec 02 17:00:00 IST 2020 | Sat Oct 10 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1495 | TT_TASK | Duct Bank Admin UPM to COLO-1 UPM | Thu Sep 24 07:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1496 | TT_TASK | Duct Back- Admin UPM to Vault | Fri Oct 23 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Mon Aug 24 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
1497 | TT_TASK | Duct Bank COLO-2 UPM to Vault | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Mon Sep 28 00:00:00 IDT 2020 | Thu Oct 01 00:00:00 IDT 2020 |  | COMPLETED
1498 | TT_TASK | Duct Bank - Building to North Vault URS run | Fri Oct 23 07:00:00 IDT 2020 | Sat Oct 31 17:00:00 IST 2020 | Fri Oct 02 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1499 | TT_TASK | Duct Bank - Builing to South Vault- URS Run | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 09 17:00:00 IST 2020 | Fri Oct 02 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1500 | TT_TASK | Duct Bank - Vault to COLO-3 UPM | Tue Nov 10 07:00:00 IST 2020 | Fri Nov 13 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1501 | TT_TASK | Duct Bank - Vault to COLO-4 UPM | Mon Nov 16 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1503 | TT_TASK | Set MV Gear (URS) | Mon Nov 23 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1504 | TT_TASK | Set MV Gear (UMS) | Mon Dec 21 07:00:00 IST 2020 | Mon Dec 28 17:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
1506 | TT_TASK | Pull UPM to UPM COLO-1 - CELL-1 to Cell-3 | Tue Jan 05 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1507 | TT_TASK | Pul UPM to UPM COLO-2- CELL-1 to Cell-3 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Sat Jan 02 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
1508 | TT_TASK | Pull UPM to UPM COLO-3 - CELL-1 to Cell-3 | Fri Jan 15 07:00:00 IST 2021 | Mon Jan 18 17:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1509 | TT_TASK | Pull UPM to UPM COLO-4 - CELL-1 to Cell-3 | Wed Feb 03 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
1511 | TT_TASK | Pull UPM to UPM Admin to COLO-1 Cell -2 | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1512 | TT_TASK | Pull UPM to UPM COLO-1 Cell 2- Cell - 4 | Thu Jan 07 07:00:00 IST 2021 | Fri Jan 08 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1513 | TT_TASK | Pull UPM to UPM COLO-2 Cell 2- Cell - 4 | Wed Feb 03 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1514 | TT_TASK | Pull UPM to UPM COLO-3 Cell 2- Cell - 4 | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1515 | TT_TASK | Pull UPM to UPM COLO-4 Cell 2- Cell - 4 | Thu Feb 11 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1517 | TT_TASK | Pull Cross Overs- COLO-1 CELL-3 to CELL-4 | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1518 | TT_TASK | Pull Cross Overs- COLO-2 CELL-3 to CELL-4 | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1519 | TT_TASK | Pull Cross Overs- COLO-3 CELL-3 to CELL-4 | Tue Feb 09 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1520 | TT_TASK | Pull Cross Overs- COLO-4 CELL-3 to CELL-4 | Sat Feb 13 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1522 | TT_TASK | PULL- URS to Admin | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Sat Dec 05 00:00:00 IST 2020 |  | COMPLETED
1523 | TT_TASK | PULL- URS to COLO-2 | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
1524 | TT_TASK | PULL- URS to COLO-3 | Tue Jan 12 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1525 | TT_TASK | PULL- URS to COLO-4 | Mon Jan 18 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1527 | TT_TASK | Pull- UMS to COLO-1,2,3 | Tue Jan 12 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Jan 11 17:00:00 IST 2021 |  | COMPLETED
1528 | TT_TASK | Pull- UMS to COLO-4 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 |  | COMPLETED
1530 | TT_TASK | Pull - JAZ to URS | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
1531 | TT_TASK | Pull - JAZ to UMS | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1534 | TT_TASK | Term COLO -1 Cell-3 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1535 | TT_TASK | Term COLO -2 Cell-3 UPM | Thu Mar 04 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1536 | TT_TASK | Term COLO -3 Cell-3 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 |  | COMPLETED
1537 | TT_TASK | Term COLO -4 Cell-3 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1538 | TT_TASK | Term COLO -1 Cell-1 UPM | Wed Feb 10 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1539 | TT_TASK | Term COLO -2 Cell-1 UPM | Sat Feb 13 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1540 | TT_TASK | Term COLO -3 Cell-1 UPM | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1541 | TT_TASK | Term COLO -4 Cell-1 UPM | Thu Mar 11 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1543 | TT_TASK | Term COLO -1 Cell-4 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
1544 | TT_TASK | Term COLO -2 Cell-4 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1545 | TT_TASK | Term COLO -3 Cell-4 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1546 | TT_TASK | Term COLO -4 Cell-4 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1547 | TT_TASK | Term Admin - UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1548 | TT_TASK | Term COLO -1 Cell-2 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
1549 | TT_TASK | Term COLO -2 Cell-2 UPM | Fri Feb 05 07:00:00 IST 2021 | Tue Feb 09 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1550 | TT_TASK | Term COLO -3 Cell-2 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1551 | TT_TASK | Term COLO -4 Cell-2 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1553 | TT_TASK | Battery Station Yellow tagging / EPMS Checkouts | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1554 | TT_TASK | GCPUD NORTH Mobile substation maintance & Mobile Sub re-energization 4/1 Â– 4/3 | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1555 | TT_TASK | GCPUD SOUTH Mobile substation maintance & Mobile Sub re-energization 4/1 Â– 4/3 | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1556 | TT_TASK | Term- UMS- Line Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1557 | TT_TASK | Term- JAZ to Structure- (Incl Stress Cones) from ums | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1558 | TT_TASK | Term- UMS- Load side | Wed Feb 10 07:00:00 IST 2021 | Tue Feb 23 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1559 | TT_TASK | Yellow Tagging for UMS (includes GC, vendor Lvl-2) | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
1560 | TT_TASK | UMS Control Power Available CYT | Wed Feb 10 07:00:00 IST 2021 | Wed Feb 17 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
1562 | TT_TASK | Term URS- Line Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
1563 | TT_TASK | Term- JAS to URS- (Incl Stress Cones) | Wed Feb 03 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1564 | TT_TASK | TERM- URS- Load Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1565 | TT_TASK | Yellow Tagging for URS | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
1566 | TT_TASK | URS Control Power Available CYT | Wed Feb 10 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
1568 | TT_TASK | Aggregate Road Base | Mon Oct 19 07:00:00 IDT 2020 | Tue Nov 24 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
1569 | TT_TASK | Plant shutdown for winter | Mon Nov 30 07:00:00 IST 2020 | Tue Apr 06 17:00:00 IDT 2021 | Mon Nov 23 00:00:00 IST 2020 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
1570 | TT_TASK | Curb & Gutter | Mon Nov 30 07:00:00 IST 2020 | Sat Jan 09 17:00:00 IST 2021 | Mon Nov 02 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1571 | TT_TASK | Pave HMA | Mon Apr 05 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Sat Nov 07 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1572 | TT_TASK | Site Lighting | Mon May 03 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 |  | 120.0 | IN_PROGRESS
1575 | TT_TASK | Landscape and Site Specialties | Mon May 17 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1581 | TT_TASK | Perimeter Foundations - Excavate/FRP | Mon Apr 27 07:00:00 IDT 2020 | Thu May 14 17:00:00 IDT 2020 | Wed Apr 22 00:00:00 IDT 2020 | Wed May 20 00:00:00 IDT 2020 |  | COMPLETED
1582 | TT_TASK | Perimeter Foundations - Waterproof/Backfill | Mon Jun 01 07:00:00 IDT 2020 | Thu Jun 04 17:00:00 IDT 2020 | Wed May 27 00:00:00 IDT 2020 | Fri Jun 05 00:00:00 IDT 2020 |  | COMPLETED
1583 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Fri Jun 05 07:00:00 IDT 2020 | Tue Jun 16 17:00:00 IDT 2020 | Tue Jun 02 00:00:00 IDT 2020 | Fri Jun 12 00:00:00 IDT 2020 |  | COMPLETED
1585 | TT_TASK | Erect PEMB Steel | Mon Jun 29 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 |  | COMPLETED
1586 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Thu Jul 02 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
1588 | TT_TASK | MEP Undeground Rough-In (Interior) | Tue Aug 18 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1589 | TT_TASK | Aggregate Base Course | Mon Aug 31 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 |  | COMPLETED
1590 | TT_TASK | Slab on Grade | Mon Sep 14 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1592 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Aug 18 07:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 |  | COMPLETED
1593 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Tue Jul 14 00:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 |  | COMPLETED
1594 | TT_TASK | Downspouts & Gutters | Tue Aug 18 07:00:00 IDT 2020 | Sat Aug 29 17:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
1604 | TT_TASK | Perimeter Foundations - Excavate/FRP | Fri May 15 07:00:00 IDT 2020 | Wed Jun 03 17:00:00 IDT 2020 | Mon May 04 00:00:00 IDT 2020 | Fri May 15 00:00:00 IDT 2020 |  | COMPLETED
1605 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Sat Jun 13 07:00:00 IDT 2020 | Thu Jun 25 17:00:00 IDT 2020 | Tue Jun 02 00:00:00 IDT 2020 | Fri Jun 12 00:00:00 IDT 2020 |  | COMPLETED
1606 | TT_TASK | Perimeter Foundations - Waterproof Backfill | Tue May 26 07:00:00 IDT 2020 | Sat Jun 06 17:00:00 IDT 2020 | Tue May 26 07:00:00 IDT 2020 | Wed Jun 17 00:00:00 IDT 2020 |  | COMPLETED
1608 | TT_TASK | Erect PEMB Steel | Mon Jun 29 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Fri Jun 26 00:00:00 IDT 2020 | Mon Jul 06 00:00:00 IDT 2020 |  | COMPLETED
1609 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 |  | COMPLETED
1610 | TT_TASK | Erect Interior Structural Steel | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
1612 | TT_TASK | MEP Undeground Rough-In (Interior) | Fri Aug 14 07:00:00 IDT 2020 | Tue Sep 01 17:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1613 | TT_TASK | Aggregate Base Course | Sat Sep 05 07:00:00 IDT 2020 | Fri Sep 11 17:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 |  | COMPLETED
1614 | TT_TASK | Slab on Grade | Mon Sep 14 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1618 | TT_TASK | Exterior Insulated Metal Panels Installation - East Elevation | Tue Aug 18 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Mon Jul 13 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1621 | TT_TASK | Exterior Insulated Metal Panels Installation - West Elevation | Tue Aug 18 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Mon Jul 13 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1623 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 |  | COMPLETED
1624 | TT_TASK | Downspouts & Gutters | Tue Aug 18 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Wed Aug 12 00:00:00 IDT 2020 |  | COMPLETED
1629 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jun 22 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Mon May 11 00:00:00 IDT 2020 | Tue Jun 16 00:00:00 IDT 2020 |  | COMPLETED
1630 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Wed Jul 08 07:00:00 IDT 2020 | Mon Jul 20 17:00:00 IDT 2020 | Tue Jun 09 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
1632 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Tue Jul 07 00:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 |  | COMPLETED
1633 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 | Tue Aug 04 00:00:00 IDT 2020 |  | COMPLETED
1634 | TT_TASK | Erect Interior Structural Steel | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1636 | TT_TASK | MEP Undeground Rough-In (Interior) | Mon Aug 31 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 |  | COMPLETED
1637 | TT_TASK | Aggregate Base Course | Mon Oct 19 07:00:00 IDT 2020 | Mon Oct 26 17:00:00 IST 2020 | Thu Oct 01 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1638 | TT_TASK | Slab on Grade | Mon Oct 19 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1640 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Aug 18 07:00:00 IDT 2020 | Tue Sep 01 17:00:00 IDT 2020 | Fri Jul 31 00:00:00 IDT 2020 | Thu Aug 13 00:00:00 IDT 2020 |  | COMPLETED
1641 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Wed Aug 26 17:00:00 IDT 2020 | Fri Jul 31 00:00:00 IDT 2020 | Fri Aug 14 00:00:00 IDT 2020 |  | COMPLETED
1642 | TT_TASK | Downspouts & Gutters | Sat Sep 05 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 |  | COMPLETED
1647 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Wed Jul 08 07:00:00 IDT 2020 | Mon Jul 20 17:00:00 IDT 2020 | Wed Jun 24 00:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 |  | COMPLETED
1648 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jun 22 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Tue Jun 16 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1650 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 |  | COMPLETED
1651 | TT_TASK | Secondary Steel | Mon Aug 31 07:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 |  | COMPLETED
1652 | TT_TASK | Erect Interior Structural Steel | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1654 | TT_TASK | MEP Undeground Rough-In (Interior) | Mon Oct 19 07:00:00 IDT 2020 | Thu Nov 05 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1655 | TT_TASK | Aggregate Base Course | Fri Nov 06 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1656 | TT_TASK | Slab on Grade | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
1658 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Sep 08 07:00:00 IDT 2020 | Tue Sep 22 17:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1659 | TT_TASK | Roof Panels Installation | Tue Sep 08 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 | Tue Sep 01 00:00:00 IDT 2020 |  | COMPLETED
1660 | TT_TASK | Downspouts & Gutters | Wed Sep 16 07:00:00 IDT 2020 | Tue Sep 22 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
1670 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jul 06 07:00:00 IDT 2020 | Thu Jul 23 17:00:00 IDT 2020 | Tue Jun 23 00:00:00 IDT 2020 | Thu Jul 30 00:00:00 IDT 2020 |  | COMPLETED
1671 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Sat Aug 29 07:00:00 IDT 2020 | Thu Sep 10 17:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 |  | COMPLETED
1673 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Sat Aug 08 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
1674 | TT_TASK | Secondary Steel | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 08 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1675 | TT_TASK | Erect Interior Structural Steel | Mon Dec 21 07:00:00 IST 2020 | Tue Dec 29 17:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
1677 | TT_TASK | MEP Undeground Rough-In (Interior) | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1678 | TT_TASK | Aggregate Base Course | Wed Nov 11 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
1679 | TT_TASK | Slab on Grade | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1681 | TT_TASK | Exterior Insulated Metal Panels Installation | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Sep 30 00:00:00 IDT 2020 |  | COMPLETED
1682 | TT_TASK | Roof Panels Installation | Thu Sep 03 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Thu Aug 27 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1683 | TT_TASK | Downspouts & Gutters | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Sep 07 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1693 | TT_TASK | Hang Wall Partitions | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1694 | TT_TASK | Hang Wall Partitions- Early Walls | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1695 | TT_TASK | MEP Rough-In / Wall & Ceiling | Mon Oct 19 07:00:00 IDT 2020 | Mon Nov 02 17:00:00 IST 2020 | Thu Oct 01 00:00:00 IDT 2020 | Tue Nov 17 00:00:00 IST 2020 |  | COMPLETED
1697 | TT_TASK | Early Room - Finishes | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1699 | TT_TASK | Loading Dock Equipment & Dock Doors | Wed May 05 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
1700 | TT_TASK | MEP Overhead | Mon Oct 19 07:00:00 IDT 2020 | Tue Nov 17 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1701 | TT_TASK | Ceilings / Ligthing / FA Devices | Mon Mar 01 07:00:00 IST 2021 | Tue Apr 13 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
1702 | TT_TASK | Concrete Floor Sealing/Epoxy | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1706 | TT_TASK | Generator Term | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
1707 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 | Fri Sep 25 00:00:00 IDT 2020 |  | COMPLETED
1708 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Fri Sep 18 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
1709 | TT_TASK | Set Exterior Electrical OFCI Equipment | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1710 | TT_TASK | Admin -Electrical Underground Rough-In | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 31 17:00:00 IDT 2020 | Fri Aug 07 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
1711 | TT_TASK | Generator & Utility Power Pull-Test | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1712 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Jan 18 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1713 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1715 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Oct 19 07:00:00 IDT 2020 | Mon Nov 02 17:00:00 IST 2020 | Fri Oct 09 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1716 | TT_TASK | Set Exterior Mechanical CFCI Equipment (remaning mini splits) | Fri Nov 06 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1717 | TT_TASK | Mechanical Underground Rough-In | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 31 17:00:00 IDT 2020 | Sat Aug 08 00:00:00 IDT 2020 | Tue Aug 25 00:00:00 IDT 2020 |  | COMPLETED
1718 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1721 | TT_TASK | Fire Alarm Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1722 | TT_TASK | Controls Installation | Tue Feb 16 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
1724 | TT_TASK | Set Electrical Equipment incl. OH raceways | Mon Nov 23 07:00:00 IST 2020 | Wed Jan 13 17:00:00 IST 2021 | Mon Nov 16 00:00:00 IST 2020 | Tue Dec 29 00:00:00 IST 2020 |  | COMPLETED
1725 | TT_TASK | Electrical Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1727 | TT_TASK | Domestic Water Piping | Mon Nov 23 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1728 | TT_TASK | Plumbing Devices & Trim | Mon Jul 26 15:00:00 IDT 2021 | Tue Aug 17 15:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
1730 | TT_TASK | Security Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
1732 | TT_TASK | Mechanical Ductwork Installation | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1733 | TT_TASK | Set Mechanical Equipment | Mon Nov 23 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
1734 | TT_TASK | Mechanical Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1739 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1740 | TT_TASK | Overhead MEPFP Rough-In | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 11 17:00:00 IST 2020 | Wed Oct 14 00:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
1741 | TT_TASK | Early Topout | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1743 | TT_TASK | Sprinkler Test | Mon Dec 21 07:00:00 IST 2020 | Tue Dec 22 17:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1744 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1747 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1748 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1749 | TT_TASK | Early Topout | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Tue Nov 10 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1751 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Nov 30 07:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1754 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 |  | COMPLETED
1755 | TT_TASK | Overhead MEPFP Rough-In | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 11 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 |  | COMPLETED
1756 | TT_TASK | Early Topout | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1758 | TT_TASK | Datahall Finishes- Ceiling Grid | Thu Dec 03 07:00:00 IST 2020 | Tue Dec 15 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1761 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1762 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1763 | TT_TASK | Early Topout | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Tue Nov 10 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1765 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1768 | TT_TASK | Remaining MER raceway across Mech chase | Tue Dec 01 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1769 | TT_TASK | Electrical OH Below Mechanical Piping | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1770 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1771 | TT_TASK | OverHead MEPFP Rough-In ( Add TCM Cross over piping HRA Level-3) | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1772 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1774 | TT_TASK | Mechanical Corridor Finishes | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1777 | TT_TASK | Remaining MER raceway across Mech chase | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1778 | TT_TASK | Electrical OH Below Mechanical Piping | Wed Jan 20 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1779 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 11 00:00:00 IST 2020 |  | COMPLETED
1780 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1781 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1783 | TT_TASK | Mechanical Corridor Finishes | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1786 | TT_TASK | Remaining MER raceway across Mech chase | Tue Dec 01 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1787 | TT_TASK | Electrical OH Below Mechanical Piping | Mon Jan 04 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1788 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1789 | TT_TASK | OverHead MEPFP Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1790 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1792 | TT_TASK | Mechanical Corridor Finishes | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1795 | TT_TASK | Remaining MER raceway across Mech chase | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1796 | TT_TASK | Electrical OH Below Mechanical Piping | Wed Jan 20 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1797 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 11 00:00:00 IST 2020 |  | COMPLETED
1798 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1799 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1801 | TT_TASK | Mechanical Corridor Finishes | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Tue Nov 17 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1805 | TT_TASK | Generator & Utility Power Term | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1806 | TT_TASK | Remaining Mechanical Equipment (ADP01) Termimations | Thu Mar 18 07:00:00 IST 2021 | Tue Mar 23 17:00:00 IST 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1807 | TT_TASK | Electrical Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 14 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1808 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1809 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1810 | TT_TASK | Exterior Equipment Pads - Electrical | Thu Sep 03 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1811 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Oct 12 07:00:00 IDT 2020 | Mon Oct 26 17:00:00 IST 2020 | Mon Oct 12 07:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1812 | TT_TASK | Lift & Set MER in Place | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Wed Dec 16 00:00:00 IST 2020 | Wed Dec 16 17:00:00 IST 2020 |  | COMPLETED
1813 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
1814 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 13 17:00:00 IST 2021 | Thu Dec 17 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1815 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Jan 11 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Tue Jan 05 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1816 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1817 | TT_TASK | Generator & Utility Power Pull | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1819 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1820 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1821 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1822 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1823 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Sat Dec 05 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1824 | TT_TASK | Mechanical Equipment Piping Connections | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1825 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
1828 | TT_TASK | Fire Alarm Installation | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1829 | TT_TASK | Controls Installation | Fri Mar 05 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1832 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 22 07:00:00 IST 2021 | Tue Mar 30 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1833 | TT_TASK | Electrical Underground Rough-In | Thu Sep 03 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1834 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1835 | TT_TASK | Set Electrical Equipment-UPM Cell -3 | Fri Dec 11 07:00:00 IST 2020 | Tue Dec 15 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1836 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
1837 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1838 | TT_TASK | Lift & Set MER in Place | Mon Jan 11 08:00:00 IST 2021 | Mon Jan 18 08:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1839 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 18 08:00:00 IST 2021 | Fri Jan 22 08:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1840 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
1841 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1842 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
1843 | TT_TASK | Generator & Utility Power Pull | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1845 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1846 | TT_TASK | Exterior Equipment Pads - Mechanical | Fri Oct 16 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Sat Sep 19 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
1847 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1848 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1849 | TT_TASK | Set Exterior Water Treatment equipment | Mon Dec 07 07:00:00 IST 2020 | Tue Dec 08 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1850 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1851 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 15 07:00:00 IST 2021 | Mon Mar 22 17:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
1854 | TT_TASK | Fire Alarm Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1855 | TT_TASK | Controls Installation | Tue Mar 09 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1858 | TT_TASK | Generator & Utility Power Pull | Tue Feb 02 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Feb 26 07:00:00 IST 2021 |  | COMPLETED
1859 | TT_TASK | Remaining Mechanical Equipment (ADP01) Termimations | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1860 | TT_TASK | Electrical Underground Rough-In | Fri Aug 14 07:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1861 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 05 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1862 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1863 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Sep 05 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Fri Oct 02 00:00:00 IDT 2020 |  | COMPLETED
1864 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Oct 26 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1865 | TT_TASK | Lift & Set MER in Place | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
1866 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 11 08:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1867 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1868 | TT_TASK | GEN & UPM to MER Cable Bus Install | Wed Jan 20 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1869 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1870 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1872 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1873 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Oct 05 07:00:00 IDT 2020 | Sat Oct 17 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
1874 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1875 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1876 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1877 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1878 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 08 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1881 | TT_TASK | Fire Alarm Installation | Thu Feb 18 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1882 | TT_TASK | Controls Installation | Sat Mar 06 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
1885 | TT_TASK | Generator & Utility Power Pull | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1886 | TT_TASK | Electrical Underground Rough-In | Sat Sep 05 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1887 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1888 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1889 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1890 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1891 | TT_TASK | Lift & Set MER in Place | Mon Jan 11 08:00:00 IST 2021 | Mon Jan 18 08:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1892 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 11 08:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Jan 11 08:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1893 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1894 | TT_TASK | GEN & UPM to MER Cable Bus Install | Thu Feb 04 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1895 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Wed Apr 07 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
1896 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 15 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
1898 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Sep 14 07:00:00 IDT 2020 | Sat Sep 26 17:00:00 IDT 2020 | Mon Sep 14 07:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1899 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1900 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1901 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1902 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1903 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1904 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
1907 | TT_TASK | Fire Alarm Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1908 | TT_TASK | Controls Installation | Thu Apr 15 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1911 | TT_TASK | VFD'S Installation & wirepull | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1912 | TT_TASK | Ligthing Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 |  | COMPLETED
1914 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Thu Nov 26 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
1915 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1917 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1919 | TT_TASK | Fire Riser Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1920 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1921 | TT_TASK | Controls Installation | Fri Mar 26 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1924 | TT_TASK | VFD'S Installation & Wiring | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
1925 | TT_TASK | Ligthing Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1927 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
1928 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1930 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1932 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1933 | TT_TASK | Controls Installation | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1936 | TT_TASK | VFD'S Installation & Wiring | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1937 | TT_TASK | Ligthing Installation | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1939 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
1940 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1942 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1944 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1945 | TT_TASK | Controls Installation | Tue Apr 13 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1948 | TT_TASK | VFD'S Installation & Wiring | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
1949 | TT_TASK | Ligthing Installation | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jul 29 00:00:00 IDT 2021 |  | COMPLETED
1951 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
1952 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1954 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1956 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1957 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1961 | TT_TASK | HAC Installation | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
1962 | TT_TASK | Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1963 | TT_TASK | Power Bus Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1964 | TT_TASK | PDU's Installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1965 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Apr 05 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1966 | TT_TASK | Light Fixtures Installation | Wed May 05 07:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
1967 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
1969 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
1970 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1971 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1972 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1974 | TT_TASK | Security Devices & Trim | Mon May 17 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
1975 | TT_TASK | Controls Installation | Fri Mar 26 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1976 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1979 | TT_TASK | HAC Installation | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1980 | TT_TASK | Cable Tray Installation | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
1981 | TT_TASK | Power Bus Installation | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1982 | TT_TASK | PDU's Installation | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
1983 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Apr 26 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1984 | TT_TASK | Light Fixtures Installation | Wed May 12 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1985 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Apr 26 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
1987 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
1988 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1989 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1990 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Thu Jul 01 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1992 | TT_TASK | Security Devices & Trim | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
1993 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1994 | TT_TASK | Fire Alarm System | Tue May 04 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1997 | TT_TASK | HAC Installation | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1998 | TT_TASK | Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1999 | TT_TASK | Power Bus Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
2000 | TT_TASK | PDU's Installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
2001 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Apr 01 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2002 | TT_TASK | Light Fixtures Installation | Tue May 11 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
2003 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 23 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
2005 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2006 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2007 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2008 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed May 19 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2010 | TT_TASK | Security Devices & Trim | Mon May 17 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2011 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2012 | TT_TASK | Fire Alarm System | Thu May 06 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2015 | TT_TASK | HAC Installation | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2016 | TT_TASK | Cable Tray Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2017 | TT_TASK | Power Bus Installation | Fri Mar 12 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2018 | TT_TASK | PDU's Installation | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2019 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon May 03 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
2020 | TT_TASK | Light Fixtures Installation | Fri May 21 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2021 | TT_TASK | Pull/term/Test PDU to Power bus | Mon May 03 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2023 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2024 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2025 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2026 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed May 19 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2028 | TT_TASK | Security Devices & Trim | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 |  | COMPLETED
2029 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2030 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2036 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2037 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
2038 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2040 | TT_TASK | Datahall Finishes - Ceiling Grid | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2043 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2044 | TT_TASK | Overhead MEPFP Rough-In | Fri Nov 06 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2045 | TT_TASK | Hang drywall / Mud / Tape | Wed Jan 06 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2047 | TT_TASK | Datahall Finishes - Ceiling Grid | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2050 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2051 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
2052 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2054 | TT_TASK | Datahall Finishes - Ceiling Grid | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2057 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2058 | TT_TASK | Overhead MEPFP Rough-In | Fri Nov 06 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2059 | TT_TASK | Hang drywall / Mud / Tape | Wed Jan 06 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2061 | TT_TASK | Datahall Finishes - Ceiling Grid | Mon Jan 11 07:00:00 IST 2021 | Wed Jan 20 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2064 | TT_TASK | Remaining Post MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2065 | TT_TASK | Frame & Top out | Mon Nov 23 07:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2066 | TT_TASK | OverHead MEPFP Rough-In | Thu Nov 19 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2067 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Dec 12 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2069 | TT_TASK | Mechanical Corridor Finishes | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2072 | TT_TASK | Remaining MER raceway across Mech chase | Thu Mar 25 07:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2073 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2074 | TT_TASK | OverHead MEPFP Rough-In | Tue Dec 08 07:00:00 IST 2020 | Mon Dec 21 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2075 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Dec 14 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2077 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2080 | TT_TASK | Remaining MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 |  | COMPLETED
2081 | TT_TASK | Frame & Top out | Mon Nov 30 07:00:00 IST 2020 | Wed Dec 09 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2082 | TT_TASK | OverHead MEPFP Rough-In | Sat Dec 19 07:00:00 IST 2020 | Thu Jan 07 17:00:00 IST 2021 | Mon Oct 26 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2083 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Dec 12 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2085 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2088 | TT_TASK | Remaining MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Mar 12 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2089 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2090 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2091 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 30 07:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
2093 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2097 | TT_TASK | Generator & Utility Power Pull | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
2098 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
2099 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2100 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
2101 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Dec 14 07:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 |  | COMPLETED
2102 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Tue Dec 29 00:00:00 IST 2020 |  | COMPLETED
2103 | TT_TASK | Lift & Set MER in Place | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2104 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 |  | COMPLETED
2105 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
2106 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Mar 22 07:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Fri Mar 05 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
2107 | TT_TASK | Generator & Utility Power Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2108 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2110 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
2111 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 08 17:00:00 IST 2021 | Mon Nov 02 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
2112 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2113 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2114 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2115 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2116 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2119 | TT_TASK | Fire Alarm Installation | Tue May 11 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2120 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2123 | TT_TASK | Generator & Utility Power Pull | Tue May 11 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
2124 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 21 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2125 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2126 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Wed Dec 16 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2127 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Dec 14 07:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2128 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2129 | TT_TASK | Lift & Set MER in Place | Tue Mar 23 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
2130 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Mar 29 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2131 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Mar 29 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2132 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Fri Apr 16 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
2133 | TT_TASK | Generator & Utility Power Test-Term | Thu May 06 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2134 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
2136 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2137 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 08 17:00:00 IST 2021 | Mon Nov 16 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2138 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2139 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2140 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2141 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2142 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
2145 | TT_TASK | Fire Alarm Installation | Wed May 26 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2146 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2149 | TT_TASK | Generator & Utility Power Pull | Fri Mar 26 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
2150 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2151 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
2152 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Wed Nov 04 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2153 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Tue Nov 03 00:00:00 IST 2020 |  | COMPLETED
2154 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
2155 | TT_TASK | Lift & Set MER in Place | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2156 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Mar 27 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2157 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Mar 27 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2158 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Thu Mar 25 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
2159 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2160 | TT_TASK | Generator & Utility Power Test-Term | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Tue Apr 06 07:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2162 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2163 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2164 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2165 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2166 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Fri Jan 15 07:00:00 IST 2021 | Fri Jan 29 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2167 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
2168 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
2171 | TT_TASK | Fire Alarm Installation | Tue May 11 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2172 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2175 | TT_TASK | Generator & Utility Power Pull | Thu May 13 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2176 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2177 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2178 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2179 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2180 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
2181 | TT_TASK | Lift & Set MER in Place | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
2182 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Mar 27 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2183 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Mar 27 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
2184 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Thu Apr 15 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
2185 | TT_TASK | Generator & Utility Power Test-Term | Tue May 18 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2186 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2188 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2189 | TT_TASK | Set Gen Stack / Exhaust duct | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2192 | TT_TASK | Fire Alarm Installation | Wed May 12 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2193 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2196 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 |  | COMPLETED
2197 | TT_TASK | Ligthing Installation | Fri Jul 23 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2199 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2200 | TT_TASK | Hydronic Piping Installation | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2202 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2203 | TT_TASK | Toilet Piping Installation / DW | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2205 | TT_TASK | Fire Riser Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2206 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2207 | TT_TASK | Controls Installation | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue Jun 08 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2210 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2211 | TT_TASK | Ligthing Installation | Sat Aug 07 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2213 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
2214 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2216 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2217 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2219 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2220 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
2223 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2224 | TT_TASK | Ligthing Installation | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2226 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
2227 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2229 | TT_TASK | Toilet Piping Installation / DW | Mon May 03 07:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2230 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2232 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2233 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri Jul 09 08:12:00 IDT 2021 |  | COMPLETED
2236 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2237 | TT_TASK | Ligthing Installation | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2239 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
2240 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2242 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2243 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2245 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2246 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2249 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2250 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2251 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
2252 | TT_TASK | Power Bus Installation | Fri Mar 26 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2253 | TT_TASK | PDU's Installation | Fri Mar 26 07:00:00 IDT 2021 | Mon Mar 29 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
2254 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2255 | TT_TASK | Light Fixtures Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2256 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 23 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
2258 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Jun 10 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2259 | TT_TASK | BMS Pull Wire / Term / Test | Thu Jun 10 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2260 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Jul 23 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2262 | TT_TASK | Fire Alarm System | Tue May 04 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2263 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2266 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2267 | TT_TASK | HAC Installation | Wed Feb 03 07:00:00 IST 2021 | Wed Feb 17 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Wed Feb 03 00:00:00 IST 2021 |  | COMPLETED
2268 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
2269 | TT_TASK | Power Bus Installation | Mon Mar 22 07:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2270 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2271 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Tue Jun 08 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2272 | TT_TASK | Light Fixtures Installation | Wed Jun 23 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
2273 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2275 | TT_TASK | EPMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 |  | COMPLETED
2276 | TT_TASK | BMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 |  | COMPLETED
2277 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon Aug 09 07:00:00 IDT 2021 | Wed Sep 01 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2279 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2280 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2283 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2284 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2285 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
2286 | TT_TASK | Power Bus Installation | Fri Mar 26 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2287 | TT_TASK | PDU's Installation | Mon Mar 22 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2288 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2289 | TT_TASK | Light Fixtures Installation | Fri Jun 18 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Jun 18 07:00:00 IDT 2021 | Thu Jul 01 00:00:00 IDT 2021 |  | COMPLETED
2290 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 02 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
2292 | TT_TASK | EPMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2293 | TT_TASK | BMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2294 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Jul 30 07:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2296 | TT_TASK | Fire Alarm System | Mon May 10 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon May 10 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 |  | COMPLETED
2297 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2300 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Thu Apr 22 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2301 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
2302 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2303 | TT_TASK | Power Bus Installation | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2304 | TT_TASK | PDU's Installation | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2305 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Jun 09 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2306 | TT_TASK | Light Fixtures Installation | Wed Jun 23 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2307 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2309 | TT_TASK | EPMS Pull Wire / Term / Test | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2310 | TT_TASK | BMS Pull Wire / Term / Test | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2311 | TT_TASK | ` | Tue Aug 24 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2313 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2314 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2319 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2320 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
2321 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2323 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2326 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
2327 | TT_TASK | Overhead MEPFP Rough-In | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 |  | COMPLETED
2328 | TT_TASK | Hang drywall / Mud / Tape | Thu Jan 14 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2330 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2333 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2334 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2335 | TT_TASK | Hang drywall / Mud / Tape | Fri Jan 08 07:00:00 IST 2021 | Mon Jan 18 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2337 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2340 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
2341 | TT_TASK | Overhead MEPFP Rough-In | Fri Jan 15 07:00:00 IST 2021 | Wed Jan 27 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2342 | TT_TASK | Hang drywall / Mud / Tape | Thu Jan 14 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2344 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2347 | TT_TASK | Remaining MER raceway across Mech chase | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2348 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
2349 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2350 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Thu Jan 21 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Thu Jan 21 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 |  | COMPLETED
2352 | TT_TASK | Mechanical Corridor Finishes | Fri Mar 05 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2355 | TT_TASK | Remaining MER raceway across Mech chase | Thu Jun 17 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2356 | TT_TASK | Frame & Top out | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2357 | TT_TASK | OverHead MEPFP Rough-In | Wed Jan 13 07:00:00 IST 2021 | Wed Jan 27 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2358 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
2360 | TT_TASK | Mechanical Corridor Finishes | Wed Feb 03 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2363 | TT_TASK | Remaining MER raceway across Mech chase | Mon May 03 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2364 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
2365 | TT_TASK | OverHead MEPFP Rough-In | Tue Jan 12 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2366 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2368 | TT_TASK | Mechanical Corridor Finishes | Tue Feb 02 07:00:00 IST 2021 | Tue Feb 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2371 | TT_TASK | Remaining MER raceway across Mech chase | Thu Jun 17 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
2372 | TT_TASK | Frame & Top out | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2373 | TT_TASK | OverHead MEPFP Rough-In | Fri Jan 08 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2374 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2376 | TT_TASK | Mechanical Corridor Finishes | Tue Feb 23 07:00:00 IST 2021 | Tue Mar 16 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2380 | TT_TASK | Generator & Utility Power Pull | Wed May 19 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2381 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
2382 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2383 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 29 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
2384 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 07:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
2385 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2386 | TT_TASK | Lift & Set MER in Place | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
2387 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
2388 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon May 03 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2389 | TT_TASK | GEN & UPM to MER Cable Bus Install | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2390 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2391 | TT_TASK | Generator & Utility Power Test-Term | Wed Jun 02 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
2393 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
2394 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2395 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
2396 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2397 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2398 | TT_TASK | Set Exterior Water Treatment equipment | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 01 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2399 | TT_TASK | Mechanical Equipment Piping Connections | Fri Apr 30 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2402 | TT_TASK | Fire Alarm Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2403 | TT_TASK | Controls Installation | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2406 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2407 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
2408 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2409 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2410 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 02 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2411 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 15 08:00:00 IST 2021 | Mon Mar 22 08:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2412 | TT_TASK | Lift & Set MER in Place | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2413 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2414 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Fri May 07 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2415 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2416 | TT_TASK | Generator & Utility Power Test-Term | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2417 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Jun 08 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Tue Jun 08 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2419 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
2420 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
2423 | TT_TASK | Fire Alarm Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 15 07:00:00 IDT 2021 |  | COMPLETED
2424 | TT_TASK | Controls Installation | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 29 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2427 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2428 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2429 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2430 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 08:00:00 IST 2021 | Tue Jan 12 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2431 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Fri Nov 27 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2432 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
2433 | TT_TASK | Lift & Set MER in Place | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
2434 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2435 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon May 03 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
2436 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Mon May 17 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 |  | COMPLETED
2437 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Thu Jun 10 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2438 | TT_TASK | Generator & Utility Power Test-Term | Thu Jun 03 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
2440 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2441 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2442 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2443 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Apr 26 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2444 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 |  | COMPLETED
2445 | TT_TASK | Set Exterior Water Treatment equipment | Mon Apr 26 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2446 | TT_TASK | Mechanical Equipment Piping Connections | Mon May 03 07:00:00 IDT 2021 | Sat May 08 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2449 | TT_TASK | Fire Alarm Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2450 | TT_TASK | Controls Installation | Fri Jun 25 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2453 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2454 | TT_TASK | Electrical Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2455 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Fri Dec 04 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2456 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2457 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 02 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2458 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
2459 | TT_TASK | Lift & Set MER in Place | Fri May 07 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2460 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2461 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2462 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2463 | TT_TASK | Generator & Utility Power Test-Term | Tue Jul 06 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 | Thu Jul 15 12:00:00 IDT 2021 |  | COMPLETED
2464 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2466 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Fri Dec 04 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2467 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2468 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2469 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2470 | TT_TASK | Set Exterior Water Treatment equipment | Fri Apr 30 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2471 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
2472 | TT_TASK | Mechanical Equipment Piping Connections | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2475 | TT_TASK | Fire Alarm Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jul 07 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2476 | TT_TASK | Controls Installation | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
2479 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2480 | TT_TASK | Ligthing Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2482 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
2483 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2485 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 00:00:00 IDT 2021 |  | COMPLETED
2486 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2488 | TT_TASK | Fire Riser Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2489 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2490 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2493 | TT_TASK | VFD'S Installation & Wiring | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2494 | TT_TASK | Ligthing Installation | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
2496 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
2497 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2499 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2500 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2502 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2503 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2506 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2507 | TT_TASK | Ligthing Installation | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
2509 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
2510 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2512 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2513 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2515 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2516 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
2519 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
2520 | TT_TASK | Ligthing Installation | Mon Aug 30 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2522 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
2523 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2525 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2526 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2528 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2529 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2532 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 |  | COMPLETED
2533 | TT_TASK | HAC Installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2534 | TT_TASK | Cable Tray Installation | Sat Apr 03 07:00:00 IDT 2021 | Sat Apr 17 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
2535 | TT_TASK | Power Bus Installation | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2536 | TT_TASK | PDU's Installation | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2537 | TT_TASK | Pull/term/Test PDU to Power bus | Sat Jun 19 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2538 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2539 | TT_TASK | Light Fixtures Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
2541 | TT_TASK | EPMS Pull Wire / Term / Test | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2542 | TT_TASK | BMS Pull Wire / Term / Test | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2543 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Aug 20 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Jul 07 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2545 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2546 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
2549 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2550 | TT_TASK | HAC Installation | Wed Apr 07 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2551 | TT_TASK | Cable Tray Installation | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2552 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
2553 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
2554 | TT_TASK | Pull/term/Test PDU to Power bus | Fri Jul 02 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
2555 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Aug 16 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Thu Jul 08 00:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2556 | TT_TASK | Light Fixtures Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2558 | TT_TASK | EPMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2559 | TT_TASK | BMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2560 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2562 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2563 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2566 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 |  | COMPLETED
2567 | TT_TASK | HAC Installation | Sat Apr 03 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2568 | TT_TASK | Cable Tray Installation | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2569 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 |  | COMPLETED
2570 | TT_TASK | PDU's Installation | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2571 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Sat Jul 24 00:00:00 IDT 2021 |  | COMPLETED
2572 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 23 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2573 | TT_TASK | Light Fixtures Installation | Wed Jul 21 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2575 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2576 | TT_TASK | BMS Pull Wire / Term / Test | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2577 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Aug 20 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2579 | TT_TASK | Fire Alarm System | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2580 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2583 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2584 | TT_TASK | HAC Installation | Mon Apr 12 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2585 | TT_TASK | Cable Tray Installation | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2586 | TT_TASK | Power Bus Installation | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
2587 | TT_TASK | PDU's Installation | Mon Jun 14 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
2588 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
2589 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2590 | TT_TASK | Light Fixtures Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2592 | TT_TASK | EPMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2593 | TT_TASK | BMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2594 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed Sep 15 07:00:00 IDT 2021 | Fri Oct 08 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2596 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2597 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2602 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2603 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2604 | TT_TASK | Early Topout | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2606 | TT_TASK | Datahall Finishes | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
2609 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Jan 18 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2610 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2611 | TT_TASK | Early Topout | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
2613 | TT_TASK | Datahall Finishes | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2616 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2617 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2618 | TT_TASK | Early Topout | Tue Feb 09 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2620 | TT_TASK | Datahall Finishes | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
2623 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Jan 18 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2624 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2625 | TT_TASK | Early Topout | Mon Feb 08 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2627 | TT_TASK | Datahall Finishes | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2630 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2631 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2632 | TT_TASK | OverHead MEPFP Rough-In | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
2633 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 15 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
2635 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Sat Jan 09 00:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 |  | COMPLETED
2638 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2639 | TT_TASK | Frame & Top out | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Sat Jan 09 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
2640 | TT_TASK | OverHead MEPFP Rough-In | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2641 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Tue Mar 30 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2643 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 29 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Thu Jan 21 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
2646 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 |  | COMPLETED
2647 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
2648 | TT_TASK | OverHead MEPFP Rough-In | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Feb 05 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2649 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 15 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2651 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
2654 | TT_TASK | Remaining MER raceway across Mech chase | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
2655 | TT_TASK | Frame & Top out | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
2656 | TT_TASK | OverHead MEPFP Rough-In | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2657 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Tue Mar 30 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Fri Feb 12 00:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
2659 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 29 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2663 | TT_TASK | Generator & Utility Power Pull | Wed Jul 28 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2664 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2665 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2666 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Wed Dec 30 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2667 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2668 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Apr 26 08:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2669 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
2670 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2671 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2672 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 |  | COMPLETED
2673 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2674 | TT_TASK | Generator & Utility Power Test-Term | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
2676 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2677 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2678 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2679 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2680 | TT_TASK | Set Exterior Water Treatment equipment | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 01 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2681 | TT_TASK | Mechanical Equipment Piping Connections | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2682 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2685 | TT_TASK | Fire Alarm Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
2686 | TT_TASK | Controls Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2689 | TT_TASK | Generator & Utility Power Pull | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 19 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2690 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2691 | TT_TASK | Exterior Equipment Pads - for UPM's | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2692 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2693 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2694 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Apr 26 08:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2695 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2696 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2697 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
2698 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jul 10 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2699 | TT_TASK | Generator & Utility Power Test-Term | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Sat Aug 07 17:00:00 IDT 2021 |  | COMPLETED
2700 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2702 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2703 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2704 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2705 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2706 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2707 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2708 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2711 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
2712 | TT_TASK | Controls Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
2715 | TT_TASK | Generator & Utility Power Pull | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 | Thu Aug 05 09:30:00 IDT 2021 |  | COMPLETED
2716 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2717 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2718 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2719 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2720 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2721 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2722 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2723 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2724 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jul 15 00:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2725 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2726 | TT_TASK | Generator & Utility Power Test-Term | Fri Sep 03 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
2728 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 09 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2729 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2730 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2731 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2732 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2733 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2734 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
2737 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2738 | TT_TASK | Controls Installation | Wed Sep 01 07:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Thu Aug 26 07:00:00 IDT 2021 |  | 1210.0 | IN_PROGRESS
2741 | TT_TASK | Generator & Utility Power Pull | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Thu Jul 29 00:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
2742 | TT_TASK | Electrical Underground Rough-In | Sat Nov 07 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2743 | TT_TASK | Exterior Equipment Pads - for UPM's | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2744 | TT_TASK | Set Electrical Equipment-UPM | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2745 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Jan 18 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2746 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2747 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2748 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2749 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
2750 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2751 | TT_TASK | Generator & Utility Power Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2752 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2754 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2755 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2756 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2757 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2758 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2759 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2760 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2763 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
2764 | TT_TASK | Controls Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
2767 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2768 | TT_TASK | Ligthing Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2770 | TT_TASK | AHU/DOAS Equipment Setting | Sat May 15 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2771 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2773 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2774 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2776 | TT_TASK | Fire Riser Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed May 19 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2777 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2778 | TT_TASK | Controls Installation | Sat Jul 31 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2781 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
2782 | TT_TASK | Ligthing Installation | Thu Sep 16 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
2784 | TT_TASK | AHU/DOAS Equipment Setting | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2785 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2787 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2788 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2790 | TT_TASK | Fire Alarm System | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2791 | TT_TASK | Controls Installation | Mon Aug 23 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2794 | TT_TASK | VFD'S Installation & Wiring | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2795 | TT_TASK | Lighting Installation | Sat Sep 11 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
2797 | TT_TASK | AHU/DOAS Equipment Setting | Sat May 15 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2798 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2800 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2801 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2803 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2804 | TT_TASK | Controls Installation | Mon Aug 16 07:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 |  | COMPLETED
2807 | TT_TASK | VFD'S Installation & Wiring | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2808 | TT_TASK | Ligthing Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
2810 | TT_TASK | AHU/DOAS Equipment Setting | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2811 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2813 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2814 | TT_TASK | Toilet Piping Installation / DW | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
2816 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2817 | TT_TASK | Controls Installation | Wed Sep 08 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2820 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 09 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2821 | TT_TASK | HAC Installation | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2822 | TT_TASK | Cable Tray Installation | Tue May 04 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2823 | TT_TASK | Power Bus Installation | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2824 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2825 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 27 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2826 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Aug 25 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2827 | TT_TASK | Light Fixtures Installation | Sat Aug 21 07:00:00 IDT 2021 | Fri Aug 27 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
2829 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2830 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
2831 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon Sep 27 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2833 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2834 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2837 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 16 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2838 | TT_TASK | HAC Installation | Thu Apr 29 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2839 | TT_TASK | Cable Tray Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2840 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 |  | COMPLETED
2841 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2842 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Fri Sep 03 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2843 | TT_TASK | Pull/term/Test PDU to Power bus | Fri Sep 03 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  | 210.0 | NOT_STARTED
2844 | TT_TASK | Light Fixtures Installation | Fri Oct 01 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2846 | TT_TASK | EPMS Pull Wire / Term / Test | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2847 | TT_TASK | BMS Pull Wire / Term / Test | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
2848 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Thu Oct 21 07:00:00 IDT 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  | 801.0 | NOT_STARTED
2850 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2851 | TT_TASK | Controls Installation | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2854 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 16 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2855 | TT_TASK | HAC Installation | Thu Apr 29 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2856 | TT_TASK | Cable Tray Installation | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2857 | TT_TASK | Power Bus Installation | Mon Jun 14 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2858 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2859 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Sep 01 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2860 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Aug 25 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2861 | TT_TASK | Light Fixtures Installation | Mon Aug 30 07:00:00 IDT 2021 | Tue Sep 07 08:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  | 89.0 | IN_PROGRESS
2863 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2864 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 170.0 | NOT_STARTED
2865 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Sat Oct 09 07:00:00 IDT 2021 | Tue Nov 02 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2867 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2868 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2871 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 23 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2872 | TT_TASK | HAC Installation | Fri May 07 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2873 | TT_TASK | Cable Tray Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2874 | TT_TASK | Power Bus Installation | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Thu Jun 24 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2875 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed Jul 14 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2876 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Sep 01 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 25 00:00:00 IDT 2021 |  |  | IN_PROGRESS
2877 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 22 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2878 | TT_TASK | Light Fixtures Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2880 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2881 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 300.0 | NOT_STARTED
2882 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed Nov 03 07:00:00 IST 2021 | Tue Nov 30 17:00:00 IST 2021 |  |  | 691.0 | NOT_STARTED
2884 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2885 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jul 27 00:00:00 IDT 2021 | Tue Aug 24 13:00:00 IDT 2021 |  | COMPLETED
2889 | TT_TASK | ATS Equipment Yellow Tagging (S2 from MER) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2890 | TT_TASK | Control Power Available | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Fri Apr 30 07:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
2891 | TT_TASK | Power available for Start up | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2892 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2893 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 |  | COMPLETED
2895 | TT_TASK | Admin - NETA test validation Inpections- VECA-EPS-RTS Admin | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Mar 11 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
2896 | TT_TASK | Electrical Equipment Yellow Tagging | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2897 | TT_TASK | Admin/Colo-1 Network Startup | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2898 | TT_TASK | EPMS Checkout / Point to Point | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2902 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2903 | TT_TASK | UPM Yellow tagging - Admin & COLO-1 CELL-1 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2904 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
2905 | TT_TASK | SE- Completed L2 QC Checklist | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
2906 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-1 | Sat Apr 17 07:00:00 IDT 2021 | Tue Apr 20 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2907 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2908 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2909 | TT_TASK | Network Startup | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
2910 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2911 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2912 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2914 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2915 | TT_TASK | Power available for Start up | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2916 | TT_TASK | SE- Completed L2 QC Checklist | Mon Jun 14 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
2917 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Jul 13 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2918 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-3 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2919 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-3 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2920 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Thu Jun 10 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2921 | TT_TASK | Network Startup | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 |  | COMPLETED
2922 | TT_TASK | EPMS Checkout / Point to Point | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jul 06 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2923 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2924 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2926 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2927 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2928 | TT_TASK | SE- Completed L2 QC Checklist | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2929 | TT_TASK | Mechanical Equipment Yellow Tag | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 |  | COMPLETED
2930 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-2 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2931 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-2 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2932 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2933 | TT_TASK | Network Startup | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2934 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2935 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2936 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 20 15:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2938 | TT_TASK | Control Power Available | Tue Jun 22 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue Jun 22 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2939 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2940 | TT_TASK | SE- Completed L2 QC Checklist | Mon Jun 14 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
2941 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Jul 02 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2942 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-4 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2943 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-4 | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
2944 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Jul 07 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2945 | TT_TASK | Network Startup | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2946 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2947 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2948 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2950 | TT_TASK | GEN SCR testing and Burnins | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jul 14 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2951 | TT_TASK | Admin GEN SCR testing and Burnins | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2952 | TT_TASK | ATS- Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 |  | 100.0 | IN_PROGRESS
2953 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Tue Jul 13 11:00:00 IDT 2021 | Wed Jul 28 11:00:00 IDT 2021 | Tue Jul 13 11:00:00 IDT 2021 | Wed Jul 28 11:00:00 IDT 2021 |  | COMPLETED
2954 | TT_TASK | Cooling Automation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2955 | TT_TASK | BAS Prefunctional Testing on Construction Server | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Sat Aug 28 00:00:00 IDT 2021 |  | COMPLETED
2956 | TT_TASK | Additional Go-Back loadbanking (ASCO) | Fri Sep 10 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2957 | TT_TASK | Load Bank & IR Scan | Wed Sep 15 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2958 | TT_TASK | Level 3 Cx - ADMIN AND COLO1 | Fri Sep 17 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2959 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Sat Oct 02 07:00:00 IDT 2021 | Sat Oct 02 07:00:00 IDT 2021 |  |  |  | NOT_STARTED
2961 | TT_TASK | COLO 1 Level 4 & Level 5 IST | Sat Oct 02 08:00:00 IDT 2021 | Fri Oct 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2962 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Sat Oct 30 08:00:00 IDT 2021 | Mon Nov 08 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2963 | TT_TASK | Security Commissioning (level3 DCPS) | Tue Nov 09 08:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2964 | TT_TASK | Punch List - Admin/COLO 1 | Sat Oct 30 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2965 | TT_TASK | MST Ready for Network Install | Sat Oct 02 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2966 | TT_TASK | Final Clean/ ready for lock down | Sat Nov 13 07:00:00 IST 2021 | Mon Nov 22 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2970 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 18 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2971 | TT_TASK | Power available for Start up | Sat Sep 11 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2972 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2973 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  | 20.0 | IN_PROGRESS
2974 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-1 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2975 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-1 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2976 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Aug 04 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2977 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2978 | TT_TASK | EPMS Checkout / Point to Point | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 200.0 | NOT_STARTED
2979 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Thu Sep 16 07:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 |  |  | 20.0 | NOT_STARTED
2980 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Thu Sep 16 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  | 50.0 | NOT_STARTED
2982 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2983 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2984 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2985 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2986 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-3 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2987 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-3 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2988 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2989 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2990 | TT_TASK | EPMS Checkout / Point to Point | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
2991 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2992 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2994 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2995 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2996 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2997 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2998 | TT_TASK | UPM Yellow tagging - COLO-2 CELL-2 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2999 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-2 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
3000 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jul 13 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3001 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3002 | TT_TASK | EPMS Checkout / Point to Point | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3003 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3004 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3006 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3007 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3008 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
3009 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3010 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-4 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
3011 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-4 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
3012 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Aug 18 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3013 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3014 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3015 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3016 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  | 30.0 | NOT_STARTED
3018 | TT_TASK | GEN SCR testing and Burnins | Sat Sep 18 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  | 150.0 | NOT_STARTED
3019 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Mon Sep 27 07:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3020 | TT_TASK | Cooling Automation | Mon Oct 11 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3021 | TT_TASK | BAS Prefunctional Testing on Construction Server | Thu Oct 07 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3022 | TT_TASK | Load Bank & IR Scan | Tue Oct 26 07:00:00 IDT 2021 | Tue Nov 16 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3023 | TT_TASK | Level 3 Cx- COLO-2 | Wed Nov 17 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3024 | TT_TASK | Weather (5 Days) - 0 remaining Check Delay #14 for updates | Sat Dec 04 07:00:00 IST 2021 | Sat Dec 04 07:00:00 IST 2021 |  |  |  | NOT_STARTED
3026 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Mon Dec 27 07:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3027 | TT_TASK | Security Commissioning (level3 DCPS) | Tue Jan 11 07:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3028 | TT_TASK | COLO 2 Level 4 & Level 5 IST | Sat Dec 04 08:00:00 IST 2021 | Fri Dec 24 17:00:00 IST 2021 |  |  | 16.0 | NOT_STARTED
3029 | TT_TASK | Punch List COLO-2 | Mon Dec 27 08:00:00 IST 2021 | Sun Jan 09 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3030 | TT_TASK | MST Ready for Network Install | Sat Dec 04 07:00:00 IST 2021 | Thu Dec 09 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3031 | TT_TASK | Final Clean/ ready for lock down | Mon Jan 10 08:00:00 IST 2022 | Fri Jan 21 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3035 | TT_TASK | Control Power Available | Thu Sep 09 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3036 | TT_TASK | Power available for Start up | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3037 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3038 | TT_TASK | Mechanical Equipment Yellow Tag | Wed Sep 22 07:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3039 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-1 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3040 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-1 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3041 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3042 | TT_TASK | Network Startup | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3043 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3044 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3045 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Tue Oct 05 07:00:00 IDT 2021 | Tue Oct 19 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3047 | TT_TASK | Control Power Available | Tue Sep 21 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3048 | TT_TASK | Power available for Start up | Mon Oct 04 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3049 | TT_TASK | SE- Completed L2 QC Checklist | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3050 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Oct 05 07:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3051 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-3 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 160.0 | NOT_STARTED
3052 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-3 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3053 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3054 | TT_TASK | Network Startup | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3055 | TT_TASK | EPMS Checkout / Point to Point | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3056 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3057 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Oct 18 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3059 | TT_TASK | Control Power Available | Thu Sep 09 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3060 | TT_TASK | Power available for Start up | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3061 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3062 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3063 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-2 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3064 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-2 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3065 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Fri Aug 13 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3066 | TT_TASK | Network Startup | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3067 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3068 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3069 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  |  | 170.0 | NOT_STARTED
3071 | TT_TASK | Control Power Available | Tue Sep 21 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3072 | TT_TASK | Power available for Start up | Mon Oct 04 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3073 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3074 | TT_TASK | Mechanical Equipment Yellow Tag | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3075 | TT_TASK | UPM Yellow tagging COLO-3 CELL-4 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 160.0 | NOT_STARTED
3076 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-4 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
3077 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3078 | TT_TASK | Network Startup | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3079 | TT_TASK | EPMS Checkout / Point to Point | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3080 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3081 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  |  | 70.0 | NOT_STARTED
3083 | TT_TASK | GEN SCR testing and Burnins | Fri Oct 08 07:00:00 IDT 2021 | Tue Oct 26 17:00:00 IDT 2021 |  |  | 320.0 | NOT_STARTED
3084 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Fri Oct 22 07:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3085 | TT_TASK | Cooling Automation | Fri Nov 05 07:00:00 IST 2021 | Fri Nov 19 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3086 | TT_TASK | BAS Prefunctional Testing on Construction Server | Mon Nov 01 07:00:00 IST 2021 | Wed Nov 24 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3087 | TT_TASK | Load Bank & IR Scan | Wed Dec 08 07:00:00 IST 2021 | Mon Jan 03 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3088 | TT_TASK | Level 3 Cx- COLO-3 | Tue Jan 04 07:00:00 IST 2022 | Tue Jan 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3089 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Wed Jan 19 07:00:00 IST 2022 | Wed Jan 19 07:00:00 IST 2022 |  |  |  | NOT_STARTED
3091 | TT_TASK | COLO 3 Level 4 & Level 5 IST | Wed Jan 19 08:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3092 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Wed Feb 09 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3093 | TT_TASK | Security Commissioning (level3 DCPS) | Sat Feb 19 08:00:00 IST 2022 | Wed Feb 23 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3094 | TT_TASK | Punch List COLO-3 | Wed Feb 09 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3095 | TT_TASK | MST Ready for Network Install | Wed Jan 19 08:00:00 IST 2022 | Tue Jan 25 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3096 | TT_TASK | Final Clean/ ready for lock down | Wed Feb 23 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3100 | TT_TASK | Control Power Available | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3101 | TT_TASK | Power available for Start up | Tue Nov 02 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3102 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3103 | TT_TASK | Mechanical Equipment Yellow Tag | Mon Oct 18 07:00:00 IDT 2021 | Thu Oct 28 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3104 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-1 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
3105 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-1 | Fri Sep 17 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
3106 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3107 | TT_TASK | Network Startup | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3108 | TT_TASK | EPMS Checkout / Point to Point | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  | 40.0 | NOT_STARTED
3109 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3110 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3112 | TT_TASK | Control Power Available | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3113 | TT_TASK | Power available for Start up | Mon Nov 15 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3114 | TT_TASK | SE- Completed L2 QC Checklist | Sat Oct 23 07:00:00 IDT 2021 | Wed Nov 03 17:00:00 IST 2021 |  |  | 20.0 | NOT_STARTED
3115 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Oct 29 07:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 |  |  | 70.0 | NOT_STARTED
3116 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-3 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Mon Aug 16 00:00:00 IDT 2021 |  | COMPLETED
3117 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-3 | Tue Sep 28 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  | 200.0 | NOT_STARTED
3118 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3119 | TT_TASK | Network Startup | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3120 | TT_TASK | EPMS Checkout / Point to Point | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3121 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3122 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3124 | TT_TASK | Control Power Available | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3125 | TT_TASK | Power available for Start up | Tue Nov 02 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3126 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3127 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3128 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-2 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3129 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-2 | Fri Sep 17 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
3130 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3131 | TT_TASK | Network Startup | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3132 | TT_TASK | EPMS Checkout / Point to Point | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3133 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3134 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3136 | TT_TASK | Control Power Available | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3137 | TT_TASK | Power available for Start up | Mon Nov 15 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3138 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3139 | TT_TASK | Mechanical Equipment Yellow Tag | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  | 140.0 | NOT_STARTED
3140 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-4 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3141 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-4 | Sat Sep 18 07:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 |  |  | 270.0 | NOT_STARTED
3142 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3143 | TT_TASK | Network Startup | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3144 | TT_TASK | EPMS Checkout / Point to Point | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3145 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3146 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3148 | TT_TASK | GEN SCR testing and Burnins | Fri Nov 19 07:00:00 IST 2021 | Thu Dec 09 17:00:00 IST 2021 |  |  | 310.0 | NOT_STARTED
3149 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Tue Nov 30 07:00:00 IST 2021 | Mon Dec 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3150 | TT_TASK | Cooling Automation | Tue Dec 14 07:00:00 IST 2021 | Thu Dec 30 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3151 | TT_TASK | BAS Prefunctional Testing on Construction Server | Tue Dec 07 07:00:00 IST 2021 | Tue Jan 04 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3152 | TT_TASK | Load Bank & IR Scan | Sat Jan 22 07:00:00 IST 2022 | Sat Feb 12 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3153 | TT_TASK | Level 3 Cx - COLO-4 | Mon Feb 14 07:00:00 IST 2022 | Sat Feb 26 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3154 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Mon Feb 28 07:00:00 IST 2022 | Mon Feb 28 07:00:00 IST 2022 |  |  |  | NOT_STARTED
3156 | TT_TASK | COLO 4 Level 4 & Level 5 IST | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 20 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3157 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Mon Mar 21 08:00:00 IST 2022 | Wed Mar 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3158 | TT_TASK | Security Commissioning (level3 DCPS) | Thu Mar 31 08:00:00 IDT 2022 | Mon Apr 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3159 | TT_TASK | Punch List COLO-4 | Mon Mar 21 08:00:00 IST 2022 | Sat Apr 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3160 | TT_TASK | MST Ready for Network Install | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3161 | TT_TASK | Final Clean/ ready for lock down | Sun Apr 03 08:00:00 IDT 2022 | Wed Apr 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3163 | TT_TASK | CSA Punchlist - COLO-1 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  | COMPLETED
3164 | TT_TASK | CSA Punchlist - COLO-2 | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 220.0 | NOT_STARTED
3165 | TT_TASK | CSA Punchlist - COLO-3 | Mon Nov 01 07:00:00 IST 2021 | Fri Nov 12 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3166 | TT_TASK | CSA Punchlist - COLO-4 | Sat Dec 11 07:00:00 IST 2021 | Thu Dec 23 17:00:00 IST 2021 |  |  | 380.0 | NOT_STARTED
3167 | TT_TASK | MEP Punchlist - COLO-1 | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 110.0 | NOT_STARTED
3168 | TT_TASK | MEP Punchlist - COLO-2 | Wed Nov 17 07:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 |  |  | 20.0 | NOT_STARTED
3169 | TT_TASK | MEP Punchlist - COLO-3 | Tue Jan 04 07:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  |  | 20.0 | NOT_STARTED
3170 | TT_TASK | MEP Punchlist - COLO-4 | Mon Feb 14 07:00:00 IST 2022 | Thu Feb 24 17:00:00 IST 2022 |  |  | 20.0 | NOT_STARTED
3171 | TT_TASK | AE/Owner Punchlist - COLO-1 | Sat Oct 30 07:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  |  | 60.0 | NOT_STARTED
3172 | TT_TASK | AE/Owner Punchlist - COLO-2 | Mon Dec 27 07:00:00 IST 2021 | Mon Jan 03 17:00:00 IST 2022 |  |  | 41.0 | NOT_STARTED
3173 | TT_TASK | AE/Owner Punchlist - COLO-3 | Wed Feb 09 07:00:00 IST 2022 | Mon Feb 14 17:00:00 IST 2022 |  |  | 71.0 | NOT_STARTED
3174 | TT_TASK | AE/Owner Punchlist - COLO-4 | Mon Mar 21 07:00:00 IST 2022 | Fri Mar 25 17:00:00 IDT 2022 |  |  | 70.0 | NOT_STARTED
3182 | TT_TASK | UMS - ROJ COLO-2 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3183 | TT_TASK | UMS - ROJ COLO-3 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3184 | TT_TASK | UMS - ROJ COLO-4 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3185 | TT_TASK | MSFT Delivery -UMS -COLO 4 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3186 | TT_TASK | MSFT Delivery -UMS -COLO 3 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3187 | TT_TASK | MSFT Delivery -UMS -COLO 2 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3190 | TT_TASK | TCO COLO 2 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3191 | TT_TASK | Weather Tight | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3192 | TT_TASK | Duct Bank - UMS01 to UPM COLO-1 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3193 | TT_TASK | Duct Bank - UMS02 to UPM COLO-2 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3194 | TT_TASK | Duct Bank - UMS03 to UPM COLO-3 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3195 | TT_TASK | Duct Bank - UMS04 to UPM COLO-4 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3196 | TT_TASK | PAD- COLO-1 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3197 | TT_TASK | PAD- COLO-2 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3198 | TT_TASK | PAD- COLO-3 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3199 | TT_TASK | PAD- COLO-4 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3200 | TT_TASK | Pull- UMS01- UPM COLO-1 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3201 | TT_TASK | Pull- UMS02- UPM COLO-2 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3202 | TT_TASK | Pull- UMS03- UPM COLO-3 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3203 | TT_TASK | Pull- UMS04- UPM COLO-4 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3204 | TT_TASK | Set- COLO-1 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3205 | TT_TASK | Set- COLO-2 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3206 | TT_TASK | Set- COLO-3 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3207 | TT_TASK | Set- COLO-4 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3208 | TT_TASK | Term Admin - UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3209 | TT_TASK | Term COLO -1 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3210 | TT_TASK | Term COLO -1 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3211 | TT_TASK | Term COLO -2 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3212 | TT_TASK | Term COLO -2 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3213 | TT_TASK | Term COLO -3 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3214 | TT_TASK | Term COLO -3 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3215 | TT_TASK | Term COLO -4 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3216 | TT_TASK | Term COLO -4 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3217 | TT_TASK | Term- UMS01- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3218 | TT_TASK | Term- UMS02- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3219 | TT_TASK | Term- UMS03- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3220 | TT_TASK | Term- UMS04- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3221 | TT_TASK | Yellow Tagging for UMS01 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3222 | TT_TASK | Yellow Tagging for UMS02 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3223 | TT_TASK | Yellow Tagging for UMS03 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3224 | TT_TASK | Yellow Tagging for UMS04 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3225 | TT_TASK | URS Vault design and Approval | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3227 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Thu Oct 22 07:00:00 IDT 2020 | Thu Oct 22 07:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3228 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3229 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jan 23 07:00:00 IST 2021 | Sat Jan 23 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3230 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Thu Oct 22 07:00:00 IDT 2020 | Thu Oct 22 07:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3231 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3232 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jan 23 07:00:00 IST 2021 | Sat Jan 23 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3233 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Nov 04 07:00:00 IST 2020 | Wed Nov 04 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3234 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3235 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Feb 04 07:00:00 IST 2021 | Thu Feb 04 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3236 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Nov 04 07:00:00 IST 2020 | Wed Nov 04 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3237 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3238 | TT_TASK | COLO Lighting installation (DRB#2) | Mon Feb 08 07:00:00 IST 2021 | Mon Feb 08 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3239 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3240 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Dec 02 07:00:00 IST 2020 | Wed Dec 02 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3241 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Mar 11 07:00:00 IST 2021 | Thu Mar 11 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3242 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Tue Dec 29 07:00:00 IST 2020 | Tue Dec 29 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3243 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Dec 02 07:00:00 IST 2020 | Wed Dec 02 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3244 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Mar 11 07:00:00 IST 2021 | Thu Mar 11 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3245 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Dec 18 07:00:00 IST 2020 | Fri Dec 18 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3246 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Dec 15 07:00:00 IST 2020 | Tue Dec 15 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3247 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Mar 26 07:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3248 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Dec 15 07:00:00 IST 2020 | Tue Dec 15 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3249 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Mar 26 07:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3250 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Jan 07 07:00:00 IST 2021 | Thu Jan 07 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3251 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3252 | TT_TASK | COLO Lighting installation (DRB#2) | Tue Apr 27 07:00:00 IDT 2021 | Tue Apr 27 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3253 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Jan 14 07:00:00 IST 2021 | Thu Jan 14 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3254 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3255 | TT_TASK | COLO Lighting installation (DRB#2) | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3256 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Fri Feb 12 07:00:00 IST 2021 | Fri Feb 12 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3257 | TT_TASK | COLO Lighting installation (DRB#2) | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3258 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Jan 29 07:00:00 IST 2021 | Fri Jan 29 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3259 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Fri Feb 12 07:00:00 IST 2021 | Fri Feb 12 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3260 | TT_TASK | COLO Lighting installation (DRB#2) | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3261 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3262 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Mar 09 07:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3263 | TT_TASK | COLO Lighting installation (DRB#2) | Wed Jun 09 07:00:00 IDT 2021 | Wed Jun 09 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3264 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3265 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Mar 09 07:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3266 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Jun 04 07:00:00 IDT 2021 | Fri Jun 04 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3267 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Sat Feb 20 07:00:00 IST 2021 | Sat Feb 20 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3268 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Mon Mar 22 07:00:00 IST 2021 | Mon Mar 22 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3269 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jun 19 07:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3270 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Sat Feb 20 07:00:00 IST 2021 | Sat Feb 20 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3271 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Mon Mar 22 07:00:00 IST 2021 | Mon Mar 22 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3272 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jun 19 07:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3273 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3274 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3275 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3276 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3277 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3278 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3279 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3280 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3281 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3282 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3283 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3284 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3285 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3286 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3287 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3288 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3290 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 05 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3291 | TT_TASK | Mechanical Equipment Piping Connections | Tue Nov 03 07:00:00 IST 2020 | Tue Nov 17 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3292 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3293 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3294 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3295 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3296 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3297 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3298 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3299 | TT_TASK | Fluid Cooler RI prefabrication | Thu Dec 10 07:00:00 IST 2020 | Wed Dec 16 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3300 | TT_TASK | Fluid Cooler RI prefabrication | Wed Dec 16 07:00:00 IST 2020 | Tue Dec 22 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3301 | TT_TASK | Fluid Cooler RI prefabrication | Wed Dec 23 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3302 | TT_TASK | Fluid Cooler RI prefabrication | Thu Jan 07 07:00:00 IST 2021 | Wed Jan 13 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3303 | TT_TASK | Fluid Cooler RI prefabrication | Thu Jan 14 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3304 | TT_TASK | Fluid Cooler RI prefabrication | Fri Jan 22 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3305 | TT_TASK | Fluid Cooler RI prefabrication | Tue Jan 26 07:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3306 | TT_TASK | Submit and approve shop drawing for PEMB penetrations | Mon Oct 19 08:00:00 IDT 2020 | Sun Nov 08 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3308 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3309 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3310 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3311 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3312 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3313 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3314 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3315 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3316 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3317 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3318 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3319 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3321 | TT_TASK | Yellow Tagging for COLO-2 UPM's | Fri Jan 29 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3322 | TT_TASK | Yellow Tagging for COLO-3 UPM's | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 |  | COMPLETED
3323 | TT_TASK | Yellow Tagging for COLO-4 UPM's | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 |  | COMPLETED
3324 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 11 07:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3326 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3327 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3328 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Mar 10 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3329 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 08 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3330 | TT_TASK | Fluid Cooler QAQC and Cx | Thu Mar 18 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3331 | TT_TASK | Fluid Cooler QAQC and Cx | Fri Apr 02 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3332 | TT_TASK | Fluid Cooler QAQC and Cx | Fri Mar 26 07:00:00 IDT 2021 | Sat Mar 27 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3333 | TT_TASK | Fluid Cooler QAQC and Cx | Tue Apr 06 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3334 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 14 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3335 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 21 07:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3336 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 14 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3337 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 28 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3338 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 21 07:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3339 | TT_TASK | Fluid Cooler QAQC and Cx | Thu May 06 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3341 | TT_TASK | COLO-2 CELL3 Rearrange Roxtec blocks per coordination layout | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3342 | TT_TASK | COLO2 CELL3 Interior MER conduit installation utility side | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 06 07:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3343 | TT_TASK | COLO-2 CELL3 Interior MER conduit installation building side | Tue Apr 20 07:00:00 IDT 2021 | Tue Apr 20 07:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3345 | TT_TASK | COLO-2 Cell-4 Rearrange Roxtec blocks per coordination layout | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3346 | TT_TASK | COLO2 CELL4 Interior MER conduit installation utility side | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3347 | TT_TASK | COLO2 CELL4 Interior MER conduit installation building side | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3350 | TT_TASK | COLO-2 Cell-1 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3351 | TT_TASK | COLO-2 Cell-2 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3352 | TT_TASK | COLO-2 Cell-3 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3353 | TT_TASK | COLO-2 Cell-4 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3354 | TT_TASK | COLO2 CELL1 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3355 | TT_TASK | COLO2 CELL2 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3356 | TT_TASK | COLO2 CELL3 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3357 | TT_TASK | COLO2 CELL4 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3360 | TT_TASK | Concrete interior - Create Punch list | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
3361 | TT_TASK | Concrete interior - Complete Punch List | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
3362 | TT_TASK | Garco Steel (Mezz steel, Yard) - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3363 | TT_TASK | Garco Steel (Mezz steel, Yard) - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3364 | TT_TASK | Sure Steel (Building, Mezz, Ceiling) - Create Punch list | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
3365 | TT_TASK | Sure Steel (Building, Mezz, Ceiling) - Complete Punch List | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
3366 | TT_TASK | Advantage - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3367 | TT_TASK | Advantage - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3368 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3369 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3370 | TT_TASK | VECA - Create Punch list | Tue Sep 07 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3371 | TT_TASK | VECA - Complete Punch List | Thu Sep 09 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3372 | TT_TASK | LINX - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3373 | TT_TASK | LINX - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3374 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3375 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3376 | TT_TASK | TCM- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3377 | TT_TASK | TCM - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3378 | TT_TASK | Cascade- Create Punch list | Mon Apr 26 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
3379 | TT_TASK | Cascade - Complete Punch List | Wed Apr 28 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3380 | TT_TASK | Submit GC Punch List to A/E | Tue Sep 21 07:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3381 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3382 | TT_TASK | Complete A/E Punchlist | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3383 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3384 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3385 | TT_TASK | VECA - Create Punch list | Fri Oct 29 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3386 | TT_TASK | VECA - Complete Punch List | Mon Nov 01 07:00:00 IST 2021 | Mon Nov 08 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3387 | TT_TASK | LINX - Create Punch list | Mon Aug 16 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3388 | TT_TASK | LINX - Complete Punch List | Wed Aug 18 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3389 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3390 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3391 | TT_TASK | TCM- Create Punch list | Wed Sep 22 07:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3392 | TT_TASK | TCM - Complete Punch List | Fri Sep 24 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3393 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3394 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3395 | TT_TASK | Submit GC Punch List to A/E | Tue Nov 09 07:00:00 IST 2021 | Tue Nov 09 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3396 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Nov 10 07:00:00 IST 2021 | Tue Nov 16 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3397 | TT_TASK | Complete A/E Punchlist | Wed Nov 17 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3398 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3399 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3400 | TT_TASK | VECA - Create Punch list | Tue Dec 14 07:00:00 IST 2021 | Wed Dec 15 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3401 | TT_TASK | VECA - Complete Punch List | Thu Dec 16 07:00:00 IST 2021 | Thu Dec 23 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3402 | TT_TASK | LINX - Create Punch list | Wed Oct 13 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3403 | TT_TASK | LINX - Complete Punch List | Fri Oct 15 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3404 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3405 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3406 | TT_TASK | TCM- Create Punch list | Wed Sep 22 07:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3407 | TT_TASK | TCM - Complete Punch List | Fri Sep 24 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3408 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3409 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3410 | TT_TASK | Submit GC Punch List to A/E | Mon Dec 27 07:00:00 IST 2021 | Mon Dec 27 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3411 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Tue Dec 28 07:00:00 IST 2021 | Wed Jan 05 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3412 | TT_TASK | Complete A/E Punchlist | Thu Jan 06 07:00:00 IST 2022 | Thu Jan 20 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3413 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3414 | TT_TASK | PCI - Complete Punch List | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3415 | TT_TASK | VECA - Create Punch list | Fri Jan 28 07:00:00 IST 2022 | Mon Jan 31 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3416 | TT_TASK | VECA - Complete Punch List | Tue Feb 01 07:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3417 | TT_TASK | LINX - Create Punch list | Fri Nov 19 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3418 | TT_TASK | LINX - Complete Punch List | Mon Nov 22 07:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3419 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3420 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3421 | TT_TASK | TCM- Create Punch list | Thu Nov 04 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3422 | TT_TASK | TCM - Complete Punch List | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3423 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3424 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3425 | TT_TASK | Submit GC Punch List to A/E | Tue Feb 08 07:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3426 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Feb 09 07:00:00 IST 2022 | Tue Feb 15 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3427 | TT_TASK | Complete A/E Punchlist | Wed Feb 16 07:00:00 IST 2022 | Tue Mar 01 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3428 | TT_TASK | COLO-2 Cell2 Rearrange Roxtec blocks per coordination layout (delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
3429 | TT_TASK | COLO2 CELL2 Interior MER conduit installation utility side(delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
3430 | TT_TASK | COLO-2 CELL2 Interior MER conduit installation building (delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
3432 | TT_TASK | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change(delete) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
3433 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3434 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3435 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3436 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
303 | TT_TASK | MSFT Issue DRB #1 for Review | Tue May 26 07:00:00 IDT 2020 | Mon Jun 01 17:00:00 IDT 2020 | Tue May 19 00:00:00 IDT 2020 | Mon Jul 20 00:00:00 IDT 2020 |  | COMPLETED
306 | TT_TASK | Lead Time for PEMB | Wed Feb 19 08:00:00 IST 2020 | Thu Jun 18 17:00:00 IDT 2020 | Mon Feb 24 00:00:00 IST 2020 | Thu Jun 18 00:00:00 IDT 2020 |  | COMPLETED
307 | TT_TASK | Lead Time for Rebar (Footings & Walls) | Mon Apr 27 08:00:00 IDT 2020 | Sun May 31 17:00:00 IDT 2020 | Mon Mar 30 00:00:00 IDT 2020 | Tue Apr 21 00:00:00 IDT 2020 |  | COMPLETED
308 | TT_TASK | Lead Time for COLO 1 Structural Interior Steel | Mon Aug 10 08:00:00 IDT 2020 | Sat Oct 31 17:00:00 IST 2020 | Tue Jun 30 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
309 | TT_TASK | Lead Time for Wall & Roof Metal Panels | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Mon Jun 29 00:00:00 IDT 2020 |  | COMPLETED
310 | TT_TASK | Lead Time for Admin/COLO 1 Yard Steel | Mon Aug 31 08:00:00 IDT 2020 | Sun Oct 18 17:00:00 IDT 2020 | Tue Jun 30 00:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 |  | COMPLETED
311 | TT_TASK | Lead Time for HM Ext. frames | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
312 | TT_TASK | Lead time for Drywall/Framing | Mon Aug 10 08:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Mon Aug 10 08:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
592 | TT_TASK | MV Ductbanks Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | Mon Sep 14 08:00:00 IDT 2020 | Sun Sep 20 17:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 | Sun Sep 06 00:00:00 IDT 2020 |  | COMPLETED
593 | TT_TASK | MV Wire Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | Wed Aug 12 08:00:00 IDT 2020 | Tue Nov 03 17:00:00 IST 2020 | Tue Aug 04 00:00:00 IDT 2020 | Mon Oct 26 00:00:00 IST 2020 |  | COMPLETED
594 | TT_TASK | UMS Vault Procurement DRB#1 | Mon Sep 28 08:00:00 IDT 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
595 | TT_TASK | DRB#1 BIM Modeling & Coordination DRB#1 JAZ to UMS/URS & UPM to UMS | Mon Aug 10 08:00:00 IDT 2020 | Sun Aug 23 17:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
596 | TT_TASK | Site- Neher Mcgrath Study DRB#1 JAZ to UMS/URS & UPM to UMS | Tue Aug 11 08:00:00 IDT 2020 | Mon Aug 24 17:00:00 IDT 2020 | Tue Aug 04 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
597 | TT_TASK | JAZ Riser Support DRB#1 Procurement/ Jaz Foundations/Construction | Mon Aug 10 08:00:00 IDT 2020 | Sun Oct 18 17:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
598 | TT_TASK | UPM to UMS Vaults Procurement DRB#1 | Tue Sep 08 08:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
600 | TT_TASK | MV Ductbanks Procurement | Wed Aug 12 08:00:00 IDT 2020 | Thu Aug 20 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
601 | TT_TASK | Telecom DuctBank / Vaults Procurement | Thu May 14 08:00:00 IDT 2020 | Mon May 18 17:00:00 IDT 2020 | Wed May 06 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
602 | TT_TASK | MV Wire Procurement | Wed Aug 12 08:00:00 IDT 2020 | Tue Nov 03 17:00:00 IST 2020 | Tue Jul 21 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
603 | TT_TASK | Off-Site BIM Modeling & Coordination | Mon Apr 27 08:00:00 IDT 2020 | Sun May 24 17:00:00 IDT 2020 | Tue Apr 14 00:00:00 IDT 2020 | Tue May 05 00:00:00 IDT 2020 |  | COMPLETED
604 | TT_TASK | Neher Mcgrath Study | Thu Jul 02 08:00:00 IDT 2020 | Thu Aug 06 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Fri Jul 24 00:00:00 IDT 2020 |  | COMPLETED
605 | TT_TASK | URS Vault Procurement | Mon Sep 28 08:00:00 IDT 2020 | Wed Nov 11 17:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
607 | TT_TASK | Site Temp Power Procurement & Infrastructure | Mon Jun 29 08:00:00 IDT 2020 | Mon Aug 31 08:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
609 | TT_TASK | Underground Grounding Procurement | Mon Apr 27 08:00:00 IDT 2020 | Sun May 17 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Tue Apr 28 00:00:00 IDT 2020 |  | COMPLETED
610 | TT_TASK | BIM Modeling (Under ground) | Tue May 05 08:00:00 IDT 2020 | Mon Jun 08 17:00:00 IDT 2020 | Tue May 05 08:00:00 IDT 2020 | Mon Jun 08 00:00:00 IDT 2020 |  | COMPLETED
611 | TT_TASK | Electrical Long Lead Equipment Procurement (Cablebus, Panel Boards) | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Mon Apr 27 08:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
612 | TT_TASK | BIM Modeling (Above ground) | Sun Aug 02 08:00:00 IDT 2020 | Wed Sep 30 17:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
615 | TT_TASK | Design / Lead Time for Electrical/Telecom (OFCI Telecom BOM Materials) | Mon Aug 10 08:00:00 IDT 2020 | Sat Nov 07 17:00:00 IST 2020 | Wed Jul 01 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
616 | TT_TASK | Design / Lead Time for Busway (OFCI Starline BOM Materials) | Thu Nov 26 08:00:00 IST 2020 | Thu Jan 14 17:00:00 IST 2021 | Mon Sep 21 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
619 | TT_TASK | Water treatment Skids Procurement ( sourcing materials and Materail approval only) | Mon Apr 27 08:00:00 IDT 2020 | Fri Nov 06 12:00:00 IST 2020 | Tue Apr 07 00:00:00 IDT 2020 | Mon Jul 06 00:00:00 IDT 2020 |  | COMPLETED
620 | TT_TASK | Design / Lead Time for M&P overhead | Mon Jun 29 08:00:00 IDT 2020 | Tue Jul 28 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
621 | TT_TASK | Design / Lead Time for Fire Protection | Mon Aug 31 08:00:00 IDT 2020 | Tue Sep 29 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
622 | TT_TASK | Design / Lead Time for Fire Alarm | Mon Jun 29 08:00:00 IDT 2020 | Thu Aug 27 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
628 | TT_TASK | URS/UMS Concrete Anchor and Vault Design | Mon Aug 10 07:00:00 IDT 2020 | Wed Aug 26 17:00:00 IDT 2020 | Wed Aug 05 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
629 | TT_TASK | URS/UMS Vault Submiital Review by EOR | Mon Sep 14 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Fri Sep 25 00:00:00 IDT 2020 |  | COMPLETED
632 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-2 PSR(10/13) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sat Dec 12 17:00:00 IST 2020 | Tue Oct 13 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
633 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-3 PSR(9/28) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Mon Dec 28 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
634 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-4 PSR (10/28) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Fri Nov 27 16:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
635 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-1 PSR (9/19) to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Tue Dec 15 17:00:00 IST 2020 | Sat Sep 19 00:00:00 IDT 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
637 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-1 11/25 to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Fri Oct 09 17:00:00 IDT 2020 | Wed Nov 25 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
638 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-2 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sun Nov 15 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
639 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-4 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Fri Nov 06 16:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
640 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-3 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sun Nov 15 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
642 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-1 PSR 11/23 to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Wed Oct 14 17:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
643 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-2 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
644 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-4 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Wed Nov 11 16:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Sun Jan 03 00:00:00 IST 2021 |  | COMPLETED
645 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-3 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Sun Jan 03 00:00:00 IST 2021 |  | COMPLETED
647 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-1 12/7 to MSFT delivery) | Sat Jan 09 08:00:00 IST 2021 | Sat Jan 09 08:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
648 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-2 12/7 to MSFT delivery) | Tue Jan 05 08:00:00 IST 2021 | Tue Jan 05 08:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
649 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-4 12/18 to MSFT delivery) | Sat Jan 09 08:00:00 IST 2021 | Sat Jan 09 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
650 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-3 12/18 to MSFT delivery) | Thu Jan 14 08:00:00 IST 2021 | Thu Jan 14 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
653 | TT_TASK | Review Fluid Cooler wiring and devices buyout with Stetner | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Wed Sep 23 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
654 | TT_TASK | Change order release for fluid cooler wiring devices | Mon Oct 19 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 | Mon Oct 26 00:00:00 IST 2020 |  | COMPLETED
657 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
658 | TT_TASK | Fluid Cooler RI in place | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
659 | TT_TASK | Fluid Cooler Wire install and Term | Fri Mar 05 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
661 | TT_TASK | Fluid Cooler Panel installation | Tue Mar 23 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
662 | TT_TASK | Fluid Cooler RI in place | Thu Mar 18 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
663 | TT_TASK | Fluid Cooler Wire install and Term | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 |  | COMPLETED
665 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 15 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
666 | TT_TASK | Fluid Cooler RI in place | Fri Feb 19 07:00:00 IST 2021 | Thu Feb 25 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
667 | TT_TASK | Fluid Cooler Wire install and Term | Thu Mar 18 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
669 | TT_TASK | Fluid Cooler Panel installation | Thu Mar 18 07:00:00 IST 2021 | Mon Mar 22 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
670 | TT_TASK | Fluid Cooler RI in place | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
671 | TT_TASK | Fluid Cooler Wire install and Term | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
674 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 29 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
675 | TT_TASK | Fluid Cooler RI in place | Thu Mar 25 07:00:00 IST 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
676 | TT_TASK | Fluid Cooler Wire install and Term | Thu Apr 01 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
678 | TT_TASK | Fluid Cooler Panel installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
679 | TT_TASK | Fluid Cooler RI in place | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
680 | TT_TASK | Fluid Cooler Wire install and Term | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
682 | TT_TASK | Fluid Cooler Panel installation | Thu Apr 01 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Sat Mar 27 00:00:00 IDT 2021 |  | COMPLETED
683 | TT_TASK | Fluid Cooler RI in place | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
684 | TT_TASK | Fluid Cooler Wire install and Term | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
687 | TT_TASK | Fluid Cooler Panel installation | Tue May 04 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
688 | TT_TASK | Fluid Cooler RI in place | Fri May 07 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
689 | TT_TASK | Fluid Cooler Wire install and Term | Fri May 14 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
691 | TT_TASK | Fluid Cooler Panel installation | Mon May 17 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
692 | TT_TASK | Fluid Cooler RI in place | Thu May 20 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
693 | TT_TASK | Fluid Cooler Wire install and Term | Fri May 28 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
695 | TT_TASK | Fluid Cooler Panel installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
696 | TT_TASK | Fluid Cooler RI in place | Fri Jun 04 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
697 | TT_TASK | Fluid Cooler Wire install and Term | Fri Jun 11 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
700 | TT_TASK | Fluid Cooler Panel installation | Tue Jun 08 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
701 | TT_TASK | Fluid Cooler RI in place | Fri Jun 11 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
702 | TT_TASK | Fluid Cooler Wire install and Term | Sat Jun 19 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
704 | TT_TASK | Fluid Cooler Panel installation | Fri Jun 11 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
705 | TT_TASK | Fluid Cooler RI in place | Sat Jun 19 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
706 | TT_TASK | Fluid Cooler Wire install and Term | Sat Jun 26 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
708 | TT_TASK | Fluid Cooler Panel installation | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
709 | TT_TASK | Fluid Cooler RI in place | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
710 | TT_TASK | Fluid Cooler Wire install and Term | Tue Jul 13 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
712 | TT_TASK | Fluid Cooler Panel installation | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
713 | TT_TASK | Fluid Cooler RI in place | Tue Jul 13 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
714 | TT_TASK | Fluid Cooler Wire install and Term | Tue Jul 20 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
718 | TT_TASK | ADMIN Overhead Rough-in (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
719 | TT_TASK | ADMIN Electrical Room Build out (DRB#2) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
720 | TT_TASK | ADMIN Lighting installation (DRB#2) | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
742 | TT_TASK | Water Treatmant Skid Fabrication | Mon Sep 14 08:00:00 IDT 2020 | Mon Dec 07 17:00:00 IST 2020 | Tue Aug 25 00:00:00 IDT 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
743 | TT_TASK | L&I approval process | Mon Sep 14 08:00:00 IDT 2020 | Tue Oct 13 17:00:00 IDT 2020 | Tue Aug 25 00:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 |  | COMPLETED
745 | TT_TASK | Water treatment delivery COLO-1 | Mon Dec 21 08:00:00 IST 2020 | Sun Dec 27 17:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
750 | TT_TASK | Submit and approve Shop drawings for UPM junstion box | Mon Oct 19 08:00:00 IDT 2020 | Sun Nov 08 17:00:00 IST 2020 | Fri Oct 09 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
751 | TT_TASK | Lead time for junction box | Mon Nov 02 08:00:00 IST 2020 | Sun Dec 13 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
752 | TT_TASK | Fabrication and Delivery of PEMB pentrations support steel | Mon Nov 09 08:00:00 IST 2020 | Fri Nov 13 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
756 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
757 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Tue Dec 15 00:00:00 IST 2020 |  | COMPLETED
758 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
760 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
761 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
762 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Feb 13 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
763 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
764 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Mar 05 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
765 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
768 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
769 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
770 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Feb 08 08:00:00 IST 2021 | Thu Feb 11 08:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
772 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
773 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
774 | TT_TASK | Install additional Cable bus (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
775 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
776 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Mar 02 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
777 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
780 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
781 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Tue Dec 15 00:00:00 IST 2020 |  | COMPLETED
782 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
784 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
785 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
786 | TT_TASK | Install additional Cable bus (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
787 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
788 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
789 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
792 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Dec 04 07:00:00 IST 2020 | Wed Dec 09 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
793 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
794 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
796 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
797 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
798 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 03 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
799 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
800 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Thu Mar 04 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
801 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
803 | TT_TASK | COLO-1 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon Mar 22 07:00:00 IST 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
804 | TT_TASK | COLO-1 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon Apr 05 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
805 | TT_TASK | COLO-1 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
806 | TT_TASK | COLO-1 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
810 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Sat Jan 02 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
811 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
812 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
814 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
815 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
816 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
817 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
818 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
819 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
822 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
823 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Thu Feb 11 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
824 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Mar 26 07:00:00 IDT 2021 | Mon Mar 29 17:00:00 IDT 2021 | Sat Feb 27 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
826 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
827 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
828 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
829 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
830 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
831 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
834 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
835 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
836 | TT_TASK | Install added DRB#3 Tray and conduit | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
838 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Sat Mar 27 00:00:00 IDT 2021 |  | COMPLETED
839 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 |  | COMPLETED
840 | TT_TASK | Install additional Cable bus (DRB#3) | Mon May 03 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
841 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
842 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue May 04 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
843 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
846 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
847 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Thu Feb 11 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
848 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 02 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
850 | TT_TASK | Install MER Supply duct | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
851 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri May 07 07:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
852 | TT_TASK | Install additional Cable bus (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
853 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue May 04 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
854 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
855 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 |  | COMPLETED
857 | TT_TASK | COLO-2 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Fri Apr 30 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
858 | TT_TASK | COLO-2 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
859 | TT_TASK | COLO-2 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 03 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
860 | TT_TASK | COLO-2 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
864 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
865 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
866 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
868 | TT_TASK | Install MER Supply duct | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
869 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
870 | TT_TASK | Install Roxtec block sealing and Install added tray cable (DRB#3) | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
871 | TT_TASK | Install additional Cable bus (DRB#3) | Tue May 18 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
872 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
873 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
876 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
877 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
878 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
880 | TT_TASK | Install MER Supply duct | Mon May 24 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
881 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
882 | TT_TASK | Install additional Cable bus (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
883 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 |  | COMPLETED
884 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Sat Aug 14 07:00:00 IDT 2021 | Sat Aug 14 17:00:00 IDT 2021 |  | COMPLETED
885 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Fri Sep 03 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Thu Aug 26 00:00:00 IDT 2021 |  | COMPLETED
888 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
889 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 |  | COMPLETED
890 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
892 | TT_TASK | Install MER Supply duct | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
893 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 |  | COMPLETED
894 | TT_TASK | Install additional Cable bus (DRB#3) | Sat May 29 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
895 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
896 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 |  | COMPLETED
897 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Mon Aug 09 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
900 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
901 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
902 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
904 | TT_TASK | Install MER Supply duct | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
905 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
906 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jun 05 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
907 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
908 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
909 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
911 | TT_TASK | COLO-3 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
912 | TT_TASK | COLO-3 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 |  | COMPLETED
913 | TT_TASK | COLO-3 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
914 | TT_TASK | COLO-3 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
918 | TT_TASK | Sure steel - PEMB MER penetration framing | Thu Feb 11 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
919 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
920 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
922 | TT_TASK | Install MER Supply duct | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
923 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Thu Jul 08 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
924 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
925 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
926 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
927 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
930 | TT_TASK | Sure steel - PEMB MER penetration framing | Tue Feb 16 07:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
931 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
932 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
934 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
935 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
936 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
937 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Fri Sep 03 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 |  |  | 400.0 | NOT_STARTED
938 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
939 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Sat Oct 02 07:00:00 IDT 2021 | Fri Oct 08 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
942 | TT_TASK | Sure steel - PEMB MER penetration framing | Thu Feb 11 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
943 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
944 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
946 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
947 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Thu Jul 08 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 |  | COMPLETED
948 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Jul 28 00:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 |  | COMPLETED
949 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
950 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
951 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
954 | TT_TASK | Sure steel - PEMB MER penetration framing | Tue Feb 16 07:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
955 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
956 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 00:00:00 IDT 2021 |  | COMPLETED
958 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
959 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
960 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
961 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
962 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
963 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
965 | TT_TASK | COLO-4 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Thu Sep 09 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
966 | TT_TASK | COLO-4 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Wed Aug 18 00:00:00 IDT 2021 |  |  | IN_PROGRESS
967 | TT_TASK | COLO-4 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
968 | TT_TASK | COLO-4 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
970 | TT_TASK | Site Shut Down - 9/9/2020 | Mon Sep 14 07:00:00 IDT 2020 | Mon Sep 14 17:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 |  | COMPLETED
971 | TT_TASK | Site Shut Down - 9/10/2020 | Tue Sep 15 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Thu Sep 10 00:00:00 IDT 2020 | Thu Sep 10 00:00:00 IDT 2020 |  | COMPLETED
972 | TT_TASK | Site Shut Down - 9/11/2020 | Wed Sep 16 07:00:00 IDT 2020 | Wed Sep 16 17:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
973 | TT_TASK | Site Shut Down - 9/12/2020 | Thu Sep 17 07:00:00 IDT 2020 | Thu Sep 17 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
974 | TT_TASK | Site Shut Down - 9/14/2020 | Mon Sep 28 07:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 |  | COMPLETED
975 | TT_TASK | Site Shut Down - 9/15/2020 | Tue Sep 29 07:00:00 IDT 2020 | Tue Sep 29 17:00:00 IDT 2020 | Tue Sep 15 00:00:00 IDT 2020 | Tue Sep 15 00:00:00 IDT 2020 |  | COMPLETED
976 | TT_TASK | Site Shut Down - 9/16/2020 | Wed Sep 30 07:00:00 IDT 2020 | Wed Sep 30 17:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 |  | COMPLETED
979 | TT_TASK | Complete Remaining IWW piping to tie-in point | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 29 17:00:00 IST 2020 | Mon Sep 21 00:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
980 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
982 | TT_TASK | Complete Remaining Sanitary piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
983 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
985 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
986 | TT_TASK | Complete Remaining Fire Main piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
988 | TT_TASK | Complete Remaining ITW piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
989 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
991 | TT_TASK | Complete Remaining Telecom Duct Back (excluding Tie-in) | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
992 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
995 | TT_TASK | Delay in COLO-1- Cell-1 MER Delivery (Duration = COLO1 Cell-1 PSR(11/6/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sat Jan 30 17:00:00 IST 2021 | Fri Nov 06 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
996 | TT_TASK | Delay in COLO-1- Cell-2 MER Delivery (Duration = COLO1 Cell-2 PSR(11/13/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Fri Jan 29 17:00:00 IST 2021 | Fri Nov 13 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
997 | TT_TASK | Delay in COLO-1- Cell-3 MER Delivery (Duration = COLO1 Cell-3 PSR(11/20/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Feb 04 17:00:00 IST 2021 | Fri Nov 20 00:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 |  | COMPLETED
998 | TT_TASK | Delay in COLO-1- Cell-4 MER Delivery (Duration = COLO1 Cell-4 PSR(11/30/20) to MSFT delivery) | Mon Feb 01 08:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1000 | TT_TASK | Delay in COLO-2- Cell-1 MER Delivery (Duration = Colo1 Cell-1 PSR(12/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Feb 11 10:00:00 IST 2021 | Tue Dec 15 00:00:00 IST 2020 | Wed Feb 03 00:00:00 IST 2021 |  | COMPLETED
1001 | TT_TASK | Delay in COLO-2- Cell-2 MER Delivery (Duration = COLO 2 Cell-2 PSR(12/22/20) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1002 | TT_TASK | Delay in COLO-2- Cell-3 MER Delivery (Duration = COLO 2- Cell-3 PSR(12/28/20) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1003 | TT_TASK | Delay in COLO-2- Cell-4 MER Delivery (Duration = COLO 2- Cell-4 PSR(1/5/21) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Jan 05 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1005 | TT_TASK | Delay in COLO-3- Cell-1 MER Delivery (Duration = COLO-3 Cell-1 PSR(1/29/21) to MSFT delivery) | Sun Jan 31 08:00:00 IST 2021 | Sat Apr 03 17:00:00 IDT 2021 | Fri Jan 29 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1006 | TT_TASK | Delay in COLO-3- Cell-2 MER Delivery (Duration = COLO-3 Cell-2 PSR(2/5/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 05 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1007 | TT_TASK | Delay in COLO-3 Cell-3 MER Delivery (Duration = COLO-3 Cell-3 PSR(2/12/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Feb 12 00:00:00 IST 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1008 | TT_TASK | Delay in COLO-3 Cell-4 MER Delivery (Duration = COLO-3 Cell-4 PSR(2/19/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Thu Apr 22 00:00:00 IDT 2021 |  | COMPLETED
1010 | TT_TASK | Delay in COLO-4- Cell-1 MER Delivery (Duration= COLO-4 Cell-1 PSR(3/12/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Mar 12 00:00:00 IST 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
1011 | TT_TASK | Delay in COLO-4- Cell-2 MER Delivery (Duration = COLO-4 Cell-2 PSR(3/19/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1012 | TT_TASK | Delay in COLO-4- Cell-3 MER Delivery (Duration = COLO-4 Cell-3 PSR(3/26/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1013 | TT_TASK | Delay in COLO-4- Cell-4 MER Delivery (Duration = COLO-4 Cell-4 PSR(4/2/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 | Sun May 09 00:00:00 IDT 2021 |  | COMPLETED
1015 | TT_TASK | Wire Mesh Procurement | Mon Nov 16 08:00:00 IST 2020 | Wed Dec 23 12:00:00 IST 2020 | Thu Sep 24 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
1016 | TT_TASK | Wire Mesh Submittal Approval | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Wed Sep 16 00:00:00 IDT 2020 | Wed Sep 23 00:00:00 IDT 2020 |  | COMPLETED
1017 | TT_TASK | Wire Mesh Procurement Delay | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Sat Oct 24 00:00:00 IDT 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1019 | TT_TASK | Complete Remaining Telecom Duct Back tie-in Install to MWH02 | Mon Dec 21 07:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1020 | TT_TASK | Clayco waiting on MSOW Approval | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Tue Dec 01 00:00:00 IST 2020 |  | COMPLETED
1021 | TT_TASK | Clayco MSOW Submited for approval | Mon Nov 16 07:00:00 IST 2020 | Tue Nov 17 17:00:00 IST 2020 | Fri Oct 16 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
1022 | TT_TASK | MSFT Stand down/ Additional Hydro excavation | Mon Dec 21 07:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
1024 | TT_TASK | Delay in UMS delivery (Duration = (9/19) to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Thu Nov 19 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
1027 | TT_TASK | Delay In COLO-1 Cell-1 Generator (Duration= COLO-1 Cell-1 PSR(9/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Tue Jan 19 17:00:00 IST 2021 | Tue Sep 15 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1028 | TT_TASK | Delay In COLO-1 Cell-2 Generator (Duration= COLO-1 Cell-2 PSR(9/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sat Feb 06 17:00:00 IST 2021 | Tue Sep 15 00:00:00 IDT 2020 | Mon Nov 02 00:00:00 IST 2020 |  | COMPLETED
1029 | TT_TASK | Delay In COLO-1 Cell-4 Generator (Duration= COLO-1 Cell-4 PSR(9/29/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Sep 29 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1030 | TT_TASK | Delay In COLO-1 Cell-3 Generator (Duration= COLO-1 Cell-3 PSR(9/29/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Wed Feb 03 17:00:00 IST 2021 | Tue Sep 29 00:00:00 IDT 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1032 | TT_TASK | Delay In COLO-2 Cell-1 Generator (Duration= COLO-2 Cell-1 PSR(10/12/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sun Mar 07 17:00:00 IST 2021 | Mon Oct 12 00:00:00 IDT 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1033 | TT_TASK | Delay In COLO-2 Cell-2 Generator (Duration= COLO-2 Cell-2 PSR(11/6/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sun Feb 21 17:00:00 IST 2021 | Fri Nov 06 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
1034 | TT_TASK | Delay In COLO-2 Cell-4 Generator (Duration= COLO-2 Cell-4 PSR(11/21/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Fri Feb 19 17:00:00 IST 2021 | Sat Nov 21 00:00:00 IST 2020 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
1035 | TT_TASK | Delay In COLO-2 Cell-3 Generator (Duration= COLO-2 Cell-3 PSR(10/22/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Mar 18 17:00:00 IST 2021 | Thu Oct 22 00:00:00 IDT 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1037 | TT_TASK | 6.1.39.1- COLO-3 CEll-1 GEN Belly tank Failed pressure test | Mon Mar 15 07:00:00 IST 2021 | Fri Apr 09 17:00:00 IDT 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
1038 | TT_TASK | 6.1.39.2- COLO-3 Cell-1 Replace Belly Tank and Set GEN | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1039 | TT_TASK | Delay In COLO-3 Cell-1 Generator (Duration= COLO-3 Cell-1 PSR(10/12/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Sat May 08 17:00:00 IDT 2021 | Mon Nov 09 00:00:00 IST 2020 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1040 | TT_TASK | Delay In COLO-3 Cell-2 Generator (Duration= COLO-3 Cell-2 PSR(11/6/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Tue Mar 30 17:00:00 IDT 2021 | Sat Nov 21 00:00:00 IST 2020 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
1041 | TT_TASK | Delay In COLO-3 Cell-4 Generator (Duration= COLO-3 Cell-4 PSR(11/21/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Mar 18 17:00:00 IST 2021 | Wed Dec 09 00:00:00 IST 2020 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
1042 | TT_TASK | Delay In COLO-3 Cell-3 Generator (Duration= COLO-3 Cell-3 PSR(10/22/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Apr 29 17:00:00 IDT 2021 | Thu Nov 05 00:00:00 IST 2020 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1044 | TT_TASK | Delay In COLO-4 Cell-1 Generator (Duration= COLO-4 Cell-1 PSR(10/12/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Sat Jun 05 17:00:00 IDT 2021 | Mon Nov 09 00:00:00 IST 2020 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
1045 | TT_TASK | Delay In COLO-4 Cell-2 Generator (Duration= COLO-4 Cell-2 PSR(11/6/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Apr 01 17:00:00 IDT 2021 | Wed Dec 09 00:00:00 IST 2020 | Thu Mar 11 00:00:00 IST 2021 |  | COMPLETED
1046 | TT_TASK | Delay In COLO-4 Cell-4 Generator (Duration= COLO-4 Cell-4 PSR(11/21/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Wed Apr 14 17:00:00 IDT 2021 | Mon Nov 30 00:00:00 IST 2020 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
1047 | TT_TASK | Delay In COLO-4 Cell-3 Generator (Duration= COLO-4 Cell-3 PSR(10/22/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Tue May 11 17:00:00 IDT 2021 | Fri Nov 20 00:00:00 IST 2020 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1050 | TT_TASK | COLO1 CELL1 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1051 | TT_TASK | COLO1 CELL3 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
1052 | TT_TASK | COLO1 CELL2 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1053 | TT_TASK | COLO1 CELL4 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
1058 | TT_TASK | COLO-1 Cell-1 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1059 | TT_TASK | COLO1 CELL1 Interior MER conduit installation utility side | Fri Mar 05 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1060 | TT_TASK | COLO-1 Cell-1 Interior MER conduit installation building side Complete March1st (MER discovery Corrections & Signoff) | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1063 | TT_TASK | COLO-1 CELL3 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1064 | TT_TASK | COLO1 CELL3 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1065 | TT_TASK | COLO-1 CELL3 Interior MER conduit installation building side | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
1068 | TT_TASK | COLO-1 CELL2 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1069 | TT_TASK | COLO1 CELL2 Interior MER conduit installation utility side | Sat Mar 06 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1070 | TT_TASK | COLO-1 CELL2 Interior MER conduit installation building side | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1073 | TT_TASK | COLO-1 CELL4 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1074 | TT_TASK | COLO1 CELL4 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1075 | TT_TASK | COLO-1 CELL4 Interior MER conduit installation building side | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
1079 | TT_TASK | COLO-2 Cell-1 Rearrange Roxtec blocks per coordination layout | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1080 | TT_TASK | COLO2 CELL1 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1081 | TT_TASK | COLO-2 Cell-1 Interior MER conduit installation building side | Mon Apr 05 07:00:00 IDT 2021 | Mon Apr 19 17:00:00 IDT 2021 | Fri Mar 05 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1089 | TT_TASK | COLO-1 Cell-1 MER Flex Conduit fixes | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1090 | TT_TASK | COLO-1 Cell-3 MER Flex Conduit fixes | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1091 | TT_TASK | COLO-1 Cell-2 MER Flex Conduit fixes | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1092 | TT_TASK | COLO-1 Cell-4 MER Flex Conduit fixes | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1095 | TT_TASK | Safety Stop work due to failed Starline Hangers | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 01 07:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
1096 | TT_TASK | Lead time for replacement hangers from Starline | Mon Feb 01 08:00:00 IST 2021 | Sun Feb 07 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
1097 | TT_TASK | COLO-1 Cell-1 Remove/ Replace busway & hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1098 | TT_TASK | COLO-1 Cell-3 Remove/ Replace busway & hangers | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1099 | TT_TASK | COLO-1 Cell-2 Remove/ Replace busway & hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1100 | TT_TASK | COLO-1 Cell-4 Remove/ Replace busway & hangers | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1101 | TT_TASK | Determined Startline hanger Design Issue & Approve replacement hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
1102 | TT_TASK | COLO-2 Cell-1 Remove/ Replace busway & hangers | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1103 | TT_TASK | COLO-2 Cell-2 Remove/ Replace busway & hangers | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1105 | TT_TASK | Lead time for missing Admin Gen Bussing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 |  | COMPLETED
1106 | TT_TASK | Admin Gen Bussing Install | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1107 | TT_TASK | Awaiting DCE approval of Non NEMA standard Lugs | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1108 | TT_TASK | Awaiting Phase conductor lugs from NC power as per RFI#412 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1109 | TT_TASK | 6.1.41 - Incorrect Lugs for Admin Gen Main Bussing | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1112 | TT_TASK | COLO-1 Cell-4 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
1113 | TT_TASK | COLO-1 Cell-3 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Thu Mar 11 00:00:00 IST 2021 |  | COMPLETED
1114 | TT_TASK | COLO-1 Cell-2 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1115 | TT_TASK | COLO-1 Cell-1 SE Install UPS batteries in cabinet | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1117 | TT_TASK | COLO-2 Cell-1 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
1118 | TT_TASK | COLO-2 Cell-2 SE Install UPS batteries in cabinet | Fri Apr 30 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
1119 | TT_TASK | COLO-2 Cell-3 SE Install UPS batteries in cabinet | Sat May 08 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1120 | TT_TASK | COLO-2 Cell-4 SE Install UPS batteries in cabinet | Sat May 15 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
1122 | TT_TASK | COLO-3 Cell-1 SE Install UPS batteries in cabinet | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1123 | TT_TASK | COLO-3 Cell-2 SE Install UPS batteries in cabinet | Tue May 25 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1124 | TT_TASK | COLO-3 Cell-3 SE Install UPS batteries in cabinet | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1125 | TT_TASK | COLO-3 Cell-4 SE Install UPS batteries in cabinet | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1127 | TT_TASK | COLO-4 Cell-1 SE Install UPS batteries in cabinet | Tue Sep 14 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1128 | TT_TASK | COLO-4 Cell-2 SE Install UPS batteries in cabinet | Wed Sep 29 07:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  | 320.0 | IN_PROGRESS
1129 | TT_TASK | COLO-4 Cell-3 SE Install UPS batteries in cabinet | Tue Sep 07 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
1130 | TT_TASK | COLO-4 Cell-4 SE Install UPS batteries in cabinet | Tue Sep 21 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
1132 | TT_TASK | COLO-2 CEll-2 Awaiting SE Revised tool Come along for MER Lift & Set | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
1133 | TT_TASK | COLO-2 CEll-3 Awaiting SE Revised tool Come along for MER Lift & Set | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1134 | TT_TASK | MER shipping split connection Safety Standown & RCA Review | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1137 | TT_TASK | COLO-2 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1138 | TT_TASK | RFI#432 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
1139 | TT_TASK | Lead time for tube steel | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
1140 | TT_TASK | COLO-2 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1141 | TT_TASK | COLO-2 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Thu Apr 01 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1142 | TT_TASK | COLO-2 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1144 | TT_TASK | COLO-3 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Fri May 07 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 |  | COMPLETED
1145 | TT_TASK | COLO-3 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Wed May 19 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed May 19 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 |  | COMPLETED
1146 | TT_TASK | COLO-3 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Thu May 13 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Thu May 13 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 |  | COMPLETED
1147 | TT_TASK | COLO-3 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Wed May 26 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Wed May 26 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 |  | COMPLETED
1149 | TT_TASK | COLO-4 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1150 | TT_TASK | COLO-4 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1151 | TT_TASK | COLO-4 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1152 | TT_TASK | COLO-4 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Mon Jun 14 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1154 | TT_TASK | All Construction activities -Safety Standown due to Admin Gen unplanned Energization | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
1156 | TT_TASK | COLO-1 Cell-1 Field Modification of tray | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1157 | TT_TASK | COLO-1 Cell-2 Field Modification of tray | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Jan 21 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1160 | TT_TASK | #3. Snow- 1/27/2021(one full day) | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 |  | COMPLETED
1161 | TT_TASK | #4. Extreme Heat - 6/28/21- 7/2/21(Effecting COLO-4 Yard work) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
1162 | TT_TASK | #5 Extreme heat -production loss in Yards 7/1/21 through 7/14/21 (11 half days of loss) | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 09 00:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
1163 | TT_TASK | #6 Extreme heat - Production loss in Yards 7/15/21 through 7/31/21 (3 half days) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
1164 | TT_TASK | #1. Rain And High Winds- 10/13/2020(half day only) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Tue Oct 13 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1165 | TT_TASK | #2. Snow -12/30/20 (one full day) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Wed Dec 30 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
1168 | TT_TASK | COLO-1 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Mon Jan 11 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
1169 | TT_TASK | COLO-1 CELL-3 WA State L&I onsite inspection & Approval to Connect to MER | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1170 | TT_TASK | COLO-1 CELL-2 WA State L&I onsite inspection & Approval to Connect to MER | Sat Jan 23 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1171 | TT_TASK | COLO-1 CELL-4 WA State L&I onsite inspection & Approval to Connect to MER | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1173 | TT_TASK | COLO-2 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Fri Mar 12 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1174 | TT_TASK | COLO-2 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Tue Mar 23 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1175 | TT_TASK | COLO-2 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
1176 | TT_TASK | COLO-2 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Fri Apr 09 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1178 | TT_TASK | COLO-3 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Sat May 08 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1179 | TT_TASK | COLO-3 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Fri May 14 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1180 | TT_TASK | COLO-3 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1181 | TT_TASK | COLO-3 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1183 | TT_TASK | COLO-4 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 |  | COMPLETED
1184 | TT_TASK | COLO-4 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Sat Jun 19 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1185 | TT_TASK | COLO-4 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
1186 | TT_TASK | COLO-4 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 |  | COMPLETED
1189 | TT_TASK | 6.1.36 Rework for Addtional circuits for UMS URS Battery charger feed upsize | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1190 | TT_TASK | 6.1.34.1 COLO-1 Cell-1 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1191 | TT_TASK | 6.1.34.2 COLO-1 Cell-2 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1192 | TT_TASK | 6.1.34.3 COLO-1 Cell-3 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 |  | COMPLETED
1193 | TT_TASK | 6.1.34.4 COLO-1 Cell-4 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 |  | COMPLETED
1194 | TT_TASK | 6.1.01.0 Awaiting MER 10A HRG's (lead time= 8 weeks from 2/2/2021) | Mon Mar 01 07:00:00 IST 2021 | Mon Apr 12 17:00:00 IDT 2021 | Tue Feb 02 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
1195 | TT_TASK | 6.1.09 Awaiting Rev-D for Coordination study (DRB3/SCCS/ Submittal Breaker verification) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1196 | TT_TASK | 6.1.26.1 L2/L3 Scripts SE MER overall Script | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
1197 | TT_TASK | 6.1.33 URS UMS Ground Buss hole Pattern | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1198 | TT_TASK | 6.1.35 UPS battery IR Scanning | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1199 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-1 Cell-1 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1200 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-1 Cell-4 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1201 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-1 Cell-3 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1202 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-1 Cell-2 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1203 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-2 Cell-1 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1204 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-2 Cell-2 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1205 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-2 Cell-3 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1206 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-2 Cell-4 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue Jul 13 00:00:00 IDT 2021 | Mon Jul 19 00:00:00 IDT 2021 |  | COMPLETED
1207 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-3 Cell-1 | Tue Aug 31 07:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
1208 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-3 Cell-4 | Tue Sep 07 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  |  | 10.0 | NOT_STARTED
1209 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-3 Cell-3 | Tue Sep 07 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  |  | 10.0 | NOT_STARTED
1210 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-3 Cell-2 | Thu Sep 09 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1211 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-4 Cell-1 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1212 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-4 Cell-4 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1213 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-4 Cell-3 | Mon Oct 18 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1214 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-4 Cell-2 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1216 | TT_TASK | 6.1.37- 6.2.01- Ground Fault setting on COLO-2 Gen MCB01 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Wed Apr 28 17:00:00 IDT 2021 |  | COMPLETED
1218 | TT_TASK | 6.1.38 PDU MCB01 LOTO Provisions | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1220 | TT_TASK | 6.1.11 Awaiting BAS Backplanes from Siemens to VECA for Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
1221 | TT_TASK | 6.1.26.2 L2/L3 Scripts Siemens BAS SAT Scripts | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1222 | TT_TASK | 6.1.11 Awaiting Liftstation #3 BAS Backplanes from Siemens to VECA for Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1223 | TT_TASK | 6.1.11 Liftstation #3 BAS Install / Pull wire / term Backplanes | Mon May 17 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 |  | COMPLETED
1226 | TT_TASK | COLO-2 Cell-1 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Dec 29 00:00:00 IST 2020 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1227 | TT_TASK | COLO-2 Cell-2 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sun Jan 10 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1228 | TT_TASK | COLO-2 Cell-3 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Jan 20 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1229 | TT_TASK | COLO-2 Cell-4 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sat Jan 23 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1231 | TT_TASK | COLO-3 Cell-1 Install Missing Raceway & Bussing within generator | Mon Apr 26 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1232 | TT_TASK | COLO-3 Cell-2 Install Missing Raceway & Bussing within generator | Thu Apr 29 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1233 | TT_TASK | COLO-3 Cell-3 Install Missing Raceway & Bussing within generator | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
1234 | TT_TASK | COLO-3 Cell-4 Install Missing Raceway & Bussing within generator | Tue May 04 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1236 | TT_TASK | COLO-4 Cell-1 Install Missing Raceway & Bussing within generator | Tue May 25 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
1237 | TT_TASK | COLO-4 Cell-2 Install Missing Raceway & Bussing within generator | Tue May 11 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1238 | TT_TASK | COLO-4 Cell-3 Install Missing Raceway & Bussing within generator | Thu May 20 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1239 | TT_TASK | COLO-4 Cell-4 Install Missing Raceway & Bussing within generator | Mon May 17 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
1242 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1243 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 2weeks- fab and ship | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Mon Apr 05 00:00:00 IDT 2021 |  | COMPLETED
1244 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 1 week to install | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
1245 | TT_TASK | 6.1.44- MER Battery Monitoring Software Â– Constraint to EPMS checkouts/Point Â– Point(needed by 4/23) | Mon Mar 15 07:00:00 IST 2021 | Mon Jun 07 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Aug 07 07:00:00 IDT 2021 |  | COMPLETED
1246 | TT_TASK | 6.1.46- Site UPM Inspections | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
1247 | TT_TASK | 6.1.47- COLO-1 Cell-2 UPS01- Factory Test thermal event | Mon Mar 15 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
1249 | TT_TASK | 6.1.40- 480V house power to Gen Enclousure is Fed OH vs UG | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1254 | TT_TASK | Downtime awaiting solution for safety space constraint | Mon Apr 26 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1256 | TT_TASK | NOPC-18 Remove COLO-1 Cell-1 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1257 | TT_TASK | Rubicon MSB inspection complete (ready for transformer reinstall) | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Mon Apr 26 07:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1258 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-1 transformer | Tue May 25 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1260 | TT_TASK | NOPC-18 Remove COLO-1 Cell-2 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
1261 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1262 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-2 transformer | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1264 | TT_TASK | NOPC-18 Remove COLO-1 Cell-3 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 |  | COMPLETED
1265 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1266 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-3 transformer | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1268 | TT_TASK | NOPC-18 Remove COLO-1 Cell-4 transformer | Mon May 17 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1269 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1270 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-4 transformer | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1273 | TT_TASK | NOPC-18 Remove COLO-2 Cell-1 transformer | Tue Jun 01 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue Jun 08 00:00:00 IDT 2021 |  | COMPLETED
1274 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-1 transformer | Thu Jul 22 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1276 | TT_TASK | NOPC-18 Remove COLO-2 Cell-2 transformer | Wed Jun 02 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
1277 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-2 transformer | Fri Jul 23 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
1279 | TT_TASK | NOPC-18 Remove COLO-2 Cell-3 transformer | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 |  | COMPLETED
1280 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-3 transformer | Thu Jul 29 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1282 | TT_TASK | NOPC-18 Remove COLO-2 Cell-4 transformer | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1283 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-4 transformer | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Jul 09 00:00:00 IDT 2021 | Mon Jul 12 00:00:00 IDT 2021 |  | COMPLETED
1286 | TT_TASK | NOPC-18 Remove COLO-3 Cell-1 transformer | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
1287 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-1 transformer | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 22 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1289 | TT_TASK | NOPC-18 Remove COLO-3 Cell-2 transformer | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jul 24 07:00:00 IDT 2021 | Sat Jul 24 17:00:00 IDT 2021 |  | COMPLETED
1290 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-2 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
1292 | TT_TASK | NOPC-18 Remove COLO-3 Cell-3 transformer | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Thu Aug 19 07:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1293 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-3 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1295 | TT_TASK | NOPC-18 Remove COLO-3 Cell-4 transformer | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1296 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-4 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1299 | TT_TASK | NOPC-18 Remove COLO-4 Cell-1 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1300 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-1 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1302 | TT_TASK | NOPC-18 Remove COLO-4 Cell-2 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1303 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-2 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1305 | TT_TASK | NOPC-18 Remove COLO-4 Cell-3 transformer | Wed Sep 29 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1306 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-3 transformer | Sat Oct 09 07:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1308 | TT_TASK | NOPC-18 Remove COLO-4 Cell-4 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1309 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-4 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1311 | TT_TASK | PDU termination crew downtime due to COVID-19 | Sat Apr 24 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Sat Apr 24 07:00:00 IDT 2021 |  | COMPLETED
1314 | TT_TASK | 6.2.03- Replace ADP01 faulty trip units | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1315 | TT_TASK | 6.1.51-COLO-1 Cell-1,2 Factory conductors not terminated per drawings | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1316 | TT_TASK | 6.1.49 - COLO-1 Cell-1 Awaiting Ground Lug solution, procurement, installation of labelling ATS 01-06 | Fri Apr 30 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
1317 | TT_TASK | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
1318 | TT_TASK | 6.1.53-COLO-1 Cell-1,2 UPS01, PNL01 awaiting missing breakers | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1319 | TT_TASK | 6.1.53-COLO-1 Cell-1,2,3,4 UPS01, PNL01 Install/ term Missing breakers | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1320 | TT_TASK | 6.1.59 (6.1.51 carryover) -COLO-1 Cell-1,2 Factory conductors exertherm corrections | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
1321 | TT_TASK | 6.1.50- SCCS Revision#10 (RFI-540) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1325 | TT_TASK | 6.1.54- TCM Awaiting Admin Siemens Break tank parts | Mon May 17 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1326 | TT_TASK | 6.1.54- Install Breaktank parts | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1328 | TT_TASK | 6.2.03- Replace Damaged UPM in COLO-4 Cell-4 | Thu May 06 07:00:00 IDT 2021 | Sat May 08 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1330 | TT_TASK | 6.1.55-COLO-1 - FC Factoy Re-wire (RFI-502) | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1331 | TT_TASK | 6.1.55-COLO-2 - FC Factoy Re-wire (RFI-502) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1332 | TT_TASK | 6.1.55-COLO-3 - FC Factoy Re-wire (RFI-502) | Sat Jun 05 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1333 | TT_TASK | 6.1.55-COLO-4 - FC Factoy Re-wire (RFI-502) | Thu Jun 10 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1335 | TT_TASK | 6.1.57 -Awaiting revised coordination study #9 | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
1336 | TT_TASK | Reprint revised panel 3,4 Arc flash labels | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1337 | TT_TASK | Print new DC Arc flash labels for Admin ELP | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1340 | TT_TASK | 6.1.58-RFI-528- COLO-1 - SF/RF Circuitry & terminal block rework | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
1341 | TT_TASK | 6.1.63- COLO1-UPS01-PNL01 Compass Issues Constraining L3Â’s | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
1342 | TT_TASK | 6.1.56 - COLO-1 Awaiting MSB/ADP Ground Lug replacements, Installation of labelling | Fri Apr 30 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
1349 | TT_TASK | All trades stand down | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
1350 | TT_TASK | Veca standown | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
1353 | TT_TASK | COLO-1 Cell-1 MER-UPS Battery Disconnect modifications rework | Wed Jun 16 07:00:00 IDT 2021 | Sat Jun 19 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1354 | TT_TASK | COLO-1 Cell-2 MER-UPS Battery Disconnect modifications rework | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1355 | TT_TASK | COLO-1 Cell-3 MER-UPS Battery Disconnect modifications rework | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
1356 | TT_TASK | COLO-1 Cell-4 MER-UPS Battery Disconnect modifications rework | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
1357 | TT_TASK | RFI-548 COLO MSB to UPS Battery disconnect solution approval | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1358 | TT_TASK | ADMIN-UPS Battery Disconnect modifications rework | Wed Jun 16 07:00:00 IDT 2021 | Sat Jun 19 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1359 | TT_TASK | RFI-552 Admin MSB to UPS Battery disconnect solution approval | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
1361 | TT_TASK | COLO-2 Cell-2 MER-UPS Battery Disconnect modifications rework | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 |  | COMPLETED
1362 | TT_TASK | COLO-2 Cell-1 MER-UPS Battery Disconnect modifications rework | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  | COMPLETED
1363 | TT_TASK | COLO-2 Cell-3 MER-UPS Battery Disconnect modifications rework | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  | COMPLETED
1364 | TT_TASK | COLO-2 Cell-4 MER-UPS Battery Disconnect modifications rework | Fri Jul 02 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 23 07:00:00 IDT 2021 |  | COMPLETED
1366 | TT_TASK | COLO-3 Cell-1 MER-UPS Battery Disconnect modifications rework | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 |  | COMPLETED
1367 | TT_TASK | COLO-3 Cell-2 MER-UPS Battery Disconnect modifications rework | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1368 | TT_TASK | COLO-3 Cell-3 MER-UPS Battery Disconnect modifications rework | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
1369 | TT_TASK | COLO-3 Cell-4 MER-UPS Battery Disconnect modifications rework | Sat Sep 11 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Mon Aug 16 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1371 | TT_TASK | COLO-4 Cell-1 MER-UPS Battery Disconnect modifications rework | Thu Sep 16 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
1372 | TT_TASK | COLO-4 Cell-2 MER-UPS Battery Disconnect modifications rework | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
1373 | TT_TASK | COLO-4 Cell-3 MER-UPS Battery Disconnect modifications rework | Mon Sep 27 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1374 | TT_TASK | COLO-4 Cell-4 MER-UPS Battery Disconnect modifications rework | Fri Sep 03 07:00:00 IDT 2021 | Thu Sep 09 17:00:00 IDT 2021 |  |  | 270.0 | NOT_STARTED
1377 | TT_TASK | COLO-3 Cell-3 Remove inaccessible tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 |  | COMPLETED
1378 | TT_TASK | COLO-3 CEll-3 Reinstall tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
1379 | TT_TASK | COLO-3 Cell-4 Remove inaccessible tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Sat Jun 12 00:00:00 IDT 2021 |  | COMPLETED
1380 | TT_TASK | COLO-3 Cell-4 Reinstall tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1381 | TT_TASK | COLO-4 Cell-1 Remove inaccessible tray in MER | Mon Jul 12 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Sat Jun 12 00:00:00 IDT 2021 |  | COMPLETED
1382 | TT_TASK | COLO-4 Cell-1 Reinstall tray in MER | Tue Aug 03 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
1383 | TT_TASK | COLO-4 Cell-2 Remove inaccessible tray in MER | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
1384 | TT_TASK | COLO-4 Cell-2 Reinstall tray in MER | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1385 | TT_TASK | COLO-4 Cell-3 Remove inaccessible tray in MER | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Thu Jul 15 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
1386 | TT_TASK | COLO-4 Cell-3 Reinstall tray in MER | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
1387 | TT_TASK | COLO-4 Cell-4 Remove inaccessible tray in MER4 | Wed Aug 04 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
1388 | TT_TASK | COLO-4 Cell-4 Reinstall tray in MER | Fri Sep 03 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Mon Aug 09 07:00:00 IDT 2021 | Thu Aug 12 00:00:00 IDT 2021 |  | COMPLETED
1389 | TT_TASK | COLO-3 Cell-1 Remove inaccessible tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
1390 | TT_TASK | COLO-3 CEll-1 Reinstall tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 |  | COMPLETED
1391 | TT_TASK | COLO-3 Cell-2 Remove inaccessible tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1392 | TT_TASK | COLO-3 Cell-2 Reinstall tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1395 | TT_TASK | COLO-3 Cell-3 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 14 00:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1397 | TT_TASK | COLO-4 Cell-1 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Fri Jul 23 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1398 | TT_TASK | COLO-4 Cell-2 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
1399 | TT_TASK | COLO-4 Cell-3 Conduit rework | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 |  | COMPLETED
1400 | TT_TASK | COLO-4 Cell-4 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1404 | TT_TASK | 6.1-88 COLO-1 MER awaiting updated UPS L3 test script approval | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 31 07:00:00 IDT 2021 |  | COMPLETED
1405 | TT_TASK | 6.1-89 RFI574- COLO-1 Relocating MSB EPMS device to different cabinet | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1406 | TT_TASK | 6.1-92 COLO-1 SF/ RF startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
1407 | TT_TASK | 6.1-93 COLO-1 HVAC minisplits startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1409 | TT_TASK | 6.2-08 COLO-2 Cell- 1,2 MER equipment Phenolic labelling | Wed Jul 14 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
1410 | TT_TASK | 6.2-08 COLO-2 Cell- 3,4 MER equipment Phenolic labelling | Wed Jul 14 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Mon Aug 02 00:00:00 IDT 2021 |  | COMPLETED
1411 | TT_TASK | 6.2-12 COLO-2 All Cells- Factory connection Torque verification | Wed Jul 14 07:00:00 IDT 2021 | Wed Jul 21 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
1413 | TT_TASK | 6.1-95 COLO-1 ATS's L3 startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  | COMPLETED
1415 | TT_TASK | 6.1-96 COLO-1 PDU - EPMS L3 startup delay (vendor schedule availability) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Mon Aug 02 07:00:00 IDT 2021 |  | COMPLETED
1420 | TT_TASK | COLO-2 Cell-1 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1421 | TT_TASK | COLO-2 Cell-2 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1422 | TT_TASK | COLO-2 Cell-3 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1423 | TT_TASK | COLO-2 Cell-4 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 00:00:00 IDT 2021 |  | COMPLETED
1429 | TT_TASK | 6.1-98 Admin/COLO-1 ASCO EPMS Connectivity Issues | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1430 | TT_TASK | 6.1-88 Admin/ COLO-1 MER/ADMIN UPS L3 Testing (includes shutdown to move PQM's & PQM data post proccessing) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 31 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1431 | TT_TASK | 6.1-106 COLO-1 Cell-2 UPS01 Power module failure | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1433 | TT_TASK | COLO-2 Cell-1 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1434 | TT_TASK | COLO-2 Cell-3 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1435 | TT_TASK | COLO-2 Cell-4 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1437 | TT_TASK | COLO-3 Delay in SE uploading QC Checkilst | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Fri Aug 06 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1439 | TT_TASK | COLO-2 Cell-2 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1442 | TT_TASK | Mobilization | Mon Apr 27 07:00:00 IDT 2020 | Wed May 20 17:00:00 IDT 2020 | Mon Apr 06 00:00:00 IDT 2020 | Sat May 02 17:00:00 IDT 2020 |  | COMPLETED
1444 | TT_TASK | Establish Access Roads / Laydown / Craft Parking / Temp Utilities | Thu May 14 07:00:00 IDT 2020 | Fri Jun 19 17:00:00 IDT 2020 | Fri Apr 24 00:00:00 IDT 2020 | Sat May 23 00:00:00 IDT 2020 |  | COMPLETED
1446 | TT_TASK | Site Sanitary | Mon May 11 07:00:00 IDT 2020 | Fri Jul 24 17:00:00 IDT 2020 | Tue May 05 00:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 |  | COMPLETED
1447 | TT_TASK | Remaining Site Sanitary | Mon May 11 07:00:00 IDT 2020 | Fri Jul 24 17:00:00 IDT 2020 | Tue Aug 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
1448 | TT_TASK | IWW System | Tue May 26 07:00:00 IDT 2020 | Sat Aug 08 17:00:00 IDT 2020 | Mon May 18 00:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 |  | COMPLETED
1449 | TT_TASK | Remaining IWW System | Tue May 26 07:00:00 IDT 2020 | Sat Aug 08 17:00:00 IDT 2020 | Tue Aug 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
1450 | TT_TASK | Site Water / Fire Loop | Fri Jul 24 07:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1451 | TT_TASK | Site Storm | Mon Jun 29 07:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
1454 | TT_TASK | Telecom-Communications Site Loop/Ductbank | Mon Jun 29 08:00:00 IDT 2020 | Thu Oct 01 08:00:00 IDT 2020 | Thu Jun 25 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1455 | TT_TASK | Telecom-RNG Fiber Underground installation | Mon Feb 01 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
1456 | TT_TASK | Telecom-RNG Fiber CNR buildout | Mon Oct 05 07:00:00 IDT 2020 | Tue Dec 08 17:00:00 IST 2020 | Mon Oct 05 07:00:00 IDT 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
1461 | TT_TASK | Temp Power/ Telecom duct bank | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Thu Aug 27 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1462 | TT_TASK | Vault- set 1st Vault Along UMS Duct bank run | Thu Sep 03 07:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1463 | TT_TASK | Vault- Set 2nd vault Along UMS Duct Run near COLO-2 | Tue Sep 08 07:00:00 IDT 2020 | Thu Sep 10 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1464 | TT_TASK | Vault- Set vault along URS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1465 | TT_TASK | Vault- Set vault along UMS to JAZ run | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1466 | TT_TASK | Set URS Vault | Mon Nov 16 08:00:00 IST 2020 | Wed Nov 25 08:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1467 | TT_TASK | Set UMS vault | Wed Nov 25 08:00:00 IST 2020 | Tue Dec 08 08:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1469 | TT_TASK | Vault- Set North vault- Along UPM to Vault | Fri Oct 09 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1470 | TT_TASK | Vault - Set North Vault Along Vault to URS run | Fri Oct 23 07:00:00 IDT 2020 | Tue Oct 27 17:00:00 IST 2020 | Thu Aug 20 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1471 | TT_TASK | Vault - Set South Vault Along Vault to URS run | Sat Nov 07 07:00:00 IST 2020 | Tue Nov 10 17:00:00 IST 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1472 | TT_TASK | Vault - Set South Vault along UPM to Vault | Mon Nov 23 07:00:00 IST 2020 | Wed Nov 25 17:00:00 IST 2020 | Thu Aug 20 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1475 | TT_TASK | Duct bank- COLO-1 UPM to north vault | Mon Oct 19 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Fri Oct 02 00:00:00 IDT 2020 | Mon Oct 05 00:00:00 IDT 2020 |  | COMPLETED
1476 | TT_TASK | Duct bank- COLO-2 UPM to north Valut | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Mon Oct 05 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1477 | TT_TASK | Duct Bank- Building to URS - 1st Half | Sat Sep 26 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 07:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
1478 | TT_TASK | Duct Bank- Building to URS(upto horse shoe) - 2nd Half | Wed Sep 30 07:00:00 IDT 2020 | Thu Oct 08 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
1479 | TT_TASK | Duct Bank - JAZ to vault- UMS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Thu Oct 29 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1480 | TT_TASK | Duct Bank - Vault to Vault along UMS duct Run - horseshoe | Mon Oct 26 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
1481 | TT_TASK | Duct Bank - COLO-3 UPM to Vault UMS Run | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1482 | TT_TASK | Duct Bank - URS to vault - URS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1483 | TT_TASK | Duct Bank - Vault To JAZ - URS to JAZ run | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 09 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1484 | TT_TASK | Duct Bank - Vault to UMS- UMS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1485 | TT_TASK | Duct Bank - south vault (along UMS duct run) to UMS | Sat Nov 21 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1486 | TT_TASK | Duct Bank - COLO-4 UPM to UMS | Mon Nov 23 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
1488 | TT_TASK | Duct Bank - COLO1- UPM to UPM | Mon Aug 10 07:00:00 IDT 2020 | Thu Aug 13 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1489 | TT_TASK | Duct Bank - COLO2- UPM to UPM | Mon Aug 31 07:00:00 IDT 2020 | Thu Sep 03 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
1490 | TT_TASK | Duct Bank - North Crossover (URS to west Vault Run) | Mon Sep 14 07:00:00 IDT 2020 | Sat Sep 26 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
1491 | TT_TASK | Duct Bank - South Cross over (URS to west Vault Run) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
1492 | TT_TASK | Duct Bank - COLO-3 UPM to UPM | Fri Nov 06 07:00:00 IST 2020 | Tue Nov 10 17:00:00 IST 2020 | Sat Oct 10 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1493 | TT_TASK | Duct Bank - COLO-4 UPM to UPM | Wed Nov 25 07:00:00 IST 2020 | Wed Dec 02 17:00:00 IST 2020 | Sat Oct 10 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1495 | TT_TASK | Duct Bank Admin UPM to COLO-1 UPM | Thu Sep 24 07:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1496 | TT_TASK | Duct Back- Admin UPM to Vault | Fri Oct 23 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Mon Aug 24 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
1497 | TT_TASK | Duct Bank COLO-2 UPM to Vault | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Mon Sep 28 00:00:00 IDT 2020 | Thu Oct 01 00:00:00 IDT 2020 |  | COMPLETED
1498 | TT_TASK | Duct Bank - Building to North Vault URS run | Fri Oct 23 07:00:00 IDT 2020 | Sat Oct 31 17:00:00 IST 2020 | Fri Oct 02 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1499 | TT_TASK | Duct Bank - Builing to South Vault- URS Run | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 09 17:00:00 IST 2020 | Fri Oct 02 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1500 | TT_TASK | Duct Bank - Vault to COLO-3 UPM | Tue Nov 10 07:00:00 IST 2020 | Fri Nov 13 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1501 | TT_TASK | Duct Bank - Vault to COLO-4 UPM | Mon Nov 16 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1503 | TT_TASK | Set MV Gear (URS) | Mon Nov 23 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1504 | TT_TASK | Set MV Gear (UMS) | Mon Dec 21 07:00:00 IST 2020 | Mon Dec 28 17:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
1506 | TT_TASK | Pull UPM to UPM COLO-1 - CELL-1 to Cell-3 | Tue Jan 05 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1507 | TT_TASK | Pul UPM to UPM COLO-2- CELL-1 to Cell-3 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Sat Jan 02 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
1508 | TT_TASK | Pull UPM to UPM COLO-3 - CELL-1 to Cell-3 | Fri Jan 15 07:00:00 IST 2021 | Mon Jan 18 17:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1509 | TT_TASK | Pull UPM to UPM COLO-4 - CELL-1 to Cell-3 | Wed Feb 03 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
1511 | TT_TASK | Pull UPM to UPM Admin to COLO-1 Cell -2 | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1512 | TT_TASK | Pull UPM to UPM COLO-1 Cell 2- Cell - 4 | Thu Jan 07 07:00:00 IST 2021 | Fri Jan 08 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1513 | TT_TASK | Pull UPM to UPM COLO-2 Cell 2- Cell - 4 | Wed Feb 03 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1514 | TT_TASK | Pull UPM to UPM COLO-3 Cell 2- Cell - 4 | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1515 | TT_TASK | Pull UPM to UPM COLO-4 Cell 2- Cell - 4 | Thu Feb 11 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1517 | TT_TASK | Pull Cross Overs- COLO-1 CELL-3 to CELL-4 | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1518 | TT_TASK | Pull Cross Overs- COLO-2 CELL-3 to CELL-4 | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1519 | TT_TASK | Pull Cross Overs- COLO-3 CELL-3 to CELL-4 | Tue Feb 09 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1520 | TT_TASK | Pull Cross Overs- COLO-4 CELL-3 to CELL-4 | Sat Feb 13 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1522 | TT_TASK | PULL- URS to Admin | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Sat Dec 05 00:00:00 IST 2020 |  | COMPLETED
1523 | TT_TASK | PULL- URS to COLO-2 | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
1524 | TT_TASK | PULL- URS to COLO-3 | Tue Jan 12 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1525 | TT_TASK | PULL- URS to COLO-4 | Mon Jan 18 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1527 | TT_TASK | Pull- UMS to COLO-1,2,3 | Tue Jan 12 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Jan 11 17:00:00 IST 2021 |  | COMPLETED
1528 | TT_TASK | Pull- UMS to COLO-4 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 |  | COMPLETED
1530 | TT_TASK | Pull - JAZ to URS | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
1531 | TT_TASK | Pull - JAZ to UMS | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1534 | TT_TASK | Term COLO -1 Cell-3 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1535 | TT_TASK | Term COLO -2 Cell-3 UPM | Thu Mar 04 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1536 | TT_TASK | Term COLO -3 Cell-3 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 |  | COMPLETED
1537 | TT_TASK | Term COLO -4 Cell-3 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1538 | TT_TASK | Term COLO -1 Cell-1 UPM | Wed Feb 10 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1539 | TT_TASK | Term COLO -2 Cell-1 UPM | Sat Feb 13 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1540 | TT_TASK | Term COLO -3 Cell-1 UPM | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1541 | TT_TASK | Term COLO -4 Cell-1 UPM | Thu Mar 11 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1543 | TT_TASK | Term COLO -1 Cell-4 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
1544 | TT_TASK | Term COLO -2 Cell-4 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1545 | TT_TASK | Term COLO -3 Cell-4 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1546 | TT_TASK | Term COLO -4 Cell-4 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1547 | TT_TASK | Term Admin - UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1548 | TT_TASK | Term COLO -1 Cell-2 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
1549 | TT_TASK | Term COLO -2 Cell-2 UPM | Fri Feb 05 07:00:00 IST 2021 | Tue Feb 09 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1550 | TT_TASK | Term COLO -3 Cell-2 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1551 | TT_TASK | Term COLO -4 Cell-2 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1553 | TT_TASK | Battery Station Yellow tagging / EPMS Checkouts | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1554 | TT_TASK | GCPUD NORTH Mobile substation maintance & Mobile Sub re-energization 4/1 Â– 4/3 | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1555 | TT_TASK | GCPUD SOUTH Mobile substation maintance & Mobile Sub re-energization 4/1 Â– 4/3 | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1556 | TT_TASK | Term- UMS- Line Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1557 | TT_TASK | Term- JAZ to Structure- (Incl Stress Cones) from ums | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1558 | TT_TASK | Term- UMS- Load side | Wed Feb 10 07:00:00 IST 2021 | Tue Feb 23 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1559 | TT_TASK | Yellow Tagging for UMS (includes GC, vendor Lvl-2) | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
1560 | TT_TASK | UMS Control Power Available CYT | Wed Feb 10 07:00:00 IST 2021 | Wed Feb 17 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
1562 | TT_TASK | Term URS- Line Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
1563 | TT_TASK | Term- JAS to URS- (Incl Stress Cones) | Wed Feb 03 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1564 | TT_TASK | TERM- URS- Load Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1565 | TT_TASK | Yellow Tagging for URS | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
1566 | TT_TASK | URS Control Power Available CYT | Wed Feb 10 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
1568 | TT_TASK | Aggregate Road Base | Mon Oct 19 07:00:00 IDT 2020 | Tue Nov 24 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
1569 | TT_TASK | Plant shutdown for winter | Mon Nov 30 07:00:00 IST 2020 | Tue Apr 06 17:00:00 IDT 2021 | Mon Nov 23 00:00:00 IST 2020 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
1570 | TT_TASK | Curb & Gutter | Mon Nov 30 07:00:00 IST 2020 | Sat Jan 09 17:00:00 IST 2021 | Mon Nov 02 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1571 | TT_TASK | Pave HMA | Mon Apr 05 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Sat Nov 07 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1572 | TT_TASK | Site Lighting | Mon May 03 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 |  | 120.0 | IN_PROGRESS
1575 | TT_TASK | Landscape and Site Specialties | Mon May 17 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1581 | TT_TASK | Perimeter Foundations - Excavate/FRP | Mon Apr 27 07:00:00 IDT 2020 | Thu May 14 17:00:00 IDT 2020 | Wed Apr 22 00:00:00 IDT 2020 | Wed May 20 00:00:00 IDT 2020 |  | COMPLETED
1582 | TT_TASK | Perimeter Foundations - Waterproof/Backfill | Mon Jun 01 07:00:00 IDT 2020 | Thu Jun 04 17:00:00 IDT 2020 | Wed May 27 00:00:00 IDT 2020 | Fri Jun 05 00:00:00 IDT 2020 |  | COMPLETED
1583 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Fri Jun 05 07:00:00 IDT 2020 | Tue Jun 16 17:00:00 IDT 2020 | Tue Jun 02 00:00:00 IDT 2020 | Fri Jun 12 00:00:00 IDT 2020 |  | COMPLETED
1585 | TT_TASK | Erect PEMB Steel | Mon Jun 29 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 |  | COMPLETED
1586 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Thu Jul 02 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
1588 | TT_TASK | MEP Undeground Rough-In (Interior) | Tue Aug 18 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1589 | TT_TASK | Aggregate Base Course | Mon Aug 31 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 |  | COMPLETED
1590 | TT_TASK | Slab on Grade | Mon Sep 14 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1592 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Aug 18 07:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 |  | COMPLETED
1593 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Tue Jul 14 00:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 |  | COMPLETED
1594 | TT_TASK | Downspouts & Gutters | Tue Aug 18 07:00:00 IDT 2020 | Sat Aug 29 17:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
1604 | TT_TASK | Perimeter Foundations - Excavate/FRP | Fri May 15 07:00:00 IDT 2020 | Wed Jun 03 17:00:00 IDT 2020 | Mon May 04 00:00:00 IDT 2020 | Fri May 15 00:00:00 IDT 2020 |  | COMPLETED
1605 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Sat Jun 13 07:00:00 IDT 2020 | Thu Jun 25 17:00:00 IDT 2020 | Tue Jun 02 00:00:00 IDT 2020 | Fri Jun 12 00:00:00 IDT 2020 |  | COMPLETED
1606 | TT_TASK | Perimeter Foundations - Waterproof Backfill | Tue May 26 07:00:00 IDT 2020 | Sat Jun 06 17:00:00 IDT 2020 | Tue May 26 07:00:00 IDT 2020 | Wed Jun 17 00:00:00 IDT 2020 |  | COMPLETED
1608 | TT_TASK | Erect PEMB Steel | Mon Jun 29 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Fri Jun 26 00:00:00 IDT 2020 | Mon Jul 06 00:00:00 IDT 2020 |  | COMPLETED
1609 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 |  | COMPLETED
1610 | TT_TASK | Erect Interior Structural Steel | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
1612 | TT_TASK | MEP Undeground Rough-In (Interior) | Fri Aug 14 07:00:00 IDT 2020 | Tue Sep 01 17:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1613 | TT_TASK | Aggregate Base Course | Sat Sep 05 07:00:00 IDT 2020 | Fri Sep 11 17:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 |  | COMPLETED
1614 | TT_TASK | Slab on Grade | Mon Sep 14 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1618 | TT_TASK | Exterior Insulated Metal Panels Installation - East Elevation | Tue Aug 18 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Mon Jul 13 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1621 | TT_TASK | Exterior Insulated Metal Panels Installation - West Elevation | Tue Aug 18 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Mon Jul 13 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1623 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 |  | COMPLETED
1624 | TT_TASK | Downspouts & Gutters | Tue Aug 18 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Wed Aug 12 00:00:00 IDT 2020 |  | COMPLETED
1629 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jun 22 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Mon May 11 00:00:00 IDT 2020 | Tue Jun 16 00:00:00 IDT 2020 |  | COMPLETED
1630 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Wed Jul 08 07:00:00 IDT 2020 | Mon Jul 20 17:00:00 IDT 2020 | Tue Jun 09 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
1632 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Tue Jul 07 00:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 |  | COMPLETED
1633 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 | Tue Aug 04 00:00:00 IDT 2020 |  | COMPLETED
1634 | TT_TASK | Erect Interior Structural Steel | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1636 | TT_TASK | MEP Undeground Rough-In (Interior) | Mon Aug 31 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 |  | COMPLETED
1637 | TT_TASK | Aggregate Base Course | Mon Oct 19 07:00:00 IDT 2020 | Mon Oct 26 17:00:00 IST 2020 | Thu Oct 01 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1638 | TT_TASK | Slab on Grade | Mon Oct 19 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1640 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Aug 18 07:00:00 IDT 2020 | Tue Sep 01 17:00:00 IDT 2020 | Fri Jul 31 00:00:00 IDT 2020 | Thu Aug 13 00:00:00 IDT 2020 |  | COMPLETED
1641 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Wed Aug 26 17:00:00 IDT 2020 | Fri Jul 31 00:00:00 IDT 2020 | Fri Aug 14 00:00:00 IDT 2020 |  | COMPLETED
1642 | TT_TASK | Downspouts & Gutters | Sat Sep 05 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 |  | COMPLETED
1647 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Wed Jul 08 07:00:00 IDT 2020 | Mon Jul 20 17:00:00 IDT 2020 | Wed Jun 24 00:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 |  | COMPLETED
1648 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jun 22 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Tue Jun 16 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1650 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 |  | COMPLETED
1651 | TT_TASK | Secondary Steel | Mon Aug 31 07:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 |  | COMPLETED
1652 | TT_TASK | Erect Interior Structural Steel | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1654 | TT_TASK | MEP Undeground Rough-In (Interior) | Mon Oct 19 07:00:00 IDT 2020 | Thu Nov 05 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1655 | TT_TASK | Aggregate Base Course | Fri Nov 06 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1656 | TT_TASK | Slab on Grade | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
1658 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Sep 08 07:00:00 IDT 2020 | Tue Sep 22 17:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1659 | TT_TASK | Roof Panels Installation | Tue Sep 08 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 | Tue Sep 01 00:00:00 IDT 2020 |  | COMPLETED
1660 | TT_TASK | Downspouts & Gutters | Wed Sep 16 07:00:00 IDT 2020 | Tue Sep 22 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
1670 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jul 06 07:00:00 IDT 2020 | Thu Jul 23 17:00:00 IDT 2020 | Tue Jun 23 00:00:00 IDT 2020 | Thu Jul 30 00:00:00 IDT 2020 |  | COMPLETED
1671 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Sat Aug 29 07:00:00 IDT 2020 | Thu Sep 10 17:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 |  | COMPLETED
1673 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Sat Aug 08 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
1674 | TT_TASK | Secondary Steel | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 08 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1675 | TT_TASK | Erect Interior Structural Steel | Mon Dec 21 07:00:00 IST 2020 | Tue Dec 29 17:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
1677 | TT_TASK | MEP Undeground Rough-In (Interior) | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1678 | TT_TASK | Aggregate Base Course | Wed Nov 11 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
1679 | TT_TASK | Slab on Grade | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1681 | TT_TASK | Exterior Insulated Metal Panels Installation | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Sep 30 00:00:00 IDT 2020 |  | COMPLETED
1682 | TT_TASK | Roof Panels Installation | Thu Sep 03 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Thu Aug 27 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1683 | TT_TASK | Downspouts & Gutters | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Sep 07 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1693 | TT_TASK | Hang Wall Partitions | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1694 | TT_TASK | Hang Wall Partitions- Early Walls | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1695 | TT_TASK | MEP Rough-In / Wall & Ceiling | Mon Oct 19 07:00:00 IDT 2020 | Mon Nov 02 17:00:00 IST 2020 | Thu Oct 01 00:00:00 IDT 2020 | Tue Nov 17 00:00:00 IST 2020 |  | COMPLETED
1697 | TT_TASK | Early Room - Finishes | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1699 | TT_TASK | Loading Dock Equipment & Dock Doors | Wed May 05 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
1700 | TT_TASK | MEP Overhead | Mon Oct 19 07:00:00 IDT 2020 | Tue Nov 17 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1701 | TT_TASK | Ceilings / Ligthing / FA Devices | Mon Mar 01 07:00:00 IST 2021 | Tue Apr 13 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
1702 | TT_TASK | Concrete Floor Sealing/Epoxy | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1706 | TT_TASK | Generator Term | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
1707 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 | Fri Sep 25 00:00:00 IDT 2020 |  | COMPLETED
1708 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Fri Sep 18 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
1709 | TT_TASK | Set Exterior Electrical OFCI Equipment | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1710 | TT_TASK | Admin -Electrical Underground Rough-In | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 31 17:00:00 IDT 2020 | Fri Aug 07 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
1711 | TT_TASK | Generator & Utility Power Pull-Test | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1712 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Jan 18 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1713 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1715 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Oct 19 07:00:00 IDT 2020 | Mon Nov 02 17:00:00 IST 2020 | Fri Oct 09 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1716 | TT_TASK | Set Exterior Mechanical CFCI Equipment (remaning mini splits) | Fri Nov 06 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1717 | TT_TASK | Mechanical Underground Rough-In | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 31 17:00:00 IDT 2020 | Sat Aug 08 00:00:00 IDT 2020 | Tue Aug 25 00:00:00 IDT 2020 |  | COMPLETED
1718 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1721 | TT_TASK | Fire Alarm Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1722 | TT_TASK | Controls Installation | Tue Feb 16 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
1724 | TT_TASK | Set Electrical Equipment incl. OH raceways | Mon Nov 23 07:00:00 IST 2020 | Wed Jan 13 17:00:00 IST 2021 | Mon Nov 16 00:00:00 IST 2020 | Tue Dec 29 00:00:00 IST 2020 |  | COMPLETED
1725 | TT_TASK | Electrical Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1727 | TT_TASK | Domestic Water Piping | Mon Nov 23 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1728 | TT_TASK | Plumbing Devices & Trim | Mon Jul 26 15:00:00 IDT 2021 | Tue Aug 17 15:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
1730 | TT_TASK | Security Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
1732 | TT_TASK | Mechanical Ductwork Installation | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1733 | TT_TASK | Set Mechanical Equipment | Mon Nov 23 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
1734 | TT_TASK | Mechanical Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1739 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1740 | TT_TASK | Overhead MEPFP Rough-In | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 11 17:00:00 IST 2020 | Wed Oct 14 00:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
1741 | TT_TASK | Early Topout | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1743 | TT_TASK | Sprinkler Test | Mon Dec 21 07:00:00 IST 2020 | Tue Dec 22 17:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1744 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1747 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1748 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1749 | TT_TASK | Early Topout | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Tue Nov 10 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1751 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Nov 30 07:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1754 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 |  | COMPLETED
1755 | TT_TASK | Overhead MEPFP Rough-In | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 11 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 |  | COMPLETED
1756 | TT_TASK | Early Topout | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1758 | TT_TASK | Datahall Finishes- Ceiling Grid | Thu Dec 03 07:00:00 IST 2020 | Tue Dec 15 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1761 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1762 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1763 | TT_TASK | Early Topout | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Tue Nov 10 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1765 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1768 | TT_TASK | Remaining MER raceway across Mech chase | Tue Dec 01 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1769 | TT_TASK | Electrical OH Below Mechanical Piping | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1770 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1771 | TT_TASK | OverHead MEPFP Rough-In ( Add TCM Cross over piping HRA Level-3) | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1772 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1774 | TT_TASK | Mechanical Corridor Finishes | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1777 | TT_TASK | Remaining MER raceway across Mech chase | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1778 | TT_TASK | Electrical OH Below Mechanical Piping | Wed Jan 20 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1779 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 11 00:00:00 IST 2020 |  | COMPLETED
1780 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1781 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1783 | TT_TASK | Mechanical Corridor Finishes | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1786 | TT_TASK | Remaining MER raceway across Mech chase | Tue Dec 01 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1787 | TT_TASK | Electrical OH Below Mechanical Piping | Mon Jan 04 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1788 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1789 | TT_TASK | OverHead MEPFP Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1790 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1792 | TT_TASK | Mechanical Corridor Finishes | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1795 | TT_TASK | Remaining MER raceway across Mech chase | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1796 | TT_TASK | Electrical OH Below Mechanical Piping | Wed Jan 20 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1797 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 11 00:00:00 IST 2020 |  | COMPLETED
1798 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1799 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1801 | TT_TASK | Mechanical Corridor Finishes | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Tue Nov 17 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1805 | TT_TASK | Generator & Utility Power Term | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1806 | TT_TASK | Remaining Mechanical Equipment (ADP01) Termimations | Thu Mar 18 07:00:00 IST 2021 | Tue Mar 23 17:00:00 IST 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1807 | TT_TASK | Electrical Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 14 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1808 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1809 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1810 | TT_TASK | Exterior Equipment Pads - Electrical | Thu Sep 03 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1811 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Oct 12 07:00:00 IDT 2020 | Mon Oct 26 17:00:00 IST 2020 | Mon Oct 12 07:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1812 | TT_TASK | Lift & Set MER in Place | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Wed Dec 16 00:00:00 IST 2020 | Wed Dec 16 17:00:00 IST 2020 |  | COMPLETED
1813 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
1814 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 13 17:00:00 IST 2021 | Thu Dec 17 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1815 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Jan 11 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Tue Jan 05 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1816 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1817 | TT_TASK | Generator & Utility Power Pull | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1819 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1820 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1821 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1822 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1823 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Sat Dec 05 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1824 | TT_TASK | Mechanical Equipment Piping Connections | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1825 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
1828 | TT_TASK | Fire Alarm Installation | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1829 | TT_TASK | Controls Installation | Fri Mar 05 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1832 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 22 07:00:00 IST 2021 | Tue Mar 30 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1833 | TT_TASK | Electrical Underground Rough-In | Thu Sep 03 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1834 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1835 | TT_TASK | Set Electrical Equipment-UPM Cell -3 | Fri Dec 11 07:00:00 IST 2020 | Tue Dec 15 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1836 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
1837 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1838 | TT_TASK | Lift & Set MER in Place | Mon Jan 11 08:00:00 IST 2021 | Mon Jan 18 08:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1839 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 18 08:00:00 IST 2021 | Fri Jan 22 08:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1840 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
1841 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1842 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
1843 | TT_TASK | Generator & Utility Power Pull | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1845 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1846 | TT_TASK | Exterior Equipment Pads - Mechanical | Fri Oct 16 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Sat Sep 19 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
1847 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1848 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1849 | TT_TASK | Set Exterior Water Treatment equipment | Mon Dec 07 07:00:00 IST 2020 | Tue Dec 08 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1850 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1851 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 15 07:00:00 IST 2021 | Mon Mar 22 17:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
1854 | TT_TASK | Fire Alarm Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1855 | TT_TASK | Controls Installation | Tue Mar 09 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1858 | TT_TASK | Generator & Utility Power Pull | Tue Feb 02 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Feb 26 07:00:00 IST 2021 |  | COMPLETED
1859 | TT_TASK | Remaining Mechanical Equipment (ADP01) Termimations | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1860 | TT_TASK | Electrical Underground Rough-In | Fri Aug 14 07:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1861 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 05 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1862 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1863 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Sep 05 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Fri Oct 02 00:00:00 IDT 2020 |  | COMPLETED
1864 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Oct 26 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1865 | TT_TASK | Lift & Set MER in Place | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
1866 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 11 08:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1867 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1868 | TT_TASK | GEN & UPM to MER Cable Bus Install | Wed Jan 20 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1869 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1870 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1872 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1873 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Oct 05 07:00:00 IDT 2020 | Sat Oct 17 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
1874 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1875 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1876 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1877 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1878 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 08 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1881 | TT_TASK | Fire Alarm Installation | Thu Feb 18 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1882 | TT_TASK | Controls Installation | Sat Mar 06 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
1885 | TT_TASK | Generator & Utility Power Pull | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1886 | TT_TASK | Electrical Underground Rough-In | Sat Sep 05 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1887 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1888 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1889 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1890 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1891 | TT_TASK | Lift & Set MER in Place | Mon Jan 11 08:00:00 IST 2021 | Mon Jan 18 08:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1892 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 11 08:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Jan 11 08:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1893 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1894 | TT_TASK | GEN & UPM to MER Cable Bus Install | Thu Feb 04 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1895 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Wed Apr 07 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
1896 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 15 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
1898 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Sep 14 07:00:00 IDT 2020 | Sat Sep 26 17:00:00 IDT 2020 | Mon Sep 14 07:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1899 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1900 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1901 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1902 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1903 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1904 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
1907 | TT_TASK | Fire Alarm Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1908 | TT_TASK | Controls Installation | Thu Apr 15 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1911 | TT_TASK | VFD'S Installation & wirepull | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1912 | TT_TASK | Ligthing Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 |  | COMPLETED
1914 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Thu Nov 26 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
1915 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1917 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1919 | TT_TASK | Fire Riser Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1920 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1921 | TT_TASK | Controls Installation | Fri Mar 26 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1924 | TT_TASK | VFD'S Installation & Wiring | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
1925 | TT_TASK | Ligthing Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1927 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
1928 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1930 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1932 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1933 | TT_TASK | Controls Installation | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1936 | TT_TASK | VFD'S Installation & Wiring | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1937 | TT_TASK | Ligthing Installation | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1939 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
1940 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1942 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1944 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1945 | TT_TASK | Controls Installation | Tue Apr 13 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1948 | TT_TASK | VFD'S Installation & Wiring | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
1949 | TT_TASK | Ligthing Installation | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jul 29 00:00:00 IDT 2021 |  | COMPLETED
1951 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
1952 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1954 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1956 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1957 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1961 | TT_TASK | HAC Installation | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
1962 | TT_TASK | Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1963 | TT_TASK | Power Bus Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1964 | TT_TASK | PDU's Installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1965 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Apr 05 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1966 | TT_TASK | Light Fixtures Installation | Wed May 05 07:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
1967 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
1969 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
1970 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1971 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1972 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1974 | TT_TASK | Security Devices & Trim | Mon May 17 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
1975 | TT_TASK | Controls Installation | Fri Mar 26 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1976 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1979 | TT_TASK | HAC Installation | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1980 | TT_TASK | Cable Tray Installation | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
1981 | TT_TASK | Power Bus Installation | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1982 | TT_TASK | PDU's Installation | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
1983 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Apr 26 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1984 | TT_TASK | Light Fixtures Installation | Wed May 12 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1985 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Apr 26 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
1987 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
1988 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1989 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1990 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Thu Jul 01 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1992 | TT_TASK | Security Devices & Trim | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
1993 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1994 | TT_TASK | Fire Alarm System | Tue May 04 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1997 | TT_TASK | HAC Installation | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1998 | TT_TASK | Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1999 | TT_TASK | Power Bus Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
2000 | TT_TASK | PDU's Installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
2001 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Apr 01 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2002 | TT_TASK | Light Fixtures Installation | Tue May 11 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
2003 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 23 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
2005 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2006 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2007 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2008 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed May 19 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2010 | TT_TASK | Security Devices & Trim | Mon May 17 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2011 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2012 | TT_TASK | Fire Alarm System | Thu May 06 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2015 | TT_TASK | HAC Installation | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2016 | TT_TASK | Cable Tray Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2017 | TT_TASK | Power Bus Installation | Fri Mar 12 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2018 | TT_TASK | PDU's Installation | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2019 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon May 03 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
2020 | TT_TASK | Light Fixtures Installation | Fri May 21 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2021 | TT_TASK | Pull/term/Test PDU to Power bus | Mon May 03 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2023 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2024 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2025 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2026 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed May 19 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2028 | TT_TASK | Security Devices & Trim | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 |  | COMPLETED
2029 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2030 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2036 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2037 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
2038 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2040 | TT_TASK | Datahall Finishes - Ceiling Grid | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2043 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2044 | TT_TASK | Overhead MEPFP Rough-In | Fri Nov 06 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2045 | TT_TASK | Hang drywall / Mud / Tape | Wed Jan 06 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2047 | TT_TASK | Datahall Finishes - Ceiling Grid | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2050 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2051 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
2052 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2054 | TT_TASK | Datahall Finishes - Ceiling Grid | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2057 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2058 | TT_TASK | Overhead MEPFP Rough-In | Fri Nov 06 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2059 | TT_TASK | Hang drywall / Mud / Tape | Wed Jan 06 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2061 | TT_TASK | Datahall Finishes - Ceiling Grid | Mon Jan 11 07:00:00 IST 2021 | Wed Jan 20 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2064 | TT_TASK | Remaining Post MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2065 | TT_TASK | Frame & Top out | Mon Nov 23 07:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2066 | TT_TASK | OverHead MEPFP Rough-In | Thu Nov 19 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2067 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Dec 12 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2069 | TT_TASK | Mechanical Corridor Finishes | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2072 | TT_TASK | Remaining MER raceway across Mech chase | Thu Mar 25 07:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2073 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2074 | TT_TASK | OverHead MEPFP Rough-In | Tue Dec 08 07:00:00 IST 2020 | Mon Dec 21 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2075 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Dec 14 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2077 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2080 | TT_TASK | Remaining MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 |  | COMPLETED
2081 | TT_TASK | Frame & Top out | Mon Nov 30 07:00:00 IST 2020 | Wed Dec 09 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2082 | TT_TASK | OverHead MEPFP Rough-In | Sat Dec 19 07:00:00 IST 2020 | Thu Jan 07 17:00:00 IST 2021 | Mon Oct 26 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2083 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Dec 12 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2085 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2088 | TT_TASK | Remaining MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Mar 12 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2089 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2090 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2091 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 30 07:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
2093 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2097 | TT_TASK | Generator & Utility Power Pull | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
2098 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
2099 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2100 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
2101 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Dec 14 07:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 |  | COMPLETED
2102 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Tue Dec 29 00:00:00 IST 2020 |  | COMPLETED
2103 | TT_TASK | Lift & Set MER in Place | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2104 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 |  | COMPLETED
2105 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
2106 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Mar 22 07:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Fri Mar 05 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
2107 | TT_TASK | Generator & Utility Power Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2108 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2110 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
2111 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 08 17:00:00 IST 2021 | Mon Nov 02 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
2112 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2113 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2114 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2115 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2116 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2119 | TT_TASK | Fire Alarm Installation | Tue May 11 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2120 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2123 | TT_TASK | Generator & Utility Power Pull | Tue May 11 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
2124 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 21 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2125 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2126 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Wed Dec 16 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2127 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Dec 14 07:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2128 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2129 | TT_TASK | Lift & Set MER in Place | Tue Mar 23 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
2130 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Mar 29 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2131 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Mar 29 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2132 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Fri Apr 16 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
2133 | TT_TASK | Generator & Utility Power Test-Term | Thu May 06 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2134 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
2136 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2137 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 08 17:00:00 IST 2021 | Mon Nov 16 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2138 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2139 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2140 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2141 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2142 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
2145 | TT_TASK | Fire Alarm Installation | Wed May 26 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2146 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2149 | TT_TASK | Generator & Utility Power Pull | Fri Mar 26 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
2150 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2151 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
2152 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Wed Nov 04 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2153 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Tue Nov 03 00:00:00 IST 2020 |  | COMPLETED
2154 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
2155 | TT_TASK | Lift & Set MER in Place | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2156 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Mar 27 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2157 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Mar 27 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2158 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Thu Mar 25 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
2159 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2160 | TT_TASK | Generator & Utility Power Test-Term | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Tue Apr 06 07:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2162 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2163 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2164 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2165 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2166 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Fri Jan 15 07:00:00 IST 2021 | Fri Jan 29 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2167 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
2168 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
2171 | TT_TASK | Fire Alarm Installation | Tue May 11 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2172 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2175 | TT_TASK | Generator & Utility Power Pull | Thu May 13 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2176 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2177 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2178 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2179 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2180 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
2181 | TT_TASK | Lift & Set MER in Place | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
2182 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Mar 27 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2183 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Mar 27 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
2184 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Thu Apr 15 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
2185 | TT_TASK | Generator & Utility Power Test-Term | Tue May 18 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2186 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2188 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2189 | TT_TASK | Set Gen Stack / Exhaust duct | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2192 | TT_TASK | Fire Alarm Installation | Wed May 12 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2193 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2196 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 |  | COMPLETED
2197 | TT_TASK | Ligthing Installation | Fri Jul 23 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2199 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2200 | TT_TASK | Hydronic Piping Installation | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2202 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2203 | TT_TASK | Toilet Piping Installation / DW | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2205 | TT_TASK | Fire Riser Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2206 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2207 | TT_TASK | Controls Installation | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue Jun 08 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2210 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2211 | TT_TASK | Ligthing Installation | Sat Aug 07 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2213 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
2214 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2216 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2217 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2219 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2220 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
2223 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2224 | TT_TASK | Ligthing Installation | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2226 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
2227 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2229 | TT_TASK | Toilet Piping Installation / DW | Mon May 03 07:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2230 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2232 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2233 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri Jul 09 08:12:00 IDT 2021 |  | COMPLETED
2236 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2237 | TT_TASK | Ligthing Installation | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2239 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
2240 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2242 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2243 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2245 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2246 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2249 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2250 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2251 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
2252 | TT_TASK | Power Bus Installation | Fri Mar 26 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2253 | TT_TASK | PDU's Installation | Fri Mar 26 07:00:00 IDT 2021 | Mon Mar 29 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
2254 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2255 | TT_TASK | Light Fixtures Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2256 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 23 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
2258 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Jun 10 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2259 | TT_TASK | BMS Pull Wire / Term / Test | Thu Jun 10 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2260 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Jul 23 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2262 | TT_TASK | Fire Alarm System | Tue May 04 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2263 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2266 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2267 | TT_TASK | HAC Installation | Wed Feb 03 07:00:00 IST 2021 | Wed Feb 17 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Wed Feb 03 00:00:00 IST 2021 |  | COMPLETED
2268 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
2269 | TT_TASK | Power Bus Installation | Mon Mar 22 07:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2270 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2271 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Tue Jun 08 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2272 | TT_TASK | Light Fixtures Installation | Wed Jun 23 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
2273 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2275 | TT_TASK | EPMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 |  | COMPLETED
2276 | TT_TASK | BMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 |  | COMPLETED
2277 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon Aug 09 07:00:00 IDT 2021 | Wed Sep 01 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2279 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2280 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2283 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2284 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2285 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
2286 | TT_TASK | Power Bus Installation | Fri Mar 26 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2287 | TT_TASK | PDU's Installation | Mon Mar 22 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2288 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2289 | TT_TASK | Light Fixtures Installation | Fri Jun 18 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Jun 18 07:00:00 IDT 2021 | Thu Jul 01 00:00:00 IDT 2021 |  | COMPLETED
2290 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 02 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
2292 | TT_TASK | EPMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2293 | TT_TASK | BMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2294 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Jul 30 07:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2296 | TT_TASK | Fire Alarm System | Mon May 10 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon May 10 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 |  | COMPLETED
2297 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2300 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Thu Apr 22 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2301 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
2302 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2303 | TT_TASK | Power Bus Installation | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2304 | TT_TASK | PDU's Installation | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2305 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Jun 09 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2306 | TT_TASK | Light Fixtures Installation | Wed Jun 23 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2307 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2309 | TT_TASK | EPMS Pull Wire / Term / Test | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2310 | TT_TASK | BMS Pull Wire / Term / Test | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2311 | TT_TASK | ` | Tue Aug 24 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2313 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2314 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2319 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2320 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
2321 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2323 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2326 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
2327 | TT_TASK | Overhead MEPFP Rough-In | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 |  | COMPLETED
2328 | TT_TASK | Hang drywall / Mud / Tape | Thu Jan 14 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2330 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2333 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2334 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2335 | TT_TASK | Hang drywall / Mud / Tape | Fri Jan 08 07:00:00 IST 2021 | Mon Jan 18 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2337 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2340 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
2341 | TT_TASK | Overhead MEPFP Rough-In | Fri Jan 15 07:00:00 IST 2021 | Wed Jan 27 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2342 | TT_TASK | Hang drywall / Mud / Tape | Thu Jan 14 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2344 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2347 | TT_TASK | Remaining MER raceway across Mech chase | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2348 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
2349 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2350 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Thu Jan 21 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Thu Jan 21 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 |  | COMPLETED
2352 | TT_TASK | Mechanical Corridor Finishes | Fri Mar 05 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2355 | TT_TASK | Remaining MER raceway across Mech chase | Thu Jun 17 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2356 | TT_TASK | Frame & Top out | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2357 | TT_TASK | OverHead MEPFP Rough-In | Wed Jan 13 07:00:00 IST 2021 | Wed Jan 27 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2358 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
2360 | TT_TASK | Mechanical Corridor Finishes | Wed Feb 03 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2363 | TT_TASK | Remaining MER raceway across Mech chase | Mon May 03 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2364 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
2365 | TT_TASK | OverHead MEPFP Rough-In | Tue Jan 12 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2366 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2368 | TT_TASK | Mechanical Corridor Finishes | Tue Feb 02 07:00:00 IST 2021 | Tue Feb 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2371 | TT_TASK | Remaining MER raceway across Mech chase | Thu Jun 17 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
2372 | TT_TASK | Frame & Top out | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2373 | TT_TASK | OverHead MEPFP Rough-In | Fri Jan 08 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2374 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2376 | TT_TASK | Mechanical Corridor Finishes | Tue Feb 23 07:00:00 IST 2021 | Tue Mar 16 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2380 | TT_TASK | Generator & Utility Power Pull | Wed May 19 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2381 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
2382 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2383 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 29 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
2384 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 07:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
2385 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2386 | TT_TASK | Lift & Set MER in Place | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
2387 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
2388 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon May 03 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2389 | TT_TASK | GEN & UPM to MER Cable Bus Install | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2390 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2391 | TT_TASK | Generator & Utility Power Test-Term | Wed Jun 02 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
2393 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
2394 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2395 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
2396 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2397 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2398 | TT_TASK | Set Exterior Water Treatment equipment | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 01 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2399 | TT_TASK | Mechanical Equipment Piping Connections | Fri Apr 30 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2402 | TT_TASK | Fire Alarm Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2403 | TT_TASK | Controls Installation | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2406 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2407 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
2408 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2409 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2410 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 02 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2411 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 15 08:00:00 IST 2021 | Mon Mar 22 08:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2412 | TT_TASK | Lift & Set MER in Place | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2413 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2414 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Fri May 07 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2415 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2416 | TT_TASK | Generator & Utility Power Test-Term | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2417 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Jun 08 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Tue Jun 08 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2419 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
2420 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
2423 | TT_TASK | Fire Alarm Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 15 07:00:00 IDT 2021 |  | COMPLETED
2424 | TT_TASK | Controls Installation | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 29 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2427 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2428 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2429 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2430 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 08:00:00 IST 2021 | Tue Jan 12 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2431 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Fri Nov 27 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2432 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
2433 | TT_TASK | Lift & Set MER in Place | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
2434 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2435 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon May 03 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
2436 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Mon May 17 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 |  | COMPLETED
2437 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Thu Jun 10 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2438 | TT_TASK | Generator & Utility Power Test-Term | Thu Jun 03 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
2440 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2441 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2442 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2443 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Apr 26 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2444 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 |  | COMPLETED
2445 | TT_TASK | Set Exterior Water Treatment equipment | Mon Apr 26 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2446 | TT_TASK | Mechanical Equipment Piping Connections | Mon May 03 07:00:00 IDT 2021 | Sat May 08 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2449 | TT_TASK | Fire Alarm Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2450 | TT_TASK | Controls Installation | Fri Jun 25 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2453 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2454 | TT_TASK | Electrical Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2455 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Fri Dec 04 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2456 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2457 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 02 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2458 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
2459 | TT_TASK | Lift & Set MER in Place | Fri May 07 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2460 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2461 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2462 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2463 | TT_TASK | Generator & Utility Power Test-Term | Tue Jul 06 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 | Thu Jul 15 12:00:00 IDT 2021 |  | COMPLETED
2464 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2466 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Fri Dec 04 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2467 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2468 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2469 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2470 | TT_TASK | Set Exterior Water Treatment equipment | Fri Apr 30 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2471 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
2472 | TT_TASK | Mechanical Equipment Piping Connections | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2475 | TT_TASK | Fire Alarm Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jul 07 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2476 | TT_TASK | Controls Installation | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
2479 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2480 | TT_TASK | Ligthing Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2482 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
2483 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2485 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 00:00:00 IDT 2021 |  | COMPLETED
2486 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2488 | TT_TASK | Fire Riser Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2489 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2490 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2493 | TT_TASK | VFD'S Installation & Wiring | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2494 | TT_TASK | Ligthing Installation | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
2496 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
2497 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2499 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2500 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2502 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2503 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2506 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2507 | TT_TASK | Ligthing Installation | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
2509 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
2510 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2512 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2513 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2515 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2516 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
2519 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
2520 | TT_TASK | Ligthing Installation | Mon Aug 30 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2522 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
2523 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2525 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2526 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2528 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2529 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2532 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 |  | COMPLETED
2533 | TT_TASK | HAC Installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2534 | TT_TASK | Cable Tray Installation | Sat Apr 03 07:00:00 IDT 2021 | Sat Apr 17 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
2535 | TT_TASK | Power Bus Installation | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2536 | TT_TASK | PDU's Installation | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2537 | TT_TASK | Pull/term/Test PDU to Power bus | Sat Jun 19 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2538 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2539 | TT_TASK | Light Fixtures Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
2541 | TT_TASK | EPMS Pull Wire / Term / Test | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2542 | TT_TASK | BMS Pull Wire / Term / Test | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2543 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Aug 20 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Jul 07 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2545 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2546 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
2549 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2550 | TT_TASK | HAC Installation | Wed Apr 07 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2551 | TT_TASK | Cable Tray Installation | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2552 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
2553 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
2554 | TT_TASK | Pull/term/Test PDU to Power bus | Fri Jul 02 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
2555 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Aug 16 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Thu Jul 08 00:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2556 | TT_TASK | Light Fixtures Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2558 | TT_TASK | EPMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2559 | TT_TASK | BMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2560 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2562 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2563 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2566 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 |  | COMPLETED
2567 | TT_TASK | HAC Installation | Sat Apr 03 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2568 | TT_TASK | Cable Tray Installation | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2569 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 |  | COMPLETED
2570 | TT_TASK | PDU's Installation | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2571 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Sat Jul 24 00:00:00 IDT 2021 |  | COMPLETED
2572 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 23 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2573 | TT_TASK | Light Fixtures Installation | Wed Jul 21 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2575 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2576 | TT_TASK | BMS Pull Wire / Term / Test | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2577 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Aug 20 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2579 | TT_TASK | Fire Alarm System | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2580 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2583 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2584 | TT_TASK | HAC Installation | Mon Apr 12 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2585 | TT_TASK | Cable Tray Installation | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2586 | TT_TASK | Power Bus Installation | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
2587 | TT_TASK | PDU's Installation | Mon Jun 14 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
2588 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
2589 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2590 | TT_TASK | Light Fixtures Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2592 | TT_TASK | EPMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2593 | TT_TASK | BMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2594 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed Sep 15 07:00:00 IDT 2021 | Fri Oct 08 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2596 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2597 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2602 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2603 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2604 | TT_TASK | Early Topout | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2606 | TT_TASK | Datahall Finishes | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
2609 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Jan 18 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2610 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2611 | TT_TASK | Early Topout | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
2613 | TT_TASK | Datahall Finishes | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2616 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2617 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2618 | TT_TASK | Early Topout | Tue Feb 09 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2620 | TT_TASK | Datahall Finishes | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
2623 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Jan 18 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2624 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2625 | TT_TASK | Early Topout | Mon Feb 08 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2627 | TT_TASK | Datahall Finishes | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2630 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2631 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2632 | TT_TASK | OverHead MEPFP Rough-In | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
2633 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 15 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
2635 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Sat Jan 09 00:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 |  | COMPLETED
2638 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2639 | TT_TASK | Frame & Top out | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Sat Jan 09 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
2640 | TT_TASK | OverHead MEPFP Rough-In | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2641 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Tue Mar 30 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2643 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 29 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Thu Jan 21 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
2646 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 |  | COMPLETED
2647 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
2648 | TT_TASK | OverHead MEPFP Rough-In | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Feb 05 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2649 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 15 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2651 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
2654 | TT_TASK | Remaining MER raceway across Mech chase | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
2655 | TT_TASK | Frame & Top out | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
2656 | TT_TASK | OverHead MEPFP Rough-In | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2657 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Tue Mar 30 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Fri Feb 12 00:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
2659 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 29 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2663 | TT_TASK | Generator & Utility Power Pull | Wed Jul 28 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2664 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2665 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2666 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Wed Dec 30 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2667 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2668 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Apr 26 08:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2669 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
2670 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2671 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2672 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 |  | COMPLETED
2673 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2674 | TT_TASK | Generator & Utility Power Test-Term | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
2676 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2677 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2678 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2679 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2680 | TT_TASK | Set Exterior Water Treatment equipment | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 01 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2681 | TT_TASK | Mechanical Equipment Piping Connections | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2682 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2685 | TT_TASK | Fire Alarm Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
2686 | TT_TASK | Controls Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2689 | TT_TASK | Generator & Utility Power Pull | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 19 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2690 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2691 | TT_TASK | Exterior Equipment Pads - for UPM's | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2692 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2693 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2694 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Apr 26 08:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2695 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2696 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2697 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
2698 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jul 10 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2699 | TT_TASK | Generator & Utility Power Test-Term | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Sat Aug 07 17:00:00 IDT 2021 |  | COMPLETED
2700 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2702 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2703 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2704 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2705 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2706 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2707 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2708 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2711 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
2712 | TT_TASK | Controls Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
2715 | TT_TASK | Generator & Utility Power Pull | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 | Thu Aug 05 09:30:00 IDT 2021 |  | COMPLETED
2716 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2717 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2718 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2719 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2720 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2721 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2722 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2723 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2724 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jul 15 00:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2725 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2726 | TT_TASK | Generator & Utility Power Test-Term | Fri Sep 03 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
2728 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 09 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2729 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2730 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2731 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2732 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2733 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2734 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
2737 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2738 | TT_TASK | Controls Installation | Wed Sep 01 07:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Thu Aug 26 07:00:00 IDT 2021 |  | 1210.0 | IN_PROGRESS
2741 | TT_TASK | Generator & Utility Power Pull | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Thu Jul 29 00:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
2742 | TT_TASK | Electrical Underground Rough-In | Sat Nov 07 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2743 | TT_TASK | Exterior Equipment Pads - for UPM's | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2744 | TT_TASK | Set Electrical Equipment-UPM | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2745 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Jan 18 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2746 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2747 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2748 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2749 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
2750 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2751 | TT_TASK | Generator & Utility Power Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2752 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2754 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2755 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2756 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2757 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2758 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2759 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2760 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2763 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
2764 | TT_TASK | Controls Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
2767 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2768 | TT_TASK | Ligthing Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2770 | TT_TASK | AHU/DOAS Equipment Setting | Sat May 15 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2771 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2773 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2774 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2776 | TT_TASK | Fire Riser Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed May 19 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2777 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2778 | TT_TASK | Controls Installation | Sat Jul 31 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2781 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
2782 | TT_TASK | Ligthing Installation | Thu Sep 16 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
2784 | TT_TASK | AHU/DOAS Equipment Setting | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2785 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2787 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2788 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2790 | TT_TASK | Fire Alarm System | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2791 | TT_TASK | Controls Installation | Mon Aug 23 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2794 | TT_TASK | VFD'S Installation & Wiring | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2795 | TT_TASK | Lighting Installation | Sat Sep 11 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
2797 | TT_TASK | AHU/DOAS Equipment Setting | Sat May 15 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2798 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2800 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2801 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2803 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2804 | TT_TASK | Controls Installation | Mon Aug 16 07:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 |  | COMPLETED
2807 | TT_TASK | VFD'S Installation & Wiring | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2808 | TT_TASK | Ligthing Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
2810 | TT_TASK | AHU/DOAS Equipment Setting | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2811 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2813 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2814 | TT_TASK | Toilet Piping Installation / DW | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
2816 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2817 | TT_TASK | Controls Installation | Wed Sep 08 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2820 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 09 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2821 | TT_TASK | HAC Installation | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2822 | TT_TASK | Cable Tray Installation | Tue May 04 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2823 | TT_TASK | Power Bus Installation | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2824 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2825 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 27 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2826 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Aug 25 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2827 | TT_TASK | Light Fixtures Installation | Sat Aug 21 07:00:00 IDT 2021 | Fri Aug 27 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
2829 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2830 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
2831 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon Sep 27 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2833 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2834 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2837 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 16 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2838 | TT_TASK | HAC Installation | Thu Apr 29 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2839 | TT_TASK | Cable Tray Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2840 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 |  | COMPLETED
2841 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2842 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Fri Sep 03 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2843 | TT_TASK | Pull/term/Test PDU to Power bus | Fri Sep 03 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  | 210.0 | NOT_STARTED
2844 | TT_TASK | Light Fixtures Installation | Fri Oct 01 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2846 | TT_TASK | EPMS Pull Wire / Term / Test | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2847 | TT_TASK | BMS Pull Wire / Term / Test | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
2848 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Thu Oct 21 07:00:00 IDT 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  | 801.0 | NOT_STARTED
2850 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2851 | TT_TASK | Controls Installation | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2854 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 16 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2855 | TT_TASK | HAC Installation | Thu Apr 29 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2856 | TT_TASK | Cable Tray Installation | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2857 | TT_TASK | Power Bus Installation | Mon Jun 14 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2858 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2859 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Sep 01 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2860 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Aug 25 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2861 | TT_TASK | Light Fixtures Installation | Mon Aug 30 07:00:00 IDT 2021 | Tue Sep 07 08:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  | 89.0 | IN_PROGRESS
2863 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2864 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 170.0 | NOT_STARTED
2865 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Sat Oct 09 07:00:00 IDT 2021 | Tue Nov 02 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2867 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2868 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2871 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 23 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2872 | TT_TASK | HAC Installation | Fri May 07 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2873 | TT_TASK | Cable Tray Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2874 | TT_TASK | Power Bus Installation | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Thu Jun 24 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2875 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed Jul 14 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2876 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Sep 01 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 25 00:00:00 IDT 2021 |  |  | IN_PROGRESS
2877 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 22 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2878 | TT_TASK | Light Fixtures Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2880 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2881 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 300.0 | NOT_STARTED
2882 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed Nov 03 07:00:00 IST 2021 | Tue Nov 30 17:00:00 IST 2021 |  |  | 691.0 | NOT_STARTED
2884 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2885 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jul 27 00:00:00 IDT 2021 | Tue Aug 24 13:00:00 IDT 2021 |  | COMPLETED
2889 | TT_TASK | ATS Equipment Yellow Tagging (S2 from MER) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2890 | TT_TASK | Control Power Available | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Fri Apr 30 07:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
2891 | TT_TASK | Power available for Start up | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2892 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2893 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 |  | COMPLETED
2895 | TT_TASK | Admin - NETA test validation Inpections- VECA-EPS-RTS Admin | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Mar 11 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
2896 | TT_TASK | Electrical Equipment Yellow Tagging | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2897 | TT_TASK | Admin/Colo-1 Network Startup | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2898 | TT_TASK | EPMS Checkout / Point to Point | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2902 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2903 | TT_TASK | UPM Yellow tagging - Admin & COLO-1 CELL-1 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2904 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
2905 | TT_TASK | SE- Completed L2 QC Checklist | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
2906 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-1 | Sat Apr 17 07:00:00 IDT 2021 | Tue Apr 20 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2907 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2908 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2909 | TT_TASK | Network Startup | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
2910 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2911 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2912 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2914 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2915 | TT_TASK | Power available for Start up | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2916 | TT_TASK | SE- Completed L2 QC Checklist | Mon Jun 14 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
2917 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Jul 13 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2918 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-3 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2919 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-3 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2920 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Thu Jun 10 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2921 | TT_TASK | Network Startup | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 |  | COMPLETED
2922 | TT_TASK | EPMS Checkout / Point to Point | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jul 06 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2923 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2924 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2926 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2927 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2928 | TT_TASK | SE- Completed L2 QC Checklist | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2929 | TT_TASK | Mechanical Equipment Yellow Tag | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 |  | COMPLETED
2930 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-2 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2931 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-2 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2932 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2933 | TT_TASK | Network Startup | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2934 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2935 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2936 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 20 15:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2938 | TT_TASK | Control Power Available | Tue Jun 22 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue Jun 22 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2939 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2940 | TT_TASK | SE- Completed L2 QC Checklist | Mon Jun 14 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
2941 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Jul 02 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2942 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-4 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2943 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-4 | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
2944 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Jul 07 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2945 | TT_TASK | Network Startup | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2946 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2947 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2948 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2950 | TT_TASK | GEN SCR testing and Burnins | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jul 14 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2951 | TT_TASK | Admin GEN SCR testing and Burnins | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2952 | TT_TASK | ATS- Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 |  | 100.0 | IN_PROGRESS
2953 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Tue Jul 13 11:00:00 IDT 2021 | Wed Jul 28 11:00:00 IDT 2021 | Tue Jul 13 11:00:00 IDT 2021 | Wed Jul 28 11:00:00 IDT 2021 |  | COMPLETED
2954 | TT_TASK | Cooling Automation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2955 | TT_TASK | BAS Prefunctional Testing on Construction Server | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Sat Aug 28 00:00:00 IDT 2021 |  | COMPLETED
2956 | TT_TASK | Additional Go-Back loadbanking (ASCO) | Fri Sep 10 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2957 | TT_TASK | Load Bank & IR Scan | Wed Sep 15 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2958 | TT_TASK | Level 3 Cx - ADMIN AND COLO1 | Fri Sep 17 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2959 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Sat Oct 02 07:00:00 IDT 2021 | Sat Oct 02 07:00:00 IDT 2021 |  |  |  | NOT_STARTED
2961 | TT_TASK | COLO 1 Level 4 & Level 5 IST | Sat Oct 02 08:00:00 IDT 2021 | Fri Oct 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2962 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Sat Oct 30 08:00:00 IDT 2021 | Mon Nov 08 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2963 | TT_TASK | Security Commissioning (level3 DCPS) | Tue Nov 09 08:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2964 | TT_TASK | Punch List - Admin/COLO 1 | Sat Oct 30 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2965 | TT_TASK | MST Ready for Network Install | Sat Oct 02 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2966 | TT_TASK | Final Clean/ ready for lock down | Sat Nov 13 07:00:00 IST 2021 | Mon Nov 22 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2970 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 18 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2971 | TT_TASK | Power available for Start up | Sat Sep 11 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2972 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2973 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  | 20.0 | IN_PROGRESS
2974 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-1 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2975 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-1 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2976 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Aug 04 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2977 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2978 | TT_TASK | EPMS Checkout / Point to Point | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 200.0 | NOT_STARTED
2979 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Thu Sep 16 07:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 |  |  | 20.0 | NOT_STARTED
2980 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Thu Sep 16 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  | 50.0 | NOT_STARTED
2982 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2983 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2984 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2985 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2986 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-3 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2987 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-3 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2988 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2989 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2990 | TT_TASK | EPMS Checkout / Point to Point | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
2991 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2992 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2994 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2995 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2996 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2997 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2998 | TT_TASK | UPM Yellow tagging - COLO-2 CELL-2 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2999 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-2 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
3000 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jul 13 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3001 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3002 | TT_TASK | EPMS Checkout / Point to Point | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3003 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3004 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3006 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3007 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3008 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
3009 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3010 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-4 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
3011 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-4 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
3012 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Aug 18 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3013 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3014 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3015 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3016 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  | 30.0 | NOT_STARTED
3018 | TT_TASK | GEN SCR testing and Burnins | Sat Sep 18 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  | 150.0 | NOT_STARTED
3019 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Mon Sep 27 07:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3020 | TT_TASK | Cooling Automation | Mon Oct 11 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3021 | TT_TASK | BAS Prefunctional Testing on Construction Server | Thu Oct 07 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3022 | TT_TASK | Load Bank & IR Scan | Tue Oct 26 07:00:00 IDT 2021 | Tue Nov 16 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3023 | TT_TASK | Level 3 Cx- COLO-2 | Wed Nov 17 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3024 | TT_TASK | Weather (5 Days) - 0 remaining Check Delay #14 for updates | Sat Dec 04 07:00:00 IST 2021 | Sat Dec 04 07:00:00 IST 2021 |  |  |  | NOT_STARTED
3026 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Mon Dec 27 07:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3027 | TT_TASK | Security Commissioning (level3 DCPS) | Tue Jan 11 07:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3028 | TT_TASK | COLO 2 Level 4 & Level 5 IST | Sat Dec 04 08:00:00 IST 2021 | Fri Dec 24 17:00:00 IST 2021 |  |  | 16.0 | NOT_STARTED
3029 | TT_TASK | Punch List COLO-2 | Mon Dec 27 08:00:00 IST 2021 | Sun Jan 09 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3030 | TT_TASK | MST Ready for Network Install | Sat Dec 04 07:00:00 IST 2021 | Thu Dec 09 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3031 | TT_TASK | Final Clean/ ready for lock down | Mon Jan 10 08:00:00 IST 2022 | Fri Jan 21 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3035 | TT_TASK | Control Power Available | Thu Sep 09 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3036 | TT_TASK | Power available for Start up | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3037 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3038 | TT_TASK | Mechanical Equipment Yellow Tag | Wed Sep 22 07:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3039 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-1 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3040 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-1 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3041 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3042 | TT_TASK | Network Startup | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3043 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3044 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3045 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Tue Oct 05 07:00:00 IDT 2021 | Tue Oct 19 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3047 | TT_TASK | Control Power Available | Tue Sep 21 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3048 | TT_TASK | Power available for Start up | Mon Oct 04 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3049 | TT_TASK | SE- Completed L2 QC Checklist | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3050 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Oct 05 07:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3051 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-3 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 160.0 | NOT_STARTED
3052 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-3 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3053 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3054 | TT_TASK | Network Startup | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3055 | TT_TASK | EPMS Checkout / Point to Point | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3056 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3057 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Oct 18 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3059 | TT_TASK | Control Power Available | Thu Sep 09 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3060 | TT_TASK | Power available for Start up | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3061 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3062 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3063 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-2 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3064 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-2 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3065 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Fri Aug 13 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3066 | TT_TASK | Network Startup | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3067 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3068 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3069 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  |  | 170.0 | NOT_STARTED
3071 | TT_TASK | Control Power Available | Tue Sep 21 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3072 | TT_TASK | Power available for Start up | Mon Oct 04 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3073 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3074 | TT_TASK | Mechanical Equipment Yellow Tag | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3075 | TT_TASK | UPM Yellow tagging COLO-3 CELL-4 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 160.0 | NOT_STARTED
3076 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-4 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
3077 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3078 | TT_TASK | Network Startup | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3079 | TT_TASK | EPMS Checkout / Point to Point | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3080 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3081 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  |  | 70.0 | NOT_STARTED
3083 | TT_TASK | GEN SCR testing and Burnins | Fri Oct 08 07:00:00 IDT 2021 | Tue Oct 26 17:00:00 IDT 2021 |  |  | 320.0 | NOT_STARTED
3084 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Fri Oct 22 07:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3085 | TT_TASK | Cooling Automation | Fri Nov 05 07:00:00 IST 2021 | Fri Nov 19 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3086 | TT_TASK | BAS Prefunctional Testing on Construction Server | Mon Nov 01 07:00:00 IST 2021 | Wed Nov 24 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3087 | TT_TASK | Load Bank & IR Scan | Wed Dec 08 07:00:00 IST 2021 | Mon Jan 03 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3088 | TT_TASK | Level 3 Cx- COLO-3 | Tue Jan 04 07:00:00 IST 2022 | Tue Jan 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3089 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Wed Jan 19 07:00:00 IST 2022 | Wed Jan 19 07:00:00 IST 2022 |  |  |  | NOT_STARTED
3091 | TT_TASK | COLO 3 Level 4 & Level 5 IST | Wed Jan 19 08:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3092 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Wed Feb 09 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3093 | TT_TASK | Security Commissioning (level3 DCPS) | Sat Feb 19 08:00:00 IST 2022 | Wed Feb 23 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3094 | TT_TASK | Punch List COLO-3 | Wed Feb 09 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3095 | TT_TASK | MST Ready for Network Install | Wed Jan 19 08:00:00 IST 2022 | Tue Jan 25 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3096 | TT_TASK | Final Clean/ ready for lock down | Wed Feb 23 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3100 | TT_TASK | Control Power Available | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3101 | TT_TASK | Power available for Start up | Tue Nov 02 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3102 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3103 | TT_TASK | Mechanical Equipment Yellow Tag | Mon Oct 18 07:00:00 IDT 2021 | Thu Oct 28 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3104 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-1 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
3105 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-1 | Fri Sep 17 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
3106 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3107 | TT_TASK | Network Startup | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3108 | TT_TASK | EPMS Checkout / Point to Point | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  | 40.0 | NOT_STARTED
3109 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3110 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3112 | TT_TASK | Control Power Available | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3113 | TT_TASK | Power available for Start up | Mon Nov 15 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3114 | TT_TASK | SE- Completed L2 QC Checklist | Sat Oct 23 07:00:00 IDT 2021 | Wed Nov 03 17:00:00 IST 2021 |  |  | 20.0 | NOT_STARTED
3115 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Oct 29 07:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 |  |  | 70.0 | NOT_STARTED
3116 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-3 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Mon Aug 16 00:00:00 IDT 2021 |  | COMPLETED
3117 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-3 | Tue Sep 28 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  | 200.0 | NOT_STARTED
3118 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3119 | TT_TASK | Network Startup | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3120 | TT_TASK | EPMS Checkout / Point to Point | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3121 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3122 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3124 | TT_TASK | Control Power Available | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3125 | TT_TASK | Power available for Start up | Tue Nov 02 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3126 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3127 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3128 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-2 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3129 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-2 | Fri Sep 17 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
3130 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3131 | TT_TASK | Network Startup | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3132 | TT_TASK | EPMS Checkout / Point to Point | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3133 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3134 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3136 | TT_TASK | Control Power Available | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3137 | TT_TASK | Power available for Start up | Mon Nov 15 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3138 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3139 | TT_TASK | Mechanical Equipment Yellow Tag | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  | 140.0 | NOT_STARTED
3140 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-4 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3141 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-4 | Sat Sep 18 07:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 |  |  | 270.0 | NOT_STARTED
3142 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3143 | TT_TASK | Network Startup | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3144 | TT_TASK | EPMS Checkout / Point to Point | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3145 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3146 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3148 | TT_TASK | GEN SCR testing and Burnins | Fri Nov 19 07:00:00 IST 2021 | Thu Dec 09 17:00:00 IST 2021 |  |  | 310.0 | NOT_STARTED
3149 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Tue Nov 30 07:00:00 IST 2021 | Mon Dec 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3150 | TT_TASK | Cooling Automation | Tue Dec 14 07:00:00 IST 2021 | Thu Dec 30 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3151 | TT_TASK | BAS Prefunctional Testing on Construction Server | Tue Dec 07 07:00:00 IST 2021 | Tue Jan 04 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3152 | TT_TASK | Load Bank & IR Scan | Sat Jan 22 07:00:00 IST 2022 | Sat Feb 12 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3153 | TT_TASK | Level 3 Cx - COLO-4 | Mon Feb 14 07:00:00 IST 2022 | Sat Feb 26 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3154 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Mon Feb 28 07:00:00 IST 2022 | Mon Feb 28 07:00:00 IST 2022 |  |  |  | NOT_STARTED
3156 | TT_TASK | COLO 4 Level 4 & Level 5 IST | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 20 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3157 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Mon Mar 21 08:00:00 IST 2022 | Wed Mar 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3158 | TT_TASK | Security Commissioning (level3 DCPS) | Thu Mar 31 08:00:00 IDT 2022 | Mon Apr 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3159 | TT_TASK | Punch List COLO-4 | Mon Mar 21 08:00:00 IST 2022 | Sat Apr 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3160 | TT_TASK | MST Ready for Network Install | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3161 | TT_TASK | Final Clean/ ready for lock down | Sun Apr 03 08:00:00 IDT 2022 | Wed Apr 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3163 | TT_TASK | CSA Punchlist - COLO-1 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  | COMPLETED
3164 | TT_TASK | CSA Punchlist - COLO-2 | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 220.0 | NOT_STARTED
3165 | TT_TASK | CSA Punchlist - COLO-3 | Mon Nov 01 07:00:00 IST 2021 | Fri Nov 12 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3166 | TT_TASK | CSA Punchlist - COLO-4 | Sat Dec 11 07:00:00 IST 2021 | Thu Dec 23 17:00:00 IST 2021 |  |  | 380.0 | NOT_STARTED
3167 | TT_TASK | MEP Punchlist - COLO-1 | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 110.0 | NOT_STARTED
3168 | TT_TASK | MEP Punchlist - COLO-2 | Wed Nov 17 07:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 |  |  | 20.0 | NOT_STARTED
3169 | TT_TASK | MEP Punchlist - COLO-3 | Tue Jan 04 07:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  |  | 20.0 | NOT_STARTED
3170 | TT_TASK | MEP Punchlist - COLO-4 | Mon Feb 14 07:00:00 IST 2022 | Thu Feb 24 17:00:00 IST 2022 |  |  | 20.0 | NOT_STARTED
3171 | TT_TASK | AE/Owner Punchlist - COLO-1 | Sat Oct 30 07:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  |  | 60.0 | NOT_STARTED
3172 | TT_TASK | AE/Owner Punchlist - COLO-2 | Mon Dec 27 07:00:00 IST 2021 | Mon Jan 03 17:00:00 IST 2022 |  |  | 41.0 | NOT_STARTED
3173 | TT_TASK | AE/Owner Punchlist - COLO-3 | Wed Feb 09 07:00:00 IST 2022 | Mon Feb 14 17:00:00 IST 2022 |  |  | 71.0 | NOT_STARTED
3174 | TT_TASK | AE/Owner Punchlist - COLO-4 | Mon Mar 21 07:00:00 IST 2022 | Fri Mar 25 17:00:00 IDT 2022 |  |  | 70.0 | NOT_STARTED
3182 | TT_TASK | UMS - ROJ COLO-2 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3183 | TT_TASK | UMS - ROJ COLO-3 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3184 | TT_TASK | UMS - ROJ COLO-4 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3185 | TT_TASK | MSFT Delivery -UMS -COLO 4 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3186 | TT_TASK | MSFT Delivery -UMS -COLO 3 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3187 | TT_TASK | MSFT Delivery -UMS -COLO 2 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3190 | TT_TASK | TCO COLO 2 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3191 | TT_TASK | Weather Tight | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3192 | TT_TASK | Duct Bank - UMS01 to UPM COLO-1 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3193 | TT_TASK | Duct Bank - UMS02 to UPM COLO-2 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3194 | TT_TASK | Duct Bank - UMS03 to UPM COLO-3 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3195 | TT_TASK | Duct Bank - UMS04 to UPM COLO-4 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3196 | TT_TASK | PAD- COLO-1 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3197 | TT_TASK | PAD- COLO-2 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3198 | TT_TASK | PAD- COLO-3 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3199 | TT_TASK | PAD- COLO-4 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3200 | TT_TASK | Pull- UMS01- UPM COLO-1 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3201 | TT_TASK | Pull- UMS02- UPM COLO-2 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3202 | TT_TASK | Pull- UMS03- UPM COLO-3 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3203 | TT_TASK | Pull- UMS04- UPM COLO-4 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3204 | TT_TASK | Set- COLO-1 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3205 | TT_TASK | Set- COLO-2 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3206 | TT_TASK | Set- COLO-3 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3207 | TT_TASK | Set- COLO-4 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3208 | TT_TASK | Term Admin - UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3209 | TT_TASK | Term COLO -1 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3210 | TT_TASK | Term COLO -1 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3211 | TT_TASK | Term COLO -2 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3212 | TT_TASK | Term COLO -2 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3213 | TT_TASK | Term COLO -3 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3214 | TT_TASK | Term COLO -3 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3215 | TT_TASK | Term COLO -4 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3216 | TT_TASK | Term COLO -4 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3217 | TT_TASK | Term- UMS01- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3218 | TT_TASK | Term- UMS02- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3219 | TT_TASK | Term- UMS03- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3220 | TT_TASK | Term- UMS04- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3221 | TT_TASK | Yellow Tagging for UMS01 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3222 | TT_TASK | Yellow Tagging for UMS02 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3223 | TT_TASK | Yellow Tagging for UMS03 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3224 | TT_TASK | Yellow Tagging for UMS04 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3225 | TT_TASK | URS Vault design and Approval | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3227 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Thu Oct 22 07:00:00 IDT 2020 | Thu Oct 22 07:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3228 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3229 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jan 23 07:00:00 IST 2021 | Sat Jan 23 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3230 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Thu Oct 22 07:00:00 IDT 2020 | Thu Oct 22 07:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3231 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3232 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jan 23 07:00:00 IST 2021 | Sat Jan 23 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3233 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Nov 04 07:00:00 IST 2020 | Wed Nov 04 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3234 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3235 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Feb 04 07:00:00 IST 2021 | Thu Feb 04 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3236 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Nov 04 07:00:00 IST 2020 | Wed Nov 04 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3237 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3238 | TT_TASK | COLO Lighting installation (DRB#2) | Mon Feb 08 07:00:00 IST 2021 | Mon Feb 08 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3239 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3240 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Dec 02 07:00:00 IST 2020 | Wed Dec 02 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3241 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Mar 11 07:00:00 IST 2021 | Thu Mar 11 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3242 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Tue Dec 29 07:00:00 IST 2020 | Tue Dec 29 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3243 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Dec 02 07:00:00 IST 2020 | Wed Dec 02 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3244 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Mar 11 07:00:00 IST 2021 | Thu Mar 11 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3245 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Dec 18 07:00:00 IST 2020 | Fri Dec 18 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3246 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Dec 15 07:00:00 IST 2020 | Tue Dec 15 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3247 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Mar 26 07:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3248 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Dec 15 07:00:00 IST 2020 | Tue Dec 15 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3249 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Mar 26 07:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3250 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Jan 07 07:00:00 IST 2021 | Thu Jan 07 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3251 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3252 | TT_TASK | COLO Lighting installation (DRB#2) | Tue Apr 27 07:00:00 IDT 2021 | Tue Apr 27 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3253 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Jan 14 07:00:00 IST 2021 | Thu Jan 14 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3254 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3255 | TT_TASK | COLO Lighting installation (DRB#2) | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3256 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Fri Feb 12 07:00:00 IST 2021 | Fri Feb 12 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3257 | TT_TASK | COLO Lighting installation (DRB#2) | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3258 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Jan 29 07:00:00 IST 2021 | Fri Jan 29 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3259 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Fri Feb 12 07:00:00 IST 2021 | Fri Feb 12 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3260 | TT_TASK | COLO Lighting installation (DRB#2) | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3261 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3262 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Mar 09 07:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3263 | TT_TASK | COLO Lighting installation (DRB#2) | Wed Jun 09 07:00:00 IDT 2021 | Wed Jun 09 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3264 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3265 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Mar 09 07:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3266 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Jun 04 07:00:00 IDT 2021 | Fri Jun 04 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3267 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Sat Feb 20 07:00:00 IST 2021 | Sat Feb 20 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3268 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Mon Mar 22 07:00:00 IST 2021 | Mon Mar 22 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3269 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jun 19 07:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3270 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Sat Feb 20 07:00:00 IST 2021 | Sat Feb 20 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3271 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Mon Mar 22 07:00:00 IST 2021 | Mon Mar 22 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3272 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jun 19 07:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3273 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3274 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3275 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3276 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3277 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3278 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3279 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3280 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3281 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3282 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3283 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3284 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3285 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3286 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3287 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3288 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3290 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 05 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3291 | TT_TASK | Mechanical Equipment Piping Connections | Tue Nov 03 07:00:00 IST 2020 | Tue Nov 17 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3292 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3293 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3294 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3295 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3296 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3297 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3298 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3299 | TT_TASK | Fluid Cooler RI prefabrication | Thu Dec 10 07:00:00 IST 2020 | Wed Dec 16 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3300 | TT_TASK | Fluid Cooler RI prefabrication | Wed Dec 16 07:00:00 IST 2020 | Tue Dec 22 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3301 | TT_TASK | Fluid Cooler RI prefabrication | Wed Dec 23 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3302 | TT_TASK | Fluid Cooler RI prefabrication | Thu Jan 07 07:00:00 IST 2021 | Wed Jan 13 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3303 | TT_TASK | Fluid Cooler RI prefabrication | Thu Jan 14 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3304 | TT_TASK | Fluid Cooler RI prefabrication | Fri Jan 22 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3305 | TT_TASK | Fluid Cooler RI prefabrication | Tue Jan 26 07:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3306 | TT_TASK | Submit and approve shop drawing for PEMB penetrations | Mon Oct 19 08:00:00 IDT 2020 | Sun Nov 08 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3308 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3309 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3310 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3311 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3312 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3313 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3314 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3315 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3316 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3317 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3318 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3319 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3321 | TT_TASK | Yellow Tagging for COLO-2 UPM's | Fri Jan 29 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3322 | TT_TASK | Yellow Tagging for COLO-3 UPM's | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 |  | COMPLETED
3323 | TT_TASK | Yellow Tagging for COLO-4 UPM's | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 |  | COMPLETED
3324 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 11 07:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3326 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3327 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3328 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Mar 10 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3329 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 08 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3330 | TT_TASK | Fluid Cooler QAQC and Cx | Thu Mar 18 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3331 | TT_TASK | Fluid Cooler QAQC and Cx | Fri Apr 02 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3332 | TT_TASK | Fluid Cooler QAQC and Cx | Fri Mar 26 07:00:00 IDT 2021 | Sat Mar 27 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3333 | TT_TASK | Fluid Cooler QAQC and Cx | Tue Apr 06 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3334 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 14 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3335 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 21 07:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3336 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 14 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3337 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 28 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3338 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 21 07:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3339 | TT_TASK | Fluid Cooler QAQC and Cx | Thu May 06 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3341 | TT_TASK | COLO-2 CELL3 Rearrange Roxtec blocks per coordination layout | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3342 | TT_TASK | COLO2 CELL3 Interior MER conduit installation utility side | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 06 07:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3343 | TT_TASK | COLO-2 CELL3 Interior MER conduit installation building side | Tue Apr 20 07:00:00 IDT 2021 | Tue Apr 20 07:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3345 | TT_TASK | COLO-2 Cell-4 Rearrange Roxtec blocks per coordination layout | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3346 | TT_TASK | COLO2 CELL4 Interior MER conduit installation utility side | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3347 | TT_TASK | COLO2 CELL4 Interior MER conduit installation building side | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3350 | TT_TASK | COLO-2 Cell-1 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3351 | TT_TASK | COLO-2 Cell-2 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3352 | TT_TASK | COLO-2 Cell-3 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3353 | TT_TASK | COLO-2 Cell-4 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3354 | TT_TASK | COLO2 CELL1 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3355 | TT_TASK | COLO2 CELL2 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3356 | TT_TASK | COLO2 CELL3 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3357 | TT_TASK | COLO2 CELL4 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3360 | TT_TASK | Concrete interior - Create Punch list | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
3361 | TT_TASK | Concrete interior - Complete Punch List | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
3362 | TT_TASK | Garco Steel (Mezz steel, Yard) - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3363 | TT_TASK | Garco Steel (Mezz steel, Yard) - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3364 | TT_TASK | Sure Steel (Building, Mezz, Ceiling) - Create Punch list | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
3365 | TT_TASK | Sure Steel (Building, Mezz, Ceiling) - Complete Punch List | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
3366 | TT_TASK | Advantage - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3367 | TT_TASK | Advantage - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3368 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3369 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3370 | TT_TASK | VECA - Create Punch list | Tue Sep 07 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3371 | TT_TASK | VECA - Complete Punch List | Thu Sep 09 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3372 | TT_TASK | LINX - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3373 | TT_TASK | LINX - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3374 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3375 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3376 | TT_TASK | TCM- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3377 | TT_TASK | TCM - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3378 | TT_TASK | Cascade- Create Punch list | Mon Apr 26 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
3379 | TT_TASK | Cascade - Complete Punch List | Wed Apr 28 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3380 | TT_TASK | Submit GC Punch List to A/E | Tue Sep 21 07:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3381 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3382 | TT_TASK | Complete A/E Punchlist | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3383 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3384 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3385 | TT_TASK | VECA - Create Punch list | Fri Oct 29 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3386 | TT_TASK | VECA - Complete Punch List | Mon Nov 01 07:00:00 IST 2021 | Mon Nov 08 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3387 | TT_TASK | LINX - Create Punch list | Mon Aug 16 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3388 | TT_TASK | LINX - Complete Punch List | Wed Aug 18 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3389 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3390 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3391 | TT_TASK | TCM- Create Punch list | Wed Sep 22 07:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3392 | TT_TASK | TCM - Complete Punch List | Fri Sep 24 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3393 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3394 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3395 | TT_TASK | Submit GC Punch List to A/E | Tue Nov 09 07:00:00 IST 2021 | Tue Nov 09 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3396 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Nov 10 07:00:00 IST 2021 | Tue Nov 16 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3397 | TT_TASK | Complete A/E Punchlist | Wed Nov 17 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3398 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3399 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3400 | TT_TASK | VECA - Create Punch list | Tue Dec 14 07:00:00 IST 2021 | Wed Dec 15 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3401 | TT_TASK | VECA - Complete Punch List | Thu Dec 16 07:00:00 IST 2021 | Thu Dec 23 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3402 | TT_TASK | LINX - Create Punch list | Wed Oct 13 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3403 | TT_TASK | LINX - Complete Punch List | Fri Oct 15 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3404 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3405 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3406 | TT_TASK | TCM- Create Punch list | Wed Sep 22 07:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3407 | TT_TASK | TCM - Complete Punch List | Fri Sep 24 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3408 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3409 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3410 | TT_TASK | Submit GC Punch List to A/E | Mon Dec 27 07:00:00 IST 2021 | Mon Dec 27 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3411 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Tue Dec 28 07:00:00 IST 2021 | Wed Jan 05 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3412 | TT_TASK | Complete A/E Punchlist | Thu Jan 06 07:00:00 IST 2022 | Thu Jan 20 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3413 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3414 | TT_TASK | PCI - Complete Punch List | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3415 | TT_TASK | VECA - Create Punch list | Fri Jan 28 07:00:00 IST 2022 | Mon Jan 31 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3416 | TT_TASK | VECA - Complete Punch List | Tue Feb 01 07:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3417 | TT_TASK | LINX - Create Punch list | Fri Nov 19 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3418 | TT_TASK | LINX - Complete Punch List | Mon Nov 22 07:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3419 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3420 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3421 | TT_TASK | TCM- Create Punch list | Thu Nov 04 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3422 | TT_TASK | TCM - Complete Punch List | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3423 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3424 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3425 | TT_TASK | Submit GC Punch List to A/E | Tue Feb 08 07:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3426 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Feb 09 07:00:00 IST 2022 | Tue Feb 15 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3427 | TT_TASK | Complete A/E Punchlist | Wed Feb 16 07:00:00 IST 2022 | Tue Mar 01 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3428 | TT_TASK | COLO-2 Cell2 Rearrange Roxtec blocks per coordination layout (delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
3429 | TT_TASK | COLO2 CELL2 Interior MER conduit installation utility side(delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
3430 | TT_TASK | COLO-2 CELL2 Interior MER conduit installation building (delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
3432 | TT_TASK | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change(delete) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
3433 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3434 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3435 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3436 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
303 | TT_TASK | MSFT Issue DRB #1 for Review | Tue May 26 07:00:00 IDT 2020 | Mon Jun 01 17:00:00 IDT 2020 | Tue May 19 00:00:00 IDT 2020 | Mon Jul 20 00:00:00 IDT 2020 |  | COMPLETED
306 | TT_TASK | Lead Time for PEMB | Wed Feb 19 08:00:00 IST 2020 | Thu Jun 18 17:00:00 IDT 2020 | Mon Feb 24 00:00:00 IST 2020 | Thu Jun 18 00:00:00 IDT 2020 |  | COMPLETED
307 | TT_TASK | Lead Time for Rebar (Footings & Walls) | Mon Apr 27 08:00:00 IDT 2020 | Sun May 31 17:00:00 IDT 2020 | Mon Mar 30 00:00:00 IDT 2020 | Tue Apr 21 00:00:00 IDT 2020 |  | COMPLETED
308 | TT_TASK | Lead Time for COLO 1 Structural Interior Steel | Mon Aug 10 08:00:00 IDT 2020 | Sat Oct 31 17:00:00 IST 2020 | Tue Jun 30 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
309 | TT_TASK | Lead Time for Wall & Roof Metal Panels | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Mon Jun 29 00:00:00 IDT 2020 |  | COMPLETED
310 | TT_TASK | Lead Time for Admin/COLO 1 Yard Steel | Mon Aug 31 08:00:00 IDT 2020 | Sun Oct 18 17:00:00 IDT 2020 | Tue Jun 30 00:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 |  | COMPLETED
311 | TT_TASK | Lead Time for HM Ext. frames | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
312 | TT_TASK | Lead time for Drywall/Framing | Mon Aug 10 08:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Mon Aug 10 08:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
592 | TT_TASK | MV Ductbanks Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | Mon Sep 14 08:00:00 IDT 2020 | Sun Sep 20 17:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 | Sun Sep 06 00:00:00 IDT 2020 |  | COMPLETED
593 | TT_TASK | MV Wire Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | Wed Aug 12 08:00:00 IDT 2020 | Tue Nov 03 17:00:00 IST 2020 | Tue Aug 04 00:00:00 IDT 2020 | Mon Oct 26 00:00:00 IST 2020 |  | COMPLETED
594 | TT_TASK | UMS Vault Procurement DRB#1 | Mon Sep 28 08:00:00 IDT 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
595 | TT_TASK | DRB#1 BIM Modeling & Coordination DRB#1 JAZ to UMS/URS & UPM to UMS | Mon Aug 10 08:00:00 IDT 2020 | Sun Aug 23 17:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
596 | TT_TASK | Site- Neher Mcgrath Study DRB#1 JAZ to UMS/URS & UPM to UMS | Tue Aug 11 08:00:00 IDT 2020 | Mon Aug 24 17:00:00 IDT 2020 | Tue Aug 04 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
597 | TT_TASK | JAZ Riser Support DRB#1 Procurement/ Jaz Foundations/Construction | Mon Aug 10 08:00:00 IDT 2020 | Sun Oct 18 17:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
598 | TT_TASK | UPM to UMS Vaults Procurement DRB#1 | Tue Sep 08 08:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
600 | TT_TASK | MV Ductbanks Procurement | Wed Aug 12 08:00:00 IDT 2020 | Thu Aug 20 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
601 | TT_TASK | Telecom DuctBank / Vaults Procurement | Thu May 14 08:00:00 IDT 2020 | Mon May 18 17:00:00 IDT 2020 | Wed May 06 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
602 | TT_TASK | MV Wire Procurement | Wed Aug 12 08:00:00 IDT 2020 | Tue Nov 03 17:00:00 IST 2020 | Tue Jul 21 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
603 | TT_TASK | Off-Site BIM Modeling & Coordination | Mon Apr 27 08:00:00 IDT 2020 | Sun May 24 17:00:00 IDT 2020 | Tue Apr 14 00:00:00 IDT 2020 | Tue May 05 00:00:00 IDT 2020 |  | COMPLETED
604 | TT_TASK | Neher Mcgrath Study | Thu Jul 02 08:00:00 IDT 2020 | Thu Aug 06 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Fri Jul 24 00:00:00 IDT 2020 |  | COMPLETED
605 | TT_TASK | URS Vault Procurement | Mon Sep 28 08:00:00 IDT 2020 | Wed Nov 11 17:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
607 | TT_TASK | Site Temp Power Procurement & Infrastructure | Mon Jun 29 08:00:00 IDT 2020 | Mon Aug 31 08:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
609 | TT_TASK | Underground Grounding Procurement | Mon Apr 27 08:00:00 IDT 2020 | Sun May 17 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Tue Apr 28 00:00:00 IDT 2020 |  | COMPLETED
610 | TT_TASK | BIM Modeling (Under ground) | Tue May 05 08:00:00 IDT 2020 | Mon Jun 08 17:00:00 IDT 2020 | Tue May 05 08:00:00 IDT 2020 | Mon Jun 08 00:00:00 IDT 2020 |  | COMPLETED
611 | TT_TASK | Electrical Long Lead Equipment Procurement (Cablebus, Panel Boards) | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Mon Apr 27 08:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
612 | TT_TASK | BIM Modeling (Above ground) | Sun Aug 02 08:00:00 IDT 2020 | Wed Sep 30 17:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
615 | TT_TASK | Design / Lead Time for Electrical/Telecom (OFCI Telecom BOM Materials) | Mon Aug 10 08:00:00 IDT 2020 | Sat Nov 07 17:00:00 IST 2020 | Wed Jul 01 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
616 | TT_TASK | Design / Lead Time for Busway (OFCI Starline BOM Materials) | Thu Nov 26 08:00:00 IST 2020 | Thu Jan 14 17:00:00 IST 2021 | Mon Sep 21 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
619 | TT_TASK | Water treatment Skids Procurement ( sourcing materials and Materail approval only) | Mon Apr 27 08:00:00 IDT 2020 | Fri Nov 06 12:00:00 IST 2020 | Tue Apr 07 00:00:00 IDT 2020 | Mon Jul 06 00:00:00 IDT 2020 |  | COMPLETED
620 | TT_TASK | Design / Lead Time for M&P overhead | Mon Jun 29 08:00:00 IDT 2020 | Tue Jul 28 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
621 | TT_TASK | Design / Lead Time for Fire Protection | Mon Aug 31 08:00:00 IDT 2020 | Tue Sep 29 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
622 | TT_TASK | Design / Lead Time for Fire Alarm | Mon Jun 29 08:00:00 IDT 2020 | Thu Aug 27 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
628 | TT_TASK | URS/UMS Concrete Anchor and Vault Design | Mon Aug 10 07:00:00 IDT 2020 | Wed Aug 26 17:00:00 IDT 2020 | Wed Aug 05 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
629 | TT_TASK | URS/UMS Vault Submiital Review by EOR | Mon Sep 14 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Fri Sep 25 00:00:00 IDT 2020 |  | COMPLETED
632 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-2 PSR(10/13) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sat Dec 12 17:00:00 IST 2020 | Tue Oct 13 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
633 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-3 PSR(9/28) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Mon Dec 28 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
634 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-4 PSR (10/28) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Fri Nov 27 16:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
635 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-1 PSR (9/19) to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Tue Dec 15 17:00:00 IST 2020 | Sat Sep 19 00:00:00 IDT 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
637 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-1 11/25 to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Fri Oct 09 17:00:00 IDT 2020 | Wed Nov 25 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
638 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-2 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sun Nov 15 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
639 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-4 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Fri Nov 06 16:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
640 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-3 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sun Nov 15 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
642 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-1 PSR 11/23 to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Wed Oct 14 17:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
643 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-2 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
644 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-4 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Wed Nov 11 16:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Sun Jan 03 00:00:00 IST 2021 |  | COMPLETED
645 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-3 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Sun Jan 03 00:00:00 IST 2021 |  | COMPLETED
647 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-1 12/7 to MSFT delivery) | Sat Jan 09 08:00:00 IST 2021 | Sat Jan 09 08:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
648 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-2 12/7 to MSFT delivery) | Tue Jan 05 08:00:00 IST 2021 | Tue Jan 05 08:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
649 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-4 12/18 to MSFT delivery) | Sat Jan 09 08:00:00 IST 2021 | Sat Jan 09 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
650 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-3 12/18 to MSFT delivery) | Thu Jan 14 08:00:00 IST 2021 | Thu Jan 14 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
653 | TT_TASK | Review Fluid Cooler wiring and devices buyout with Stetner | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Wed Sep 23 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
654 | TT_TASK | Change order release for fluid cooler wiring devices | Mon Oct 19 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 | Mon Oct 26 00:00:00 IST 2020 |  | COMPLETED
657 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
658 | TT_TASK | Fluid Cooler RI in place | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
659 | TT_TASK | Fluid Cooler Wire install and Term | Fri Mar 05 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
661 | TT_TASK | Fluid Cooler Panel installation | Tue Mar 23 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
662 | TT_TASK | Fluid Cooler RI in place | Thu Mar 18 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
663 | TT_TASK | Fluid Cooler Wire install and Term | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 |  | COMPLETED
665 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 15 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
666 | TT_TASK | Fluid Cooler RI in place | Fri Feb 19 07:00:00 IST 2021 | Thu Feb 25 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
667 | TT_TASK | Fluid Cooler Wire install and Term | Thu Mar 18 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
669 | TT_TASK | Fluid Cooler Panel installation | Thu Mar 18 07:00:00 IST 2021 | Mon Mar 22 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
670 | TT_TASK | Fluid Cooler RI in place | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
671 | TT_TASK | Fluid Cooler Wire install and Term | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
674 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 29 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
675 | TT_TASK | Fluid Cooler RI in place | Thu Mar 25 07:00:00 IST 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
676 | TT_TASK | Fluid Cooler Wire install and Term | Thu Apr 01 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
678 | TT_TASK | Fluid Cooler Panel installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
679 | TT_TASK | Fluid Cooler RI in place | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
680 | TT_TASK | Fluid Cooler Wire install and Term | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
682 | TT_TASK | Fluid Cooler Panel installation | Thu Apr 01 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Sat Mar 27 00:00:00 IDT 2021 |  | COMPLETED
683 | TT_TASK | Fluid Cooler RI in place | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
684 | TT_TASK | Fluid Cooler Wire install and Term | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
687 | TT_TASK | Fluid Cooler Panel installation | Tue May 04 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
688 | TT_TASK | Fluid Cooler RI in place | Fri May 07 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
689 | TT_TASK | Fluid Cooler Wire install and Term | Fri May 14 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
691 | TT_TASK | Fluid Cooler Panel installation | Mon May 17 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
692 | TT_TASK | Fluid Cooler RI in place | Thu May 20 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
693 | TT_TASK | Fluid Cooler Wire install and Term | Fri May 28 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
695 | TT_TASK | Fluid Cooler Panel installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
696 | TT_TASK | Fluid Cooler RI in place | Fri Jun 04 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
697 | TT_TASK | Fluid Cooler Wire install and Term | Fri Jun 11 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
700 | TT_TASK | Fluid Cooler Panel installation | Tue Jun 08 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
701 | TT_TASK | Fluid Cooler RI in place | Fri Jun 11 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
702 | TT_TASK | Fluid Cooler Wire install and Term | Sat Jun 19 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
704 | TT_TASK | Fluid Cooler Panel installation | Fri Jun 11 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
705 | TT_TASK | Fluid Cooler RI in place | Sat Jun 19 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
706 | TT_TASK | Fluid Cooler Wire install and Term | Sat Jun 26 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
708 | TT_TASK | Fluid Cooler Panel installation | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
709 | TT_TASK | Fluid Cooler RI in place | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
710 | TT_TASK | Fluid Cooler Wire install and Term | Tue Jul 13 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
712 | TT_TASK | Fluid Cooler Panel installation | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
713 | TT_TASK | Fluid Cooler RI in place | Tue Jul 13 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
714 | TT_TASK | Fluid Cooler Wire install and Term | Tue Jul 20 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
718 | TT_TASK | ADMIN Overhead Rough-in (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
719 | TT_TASK | ADMIN Electrical Room Build out (DRB#2) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
720 | TT_TASK | ADMIN Lighting installation (DRB#2) | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
742 | TT_TASK | Water Treatmant Skid Fabrication | Mon Sep 14 08:00:00 IDT 2020 | Mon Dec 07 17:00:00 IST 2020 | Tue Aug 25 00:00:00 IDT 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
743 | TT_TASK | L&I approval process | Mon Sep 14 08:00:00 IDT 2020 | Tue Oct 13 17:00:00 IDT 2020 | Tue Aug 25 00:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 |  | COMPLETED
745 | TT_TASK | Water treatment delivery COLO-1 | Mon Dec 21 08:00:00 IST 2020 | Sun Dec 27 17:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
750 | TT_TASK | Submit and approve Shop drawings for UPM junstion box | Mon Oct 19 08:00:00 IDT 2020 | Sun Nov 08 17:00:00 IST 2020 | Fri Oct 09 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
751 | TT_TASK | Lead time for junction box | Mon Nov 02 08:00:00 IST 2020 | Sun Dec 13 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
752 | TT_TASK | Fabrication and Delivery of PEMB pentrations support steel | Mon Nov 09 08:00:00 IST 2020 | Fri Nov 13 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
756 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
757 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Tue Dec 15 00:00:00 IST 2020 |  | COMPLETED
758 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
760 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
761 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
762 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Feb 13 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
763 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
764 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Mar 05 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
765 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
768 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
769 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
770 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Feb 08 08:00:00 IST 2021 | Thu Feb 11 08:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
772 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
773 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
774 | TT_TASK | Install additional Cable bus (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
775 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
776 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Mar 02 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
777 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
780 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
781 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Tue Dec 15 00:00:00 IST 2020 |  | COMPLETED
782 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
784 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
785 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
786 | TT_TASK | Install additional Cable bus (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
787 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
788 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
789 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
792 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Dec 04 07:00:00 IST 2020 | Wed Dec 09 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
793 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
794 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
796 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
797 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
798 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 03 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
799 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
800 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Thu Mar 04 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
801 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
803 | TT_TASK | COLO-1 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon Mar 22 07:00:00 IST 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
804 | TT_TASK | COLO-1 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon Apr 05 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
805 | TT_TASK | COLO-1 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
806 | TT_TASK | COLO-1 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
810 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Sat Jan 02 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
811 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
812 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
814 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
815 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
816 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
817 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
818 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
819 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
822 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
823 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Thu Feb 11 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
824 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Mar 26 07:00:00 IDT 2021 | Mon Mar 29 17:00:00 IDT 2021 | Sat Feb 27 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
826 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
827 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
828 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
829 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
830 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
831 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
834 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
835 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
836 | TT_TASK | Install added DRB#3 Tray and conduit | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
838 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Sat Mar 27 00:00:00 IDT 2021 |  | COMPLETED
839 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 |  | COMPLETED
840 | TT_TASK | Install additional Cable bus (DRB#3) | Mon May 03 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
841 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
842 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue May 04 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
843 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
846 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
847 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Thu Feb 11 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
848 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 02 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
850 | TT_TASK | Install MER Supply duct | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
851 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri May 07 07:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
852 | TT_TASK | Install additional Cable bus (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
853 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue May 04 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
854 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
855 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 |  | COMPLETED
857 | TT_TASK | COLO-2 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Fri Apr 30 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
858 | TT_TASK | COLO-2 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
859 | TT_TASK | COLO-2 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 03 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
860 | TT_TASK | COLO-2 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
864 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
865 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
866 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
868 | TT_TASK | Install MER Supply duct | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
869 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
870 | TT_TASK | Install Roxtec block sealing and Install added tray cable (DRB#3) | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
871 | TT_TASK | Install additional Cable bus (DRB#3) | Tue May 18 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
872 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
873 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
876 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
877 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
878 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
880 | TT_TASK | Install MER Supply duct | Mon May 24 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
881 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
882 | TT_TASK | Install additional Cable bus (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
883 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 |  | COMPLETED
884 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Sat Aug 14 07:00:00 IDT 2021 | Sat Aug 14 17:00:00 IDT 2021 |  | COMPLETED
885 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Fri Sep 03 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Thu Aug 26 00:00:00 IDT 2021 |  | COMPLETED
888 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
889 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 |  | COMPLETED
890 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
892 | TT_TASK | Install MER Supply duct | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
893 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 |  | COMPLETED
894 | TT_TASK | Install additional Cable bus (DRB#3) | Sat May 29 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
895 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
896 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 |  | COMPLETED
897 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Mon Aug 09 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
900 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
901 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
902 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
904 | TT_TASK | Install MER Supply duct | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
905 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
906 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jun 05 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
907 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
908 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
909 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
911 | TT_TASK | COLO-3 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
912 | TT_TASK | COLO-3 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 |  | COMPLETED
913 | TT_TASK | COLO-3 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
914 | TT_TASK | COLO-3 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
918 | TT_TASK | Sure steel - PEMB MER penetration framing | Thu Feb 11 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
919 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
920 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
922 | TT_TASK | Install MER Supply duct | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
923 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Thu Jul 08 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
924 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
925 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
926 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
927 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
930 | TT_TASK | Sure steel - PEMB MER penetration framing | Tue Feb 16 07:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
931 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
932 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
934 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
935 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
936 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
937 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Fri Sep 03 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 |  |  | 400.0 | NOT_STARTED
938 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
939 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Sat Oct 02 07:00:00 IDT 2021 | Fri Oct 08 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
942 | TT_TASK | Sure steel - PEMB MER penetration framing | Thu Feb 11 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
943 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
944 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
946 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
947 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Thu Jul 08 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 |  | COMPLETED
948 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Jul 28 00:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 |  | COMPLETED
949 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
950 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
951 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
954 | TT_TASK | Sure steel - PEMB MER penetration framing | Tue Feb 16 07:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
955 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
956 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 00:00:00 IDT 2021 |  | COMPLETED
958 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
959 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
960 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
961 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
962 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
963 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
965 | TT_TASK | COLO-4 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Thu Sep 09 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
966 | TT_TASK | COLO-4 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Wed Aug 18 00:00:00 IDT 2021 |  |  | IN_PROGRESS
967 | TT_TASK | COLO-4 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
968 | TT_TASK | COLO-4 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
970 | TT_TASK | Site Shut Down - 9/9/2020 | Mon Sep 14 07:00:00 IDT 2020 | Mon Sep 14 17:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 |  | COMPLETED
971 | TT_TASK | Site Shut Down - 9/10/2020 | Tue Sep 15 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Thu Sep 10 00:00:00 IDT 2020 | Thu Sep 10 00:00:00 IDT 2020 |  | COMPLETED
972 | TT_TASK | Site Shut Down - 9/11/2020 | Wed Sep 16 07:00:00 IDT 2020 | Wed Sep 16 17:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
973 | TT_TASK | Site Shut Down - 9/12/2020 | Thu Sep 17 07:00:00 IDT 2020 | Thu Sep 17 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
974 | TT_TASK | Site Shut Down - 9/14/2020 | Mon Sep 28 07:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 |  | COMPLETED
975 | TT_TASK | Site Shut Down - 9/15/2020 | Tue Sep 29 07:00:00 IDT 2020 | Tue Sep 29 17:00:00 IDT 2020 | Tue Sep 15 00:00:00 IDT 2020 | Tue Sep 15 00:00:00 IDT 2020 |  | COMPLETED
976 | TT_TASK | Site Shut Down - 9/16/2020 | Wed Sep 30 07:00:00 IDT 2020 | Wed Sep 30 17:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 |  | COMPLETED
979 | TT_TASK | Complete Remaining IWW piping to tie-in point | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 29 17:00:00 IST 2020 | Mon Sep 21 00:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
980 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
982 | TT_TASK | Complete Remaining Sanitary piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
983 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
985 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
986 | TT_TASK | Complete Remaining Fire Main piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
988 | TT_TASK | Complete Remaining ITW piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
989 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
991 | TT_TASK | Complete Remaining Telecom Duct Back (excluding Tie-in) | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
992 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
995 | TT_TASK | Delay in COLO-1- Cell-1 MER Delivery (Duration = COLO1 Cell-1 PSR(11/6/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sat Jan 30 17:00:00 IST 2021 | Fri Nov 06 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
996 | TT_TASK | Delay in COLO-1- Cell-2 MER Delivery (Duration = COLO1 Cell-2 PSR(11/13/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Fri Jan 29 17:00:00 IST 2021 | Fri Nov 13 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
997 | TT_TASK | Delay in COLO-1- Cell-3 MER Delivery (Duration = COLO1 Cell-3 PSR(11/20/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Feb 04 17:00:00 IST 2021 | Fri Nov 20 00:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 |  | COMPLETED
998 | TT_TASK | Delay in COLO-1- Cell-4 MER Delivery (Duration = COLO1 Cell-4 PSR(11/30/20) to MSFT delivery) | Mon Feb 01 08:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1000 | TT_TASK | Delay in COLO-2- Cell-1 MER Delivery (Duration = Colo1 Cell-1 PSR(12/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Feb 11 10:00:00 IST 2021 | Tue Dec 15 00:00:00 IST 2020 | Wed Feb 03 00:00:00 IST 2021 |  | COMPLETED
1001 | TT_TASK | Delay in COLO-2- Cell-2 MER Delivery (Duration = COLO 2 Cell-2 PSR(12/22/20) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1002 | TT_TASK | Delay in COLO-2- Cell-3 MER Delivery (Duration = COLO 2- Cell-3 PSR(12/28/20) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1003 | TT_TASK | Delay in COLO-2- Cell-4 MER Delivery (Duration = COLO 2- Cell-4 PSR(1/5/21) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Jan 05 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1005 | TT_TASK | Delay in COLO-3- Cell-1 MER Delivery (Duration = COLO-3 Cell-1 PSR(1/29/21) to MSFT delivery) | Sun Jan 31 08:00:00 IST 2021 | Sat Apr 03 17:00:00 IDT 2021 | Fri Jan 29 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1006 | TT_TASK | Delay in COLO-3- Cell-2 MER Delivery (Duration = COLO-3 Cell-2 PSR(2/5/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 05 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1007 | TT_TASK | Delay in COLO-3 Cell-3 MER Delivery (Duration = COLO-3 Cell-3 PSR(2/12/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Feb 12 00:00:00 IST 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1008 | TT_TASK | Delay in COLO-3 Cell-4 MER Delivery (Duration = COLO-3 Cell-4 PSR(2/19/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Thu Apr 22 00:00:00 IDT 2021 |  | COMPLETED
1010 | TT_TASK | Delay in COLO-4- Cell-1 MER Delivery (Duration= COLO-4 Cell-1 PSR(3/12/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Mar 12 00:00:00 IST 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
1011 | TT_TASK | Delay in COLO-4- Cell-2 MER Delivery (Duration = COLO-4 Cell-2 PSR(3/19/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1012 | TT_TASK | Delay in COLO-4- Cell-3 MER Delivery (Duration = COLO-4 Cell-3 PSR(3/26/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1013 | TT_TASK | Delay in COLO-4- Cell-4 MER Delivery (Duration = COLO-4 Cell-4 PSR(4/2/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 | Sun May 09 00:00:00 IDT 2021 |  | COMPLETED
1015 | TT_TASK | Wire Mesh Procurement | Mon Nov 16 08:00:00 IST 2020 | Wed Dec 23 12:00:00 IST 2020 | Thu Sep 24 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
1016 | TT_TASK | Wire Mesh Submittal Approval | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Wed Sep 16 00:00:00 IDT 2020 | Wed Sep 23 00:00:00 IDT 2020 |  | COMPLETED
1017 | TT_TASK | Wire Mesh Procurement Delay | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Sat Oct 24 00:00:00 IDT 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1019 | TT_TASK | Complete Remaining Telecom Duct Back tie-in Install to MWH02 | Mon Dec 21 07:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1020 | TT_TASK | Clayco waiting on MSOW Approval | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Tue Dec 01 00:00:00 IST 2020 |  | COMPLETED
1021 | TT_TASK | Clayco MSOW Submited for approval | Mon Nov 16 07:00:00 IST 2020 | Tue Nov 17 17:00:00 IST 2020 | Fri Oct 16 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
1022 | TT_TASK | MSFT Stand down/ Additional Hydro excavation | Mon Dec 21 07:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
1024 | TT_TASK | Delay in UMS delivery (Duration = (9/19) to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Thu Nov 19 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
1027 | TT_TASK | Delay In COLO-1 Cell-1 Generator (Duration= COLO-1 Cell-1 PSR(9/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Tue Jan 19 17:00:00 IST 2021 | Tue Sep 15 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1028 | TT_TASK | Delay In COLO-1 Cell-2 Generator (Duration= COLO-1 Cell-2 PSR(9/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sat Feb 06 17:00:00 IST 2021 | Tue Sep 15 00:00:00 IDT 2020 | Mon Nov 02 00:00:00 IST 2020 |  | COMPLETED
1029 | TT_TASK | Delay In COLO-1 Cell-4 Generator (Duration= COLO-1 Cell-4 PSR(9/29/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Sep 29 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1030 | TT_TASK | Delay In COLO-1 Cell-3 Generator (Duration= COLO-1 Cell-3 PSR(9/29/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Wed Feb 03 17:00:00 IST 2021 | Tue Sep 29 00:00:00 IDT 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1032 | TT_TASK | Delay In COLO-2 Cell-1 Generator (Duration= COLO-2 Cell-1 PSR(10/12/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sun Mar 07 17:00:00 IST 2021 | Mon Oct 12 00:00:00 IDT 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1033 | TT_TASK | Delay In COLO-2 Cell-2 Generator (Duration= COLO-2 Cell-2 PSR(11/6/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sun Feb 21 17:00:00 IST 2021 | Fri Nov 06 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
1034 | TT_TASK | Delay In COLO-2 Cell-4 Generator (Duration= COLO-2 Cell-4 PSR(11/21/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Fri Feb 19 17:00:00 IST 2021 | Sat Nov 21 00:00:00 IST 2020 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
1035 | TT_TASK | Delay In COLO-2 Cell-3 Generator (Duration= COLO-2 Cell-3 PSR(10/22/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Mar 18 17:00:00 IST 2021 | Thu Oct 22 00:00:00 IDT 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1037 | TT_TASK | 6.1.39.1- COLO-3 CEll-1 GEN Belly tank Failed pressure test | Mon Mar 15 07:00:00 IST 2021 | Fri Apr 09 17:00:00 IDT 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
1038 | TT_TASK | 6.1.39.2- COLO-3 Cell-1 Replace Belly Tank and Set GEN | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1039 | TT_TASK | Delay In COLO-3 Cell-1 Generator (Duration= COLO-3 Cell-1 PSR(10/12/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Sat May 08 17:00:00 IDT 2021 | Mon Nov 09 00:00:00 IST 2020 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1040 | TT_TASK | Delay In COLO-3 Cell-2 Generator (Duration= COLO-3 Cell-2 PSR(11/6/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Tue Mar 30 17:00:00 IDT 2021 | Sat Nov 21 00:00:00 IST 2020 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
1041 | TT_TASK | Delay In COLO-3 Cell-4 Generator (Duration= COLO-3 Cell-4 PSR(11/21/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Mar 18 17:00:00 IST 2021 | Wed Dec 09 00:00:00 IST 2020 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
1042 | TT_TASK | Delay In COLO-3 Cell-3 Generator (Duration= COLO-3 Cell-3 PSR(10/22/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Apr 29 17:00:00 IDT 2021 | Thu Nov 05 00:00:00 IST 2020 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1044 | TT_TASK | Delay In COLO-4 Cell-1 Generator (Duration= COLO-4 Cell-1 PSR(10/12/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Sat Jun 05 17:00:00 IDT 2021 | Mon Nov 09 00:00:00 IST 2020 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
1045 | TT_TASK | Delay In COLO-4 Cell-2 Generator (Duration= COLO-4 Cell-2 PSR(11/6/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Apr 01 17:00:00 IDT 2021 | Wed Dec 09 00:00:00 IST 2020 | Thu Mar 11 00:00:00 IST 2021 |  | COMPLETED
1046 | TT_TASK | Delay In COLO-4 Cell-4 Generator (Duration= COLO-4 Cell-4 PSR(11/21/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Wed Apr 14 17:00:00 IDT 2021 | Mon Nov 30 00:00:00 IST 2020 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
1047 | TT_TASK | Delay In COLO-4 Cell-3 Generator (Duration= COLO-4 Cell-3 PSR(10/22/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Tue May 11 17:00:00 IDT 2021 | Fri Nov 20 00:00:00 IST 2020 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1050 | TT_TASK | COLO1 CELL1 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1051 | TT_TASK | COLO1 CELL3 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
1052 | TT_TASK | COLO1 CELL2 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1053 | TT_TASK | COLO1 CELL4 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
1058 | TT_TASK | COLO-1 Cell-1 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1059 | TT_TASK | COLO1 CELL1 Interior MER conduit installation utility side | Fri Mar 05 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1060 | TT_TASK | COLO-1 Cell-1 Interior MER conduit installation building side Complete March1st (MER discovery Corrections & Signoff) | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1063 | TT_TASK | COLO-1 CELL3 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1064 | TT_TASK | COLO1 CELL3 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1065 | TT_TASK | COLO-1 CELL3 Interior MER conduit installation building side | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
1068 | TT_TASK | COLO-1 CELL2 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1069 | TT_TASK | COLO1 CELL2 Interior MER conduit installation utility side | Sat Mar 06 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1070 | TT_TASK | COLO-1 CELL2 Interior MER conduit installation building side | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1073 | TT_TASK | COLO-1 CELL4 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1074 | TT_TASK | COLO1 CELL4 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1075 | TT_TASK | COLO-1 CELL4 Interior MER conduit installation building side | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
1079 | TT_TASK | COLO-2 Cell-1 Rearrange Roxtec blocks per coordination layout | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1080 | TT_TASK | COLO2 CELL1 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1081 | TT_TASK | COLO-2 Cell-1 Interior MER conduit installation building side | Mon Apr 05 07:00:00 IDT 2021 | Mon Apr 19 17:00:00 IDT 2021 | Fri Mar 05 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1089 | TT_TASK | COLO-1 Cell-1 MER Flex Conduit fixes | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1090 | TT_TASK | COLO-1 Cell-3 MER Flex Conduit fixes | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1091 | TT_TASK | COLO-1 Cell-2 MER Flex Conduit fixes | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1092 | TT_TASK | COLO-1 Cell-4 MER Flex Conduit fixes | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1095 | TT_TASK | Safety Stop work due to failed Starline Hangers | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 01 07:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
1096 | TT_TASK | Lead time for replacement hangers from Starline | Mon Feb 01 08:00:00 IST 2021 | Sun Feb 07 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
1097 | TT_TASK | COLO-1 Cell-1 Remove/ Replace busway & hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1098 | TT_TASK | COLO-1 Cell-3 Remove/ Replace busway & hangers | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1099 | TT_TASK | COLO-1 Cell-2 Remove/ Replace busway & hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1100 | TT_TASK | COLO-1 Cell-4 Remove/ Replace busway & hangers | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1101 | TT_TASK | Determined Startline hanger Design Issue & Approve replacement hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
1102 | TT_TASK | COLO-2 Cell-1 Remove/ Replace busway & hangers | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1103 | TT_TASK | COLO-2 Cell-2 Remove/ Replace busway & hangers | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1105 | TT_TASK | Lead time for missing Admin Gen Bussing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 |  | COMPLETED
1106 | TT_TASK | Admin Gen Bussing Install | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1107 | TT_TASK | Awaiting DCE approval of Non NEMA standard Lugs | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1108 | TT_TASK | Awaiting Phase conductor lugs from NC power as per RFI#412 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1109 | TT_TASK | 6.1.41 - Incorrect Lugs for Admin Gen Main Bussing | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1112 | TT_TASK | COLO-1 Cell-4 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
1113 | TT_TASK | COLO-1 Cell-3 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Thu Mar 11 00:00:00 IST 2021 |  | COMPLETED
1114 | TT_TASK | COLO-1 Cell-2 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1115 | TT_TASK | COLO-1 Cell-1 SE Install UPS batteries in cabinet | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1117 | TT_TASK | COLO-2 Cell-1 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
1118 | TT_TASK | COLO-2 Cell-2 SE Install UPS batteries in cabinet | Fri Apr 30 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
1119 | TT_TASK | COLO-2 Cell-3 SE Install UPS batteries in cabinet | Sat May 08 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1120 | TT_TASK | COLO-2 Cell-4 SE Install UPS batteries in cabinet | Sat May 15 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
1122 | TT_TASK | COLO-3 Cell-1 SE Install UPS batteries in cabinet | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1123 | TT_TASK | COLO-3 Cell-2 SE Install UPS batteries in cabinet | Tue May 25 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1124 | TT_TASK | COLO-3 Cell-3 SE Install UPS batteries in cabinet | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1125 | TT_TASK | COLO-3 Cell-4 SE Install UPS batteries in cabinet | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1127 | TT_TASK | COLO-4 Cell-1 SE Install UPS batteries in cabinet | Tue Sep 14 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1128 | TT_TASK | COLO-4 Cell-2 SE Install UPS batteries in cabinet | Wed Sep 29 07:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  | 320.0 | IN_PROGRESS
1129 | TT_TASK | COLO-4 Cell-3 SE Install UPS batteries in cabinet | Tue Sep 07 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
1130 | TT_TASK | COLO-4 Cell-4 SE Install UPS batteries in cabinet | Tue Sep 21 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
1132 | TT_TASK | COLO-2 CEll-2 Awaiting SE Revised tool Come along for MER Lift & Set | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
1133 | TT_TASK | COLO-2 CEll-3 Awaiting SE Revised tool Come along for MER Lift & Set | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1134 | TT_TASK | MER shipping split connection Safety Standown & RCA Review | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1137 | TT_TASK | COLO-2 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1138 | TT_TASK | RFI#432 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
1139 | TT_TASK | Lead time for tube steel | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
1140 | TT_TASK | COLO-2 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1141 | TT_TASK | COLO-2 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Thu Apr 01 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1142 | TT_TASK | COLO-2 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1144 | TT_TASK | COLO-3 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Fri May 07 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 |  | COMPLETED
1145 | TT_TASK | COLO-3 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Wed May 19 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed May 19 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 |  | COMPLETED
1146 | TT_TASK | COLO-3 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Thu May 13 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Thu May 13 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 |  | COMPLETED
1147 | TT_TASK | COLO-3 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Wed May 26 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Wed May 26 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 |  | COMPLETED
1149 | TT_TASK | COLO-4 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1150 | TT_TASK | COLO-4 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1151 | TT_TASK | COLO-4 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1152 | TT_TASK | COLO-4 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Mon Jun 14 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1154 | TT_TASK | All Construction activities -Safety Standown due to Admin Gen unplanned Energization | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
1156 | TT_TASK | COLO-1 Cell-1 Field Modification of tray | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1157 | TT_TASK | COLO-1 Cell-2 Field Modification of tray | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Jan 21 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1160 | TT_TASK | #3. Snow- 1/27/2021(one full day) | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 |  | COMPLETED
1161 | TT_TASK | #4. Extreme Heat - 6/28/21- 7/2/21(Effecting COLO-4 Yard work) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
1162 | TT_TASK | #5 Extreme heat -production loss in Yards 7/1/21 through 7/14/21 (11 half days of loss) | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 09 00:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
1163 | TT_TASK | #6 Extreme heat - Production loss in Yards 7/15/21 through 7/31/21 (3 half days) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
1164 | TT_TASK | #1. Rain And High Winds- 10/13/2020(half day only) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Tue Oct 13 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1165 | TT_TASK | #2. Snow -12/30/20 (one full day) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Wed Dec 30 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
1168 | TT_TASK | COLO-1 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Mon Jan 11 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
1169 | TT_TASK | COLO-1 CELL-3 WA State L&I onsite inspection & Approval to Connect to MER | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1170 | TT_TASK | COLO-1 CELL-2 WA State L&I onsite inspection & Approval to Connect to MER | Sat Jan 23 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1171 | TT_TASK | COLO-1 CELL-4 WA State L&I onsite inspection & Approval to Connect to MER | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1173 | TT_TASK | COLO-2 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Fri Mar 12 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1174 | TT_TASK | COLO-2 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Tue Mar 23 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1175 | TT_TASK | COLO-2 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
1176 | TT_TASK | COLO-2 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Fri Apr 09 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1178 | TT_TASK | COLO-3 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Sat May 08 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1179 | TT_TASK | COLO-3 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Fri May 14 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1180 | TT_TASK | COLO-3 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1181 | TT_TASK | COLO-3 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1183 | TT_TASK | COLO-4 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 |  | COMPLETED
1184 | TT_TASK | COLO-4 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Sat Jun 19 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1185 | TT_TASK | COLO-4 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
1186 | TT_TASK | COLO-4 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 |  | COMPLETED
1189 | TT_TASK | 6.1.36 Rework for Addtional circuits for UMS URS Battery charger feed upsize | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1190 | TT_TASK | 6.1.34.1 COLO-1 Cell-1 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1191 | TT_TASK | 6.1.34.2 COLO-1 Cell-2 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1192 | TT_TASK | 6.1.34.3 COLO-1 Cell-3 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 |  | COMPLETED
1193 | TT_TASK | 6.1.34.4 COLO-1 Cell-4 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 |  | COMPLETED
1194 | TT_TASK | 6.1.01.0 Awaiting MER 10A HRG's (lead time= 8 weeks from 2/2/2021) | Mon Mar 01 07:00:00 IST 2021 | Mon Apr 12 17:00:00 IDT 2021 | Tue Feb 02 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
1195 | TT_TASK | 6.1.09 Awaiting Rev-D for Coordination study (DRB3/SCCS/ Submittal Breaker verification) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1196 | TT_TASK | 6.1.26.1 L2/L3 Scripts SE MER overall Script | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
1197 | TT_TASK | 6.1.33 URS UMS Ground Buss hole Pattern | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1198 | TT_TASK | 6.1.35 UPS battery IR Scanning | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1199 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-1 Cell-1 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1200 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-1 Cell-4 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1201 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-1 Cell-3 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1202 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-1 Cell-2 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1203 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-2 Cell-1 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1204 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-2 Cell-2 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1205 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-2 Cell-3 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1206 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-2 Cell-4 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue Jul 13 00:00:00 IDT 2021 | Mon Jul 19 00:00:00 IDT 2021 |  | COMPLETED
1207 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-3 Cell-1 | Tue Aug 31 07:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
1208 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-3 Cell-4 | Tue Sep 07 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  |  | 10.0 | NOT_STARTED
1209 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-3 Cell-3 | Tue Sep 07 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  |  | 10.0 | NOT_STARTED
1210 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-3 Cell-2 | Thu Sep 09 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1211 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-4 Cell-1 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1212 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-4 Cell-4 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1213 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-4 Cell-3 | Mon Oct 18 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1214 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-4 Cell-2 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1216 | TT_TASK | 6.1.37- 6.2.01- Ground Fault setting on COLO-2 Gen MCB01 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Wed Apr 28 17:00:00 IDT 2021 |  | COMPLETED
1218 | TT_TASK | 6.1.38 PDU MCB01 LOTO Provisions | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1220 | TT_TASK | 6.1.11 Awaiting BAS Backplanes from Siemens to VECA for Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
1221 | TT_TASK | 6.1.26.2 L2/L3 Scripts Siemens BAS SAT Scripts | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1222 | TT_TASK | 6.1.11 Awaiting Liftstation #3 BAS Backplanes from Siemens to VECA for Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1223 | TT_TASK | 6.1.11 Liftstation #3 BAS Install / Pull wire / term Backplanes | Mon May 17 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 |  | COMPLETED
1226 | TT_TASK | COLO-2 Cell-1 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Dec 29 00:00:00 IST 2020 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1227 | TT_TASK | COLO-2 Cell-2 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sun Jan 10 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1228 | TT_TASK | COLO-2 Cell-3 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Jan 20 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1229 | TT_TASK | COLO-2 Cell-4 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sat Jan 23 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1231 | TT_TASK | COLO-3 Cell-1 Install Missing Raceway & Bussing within generator | Mon Apr 26 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1232 | TT_TASK | COLO-3 Cell-2 Install Missing Raceway & Bussing within generator | Thu Apr 29 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1233 | TT_TASK | COLO-3 Cell-3 Install Missing Raceway & Bussing within generator | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
1234 | TT_TASK | COLO-3 Cell-4 Install Missing Raceway & Bussing within generator | Tue May 04 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1236 | TT_TASK | COLO-4 Cell-1 Install Missing Raceway & Bussing within generator | Tue May 25 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
1237 | TT_TASK | COLO-4 Cell-2 Install Missing Raceway & Bussing within generator | Tue May 11 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1238 | TT_TASK | COLO-4 Cell-3 Install Missing Raceway & Bussing within generator | Thu May 20 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1239 | TT_TASK | COLO-4 Cell-4 Install Missing Raceway & Bussing within generator | Mon May 17 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
1242 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1243 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 2weeks- fab and ship | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Mon Apr 05 00:00:00 IDT 2021 |  | COMPLETED
1244 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 1 week to install | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
1245 | TT_TASK | 6.1.44- MER Battery Monitoring Software Â– Constraint to EPMS checkouts/Point Â– Point(needed by 4/23) | Mon Mar 15 07:00:00 IST 2021 | Mon Jun 07 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Aug 07 07:00:00 IDT 2021 |  | COMPLETED
1246 | TT_TASK | 6.1.46- Site UPM Inspections | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
1247 | TT_TASK | 6.1.47- COLO-1 Cell-2 UPS01- Factory Test thermal event | Mon Mar 15 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
1249 | TT_TASK | 6.1.40- 480V house power to Gen Enclousure is Fed OH vs UG | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1254 | TT_TASK | Downtime awaiting solution for safety space constraint | Mon Apr 26 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1256 | TT_TASK | NOPC-18 Remove COLO-1 Cell-1 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1257 | TT_TASK | Rubicon MSB inspection complete (ready for transformer reinstall) | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Mon Apr 26 07:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1258 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-1 transformer | Tue May 25 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1260 | TT_TASK | NOPC-18 Remove COLO-1 Cell-2 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
1261 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1262 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-2 transformer | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1264 | TT_TASK | NOPC-18 Remove COLO-1 Cell-3 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 |  | COMPLETED
1265 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1266 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-3 transformer | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1268 | TT_TASK | NOPC-18 Remove COLO-1 Cell-4 transformer | Mon May 17 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1269 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1270 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-4 transformer | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1273 | TT_TASK | NOPC-18 Remove COLO-2 Cell-1 transformer | Tue Jun 01 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue Jun 08 00:00:00 IDT 2021 |  | COMPLETED
1274 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-1 transformer | Thu Jul 22 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1276 | TT_TASK | NOPC-18 Remove COLO-2 Cell-2 transformer | Wed Jun 02 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
1277 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-2 transformer | Fri Jul 23 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
1279 | TT_TASK | NOPC-18 Remove COLO-2 Cell-3 transformer | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 |  | COMPLETED
1280 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-3 transformer | Thu Jul 29 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1282 | TT_TASK | NOPC-18 Remove COLO-2 Cell-4 transformer | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1283 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-4 transformer | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Jul 09 00:00:00 IDT 2021 | Mon Jul 12 00:00:00 IDT 2021 |  | COMPLETED
1286 | TT_TASK | NOPC-18 Remove COLO-3 Cell-1 transformer | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
1287 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-1 transformer | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 22 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1289 | TT_TASK | NOPC-18 Remove COLO-3 Cell-2 transformer | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jul 24 07:00:00 IDT 2021 | Sat Jul 24 17:00:00 IDT 2021 |  | COMPLETED
1290 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-2 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
1292 | TT_TASK | NOPC-18 Remove COLO-3 Cell-3 transformer | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Thu Aug 19 07:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1293 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-3 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1295 | TT_TASK | NOPC-18 Remove COLO-3 Cell-4 transformer | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1296 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-4 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1299 | TT_TASK | NOPC-18 Remove COLO-4 Cell-1 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1300 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-1 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1302 | TT_TASK | NOPC-18 Remove COLO-4 Cell-2 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1303 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-2 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1305 | TT_TASK | NOPC-18 Remove COLO-4 Cell-3 transformer | Wed Sep 29 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1306 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-3 transformer | Sat Oct 09 07:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1308 | TT_TASK | NOPC-18 Remove COLO-4 Cell-4 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1309 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-4 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1311 | TT_TASK | PDU termination crew downtime due to COVID-19 | Sat Apr 24 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Sat Apr 24 07:00:00 IDT 2021 |  | COMPLETED
1314 | TT_TASK | 6.2.03- Replace ADP01 faulty trip units | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1315 | TT_TASK | 6.1.51-COLO-1 Cell-1,2 Factory conductors not terminated per drawings | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1316 | TT_TASK | 6.1.49 - COLO-1 Cell-1 Awaiting Ground Lug solution, procurement, installation of labelling ATS 01-06 | Fri Apr 30 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
1317 | TT_TASK | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
1318 | TT_TASK | 6.1.53-COLO-1 Cell-1,2 UPS01, PNL01 awaiting missing breakers | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1319 | TT_TASK | 6.1.53-COLO-1 Cell-1,2,3,4 UPS01, PNL01 Install/ term Missing breakers | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1320 | TT_TASK | 6.1.59 (6.1.51 carryover) -COLO-1 Cell-1,2 Factory conductors exertherm corrections | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
1321 | TT_TASK | 6.1.50- SCCS Revision#10 (RFI-540) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1325 | TT_TASK | 6.1.54- TCM Awaiting Admin Siemens Break tank parts | Mon May 17 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1326 | TT_TASK | 6.1.54- Install Breaktank parts | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1328 | TT_TASK | 6.2.03- Replace Damaged UPM in COLO-4 Cell-4 | Thu May 06 07:00:00 IDT 2021 | Sat May 08 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1330 | TT_TASK | 6.1.55-COLO-1 - FC Factoy Re-wire (RFI-502) | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1331 | TT_TASK | 6.1.55-COLO-2 - FC Factoy Re-wire (RFI-502) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1332 | TT_TASK | 6.1.55-COLO-3 - FC Factoy Re-wire (RFI-502) | Sat Jun 05 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1333 | TT_TASK | 6.1.55-COLO-4 - FC Factoy Re-wire (RFI-502) | Thu Jun 10 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1335 | TT_TASK | 6.1.57 -Awaiting revised coordination study #9 | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
1336 | TT_TASK | Reprint revised panel 3,4 Arc flash labels | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1337 | TT_TASK | Print new DC Arc flash labels for Admin ELP | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1340 | TT_TASK | 6.1.58-RFI-528- COLO-1 - SF/RF Circuitry & terminal block rework | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
1341 | TT_TASK | 6.1.63- COLO1-UPS01-PNL01 Compass Issues Constraining L3Â’s | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
1342 | TT_TASK | 6.1.56 - COLO-1 Awaiting MSB/ADP Ground Lug replacements, Installation of labelling | Fri Apr 30 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
1349 | TT_TASK | All trades stand down | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
1350 | TT_TASK | Veca standown | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
1353 | TT_TASK | COLO-1 Cell-1 MER-UPS Battery Disconnect modifications rework | Wed Jun 16 07:00:00 IDT 2021 | Sat Jun 19 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1354 | TT_TASK | COLO-1 Cell-2 MER-UPS Battery Disconnect modifications rework | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1355 | TT_TASK | COLO-1 Cell-3 MER-UPS Battery Disconnect modifications rework | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
1356 | TT_TASK | COLO-1 Cell-4 MER-UPS Battery Disconnect modifications rework | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
1357 | TT_TASK | RFI-548 COLO MSB to UPS Battery disconnect solution approval | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1358 | TT_TASK | ADMIN-UPS Battery Disconnect modifications rework | Wed Jun 16 07:00:00 IDT 2021 | Sat Jun 19 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1359 | TT_TASK | RFI-552 Admin MSB to UPS Battery disconnect solution approval | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
1361 | TT_TASK | COLO-2 Cell-2 MER-UPS Battery Disconnect modifications rework | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 |  | COMPLETED
1362 | TT_TASK | COLO-2 Cell-1 MER-UPS Battery Disconnect modifications rework | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  | COMPLETED
1363 | TT_TASK | COLO-2 Cell-3 MER-UPS Battery Disconnect modifications rework | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  | COMPLETED
1364 | TT_TASK | COLO-2 Cell-4 MER-UPS Battery Disconnect modifications rework | Fri Jul 02 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 23 07:00:00 IDT 2021 |  | COMPLETED
1366 | TT_TASK | COLO-3 Cell-1 MER-UPS Battery Disconnect modifications rework | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 |  | COMPLETED
1367 | TT_TASK | COLO-3 Cell-2 MER-UPS Battery Disconnect modifications rework | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1368 | TT_TASK | COLO-3 Cell-3 MER-UPS Battery Disconnect modifications rework | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
1369 | TT_TASK | COLO-3 Cell-4 MER-UPS Battery Disconnect modifications rework | Sat Sep 11 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Mon Aug 16 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1371 | TT_TASK | COLO-4 Cell-1 MER-UPS Battery Disconnect modifications rework | Thu Sep 16 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
1372 | TT_TASK | COLO-4 Cell-2 MER-UPS Battery Disconnect modifications rework | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
1373 | TT_TASK | COLO-4 Cell-3 MER-UPS Battery Disconnect modifications rework | Mon Sep 27 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1374 | TT_TASK | COLO-4 Cell-4 MER-UPS Battery Disconnect modifications rework | Fri Sep 03 07:00:00 IDT 2021 | Thu Sep 09 17:00:00 IDT 2021 |  |  | 270.0 | NOT_STARTED
1377 | TT_TASK | COLO-3 Cell-3 Remove inaccessible tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 |  | COMPLETED
1378 | TT_TASK | COLO-3 CEll-3 Reinstall tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
1379 | TT_TASK | COLO-3 Cell-4 Remove inaccessible tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Sat Jun 12 00:00:00 IDT 2021 |  | COMPLETED
1380 | TT_TASK | COLO-3 Cell-4 Reinstall tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1381 | TT_TASK | COLO-4 Cell-1 Remove inaccessible tray in MER | Mon Jul 12 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Sat Jun 12 00:00:00 IDT 2021 |  | COMPLETED
1382 | TT_TASK | COLO-4 Cell-1 Reinstall tray in MER | Tue Aug 03 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
1383 | TT_TASK | COLO-4 Cell-2 Remove inaccessible tray in MER | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
1384 | TT_TASK | COLO-4 Cell-2 Reinstall tray in MER | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1385 | TT_TASK | COLO-4 Cell-3 Remove inaccessible tray in MER | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Thu Jul 15 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
1386 | TT_TASK | COLO-4 Cell-3 Reinstall tray in MER | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
1387 | TT_TASK | COLO-4 Cell-4 Remove inaccessible tray in MER4 | Wed Aug 04 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
1388 | TT_TASK | COLO-4 Cell-4 Reinstall tray in MER | Fri Sep 03 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Mon Aug 09 07:00:00 IDT 2021 | Thu Aug 12 00:00:00 IDT 2021 |  | COMPLETED
1389 | TT_TASK | COLO-3 Cell-1 Remove inaccessible tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
1390 | TT_TASK | COLO-3 CEll-1 Reinstall tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 |  | COMPLETED
1391 | TT_TASK | COLO-3 Cell-2 Remove inaccessible tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1392 | TT_TASK | COLO-3 Cell-2 Reinstall tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1395 | TT_TASK | COLO-3 Cell-3 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 14 00:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1397 | TT_TASK | COLO-4 Cell-1 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Fri Jul 23 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1398 | TT_TASK | COLO-4 Cell-2 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
1399 | TT_TASK | COLO-4 Cell-3 Conduit rework | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 |  | COMPLETED
1400 | TT_TASK | COLO-4 Cell-4 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1404 | TT_TASK | 6.1-88 COLO-1 MER awaiting updated UPS L3 test script approval | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 31 07:00:00 IDT 2021 |  | COMPLETED
1405 | TT_TASK | 6.1-89 RFI574- COLO-1 Relocating MSB EPMS device to different cabinet | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1406 | TT_TASK | 6.1-92 COLO-1 SF/ RF startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
1407 | TT_TASK | 6.1-93 COLO-1 HVAC minisplits startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1409 | TT_TASK | 6.2-08 COLO-2 Cell- 1,2 MER equipment Phenolic labelling | Wed Jul 14 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
1410 | TT_TASK | 6.2-08 COLO-2 Cell- 3,4 MER equipment Phenolic labelling | Wed Jul 14 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Mon Aug 02 00:00:00 IDT 2021 |  | COMPLETED
1411 | TT_TASK | 6.2-12 COLO-2 All Cells- Factory connection Torque verification | Wed Jul 14 07:00:00 IDT 2021 | Wed Jul 21 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
1413 | TT_TASK | 6.1-95 COLO-1 ATS's L3 startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  | COMPLETED
1415 | TT_TASK | 6.1-96 COLO-1 PDU - EPMS L3 startup delay (vendor schedule availability) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Mon Aug 02 07:00:00 IDT 2021 |  | COMPLETED
1420 | TT_TASK | COLO-2 Cell-1 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1421 | TT_TASK | COLO-2 Cell-2 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1422 | TT_TASK | COLO-2 Cell-3 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1423 | TT_TASK | COLO-2 Cell-4 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 00:00:00 IDT 2021 |  | COMPLETED
1429 | TT_TASK | 6.1-98 Admin/COLO-1 ASCO EPMS Connectivity Issues | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1430 | TT_TASK | 6.1-88 Admin/ COLO-1 MER/ADMIN UPS L3 Testing (includes shutdown to move PQM's & PQM data post proccessing) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 31 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1431 | TT_TASK | 6.1-106 COLO-1 Cell-2 UPS01 Power module failure | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1433 | TT_TASK | COLO-2 Cell-1 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1434 | TT_TASK | COLO-2 Cell-3 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1435 | TT_TASK | COLO-2 Cell-4 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1437 | TT_TASK | COLO-3 Delay in SE uploading QC Checkilst | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Fri Aug 06 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1439 | TT_TASK | COLO-2 Cell-2 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1442 | TT_TASK | Mobilization | Mon Apr 27 07:00:00 IDT 2020 | Wed May 20 17:00:00 IDT 2020 | Mon Apr 06 00:00:00 IDT 2020 | Sat May 02 17:00:00 IDT 2020 |  | COMPLETED
1444 | TT_TASK | Establish Access Roads / Laydown / Craft Parking / Temp Utilities | Thu May 14 07:00:00 IDT 2020 | Fri Jun 19 17:00:00 IDT 2020 | Fri Apr 24 00:00:00 IDT 2020 | Sat May 23 00:00:00 IDT 2020 |  | COMPLETED
1446 | TT_TASK | Site Sanitary | Mon May 11 07:00:00 IDT 2020 | Fri Jul 24 17:00:00 IDT 2020 | Tue May 05 00:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 |  | COMPLETED
1447 | TT_TASK | Remaining Site Sanitary | Mon May 11 07:00:00 IDT 2020 | Fri Jul 24 17:00:00 IDT 2020 | Tue Aug 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
1448 | TT_TASK | IWW System | Tue May 26 07:00:00 IDT 2020 | Sat Aug 08 17:00:00 IDT 2020 | Mon May 18 00:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 |  | COMPLETED
1449 | TT_TASK | Remaining IWW System | Tue May 26 07:00:00 IDT 2020 | Sat Aug 08 17:00:00 IDT 2020 | Tue Aug 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
1450 | TT_TASK | Site Water / Fire Loop | Fri Jul 24 07:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1451 | TT_TASK | Site Storm | Mon Jun 29 07:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
1454 | TT_TASK | Telecom-Communications Site Loop/Ductbank | Mon Jun 29 08:00:00 IDT 2020 | Thu Oct 01 08:00:00 IDT 2020 | Thu Jun 25 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1455 | TT_TASK | Telecom-RNG Fiber Underground installation | Mon Feb 01 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
1456 | TT_TASK | Telecom-RNG Fiber CNR buildout | Mon Oct 05 07:00:00 IDT 2020 | Tue Dec 08 17:00:00 IST 2020 | Mon Oct 05 07:00:00 IDT 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
1461 | TT_TASK | Temp Power/ Telecom duct bank | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Thu Aug 27 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1462 | TT_TASK | Vault- set 1st Vault Along UMS Duct bank run | Thu Sep 03 07:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1463 | TT_TASK | Vault- Set 2nd vault Along UMS Duct Run near COLO-2 | Tue Sep 08 07:00:00 IDT 2020 | Thu Sep 10 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1464 | TT_TASK | Vault- Set vault along URS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1465 | TT_TASK | Vault- Set vault along UMS to JAZ run | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1466 | TT_TASK | Set URS Vault | Mon Nov 16 08:00:00 IST 2020 | Wed Nov 25 08:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1467 | TT_TASK | Set UMS vault | Wed Nov 25 08:00:00 IST 2020 | Tue Dec 08 08:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1469 | TT_TASK | Vault- Set North vault- Along UPM to Vault | Fri Oct 09 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1470 | TT_TASK | Vault - Set North Vault Along Vault to URS run | Fri Oct 23 07:00:00 IDT 2020 | Tue Oct 27 17:00:00 IST 2020 | Thu Aug 20 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1471 | TT_TASK | Vault - Set South Vault Along Vault to URS run | Sat Nov 07 07:00:00 IST 2020 | Tue Nov 10 17:00:00 IST 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1472 | TT_TASK | Vault - Set South Vault along UPM to Vault | Mon Nov 23 07:00:00 IST 2020 | Wed Nov 25 17:00:00 IST 2020 | Thu Aug 20 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1475 | TT_TASK | Duct bank- COLO-1 UPM to north vault | Mon Oct 19 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Fri Oct 02 00:00:00 IDT 2020 | Mon Oct 05 00:00:00 IDT 2020 |  | COMPLETED
1476 | TT_TASK | Duct bank- COLO-2 UPM to north Valut | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Mon Oct 05 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1477 | TT_TASK | Duct Bank- Building to URS - 1st Half | Sat Sep 26 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 07:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
1478 | TT_TASK | Duct Bank- Building to URS(upto horse shoe) - 2nd Half | Wed Sep 30 07:00:00 IDT 2020 | Thu Oct 08 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
1479 | TT_TASK | Duct Bank - JAZ to vault- UMS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Thu Oct 29 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1480 | TT_TASK | Duct Bank - Vault to Vault along UMS duct Run - horseshoe | Mon Oct 26 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
1481 | TT_TASK | Duct Bank - COLO-3 UPM to Vault UMS Run | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1482 | TT_TASK | Duct Bank - URS to vault - URS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1483 | TT_TASK | Duct Bank - Vault To JAZ - URS to JAZ run | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 09 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1484 | TT_TASK | Duct Bank - Vault to UMS- UMS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1485 | TT_TASK | Duct Bank - south vault (along UMS duct run) to UMS | Sat Nov 21 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1486 | TT_TASK | Duct Bank - COLO-4 UPM to UMS | Mon Nov 23 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
1488 | TT_TASK | Duct Bank - COLO1- UPM to UPM | Mon Aug 10 07:00:00 IDT 2020 | Thu Aug 13 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1489 | TT_TASK | Duct Bank - COLO2- UPM to UPM | Mon Aug 31 07:00:00 IDT 2020 | Thu Sep 03 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
1490 | TT_TASK | Duct Bank - North Crossover (URS to west Vault Run) | Mon Sep 14 07:00:00 IDT 2020 | Sat Sep 26 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
1491 | TT_TASK | Duct Bank - South Cross over (URS to west Vault Run) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
1492 | TT_TASK | Duct Bank - COLO-3 UPM to UPM | Fri Nov 06 07:00:00 IST 2020 | Tue Nov 10 17:00:00 IST 2020 | Sat Oct 10 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1493 | TT_TASK | Duct Bank - COLO-4 UPM to UPM | Wed Nov 25 07:00:00 IST 2020 | Wed Dec 02 17:00:00 IST 2020 | Sat Oct 10 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1495 | TT_TASK | Duct Bank Admin UPM to COLO-1 UPM | Thu Sep 24 07:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1496 | TT_TASK | Duct Back- Admin UPM to Vault | Fri Oct 23 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Mon Aug 24 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
1497 | TT_TASK | Duct Bank COLO-2 UPM to Vault | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Mon Sep 28 00:00:00 IDT 2020 | Thu Oct 01 00:00:00 IDT 2020 |  | COMPLETED
1498 | TT_TASK | Duct Bank - Building to North Vault URS run | Fri Oct 23 07:00:00 IDT 2020 | Sat Oct 31 17:00:00 IST 2020 | Fri Oct 02 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1499 | TT_TASK | Duct Bank - Builing to South Vault- URS Run | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 09 17:00:00 IST 2020 | Fri Oct 02 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1500 | TT_TASK | Duct Bank - Vault to COLO-3 UPM | Tue Nov 10 07:00:00 IST 2020 | Fri Nov 13 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1501 | TT_TASK | Duct Bank - Vault to COLO-4 UPM | Mon Nov 16 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1503 | TT_TASK | Set MV Gear (URS) | Mon Nov 23 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1504 | TT_TASK | Set MV Gear (UMS) | Mon Dec 21 07:00:00 IST 2020 | Mon Dec 28 17:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
1506 | TT_TASK | Pull UPM to UPM COLO-1 - CELL-1 to Cell-3 | Tue Jan 05 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1507 | TT_TASK | Pul UPM to UPM COLO-2- CELL-1 to Cell-3 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Sat Jan 02 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
1508 | TT_TASK | Pull UPM to UPM COLO-3 - CELL-1 to Cell-3 | Fri Jan 15 07:00:00 IST 2021 | Mon Jan 18 17:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1509 | TT_TASK | Pull UPM to UPM COLO-4 - CELL-1 to Cell-3 | Wed Feb 03 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
1511 | TT_TASK | Pull UPM to UPM Admin to COLO-1 Cell -2 | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1512 | TT_TASK | Pull UPM to UPM COLO-1 Cell 2- Cell - 4 | Thu Jan 07 07:00:00 IST 2021 | Fri Jan 08 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1513 | TT_TASK | Pull UPM to UPM COLO-2 Cell 2- Cell - 4 | Wed Feb 03 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1514 | TT_TASK | Pull UPM to UPM COLO-3 Cell 2- Cell - 4 | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1515 | TT_TASK | Pull UPM to UPM COLO-4 Cell 2- Cell - 4 | Thu Feb 11 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1517 | TT_TASK | Pull Cross Overs- COLO-1 CELL-3 to CELL-4 | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1518 | TT_TASK | Pull Cross Overs- COLO-2 CELL-3 to CELL-4 | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1519 | TT_TASK | Pull Cross Overs- COLO-3 CELL-3 to CELL-4 | Tue Feb 09 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1520 | TT_TASK | Pull Cross Overs- COLO-4 CELL-3 to CELL-4 | Sat Feb 13 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1522 | TT_TASK | PULL- URS to Admin | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Sat Dec 05 00:00:00 IST 2020 |  | COMPLETED
1523 | TT_TASK | PULL- URS to COLO-2 | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
1524 | TT_TASK | PULL- URS to COLO-3 | Tue Jan 12 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1525 | TT_TASK | PULL- URS to COLO-4 | Mon Jan 18 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1527 | TT_TASK | Pull- UMS to COLO-1,2,3 | Tue Jan 12 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Jan 11 17:00:00 IST 2021 |  | COMPLETED
1528 | TT_TASK | Pull- UMS to COLO-4 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 |  | COMPLETED
1530 | TT_TASK | Pull - JAZ to URS | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
1531 | TT_TASK | Pull - JAZ to UMS | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1534 | TT_TASK | Term COLO -1 Cell-3 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1535 | TT_TASK | Term COLO -2 Cell-3 UPM | Thu Mar 04 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1536 | TT_TASK | Term COLO -3 Cell-3 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 |  | COMPLETED
1537 | TT_TASK | Term COLO -4 Cell-3 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1538 | TT_TASK | Term COLO -1 Cell-1 UPM | Wed Feb 10 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1539 | TT_TASK | Term COLO -2 Cell-1 UPM | Sat Feb 13 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1540 | TT_TASK | Term COLO -3 Cell-1 UPM | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1541 | TT_TASK | Term COLO -4 Cell-1 UPM | Thu Mar 11 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1543 | TT_TASK | Term COLO -1 Cell-4 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
1544 | TT_TASK | Term COLO -2 Cell-4 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1545 | TT_TASK | Term COLO -3 Cell-4 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1546 | TT_TASK | Term COLO -4 Cell-4 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1547 | TT_TASK | Term Admin - UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1548 | TT_TASK | Term COLO -1 Cell-2 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
1549 | TT_TASK | Term COLO -2 Cell-2 UPM | Fri Feb 05 07:00:00 IST 2021 | Tue Feb 09 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1550 | TT_TASK | Term COLO -3 Cell-2 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1551 | TT_TASK | Term COLO -4 Cell-2 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1553 | TT_TASK | Battery Station Yellow tagging / EPMS Checkouts | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1554 | TT_TASK | GCPUD NORTH Mobile substation maintance & Mobile Sub re-energization 4/1 Â– 4/3 | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1555 | TT_TASK | GCPUD SOUTH Mobile substation maintance & Mobile Sub re-energization 4/1 Â– 4/3 | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1556 | TT_TASK | Term- UMS- Line Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1557 | TT_TASK | Term- JAZ to Structure- (Incl Stress Cones) from ums | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1558 | TT_TASK | Term- UMS- Load side | Wed Feb 10 07:00:00 IST 2021 | Tue Feb 23 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1559 | TT_TASK | Yellow Tagging for UMS (includes GC, vendor Lvl-2) | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
1560 | TT_TASK | UMS Control Power Available CYT | Wed Feb 10 07:00:00 IST 2021 | Wed Feb 17 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
1562 | TT_TASK | Term URS- Line Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
1563 | TT_TASK | Term- JAS to URS- (Incl Stress Cones) | Wed Feb 03 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1564 | TT_TASK | TERM- URS- Load Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1565 | TT_TASK | Yellow Tagging for URS | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
1566 | TT_TASK | URS Control Power Available CYT | Wed Feb 10 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
1568 | TT_TASK | Aggregate Road Base | Mon Oct 19 07:00:00 IDT 2020 | Tue Nov 24 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
1569 | TT_TASK | Plant shutdown for winter | Mon Nov 30 07:00:00 IST 2020 | Tue Apr 06 17:00:00 IDT 2021 | Mon Nov 23 00:00:00 IST 2020 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
1570 | TT_TASK | Curb & Gutter | Mon Nov 30 07:00:00 IST 2020 | Sat Jan 09 17:00:00 IST 2021 | Mon Nov 02 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1571 | TT_TASK | Pave HMA | Mon Apr 05 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Sat Nov 07 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1572 | TT_TASK | Site Lighting | Mon May 03 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 |  | 120.0 | IN_PROGRESS
1575 | TT_TASK | Landscape and Site Specialties | Mon May 17 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1581 | TT_TASK | Perimeter Foundations - Excavate/FRP | Mon Apr 27 07:00:00 IDT 2020 | Thu May 14 17:00:00 IDT 2020 | Wed Apr 22 00:00:00 IDT 2020 | Wed May 20 00:00:00 IDT 2020 |  | COMPLETED
1582 | TT_TASK | Perimeter Foundations - Waterproof/Backfill | Mon Jun 01 07:00:00 IDT 2020 | Thu Jun 04 17:00:00 IDT 2020 | Wed May 27 00:00:00 IDT 2020 | Fri Jun 05 00:00:00 IDT 2020 |  | COMPLETED
1583 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Fri Jun 05 07:00:00 IDT 2020 | Tue Jun 16 17:00:00 IDT 2020 | Tue Jun 02 00:00:00 IDT 2020 | Fri Jun 12 00:00:00 IDT 2020 |  | COMPLETED
1585 | TT_TASK | Erect PEMB Steel | Mon Jun 29 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 |  | COMPLETED
1586 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Thu Jul 02 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
1588 | TT_TASK | MEP Undeground Rough-In (Interior) | Tue Aug 18 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1589 | TT_TASK | Aggregate Base Course | Mon Aug 31 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 |  | COMPLETED
1590 | TT_TASK | Slab on Grade | Mon Sep 14 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1592 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Aug 18 07:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 |  | COMPLETED
1593 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Tue Jul 14 00:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 |  | COMPLETED
1594 | TT_TASK | Downspouts & Gutters | Tue Aug 18 07:00:00 IDT 2020 | Sat Aug 29 17:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
1604 | TT_TASK | Perimeter Foundations - Excavate/FRP | Fri May 15 07:00:00 IDT 2020 | Wed Jun 03 17:00:00 IDT 2020 | Mon May 04 00:00:00 IDT 2020 | Fri May 15 00:00:00 IDT 2020 |  | COMPLETED
1605 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Sat Jun 13 07:00:00 IDT 2020 | Thu Jun 25 17:00:00 IDT 2020 | Tue Jun 02 00:00:00 IDT 2020 | Fri Jun 12 00:00:00 IDT 2020 |  | COMPLETED
1606 | TT_TASK | Perimeter Foundations - Waterproof Backfill | Tue May 26 07:00:00 IDT 2020 | Sat Jun 06 17:00:00 IDT 2020 | Tue May 26 07:00:00 IDT 2020 | Wed Jun 17 00:00:00 IDT 2020 |  | COMPLETED
1608 | TT_TASK | Erect PEMB Steel | Mon Jun 29 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Fri Jun 26 00:00:00 IDT 2020 | Mon Jul 06 00:00:00 IDT 2020 |  | COMPLETED
1609 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 |  | COMPLETED
1610 | TT_TASK | Erect Interior Structural Steel | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
1612 | TT_TASK | MEP Undeground Rough-In (Interior) | Fri Aug 14 07:00:00 IDT 2020 | Tue Sep 01 17:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1613 | TT_TASK | Aggregate Base Course | Sat Sep 05 07:00:00 IDT 2020 | Fri Sep 11 17:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 |  | COMPLETED
1614 | TT_TASK | Slab on Grade | Mon Sep 14 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1618 | TT_TASK | Exterior Insulated Metal Panels Installation - East Elevation | Tue Aug 18 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Mon Jul 13 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1621 | TT_TASK | Exterior Insulated Metal Panels Installation - West Elevation | Tue Aug 18 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Mon Jul 13 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1623 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 |  | COMPLETED
1624 | TT_TASK | Downspouts & Gutters | Tue Aug 18 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Wed Aug 12 00:00:00 IDT 2020 |  | COMPLETED
1629 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jun 22 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Mon May 11 00:00:00 IDT 2020 | Tue Jun 16 00:00:00 IDT 2020 |  | COMPLETED
1630 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Wed Jul 08 07:00:00 IDT 2020 | Mon Jul 20 17:00:00 IDT 2020 | Tue Jun 09 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
1632 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Tue Jul 07 00:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 |  | COMPLETED
1633 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 | Tue Aug 04 00:00:00 IDT 2020 |  | COMPLETED
1634 | TT_TASK | Erect Interior Structural Steel | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1636 | TT_TASK | MEP Undeground Rough-In (Interior) | Mon Aug 31 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 |  | COMPLETED
1637 | TT_TASK | Aggregate Base Course | Mon Oct 19 07:00:00 IDT 2020 | Mon Oct 26 17:00:00 IST 2020 | Thu Oct 01 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1638 | TT_TASK | Slab on Grade | Mon Oct 19 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1640 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Aug 18 07:00:00 IDT 2020 | Tue Sep 01 17:00:00 IDT 2020 | Fri Jul 31 00:00:00 IDT 2020 | Thu Aug 13 00:00:00 IDT 2020 |  | COMPLETED
1641 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Wed Aug 26 17:00:00 IDT 2020 | Fri Jul 31 00:00:00 IDT 2020 | Fri Aug 14 00:00:00 IDT 2020 |  | COMPLETED
1642 | TT_TASK | Downspouts & Gutters | Sat Sep 05 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 |  | COMPLETED
1647 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Wed Jul 08 07:00:00 IDT 2020 | Mon Jul 20 17:00:00 IDT 2020 | Wed Jun 24 00:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 |  | COMPLETED
1648 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jun 22 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Tue Jun 16 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1650 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 |  | COMPLETED
1651 | TT_TASK | Secondary Steel | Mon Aug 31 07:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 |  | COMPLETED
1652 | TT_TASK | Erect Interior Structural Steel | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1654 | TT_TASK | MEP Undeground Rough-In (Interior) | Mon Oct 19 07:00:00 IDT 2020 | Thu Nov 05 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1655 | TT_TASK | Aggregate Base Course | Fri Nov 06 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1656 | TT_TASK | Slab on Grade | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
1658 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Sep 08 07:00:00 IDT 2020 | Tue Sep 22 17:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1659 | TT_TASK | Roof Panels Installation | Tue Sep 08 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 | Tue Sep 01 00:00:00 IDT 2020 |  | COMPLETED
1660 | TT_TASK | Downspouts & Gutters | Wed Sep 16 07:00:00 IDT 2020 | Tue Sep 22 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
1670 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jul 06 07:00:00 IDT 2020 | Thu Jul 23 17:00:00 IDT 2020 | Tue Jun 23 00:00:00 IDT 2020 | Thu Jul 30 00:00:00 IDT 2020 |  | COMPLETED
1671 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Sat Aug 29 07:00:00 IDT 2020 | Thu Sep 10 17:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 |  | COMPLETED
1673 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Sat Aug 08 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
1674 | TT_TASK | Secondary Steel | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 08 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1675 | TT_TASK | Erect Interior Structural Steel | Mon Dec 21 07:00:00 IST 2020 | Tue Dec 29 17:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
1677 | TT_TASK | MEP Undeground Rough-In (Interior) | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1678 | TT_TASK | Aggregate Base Course | Wed Nov 11 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
1679 | TT_TASK | Slab on Grade | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1681 | TT_TASK | Exterior Insulated Metal Panels Installation | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Sep 30 00:00:00 IDT 2020 |  | COMPLETED
1682 | TT_TASK | Roof Panels Installation | Thu Sep 03 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Thu Aug 27 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1683 | TT_TASK | Downspouts & Gutters | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Sep 07 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1693 | TT_TASK | Hang Wall Partitions | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1694 | TT_TASK | Hang Wall Partitions- Early Walls | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1695 | TT_TASK | MEP Rough-In / Wall & Ceiling | Mon Oct 19 07:00:00 IDT 2020 | Mon Nov 02 17:00:00 IST 2020 | Thu Oct 01 00:00:00 IDT 2020 | Tue Nov 17 00:00:00 IST 2020 |  | COMPLETED
1697 | TT_TASK | Early Room - Finishes | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1699 | TT_TASK | Loading Dock Equipment & Dock Doors | Wed May 05 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
1700 | TT_TASK | MEP Overhead | Mon Oct 19 07:00:00 IDT 2020 | Tue Nov 17 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1701 | TT_TASK | Ceilings / Ligthing / FA Devices | Mon Mar 01 07:00:00 IST 2021 | Tue Apr 13 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
1702 | TT_TASK | Concrete Floor Sealing/Epoxy | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1706 | TT_TASK | Generator Term | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
1707 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 | Fri Sep 25 00:00:00 IDT 2020 |  | COMPLETED
1708 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Fri Sep 18 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
1709 | TT_TASK | Set Exterior Electrical OFCI Equipment | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1710 | TT_TASK | Admin -Electrical Underground Rough-In | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 31 17:00:00 IDT 2020 | Fri Aug 07 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
1711 | TT_TASK | Generator & Utility Power Pull-Test | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1712 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Jan 18 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1713 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1715 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Oct 19 07:00:00 IDT 2020 | Mon Nov 02 17:00:00 IST 2020 | Fri Oct 09 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1716 | TT_TASK | Set Exterior Mechanical CFCI Equipment (remaning mini splits) | Fri Nov 06 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1717 | TT_TASK | Mechanical Underground Rough-In | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 31 17:00:00 IDT 2020 | Sat Aug 08 00:00:00 IDT 2020 | Tue Aug 25 00:00:00 IDT 2020 |  | COMPLETED
1718 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1721 | TT_TASK | Fire Alarm Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1722 | TT_TASK | Controls Installation | Tue Feb 16 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
1724 | TT_TASK | Set Electrical Equipment incl. OH raceways | Mon Nov 23 07:00:00 IST 2020 | Wed Jan 13 17:00:00 IST 2021 | Mon Nov 16 00:00:00 IST 2020 | Tue Dec 29 00:00:00 IST 2020 |  | COMPLETED
1725 | TT_TASK | Electrical Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1727 | TT_TASK | Domestic Water Piping | Mon Nov 23 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1728 | TT_TASK | Plumbing Devices & Trim | Mon Jul 26 15:00:00 IDT 2021 | Tue Aug 17 15:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
1730 | TT_TASK | Security Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
1732 | TT_TASK | Mechanical Ductwork Installation | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1733 | TT_TASK | Set Mechanical Equipment | Mon Nov 23 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
1734 | TT_TASK | Mechanical Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1739 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1740 | TT_TASK | Overhead MEPFP Rough-In | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 11 17:00:00 IST 2020 | Wed Oct 14 00:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
1741 | TT_TASK | Early Topout | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1743 | TT_TASK | Sprinkler Test | Mon Dec 21 07:00:00 IST 2020 | Tue Dec 22 17:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1744 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1747 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1748 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1749 | TT_TASK | Early Topout | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Tue Nov 10 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1751 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Nov 30 07:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1754 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 |  | COMPLETED
1755 | TT_TASK | Overhead MEPFP Rough-In | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 11 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 |  | COMPLETED
1756 | TT_TASK | Early Topout | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1758 | TT_TASK | Datahall Finishes- Ceiling Grid | Thu Dec 03 07:00:00 IST 2020 | Tue Dec 15 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1761 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1762 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1763 | TT_TASK | Early Topout | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Tue Nov 10 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1765 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1768 | TT_TASK | Remaining MER raceway across Mech chase | Tue Dec 01 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1769 | TT_TASK | Electrical OH Below Mechanical Piping | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1770 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1771 | TT_TASK | OverHead MEPFP Rough-In ( Add TCM Cross over piping HRA Level-3) | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1772 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1774 | TT_TASK | Mechanical Corridor Finishes | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1777 | TT_TASK | Remaining MER raceway across Mech chase | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1778 | TT_TASK | Electrical OH Below Mechanical Piping | Wed Jan 20 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1779 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 11 00:00:00 IST 2020 |  | COMPLETED
1780 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1781 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1783 | TT_TASK | Mechanical Corridor Finishes | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1786 | TT_TASK | Remaining MER raceway across Mech chase | Tue Dec 01 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1787 | TT_TASK | Electrical OH Below Mechanical Piping | Mon Jan 04 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1788 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1789 | TT_TASK | OverHead MEPFP Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1790 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1792 | TT_TASK | Mechanical Corridor Finishes | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1795 | TT_TASK | Remaining MER raceway across Mech chase | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1796 | TT_TASK | Electrical OH Below Mechanical Piping | Wed Jan 20 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1797 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 11 00:00:00 IST 2020 |  | COMPLETED
1798 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1799 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1801 | TT_TASK | Mechanical Corridor Finishes | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Tue Nov 17 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1805 | TT_TASK | Generator & Utility Power Term | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1806 | TT_TASK | Remaining Mechanical Equipment (ADP01) Termimations | Thu Mar 18 07:00:00 IST 2021 | Tue Mar 23 17:00:00 IST 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1807 | TT_TASK | Electrical Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 14 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1808 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1809 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1810 | TT_TASK | Exterior Equipment Pads - Electrical | Thu Sep 03 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1811 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Oct 12 07:00:00 IDT 2020 | Mon Oct 26 17:00:00 IST 2020 | Mon Oct 12 07:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1812 | TT_TASK | Lift & Set MER in Place | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Wed Dec 16 00:00:00 IST 2020 | Wed Dec 16 17:00:00 IST 2020 |  | COMPLETED
1813 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
1814 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 13 17:00:00 IST 2021 | Thu Dec 17 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1815 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Jan 11 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Tue Jan 05 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1816 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1817 | TT_TASK | Generator & Utility Power Pull | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1819 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1820 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1821 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1822 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1823 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Sat Dec 05 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1824 | TT_TASK | Mechanical Equipment Piping Connections | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1825 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
1828 | TT_TASK | Fire Alarm Installation | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1829 | TT_TASK | Controls Installation | Fri Mar 05 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1832 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 22 07:00:00 IST 2021 | Tue Mar 30 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1833 | TT_TASK | Electrical Underground Rough-In | Thu Sep 03 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1834 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1835 | TT_TASK | Set Electrical Equipment-UPM Cell -3 | Fri Dec 11 07:00:00 IST 2020 | Tue Dec 15 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1836 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
1837 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1838 | TT_TASK | Lift & Set MER in Place | Mon Jan 11 08:00:00 IST 2021 | Mon Jan 18 08:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1839 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 18 08:00:00 IST 2021 | Fri Jan 22 08:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1840 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
1841 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1842 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
1843 | TT_TASK | Generator & Utility Power Pull | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1845 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1846 | TT_TASK | Exterior Equipment Pads - Mechanical | Fri Oct 16 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Sat Sep 19 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
1847 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1848 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1849 | TT_TASK | Set Exterior Water Treatment equipment | Mon Dec 07 07:00:00 IST 2020 | Tue Dec 08 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1850 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1851 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 15 07:00:00 IST 2021 | Mon Mar 22 17:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
1854 | TT_TASK | Fire Alarm Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1855 | TT_TASK | Controls Installation | Tue Mar 09 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1858 | TT_TASK | Generator & Utility Power Pull | Tue Feb 02 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Feb 26 07:00:00 IST 2021 |  | COMPLETED
1859 | TT_TASK | Remaining Mechanical Equipment (ADP01) Termimations | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1860 | TT_TASK | Electrical Underground Rough-In | Fri Aug 14 07:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1861 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 05 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1862 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1863 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Sep 05 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Fri Oct 02 00:00:00 IDT 2020 |  | COMPLETED
1864 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Oct 26 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1865 | TT_TASK | Lift & Set MER in Place | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
1866 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 11 08:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1867 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1868 | TT_TASK | GEN & UPM to MER Cable Bus Install | Wed Jan 20 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1869 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1870 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1872 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1873 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Oct 05 07:00:00 IDT 2020 | Sat Oct 17 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
1874 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1875 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1876 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1877 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1878 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 08 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1881 | TT_TASK | Fire Alarm Installation | Thu Feb 18 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1882 | TT_TASK | Controls Installation | Sat Mar 06 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
1885 | TT_TASK | Generator & Utility Power Pull | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1886 | TT_TASK | Electrical Underground Rough-In | Sat Sep 05 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1887 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1888 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1889 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1890 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1891 | TT_TASK | Lift & Set MER in Place | Mon Jan 11 08:00:00 IST 2021 | Mon Jan 18 08:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1892 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 11 08:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Jan 11 08:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1893 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1894 | TT_TASK | GEN & UPM to MER Cable Bus Install | Thu Feb 04 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1895 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Wed Apr 07 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
1896 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 15 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
1898 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Sep 14 07:00:00 IDT 2020 | Sat Sep 26 17:00:00 IDT 2020 | Mon Sep 14 07:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1899 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1900 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1901 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1902 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1903 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1904 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
1907 | TT_TASK | Fire Alarm Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1908 | TT_TASK | Controls Installation | Thu Apr 15 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1911 | TT_TASK | VFD'S Installation & wirepull | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1912 | TT_TASK | Ligthing Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 |  | COMPLETED
1914 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Thu Nov 26 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
1915 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1917 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1919 | TT_TASK | Fire Riser Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1920 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1921 | TT_TASK | Controls Installation | Fri Mar 26 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1924 | TT_TASK | VFD'S Installation & Wiring | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
1925 | TT_TASK | Ligthing Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1927 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
1928 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1930 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1932 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1933 | TT_TASK | Controls Installation | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1936 | TT_TASK | VFD'S Installation & Wiring | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1937 | TT_TASK | Ligthing Installation | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1939 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
1940 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1942 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1944 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1945 | TT_TASK | Controls Installation | Tue Apr 13 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1948 | TT_TASK | VFD'S Installation & Wiring | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
1949 | TT_TASK | Ligthing Installation | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jul 29 00:00:00 IDT 2021 |  | COMPLETED
1951 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
1952 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1954 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1956 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1957 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1961 | TT_TASK | HAC Installation | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
1962 | TT_TASK | Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1963 | TT_TASK | Power Bus Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1964 | TT_TASK | PDU's Installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1965 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Apr 05 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1966 | TT_TASK | Light Fixtures Installation | Wed May 05 07:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
1967 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
1969 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
1970 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1971 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1972 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1974 | TT_TASK | Security Devices & Trim | Mon May 17 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
1975 | TT_TASK | Controls Installation | Fri Mar 26 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1976 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1979 | TT_TASK | HAC Installation | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1980 | TT_TASK | Cable Tray Installation | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
1981 | TT_TASK | Power Bus Installation | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1982 | TT_TASK | PDU's Installation | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
1983 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Apr 26 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1984 | TT_TASK | Light Fixtures Installation | Wed May 12 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1985 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Apr 26 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
1987 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
1988 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1989 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1990 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Thu Jul 01 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1992 | TT_TASK | Security Devices & Trim | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
1993 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1994 | TT_TASK | Fire Alarm System | Tue May 04 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1997 | TT_TASK | HAC Installation | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1998 | TT_TASK | Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1999 | TT_TASK | Power Bus Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
2000 | TT_TASK | PDU's Installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
2001 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Apr 01 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2002 | TT_TASK | Light Fixtures Installation | Tue May 11 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
2003 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 23 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
2005 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2006 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2007 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2008 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed May 19 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2010 | TT_TASK | Security Devices & Trim | Mon May 17 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2011 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2012 | TT_TASK | Fire Alarm System | Thu May 06 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2015 | TT_TASK | HAC Installation | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2016 | TT_TASK | Cable Tray Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2017 | TT_TASK | Power Bus Installation | Fri Mar 12 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2018 | TT_TASK | PDU's Installation | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2019 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon May 03 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
2020 | TT_TASK | Light Fixtures Installation | Fri May 21 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2021 | TT_TASK | Pull/term/Test PDU to Power bus | Mon May 03 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2023 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2024 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2025 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2026 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed May 19 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2028 | TT_TASK | Security Devices & Trim | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 |  | COMPLETED
2029 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2030 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2036 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2037 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
2038 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2040 | TT_TASK | Datahall Finishes - Ceiling Grid | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2043 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2044 | TT_TASK | Overhead MEPFP Rough-In | Fri Nov 06 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2045 | TT_TASK | Hang drywall / Mud / Tape | Wed Jan 06 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2047 | TT_TASK | Datahall Finishes - Ceiling Grid | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2050 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2051 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
2052 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2054 | TT_TASK | Datahall Finishes - Ceiling Grid | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2057 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2058 | TT_TASK | Overhead MEPFP Rough-In | Fri Nov 06 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2059 | TT_TASK | Hang drywall / Mud / Tape | Wed Jan 06 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2061 | TT_TASK | Datahall Finishes - Ceiling Grid | Mon Jan 11 07:00:00 IST 2021 | Wed Jan 20 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2064 | TT_TASK | Remaining Post MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2065 | TT_TASK | Frame & Top out | Mon Nov 23 07:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2066 | TT_TASK | OverHead MEPFP Rough-In | Thu Nov 19 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2067 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Dec 12 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2069 | TT_TASK | Mechanical Corridor Finishes | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2072 | TT_TASK | Remaining MER raceway across Mech chase | Thu Mar 25 07:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2073 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2074 | TT_TASK | OverHead MEPFP Rough-In | Tue Dec 08 07:00:00 IST 2020 | Mon Dec 21 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2075 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Dec 14 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2077 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2080 | TT_TASK | Remaining MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 |  | COMPLETED
2081 | TT_TASK | Frame & Top out | Mon Nov 30 07:00:00 IST 2020 | Wed Dec 09 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2082 | TT_TASK | OverHead MEPFP Rough-In | Sat Dec 19 07:00:00 IST 2020 | Thu Jan 07 17:00:00 IST 2021 | Mon Oct 26 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2083 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Dec 12 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2085 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2088 | TT_TASK | Remaining MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Mar 12 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2089 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2090 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2091 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 30 07:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
2093 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2097 | TT_TASK | Generator & Utility Power Pull | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
2098 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
2099 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2100 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
2101 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Dec 14 07:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 |  | COMPLETED
2102 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Tue Dec 29 00:00:00 IST 2020 |  | COMPLETED
2103 | TT_TASK | Lift & Set MER in Place | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2104 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 |  | COMPLETED
2105 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
2106 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Mar 22 07:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Fri Mar 05 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
2107 | TT_TASK | Generator & Utility Power Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2108 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2110 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
2111 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 08 17:00:00 IST 2021 | Mon Nov 02 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
2112 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2113 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2114 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2115 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2116 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2119 | TT_TASK | Fire Alarm Installation | Tue May 11 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2120 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2123 | TT_TASK | Generator & Utility Power Pull | Tue May 11 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
2124 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 21 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2125 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2126 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Wed Dec 16 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2127 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Dec 14 07:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2128 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2129 | TT_TASK | Lift & Set MER in Place | Tue Mar 23 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
2130 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Mar 29 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2131 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Mar 29 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2132 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Fri Apr 16 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
2133 | TT_TASK | Generator & Utility Power Test-Term | Thu May 06 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2134 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
2136 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2137 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 08 17:00:00 IST 2021 | Mon Nov 16 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2138 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2139 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2140 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2141 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2142 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
2145 | TT_TASK | Fire Alarm Installation | Wed May 26 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2146 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2149 | TT_TASK | Generator & Utility Power Pull | Fri Mar 26 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
2150 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2151 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
2152 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Wed Nov 04 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2153 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Tue Nov 03 00:00:00 IST 2020 |  | COMPLETED
2154 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
2155 | TT_TASK | Lift & Set MER in Place | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2156 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Mar 27 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2157 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Mar 27 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2158 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Thu Mar 25 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
2159 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2160 | TT_TASK | Generator & Utility Power Test-Term | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Tue Apr 06 07:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2162 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2163 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2164 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2165 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2166 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Fri Jan 15 07:00:00 IST 2021 | Fri Jan 29 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2167 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
2168 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
2171 | TT_TASK | Fire Alarm Installation | Tue May 11 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2172 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2175 | TT_TASK | Generator & Utility Power Pull | Thu May 13 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2176 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2177 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2178 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2179 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2180 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
2181 | TT_TASK | Lift & Set MER in Place | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
2182 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Mar 27 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2183 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Mar 27 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
2184 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Thu Apr 15 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
2185 | TT_TASK | Generator & Utility Power Test-Term | Tue May 18 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2186 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2188 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2189 | TT_TASK | Set Gen Stack / Exhaust duct | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2192 | TT_TASK | Fire Alarm Installation | Wed May 12 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2193 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2196 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 |  | COMPLETED
2197 | TT_TASK | Ligthing Installation | Fri Jul 23 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2199 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2200 | TT_TASK | Hydronic Piping Installation | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2202 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2203 | TT_TASK | Toilet Piping Installation / DW | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2205 | TT_TASK | Fire Riser Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2206 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2207 | TT_TASK | Controls Installation | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue Jun 08 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2210 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2211 | TT_TASK | Ligthing Installation | Sat Aug 07 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2213 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
2214 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2216 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2217 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2219 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2220 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
2223 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2224 | TT_TASK | Ligthing Installation | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2226 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
2227 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2229 | TT_TASK | Toilet Piping Installation / DW | Mon May 03 07:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2230 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2232 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2233 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri Jul 09 08:12:00 IDT 2021 |  | COMPLETED
2236 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2237 | TT_TASK | Ligthing Installation | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2239 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
2240 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2242 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2243 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2245 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2246 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2249 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2250 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2251 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
2252 | TT_TASK | Power Bus Installation | Fri Mar 26 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2253 | TT_TASK | PDU's Installation | Fri Mar 26 07:00:00 IDT 2021 | Mon Mar 29 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
2254 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2255 | TT_TASK | Light Fixtures Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2256 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 23 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
2258 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Jun 10 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2259 | TT_TASK | BMS Pull Wire / Term / Test | Thu Jun 10 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2260 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Jul 23 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2262 | TT_TASK | Fire Alarm System | Tue May 04 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2263 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2266 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2267 | TT_TASK | HAC Installation | Wed Feb 03 07:00:00 IST 2021 | Wed Feb 17 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Wed Feb 03 00:00:00 IST 2021 |  | COMPLETED
2268 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
2269 | TT_TASK | Power Bus Installation | Mon Mar 22 07:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2270 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2271 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Tue Jun 08 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2272 | TT_TASK | Light Fixtures Installation | Wed Jun 23 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
2273 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2275 | TT_TASK | EPMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 |  | COMPLETED
2276 | TT_TASK | BMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 |  | COMPLETED
2277 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon Aug 09 07:00:00 IDT 2021 | Wed Sep 01 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2279 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2280 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2283 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2284 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2285 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
2286 | TT_TASK | Power Bus Installation | Fri Mar 26 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2287 | TT_TASK | PDU's Installation | Mon Mar 22 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2288 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2289 | TT_TASK | Light Fixtures Installation | Fri Jun 18 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Jun 18 07:00:00 IDT 2021 | Thu Jul 01 00:00:00 IDT 2021 |  | COMPLETED
2290 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 02 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
2292 | TT_TASK | EPMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2293 | TT_TASK | BMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2294 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Jul 30 07:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2296 | TT_TASK | Fire Alarm System | Mon May 10 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon May 10 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 |  | COMPLETED
2297 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2300 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Thu Apr 22 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2301 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
2302 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2303 | TT_TASK | Power Bus Installation | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2304 | TT_TASK | PDU's Installation | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2305 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Jun 09 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2306 | TT_TASK | Light Fixtures Installation | Wed Jun 23 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2307 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2309 | TT_TASK | EPMS Pull Wire / Term / Test | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2310 | TT_TASK | BMS Pull Wire / Term / Test | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2311 | TT_TASK | ` | Tue Aug 24 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2313 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2314 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2319 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2320 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
2321 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2323 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2326 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
2327 | TT_TASK | Overhead MEPFP Rough-In | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 |  | COMPLETED
2328 | TT_TASK | Hang drywall / Mud / Tape | Thu Jan 14 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2330 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2333 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2334 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2335 | TT_TASK | Hang drywall / Mud / Tape | Fri Jan 08 07:00:00 IST 2021 | Mon Jan 18 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2337 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2340 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
2341 | TT_TASK | Overhead MEPFP Rough-In | Fri Jan 15 07:00:00 IST 2021 | Wed Jan 27 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2342 | TT_TASK | Hang drywall / Mud / Tape | Thu Jan 14 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2344 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2347 | TT_TASK | Remaining MER raceway across Mech chase | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2348 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
2349 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2350 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Thu Jan 21 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Thu Jan 21 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 |  | COMPLETED
2352 | TT_TASK | Mechanical Corridor Finishes | Fri Mar 05 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2355 | TT_TASK | Remaining MER raceway across Mech chase | Thu Jun 17 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2356 | TT_TASK | Frame & Top out | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2357 | TT_TASK | OverHead MEPFP Rough-In | Wed Jan 13 07:00:00 IST 2021 | Wed Jan 27 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2358 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
2360 | TT_TASK | Mechanical Corridor Finishes | Wed Feb 03 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2363 | TT_TASK | Remaining MER raceway across Mech chase | Mon May 03 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2364 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
2365 | TT_TASK | OverHead MEPFP Rough-In | Tue Jan 12 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2366 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2368 | TT_TASK | Mechanical Corridor Finishes | Tue Feb 02 07:00:00 IST 2021 | Tue Feb 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2371 | TT_TASK | Remaining MER raceway across Mech chase | Thu Jun 17 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
2372 | TT_TASK | Frame & Top out | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2373 | TT_TASK | OverHead MEPFP Rough-In | Fri Jan 08 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2374 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2376 | TT_TASK | Mechanical Corridor Finishes | Tue Feb 23 07:00:00 IST 2021 | Tue Mar 16 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2380 | TT_TASK | Generator & Utility Power Pull | Wed May 19 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2381 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
2382 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2383 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 29 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
2384 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 07:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
2385 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2386 | TT_TASK | Lift & Set MER in Place | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
2387 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
2388 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon May 03 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2389 | TT_TASK | GEN & UPM to MER Cable Bus Install | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2390 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2391 | TT_TASK | Generator & Utility Power Test-Term | Wed Jun 02 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
2393 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
2394 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2395 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
2396 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2397 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2398 | TT_TASK | Set Exterior Water Treatment equipment | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 01 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2399 | TT_TASK | Mechanical Equipment Piping Connections | Fri Apr 30 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2402 | TT_TASK | Fire Alarm Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2403 | TT_TASK | Controls Installation | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2406 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2407 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
2408 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2409 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2410 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 02 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2411 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 15 08:00:00 IST 2021 | Mon Mar 22 08:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2412 | TT_TASK | Lift & Set MER in Place | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2413 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2414 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Fri May 07 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2415 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2416 | TT_TASK | Generator & Utility Power Test-Term | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2417 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Jun 08 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Tue Jun 08 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2419 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
2420 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
2423 | TT_TASK | Fire Alarm Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 15 07:00:00 IDT 2021 |  | COMPLETED
2424 | TT_TASK | Controls Installation | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 29 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2427 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2428 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2429 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2430 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 08:00:00 IST 2021 | Tue Jan 12 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2431 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Fri Nov 27 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2432 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
2433 | TT_TASK | Lift & Set MER in Place | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
2434 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2435 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon May 03 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
2436 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Mon May 17 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 |  | COMPLETED
2437 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Thu Jun 10 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2438 | TT_TASK | Generator & Utility Power Test-Term | Thu Jun 03 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
2440 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2441 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2442 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2443 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Apr 26 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2444 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 |  | COMPLETED
2445 | TT_TASK | Set Exterior Water Treatment equipment | Mon Apr 26 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2446 | TT_TASK | Mechanical Equipment Piping Connections | Mon May 03 07:00:00 IDT 2021 | Sat May 08 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2449 | TT_TASK | Fire Alarm Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2450 | TT_TASK | Controls Installation | Fri Jun 25 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2453 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2454 | TT_TASK | Electrical Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2455 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Fri Dec 04 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2456 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2457 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 02 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2458 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
2459 | TT_TASK | Lift & Set MER in Place | Fri May 07 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2460 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2461 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2462 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2463 | TT_TASK | Generator & Utility Power Test-Term | Tue Jul 06 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 | Thu Jul 15 12:00:00 IDT 2021 |  | COMPLETED
2464 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2466 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Fri Dec 04 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2467 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2468 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2469 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2470 | TT_TASK | Set Exterior Water Treatment equipment | Fri Apr 30 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2471 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
2472 | TT_TASK | Mechanical Equipment Piping Connections | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2475 | TT_TASK | Fire Alarm Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jul 07 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2476 | TT_TASK | Controls Installation | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
2479 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2480 | TT_TASK | Ligthing Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2482 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
2483 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2485 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 00:00:00 IDT 2021 |  | COMPLETED
2486 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2488 | TT_TASK | Fire Riser Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2489 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2490 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2493 | TT_TASK | VFD'S Installation & Wiring | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2494 | TT_TASK | Ligthing Installation | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
2496 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
2497 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2499 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2500 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2502 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2503 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2506 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2507 | TT_TASK | Ligthing Installation | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
2509 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
2510 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2512 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2513 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2515 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2516 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
2519 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
2520 | TT_TASK | Ligthing Installation | Mon Aug 30 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2522 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
2523 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2525 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2526 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2528 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2529 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2532 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 |  | COMPLETED
2533 | TT_TASK | HAC Installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2534 | TT_TASK | Cable Tray Installation | Sat Apr 03 07:00:00 IDT 2021 | Sat Apr 17 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
2535 | TT_TASK | Power Bus Installation | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2536 | TT_TASK | PDU's Installation | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2537 | TT_TASK | Pull/term/Test PDU to Power bus | Sat Jun 19 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2538 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2539 | TT_TASK | Light Fixtures Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
2541 | TT_TASK | EPMS Pull Wire / Term / Test | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2542 | TT_TASK | BMS Pull Wire / Term / Test | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2543 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Aug 20 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Jul 07 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2545 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2546 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
2549 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2550 | TT_TASK | HAC Installation | Wed Apr 07 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2551 | TT_TASK | Cable Tray Installation | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2552 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
2553 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
2554 | TT_TASK | Pull/term/Test PDU to Power bus | Fri Jul 02 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
2555 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Aug 16 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Thu Jul 08 00:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2556 | TT_TASK | Light Fixtures Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2558 | TT_TASK | EPMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2559 | TT_TASK | BMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2560 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2562 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2563 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2566 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 |  | COMPLETED
2567 | TT_TASK | HAC Installation | Sat Apr 03 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2568 | TT_TASK | Cable Tray Installation | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2569 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 |  | COMPLETED
2570 | TT_TASK | PDU's Installation | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2571 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Sat Jul 24 00:00:00 IDT 2021 |  | COMPLETED
2572 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 23 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2573 | TT_TASK | Light Fixtures Installation | Wed Jul 21 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2575 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2576 | TT_TASK | BMS Pull Wire / Term / Test | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2577 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Aug 20 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2579 | TT_TASK | Fire Alarm System | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2580 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2583 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2584 | TT_TASK | HAC Installation | Mon Apr 12 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2585 | TT_TASK | Cable Tray Installation | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2586 | TT_TASK | Power Bus Installation | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
2587 | TT_TASK | PDU's Installation | Mon Jun 14 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
2588 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
2589 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2590 | TT_TASK | Light Fixtures Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2592 | TT_TASK | EPMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2593 | TT_TASK | BMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2594 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed Sep 15 07:00:00 IDT 2021 | Fri Oct 08 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2596 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2597 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2602 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2603 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2604 | TT_TASK | Early Topout | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2606 | TT_TASK | Datahall Finishes | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
2609 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Jan 18 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2610 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2611 | TT_TASK | Early Topout | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
2613 | TT_TASK | Datahall Finishes | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2616 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2617 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2618 | TT_TASK | Early Topout | Tue Feb 09 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2620 | TT_TASK | Datahall Finishes | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
2623 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Jan 18 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2624 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2625 | TT_TASK | Early Topout | Mon Feb 08 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2627 | TT_TASK | Datahall Finishes | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2630 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2631 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2632 | TT_TASK | OverHead MEPFP Rough-In | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
2633 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 15 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
2635 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Sat Jan 09 00:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 |  | COMPLETED
2638 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2639 | TT_TASK | Frame & Top out | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Sat Jan 09 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
2640 | TT_TASK | OverHead MEPFP Rough-In | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2641 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Tue Mar 30 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2643 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 29 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Thu Jan 21 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
2646 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 |  | COMPLETED
2647 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
2648 | TT_TASK | OverHead MEPFP Rough-In | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Feb 05 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2649 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 15 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2651 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
2654 | TT_TASK | Remaining MER raceway across Mech chase | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
2655 | TT_TASK | Frame & Top out | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
2656 | TT_TASK | OverHead MEPFP Rough-In | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2657 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Tue Mar 30 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Fri Feb 12 00:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
2659 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 29 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2663 | TT_TASK | Generator & Utility Power Pull | Wed Jul 28 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2664 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2665 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2666 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Wed Dec 30 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2667 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2668 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Apr 26 08:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2669 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
2670 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2671 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2672 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 |  | COMPLETED
2673 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2674 | TT_TASK | Generator & Utility Power Test-Term | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
2676 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2677 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2678 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2679 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2680 | TT_TASK | Set Exterior Water Treatment equipment | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 01 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2681 | TT_TASK | Mechanical Equipment Piping Connections | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2682 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2685 | TT_TASK | Fire Alarm Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
2686 | TT_TASK | Controls Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2689 | TT_TASK | Generator & Utility Power Pull | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 19 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2690 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2691 | TT_TASK | Exterior Equipment Pads - for UPM's | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2692 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2693 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2694 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Apr 26 08:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2695 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2696 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2697 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
2698 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jul 10 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2699 | TT_TASK | Generator & Utility Power Test-Term | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Sat Aug 07 17:00:00 IDT 2021 |  | COMPLETED
2700 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2702 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2703 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2704 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2705 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2706 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2707 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2708 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2711 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
2712 | TT_TASK | Controls Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
2715 | TT_TASK | Generator & Utility Power Pull | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 | Thu Aug 05 09:30:00 IDT 2021 |  | COMPLETED
2716 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2717 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2718 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2719 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2720 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2721 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2722 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2723 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2724 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jul 15 00:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2725 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2726 | TT_TASK | Generator & Utility Power Test-Term | Fri Sep 03 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
2728 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 09 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2729 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2730 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2731 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2732 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2733 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2734 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
2737 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2738 | TT_TASK | Controls Installation | Wed Sep 01 07:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Thu Aug 26 07:00:00 IDT 2021 |  | 1210.0 | IN_PROGRESS
2741 | TT_TASK | Generator & Utility Power Pull | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Thu Jul 29 00:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
2742 | TT_TASK | Electrical Underground Rough-In | Sat Nov 07 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2743 | TT_TASK | Exterior Equipment Pads - for UPM's | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2744 | TT_TASK | Set Electrical Equipment-UPM | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2745 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Jan 18 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2746 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2747 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2748 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2749 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
2750 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2751 | TT_TASK | Generator & Utility Power Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2752 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2754 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2755 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2756 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2757 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2758 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2759 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2760 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2763 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
2764 | TT_TASK | Controls Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
2767 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2768 | TT_TASK | Ligthing Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2770 | TT_TASK | AHU/DOAS Equipment Setting | Sat May 15 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2771 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2773 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2774 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2776 | TT_TASK | Fire Riser Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed May 19 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2777 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2778 | TT_TASK | Controls Installation | Sat Jul 31 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2781 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
2782 | TT_TASK | Ligthing Installation | Thu Sep 16 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
2784 | TT_TASK | AHU/DOAS Equipment Setting | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2785 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2787 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2788 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2790 | TT_TASK | Fire Alarm System | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2791 | TT_TASK | Controls Installation | Mon Aug 23 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2794 | TT_TASK | VFD'S Installation & Wiring | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2795 | TT_TASK | Lighting Installation | Sat Sep 11 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
2797 | TT_TASK | AHU/DOAS Equipment Setting | Sat May 15 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2798 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2800 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2801 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2803 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2804 | TT_TASK | Controls Installation | Mon Aug 16 07:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 |  | COMPLETED
2807 | TT_TASK | VFD'S Installation & Wiring | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2808 | TT_TASK | Ligthing Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
2810 | TT_TASK | AHU/DOAS Equipment Setting | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2811 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2813 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2814 | TT_TASK | Toilet Piping Installation / DW | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
2816 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2817 | TT_TASK | Controls Installation | Wed Sep 08 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2820 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 09 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2821 | TT_TASK | HAC Installation | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2822 | TT_TASK | Cable Tray Installation | Tue May 04 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2823 | TT_TASK | Power Bus Installation | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2824 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2825 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 27 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2826 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Aug 25 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2827 | TT_TASK | Light Fixtures Installation | Sat Aug 21 07:00:00 IDT 2021 | Fri Aug 27 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
2829 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2830 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
2831 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon Sep 27 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2833 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2834 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2837 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 16 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2838 | TT_TASK | HAC Installation | Thu Apr 29 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2839 | TT_TASK | Cable Tray Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2840 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 |  | COMPLETED
2841 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2842 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Fri Sep 03 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2843 | TT_TASK | Pull/term/Test PDU to Power bus | Fri Sep 03 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  | 210.0 | NOT_STARTED
2844 | TT_TASK | Light Fixtures Installation | Fri Oct 01 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2846 | TT_TASK | EPMS Pull Wire / Term / Test | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2847 | TT_TASK | BMS Pull Wire / Term / Test | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
2848 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Thu Oct 21 07:00:00 IDT 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  | 801.0 | NOT_STARTED
2850 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2851 | TT_TASK | Controls Installation | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2854 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 16 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2855 | TT_TASK | HAC Installation | Thu Apr 29 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2856 | TT_TASK | Cable Tray Installation | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2857 | TT_TASK | Power Bus Installation | Mon Jun 14 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2858 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2859 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Sep 01 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2860 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Aug 25 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2861 | TT_TASK | Light Fixtures Installation | Mon Aug 30 07:00:00 IDT 2021 | Tue Sep 07 08:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  | 89.0 | IN_PROGRESS
2863 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2864 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 170.0 | NOT_STARTED
2865 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Sat Oct 09 07:00:00 IDT 2021 | Tue Nov 02 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2867 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2868 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2871 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 23 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2872 | TT_TASK | HAC Installation | Fri May 07 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2873 | TT_TASK | Cable Tray Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2874 | TT_TASK | Power Bus Installation | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Thu Jun 24 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2875 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed Jul 14 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2876 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Sep 01 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 25 00:00:00 IDT 2021 |  |  | IN_PROGRESS
2877 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 22 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2878 | TT_TASK | Light Fixtures Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2880 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2881 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 300.0 | NOT_STARTED
2882 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed Nov 03 07:00:00 IST 2021 | Tue Nov 30 17:00:00 IST 2021 |  |  | 691.0 | NOT_STARTED
2884 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2885 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jul 27 00:00:00 IDT 2021 | Tue Aug 24 13:00:00 IDT 2021 |  | COMPLETED
2889 | TT_TASK | ATS Equipment Yellow Tagging (S2 from MER) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2890 | TT_TASK | Control Power Available | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Fri Apr 30 07:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
2891 | TT_TASK | Power available for Start up | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2892 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2893 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 |  | COMPLETED
2895 | TT_TASK | Admin - NETA test validation Inpections- VECA-EPS-RTS Admin | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Mar 11 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
2896 | TT_TASK | Electrical Equipment Yellow Tagging | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2897 | TT_TASK | Admin/Colo-1 Network Startup | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2898 | TT_TASK | EPMS Checkout / Point to Point | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2902 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2903 | TT_TASK | UPM Yellow tagging - Admin & COLO-1 CELL-1 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2904 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
2905 | TT_TASK | SE- Completed L2 QC Checklist | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
2906 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-1 | Sat Apr 17 07:00:00 IDT 2021 | Tue Apr 20 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2907 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2908 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2909 | TT_TASK | Network Startup | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
2910 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2911 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2912 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2914 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2915 | TT_TASK | Power available for Start up | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2916 | TT_TASK | SE- Completed L2 QC Checklist | Mon Jun 14 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
2917 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Jul 13 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2918 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-3 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2919 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-3 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2920 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Thu Jun 10 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2921 | TT_TASK | Network Startup | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 |  | COMPLETED
2922 | TT_TASK | EPMS Checkout / Point to Point | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jul 06 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2923 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2924 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2926 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2927 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2928 | TT_TASK | SE- Completed L2 QC Checklist | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2929 | TT_TASK | Mechanical Equipment Yellow Tag | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 |  | COMPLETED
2930 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-2 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2931 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-2 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2932 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2933 | TT_TASK | Network Startup | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2934 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2935 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2936 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 20 15:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2938 | TT_TASK | Control Power Available | Tue Jun 22 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue Jun 22 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2939 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2940 | TT_TASK | SE- Completed L2 QC Checklist | Mon Jun 14 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
2941 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Jul 02 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2942 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-4 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2943 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-4 | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
2944 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Jul 07 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2945 | TT_TASK | Network Startup | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2946 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2947 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2948 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2950 | TT_TASK | GEN SCR testing and Burnins | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jul 14 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2951 | TT_TASK | Admin GEN SCR testing and Burnins | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2952 | TT_TASK | ATS- Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 |  | 100.0 | IN_PROGRESS
2953 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Tue Jul 13 11:00:00 IDT 2021 | Wed Jul 28 11:00:00 IDT 2021 | Tue Jul 13 11:00:00 IDT 2021 | Wed Jul 28 11:00:00 IDT 2021 |  | COMPLETED
2954 | TT_TASK | Cooling Automation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2955 | TT_TASK | BAS Prefunctional Testing on Construction Server | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Sat Aug 28 00:00:00 IDT 2021 |  | COMPLETED
2956 | TT_TASK | Additional Go-Back loadbanking (ASCO) | Fri Sep 10 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2957 | TT_TASK | Load Bank & IR Scan | Wed Sep 15 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2958 | TT_TASK | Level 3 Cx - ADMIN AND COLO1 | Fri Sep 17 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2959 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Sat Oct 02 07:00:00 IDT 2021 | Sat Oct 02 07:00:00 IDT 2021 |  |  |  | NOT_STARTED
2961 | TT_TASK | COLO 1 Level 4 & Level 5 IST | Sat Oct 02 08:00:00 IDT 2021 | Fri Oct 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2962 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Sat Oct 30 08:00:00 IDT 2021 | Mon Nov 08 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2963 | TT_TASK | Security Commissioning (level3 DCPS) | Tue Nov 09 08:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2964 | TT_TASK | Punch List - Admin/COLO 1 | Sat Oct 30 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2965 | TT_TASK | MST Ready for Network Install | Sat Oct 02 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2966 | TT_TASK | Final Clean/ ready for lock down | Sat Nov 13 07:00:00 IST 2021 | Mon Nov 22 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2970 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 18 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2971 | TT_TASK | Power available for Start up | Sat Sep 11 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2972 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2973 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  | 20.0 | IN_PROGRESS
2974 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-1 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2975 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-1 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2976 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Aug 04 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2977 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2978 | TT_TASK | EPMS Checkout / Point to Point | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 200.0 | NOT_STARTED
2979 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Thu Sep 16 07:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 |  |  | 20.0 | NOT_STARTED
2980 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Thu Sep 16 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  | 50.0 | NOT_STARTED
2982 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2983 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2984 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2985 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2986 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-3 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2987 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-3 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2988 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2989 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2990 | TT_TASK | EPMS Checkout / Point to Point | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
2991 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2992 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2994 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2995 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2996 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2997 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2998 | TT_TASK | UPM Yellow tagging - COLO-2 CELL-2 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2999 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-2 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
3000 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jul 13 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3001 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3002 | TT_TASK | EPMS Checkout / Point to Point | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3003 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3004 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3006 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3007 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3008 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
3009 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3010 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-4 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
3011 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-4 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
3012 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Aug 18 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3013 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3014 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3015 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3016 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  | 30.0 | NOT_STARTED
3018 | TT_TASK | GEN SCR testing and Burnins | Sat Sep 18 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  | 150.0 | NOT_STARTED
3019 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Mon Sep 27 07:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3020 | TT_TASK | Cooling Automation | Mon Oct 11 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3021 | TT_TASK | BAS Prefunctional Testing on Construction Server | Thu Oct 07 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3022 | TT_TASK | Load Bank & IR Scan | Tue Oct 26 07:00:00 IDT 2021 | Tue Nov 16 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3023 | TT_TASK | Level 3 Cx- COLO-2 | Wed Nov 17 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3024 | TT_TASK | Weather (5 Days) - 0 remaining Check Delay #14 for updates | Sat Dec 04 07:00:00 IST 2021 | Sat Dec 04 07:00:00 IST 2021 |  |  |  | NOT_STARTED
3026 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Mon Dec 27 07:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3027 | TT_TASK | Security Commissioning (level3 DCPS) | Tue Jan 11 07:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3028 | TT_TASK | COLO 2 Level 4 & Level 5 IST | Sat Dec 04 08:00:00 IST 2021 | Fri Dec 24 17:00:00 IST 2021 |  |  | 16.0 | NOT_STARTED
3029 | TT_TASK | Punch List COLO-2 | Mon Dec 27 08:00:00 IST 2021 | Sun Jan 09 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3030 | TT_TASK | MST Ready for Network Install | Sat Dec 04 07:00:00 IST 2021 | Thu Dec 09 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3031 | TT_TASK | Final Clean/ ready for lock down | Mon Jan 10 08:00:00 IST 2022 | Fri Jan 21 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3035 | TT_TASK | Control Power Available | Thu Sep 09 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3036 | TT_TASK | Power available for Start up | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3037 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3038 | TT_TASK | Mechanical Equipment Yellow Tag | Wed Sep 22 07:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3039 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-1 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3040 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-1 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3041 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3042 | TT_TASK | Network Startup | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3043 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3044 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3045 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Tue Oct 05 07:00:00 IDT 2021 | Tue Oct 19 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3047 | TT_TASK | Control Power Available | Tue Sep 21 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3048 | TT_TASK | Power available for Start up | Mon Oct 04 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3049 | TT_TASK | SE- Completed L2 QC Checklist | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3050 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Oct 05 07:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3051 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-3 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 160.0 | NOT_STARTED
3052 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-3 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3053 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3054 | TT_TASK | Network Startup | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3055 | TT_TASK | EPMS Checkout / Point to Point | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3056 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3057 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Oct 18 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3059 | TT_TASK | Control Power Available | Thu Sep 09 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3060 | TT_TASK | Power available for Start up | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3061 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3062 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3063 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-2 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3064 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-2 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3065 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Fri Aug 13 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3066 | TT_TASK | Network Startup | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3067 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3068 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3069 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  |  | 170.0 | NOT_STARTED
3071 | TT_TASK | Control Power Available | Tue Sep 21 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3072 | TT_TASK | Power available for Start up | Mon Oct 04 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3073 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3074 | TT_TASK | Mechanical Equipment Yellow Tag | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3075 | TT_TASK | UPM Yellow tagging COLO-3 CELL-4 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 160.0 | NOT_STARTED
3076 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-4 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
3077 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3078 | TT_TASK | Network Startup | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3079 | TT_TASK | EPMS Checkout / Point to Point | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3080 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3081 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  |  | 70.0 | NOT_STARTED
3083 | TT_TASK | GEN SCR testing and Burnins | Fri Oct 08 07:00:00 IDT 2021 | Tue Oct 26 17:00:00 IDT 2021 |  |  | 320.0 | NOT_STARTED
3084 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Fri Oct 22 07:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3085 | TT_TASK | Cooling Automation | Fri Nov 05 07:00:00 IST 2021 | Fri Nov 19 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3086 | TT_TASK | BAS Prefunctional Testing on Construction Server | Mon Nov 01 07:00:00 IST 2021 | Wed Nov 24 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3087 | TT_TASK | Load Bank & IR Scan | Wed Dec 08 07:00:00 IST 2021 | Mon Jan 03 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3088 | TT_TASK | Level 3 Cx- COLO-3 | Tue Jan 04 07:00:00 IST 2022 | Tue Jan 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3089 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Wed Jan 19 07:00:00 IST 2022 | Wed Jan 19 07:00:00 IST 2022 |  |  |  | NOT_STARTED
3091 | TT_TASK | COLO 3 Level 4 & Level 5 IST | Wed Jan 19 08:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3092 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Wed Feb 09 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3093 | TT_TASK | Security Commissioning (level3 DCPS) | Sat Feb 19 08:00:00 IST 2022 | Wed Feb 23 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3094 | TT_TASK | Punch List COLO-3 | Wed Feb 09 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3095 | TT_TASK | MST Ready for Network Install | Wed Jan 19 08:00:00 IST 2022 | Tue Jan 25 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3096 | TT_TASK | Final Clean/ ready for lock down | Wed Feb 23 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3100 | TT_TASK | Control Power Available | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3101 | TT_TASK | Power available for Start up | Tue Nov 02 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3102 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3103 | TT_TASK | Mechanical Equipment Yellow Tag | Mon Oct 18 07:00:00 IDT 2021 | Thu Oct 28 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3104 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-1 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
3105 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-1 | Fri Sep 17 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
3106 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3107 | TT_TASK | Network Startup | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3108 | TT_TASK | EPMS Checkout / Point to Point | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  | 40.0 | NOT_STARTED
3109 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3110 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3112 | TT_TASK | Control Power Available | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3113 | TT_TASK | Power available for Start up | Mon Nov 15 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3114 | TT_TASK | SE- Completed L2 QC Checklist | Sat Oct 23 07:00:00 IDT 2021 | Wed Nov 03 17:00:00 IST 2021 |  |  | 20.0 | NOT_STARTED
3115 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Oct 29 07:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 |  |  | 70.0 | NOT_STARTED
3116 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-3 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Mon Aug 16 00:00:00 IDT 2021 |  | COMPLETED
3117 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-3 | Tue Sep 28 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  | 200.0 | NOT_STARTED
3118 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3119 | TT_TASK | Network Startup | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3120 | TT_TASK | EPMS Checkout / Point to Point | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3121 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3122 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3124 | TT_TASK | Control Power Available | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3125 | TT_TASK | Power available for Start up | Tue Nov 02 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3126 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3127 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3128 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-2 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3129 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-2 | Fri Sep 17 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
3130 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3131 | TT_TASK | Network Startup | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3132 | TT_TASK | EPMS Checkout / Point to Point | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3133 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3134 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3136 | TT_TASK | Control Power Available | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3137 | TT_TASK | Power available for Start up | Mon Nov 15 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3138 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3139 | TT_TASK | Mechanical Equipment Yellow Tag | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  | 140.0 | NOT_STARTED
3140 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-4 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3141 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-4 | Sat Sep 18 07:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 |  |  | 270.0 | NOT_STARTED
3142 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3143 | TT_TASK | Network Startup | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3144 | TT_TASK | EPMS Checkout / Point to Point | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3145 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3146 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3148 | TT_TASK | GEN SCR testing and Burnins | Fri Nov 19 07:00:00 IST 2021 | Thu Dec 09 17:00:00 IST 2021 |  |  | 310.0 | NOT_STARTED
3149 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Tue Nov 30 07:00:00 IST 2021 | Mon Dec 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3150 | TT_TASK | Cooling Automation | Tue Dec 14 07:00:00 IST 2021 | Thu Dec 30 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3151 | TT_TASK | BAS Prefunctional Testing on Construction Server | Tue Dec 07 07:00:00 IST 2021 | Tue Jan 04 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3152 | TT_TASK | Load Bank & IR Scan | Sat Jan 22 07:00:00 IST 2022 | Sat Feb 12 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3153 | TT_TASK | Level 3 Cx - COLO-4 | Mon Feb 14 07:00:00 IST 2022 | Sat Feb 26 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3154 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Mon Feb 28 07:00:00 IST 2022 | Mon Feb 28 07:00:00 IST 2022 |  |  |  | NOT_STARTED
3156 | TT_TASK | COLO 4 Level 4 & Level 5 IST | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 20 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3157 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Mon Mar 21 08:00:00 IST 2022 | Wed Mar 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3158 | TT_TASK | Security Commissioning (level3 DCPS) | Thu Mar 31 08:00:00 IDT 2022 | Mon Apr 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3159 | TT_TASK | Punch List COLO-4 | Mon Mar 21 08:00:00 IST 2022 | Sat Apr 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3160 | TT_TASK | MST Ready for Network Install | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3161 | TT_TASK | Final Clean/ ready for lock down | Sun Apr 03 08:00:00 IDT 2022 | Wed Apr 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3163 | TT_TASK | CSA Punchlist - COLO-1 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  | COMPLETED
3164 | TT_TASK | CSA Punchlist - COLO-2 | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 220.0 | NOT_STARTED
3165 | TT_TASK | CSA Punchlist - COLO-3 | Mon Nov 01 07:00:00 IST 2021 | Fri Nov 12 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3166 | TT_TASK | CSA Punchlist - COLO-4 | Sat Dec 11 07:00:00 IST 2021 | Thu Dec 23 17:00:00 IST 2021 |  |  | 380.0 | NOT_STARTED
3167 | TT_TASK | MEP Punchlist - COLO-1 | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 110.0 | NOT_STARTED
3168 | TT_TASK | MEP Punchlist - COLO-2 | Wed Nov 17 07:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 |  |  | 20.0 | NOT_STARTED
3169 | TT_TASK | MEP Punchlist - COLO-3 | Tue Jan 04 07:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  |  | 20.0 | NOT_STARTED
3170 | TT_TASK | MEP Punchlist - COLO-4 | Mon Feb 14 07:00:00 IST 2022 | Thu Feb 24 17:00:00 IST 2022 |  |  | 20.0 | NOT_STARTED
3171 | TT_TASK | AE/Owner Punchlist - COLO-1 | Sat Oct 30 07:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  |  | 60.0 | NOT_STARTED
3172 | TT_TASK | AE/Owner Punchlist - COLO-2 | Mon Dec 27 07:00:00 IST 2021 | Mon Jan 03 17:00:00 IST 2022 |  |  | 41.0 | NOT_STARTED
3173 | TT_TASK | AE/Owner Punchlist - COLO-3 | Wed Feb 09 07:00:00 IST 2022 | Mon Feb 14 17:00:00 IST 2022 |  |  | 71.0 | NOT_STARTED
3174 | TT_TASK | AE/Owner Punchlist - COLO-4 | Mon Mar 21 07:00:00 IST 2022 | Fri Mar 25 17:00:00 IDT 2022 |  |  | 70.0 | NOT_STARTED
3182 | TT_TASK | UMS - ROJ COLO-2 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3183 | TT_TASK | UMS - ROJ COLO-3 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3184 | TT_TASK | UMS - ROJ COLO-4 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3185 | TT_TASK | MSFT Delivery -UMS -COLO 4 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3186 | TT_TASK | MSFT Delivery -UMS -COLO 3 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3187 | TT_TASK | MSFT Delivery -UMS -COLO 2 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3190 | TT_TASK | TCO COLO 2 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3191 | TT_TASK | Weather Tight | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3192 | TT_TASK | Duct Bank - UMS01 to UPM COLO-1 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3193 | TT_TASK | Duct Bank - UMS02 to UPM COLO-2 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3194 | TT_TASK | Duct Bank - UMS03 to UPM COLO-3 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3195 | TT_TASK | Duct Bank - UMS04 to UPM COLO-4 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3196 | TT_TASK | PAD- COLO-1 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3197 | TT_TASK | PAD- COLO-2 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3198 | TT_TASK | PAD- COLO-3 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3199 | TT_TASK | PAD- COLO-4 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3200 | TT_TASK | Pull- UMS01- UPM COLO-1 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3201 | TT_TASK | Pull- UMS02- UPM COLO-2 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3202 | TT_TASK | Pull- UMS03- UPM COLO-3 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3203 | TT_TASK | Pull- UMS04- UPM COLO-4 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3204 | TT_TASK | Set- COLO-1 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3205 | TT_TASK | Set- COLO-2 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3206 | TT_TASK | Set- COLO-3 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3207 | TT_TASK | Set- COLO-4 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3208 | TT_TASK | Term Admin - UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3209 | TT_TASK | Term COLO -1 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3210 | TT_TASK | Term COLO -1 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3211 | TT_TASK | Term COLO -2 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3212 | TT_TASK | Term COLO -2 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3213 | TT_TASK | Term COLO -3 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3214 | TT_TASK | Term COLO -3 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3215 | TT_TASK | Term COLO -4 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3216 | TT_TASK | Term COLO -4 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3217 | TT_TASK | Term- UMS01- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3218 | TT_TASK | Term- UMS02- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3219 | TT_TASK | Term- UMS03- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3220 | TT_TASK | Term- UMS04- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3221 | TT_TASK | Yellow Tagging for UMS01 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3222 | TT_TASK | Yellow Tagging for UMS02 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3223 | TT_TASK | Yellow Tagging for UMS03 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3224 | TT_TASK | Yellow Tagging for UMS04 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3225 | TT_TASK | URS Vault design and Approval | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3227 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Thu Oct 22 07:00:00 IDT 2020 | Thu Oct 22 07:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3228 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3229 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jan 23 07:00:00 IST 2021 | Sat Jan 23 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3230 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Thu Oct 22 07:00:00 IDT 2020 | Thu Oct 22 07:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3231 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3232 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jan 23 07:00:00 IST 2021 | Sat Jan 23 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3233 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Nov 04 07:00:00 IST 2020 | Wed Nov 04 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3234 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3235 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Feb 04 07:00:00 IST 2021 | Thu Feb 04 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3236 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Nov 04 07:00:00 IST 2020 | Wed Nov 04 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3237 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3238 | TT_TASK | COLO Lighting installation (DRB#2) | Mon Feb 08 07:00:00 IST 2021 | Mon Feb 08 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3239 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3240 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Dec 02 07:00:00 IST 2020 | Wed Dec 02 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3241 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Mar 11 07:00:00 IST 2021 | Thu Mar 11 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3242 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Tue Dec 29 07:00:00 IST 2020 | Tue Dec 29 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3243 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Dec 02 07:00:00 IST 2020 | Wed Dec 02 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3244 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Mar 11 07:00:00 IST 2021 | Thu Mar 11 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3245 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Dec 18 07:00:00 IST 2020 | Fri Dec 18 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3246 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Dec 15 07:00:00 IST 2020 | Tue Dec 15 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3247 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Mar 26 07:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3248 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Dec 15 07:00:00 IST 2020 | Tue Dec 15 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3249 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Mar 26 07:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3250 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Jan 07 07:00:00 IST 2021 | Thu Jan 07 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3251 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3252 | TT_TASK | COLO Lighting installation (DRB#2) | Tue Apr 27 07:00:00 IDT 2021 | Tue Apr 27 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3253 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Jan 14 07:00:00 IST 2021 | Thu Jan 14 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3254 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3255 | TT_TASK | COLO Lighting installation (DRB#2) | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3256 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Fri Feb 12 07:00:00 IST 2021 | Fri Feb 12 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3257 | TT_TASK | COLO Lighting installation (DRB#2) | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3258 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Jan 29 07:00:00 IST 2021 | Fri Jan 29 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3259 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Fri Feb 12 07:00:00 IST 2021 | Fri Feb 12 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3260 | TT_TASK | COLO Lighting installation (DRB#2) | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3261 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3262 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Mar 09 07:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3263 | TT_TASK | COLO Lighting installation (DRB#2) | Wed Jun 09 07:00:00 IDT 2021 | Wed Jun 09 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3264 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3265 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Mar 09 07:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3266 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Jun 04 07:00:00 IDT 2021 | Fri Jun 04 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3267 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Sat Feb 20 07:00:00 IST 2021 | Sat Feb 20 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3268 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Mon Mar 22 07:00:00 IST 2021 | Mon Mar 22 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3269 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jun 19 07:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3270 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Sat Feb 20 07:00:00 IST 2021 | Sat Feb 20 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3271 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Mon Mar 22 07:00:00 IST 2021 | Mon Mar 22 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3272 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jun 19 07:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3273 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3274 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3275 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3276 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3277 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3278 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3279 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3280 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3281 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3282 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3283 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3284 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3285 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3286 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3287 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3288 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3290 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 05 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3291 | TT_TASK | Mechanical Equipment Piping Connections | Tue Nov 03 07:00:00 IST 2020 | Tue Nov 17 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3292 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3293 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3294 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3295 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3296 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3297 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3298 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3299 | TT_TASK | Fluid Cooler RI prefabrication | Thu Dec 10 07:00:00 IST 2020 | Wed Dec 16 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3300 | TT_TASK | Fluid Cooler RI prefabrication | Wed Dec 16 07:00:00 IST 2020 | Tue Dec 22 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3301 | TT_TASK | Fluid Cooler RI prefabrication | Wed Dec 23 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3302 | TT_TASK | Fluid Cooler RI prefabrication | Thu Jan 07 07:00:00 IST 2021 | Wed Jan 13 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3303 | TT_TASK | Fluid Cooler RI prefabrication | Thu Jan 14 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3304 | TT_TASK | Fluid Cooler RI prefabrication | Fri Jan 22 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3305 | TT_TASK | Fluid Cooler RI prefabrication | Tue Jan 26 07:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3306 | TT_TASK | Submit and approve shop drawing for PEMB penetrations | Mon Oct 19 08:00:00 IDT 2020 | Sun Nov 08 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3308 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3309 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3310 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3311 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3312 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3313 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3314 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3315 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3316 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3317 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3318 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3319 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3321 | TT_TASK | Yellow Tagging for COLO-2 UPM's | Fri Jan 29 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3322 | TT_TASK | Yellow Tagging for COLO-3 UPM's | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 |  | COMPLETED
3323 | TT_TASK | Yellow Tagging for COLO-4 UPM's | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 |  | COMPLETED
3324 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 11 07:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3326 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3327 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3328 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Mar 10 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3329 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 08 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3330 | TT_TASK | Fluid Cooler QAQC and Cx | Thu Mar 18 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3331 | TT_TASK | Fluid Cooler QAQC and Cx | Fri Apr 02 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3332 | TT_TASK | Fluid Cooler QAQC and Cx | Fri Mar 26 07:00:00 IDT 2021 | Sat Mar 27 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3333 | TT_TASK | Fluid Cooler QAQC and Cx | Tue Apr 06 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3334 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 14 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3335 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 21 07:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3336 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 14 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3337 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 28 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3338 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 21 07:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3339 | TT_TASK | Fluid Cooler QAQC and Cx | Thu May 06 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3341 | TT_TASK | COLO-2 CELL3 Rearrange Roxtec blocks per coordination layout | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3342 | TT_TASK | COLO2 CELL3 Interior MER conduit installation utility side | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 06 07:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3343 | TT_TASK | COLO-2 CELL3 Interior MER conduit installation building side | Tue Apr 20 07:00:00 IDT 2021 | Tue Apr 20 07:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3345 | TT_TASK | COLO-2 Cell-4 Rearrange Roxtec blocks per coordination layout | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3346 | TT_TASK | COLO2 CELL4 Interior MER conduit installation utility side | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3347 | TT_TASK | COLO2 CELL4 Interior MER conduit installation building side | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3350 | TT_TASK | COLO-2 Cell-1 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3351 | TT_TASK | COLO-2 Cell-2 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3352 | TT_TASK | COLO-2 Cell-3 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3353 | TT_TASK | COLO-2 Cell-4 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3354 | TT_TASK | COLO2 CELL1 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3355 | TT_TASK | COLO2 CELL2 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3356 | TT_TASK | COLO2 CELL3 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3357 | TT_TASK | COLO2 CELL4 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3360 | TT_TASK | Concrete interior - Create Punch list | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
3361 | TT_TASK | Concrete interior - Complete Punch List | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
3362 | TT_TASK | Garco Steel (Mezz steel, Yard) - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3363 | TT_TASK | Garco Steel (Mezz steel, Yard) - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3364 | TT_TASK | Sure Steel (Building, Mezz, Ceiling) - Create Punch list | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
3365 | TT_TASK | Sure Steel (Building, Mezz, Ceiling) - Complete Punch List | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
3366 | TT_TASK | Advantage - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3367 | TT_TASK | Advantage - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3368 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3369 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3370 | TT_TASK | VECA - Create Punch list | Tue Sep 07 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3371 | TT_TASK | VECA - Complete Punch List | Thu Sep 09 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3372 | TT_TASK | LINX - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3373 | TT_TASK | LINX - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3374 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3375 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3376 | TT_TASK | TCM- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3377 | TT_TASK | TCM - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3378 | TT_TASK | Cascade- Create Punch list | Mon Apr 26 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
3379 | TT_TASK | Cascade - Complete Punch List | Wed Apr 28 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3380 | TT_TASK | Submit GC Punch List to A/E | Tue Sep 21 07:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3381 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3382 | TT_TASK | Complete A/E Punchlist | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3383 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3384 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3385 | TT_TASK | VECA - Create Punch list | Fri Oct 29 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3386 | TT_TASK | VECA - Complete Punch List | Mon Nov 01 07:00:00 IST 2021 | Mon Nov 08 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3387 | TT_TASK | LINX - Create Punch list | Mon Aug 16 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3388 | TT_TASK | LINX - Complete Punch List | Wed Aug 18 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3389 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3390 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3391 | TT_TASK | TCM- Create Punch list | Wed Sep 22 07:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3392 | TT_TASK | TCM - Complete Punch List | Fri Sep 24 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3393 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3394 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3395 | TT_TASK | Submit GC Punch List to A/E | Tue Nov 09 07:00:00 IST 2021 | Tue Nov 09 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3396 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Nov 10 07:00:00 IST 2021 | Tue Nov 16 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3397 | TT_TASK | Complete A/E Punchlist | Wed Nov 17 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3398 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3399 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3400 | TT_TASK | VECA - Create Punch list | Tue Dec 14 07:00:00 IST 2021 | Wed Dec 15 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3401 | TT_TASK | VECA - Complete Punch List | Thu Dec 16 07:00:00 IST 2021 | Thu Dec 23 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3402 | TT_TASK | LINX - Create Punch list | Wed Oct 13 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3403 | TT_TASK | LINX - Complete Punch List | Fri Oct 15 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3404 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3405 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3406 | TT_TASK | TCM- Create Punch list | Wed Sep 22 07:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3407 | TT_TASK | TCM - Complete Punch List | Fri Sep 24 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3408 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3409 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3410 | TT_TASK | Submit GC Punch List to A/E | Mon Dec 27 07:00:00 IST 2021 | Mon Dec 27 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3411 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Tue Dec 28 07:00:00 IST 2021 | Wed Jan 05 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3412 | TT_TASK | Complete A/E Punchlist | Thu Jan 06 07:00:00 IST 2022 | Thu Jan 20 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3413 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3414 | TT_TASK | PCI - Complete Punch List | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3415 | TT_TASK | VECA - Create Punch list | Fri Jan 28 07:00:00 IST 2022 | Mon Jan 31 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3416 | TT_TASK | VECA - Complete Punch List | Tue Feb 01 07:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3417 | TT_TASK | LINX - Create Punch list | Fri Nov 19 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3418 | TT_TASK | LINX - Complete Punch List | Mon Nov 22 07:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3419 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3420 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3421 | TT_TASK | TCM- Create Punch list | Thu Nov 04 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3422 | TT_TASK | TCM - Complete Punch List | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3423 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3424 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3425 | TT_TASK | Submit GC Punch List to A/E | Tue Feb 08 07:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3426 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Feb 09 07:00:00 IST 2022 | Tue Feb 15 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3427 | TT_TASK | Complete A/E Punchlist | Wed Feb 16 07:00:00 IST 2022 | Tue Mar 01 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3428 | TT_TASK | COLO-2 Cell2 Rearrange Roxtec blocks per coordination layout (delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
3429 | TT_TASK | COLO2 CELL2 Interior MER conduit installation utility side(delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
3430 | TT_TASK | COLO-2 CELL2 Interior MER conduit installation building (delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
3432 | TT_TASK | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change(delete) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
3433 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3434 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3435 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3436 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
303 | TT_TASK | MSFT Issue DRB #1 for Review | Tue May 26 07:00:00 IDT 2020 | Mon Jun 01 17:00:00 IDT 2020 | Tue May 19 00:00:00 IDT 2020 | Mon Jul 20 00:00:00 IDT 2020 |  | COMPLETED
306 | TT_TASK | Lead Time for PEMB | Wed Feb 19 08:00:00 IST 2020 | Thu Jun 18 17:00:00 IDT 2020 | Mon Feb 24 00:00:00 IST 2020 | Thu Jun 18 00:00:00 IDT 2020 |  | COMPLETED
307 | TT_TASK | Lead Time for Rebar (Footings & Walls) | Mon Apr 27 08:00:00 IDT 2020 | Sun May 31 17:00:00 IDT 2020 | Mon Mar 30 00:00:00 IDT 2020 | Tue Apr 21 00:00:00 IDT 2020 |  | COMPLETED
308 | TT_TASK | Lead Time for COLO 1 Structural Interior Steel | Mon Aug 10 08:00:00 IDT 2020 | Sat Oct 31 17:00:00 IST 2020 | Tue Jun 30 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
309 | TT_TASK | Lead Time for Wall & Roof Metal Panels | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Mon Jun 29 00:00:00 IDT 2020 |  | COMPLETED
310 | TT_TASK | Lead Time for Admin/COLO 1 Yard Steel | Mon Aug 31 08:00:00 IDT 2020 | Sun Oct 18 17:00:00 IDT 2020 | Tue Jun 30 00:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 |  | COMPLETED
311 | TT_TASK | Lead Time for HM Ext. frames | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
312 | TT_TASK | Lead time for Drywall/Framing | Mon Aug 10 08:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Mon Aug 10 08:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
592 | TT_TASK | MV Ductbanks Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | Mon Sep 14 08:00:00 IDT 2020 | Sun Sep 20 17:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 | Sun Sep 06 00:00:00 IDT 2020 |  | COMPLETED
593 | TT_TASK | MV Wire Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | Wed Aug 12 08:00:00 IDT 2020 | Tue Nov 03 17:00:00 IST 2020 | Tue Aug 04 00:00:00 IDT 2020 | Mon Oct 26 00:00:00 IST 2020 |  | COMPLETED
594 | TT_TASK | UMS Vault Procurement DRB#1 | Mon Sep 28 08:00:00 IDT 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
595 | TT_TASK | DRB#1 BIM Modeling & Coordination DRB#1 JAZ to UMS/URS & UPM to UMS | Mon Aug 10 08:00:00 IDT 2020 | Sun Aug 23 17:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
596 | TT_TASK | Site- Neher Mcgrath Study DRB#1 JAZ to UMS/URS & UPM to UMS | Tue Aug 11 08:00:00 IDT 2020 | Mon Aug 24 17:00:00 IDT 2020 | Tue Aug 04 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
597 | TT_TASK | JAZ Riser Support DRB#1 Procurement/ Jaz Foundations/Construction | Mon Aug 10 08:00:00 IDT 2020 | Sun Oct 18 17:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
598 | TT_TASK | UPM to UMS Vaults Procurement DRB#1 | Tue Sep 08 08:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
600 | TT_TASK | MV Ductbanks Procurement | Wed Aug 12 08:00:00 IDT 2020 | Thu Aug 20 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
601 | TT_TASK | Telecom DuctBank / Vaults Procurement | Thu May 14 08:00:00 IDT 2020 | Mon May 18 17:00:00 IDT 2020 | Wed May 06 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
602 | TT_TASK | MV Wire Procurement | Wed Aug 12 08:00:00 IDT 2020 | Tue Nov 03 17:00:00 IST 2020 | Tue Jul 21 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
603 | TT_TASK | Off-Site BIM Modeling & Coordination | Mon Apr 27 08:00:00 IDT 2020 | Sun May 24 17:00:00 IDT 2020 | Tue Apr 14 00:00:00 IDT 2020 | Tue May 05 00:00:00 IDT 2020 |  | COMPLETED
604 | TT_TASK | Neher Mcgrath Study | Thu Jul 02 08:00:00 IDT 2020 | Thu Aug 06 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Fri Jul 24 00:00:00 IDT 2020 |  | COMPLETED
605 | TT_TASK | URS Vault Procurement | Mon Sep 28 08:00:00 IDT 2020 | Wed Nov 11 17:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
607 | TT_TASK | Site Temp Power Procurement & Infrastructure | Mon Jun 29 08:00:00 IDT 2020 | Mon Aug 31 08:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
609 | TT_TASK | Underground Grounding Procurement | Mon Apr 27 08:00:00 IDT 2020 | Sun May 17 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Tue Apr 28 00:00:00 IDT 2020 |  | COMPLETED
610 | TT_TASK | BIM Modeling (Under ground) | Tue May 05 08:00:00 IDT 2020 | Mon Jun 08 17:00:00 IDT 2020 | Tue May 05 08:00:00 IDT 2020 | Mon Jun 08 00:00:00 IDT 2020 |  | COMPLETED
611 | TT_TASK | Electrical Long Lead Equipment Procurement (Cablebus, Panel Boards) | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Mon Apr 27 08:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
612 | TT_TASK | BIM Modeling (Above ground) | Sun Aug 02 08:00:00 IDT 2020 | Wed Sep 30 17:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
615 | TT_TASK | Design / Lead Time for Electrical/Telecom (OFCI Telecom BOM Materials) | Mon Aug 10 08:00:00 IDT 2020 | Sat Nov 07 17:00:00 IST 2020 | Wed Jul 01 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
616 | TT_TASK | Design / Lead Time for Busway (OFCI Starline BOM Materials) | Thu Nov 26 08:00:00 IST 2020 | Thu Jan 14 17:00:00 IST 2021 | Mon Sep 21 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
619 | TT_TASK | Water treatment Skids Procurement ( sourcing materials and Materail approval only) | Mon Apr 27 08:00:00 IDT 2020 | Fri Nov 06 12:00:00 IST 2020 | Tue Apr 07 00:00:00 IDT 2020 | Mon Jul 06 00:00:00 IDT 2020 |  | COMPLETED
620 | TT_TASK | Design / Lead Time for M&P overhead | Mon Jun 29 08:00:00 IDT 2020 | Tue Jul 28 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
621 | TT_TASK | Design / Lead Time for Fire Protection | Mon Aug 31 08:00:00 IDT 2020 | Tue Sep 29 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
622 | TT_TASK | Design / Lead Time for Fire Alarm | Mon Jun 29 08:00:00 IDT 2020 | Thu Aug 27 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
628 | TT_TASK | URS/UMS Concrete Anchor and Vault Design | Mon Aug 10 07:00:00 IDT 2020 | Wed Aug 26 17:00:00 IDT 2020 | Wed Aug 05 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
629 | TT_TASK | URS/UMS Vault Submiital Review by EOR | Mon Sep 14 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Fri Sep 25 00:00:00 IDT 2020 |  | COMPLETED
632 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-2 PSR(10/13) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sat Dec 12 17:00:00 IST 2020 | Tue Oct 13 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
633 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-3 PSR(9/28) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Mon Dec 28 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
634 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-4 PSR (10/28) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Fri Nov 27 16:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
635 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-1 PSR (9/19) to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Tue Dec 15 17:00:00 IST 2020 | Sat Sep 19 00:00:00 IDT 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
637 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-1 11/25 to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Fri Oct 09 17:00:00 IDT 2020 | Wed Nov 25 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
638 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-2 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sun Nov 15 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
639 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-4 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Fri Nov 06 16:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
640 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-3 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sun Nov 15 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
642 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-1 PSR 11/23 to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Wed Oct 14 17:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
643 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-2 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
644 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-4 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Wed Nov 11 16:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Sun Jan 03 00:00:00 IST 2021 |  | COMPLETED
645 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-3 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Sun Jan 03 00:00:00 IST 2021 |  | COMPLETED
647 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-1 12/7 to MSFT delivery) | Sat Jan 09 08:00:00 IST 2021 | Sat Jan 09 08:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
648 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-2 12/7 to MSFT delivery) | Tue Jan 05 08:00:00 IST 2021 | Tue Jan 05 08:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
649 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-4 12/18 to MSFT delivery) | Sat Jan 09 08:00:00 IST 2021 | Sat Jan 09 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
650 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-3 12/18 to MSFT delivery) | Thu Jan 14 08:00:00 IST 2021 | Thu Jan 14 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
653 | TT_TASK | Review Fluid Cooler wiring and devices buyout with Stetner | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Wed Sep 23 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
654 | TT_TASK | Change order release for fluid cooler wiring devices | Mon Oct 19 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 | Mon Oct 26 00:00:00 IST 2020 |  | COMPLETED
657 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
658 | TT_TASK | Fluid Cooler RI in place | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
659 | TT_TASK | Fluid Cooler Wire install and Term | Fri Mar 05 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
661 | TT_TASK | Fluid Cooler Panel installation | Tue Mar 23 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
662 | TT_TASK | Fluid Cooler RI in place | Thu Mar 18 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
663 | TT_TASK | Fluid Cooler Wire install and Term | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 |  | COMPLETED
665 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 15 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
666 | TT_TASK | Fluid Cooler RI in place | Fri Feb 19 07:00:00 IST 2021 | Thu Feb 25 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
667 | TT_TASK | Fluid Cooler Wire install and Term | Thu Mar 18 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
669 | TT_TASK | Fluid Cooler Panel installation | Thu Mar 18 07:00:00 IST 2021 | Mon Mar 22 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
670 | TT_TASK | Fluid Cooler RI in place | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
671 | TT_TASK | Fluid Cooler Wire install and Term | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
674 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 29 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
675 | TT_TASK | Fluid Cooler RI in place | Thu Mar 25 07:00:00 IST 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
676 | TT_TASK | Fluid Cooler Wire install and Term | Thu Apr 01 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
678 | TT_TASK | Fluid Cooler Panel installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
679 | TT_TASK | Fluid Cooler RI in place | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
680 | TT_TASK | Fluid Cooler Wire install and Term | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
682 | TT_TASK | Fluid Cooler Panel installation | Thu Apr 01 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Sat Mar 27 00:00:00 IDT 2021 |  | COMPLETED
683 | TT_TASK | Fluid Cooler RI in place | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
684 | TT_TASK | Fluid Cooler Wire install and Term | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
687 | TT_TASK | Fluid Cooler Panel installation | Tue May 04 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
688 | TT_TASK | Fluid Cooler RI in place | Fri May 07 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
689 | TT_TASK | Fluid Cooler Wire install and Term | Fri May 14 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
691 | TT_TASK | Fluid Cooler Panel installation | Mon May 17 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
692 | TT_TASK | Fluid Cooler RI in place | Thu May 20 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
693 | TT_TASK | Fluid Cooler Wire install and Term | Fri May 28 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
695 | TT_TASK | Fluid Cooler Panel installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
696 | TT_TASK | Fluid Cooler RI in place | Fri Jun 04 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
697 | TT_TASK | Fluid Cooler Wire install and Term | Fri Jun 11 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
700 | TT_TASK | Fluid Cooler Panel installation | Tue Jun 08 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
701 | TT_TASK | Fluid Cooler RI in place | Fri Jun 11 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
702 | TT_TASK | Fluid Cooler Wire install and Term | Sat Jun 19 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
704 | TT_TASK | Fluid Cooler Panel installation | Fri Jun 11 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
705 | TT_TASK | Fluid Cooler RI in place | Sat Jun 19 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
706 | TT_TASK | Fluid Cooler Wire install and Term | Sat Jun 26 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
708 | TT_TASK | Fluid Cooler Panel installation | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
709 | TT_TASK | Fluid Cooler RI in place | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
710 | TT_TASK | Fluid Cooler Wire install and Term | Tue Jul 13 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
712 | TT_TASK | Fluid Cooler Panel installation | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
713 | TT_TASK | Fluid Cooler RI in place | Tue Jul 13 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
714 | TT_TASK | Fluid Cooler Wire install and Term | Tue Jul 20 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
718 | TT_TASK | ADMIN Overhead Rough-in (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
719 | TT_TASK | ADMIN Electrical Room Build out (DRB#2) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
720 | TT_TASK | ADMIN Lighting installation (DRB#2) | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
742 | TT_TASK | Water Treatmant Skid Fabrication | Mon Sep 14 08:00:00 IDT 2020 | Mon Dec 07 17:00:00 IST 2020 | Tue Aug 25 00:00:00 IDT 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
743 | TT_TASK | L&I approval process | Mon Sep 14 08:00:00 IDT 2020 | Tue Oct 13 17:00:00 IDT 2020 | Tue Aug 25 00:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 |  | COMPLETED
745 | TT_TASK | Water treatment delivery COLO-1 | Mon Dec 21 08:00:00 IST 2020 | Sun Dec 27 17:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
750 | TT_TASK | Submit and approve Shop drawings for UPM junstion box | Mon Oct 19 08:00:00 IDT 2020 | Sun Nov 08 17:00:00 IST 2020 | Fri Oct 09 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
751 | TT_TASK | Lead time for junction box | Mon Nov 02 08:00:00 IST 2020 | Sun Dec 13 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
752 | TT_TASK | Fabrication and Delivery of PEMB pentrations support steel | Mon Nov 09 08:00:00 IST 2020 | Fri Nov 13 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
756 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
757 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Tue Dec 15 00:00:00 IST 2020 |  | COMPLETED
758 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
760 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
761 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
762 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Feb 13 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
763 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
764 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Mar 05 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
765 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
768 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
769 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
770 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Feb 08 08:00:00 IST 2021 | Thu Feb 11 08:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
772 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
773 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
774 | TT_TASK | Install additional Cable bus (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
775 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
776 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Mar 02 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
777 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
780 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
781 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Tue Dec 15 00:00:00 IST 2020 |  | COMPLETED
782 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
784 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
785 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
786 | TT_TASK | Install additional Cable bus (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
787 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
788 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
789 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
792 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Dec 04 07:00:00 IST 2020 | Wed Dec 09 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
793 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
794 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
796 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
797 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
798 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 03 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
799 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
800 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Thu Mar 04 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
801 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
803 | TT_TASK | COLO-1 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon Mar 22 07:00:00 IST 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
804 | TT_TASK | COLO-1 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon Apr 05 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
805 | TT_TASK | COLO-1 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
806 | TT_TASK | COLO-1 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
810 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Sat Jan 02 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
811 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
812 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
814 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
815 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
816 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
817 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
818 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
819 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
822 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
823 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Thu Feb 11 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
824 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Mar 26 07:00:00 IDT 2021 | Mon Mar 29 17:00:00 IDT 2021 | Sat Feb 27 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
826 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
827 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
828 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
829 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
830 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
831 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
834 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
835 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
836 | TT_TASK | Install added DRB#3 Tray and conduit | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
838 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Sat Mar 27 00:00:00 IDT 2021 |  | COMPLETED
839 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 |  | COMPLETED
840 | TT_TASK | Install additional Cable bus (DRB#3) | Mon May 03 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
841 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
842 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue May 04 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
843 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
846 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
847 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Thu Feb 11 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
848 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 02 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
850 | TT_TASK | Install MER Supply duct | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
851 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri May 07 07:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
852 | TT_TASK | Install additional Cable bus (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
853 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue May 04 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
854 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
855 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 |  | COMPLETED
857 | TT_TASK | COLO-2 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Fri Apr 30 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
858 | TT_TASK | COLO-2 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
859 | TT_TASK | COLO-2 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 03 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
860 | TT_TASK | COLO-2 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
864 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
865 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
866 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
868 | TT_TASK | Install MER Supply duct | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
869 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
870 | TT_TASK | Install Roxtec block sealing and Install added tray cable (DRB#3) | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
871 | TT_TASK | Install additional Cable bus (DRB#3) | Tue May 18 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
872 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
873 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
876 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
877 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
878 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
880 | TT_TASK | Install MER Supply duct | Mon May 24 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
881 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
882 | TT_TASK | Install additional Cable bus (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
883 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 |  | COMPLETED
884 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Sat Aug 14 07:00:00 IDT 2021 | Sat Aug 14 17:00:00 IDT 2021 |  | COMPLETED
885 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Fri Sep 03 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Thu Aug 26 00:00:00 IDT 2021 |  | COMPLETED
888 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
889 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 |  | COMPLETED
890 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
892 | TT_TASK | Install MER Supply duct | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
893 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 |  | COMPLETED
894 | TT_TASK | Install additional Cable bus (DRB#3) | Sat May 29 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
895 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
896 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 |  | COMPLETED
897 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Mon Aug 09 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
900 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
901 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
902 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
904 | TT_TASK | Install MER Supply duct | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
905 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
906 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jun 05 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
907 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
908 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
909 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
911 | TT_TASK | COLO-3 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
912 | TT_TASK | COLO-3 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 |  | COMPLETED
913 | TT_TASK | COLO-3 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
914 | TT_TASK | COLO-3 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
918 | TT_TASK | Sure steel - PEMB MER penetration framing | Thu Feb 11 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
919 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
920 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
922 | TT_TASK | Install MER Supply duct | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
923 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Thu Jul 08 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
924 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
925 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
926 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
927 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
930 | TT_TASK | Sure steel - PEMB MER penetration framing | Tue Feb 16 07:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
931 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
932 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
934 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
935 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
936 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
937 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Fri Sep 03 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 |  |  | 400.0 | NOT_STARTED
938 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
939 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Sat Oct 02 07:00:00 IDT 2021 | Fri Oct 08 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
942 | TT_TASK | Sure steel - PEMB MER penetration framing | Thu Feb 11 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
943 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
944 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
946 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
947 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Thu Jul 08 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 |  | COMPLETED
948 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Jul 28 00:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 |  | COMPLETED
949 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
950 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
951 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
954 | TT_TASK | Sure steel - PEMB MER penetration framing | Tue Feb 16 07:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
955 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
956 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 00:00:00 IDT 2021 |  | COMPLETED
958 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
959 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
960 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
961 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
962 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
963 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
965 | TT_TASK | COLO-4 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Thu Sep 09 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
966 | TT_TASK | COLO-4 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Wed Aug 18 00:00:00 IDT 2021 |  |  | IN_PROGRESS
967 | TT_TASK | COLO-4 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
968 | TT_TASK | COLO-4 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
970 | TT_TASK | Site Shut Down - 9/9/2020 | Mon Sep 14 07:00:00 IDT 2020 | Mon Sep 14 17:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 |  | COMPLETED
971 | TT_TASK | Site Shut Down - 9/10/2020 | Tue Sep 15 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Thu Sep 10 00:00:00 IDT 2020 | Thu Sep 10 00:00:00 IDT 2020 |  | COMPLETED
972 | TT_TASK | Site Shut Down - 9/11/2020 | Wed Sep 16 07:00:00 IDT 2020 | Wed Sep 16 17:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
973 | TT_TASK | Site Shut Down - 9/12/2020 | Thu Sep 17 07:00:00 IDT 2020 | Thu Sep 17 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
974 | TT_TASK | Site Shut Down - 9/14/2020 | Mon Sep 28 07:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 |  | COMPLETED
975 | TT_TASK | Site Shut Down - 9/15/2020 | Tue Sep 29 07:00:00 IDT 2020 | Tue Sep 29 17:00:00 IDT 2020 | Tue Sep 15 00:00:00 IDT 2020 | Tue Sep 15 00:00:00 IDT 2020 |  | COMPLETED
976 | TT_TASK | Site Shut Down - 9/16/2020 | Wed Sep 30 07:00:00 IDT 2020 | Wed Sep 30 17:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 |  | COMPLETED
979 | TT_TASK | Complete Remaining IWW piping to tie-in point | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 29 17:00:00 IST 2020 | Mon Sep 21 00:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
980 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
982 | TT_TASK | Complete Remaining Sanitary piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
983 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
985 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
986 | TT_TASK | Complete Remaining Fire Main piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
988 | TT_TASK | Complete Remaining ITW piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
989 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
991 | TT_TASK | Complete Remaining Telecom Duct Back (excluding Tie-in) | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
992 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
995 | TT_TASK | Delay in COLO-1- Cell-1 MER Delivery (Duration = COLO1 Cell-1 PSR(11/6/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sat Jan 30 17:00:00 IST 2021 | Fri Nov 06 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
996 | TT_TASK | Delay in COLO-1- Cell-2 MER Delivery (Duration = COLO1 Cell-2 PSR(11/13/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Fri Jan 29 17:00:00 IST 2021 | Fri Nov 13 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
997 | TT_TASK | Delay in COLO-1- Cell-3 MER Delivery (Duration = COLO1 Cell-3 PSR(11/20/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Feb 04 17:00:00 IST 2021 | Fri Nov 20 00:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 |  | COMPLETED
998 | TT_TASK | Delay in COLO-1- Cell-4 MER Delivery (Duration = COLO1 Cell-4 PSR(11/30/20) to MSFT delivery) | Mon Feb 01 08:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1000 | TT_TASK | Delay in COLO-2- Cell-1 MER Delivery (Duration = Colo1 Cell-1 PSR(12/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Feb 11 10:00:00 IST 2021 | Tue Dec 15 00:00:00 IST 2020 | Wed Feb 03 00:00:00 IST 2021 |  | COMPLETED
1001 | TT_TASK | Delay in COLO-2- Cell-2 MER Delivery (Duration = COLO 2 Cell-2 PSR(12/22/20) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1002 | TT_TASK | Delay in COLO-2- Cell-3 MER Delivery (Duration = COLO 2- Cell-3 PSR(12/28/20) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1003 | TT_TASK | Delay in COLO-2- Cell-4 MER Delivery (Duration = COLO 2- Cell-4 PSR(1/5/21) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Jan 05 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1005 | TT_TASK | Delay in COLO-3- Cell-1 MER Delivery (Duration = COLO-3 Cell-1 PSR(1/29/21) to MSFT delivery) | Sun Jan 31 08:00:00 IST 2021 | Sat Apr 03 17:00:00 IDT 2021 | Fri Jan 29 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1006 | TT_TASK | Delay in COLO-3- Cell-2 MER Delivery (Duration = COLO-3 Cell-2 PSR(2/5/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 05 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1007 | TT_TASK | Delay in COLO-3 Cell-3 MER Delivery (Duration = COLO-3 Cell-3 PSR(2/12/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Feb 12 00:00:00 IST 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1008 | TT_TASK | Delay in COLO-3 Cell-4 MER Delivery (Duration = COLO-3 Cell-4 PSR(2/19/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Thu Apr 22 00:00:00 IDT 2021 |  | COMPLETED
1010 | TT_TASK | Delay in COLO-4- Cell-1 MER Delivery (Duration= COLO-4 Cell-1 PSR(3/12/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Mar 12 00:00:00 IST 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
1011 | TT_TASK | Delay in COLO-4- Cell-2 MER Delivery (Duration = COLO-4 Cell-2 PSR(3/19/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1012 | TT_TASK | Delay in COLO-4- Cell-3 MER Delivery (Duration = COLO-4 Cell-3 PSR(3/26/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1013 | TT_TASK | Delay in COLO-4- Cell-4 MER Delivery (Duration = COLO-4 Cell-4 PSR(4/2/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 | Sun May 09 00:00:00 IDT 2021 |  | COMPLETED
1015 | TT_TASK | Wire Mesh Procurement | Mon Nov 16 08:00:00 IST 2020 | Wed Dec 23 12:00:00 IST 2020 | Thu Sep 24 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
1016 | TT_TASK | Wire Mesh Submittal Approval | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Wed Sep 16 00:00:00 IDT 2020 | Wed Sep 23 00:00:00 IDT 2020 |  | COMPLETED
1017 | TT_TASK | Wire Mesh Procurement Delay | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Sat Oct 24 00:00:00 IDT 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1019 | TT_TASK | Complete Remaining Telecom Duct Back tie-in Install to MWH02 | Mon Dec 21 07:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1020 | TT_TASK | Clayco waiting on MSOW Approval | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Tue Dec 01 00:00:00 IST 2020 |  | COMPLETED
1021 | TT_TASK | Clayco MSOW Submited for approval | Mon Nov 16 07:00:00 IST 2020 | Tue Nov 17 17:00:00 IST 2020 | Fri Oct 16 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
1022 | TT_TASK | MSFT Stand down/ Additional Hydro excavation | Mon Dec 21 07:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
1024 | TT_TASK | Delay in UMS delivery (Duration = (9/19) to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Thu Nov 19 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
1027 | TT_TASK | Delay In COLO-1 Cell-1 Generator (Duration= COLO-1 Cell-1 PSR(9/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Tue Jan 19 17:00:00 IST 2021 | Tue Sep 15 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1028 | TT_TASK | Delay In COLO-1 Cell-2 Generator (Duration= COLO-1 Cell-2 PSR(9/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sat Feb 06 17:00:00 IST 2021 | Tue Sep 15 00:00:00 IDT 2020 | Mon Nov 02 00:00:00 IST 2020 |  | COMPLETED
1029 | TT_TASK | Delay In COLO-1 Cell-4 Generator (Duration= COLO-1 Cell-4 PSR(9/29/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Sep 29 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1030 | TT_TASK | Delay In COLO-1 Cell-3 Generator (Duration= COLO-1 Cell-3 PSR(9/29/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Wed Feb 03 17:00:00 IST 2021 | Tue Sep 29 00:00:00 IDT 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1032 | TT_TASK | Delay In COLO-2 Cell-1 Generator (Duration= COLO-2 Cell-1 PSR(10/12/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sun Mar 07 17:00:00 IST 2021 | Mon Oct 12 00:00:00 IDT 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1033 | TT_TASK | Delay In COLO-2 Cell-2 Generator (Duration= COLO-2 Cell-2 PSR(11/6/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sun Feb 21 17:00:00 IST 2021 | Fri Nov 06 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
1034 | TT_TASK | Delay In COLO-2 Cell-4 Generator (Duration= COLO-2 Cell-4 PSR(11/21/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Fri Feb 19 17:00:00 IST 2021 | Sat Nov 21 00:00:00 IST 2020 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
1035 | TT_TASK | Delay In COLO-2 Cell-3 Generator (Duration= COLO-2 Cell-3 PSR(10/22/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Mar 18 17:00:00 IST 2021 | Thu Oct 22 00:00:00 IDT 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1037 | TT_TASK | 6.1.39.1- COLO-3 CEll-1 GEN Belly tank Failed pressure test | Mon Mar 15 07:00:00 IST 2021 | Fri Apr 09 17:00:00 IDT 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
1038 | TT_TASK | 6.1.39.2- COLO-3 Cell-1 Replace Belly Tank and Set GEN | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1039 | TT_TASK | Delay In COLO-3 Cell-1 Generator (Duration= COLO-3 Cell-1 PSR(10/12/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Sat May 08 17:00:00 IDT 2021 | Mon Nov 09 00:00:00 IST 2020 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1040 | TT_TASK | Delay In COLO-3 Cell-2 Generator (Duration= COLO-3 Cell-2 PSR(11/6/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Tue Mar 30 17:00:00 IDT 2021 | Sat Nov 21 00:00:00 IST 2020 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
1041 | TT_TASK | Delay In COLO-3 Cell-4 Generator (Duration= COLO-3 Cell-4 PSR(11/21/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Mar 18 17:00:00 IST 2021 | Wed Dec 09 00:00:00 IST 2020 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
1042 | TT_TASK | Delay In COLO-3 Cell-3 Generator (Duration= COLO-3 Cell-3 PSR(10/22/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Apr 29 17:00:00 IDT 2021 | Thu Nov 05 00:00:00 IST 2020 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1044 | TT_TASK | Delay In COLO-4 Cell-1 Generator (Duration= COLO-4 Cell-1 PSR(10/12/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Sat Jun 05 17:00:00 IDT 2021 | Mon Nov 09 00:00:00 IST 2020 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
1045 | TT_TASK | Delay In COLO-4 Cell-2 Generator (Duration= COLO-4 Cell-2 PSR(11/6/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Apr 01 17:00:00 IDT 2021 | Wed Dec 09 00:00:00 IST 2020 | Thu Mar 11 00:00:00 IST 2021 |  | COMPLETED
1046 | TT_TASK | Delay In COLO-4 Cell-4 Generator (Duration= COLO-4 Cell-4 PSR(11/21/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Wed Apr 14 17:00:00 IDT 2021 | Mon Nov 30 00:00:00 IST 2020 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
1047 | TT_TASK | Delay In COLO-4 Cell-3 Generator (Duration= COLO-4 Cell-3 PSR(10/22/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Tue May 11 17:00:00 IDT 2021 | Fri Nov 20 00:00:00 IST 2020 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1050 | TT_TASK | COLO1 CELL1 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1051 | TT_TASK | COLO1 CELL3 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
1052 | TT_TASK | COLO1 CELL2 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1053 | TT_TASK | COLO1 CELL4 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
1058 | TT_TASK | COLO-1 Cell-1 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1059 | TT_TASK | COLO1 CELL1 Interior MER conduit installation utility side | Fri Mar 05 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1060 | TT_TASK | COLO-1 Cell-1 Interior MER conduit installation building side Complete March1st (MER discovery Corrections & Signoff) | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1063 | TT_TASK | COLO-1 CELL3 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1064 | TT_TASK | COLO1 CELL3 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1065 | TT_TASK | COLO-1 CELL3 Interior MER conduit installation building side | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
1068 | TT_TASK | COLO-1 CELL2 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1069 | TT_TASK | COLO1 CELL2 Interior MER conduit installation utility side | Sat Mar 06 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1070 | TT_TASK | COLO-1 CELL2 Interior MER conduit installation building side | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1073 | TT_TASK | COLO-1 CELL4 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1074 | TT_TASK | COLO1 CELL4 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1075 | TT_TASK | COLO-1 CELL4 Interior MER conduit installation building side | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
1079 | TT_TASK | COLO-2 Cell-1 Rearrange Roxtec blocks per coordination layout | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1080 | TT_TASK | COLO2 CELL1 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1081 | TT_TASK | COLO-2 Cell-1 Interior MER conduit installation building side | Mon Apr 05 07:00:00 IDT 2021 | Mon Apr 19 17:00:00 IDT 2021 | Fri Mar 05 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1089 | TT_TASK | COLO-1 Cell-1 MER Flex Conduit fixes | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1090 | TT_TASK | COLO-1 Cell-3 MER Flex Conduit fixes | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1091 | TT_TASK | COLO-1 Cell-2 MER Flex Conduit fixes | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1092 | TT_TASK | COLO-1 Cell-4 MER Flex Conduit fixes | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1095 | TT_TASK | Safety Stop work due to failed Starline Hangers | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 01 07:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
1096 | TT_TASK | Lead time for replacement hangers from Starline | Mon Feb 01 08:00:00 IST 2021 | Sun Feb 07 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
1097 | TT_TASK | COLO-1 Cell-1 Remove/ Replace busway & hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1098 | TT_TASK | COLO-1 Cell-3 Remove/ Replace busway & hangers | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1099 | TT_TASK | COLO-1 Cell-2 Remove/ Replace busway & hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1100 | TT_TASK | COLO-1 Cell-4 Remove/ Replace busway & hangers | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1101 | TT_TASK | Determined Startline hanger Design Issue & Approve replacement hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
1102 | TT_TASK | COLO-2 Cell-1 Remove/ Replace busway & hangers | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1103 | TT_TASK | COLO-2 Cell-2 Remove/ Replace busway & hangers | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1105 | TT_TASK | Lead time for missing Admin Gen Bussing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 |  | COMPLETED
1106 | TT_TASK | Admin Gen Bussing Install | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1107 | TT_TASK | Awaiting DCE approval of Non NEMA standard Lugs | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1108 | TT_TASK | Awaiting Phase conductor lugs from NC power as per RFI#412 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1109 | TT_TASK | 6.1.41 - Incorrect Lugs for Admin Gen Main Bussing | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1112 | TT_TASK | COLO-1 Cell-4 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
1113 | TT_TASK | COLO-1 Cell-3 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Thu Mar 11 00:00:00 IST 2021 |  | COMPLETED
1114 | TT_TASK | COLO-1 Cell-2 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1115 | TT_TASK | COLO-1 Cell-1 SE Install UPS batteries in cabinet | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1117 | TT_TASK | COLO-2 Cell-1 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
1118 | TT_TASK | COLO-2 Cell-2 SE Install UPS batteries in cabinet | Fri Apr 30 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
1119 | TT_TASK | COLO-2 Cell-3 SE Install UPS batteries in cabinet | Sat May 08 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1120 | TT_TASK | COLO-2 Cell-4 SE Install UPS batteries in cabinet | Sat May 15 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
1122 | TT_TASK | COLO-3 Cell-1 SE Install UPS batteries in cabinet | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1123 | TT_TASK | COLO-3 Cell-2 SE Install UPS batteries in cabinet | Tue May 25 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1124 | TT_TASK | COLO-3 Cell-3 SE Install UPS batteries in cabinet | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1125 | TT_TASK | COLO-3 Cell-4 SE Install UPS batteries in cabinet | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1127 | TT_TASK | COLO-4 Cell-1 SE Install UPS batteries in cabinet | Tue Sep 14 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1128 | TT_TASK | COLO-4 Cell-2 SE Install UPS batteries in cabinet | Wed Sep 29 07:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  | 320.0 | IN_PROGRESS
1129 | TT_TASK | COLO-4 Cell-3 SE Install UPS batteries in cabinet | Tue Sep 07 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
1130 | TT_TASK | COLO-4 Cell-4 SE Install UPS batteries in cabinet | Tue Sep 21 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
1132 | TT_TASK | COLO-2 CEll-2 Awaiting SE Revised tool Come along for MER Lift & Set | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
1133 | TT_TASK | COLO-2 CEll-3 Awaiting SE Revised tool Come along for MER Lift & Set | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1134 | TT_TASK | MER shipping split connection Safety Standown & RCA Review | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1137 | TT_TASK | COLO-2 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1138 | TT_TASK | RFI#432 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
1139 | TT_TASK | Lead time for tube steel | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
1140 | TT_TASK | COLO-2 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1141 | TT_TASK | COLO-2 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Thu Apr 01 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1142 | TT_TASK | COLO-2 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1144 | TT_TASK | COLO-3 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Fri May 07 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 |  | COMPLETED
1145 | TT_TASK | COLO-3 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Wed May 19 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed May 19 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 |  | COMPLETED
1146 | TT_TASK | COLO-3 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Thu May 13 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Thu May 13 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 |  | COMPLETED
1147 | TT_TASK | COLO-3 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Wed May 26 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Wed May 26 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 |  | COMPLETED
1149 | TT_TASK | COLO-4 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1150 | TT_TASK | COLO-4 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1151 | TT_TASK | COLO-4 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1152 | TT_TASK | COLO-4 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Mon Jun 14 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1154 | TT_TASK | All Construction activities -Safety Standown due to Admin Gen unplanned Energization | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
1156 | TT_TASK | COLO-1 Cell-1 Field Modification of tray | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1157 | TT_TASK | COLO-1 Cell-2 Field Modification of tray | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Jan 21 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1160 | TT_TASK | #3. Snow- 1/27/2021(one full day) | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 |  | COMPLETED
1161 | TT_TASK | #4. Extreme Heat - 6/28/21- 7/2/21(Effecting COLO-4 Yard work) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
1162 | TT_TASK | #5 Extreme heat -production loss in Yards 7/1/21 through 7/14/21 (11 half days of loss) | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 09 00:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
1163 | TT_TASK | #6 Extreme heat - Production loss in Yards 7/15/21 through 7/31/21 (3 half days) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
1164 | TT_TASK | #1. Rain And High Winds- 10/13/2020(half day only) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Tue Oct 13 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1165 | TT_TASK | #2. Snow -12/30/20 (one full day) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Wed Dec 30 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
1168 | TT_TASK | COLO-1 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Mon Jan 11 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
1169 | TT_TASK | COLO-1 CELL-3 WA State L&I onsite inspection & Approval to Connect to MER | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1170 | TT_TASK | COLO-1 CELL-2 WA State L&I onsite inspection & Approval to Connect to MER | Sat Jan 23 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1171 | TT_TASK | COLO-1 CELL-4 WA State L&I onsite inspection & Approval to Connect to MER | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1173 | TT_TASK | COLO-2 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Fri Mar 12 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1174 | TT_TASK | COLO-2 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Tue Mar 23 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1175 | TT_TASK | COLO-2 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
1176 | TT_TASK | COLO-2 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Fri Apr 09 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1178 | TT_TASK | COLO-3 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Sat May 08 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1179 | TT_TASK | COLO-3 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Fri May 14 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1180 | TT_TASK | COLO-3 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1181 | TT_TASK | COLO-3 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1183 | TT_TASK | COLO-4 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 |  | COMPLETED
1184 | TT_TASK | COLO-4 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Sat Jun 19 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1185 | TT_TASK | COLO-4 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
1186 | TT_TASK | COLO-4 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 |  | COMPLETED
1189 | TT_TASK | 6.1.36 Rework for Addtional circuits for UMS URS Battery charger feed upsize | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1190 | TT_TASK | 6.1.34.1 COLO-1 Cell-1 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1191 | TT_TASK | 6.1.34.2 COLO-1 Cell-2 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1192 | TT_TASK | 6.1.34.3 COLO-1 Cell-3 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 |  | COMPLETED
1193 | TT_TASK | 6.1.34.4 COLO-1 Cell-4 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 |  | COMPLETED
1194 | TT_TASK | 6.1.01.0 Awaiting MER 10A HRG's (lead time= 8 weeks from 2/2/2021) | Mon Mar 01 07:00:00 IST 2021 | Mon Apr 12 17:00:00 IDT 2021 | Tue Feb 02 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
1195 | TT_TASK | 6.1.09 Awaiting Rev-D for Coordination study (DRB3/SCCS/ Submittal Breaker verification) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1196 | TT_TASK | 6.1.26.1 L2/L3 Scripts SE MER overall Script | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
1197 | TT_TASK | 6.1.33 URS UMS Ground Buss hole Pattern | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1198 | TT_TASK | 6.1.35 UPS battery IR Scanning | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1199 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-1 Cell-1 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1200 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-1 Cell-4 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1201 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-1 Cell-3 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1202 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-1 Cell-2 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1203 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-2 Cell-1 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1204 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-2 Cell-2 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1205 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-2 Cell-3 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1206 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-2 Cell-4 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue Jul 13 00:00:00 IDT 2021 | Mon Jul 19 00:00:00 IDT 2021 |  | COMPLETED
1207 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-3 Cell-1 | Tue Aug 31 07:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
1208 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-3 Cell-4 | Tue Sep 07 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  |  | 10.0 | NOT_STARTED
1209 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-3 Cell-3 | Tue Sep 07 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  |  | 10.0 | NOT_STARTED
1210 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-3 Cell-2 | Thu Sep 09 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1211 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-4 Cell-1 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1212 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-4 Cell-4 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1213 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-4 Cell-3 | Mon Oct 18 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1214 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-4 Cell-2 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1216 | TT_TASK | 6.1.37- 6.2.01- Ground Fault setting on COLO-2 Gen MCB01 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Wed Apr 28 17:00:00 IDT 2021 |  | COMPLETED
1218 | TT_TASK | 6.1.38 PDU MCB01 LOTO Provisions | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1220 | TT_TASK | 6.1.11 Awaiting BAS Backplanes from Siemens to VECA for Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
1221 | TT_TASK | 6.1.26.2 L2/L3 Scripts Siemens BAS SAT Scripts | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1222 | TT_TASK | 6.1.11 Awaiting Liftstation #3 BAS Backplanes from Siemens to VECA for Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1223 | TT_TASK | 6.1.11 Liftstation #3 BAS Install / Pull wire / term Backplanes | Mon May 17 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 |  | COMPLETED
1226 | TT_TASK | COLO-2 Cell-1 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Dec 29 00:00:00 IST 2020 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1227 | TT_TASK | COLO-2 Cell-2 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sun Jan 10 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1228 | TT_TASK | COLO-2 Cell-3 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Jan 20 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1229 | TT_TASK | COLO-2 Cell-4 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sat Jan 23 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1231 | TT_TASK | COLO-3 Cell-1 Install Missing Raceway & Bussing within generator | Mon Apr 26 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1232 | TT_TASK | COLO-3 Cell-2 Install Missing Raceway & Bussing within generator | Thu Apr 29 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1233 | TT_TASK | COLO-3 Cell-3 Install Missing Raceway & Bussing within generator | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
1234 | TT_TASK | COLO-3 Cell-4 Install Missing Raceway & Bussing within generator | Tue May 04 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1236 | TT_TASK | COLO-4 Cell-1 Install Missing Raceway & Bussing within generator | Tue May 25 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
1237 | TT_TASK | COLO-4 Cell-2 Install Missing Raceway & Bussing within generator | Tue May 11 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1238 | TT_TASK | COLO-4 Cell-3 Install Missing Raceway & Bussing within generator | Thu May 20 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1239 | TT_TASK | COLO-4 Cell-4 Install Missing Raceway & Bussing within generator | Mon May 17 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
1242 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1243 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 2weeks- fab and ship | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Mon Apr 05 00:00:00 IDT 2021 |  | COMPLETED
1244 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 1 week to install | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
1245 | TT_TASK | 6.1.44- MER Battery Monitoring Software Â– Constraint to EPMS checkouts/Point Â– Point(needed by 4/23) | Mon Mar 15 07:00:00 IST 2021 | Mon Jun 07 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Aug 07 07:00:00 IDT 2021 |  | COMPLETED
1246 | TT_TASK | 6.1.46- Site UPM Inspections | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
1247 | TT_TASK | 6.1.47- COLO-1 Cell-2 UPS01- Factory Test thermal event | Mon Mar 15 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
1249 | TT_TASK | 6.1.40- 480V house power to Gen Enclousure is Fed OH vs UG | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1254 | TT_TASK | Downtime awaiting solution for safety space constraint | Mon Apr 26 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1256 | TT_TASK | NOPC-18 Remove COLO-1 Cell-1 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1257 | TT_TASK | Rubicon MSB inspection complete (ready for transformer reinstall) | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Mon Apr 26 07:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1258 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-1 transformer | Tue May 25 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1260 | TT_TASK | NOPC-18 Remove COLO-1 Cell-2 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
1261 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1262 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-2 transformer | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1264 | TT_TASK | NOPC-18 Remove COLO-1 Cell-3 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 |  | COMPLETED
1265 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1266 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-3 transformer | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1268 | TT_TASK | NOPC-18 Remove COLO-1 Cell-4 transformer | Mon May 17 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1269 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1270 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-4 transformer | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1273 | TT_TASK | NOPC-18 Remove COLO-2 Cell-1 transformer | Tue Jun 01 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue Jun 08 00:00:00 IDT 2021 |  | COMPLETED
1274 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-1 transformer | Thu Jul 22 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1276 | TT_TASK | NOPC-18 Remove COLO-2 Cell-2 transformer | Wed Jun 02 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
1277 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-2 transformer | Fri Jul 23 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
1279 | TT_TASK | NOPC-18 Remove COLO-2 Cell-3 transformer | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 |  | COMPLETED
1280 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-3 transformer | Thu Jul 29 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1282 | TT_TASK | NOPC-18 Remove COLO-2 Cell-4 transformer | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1283 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-4 transformer | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Jul 09 00:00:00 IDT 2021 | Mon Jul 12 00:00:00 IDT 2021 |  | COMPLETED
1286 | TT_TASK | NOPC-18 Remove COLO-3 Cell-1 transformer | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
1287 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-1 transformer | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 22 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1289 | TT_TASK | NOPC-18 Remove COLO-3 Cell-2 transformer | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jul 24 07:00:00 IDT 2021 | Sat Jul 24 17:00:00 IDT 2021 |  | COMPLETED
1290 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-2 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
1292 | TT_TASK | NOPC-18 Remove COLO-3 Cell-3 transformer | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Thu Aug 19 07:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1293 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-3 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1295 | TT_TASK | NOPC-18 Remove COLO-3 Cell-4 transformer | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1296 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-4 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1299 | TT_TASK | NOPC-18 Remove COLO-4 Cell-1 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1300 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-1 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1302 | TT_TASK | NOPC-18 Remove COLO-4 Cell-2 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1303 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-2 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1305 | TT_TASK | NOPC-18 Remove COLO-4 Cell-3 transformer | Wed Sep 29 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1306 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-3 transformer | Sat Oct 09 07:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1308 | TT_TASK | NOPC-18 Remove COLO-4 Cell-4 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1309 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-4 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1311 | TT_TASK | PDU termination crew downtime due to COVID-19 | Sat Apr 24 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Sat Apr 24 07:00:00 IDT 2021 |  | COMPLETED
1314 | TT_TASK | 6.2.03- Replace ADP01 faulty trip units | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1315 | TT_TASK | 6.1.51-COLO-1 Cell-1,2 Factory conductors not terminated per drawings | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1316 | TT_TASK | 6.1.49 - COLO-1 Cell-1 Awaiting Ground Lug solution, procurement, installation of labelling ATS 01-06 | Fri Apr 30 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
1317 | TT_TASK | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
1318 | TT_TASK | 6.1.53-COLO-1 Cell-1,2 UPS01, PNL01 awaiting missing breakers | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1319 | TT_TASK | 6.1.53-COLO-1 Cell-1,2,3,4 UPS01, PNL01 Install/ term Missing breakers | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1320 | TT_TASK | 6.1.59 (6.1.51 carryover) -COLO-1 Cell-1,2 Factory conductors exertherm corrections | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
1321 | TT_TASK | 6.1.50- SCCS Revision#10 (RFI-540) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1325 | TT_TASK | 6.1.54- TCM Awaiting Admin Siemens Break tank parts | Mon May 17 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1326 | TT_TASK | 6.1.54- Install Breaktank parts | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1328 | TT_TASK | 6.2.03- Replace Damaged UPM in COLO-4 Cell-4 | Thu May 06 07:00:00 IDT 2021 | Sat May 08 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1330 | TT_TASK | 6.1.55-COLO-1 - FC Factoy Re-wire (RFI-502) | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1331 | TT_TASK | 6.1.55-COLO-2 - FC Factoy Re-wire (RFI-502) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1332 | TT_TASK | 6.1.55-COLO-3 - FC Factoy Re-wire (RFI-502) | Sat Jun 05 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1333 | TT_TASK | 6.1.55-COLO-4 - FC Factoy Re-wire (RFI-502) | Thu Jun 10 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1335 | TT_TASK | 6.1.57 -Awaiting revised coordination study #9 | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
1336 | TT_TASK | Reprint revised panel 3,4 Arc flash labels | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1337 | TT_TASK | Print new DC Arc flash labels for Admin ELP | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1340 | TT_TASK | 6.1.58-RFI-528- COLO-1 - SF/RF Circuitry & terminal block rework | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
1341 | TT_TASK | 6.1.63- COLO1-UPS01-PNL01 Compass Issues Constraining L3Â’s | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
1342 | TT_TASK | 6.1.56 - COLO-1 Awaiting MSB/ADP Ground Lug replacements, Installation of labelling | Fri Apr 30 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
1349 | TT_TASK | All trades stand down | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
1350 | TT_TASK | Veca standown | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
1353 | TT_TASK | COLO-1 Cell-1 MER-UPS Battery Disconnect modifications rework | Wed Jun 16 07:00:00 IDT 2021 | Sat Jun 19 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1354 | TT_TASK | COLO-1 Cell-2 MER-UPS Battery Disconnect modifications rework | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1355 | TT_TASK | COLO-1 Cell-3 MER-UPS Battery Disconnect modifications rework | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
1356 | TT_TASK | COLO-1 Cell-4 MER-UPS Battery Disconnect modifications rework | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
1357 | TT_TASK | RFI-548 COLO MSB to UPS Battery disconnect solution approval | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1358 | TT_TASK | ADMIN-UPS Battery Disconnect modifications rework | Wed Jun 16 07:00:00 IDT 2021 | Sat Jun 19 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1359 | TT_TASK | RFI-552 Admin MSB to UPS Battery disconnect solution approval | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
1361 | TT_TASK | COLO-2 Cell-2 MER-UPS Battery Disconnect modifications rework | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 |  | COMPLETED
1362 | TT_TASK | COLO-2 Cell-1 MER-UPS Battery Disconnect modifications rework | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  | COMPLETED
1363 | TT_TASK | COLO-2 Cell-3 MER-UPS Battery Disconnect modifications rework | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  | COMPLETED
1364 | TT_TASK | COLO-2 Cell-4 MER-UPS Battery Disconnect modifications rework | Fri Jul 02 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 23 07:00:00 IDT 2021 |  | COMPLETED
1366 | TT_TASK | COLO-3 Cell-1 MER-UPS Battery Disconnect modifications rework | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 |  | COMPLETED
1367 | TT_TASK | COLO-3 Cell-2 MER-UPS Battery Disconnect modifications rework | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1368 | TT_TASK | COLO-3 Cell-3 MER-UPS Battery Disconnect modifications rework | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
1369 | TT_TASK | COLO-3 Cell-4 MER-UPS Battery Disconnect modifications rework | Sat Sep 11 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Mon Aug 16 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1371 | TT_TASK | COLO-4 Cell-1 MER-UPS Battery Disconnect modifications rework | Thu Sep 16 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
1372 | TT_TASK | COLO-4 Cell-2 MER-UPS Battery Disconnect modifications rework | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
1373 | TT_TASK | COLO-4 Cell-3 MER-UPS Battery Disconnect modifications rework | Mon Sep 27 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1374 | TT_TASK | COLO-4 Cell-4 MER-UPS Battery Disconnect modifications rework | Fri Sep 03 07:00:00 IDT 2021 | Thu Sep 09 17:00:00 IDT 2021 |  |  | 270.0 | NOT_STARTED
1377 | TT_TASK | COLO-3 Cell-3 Remove inaccessible tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 |  | COMPLETED
1378 | TT_TASK | COLO-3 CEll-3 Reinstall tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
1379 | TT_TASK | COLO-3 Cell-4 Remove inaccessible tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Sat Jun 12 00:00:00 IDT 2021 |  | COMPLETED
1380 | TT_TASK | COLO-3 Cell-4 Reinstall tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1381 | TT_TASK | COLO-4 Cell-1 Remove inaccessible tray in MER | Mon Jul 12 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Sat Jun 12 00:00:00 IDT 2021 |  | COMPLETED
1382 | TT_TASK | COLO-4 Cell-1 Reinstall tray in MER | Tue Aug 03 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
1383 | TT_TASK | COLO-4 Cell-2 Remove inaccessible tray in MER | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
1384 | TT_TASK | COLO-4 Cell-2 Reinstall tray in MER | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1385 | TT_TASK | COLO-4 Cell-3 Remove inaccessible tray in MER | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Thu Jul 15 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
1386 | TT_TASK | COLO-4 Cell-3 Reinstall tray in MER | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
1387 | TT_TASK | COLO-4 Cell-4 Remove inaccessible tray in MER4 | Wed Aug 04 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
1388 | TT_TASK | COLO-4 Cell-4 Reinstall tray in MER | Fri Sep 03 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Mon Aug 09 07:00:00 IDT 2021 | Thu Aug 12 00:00:00 IDT 2021 |  | COMPLETED
1389 | TT_TASK | COLO-3 Cell-1 Remove inaccessible tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
1390 | TT_TASK | COLO-3 CEll-1 Reinstall tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 |  | COMPLETED
1391 | TT_TASK | COLO-3 Cell-2 Remove inaccessible tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1392 | TT_TASK | COLO-3 Cell-2 Reinstall tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1395 | TT_TASK | COLO-3 Cell-3 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 14 00:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1397 | TT_TASK | COLO-4 Cell-1 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Fri Jul 23 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1398 | TT_TASK | COLO-4 Cell-2 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
1399 | TT_TASK | COLO-4 Cell-3 Conduit rework | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 |  | COMPLETED
1400 | TT_TASK | COLO-4 Cell-4 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1404 | TT_TASK | 6.1-88 COLO-1 MER awaiting updated UPS L3 test script approval | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 31 07:00:00 IDT 2021 |  | COMPLETED
1405 | TT_TASK | 6.1-89 RFI574- COLO-1 Relocating MSB EPMS device to different cabinet | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1406 | TT_TASK | 6.1-92 COLO-1 SF/ RF startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
1407 | TT_TASK | 6.1-93 COLO-1 HVAC minisplits startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1409 | TT_TASK | 6.2-08 COLO-2 Cell- 1,2 MER equipment Phenolic labelling | Wed Jul 14 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
1410 | TT_TASK | 6.2-08 COLO-2 Cell- 3,4 MER equipment Phenolic labelling | Wed Jul 14 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Mon Aug 02 00:00:00 IDT 2021 |  | COMPLETED
1411 | TT_TASK | 6.2-12 COLO-2 All Cells- Factory connection Torque verification | Wed Jul 14 07:00:00 IDT 2021 | Wed Jul 21 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
1413 | TT_TASK | 6.1-95 COLO-1 ATS's L3 startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  | COMPLETED
1415 | TT_TASK | 6.1-96 COLO-1 PDU - EPMS L3 startup delay (vendor schedule availability) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Mon Aug 02 07:00:00 IDT 2021 |  | COMPLETED
1420 | TT_TASK | COLO-2 Cell-1 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1421 | TT_TASK | COLO-2 Cell-2 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1422 | TT_TASK | COLO-2 Cell-3 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1423 | TT_TASK | COLO-2 Cell-4 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 00:00:00 IDT 2021 |  | COMPLETED
1429 | TT_TASK | 6.1-98 Admin/COLO-1 ASCO EPMS Connectivity Issues | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1430 | TT_TASK | 6.1-88 Admin/ COLO-1 MER/ADMIN UPS L3 Testing (includes shutdown to move PQM's & PQM data post proccessing) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 31 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1431 | TT_TASK | 6.1-106 COLO-1 Cell-2 UPS01 Power module failure | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1433 | TT_TASK | COLO-2 Cell-1 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1434 | TT_TASK | COLO-2 Cell-3 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1435 | TT_TASK | COLO-2 Cell-4 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1437 | TT_TASK | COLO-3 Delay in SE uploading QC Checkilst | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Fri Aug 06 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1439 | TT_TASK | COLO-2 Cell-2 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1442 | TT_TASK | Mobilization | Mon Apr 27 07:00:00 IDT 2020 | Wed May 20 17:00:00 IDT 2020 | Mon Apr 06 00:00:00 IDT 2020 | Sat May 02 17:00:00 IDT 2020 |  | COMPLETED
1444 | TT_TASK | Establish Access Roads / Laydown / Craft Parking / Temp Utilities | Thu May 14 07:00:00 IDT 2020 | Fri Jun 19 17:00:00 IDT 2020 | Fri Apr 24 00:00:00 IDT 2020 | Sat May 23 00:00:00 IDT 2020 |  | COMPLETED
1446 | TT_TASK | Site Sanitary | Mon May 11 07:00:00 IDT 2020 | Fri Jul 24 17:00:00 IDT 2020 | Tue May 05 00:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 |  | COMPLETED
1447 | TT_TASK | Remaining Site Sanitary | Mon May 11 07:00:00 IDT 2020 | Fri Jul 24 17:00:00 IDT 2020 | Tue Aug 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
1448 | TT_TASK | IWW System | Tue May 26 07:00:00 IDT 2020 | Sat Aug 08 17:00:00 IDT 2020 | Mon May 18 00:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 |  | COMPLETED
1449 | TT_TASK | Remaining IWW System | Tue May 26 07:00:00 IDT 2020 | Sat Aug 08 17:00:00 IDT 2020 | Tue Aug 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
1450 | TT_TASK | Site Water / Fire Loop | Fri Jul 24 07:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1451 | TT_TASK | Site Storm | Mon Jun 29 07:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
1454 | TT_TASK | Telecom-Communications Site Loop/Ductbank | Mon Jun 29 08:00:00 IDT 2020 | Thu Oct 01 08:00:00 IDT 2020 | Thu Jun 25 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1455 | TT_TASK | Telecom-RNG Fiber Underground installation | Mon Feb 01 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
1456 | TT_TASK | Telecom-RNG Fiber CNR buildout | Mon Oct 05 07:00:00 IDT 2020 | Tue Dec 08 17:00:00 IST 2020 | Mon Oct 05 07:00:00 IDT 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
1461 | TT_TASK | Temp Power/ Telecom duct bank | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Thu Aug 27 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1462 | TT_TASK | Vault- set 1st Vault Along UMS Duct bank run | Thu Sep 03 07:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1463 | TT_TASK | Vault- Set 2nd vault Along UMS Duct Run near COLO-2 | Tue Sep 08 07:00:00 IDT 2020 | Thu Sep 10 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1464 | TT_TASK | Vault- Set vault along URS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1465 | TT_TASK | Vault- Set vault along UMS to JAZ run | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1466 | TT_TASK | Set URS Vault | Mon Nov 16 08:00:00 IST 2020 | Wed Nov 25 08:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1467 | TT_TASK | Set UMS vault | Wed Nov 25 08:00:00 IST 2020 | Tue Dec 08 08:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1469 | TT_TASK | Vault- Set North vault- Along UPM to Vault | Fri Oct 09 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1470 | TT_TASK | Vault - Set North Vault Along Vault to URS run | Fri Oct 23 07:00:00 IDT 2020 | Tue Oct 27 17:00:00 IST 2020 | Thu Aug 20 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1471 | TT_TASK | Vault - Set South Vault Along Vault to URS run | Sat Nov 07 07:00:00 IST 2020 | Tue Nov 10 17:00:00 IST 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1472 | TT_TASK | Vault - Set South Vault along UPM to Vault | Mon Nov 23 07:00:00 IST 2020 | Wed Nov 25 17:00:00 IST 2020 | Thu Aug 20 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1475 | TT_TASK | Duct bank- COLO-1 UPM to north vault | Mon Oct 19 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Fri Oct 02 00:00:00 IDT 2020 | Mon Oct 05 00:00:00 IDT 2020 |  | COMPLETED
1476 | TT_TASK | Duct bank- COLO-2 UPM to north Valut | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Mon Oct 05 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1477 | TT_TASK | Duct Bank- Building to URS - 1st Half | Sat Sep 26 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 07:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
1478 | TT_TASK | Duct Bank- Building to URS(upto horse shoe) - 2nd Half | Wed Sep 30 07:00:00 IDT 2020 | Thu Oct 08 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
1479 | TT_TASK | Duct Bank - JAZ to vault- UMS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Thu Oct 29 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1480 | TT_TASK | Duct Bank - Vault to Vault along UMS duct Run - horseshoe | Mon Oct 26 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
1481 | TT_TASK | Duct Bank - COLO-3 UPM to Vault UMS Run | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1482 | TT_TASK | Duct Bank - URS to vault - URS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1483 | TT_TASK | Duct Bank - Vault To JAZ - URS to JAZ run | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 09 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1484 | TT_TASK | Duct Bank - Vault to UMS- UMS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1485 | TT_TASK | Duct Bank - south vault (along UMS duct run) to UMS | Sat Nov 21 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1486 | TT_TASK | Duct Bank - COLO-4 UPM to UMS | Mon Nov 23 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
1488 | TT_TASK | Duct Bank - COLO1- UPM to UPM | Mon Aug 10 07:00:00 IDT 2020 | Thu Aug 13 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1489 | TT_TASK | Duct Bank - COLO2- UPM to UPM | Mon Aug 31 07:00:00 IDT 2020 | Thu Sep 03 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
1490 | TT_TASK | Duct Bank - North Crossover (URS to west Vault Run) | Mon Sep 14 07:00:00 IDT 2020 | Sat Sep 26 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
1491 | TT_TASK | Duct Bank - South Cross over (URS to west Vault Run) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
1492 | TT_TASK | Duct Bank - COLO-3 UPM to UPM | Fri Nov 06 07:00:00 IST 2020 | Tue Nov 10 17:00:00 IST 2020 | Sat Oct 10 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1493 | TT_TASK | Duct Bank - COLO-4 UPM to UPM | Wed Nov 25 07:00:00 IST 2020 | Wed Dec 02 17:00:00 IST 2020 | Sat Oct 10 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1495 | TT_TASK | Duct Bank Admin UPM to COLO-1 UPM | Thu Sep 24 07:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1496 | TT_TASK | Duct Back- Admin UPM to Vault | Fri Oct 23 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Mon Aug 24 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
1497 | TT_TASK | Duct Bank COLO-2 UPM to Vault | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Mon Sep 28 00:00:00 IDT 2020 | Thu Oct 01 00:00:00 IDT 2020 |  | COMPLETED
1498 | TT_TASK | Duct Bank - Building to North Vault URS run | Fri Oct 23 07:00:00 IDT 2020 | Sat Oct 31 17:00:00 IST 2020 | Fri Oct 02 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1499 | TT_TASK | Duct Bank - Builing to South Vault- URS Run | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 09 17:00:00 IST 2020 | Fri Oct 02 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1500 | TT_TASK | Duct Bank - Vault to COLO-3 UPM | Tue Nov 10 07:00:00 IST 2020 | Fri Nov 13 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1501 | TT_TASK | Duct Bank - Vault to COLO-4 UPM | Mon Nov 16 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1503 | TT_TASK | Set MV Gear (URS) | Mon Nov 23 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1504 | TT_TASK | Set MV Gear (UMS) | Mon Dec 21 07:00:00 IST 2020 | Mon Dec 28 17:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
1506 | TT_TASK | Pull UPM to UPM COLO-1 - CELL-1 to Cell-3 | Tue Jan 05 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1507 | TT_TASK | Pul UPM to UPM COLO-2- CELL-1 to Cell-3 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Sat Jan 02 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
1508 | TT_TASK | Pull UPM to UPM COLO-3 - CELL-1 to Cell-3 | Fri Jan 15 07:00:00 IST 2021 | Mon Jan 18 17:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1509 | TT_TASK | Pull UPM to UPM COLO-4 - CELL-1 to Cell-3 | Wed Feb 03 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
1511 | TT_TASK | Pull UPM to UPM Admin to COLO-1 Cell -2 | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1512 | TT_TASK | Pull UPM to UPM COLO-1 Cell 2- Cell - 4 | Thu Jan 07 07:00:00 IST 2021 | Fri Jan 08 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1513 | TT_TASK | Pull UPM to UPM COLO-2 Cell 2- Cell - 4 | Wed Feb 03 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1514 | TT_TASK | Pull UPM to UPM COLO-3 Cell 2- Cell - 4 | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1515 | TT_TASK | Pull UPM to UPM COLO-4 Cell 2- Cell - 4 | Thu Feb 11 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1517 | TT_TASK | Pull Cross Overs- COLO-1 CELL-3 to CELL-4 | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1518 | TT_TASK | Pull Cross Overs- COLO-2 CELL-3 to CELL-4 | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1519 | TT_TASK | Pull Cross Overs- COLO-3 CELL-3 to CELL-4 | Tue Feb 09 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1520 | TT_TASK | Pull Cross Overs- COLO-4 CELL-3 to CELL-4 | Sat Feb 13 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1522 | TT_TASK | PULL- URS to Admin | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Sat Dec 05 00:00:00 IST 2020 |  | COMPLETED
1523 | TT_TASK | PULL- URS to COLO-2 | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
1524 | TT_TASK | PULL- URS to COLO-3 | Tue Jan 12 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1525 | TT_TASK | PULL- URS to COLO-4 | Mon Jan 18 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1527 | TT_TASK | Pull- UMS to COLO-1,2,3 | Tue Jan 12 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Jan 11 17:00:00 IST 2021 |  | COMPLETED
1528 | TT_TASK | Pull- UMS to COLO-4 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 |  | COMPLETED
1530 | TT_TASK | Pull - JAZ to URS | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
1531 | TT_TASK | Pull - JAZ to UMS | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1534 | TT_TASK | Term COLO -1 Cell-3 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1535 | TT_TASK | Term COLO -2 Cell-3 UPM | Thu Mar 04 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1536 | TT_TASK | Term COLO -3 Cell-3 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 |  | COMPLETED
1537 | TT_TASK | Term COLO -4 Cell-3 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1538 | TT_TASK | Term COLO -1 Cell-1 UPM | Wed Feb 10 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1539 | TT_TASK | Term COLO -2 Cell-1 UPM | Sat Feb 13 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1540 | TT_TASK | Term COLO -3 Cell-1 UPM | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1541 | TT_TASK | Term COLO -4 Cell-1 UPM | Thu Mar 11 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1543 | TT_TASK | Term COLO -1 Cell-4 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
1544 | TT_TASK | Term COLO -2 Cell-4 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1545 | TT_TASK | Term COLO -3 Cell-4 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1546 | TT_TASK | Term COLO -4 Cell-4 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1547 | TT_TASK | Term Admin - UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1548 | TT_TASK | Term COLO -1 Cell-2 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
1549 | TT_TASK | Term COLO -2 Cell-2 UPM | Fri Feb 05 07:00:00 IST 2021 | Tue Feb 09 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1550 | TT_TASK | Term COLO -3 Cell-2 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1551 | TT_TASK | Term COLO -4 Cell-2 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1553 | TT_TASK | Battery Station Yellow tagging / EPMS Checkouts | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1554 | TT_TASK | GCPUD NORTH Mobile substation maintance & Mobile Sub re-energization 4/1 Â– 4/3 | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1555 | TT_TASK | GCPUD SOUTH Mobile substation maintance & Mobile Sub re-energization 4/1 Â– 4/3 | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1556 | TT_TASK | Term- UMS- Line Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1557 | TT_TASK | Term- JAZ to Structure- (Incl Stress Cones) from ums | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1558 | TT_TASK | Term- UMS- Load side | Wed Feb 10 07:00:00 IST 2021 | Tue Feb 23 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1559 | TT_TASK | Yellow Tagging for UMS (includes GC, vendor Lvl-2) | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
1560 | TT_TASK | UMS Control Power Available CYT | Wed Feb 10 07:00:00 IST 2021 | Wed Feb 17 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
1562 | TT_TASK | Term URS- Line Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
1563 | TT_TASK | Term- JAS to URS- (Incl Stress Cones) | Wed Feb 03 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1564 | TT_TASK | TERM- URS- Load Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1565 | TT_TASK | Yellow Tagging for URS | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
1566 | TT_TASK | URS Control Power Available CYT | Wed Feb 10 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
1568 | TT_TASK | Aggregate Road Base | Mon Oct 19 07:00:00 IDT 2020 | Tue Nov 24 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
1569 | TT_TASK | Plant shutdown for winter | Mon Nov 30 07:00:00 IST 2020 | Tue Apr 06 17:00:00 IDT 2021 | Mon Nov 23 00:00:00 IST 2020 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
1570 | TT_TASK | Curb & Gutter | Mon Nov 30 07:00:00 IST 2020 | Sat Jan 09 17:00:00 IST 2021 | Mon Nov 02 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1571 | TT_TASK | Pave HMA | Mon Apr 05 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Sat Nov 07 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1572 | TT_TASK | Site Lighting | Mon May 03 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 |  | 120.0 | IN_PROGRESS
1575 | TT_TASK | Landscape and Site Specialties | Mon May 17 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1581 | TT_TASK | Perimeter Foundations - Excavate/FRP | Mon Apr 27 07:00:00 IDT 2020 | Thu May 14 17:00:00 IDT 2020 | Wed Apr 22 00:00:00 IDT 2020 | Wed May 20 00:00:00 IDT 2020 |  | COMPLETED
1582 | TT_TASK | Perimeter Foundations - Waterproof/Backfill | Mon Jun 01 07:00:00 IDT 2020 | Thu Jun 04 17:00:00 IDT 2020 | Wed May 27 00:00:00 IDT 2020 | Fri Jun 05 00:00:00 IDT 2020 |  | COMPLETED
1583 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Fri Jun 05 07:00:00 IDT 2020 | Tue Jun 16 17:00:00 IDT 2020 | Tue Jun 02 00:00:00 IDT 2020 | Fri Jun 12 00:00:00 IDT 2020 |  | COMPLETED
1585 | TT_TASK | Erect PEMB Steel | Mon Jun 29 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 |  | COMPLETED
1586 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Thu Jul 02 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
1588 | TT_TASK | MEP Undeground Rough-In (Interior) | Tue Aug 18 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1589 | TT_TASK | Aggregate Base Course | Mon Aug 31 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 |  | COMPLETED
1590 | TT_TASK | Slab on Grade | Mon Sep 14 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1592 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Aug 18 07:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 |  | COMPLETED
1593 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Tue Jul 14 00:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 |  | COMPLETED
1594 | TT_TASK | Downspouts & Gutters | Tue Aug 18 07:00:00 IDT 2020 | Sat Aug 29 17:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
1604 | TT_TASK | Perimeter Foundations - Excavate/FRP | Fri May 15 07:00:00 IDT 2020 | Wed Jun 03 17:00:00 IDT 2020 | Mon May 04 00:00:00 IDT 2020 | Fri May 15 00:00:00 IDT 2020 |  | COMPLETED
1605 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Sat Jun 13 07:00:00 IDT 2020 | Thu Jun 25 17:00:00 IDT 2020 | Tue Jun 02 00:00:00 IDT 2020 | Fri Jun 12 00:00:00 IDT 2020 |  | COMPLETED
1606 | TT_TASK | Perimeter Foundations - Waterproof Backfill | Tue May 26 07:00:00 IDT 2020 | Sat Jun 06 17:00:00 IDT 2020 | Tue May 26 07:00:00 IDT 2020 | Wed Jun 17 00:00:00 IDT 2020 |  | COMPLETED
1608 | TT_TASK | Erect PEMB Steel | Mon Jun 29 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Fri Jun 26 00:00:00 IDT 2020 | Mon Jul 06 00:00:00 IDT 2020 |  | COMPLETED
1609 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 |  | COMPLETED
1610 | TT_TASK | Erect Interior Structural Steel | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
1612 | TT_TASK | MEP Undeground Rough-In (Interior) | Fri Aug 14 07:00:00 IDT 2020 | Tue Sep 01 17:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1613 | TT_TASK | Aggregate Base Course | Sat Sep 05 07:00:00 IDT 2020 | Fri Sep 11 17:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 |  | COMPLETED
1614 | TT_TASK | Slab on Grade | Mon Sep 14 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1618 | TT_TASK | Exterior Insulated Metal Panels Installation - East Elevation | Tue Aug 18 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Mon Jul 13 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1621 | TT_TASK | Exterior Insulated Metal Panels Installation - West Elevation | Tue Aug 18 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Mon Jul 13 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1623 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 |  | COMPLETED
1624 | TT_TASK | Downspouts & Gutters | Tue Aug 18 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Wed Aug 12 00:00:00 IDT 2020 |  | COMPLETED
1629 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jun 22 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Mon May 11 00:00:00 IDT 2020 | Tue Jun 16 00:00:00 IDT 2020 |  | COMPLETED
1630 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Wed Jul 08 07:00:00 IDT 2020 | Mon Jul 20 17:00:00 IDT 2020 | Tue Jun 09 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
1632 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Tue Jul 07 00:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 |  | COMPLETED
1633 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 | Tue Aug 04 00:00:00 IDT 2020 |  | COMPLETED
1634 | TT_TASK | Erect Interior Structural Steel | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1636 | TT_TASK | MEP Undeground Rough-In (Interior) | Mon Aug 31 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 |  | COMPLETED
1637 | TT_TASK | Aggregate Base Course | Mon Oct 19 07:00:00 IDT 2020 | Mon Oct 26 17:00:00 IST 2020 | Thu Oct 01 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1638 | TT_TASK | Slab on Grade | Mon Oct 19 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1640 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Aug 18 07:00:00 IDT 2020 | Tue Sep 01 17:00:00 IDT 2020 | Fri Jul 31 00:00:00 IDT 2020 | Thu Aug 13 00:00:00 IDT 2020 |  | COMPLETED
1641 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Wed Aug 26 17:00:00 IDT 2020 | Fri Jul 31 00:00:00 IDT 2020 | Fri Aug 14 00:00:00 IDT 2020 |  | COMPLETED
1642 | TT_TASK | Downspouts & Gutters | Sat Sep 05 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 |  | COMPLETED
1647 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Wed Jul 08 07:00:00 IDT 2020 | Mon Jul 20 17:00:00 IDT 2020 | Wed Jun 24 00:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 |  | COMPLETED
1648 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jun 22 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Tue Jun 16 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1650 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 |  | COMPLETED
1651 | TT_TASK | Secondary Steel | Mon Aug 31 07:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 |  | COMPLETED
1652 | TT_TASK | Erect Interior Structural Steel | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1654 | TT_TASK | MEP Undeground Rough-In (Interior) | Mon Oct 19 07:00:00 IDT 2020 | Thu Nov 05 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1655 | TT_TASK | Aggregate Base Course | Fri Nov 06 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1656 | TT_TASK | Slab on Grade | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
1658 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Sep 08 07:00:00 IDT 2020 | Tue Sep 22 17:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1659 | TT_TASK | Roof Panels Installation | Tue Sep 08 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 | Tue Sep 01 00:00:00 IDT 2020 |  | COMPLETED
1660 | TT_TASK | Downspouts & Gutters | Wed Sep 16 07:00:00 IDT 2020 | Tue Sep 22 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
1670 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jul 06 07:00:00 IDT 2020 | Thu Jul 23 17:00:00 IDT 2020 | Tue Jun 23 00:00:00 IDT 2020 | Thu Jul 30 00:00:00 IDT 2020 |  | COMPLETED
1671 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Sat Aug 29 07:00:00 IDT 2020 | Thu Sep 10 17:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 |  | COMPLETED
1673 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Sat Aug 08 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
1674 | TT_TASK | Secondary Steel | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 08 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1675 | TT_TASK | Erect Interior Structural Steel | Mon Dec 21 07:00:00 IST 2020 | Tue Dec 29 17:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
1677 | TT_TASK | MEP Undeground Rough-In (Interior) | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1678 | TT_TASK | Aggregate Base Course | Wed Nov 11 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
1679 | TT_TASK | Slab on Grade | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1681 | TT_TASK | Exterior Insulated Metal Panels Installation | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Sep 30 00:00:00 IDT 2020 |  | COMPLETED
1682 | TT_TASK | Roof Panels Installation | Thu Sep 03 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Thu Aug 27 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1683 | TT_TASK | Downspouts & Gutters | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Sep 07 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1693 | TT_TASK | Hang Wall Partitions | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1694 | TT_TASK | Hang Wall Partitions- Early Walls | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1695 | TT_TASK | MEP Rough-In / Wall & Ceiling | Mon Oct 19 07:00:00 IDT 2020 | Mon Nov 02 17:00:00 IST 2020 | Thu Oct 01 00:00:00 IDT 2020 | Tue Nov 17 00:00:00 IST 2020 |  | COMPLETED
1697 | TT_TASK | Early Room - Finishes | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1699 | TT_TASK | Loading Dock Equipment & Dock Doors | Wed May 05 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
1700 | TT_TASK | MEP Overhead | Mon Oct 19 07:00:00 IDT 2020 | Tue Nov 17 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1701 | TT_TASK | Ceilings / Ligthing / FA Devices | Mon Mar 01 07:00:00 IST 2021 | Tue Apr 13 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
1702 | TT_TASK | Concrete Floor Sealing/Epoxy | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1706 | TT_TASK | Generator Term | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
1707 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 | Fri Sep 25 00:00:00 IDT 2020 |  | COMPLETED
1708 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Fri Sep 18 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
1709 | TT_TASK | Set Exterior Electrical OFCI Equipment | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1710 | TT_TASK | Admin -Electrical Underground Rough-In | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 31 17:00:00 IDT 2020 | Fri Aug 07 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
1711 | TT_TASK | Generator & Utility Power Pull-Test | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1712 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Jan 18 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1713 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1715 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Oct 19 07:00:00 IDT 2020 | Mon Nov 02 17:00:00 IST 2020 | Fri Oct 09 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1716 | TT_TASK | Set Exterior Mechanical CFCI Equipment (remaning mini splits) | Fri Nov 06 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1717 | TT_TASK | Mechanical Underground Rough-In | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 31 17:00:00 IDT 2020 | Sat Aug 08 00:00:00 IDT 2020 | Tue Aug 25 00:00:00 IDT 2020 |  | COMPLETED
1718 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1721 | TT_TASK | Fire Alarm Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1722 | TT_TASK | Controls Installation | Tue Feb 16 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
1724 | TT_TASK | Set Electrical Equipment incl. OH raceways | Mon Nov 23 07:00:00 IST 2020 | Wed Jan 13 17:00:00 IST 2021 | Mon Nov 16 00:00:00 IST 2020 | Tue Dec 29 00:00:00 IST 2020 |  | COMPLETED
1725 | TT_TASK | Electrical Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1727 | TT_TASK | Domestic Water Piping | Mon Nov 23 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1728 | TT_TASK | Plumbing Devices & Trim | Mon Jul 26 15:00:00 IDT 2021 | Tue Aug 17 15:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
1730 | TT_TASK | Security Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
1732 | TT_TASK | Mechanical Ductwork Installation | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1733 | TT_TASK | Set Mechanical Equipment | Mon Nov 23 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
1734 | TT_TASK | Mechanical Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1739 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1740 | TT_TASK | Overhead MEPFP Rough-In | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 11 17:00:00 IST 2020 | Wed Oct 14 00:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
1741 | TT_TASK | Early Topout | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1743 | TT_TASK | Sprinkler Test | Mon Dec 21 07:00:00 IST 2020 | Tue Dec 22 17:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1744 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1747 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1748 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1749 | TT_TASK | Early Topout | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Tue Nov 10 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1751 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Nov 30 07:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1754 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 |  | COMPLETED
1755 | TT_TASK | Overhead MEPFP Rough-In | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 11 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 |  | COMPLETED
1756 | TT_TASK | Early Topout | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1758 | TT_TASK | Datahall Finishes- Ceiling Grid | Thu Dec 03 07:00:00 IST 2020 | Tue Dec 15 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1761 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1762 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1763 | TT_TASK | Early Topout | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Tue Nov 10 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1765 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1768 | TT_TASK | Remaining MER raceway across Mech chase | Tue Dec 01 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1769 | TT_TASK | Electrical OH Below Mechanical Piping | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1770 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1771 | TT_TASK | OverHead MEPFP Rough-In ( Add TCM Cross over piping HRA Level-3) | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1772 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1774 | TT_TASK | Mechanical Corridor Finishes | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1777 | TT_TASK | Remaining MER raceway across Mech chase | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1778 | TT_TASK | Electrical OH Below Mechanical Piping | Wed Jan 20 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1779 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 11 00:00:00 IST 2020 |  | COMPLETED
1780 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1781 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1783 | TT_TASK | Mechanical Corridor Finishes | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1786 | TT_TASK | Remaining MER raceway across Mech chase | Tue Dec 01 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1787 | TT_TASK | Electrical OH Below Mechanical Piping | Mon Jan 04 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1788 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1789 | TT_TASK | OverHead MEPFP Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1790 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1792 | TT_TASK | Mechanical Corridor Finishes | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1795 | TT_TASK | Remaining MER raceway across Mech chase | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1796 | TT_TASK | Electrical OH Below Mechanical Piping | Wed Jan 20 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1797 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 11 00:00:00 IST 2020 |  | COMPLETED
1798 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1799 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1801 | TT_TASK | Mechanical Corridor Finishes | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Tue Nov 17 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1805 | TT_TASK | Generator & Utility Power Term | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1806 | TT_TASK | Remaining Mechanical Equipment (ADP01) Termimations | Thu Mar 18 07:00:00 IST 2021 | Tue Mar 23 17:00:00 IST 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1807 | TT_TASK | Electrical Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 14 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1808 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1809 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1810 | TT_TASK | Exterior Equipment Pads - Electrical | Thu Sep 03 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1811 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Oct 12 07:00:00 IDT 2020 | Mon Oct 26 17:00:00 IST 2020 | Mon Oct 12 07:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1812 | TT_TASK | Lift & Set MER in Place | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Wed Dec 16 00:00:00 IST 2020 | Wed Dec 16 17:00:00 IST 2020 |  | COMPLETED
1813 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
1814 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 13 17:00:00 IST 2021 | Thu Dec 17 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1815 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Jan 11 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Tue Jan 05 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1816 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1817 | TT_TASK | Generator & Utility Power Pull | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1819 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1820 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1821 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1822 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1823 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Sat Dec 05 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1824 | TT_TASK | Mechanical Equipment Piping Connections | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1825 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
1828 | TT_TASK | Fire Alarm Installation | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1829 | TT_TASK | Controls Installation | Fri Mar 05 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1832 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 22 07:00:00 IST 2021 | Tue Mar 30 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1833 | TT_TASK | Electrical Underground Rough-In | Thu Sep 03 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1834 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1835 | TT_TASK | Set Electrical Equipment-UPM Cell -3 | Fri Dec 11 07:00:00 IST 2020 | Tue Dec 15 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1836 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
1837 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1838 | TT_TASK | Lift & Set MER in Place | Mon Jan 11 08:00:00 IST 2021 | Mon Jan 18 08:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1839 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 18 08:00:00 IST 2021 | Fri Jan 22 08:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1840 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
1841 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1842 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
1843 | TT_TASK | Generator & Utility Power Pull | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1845 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1846 | TT_TASK | Exterior Equipment Pads - Mechanical | Fri Oct 16 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Sat Sep 19 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
1847 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1848 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1849 | TT_TASK | Set Exterior Water Treatment equipment | Mon Dec 07 07:00:00 IST 2020 | Tue Dec 08 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1850 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1851 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 15 07:00:00 IST 2021 | Mon Mar 22 17:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
1854 | TT_TASK | Fire Alarm Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1855 | TT_TASK | Controls Installation | Tue Mar 09 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1858 | TT_TASK | Generator & Utility Power Pull | Tue Feb 02 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Feb 26 07:00:00 IST 2021 |  | COMPLETED
1859 | TT_TASK | Remaining Mechanical Equipment (ADP01) Termimations | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1860 | TT_TASK | Electrical Underground Rough-In | Fri Aug 14 07:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1861 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 05 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1862 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1863 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Sep 05 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Fri Oct 02 00:00:00 IDT 2020 |  | COMPLETED
1864 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Oct 26 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1865 | TT_TASK | Lift & Set MER in Place | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
1866 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 11 08:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1867 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1868 | TT_TASK | GEN & UPM to MER Cable Bus Install | Wed Jan 20 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1869 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1870 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1872 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1873 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Oct 05 07:00:00 IDT 2020 | Sat Oct 17 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
1874 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1875 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1876 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1877 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1878 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 08 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1881 | TT_TASK | Fire Alarm Installation | Thu Feb 18 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1882 | TT_TASK | Controls Installation | Sat Mar 06 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
1885 | TT_TASK | Generator & Utility Power Pull | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1886 | TT_TASK | Electrical Underground Rough-In | Sat Sep 05 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1887 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1888 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1889 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1890 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1891 | TT_TASK | Lift & Set MER in Place | Mon Jan 11 08:00:00 IST 2021 | Mon Jan 18 08:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1892 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 11 08:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Jan 11 08:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1893 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1894 | TT_TASK | GEN & UPM to MER Cable Bus Install | Thu Feb 04 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1895 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Wed Apr 07 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
1896 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 15 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
1898 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Sep 14 07:00:00 IDT 2020 | Sat Sep 26 17:00:00 IDT 2020 | Mon Sep 14 07:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1899 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1900 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1901 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1902 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1903 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1904 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
1907 | TT_TASK | Fire Alarm Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1908 | TT_TASK | Controls Installation | Thu Apr 15 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1911 | TT_TASK | VFD'S Installation & wirepull | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1912 | TT_TASK | Ligthing Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 |  | COMPLETED
1914 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Thu Nov 26 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
1915 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1917 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1919 | TT_TASK | Fire Riser Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1920 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1921 | TT_TASK | Controls Installation | Fri Mar 26 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1924 | TT_TASK | VFD'S Installation & Wiring | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
1925 | TT_TASK | Ligthing Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1927 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
1928 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1930 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1932 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1933 | TT_TASK | Controls Installation | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1936 | TT_TASK | VFD'S Installation & Wiring | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1937 | TT_TASK | Ligthing Installation | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1939 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
1940 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1942 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1944 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1945 | TT_TASK | Controls Installation | Tue Apr 13 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1948 | TT_TASK | VFD'S Installation & Wiring | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
1949 | TT_TASK | Ligthing Installation | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jul 29 00:00:00 IDT 2021 |  | COMPLETED
1951 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
1952 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1954 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1956 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1957 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1961 | TT_TASK | HAC Installation | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
1962 | TT_TASK | Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1963 | TT_TASK | Power Bus Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1964 | TT_TASK | PDU's Installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1965 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Apr 05 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1966 | TT_TASK | Light Fixtures Installation | Wed May 05 07:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
1967 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
1969 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
1970 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1971 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1972 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1974 | TT_TASK | Security Devices & Trim | Mon May 17 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
1975 | TT_TASK | Controls Installation | Fri Mar 26 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1976 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1979 | TT_TASK | HAC Installation | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1980 | TT_TASK | Cable Tray Installation | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
1981 | TT_TASK | Power Bus Installation | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1982 | TT_TASK | PDU's Installation | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
1983 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Apr 26 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1984 | TT_TASK | Light Fixtures Installation | Wed May 12 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1985 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Apr 26 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
1987 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
1988 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1989 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1990 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Thu Jul 01 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1992 | TT_TASK | Security Devices & Trim | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
1993 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1994 | TT_TASK | Fire Alarm System | Tue May 04 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1997 | TT_TASK | HAC Installation | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1998 | TT_TASK | Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1999 | TT_TASK | Power Bus Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
2000 | TT_TASK | PDU's Installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
2001 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Apr 01 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2002 | TT_TASK | Light Fixtures Installation | Tue May 11 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
2003 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 23 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
2005 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2006 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2007 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2008 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed May 19 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2010 | TT_TASK | Security Devices & Trim | Mon May 17 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2011 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2012 | TT_TASK | Fire Alarm System | Thu May 06 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2015 | TT_TASK | HAC Installation | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2016 | TT_TASK | Cable Tray Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2017 | TT_TASK | Power Bus Installation | Fri Mar 12 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2018 | TT_TASK | PDU's Installation | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2019 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon May 03 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
2020 | TT_TASK | Light Fixtures Installation | Fri May 21 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2021 | TT_TASK | Pull/term/Test PDU to Power bus | Mon May 03 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2023 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2024 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2025 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2026 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed May 19 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2028 | TT_TASK | Security Devices & Trim | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 |  | COMPLETED
2029 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2030 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2036 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2037 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
2038 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2040 | TT_TASK | Datahall Finishes - Ceiling Grid | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2043 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2044 | TT_TASK | Overhead MEPFP Rough-In | Fri Nov 06 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2045 | TT_TASK | Hang drywall / Mud / Tape | Wed Jan 06 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2047 | TT_TASK | Datahall Finishes - Ceiling Grid | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2050 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2051 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
2052 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2054 | TT_TASK | Datahall Finishes - Ceiling Grid | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2057 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2058 | TT_TASK | Overhead MEPFP Rough-In | Fri Nov 06 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2059 | TT_TASK | Hang drywall / Mud / Tape | Wed Jan 06 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2061 | TT_TASK | Datahall Finishes - Ceiling Grid | Mon Jan 11 07:00:00 IST 2021 | Wed Jan 20 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2064 | TT_TASK | Remaining Post MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2065 | TT_TASK | Frame & Top out | Mon Nov 23 07:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2066 | TT_TASK | OverHead MEPFP Rough-In | Thu Nov 19 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2067 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Dec 12 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2069 | TT_TASK | Mechanical Corridor Finishes | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2072 | TT_TASK | Remaining MER raceway across Mech chase | Thu Mar 25 07:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2073 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2074 | TT_TASK | OverHead MEPFP Rough-In | Tue Dec 08 07:00:00 IST 2020 | Mon Dec 21 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2075 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Dec 14 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2077 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2080 | TT_TASK | Remaining MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 |  | COMPLETED
2081 | TT_TASK | Frame & Top out | Mon Nov 30 07:00:00 IST 2020 | Wed Dec 09 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2082 | TT_TASK | OverHead MEPFP Rough-In | Sat Dec 19 07:00:00 IST 2020 | Thu Jan 07 17:00:00 IST 2021 | Mon Oct 26 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2083 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Dec 12 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2085 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2088 | TT_TASK | Remaining MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Mar 12 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2089 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2090 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2091 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 30 07:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
2093 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2097 | TT_TASK | Generator & Utility Power Pull | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
2098 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
2099 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2100 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
2101 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Dec 14 07:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 |  | COMPLETED
2102 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Tue Dec 29 00:00:00 IST 2020 |  | COMPLETED
2103 | TT_TASK | Lift & Set MER in Place | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2104 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 |  | COMPLETED
2105 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
2106 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Mar 22 07:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Fri Mar 05 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
2107 | TT_TASK | Generator & Utility Power Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2108 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2110 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
2111 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 08 17:00:00 IST 2021 | Mon Nov 02 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
2112 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2113 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2114 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2115 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2116 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2119 | TT_TASK | Fire Alarm Installation | Tue May 11 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2120 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2123 | TT_TASK | Generator & Utility Power Pull | Tue May 11 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
2124 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 21 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2125 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2126 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Wed Dec 16 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2127 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Dec 14 07:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2128 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2129 | TT_TASK | Lift & Set MER in Place | Tue Mar 23 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
2130 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Mar 29 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2131 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Mar 29 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2132 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Fri Apr 16 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
2133 | TT_TASK | Generator & Utility Power Test-Term | Thu May 06 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2134 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
2136 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2137 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 08 17:00:00 IST 2021 | Mon Nov 16 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2138 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2139 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2140 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2141 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2142 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
2145 | TT_TASK | Fire Alarm Installation | Wed May 26 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2146 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2149 | TT_TASK | Generator & Utility Power Pull | Fri Mar 26 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
2150 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2151 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
2152 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Wed Nov 04 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2153 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Tue Nov 03 00:00:00 IST 2020 |  | COMPLETED
2154 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
2155 | TT_TASK | Lift & Set MER in Place | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2156 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Mar 27 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2157 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Mar 27 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2158 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Thu Mar 25 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
2159 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2160 | TT_TASK | Generator & Utility Power Test-Term | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Tue Apr 06 07:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2162 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2163 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2164 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2165 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2166 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Fri Jan 15 07:00:00 IST 2021 | Fri Jan 29 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2167 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
2168 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
2171 | TT_TASK | Fire Alarm Installation | Tue May 11 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2172 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2175 | TT_TASK | Generator & Utility Power Pull | Thu May 13 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2176 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2177 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2178 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2179 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2180 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
2181 | TT_TASK | Lift & Set MER in Place | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
2182 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Mar 27 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2183 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Mar 27 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
2184 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Thu Apr 15 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
2185 | TT_TASK | Generator & Utility Power Test-Term | Tue May 18 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2186 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2188 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2189 | TT_TASK | Set Gen Stack / Exhaust duct | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2192 | TT_TASK | Fire Alarm Installation | Wed May 12 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2193 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2196 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 |  | COMPLETED
2197 | TT_TASK | Ligthing Installation | Fri Jul 23 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2199 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2200 | TT_TASK | Hydronic Piping Installation | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2202 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2203 | TT_TASK | Toilet Piping Installation / DW | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2205 | TT_TASK | Fire Riser Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2206 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2207 | TT_TASK | Controls Installation | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue Jun 08 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2210 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2211 | TT_TASK | Ligthing Installation | Sat Aug 07 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2213 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
2214 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2216 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2217 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2219 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2220 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
2223 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2224 | TT_TASK | Ligthing Installation | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2226 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
2227 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2229 | TT_TASK | Toilet Piping Installation / DW | Mon May 03 07:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2230 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2232 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2233 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri Jul 09 08:12:00 IDT 2021 |  | COMPLETED
2236 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2237 | TT_TASK | Ligthing Installation | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2239 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
2240 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2242 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2243 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2245 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2246 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2249 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2250 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2251 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
2252 | TT_TASK | Power Bus Installation | Fri Mar 26 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2253 | TT_TASK | PDU's Installation | Fri Mar 26 07:00:00 IDT 2021 | Mon Mar 29 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
2254 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2255 | TT_TASK | Light Fixtures Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2256 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 23 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
2258 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Jun 10 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2259 | TT_TASK | BMS Pull Wire / Term / Test | Thu Jun 10 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2260 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Jul 23 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2262 | TT_TASK | Fire Alarm System | Tue May 04 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2263 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2266 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2267 | TT_TASK | HAC Installation | Wed Feb 03 07:00:00 IST 2021 | Wed Feb 17 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Wed Feb 03 00:00:00 IST 2021 |  | COMPLETED
2268 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
2269 | TT_TASK | Power Bus Installation | Mon Mar 22 07:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2270 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2271 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Tue Jun 08 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2272 | TT_TASK | Light Fixtures Installation | Wed Jun 23 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
2273 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2275 | TT_TASK | EPMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 |  | COMPLETED
2276 | TT_TASK | BMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 |  | COMPLETED
2277 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon Aug 09 07:00:00 IDT 2021 | Wed Sep 01 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2279 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2280 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2283 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2284 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2285 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
2286 | TT_TASK | Power Bus Installation | Fri Mar 26 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2287 | TT_TASK | PDU's Installation | Mon Mar 22 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2288 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2289 | TT_TASK | Light Fixtures Installation | Fri Jun 18 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Jun 18 07:00:00 IDT 2021 | Thu Jul 01 00:00:00 IDT 2021 |  | COMPLETED
2290 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 02 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
2292 | TT_TASK | EPMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2293 | TT_TASK | BMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2294 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Jul 30 07:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2296 | TT_TASK | Fire Alarm System | Mon May 10 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon May 10 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 |  | COMPLETED
2297 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2300 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Thu Apr 22 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2301 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
2302 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2303 | TT_TASK | Power Bus Installation | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2304 | TT_TASK | PDU's Installation | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2305 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Jun 09 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2306 | TT_TASK | Light Fixtures Installation | Wed Jun 23 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2307 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2309 | TT_TASK | EPMS Pull Wire / Term / Test | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2310 | TT_TASK | BMS Pull Wire / Term / Test | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2311 | TT_TASK | ` | Tue Aug 24 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2313 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2314 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2319 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2320 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
2321 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2323 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2326 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
2327 | TT_TASK | Overhead MEPFP Rough-In | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 |  | COMPLETED
2328 | TT_TASK | Hang drywall / Mud / Tape | Thu Jan 14 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2330 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2333 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2334 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2335 | TT_TASK | Hang drywall / Mud / Tape | Fri Jan 08 07:00:00 IST 2021 | Mon Jan 18 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2337 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2340 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
2341 | TT_TASK | Overhead MEPFP Rough-In | Fri Jan 15 07:00:00 IST 2021 | Wed Jan 27 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2342 | TT_TASK | Hang drywall / Mud / Tape | Thu Jan 14 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2344 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2347 | TT_TASK | Remaining MER raceway across Mech chase | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2348 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
2349 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2350 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Thu Jan 21 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Thu Jan 21 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 |  | COMPLETED
2352 | TT_TASK | Mechanical Corridor Finishes | Fri Mar 05 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2355 | TT_TASK | Remaining MER raceway across Mech chase | Thu Jun 17 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2356 | TT_TASK | Frame & Top out | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2357 | TT_TASK | OverHead MEPFP Rough-In | Wed Jan 13 07:00:00 IST 2021 | Wed Jan 27 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2358 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
2360 | TT_TASK | Mechanical Corridor Finishes | Wed Feb 03 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2363 | TT_TASK | Remaining MER raceway across Mech chase | Mon May 03 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2364 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
2365 | TT_TASK | OverHead MEPFP Rough-In | Tue Jan 12 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2366 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2368 | TT_TASK | Mechanical Corridor Finishes | Tue Feb 02 07:00:00 IST 2021 | Tue Feb 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2371 | TT_TASK | Remaining MER raceway across Mech chase | Thu Jun 17 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
2372 | TT_TASK | Frame & Top out | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2373 | TT_TASK | OverHead MEPFP Rough-In | Fri Jan 08 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2374 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2376 | TT_TASK | Mechanical Corridor Finishes | Tue Feb 23 07:00:00 IST 2021 | Tue Mar 16 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2380 | TT_TASK | Generator & Utility Power Pull | Wed May 19 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2381 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
2382 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2383 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 29 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
2384 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 07:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
2385 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2386 | TT_TASK | Lift & Set MER in Place | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
2387 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
2388 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon May 03 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2389 | TT_TASK | GEN & UPM to MER Cable Bus Install | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2390 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2391 | TT_TASK | Generator & Utility Power Test-Term | Wed Jun 02 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
2393 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
2394 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2395 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
2396 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2397 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2398 | TT_TASK | Set Exterior Water Treatment equipment | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 01 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2399 | TT_TASK | Mechanical Equipment Piping Connections | Fri Apr 30 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2402 | TT_TASK | Fire Alarm Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2403 | TT_TASK | Controls Installation | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2406 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2407 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
2408 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2409 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2410 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 02 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2411 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 15 08:00:00 IST 2021 | Mon Mar 22 08:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2412 | TT_TASK | Lift & Set MER in Place | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2413 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2414 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Fri May 07 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2415 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2416 | TT_TASK | Generator & Utility Power Test-Term | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2417 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Jun 08 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Tue Jun 08 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2419 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
2420 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
2423 | TT_TASK | Fire Alarm Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 15 07:00:00 IDT 2021 |  | COMPLETED
2424 | TT_TASK | Controls Installation | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 29 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2427 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2428 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2429 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2430 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 08:00:00 IST 2021 | Tue Jan 12 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2431 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Fri Nov 27 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2432 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
2433 | TT_TASK | Lift & Set MER in Place | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
2434 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2435 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon May 03 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
2436 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Mon May 17 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 |  | COMPLETED
2437 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Thu Jun 10 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2438 | TT_TASK | Generator & Utility Power Test-Term | Thu Jun 03 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
2440 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2441 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2442 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2443 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Apr 26 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2444 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 |  | COMPLETED
2445 | TT_TASK | Set Exterior Water Treatment equipment | Mon Apr 26 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2446 | TT_TASK | Mechanical Equipment Piping Connections | Mon May 03 07:00:00 IDT 2021 | Sat May 08 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2449 | TT_TASK | Fire Alarm Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2450 | TT_TASK | Controls Installation | Fri Jun 25 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2453 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2454 | TT_TASK | Electrical Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2455 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Fri Dec 04 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2456 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2457 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 02 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2458 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
2459 | TT_TASK | Lift & Set MER in Place | Fri May 07 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2460 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2461 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2462 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2463 | TT_TASK | Generator & Utility Power Test-Term | Tue Jul 06 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 | Thu Jul 15 12:00:00 IDT 2021 |  | COMPLETED
2464 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2466 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Fri Dec 04 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2467 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2468 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2469 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2470 | TT_TASK | Set Exterior Water Treatment equipment | Fri Apr 30 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2471 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
2472 | TT_TASK | Mechanical Equipment Piping Connections | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2475 | TT_TASK | Fire Alarm Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jul 07 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2476 | TT_TASK | Controls Installation | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
2479 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2480 | TT_TASK | Ligthing Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2482 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
2483 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2485 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 00:00:00 IDT 2021 |  | COMPLETED
2486 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2488 | TT_TASK | Fire Riser Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2489 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2490 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2493 | TT_TASK | VFD'S Installation & Wiring | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2494 | TT_TASK | Ligthing Installation | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
2496 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
2497 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2499 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2500 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2502 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2503 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2506 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2507 | TT_TASK | Ligthing Installation | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
2509 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
2510 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2512 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2513 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2515 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2516 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
2519 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
2520 | TT_TASK | Ligthing Installation | Mon Aug 30 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2522 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
2523 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2525 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2526 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2528 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2529 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2532 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 |  | COMPLETED
2533 | TT_TASK | HAC Installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2534 | TT_TASK | Cable Tray Installation | Sat Apr 03 07:00:00 IDT 2021 | Sat Apr 17 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
2535 | TT_TASK | Power Bus Installation | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2536 | TT_TASK | PDU's Installation | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2537 | TT_TASK | Pull/term/Test PDU to Power bus | Sat Jun 19 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2538 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2539 | TT_TASK | Light Fixtures Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
2541 | TT_TASK | EPMS Pull Wire / Term / Test | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2542 | TT_TASK | BMS Pull Wire / Term / Test | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2543 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Aug 20 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Jul 07 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2545 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2546 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
2549 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2550 | TT_TASK | HAC Installation | Wed Apr 07 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2551 | TT_TASK | Cable Tray Installation | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2552 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
2553 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
2554 | TT_TASK | Pull/term/Test PDU to Power bus | Fri Jul 02 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
2555 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Aug 16 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Thu Jul 08 00:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2556 | TT_TASK | Light Fixtures Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2558 | TT_TASK | EPMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2559 | TT_TASK | BMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2560 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2562 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2563 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2566 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 |  | COMPLETED
2567 | TT_TASK | HAC Installation | Sat Apr 03 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2568 | TT_TASK | Cable Tray Installation | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2569 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 |  | COMPLETED
2570 | TT_TASK | PDU's Installation | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2571 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Sat Jul 24 00:00:00 IDT 2021 |  | COMPLETED
2572 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 23 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2573 | TT_TASK | Light Fixtures Installation | Wed Jul 21 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2575 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2576 | TT_TASK | BMS Pull Wire / Term / Test | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2577 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Aug 20 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2579 | TT_TASK | Fire Alarm System | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2580 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2583 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2584 | TT_TASK | HAC Installation | Mon Apr 12 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2585 | TT_TASK | Cable Tray Installation | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2586 | TT_TASK | Power Bus Installation | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
2587 | TT_TASK | PDU's Installation | Mon Jun 14 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
2588 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
2589 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2590 | TT_TASK | Light Fixtures Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2592 | TT_TASK | EPMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2593 | TT_TASK | BMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2594 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed Sep 15 07:00:00 IDT 2021 | Fri Oct 08 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2596 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2597 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2602 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2603 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2604 | TT_TASK | Early Topout | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2606 | TT_TASK | Datahall Finishes | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
2609 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Jan 18 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2610 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2611 | TT_TASK | Early Topout | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
2613 | TT_TASK | Datahall Finishes | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2616 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2617 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2618 | TT_TASK | Early Topout | Tue Feb 09 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2620 | TT_TASK | Datahall Finishes | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
2623 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Jan 18 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2624 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2625 | TT_TASK | Early Topout | Mon Feb 08 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2627 | TT_TASK | Datahall Finishes | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2630 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2631 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2632 | TT_TASK | OverHead MEPFP Rough-In | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
2633 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 15 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
2635 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Sat Jan 09 00:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 |  | COMPLETED
2638 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2639 | TT_TASK | Frame & Top out | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Sat Jan 09 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
2640 | TT_TASK | OverHead MEPFP Rough-In | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2641 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Tue Mar 30 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2643 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 29 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Thu Jan 21 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
2646 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 |  | COMPLETED
2647 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
2648 | TT_TASK | OverHead MEPFP Rough-In | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Feb 05 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2649 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 15 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2651 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
2654 | TT_TASK | Remaining MER raceway across Mech chase | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
2655 | TT_TASK | Frame & Top out | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
2656 | TT_TASK | OverHead MEPFP Rough-In | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2657 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Tue Mar 30 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Fri Feb 12 00:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
2659 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 29 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2663 | TT_TASK | Generator & Utility Power Pull | Wed Jul 28 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2664 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2665 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2666 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Wed Dec 30 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2667 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2668 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Apr 26 08:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2669 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
2670 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2671 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2672 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 |  | COMPLETED
2673 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2674 | TT_TASK | Generator & Utility Power Test-Term | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
2676 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2677 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2678 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2679 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2680 | TT_TASK | Set Exterior Water Treatment equipment | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 01 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2681 | TT_TASK | Mechanical Equipment Piping Connections | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2682 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2685 | TT_TASK | Fire Alarm Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
2686 | TT_TASK | Controls Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2689 | TT_TASK | Generator & Utility Power Pull | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 19 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2690 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2691 | TT_TASK | Exterior Equipment Pads - for UPM's | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2692 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2693 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2694 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Apr 26 08:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2695 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2696 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2697 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
2698 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jul 10 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2699 | TT_TASK | Generator & Utility Power Test-Term | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Sat Aug 07 17:00:00 IDT 2021 |  | COMPLETED
2700 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2702 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2703 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2704 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2705 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2706 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2707 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2708 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2711 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
2712 | TT_TASK | Controls Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
2715 | TT_TASK | Generator & Utility Power Pull | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 | Thu Aug 05 09:30:00 IDT 2021 |  | COMPLETED
2716 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2717 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2718 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2719 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2720 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2721 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2722 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2723 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2724 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jul 15 00:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2725 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2726 | TT_TASK | Generator & Utility Power Test-Term | Fri Sep 03 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
2728 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 09 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2729 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2730 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2731 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2732 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2733 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2734 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
2737 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2738 | TT_TASK | Controls Installation | Wed Sep 01 07:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Thu Aug 26 07:00:00 IDT 2021 |  | 1210.0 | IN_PROGRESS
2741 | TT_TASK | Generator & Utility Power Pull | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Thu Jul 29 00:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
2742 | TT_TASK | Electrical Underground Rough-In | Sat Nov 07 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2743 | TT_TASK | Exterior Equipment Pads - for UPM's | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2744 | TT_TASK | Set Electrical Equipment-UPM | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2745 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Jan 18 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2746 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2747 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2748 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2749 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
2750 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2751 | TT_TASK | Generator & Utility Power Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2752 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2754 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2755 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2756 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2757 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2758 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2759 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2760 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2763 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
2764 | TT_TASK | Controls Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
2767 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2768 | TT_TASK | Ligthing Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2770 | TT_TASK | AHU/DOAS Equipment Setting | Sat May 15 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2771 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2773 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2774 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2776 | TT_TASK | Fire Riser Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed May 19 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2777 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2778 | TT_TASK | Controls Installation | Sat Jul 31 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2781 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
2782 | TT_TASK | Ligthing Installation | Thu Sep 16 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
2784 | TT_TASK | AHU/DOAS Equipment Setting | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2785 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2787 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2788 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2790 | TT_TASK | Fire Alarm System | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2791 | TT_TASK | Controls Installation | Mon Aug 23 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2794 | TT_TASK | VFD'S Installation & Wiring | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2795 | TT_TASK | Lighting Installation | Sat Sep 11 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
2797 | TT_TASK | AHU/DOAS Equipment Setting | Sat May 15 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2798 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2800 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2801 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2803 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2804 | TT_TASK | Controls Installation | Mon Aug 16 07:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 |  | COMPLETED
2807 | TT_TASK | VFD'S Installation & Wiring | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2808 | TT_TASK | Ligthing Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
2810 | TT_TASK | AHU/DOAS Equipment Setting | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2811 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2813 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2814 | TT_TASK | Toilet Piping Installation / DW | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
2816 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2817 | TT_TASK | Controls Installation | Wed Sep 08 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2820 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 09 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2821 | TT_TASK | HAC Installation | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2822 | TT_TASK | Cable Tray Installation | Tue May 04 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2823 | TT_TASK | Power Bus Installation | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2824 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2825 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 27 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2826 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Aug 25 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2827 | TT_TASK | Light Fixtures Installation | Sat Aug 21 07:00:00 IDT 2021 | Fri Aug 27 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
2829 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2830 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
2831 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon Sep 27 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2833 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2834 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2837 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 16 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2838 | TT_TASK | HAC Installation | Thu Apr 29 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2839 | TT_TASK | Cable Tray Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2840 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 |  | COMPLETED
2841 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2842 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Fri Sep 03 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2843 | TT_TASK | Pull/term/Test PDU to Power bus | Fri Sep 03 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  | 210.0 | NOT_STARTED
2844 | TT_TASK | Light Fixtures Installation | Fri Oct 01 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2846 | TT_TASK | EPMS Pull Wire / Term / Test | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2847 | TT_TASK | BMS Pull Wire / Term / Test | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
2848 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Thu Oct 21 07:00:00 IDT 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  | 801.0 | NOT_STARTED
2850 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2851 | TT_TASK | Controls Installation | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2854 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 16 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2855 | TT_TASK | HAC Installation | Thu Apr 29 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2856 | TT_TASK | Cable Tray Installation | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2857 | TT_TASK | Power Bus Installation | Mon Jun 14 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2858 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2859 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Sep 01 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2860 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Aug 25 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2861 | TT_TASK | Light Fixtures Installation | Mon Aug 30 07:00:00 IDT 2021 | Tue Sep 07 08:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  | 89.0 | IN_PROGRESS
2863 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2864 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 170.0 | NOT_STARTED
2865 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Sat Oct 09 07:00:00 IDT 2021 | Tue Nov 02 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2867 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2868 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2871 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 23 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2872 | TT_TASK | HAC Installation | Fri May 07 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2873 | TT_TASK | Cable Tray Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2874 | TT_TASK | Power Bus Installation | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Thu Jun 24 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2875 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed Jul 14 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2876 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Sep 01 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 25 00:00:00 IDT 2021 |  |  | IN_PROGRESS
2877 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 22 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2878 | TT_TASK | Light Fixtures Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2880 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2881 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 300.0 | NOT_STARTED
2882 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed Nov 03 07:00:00 IST 2021 | Tue Nov 30 17:00:00 IST 2021 |  |  | 691.0 | NOT_STARTED
2884 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2885 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jul 27 00:00:00 IDT 2021 | Tue Aug 24 13:00:00 IDT 2021 |  | COMPLETED
2889 | TT_TASK | ATS Equipment Yellow Tagging (S2 from MER) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2890 | TT_TASK | Control Power Available | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Fri Apr 30 07:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
2891 | TT_TASK | Power available for Start up | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2892 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2893 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 |  | COMPLETED
2895 | TT_TASK | Admin - NETA test validation Inpections- VECA-EPS-RTS Admin | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Mar 11 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
2896 | TT_TASK | Electrical Equipment Yellow Tagging | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2897 | TT_TASK | Admin/Colo-1 Network Startup | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2898 | TT_TASK | EPMS Checkout / Point to Point | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2902 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2903 | TT_TASK | UPM Yellow tagging - Admin & COLO-1 CELL-1 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2904 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
2905 | TT_TASK | SE- Completed L2 QC Checklist | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
2906 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-1 | Sat Apr 17 07:00:00 IDT 2021 | Tue Apr 20 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2907 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2908 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2909 | TT_TASK | Network Startup | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
2910 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2911 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2912 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2914 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2915 | TT_TASK | Power available for Start up | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2916 | TT_TASK | SE- Completed L2 QC Checklist | Mon Jun 14 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
2917 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Jul 13 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2918 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-3 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2919 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-3 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2920 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Thu Jun 10 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2921 | TT_TASK | Network Startup | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 |  | COMPLETED
2922 | TT_TASK | EPMS Checkout / Point to Point | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jul 06 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2923 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2924 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2926 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2927 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2928 | TT_TASK | SE- Completed L2 QC Checklist | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2929 | TT_TASK | Mechanical Equipment Yellow Tag | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 |  | COMPLETED
2930 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-2 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2931 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-2 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2932 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2933 | TT_TASK | Network Startup | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2934 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2935 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2936 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 20 15:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2938 | TT_TASK | Control Power Available | Tue Jun 22 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue Jun 22 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2939 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2940 | TT_TASK | SE- Completed L2 QC Checklist | Mon Jun 14 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
2941 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Jul 02 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2942 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-4 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2943 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-4 | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
2944 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Jul 07 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2945 | TT_TASK | Network Startup | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2946 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2947 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2948 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2950 | TT_TASK | GEN SCR testing and Burnins | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jul 14 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2951 | TT_TASK | Admin GEN SCR testing and Burnins | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2952 | TT_TASK | ATS- Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 |  | 100.0 | IN_PROGRESS
2953 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Tue Jul 13 11:00:00 IDT 2021 | Wed Jul 28 11:00:00 IDT 2021 | Tue Jul 13 11:00:00 IDT 2021 | Wed Jul 28 11:00:00 IDT 2021 |  | COMPLETED
2954 | TT_TASK | Cooling Automation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2955 | TT_TASK | BAS Prefunctional Testing on Construction Server | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Sat Aug 28 00:00:00 IDT 2021 |  | COMPLETED
2956 | TT_TASK | Additional Go-Back loadbanking (ASCO) | Fri Sep 10 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2957 | TT_TASK | Load Bank & IR Scan | Wed Sep 15 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2958 | TT_TASK | Level 3 Cx - ADMIN AND COLO1 | Fri Sep 17 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2959 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Sat Oct 02 07:00:00 IDT 2021 | Sat Oct 02 07:00:00 IDT 2021 |  |  |  | NOT_STARTED
2961 | TT_TASK | COLO 1 Level 4 & Level 5 IST | Sat Oct 02 08:00:00 IDT 2021 | Fri Oct 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2962 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Sat Oct 30 08:00:00 IDT 2021 | Mon Nov 08 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2963 | TT_TASK | Security Commissioning (level3 DCPS) | Tue Nov 09 08:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2964 | TT_TASK | Punch List - Admin/COLO 1 | Sat Oct 30 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2965 | TT_TASK | MST Ready for Network Install | Sat Oct 02 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2966 | TT_TASK | Final Clean/ ready for lock down | Sat Nov 13 07:00:00 IST 2021 | Mon Nov 22 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2970 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 18 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2971 | TT_TASK | Power available for Start up | Sat Sep 11 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2972 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2973 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  | 20.0 | IN_PROGRESS
2974 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-1 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2975 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-1 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2976 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Aug 04 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2977 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2978 | TT_TASK | EPMS Checkout / Point to Point | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 200.0 | NOT_STARTED
2979 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Thu Sep 16 07:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 |  |  | 20.0 | NOT_STARTED
2980 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Thu Sep 16 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  | 50.0 | NOT_STARTED
2982 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2983 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2984 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2985 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2986 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-3 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2987 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-3 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2988 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2989 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2990 | TT_TASK | EPMS Checkout / Point to Point | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
2991 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2992 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2994 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2995 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2996 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2997 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2998 | TT_TASK | UPM Yellow tagging - COLO-2 CELL-2 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2999 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-2 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
3000 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jul 13 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3001 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3002 | TT_TASK | EPMS Checkout / Point to Point | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3003 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3004 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3006 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3007 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3008 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
3009 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3010 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-4 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
3011 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-4 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
3012 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Aug 18 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3013 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3014 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3015 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3016 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  | 30.0 | NOT_STARTED
3018 | TT_TASK | GEN SCR testing and Burnins | Sat Sep 18 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  | 150.0 | NOT_STARTED
3019 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Mon Sep 27 07:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3020 | TT_TASK | Cooling Automation | Mon Oct 11 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3021 | TT_TASK | BAS Prefunctional Testing on Construction Server | Thu Oct 07 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3022 | TT_TASK | Load Bank & IR Scan | Tue Oct 26 07:00:00 IDT 2021 | Tue Nov 16 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3023 | TT_TASK | Level 3 Cx- COLO-2 | Wed Nov 17 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3024 | TT_TASK | Weather (5 Days) - 0 remaining Check Delay #14 for updates | Sat Dec 04 07:00:00 IST 2021 | Sat Dec 04 07:00:00 IST 2021 |  |  |  | NOT_STARTED
3026 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Mon Dec 27 07:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3027 | TT_TASK | Security Commissioning (level3 DCPS) | Tue Jan 11 07:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3028 | TT_TASK | COLO 2 Level 4 & Level 5 IST | Sat Dec 04 08:00:00 IST 2021 | Fri Dec 24 17:00:00 IST 2021 |  |  | 16.0 | NOT_STARTED
3029 | TT_TASK | Punch List COLO-2 | Mon Dec 27 08:00:00 IST 2021 | Sun Jan 09 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3030 | TT_TASK | MST Ready for Network Install | Sat Dec 04 07:00:00 IST 2021 | Thu Dec 09 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3031 | TT_TASK | Final Clean/ ready for lock down | Mon Jan 10 08:00:00 IST 2022 | Fri Jan 21 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3035 | TT_TASK | Control Power Available | Thu Sep 09 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3036 | TT_TASK | Power available for Start up | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3037 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3038 | TT_TASK | Mechanical Equipment Yellow Tag | Wed Sep 22 07:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3039 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-1 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3040 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-1 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3041 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3042 | TT_TASK | Network Startup | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3043 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3044 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3045 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Tue Oct 05 07:00:00 IDT 2021 | Tue Oct 19 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3047 | TT_TASK | Control Power Available | Tue Sep 21 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3048 | TT_TASK | Power available for Start up | Mon Oct 04 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3049 | TT_TASK | SE- Completed L2 QC Checklist | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3050 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Oct 05 07:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3051 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-3 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 160.0 | NOT_STARTED
3052 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-3 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3053 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3054 | TT_TASK | Network Startup | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3055 | TT_TASK | EPMS Checkout / Point to Point | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3056 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3057 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Oct 18 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3059 | TT_TASK | Control Power Available | Thu Sep 09 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3060 | TT_TASK | Power available for Start up | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3061 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3062 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3063 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-2 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3064 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-2 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3065 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Fri Aug 13 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3066 | TT_TASK | Network Startup | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3067 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3068 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3069 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  |  | 170.0 | NOT_STARTED
3071 | TT_TASK | Control Power Available | Tue Sep 21 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3072 | TT_TASK | Power available for Start up | Mon Oct 04 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3073 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3074 | TT_TASK | Mechanical Equipment Yellow Tag | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3075 | TT_TASK | UPM Yellow tagging COLO-3 CELL-4 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 160.0 | NOT_STARTED
3076 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-4 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
3077 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3078 | TT_TASK | Network Startup | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3079 | TT_TASK | EPMS Checkout / Point to Point | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3080 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3081 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  |  | 70.0 | NOT_STARTED
3083 | TT_TASK | GEN SCR testing and Burnins | Fri Oct 08 07:00:00 IDT 2021 | Tue Oct 26 17:00:00 IDT 2021 |  |  | 320.0 | NOT_STARTED
3084 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Fri Oct 22 07:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3085 | TT_TASK | Cooling Automation | Fri Nov 05 07:00:00 IST 2021 | Fri Nov 19 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3086 | TT_TASK | BAS Prefunctional Testing on Construction Server | Mon Nov 01 07:00:00 IST 2021 | Wed Nov 24 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3087 | TT_TASK | Load Bank & IR Scan | Wed Dec 08 07:00:00 IST 2021 | Mon Jan 03 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3088 | TT_TASK | Level 3 Cx- COLO-3 | Tue Jan 04 07:00:00 IST 2022 | Tue Jan 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3089 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Wed Jan 19 07:00:00 IST 2022 | Wed Jan 19 07:00:00 IST 2022 |  |  |  | NOT_STARTED
3091 | TT_TASK | COLO 3 Level 4 & Level 5 IST | Wed Jan 19 08:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3092 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Wed Feb 09 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3093 | TT_TASK | Security Commissioning (level3 DCPS) | Sat Feb 19 08:00:00 IST 2022 | Wed Feb 23 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3094 | TT_TASK | Punch List COLO-3 | Wed Feb 09 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3095 | TT_TASK | MST Ready for Network Install | Wed Jan 19 08:00:00 IST 2022 | Tue Jan 25 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3096 | TT_TASK | Final Clean/ ready for lock down | Wed Feb 23 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3100 | TT_TASK | Control Power Available | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3101 | TT_TASK | Power available for Start up | Tue Nov 02 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3102 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3103 | TT_TASK | Mechanical Equipment Yellow Tag | Mon Oct 18 07:00:00 IDT 2021 | Thu Oct 28 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3104 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-1 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
3105 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-1 | Fri Sep 17 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
3106 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3107 | TT_TASK | Network Startup | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3108 | TT_TASK | EPMS Checkout / Point to Point | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  | 40.0 | NOT_STARTED
3109 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3110 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3112 | TT_TASK | Control Power Available | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3113 | TT_TASK | Power available for Start up | Mon Nov 15 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3114 | TT_TASK | SE- Completed L2 QC Checklist | Sat Oct 23 07:00:00 IDT 2021 | Wed Nov 03 17:00:00 IST 2021 |  |  | 20.0 | NOT_STARTED
3115 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Oct 29 07:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 |  |  | 70.0 | NOT_STARTED
3116 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-3 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Mon Aug 16 00:00:00 IDT 2021 |  | COMPLETED
3117 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-3 | Tue Sep 28 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  | 200.0 | NOT_STARTED
3118 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3119 | TT_TASK | Network Startup | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3120 | TT_TASK | EPMS Checkout / Point to Point | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3121 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3122 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3124 | TT_TASK | Control Power Available | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3125 | TT_TASK | Power available for Start up | Tue Nov 02 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3126 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3127 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3128 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-2 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3129 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-2 | Fri Sep 17 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
3130 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3131 | TT_TASK | Network Startup | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3132 | TT_TASK | EPMS Checkout / Point to Point | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3133 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3134 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3136 | TT_TASK | Control Power Available | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3137 | TT_TASK | Power available for Start up | Mon Nov 15 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3138 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3139 | TT_TASK | Mechanical Equipment Yellow Tag | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  | 140.0 | NOT_STARTED
3140 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-4 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3141 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-4 | Sat Sep 18 07:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 |  |  | 270.0 | NOT_STARTED
3142 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3143 | TT_TASK | Network Startup | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3144 | TT_TASK | EPMS Checkout / Point to Point | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3145 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3146 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3148 | TT_TASK | GEN SCR testing and Burnins | Fri Nov 19 07:00:00 IST 2021 | Thu Dec 09 17:00:00 IST 2021 |  |  | 310.0 | NOT_STARTED
3149 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Tue Nov 30 07:00:00 IST 2021 | Mon Dec 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3150 | TT_TASK | Cooling Automation | Tue Dec 14 07:00:00 IST 2021 | Thu Dec 30 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3151 | TT_TASK | BAS Prefunctional Testing on Construction Server | Tue Dec 07 07:00:00 IST 2021 | Tue Jan 04 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3152 | TT_TASK | Load Bank & IR Scan | Sat Jan 22 07:00:00 IST 2022 | Sat Feb 12 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3153 | TT_TASK | Level 3 Cx - COLO-4 | Mon Feb 14 07:00:00 IST 2022 | Sat Feb 26 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3154 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Mon Feb 28 07:00:00 IST 2022 | Mon Feb 28 07:00:00 IST 2022 |  |  |  | NOT_STARTED
3156 | TT_TASK | COLO 4 Level 4 & Level 5 IST | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 20 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3157 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Mon Mar 21 08:00:00 IST 2022 | Wed Mar 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3158 | TT_TASK | Security Commissioning (level3 DCPS) | Thu Mar 31 08:00:00 IDT 2022 | Mon Apr 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3159 | TT_TASK | Punch List COLO-4 | Mon Mar 21 08:00:00 IST 2022 | Sat Apr 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3160 | TT_TASK | MST Ready for Network Install | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3161 | TT_TASK | Final Clean/ ready for lock down | Sun Apr 03 08:00:00 IDT 2022 | Wed Apr 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3163 | TT_TASK | CSA Punchlist - COLO-1 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  | COMPLETED
3164 | TT_TASK | CSA Punchlist - COLO-2 | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 220.0 | NOT_STARTED
3165 | TT_TASK | CSA Punchlist - COLO-3 | Mon Nov 01 07:00:00 IST 2021 | Fri Nov 12 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3166 | TT_TASK | CSA Punchlist - COLO-4 | Sat Dec 11 07:00:00 IST 2021 | Thu Dec 23 17:00:00 IST 2021 |  |  | 380.0 | NOT_STARTED
3167 | TT_TASK | MEP Punchlist - COLO-1 | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 110.0 | NOT_STARTED
3168 | TT_TASK | MEP Punchlist - COLO-2 | Wed Nov 17 07:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 |  |  | 20.0 | NOT_STARTED
3169 | TT_TASK | MEP Punchlist - COLO-3 | Tue Jan 04 07:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  |  | 20.0 | NOT_STARTED
3170 | TT_TASK | MEP Punchlist - COLO-4 | Mon Feb 14 07:00:00 IST 2022 | Thu Feb 24 17:00:00 IST 2022 |  |  | 20.0 | NOT_STARTED
3171 | TT_TASK | AE/Owner Punchlist - COLO-1 | Sat Oct 30 07:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  |  | 60.0 | NOT_STARTED
3172 | TT_TASK | AE/Owner Punchlist - COLO-2 | Mon Dec 27 07:00:00 IST 2021 | Mon Jan 03 17:00:00 IST 2022 |  |  | 41.0 | NOT_STARTED
3173 | TT_TASK | AE/Owner Punchlist - COLO-3 | Wed Feb 09 07:00:00 IST 2022 | Mon Feb 14 17:00:00 IST 2022 |  |  | 71.0 | NOT_STARTED
3174 | TT_TASK | AE/Owner Punchlist - COLO-4 | Mon Mar 21 07:00:00 IST 2022 | Fri Mar 25 17:00:00 IDT 2022 |  |  | 70.0 | NOT_STARTED
3182 | TT_TASK | UMS - ROJ COLO-2 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3183 | TT_TASK | UMS - ROJ COLO-3 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3184 | TT_TASK | UMS - ROJ COLO-4 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3185 | TT_TASK | MSFT Delivery -UMS -COLO 4 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3186 | TT_TASK | MSFT Delivery -UMS -COLO 3 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3187 | TT_TASK | MSFT Delivery -UMS -COLO 2 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3190 | TT_TASK | TCO COLO 2 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3191 | TT_TASK | Weather Tight | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3192 | TT_TASK | Duct Bank - UMS01 to UPM COLO-1 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3193 | TT_TASK | Duct Bank - UMS02 to UPM COLO-2 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3194 | TT_TASK | Duct Bank - UMS03 to UPM COLO-3 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3195 | TT_TASK | Duct Bank - UMS04 to UPM COLO-4 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3196 | TT_TASK | PAD- COLO-1 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3197 | TT_TASK | PAD- COLO-2 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3198 | TT_TASK | PAD- COLO-3 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3199 | TT_TASK | PAD- COLO-4 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3200 | TT_TASK | Pull- UMS01- UPM COLO-1 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3201 | TT_TASK | Pull- UMS02- UPM COLO-2 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3202 | TT_TASK | Pull- UMS03- UPM COLO-3 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3203 | TT_TASK | Pull- UMS04- UPM COLO-4 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3204 | TT_TASK | Set- COLO-1 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3205 | TT_TASK | Set- COLO-2 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3206 | TT_TASK | Set- COLO-3 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3207 | TT_TASK | Set- COLO-4 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3208 | TT_TASK | Term Admin - UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3209 | TT_TASK | Term COLO -1 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3210 | TT_TASK | Term COLO -1 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3211 | TT_TASK | Term COLO -2 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3212 | TT_TASK | Term COLO -2 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3213 | TT_TASK | Term COLO -3 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3214 | TT_TASK | Term COLO -3 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3215 | TT_TASK | Term COLO -4 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3216 | TT_TASK | Term COLO -4 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3217 | TT_TASK | Term- UMS01- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3218 | TT_TASK | Term- UMS02- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3219 | TT_TASK | Term- UMS03- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3220 | TT_TASK | Term- UMS04- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3221 | TT_TASK | Yellow Tagging for UMS01 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3222 | TT_TASK | Yellow Tagging for UMS02 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3223 | TT_TASK | Yellow Tagging for UMS03 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3224 | TT_TASK | Yellow Tagging for UMS04 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3225 | TT_TASK | URS Vault design and Approval | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3227 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Thu Oct 22 07:00:00 IDT 2020 | Thu Oct 22 07:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3228 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3229 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jan 23 07:00:00 IST 2021 | Sat Jan 23 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3230 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Thu Oct 22 07:00:00 IDT 2020 | Thu Oct 22 07:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3231 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3232 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jan 23 07:00:00 IST 2021 | Sat Jan 23 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3233 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Nov 04 07:00:00 IST 2020 | Wed Nov 04 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3234 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3235 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Feb 04 07:00:00 IST 2021 | Thu Feb 04 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3236 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Nov 04 07:00:00 IST 2020 | Wed Nov 04 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3237 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3238 | TT_TASK | COLO Lighting installation (DRB#2) | Mon Feb 08 07:00:00 IST 2021 | Mon Feb 08 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3239 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3240 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Dec 02 07:00:00 IST 2020 | Wed Dec 02 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3241 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Mar 11 07:00:00 IST 2021 | Thu Mar 11 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3242 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Tue Dec 29 07:00:00 IST 2020 | Tue Dec 29 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3243 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Dec 02 07:00:00 IST 2020 | Wed Dec 02 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3244 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Mar 11 07:00:00 IST 2021 | Thu Mar 11 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3245 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Dec 18 07:00:00 IST 2020 | Fri Dec 18 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3246 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Dec 15 07:00:00 IST 2020 | Tue Dec 15 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3247 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Mar 26 07:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3248 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Dec 15 07:00:00 IST 2020 | Tue Dec 15 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3249 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Mar 26 07:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3250 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Jan 07 07:00:00 IST 2021 | Thu Jan 07 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3251 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3252 | TT_TASK | COLO Lighting installation (DRB#2) | Tue Apr 27 07:00:00 IDT 2021 | Tue Apr 27 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3253 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Jan 14 07:00:00 IST 2021 | Thu Jan 14 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3254 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3255 | TT_TASK | COLO Lighting installation (DRB#2) | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3256 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Fri Feb 12 07:00:00 IST 2021 | Fri Feb 12 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3257 | TT_TASK | COLO Lighting installation (DRB#2) | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3258 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Jan 29 07:00:00 IST 2021 | Fri Jan 29 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3259 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Fri Feb 12 07:00:00 IST 2021 | Fri Feb 12 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3260 | TT_TASK | COLO Lighting installation (DRB#2) | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3261 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3262 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Mar 09 07:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3263 | TT_TASK | COLO Lighting installation (DRB#2) | Wed Jun 09 07:00:00 IDT 2021 | Wed Jun 09 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3264 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3265 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Mar 09 07:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3266 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Jun 04 07:00:00 IDT 2021 | Fri Jun 04 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3267 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Sat Feb 20 07:00:00 IST 2021 | Sat Feb 20 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3268 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Mon Mar 22 07:00:00 IST 2021 | Mon Mar 22 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3269 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jun 19 07:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3270 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Sat Feb 20 07:00:00 IST 2021 | Sat Feb 20 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3271 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Mon Mar 22 07:00:00 IST 2021 | Mon Mar 22 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3272 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jun 19 07:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3273 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3274 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3275 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3276 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3277 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3278 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3279 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3280 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3281 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3282 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3283 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3284 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3285 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3286 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3287 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3288 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3290 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 05 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3291 | TT_TASK | Mechanical Equipment Piping Connections | Tue Nov 03 07:00:00 IST 2020 | Tue Nov 17 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3292 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3293 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3294 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3295 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3296 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3297 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3298 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3299 | TT_TASK | Fluid Cooler RI prefabrication | Thu Dec 10 07:00:00 IST 2020 | Wed Dec 16 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3300 | TT_TASK | Fluid Cooler RI prefabrication | Wed Dec 16 07:00:00 IST 2020 | Tue Dec 22 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3301 | TT_TASK | Fluid Cooler RI prefabrication | Wed Dec 23 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3302 | TT_TASK | Fluid Cooler RI prefabrication | Thu Jan 07 07:00:00 IST 2021 | Wed Jan 13 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3303 | TT_TASK | Fluid Cooler RI prefabrication | Thu Jan 14 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3304 | TT_TASK | Fluid Cooler RI prefabrication | Fri Jan 22 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3305 | TT_TASK | Fluid Cooler RI prefabrication | Tue Jan 26 07:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3306 | TT_TASK | Submit and approve shop drawing for PEMB penetrations | Mon Oct 19 08:00:00 IDT 2020 | Sun Nov 08 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3308 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3309 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3310 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3311 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3312 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3313 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3314 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3315 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3316 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3317 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3318 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3319 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3321 | TT_TASK | Yellow Tagging for COLO-2 UPM's | Fri Jan 29 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3322 | TT_TASK | Yellow Tagging for COLO-3 UPM's | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 |  | COMPLETED
3323 | TT_TASK | Yellow Tagging for COLO-4 UPM's | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 |  | COMPLETED
3324 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 11 07:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3326 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3327 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3328 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Mar 10 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3329 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 08 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3330 | TT_TASK | Fluid Cooler QAQC and Cx | Thu Mar 18 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3331 | TT_TASK | Fluid Cooler QAQC and Cx | Fri Apr 02 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3332 | TT_TASK | Fluid Cooler QAQC and Cx | Fri Mar 26 07:00:00 IDT 2021 | Sat Mar 27 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3333 | TT_TASK | Fluid Cooler QAQC and Cx | Tue Apr 06 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3334 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 14 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3335 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 21 07:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3336 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 14 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3337 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 28 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3338 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 21 07:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3339 | TT_TASK | Fluid Cooler QAQC and Cx | Thu May 06 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3341 | TT_TASK | COLO-2 CELL3 Rearrange Roxtec blocks per coordination layout | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3342 | TT_TASK | COLO2 CELL3 Interior MER conduit installation utility side | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 06 07:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3343 | TT_TASK | COLO-2 CELL3 Interior MER conduit installation building side | Tue Apr 20 07:00:00 IDT 2021 | Tue Apr 20 07:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3345 | TT_TASK | COLO-2 Cell-4 Rearrange Roxtec blocks per coordination layout | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3346 | TT_TASK | COLO2 CELL4 Interior MER conduit installation utility side | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3347 | TT_TASK | COLO2 CELL4 Interior MER conduit installation building side | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3350 | TT_TASK | COLO-2 Cell-1 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3351 | TT_TASK | COLO-2 Cell-2 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3352 | TT_TASK | COLO-2 Cell-3 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3353 | TT_TASK | COLO-2 Cell-4 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3354 | TT_TASK | COLO2 CELL1 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3355 | TT_TASK | COLO2 CELL2 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3356 | TT_TASK | COLO2 CELL3 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3357 | TT_TASK | COLO2 CELL4 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3360 | TT_TASK | Concrete interior - Create Punch list | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
3361 | TT_TASK | Concrete interior - Complete Punch List | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
3362 | TT_TASK | Garco Steel (Mezz steel, Yard) - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3363 | TT_TASK | Garco Steel (Mezz steel, Yard) - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3364 | TT_TASK | Sure Steel (Building, Mezz, Ceiling) - Create Punch list | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
3365 | TT_TASK | Sure Steel (Building, Mezz, Ceiling) - Complete Punch List | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
3366 | TT_TASK | Advantage - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3367 | TT_TASK | Advantage - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3368 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3369 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3370 | TT_TASK | VECA - Create Punch list | Tue Sep 07 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3371 | TT_TASK | VECA - Complete Punch List | Thu Sep 09 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3372 | TT_TASK | LINX - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3373 | TT_TASK | LINX - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3374 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3375 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3376 | TT_TASK | TCM- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3377 | TT_TASK | TCM - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3378 | TT_TASK | Cascade- Create Punch list | Mon Apr 26 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
3379 | TT_TASK | Cascade - Complete Punch List | Wed Apr 28 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3380 | TT_TASK | Submit GC Punch List to A/E | Tue Sep 21 07:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3381 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3382 | TT_TASK | Complete A/E Punchlist | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3383 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3384 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3385 | TT_TASK | VECA - Create Punch list | Fri Oct 29 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3386 | TT_TASK | VECA - Complete Punch List | Mon Nov 01 07:00:00 IST 2021 | Mon Nov 08 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3387 | TT_TASK | LINX - Create Punch list | Mon Aug 16 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3388 | TT_TASK | LINX - Complete Punch List | Wed Aug 18 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3389 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3390 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3391 | TT_TASK | TCM- Create Punch list | Wed Sep 22 07:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3392 | TT_TASK | TCM - Complete Punch List | Fri Sep 24 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3393 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3394 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3395 | TT_TASK | Submit GC Punch List to A/E | Tue Nov 09 07:00:00 IST 2021 | Tue Nov 09 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3396 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Nov 10 07:00:00 IST 2021 | Tue Nov 16 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3397 | TT_TASK | Complete A/E Punchlist | Wed Nov 17 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3398 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3399 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3400 | TT_TASK | VECA - Create Punch list | Tue Dec 14 07:00:00 IST 2021 | Wed Dec 15 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3401 | TT_TASK | VECA - Complete Punch List | Thu Dec 16 07:00:00 IST 2021 | Thu Dec 23 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3402 | TT_TASK | LINX - Create Punch list | Wed Oct 13 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3403 | TT_TASK | LINX - Complete Punch List | Fri Oct 15 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3404 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3405 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3406 | TT_TASK | TCM- Create Punch list | Wed Sep 22 07:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3407 | TT_TASK | TCM - Complete Punch List | Fri Sep 24 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3408 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3409 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3410 | TT_TASK | Submit GC Punch List to A/E | Mon Dec 27 07:00:00 IST 2021 | Mon Dec 27 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3411 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Tue Dec 28 07:00:00 IST 2021 | Wed Jan 05 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3412 | TT_TASK | Complete A/E Punchlist | Thu Jan 06 07:00:00 IST 2022 | Thu Jan 20 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3413 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3414 | TT_TASK | PCI - Complete Punch List | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3415 | TT_TASK | VECA - Create Punch list | Fri Jan 28 07:00:00 IST 2022 | Mon Jan 31 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3416 | TT_TASK | VECA - Complete Punch List | Tue Feb 01 07:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3417 | TT_TASK | LINX - Create Punch list | Fri Nov 19 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3418 | TT_TASK | LINX - Complete Punch List | Mon Nov 22 07:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3419 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3420 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3421 | TT_TASK | TCM- Create Punch list | Thu Nov 04 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3422 | TT_TASK | TCM - Complete Punch List | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3423 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3424 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3425 | TT_TASK | Submit GC Punch List to A/E | Tue Feb 08 07:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3426 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Feb 09 07:00:00 IST 2022 | Tue Feb 15 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3427 | TT_TASK | Complete A/E Punchlist | Wed Feb 16 07:00:00 IST 2022 | Tue Mar 01 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3428 | TT_TASK | COLO-2 Cell2 Rearrange Roxtec blocks per coordination layout (delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
3429 | TT_TASK | COLO2 CELL2 Interior MER conduit installation utility side(delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
3430 | TT_TASK | COLO-2 CELL2 Interior MER conduit installation building (delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
3432 | TT_TASK | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change(delete) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
3433 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3434 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3435 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3436 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
73 | TT_TASK | Prepare Drainage Diversion Submission | Thu Mar 31 08:00:00 IDT 2016 | Wed Apr 27 16:00:00 IDT 2016 | Thu Mar 31 08:00:00 IDT 2016 | Sat Apr 23 17:00:00 IDT 2016 |  | COMPLETED
75 | TT_TASK | Drainage Diversion 1st Submission | Wed Jun 01 08:00:00 IDT 2016 | Wed Aug 17 16:00:00 IDT 2016 | Thu May 26 00:00:00 IDT 2016 | Wed Jul 20 17:00:00 IDT 2016 |  | COMPLETED
76 | TT_TASK | Drainage Diversion GBP | Thu Sep 15 08:00:00 IDT 2016 | Mon Dec 05 16:00:00 IST 2016 | Thu Sep 15 08:00:00 IDT 2016 | Fri Nov 11 17:00:00 IST 2016 |  | COMPLETED
77 | TT_TASK | Drainage Diversion - Consent | Thu Dec 01 08:00:00 IST 2016 | Mon Jan 09 16:00:00 IST 2017 | Thu Dec 01 08:00:00 IST 2016 | Wed Dec 28 17:00:00 IST 2016 |  | COMPLETED
78 | TT_TASK | Drainage Diversion Resubmission (Structural) | Thu Sep 15 09:00:00 IDT 2016 | Thu Nov 17 09:00:00 IST 2016 | Thu Sep 15 09:00:00 IDT 2016 | Wed Nov 09 17:00:00 IST 2016 |  | COMPLETED
79 | TT_TASK | Drainage Diversion Resubmission (Drainage Plans) | Thu Sep 15 09:00:00 IDT 2016 | Thu Nov 17 09:00:00 IST 2016 | Thu Sep 15 09:00:00 IDT 2016 | Wed Nov 09 17:00:00 IST 2016 |  | COMPLETED
80 | TT_TASK | Drainage Diversion 1st Amendment (Structural) | Fri May 19 08:00:00 IDT 2017 | Mon Jun 19 16:00:00 IDT 2017 | Fri May 19 08:00:00 IDT 2017 | Wed Jun 14 18:00:00 IDT 2017 |  | COMPLETED
81 | TT_TASK | Drainage Diversion ELS 1st Submission | Wed Jan 18 08:00:00 IST 2017 | Thu Mar 23 16:00:00 IST 2017 | Wed Jan 18 08:00:00 IST 2017 | Thu Mar 16 17:00:00 IST 2017 |  | COMPLETED
82 | TT_TASK | Drainage Diversion ELS 1st Amendment | Fri Apr 21 08:00:00 IDT 2017 | Tue May 23 16:00:00 IDT 2017 | Fri Apr 21 08:00:00 IDT 2017 | Fri May 19 17:00:00 IDT 2017 |  | COMPLETED
85 | TT_TASK | Prepare warehouse demolition and A&A works | Wed Jul 29 08:00:00 IDT 2015 | Tue Nov 03 16:00:00 IST 2015 | Wed Jul 29 08:00:00 IDT 2015 | Mon Nov 02 17:00:00 IST 2015 |  | COMPLETED
86 | TT_TASK | Prepare warehouse demolition and A&A works amendment | Mon Jul 04 08:00:00 IDT 2016 | Mon Sep 05 16:00:00 IDT 2016 | Sat Jul 02 09:00:00 IDT 2016 | Wed Aug 24 18:00:00 IDT 2016 |  | COMPLETED
88 | TT_TASK | Warehouse demolition and A&A works (GBP & Structural) - 1st Submission | Tue Nov 03 08:00:00 IST 2015 | Tue Jan 05 16:00:00 IST 2016 | Tue Nov 03 08:00:00 IST 2015 | Mon Dec 28 17:00:00 IST 2015 |  | COMPLETED
89 | TT_TASK | Warehouse demolition and A&A works (GBP) - Amendment Submission | Thu Sep 01 08:00:00 IDT 2016 | Wed Oct 12 16:00:00 IDT 2016 | Thu Aug 25 08:00:00 IDT 2016 | Tue Oct 04 17:00:00 IDT 2016 |  | COMPLETED
90 | TT_TASK | Warehouse demolition and A&A works (Structural)- Amendment Submission | Thu Sep 01 08:00:00 IDT 2016 | Wed Oct 12 16:00:00 IDT 2016 | Wed Apr 05 00:00:00 IDT 2017 | Fri Apr 28 00:00:00 IDT 2017 |  | COMPLETED
91 | TT_TASK | Warehouse demolition and A&A works - Consent | Mon Sep 26 08:00:00 IDT 2016 | Thu Nov 03 16:00:00 IST 2016 | Thu Oct 20 08:00:00 IDT 2016 | Mon Nov 21 17:00:00 IST 2016 |  | COMPLETED
94 | TT_TASK | Prepare Power Island Piling Submission | Tue Dec 01 08:00:00 IST 2015 | Fri Feb 19 16:00:00 IST 2016 | Tue Dec 01 08:00:00 IST 2015 | Thu Jan 28 17:00:00 IST 2016 |  | COMPLETED
96 | TT_TASK | Power Island Piling - 1st Submission | Mon Feb 01 08:00:00 IST 2016 | Mon Apr 18 16:00:00 IDT 2016 | Fri Jan 29 00:00:00 IST 2016 | Thu Mar 24 17:00:00 IST 2016 |  | COMPLETED
97 | TT_TASK | Power Island Piling - Amendment | Tue Aug 09 08:00:00 IDT 2016 | Wed Sep 21 16:00:00 IDT 2016 | Tue Aug 09 08:00:00 IDT 2016 | Fri Sep 09 17:00:00 IDT 2016 |  | COMPLETED
98 | TT_TASK | Power Island Piling - Consent | Mon Sep 12 08:00:00 IDT 2016 | Fri Nov 11 16:00:00 IST 2016 | Fri Sep 09 16:00:00 IDT 2016 | Tue Oct 25 00:00:00 IDT 2016 |  | COMPLETED
99 | TT_TASK | BA14 submission & pile test | Thu May 25 08:00:00 IDT 2017 | Mon Jul 03 16:00:00 IDT 2017 | Thu May 25 08:00:00 IDT 2017 | Wed Jun 21 17:00:00 IDT 2017 |  | COMPLETED
100 | TT_TASK | Piling 1st Submission | Fri Jan 29 08:00:00 IST 2016 | Mon Mar 28 16:00:00 IDT 2016 | Fri Jan 29 08:00:00 IST 2016 | Thu Mar 24 17:00:00 IST 2016 |  | COMPLETED
101 | TT_TASK | Piling 1st Amendment | Tue Aug 09 08:00:00 IDT 2016 | Thu Sep 15 16:00:00 IDT 2016 | Tue Aug 09 08:00:00 IDT 2016 | Fri Sep 09 18:00:00 IDT 2016 |  | COMPLETED
102 | TT_TASK | Piling 2nd Amendment | Mon Nov 07 08:00:00 IST 2016 | Wed Dec 07 16:00:00 IST 2016 | Mon Nov 07 08:00:00 IST 2016 | Fri Dec 02 17:00:00 IST 2016 |  | COMPLETED
103 | TT_TASK | Piling 3rd Amendment | Tue Feb 21 08:00:00 IST 2017 | Fri Mar 24 16:00:00 IDT 2017 | Tue Feb 21 08:00:00 IST 2017 | Tue Mar 21 17:00:00 IST 2017 |  | COMPLETED
104 | TT_TASK | Piling 4th Amendment | Tue Mar 21 08:00:00 IST 2017 | Fri Apr 14 16:00:00 IDT 2017 | Tue Mar 21 08:00:00 IST 2017 | Wed Apr 12 17:00:00 IDT 2017 |  | COMPLETED
105 | TT_TASK | Piling 5th Amendment | Tue May 02 08:00:00 IDT 2017 | Mon May 22 16:00:00 IDT 2017 | Tue May 02 08:00:00 IDT 2017 | Fri May 19 17:00:00 IDT 2017 |  | COMPLETED
108 | TT_TASK | Warehouse Demolition works | Tue Jun 01 08:00:00 IDT 2021 | Mon Jul 05 16:00:00 IDT 2021 | Fri Dec 16 08:00:00 IST 2016 | Tue Jan 17 16:00:00 IST 2017 |  | COMPLETED
109 | TT_TASK | Warehouse A&A Works, ready for main contract fitout (150 Days - 14/5/2017) | Tue Jun 01 08:00:00 IDT 2021 | Thu Sep 09 16:00:00 IDT 2021 | Wed Jan 18 00:00:00 IST 2017 | Fri Apr 21 16:00:00 IDT 2017 |  | COMPLETED
111 | TT_TASK | Turbine Hall (Driven Piles) | Tue Jun 01 08:00:00 IDT 2021 | Thu Oct 14 16:00:00 IDT 2021 | Tue Dec 20 08:00:00 IST 2016 | Thu May 04 16:00:00 IDT 2017 |  | COMPLETED
112 | TT_TASK | Site Drainage A&A works & Site Demob | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Tue Dec 20 08:00:00 IST 2016 | Sat Sep 30 16:00:00 IDT 2017 |  | COMPLETED
113 | TT_TASK | Turbine Hall (Pre-Bore Socket H-Piles) | Tue Jun 01 08:00:00 IDT 2021 | Mon Jul 12 16:00:00 IDT 2021 | Tue Dec 20 08:00:00 IST 2016 | Sat May 06 16:00:00 IDT 2017 |  | COMPLETED
114 | TT_TASK | HRSG (Driven H-Piles) | Tue Jun 01 08:00:00 IDT 2021 | Fri Jul 09 16:00:00 IDT 2021 | Tue Dec 20 08:00:00 IST 2016 | Thu May 04 16:00:00 IDT 2017 |  | COMPLETED
115 | TT_TASK | Post Drilling / BD Selection / Load Tests / BD Consent for Pile Cap | Tue Jun 01 08:00:00 IDT 2021 | Fri Jul 23 16:00:00 IDT 2021 | Tue May 09 08:00:00 IDT 2017 | Fri Jun 30 16:00:00 IDT 2017 |  | COMPLETED
116 | TT_TASK | Construct Trials & Test for BD inspection and acknowledgement | Tue Jun 01 08:00:00 IDT 2021 | Fri Jun 18 16:00:00 IDT 2021 | Tue Nov 08 08:00:00 IST 2016 | Wed Nov 23 16:00:00 IST 2016 |  | COMPLETED
118 | TT_TASK | Bulk excavation | Tue Jun 01 08:00:00 IDT 2021 | Mon Jul 05 16:00:00 IDT 2021 | Wed Jun 14 00:00:00 IDT 2017 | Wed Jul 19 00:00:00 IDT 2017 |  | COMPLETED
171 | TT_TASK | SEISMIC REPORT | Sat Jul 09 08:00:00 IDT 2016 | Thu Aug 04 17:00:00 IDT 2016 | Sat Jul 09 08:00:00 IDT 2016 | Fri Aug 05 17:00:00 IDT 2016 |  | COMPLETED
173 | TT_TASK | GENERAL DESIGN CRITERIA (SIEMENS SCOPE ONLY) | Thu Nov 03 08:00:00 IST 2016 | Wed Dec 14 17:00:00 IST 2016 | Thu Nov 03 08:00:00 IST 2016 | Wed Dec 14 17:00:00 IST 2016 |  | COMPLETED
176 | TT_TASK | PREPARATION FINAL FIRE- / EXPLOSION PROT. CONCEPT AND ESCAPE ROUTE/FIRE PROTECTION DWGs | Tue Feb 14 08:00:00 IST 2017 | Mon Mar 13 17:00:00 IST 2017 | Wed Feb 01 08:00:00 IST 2017 | Wed Mar 08 17:00:00 IST 2017 |  | COMPLETED
179 | TT_TASK | NOISE PROTECTION CONCEPT | Sat Oct 01 08:00:00 IDT 2016 | Wed Apr 05 17:00:00 IDT 2017 | Sat Jun 11 08:00:00 IDT 2016 | Mon Dec 26 17:00:00 IST 2016 |  | COMPLETED
184 | TT_TASK | QUOTATION STAGE STEEL WORKS (excl.EMBEDDED PARTS) | Tue Feb 14 08:00:00 IST 2017 | Wed Apr 12 17:00:00 IDT 2017 | Wed Jan 18 00:00:00 IST 2017 | Sun Apr 23 17:00:00 IDT 2017 |  | COMPLETED
186 | TT_TASK | REVIEW BY CLIENT FOR CONCEPT DESIGN DOCUMENTS | Wed Mar 01 08:00:00 IST 2017 | Tue Mar 21 17:00:00 IST 2017 | Tue Feb 28 08:00:00 IST 2017 | Mon Mar 20 17:00:00 IST 2017 |  | COMPLETED
188 | TT_TASK | CONCEPT DESIGN (part I) PLOT PLAN | Sat Oct 01 08:00:00 IDT 2016 | Thu Oct 27 17:00:00 IDT 2016 | Sat Aug 20 08:00:00 IDT 2016 | Fri Sep 16 17:00:00 IDT 2016 |  | COMPLETED
197 | TT_TASK | BASIC DESIGN PLANT LAYOUT | Thu Jan 19 08:00:00 IST 2017 | Sat Mar 11 17:00:00 IST 2017 | Thu Dec 15 08:00:00 IST 2016 | Wed Mar 08 17:00:00 IST 2017 |  | COMPLETED
204 | TT_TASK | PREPARATION RFQ PREFAB. MODULES | Sat Nov 26 08:00:00 IST 2016 | Sat Mar 04 17:00:00 IST 2017 | Thu Nov 03 08:00:00 IST 2016 | Tue Feb 28 17:00:00 IST 2017 |  | COMPLETED
205 | TT_TASK | QUOTATION STAGE PREFAB. MODULES | Thu Mar 16 08:00:00 IST 2017 | Thu May 18 17:00:00 IDT 2017 | Wed Mar 01 08:00:00 IST 2017 | Sun Apr 30 17:00:00 IDT 2017 |  | COMPLETED
208 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST SUMP PUMP GM/UGU | Sun Nov 26 08:00:00 IST 2017 | Wed Apr 25 17:00:00 IDT 2018 | Thu Oct 26 00:00:00 IDT 2017 | Fri Oct 05 17:00:00 IDT 2018 |  | COMPLETED
210 | TT_TASK | TRANSPORT SUMP PUMP GM/UGU | Sat Jun 16 08:00:00 IDT 2018 | Tue Aug 14 17:00:00 IDT 2018 | Wed Nov 21 08:00:00 IST 2018 | Sun Nov 25 17:00:00 IST 2018 |  | COMPLETED
213 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST FIRE FIGHTING RING MAIN SGA | Wed Aug 30 08:00:00 IDT 2017 | Wed Dec 27 17:00:00 IST 2017 | Fri Aug 18 08:00:00 IDT 2017 | Thu Nov 15 17:00:00 IST 2018 |  | COMPLETED
216 | TT_TASK | TRANSPORT FIRE FIGHTING RING MAIN SGA | Wed May 30 08:00:00 IDT 2018 | Tue Jul 24 17:00:00 IDT 2018 | Wed Nov 21 08:00:00 IST 2018 | Thu Nov 29 17:00:00 IST 2018 |  | COMPLETED
227 | TT_TASK | PREPARATION OF LENGTH MATRIX | Tue Apr 11 08:00:00 IDT 2017 | Mon Apr 24 17:00:00 IDT 2017 | Tue Mar 28 08:00:00 IDT 2017 | Mon Apr 10 17:00:00 IDT 2017 |  | COMPLETED
229 | TT_TASK | DESIGN POWER / CONTROL CABLES | Thu May 11 08:00:00 IDT 2017 | Fri Oct 27 17:00:00 IDT 2017 | Tue Apr 11 08:00:00 IDT 2017 | Wed Sep 27 17:00:00 IDT 2017 |  | COMPLETED
231 | TT_TASK | DETAIL DESIGN CABLE ROUTING | Mon Jun 26 08:00:00 IDT 2017 | Wed Jan 03 17:00:00 IST 2018 | Tue Jun 13 08:00:00 IDT 2017 | Thu Dec 21 17:00:00 IST 2017 |  | COMPLETED
235 | TT_TASK | MANUFACTURING, SHOP TEST MV/LV CABLES BZK (1ST SET 30%) | Sat Aug 26 08:00:00 IDT 2017 | Fri Feb 09 17:00:00 IST 2018 | Fri Aug 25 08:00:00 IDT 2017 | Tue Mar 06 17:00:00 IST 2018 |  | COMPLETED
237 | TT_TASK | MANUFACTURING, SHOP TEST MV/LV CABLES BZK (2ND SET 80%) | Thu Mar 29 08:00:00 IDT 2018 | Sun May 27 17:00:00 IDT 2018 | Tue May 15 08:00:00 IDT 2018 | Tue Jul 10 17:00:00 IDT 2018 |  | COMPLETED
239 | TT_TASK | TRANSPORT MV/LV CABLES BZK (1ST SET 30%) | Thu Mar 29 08:00:00 IDT 2018 | Fri Apr 27 17:00:00 IDT 2018 | Sat Apr 14 08:00:00 IDT 2018 | Tue Apr 24 17:00:00 IDT 2018 |  | COMPLETED
240 | TT_TASK | TRANSPORT MV/LV CABLES BZK (2ND SET 80%) | Mon May 28 08:00:00 IDT 2018 | Sun Jul 15 17:00:00 IDT 2018 | Sat Jul 21 08:00:00 IDT 2018 | Thu Jul 26 17:00:00 IDT 2018 |  | COMPLETED
242 | TT_TASK | MANUFACTURING, SHOP TEST FIRST CABLE SUPPORT SYSTEM BZP (FOR PRE-FAB MODULES) | Mon Jun 26 08:00:00 IDT 2017 | Fri Aug 18 17:00:00 IDT 2017 | Fri Jun 02 08:00:00 IDT 2017 | Fri Sep 01 17:00:00 IDT 2017 |  | COMPLETED
244 | TT_TASK | MANUFACTURING, SHOP TEST CABLE SUPPORT SYSTEM BZP (MAIN) | Mon Oct 16 08:00:00 IDT 2017 | Sun Dec 10 17:00:00 IST 2017 | Fri Sep 15 08:00:00 IDT 2017 | Thu Mar 08 17:00:00 IST 2018 |  | COMPLETED
246 | TT_TASK | MANUFACTURING, SHOP TEST CABLE SUPPORT SYSTEM BZP (BOP) | Sun Nov 26 08:00:00 IST 2017 | Sat Jan 20 17:00:00 IST 2018 | Fri Nov 17 08:00:00 IST 2017 | Thu May 31 17:00:00 IDT 2018 |  | COMPLETED
248 | TT_TASK | TRANSPORT FIRST CABLE SUPPORT SYSTEM BZP (MAIN) | Mon Apr 09 08:00:00 IDT 2018 | Thu Jun 07 17:00:00 IDT 2018 | Mon Apr 09 08:00:00 IDT 2018 | Sat Apr 21 17:00:00 IDT 2018 |  | COMPLETED
249 | TT_TASK | TRANSPORT FIRST CABLE SUPPORT SYSTEM BZP (FOR PRE-FAB MODULES) | Thu Oct 26 08:00:00 IDT 2017 | Tue Dec 12 17:00:00 IST 2017 | Fri Sep 29 08:00:00 IDT 2017 | Fri Dec 29 17:00:00 IST 2017 |  | COMPLETED
250 | TT_TASK | TRANSPORT SECOND CABLE SUPPORT SYSTEM BZP (BOP) | Tue Apr 24 08:00:00 IDT 2018 | Fri Jun 22 17:00:00 IDT 2018 | Fri Jun 01 08:00:00 IDT 2018 | Wed Jun 20 17:00:00 IDT 2018 |  | COMPLETED
252 | TT_TASK | MANUFACTURING, SHOP TEST TELECOMMUNICATION CYA | Thu Oct 26 08:00:00 IDT 2017 | Fri Feb 09 17:00:00 IST 2018 | Fri Sep 29 08:00:00 IDT 2017 | Mon Jun 25 17:00:00 IDT 2018 |  | COMPLETED
254 | TT_TASK | TRANSPORT TELECOMMUNICATION CYA | Tue May 15 08:00:00 IDT 2018 | Fri Jul 06 17:00:00 IDT 2018 | Fri Jun 29 08:00:00 IDT 2018 | Fri Jul 13 17:00:00 IDT 2018 |  | COMPLETED
256 | TT_TASK | MANUFACTURING, SHOP TEST SECURITY CYP | Thu Oct 26 08:00:00 IDT 2017 | Fri Feb 09 17:00:00 IST 2018 | Fri Sep 29 08:00:00 IDT 2017 | Mon Jun 25 17:00:00 IDT 2018 |  | COMPLETED
258 | TT_TASK | TRANSPORT SECURITY CYP | Tue May 15 08:00:00 IDT 2018 | Fri Jul 06 17:00:00 IDT 2018 | Fri Jun 29 08:00:00 IDT 2018 | Fri Jul 13 17:00:00 IDT 2018 |  | COMPLETED
261 | TT_TASK | ST I&C TRANSPORT TO SITE FIELD INSTRUMENTATION | Mon Mar 26 08:00:00 IDT 2018 | Thu May 24 17:00:00 IDT 2018 | Fri Mar 16 08:00:00 IST 2018 | Sun May 13 17:00:00 IDT 2018 |  | COMPLETED
264 | TT_TASK | ENGINEERING P&IDs, SYSTEM DESCRIPTION HRSG-SYSTEMS | Sat Jan 14 08:00:00 IST 2017 | Fri Jan 20 17:00:00 IST 2017 | Sat Dec 10 08:00:00 IST 2016 | Fri Dec 16 17:00:00 IST 2016 |  | COMPLETED
267 | TT_TASK | DESIGN REVIEW INCL. SIL-STUDY HRSG-SYSTEMS | Sat Jan 21 08:00:00 IST 2017 | Fri Feb 24 17:00:00 IST 2017 | Sat Dec 17 08:00:00 IST 2016 | Fri Mar 31 17:00:00 IDT 2017 |  | COMPLETED
270 | TT_TASK | PREPARING DOCUMENTS INQUIRY/ CONTRACT ODER FOR HRSG | Sat Oct 01 08:00:00 IDT 2016 | Thu Nov 10 17:00:00 IST 2016 | Sat Jun 11 08:00:00 IDT 2016 | Fri Jul 22 17:00:00 IDT 2016 |  | COMPLETED
271 | TT_TASK | SYSTEM MEETINGS WITH HRSG SUPPLIERS | Thu Nov 03 08:00:00 IST 2016 | Thu Dec 15 17:00:00 IST 2016 | Thu Nov 03 08:00:00 IST 2016 | Thu Dec 15 17:00:00 IST 2016 |  | COMPLETED
274 | TT_TASK | PREPARATION P&IDs L- SYSTEMS (FIRST ISSUE) | Sat Dec 10 08:00:00 IST 2016 | Sat Jan 21 17:00:00 IST 2017 | Thu Nov 17 00:00:00 IST 2016 | Wed Dec 28 17:00:00 IST 2016 |  | COMPLETED
275 | TT_TASK | ENGINEERING P&IDs, SYSTEM DESCRIPTION L- SYSTEMS | Fri Feb 03 08:00:00 IST 2017 | Thu Mar 23 17:00:00 IST 2017 | Thu Dec 29 08:00:00 IST 2016 | Wed Feb 15 17:00:00 IST 2017 |  | COMPLETED
276 | TT_TASK | DESIGN REVIEW INTERFACE ST / L- SYSTEMS | Sat Jan 14 08:00:00 IST 2017 | Fri Feb 03 17:00:00 IST 2017 | Fri Jan 13 08:00:00 IST 2017 | Wed Feb 15 17:00:00 IST 2017 |  | COMPLETED
278 | TT_TASK | REVISION P&IDs AFTER 3D DRV L- SYSTEMS | Fri Sep 08 08:00:00 IDT 2017 | Thu Oct 05 17:00:00 IDT 2017 | Mon Aug 07 08:00:00 IDT 2017 | Sat Sep 09 17:00:00 IDT 2017 |  | COMPLETED
279 | TT_TASK | DESIGN DATA SHEETS L- COMPONENTS | Sat Nov 26 08:00:00 IST 2016 | Sat Mar 11 17:00:00 IST 2017 | Thu Nov 03 00:00:00 IST 2016 | Thu Feb 16 17:00:00 IST 2017 |  | COMPLETED
285 | TT_TASK | DESIGN REVIEW INCL. SIL-STUDY L- SYSTEMS | Wed Mar 01 08:00:00 IST 2017 | Tue Apr 04 17:00:00 IDT 2017 | Fri Feb 17 08:00:00 IST 2017 | Fri Mar 10 17:00:00 IST 2017 |  | COMPLETED
288 | TT_TASK | PREPARATION P&IDs P-SYSTEMS (FIRST ISSUE) | Sat Dec 10 08:00:00 IST 2016 | Sat Jan 21 17:00:00 IST 2017 | Thu Nov 17 00:00:00 IST 2016 | Thu Dec 29 17:00:00 IST 2016 |  | COMPLETED
289 | TT_TASK | ENGINEERING P&IDs, SYSTEM DESCRIPTION P-SYSTEMS | Sat Jan 14 08:00:00 IST 2017 | Fri Mar 03 17:00:00 IST 2017 | Fri Dec 30 08:00:00 IST 2016 | Thu Feb 16 17:00:00 IST 2017 |  | COMPLETED
290 | TT_TASK | SUMMARY DATA MANAGEMENT P-SYSTEMS | Sat Apr 01 08:00:00 IDT 2017 | Sat Aug 12 17:00:00 IDT 2017 | Sat Mar 11 08:00:00 IST 2017 | Sat Jul 29 17:00:00 IDT 2017 |  | COMPLETED
291 | TT_TASK | REVISION P&IDs AFTER 3D DRV P-SYSTEM | Tue Sep 26 08:00:00 IDT 2017 | Mon Oct 23 17:00:00 IDT 2017 | Tue Sep 05 08:00:00 IDT 2017 | Fri Sep 29 17:00:00 IDT 2017 |  | COMPLETED
292 | TT_TASK | DESIGN DATA SHEETS P-COMPONENTS | Sat Nov 26 08:00:00 IST 2016 | Sat Feb 25 17:00:00 IST 2017 | Thu Nov 03 00:00:00 IST 2016 | Wed Feb 15 17:00:00 IST 2017 |  | COMPLETED
298 | TT_TASK | DESIGN REVIEW INCL. SIL-STUDY P-SYSTEMS | Wed Mar 01 08:00:00 IST 2017 | Tue Apr 04 17:00:00 IDT 2017 | Fri Feb 17 08:00:00 IST 2017 | Fri Mar 10 17:00:00 IST 2017 |  | COMPLETED
302 | TT_TASK | PREPARATION P&IDs GA-/GHC/GM-/MBU20 - SYSTEMS (FIRST ISSUE) AND WATER BALANCE | Sat Dec 10 08:00:00 IST 2016 | Sat Jan 21 17:00:00 IST 2017 | Thu Nov 17 00:00:00 IST 2016 | Mon Dec 26 17:00:00 IST 2016 |  | COMPLETED
303 | TT_TASK | ENGINEERING P&IDs, SYSTEM DESCRIPTION G-/S-/MBU20 - SYSTEMS | Fri Feb 03 08:00:00 IST 2017 | Thu Apr 20 17:00:00 IDT 2017 | Tue Dec 27 08:00:00 IST 2016 | Mon Mar 13 17:00:00 IST 2017 |  | COMPLETED
305 | TT_TASK | REVISION P&IDs AFTER 3D DRV G-/S-/MBU20 | Fri Oct 27 08:00:00 IDT 2017 | Thu Nov 09 17:00:00 IST 2017 | Wed Sep 27 08:00:00 IDT 2017 | Thu Oct 12 17:00:00 IDT 2017 |  | COMPLETED
306 | TT_TASK | DESIGN DATA SHEETS G-/MBU20 - COMPONENTS | Thu Nov 03 08:00:00 IST 2016 | Thu Feb 09 17:00:00 IST 2017 | Thu Nov 03 08:00:00 IST 2016 | Thu Feb 09 17:00:00 IST 2017 |  | COMPLETED
311 | TT_TASK | DESIGN REVIEW INCL. SIL-STUDY G-/S-/MBU20-SYSTEMS | Thu Mar 16 08:00:00 IST 2017 | Wed Apr 26 17:00:00 IDT 2017 | Tue Mar 14 08:00:00 IST 2017 | Mon Apr 24 17:00:00 IDT 2017 |  | COMPLETED
312 | TT_TASK | PREPARATION P&IDs GHD/GKB/SCB - SYSTEMS (FIRST ISSUE) | Sat Dec 10 08:00:00 IST 2016 | Sat Feb 18 17:00:00 IST 2017 | Thu Nov 17 00:00:00 IST 2016 | Mon Jan 09 17:00:00 IST 2017 |  | COMPLETED
317 | TT_TASK | BASIC DESIGN, SPECIFICATION BOP I&C | Thu Nov 03 08:00:00 IST 2016 | Wed Jan 18 17:00:00 IST 2017 | Thu Nov 03 08:00:00 IST 2016 | Wed Jan 18 17:00:00 IST 2017 |  | COMPLETED
320 | TT_TASK | HW ENGINEERING BOP I&C | Wed Feb 15 08:00:00 IST 2017 | Tue Sep 26 17:00:00 IDT 2017 | Thu Feb 02 08:00:00 IST 2017 | Wed Sep 13 17:00:00 IDT 2017 |  | COMPLETED
323 | TT_TASK | SW ENGINEERING BOP I&C, T3000 DB MERGING | Mon May 01 08:00:00 IDT 2017 | Sun Nov 19 17:00:00 IST 2017 | Fri Apr 07 08:00:00 IDT 2017 | Wed Jan 24 17:00:00 IST 2018 |  | COMPLETED
325 | TT_TASK | SW ENGINEERING BOP I&C, T3000 DB MERGING, PROXIE GENERATION | Fri Jan 26 08:00:00 IST 2018 | Thu Mar 08 17:00:00 IST 2018 | Thu Jan 25 08:00:00 IST 2018 | Sat Mar 24 17:00:00 IDT 2018 |  | COMPLETED
338 | TT_TASK | DETAIL DESIGN HW ENGINEERING BOP I&C CABINETS FOR PLANT SHOP TEST AND I&C FOR UQA ELEC. ROOM | Wed Jun 21 08:00:00 IDT 2017 | Tue Sep 26 17:00:00 IDT 2017 | Sun May 21 08:00:00 IDT 2017 | Sat Aug 26 17:00:00 IDT 2017 |  | COMPLETED
339 | TT_TASK | MANUFACTURING BOP I&C CABINETS FOR PLANT SHOP TEST AND I&C FOR UQA ELEC. ROOM | Wed Sep 27 08:00:00 IDT 2017 | Tue Dec 26 17:00:00 IST 2017 | Thu Sep 14 08:00:00 IDT 2017 | Mon Dec 25 17:00:00 IST 2017 |  | COMPLETED
341 | TT_TASK | TRANSPORT TO WORKSHOP BOP I&C CABINETS FOR PLANT SHOP TEST AND I&C FOR UQA ELEC. ROOM | Mon Feb 19 08:00:00 IST 2018 | Sun Mar 04 17:00:00 IST 2018 | Tue Jan 09 08:00:00 IST 2018 | Mon Jan 22 17:00:00 IST 2018 |  | COMPLETED
345 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST FOR BOP I&C FIELD DEVICES AND ERECTION MATERIAL | Sat Aug 26 08:00:00 IDT 2017 | Fri Mar 02 17:00:00 IST 2018 | Sat Jul 29 08:00:00 IDT 2017 | Fri Jul 06 17:00:00 IDT 2018 |  | COMPLETED
347 | TT_TASK | TRANSPORT TO SITE BOP I&C FIELD DEVICES AND ERECTION MATERIAL | Wed Jun 20 08:00:00 IDT 2018 | Sat Aug 18 17:00:00 IDT 2018 | Wed Jul 25 08:00:00 IDT 2018 | Sat Aug 25 17:00:00 IDT 2018 |  | COMPLETED
349 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST FOR BOP I&C FIELD CABINETS | Thu Jun 01 08:00:00 IDT 2017 | Wed Feb 14 17:00:00 IST 2018 | Sat May 20 08:00:00 IDT 2017 | Tue Jul 24 17:00:00 IDT 2018 |  | COMPLETED
350 | TT_TASK | TRANSPORT TO SITE BOP I&C FIELD CABINETS | Wed Jun 20 08:00:00 IDT 2018 | Sat Aug 18 17:00:00 IDT 2018 | Wed Jul 25 08:00:00 IDT 2018 | Sat Aug 25 17:00:00 IDT 2018 |  | COMPLETED
353 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST FOR BOP I&C CABLES | Tue Sep 26 08:00:00 IDT 2017 | Mon Feb 12 17:00:00 IST 2018 | Sat Sep 16 08:00:00 IDT 2017 | Sat Jun 30 17:00:00 IDT 2018 |  | COMPLETED
355 | TT_TASK | TRANSPORT TO SITE FOR BOP I&C CABLES | Wed Jun 20 08:00:00 IDT 2018 | Sat Aug 18 17:00:00 IDT 2018 | Sun Jul 01 08:00:00 IDT 2018 | Mon Aug 06 17:00:00 IDT 2018 |  | COMPLETED
358 | TT_TASK | DETAIL DESIGN, MANUFACTURING/ SHOP TEST FOR CCR HMI EQUIPMENT | Thu Jun 01 08:00:00 IDT 2017 | Wed Jan 17 17:00:00 IST 2018 | Thu May 18 08:00:00 IDT 2017 | Wed Aug 22 17:00:00 IDT 2018 |  | COMPLETED
361 | TT_TASK | TRANSPORT TO SITE CCR HMI EQUIPMENT | Wed Jun 20 08:00:00 IDT 2018 | Sat Aug 18 17:00:00 IDT 2018 | Sun Oct 07 08:00:00 IDT 2018 | Mon Nov 12 17:00:00 IST 2018 |  | COMPLETED
364 | TT_TASK | DETAIL DESIGN, MANUFACTURING/ SHOP TEST FOR EMISSION MONITORING SYSTEM | Mon May 01 08:00:00 IDT 2017 | Sun Feb 18 17:00:00 IST 2018 | Sat Apr 15 08:00:00 IDT 2017 | Thu May 24 17:00:00 IDT 2018 |  | COMPLETED
366 | TT_TASK | TRANSPORT TO SITE EMISSION MONITORING SYSTEM | Sun Jul 01 08:00:00 IDT 2018 | Wed Aug 29 17:00:00 IDT 2018 | Thu Oct 31 08:00:00 IST 2019 | Thu Nov 14 17:00:00 IST 2019 |  | COMPLETED
373 | TT_TASK | DETAIL DESIGN / CHECKER CONCRETE STRUCTURE TS FOUNDATION UMC | Tue Feb 14 08:00:00 IST 2017 | Mon May 15 17:00:00 IDT 2017 | Thu Feb 02 08:00:00 IST 2017 | Fri Oct 13 17:00:00 IDT 2017 |  | COMPLETED
374 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT EMBEDDED PARTS FOR TURBOSET FDN UMC | Mon May 01 08:00:00 IDT 2017 | Tue Aug 01 17:00:00 IDT 2017 | Sat Apr 01 00:00:00 IDT 2017 | Tue Jul 11 17:00:00 IDT 2017 |  | COMPLETED
377 | TT_TASK | PREPARATION BASIC BUILDING DWGS COND. PIT UMC | Tue Feb 14 08:00:00 IST 2017 | Mon Mar 20 17:00:00 IST 2017 | Sun Feb 05 08:00:00 IST 2017 | Wed Feb 22 17:00:00 IST 2017 |  | COMPLETED
380 | TT_TASK | PREPARATION BASIC BUILDING DWGS UMC | Wed Mar 29 08:00:00 IDT 2017 | Tue May 02 17:00:00 IDT 2017 | Tue Mar 14 08:00:00 IST 2017 | Wed Mar 29 17:00:00 IDT 2017 |  | COMPLETED
384 | TT_TASK | DETAIL DESIGN / CHECKER CRANE WALKWAY UMC | Sat Apr 01 08:00:00 IDT 2017 | Fri Jun 23 17:00:00 IDT 2017 | Thu Mar 16 08:00:00 IST 2017 | Mon Jul 24 17:00:00 IDT 2017 |  | COMPLETED
387 | TT_TASK | DETAIL DESIGN / CHECKER STEEL PLATFORM LUBE OIL UMC | Mon Jun 26 08:00:00 IDT 2017 | Fri Aug 11 17:00:00 IDT 2017 | Fri Jun 02 08:00:00 IDT 2017 | Mon Jul 24 17:00:00 IDT 2017 |  | COMPLETED
389 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE CRANE WALKWAY UMC | Tue Oct 31 08:00:00 IST 2017 | Thu Jan 18 17:00:00 IST 2018 | Fri Nov 10 00:00:00 IST 2017 | Mon Apr 23 17:00:00 IDT 2018 |  | COMPLETED
390 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM LUBE OIL UMC | Tue Oct 31 08:00:00 IST 2017 | Thu Jan 18 17:00:00 IST 2018 | Fri Nov 10 00:00:00 IST 2017 | Mon Apr 23 17:00:00 IDT 2018 |  | COMPLETED
393 | TT_TASK | DETAIL DESIGN / CHECKER STEEL PLATFORM CRANE RAILS UMC | Sun Jul 02 08:00:00 IDT 2017 | Sat Sep 02 17:00:00 IDT 2017 | Fri Jun 02 08:00:00 IDT 2017 | Mon Aug 07 17:00:00 IDT 2017 |  | COMPLETED
395 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT STEEL PLATFORM CRANE RAILS UMC | Tue Oct 31 08:00:00 IST 2017 | Thu Jan 18 17:00:00 IST 2018 | Sat Nov 25 00:00:00 IST 2017 | Wed Feb 14 17:00:00 IST 2018 |  | COMPLETED
398 | TT_TASK | DETAIL DESIGN / CHECKER STEEL PLATFORM ENTRANCE UMC | Thu Jun 01 08:00:00 IDT 2017 | Wed Jul 26 17:00:00 IDT 2017 | Fri May 26 08:00:00 IDT 2017 | Tue Jul 25 17:00:00 IDT 2017 |  | COMPLETED
400 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM ENTRANCE UMC | Tue Nov 21 08:00:00 IST 2017 | Thu Feb 08 17:00:00 IST 2018 | Fri Nov 24 00:00:00 IST 2017 | Wed Jun 27 17:00:00 IDT 2018 |  | COMPLETED
403 | TT_TASK | DETAIL DESIGN / CHECKER STEEL PLATFORM COND. PIT UMC | Mon May 01 08:00:00 IDT 2017 | Sun Jul 02 17:00:00 IDT 2017 | Sun Apr 09 00:00:00 IDT 2017 | Tue May 30 17:00:00 IDT 2017 |  | COMPLETED
405 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM COND. PIT UMC | Sun Nov 26 08:00:00 IST 2017 | Thu Jan 18 17:00:00 IST 2018 | Sat Nov 25 00:00:00 IST 2017 | Mon Apr 23 17:00:00 IDT 2018 |  | COMPLETED
408 | TT_TASK | DETAIL DESIGN / CHECKER STEEL PLATFORM ST UMC | Mon Jun 26 08:00:00 IDT 2017 | Thu Aug 17 17:00:00 IDT 2017 | Fri Jun 02 08:00:00 IDT 2017 | Wed Jul 26 17:00:00 IDT 2017 |  | COMPLETED
410 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM GENERATOR UMC | Sun Nov 26 08:00:00 IST 2017 | Fri Mar 09 17:00:00 IST 2018 | Sat Nov 25 00:00:00 IST 2017 | Thu Aug 30 17:00:00 IDT 2018 |  | COMPLETED
413 | TT_TASK | DETAIL DESIGN / CHECKER STEEL PLATFORM GT UMC | Thu Jun 01 08:00:00 IDT 2017 | Wed Aug 02 17:00:00 IDT 2017 | Mon May 01 08:00:00 IDT 2017 | Wed May 24 17:00:00 IDT 2017 |  | COMPLETED
415 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM GT UMC | Sun Nov 26 08:00:00 IST 2017 | Tue Feb 13 17:00:00 IST 2018 | Wed Nov 01 00:00:00 IST 2017 | Mon Apr 23 17:00:00 IDT 2018 |  | COMPLETED
418 | TT_TASK | DETAIL DESIGN / CHECKER STEEL PLATFORM CONDENSER MANHOLE ACCESS UMC | Mon Jun 26 08:00:00 IDT 2017 | Sat Sep 16 17:00:00 IDT 2017 | Fri Jun 02 08:00:00 IDT 2017 | Tue Nov 14 17:00:00 IST 2017 |  | COMPLETED
420 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM CONDENSER MANHOLE ACCESS UMC | Fri Jan 26 08:00:00 IST 2018 | Thu Apr 05 17:00:00 IDT 2018 | Wed Jan 24 08:00:00 IST 2018 | Wed Jun 27 17:00:00 IDT 2018 |  | COMPLETED
423 | TT_TASK | DETAIL DESIGN / CHECKER STEEL PLATFORM OVER TG FDN UMC | Mon Jul 03 08:00:00 IDT 2017 | Sat Sep 16 17:00:00 IDT 2017 | Fri Jun 09 08:00:00 IDT 2017 | Fri Sep 15 17:00:00 IDT 2017 |  | COMPLETED
425 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM OVER TG FDN UMC | Fri Jan 26 08:00:00 IST 2018 | Wed Jun 06 17:00:00 IDT 2018 | Sat Jan 20 08:00:00 IST 2018 | Thu Nov 15 17:00:00 IST 2018 |  | COMPLETED
428 | TT_TASK | DETAIL DESIGN / CHECKER STEEL MISC. PLATFORM UMC | Mon Jul 03 08:00:00 IDT 2017 | Sat Sep 16 17:00:00 IDT 2017 | Fri Jun 09 08:00:00 IDT 2017 | Thu Jan 04 17:00:00 IST 2018 |  | COMPLETED
430 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL MISC. PLATFORM UMC | Fri Mar 02 08:00:00 IST 2018 | Tue Jul 10 17:00:00 IDT 2018 | Sat Jan 20 08:00:00 IST 2018 | Thu Nov 15 17:00:00 IST 2018 |  | COMPLETED
433 | TT_TASK | DETAIL DESIGN / CHECKER STEEL PLATFORM BEARING ACCESS UMC | Mon Jun 26 08:00:00 IDT 2017 | Sat Sep 16 17:00:00 IDT 2017 | Fri Jun 02 08:00:00 IDT 2017 | Fri Sep 15 17:00:00 IDT 2017 |  | COMPLETED
435 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM BEARING ACCESS UMC | Fri Jan 26 08:00:00 IST 2018 | Tue Jun 05 17:00:00 IDT 2018 | Sat Jan 20 08:00:00 IST 2018 | Thu Nov 15 17:00:00 IST 2018 |  | COMPLETED
438 | TT_TASK | DETAIL DESIGN / CHECKER STEEL PLATFORM PIPE ACCESS NEAR CEP UMC | Sat Apr 01 08:00:00 IDT 2017 | Fri Jun 02 17:00:00 IDT 2017 | Thu Mar 16 08:00:00 IST 2017 | Fri May 12 17:00:00 IDT 2017 |  | COMPLETED
440 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM PIPE ACCESS NEAR CEP UMC | Sun Nov 26 08:00:00 IST 2017 | Fri Mar 09 17:00:00 IST 2018 | Tue Nov 21 08:00:00 IST 2017 | Thu Aug 30 17:00:00 IDT 2018 |  | COMPLETED
443 | TT_TASK | DETAIL DESIGN / CHECKER STEEL PLATFORM LP BY-PASS UMC | Mon Jun 26 08:00:00 IDT 2017 | Thu Aug 17 17:00:00 IDT 2017 | Fri Jun 02 08:00:00 IDT 2017 | Wed Jul 26 17:00:00 IDT 2017 |  | COMPLETED
445 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM LP BY-PASS UMC | Sun Nov 26 08:00:00 IST 2017 | Sat Feb 03 17:00:00 IST 2018 | Tue Nov 21 08:00:00 IST 2017 | Thu Aug 30 17:00:00 IDT 2018 |  | COMPLETED
448 | TT_TASK | DETAIL DESIGN / CHECKER STEEL PLATFORM BUS DUCT SUPPORT UMC | Mon Jun 26 08:00:00 IDT 2017 | Sat Sep 16 17:00:00 IDT 2017 | Fri Jun 02 08:00:00 IDT 2017 | Tue Nov 14 17:00:00 IST 2017 |  | COMPLETED
450 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM BUS DUCT SUPPORT UMC | Fri Jan 26 08:00:00 IST 2018 | Wed Jun 06 17:00:00 IDT 2018 | Sat Jan 20 08:00:00 IST 2018 | Thu Nov 15 17:00:00 IST 2018 |  | COMPLETED
453 | TT_TASK | DETAIL DESIGN / CHECKER STEEL ATTACHED TO MAIN FRAME | Sat Aug 26 08:00:00 IDT 2017 | Fri Oct 20 17:00:00 IDT 2017 | Fri Aug 04 08:00:00 IDT 2017 | Tue Nov 14 17:00:00 IST 2017 |  | COMPLETED
456 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL ATTACHED TO MAIN FRAME | Fri Jan 26 08:00:00 IST 2018 | Wed Jun 06 17:00:00 IDT 2018 | Sat Jan 20 08:00:00 IST 2018 | Wed Jun 27 17:00:00 IDT 2018 |  | COMPLETED
459 | TT_TASK | DETAIL DESIGN UMCM1Y MODULE PIPE RACK | Wed Mar 01 08:00:00 IST 2017 | Tue Sep 12 17:00:00 IDT 2017 | Tue Feb 14 08:00:00 IST 2017 | Mon Aug 28 17:00:00 IDT 2017 |  | COMPLETED
460 | TT_TASK | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL UMCM1Y MODULE PIPE RACK | Fri Sep 29 08:00:00 IDT 2017 | Wed Dec 13 17:00:00 IST 2017 | Tue Aug 29 08:00:00 IDT 2017 | Sun Nov 12 17:00:00 IST 2017 |  | COMPLETED
461 | TT_TASK | MANUFACTURING UMCM1Y MODULE PIPE RACK | Thu Oct 26 08:00:00 IDT 2017 | Fri Feb 02 17:00:00 IST 2018 | Mon Oct 02 08:00:00 IDT 2017 | Thu Apr 26 17:00:00 IDT 2018 |  | COMPLETED
462 | TT_TASK | TRANSPORT UMCM1Y MODULE PIPE RACK | Sun Apr 15 08:00:00 IDT 2018 | Fri Apr 27 17:00:00 IDT 2018 | Wed May 23 08:00:00 IDT 2018 | Tue May 29 17:00:00 IDT 2018 |  | COMPLETED
466 | TT_TASK | DETAIL DESIGN UMCL1Y MODULE PIPE RACK | Tue Feb 14 08:00:00 IST 2017 | Mon Jul 17 17:00:00 IDT 2017 | Tue Feb 07 08:00:00 IST 2017 | Mon Jul 10 17:00:00 IDT 2017 |  | COMPLETED
467 | TT_TASK | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL UMCL1Y MODULE PIPE RACK | Wed Aug 09 08:00:00 IDT 2017 | Sun Nov 19 17:00:00 IST 2017 | Tue Jul 11 08:00:00 IDT 2017 | Sat Oct 21 17:00:00 IDT 2017 |  | COMPLETED
468 | TT_TASK | MANUFACTURING UMCL1Y MODULE PIPE RACK | Tue Nov 21 08:00:00 IST 2017 | Thu Feb 08 17:00:00 IST 2018 | Sun Oct 22 08:00:00 IDT 2017 | Thu Mar 01 17:00:00 IST 2018 |  | COMPLETED
469 | TT_TASK | TRANSPORT UMCL1Y MODULE PIPE RACK | Sun Apr 15 08:00:00 IDT 2018 | Fri Apr 27 17:00:00 IDT 2018 | Tue Apr 17 08:00:00 IDT 2018 | Fri Apr 27 17:00:00 IDT 2018 |  | COMPLETED
472 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM STEEL PLATFOR UMC | Tue Jul 25 08:00:00 IDT 2017 | Mon Sep 18 17:00:00 IDT 2017 | Fri Jun 30 08:00:00 IDT 2017 | Thu Aug 24 17:00:00 IDT 2017 |  | COMPLETED
474 | TT_TASK | DETAIL DESIGN MAL00Y MODULE | Thu Mar 16 08:00:00 IST 2017 | Wed Aug 23 17:00:00 IDT 2017 | Thu Mar 02 08:00:00 IST 2017 | Thu Jul 27 17:00:00 IDT 2017 |  | COMPLETED
476 | TT_TASK | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL MAL00Y MODULE | Mon Sep 11 08:00:00 IDT 2017 | Wed Dec 06 17:00:00 IST 2017 | Fri Jul 28 08:00:00 IDT 2017 | Sat Nov 04 17:00:00 IST 2017 |  | COMPLETED
477 | TT_TASK | MANUFACTURING MAL00Y MODULE | Wed Dec 06 08:00:00 IST 2017 | Fri Feb 09 17:00:00 IST 2018 | Sun Nov 05 08:00:00 IST 2017 | Thu Mar 15 17:00:00 IST 2018 |  | COMPLETED
478 | TT_TASK | TRANSPORT MAL00Y MODULE | Sun Apr 15 08:00:00 IDT 2018 | Fri Apr 27 17:00:00 IDT 2018 | Tue Apr 17 08:00:00 IDT 2018 | Fri Apr 27 17:00:00 IDT 2018 |  | COMPLETED
482 | TT_TASK | CONTRACT REVIEW, PREPARATION RFQ CRANE SMM01/02 FOR UMC | Sat Jan 14 08:00:00 IST 2017 | Sun Feb 12 17:00:00 IST 2017 | Mon Dec 12 08:00:00 IST 2016 | Fri Dec 30 17:00:00 IST 2016 |  | COMPLETED
483 | TT_TASK | QUOTATION STAGE CRANE SMM01/02 FOR UMC | Mon Feb 13 08:00:00 IST 2017 | Sun Mar 19 17:00:00 IST 2017 | Sat Dec 31 08:00:00 IST 2016 | Mon Feb 27 17:00:00 IST 2017 |  | COMPLETED
485 | TT_TASK | FABRICATION DESIGN, MANUFACTURING, SHOP TEST CRANE SMM01, 02 FOR UMC | Thu Mar 16 08:00:00 IST 2017 | Thu Dec 21 17:00:00 IST 2017 | Wed Mar 01 08:00:00 IST 2017 | Thu Nov 30 17:00:00 IST 2017 |  | COMPLETED
487 | TT_TASK | TRANSPORT CRANE SMM01/02 FOR UMC | Sat Dec 16 08:00:00 IST 2017 | Sun Jan 14 17:00:00 IST 2018 | Wed Dec 13 08:00:00 IST 2017 | Mon Jan 01 17:00:00 IST 2018 |  | COMPLETED
490 | TT_TASK | FABRICATION DESIGN, MANUFACTURING, SHOP TEST CRANE SMM03 FOR UMC | Thu Jun 01 08:00:00 IDT 2017 | Wed Nov 29 17:00:00 IST 2017 | Tue May 30 08:00:00 IDT 2017 | Fri Dec 15 17:00:00 IST 2017 |  | COMPLETED
492 | TT_TASK | TRANSPORT CRANES SMM03 FOR UMC | Fri Jan 26 08:00:00 IST 2018 | Sat Feb 24 17:00:00 IST 2018 | Fri Dec 15 08:00:00 IST 2017 | Mon Jan 15 17:00:00 IST 2018 |  | COMPLETED
496 | TT_TASK | DETAIL DESIGN / MANUFACTURING / ASSEMBLY HP/IP-LP ST & ST-AUXILIARIES MA | Sat Nov 26 08:00:00 IST 2016 | Wed Jan 24 17:00:00 IST 2018 | Sun Nov 20 08:00:00 IST 2016 | Tue Nov 21 17:00:00 IST 2017 |  | COMPLETED
498 | TT_TASK | TRANSPORT ST BEARINGS MAD | Sat Dec 16 08:00:00 IST 2017 | Sun Jan 21 17:00:00 IST 2018 | Sun Dec 03 08:00:00 IST 2017 | Mon Jan 08 17:00:00 IST 2018 |  | COMPLETED
500 | TT_TASK | TRANSPORT ST BEARINGS MAD TO NORTH SEA PORT | Thu Oct 26 08:00:00 IDT 2017 | Wed Nov 01 17:00:00 IST 2017 | Fri Oct 06 08:00:00 IDT 2017 | Thu Oct 12 17:00:00 IDT 2017 |  | COMPLETED
502 | TT_TASK | TRANSPORT STEAM TURBINE MA- (HP/IP) (incl. FCA) | Fri Jan 26 08:00:00 IST 2018 | Sat Mar 31 17:00:00 IDT 2018 | Thu Jan 18 08:00:00 IST 2018 | Sun Apr 01 17:00:00 IDT 2018 |  | COMPLETED
504 | TT_TASK | TRANSPORT STEAM TURBINE MA- (HP/IP) TO NORTH SEA PORT | Fri Jan 26 08:00:00 IST 2018 | Thu Feb 01 17:00:00 IST 2018 | Fri Jan 12 08:00:00 IST 2018 | Mon Jan 15 17:00:00 IST 2018 |  | COMPLETED
506 | TT_TASK | TRANSPORT ST MA- (LP OUTER CASING) | Mon Mar 26 08:00:00 IDT 2018 | Thu Apr 12 17:00:00 IDT 2018 | Wed Mar 07 08:00:00 IST 2018 | Wed Apr 04 17:00:00 IDT 2018 |  | COMPLETED
507 | TT_TASK | TRANSPORT ST MA- (LP-ROTOR, INNER CASING) | Fri Jan 26 08:00:00 IST 2018 | Thu Apr 05 17:00:00 IDT 2018 | Thu Jan 18 08:00:00 IST 2018 | Sun Apr 01 17:00:00 IDT 2018 |  | COMPLETED
510 | TT_TASK | TRANSPORT ST MA- (LP OUTER CASING) TO BANTEN PORT | Fri Jan 26 08:00:00 IST 2018 | Thu Feb 01 17:00:00 IST 2018 | Thu Nov 30 08:00:00 IST 2017 | Wed Dec 06 17:00:00 IST 2017 |  | COMPLETED
511 | TT_TASK | TRANSPORT ST MA- (LP-ROTOR, INNER CASING) TO NORTH SEA PORT | Fri Jan 26 08:00:00 IST 2018 | Thu Feb 01 17:00:00 IST 2018 | Thu Dec 28 08:00:00 IST 2017 | Wed Jan 03 17:00:00 IST 2018 |  | COMPLETED
513 | TT_TASK | TRANSPORT ST VALVES (for MAL00Y MODULE) TO MODULE ASSEMBLY SHOP | Tue Sep 26 08:00:00 IDT 2017 | Mon Nov 13 17:00:00 IST 2017 | Fri Sep 15 08:00:00 IDT 2017 | Tue Oct 24 17:00:00 IDT 2017 |  | COMPLETED
516 | TT_TASK | TRANSPORT CONDENSER MAG | Wed Mar 07 08:00:00 IST 2018 | Sat Mar 24 17:00:00 IDT 2018 | Wed Mar 07 08:00:00 IST 2018 | Wed Apr 04 17:00:00 IDT 2018 |  | COMPLETED
518 | TT_TASK | DESIGN / MANUFACTURING ST CONDENSER MAG | Wed Mar 01 08:00:00 IST 2017 | Fri Feb 23 17:00:00 IST 2018 | Wed Feb 22 08:00:00 IST 2017 | Wed Jan 03 17:00:00 IST 2018 |  | COMPLETED
520 | TT_TASK | TRANSPORT ST CONDENSER MAG TO PORT OF EXPORT | Mon Mar 26 08:00:00 IDT 2018 | Sun Apr 01 17:00:00 IDT 2018 | Mon Feb 26 08:00:00 IST 2018 | Wed Feb 28 17:00:00 IST 2018 |  | COMPLETED
522 | TT_TASK | TRANSPORT REMOVAL SYSTEM MAJ (China factory to Site) | Sun Mar 04 08:00:00 IST 2018 | Sun Mar 18 17:00:00 IST 2018 | Sun Mar 04 08:00:00 IST 2018 | Fri Mar 23 17:00:00 IDT 2018 |  | COMPLETED
526 | TT_TASK | TRANSPORT LUBE OIL MODUL MAV | Fri Jan 26 08:00:00 IST 2018 | Thu Mar 15 17:00:00 IST 2018 | Thu Jan 18 08:00:00 IST 2018 | Sun Apr 01 17:00:00 IDT 2018 |  | COMPLETED
529 | TT_TASK | TRANSPORT ST LUBE OIL MODULE MAV TO NORTH SEA PORT | Fri Jan 26 08:00:00 IST 2018 | Thu Feb 01 17:00:00 IST 2018 | Mon Jan 08 08:00:00 IST 2018 | Sun Jan 14 17:00:00 IST 2018 |  | COMPLETED
531 | TT_TASK | TRANSPORT TO SITE ST GLAND STEAM CONDENSER MAW | Thu Jan 18 08:00:00 IST 2018 | Wed Mar 28 17:00:00 IDT 2018 | Thu Jan 18 08:00:00 IST 2018 | Sun Apr 01 17:00:00 IDT 2018 |  | COMPLETED
534 | TT_TASK | TRANSPORT ST GLAND STEAM CONDENSER MAW TO NORTH SEA PORT | Fri Jan 26 08:00:00 IST 2018 | Thu Feb 01 17:00:00 IST 2018 | Mon Jan 08 08:00:00 IST 2018 | Sun Jan 14 17:00:00 IST 2018 |  | COMPLETED
536 | TT_TASK | TRANSPORT TO SITE HYDRAULIC SYSTEM MAX | Fri Jan 26 08:00:00 IST 2018 | Mon Mar 26 17:00:00 IDT 2018 | Thu Jan 18 08:00:00 IST 2018 | Sun Apr 01 17:00:00 IDT 2018 |  | COMPLETED
539 | TT_TASK | TRANSPORT ST HYDRAULIC SYSTEM MAX TO NORTH SEA PORT | Fri Jan 26 08:00:00 IST 2018 | Thu Feb 01 17:00:00 IST 2018 | Mon Jan 08 08:00:00 IST 2018 | Sun Jan 14 17:00:00 IST 2018 |  | COMPLETED
541 | TT_TASK | TRANSPORT ST NOISE PROTECTION SYSTEM MPB20 | Thu Feb 15 08:00:00 IST 2018 | Wed Apr 18 17:00:00 IDT 2018 | Thu Feb 15 08:00:00 IST 2018 | Wed Mar 21 17:00:00 IST 2018 |  | COMPLETED
543 | TT_TASK | TRANSPORT ST ENCLOSURE MPB20 TO NORTH SEA PORT | Fri Jan 26 08:00:00 IST 2018 | Thu Feb 01 17:00:00 IST 2018 | Fri Jan 19 08:00:00 IST 2018 | Thu Jan 25 17:00:00 IST 2018 |  | COMPLETED
546 | TT_TASK | TRANSPORT GENERATOR MK | Fri Jan 26 08:00:00 IST 2018 | Thu Apr 05 17:00:00 IDT 2018 | Thu Jan 18 08:00:00 IST 2018 | Sun Apr 01 17:00:00 IDT 2018 |  | COMPLETED
548 | TT_TASK | MANUFACTURING ST GENERATOR MKA INCL. COOLER MKA70 | Thu Nov 24 08:00:00 IST 2016 | Sat Jan 13 17:00:00 IST 2018 | Thu Nov 24 08:00:00 IST 2016 | Thu Dec 14 17:00:00 IST 2017 |  | COMPLETED
550 | TT_TASK | TRANSPORT ST GENERATOR MKA INCL. COOLER MKA70 TO PORT OF EXPORT | Fri Jan 26 08:00:00 IST 2018 | Thu Feb 01 17:00:00 IST 2018 | Tue Jan 02 08:00:00 IST 2018 | Wed Jan 10 17:00:00 IST 2018 |  | COMPLETED
552 | TT_TASK | TRANSPORT GENERATOR SKIDS MKA | Mon Mar 26 08:00:00 IDT 2018 | Tue May 08 17:00:00 IDT 2018 | Sun Mar 18 08:00:00 IST 2018 | Sun May 13 17:00:00 IDT 2018 |  | COMPLETED
555 | TT_TASK | TRANSPORT GT INTERCONNECTING PIPING MB- | Mon Feb 26 08:00:00 IST 2018 | Sun May 06 17:00:00 IDT 2018 | Thu Feb 15 08:00:00 IST 2018 | Wed Mar 21 17:00:00 IST 2018 |  | COMPLETED
558 | TT_TASK | TRANSPORT GAS TURBINE MB | Fri Feb 02 08:00:00 IST 2018 | Thu Apr 12 17:00:00 IDT 2018 | Thu Jan 18 08:00:00 IST 2018 | Sun Apr 01 17:00:00 IDT 2018 |  | COMPLETED
559 | TT_TASK | PREPARATION OF RFQ GT INSULATION MB- | Mon May 01 08:00:00 IDT 2017 | Sun May 14 17:00:00 IDT 2017 | Sun Apr 16 08:00:00 IDT 2017 | Sat Apr 29 17:00:00 IDT 2017 |  | COMPLETED
560 | TT_TASK | QUOTATION STAGE GT INSULATION MB- | Mon May 15 08:00:00 IDT 2017 | Sun May 28 17:00:00 IDT 2017 | Sun Apr 30 08:00:00 IDT 2017 | Sat May 13 17:00:00 IDT 2017 |  | COMPLETED
562 | TT_TASK | DESIGN / PROCUREMENT / MANUFACTURING GAS TURBINE | Sat Jan 14 08:00:00 IST 2017 | Mon Mar 12 17:00:00 IST 2018 | Sun Dec 18 08:00:00 IST 2016 | Thu Dec 14 17:00:00 IST 2017 |  | COMPLETED
564 | TT_TASK | DESIGN / MANUFACTURING GT INSULATION MB- | Thu Jun 01 08:00:00 IDT 2017 | Mon Jan 01 17:00:00 IST 2018 | Sun May 14 08:00:00 IDT 2017 | Thu Dec 14 17:00:00 IST 2017 |  | COMPLETED
566 | TT_TASK | TRANSPORT GAS TURBINE MB- TO NORTH SEA PORT | Fri Jan 26 08:00:00 IST 2018 | Thu Feb 01 17:00:00 IST 2018 | Tue Jan 02 08:00:00 IST 2018 | Wed Jan 10 17:00:00 IST 2018 |  | COMPLETED
568 | TT_TASK | TRANSPORT GT AUXILIARIES MB- | Mon Mar 26 08:00:00 IDT 2018 | Tue May 08 17:00:00 IDT 2018 | Sun Mar 18 08:00:00 IST 2018 | Sun May 13 17:00:00 IDT 2018 |  | COMPLETED
570 | TT_TASK | TRANSPORT AIR INTAKE SYSTEM MBL | Fri Feb 09 08:00:00 IST 2018 | Thu Apr 19 17:00:00 IDT 2018 | Thu Jan 18 08:00:00 IST 2018 | Sun Apr 01 17:00:00 IDT 2018 |  | COMPLETED
572 | TT_TASK | DETAIL DESIGN / MANUFACTURING AIR INTAKE SYSTEM MBL | Thu Mar 16 08:00:00 IST 2017 | Thu Dec 07 17:00:00 IST 2017 | Thu Mar 02 08:00:00 IST 2017 | Thu Nov 23 17:00:00 IST 2017 |  | COMPLETED
574 | TT_TASK | TRANSPORT AIR INTAKE SYSTEM MBL TO PORT OF EXPORT | Fri Jan 26 08:00:00 IST 2018 | Thu Feb 08 17:00:00 IST 2018 | Tue Jan 02 08:00:00 IST 2018 | Wed Jan 10 17:00:00 IST 2018 |  | COMPLETED
576 | TT_TASK | TRANSPORT GT ENCLOSURE INCL.VENT.MPB/SAM | Mon Feb 26 08:00:00 IST 2018 | Sun May 06 17:00:00 IDT 2018 | Sun Jan 14 08:00:00 IST 2018 | Thu Feb 22 17:00:00 IST 2018 |  | COMPLETED
578 | TT_TASK | TRANSPORT ECONOPAC FIRE PROT.SYSTEM CYE/SGJ | Mon Mar 26 08:00:00 IDT 2018 | Tue May 08 17:00:00 IDT 2018 | Sun Mar 18 08:00:00 IST 2018 | Sun May 13 17:00:00 IDT 2018 |  | COMPLETED
579 | TT_TASK | DETAIL DESIGN / MANUFACTURING FIRE FIGHTING / GAS DETECTION SGJ / CYQ / CYE | Sat Apr 01 08:00:00 IDT 2017 | Fri Dec 22 17:00:00 IST 2017 | Thu Mar 16 08:00:00 IST 2017 | Sat Nov 25 17:00:00 IST 2017 |  | COMPLETED
583 | TT_TASK | FABRICATION DESIGN, PROCUREMENT, PRE-FABRICATION EL.SUPERHEATER LBG | Mon May 01 08:00:00 IDT 2017 | Sat Oct 07 17:00:00 IDT 2017 | Sat Apr 29 08:00:00 IDT 2017 | Fri Dec 08 17:00:00 IST 2017 |  | COMPLETED
585 | TT_TASK | TRANSPORT ELECTRICAL SUPERHEATER LBG | Thu Mar 08 08:00:00 IST 2018 | Thu Apr 12 17:00:00 IDT 2018 | Thu Feb 08 08:00:00 IST 2018 | Thu Mar 15 17:00:00 IST 2018 |  | COMPLETED
592 | TT_TASK | CONTRACT REVIEW, PREPARATION RFQ CONDENSATE EXTRACTION PUMP LCB | Sat Nov 26 08:00:00 IST 2016 | Sat Jan 14 17:00:00 IST 2017 | Thu Nov 10 08:00:00 IST 2016 | Thu Dec 29 17:00:00 IST 2016 |  | COMPLETED
593 | TT_TASK | QUOTATION STAGE CONDENSATE EXTRACTION PUMP LCB | Fri Feb 03 08:00:00 IST 2017 | Fri Apr 14 17:00:00 IDT 2017 | Fri Dec 30 08:00:00 IST 2016 | Tue Mar 14 17:00:00 IST 2017 |  | COMPLETED
595 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST CONDENSATE EXTRACTION PUMP LCB | Sat Aug 26 08:00:00 IDT 2017 | Thu Jun 14 17:00:00 IDT 2018 | Tue Aug 08 08:00:00 IDT 2017 | Tue Apr 24 17:00:00 IDT 2018 |  | COMPLETED
597 | TT_TASK | TRANSPORT CONDENSATE EXTRACTION PUMP LCB | Sat Apr 28 08:00:00 IDT 2018 | Fri Jun 08 17:00:00 IDT 2018 | Fri May 25 08:00:00 IDT 2018 | Fri Jun 01 17:00:00 IDT 2018 |  | COMPLETED
602 | TT_TASK | PREPARATION RFQ CONDENSER TUBE CLEANING SYSTEM PAH | Sat Dec 10 08:00:00 IST 2016 | Fri Dec 30 17:00:00 IST 2016 | Fri Dec 09 08:00:00 IST 2016 | Thu Dec 29 17:00:00 IST 2016 |  | COMPLETED
603 | TT_TASK | QUOTATION STAGE CONDENSER TUBE CLEANING SYSTEM PAH | Sat Jan 14 08:00:00 IST 2017 | Tue Mar 14 17:00:00 IST 2017 | Fri Dec 30 08:00:00 IST 2016 | Fri Apr 21 17:00:00 IDT 2017 |  | COMPLETED
606 | TT_TASK | DETAIL DESIGN, MANUFACTURING CONDENSER TUBE CLEANING SYSTEM PAH | Mon May 01 08:00:00 IDT 2017 | Sun Jan 14 17:00:00 IST 2018 | Sun Apr 23 08:00:00 IDT 2017 | Mon Dec 18 17:00:00 IST 2017 |  | COMPLETED
608 | TT_TASK | TRANSPORT CONDENSER TUBE CLEANING SYSTEM PAH | Fri Jan 26 08:00:00 IST 2018 | Thu Mar 15 17:00:00 IST 2018 | Sat Dec 16 08:00:00 IST 2017 | Wed Jan 17 17:00:00 IST 2018 |  | COMPLETED
612 | TT_TASK | CONTRACT REVIEW, PREPARATION RFQ SERVICE COOLING WATER PUMP PCB | Sat Dec 17 08:00:00 IST 2016 | Sun Jan 08 17:00:00 IST 2017 | Thu Nov 24 08:00:00 IST 2016 | Fri Dec 16 17:00:00 IST 2016 |  | COMPLETED
613 | TT_TASK | QUOTATION STAGE SERVICE COOLING WATER PUMP PCB | Thu Feb 02 08:00:00 IST 2017 | Wed Mar 08 17:00:00 IST 2017 | Thu Dec 29 08:00:00 IST 2016 | Thu Mar 02 17:00:00 IST 2017 |  | COMPLETED
615 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST SERVICE COOLING WATER PUMP PCB | Sun Mar 19 08:00:00 IST 2017 | Sat Nov 04 17:00:00 IST 2017 | Sat Mar 04 08:00:00 IST 2017 | Wed Dec 06 17:00:00 IST 2017 |  | COMPLETED
617 | TT_TASK | TRANSPORT SERVICE COOLING WATER PUMP PCB | Fri Jan 26 08:00:00 IST 2018 | Thu Mar 15 17:00:00 IST 2018 | Wed Jan 31 08:00:00 IST 2018 | Wed Mar 14 17:00:00 IST 2018 |  | COMPLETED
621 | TT_TASK | PREPARATION RFQ DEBRIS FILTER PDB | Sat Dec 10 08:00:00 IST 2016 | Fri Dec 30 17:00:00 IST 2016 | Fri Dec 09 08:00:00 IST 2016 | Thu Dec 29 17:00:00 IST 2016 |  | COMPLETED
622 | TT_TASK | QUOTATION STAGE DEBRIS FILTER PDB | Fri Feb 03 08:00:00 IST 2017 | Thu Mar 09 17:00:00 IST 2017 | Fri Dec 30 08:00:00 IST 2016 | Fri Apr 21 17:00:00 IDT 2017 |  | COMPLETED
625 | TT_TASK | DETAIL DESIGN, MANUFACTURING DEBRIS FILTER PDB | Mon May 15 08:00:00 IDT 2017 | Sun Feb 04 17:00:00 IST 2018 | Sun Apr 23 08:00:00 IDT 2017 | Thu Jan 04 17:00:00 IST 2018 |  | COMPLETED
627 | TT_TASK | TRANSPORT DEBRIS FILTER PDB | Thu Feb 15 08:00:00 IST 2018 | Wed Mar 28 17:00:00 IDT 2018 | Thu Feb 08 08:00:00 IST 2018 | Tue Mar 20 17:00:00 IST 2018 |  | COMPLETED
631 | TT_TASK | CONTRACT REVIEW, PREPARATION RFQ CCW PUMP PGB | Sat Nov 26 08:00:00 IST 2016 | Fri Dec 30 17:00:00 IST 2016 | Thu Nov 24 08:00:00 IST 2016 | Wed Dec 28 17:00:00 IST 2016 |  | COMPLETED
632 | TT_TASK | QUOTATION STAGE CCW PUMP PGB | Thu Feb 02 08:00:00 IST 2017 | Wed Apr 05 17:00:00 IDT 2017 | Thu Dec 29 08:00:00 IST 2016 | Thu Mar 02 17:00:00 IST 2017 |  | COMPLETED
634 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST CCW PUMP PGB | Fri Mar 17 08:00:00 IST 2017 | Tue Dec 12 17:00:00 IST 2017 | Sat Mar 04 08:00:00 IST 2017 | Wed Dec 06 17:00:00 IST 2017 |  | COMPLETED
636 | TT_TASK | TRANSPORT CCW PUMP PGB | Fri Jan 26 08:00:00 IST 2018 | Thu Mar 15 17:00:00 IST 2018 | Wed Jan 31 08:00:00 IST 2018 | Tue Mar 13 17:00:00 IST 2018 |  | COMPLETED
640 | TT_TASK | PREPARATION RFQ HEAT EXCHANGER PGB | Wed Feb 01 08:00:00 IST 2017 | Tue Feb 28 17:00:00 IST 2017 | Thu Jan 19 08:00:00 IST 2017 | Wed Mar 15 17:00:00 IST 2017 |  | COMPLETED
641 | TT_TASK | QUOTATION STAGE HEAT EXCHANGER PGB | Sat Apr 01 08:00:00 IDT 2017 | Wed Apr 26 17:00:00 IDT 2017 | Thu Mar 16 08:00:00 IST 2017 | Tue May 16 17:00:00 IDT 2017 |  | COMPLETED
643 | TT_TASK | FABRICATION DESIGN, PROCUREMENT, PRE-FABRICATION HEAT EXCHANGER PGB | Fri Jun 02 08:00:00 IDT 2017 | Mon Dec 18 17:00:00 IST 2017 | Thu May 18 08:00:00 IDT 2017 | Fri Dec 15 17:00:00 IST 2017 |  | COMPLETED
645 | TT_TASK | TRANSPORT HEAT EXCHANGER PGB | Fri Jan 26 08:00:00 IST 2018 | Thu Mar 15 17:00:00 IST 2018 | Wed Jan 31 08:00:00 IST 2018 | Tue Mar 13 17:00:00 IST 2018 |  | COMPLETED
649 | TT_TASK | PREPARATION RFQ EXPANSION TANK PGB | Wed Feb 01 08:00:00 IST 2017 | Tue Feb 28 17:00:00 IST 2017 | Mon Jan 23 08:00:00 IST 2017 | Wed Mar 15 17:00:00 IST 2017 |  | COMPLETED
650 | TT_TASK | QUOTATION STAGE EXPANSION TANK PGB | Sat Apr 01 08:00:00 IDT 2017 | Wed Apr 26 17:00:00 IDT 2017 | Thu Mar 16 08:00:00 IST 2017 | Tue Jul 11 17:00:00 IDT 2017 |  | COMPLETED
652 | TT_TASK | FABRICATION DESIGN, PROCUREMENT, PRE-FABRICATION EXPANSION TANK PGB | Wed Jul 26 08:00:00 IDT 2017 | Tue Jan 23 17:00:00 IST 2018 | Wed Jul 12 08:00:00 IDT 2017 | Fri Dec 15 17:00:00 IST 2017 |  | COMPLETED
654 | TT_TASK | TRANSPORT EXPANSION TANK PGB | Fri Jan 26 08:00:00 IST 2018 | Thu Mar 15 17:00:00 IST 2018 | Thu Feb 08 08:00:00 IST 2018 | Tue Mar 20 17:00:00 IST 2018 |  | COMPLETED
656 | TT_TASK | DETAIL DESIGN PXB00Y MODULE | Tue Jun 13 08:00:00 IDT 2017 | Tue Nov 21 17:00:00 IST 2017 | Sat May 13 08:00:00 IDT 2017 | Mon Oct 09 17:00:00 IDT 2017 |  | COMPLETED
658 | TT_TASK | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL PXB00Y MODULE | Thu Nov 09 08:00:00 IST 2017 | Mon Feb 12 17:00:00 IST 2018 | Tue Oct 10 08:00:00 IDT 2017 | Sat Jan 13 17:00:00 IST 2018 |  | COMPLETED
660 | TT_TASK | MANUFACTURING PXB00Y MODULE | Fri Jan 26 08:00:00 IST 2018 | Sun Apr 08 17:00:00 IDT 2018 | Sun Jan 14 08:00:00 IST 2018 | Thu May 31 17:00:00 IDT 2018 |  | COMPLETED
661 | TT_TASK | TRANSPORT PXB00Y MODULE | Tue May 15 08:00:00 IDT 2018 | Wed May 30 17:00:00 IDT 2018 | Mon Jun 18 08:00:00 IDT 2018 | Mon Jun 25 17:00:00 IDT 2018 |  | COMPLETED
665 | TT_TASK | TRANSPORT TO SITE SFC/SEE CUBICLE CJT | Mon Mar 26 08:00:00 IDT 2018 | Tue May 08 17:00:00 IDT 2018 | Sun Mar 18 08:00:00 IST 2018 | Sun May 13 17:00:00 IDT 2018 |  | COMPLETED
669 | TT_TASK | TRANSPORT COMPRESSOR MAIN BODY SCA | Sat Jul 14 08:00:00 IDT 2018 | Tue Sep 11 17:00:00 IDT 2018 | Sat Nov 24 08:00:00 IST 2018 | Wed Jan 02 17:00:00 IST 2019 |  | COMPLETED
670 | TT_TASK | TRANSPORT RECEIVER TANKS SCA | Sat Sep 01 08:00:00 IDT 2018 | Tue Oct 30 17:00:00 IST 2018 | Sat Nov 24 08:00:00 IST 2018 | Wed Jan 02 17:00:00 IST 2019 |  | COMPLETED
676 | TT_TASK | PREPARATION BASIC BUILDING DWGS UBA BUILDING | Tue Feb 14 08:00:00 IST 2017 | Mon Mar 20 17:00:00 IST 2017 | Fri Feb 03 08:00:00 IST 2017 | Wed Feb 22 17:00:00 IST 2017 |  | COMPLETED
680 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM UBA/UBD | Wed Mar 01 08:00:00 IST 2017 | Tue May 23 17:00:00 IDT 2017 | Tue Feb 21 08:00:00 IST 2017 | Sun Apr 30 17:00:00 IDT 2017 |  | COMPLETED
682 | TT_TASK | MANUFACTURING, SHOP TEST MV-SWITCHGEAR BBA | Sat Sep 02 08:00:00 IDT 2017 | Fri Feb 23 17:00:00 IST 2018 | Tue Aug 01 08:00:00 IDT 2017 | Fri Mar 30 17:00:00 IDT 2018 |  | COMPLETED
684 | TT_TASK | TRANSPORT TO SITE MV-SWITCHGEAR BBA | Mon Apr 02 08:00:00 IDT 2018 | Mon Apr 30 17:00:00 IDT 2018 | Sun Jun 17 08:00:00 IDT 2018 | Mon Jul 23 17:00:00 IDT 2018 |  | COMPLETED
686 | TT_TASK | MANUFACTURING, SHOP TEST LV-/DC-SWITCHGEAR BFA | Mon Oct 30 08:00:00 IST 2017 | Sun Feb 25 17:00:00 IST 2018 | Sat Sep 30 08:00:00 IDT 2017 | Mon Jun 25 17:00:00 IDT 2018 |  | COMPLETED
688 | TT_TASK | TRANSPORT TO SITE LV-/DC-SWITCHGEAR BFA | Thu May 17 08:00:00 IDT 2018 | Sun Jul 15 17:00:00 IDT 2018 | Tue Aug 14 08:00:00 IDT 2018 | Thu Sep 20 17:00:00 IDT 2018 |  | COMPLETED
693 | TT_TASK | PREPARATION, SHOP TEST, DISMANTLING CABINET 10UBA BUILDING | Mon Mar 26 08:00:00 IDT 2018 | Sun Jun 03 17:00:00 IDT 2018 | Sat Mar 03 08:00:00 IST 2018 | Sat Jun 30 17:00:00 IDT 2018 |  | COMPLETED
695 | TT_TASK | TRANSPORT TO SITE CABINET 10UBA BUILDING | Wed Jun 06 08:00:00 IDT 2018 | Sat Aug 04 17:00:00 IDT 2018 | Wed Jul 25 08:00:00 IDT 2018 | Sat Aug 25 17:00:00 IDT 2018 |  | COMPLETED
697 | TT_TASK | MANUFACTURING, SHOP TEST PROT./SYNCHR./METERING CHA | Sat Aug 26 08:00:00 IDT 2017 | Mon Mar 05 17:00:00 IST 2018 | Tue Aug 15 08:00:00 IDT 2017 | Fri Apr 13 17:00:00 IDT 2018 |  | COMPLETED
699 | TT_TASK | TRANSPORT TO SITE PROT., SYNCHR., METERING CHA | Fri Apr 27 08:00:00 IDT 2018 | Thu Jun 07 17:00:00 IDT 2018 | Sun May 27 08:00:00 IDT 2018 | Sat Jun 30 17:00:00 IDT 2018 |  | COMPLETED
701 | TT_TASK | TRANSPORT TO SITE SFC TRANSFORMER MBJ | Thu Mar 01 08:00:00 IST 2018 | Wed May 09 17:00:00 IDT 2018 | Thu Jan 18 08:00:00 IST 2018 | Sun Apr 01 17:00:00 IDT 2018 |  | COMPLETED
702 | TT_TASK | PREPARATION FOR DISPATCH TO SITE SEE/SFC TRANSFORMER MBJ | Fri Jan 26 08:00:00 IST 2018 | Sun Mar 11 17:00:00 IST 2018 | Fri Dec 15 08:00:00 IST 2017 | Mon Jan 15 17:00:00 IST 2018 |  | COMPLETED
703 | TT_TASK | TRANSPORT TO SITE SEE TRANSFORMER MKC | Mon Mar 26 08:00:00 IDT 2018 | Thu Apr 26 17:00:00 IDT 2018 | Fri Mar 23 08:00:00 IDT 2018 | Tue May 01 17:00:00 IDT 2018 |  | COMPLETED
704 | TT_TASK | ORDERING / NEGOTIATIONS SEE/SFC TRANSFORMER MKC / MBJ | Tue Feb 14 08:00:00 IST 2017 | Wed Mar 01 17:00:00 IST 2017 | Wed Feb 01 08:00:00 IST 2017 | Wed Mar 01 17:00:00 IST 2017 |  | COMPLETED
706 | TT_TASK | MANUFACTURING SEE/SFC TRANSFORMER MKC / MBJ | Fri Mar 17 08:00:00 IST 2017 | Fri Dec 22 17:00:00 IST 2017 | Thu Mar 02 08:00:00 IST 2017 | Tue Dec 12 17:00:00 IST 2017 |  | COMPLETED
707 | TT_TASK | FINAL CHECK & DISPATCH SEE/SFC TRANSFORMER MKC / MBJ | Sat Dec 16 08:00:00 IST 2017 | Fri Dec 22 17:00:00 IST 2017 | Wed Dec 13 08:00:00 IST 2017 | Tue Dec 19 17:00:00 IST 2017 |  | COMPLETED
711 | TT_TASK | PREPARATION BASIC BUILDING DWGS UBD01/02/03/04 | Thu Jun 01 08:00:00 IDT 2017 | Wed Jul 05 17:00:00 IDT 2017 | Wed May 10 08:00:00 IDT 2017 | Fri Jun 09 17:00:00 IDT 2017 |  | COMPLETED
713 | TT_TASK | DETAIL DESIGN / CHECKER CONCRETE STRUCTURE UBD01/02/03/04 | Sun Jul 09 08:00:00 IDT 2017 | Sun Sep 10 17:00:00 IDT 2017 | Sat Jun 10 08:00:00 IDT 2017 | Fri Jun 30 17:00:00 IDT 2017 |  | COMPLETED
714 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM UBD | Fri Jan 26 08:00:00 IST 2018 | Mon May 07 17:00:00 IDT 2018 | Fri Dec 29 08:00:00 IST 2017 | Wed Jun 27 17:00:00 IDT 2018 |  | COMPLETED
716 | TT_TASK | PREPARATION BASIC BUILDING DWGS UBF/UBE | Thu Jun 01 08:00:00 IDT 2017 | Wed Jul 05 17:00:00 IDT 2017 | Thu May 04 08:00:00 IDT 2017 | Wed May 24 17:00:00 IDT 2017 |  | COMPLETED
720 | TT_TASK | DETAIL DESIGN / CHECKER STEEL STRUCTURE UBF/UBE | Tue Jul 25 08:00:00 IDT 2017 | Mon Sep 18 17:00:00 IDT 2017 | Wed Jul 19 08:00:00 IDT 2017 | Mon Oct 09 17:00:00 IDT 2017 |  | COMPLETED
721 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM UBF | Fri Jan 26 08:00:00 IST 2018 | Mon May 07 17:00:00 IDT 2018 | Fri Dec 29 08:00:00 IST 2017 | Wed Jun 27 17:00:00 IDT 2018 |  | COMPLETED
723 | TT_TASK | PREPARATION BASIC BUILDING DWGS UBL | Mon Jun 26 08:00:00 IDT 2017 | Sun Jul 30 17:00:00 IDT 2017 | Mon May 01 08:00:00 IDT 2017 | Wed May 24 17:00:00 IDT 2017 |  | COMPLETED
725 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM UBL | Fri Jan 26 08:00:00 IST 2018 | Sun May 27 17:00:00 IDT 2018 | Fri Dec 29 08:00:00 IST 2017 | Wed Jun 27 17:00:00 IDT 2018 |  | COMPLETED
727 | TT_TASK | MANUFACTURING, SHOP TEST IPB BAA | Fri Sep 01 08:00:00 IDT 2017 | Thu Mar 01 17:00:00 IST 2018 | Mon Jul 31 08:00:00 IDT 2017 | Tue Feb 27 17:00:00 IST 2018 |  | COMPLETED
729 | TT_TASK | TRANSPORT IPB BAA | Wed Aug 26 08:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Mon May 07 08:00:00 IDT 2018 | Wed Jun 20 17:00:00 IDT 2018 |  | COMPLETED
732 | TT_TASK | MANUFACTURING, SHOP TEST MAIN TRANSFORMER BAT | Wed Feb 01 08:00:00 IST 2017 | Wed Dec 27 17:00:00 IST 2017 | Tue Jan 24 08:00:00 IST 2017 | Fri Mar 02 17:00:00 IST 2018 |  | COMPLETED
734 | TT_TASK | TRANSPORT MAIN TRANSFORMER BAT | Wed May 02 08:00:00 IDT 2018 | Wed May 16 17:00:00 IDT 2018 | Thu May 03 08:00:00 IDT 2018 | Sat May 05 17:00:00 IDT 2018 |  | COMPLETED
736 | TT_TASK | MANUFACTURING, SHOP TEST AUXILIARY TRANSFORMER BBT | Wed Feb 01 08:00:00 IST 2017 | Wed Dec 27 17:00:00 IST 2017 | Tue Jan 24 08:00:00 IST 2017 | Wed Dec 27 17:00:00 IST 2017 |  | COMPLETED
738 | TT_TASK | TRANSPORT AUXILIARY TRANSFORMER BBT | Mon Feb 26 08:00:00 IST 2018 | Wed Feb 28 17:00:00 IST 2018 | Wed Jan 31 08:00:00 IST 2018 | Sat Feb 03 17:00:00 IST 2018 |  | COMPLETED
740 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM UBE/UBF | Sat Jul 01 08:00:00 IDT 2017 | Fri Aug 11 17:00:00 IDT 2017 | Thu Jun 08 08:00:00 IDT 2017 | Mon Aug 28 17:00:00 IDT 2017 |  | COMPLETED
743 | TT_TASK | PREPARATION BASIC BUILDING DWGS ULD | Wed Apr 12 08:00:00 IDT 2017 | Tue May 16 17:00:00 IDT 2017 | Mon Mar 27 08:00:00 IDT 2017 | Tue Apr 25 00:00:00 IDT 2017 |  | COMPLETED
748 | TT_TASK | DESIGN, MANUFACTURING, SHOP TEST CONDENSATE POLISHING PLANT LD | Thu Mar 16 08:00:00 IST 2017 | Fri Jan 12 17:00:00 IST 2018 | Wed Mar 01 08:00:00 IST 2017 | Fri Jul 20 17:00:00 IDT 2018 |  | COMPLETED
750 | TT_TASK | TRANSPORT CONDENSATE POLISHING PLANT LD | Thu Jun 07 08:00:00 IDT 2018 | Wed Jul 25 17:00:00 IDT 2018 | Tue Oct 02 08:00:00 IDT 2018 | Tue Nov 06 17:00:00 IST 2018 |  | COMPLETED
753 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST CONDENSATE POLISHING PUMP LDK | Thu Jun 15 08:00:00 IDT 2017 | Tue Apr 10 17:00:00 IDT 2018 | Sat May 20 08:00:00 IDT 2017 | Fri Dec 15 17:00:00 IST 2017 |  | COMPLETED
755 | TT_TASK | TRANSPORT CONDENSATE POLISHING PUMP LDK | Mon Feb 26 08:00:00 IST 2018 | Tue Apr 17 17:00:00 IDT 2018 | Sun Feb 25 08:00:00 IST 2018 | Fri Apr 06 17:00:00 IDT 2018 |  | COMPLETED
759 | TT_TASK | PREPARATION BASIC BUILDING DWGS UEZ01/02 | Mon Jun 26 08:00:00 IDT 2017 | Sun Jul 30 17:00:00 IDT 2017 | Sat Jun 17 08:00:00 IDT 2017 | Mon Aug 07 17:00:00 IDT 2017 |  | COMPLETED
761 | TT_TASK | DETAIL DESIGN / CHECKER CONCRETE STRUCTURE UEZ01/02 | Tue Sep 05 08:00:00 IDT 2017 | Mon Nov 06 17:00:00 IST 2017 | Tue Aug 08 08:00:00 IDT 2017 | Sat Nov 04 17:00:00 IST 2017 |  | COMPLETED
765 | TT_TASK | QUOTATION STAGE GENERATOR CIRCUIT BREAKER BAC | Mon May 08 08:00:00 IDT 2017 | Sun Jun 04 17:00:00 IDT 2017 | Sat Apr 08 08:00:00 IDT 2017 | Fri May 05 17:00:00 IDT 2017 |  | COMPLETED
767 | TT_TASK | MANUFACTURING, SHOP TEST GENERATOR CIRCUIT BREAKER BAC | Thu Jun 01 08:00:00 IDT 2017 | Tue Mar 13 17:00:00 IST 2018 | Sat May 06 08:00:00 IDT 2017 | Wed Dec 20 17:00:00 IST 2017 |  | COMPLETED
769 | TT_TASK | TRANSPORT GENERATOR CIRCUIT BREAKER BAC | Mon Feb 05 08:00:00 IST 2018 | Tue Mar 06 17:00:00 IST 2018 | Mon Feb 05 08:00:00 IST 2018 | Fri Mar 16 17:00:00 IST 2018 |  | COMPLETED
772 | TT_TASK | PREPARATION BASIC BUILDING DWGS UBN | Thu Jun 01 08:00:00 IDT 2017 | Wed Jul 05 17:00:00 IDT 2017 | Wed May 10 08:00:00 IDT 2017 | Tue Jul 25 17:00:00 IDT 2017 |  | COMPLETED
775 | TT_TASK | BASIC DESIGN, SPECIFICATION EMERGENCY DIESEL GENERATOR SET XKA | Thu Jun 01 08:00:00 IDT 2017 | Wed Jun 28 17:00:00 IDT 2017 | Tue May 16 08:00:00 IDT 2017 | Mon Jun 12 17:00:00 IDT 2017 |  | COMPLETED
777 | TT_TASK | QUOTATION STAGE EMERGENCY DIESEL GENERATOR SET XKA | Sat Jul 08 08:00:00 IDT 2017 | Fri Aug 04 17:00:00 IDT 2017 | Tue Jun 13 08:00:00 IDT 2017 | Mon Jul 31 17:00:00 IDT 2017 |  | COMPLETED
779 | TT_TASK | MANUFACTURING, SHOP TEST EMERGENCY DIESEL GENERATOR SET XKA | Sat Sep 02 08:00:00 IDT 2017 | Fri May 18 17:00:00 IDT 2018 | Tue Aug 01 08:00:00 IDT 2017 | Thu May 31 17:00:00 IDT 2018 |  | COMPLETED
781 | TT_TASK | TRANSPORT EMERGENCY DIESEL GENERATOR .SET XKA | Thu May 24 08:00:00 IDT 2018 | Sun Jul 22 17:00:00 IDT 2018 | Mon Oct 15 08:00:00 IDT 2018 | Sat Nov 17 17:00:00 IST 2018 |  | COMPLETED
783 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM UBN | Tue Jul 25 08:00:00 IDT 2017 | Mon Sep 04 17:00:00 IDT 2017 | Sat Jul 01 08:00:00 IDT 2017 | Thu Aug 24 17:00:00 IDT 2017 |  | COMPLETED
786 | TT_TASK | MANUFACTURING, SHOP TEST LV-TRANSFORMERS BFT | Tue Jul 25 08:00:00 IDT 2017 | Mon Jan 22 17:00:00 IST 2018 | Thu Jul 20 08:00:00 IDT 2017 | Wed Feb 21 17:00:00 IST 2018 |  | COMPLETED
788 | TT_TASK | TRANSPORT LV-TRANSFORMERS BFT | Sun Mar 25 08:00:00 IDT 2018 | Wed May 23 17:00:00 IDT 2018 | Sun Apr 08 08:00:00 IDT 2018 | Tue May 15 17:00:00 IDT 2018 |  | COMPLETED
794 | TT_TASK | PREPARATION BASIC BUILDING DWGS UMX | Mon May 01 08:00:00 IDT 2017 | Sun Jun 04 17:00:00 IDT 2017 | Sat Apr 08 08:00:00 IDT 2017 | Fri May 12 17:00:00 IDT 2017 |  | COMPLETED
797 | TT_TASK | TRANSPORT DIFFUSER MBR | Mon Mar 26 08:00:00 IDT 2018 | Tue Mar 27 17:00:00 IDT 2018 | Wed Feb 28 08:00:00 IST 2018 | Fri Mar 02 17:00:00 IST 2018 |  | COMPLETED
800 | TT_TASK | TRANSPORT TURBINE EXHAUST MANIFOLD MBR | Mon Mar 26 08:00:00 IDT 2018 | Sun Apr 01 17:00:00 IDT 2018 | Fri Mar 02 08:00:00 IST 2018 | Sat Mar 10 17:00:00 IST 2018 |  | COMPLETED
801 | TT_TASK | DETAIL DESIGN / MANUFACTURING DIFFUSER MBR | Thu Mar 16 08:00:00 IST 2017 | Wed Dec 06 17:00:00 IST 2017 | Fri Mar 10 08:00:00 IST 2017 | Thu Nov 30 17:00:00 IST 2017 |  | COMPLETED
803 | TT_TASK | DETAIL DESIGN / MANUFACTURING TURBINE EXHAUST MANIFOLD MBR | Sun Apr 09 08:00:00 IDT 2017 | Sat Dec 30 17:00:00 IST 2017 | Fri Mar 24 08:00:00 IDT 2017 | Thu Dec 14 17:00:00 IST 2017 |  | COMPLETED
805 | TT_TASK | TRANSPORT DIFFUSER MBR TO PORT OF EXPORT | Fri Jan 26 08:00:00 IST 2018 | Thu Feb 08 17:00:00 IST 2018 | Fri Dec 15 08:00:00 IST 2017 | Thu Dec 28 17:00:00 IST 2017 |  | COMPLETED
806 | TT_TASK | TRANSPORT TURBINE EXHAUST MANIFOLD MBR TO PORT OF EXPORT | Fri Jan 26 08:00:00 IST 2018 | Thu Feb 08 17:00:00 IST 2018 | Fri Dec 15 08:00:00 IST 2017 | Thu Dec 28 17:00:00 IST 2017 |  | COMPLETED
813 | TT_TASK | PREPARATION BASIC BUILDING DWGS 10UEN | Mon Jun 26 08:00:00 IDT 2017 | Sun Jul 30 17:00:00 IDT 2017 | Sat Jun 17 08:00:00 IDT 2017 | Fri Jun 30 17:00:00 IDT 2017 |  | COMPLETED
816 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM 10UEN | Tue Jul 25 08:00:00 IDT 2017 | Mon Sep 04 17:00:00 IDT 2017 | Sat Jul 22 08:00:00 IDT 2017 | Fri Sep 01 17:00:00 IDT 2017 |  | COMPLETED
822 | TT_TASK | QUOTATION STAGE FUEL GAS SUPPLY SYSTEM EK/EKC | Wed Feb 01 08:00:00 IST 2017 | Tue Mar 28 17:00:00 IDT 2017 | Sat Jan 21 08:00:00 IST 2017 | Thu Apr 27 17:00:00 IDT 2017 |  | COMPLETED
824 | TT_TASK | DETAIL DESIGN, MANUFACTURING FUEL GAS SUPPLY SYSTEM EK/EKC | Mon May 01 08:00:00 IDT 2017 | Wed Oct 25 17:00:00 IDT 2017 | Fri Apr 28 08:00:00 IDT 2017 | Sun Dec 24 17:00:00 IST 2017 |  | COMPLETED
825 | TT_TASK | PRE ERECTION GAS SYSTEM/ PREHEATER EK/EKC | Fri Feb 16 08:00:00 IST 2018 | Mon Jul 02 17:00:00 IDT 2018 | Sat Jan 06 08:00:00 IST 2018 | Thu Mar 29 17:00:00 IDT 2018 |  | COMPLETED
827 | TT_TASK | TRANSPORT FUEL GAS SUPPLY SYSTEM EK/EKC | Sun May 06 08:00:00 IDT 2018 | Wed Jul 04 17:00:00 IDT 2018 | Sun Apr 22 08:00:00 IDT 2018 | Tue May 29 17:00:00 IDT 2018 |  | COMPLETED
831 | TT_TASK | PREPARATION BASIC BUILDING DWGS UHA | Wed Feb 15 08:00:00 IST 2017 | Tue Mar 21 17:00:00 IST 2017 | Thu Feb 02 08:00:00 IST 2017 | Fri Mar 03 17:00:00 IST 2017 |  | COMPLETED
841 | TT_TASK | TECHNICAL CLARIFICATION WITH HRSG SUPPLIER | Sat Nov 05 08:00:00 IST 2016 | Thu Nov 24 17:00:00 IST 2016 | Sat Sep 10 08:00:00 IDT 2016 | Fri Sep 30 17:00:00 IDT 2016 |  | COMPLETED
843 | TT_TASK | PROJECT SPECIFIC ADAPTION OF HRSG SPECIFICATION | Sat Jul 02 08:00:00 IDT 2016 | Thu Jul 28 17:00:00 IDT 2016 | Sat Jul 09 08:00:00 IDT 2016 | Fri Aug 05 17:00:00 IDT 2016 |  | COMPLETED
845 | TT_TASK | OFFER PREPARATION BY HRSG SUPPLIER | Sat Oct 01 08:00:00 IDT 2016 | Thu Nov 03 17:00:00 IST 2016 | Sat Aug 06 08:00:00 IDT 2016 | Fri Sep 09 17:00:00 IDT 2016 |  | COMPLETED
853 | TT_TASK | BASIC DESIGN MAIN STEEL STRUCTURE HRSG | Thu Nov 03 08:00:00 IST 2016 | Tue Feb 07 17:00:00 IST 2017 | Thu Nov 03 08:00:00 IST 2016 | Wed Feb 15 17:00:00 IST 2017 |  | COMPLETED
854 | TT_TASK | DETAIL DESIGN, MANUFACTURING MAIN STEEL STRUCTURE HRSG (Main Frame/Casing) | Wed Mar 01 08:00:00 IST 2017 | Sat Dec 30 17:00:00 IST 2017 | Thu Feb 16 08:00:00 IST 2017 | Tue Jan 30 17:00:00 IST 2018 |  | COMPLETED
858 | TT_TASK | TRANSPORT MAIN STEEL STRUCTURE HRSG (Main Frame/Casing)) | Mon Mar 26 08:00:00 IDT 2018 | Fri Mar 30 17:00:00 IDT 2018 | Thu Mar 01 08:00:00 IST 2018 | Thu Mar 08 17:00:00 IST 2018 |  | COMPLETED
861 | TT_TASK | BASIC AND DETAIL DESIGN, MANUFACTURING STEEL STRUCTURE HRSG - SECONDARY STEEL | Mon Jun 26 08:00:00 IDT 2017 | Mon Dec 25 17:00:00 IST 2017 | Thu Jun 15 08:00:00 IDT 2017 | Wed Apr 04 17:00:00 IDT 2018 |  | COMPLETED
864 | TT_TASK | TRANSPORT STEEL STRUCTURE HRSG - SECONDARY STEEL | Wed Jun 06 08:00:00 IDT 2018 | Wed Jun 13 17:00:00 IDT 2018 | Sat May 12 08:00:00 IDT 2018 | Thu May 31 17:00:00 IDT 2018 |  | COMPLETED
867 | TT_TASK | BASIC AND DETAIL DESIGN / ORDERING STEEL STRUCTURE HRSG - STACK | Thu Nov 24 08:00:00 IST 2016 | Wed Feb 15 17:00:00 IST 2017 | Thu Nov 24 08:00:00 IST 2016 | Fri Jul 28 17:00:00 IDT 2017 |  | COMPLETED
868 | TT_TASK | MANUFACTURING STEEL STRUCTURE HRSG - STACK | Sat Dec 16 08:00:00 IST 2017 | Wed Jun 13 17:00:00 IDT 2018 | Thu Nov 30 08:00:00 IST 2017 | Fri Aug 17 17:00:00 IDT 2018 |  | COMPLETED
871 | TT_TASK | TRANSPORT STEEL STRUCTURE HRSG - STACK | Mon Aug 06 08:00:00 IDT 2018 | Fri Aug 24 17:00:00 IDT 2018 | Tue Aug 21 08:00:00 IDT 2018 | Thu Aug 30 17:00:00 IDT 2018 |  | COMPLETED
875 | TT_TASK | TRANSPORT INLET & OUTLET DUCT | Mon Mar 26 08:00:00 IDT 2018 | Fri Mar 30 17:00:00 IDT 2018 | Thu Mar 01 08:00:00 IST 2018 | Thu Mar 08 17:00:00 IST 2018 |  | COMPLETED
879 | TT_TASK | TRANSPORT MODULES | Mon Mar 26 08:00:00 IDT 2018 | Fri Apr 06 17:00:00 IDT 2018 | Wed Mar 14 08:00:00 IST 2018 | Sun Apr 08 17:00:00 IDT 2018 |  | COMPLETED
881 | TT_TASK | DESIGN, MANUFACTURING, DELIVERY HRSG DRUMS | Thu Nov 03 08:00:00 IST 2016 | Tue Jan 23 17:00:00 IST 2018 | Thu Nov 03 08:00:00 IST 2016 | Mon Apr 09 17:00:00 IDT 2018 |  | COMPLETED
883 | TT_TASK | TRANSPORT HRSG DRUMS | Thu May 17 08:00:00 IDT 2018 | Sun May 27 17:00:00 IDT 2018 | Tue Apr 17 08:00:00 IDT 2018 | Thu Apr 26 17:00:00 IDT 2018 |  | COMPLETED
886 | TT_TASK | PROJECT SPECIFIC PRELIMINARY PIPE ROUTING AND SUPPORT CONCEPT HRSG | Thu Nov 03 08:00:00 IST 2016 | Tue Jan 31 17:00:00 IST 2017 | Thu Nov 03 08:00:00 IST 2016 | Tue Jan 31 17:00:00 IST 2017 |  | COMPLETED
888 | TT_TASK | STRESS ANALYSIS BY MTEC FOR HRSG-SYSTEMS LAB/LBA10/LBB/C | Tue Feb 14 08:00:00 IST 2017 | Tue Apr 18 17:00:00 IDT 2017 | Wed Feb 01 08:00:00 IST 2017 | Fri Apr 28 17:00:00 IDT 2017 |  | COMPLETED
890 | TT_TASK | REVIEW PIPE STRESS CALCULATION FOR HRSG SYSTEMS LAB/LBA10/LBB/LBC | Mon May 01 08:00:00 IDT 2017 | Sun May 21 17:00:00 IDT 2017 | Sat Apr 29 08:00:00 IDT 2017 | Thu Aug 03 17:00:00 IDT 2017 |  | COMPLETED
894 | TT_TASK | BASIC DESIGN, DETAIL DESIGN, ORDERING, DELIVERY, MANUFACTURING PIPING MATERIAL HRSG | Tue Feb 14 08:00:00 IST 2017 | Tue May 01 17:00:00 IDT 2018 | Wed Feb 01 08:00:00 IST 2017 | Mon Jun 25 17:00:00 IDT 2018 |  | COMPLETED
896 | TT_TASK | TRANSPORT PIPING MATERIAL HRSG | Fri Jul 06 08:00:00 IDT 2018 | Wed Jul 25 17:00:00 IDT 2018 | Mon Jul 23 08:00:00 IDT 2018 | Sat Aug 18 17:00:00 IDT 2018 |  | COMPLETED
899 | TT_TASK | BASIC DESIGN,QUOTATION STAGE, ODERING ELECTRICAL AND I&C-EQUIPMENT FOR HRSG | Sat Jun 10 08:00:00 IDT 2017 | Mon Oct 09 17:00:00 IDT 2017 | Sun May 07 08:00:00 IDT 2017 | Mon Oct 02 17:00:00 IDT 2017 |  | COMPLETED
900 | TT_TASK | DETAIL DESIGN, MANUFACTURING ELECTRICAL AND I&C-EQUIPMENT FOR HRSG | Thu Nov 02 08:00:00 IST 2017 | Sun Apr 29 17:00:00 IDT 2018 | Tue Oct 03 08:00:00 IDT 2017 | Fri Jun 15 17:00:00 IDT 2018 |  | COMPLETED
903 | TT_TASK | TRANSPORT ELECTRICAL AND I&C-EQUIPMENT FOR HRSG | Fri Jul 06 08:00:00 IDT 2018 | Wed Aug 08 17:00:00 IDT 2018 | Mon Jun 25 08:00:00 IDT 2018 | Tue Jul 31 17:00:00 IDT 2018 |  | COMPLETED
908 | TT_TASK | PREPARATION BASIC BUILDING DWGS UHW | Fri Mar 10 08:00:00 IST 2017 | Thu Apr 13 17:00:00 IDT 2017 | Thu Feb 23 08:00:00 IST 2017 | Wed Mar 29 17:00:00 IDT 2017 |  | COMPLETED
912 | TT_TASK | DETAIL DESIGN / CHECKER STEEL STRUCTURE UHW | Tue Jul 25 08:00:00 IDT 2017 | Mon Sep 18 17:00:00 IDT 2017 | Mon Jul 24 08:00:00 IDT 2017 | Mon Oct 09 17:00:00 IDT 2017 |  | COMPLETED
914 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL STRUCTURE UHW | Fri Jan 26 08:00:00 IST 2018 | Sun May 27 17:00:00 IDT 2018 | Fri Dec 29 08:00:00 IST 2017 | Wed Jun 27 17:00:00 IDT 2018 |  | COMPLETED
916 | TT_TASK | BASIC DESIGN, QUOTATION STAGE, ORDERING CLEAN DRAIN FLASH TANK LBH | Sat Nov 26 08:00:00 IST 2016 | Fri Mar 17 17:00:00 IST 2017 | Thu Nov 17 08:00:00 IST 2016 | Fri Apr 28 17:00:00 IDT 2017 |  | COMPLETED
917 | TT_TASK | DETAIL DESIGN, MANUFTURING CLEAN DRAIN FLASH TANK LBH | Mon May 29 08:00:00 IDT 2017 | Tue Apr 10 17:00:00 IDT 2018 | Sat Apr 29 08:00:00 IDT 2017 | Tue Jun 12 17:00:00 IDT 2018 |  | COMPLETED
920 | TT_TASK | TRANSPORT CLEAN DRAIN FLASH TANK LBH | Sun May 27 08:00:00 IDT 2018 | Sun Jul 22 17:00:00 IDT 2018 | Thu Jun 14 08:00:00 IDT 2018 | Wed Jul 25 17:00:00 IDT 2018 |  | COMPLETED
922 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST STEAM GENERATOR DRAIN PUMP LCL | Mon Jun 26 08:00:00 IDT 2017 | Fri Feb 09 17:00:00 IST 2018 | Fri Jun 02 08:00:00 IDT 2017 | Mon Dec 11 17:00:00 IST 2017 |  | COMPLETED
924 | TT_TASK | TRANSPORT STEAM GENERATOR DRAIN PUMP LCL | Mon Feb 26 08:00:00 IST 2018 | Mon Apr 02 17:00:00 IDT 2018 | Thu Feb 08 08:00:00 IST 2018 | Thu Mar 15 17:00:00 IST 2018 |  | COMPLETED
928 | TT_TASK | PREPARATION BASIC BUILDING DWGS ULA | Mon May 15 08:00:00 IDT 2017 | Sun Jun 18 17:00:00 IDT 2017 | Mon Apr 10 08:00:00 IDT 2017 | Tue May 30 17:00:00 IDT 2017 |  | COMPLETED
932 | TT_TASK | DETAIL DESIGN / CHECKER STEEL STRUCTURE ULA | Mon Jun 26 08:00:00 IDT 2017 | Sun Aug 27 17:00:00 IDT 2017 | Fri Jun 02 08:00:00 IDT 2017 | Thu Jul 27 17:00:00 IDT 2017 |  | COMPLETED
934 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL STRUCTURE ULA | Fri Jan 26 08:00:00 IST 2018 | Tue Jun 12 17:00:00 IDT 2018 | Fri Dec 29 08:00:00 IST 2017 | Sun Sep 30 17:00:00 IDT 2018 |  | COMPLETED
936 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM ULA | Mon Jul 17 08:00:00 IDT 2017 | Sun Sep 10 17:00:00 IDT 2017 | Fri Jun 23 08:00:00 IDT 2017 | Thu Aug 24 17:00:00 IDT 2017 |  | COMPLETED
941 | TT_TASK | CONTRACT REVIEW, PREPARATION RFQ CONDENSATE RECIRC.PUMP LCA51 | Sat Jan 14 08:00:00 IST 2017 | Tue Feb 28 17:00:00 IST 2017 | Thu Dec 15 08:00:00 IST 2016 | Mon Jan 23 17:00:00 IST 2017 |  | COMPLETED
942 | TT_TASK | QUOTATION STAGE CONDENSATE RECIRC.PUMP LCA51 | Wed Feb 01 08:00:00 IST 2017 | Fri Mar 17 17:00:00 IST 2017 | Tue Jan 24 08:00:00 IST 2017 | Thu May 18 17:00:00 IDT 2017 |  | COMPLETED
944 | TT_TASK | MANUFACTURING, SHOP TEST CONDENSATE RECIRCULATION PUMP LCA51 | Thu Jun 01 08:00:00 IDT 2017 | Mon Jan 08 17:00:00 IST 2018 | Fri May 19 08:00:00 IDT 2017 | Fri Dec 15 17:00:00 IST 2017 |  | COMPLETED
946 | TT_TASK | TRANSPORT CONDENSATE RECIRCULATING PUMP LCA51 | Fri Jan 26 08:00:00 IST 2018 | Thu Mar 15 17:00:00 IST 2018 | Tue Jan 02 08:00:00 IST 2018 | Sat Feb 10 17:00:00 IST 2018 |  | COMPLETED
948 | TT_TASK | DETAIL DESIGN LCA50Y MODULE | Thu Jun 01 08:00:00 IDT 2017 | Thu Nov 09 17:00:00 IST 2017 | Sat May 20 08:00:00 IDT 2017 | Sat Oct 28 17:00:00 IDT 2017 |  | COMPLETED
949 | TT_TASK | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL LCA50Y MODULE | Wed Nov 29 08:00:00 IST 2017 | Sun Mar 04 17:00:00 IST 2018 | Sun Oct 29 08:00:00 IST 2017 | Thu Feb 01 17:00:00 IST 2018 |  | COMPLETED
951 | TT_TASK | MANUFACTURING LCA50Y MODULE | Mon Mar 05 08:00:00 IST 2018 | Wed May 16 17:00:00 IDT 2018 | Fri Feb 02 08:00:00 IST 2018 | Thu May 31 17:00:00 IDT 2018 |  | COMPLETED
952 | TT_TASK | TRANSPORT LCA50Y MODULE | Thu Sep 20 08:00:00 IDT 2018 | Fri Oct 05 17:00:00 IDT 2018 | Mon Jun 18 08:00:00 IDT 2018 | Mon Jun 25 17:00:00 IDT 2018 |  | COMPLETED
959 | TT_TASK | CONTRACT REVIEW, PREPARATION RFQ FEEDWATER PUMP LAC | Sat Nov 26 08:00:00 IST 2016 | Sun Jan 08 17:00:00 IST 2017 | Thu Nov 03 08:00:00 IST 2016 | Fri Dec 16 17:00:00 IST 2016 |  | COMPLETED
960 | TT_TASK | QUOTATION STAGE FEEDWATER PUMP LAC (MPA) | Sat Jan 21 08:00:00 IST 2017 | Fri Feb 17 17:00:00 IST 2017 | Sat Dec 17 08:00:00 IST 2016 | Fri Jan 13 17:00:00 IST 2017 |  | COMPLETED
962 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST FEEDWATER PUMP LAC | Wed Mar 01 08:00:00 IST 2017 | Mon Dec 04 17:00:00 IST 2017 | Tue Feb 14 08:00:00 IST 2017 | Sun Nov 19 00:00:00 IST 2017 |  | COMPLETED
964 | TT_TASK | TRANSPORT FEEDWATER PUMP LAC | Sun Nov 26 08:00:00 IST 2017 | Sat Jan 13 17:00:00 IST 2018 | Tue Dec 12 00:00:00 IST 2017 | Mon Feb 05 17:00:00 IST 2018 |  | COMPLETED
966 | TT_TASK | DETAIL DESIGN LAC10Y MODULE | Thu Mar 16 08:00:00 IST 2017 | Mon Aug 28 17:00:00 IDT 2017 | Tue Mar 14 08:00:00 IST 2017 | Sat Aug 26 17:00:00 IDT 2017 |  | COMPLETED
967 | TT_TASK | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL LAC10Y MODULE | Wed Sep 27 08:00:00 IDT 2017 | Wed Dec 20 17:00:00 IST 2017 | Sun Aug 27 08:00:00 IDT 2017 | Sun Nov 19 17:00:00 IST 2017 |  | COMPLETED
969 | TT_TASK | MANUFACTURING LAC10Y MODULE | Sun Dec 17 08:00:00 IST 2017 | Sat May 12 17:00:00 IDT 2018 | Thu Nov 16 08:00:00 IST 2017 | Thu May 31 17:00:00 IDT 2018 |  | COMPLETED
970 | TT_TASK | TRANSPORT LAC10Y MODULE | Thu Sep 20 08:00:00 IDT 2018 | Fri Oct 05 17:00:00 IDT 2018 | Mon Jun 18 08:00:00 IDT 2018 | Mon Jun 25 17:00:00 IDT 2018 |  | COMPLETED
973 | TT_TASK | DESIGN, MANUFACTURING, SHOP TEST DOSING CONTAINER QC | Sun Jun 04 08:00:00 IDT 2017 | Wed Oct 11 17:00:00 IDT 2017 | Thu May 11 08:00:00 IDT 2017 | Tue Apr 17 17:00:00 IDT 2018 |  | COMPLETED
975 | TT_TASK | TRANSPORT DOSING CONTAINER QC | Sat Aug 25 08:00:00 IDT 2018 | Fri Oct 12 17:00:00 IDT 2018 | Fri May 25 08:00:00 IDT 2018 | Sat Jul 07 17:00:00 IDT 2018 |  | COMPLETED
978 | TT_TASK | DESIGN, MANUFACTURING, SHOP TEST SAMPLING CONTAINER QU | Mon Jun 05 08:00:00 IDT 2017 | Tue Nov 21 17:00:00 IST 2017 | Thu May 11 08:00:00 IDT 2017 | Wed Jun 06 17:00:00 IDT 2018 |  | COMPLETED
980 | TT_TASK | TRANSPORT SAMPLING CONTAINER QU | Fri Oct 05 08:00:00 IDT 2018 | Thu Nov 22 17:00:00 IST 2018 | Sun Sep 02 08:00:00 IDT 2018 | Sat Oct 06 17:00:00 IDT 2018 |  | COMPLETED
984 | TT_TASK | PREPARATION BASIC BUILDING DWGS UMY | Mon Jun 26 08:00:00 IDT 2017 | Sun Jul 30 17:00:00 IDT 2017 | Fri Jun 02 08:00:00 IDT 2017 | Wed Jun 21 17:00:00 IDT 2017 |  | COMPLETED
986 | TT_TASK | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL STRUCTURE UMY | Fri Jan 26 08:00:00 IST 2018 | Sun May 27 17:00:00 IDT 2018 | Fri Dec 29 08:00:00 IST 2017 | Sat Sep 15 17:00:00 IDT 2018 |  | COMPLETED
989 | TT_TASK | DETAIL DESIGN / CHECKER STEEL STRUCTURE UMY00Y | Fri Jun 02 08:00:00 IDT 2017 | Sat Nov 25 17:00:00 IST 2017 | Sat May 13 08:00:00 IDT 2017 | Mon Dec 25 17:00:00 IST 2017 |  | COMPLETED
990 | TT_TASK | MANUFACTURING UMY00Y MODULE | Wed Aug 01 08:00:00 IDT 2018 | Sat Oct 06 17:00:00 IDT 2018 | Thu Apr 26 08:00:00 IDT 2018 | Sat Oct 06 17:00:00 IDT 2018 |  | COMPLETED
991 | TT_TASK | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL UMY00Y MODULE | Mon Feb 05 08:00:00 IST 2018 | Wed May 02 17:00:00 IDT 2018 | Tue Dec 26 08:00:00 IST 2017 | Wed May 23 17:00:00 IDT 2018 |  | COMPLETED
993 | TT_TASK | TRANSPORT STEEL STRUCTURE UMY00Y | Mon Oct 22 08:00:00 IDT 2018 | Mon Nov 05 17:00:00 IST 2018 | Wed Oct 17 08:00:00 IDT 2018 | Mon Nov 05 17:00:00 IST 2018 |  | COMPLETED
995 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM UMY | Mon Oct 23 08:00:00 IDT 2017 | Sun Dec 17 17:00:00 IST 2017 | Fri Sep 22 08:00:00 IDT 2017 | Thu Nov 16 17:00:00 IST 2017 |  | COMPLETED
998 | TT_TASK | PREPARATION BASIC BUILDING DWGS UHX | Sat Aug 26 08:00:00 IDT 2017 | Fri Sep 29 17:00:00 IDT 2017 | Fri Aug 25 08:00:00 IDT 2017 | Sun Sep 24 17:00:00 IDT 2017 |  | COMPLETED
1002 | TT_TASK | PREPARATION BASIC BUILDING DWGS UTX | Thu Nov 02 08:00:00 IST 2017 | Wed Dec 06 17:00:00 IST 2017 | Mon Sep 25 08:00:00 IDT 2017 | Wed Oct 18 17:00:00 IDT 2017 |  | COMPLETED
1006 | TT_TASK | PREPARATION BASIC BUILDING DWGS SCR UNIT | Mon May 01 08:00:00 IDT 2017 | Sun Jun 04 17:00:00 IDT 2017 | Sat Apr 29 08:00:00 IDT 2017 | Fri Jun 30 17:00:00 IDT 2017 |  | COMPLETED
1007 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS SCR UNIT | Mon May 01 08:00:00 IDT 2017 | Sun May 14 17:00:00 IDT 2017 | Sat Apr 29 08:00:00 IDT 2017 | Fri May 12 17:00:00 IDT 2017 |  | COMPLETED
1010 | TT_TASK | DESIGN, MANUFACTURING, SHOP TEST SCR UNIT | Mon May 15 08:00:00 IDT 2017 | Thu Mar 08 17:00:00 IST 2018 | Sat Apr 15 08:00:00 IDT 2017 | Fri Jun 15 17:00:00 IDT 2018 |  | COMPLETED
1014 | TT_TASK | TRANSPORT SCR UNIT | Wed Sep 05 08:00:00 IDT 2018 | Sat Nov 03 17:00:00 IST 2018 | Wed Jul 18 08:00:00 IDT 2018 | Fri Oct 26 17:00:00 IDT 2018 |  | COMPLETED
1015 | TT_TASK | TRANSPORT SCR CATALYST | Mon Nov 05 08:00:00 IST 2018 | Thu Jan 03 17:00:00 IST 2019 | Sun Jan 27 08:00:00 IST 2019 | Thu Feb 21 17:00:00 IST 2019 |  | COMPLETED
1020 | TT_TASK | DETAIL DESIGN, SUPPLY, PREFAB., SHOP TEST STANDARD PIPING SUPPORT PARTS ALL SIZES | Sat Aug 26 08:00:00 IDT 2017 | Mon Feb 05 17:00:00 IST 2018 | Fri Aug 04 08:00:00 IDT 2017 | Sun Jan 14 17:00:00 IST 2018 |  | COMPLETED
1021 | TT_TASK | PREFABRICATION, SHOP TEST ALLOYED AND OTHER PIPING MATERIAL (DN>=80) ALL SIZES | Wed Nov 29 08:00:00 IST 2017 | Tue Jan 23 17:00:00 IST 2018 | Mon Nov 20 08:00:00 IST 2017 | Fri Mar 02 17:00:00 IST 2018 |  | COMPLETED
1023 | TT_TASK | TRANSPORT (1ST) PIPING (DN >=80) AND STANDARD SUPPORT PARTS ALL SIZES | Mon Mar 26 08:00:00 IDT 2018 | Sun Apr 08 17:00:00 IDT 2018 | Tue Mar 20 08:00:00 IST 2018 | Tue Apr 10 17:00:00 IDT 2018 |  | COMPLETED
1024 | TT_TASK | TRANSPORT (2ND) PIPING (DN >=80) AND STANDARD SUPPORT PARTS ALL SIZES | Tue Mar 12 08:00:00 IST 2019 | Mon Mar 25 17:00:00 IST 2019 | Fri Apr 20 08:00:00 IDT 2018 | Wed May 02 17:00:00 IDT 2018 |  | COMPLETED
1026 | TT_TASK | TRANSPORT (3RD) PIPING (DN >=80) AND STANDARD SUPPORT PARTS ALL SIZES | Mon May 14 08:00:00 IDT 2018 | Sun May 27 17:00:00 IDT 2018 | Wed Jul 04 08:00:00 IDT 2018 | Fri Jul 13 17:00:00 IDT 2018 |  | COMPLETED
1028 | TT_TASK | TRANSPORT (4TH) PIPING (DN >=80) AND STANDARD SUPPORT PARTS ALL SIZES | Sun Jun 03 08:00:00 IDT 2018 | Sat Jun 16 17:00:00 IDT 2018 | Mon Jul 16 08:00:00 IDT 2018 | Fri Jul 20 17:00:00 IDT 2018 |  | COMPLETED
1032 | TT_TASK | DETAIL DESIGN, SUPPLY, SHOP TEST PIPING (DN | Sat Aug 26 08:00:00 IDT 2017 | Sun Jan 28 17:00:00 IST 2018 | Wed Jul 26 08:00:00 IDT 2017 | Fri Dec 29 08:00:00 IST 2017 |  | COMPLETED
1034 | TT_TASK | TRANSPORT (1ST) PIPING (DN | Wed May 02 08:00:00 IDT 2018 | Tue May 08 17:00:00 IDT 2018 | Fri Mar 30 08:00:00 IDT 2018 | Tue Apr 10 17:00:00 IDT 2018 |  | COMPLETED
1035 | TT_TASK | TRANSPORT (2ND) PIPING (DN | Mon May 14 08:00:00 IDT 2018 | Sun May 27 17:00:00 IDT 2018 | Sun Apr 22 08:00:00 IDT 2018 | Wed May 02 17:00:00 IDT 2018 |  | COMPLETED
1039 | TT_TASK | TRANSPORT TO PREFABRICATION SHOP (ALLOYED MATERIAL) | Tue Oct 31 08:00:00 IST 2017 | Mon Nov 27 17:00:00 IST 2017 | Sun Oct 01 08:00:00 IDT 2017 | Sat Oct 28 17:00:00 IDT 2017 |  | COMPLETED
1041 | TT_TASK | TRANSPORT TO PREFABRICATION SHOP (NON-ALLOYED MATERIALS) | Mon Oct 09 08:00:00 IDT 2017 | Sun Nov 12 17:00:00 IST 2017 | Fri Sep 08 08:00:00 IDT 2017 | Thu Oct 12 17:00:00 IDT 2017 |  | COMPLETED
1043 | TT_TASK | TRANSPORT TO PREFABRICATION SHOP (GRP MATERIALS) | Fri Nov 17 08:00:00 IST 2017 | Thu Jan 04 17:00:00 IST 2018 | Wed Oct 18 08:00:00 IDT 2017 | Mon Dec 25 17:00:00 IST 2017 |  | COMPLETED
1045 | TT_TASK | TRANSPORT VALVES | Mon Mar 05 08:00:00 IST 2018 | Sun Mar 18 17:00:00 IST 2018 | Fri Feb 02 08:00:00 IST 2018 | Fri Feb 23 17:00:00 IST 2018 |  | COMPLETED
1049 | TT_TASK | TRANSPORT PIPING FOR STEAM BLOWING SYSTEM ZTB | Wed May 02 08:00:00 IDT 2018 | Tue Jun 19 17:00:00 IDT 2018 | Fri Nov 16 08:00:00 IST 2018 | Fri Nov 23 17:00:00 IST 2018 |  | COMPLETED
1053 | TT_TASK | DETAIL DESIGN UPY00Y MODULE | Mon Jun 26 08:00:00 IDT 2017 | Sun Dec 03 17:00:00 IST 2017 | Mon Jun 05 08:00:00 IDT 2017 | Fri Nov 17 17:00:00 IST 2017 |  | COMPLETED
1055 | TT_TASK | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL UPY00Y MODULE | Tue Dec 19 08:00:00 IST 2017 | Sat Mar 24 17:00:00 IDT 2018 | Sat Nov 18 08:00:00 IST 2017 | Wed Feb 21 17:00:00 IST 2018 |  | COMPLETED
1057 | TT_TASK | MANUFACTURING UPY00Y MODULE | Sun Mar 25 08:00:00 IDT 2018 | Sun Jul 01 17:00:00 IDT 2018 | Thu Feb 22 08:00:00 IST 2018 | Thu Nov 15 17:00:00 IST 2018 |  | COMPLETED
1058 | TT_TASK | TRANSPORT UPY00Y MODULE | Mon Jul 23 08:00:00 IDT 2018 | Mon Aug 06 17:00:00 IDT 2018 | Fri Nov 23 08:00:00 IST 2018 | Fri Nov 30 17:00:00 IST 2018 |  | COMPLETED
1062 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM UQA ELECTRICAL ROOM | Mon Jun 26 08:00:00 IDT 2017 | Sun Aug 06 17:00:00 IDT 2017 | Fri Jun 02 08:00:00 IDT 2017 | Thu Aug 24 17:00:00 IDT 2017 |  | COMPLETED
1065 | TT_TASK | PREPARATION BASIC BUILDING DWGS 10UQA | Wed May 03 08:00:00 IDT 2017 | Tue Jun 06 17:00:00 IDT 2017 | Sat Apr 01 08:00:00 IDT 2017 | Fri Apr 28 17:00:00 IDT 2017 |  | COMPLETED
1072 | TT_TASK | CONTRACT REVIEW, PREPARATION RFQ DEBRIS FILTER PBB | Sat Jan 14 08:00:00 IST 2017 | Fri Feb 10 17:00:00 IST 2017 | Mon Dec 19 08:00:00 IST 2016 | Sun Jan 15 17:00:00 IST 2017 |  | COMPLETED
1073 | TT_TASK | QUOTATION STAGE DEBRIS FILTER PBB | Sun Mar 05 08:00:00 IST 2017 | Sat Mar 18 17:00:00 IST 2017 | Thu Jan 26 08:00:00 IST 2017 | Fri Apr 21 17:00:00 IDT 2017 |  | COMPLETED
1074 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST DEBRIS FILTER PBB | Mon May 15 08:00:00 IDT 2017 | Mon Feb 05 17:00:00 IST 2018 | Sun Apr 23 08:00:00 IDT 2017 | Mon Dec 18 17:00:00 IST 2017 |  | COMPLETED
1076 | TT_TASK | TRANSPORT DEBRIS FILTER PBB | Fri Jan 26 08:00:00 IST 2018 | Thu Mar 15 17:00:00 IST 2018 | Tue Dec 19 08:00:00 IST 2017 | Wed Jan 17 17:00:00 IST 2018 |  | COMPLETED
1078 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST CIRC. CW PUMP PAC | Sat May 06 08:00:00 IDT 2017 | Sat Jun 23 17:00:00 IDT 2018 | Sun Apr 16 08:00:00 IDT 2017 | Sun Apr 22 17:00:00 IDT 2018 |  | COMPLETED
1080 | TT_TASK | TRANSPORT CIRC. CW PUMP PAC | Sun Jul 01 08:00:00 IDT 2018 | Sat Aug 18 17:00:00 IDT 2018 | Sat Jun 09 08:00:00 IDT 2018 | Sat Jul 07 17:00:00 IDT 2018 |  | COMPLETED
1084 | TT_TASK | FABRICATION DESIGN, MANUFACTURING, SHOP TEST CRANE SMQ FOR UQA | Tue Jul 25 08:00:00 IDT 2017 | Mon Jan 22 17:00:00 IST 2018 | Wed Jul 19 08:00:00 IDT 2017 | Wed Feb 28 17:00:00 IST 2018 |  | COMPLETED
1086 | TT_TASK | TRANSPORT CRANE SMQ FOR UQA | Tue Apr 17 08:00:00 IDT 2018 | Thu May 10 17:00:00 IDT 2018 | Thu Mar 22 08:00:00 IST 2018 | Mon Apr 23 17:00:00 IDT 2018 |  | COMPLETED
1090 | TT_TASK | DETAIL DESIGN, MANUFACTURING CW BAR SCREEN FOR PAB SYSTEM | Sun Nov 26 08:00:00 IST 2017 | Mon Apr 23 17:00:00 IDT 2018 | Thu Oct 26 00:00:00 IDT 2017 | Fri Mar 23 17:00:00 IDT 2018 |  | COMPLETED
1092 | TT_TASK | TRANSPORT CW BAR SCREEN FOR PAB SYSTEM | Wed May 02 08:00:00 IDT 2018 | Tue May 15 17:00:00 IDT 2018 | Wed May 23 08:00:00 IDT 2018 | Mon May 28 17:00:00 IDT 2018 |  | COMPLETED
1097 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST PROCESS DRAINS TREATMENT GN- | Tue Aug 08 08:00:00 IDT 2017 | Thu Mar 29 17:00:00 IDT 2018 | Wed Jul 12 08:00:00 IDT 2017 | Wed Apr 18 17:00:00 IDT 2018 |  | COMPLETED
1099 | TT_TASK | TRANSPORT PROCESS DRAINS TREATMENT GN- | Sat May 26 08:00:00 IDT 2018 | Tue Jul 24 17:00:00 IDT 2018 | Sun Jun 10 08:00:00 IDT 2018 | Mon Jul 16 17:00:00 IDT 2018 |  | COMPLETED
1105 | TT_TASK | DESIGN, MANUFACTURING, SHOP TEST LABORATORY CONTAINER STG | Thu Oct 26 08:00:00 IDT 2017 | Sun Apr 08 17:00:00 IDT 2018 | Mon Sep 25 08:00:00 IDT 2017 | Thu Jun 07 17:00:00 IDT 2018 |  | COMPLETED
1107 | TT_TASK | TRANSPORT LABORATORY CONTAINER STG | Mon Jul 02 08:00:00 IDT 2018 | Sun Aug 19 17:00:00 IDT 2018 | Sun Aug 26 08:00:00 IDT 2018 | Mon Oct 08 17:00:00 IDT 2018 |  | COMPLETED
1112 | TT_TASK | PREPARATION BASIC BUILDING DWGS 00UEN | Mon Jun 26 08:00:00 IDT 2017 | Sun Jul 30 17:00:00 IDT 2017 | Sat Jun 17 08:00:00 IDT 2017 | Fri Jun 30 17:00:00 IDT 2017 |  | COMPLETED
1117 | TT_TASK | PREPARATION BASIC BUILDING DWGS UGY | Sat Aug 26 08:00:00 IDT 2017 | Fri Sep 29 17:00:00 IDT 2017 | Fri Aug 25 08:00:00 IDT 2017 | Sun Sep 24 17:00:00 IDT 2017 |  | COMPLETED
1121 | TT_TASK | DETAIL DESIGN / CHECKER STEEL STRUCTURE UGY | Tue Aug 08 08:00:00 IDT 2017 | Mon Oct 02 17:00:00 IDT 2017 | Mon Jul 10 08:00:00 IDT 2017 | Wed Nov 15 17:00:00 IST 2017 |  | COMPLETED
1125 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM UCA | Wed Mar 01 08:00:00 IST 2017 | Tue Apr 11 17:00:00 IDT 2017 | Tue Feb 21 08:00:00 IST 2017 | Mon Apr 03 17:00:00 IDT 2017 |  | COMPLETED
1129 | TT_TASK | MANUFACTURING, SHOP TEST HV-SWITCHGEAR GIL | Fri Apr 14 08:00:00 IDT 2017 | Fri Mar 30 17:00:00 IDT 2018 | Thu Mar 30 08:00:00 IDT 2017 | Fri Mar 09 17:00:00 IST 2018 |  | COMPLETED
1131 | TT_TASK | PACKING HV-SWITCHGEAR GIL | Sat Apr 07 08:00:00 IDT 2018 | Sun May 06 17:00:00 IDT 2018 | Sat Mar 10 08:00:00 IST 2018 | Fri Mar 30 17:00:00 IDT 2018 |  | COMPLETED
1132 | TT_TASK | TRANSPORT HV-SWITCHGEAR GIL | Mon May 07 08:00:00 IDT 2018 | Mon Jun 04 17:00:00 IDT 2018 | Fri Jun 01 08:00:00 IDT 2018 | Tue Jul 10 17:00:00 IDT 2018 |  | COMPLETED
1137 | TT_TASK | (BOP) TECHNICAL CLARIFICATION FIRE ALARM SYSTEM CYE | Sat Jan 14 08:00:00 IST 2017 | Fri Feb 10 17:00:00 IST 2017 | Sat Dec 10 08:00:00 IST 2016 | Fri Jan 06 17:00:00 IST 2017 |  | COMPLETED
1138 | TT_TASK | (BOP) BASIC DESIGN, SPECIFICATION FIRE ALARM SYSTEM CYE | Sat Jan 14 08:00:00 IST 2017 | Fri Feb 10 17:00:00 IST 2017 | Sat Jan 07 08:00:00 IST 2017 | Wed Mar 22 17:00:00 IST 2017 |  | COMPLETED
1140 | TT_TASK | (BOP) QUOTATION STAGE FIRE ALARM SYSTEM CYE | Wed May 17 08:00:00 IDT 2017 | Sun Jun 25 17:00:00 IDT 2017 | Sat Apr 01 08:00:00 IDT 2017 | Mon Jun 19 17:00:00 IDT 2017 |  | COMPLETED
1142 | TT_TASK | (BOP) MANUFACTURING, SHOP TEST FIRE ALARM SYSTEM CYE | Sat Aug 26 08:00:00 IDT 2017 | Sun Jan 07 17:00:00 IST 2018 | Fri Aug 18 08:00:00 IDT 2017 | Sat Feb 17 17:00:00 IST 2018 |  | COMPLETED
1144 | TT_TASK | (BOP) TRANSPORT FIRE ALARM SYSTEM CYE | Fri Mar 02 08:00:00 IST 2018 | Tue Mar 06 17:00:00 IST 2018 | Sat Feb 24 08:00:00 IST 2018 | Wed Feb 28 17:00:00 IST 2018 |  | COMPLETED
1147 | TT_TASK | (BOP) TECHNICAL CLARIFICATION FIRE FIGHTING SYSTEM SG | Wed Mar 01 08:00:00 IST 2017 | Tue Mar 28 17:00:00 IDT 2017 | Sat Feb 25 08:00:00 IST 2017 | Fri Mar 24 17:00:00 IDT 2017 |  | COMPLETED
1148 | TT_TASK | (BOP) BASIC DESIGN, SPECIFICATION FIRE FIGHTING SYSTEM SG | Sat Apr 01 08:00:00 IDT 2017 | Fri Apr 14 17:00:00 IDT 2017 | Sat Mar 25 08:00:00 IDT 2017 | Fri Apr 07 17:00:00 IDT 2017 |  | COMPLETED
1150 | TT_TASK | (BOP) QUOTATION STAGE FIRE FIGHTING SYSTEM SG | Mon May 22 08:00:00 IDT 2017 | Fri Jun 30 17:00:00 IDT 2017 | Sat Apr 01 08:00:00 IDT 2017 | Mon Jun 19 17:00:00 IDT 2017 |  | COMPLETED
1151 | TT_TASK | (BOP) MANUFACTURING, SHOP TEST FIRE FIGHTING SYSTEM SG | Sat Aug 26 08:00:00 IDT 2017 | Sun Jan 07 17:00:00 IST 2018 | Fri Aug 18 08:00:00 IDT 2017 | Wed Aug 15 17:00:00 IDT 2018 |  | COMPLETED
1153 | TT_TASK | (BOP) TRANSPORT FIRE FIGHTING SYSTEM SG | Fri Jul 06 08:00:00 IDT 2018 | Thu Aug 30 17:00:00 IDT 2018 | Fri Aug 17 08:00:00 IDT 2018 | Tue Aug 21 17:00:00 IDT 2018 |  | COMPLETED
1156 | TT_TASK | (BOP) BASIC DESIGN, PREPARATION RFQ FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | Sat Apr 01 08:00:00 IDT 2017 | Fri May 26 17:00:00 IDT 2017 | Sat Mar 18 08:00:00 IST 2017 | Fri May 12 17:00:00 IDT 2017 |  | COMPLETED
1157 | TT_TASK | (BOP) QUOTATION STAGE FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | Tue Jun 13 08:00:00 IDT 2017 | Mon Jul 03 17:00:00 IDT 2017 | Sat May 13 08:00:00 IDT 2017 | Fri Jun 02 17:00:00 IDT 2017 |  | COMPLETED
1159 | TT_TASK | (BOP) TECHNICAL CLARIFICATION FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | Wed Feb 01 08:00:00 IST 2017 | Tue Mar 28 17:00:00 IDT 2017 | Sat Jan 21 08:00:00 IST 2017 | Fri Mar 17 17:00:00 IST 2017 |  | COMPLETED
1160 | TT_TASK | (BOP) DETAIL DESIGN, MANUFACTURING FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | Mon Jun 26 08:00:00 IDT 2017 | Sat Apr 21 17:00:00 IDT 2018 | Sat Jun 03 08:00:00 IDT 2017 | Fri Mar 23 17:00:00 IDT 2018 |  | COMPLETED
1162 | TT_TASK | (BOP) TRANSPORT FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | Sun May 06 08:00:00 IDT 2018 | Wed Jul 04 17:00:00 IDT 2018 | Sun Apr 22 08:00:00 IDT 2018 | Tue May 29 17:00:00 IDT 2018 |  | COMPLETED
1166 | TT_TASK | (BOP) BASIC DESIGN, SPECIFICATION MV CABLES BZK | Sat May 20 08:00:00 IDT 2017 | Fri Jun 16 17:00:00 IDT 2017 | Thu Apr 20 08:00:00 IDT 2017 | Wed May 17 17:00:00 IDT 2017 |  | COMPLETED
1167 | TT_TASK | (BOP) TECHNICAL CLARIFICATION MV CABLES BZK | Sat Apr 01 08:00:00 IDT 2017 | Fri Apr 28 17:00:00 IDT 2017 | Thu Mar 23 08:00:00 IST 2017 | Wed Apr 19 17:00:00 IDT 2017 |  | COMPLETED
1169 | TT_TASK | (BOP) QUOTATION STAGE MV CABLES BZK | Sun Jun 18 08:00:00 IDT 2017 | Sat Jul 29 17:00:00 IDT 2017 | Thu May 18 08:00:00 IDT 2017 | Thu Aug 24 17:00:00 IDT 2017 |  | COMPLETED
1171 | TT_TASK | (BOP) MANUFACTURING, SHOP TEST MV CABLES BZK | Sat Aug 26 08:00:00 IDT 2017 | Sat May 12 17:00:00 IDT 2018 | Fri Aug 25 08:00:00 IDT 2017 | Tue Jul 10 17:00:00 IDT 2018 |  | COMPLETED
1173 | TT_TASK | (BOP) FINAL CHECK BEFORE SHIPMENT MV CABLES BZK | Mon Jun 18 08:00:00 IDT 2018 | Sun Jul 01 17:00:00 IDT 2018 | Wed Jun 27 08:00:00 IDT 2018 | Tue Jul 10 17:00:00 IDT 2018 |  | COMPLETED
1174 | TT_TASK | (BOP) TRANSPORT MV CABLES BZK | Mon Jul 02 08:00:00 IDT 2018 | Thu Aug 30 17:00:00 IDT 2018 | Fri Aug 03 08:00:00 IDT 2018 | Mon Aug 20 17:00:00 IDT 2018 |  | COMPLETED
1177 | TT_TASK | (BOP) TECHNICAL CLARIFICATION HYDROGEN SUPPLY SYSTEM | Mon May 01 08:00:00 IDT 2017 | Sun Jun 11 17:00:00 IDT 2017 | Sat Apr 22 08:00:00 IDT 2017 | Fri Jun 02 17:00:00 IDT 2017 |  | COMPLETED
1178 | TT_TASK | (BOP) BASIC DESIGN, SPECIFICATION HYDROGEN SUPPLY SYSTEM (incl. FSD COMPLIANCE CHECK) | Wed Jun 28 08:00:00 IDT 2017 | Thu Sep 07 17:00:00 IDT 2017 | Sat Jun 03 08:00:00 IDT 2017 | Sun Aug 13 17:00:00 IDT 2017 |  | COMPLETED
1180 | TT_TASK | (BOP) QUOTATION STAGE HYDROGEN SUPPLY SYSTEM | Fri Sep 15 08:00:00 IDT 2017 | Thu Oct 26 17:00:00 IDT 2017 | Mon Aug 14 08:00:00 IDT 2017 | Sun Sep 24 17:00:00 IDT 2017 |  | COMPLETED
1182 | TT_TASK | (BOP) MANUFACTURING, SHOP TEST HYDROGEN SUPPLY SYSTEM | Tue Sep 26 08:00:00 IDT 2017 | Sat Jun 02 17:00:00 IDT 2018 | Mon Sep 25 08:00:00 IDT 2017 | Fri May 11 17:00:00 IDT 2018 |  | COMPLETED
1184 | TT_TASK | (BOP) TRANSPORT HYDROGEN SUPPLY SYSTEM | Mon Jul 09 08:00:00 IDT 2018 | Thu Sep 06 17:00:00 IDT 2018 | Sat May 12 08:00:00 IDT 2018 | Fri Jul 13 17:00:00 IDT 2018 |  | COMPLETED
1187 | TT_TASK | (BOP) TECHNICAL CLARIFICATION CO2 SUPPLY SYSTEM | Mon May 01 08:00:00 IDT 2017 | Sun Jun 11 17:00:00 IDT 2017 | Sat Apr 22 08:00:00 IDT 2017 | Fri Jun 02 17:00:00 IDT 2017 |  | COMPLETED
1188 | TT_TASK | (BOP) BASIC DESIGN, SPECIFICATION CO2 SUPPLY SYSTEM (incl. FSD COMPLIANCE CHECK) | Wed Jun 28 08:00:00 IDT 2017 | Thu Sep 07 17:00:00 IDT 2017 | Sat Jun 03 08:00:00 IDT 2017 | Sun Aug 13 17:00:00 IDT 2017 |  | COMPLETED
1190 | TT_TASK | (BOP) QUOTATION STAGE CO2 SUPPLY SYSTEM | Fri Sep 15 08:00:00 IDT 2017 | Thu Oct 26 17:00:00 IDT 2017 | Mon Aug 14 08:00:00 IDT 2017 | Sun Sep 24 17:00:00 IDT 2017 |  | COMPLETED
1192 | TT_TASK | (BOP) MANUFACTURING, SHOP TEST CO2 SUPPLY SYSTEM | Tue Sep 26 08:00:00 IDT 2017 | Sat Jun 02 17:00:00 IDT 2018 | Mon Sep 25 08:00:00 IDT 2017 | Fri May 11 17:00:00 IDT 2018 |  | COMPLETED
1194 | TT_TASK | (BOP) TRANSPORT CO2 SUPPLY SYSTEM | Mon Jul 09 08:00:00 IDT 2018 | Thu Sep 06 17:00:00 IDT 2018 | Sat May 12 08:00:00 IDT 2018 | Fri Jul 13 17:00:00 IDT 2018 |  | COMPLETED
1197 | TT_TASK | (BOP) TECHNICAL CLARIFICATION FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | Tue Feb 14 08:00:00 IST 2017 | Mon Mar 20 17:00:00 IST 2017 | Sat Feb 04 08:00:00 IST 2017 | Fri Mar 10 17:00:00 IST 2017 |  | COMPLETED
1198 | TT_TASK | (BOP) QUOTATION STAGE FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | Tue Jun 20 08:00:00 IDT 2017 | Mon Aug 14 17:00:00 IDT 2017 | Fri May 26 08:00:00 IDT 2017 | Sun Aug 20 17:00:00 IDT 2017 |  | COMPLETED
1200 | TT_TASK | (BOP) BASIC DESIGN, PREPARATION RFQ FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | Sun Mar 26 08:00:00 IDT 2017 | Sat May 13 17:00:00 IDT 2017 | Sat Mar 11 08:00:00 IST 2017 | Thu May 25 17:00:00 IDT 2017 |  | COMPLETED
1201 | TT_TASK | (BOP) DETAIL DESIGN, MANUFACTURING, SHOP TEST FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | Wed Sep 13 08:00:00 IDT 2017 | Wed Jun 27 17:00:00 IDT 2018 | Mon Aug 21 08:00:00 IDT 2017 | Wed Mar 28 17:00:00 IDT 2018 |  | COMPLETED
1203 | TT_TASK | (BOP) TRANSPORT FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | Tue Jul 03 08:00:00 IDT 2018 | Fri Aug 31 17:00:00 IDT 2018 | Sun May 27 08:00:00 IDT 2018 | Sat Jun 30 17:00:00 IDT 2018 |  | COMPLETED
1207 | TT_TASK | (BOP) BASIC DESIGN, PREPARATION RFQ SEAWATER BOOSTER PUMP | Wed May 03 08:00:00 IDT 2017 | Tue Jul 04 17:00:00 IDT 2017 | Mon Apr 03 08:00:00 IDT 2017 | Sun Jun 04 17:00:00 IDT 2017 |  | COMPLETED
1208 | TT_TASK | (BOP) QUOTATION STAGE SEAWATER BOOSTER PUMP | Fri Jun 30 08:00:00 IDT 2017 | Thu Aug 24 17:00:00 IDT 2017 | Mon Jun 05 08:00:00 IDT 2017 | Thu Aug 31 17:00:00 IDT 2017 |  | COMPLETED
1210 | TT_TASK | (BOP) TECHNICAL CLARIFICATION SEAWATER BOOSTER PUMP | Wed Mar 01 08:00:00 IST 2017 | Tue Apr 04 17:00:00 IDT 2017 | Mon Feb 27 08:00:00 IST 2017 | Sun Apr 02 17:00:00 IDT 2017 |  | COMPLETED
1211 | TT_TASK | (BOP) DETAIL DESIGN, MANUFACTURING, SHOP TESTSEAWATER BOOSTER PUMP | Mon Mar 26 08:00:00 IDT 2018 | Thu Aug 09 17:00:00 IDT 2018 | Mon Feb 26 08:00:00 IST 2018 | Thu Nov 15 17:00:00 IST 2018 |  | COMPLETED
1213 | TT_TASK | (BOP) TRANSPORT SEAWATER BOOSTER PUMP | Sun Aug 19 08:00:00 IDT 2018 | Sat Oct 06 17:00:00 IDT 2018 | Fri Nov 23 08:00:00 IST 2018 | Tue Nov 27 17:00:00 IST 2018 |  | COMPLETED
1217 | TT_TASK | (BOP) BASIC DESIGN, SPECIFICATION COMPRESSED AIR INTERCONNECTION SYSTEM | Wed Jul 19 08:00:00 IDT 2017 | Tue Aug 29 17:00:00 IDT 2017 | Sat Jun 24 08:00:00 IDT 2017 | Fri Aug 04 17:00:00 IDT 2017 |  | COMPLETED
1218 | TT_TASK | (BOP) TECHNICAL CLARIFICATION COMPRESSED AIR INTERCONNECTION SYSTEM | Thu Jun 01 08:00:00 IDT 2017 | Wed Jul 12 17:00:00 IDT 2017 | Sat May 13 08:00:00 IDT 2017 | Fri Jun 23 17:00:00 IDT 2017 |  | COMPLETED
1220 | TT_TASK | (BOP) QUOTATION STAGE COMPRESSED AIR INTERCONNECTION SYSTEM | Wed Sep 06 08:00:00 IDT 2017 | Tue Oct 17 17:00:00 IDT 2017 | Sat Aug 05 08:00:00 IDT 2017 | Sun Sep 24 17:00:00 IDT 2017 |  | COMPLETED
1222 | TT_TASK | (BOP) MANUFACTURING, SHOP TEST COMPRESSED AIR INTERCONNECTION SYSTEM | Tue Sep 26 08:00:00 IDT 2017 | Sat Jul 07 17:00:00 IDT 2018 | Mon Sep 25 08:00:00 IDT 2017 | Tue Jul 31 17:00:00 IDT 2018 |  | COMPLETED
1224 | TT_TASK | (BOP) TRANSPORT COMPRESSED AIR INTERCONNECTION SYSTEM | Sat Aug 04 08:00:00 IDT 2018 | Tue Oct 02 17:00:00 IDT 2018 | Wed Aug 01 08:00:00 IDT 2018 | Wed Aug 15 17:00:00 IDT 2018 |  | COMPLETED
1227 | TT_TASK | (BOP) BASIC DESIGN, SPECIFICATION WATER PIPEWORK SYSTEM | Mon May 08 08:00:00 IDT 2017 | Sun Jul 02 17:00:00 IDT 2017 | Sat Apr 08 08:00:00 IDT 2017 | Tue Jun 27 17:00:00 IDT 2017 |  | COMPLETED
1229 | TT_TASK | (BOP) QUOTATION STAGE WATER PIPEWORK SYSTEM | Thu Jul 27 08:00:00 IDT 2017 | Wed Sep 06 17:00:00 IDT 2017 | Wed Jun 28 08:00:00 IDT 2017 | Sun Sep 24 17:00:00 IDT 2017 |  | COMPLETED
1231 | TT_TASK | (BOP) TECHNICAL CLARIFICATION WATER PIPEWORK SYSTEM | Wed Mar 01 08:00:00 IST 2017 | Tue Apr 11 17:00:00 IDT 2017 | Sat Feb 25 08:00:00 IST 2017 | Fri Apr 07 17:00:00 IDT 2017 |  | COMPLETED
1232 | TT_TASK | (BOP) MANUFACTURING, SHOP TEST WATER PIPEWORK SYSTEM | Tue Sep 26 08:00:00 IDT 2017 | Tue Jul 03 17:00:00 IDT 2018 | Mon Sep 25 08:00:00 IDT 2017 | Fri May 11 17:00:00 IDT 2018 |  | COMPLETED
1234 | TT_TASK | (BOP) TRANSPORT WATER PIPEWORK SYSTEM | Sun Jul 15 08:00:00 IDT 2018 | Wed Sep 12 17:00:00 IDT 2018 | Sat May 12 08:00:00 IDT 2018 | Fri Jul 13 17:00:00 IDT 2018 |  | COMPLETED
1236 | TT_TASK | (BOP) TECHNICAL CLARIFICATION NOX WATER INJECTION PUMP | Wed Mar 01 08:00:00 IST 2017 | Tue Apr 11 17:00:00 IDT 2017 | Sat Feb 25 08:00:00 IST 2017 | Fri Apr 07 17:00:00 IDT 2017 |  | COMPLETED
1237 | TT_TASK | (BOP) BASIC DESIGN, SPECIFICATION NOX WATER INJECTION PUMP | Mon May 08 08:00:00 IDT 2017 | Sun Jul 02 17:00:00 IDT 2017 | Sat Apr 08 08:00:00 IDT 2017 | Fri Jun 02 17:00:00 IDT 2017 |  | COMPLETED
1239 | TT_TASK | (BOP) QUOTATION STAGE NOX WATER INJECTION PUMP | Wed Jun 28 08:00:00 IDT 2017 | Tue Aug 08 17:00:00 IDT 2017 | Sat Jun 03 08:00:00 IDT 2017 | Thu Aug 31 17:00:00 IDT 2017 |  | COMPLETED
1241 | TT_TASK | (BOP) MANUFACTURING, SHOP TEST NOX WATER INJECTION PUMP | Fri Jan 26 08:00:00 IST 2018 | Sat Aug 11 17:00:00 IDT 2018 | Wed Dec 27 08:00:00 IST 2017 | Mon Oct 15 17:00:00 IDT 2018 |  | COMPLETED
1243 | TT_TASK | (BOP) TRANSPORT NOX WATER INJECTION PUMP | Sun Aug 19 08:00:00 IDT 2018 | Sat Oct 06 17:00:00 IDT 2018 | Fri Oct 19 08:00:00 IDT 2018 | Thu Oct 25 17:00:00 IDT 2018 |  | COMPLETED
1433 | TT_TASK | BA5 - Approval to GBP Amendment CW System - Diversion Culvert, Pump Station, Discharge Culvert, Shaft F, etc {4a1} | Thu Jul 06 08:00:00 IDT 2017 | Fri Aug 04 16:00:00 IDT 2017 | Tue Jun 27 08:00:00 IDT 2017 | Tue Jul 25 16:00:00 IDT 2017 |  | COMPLETED
1437 | TT_TASK | BA5 - (1st) BD Approval to Cooling Water System Permanent Drainage Plan {4d} | Wed Aug 09 08:00:00 IDT 2017 | Sun Oct 08 16:00:00 IDT 2017 | Mon Jun 26 08:00:00 IDT 2017 | Tue Aug 22 16:00:00 IDT 2017 |  | COMPLETED
1438 | TT_TASK | BA8 - (1st) BD Consent to Cooling Water System Permanent Drainage Plan {4d} - actual dates TBC | Sat Aug 26 08:00:00 IDT 2017 | Sun Sep 24 16:00:00 IDT 2017 | Wed Aug 23 08:00:00 IDT 2017 | Thu Sep 21 16:00:00 IDT 2017 |  | COMPLETED
1439 | TT_TASK | BA5 - Approval to (Minor) Amendment for Cooling Water System Permanent Drainage Plan {4di} | Thu Mar 01 08:00:00 IST 2018 | Mon Apr 30 16:00:00 IDT 2018 | Thu Mar 29 08:00:00 IDT 2018 | Wed Apr 18 16:00:00 IDT 2018 |  | COMPLETED
1441 | TT_TASK | BA5 - Approval to 2nd (Minor) Amendment for Cooling Water System Permanent Drainage Plan {4dii} | Sat Jun 01 08:00:00 IDT 2019 | Sat Jun 01 16:00:00 IDT 2019 | Thu May 02 08:00:00 IDT 2019 | Mon May 27 16:00:00 IDT 2019 |  | COMPLETED
1442 | TT_TASK | BA8 - Consent to 2nd (Minor) Amendment for Cooling Water System Permanent Drainage Plan {4dii} | Fri Aug 02 08:00:00 IDT 2019 | Thu Aug 29 16:00:00 IDT 2019 | Thu Jun 13 08:00:00 IDT 2019 | Mon Jul 22 16:00:00 IDT 2019 |  | COMPLETED
1443 | TT_TASK | BA5 - (1st) BD Approval for Permanent Works for Discharge Box Culvert {4c1} | Wed Aug 23 08:00:00 IDT 2017 | Sun Oct 22 16:00:00 IDT 2017 | Fri Jul 14 08:00:00 IDT 2017 | Tue Sep 12 16:00:00 IDT 2017 |  | COMPLETED
1444 | TT_TASK | BA8 - (1st) BD Consent to Permanent Works for Discharge Box Culvert {4c1} - actual dates TBC | Wed Sep 13 08:00:00 IDT 2017 | Thu Oct 12 16:00:00 IDT 2017 | Wed Sep 13 08:00:00 IDT 2017 | Thu Oct 12 16:00:00 IDT 2017 |  | COMPLETED
1445 | TT_TASK | BA5 - Approval to (Minor) Amendment for Permanent Works for Discharge Box Culvert {4c1i}[WITHDRAWN] | Fri Dec 08 08:00:00 IST 2017 | Tue Jan 02 16:00:00 IST 2018 | Fri Dec 08 08:00:00 IST 2017 | Tue Jan 02 16:00:00 IST 2018 |  | COMPLETED
1446 | TT_TASK | BA5 - Approval to (Minor) Amendment for Permanent Works for Discharge Box Culvert {4c1i(r1)}[RESUBMISSION#1] | Tue Mar 06 08:00:00 IST 2018 | Thu Apr 05 16:00:00 IDT 2018 | Tue Jan 02 08:00:00 IST 2018 | Thu Jan 25 16:00:00 IST 2018 |  | COMPLETED
1447 | TT_TASK | BA8 - Consent to (Major) Amendment for Permanent Works for Discharge Box Culvert {4c1i(r1)} - actual date TBC | Fri Apr 06 08:00:00 IDT 2018 | Sat May 05 16:00:00 IDT 2018 | Fri Jan 26 08:00:00 IST 2018 | Sat Feb 24 16:00:00 IST 2018 |  | COMPLETED
1448 | TT_TASK | BA5 - (1st) BD Approval to Permanent Works for Pump Station, Diversion Culvert {4c1} | Mon Aug 07 08:00:00 IDT 2017 | Fri Oct 06 16:00:00 IDT 2017 | Fri Jul 14 08:00:00 IDT 2017 | Tue Sep 12 16:00:00 IDT 2017 |  | COMPLETED
1449 | TT_TASK | BA8 - (1st) BD Consent to Permanent Works for Pump Station, Diversion Culvert {4c1} - actual dates TBC | Wed Sep 13 08:00:00 IDT 2017 | Thu Oct 12 16:00:00 IDT 2017 | Wed Sep 13 08:00:00 IDT 2017 | Thu Oct 12 16:00:00 IDT 2017 |  | COMPLETED
1450 | TT_TASK | BA5 - Approval to (Minor) Amendment for Permanent Works for Pump Station, Diversion Culvert {4c1i}[WITHDRAWN] | Fri Dec 08 08:00:00 IST 2017 | Sun Jan 07 16:00:00 IST 2018 | Fri Dec 08 08:00:00 IST 2017 | Tue Jan 02 16:00:00 IST 2018 |  | COMPLETED
1451 | TT_TASK | BA5 - Approval to (Minor) Amendment for Permanent Works for Pump Sttn, Diver.Culvert {4c1i(r1)}[RESUMIT#1] | Mon Feb 26 08:00:00 IST 2018 | Wed Mar 28 16:00:00 IDT 2018 | Tue Jan 02 08:00:00 IST 2018 | Thu Jan 25 16:00:00 IST 2018 |  | COMPLETED
1452 | TT_TASK | BA8 - Consent to (Major) Amendment for Permanent Works for Pump Station, Diversion Culvert {4c1i(r1)} | Mon Feb 26 08:00:00 IST 2018 | Tue Mar 27 16:00:00 IDT 2018 | Fri Jan 26 08:00:00 IST 2018 | Sat Feb 24 16:00:00 IST 2018 |  | COMPLETED
1453 | TT_TASK | BA5 - (1st) BD Aprpoval to Permanent works for Seal Pit (4c2} | Wed Aug 23 08:00:00 IDT 2017 | Sun Oct 22 16:00:00 IDT 2017 | Fri Aug 18 08:00:00 IDT 2017 | Mon Oct 16 16:00:00 IDT 2017 |  | COMPLETED
1454 | TT_TASK | BA8 - (1st) BD Consent to Permanent works for Seal Pit {4c2} - actual dates TBC | Wed Oct 18 08:00:00 IDT 2017 | Thu Nov 16 16:00:00 IST 2017 | Tue Oct 17 08:00:00 IDT 2017 | Wed Nov 15 16:00:00 IST 2017 |  | COMPLETED
1455 | TT_TASK | BA5 - Approval to (Major) Amendment for Permanent works for Seal Pit {4c2i} | Mon Feb 26 08:00:00 IST 2018 | Wed Mar 28 16:00:00 IDT 2018 | Fri Jan 19 08:00:00 IST 2018 | Tue Feb 13 16:00:00 IST 2018 |  | COMPLETED
1456 | TT_TASK | BA8 - Consent to (Major) Amendment for Permanent works for Seal Pit {4c2i} - actual dates TBC | Thu Mar 29 08:00:00 IDT 2018 | Fri Apr 27 16:00:00 IDT 2018 | Wed Feb 14 08:00:00 IST 2018 | Thu Mar 15 16:00:00 IST 2018 |  | COMPLETED
1457 | TT_TASK | BA5 - (1st) BD Approval to Permanent works for Shaft F {4c2} | Wed Aug 23 08:00:00 IDT 2017 | Sun Oct 22 16:00:00 IDT 2017 | Fri Aug 18 08:00:00 IDT 2017 | Mon Oct 16 16:00:00 IDT 2017 |  | COMPLETED
1458 | TT_TASK | BA8 - (1st) BD Consent to Permanent works for Shaft F {4c2} - actual dates TBC | Wed Oct 18 08:00:00 IDT 2017 | Thu Nov 16 16:00:00 IST 2017 | Tue Oct 17 08:00:00 IDT 2017 | Wed Nov 15 16:00:00 IST 2017 |  | COMPLETED
1459 | TT_TASK | BA5 - Approval to (Major) Amendment for Permanent works for Shaft F {4c2i} | Mon Feb 26 08:00:00 IST 2018 | Wed Mar 28 16:00:00 IDT 2018 | Fri Jan 19 08:00:00 IST 2018 | Tue Feb 13 16:00:00 IST 2018 |  | COMPLETED
1460 | TT_TASK | BA8 - Consent to (Major) Amendment for Permanent works for Shaft F {4c2i} | Thu Mar 29 08:00:00 IDT 2018 | Fri Apr 27 16:00:00 IDT 2018 | Wed Feb 14 08:00:00 IST 2018 | Thu Mar 15 16:00:00 IST 2018 |  | COMPLETED
1462 | TT_TASK | BA5 - (1st) BD Approval to Temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only) {4b4} | Sun Jun 11 08:00:00 IDT 2017 | Wed Aug 09 16:00:00 IDT 2017 | Tue Apr 11 08:00:00 IDT 2017 | Thu Jun 15 16:00:00 IDT 2017 |  | COMPLETED
1463 | TT_TASK | BA8 - (1st) BD Consent toTemporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only) {4b4} | Mon Aug 07 08:00:00 IDT 2017 | Sun Sep 03 16:00:00 IDT 2017 | Fri Jun 16 08:00:00 IDT 2017 | Thu Jul 13 16:00:00 IDT 2017 |  | COMPLETED
1464 | TT_TASK | BA5 & BA8 - BD Amendment (Type II) - Shaft A Location Shift {4b4-1} | Mon Aug 07 08:00:00 IDT 2017 | Sun Sep 03 16:00:00 IDT 2017 | Mon Jul 10 08:00:00 IDT 2017 | Mon Aug 07 16:00:00 IDT 2017 |  | COMPLETED
1465 | TT_TASK | BA5 - (1st) BD Approval to Temporary works for Shaft D (with LCAL's proposal incorporated) [DISAPPROVED] {4b3(r1)} | Wed Aug 16 08:00:00 IDT 2017 | Sun Oct 15 16:00:00 IDT 2017 | Wed Jun 21 08:00:00 IDT 2017 | Wed Aug 16 16:00:00 IDT 2017 |  | COMPLETED
1468 | TT_TASK | BA8 - (1st) BD Consent to Temporary works for Shaft F and Double Pipe Trench (for Shaft F Wall only) {4b1(r)} | Mon Jul 03 08:00:00 IDT 2017 | Mon Jul 03 08:00:00 IDT 2017 | Fri May 05 08:00:00 IDT 2017 | Wed Jun 21 16:00:00 IDT 2017 |  | COMPLETED
1470 | TT_TASK | BA8 - (1st) BD Consent to Temp works for Shaft F & Double Pipe Trench (Alternative for Zone A Sheet Pile) {4b1-alt A} | Mon Jul 03 08:00:00 IDT 2017 | Mon Jul 03 08:00:00 IDT 2017 | Wed May 24 08:00:00 IDT 2017 | Wed Jun 21 16:00:00 IDT 2017 |  | COMPLETED
1471 | TT_TASK | BA5 - Amendment to Temp works for Shaft F & Double Pipe Trench - Pipe Jacking [DISAPPROVED] {4b1-1} | Mon Jul 03 08:00:00 IDT 2017 | Thu Aug 31 16:00:00 IDT 2017 | Fri May 19 08:00:00 IDT 2017 | Mon Jul 10 08:00:00 IDT 2017 |  | COMPLETED
1472 | TT_TASK | BA5 - Resubmission of Amendment (Type II) for Shaft F & DPT master construction sequence {4b1-1(r)} | Thu Jun 22 08:00:00 IDT 2017 | Mon Aug 21 16:00:00 IDT 2017 | Mon Jul 24 08:00:00 IDT 2017 | Tue Aug 22 16:00:00 IDT 2017 |  | COMPLETED
1473 | TT_TASK | BA5 - Resubmission for Shaft F(Ring Beam) & Double Pipe Trench Amendment - Pipe Jacking {4b1-2} | Thu Sep 07 08:00:00 IDT 2017 | Mon Nov 06 16:00:00 IST 2017 | Mon Sep 18 08:00:00 IDT 2017 | Wed Nov 22 16:00:00 IST 2017 |  | COMPLETED
1474 | TT_TASK | BA8 - Consent for Shaft F(Ring Beam) & Double Pipe Trench Amendment - Pipe Jacking {4b1-2} | Tue Dec 05 08:00:00 IST 2017 | Thu Jan 04 16:00:00 IST 2018 | Tue Nov 28 08:00:00 IST 2017 | Thu Dec 28 16:00:00 IST 2017 |  | COMPLETED
1478 | TT_TASK | BA5 - Approval to (Major) Amendment for GBP for SCW Pump Sump A&A {5a1} AF-TBC | Mon Apr 23 08:00:00 IDT 2018 | Wed May 23 16:00:00 IDT 2018 | Tue Mar 06 08:00:00 IST 2018 | Thu Apr 05 16:00:00 IDT 2018 |  | COMPLETED
1479 | TT_TASK | BA5 - (1st) BD Approval to Drainage Plan for SCW and Culvert Modification {5d} | Wed Aug 09 08:00:00 IDT 2017 | Sun Oct 08 16:00:00 IDT 2017 | Mon Jun 26 08:00:00 IDT 2017 | Tue Aug 22 16:00:00 IDT 2017 |  | COMPLETED
1480 | TT_TASK | BA8 - (1st) BD Consent to Draiange Plan for SCW and Culvert Modification {5d} - actual dates TBC | Mon Aug 28 08:00:00 IDT 2017 | Sun Sep 24 16:00:00 IDT 2017 | Thu Mar 08 08:00:00 IST 2018 | Fri Apr 06 16:00:00 IDT 2018 |  | COMPLETED
1481 | TT_TASK | BA5 - Approval to (Major) Amendment for Drainage Plan for SCW and Culvert Modification {5di} actual dates TBC | Sun Dec 10 08:00:00 IST 2017 | Thu Feb 08 16:00:00 IST 2018 | Fri Mar 30 08:00:00 IDT 2018 |  | 2920.0 | IN_PROGRESS
1482 | TT_TASK | BA5 - (1st) BD Approval to Permanent works for SCW and Culvert Modification {5c} [DISAPPROVED] | Fri Nov 10 08:00:00 IST 2017 | Tue Jan 09 16:00:00 IST 2018 | Fri Dec 01 08:00:00 IST 2017 | Mon Jan 22 16:00:00 IST 2018 |  | COMPLETED
1483 | TT_TASK | BA8 - (1st) BD Consent to Permanent works for SCW and Culvert Modification {5c} [CANCELLED] | Mon Apr 30 08:00:00 IDT 2018 | Tue May 29 16:00:00 IDT 2018 | Mon Jan 22 08:00:00 IST 2018 | Mon Jan 22 16:00:00 IST 2018 |  | COMPLETED
1484 | TT_TASK | BA5 - Approval to (Major) Amendment for Permanent works for SCW and Culvert Modification {5c(r)} [RESUBMISSION] | Mon Apr 23 08:00:00 IDT 2018 | Fri Jun 22 16:00:00 IDT 2018 | Mon Mar 05 08:00:00 IST 2018 | Fri May 11 16:00:00 IDT 2018 |  | COMPLETED
1485 | TT_TASK | BA8 - Consent to (Major) Amendment for Permanent works for SCW and Culvert Modification {5c(r)} [RESUBMISSION] | Sun Mar 31 08:00:00 IDT 2019 | Mon Apr 29 16:00:00 IDT 2019 | Fri Nov 23 08:00:00 IST 2018 | Wed Dec 19 16:00:00 IST 2018 |  | COMPLETED
1487 | TT_TASK | BA5 - (1st) BD Approval to Temporary works for SCW and Culvert Modification (Wall only) [DISAPPROVED] {5b1} | Wed May 31 08:00:00 IDT 2017 | Tue Jul 18 16:00:00 IDT 2017 | Wed May 24 08:00:00 IDT 2017 | Tue Jul 11 16:00:00 IDT 2017 |  | COMPLETED
1488 | TT_TASK | BA5 - (1st) BD Approval to Temp works for SCW & Culvert Modification (Resubmit incl wall, excav.& anchor)(Wet){5b1(r)} | Tue Aug 29 08:00:00 IDT 2017 | Sat Oct 28 16:00:00 IDT 2017 | Wed Sep 20 08:00:00 IDT 2017 | Fri Nov 24 16:00:00 IST 2017 |  | COMPLETED
1489 | TT_TASK | BA8 - (1st) BD Consent to Temp works for SCW & Culvert Modification (Resubmit incl wall, excav.& anchor)(Wet){5b1(r)} | Mon Feb 26 08:00:00 IST 2018 | Tue Mar 27 16:00:00 IDT 2018 | Mon Jan 29 08:00:00 IST 2018 | Mon Feb 26 16:00:00 IST 2018 |  | COMPLETED
1492 | TT_TASK | BA5 - (1st) BD Approval to GBP for Outfall Modification (incl' works outside lot boundary) [p.r.t.Act.ID.CWS-2BA5] {6a} | Mon Aug 07 08:00:00 IDT 2017 | Mon Sep 04 16:00:00 IDT 2017 | Tue Jun 27 08:00:00 IDT 2017 | Tue Jul 25 16:00:00 IDT 2017 |  | COMPLETED
1493 | TT_TASK | BA5 - (1st) BD Approval to Permenent Works for Outfall Modification (incl' works outside lot boundary) {6c} [WITHDRAWN] | Fri Dec 08 08:00:00 IST 2017 | Tue Feb 06 16:00:00 IST 2018 | Tue Jan 02 08:00:00 IST 2018 | Thu Jan 25 16:00:00 IST 2018 |  | COMPLETED
1494 | TT_TASK | BA8 - (1st) BD Consent to Permanent Works for Outfall Modification (incl' works outside lot boundary) {6c} | Mon Feb 26 08:00:00 IST 2018 | Tue Mar 27 16:00:00 IDT 2018 | Fri Jan 26 08:00:00 IST 2018 | Sat Feb 24 16:00:00 IST 2018 |  | COMPLETED
1495 | TT_TASK | BA5 - Approval to (Major) Amendment for Permenent Works for Outfall Modif (incl' works outside lot boundary){6ci} AD-TBC | Sat Apr 28 08:00:00 IDT 2018 | Wed Jun 27 16:00:00 IDT 2018 | Thu Mar 08 08:00:00 IST 2018 | Mon May 07 16:00:00 IDT 2018 |  | COMPLETED
1496 | TT_TASK | BA8 - Consent to (Major) Amendment for Permanent Works for Outfall Modif (incl' works outside lot boundary) {6ci} AD-TBC | Sun Jun 10 08:00:00 IDT 2018 | Mon Jul 09 16:00:00 IDT 2018 | Tue May 08 08:00:00 IDT 2018 | Mon Aug 06 16:00:00 IDT 2018 |  | COMPLETED
1498 | TT_TASK | BA5 - (1st) BD Approval to Temp.Works for Outfall Modif (incl' works outside lot boundary) {6b incl in 4b2-2}[APPROVED] | Mon Feb 26 08:00:00 IST 2018 | Fri Apr 27 16:00:00 IDT 2018 | Wed Feb 14 08:00:00 IST 2018 | Tue Apr 24 16:00:00 IDT 2018 |  | COMPLETED
1499 | TT_TASK | BA8 - (1st) BD Consent to Temp.Works for Outfall Modif (incl' works outside lot boundary) {6b incl in 4b2-2} | Mon Jun 11 08:00:00 IDT 2018 | Sun Jul 08 16:00:00 IDT 2018 | Fri May 04 08:00:00 IDT 2018 | Fri Jul 06 16:00:00 IDT 2018 |  | COMPLETED
1504 | TT_TASK | BA5 - (1st) BD Approval to Drainage Plans for Power Island Areas {8a} | Mon Jul 10 08:00:00 IDT 2017 | Wed Aug 30 16:00:00 IDT 2017 | Wed May 10 08:00:00 IDT 2017 | Fri Jun 30 16:00:00 IDT 2017 |  | COMPLETED
1505 | TT_TASK | BA8 - (1st) BD Consent to Drainage Plans for Power Island Areas {8a} | Mon Aug 07 08:00:00 IDT 2017 | Tue Sep 05 16:00:00 IDT 2017 | Tue Aug 01 08:00:00 IDT 2017 | Thu Aug 31 16:00:00 IDT 2017 |  | COMPLETED
1508 | TT_TASK | BA5 - Approval to 2nd Amendment (Type II) for substructures of HRSG and Stack {7b2} | Mon Aug 07 08:00:00 IDT 2017 | Wed Sep 06 16:00:00 IDT 2017 | Fri Jun 30 08:00:00 IDT 2017 | Wed Jul 26 16:00:00 IDT 2017 |  | COMPLETED
1509 | TT_TASK | BA8 - Consent to 2nd Amendment (Type II) for substructures of HRSG and Stack {7b2} | Wed Sep 06 08:00:00 IDT 2017 | Thu Oct 05 16:00:00 IDT 2017 | Fri Jun 30 08:00:00 IDT 2017 | Wed Jul 26 16:00:00 IDT 2017 |  | COMPLETED
1511 | TT_TASK | BA5 - Approval to Resubmission of Structural Plan (Package 1) for Outdoor Equipment foundations and plinths {7f(r)} | Mon Aug 07 08:00:00 IDT 2017 | Fri Oct 06 16:00:00 IDT 2017 | Mon Jul 31 08:00:00 IDT 2017 | Wed Sep 27 16:00:00 IDT 2017 |  | COMPLETED
1512 | TT_TASK | BA8 - (1st) BD Consent to Structural Plan (Package 1) for Outdoor Equipment foundations and plinths {7f(r)} | Sat Sep 30 08:00:00 IDT 2017 | Sun Oct 29 16:00:00 IST 2017 | Thu Feb 08 08:00:00 IST 2018 | Wed Mar 07 16:00:00 IST 2018 |  | COMPLETED
1513 | TT_TASK | BA5 - BD Approval to Structural Plan (Package 2) for Outdoor Equipment foundations and plinths {7g} | Mon Oct 30 08:00:00 IST 2017 | Fri Dec 29 16:00:00 IST 2017 | Mon Oct 30 08:00:00 IST 2017 | Fri Dec 29 16:00:00 IST 2017 |  | COMPLETED
1514 | TT_TASK | BA8 - BD Consent to Structural Plan (Package 2) for Outdoor Equipment foundations and plinths {7g} | Tue Apr 03 08:00:00 IDT 2018 | Wed May 02 16:00:00 IDT 2018 | Thu Feb 08 08:00:00 IST 2018 | Wed Mar 07 16:00:00 IST 2018 |  | COMPLETED
1517 | TT_TASK | BA5 - Approval to 2nd Amendment (Type II) for pile caps and tie beams within Turbine Hall {7b2} | Mon Aug 07 08:00:00 IDT 2017 | Wed Sep 06 16:00:00 IDT 2017 | Fri Jun 30 08:00:00 IDT 2017 | Wed Jul 26 16:00:00 IDT 2017 |  | COMPLETED
1518 | TT_TASK | BA8 - Consent to 2nd Amendment (Type II) for pile caps and tie beams within Turbine Hall {7b2} | Mon Aug 07 08:00:00 IDT 2017 | Tue Sep 05 16:00:00 IDT 2017 | Fri Jun 30 08:00:00 IDT 2017 | Wed Jul 26 16:00:00 IDT 2017 |  | COMPLETED
1520 | TT_TASK | BA5 - Approval to (2nd) Amendment for superstructures for Turbine Hall {7d2} | Thu Jun 15 08:00:00 IDT 2017 | Fri Jul 14 16:00:00 IDT 2017 | Mon Jun 19 16:00:00 IDT 2017 | Tue Jul 18 16:00:00 IDT 2017 |  | COMPLETED
1521 | TT_TASK | BA5 - Approval to (1st) Amendment for superstructures for Turbine Hall {7d1} | Fri May 26 08:00:00 IDT 2017 | Sat Jun 24 16:00:00 IDT 2017 | Tue Apr 25 16:00:00 IDT 2017 | Wed May 24 16:00:00 IDT 2017 |  | COMPLETED
1523 | TT_TASK | BA8 - Consent to Amendment for superstructures for Turbine Hall {7d2} | Mon Aug 07 08:00:00 IDT 2017 | Tue Sep 05 16:00:00 IDT 2017 | Wed Jul 19 08:00:00 IDT 2017 | Tue Aug 01 16:00:00 IDT 2017 |  | COMPLETED
1525 | TT_TASK | BA5 - (1st) BD Approval to Cladding Plan for Turbine Hall (incl' Switchgear Block) [DISAPPROVED] {7e} | Mon Aug 07 08:00:00 IDT 2017 | Thu Oct 05 16:00:00 IDT 2017 | Tue May 09 08:00:00 IDT 2017 | Tue Jul 04 16:00:00 IDT 2017 |  | COMPLETED
1526 | TT_TASK | BA5 - Approval to Resubmission of Cladding Plan for Turbine Hall (incl' Switchgear Block) [WITHDRWN] {7e(r1)} | Fri Aug 11 08:00:00 IDT 2017 | Tue Oct 10 16:00:00 IDT 2017 | Tue Aug 15 08:00:00 IDT 2017 | Thu Oct 12 16:00:00 IDT 2017 |  | COMPLETED
1527 | TT_TASK | BA5 - Approval to Resubmission of Cladding Plan for Turbine Hall (incl' Switchgear Block) {7e(r2)} | Fri Aug 11 08:00:00 IDT 2017 | Tue Oct 10 16:00:00 IDT 2017 | Thu Oct 12 08:00:00 IDT 2017 | Tue Dec 05 16:00:00 IST 2017 |  | COMPLETED
1528 | TT_TASK | BA5 - Approval to 1st Amendment of Cladding Plan for Turbine Hall (incl' Switchgear Block) {7e(r2)(i)} | Fri Aug 11 08:00:00 IDT 2017 | Tue Oct 10 16:00:00 IDT 2017 | Thu Feb 15 08:00:00 IST 2018 | Thu Mar 15 16:00:00 IST 2018 |  | COMPLETED
1529 | TT_TASK | BA8 - (1st) BD Consent to Cladding Plan for Turbine Hall (incl' Switchgear Block) {7e(r2)} AD-TBC | Fri Mar 16 08:00:00 IST 2018 | Sat Apr 14 16:00:00 IDT 2018 | Fri Mar 16 08:00:00 IST 2018 | Sat Apr 14 16:00:00 IDT 2018 |  | COMPLETED
1535 | TT_TASK | BA5 - Amendment (Minor) for Temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only){4b4-2}[WITHDRAWN] | Fri Nov 03 08:00:00 IST 2017 | Mon Jan 01 16:00:00 IST 2018 | Thu Nov 16 08:00:00 IST 2017 | Mon Dec 11 16:00:00 IST 2017 |  | COMPLETED
1536 | TT_TASK | BA5 - Amendment (Minor) for Temp.works for Shaft A, Pump Station, Diversion Culvert (Wall Only){4b4-2(r1)} [WITHDRAWN] | Mon Nov 27 08:00:00 IST 2017 | Mon Dec 25 16:00:00 IST 2017 | Thu Dec 21 08:00:00 IST 2017 | Tue Jan 02 16:00:00 IST 2018 |  | COMPLETED
1537 | TT_TASK | BA5 - Amendment (Minor) for Temp.works for Shaft A, Pump Sttn, Div. Culvert (Wall Only){4b4-2(r2)} | Mon Nov 27 08:00:00 IST 2017 | Mon Dec 25 16:00:00 IST 2017 | Tue Jan 02 08:00:00 IST 2018 | Tue Jan 30 08:00:00 IST 2018 |  | COMPLETED
1538 | TT_TASK | BA8 - Consent for Temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only){4b4-2(r1)} [N.A.] | Mon Feb 26 08:00:00 IST 2018 | Sun Mar 25 16:00:00 IDT 2018 | Tue Jan 30 08:00:00 IST 2018 | Tue Jan 30 16:00:00 IST 2018 |  | COMPLETED
1539 | TT_TASK | BA5 - Amendment (Major) for Temporary works for Shaft A, Pump Station, Diversion Culvert (Excav & ELS) {4b5}[WITHDRAWN] | Thu Nov 30 08:00:00 IST 2017 | Wed Feb 28 16:00:00 IST 2018 | Tue Dec 05 08:00:00 IST 2017 | Mon Dec 11 16:00:00 IST 2017 |  | COMPLETED
1540 | TT_TASK | BA5 - Amendment (Major) for Temp.works for Shaft A, Pump Station, Diversion Culvert (Excav & ELS) {4b4-3} [WITHDRAWN] | Mon Mar 12 08:00:00 IST 2018 | Fri May 11 16:00:00 IDT 2018 | Wed Feb 14 08:00:00 IST 2018 | Fri Mar 23 08:00:00 IDT 2018 |  | COMPLETED
1541 | TT_TASK | BA5 - Amendment (Minor) for Temp.works for Shaft A, Pump Station, Diversion Culvert (Excav & ELS) {4b4-3(r1)} [APPROVED] | Mon Mar 12 08:00:00 IST 2018 | Tue Apr 10 16:00:00 IDT 2018 | Fri Mar 23 08:00:00 IDT 2018 | Tue Apr 24 08:00:00 IDT 2018 |  | COMPLETED
1542 | TT_TASK | BA5 - Consent for Temporary works for Shaft A, Pump Station, Diversion Culvert (Excav & ELS) {4b4-4} | Sat May 26 08:00:00 IDT 2018 | Fri Jun 22 16:00:00 IDT 2018 | Thu Jun 28 08:00:00 IDT 2018 | Wed Jul 25 16:00:00 IDT 2018 |  | COMPLETED
1543 | TT_TASK | BA5 - Resubmission of Temp works for Shaft D (Wall Only) {4b3(r2)} | Fri Oct 06 08:00:00 IDT 2017 | Mon Dec 04 16:00:00 IST 2017 | Mon Oct 09 08:00:00 IDT 2017 | Fri Dec 15 16:00:00 IST 2017 |  | COMPLETED
1544 | TT_TASK | BA5 - Resubmission of Temp works for Shaft D (Excav & ELS) {4b3(r2)-1} | Mon Apr 23 08:00:00 IDT 2018 | Thu Jun 21 16:00:00 IDT 2018 | Tue Mar 13 08:00:00 IST 2018 | Tue May 15 16:00:00 IDT 2018 |  | COMPLETED
1545 | TT_TASK | BA8 - (1st) Consent for Shaft D (Pipe Pile Wall & Grout Curtain) {4b3(r2)} | Mon Feb 26 08:00:00 IST 2018 | Tue Mar 27 16:00:00 IDT 2018 | Fri Jan 19 08:00:00 IST 2018 | Mon Feb 12 16:00:00 IST 2018 |  | COMPLETED
1546 | TT_TASK | BA8 - Consent for Shaft D (Excav & ELS) {4b3a(r2)-1}[WITHDRAWN] | Thu Jun 14 08:00:00 IDT 2018 | Wed Jul 11 16:00:00 IDT 2018 | Mon May 21 08:00:00 IDT 2018 | Mon Jun 18 16:00:00 IDT 2018 |  | COMPLETED
1547 | TT_TASK | BA5 & BA8 - Amendment (Major) for Temp.works for Shaft E & Discharge Culvert (alt sheet pile)[WITHDRAWN]{4b2-1} | Sat Nov 04 08:00:00 IST 2017 | Sun Dec 03 16:00:00 IST 2017 | Fri Jul 21 08:00:00 IDT 2017 | Fri Sep 08 16:00:00 IDT 2017 |  | COMPLETED
1548 | TT_TASK | BA5 & BA8 - Amendment (Type II) for Temp.works for Shaft E & Discharge Culvert (Wall only){4b2-1(r)} | Fri Oct 06 08:00:00 IDT 2017 | Mon Dec 04 16:00:00 IST 2017 | Fri Oct 06 08:00:00 IDT 2017 | Fri Nov 03 16:00:00 IST 2017 |  | COMPLETED
1549 | TT_TASK | BA5 - Amendment (pipe jacking) for Temp.works for Shaft E & Discharge Culvert (Excav. & ELS){4b2-2) [WITHDRAWN] | Mon Feb 26 08:00:00 IST 2018 | Fri Apr 27 16:00:00 IDT 2018 | Wed Feb 14 08:00:00 IST 2018 | Fri Mar 23 16:00:00 IDT 2018 |  | COMPLETED
1550 | TT_TASK | BA5 - Amendment (pipe jacking) for Temp.works for Shaft E & Discharge Culvert (Excav. & ELS){4b2-2(r1)} {APPROVED] | Mon Feb 26 08:00:00 IST 2018 | Tue Mar 27 16:00:00 IDT 2018 | Fri Mar 23 08:00:00 IDT 2018 | Tue Apr 24 16:00:00 IDT 2018 |  | COMPLETED
1551 | TT_TASK | BA8 - Consent (pipe jacking) for Temp.works for Shaft E & Discharge Culvert (Excav. & ELS){4b2-2(r1)} | Mon Jun 11 08:00:00 IDT 2018 | Sun Jul 08 16:00:00 IDT 2018 | Fri May 04 08:00:00 IDT 2018 | Fri Jul 06 16:00:00 IDT 2018 |  | COMPLETED
1552 | TT_TASK | BA5 & BA8 - Amendment to Zone A Sheet Pile Alternative [WITHDRA WN] {4b1i} | Thu Jun 22 08:00:00 IDT 2017 | Fri Jul 21 16:00:00 IDT 2017 | Fri Jun 23 08:00:00 IDT 2017 | Fri Jul 07 16:00:00 IDT 2017 |  | COMPLETED
1553 | TT_TASK | BA5 - Resub.of (Type II) Amendment for Zone A Sheet Pile Alternative {4b1-alt A-1} [APPROVED AS TYPE I] | Mon Nov 27 08:00:00 IST 2017 | Tue Dec 26 16:00:00 IST 2017 | Mon Jul 24 08:00:00 IDT 2017 | Tue Aug 22 16:00:00 IDT 2017 |  | COMPLETED
1554 | TT_TASK | BA8 - Consnet for Zone A Sheet Pile Alternative {4b1-alt A-1} | Thu Jun 22 08:00:00 IDT 2017 | Wed Jul 19 16:00:00 IDT 2017 | Tue Aug 29 08:00:00 IDT 2017 | Mon Sep 25 16:00:00 IDT 2017 |  | COMPLETED
1555 | TT_TASK | BA5 & BA8 - Shaft F (Type II) Amendment - Delink Effluent Pit {4b1-4} [APPROVED] | Mon Apr 23 08:00:00 IDT 2018 | Tue May 22 16:00:00 IDT 2018 | Thu Mar 08 08:00:00 IST 2018 | Tue Apr 10 16:00:00 IDT 2018 |  | COMPLETED
1556 | TT_TASK | BA5 & BA8 - Shaft F (Type II) Amendment - Increase AAA Level and Pumping Test {4b1-5} [WITHDRAWAL] | Sun May 27 08:00:00 IDT 2018 | Sat Jun 23 16:00:00 IDT 2018 | Thu Apr 26 08:00:00 IDT 2018 | Fri May 18 16:00:00 IDT 2018 |  | COMPLETED
1557 | TT_TASK | BA5 & BA8 - Shaft F (Type II) Amendment - Increase AAA Level and Pumping Test {4b1-5(r1)} | Sun May 27 08:00:00 IDT 2018 | Mon Jun 25 16:00:00 IDT 2018 | Fri May 18 08:00:00 IDT 2018 | Fri Jun 22 16:00:00 IDT 2018 |  | COMPLETED
1558 | TT_TASK | BA5 - Submission of Zone C / Resequencing (originally an Alternative but resubmitted & approved as a Major Rev) {4b1-?} | Sat Jan 26 08:00:00 IST 2019 | Tue Mar 26 16:00:00 IST 2019 | Mon Dec 24 08:00:00 IST 2018 | Wed Mar 06 16:00:00 IST 2019 |  | COMPLETED
1559 | TT_TASK | BA8 - Consent for Zone C / Resequencing {4b1-?} | Sat Apr 27 08:00:00 IDT 2019 | Fri May 24 16:00:00 IDT 2019 | Mon Feb 25 08:00:00 IST 2019 | Fri Mar 22 16:00:00 IST 2019 |  | COMPLETED
1560 | TT_TASK | BA5 - Submission of Zone B Open Cut Alternative {4b1-alt B} [APPROVED] | Thu Jun 22 08:00:00 IDT 2017 | Tue Sep 19 16:00:00 IDT 2017 | Thu Jun 22 08:00:00 IDT 2017 | Fri Aug 18 16:00:00 IDT 2017 |  | COMPLETED
1561 | TT_TASK | BA8 - Consent for Zone B Open Cut Alternative {4b1-alt B} | Tue Jun 26 08:00:00 IDT 2018 | Mon Jul 23 16:00:00 IDT 2018 | Fri May 04 08:00:00 IDT 2018 | Tue Jun 26 16:00:00 IDT 2018 |  | COMPLETED
1563 | TT_TASK | BA5 - Alternative for Temp works for SCW & Culvert Modifi (Wall Only)(Dry){5b1-alt} [DISAPPROVED] | Tue Nov 28 08:00:00 IST 2017 | Fri Jan 26 16:00:00 IST 2018 | Thu Dec 21 08:00:00 IST 2017 | Tue Feb 06 16:00:00 IST 2018 |  | COMPLETED
1564 | TT_TASK | BA5 - Alternative for Temp works for SCW & Culvert Modif (Excav)(Dry){5b1-alt} [DISAPPROVED] | Tue Nov 28 08:00:00 IST 2017 | Fri Jan 26 16:00:00 IST 2018 | Thu Dec 21 08:00:00 IST 2017 | Tue Feb 06 16:00:00 IST 2018 |  | COMPLETED
1567 | TT_TASK | BA5 & BA8 - Amendment for Excav & ELS Plan for Power Island Area (Open Cut)(Phase 1 & 2){7c2i} | Thu Jun 22 08:00:00 IDT 2017 | Tue Sep 19 16:00:00 IDT 2017 | Thu Jun 22 08:00:00 IDT 2017 | Mon Sep 25 16:00:00 IDT 2017 |  | COMPLETED
1568 | TT_TASK | BA8 - Consent for Excav & ELS Plan for Power Island Area (Open Cut)(Phase 3){7c2i} | Thu Jun 22 08:00:00 IDT 2017 | Tue Sep 19 16:00:00 IDT 2017 | Tue Sep 26 08:00:00 IDT 2017 | Fri Oct 20 16:00:00 IDT 2017 |  | COMPLETED
1569 | TT_TASK | BA5 & BA8 -Type II Amendment Power Island Open Cut (Phase 1,2,3) {7c2ii} | Thu Jun 22 08:00:00 IDT 2017 | Tue Sep 19 16:00:00 IDT 2017 | Thu Oct 26 08:00:00 IDT 2017 | Thu Nov 23 16:00:00 IST 2017 |  | COMPLETED
1570 | TT_TASK | BA5 & BA8 -Type II Amendment (for grout curtain) Power Island Open Cut (Phase 1,2,3){7c2iii} | Thu Jun 22 08:00:00 IDT 2017 | Tue Sep 19 16:00:00 IDT 2017 | Fri Dec 15 08:00:00 IST 2017 | Tue Jan 09 16:00:00 IST 2018 |  | COMPLETED
1571 | TT_TASK | BA8 -Consent for Power Island Open Cut (Phase 4){7c2iii}[WITHDRAWN] | Mon Apr 23 08:00:00 IDT 2018 | Sun May 20 16:00:00 IDT 2018 | Fri May 04 08:00:00 IDT 2018 | Wed May 30 16:00:00 IDT 2018 |  | COMPLETED
1575 | TT_TASK | Supervision Plans - Preparation and Submission to RO | Mon May 29 08:00:00 IDT 2017 | Sun Jun 11 16:00:00 IDT 2017 | Mon May 29 08:00:00 IDT 2017 | Sun Jun 11 16:00:00 IDT 2017 |  | COMPLETED
1576 | TT_TASK | Supervision Plans - RO Review and Comment | Mon Jun 12 08:00:00 IDT 2017 | Sun Jun 18 16:00:00 IDT 2017 | Mon Jun 12 08:00:00 IDT 2017 | Sun Jun 18 16:00:00 IDT 2017 |  | COMPLETED
1577 | TT_TASK | Structural Steel Shop Drawing & Calculation - Preparation and Submission to RO (1st round) | Fri Sep 01 08:00:00 IDT 2017 | Thu Sep 28 16:00:00 IDT 2017 | Fri Sep 01 08:00:00 IDT 2017 | Thu Nov 02 16:00:00 IST 2017 |  | COMPLETED
1578 | TT_TASK | Structural Steel Shop Drawing & Calculation - RO Review and Comment (1st round) | Mon Nov 13 08:00:00 IST 2017 | Sun Nov 26 16:00:00 IST 2017 | Fri Nov 03 08:00:00 IST 2017 | Thu Nov 23 16:00:00 IST 2017 |  | COMPLETED
1579 | TT_TASK | Roof Cladding Shop Drawing & Calculation - RO Review and Comment | Mon Feb 26 08:00:00 IST 2018 | Sun Mar 11 16:00:00 IST 2018 | Sat Jan 27 08:00:00 IST 2018 | Mon Feb 05 16:00:00 IST 2018 |  | COMPLETED
1580 | TT_TASK | Roof Cladding Shop Drawing & Calculation - RO Comment and Approval | Mon Mar 26 08:00:00 IDT 2018 | Sun Apr 08 16:00:00 IDT 2018 | Sat Feb 10 08:00:00 IST 2018 | Tue Feb 13 16:00:00 IST 2018 |  | COMPLETED
1581 | TT_TASK | Irrigation Shop Drawing - RO Review and Comment | Fri Mar 08 08:00:00 IST 2019 | Thu Apr 04 16:00:00 IDT 2019 | Sat Mar 24 08:00:00 IDT 2018 | Wed Oct 10 16:00:00 IDT 2018 |  | COMPLETED
1582 | TT_TASK | Irrigation Shop Drawing - RO Comment and Approval | Fri Apr 19 08:00:00 IDT 2019 | Thu May 02 16:00:00 IDT 2019 | Fri Jul 20 08:00:00 IDT 2018 | Tue Feb 12 16:00:00 IST 2019 |  | COMPLETED
1583 | TT_TASK | Lift Shop Drawing - RO Review and Comment (AD TBC) | Thu Jun 14 08:00:00 IDT 2018 | Wed Jun 27 16:00:00 IDT 2018 | Thu Jun 14 08:00:00 IDT 2018 | Wed Jun 27 16:00:00 IDT 2018 |  | COMPLETED
1584 | TT_TASK | Lift Shop Drawing - RO Comment and Approval (AD TBC) | Sat Aug 04 08:00:00 IDT 2018 | Fri Aug 10 16:00:00 IDT 2018 | Thu Jul 05 08:00:00 IDT 2018 | Wed Jul 11 16:00:00 IDT 2018 |  | COMPLETED
1585 | TT_TASK | CWP Manufacturing Drawing - Preparation and Submission to RO | Mon Feb 26 08:00:00 IST 2018 | Fri Mar 16 16:00:00 IST 2018 | Sun Dec 31 08:00:00 IST 2017 | Thu Jan 18 16:00:00 IST 2018 |  | COMPLETED
1586 | TT_TASK | CWP Manufacturing Drawing - RO Review and Comment | Sat Mar 17 08:00:00 IST 2018 | Fri Mar 23 16:00:00 IDT 2018 | Fri Jan 19 08:00:00 IST 2018 | Thu Jan 25 16:00:00 IST 2018 |  | COMPLETED
1587 | TT_TASK | Precast Concrete Intake Chamber - Submission of Quality Plan and Inspection Plan (Approval status TBC) | Mon Nov 26 08:00:00 IST 2018 | Sun Dec 09 16:00:00 IST 2018 | Fri Aug 03 08:00:00 IDT 2018 | Mon Nov 19 16:00:00 IST 2018 |  | COMPLETED
1588 | TT_TASK | Precast Concrete Intake Chamber Fabrication Drawing - Preparation and Submission to RO | Wed Dec 26 08:00:00 IST 2018 | Thu Jan 24 16:00:00 IST 2019 | Tue Dec 04 08:00:00 IST 2018 | Mon Dec 31 16:00:00 IST 2018 |  | COMPLETED
1589 | TT_TASK | Precast Concrete Intake Chamber Fabrication Drawing - RO Review and Comment | Sun Jan 27 08:00:00 IST 2019 | Mon Feb 25 16:00:00 IST 2019 | Tue Jan 01 08:00:00 IST 2019 | Thu Jan 31 16:00:00 IST 2019 |  | COMPLETED
1590 | TT_TASK | TTM for Pumping Station - Preparation and Submission to RO | Tue Aug 08 08:00:00 IDT 2017 | Mon Aug 21 16:00:00 IDT 2017 | Tue Aug 08 08:00:00 IDT 2017 | Thu Sep 07 16:00:00 IDT 2017 |  | COMPLETED
1591 | TT_TASK | TTM for Pumping Station - RO Review and Comment [APPROVED] | Mon Nov 27 08:00:00 IST 2017 | Sun Dec 10 16:00:00 IST 2017 | Fri Sep 08 08:00:00 IDT 2017 | Wed Nov 29 16:00:00 IST 2017 |  | COMPLETED
1592 | TT_TASK | TTM for Pumping Station - Issue of LWC for barricading the areas | Mon Nov 27 08:00:00 IST 2017 | Mon Nov 27 16:00:00 IST 2017 | Thu Nov 30 08:00:00 IST 2017 | Tue Dec 05 16:00:00 IST 2017 |  | COMPLETED
1593 | TT_TASK | TTM for Pumping Station - Barrication as per approved site layout and TTM | Mon Nov 27 08:00:00 IST 2017 | Mon Nov 27 16:00:00 IST 2017 | Tue Dec 05 08:00:00 IST 2017 | Tue Dec 05 16:00:00 IST 2017 |  | COMPLETED
1594 | TT_TASK | TTM for Pumping Station - Declaration of unplanted area | Mon Sep 11 08:00:00 IDT 2017 | Sun Sep 24 16:00:00 IDT 2017 | Wed Dec 06 08:00:00 IST 2017 | Sat Dec 16 16:00:00 IST 2017 |  | COMPLETED
1595 | TT_TASK | TTM for Shaft D - Preparation and Submission to RO | Sat Dec 16 08:00:00 IST 2017 | Fri Dec 29 16:00:00 IST 2017 | Tue Aug 08 08:00:00 IDT 2017 | Thu Sep 07 16:00:00 IDT 2017 |  | COMPLETED
1596 | TT_TASK | TTM for Shaft D - RO Review and Comment [APPROVED] | Mon Nov 27 08:00:00 IST 2017 | Sun Dec 10 16:00:00 IST 2017 | Fri Sep 08 08:00:00 IDT 2017 | Wed Dec 27 16:00:00 IST 2017 |  | COMPLETED
1597 | TT_TASK | TTM for Shaft D - Issue of LWC to barricade the proposed temp. EVA location | Thu Mar 01 08:00:00 IST 2018 | Thu Mar 01 16:00:00 IST 2018 | Thu Dec 28 08:00:00 IST 2017 | Thu Dec 28 16:00:00 IST 2017 |  | COMPLETED
1598 | TT_TASK | TTM for Shaft D - LWC 14 day expiry period | Thu Mar 01 08:00:00 IST 2018 | Wed Mar 14 16:00:00 IST 2018 | Fri Dec 29 08:00:00 IST 2017 | Thu Jan 11 16:00:00 IST 2018 |  | COMPLETED
1599 | TT_TASK | TTM for Shaft D - Barrication as per approved temporary EVA location | Fri Mar 02 08:00:00 IST 2018 | Wed Mar 07 16:00:00 IST 2018 | Fri Dec 29 08:00:00 IST 2017 | Wed Jan 03 16:00:00 IST 2018 |  | COMPLETED
1600 | TT_TASK | TTM for Shaft D - Issue of XP for EVA diversion | Thu Mar 08 08:00:00 IST 2018 | Thu Mar 08 16:00:00 IST 2018 | Thu Jan 04 08:00:00 IST 2018 | Fri Jan 26 16:00:00 IST 2018 |  | COMPLETED
1601 | TT_TASK | TTM for Shaft D - Extend expired LWC | Thu Mar 08 08:00:00 IST 2018 | Thu Mar 08 16:00:00 IST 2018 | Sat Jan 27 08:00:00 IST 2018 | Mon Jan 29 16:00:00 IST 2018 |  | COMPLETED
1602 | TT_TASK | TTM for Shaft D - Construct temporary EVA | Mon Apr 23 08:00:00 IDT 2018 | Thu Apr 26 16:00:00 IDT 2018 | Mon Feb 26 08:00:00 IST 2018 | Thu Mar 01 16:00:00 IST 2018 |  | COMPLETED
1603 | TT_TASK | TTM for Shaft D - Issue of LWC to barricade the proposed site area | Fri Apr 27 08:00:00 IDT 2018 | Mon Apr 30 16:00:00 IDT 2018 | Fri Mar 02 08:00:00 IST 2018 | Tue Mar 06 16:00:00 IST 2018 |  | COMPLETED
1604 | TT_TASK | TTM for Shaft D - Declaration of unplanted area | Tue May 01 08:00:00 IDT 2018 | Mon May 07 16:00:00 IDT 2018 | Wed Mar 07 08:00:00 IST 2018 | Sun Mar 18 16:00:00 IST 2018 |  | COMPLETED
1605 | TT_TASK | TTM for Sea Bank Road - Preparation and Submission to RO | Thu Aug 31 08:00:00 IDT 2017 | Wed Sep 13 16:00:00 IDT 2017 | Tue Aug 08 08:00:00 IDT 2017 | Thu Sep 07 16:00:00 IDT 2017 |  | COMPLETED
1606 | TT_TASK | TTM for Sea Bank Road - RO Review and Comment [APPROVED] | Mon Nov 27 08:00:00 IST 2017 | Sun Dec 10 16:00:00 IST 2017 | Fri Sep 08 08:00:00 IDT 2017 | Wed Dec 27 16:00:00 IST 2017 |  | COMPLETED
1607 | TT_TASK | TTM for Sea Bank Road - Issue of LWC to barricade the proposed hammer head locations | Thu Mar 01 08:00:00 IST 2018 | Thu Mar 01 16:00:00 IST 2018 | Thu Dec 28 08:00:00 IST 2017 | Thu Dec 28 16:00:00 IST 2017 |  | COMPLETED
1608 | TT_TASK | TTM for Sea Bank Road - LWC 14 day expiry period | Thu Mar 01 08:00:00 IST 2018 | Wed Mar 14 16:00:00 IST 2018 | Fri Dec 29 08:00:00 IST 2017 | Thu Jan 11 16:00:00 IST 2018 |  | COMPLETED
1609 | TT_TASK | TTM for Sea Bank Road - Barrication as per approved hammer head locations | Fri Mar 02 08:00:00 IST 2018 | Wed Mar 07 16:00:00 IST 2018 | Fri Dec 29 08:00:00 IST 2017 | Wed Jan 03 16:00:00 IST 2018 |  | COMPLETED
1610 | TT_TASK | TTM for Sea Bank Road - Issue of XP for hammer heads construction | Thu Mar 08 08:00:00 IST 2018 | Thu Mar 08 16:00:00 IST 2018 | Thu Jan 04 08:00:00 IST 2018 | Fri Jan 26 16:00:00 IST 2018 |  | COMPLETED
1611 | TT_TASK | TTM for Sea Bank Road - Extend expired LWC | Thu Mar 08 08:00:00 IST 2018 | Thu Mar 08 16:00:00 IST 2018 | Sat Jan 27 08:00:00 IST 2018 | Mon Jan 29 16:00:00 IST 2018 |  | COMPLETED
1612 | TT_TASK | TTM for Sea Bank Road - Hammer heads construction | Thu Mar 01 08:00:00 IST 2018 | Fri Mar 09 16:00:00 IST 2018 | Mon Jan 29 08:00:00 IST 2018 | Sat Feb 24 16:00:00 IST 2018 |  | COMPLETED
1613 | TT_TASK | TTM for Sea Bank Road - Issue of LWC to barricade the proposed site area | Mon Apr 23 08:00:00 IDT 2018 | Thu Apr 26 16:00:00 IDT 2018 | Fri Mar 02 08:00:00 IST 2018 | Tue Mar 06 16:00:00 IST 2018 |  | COMPLETED
1614 | TT_TASK | TTM for Sea Bank Road - Declaration of unplanted area | Fri Apr 27 08:00:00 IDT 2018 | Thu May 03 16:00:00 IDT 2018 | Wed Mar 07 08:00:00 IST 2018 | Sun Mar 18 16:00:00 IST 2018 |  | COMPLETED
1615 | TT_TASK | Wall Cladding Shop Drawing & Calculation - RO Review and Comment | Mon Apr 23 08:00:00 IDT 2018 | Sun May 20 16:00:00 IDT 2018 | Sat Feb 24 08:00:00 IST 2018 | Fri Mar 23 16:00:00 IDT 2018 |  | COMPLETED
1616 | TT_TASK | Wall Cladding Shop Drawing & Calculation - RO Comment and Approval (= ready for BD submission) | Mon Apr 23 08:00:00 IDT 2018 | Sun May 06 16:00:00 IDT 2018 | Sat Apr 14 08:00:00 IDT 2018 | Thu May 24 16:00:00 IDT 2018 |  | COMPLETED
1617 | TT_TASK | Wall Cladding - BD Approval | Sat May 26 08:00:00 IDT 2018 | Tue Jul 24 16:00:00 IDT 2018 | Fri May 25 08:00:00 IDT 2018 | Mon Jul 23 16:00:00 IDT 2018 |  | COMPLETED
1618 | TT_TASK | Wall Cladding - BD Consent | Sun Aug 26 08:00:00 IDT 2018 | Sat Sep 22 16:00:00 IDT 2018 | Fri Aug 24 08:00:00 IDT 2018 | Thu Sep 20 16:00:00 IDT 2018 |  | COMPLETED
1619 | TT_TASK | Glazing - BD Approval | Tue Jun 26 08:00:00 IDT 2018 | Fri Aug 24 16:00:00 IDT 2018 | Wed Jun 20 08:00:00 IDT 2018 | Tue Aug 21 16:00:00 IDT 2018 |  | COMPLETED
1620 | TT_TASK | Glazing - BD Consent | Mon Nov 26 08:00:00 IST 2018 | Sun Dec 23 16:00:00 IST 2018 | Thu Oct 18 08:00:00 IDT 2018 | Tue Nov 06 16:00:00 IST 2018 |  | COMPLETED
1621 | TT_TASK | Louvre - BD Approval | Mon Nov 26 08:00:00 IST 2018 | Thu Jan 24 16:00:00 IST 2019 | Mon Nov 19 08:00:00 IST 2018 | Tue Jan 15 16:00:00 IST 2019 |  | COMPLETED
1622 | TT_TASK | Louvre - BD Consent | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Thu Dec 06 08:00:00 IST 2018 | Fri Jan 18 16:00:00 IST 2019 |  | COMPLETED
1623 | TT_TASK | Lift Shaft Glazing - BD Approval | Mon Nov 26 08:00:00 IST 2018 | Thu Jan 24 16:00:00 IST 2019 | Fri Nov 09 08:00:00 IST 2018 | Mon Jan 07 16:00:00 IST 2019 |  | COMPLETED
1624 | TT_TASK | Lift Shaft Glazing - BD Consent | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Thu Dec 06 08:00:00 IST 2018 | Fri Jan 11 16:00:00 IST 2019 |  | COMPLETED
1625 | TT_TASK | Aluminum - BD Approval | Mon Nov 26 08:00:00 IST 2018 | Thu Jan 24 16:00:00 IST 2019 | Thu Nov 08 08:00:00 IST 2018 | Mon Jan 07 16:00:00 IST 2019 |  | COMPLETED
1626 | TT_TASK | Aluminum - BD Consent | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Thu Dec 06 08:00:00 IST 2018 | Fri Jan 11 16:00:00 IST 2019 |  | COMPLETED
1629 | TT_TASK | Submission and approval of temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only) {4b4-2} | Tue Jul 04 08:00:00 IDT 2017 | Mon Jul 17 16:00:00 IDT 2017 | Tue Jul 04 08:00:00 IDT 2017 | Wed Dec 20 16:00:00 IST 2017 |  | COMPLETED
1630 | TT_TASK | Submission and approval of temporary works for Shaft A, Pump Station, Diversion Culvert (Excav. & ELS) - for MS-03 {4b5} | Mon Aug 07 08:00:00 IDT 2017 | Tue Aug 15 16:00:00 IDT 2017 | Mon Aug 07 08:00:00 IDT 2017 | Tue Dec 05 16:00:00 IST 2017 |  | COMPLETED
1631 | TT_TASK | Submission and approval of temporary works for Shaft A, Pump Station, Diversion Culvert (Excav. & ELS) {4b5} | Tue Sep 05 08:00:00 IDT 2017 | Mon Sep 18 16:00:00 IDT 2017 | Tue Sep 05 08:00:00 IDT 2017 | Mon Feb 12 16:00:00 IST 2018 |  | COMPLETED
1632 | TT_TASK | Submission and approval of temporary works for Shaft D (Wall, Excav. & ELS) {4b3(r1)} | Fri Jun 02 08:00:00 IDT 2017 | Thu Jun 15 16:00:00 IDT 2017 | Thu Jun 08 08:00:00 IDT 2017 | Tue Jun 20 16:00:00 IDT 2017 |  | COMPLETED
1633 | TT_TASK | Submission and approval of temporary works for Shaft E and Discharge Culvert (Wall, Excav. & ELS) - for MS-03 {4b2i-1} | Mon Aug 07 08:00:00 IDT 2017 | Tue Aug 15 16:00:00 IDT 2017 | Mon Jul 03 08:00:00 IDT 2017 | Thu Jul 20 16:00:00 IDT 2017 |  | COMPLETED
1634 | TT_TASK | Submission and approval of temporary works for Shaft E and Discharge Culvert (Wall, Excav. & ELS) {4b2-1} | Thu Oct 05 08:00:00 IDT 2017 | Fri Nov 03 16:00:00 IST 2017 | Mon Jul 03 08:00:00 IDT 2017 | Thu Jul 20 16:00:00 IDT 2017 |  | COMPLETED
1635 | TT_TASK | Submission and approval of temporary works for Shaft F (Skin Wall) & Double Pipe (Southern Sheet Pile) {4b1i} | Sat Jun 10 08:00:00 IDT 2017 | Wed Jun 21 16:00:00 IDT 2017 | Fri Jun 09 08:00:00 IDT 2017 | Thu Jun 22 16:00:00 IDT 2017 |  | COMPLETED
1636 | TT_TASK | Resubmission and approval of temporary works for Shaft F (Skin Wall) only {4b1-1(r)} | Sat Jun 10 08:00:00 IDT 2017 | Wed Jun 21 16:00:00 IDT 2017 | Tue Jul 18 08:00:00 IDT 2017 | Sun Jul 23 16:00:00 IDT 2017 |  | COMPLETED
1637 | TT_TASK | Resubmission and approval of Zone A (Southern Sheet Pile) {4b1-alt A-1} | Sat Jun 10 08:00:00 IDT 2017 | Wed Jun 21 16:00:00 IDT 2017 | Wed Jul 19 08:00:00 IDT 2017 | Sun Jul 23 16:00:00 IDT 2017 |  | COMPLETED
1638 | TT_TASK | Submission and approval of temporary works for Shaft F and Double Pipe Trench (Open Cut) {4b1-alt B} | Sat Jun 10 08:00:00 IDT 2017 | Wed Jun 21 16:00:00 IDT 2017 | Fri Jun 09 08:00:00 IDT 2017 | Thu Jun 22 16:00:00 IDT 2017 |  | COMPLETED
1640 | TT_TASK | Submission and approval of temporary works for SCW and Intake Culvert Modification (Wall Only) - for MS-05 {5b1(r)} | Thu Aug 17 08:00:00 IDT 2017 | Wed Aug 30 16:00:00 IDT 2017 | Thu Aug 17 08:00:00 IDT 2017 | Tue Sep 19 16:00:00 IDT 2017 |  | COMPLETED
1641 | TT_TASK | Submission and approval of temporary works for SCW and Intake Culvert Modification (Wall Only) {5b1-alt} | Thu Aug 17 08:00:00 IDT 2017 | Wed Aug 30 16:00:00 IDT 2017 | Thu Aug 17 08:00:00 IDT 2017 | Tue Dec 19 16:00:00 IST 2017 |  | COMPLETED
1642 | TT_TASK | Submission and approval of temporary works for SCW and Intake Culvert Modification (Excav & ELS) - for MS-05 {5b1(r)} | Thu Aug 17 08:00:00 IDT 2017 | Wed Aug 30 16:00:00 IDT 2017 | Thu Aug 17 08:00:00 IDT 2017 | Tue Sep 19 16:00:00 IDT 2017 |  | COMPLETED
1643 | TT_TASK | Submission and approval of temporary works for SCW and Intake Culvert Modification (Excav & ELS) {5b1-alt} | Thu Aug 17 08:00:00 IDT 2017 | Wed Aug 30 16:00:00 IDT 2017 | Thu Aug 17 08:00:00 IDT 2017 | Tue Dec 19 16:00:00 IST 2017 |  | COMPLETED
1645 | TT_TASK | Submission and approval of temporary works for Outfall Apron Modification | Sun Jan 07 08:00:00 IST 2018 | Sat Feb 03 16:00:00 IST 2018 | Thu Nov 16 08:00:00 IST 2017 | Wed Jan 10 16:00:00 IST 2018 |  | COMPLETED
1647 | TT_TASK | Submission and approval of temporary works for Power Island Area (Open Cut) {7c2i} | Sat Jun 10 08:00:00 IDT 2017 | Wed Jun 21 16:00:00 IDT 2017 | Sat Jun 10 08:00:00 IDT 2017 | Wed Jun 21 16:00:00 IDT 2017 |  | COMPLETED
1654 | TT_TASK | Review and design temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only) {4b4-2} | Sun Jun 04 08:00:00 IDT 2017 | Mon Jul 03 16:00:00 IDT 2017 | Sun Jun 04 08:00:00 IDT 2017 | Mon Jul 03 16:00:00 IDT 2017 |  | COMPLETED
1655 | TT_TASK | Review and design temporary works for Shaft A, Pump Station, Diversion Culvert (Excavation & ELS) - for MS-03 {4b5} | Wed Jun 28 08:00:00 IDT 2017 | Tue Jul 11 16:00:00 IDT 2017 | Wed Jun 28 08:00:00 IDT 2017 | Tue Jul 25 16:00:00 IDT 2017 |  | COMPLETED
1656 | TT_TASK | Review and design temporary works for Shaft A, Pump Station, Diversion Culvert (Excavation & ELS) {4b5} | Fri Jul 07 08:00:00 IDT 2017 | Mon Sep 04 16:00:00 IDT 2017 | Fri Jul 07 08:00:00 IDT 2017 | Mon Sep 04 16:00:00 IDT 2017 |  | COMPLETED
1657 | TT_TASK | Review and design temporary works for Shaft D (Wall, Excav. & ELS) {4b3(r1)} | Tue May 23 08:00:00 IDT 2017 | Thu Jun 01 16:00:00 IDT 2017 | Tue May 23 08:00:00 IDT 2017 | Thu Jun 01 16:00:00 IDT 2017 |  | COMPLETED
1658 | TT_TASK | Review and design temporary works for Shaft E and Discharge Culvert (Wall, Excav. & ELS) - for MS-03 {4b2-1} | Wed Jun 28 08:00:00 IDT 2017 | Tue Jul 11 16:00:00 IDT 2017 | Mon Jun 12 08:00:00 IDT 2017 | Sun Jul 02 16:00:00 IDT 2017 |  | COMPLETED
1659 | TT_TASK | Review and design temporary works for Shaft E and Discharge Culvert (Wall, Excav. & ELS) {4b2-1} | Tue Sep 05 08:00:00 IDT 2017 | Wed Oct 04 16:00:00 IDT 2017 | Mon Jun 12 08:00:00 IDT 2017 | Sun Jul 02 16:00:00 IDT 2017 |  | COMPLETED
1660 | TT_TASK | Review and design temp works for Shaft F & Double Pipe Trench - Shaft F (Skin Wall) & Southern Section Sheet Pile {4b1i} | Sat May 27 08:00:00 IDT 2017 | Fri Jun 09 16:00:00 IDT 2017 | Sat May 27 08:00:00 IDT 2017 | Fri Jun 09 16:00:00 IDT 2017 |  | COMPLETED
1661 | TT_TASK | Review and design temp works for Shaft F & Double Pipe Trench - Open Cut {4b1-alt B} | Sat May 27 08:00:00 IDT 2017 | Fri Jun 09 16:00:00 IDT 2017 | Sat May 27 08:00:00 IDT 2017 | Fri Jun 09 16:00:00 IDT 2017 |  | COMPLETED
1663 | TT_TASK | Review and design temporary works for SCW and Intake Culvert Modification (Wall Only) - for MS-05 {5b1(r)} | Mon Aug 07 08:00:00 IDT 2017 | Sun Aug 20 16:00:00 IDT 2017 | Fri Jul 28 08:00:00 IDT 2017 | Thu Aug 10 16:00:00 IDT 2017 |  | COMPLETED
1664 | TT_TASK | Review and design temporary works for SCW and Intake Culvert Modification (Wall Only) {5b1-alt} | Fri Aug 11 08:00:00 IDT 2017 | Sat Sep 09 16:00:00 IDT 2017 | Fri Jul 28 08:00:00 IDT 2017 | Wed Aug 16 16:00:00 IDT 2017 |  | COMPLETED
1665 | TT_TASK | Review and design temporary works for SCW and Intake Culvert Modification (Excavation & ELS) - for MS-05 {5b1(r)} | Mon Aug 07 08:00:00 IDT 2017 | Sun Aug 20 16:00:00 IDT 2017 | Fri Jul 28 08:00:00 IDT 2017 | Thu Aug 10 16:00:00 IDT 2017 |  | COMPLETED
1666 | TT_TASK | Review and design temporary works for SCW and Intake Culvert Modification (Excavation & ELS) {5b1-alt} | Sun Sep 10 08:00:00 IDT 2017 | Mon Oct 09 16:00:00 IDT 2017 | Fri Jul 28 08:00:00 IDT 2017 | Wed Aug 16 16:00:00 IDT 2017 |  | COMPLETED
1668 | TT_TASK | Review and design a temporary bulkhead for Outfall Apron Modification | Mon May 29 08:00:00 IDT 2017 | Tue Jun 27 16:00:00 IDT 2017 | Wed Jul 12 08:00:00 IDT 2017 | Sat Jan 06 16:00:00 IST 2018 |  | COMPLETED
1670 | TT_TASK | Review and design temporary works for Power Island Area (Open Cut) {7c2i} | Sat May 27 08:00:00 IDT 2017 | Fri Jun 09 16:00:00 IDT 2017 | Sat May 27 08:00:00 IDT 2017 | Fri Jun 09 16:00:00 IDT 2017 |  | COMPLETED
1673 | TT_TASK | Roof Cladding - Review engineer's drawings and prepare design | Mon Oct 16 08:00:00 IDT 2017 | Sun Nov 12 16:00:00 IST 2017 | Mon Oct 16 08:00:00 IDT 2017 | Fri Jan 26 16:00:00 IST 2018 |  | COMPLETED
1674 | TT_TASK | Roof Cladding - ICE Check and Issue Cert | Thu Jul 26 08:00:00 IDT 2018 | Wed Aug 08 16:00:00 IDT 2018 | Tue Jul 10 08:00:00 IDT 2018 | Mon Jul 23 16:00:00 IDT 2018 |  | COMPLETED
1675 | TT_TASK | Roof Cladding - Performance mock-up test (by approved laboratory) | Thu Aug 09 08:00:00 IDT 2018 | Wed Sep 05 16:00:00 IDT 2018 | Tue Jul 24 08:00:00 IDT 2018 | Mon Aug 20 16:00:00 IDT 2018 |  | COMPLETED
1676 | TT_TASK | Roof Cladding - Address engineer's comment and prepare resubmission | Mon Mar 12 08:00:00 IST 2018 | Sun Mar 25 16:00:00 IDT 2018 | Tue Feb 06 08:00:00 IST 2018 | Fri Feb 09 16:00:00 IST 2018 |  | COMPLETED
1677 | TT_TASK | Roof Cladding - Review engineer's drawings and prepare design | Mon Apr 23 08:00:00 IDT 2018 | Sun May 20 16:00:00 IDT 2018 | Sat Jan 27 08:00:00 IST 2018 | Fri Feb 23 16:00:00 IST 2018 |  | COMPLETED
1678 | TT_TASK | Roof Cladding - Address engineer's comment and prepare resubmission | Mon Apr 23 08:00:00 IDT 2018 | Sun May 20 16:00:00 IDT 2018 | Sat Mar 24 08:00:00 IDT 2018 | Fri Apr 13 16:00:00 IDT 2018 |  | COMPLETED
1680 | TT_TASK | Irrigation System - Review engineer's drawings and prepare design | Fri Feb 08 08:00:00 IST 2019 | Thu Mar 07 16:00:00 IST 2019 | Wed Feb 21 08:00:00 IST 2018 | Fri Sep 21 16:00:00 IDT 2018 |  | COMPLETED
1681 | TT_TASK | Irrigation System - Address engineer's comment and prepare resubmission | Fri Apr 05 08:00:00 IDT 2019 | Thu Apr 18 16:00:00 IDT 2019 | Thu Jun 14 08:00:00 IDT 2018 | Fri Jan 18 16:00:00 IST 2019 |  | COMPLETED
1683 | TT_TASK | Lifts - Review engineer's drawings and prepare design (AD TBC) | Thu Dec 21 08:00:00 IST 2017 | Wed Jan 17 16:00:00 IST 2018 | Thu Dec 21 08:00:00 IST 2017 | Wed Jun 13 16:00:00 IDT 2018 |  | COMPLETED
1684 | TT_TASK | Lifts - Address engineer's comment and prepare resubmission (AD TBC) | Sat Jul 28 08:00:00 IDT 2018 | Fri Aug 03 16:00:00 IDT 2018 | Thu Jun 28 08:00:00 IDT 2018 | Wed Jul 04 16:00:00 IDT 2018 |  | COMPLETED
1687 | TT_TASK | Event 005 - New Requirements on Lift No.1 | Mon Nov 27 08:00:00 IST 2017 | Tue Dec 26 16:00:00 IST 2017 | Thu Nov 16 08:00:00 IST 2017 | Wed Dec 20 16:00:00 IST 2017 |  | COMPLETED
1689 | TT_TASK | Procurement of Subcontract - Excavation & ELS (and other civil works) | Mon Jul 03 08:00:00 IDT 2017 | Thu Aug 31 16:00:00 IDT 2017 | Mon May 29 08:00:00 IDT 2017 | Fri Dec 22 16:00:00 IST 2017 |  | COMPLETED
1690 | TT_TASK | Procurement of Subcontract - Grouting & Sheet /Pipe Piling | Mon Jul 03 08:00:00 IDT 2017 | Thu Aug 31 16:00:00 IDT 2017 | Mon May 29 08:00:00 IDT 2017 | Sat Aug 26 16:00:00 IDT 2017 |  | COMPLETED
1691 | TT_TASK | Procurement of Subcontract - Steel Structure & Heavy Lifting | Mon Jul 03 08:00:00 IDT 2017 | Fri Sep 15 16:00:00 IDT 2017 | Mon May 29 08:00:00 IDT 2017 | Tue Oct 24 16:00:00 IDT 2017 |  | COMPLETED
1692 | TT_TASK | Procurement of Subcontract - Standing Seam Roof, Aluminium Cladding & Curtain Wall | Mon Jul 03 08:00:00 IDT 2017 | Fri Sep 15 16:00:00 IDT 2017 | Mon May 29 08:00:00 IDT 2017 | Wed Dec 20 16:00:00 IST 2017 |  | COMPLETED
1693 | TT_TASK | Procurement of Subcontract - CWP Installation (Jacking / TBM) | Mon Jul 03 08:00:00 IDT 2017 | Fri Sep 15 16:00:00 IDT 2017 | Mon May 29 08:00:00 IDT 2017 | Thu Apr 19 16:00:00 IDT 2018 |  | COMPLETED
1694 | TT_TASK | Procurement of Subcontract - CWP Installation (Laying in trench) | Mon Nov 27 08:00:00 IST 2017 | Fri Feb 09 16:00:00 IST 2018 | Mon May 29 08:00:00 IDT 2017 | Wed Apr 04 16:00:00 IDT 2018 |  | COMPLETED
1695 | TT_TASK | Procurement of Subcontract - Building Service Installation (i.e., Elect, ACMV, FS, P&D) | Mon Sep 04 08:00:00 IDT 2017 | Fri Oct 27 16:00:00 IDT 2017 | Mon Sep 04 08:00:00 IDT 2017 | Tue Feb 20 16:00:00 IST 2018 |  | COMPLETED
1696 | TT_TASK | Procurement of Subcontract - Lift Installation (once awarded to Otis) | Mon Aug 07 08:00:00 IDT 2017 | Mon Sep 25 16:00:00 IDT 2017 | Mon Aug 07 08:00:00 IDT 2017 | Tue Oct 17 16:00:00 IDT 2017 |  | COMPLETED
1697 | TT_TASK | Procurement of Subcontract - Supply of Precast Concrete Structure (i.e. Diversion Culvert) | Mon Feb 26 08:00:00 IST 2018 | Sat Apr 14 16:00:00 IDT 2018 | Mon Feb 05 08:00:00 IST 2018 | Fri Jun 01 16:00:00 IDT 2018 |  | COMPLETED
1699 | TT_TASK | Sourcing, Reconditioning and Delivery of TBM (AD TBC) | Sat Jun 16 08:00:00 IDT 2018 | Fri Oct 05 16:00:00 IDT 2018 | Mon May 07 08:00:00 IDT 2018 | Sun Aug 26 16:00:00 IDT 2018 |  | COMPLETED
1701 | TT_TASK | Fabrication and Delivery of Lifts (AS / EF TBC) | Sat Aug 11 08:00:00 IDT 2018 | Fri Jan 25 16:00:00 IST 2019 | Thu Jul 12 08:00:00 IDT 2018 | Sun Sep 22 16:00:00 IDT 2019 |  | COMPLETED
1703 | TT_TASK | Manufacturing and Delivery of CWP materials (1st Batch) (Zone B prioritized) | Mon Feb 26 08:00:00 IST 2018 | Sun May 20 16:00:00 IDT 2018 | Fri Dec 22 08:00:00 IST 2017 | Fri Apr 27 16:00:00 IDT 2018 |  | COMPLETED
1705 | TT_TASK | Manufacturing and Delivery of CWP materials (2nd Batch) | Sat May 26 08:00:00 IDT 2018 | Mon Jul 09 16:00:00 IDT 2018 | Sat Apr 28 08:00:00 IDT 2018 | Sun May 27 16:00:00 IDT 2018 |  | COMPLETED
1706 | TT_TASK | Manufacturing and Delivery of CWP materials (3rd Batch) | Thu Jun 28 08:00:00 IDT 2018 | Tue Sep 25 16:00:00 IDT 2018 | Mon May 28 08:00:00 IDT 2018 | Sun Dec 16 16:00:00 IST 2018 |  | COMPLETED
1707 | TT_TASK | Manufacturing and Delivery of CWP materials (4th Batch) | Sat Jan 26 08:00:00 IST 2019 | Thu Apr 25 16:00:00 IDT 2019 | Mon Dec 17 08:00:00 IST 2018 | Sat May 25 16:00:00 IDT 2019 |  | COMPLETED
1709 | TT_TASK | Manufacturing and Delivery of Structural Steels (Early Delivery) | Mon Nov 06 08:00:00 IST 2017 | Sun Dec 10 16:00:00 IST 2017 | Fri Nov 24 08:00:00 IST 2017 | Fri Dec 08 16:00:00 IST 2017 |  | COMPLETED
1710 | TT_TASK | Manufacturing and Delivery of Structural Steels (1st Batch) | Tue Mar 06 08:00:00 IST 2018 | Tue Mar 06 16:00:00 IST 2018 | Fri Nov 24 08:00:00 IST 2017 | Tue Mar 27 16:00:00 IDT 2018 |  | COMPLETED
1711 | TT_TASK | Manufacturing and Delivery Roof /Wall Cladding (1st Batch) | Mon Feb 26 08:00:00 IST 2018 | Sun Apr 15 16:00:00 IDT 2018 | Thu Jan 18 08:00:00 IST 2018 | Wed Mar 21 16:00:00 IST 2018 |  | COMPLETED
1712 | TT_TASK | Manufacturing and Delivery of Curtain Wall /Glazing (1st Batch) | Mon Nov 26 08:00:00 IST 2018 | Sat Feb 23 16:00:00 IST 2019 | Fri Nov 09 08:00:00 IST 2018 | Thu Jan 10 16:00:00 IST 2019 |  | COMPLETED
1713 | TT_TASK | Fabrication and Delivery of Precast Concrete Intake Chamber | Wed May 01 08:00:00 IDT 2019 | Tue Jul 23 16:00:00 IDT 2019 | Tue Mar 26 08:00:00 IST 2019 | Tue Oct 01 16:00:00 IDT 2019 |  | COMPLETED
1714 | TT_TASK | Procurement and Delivery of Conductor Materials for Earth Mat | Mon Jul 03 08:00:00 IDT 2017 | Fri Aug 11 16:00:00 IDT 2017 | Mon Jul 03 08:00:00 IDT 2017 | Fri Sep 08 16:00:00 IDT 2017 |  | COMPLETED
1715 | TT_TASK | Fabrication and Delivery of Temporary Bulkhead | Wed Mar 14 08:00:00 IST 2018 | Tue Apr 17 16:00:00 IDT 2018 | Fri Jan 19 08:00:00 IST 2018 | Mon Feb 12 16:00:00 IST 2018 |  | COMPLETED
1722 | TT_TASK | OFCI Item No.,10 - Platforms (actual dates TBC) | Fri Nov 03 08:00:00 IST 2017 | Fri Apr 06 16:00:00 IDT 2018 | Fri Nov 03 08:00:00 IST 2017 | Mon Apr 30 16:00:00 IDT 2018 |  | COMPLETED
1726 | TT_TASK | Site Establishment - Erect Hoarding | Mon Sep 25 08:00:00 IDT 2017 | Mon Oct 16 16:00:00 IDT 2017 | Mon Sep 25 08:00:00 IDT 2017 | Mon Oct 16 16:00:00 IDT 2017 |  | COMPLETED
1727 | TT_TASK | Site Establishment - Site Clearance (incl. Fencing, Wheel Washing Facilities and Hard Standings for Area 2c, 4a, 4b & 5) | Mon Jul 17 08:00:00 IDT 2017 | Fri Aug 18 16:00:00 IDT 2017 | Mon Jul 17 08:00:00 IDT 2017 | Fri Sep 08 16:00:00 IDT 2017 |  | COMPLETED
1728 | TT_TASK | Site Establishment - Conduct Survey to Existing Structures and Structural Survey to Cooling Water Outfall Structure | Mon Jul 03 08:00:00 IDT 2017 | Fri Aug 04 16:00:00 IDT 2017 | Thu Jun 01 08:00:00 IDT 2017 | Mon Oct 23 16:00:00 IDT 2017 |  | COMPLETED
1729 | TT_TASK | Site Establishment - Site Mobilisation Works | Tue Jul 04 08:00:00 IDT 2017 | Sat Aug 05 16:00:00 IDT 2017 | Mon Jun 19 08:00:00 IDT 2017 | Mon Oct 16 16:00:00 IDT 2017 |  | COMPLETED
1731 | TT_TASK | Site Establishment - Install Instrumentation to Monitor Building Settlment, Ground/Utility Settlement and Vibrations | Wed Jun 28 08:00:00 IDT 2017 | Mon Sep 25 16:00:00 IDT 2017 | Mon Jun 26 08:00:00 IDT 2017 | Sun Feb 11 16:00:00 IST 2018 |  | COMPLETED
1734 | TT_TASK | Event 001 - SCW Penstock Repair 10~16 Sep 2017 | Sun Sep 10 08:00:00 IDT 2017 | Sat Sep 16 16:00:00 IDT 2017 | Sun Sep 10 08:00:00 IDT 2017 | Sat Sep 16 16:00:00 IDT 2017 |  | COMPLETED
1735 | TT_TASK | Event 007 - Approval of Site Arrangement and TTA | Mon Oct 23 08:00:00 IDT 2017 | Mon Oct 23 16:00:00 IDT 2017 | Thu Sep 07 08:00:00 IDT 2017 | Wed Nov 29 16:00:00 IST 2017 |  | COMPLETED
1736 | TT_TASK | Event 007 - Issue of LWC for barricading the areas | Mon Nov 27 08:00:00 IST 2017 | Mon Nov 27 16:00:00 IST 2017 | Thu Nov 30 08:00:00 IST 2017 | Tue Dec 05 16:00:00 IST 2017 |  | COMPLETED
1737 | TT_TASK | Event 007 - Barrication as per approved site layout and TTM | Mon Nov 27 08:00:00 IST 2017 | Mon Nov 27 16:00:00 IST 2017 | Tue Dec 05 08:00:00 IST 2017 | Tue Dec 05 16:00:00 IST 2017 |  | COMPLETED
1738 | TT_TASK | Event 008 - Declaration of unplanted area / Isolation of SCWP(?) | Wed Dec 13 08:00:00 IST 2017 | Fri Jan 05 16:00:00 IST 2018 | Wed Dec 06 08:00:00 IST 2017 | Sat Dec 16 16:00:00 IST 2017 |  | COMPLETED
1739 | TT_TASK | Event 008 - Excavation Permit | Mon Nov 27 08:00:00 IST 2017 | Mon Nov 27 16:00:00 IST 2017 | Fri Dec 15 08:00:00 IST 2017 | Fri Dec 29 16:00:00 IST 2017 |  | COMPLETED
1740 | TT_TASK | Event 009 - 2 nos Pre-drill abortive | Sat Mar 03 08:00:00 IST 2018 | Sat Mar 31 16:00:00 IDT 2018 | Sat Dec 30 08:00:00 IST 2017 | Fri Jan 26 16:00:00 IST 2018 |  | COMPLETED
1742 | TT_TASK | Event 009 - Additional Pre-drill (2 out of 4 nos.) | Mon Apr 23 08:00:00 IDT 2018 | Mon May 28 16:00:00 IDT 2018 | Fri Apr 20 08:00:00 IDT 2018 | Fri May 04 16:00:00 IDT 2018 |  | COMPLETED
1743 | TT_TASK | Event 009 - 3rd pre-drill encountered unchartered UU and rigs demob to help out inclinometer and SPT at Shaft F | Sat May 26 08:00:00 IDT 2018 | Mon Jun 11 16:00:00 IDT 2018 | Sat May 05 08:00:00 IDT 2018 | Mon May 28 16:00:00 IDT 2018 |  | COMPLETED
1744 | TT_TASK | Event 009 - Additional Pre-drill (remaining 2 nos.) | Fri Jun 29 08:00:00 IDT 2018 | Mon Jul 16 16:00:00 IDT 2018 | Tue May 29 08:00:00 IDT 2018 | Sat Jun 23 16:00:00 IDT 2018 |  | COMPLETED
1745 | TT_TASK | Event 017(I) - Advanced Precautionary Grouting | Sat Jan 26 08:00:00 IST 2019 | Fri Mar 08 16:00:00 IST 2019 | Thu Dec 27 08:00:00 IST 2018 | Sat Feb 09 16:00:00 IST 2019 |  | COMPLETED
1747 | TT_TASK | Event 026 - Tie beam amendment (i.e. steel tie beam, phased consent for excav below +3.5, delete TAM & CS4)[WITHDRAWN] | Sun Aug 26 08:00:00 IDT 2018 | Thu Aug 30 16:00:00 IDT 2018 | Fri Aug 24 08:00:00 IDT 2018 | Tue Aug 28 16:00:00 IDT 2018 |  | COMPLETED
1748 | TT_TASK | Event 026 - Resubmission of tie beam amendment | Thu Dec 13 08:00:00 IST 2018 | Fri Jan 11 16:00:00 IST 2019 | Thu Sep 13 08:00:00 IDT 2018 | Wed Nov 14 16:00:00 IST 2018 |  | COMPLETED
1749 | TT_TASK | Event 026 - BA8 consent for APG | Wed Dec 26 08:00:00 IST 2018 | Tue Jan 22 16:00:00 IST 2019 | Wed Nov 14 08:00:00 IST 2018 | Fri Dec 14 16:00:00 IST 2018 |  | COMPLETED
1750 | TT_TASK | Event 043 - RP11 encounter underground obstruction | Mon Nov 26 08:00:00 IST 2018 | Sun Dec 09 16:00:00 IST 2018 | Sat Sep 29 00:00:00 IDT 2018 | Fri Oct 12 16:00:00 IDT 2018 |  | COMPLETED
1751 | TT_TASK | Event 043 - RP14, 15, 16 encounter underground obstruction | Mon Nov 26 08:00:00 IST 2018 | Sun Dec 23 16:00:00 IST 2018 | Thu Nov 01 00:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 |  | COMPLETED
1752 | TT_TASK | Event 043 - Socketed H-pile amendment (Type II) [APPROVAL DEEMED] | Sat Jan 26 08:00:00 IST 2019 | Sun Feb 24 16:00:00 IST 2019 | Thu Dec 27 08:00:00 IST 2018 | Fri Jan 25 16:00:00 IST 2019 |  | COMPLETED
1753 | TT_TASK | Intake Culvert Modif - Utilities Diversion | Sat May 26 08:00:00 IDT 2018 | Fri Jun 29 16:00:00 IDT 2018 | Wed Apr 25 08:00:00 IDT 2018 | Thu Jun 21 16:00:00 IDT 2018 |  | COMPLETED
1754 | TT_TASK | Intake Culvert Modif - Remove parts of existing gantry crane | Fri Jun 01 08:00:00 IDT 2018 | Sat Jun 16 16:00:00 IDT 2018 | Fri Apr 06 08:00:00 IDT 2018 | Sat Apr 21 16:00:00 IDT 2018 |  | COMPLETED
1755 | TT_TASK | Intake Culvert Modif - Remove tie beams of existing gantry foundations | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 09 16:00:00 IDT 2019 | Mon Mar 18 08:00:00 IST 2019 | Sat Mar 23 16:00:00 IST 2019 |  | COMPLETED
1756 | TT_TASK | Intake Culvert Modif - Install socket H-pile (All except RP14-16) | Mon Aug 27 08:00:00 IDT 2018 | Sat Oct 13 16:00:00 IDT 2018 | Thu Aug 09 08:00:00 IDT 2018 | Sat Nov 10 16:00:00 IST 2018 |  | COMPLETED
1757 | TT_TASK | Intake Culvert Modif - Install socket H-pile (RP14, RP15, RP16) | Fri Feb 08 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Sat Jan 12 08:00:00 IST 2019 | Thu Jan 31 16:00:00 IST 2019 |  | COMPLETED
1758 | TT_TASK | Intake Culvert Modif - CS3 Pipe Pile Wall | Sat Jan 26 08:00:00 IST 2019 | Thu Jan 31 16:00:00 IST 2019 | Tue Jan 08 08:00:00 IST 2019 | Sat Jan 12 16:00:00 IST 2019 |  | COMPLETED
1759 | TT_TASK | Intake Culvert Modif - Grout Curtain (behind CS3) | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 12 16:00:00 IDT 2019 | Sat Feb 09 08:00:00 IST 2019 | Mon Feb 18 16:00:00 IST 2019 |  | COMPLETED
1760 | TT_TASK | Intake Culvert Modif - BA8 consent for excavation below +3.5 and above +2.425 mPD (Zone 1 for Tie Back )(AD TBC) | Wed Apr 03 08:00:00 IDT 2019 | Tue Apr 30 16:00:00 IDT 2019 | Thu Jan 31 08:00:00 IST 2019 | Fri Mar 29 16:00:00 IDT 2019 |  | COMPLETED
1761 | TT_TASK | Intake Culvert Modif - Zone 1 excavation to +2.425 mPD | Wed Apr 03 08:00:00 IDT 2019 | Tue Apr 09 16:00:00 IDT 2019 | Thu Feb 28 08:00:00 IST 2019 | Fri Mar 29 16:00:00 IDT 2019 |  | COMPLETED
1762 | TT_TASK | Intake Culvert Modif - Construct Tie-back system | Wed Apr 10 08:00:00 IDT 2019 | Tue May 21 16:00:00 IDT 2019 | Mon Mar 25 08:00:00 IST 2019 | Mon Apr 15 16:00:00 IDT 2019 |  | COMPLETED
1763 | TT_TASK | Intake Culvert Modif - Remove parts of existing crest wall and fence | Mon Sep 10 08:00:00 IDT 2018 | Sat Sep 29 16:00:00 IDT 2018 | Mon Sep 10 08:00:00 IDT 2018 | Tue Oct 09 16:00:00 IDT 2018 |  | COMPLETED
1764 | TT_TASK | Intake Culvert Modif - Install silt curtain | Mon Aug 27 08:00:00 IDT 2018 | Tue Aug 28 16:00:00 IDT 2018 | Tue Aug 21 08:00:00 IDT 2018 | Thu Aug 23 16:00:00 IDT 2018 |  | COMPLETED
1765 | TT_TASK | Intake Culvert Modif - Remove rock armour | Mon Nov 26 08:00:00 IST 2018 | Sat Dec 01 16:00:00 IST 2018 | Wed Oct 10 08:00:00 IDT 2018 | Sun Oct 14 16:00:00 IDT 2018 |  | COMPLETED
1766 | TT_TASK | Intake Culvert Modif - Rock fill to form a working platform at +3.5mPD | Mon Dec 03 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 | Mon Oct 15 08:00:00 IDT 2018 | Wed Nov 14 16:00:00 IST 2018 |  | COMPLETED
1767 | TT_TASK | Intake Culvert Modif - 406 Dia. Pipe Pile Walls (CS2) | Mon Nov 26 08:00:00 IST 2018 | Mon Jan 21 16:00:00 IST 2019 | Sat Nov 24 08:00:00 IST 2018 | Mon Jan 14 16:00:00 IST 2019 |  | COMPLETED
1768 | TT_TASK | Intake Culvert Modif - Grout Curtain (behind CS2) | Sat Jan 26 08:00:00 IST 2019 | Fri Mar 08 16:00:00 IST 2019 | Wed Jan 16 08:00:00 IST 2019 | Sat Feb 23 16:00:00 IST 2019 |  | COMPLETED
1769 | TT_TASK | Intake Culvert Modif - BA8 consent for excavation below +3.5 and above +2.425 mPD (Zone 2 for Intake Chamber)(AD TBC) | Sun Mar 31 08:00:00 IDT 2019 | Sat Apr 27 16:00:00 IDT 2019 | Thu Feb 28 08:00:00 IST 2019 | Fri Mar 29 16:00:00 IDT 2019 |  | COMPLETED
1770 | TT_TASK | Intake Culvert Modif - Zone 2 Excavate to +2.425mPD | Wed May 01 08:00:00 IDT 2019 | Tue May 07 16:00:00 IDT 2019 | Wed Apr 10 08:00:00 IDT 2019 | Thu Apr 18 16:00:00 IDT 2019 |  | COMPLETED
1771 | TT_TASK | Intake Culvert Modif - Install twin batten waling frame | Wed May 01 08:00:00 IDT 2019 | Tue May 07 16:00:00 IDT 2019 | Mon Apr 22 08:00:00 IDT 2019 | Fri Apr 26 16:00:00 IDT 2019 |  | COMPLETED
1772 | TT_TASK | Intake Culvert Modif - BA8 consent for excavation below +2.425 mPD (AD TBC) | Sun Mar 31 08:00:00 IDT 2019 | Sat Apr 27 16:00:00 IDT 2019 | Thu Feb 28 08:00:00 IST 2019 | Fri Mar 29 16:00:00 IDT 2019 |  | COMPLETED
1773 | TT_TASK | Intake Culvert Modif - Excavate to top of existing intake culvert | Wed May 01 08:00:00 IDT 2019 | Tue May 07 16:00:00 IDT 2019 | Sat Apr 27 08:00:00 IDT 2019 | Wed May 29 16:00:00 IDT 2019 |  | COMPLETED
1774 | TT_TASK | Intake Culvert Modif - Install staging platform | Thu Jun 06 08:00:00 IDT 2019 | Thu Jul 11 16:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 | Fri Jun 21 16:00:00 IDT 2019 |  | COMPLETED
1775 | TT_TASK | Intake Culvert Modif - Saw cut and remove the existing box culvert at the location of proposed diversion chamber | Thu Aug 01 08:00:00 IDT 2019 | Sat Aug 24 16:00:00 IDT 2019 | Thu Jul 18 08:00:00 IDT 2019 | Tue Sep 24 16:00:00 IDT 2019 |  | COMPLETED
1776 | TT_TASK | Intake Culvert Modif - Excavate either side of culvert to -5.4mPD | Sat Aug 10 08:00:00 IDT 2019 | Sun Aug 11 16:00:00 IDT 2019 | Sat Jun 22 08:00:00 IDT 2019 | Wed Jul 17 16:00:00 IDT 2019 |  | COMPLETED
1777 | TT_TASK | Intake Culvert Modif - Prepare bedding and leveling | Fri Nov 01 08:00:00 IST 2019 | Wed Nov 06 16:00:00 IST 2019 | Wed Sep 25 08:00:00 IDT 2019 | Tue Oct 15 16:00:00 IDT 2019 |  | COMPLETED
1778 | TT_TASK | Intake Culvert Modif - Install precast segments for the base slab | Fri Nov 01 08:00:00 IST 2019 | Fri Nov 01 16:00:00 IST 2019 | Wed Oct 16 08:00:00 IDT 2019 | Thu Oct 17 16:00:00 IDT 2019 |  | COMPLETED
1779 | TT_TASK | Intake Culvert Modif - Tremie concrete to segment joints of base slab | Fri Nov 01 08:00:00 IST 2019 | Fri Nov 01 16:00:00 IST 2019 | Mon Oct 21 08:00:00 IDT 2019 | Fri Oct 25 16:00:00 IDT 2019 |  | COMPLETED
1780 | TT_TASK | Intake Culvert Modif - Install precast segments for the columns and side walls | Sun Nov 03 08:00:00 IST 2019 | Mon Nov 04 16:00:00 IST 2019 | Fri Oct 18 08:00:00 IDT 2019 | Sat Oct 19 16:00:00 IDT 2019 |  | COMPLETED
1781 | TT_TASK | Intake Culvert Modif - Tremie concrete to segment joints of columns and side walls | Sat Nov 02 08:00:00 IST 2019 | Sun Nov 03 16:00:00 IST 2019 | Mon Oct 21 08:00:00 IDT 2019 | Fri Nov 15 16:00:00 IST 2019 |  | COMPLETED
1782 | TT_TASK | Intake Culvert Modif - Install precast segments for top slab and beams | Thu Nov 07 08:00:00 IST 2019 | Thu Nov 07 16:00:00 IST 2019 | Sun Oct 20 08:00:00 IDT 2019 | Sun Oct 20 16:00:00 IDT 2019 |  | COMPLETED
1783 | TT_TASK | Intake Culvert Modif - Tremie concrete to segment joints of top slab | Mon Nov 04 08:00:00 IST 2019 | Mon Nov 04 16:00:00 IST 2019 | Tue Oct 22 08:00:00 IDT 2019 | Mon Oct 28 16:00:00 IST 2019 |  | COMPLETED
1784 | TT_TASK | Intake Culvert Modif - Backfill between the proposed chamber and pipe pile walls | Sat Nov 23 08:00:00 IST 2019 | Wed Dec 04 16:00:00 IST 2019 | Mon Oct 21 08:00:00 IDT 2019 | Fri Nov 15 16:00:00 IST 2019 |  | COMPLETED
1785 | TT_TASK | Intake Culvert Modif - Reinstate the seawall and rock armour to 0.5m below the shoring | Thu Jan 09 08:00:00 IST 2020 | Sat Jan 11 16:00:00 IST 2020 | Wed Dec 11 08:00:00 IST 2019 | Fri Dec 13 16:00:00 IST 2019 |  | COMPLETED
1786 | TT_TASK | Intake Culvert Modif - Remove twin batten waling frame | Thu Jan 09 08:00:00 IST 2020 | Mon Jan 13 16:00:00 IST 2020 | Sat Nov 16 08:00:00 IST 2019 | Wed Nov 20 16:00:00 IST 2019 |  | COMPLETED
1787 | TT_TASK | Intake Culvert Modif - Backfill and reinstate the crest wall and fence | Thu Jan 16 08:00:00 IST 2020 | Wed Jan 22 16:00:00 IST 2020 | Thu Jan 16 08:00:00 IST 2020 | Wed Jan 22 16:00:00 IST 2020 |  | COMPLETED
1788 | TT_TASK | Intake Culvert Modif - Install temporary penstock at the connection with Diversion Culvert | Sun Nov 24 08:00:00 IST 2019 | Tue Nov 26 16:00:00 IST 2019 | Wed Oct 16 08:00:00 IDT 2019 | Sun Oct 20 16:00:00 IDT 2019 |  | COMPLETED
1789 | TT_TASK | Intake Culvert Modif - Observe and repair leaks | Mon Jan 06 08:00:00 IST 2020 | Thu Jan 09 16:00:00 IST 2020 | Wed Nov 06 08:00:00 IST 2019 | Sat Nov 09 16:00:00 IST 2019 |  | COMPLETED
1790 | TT_TASK | Intake Culvert Modif - Make good interior surface | Fri Jan 24 08:00:00 IST 2020 | Thu Jan 30 16:00:00 IST 2020 | Mon Oct 21 08:00:00 IDT 2019 | Fri Nov 15 16:00:00 IST 2019 |  | COMPLETED
1791 | TT_TASK | Intake Culvert Modif - Remove temporary penstock | Sat Feb 15 08:00:00 IST 2020 | Sun Feb 16 16:00:00 IST 2020 | Thu Dec 19 08:00:00 IST 2019 | Fri Dec 20 16:00:00 IST 2019 |  | COMPLETED
1792 | TT_TASK | Intake Culvert Modif - Reinstate existing utilities and gantry crane | Thu Jan 09 08:00:00 IST 2020 | Wed Jan 22 16:00:00 IST 2020 | Mon Dec 16 08:00:00 IST 2019 | Fri Feb 28 16:00:00 IST 2020 |  | COMPLETED
1794 | TT_TASK | Event 007 - Approval of Site Arrangement and TTA | Mon Oct 23 08:00:00 IDT 2017 | Mon Oct 23 16:00:00 IDT 2017 | Thu Sep 07 08:00:00 IDT 2017 | Wed Nov 29 16:00:00 IST 2017 |  | COMPLETED
1795 | TT_TASK | Event 007 - Issue of LWC for barricading the areas | Mon Nov 27 08:00:00 IST 2017 | Mon Nov 27 16:00:00 IST 2017 | Thu Nov 30 08:00:00 IST 2017 | Tue Dec 05 16:00:00 IST 2017 |  | COMPLETED
1796 | TT_TASK | Event 007 - Barrication as per approved site layout and TTM | Mon Nov 27 08:00:00 IST 2017 | Mon Nov 27 16:00:00 IST 2017 | Tue Dec 05 08:00:00 IST 2017 | Tue Dec 05 16:00:00 IST 2017 |  | COMPLETED
1797 | TT_TASK | Event 008 - Declaration of unplanted area | Wed Dec 13 08:00:00 IST 2017 | Sat Dec 30 16:00:00 IST 2017 | Wed Dec 06 08:00:00 IST 2017 | Sat Dec 16 16:00:00 IST 2017 |  | COMPLETED
1798 | TT_TASK | Event 008 - Excavation Permit | Mon Nov 27 08:00:00 IST 2017 | Mon Nov 27 16:00:00 IST 2017 | Fri Dec 15 08:00:00 IST 2017 | Fri Dec 29 16:00:00 IST 2017 |  | COMPLETED
1799 | TT_TASK | Event 017 - Diversion Culvert APG | Thu Dec 06 08:00:00 IST 2018 | Thu Jan 03 16:00:00 IST 2019 | Thu Oct 11 08:00:00 IDT 2018 | Tue Nov 27 16:00:00 IST 2018 |  | COMPLETED
1800 | TT_TASK | Event 019 - Diversion Culvert C1 plate load test | Fri Nov 01 08:00:00 IST 2019 | Tue Nov 05 16:00:00 IST 2019 | Fri Oct 04 08:00:00 IDT 2019 | Tue Oct 08 16:00:00 IDT 2019 |  | COMPLETED
1801 | TT_TASK | Diversion Culvert - Utilities Diversion Stage 1 | Mon Aug 27 08:00:00 IDT 2018 | Fri Aug 31 16:00:00 IDT 2018 | Tue Aug 14 08:00:00 IDT 2018 | Sat Aug 18 16:00:00 IDT 2018 |  | COMPLETED
1802 | TT_TASK | Diversion Culvert - Utilities Diversion Stage 2 | Sat Jan 26 08:00:00 IST 2019 | Mon Feb 18 16:00:00 IST 2019 | Sun Dec 30 08:00:00 IST 2018 | Mon Jan 21 16:00:00 IST 2019 |  | COMPLETED
1803 | TT_TASK | Diversion Culvert - Utilities Diversion Stage 3 | Sat Jan 26 08:00:00 IST 2019 | Mon Feb 18 16:00:00 IST 2019 | Tue Jan 22 08:00:00 IST 2019 | Tue Feb 12 16:00:00 IST 2019 |  | COMPLETED
1804 | TT_TASK | Diversion Culvert - Pipe pile along the inner cofferdam wall alignment | Wed Dec 26 08:00:00 IST 2018 | Wed Feb 06 16:00:00 IST 2019 | Wed Dec 12 08:00:00 IST 2018 | Tue Apr 30 16:00:00 IDT 2019 |  | COMPLETED
1805 | TT_TASK | Diversion Culvert - Grout curtain along the inner cofferdam wall alignment | Mon Apr 08 08:00:00 IDT 2019 | Sat May 11 16:00:00 IDT 2019 | Thu Mar 28 08:00:00 IST 2019 | Fri May 24 16:00:00 IDT 2019 |  | COMPLETED
1806 | TT_TASK | Diversion Culvert - Install silt curtain | Mon Aug 27 08:00:00 IDT 2018 | Tue Aug 28 16:00:00 IDT 2018 | Tue Aug 21 08:00:00 IDT 2018 | Thu Aug 23 16:00:00 IDT 2018 |  | COMPLETED
1807 | TT_TASK | Diversion Culvert - Remove parts of crest wall and fence | Mon Nov 26 08:00:00 IST 2018 | Sat Dec 08 16:00:00 IST 2018 | Mon Sep 03 08:00:00 IDT 2018 | Sat Sep 08 16:00:00 IDT 2018 |  | COMPLETED
1808 | TT_TASK | Diversion Culvert - Remove rock armour from the existing seawall | Mon Dec 03 08:00:00 IST 2018 | Sat Dec 08 16:00:00 IST 2018 | Mon Sep 10 08:00:00 IDT 2018 | Sat Sep 22 16:00:00 IDT 2018 |  | COMPLETED
1809 | TT_TASK | Diversion Culvert - Rock fill to +4mPD to form temporary piling platform | Mon Dec 10 08:00:00 IST 2018 | Wed Dec 12 16:00:00 IST 2018 | Mon Sep 24 08:00:00 IDT 2018 | Sat Oct 06 16:00:00 IDT 2018 |  | COMPLETED
1810 | TT_TASK | Diversion Culvert - Pipe pile along the outer cofferdam wall alignment | Wed Dec 26 08:00:00 IST 2018 | Fri Feb 01 16:00:00 IST 2019 | Sat Dec 01 08:00:00 IST 2018 | Thu Apr 11 16:00:00 IDT 2019 |  | COMPLETED
1811 | TT_TASK | Diversion Culvert - Grout curtain along the outer cofferdam wall alignment | Mon Apr 01 08:00:00 IDT 2019 | Sat May 04 16:00:00 IDT 2019 | Mon Mar 04 08:00:00 IST 2019 | Fri May 24 16:00:00 IDT 2019 |  | COMPLETED
1812 | TT_TASK | Diversion Culvert - Pumping Test and Report Submission (C1) | Thu Aug 01 08:00:00 IDT 2019 | Wed Aug 21 16:00:00 IDT 2019 | Sat Jun 01 08:00:00 IDT 2019 | Thu Jun 13 16:00:00 IDT 2019 |  | COMPLETED
1813 | TT_TASK | Diversion Culvert - Pumping Test and Report Submission (C2) | Thu Aug 01 08:00:00 IDT 2019 | Wed Aug 21 16:00:00 IDT 2019 | Sat Jun 08 08:00:00 IDT 2019 | Thu Jul 11 16:00:00 IDT 2019 |  | COMPLETED
1814 | TT_TASK | Diversion Culvert - BD Consent for Commencement of Excavation & ELS (C1) | Thu Aug 15 08:00:00 IDT 2019 | Wed Sep 11 16:00:00 IDT 2019 | Thu Jun 06 08:00:00 IDT 2019 | Tue Jul 16 16:00:00 IDT 2019 |  | COMPLETED
1815 | TT_TASK | Diversion Culvert - BD Consent for Commencement of Excavation & ELS (C2) [APPROVAL DEEMED] | Thu Aug 01 08:00:00 IDT 2019 | Wed Aug 28 16:00:00 IDT 2019 | Fri Jul 12 08:00:00 IDT 2019 | Wed Sep 04 16:00:00 IDT 2019 |  | COMPLETED
1816 | TT_TASK | Diversion Culvert - Excavate to 0.5m below 1st layer of struts | Thu Aug 01 08:00:00 IDT 2019 | Mon Aug 05 16:00:00 IDT 2019 | Mon Jun 17 08:00:00 IDT 2019 | Mon Jun 24 16:00:00 IDT 2019 |  | COMPLETED
1817 | TT_TASK | Diversion Culvert - Install 1st layer of struts and temporary support to existing utilities | Thu Aug 01 08:00:00 IDT 2019 | Mon Aug 05 16:00:00 IDT 2019 | Tue Jun 25 08:00:00 IDT 2019 | Fri Jul 26 16:00:00 IDT 2019 |  | COMPLETED
1818 | TT_TASK | Diversion Culvert - Excavate to 0.5m below 2nd layer of struts | Thu Aug 01 08:00:00 IDT 2019 | Sun Aug 04 16:00:00 IDT 2019 | Sat Jul 27 08:00:00 IDT 2019 | Sun Aug 25 16:00:00 IDT 2019 |  | COMPLETED
1819 | TT_TASK | Diversion Culvert - Install 2nd layer of struts | Mon Sep 09 08:00:00 IDT 2019 | Fri Sep 20 16:00:00 IDT 2019 | Thu Aug 15 08:00:00 IDT 2019 | Thu Aug 29 16:00:00 IDT 2019 |  | COMPLETED
1820 | TT_TASK | Diversion Culvert - Excavate to 0.5m below 3rd layer of struts | Sun Sep 01 08:00:00 IDT 2019 | Sun Sep 08 16:00:00 IDT 2019 | Tue Aug 27 08:00:00 IDT 2019 | Wed Sep 04 16:00:00 IDT 2019 |  | COMPLETED
1821 | TT_TASK | Diversion Culvert - Install 3rd layer of struts | Sat Nov 02 08:00:00 IST 2019 | Sat Nov 09 16:00:00 IST 2019 | Mon Sep 02 08:00:00 IDT 2019 | Fri Sep 13 16:00:00 IDT 2019 |  | COMPLETED
1822 | TT_TASK | Diversion Culvert - Excavate to 0.5m below 4th layer struts | Fri Nov 01 08:00:00 IST 2019 | Sat Nov 09 16:00:00 IST 2019 | Sat Sep 14 08:00:00 IDT 2019 | Sat Sep 28 16:00:00 IDT 2019 |  | COMPLETED
1823 | TT_TASK | Diversion Culvert - Install 4th layer of struts | Fri Nov 01 08:00:00 IST 2019 | Fri Nov 08 16:00:00 IST 2019 | Thu Sep 26 08:00:00 IDT 2019 | Thu Oct 10 16:00:00 IDT 2019 |  | COMPLETED
1824 | TT_TASK | Diversion Culvert - Excavate to final excavation level -5.5 mPD | Fri Nov 01 08:00:00 IST 2019 | Fri Nov 08 16:00:00 IST 2019 | Tue Oct 01 08:00:00 IDT 2019 | Tue Oct 22 16:00:00 IDT 2019 |  | COMPLETED
1825 | TT_TASK | Diversion Culvert (C1) - Cast base slab and walls to 0.5m below 4th layer of struts | Fri Nov 01 08:00:00 IST 2019 | Wed Nov 06 16:00:00 IST 2019 | Wed Oct 23 08:00:00 IDT 2019 | Mon Nov 04 16:00:00 IST 2019 |  | COMPLETED
1826 | TT_TASK | Diversion Culvert - Backfill void between culvert and pipe pile wall to 0.5m below 4th layer of struts | Sat Jan 04 08:00:00 IST 2020 | Sat Jan 04 16:00:00 IST 2020 | Mon Nov 04 08:00:00 IST 2019 | Mon Nov 04 16:00:00 IST 2019 |  | COMPLETED
1827 | TT_TASK | Diversion Culvert - Remove 4th layer of struts | Sun Jan 05 08:00:00 IST 2020 | Tue Jan 07 16:00:00 IST 2020 | Tue Nov 05 08:00:00 IST 2019 | Wed Nov 06 16:00:00 IST 2019 |  | COMPLETED
1828 | TT_TASK | Diversion Culvert (C1) - Cast remaining walls and top slab | Wed Jan 08 08:00:00 IST 2020 | Sat Jan 18 16:00:00 IST 2020 | Thu Nov 07 08:00:00 IST 2019 | Thu Nov 28 16:00:00 IST 2019 |  | COMPLETED
1829 | TT_TASK | Diversion Culvert - Trim the interfacing sheet pile wall adjoining Pumping Station to -5.5 mPD | Fri Jan 17 08:00:00 IST 2020 | Sat Jan 18 16:00:00 IST 2020 | Thu Nov 07 08:00:00 IST 2019 | Thu Nov 21 16:00:00 IST 2019 |  | COMPLETED
1830 | TT_TASK | Diversion Culvert (C1) - Connect Diversion Culvert to Pumping Station | Sat Jan 18 08:00:00 IST 2020 | Sat Jan 18 16:00:00 IST 2020 | Thu Nov 28 08:00:00 IST 2019 | Thu Nov 28 16:00:00 IST 2019 |  | COMPLETED
1831 | TT_TASK | Diversion Culvert - Backfill and reinstate quay wall concrete block to 0.5m below 3rd layer of struts | Thu Jan 02 08:00:00 IST 2020 | Mon Jan 06 16:00:00 IST 2020 | Tue Dec 03 08:00:00 IST 2019 | Tue Dec 24 16:00:00 IST 2019 |  | COMPLETED
1832 | TT_TASK | Diversion Culvert - Remove 3rd layer of struts | Tue Jan 07 08:00:00 IST 2020 | Wed Jan 08 16:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Tue Dec 24 16:00:00 IST 2019 |  | COMPLETED
1833 | TT_TASK | Diversion Culvert - Backfill and reinstate quay wall concrete block to 0.5m below 2nd layer of struts | Thu Jan 09 08:00:00 IST 2020 | Mon Jan 13 16:00:00 IST 2020 | Sun Dec 08 08:00:00 IST 2019 | Sat Dec 28 16:00:00 IST 2019 |  | COMPLETED
1834 | TT_TASK | Diversion Culvert - Remove 2nd layer of struts | Tue Jan 14 08:00:00 IST 2020 | Wed Jan 15 16:00:00 IST 2020 | Wed Dec 11 08:00:00 IST 2019 | Sat Dec 28 16:00:00 IST 2019 |  | COMPLETED
1835 | TT_TASK | Diversion Culvert - Backfill and reinstate quay wall concrete block to 0.5m below 1st layer of struts (incl' utilities) | Thu Jan 02 08:00:00 IST 2020 | Mon Jan 06 16:00:00 IST 2020 | Mon Dec 30 08:00:00 IST 2019 | Sat Feb 15 16:00:00 IST 2020 |  | COMPLETED
1836 | TT_TASK | Diversion Culvert - Remove 1st layer of struts | Mon Feb 17 08:00:00 IST 2020 | Tue Feb 18 16:00:00 IST 2020 | Mon Feb 17 08:00:00 IST 2020 | Tue Feb 18 16:00:00 IST 2020 |  | COMPLETED
1837 | TT_TASK | Diversion Culvert (C2) - Construction of Diversion Culvert including excavation & ELS | Fri Jan 10 08:00:00 IST 2020 | Sat Feb 15 16:00:00 IST 2020 | Sat Nov 02 08:00:00 IST 2019 | Sun Dec 15 16:00:00 IST 2019 |  | COMPLETED
1838 | TT_TASK | Diversion Culvert - Backfill and reinstate to ground level including crest wall and fence | Wed Feb 19 08:00:00 IST 2020 | Tue Feb 25 16:00:00 IST 2020 | Wed Feb 19 08:00:00 IST 2020 | Tue Feb 25 16:00:00 IST 2020 |  | COMPLETED
1840 | TT_TASK | Event 016 - Bund Wall Settlement / Preventive grouting (50 nos.) | Mon Feb 26 08:00:00 IST 2018 | Thu Mar 22 16:00:00 IST 2018 | Mon Apr 02 08:00:00 IDT 2018 | Thu May 03 16:00:00 IDT 2018 |  | COMPLETED
1841 | TT_TASK | Event 017P - Advanced Preventive Grouting as per AAA amendment (Part 1 - 66 out of 86) | Tue Jun 26 08:00:00 IDT 2018 | Fri Aug 24 16:00:00 IDT 2018 | Sat Jun 02 08:00:00 IDT 2018 | Wed Jul 25 16:00:00 IDT 2018 |  | COMPLETED
1842 | TT_TASK | Event 017P - Advanced Preventive Grouting as per AAA amendment (Part 2 - 20 out of 86) | Mon Nov 26 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 | Thu Aug 30 08:00:00 IDT 2018 | Fri Sep 07 16:00:00 IDT 2018 |  | COMPLETED
1843 | TT_TASK | Event 025P - Preventive grouting stopped as it's being legalized via AAA amendment | Tue Jun 26 08:00:00 IDT 2018 | Fri Jun 29 16:00:00 IDT 2018 | Sat Jun 23 08:00:00 IDT 2018 | Tue Jun 26 16:00:00 IDT 2018 |  | COMPLETED
1844 | TT_TASK | Event 027 - Finalizing strategy and preparing for resubmission of re-sequencing amendment | Sun Aug 26 08:00:00 IDT 2018 | Sat Sep 15 16:00:00 IDT 2018 | Fri Aug 24 08:00:00 IDT 2018 | Thu Sep 27 16:00:00 IDT 2018 |  | COMPLETED
1845 | TT_TASK | Event 027 - BA5 Re-sequencing alternative(by ARUP) prioritizing Pump Station | Sat Dec 15 08:00:00 IST 2018 | Tue Feb 12 16:00:00 IST 2019 | Fri Sep 28 08:00:00 IDT 2018 | Thu Dec 13 16:00:00 IST 2018 |  | COMPLETED
1846 | TT_TASK | Event 044 - Plate Load Test PL2 at stratum of Pump Station | Sun Mar 31 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Wed Mar 13 08:00:00 IST 2019 | Mon Mar 18 16:00:00 IST 2019 |  | COMPLETED
1847 | TT_TASK | CWPS - Pipe Piles | Thu Jul 26 08:00:00 IDT 2018 | Thu Oct 04 16:00:00 IDT 2018 | Thu Jul 19 08:00:00 IDT 2018 | Fri Oct 12 16:00:00 IDT 2018 |  | COMPLETED
1848 | TT_TASK | CWPS - Grout Curtain | Wed Jan 09 08:00:00 IST 2019 | Tue Feb 19 16:00:00 IST 2019 | Thu Oct 18 08:00:00 IDT 2018 | Wed Nov 28 08:00:00 IST 2018 |  | COMPLETED
1849 | TT_TASK | CWPS - Pumping Test and Report Submission | Wed Dec 26 08:00:00 IST 2018 | Tue Jan 15 16:00:00 IST 2019 | Thu Dec 06 08:00:00 IST 2018 | Mon Dec 31 16:00:00 IST 2018 |  | COMPLETED
1850 | TT_TASK | CWPS - BD Consent for Commencement of Excavation & ELS | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Mon Dec 31 08:00:00 IST 2018 | Fri Feb 01 16:00:00 IST 2019 |  | COMPLETED
1851 | TT_TASK | CWPS - Excavate to 0.5m below 1st layer of struts | Mon Jan 28 08:00:00 IST 2019 | Sat Feb 16 16:00:00 IST 2019 | Fri Dec 28 08:00:00 IST 2018 | Thu Jan 17 08:00:00 IST 2019 |  | COMPLETED
1852 | TT_TASK | CWPS - Install 1st layer of struts | Sat Jan 26 08:00:00 IST 2019 | Sat Feb 02 16:00:00 IST 2019 | Thu Jan 17 08:00:00 IST 2019 | Thu Jan 31 16:00:00 IST 2019 |  | COMPLETED
1853 | TT_TASK | CWPS - Excavate to 0.5m below 2nd layer of struts | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 05 16:00:00 IDT 2019 | Thu Jan 31 08:00:00 IST 2019 | Thu Feb 14 16:00:00 IST 2019 |  | COMPLETED
1854 | TT_TASK | CWPS - Install 2nd layer of struts | Mon Apr 01 08:00:00 IDT 2019 | Mon Apr 08 16:00:00 IDT 2019 | Fri Feb 15 08:00:00 IST 2019 | Thu Feb 21 16:00:00 IST 2019 |  | COMPLETED
1855 | TT_TASK | CWPS - Excavate to 0.5m below 3rd layer of struts | Mon Apr 01 08:00:00 IDT 2019 | Thu Apr 04 16:00:00 IDT 2019 | Fri Feb 22 08:00:00 IST 2019 | Mon Feb 25 16:00:00 IST 2019 |  | COMPLETED
1856 | TT_TASK | CWPS - Install 3rd layer of struts | Mon Apr 01 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Tue Feb 26 08:00:00 IST 2019 | Sat Mar 02 16:00:00 IST 2019 |  | COMPLETED
1857 | TT_TASK | CWPS - Excavate to 0.5m below 4th layer struts | Mon Apr 08 08:00:00 IDT 2019 | Thu Apr 11 16:00:00 IDT 2019 | Sun Mar 03 08:00:00 IST 2019 | Tue Mar 12 16:00:00 IST 2019 |  | COMPLETED
1858 | TT_TASK | CWPS - Install 4th layer of struts | Mon Apr 01 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Mon Mar 11 08:00:00 IST 2019 | Mon Mar 18 16:00:00 IST 2019 |  | COMPLETED
1859 | TT_TASK | CWPS - Excavate to final excavation level -6.5 mPD | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 02 16:00:00 IDT 2019 | Mon Mar 11 08:00:00 IST 2019 | Sat Mar 23 16:00:00 IST 2019 |  | COMPLETED
1860 | TT_TASK | CWPS - Cast base slab | Mon Apr 01 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Sun Mar 24 08:00:00 IST 2019 | Wed Mar 27 16:00:00 IST 2019 |  | COMPLETED
1861 | TT_TASK | CWPS - Remove 4th layer of struts | Mon Apr 01 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Thu Mar 28 08:00:00 IST 2019 | Sat Mar 30 16:00:00 IDT 2019 |  | COMPLETED
1862 | TT_TASK | CWPS - Construct pumping station RC structures to 0.5m below 3rd layer of strut | Wed May 01 08:00:00 IDT 2019 | Sun May 05 16:00:00 IDT 2019 | Sat Mar 30 08:00:00 IDT 2019 | Fri Apr 05 16:00:00 IDT 2019 |  | COMPLETED
1863 | TT_TASK | CWPS - Backfill the void between RC wall and pipe pile wall to 0.5m below 3rd layer of strut | Wed May 01 08:00:00 IDT 2019 | Thu May 02 16:00:00 IDT 2019 | Fri Apr 05 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 |  | COMPLETED
1864 | TT_TASK | CWPS - Remove 3rd layer of struts | Fri May 03 08:00:00 IDT 2019 | Sat May 04 16:00:00 IDT 2019 | Sat Apr 06 08:00:00 IDT 2019 | Wed Apr 10 16:00:00 IDT 2019 |  | COMPLETED
1865 | TT_TASK | CWPS - Construct pumping station RC structures to 0.5m below 2nd layer of strut | Sun May 05 08:00:00 IDT 2019 | Fri May 10 16:00:00 IDT 2019 | Tue Apr 09 08:00:00 IDT 2019 | Thu Apr 18 16:00:00 IDT 2019 |  | COMPLETED
1866 | TT_TASK | CWPS - Backfill the void between RC wall and pipe pile wall to 0.5m below 2nd layer of strut | Wed May 01 08:00:00 IDT 2019 | Thu May 02 16:00:00 IDT 2019 | Fri Apr 19 08:00:00 IDT 2019 | Fri Apr 19 16:00:00 IDT 2019 |  | COMPLETED
1867 | TT_TASK | CWPS - Remove 2nd layer of struts | Thu May 02 08:00:00 IDT 2019 | Fri May 03 16:00:00 IDT 2019 | Sat Apr 13 08:00:00 IDT 2019 | Tue Apr 23 16:00:00 IDT 2019 |  | COMPLETED
1868 | TT_TASK | CWPS - Construct pumping station RC structures to 0.5m below 1st layer of strut | Wed May 01 08:00:00 IDT 2019 | Fri May 03 16:00:00 IDT 2019 | Sun Apr 14 08:00:00 IDT 2019 | Tue Apr 30 16:00:00 IDT 2019 |  | COMPLETED
1869 | TT_TASK | CWPS - Install CW pipes between Valve Chamber and Shaft A | Wed Jan 01 08:00:00 IST 2020 | Sat Jan 04 16:00:00 IST 2020 | Tue Dec 10 08:00:00 IST 2019 | Tue Dec 17 16:00:00 IST 2019 |  | COMPLETED
1870 | TT_TASK | CWPS - Backfill the void between RC wall and pipe pile wall to 0.5m below 1st layer of strut | Thu Aug 01 08:00:00 IDT 2019 | Fri Aug 02 16:00:00 IDT 2019 | Wed May 01 08:00:00 IDT 2019 | Wed May 01 16:00:00 IDT 2019 |  | COMPLETED
1871 | TT_TASK | CWPS - Remove 1st layer of struts | Fri May 03 08:00:00 IDT 2019 | Sat May 04 16:00:00 IDT 2019 | Thu Apr 25 08:00:00 IDT 2019 | Mon May 06 16:00:00 IDT 2019 |  | COMPLETED
1872 | TT_TASK | CWPS - Cast top slab of Pumping Station | Fri May 03 08:00:00 IDT 2019 | Sat May 11 16:00:00 IDT 2019 | Thu Apr 25 08:00:00 IDT 2019 | Sat May 18 16:00:00 IDT 2019 |  | COMPLETED
1873 | TT_TASK | CWPS - Trim pipe piles | Mon Jun 03 08:00:00 IDT 2019 | Tue Jun 04 16:00:00 IDT 2019 | Tue May 07 08:00:00 IDT 2019 | Mon May 20 16:00:00 IDT 2019 |  | COMPLETED
1874 | TT_TASK | CWPS - Backfill to ground level | Sat Jun 08 08:00:00 IDT 2019 | Sat Jun 08 16:00:00 IDT 2019 | Tue May 21 08:00:00 IDT 2019 | Tue May 21 16:00:00 IDT 2019 |  | COMPLETED
1875 | TT_TASK | CWPS - Construct misc RC structures (i.e. footings, trenches, staircase and switchroom) | Mon Jun 10 08:00:00 IDT 2019 | Sat Jun 29 16:00:00 IDT 2019 | Tue May 14 08:00:00 IDT 2019 | Sat Aug 10 16:00:00 IDT 2019 |  | COMPLETED
1876 | TT_TASK | CWPS - ABWF works | Thu Aug 01 08:00:00 IDT 2019 | Fri Sep 13 16:00:00 IDT 2019 | Fri Jun 21 08:00:00 IDT 2019 | Sat Dec 21 16:00:00 IST 2019 |  | COMPLETED
1877 | TT_TASK | CWPS - Building Service installation | Sat Aug 10 08:00:00 IDT 2019 | Mon Sep 23 16:00:00 IDT 2019 | Thu Jun 13 08:00:00 IDT 2019 | Thu Dec 19 16:00:00 IST 2019 |  | COMPLETED
1880 | TT_TASK | Event 003 - 6.6kVA Cable Strike at Shaft A | Tue Oct 24 08:00:00 IDT 2017 | Mon Nov 06 16:00:00 IST 2017 | Tue Oct 24 08:00:00 IDT 2017 | Fri Nov 24 16:00:00 IST 2017 |  | COMPLETED
1881 | TT_TASK | Event 004 - Trial trench prior to pre-drill | Tue Nov 07 08:00:00 IST 2017 | Thu Nov 09 16:00:00 IST 2017 | Sat Nov 25 08:00:00 IST 2017 | Thu Nov 30 16:00:00 IST 2017 |  | COMPLETED
1882 | TT_TASK | Event 004 - Pre-drill to verifiy rock head level of Shaft A | Sat Dec 02 08:00:00 IST 2017 | Thu Dec 21 16:00:00 IST 2017 | Fri Dec 01 08:00:00 IST 2017 | Wed Dec 20 16:00:00 IST 2017 |  | COMPLETED
1883 | TT_TASK | Event 004 - Trial trench prior to piling | Mon Nov 27 08:00:00 IST 2017 | Sun Dec 17 16:00:00 IST 2017 | Thu Dec 21 08:00:00 IST 2017 | Wed Jan 10 16:00:00 IST 2018 |  | COMPLETED
1884 | TT_TASK | Event 004a - Protection to existing cables and removal of existing light post | Mon Feb 26 08:00:00 IST 2018 | Sat Mar 10 16:00:00 IST 2018 | Mon Jan 08 08:00:00 IST 2018 | Sat Jan 20 16:00:00 IST 2018 |  | COMPLETED
1886 | TT_TASK | Event 011A - Install trial jet grout ( x3 nos.) | Mon Aug 27 08:00:00 IDT 2018 | Thu Aug 30 16:00:00 IDT 2018 | Fri Jul 27 08:00:00 IDT 2018 | Tue Jul 31 16:00:00 IDT 2018 |  | COMPLETED
1887 | TT_TASK | Event 011A - Core sample after 21 days from grout installed | Mon Nov 26 08:00:00 IST 2018 | Mon Dec 03 16:00:00 IST 2018 | Mon Sep 03 08:00:00 IDT 2018 | Fri Oct 12 16:00:00 IDT 2018 |  | COMPLETED
1888 | TT_TASK | Event 011A - Test to early achievement of 28 day strength | Tue Dec 04 08:00:00 IST 2018 | Thu Dec 06 16:00:00 IST 2018 | Tue Oct 02 08:00:00 IDT 2018 | Thu Oct 11 16:00:00 IDT 2018 |  | COMPLETED
1889 | TT_TASK | Event 011A - Formal test report issued for submission in 7 calendar days | Mon Nov 26 08:00:00 IST 2018 | Sun Dec 02 16:00:00 IST 2018 | Tue Nov 13 08:00:00 IST 2018 | Fri Nov 30 16:00:00 IST 2018 |  | COMPLETED
1890 | TT_TASK | Event 011A - Shaft A - BA8 for full scale grout block and excav below -4.6 mPD | Thu Feb 21 08:00:00 IST 2019 | Wed Mar 20 16:00:00 IST 2019 | Fri Nov 30 08:00:00 IST 2018 | Mon Dec 24 16:00:00 IST 2018 |  | COMPLETED
1892 | TT_TASK | Event 013 - Crane damaged and repaired | Tue Feb 27 08:00:00 IST 2018 | Wed Mar 07 16:00:00 IST 2018 | Fri Jan 19 08:00:00 IST 2018 | Sat Jan 27 16:00:00 IST 2018 |  | COMPLETED
1894 | TT_TASK | Event 014 - Clarifying extent of monitoring and instrumentation prerequisite to start of Shaft A piling works | Mon Feb 26 08:00:00 IST 2018 | Mon Mar 05 16:00:00 IST 2018 | Sun Feb 04 08:00:00 IST 2018 | Sun Feb 11 16:00:00 IST 2018 |  | COMPLETED
1896 | TT_TASK | Event 016 - Piling rigs demobilized and site clear for preventive grouting | Mon Feb 26 08:00:00 IST 2018 | Sun Mar 04 16:00:00 IST 2018 | Mon Mar 19 08:00:00 IST 2018 | Sun Mar 25 16:00:00 IDT 2018 |  | COMPLETED
1897 | TT_TASK | Event 016 - Preventive grouting (18 nos. out of 20 critical completed) | Mon Feb 26 08:00:00 IST 2018 | Tue Mar 06 16:00:00 IST 2018 | Mon Mar 26 08:00:00 IDT 2018 | Tue Apr 03 16:00:00 IDT 2018 |  | COMPLETED
1899 | TT_TASK | Event 016 - Awaiting engineering solution and management direction | Tue Apr 17 08:00:00 IDT 2018 | Wed Apr 25 16:00:00 IDT 2018 | Wed Apr 04 08:00:00 IDT 2018 | Mon Apr 16 16:00:00 IDT 2018 |  | COMPLETED
1900 | TT_TASK | Event 016 - Remedial grouting to bund wall (5 nos.) | Tue Apr 17 08:00:00 IDT 2018 | Wed Apr 25 16:00:00 IDT 2018 | Tue Apr 17 08:00:00 IDT 2018 | Thu Apr 19 16:00:00 IDT 2018 |  | COMPLETED
1901 | TT_TASK | Event 016 - Preventive grouting (the last remaining 2 nos.) | Wed May 30 08:00:00 IDT 2018 | Thu May 31 16:00:00 IDT 2018 | Sat Apr 21 08:00:00 IDT 2018 | Mon Apr 23 16:00:00 IDT 2018 |  | COMPLETED
1902 | TT_TASK | Event 016 - Remobilize piling rig | Sun Mar 31 08:00:00 IDT 2019 | Tue Apr 02 16:00:00 IDT 2019 | Sat Jan 26 08:00:00 IST 2019 | Mon Jan 28 16:00:00 IST 2019 |  | COMPLETED
1904 | TT_TASK | Event 017A - Advanced Preventive Grouting (42 nos.) | Tue Jun 26 08:00:00 IDT 2018 | Fri Jul 27 16:00:00 IDT 2018 | Tue May 29 08:00:00 IDT 2018 | Fri Jun 29 16:00:00 IDT 2018 |  | COMPLETED
1905 | TT_TASK | Event 021A - AAA amendment for Shaft A /Pump Station/ Diversion Culvert | Fri Jun 01 08:00:00 IDT 2018 | Sat Jun 30 16:00:00 IDT 2018 | Wed May 23 08:00:00 IDT 2018 | Tue Jul 03 16:00:00 IDT 2018 |  | COMPLETED
1906 | TT_TASK | Event 021A - Additional monitoring points hand-marked on approval drawings by BD | Tue Jun 26 08:00:00 IDT 2018 | Sun Jul 08 16:00:00 IDT 2018 | Sat Jun 23 00:00:00 IDT 2018 | Tue Jul 03 16:00:00 IDT 2018 |  | COMPLETED
1907 | TT_TASK | Event 023 - Re-seqeuncing Submission (Alternative) for Shaft A /Pump Station/ Diversion Culvert (BA5)[WITHDRAWN] | Thu Jul 26 08:00:00 IDT 2018 | Sun Sep 23 16:00:00 IDT 2018 | Fri Jun 29 08:00:00 IDT 2018 | Thu Aug 23 16:00:00 IDT 2018 |  | COMPLETED
1908 | TT_TASK | Event 025A - Preventive grouting stopped as it's being legalized via AAA amendment | Tue Jun 26 08:00:00 IDT 2018 | Fri Jun 29 16:00:00 IDT 2018 | Sat Jun 23 00:00:00 IDT 2018 | Tue Jun 26 16:00:00 IDT 2018 |  | COMPLETED
1909 | TT_TASK | Event 028 - Redo PPA#39 - 5th amendment (Type II) | Mon Nov 26 08:00:00 IST 2018 | Tue Dec 25 16:00:00 IST 2018 | Fri Jul 13 08:00:00 IDT 2018 | Mon Aug 13 16:00:00 IDT 2018 |  | COMPLETED
1910 | TT_TASK | Event 028 - Redo PPA #39 - install 508 dia. pile [FAILED] | Mon Nov 26 08:00:00 IST 2018 | Mon Nov 26 16:00:00 IST 2018 | Sat Oct 13 08:00:00 IDT 2018 | Sat Oct 13 16:00:00 IDT 2018 |  | COMPLETED
1911 | TT_TASK | Event 028 - Redo PPA#39 - remedial proposal added to 6th amendment | Tue Nov 27 08:00:00 IST 2018 | Sat Dec 08 16:00:00 IST 2018 | Mon Oct 15 08:00:00 IDT 2018 | Fri Oct 26 16:00:00 IDT 2018 |  | COMPLETED
1913 | TT_TASK | Event 028 - Redo PPA#39 - install replacement pile #42, 43 | Thu Nov 29 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 | Wed Nov 14 08:00:00 IST 2018 | Sat Nov 17 16:00:00 IST 2018 |  | COMPLETED
1914 | TT_TASK | Shaft A - Grout Blocks (at receiving area) (total drilling 830m) | Sat Jan 26 08:00:00 IST 2019 | Wed Mar 27 16:00:00 IST 2019 | Fri Jan 11 08:00:00 IST 2019 | Sat Feb 02 16:00:00 IST 2019 |  | COMPLETED
1916 | TT_TASK | Shaft A /Grout Block - Full core samples | Mon Apr 01 08:00:00 IDT 2019 | Mon Apr 15 16:00:00 IDT 2019 | Tue Jan 22 08:00:00 IST 2019 | Mon Feb 18 16:00:00 IST 2019 |  | COMPLETED
1917 | TT_TASK | Shaf A /Grout Block - Grout test to 28 day strength | Sun Mar 31 08:00:00 IDT 2019 | Tue Apr 02 16:00:00 IDT 2019 | Fri Feb 08 08:00:00 IST 2019 | Sat Mar 02 16:00:00 IST 2019 |  | COMPLETED
1918 | TT_TASK | Shaft A/ Grout Block - Jet grout assessment report | Sun Mar 31 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Sun Mar 03 08:00:00 IST 2019 | Wed May 08 16:00:00 IDT 2019 |  | COMPLETED
1919 | TT_TASK | Shaft A - BA8 consent for pile wall opening | Sat Jun 01 08:00:00 IDT 2019 | Fri Jun 28 16:00:00 IDT 2019 | Sat May 11 08:00:00 IDT 2019 | Wed Jun 05 16:00:00 IDT 2019 |  | COMPLETED
1920 | TT_TASK | Shaft A - 610 Dia. Pipe Pile Wall @ 750 c/c (41nos, total driving 1558m) | Thu Mar 15 08:00:00 IST 2018 | Thu Apr 26 16:00:00 IDT 2018 | Mon Feb 12 08:00:00 IST 2018 | Thu Oct 04 16:00:00 IDT 2018 |  | COMPLETED
1921 | TT_TASK | Shaft A - Grout Curtain (behind pipe pile wall) (total drilling 1271m) | Thu Nov 29 08:00:00 IST 2018 | Thu Dec 20 16:00:00 IST 2018 | Sat Nov 03 08:00:00 IST 2018 | Tue Dec 18 16:00:00 IST 2018 |  | COMPLETED
1922 | TT_TASK | Shaft A - Dewatering / observation wells (x 6 nos.) | Thu Jan 10 08:00:00 IST 2019 | Sat Jan 12 16:00:00 IST 2019 | Wed Dec 19 08:00:00 IST 2018 | Thu Dec 20 16:00:00 IST 2018 |  | COMPLETED
1923 | TT_TASK | Shaft A - Pumping Test and Report Submission | Sat Dec 29 08:00:00 IST 2018 | Fri Jan 18 16:00:00 IST 2019 | Sat Dec 22 08:00:00 IST 2018 | Wed Jan 23 16:00:00 IST 2019 |  | COMPLETED
1924 | TT_TASK | Shaft A - BD Consent for Excavation & ELS | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Wed Jan 23 08:00:00 IST 2019 | Mon Feb 18 16:00:00 IST 2019 |  | COMPLETED
1925 | TT_TASK | Shaft A - Excavate to below 1st layer of ring beam / install lagging plate | Mon Apr 01 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Wed Feb 06 08:00:00 IST 2019 | Sun Feb 10 16:00:00 IST 2019 |  | COMPLETED
1926 | TT_TASK | Shaft A - Intstall 1st layer of ring beam | Mon Apr 08 08:00:00 IDT 2019 | Wed Apr 10 16:00:00 IDT 2019 | Mon Feb 11 08:00:00 IST 2019 | Tue Feb 19 16:00:00 IST 2019 |  | COMPLETED
1927 | TT_TASK | Shaft A - Excavate to below 2nd layer of ring beam | Mon Apr 01 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Tue Feb 19 08:00:00 IST 2019 | Mon Feb 25 16:00:00 IST 2019 |  | COMPLETED
1928 | TT_TASK | Shaft A - Intstall lagging plates and 2nd layer of ring beam | Mon Apr 01 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Tue Feb 26 08:00:00 IST 2019 | Sun Mar 03 16:00:00 IST 2019 |  | COMPLETED
1929 | TT_TASK | Shaft A - Excavate to below 3rd layer of ring beam | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 05 16:00:00 IDT 2019 | Mon Mar 04 08:00:00 IST 2019 | Tue Mar 12 16:00:00 IST 2019 |  | COMPLETED
1930 | TT_TASK | Shaft A - Intstall lagging plates and 3rd layer of ring beam | Tue Apr 02 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Wed Mar 13 08:00:00 IST 2019 | Sun Mar 17 16:00:00 IST 2019 |  | COMPLETED
1931 | TT_TASK | Shaft A - Excavate to below 4th layer of ring beam | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 05 16:00:00 IDT 2019 | Mon Mar 18 08:00:00 IST 2019 | Tue Mar 26 16:00:00 IST 2019 |  | COMPLETED
1932 | TT_TASK | Shaft A - Intstall lagging plates and 4th layer of ring beam | Tue Apr 02 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Tue Mar 26 08:00:00 IST 2019 | Fri Apr 05 16:00:00 IDT 2019 |  | COMPLETED
1933 | TT_TASK | Shaft A - Excavate to below 5th layer of ring beam | Wed May 01 08:00:00 IDT 2019 | Mon May 06 16:00:00 IDT 2019 | Thu Apr 11 08:00:00 IDT 2019 | Sun Apr 21 16:00:00 IDT 2019 |  | COMPLETED
1934 | TT_TASK | Shaft A - Intstall lagging plates and 5th layer of ring beam | Thu May 02 08:00:00 IDT 2019 | Tue May 07 16:00:00 IDT 2019 | Sun Apr 21 08:00:00 IDT 2019 | Tue Apr 23 16:00:00 IDT 2019 |  | COMPLETED
1935 | TT_TASK | Shaft A - Excavate to below 6th layer of ring beam | Wed May 08 08:00:00 IDT 2019 | Mon May 13 16:00:00 IDT 2019 | Wed Apr 24 08:00:00 IDT 2019 | Mon Apr 29 16:00:00 IDT 2019 |  | COMPLETED
1936 | TT_TASK | Shaft A - Intstall lagging plates and 6th layer of ring beam | Thu May 09 08:00:00 IDT 2019 | Tue May 14 16:00:00 IDT 2019 | Mon Apr 29 08:00:00 IDT 2019 | Thu May 02 16:00:00 IDT 2019 |  | COMPLETED
1937 | TT_TASK | Shaft A - Excavate to below 7th layer of ring beam | Tue Jun 04 08:00:00 IDT 2019 | Sat Jun 08 16:00:00 IDT 2019 | Fri May 03 08:00:00 IDT 2019 | Thu May 09 16:00:00 IDT 2019 |  | COMPLETED
1938 | TT_TASK | Shaft A - Intstall lagging plates and 7th layer of ring beam | Wed Jun 05 08:00:00 IDT 2019 | Mon Jun 10 16:00:00 IDT 2019 | Thu May 09 08:00:00 IDT 2019 | Fri May 10 16:00:00 IDT 2019 |  | COMPLETED
1939 | TT_TASK | Shaft A - Excavate to below 8th layer of ring beam | Tue Jun 11 08:00:00 IDT 2019 | Fri Jun 14 16:00:00 IDT 2019 | Sat May 11 08:00:00 IDT 2019 | Wed May 15 16:00:00 IDT 2019 |  | COMPLETED
1940 | TT_TASK | Shaft A - Intstall lagging plates and 8thnd layer of ring beam | Wed Jun 12 08:00:00 IDT 2019 | Sat Jun 15 16:00:00 IDT 2019 | Wed May 15 08:00:00 IDT 2019 | Sun May 19 16:00:00 IDT 2019 |  | COMPLETED
1941 | TT_TASK | Shaft A - Excavate to below 9th layer of ring beam | Mon Jun 17 08:00:00 IDT 2019 | Sat Jun 22 16:00:00 IDT 2019 | Mon May 20 08:00:00 IDT 2019 | Sat May 25 16:00:00 IDT 2019 |  | COMPLETED
1942 | TT_TASK | Shaft A - Intstall lagging plates and 9th layer of ring beam | Tue Jun 18 08:00:00 IDT 2019 | Mon Jun 24 16:00:00 IDT 2019 | Sat May 25 08:00:00 IDT 2019 | Tue May 28 16:00:00 IDT 2019 |  | COMPLETED
1943 | TT_TASK | Shaft A - 9th layer of skin wall achieve required strength | Sun Sep 01 08:00:00 IDT 2019 | Sun Sep 01 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 |  | COMPLETED
1944 | TT_TASK | Shaft A - Excavate to below 10th layer of ring beam | Sat Jun 01 08:00:00 IDT 2019 | Wed Jun 05 16:00:00 IDT 2019 | Tue May 28 08:00:00 IDT 2019 | Thu May 30 16:00:00 IDT 2019 |  | COMPLETED
1945 | TT_TASK | Shaft A - Excavate 10th layer further down 2m | Mon Sep 02 08:00:00 IDT 2019 | Mon Sep 02 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 |  | COMPLETED
1946 | TT_TASK | Shaft A - Construct 10th layer of 250mm skin wall | Mon Sep 02 08:00:00 IDT 2019 | Mon Sep 02 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 |  | COMPLETED
1947 | TT_TASK | Shaft A - Intstall lagging plates and 10th layer of ring beam | Sat Jun 01 08:00:00 IDT 2019 | Wed Jun 05 16:00:00 IDT 2019 | Sat Jun 01 08:00:00 IDT 2019 | Sun Jun 09 16:00:00 IDT 2019 |  | COMPLETED
1948 | TT_TASK | Shaft A - Excavate 11th layer further down 2m | Mon Sep 02 08:00:00 IDT 2019 | Mon Sep 02 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 |  | COMPLETED
1949 | TT_TASK | Shaft A - Construct 11th layer of 250mm skin wall | Mon Sep 02 08:00:00 IDT 2019 | Mon Sep 02 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 |  | COMPLETED
1950 | TT_TASK | Shaft A - 11th layer of skin wall achieve required strength | Mon Sep 02 08:00:00 IDT 2019 | Mon Sep 02 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 |  | COMPLETED
1951 | TT_TASK | Shaft A - Excavate 12th layer further down 2m | Mon Sep 02 08:00:00 IDT 2019 | Mon Sep 02 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 |  | COMPLETED
1952 | TT_TASK | Shaft A - Construct 12th layer of 250mm skin wall | Mon Sep 02 08:00:00 IDT 2019 | Mon Sep 02 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 |  | COMPLETED
1953 | TT_TASK | Shaft A - Excavate 13th layer further down 2m | Mon Sep 02 08:00:00 IDT 2019 | Mon Sep 02 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 |  | COMPLETED
1954 | TT_TASK | Shaft A - Construct 13th layer of 250mm skin wall | Mon Sep 02 08:00:00 IDT 2019 | Mon Sep 02 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 |  | COMPLETED
1955 | TT_TASK | Shaft A - 13th layer of skin wall achieve required strength | Mon Sep 02 08:00:00 IDT 2019 | Mon Sep 02 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 |  | COMPLETED
1956 | TT_TASK | Shaft A - Excavate to final excavation level -22 mPD / Install lagging plate | Thu Jun 06 08:00:00 IDT 2019 | Thu Jun 06 16:00:00 IDT 2019 | Fri May 31 08:00:00 IDT 2019 | Fri May 31 16:00:00 IDT 2019 |  | COMPLETED
1957 | TT_TASK | Shaft A - Cast bottom skin wall, base slab and receiving platform | Thu Aug 01 08:00:00 IDT 2019 | Wed Aug 14 16:00:00 IDT 2019 | Mon Jun 03 08:00:00 IDT 2019 | Thu Jul 11 16:00:00 IDT 2019 |  | COMPLETED
1958 | TT_TASK | Shaft A - Break through pipe pile wall and at the TBM receiving areas | Fri Sep 06 08:00:00 IDT 2019 | Tue Sep 10 16:00:00 IDT 2019 | Mon Aug 05 08:00:00 IDT 2019 | Fri Aug 09 16:00:00 IDT 2019 |  | COMPLETED
1959 | TT_TASK | Shaft A - Get the shaft ready for receiving TBM | Thu Aug 01 08:00:00 IDT 2019 | Mon Aug 05 16:00:00 IDT 2019 | Fri Jul 12 08:00:00 IDT 2019 | Sun Aug 04 16:00:00 IDT 2019 |  | COMPLETED
1960 | TT_TASK | Shaft A - Cement mortar and with flooding with water | Wed Sep 11 08:00:00 IDT 2019 | Thu Sep 12 16:00:00 IDT 2019 | Sat Aug 10 08:00:00 IDT 2019 | Sun Aug 11 16:00:00 IDT 2019 |  | COMPLETED
1961 | TT_TASK | Shaft A - Receive TBM and demob off site | Fri Nov 01 08:00:00 IST 2019 | Sat Nov 09 16:00:00 IST 2019 | Thu Aug 22 08:00:00 IDT 2019 | Tue Sep 24 16:00:00 IDT 2019 |  | COMPLETED
1962 | TT_TASK | Shaft A - Install 1st vertical CW pipe section | Fri Nov 01 08:00:00 IST 2019 | Wed Nov 06 16:00:00 IST 2019 | Thu Oct 10 08:00:00 IDT 2019 | Sun Oct 13 16:00:00 IDT 2019 |  | COMPLETED
1963 | TT_TASK | Shaft A - Backfill to -18 mPD approx. 1m below the next pipe joint | Fri Nov 01 08:00:00 IST 2019 | Tue Nov 05 16:00:00 IST 2019 | Mon Oct 14 08:00:00 IDT 2019 | Mon Oct 14 16:00:00 IDT 2019 |  | COMPLETED
1964 | TT_TASK | Shaft A - Install remaining vertiicle CW pipe sections / fittings / headers | Fri Nov 01 08:00:00 IST 2019 | Mon Nov 18 16:00:00 IST 2019 | Thu Oct 24 08:00:00 IDT 2019 | Sat Nov 09 16:00:00 IST 2019 |  | COMPLETED
1965 | TT_TASK | Shaft A - Backfill from -18 to +0.4 mPD | Fri Nov 01 08:00:00 IST 2019 | Mon Nov 18 16:00:00 IST 2019 | Mon Oct 28 08:00:00 IST 2019 | Tue Nov 12 16:00:00 IST 2019 |  | COMPLETED
1966 | TT_TASK | Shaft A - Construct rocket slab & open pipe pile wall | Wed Jan 01 08:00:00 IST 2020 | Tue Jan 07 16:00:00 IST 2020 | Wed Nov 13 08:00:00 IST 2019 | Mon Dec 09 16:00:00 IST 2019 |  | COMPLETED
1967 | TT_TASK | Shaft A - Backfill to ground level | Wed Jan 01 08:00:00 IST 2020 | Thu Jan 02 16:00:00 IST 2020 | Wed Dec 18 08:00:00 IST 2019 | Thu Dec 19 16:00:00 IST 2019 |  | COMPLETED
1969 | TT_TASK | Event 002 - Shaft F Pre-drilling (5 nos.) | Fri Oct 06 08:00:00 IDT 2017 | Sat Oct 14 16:00:00 IDT 2017 | Fri Oct 06 08:00:00 IDT 2017 | Tue Oct 17 16:00:00 IDT 2017 |  | COMPLETED
1970 | TT_TASK | Event 002a - Shaft F Pre-drilling (4 nos. additional) | Thu Oct 19 08:00:00 IDT 2017 | Wed Nov 01 16:00:00 IST 2017 | Thu Oct 19 08:00:00 IDT 2017 | Wed Nov 01 16:00:00 IST 2017 |  | COMPLETED
1971 | TT_TASK | Event 003a - 6.6kVA cable strike at Shaft A | Mon Oct 23 08:00:00 IDT 2017 | Mon Oct 23 16:00:00 IDT 2017 | Tue Oct 24 08:00:00 IDT 2017 | Fri Nov 17 16:00:00 IST 2017 |  | COMPLETED
1973 | TT_TASK | Event 003a - Additional trial trenhes prior to pipe piling | Mon Oct 23 08:00:00 IDT 2017 | Mon Oct 23 16:00:00 IDT 2017 | Sat Nov 18 08:00:00 IST 2017 | Thu Nov 23 16:00:00 IST 2017 |  | COMPLETED
1975 | TT_TASK | Event 011F - Install trial get grout ( x3 nos.) | Mon Apr 23 08:00:00 IDT 2018 | Wed Apr 25 16:00:00 IDT 2018 | Wed Mar 07 08:00:00 IST 2018 | Fri Mar 09 16:00:00 IST 2018 |  | COMPLETED
1976 | TT_TASK | Event 011F - Core sample after 21 days from grout installed | Mon May 07 08:00:00 IDT 2018 | Sat May 19 16:00:00 IDT 2018 | Thu Mar 29 08:00:00 IDT 2018 | Thu May 24 16:00:00 IDT 2018 |  | COMPLETED
1977 | TT_TASK | Event 011F - Test to early achievement of 28 day strength | Thu Jul 26 08:00:00 IDT 2018 | Sat Jul 28 16:00:00 IDT 2018 | Thu Jul 12 08:00:00 IDT 2018 | Sat Jul 14 16:00:00 IDT 2018 |  | COMPLETED
1978 | TT_TASK | Event 011F - Formal test report issued for submission in 7 calendar days | Thu Aug 02 08:00:00 IDT 2018 | Wed Aug 08 16:00:00 IDT 2018 | Sun Jul 15 08:00:00 IDT 2018 | Sat Jul 28 16:00:00 IDT 2018 |  | COMPLETED
1979 | TT_TASK | Event 011F - BD interview on trial jet grout assessment report | Sat Dec 01 08:00:00 IST 2018 | Sat Dec 01 16:00:00 IST 2018 | Tue Sep 04 08:00:00 IDT 2018 | Tue Sep 04 16:00:00 IDT 2018 |  | COMPLETED
1980 | TT_TASK | Event 011F - Shaft F - BA8 for full scale grout block and excav below -9.6 mPD | Tue Dec 11 08:00:00 IST 2018 | Mon Jan 07 16:00:00 IST 2019 | Fri Oct 05 08:00:00 IDT 2018 | Thu Nov 22 08:00:00 IST 2018 |  | COMPLETED
1982 | TT_TASK | Event 012F - Settlement Assessment - Report preparation and submission to BD | Mon Apr 23 08:00:00 IDT 2018 | Thu May 03 16:00:00 IDT 2018 | Fri Mar 02 08:00:00 IST 2018 | Tue Mar 13 16:00:00 IST 2018 |  | COMPLETED
1983 | TT_TASK | Event 012F - Settlement Assessment - Report review by BD | Fri May 04 08:00:00 IDT 2018 | Thu May 17 16:00:00 IDT 2018 | Wed Mar 14 08:00:00 IST 2018 | Fri Jun 22 16:00:00 IDT 2018 |  | COMPLETED
1985 | TT_TASK | Event 012F - Request and Issue of ROI for screen wall and other precautionary measures | Mon Apr 23 08:00:00 IDT 2018 | Fri Apr 27 16:00:00 IDT 2018 | Wed Mar 14 08:00:00 IST 2018 | Wed Mar 28 16:00:00 IDT 2018 |  | COMPLETED
1986 | TT_TASK | Event 012F - Settlement Assessment - Install screen wall as precautionary measure (i.e. JCG x17 nos.) | Sat Apr 28 08:00:00 IDT 2018 | Sat May 19 16:00:00 IDT 2018 | Thu Mar 29 08:00:00 IDT 2018 | Fri Apr 13 16:00:00 IDT 2018 |  | COMPLETED
1987 | TT_TASK | Event 012F - Settlement Assessment - Install TAM grout in between screen wall and Shaft F pile wall | Sat Apr 28 08:00:00 IDT 2018 | Tue May 08 16:00:00 IDT 2018 | Thu Apr 19 08:00:00 IDT 2018 | Fri Apr 27 16:00:00 IDT 2018 |  | COMPLETED
1988 | TT_TASK | Event 012F - Settlement Assessment - ADMS to existing CWP (x32) | Sat Apr 28 08:00:00 IDT 2018 | Tue May 29 16:00:00 IDT 2018 | Wed May 02 08:00:00 IDT 2018 | Fri Jun 15 16:00:00 IDT 2018 |  | COMPLETED
1989 | TT_TASK | Event 012F - Settlement Assessment - SPT (x3) | Sat Apr 28 08:00:00 IDT 2018 | Sat May 26 16:00:00 IDT 2018 | Sat May 05 08:00:00 IDT 2018 | Fri Jun 01 16:00:00 IDT 2018 |  | COMPLETED
1990 | TT_TASK | Event 012F - Settlement Assessment - Trial Pile (x3) | Sat Apr 28 08:00:00 IDT 2018 | Mon May 14 16:00:00 IDT 2018 | Thu May 17 08:00:00 IDT 2018 | Thu May 31 16:00:00 IDT 2018 |  | COMPLETED
1991 | TT_TASK | Event 012F - Settlement Assessment - Exposing CWP pipe crown (x7) | Sat Apr 28 08:00:00 IDT 2018 | Tue May 08 16:00:00 IDT 2018 | Mon May 21 08:00:00 IDT 2018 | Mon May 28 16:00:00 IDT 2018 |  | COMPLETED
1992 | TT_TASK | Event 012F - Settlement Assessment - Full core sample (x1) of jet grout screen wall | Tue Jun 26 08:00:00 IDT 2018 | Wed Jul 04 16:00:00 IDT 2018 | Sat May 26 08:00:00 IDT 2018 | Fri Jun 08 16:00:00 IDT 2018 |  | COMPLETED
1993 | TT_TASK | Event 022 - Additional monitoring points hand-marked by BD during AAA amendement | Tue Jun 26 08:00:00 IDT 2018 | Sun Jul 15 16:00:00 IDT 2018 | Sat Jun 23 08:00:00 IDT 2018 | Wed Jul 04 16:00:00 IDT 2018 |  | COMPLETED
1994 | TT_TASK | Event 022 - Re-do Stage 1 pump test as per AAA amendment | Thu Jun 28 08:00:00 IDT 2018 | Mon Jul 09 16:00:00 IDT 2018 | Thu Jun 28 08:00:00 IDT 2018 | Sun Jul 22 16:00:00 IDT 2018 |  | COMPLETED
1995 | TT_TASK | Event 022 - Stage 2 pump test as per AAA amendment | Thu Jul 26 08:00:00 IDT 2018 | Thu Aug 09 16:00:00 IDT 2018 | Mon Jul 23 08:00:00 IDT 2018 | Wed Aug 15 16:00:00 IDT 2018 |  | COMPLETED
1996 | TT_TASK | Event 022 - Re-do Stage 2 pump test at -9.6 mPD | Wed Dec 26 08:00:00 IST 2018 | Tue Jan 15 16:00:00 IST 2019 | Sat Dec 15 08:00:00 IST 2018 | Tue Jan 08 16:00:00 IST 2019 |  | COMPLETED
1997 | TT_TASK | Event 024 - Re-do full core of trial jet grout x1 no. as per AAA amendment | Thu Jul 26 08:00:00 IDT 2018 | Wed Aug 01 16:00:00 IDT 2018 | Mon Jul 09 08:00:00 IDT 2018 | Wed Jul 11 16:00:00 IDT 2018 |  | COMPLETED
1998 | TT_TASK | Event 024 - Re-do full core / backfill grout to core hole | Thu Jul 26 08:00:00 IDT 2018 | Thu Jul 26 16:00:00 IDT 2018 | Thu Jul 12 00:00:00 IDT 2018 | Thu Jul 12 16:00:00 IDT 2018 |  | COMPLETED
1999 | TT_TASK | Event 024 - Re-do full core / curing grout cube for 28 days | Thu Jul 26 08:00:00 IDT 2018 | Wed Aug 22 16:00:00 IDT 2018 | Fri Jul 13 08:00:00 IDT 2018 | Thu Aug 09 16:00:00 IDT 2018 |  | COMPLETED
2000 | TT_TASK | Event 024 - Redo full core / cube test and lab report | Mon Nov 26 08:00:00 IST 2018 | Fri Nov 30 16:00:00 IST 2018 | Fri Aug 03 08:00:00 IDT 2018 | Sat Aug 11 16:00:00 IDT 2018 |  | COMPLETED
2001 | TT_TASK | Event 029 - MC grouting note amendment (Type II) | Thu Jul 26 08:00:00 IDT 2018 | Fri Aug 24 16:00:00 IDT 2018 | Fri Jul 13 08:00:00 IDT 2018 | Mon Aug 13 16:00:00 IDT 2018 |  | COMPLETED
2002 | TT_TASK | Event 029 - Resubmit BA14 for grout curtain | Sun Aug 26 08:00:00 IDT 2018 | Sun Aug 26 16:00:00 IDT 2018 | Mon Aug 13 08:00:00 IDT 2018 | Mon Aug 13 16:00:00 IDT 2018 |  | COMPLETED
2003 | TT_TASK | Event 030 - Additional Tests / Agree and finalize test method and location | Thu Jul 26 08:00:00 IDT 2018 | Sun Sep 23 16:00:00 IDT 2018 | Sat Jun 23 08:00:00 IDT 2018 | Thu Aug 23 16:00:00 IDT 2018 |  | COMPLETED
2004 | TT_TASK | Event 030 - Additional Tests / Carry out the additional tests | Sun Aug 26 08:00:00 IDT 2018 | Fri Sep 14 16:00:00 IDT 2018 | Fri Aug 24 08:00:00 IDT 2018 | Fri Sep 14 16:00:00 IDT 2018 |  | COMPLETED
2005 | TT_TASK | Event 030 - Additional tests / (Type II) Amendment | Sun Aug 26 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Thu Aug 23 08:00:00 IDT 2018 | Wed Sep 19 16:00:00 IDT 2018 |  | COMPLETED
2006 | TT_TASK | Event 030 - Additional tests / Prepare and submit assessment report to BD 1 week prior to excavation below +3.2 | Mon Nov 26 08:00:00 IST 2018 | Sun Dec 02 16:00:00 IST 2018 | Wed Sep 19 08:00:00 IDT 2018 | Tue Sep 25 16:00:00 IDT 2018 |  | COMPLETED
2007 | TT_TASK | Shaft F - Grout Blocks (at launching areas) (total drilling 1822m) | Thu Dec 27 08:00:00 IST 2018 | Wed Jan 23 16:00:00 IST 2019 | Mon Nov 26 08:00:00 IST 2018 | Wed Feb 27 16:00:00 IST 2019 |  | COMPLETED
2009 | TT_TASK | Shaft F /Grout Block - Core sample after 21 days from grout installed (AD TBC) | Thu Apr 18 08:00:00 IDT 2019 | Wed May 15 16:00:00 IDT 2019 | Tue Feb 26 08:00:00 IST 2019 | Mon Mar 18 16:00:00 IST 2019 |  | COMPLETED
2010 | TT_TASK | Shaf F /Grout Block - Test to early achievement of 28 day strength (AD TBC) | Thu May 16 08:00:00 IDT 2019 | Sat May 18 16:00:00 IDT 2019 | Tue Mar 19 08:00:00 IST 2019 | Thu Mar 21 16:00:00 IST 2019 |  | COMPLETED
2011 | TT_TASK | Shaft F/ Grout Block - Formal test report issued for submission in 7 calendar days (AD TBC) | Sun May 19 08:00:00 IDT 2019 | Sat May 25 16:00:00 IDT 2019 | Fri Mar 22 08:00:00 IST 2019 | Thu Mar 28 16:00:00 IST 2019 |  | COMPLETED
2012 | TT_TASK | Shaft F - BA8 consent for pile wall opening | Wed May 01 08:00:00 IDT 2019 | Tue May 28 16:00:00 IDT 2019 | Thu Apr 18 08:00:00 IDT 2019 | Fri May 31 16:00:00 IDT 2019 |  | COMPLETED
2013 | TT_TASK | Shaft F - 610 Dia. Pipe Pile Wall @ 750 c/c (57 nos., total driving 2223m) | Wed Nov 01 08:00:00 IST 2017 | Thu Dec 14 16:00:00 IST 2017 | Fri Nov 24 08:00:00 IST 2017 | Fri Mar 02 16:00:00 IST 2018 |  | COMPLETED
2014 | TT_TASK | Shaft F - BD Consent for Commencement of Excavation & ELS (above +3.2 mPD) | Fri Jun 15 08:00:00 IDT 2018 | Thu Jul 12 16:00:00 IDT 2018 | Thu May 03 08:00:00 IDT 2018 | Fri Jul 06 16:00:00 IDT 2018 |  | COMPLETED
2015 | TT_TASK | Shaft F - Grout Curtain (behind pipe pile wall) (total drilling 1950m) | Thu Mar 01 08:00:00 IST 2018 | Mon Apr 09 16:00:00 IDT 2018 | Fri Feb 23 08:00:00 IST 2018 | Mon Mar 26 16:00:00 IDT 2018 |  | COMPLETED
2016 | TT_TASK | Shaft F - Install pump well and observation well | Mon Apr 23 08:00:00 IDT 2018 | Thu May 03 16:00:00 IDT 2018 | Sat Mar 17 08:00:00 IST 2018 | Mon Mar 26 16:00:00 IDT 2018 |  | COMPLETED
2017 | TT_TASK | Shaft F - Pumping Test (Stage 1) [not accepted by BD] | Sun May 06 08:00:00 IDT 2018 | Mon May 14 16:00:00 IDT 2018 | Thu Mar 29 08:00:00 IDT 2018 | Mon Apr 30 16:00:00 IDT 2018 |  | COMPLETED
2018 | TT_TASK | Shaft F - Prepare and submit Stage 1 pumping test report | Thu Jul 26 08:00:00 IDT 2018 | Mon Jul 30 16:00:00 IDT 2018 | Mon Jul 23 08:00:00 IDT 2018 | Tue Aug 07 16:00:00 IDT 2018 |  | COMPLETED
2019 | TT_TASK | Shaft F - BD Consent for Commencement of Excavation & ELS (from +3.2 to -9.6 mPD)[WITHDRAWN] | Sun Aug 26 08:00:00 IDT 2018 | Sat Sep 08 16:00:00 IDT 2018 | Mon Jul 30 08:00:00 IDT 2018 | Sun Aug 12 16:00:00 IDT 2018 |  | COMPLETED
2020 | TT_TASK | Shaft F - BD Consent for Commencement of Excavation & ELS (from +3.2 to -9.6 mPD)[RESUBMIT] | Sun Sep 09 08:00:00 IDT 2018 | Sat Oct 06 16:00:00 IDT 2018 | Mon Aug 13 08:00:00 IDT 2018 | Fri Sep 07 16:00:00 IDT 2018 |  | COMPLETED
2021 | TT_TASK | Shaft F - Excavate to below 1st layer of ring beam / Install lagging plates | Mon Aug 27 08:00:00 IDT 2018 | Thu Sep 06 16:00:00 IDT 2018 | Thu Aug 16 08:00:00 IDT 2018 | Fri Sep 07 16:00:00 IDT 2018 |  | COMPLETED
2022 | TT_TASK | Shaft F - BD Consent for Commencement of Excavation & ELS below -17 mPD | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Tue Jan 08 08:00:00 IST 2019 | Wed Feb 13 16:00:00 IST 2019 |  | COMPLETED
2023 | TT_TASK | Shaft F - Intstall 1st layer of ring beam | Tue Nov 27 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 | Sat Sep 08 08:00:00 IDT 2018 | Sat Sep 29 16:00:00 IDT 2018 |  | COMPLETED
2024 | TT_TASK | Shaft F - Excavate to below 2nd layer of ring beam | Mon Nov 26 08:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 | Tue Oct 02 08:00:00 IDT 2018 | Sat Oct 06 16:00:00 IDT 2018 |  | COMPLETED
2025 | TT_TASK | Shaft F - Intstall lagging plates and 2nd layer of ring beam | Tue Nov 27 08:00:00 IST 2018 | Fri Nov 30 16:00:00 IST 2018 | Thu Oct 04 08:00:00 IDT 2018 | Thu Oct 11 16:00:00 IDT 2018 |  | COMPLETED
2026 | TT_TASK | Shaft F - Excavate to below 3rd layer of ring beam | Sat Dec 01 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 | Thu Oct 11 08:00:00 IDT 2018 | Wed Oct 17 16:00:00 IDT 2018 |  | COMPLETED
2027 | TT_TASK | Shaft F - Intstall lagging plates and 3rd layer of ring beam | Mon Dec 03 08:00:00 IST 2018 | Thu Dec 06 16:00:00 IST 2018 | Fri Oct 12 08:00:00 IDT 2018 | Sun Oct 28 16:00:00 IST 2018 |  | COMPLETED
2028 | TT_TASK | Shaft F - Excavate to below 4th layer of ring beam | Fri Dec 07 08:00:00 IST 2018 | Tue Dec 11 16:00:00 IST 2018 | Mon Oct 29 08:00:00 IST 2018 | Sat Nov 03 16:00:00 IST 2018 |  | COMPLETED
2029 | TT_TASK | Shaft F - Intstall lagging plates and 4th layer of ring beam | Sat Dec 08 08:00:00 IST 2018 | Wed Dec 12 16:00:00 IST 2018 | Wed Oct 31 08:00:00 IST 2018 | Thu Nov 08 16:00:00 IST 2018 |  | COMPLETED
2030 | TT_TASK | Shaft F - Excavate to below 5th layer of ring beam | Mon Nov 26 08:00:00 IST 2018 | Fri Nov 30 16:00:00 IST 2018 | Fri Nov 09 08:00:00 IST 2018 | Wed Nov 14 16:00:00 IST 2018 |  | COMPLETED
2031 | TT_TASK | Shaft F - Intstall lagging plates and 5th layer of ring beam (AF TBC) | Mon Nov 26 08:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 | Sat Nov 10 08:00:00 IST 2018 | Tue Nov 20 16:00:00 IST 2018 |  | COMPLETED
2032 | TT_TASK | Shaft F - Excavate to below 6th layer of ring beam (AS TBC) | Mon Nov 26 08:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 | Wed Nov 21 08:00:00 IST 2018 | Tue Nov 27 16:00:00 IST 2018 |  | COMPLETED
2033 | TT_TASK | Shaft F - Intstall lagging plates and 6th layer of ring beam | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Fri Nov 23 08:00:00 IST 2018 | Mon Dec 03 16:00:00 IST 2018 |  | COMPLETED
2034 | TT_TASK | Shaft F - Excavate to below 7th layer of ring beam | Thu Jan 31 08:00:00 IST 2019 | Wed Feb 06 16:00:00 IST 2019 | Tue Jan 01 08:00:00 IST 2019 | Mon Jan 07 16:00:00 IST 2019 |  | COMPLETED
2035 | TT_TASK | Shaft F - Intstall lagging plates and 7th layer of ring beam | Sat Jan 26 08:00:00 IST 2019 | Tue Feb 05 16:00:00 IST 2019 | Thu Jan 03 08:00:00 IST 2019 | Tue Jan 15 16:00:00 IST 2019 |  | COMPLETED
2036 | TT_TASK | Shaft F - Excavate to below 8th layer of ring beam | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 01 16:00:00 IST 2019 | Tue Jan 15 08:00:00 IST 2019 | Sun Jan 20 16:00:00 IST 2019 |  | COMPLETED
2037 | TT_TASK | Shaft F - Intstall lagging plates and 8th layer of ring beam | Sat Jan 26 08:00:00 IST 2019 | Tue Feb 05 16:00:00 IST 2019 | Wed Jan 16 08:00:00 IST 2019 | Fri Jan 25 16:00:00 IST 2019 |  | COMPLETED
2038 | TT_TASK | Shaft F - Excavate to below 9th layer of ring beam | Mon Apr 01 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 01 16:00:00 IST 2019 |  | COMPLETED
2039 | TT_TASK | Shaft F - Intstall lagging plates and 9th layer of ring beam | Mon Apr 01 08:00:00 IDT 2019 | Wed Apr 10 16:00:00 IDT 2019 | Sun Jan 27 08:00:00 IST 2019 | Fri Feb 08 16:00:00 IST 2019 |  | COMPLETED
2040 | TT_TASK | Shaft F - Excavate to below 10th layer of ring beam | Thu Apr 11 08:00:00 IDT 2019 | Tue Apr 16 16:00:00 IDT 2019 | Fri Feb 08 08:00:00 IST 2019 | Thu Feb 14 16:00:00 IST 2019 |  | COMPLETED
2041 | TT_TASK | Shaft F - Intstall lagging plates and 10th layer of ring beam | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 05 16:00:00 IDT 2019 | Sat Feb 09 08:00:00 IST 2019 | Thu Feb 21 16:00:00 IST 2019 |  | COMPLETED
2042 | TT_TASK | Shaft F - Excavate to below 11th layer of ring beam | Sat Apr 06 08:00:00 IDT 2019 | Thu Apr 11 16:00:00 IDT 2019 | Fri Feb 22 08:00:00 IST 2019 | Thu Feb 28 16:00:00 IST 2019 |  | COMPLETED
2043 | TT_TASK | Shaft F - Intstall lagging plates and 11th layer of ring beam | Mon Apr 08 08:00:00 IDT 2019 | Fri Apr 12 16:00:00 IDT 2019 | Sat Feb 23 08:00:00 IST 2019 | Fri Mar 08 16:00:00 IST 2019 |  | COMPLETED
2044 | TT_TASK | Shaft F - Excavate to below 12th layer of ring beam | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 16 16:00:00 IDT 2019 | Sat Mar 09 08:00:00 IST 2019 | Sun Apr 07 16:00:00 IDT 2019 |  | COMPLETED
2045 | TT_TASK | Shaft F - Intstall lagging plates and 12th layer of ring beam | Thu Apr 04 08:00:00 IDT 2019 | Fri Apr 05 16:00:00 IDT 2019 | Sat Mar 16 08:00:00 IST 2019 | Tue Apr 09 16:00:00 IDT 2019 |  | COMPLETED
2046 | TT_TASK | Shaft F - Excavate to below 13th layer of ring beam | Thu May 09 08:00:00 IDT 2019 | Fri May 17 16:00:00 IDT 2019 | Wed Apr 10 08:00:00 IDT 2019 | Mon May 06 16:00:00 IDT 2019 |  | COMPLETED
2047 | TT_TASK | Shaft F - Intstall lagging plates and 13th layer of ring beam | Sat Jun 01 08:00:00 IDT 2019 | Mon Jun 10 16:00:00 IDT 2019 | Wed May 01 08:00:00 IDT 2019 | Thu May 09 16:00:00 IDT 2019 |  | COMPLETED
2048 | TT_TASK | Shaft F - BD inspection on stratum | Tue Jun 11 08:00:00 IDT 2019 | Tue Jun 11 16:00:00 IDT 2019 | Fri May 10 08:00:00 IDT 2019 | Fri May 10 16:00:00 IDT 2019 |  | COMPLETED
2049 | TT_TASK | Shaft F - Cast base slab and bottom skin wall | Sat Jun 01 08:00:00 IDT 2019 | Fri Jun 14 16:00:00 IDT 2019 | Sat May 11 08:00:00 IDT 2019 | Fri Jun 07 16:00:00 IDT 2019 |  | COMPLETED
2050 | TT_TASK | Shaft F - Break through pipe pile wall for TBM driving to Shaft A | Mon Aug 05 08:00:00 IDT 2019 | Thu Aug 15 16:00:00 IDT 2019 | Sat Jun 08 08:00:00 IDT 2019 | Tue Jun 25 16:00:00 IDT 2019 |  | COMPLETED
2051 | TT_TASK | Shaft F - Break through pipe pile wall for TBM driving from Shaft E | Thu Nov 07 08:00:00 IST 2019 | Sun Nov 17 16:00:00 IST 2019 | Mon Sep 09 08:00:00 IDT 2019 | Tue Sep 24 16:00:00 IDT 2019 |  | COMPLETED
2052 | TT_TASK | Shaft F - Install bulkhead and flooding the shaft (E drive) | Mon Nov 18 08:00:00 IST 2019 | Tue Nov 19 16:00:00 IST 2019 | Wed Oct 09 08:00:00 IDT 2019 | Sun Oct 13 16:00:00 IDT 2019 |  | COMPLETED
2053 | TT_TASK | Shaft F - Set up and launch micro TBM to Shaft A | Thu Aug 01 08:00:00 IDT 2019 | Sun Aug 25 16:00:00 IDT 2019 | Sat Jun 15 08:00:00 IDT 2019 | Mon Jul 08 16:00:00 IDT 2019 |  | COMPLETED
2054 | TT_TASK | Shaft F - Micro tunneling and pipe jacking to Shaft A | Thu Aug 01 08:00:00 IDT 2019 | Sun Aug 18 16:00:00 IDT 2019 | Tue Jul 09 08:00:00 IDT 2019 | Wed Aug 21 16:00:00 IDT 2019 |  | COMPLETED
2055 | TT_TASK | Shaft F - Grouting and Welding CWP between Shaft A and Shaft F | Sun Nov 10 08:00:00 IST 2019 | Fri Nov 29 16:00:00 IST 2019 | Thu Sep 05 08:00:00 IDT 2019 | Thu Oct 10 16:00:00 IDT 2019 |  | COMPLETED
2056 | TT_TASK | Shaft F - Testing to CWP between Shaft A and Shaft F | Wed Jan 01 08:00:00 IST 2020 | Wed Jan 01 08:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Sat Dec 07 08:00:00 IST 2019 |  | COMPLETED
2057 | TT_TASK | Shaft F - Micro tunneling and pipe jacking from Shaft E (Part 2 of 2) | Fri Nov 01 08:00:00 IST 2019 | Mon Nov 11 16:00:00 IST 2019 | Thu Sep 19 08:00:00 IDT 2019 | Thu Oct 17 16:00:00 IDT 2019 |  | COMPLETED
2058 | TT_TASK | Grouting and Welding CWP between Shaft E and Shaft F (Part 2 of 2) | Wed Jan 01 08:00:00 IST 2020 | Mon Jan 06 16:00:00 IST 2020 | Sat Nov 09 08:00:00 IST 2019 | Fri Nov 15 16:00:00 IST 2019 |  | COMPLETED
2059 | TT_TASK | Testing to CWP between Shaft E and Shaft F (Part 2 of 2) | Wed Jan 01 08:00:00 IST 2020 | Tue Jan 07 16:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Sat Dec 07 08:00:00 IST 2019 |  | COMPLETED
2060 | TT_TASK | Shaft F - Demob launching rails (F drive) and install retrieval rails (E drive) | Wed Jan 01 08:00:00 IST 2020 | Mon Jan 06 16:00:00 IST 2020 | Sun Sep 08 08:00:00 IDT 2019 | Sun Sep 08 16:00:00 IDT 2019 |  | COMPLETED
2061 | TT_TASK | Shaft F - Receive TBM and demob off site | Wed Jan 01 08:00:00 IST 2020 | Mon Jan 06 16:00:00 IST 2020 | Fri Oct 18 08:00:00 IDT 2019 | Tue Oct 29 16:00:00 IST 2019 |  | COMPLETED
2062 | TT_TASK | Shaft F - Construct permanent shaft wall (Pour 1 of 8 / standard lift 3m) | Wed Jan 01 08:00:00 IST 2020 | Wed Jan 01 08:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Sat Dec 07 08:00:00 IST 2019 |  | COMPLETED
2063 | TT_TASK | Shaft F - Construct permanent shaft wall (Pour 2 of 8) | Wed Jan 01 08:00:00 IST 2020 | Wed Jan 01 08:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Sat Dec 07 08:00:00 IST 2019 |  | COMPLETED
2064 | TT_TASK | Shaft F - Construct permanent shaft wall (Pour 3 of 8) | Wed Jan 01 08:00:00 IST 2020 | Wed Jan 01 08:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Sat Dec 07 08:00:00 IST 2019 |  | COMPLETED
2065 | TT_TASK | Shaft F - Construct permanent shaft wall (Pour 4 of 8) | Wed Jan 01 08:00:00 IST 2020 | Wed Jan 01 08:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Sat Dec 07 08:00:00 IST 2019 |  | COMPLETED
2066 | TT_TASK | Shaft F - Construct permanent shaft wall (Pour 5 of 8) | Wed Jan 01 08:00:00 IST 2020 | Wed Jan 01 08:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Sat Dec 07 08:00:00 IST 2019 |  | COMPLETED
2067 | TT_TASK | Shaft F - Construct permanent shaft wall (Pour 6 of 8) | Wed Jan 01 08:00:00 IST 2020 | Wed Jan 01 08:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Sat Dec 07 08:00:00 IST 2019 |  | COMPLETED
2068 | TT_TASK | Shaft F - Construct permanent shaft wall (Pour 7 of 8) | Wed Jan 01 08:00:00 IST 2020 | Wed Jan 01 08:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Sat Dec 07 08:00:00 IST 2019 |  | COMPLETED
2069 | TT_TASK | Shaft F - Construct the top slab of permanent shaft (with temporary opening for material delivery) | Wed Jan 01 08:00:00 IST 2020 | Wed Jan 01 08:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Sat Dec 07 08:00:00 IST 2019 |  | COMPLETED
2070 | TT_TASK | Shaft F - Construct Maintenance Access Shaft and Emergency Access Shaft | Wed Jan 01 08:00:00 IST 2020 | Wed Jan 01 08:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Sat Dec 07 08:00:00 IST 2019 |  | COMPLETED
2071 | TT_TASK | Shaft F - Install vertical sections and precast stair wells including mass fill | Wed Jan 01 08:00:00 IST 2020 | Sat Feb 08 16:00:00 IST 2020 | Wed Oct 30 08:00:00 IST 2019 | Fri Dec 06 16:00:00 IST 2019 |  | COMPLETED
2072 | TT_TASK | Shaft F - Install CW pipe bends / horizontal section of supply pipeline above the top landing unit of staircase | Tue Jan 07 08:00:00 IST 2020 | Thu Jan 09 16:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Mon Dec 23 16:00:00 IST 2019 |  | COMPLETED
2073 | TT_TASK | Shaft F - Install CW pipe bends / horizontal section of discharge pipeline above the top slab | Wed Jan 01 08:00:00 IST 2020 | Tue Jan 07 16:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Sat Dec 07 08:00:00 IST 2019 |  | COMPLETED
2074 | TT_TASK | Shaft F - Seal up pipe penetrations through the top slab | Fri Jan 10 08:00:00 IST 2020 | Fri Jan 10 08:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Sat Dec 07 08:00:00 IST 2019 |  | COMPLETED
2075 | TT_TASK | Shaft F - Backfill to 2m existing ground level | Thu Mar 26 08:00:00 IST 2020 | Wed Apr 01 16:00:00 IDT 2020 | Thu Mar 26 08:00:00 IST 2020 | Wed Apr 01 16:00:00 IDT 2020 |  | COMPLETED
2076 | TT_TASK | Shaft F - Trim pipe pile wall to 2m below ground level | Thu Apr 02 08:00:00 IDT 2020 | Fri Apr 03 16:00:00 IDT 2020 | Thu Apr 02 08:00:00 IDT 2020 | Fri Apr 03 16:00:00 IDT 2020 |  | COMPLETED
2077 | TT_TASK | Shaft F - Backfill and reinstate to ground level | Sat Apr 04 08:00:00 IDT 2020 | Fri Apr 10 16:00:00 IDT 2020 | Sat Apr 04 08:00:00 IDT 2020 | Fri Apr 10 16:00:00 IDT 2020 |  | COMPLETED
2078 | TT_TASK | Shaft F - ABWF (i.e. finishes, metal works, etc) | Thu Mar 26 08:00:00 IST 2020 | Tue Apr 21 16:00:00 IDT 2020 | Thu Mar 26 08:00:00 IST 2020 | Tue Apr 21 16:00:00 IDT 2020 |  | COMPLETED
2079 | TT_TASK | Shaft F - Building Services installation | Thu Mar 26 08:00:00 IST 2020 | Tue Apr 21 16:00:00 IDT 2020 | Thu Mar 26 08:00:00 IST 2020 | Tue Apr 21 16:00:00 IDT 2020 |  | COMPLETED
2081 | TT_TASK | DPT /Zone A (Southern Section) - Pre-boring for sheet pile wall | Tue Oct 17 08:00:00 IDT 2017 | Wed Nov 15 16:00:00 IST 2017 | Fri Oct 13 08:00:00 IDT 2017 | Sun Jan 14 16:00:00 IST 2018 |  | COMPLETED
2082 | TT_TASK | DPT /Zone A (Southern Section) - Sheet Piling | Thu Nov 02 08:00:00 IST 2017 | Mon Nov 27 16:00:00 IST 2017 | Thu Nov 02 08:00:00 IST 2017 | Wed Jan 31 16:00:00 IST 2018 |  | COMPLETED
2083 | TT_TASK | DPT /Zone A (Southern Section) - Pumping Test and Report Submission | Tue Apr 10 08:00:00 IDT 2018 | Sat Apr 21 16:00:00 IDT 2018 | Fri Feb 09 08:00:00 IST 2018 | Sat Feb 24 16:00:00 IST 2018 |  | COMPLETED
2084 | TT_TASK | DPT /Zone A (Southern Section) - BD Consent for Commencement of Excavation & ELS | Mon Jun 18 08:00:00 IDT 2018 | Sun Jul 15 16:00:00 IDT 2018 | Fri May 18 08:00:00 IDT 2018 | Fri Jun 22 16:00:00 IDT 2018 |  | COMPLETED
2085 | TT_TASK | DPT /Zone A (Southern Section) - Excavate to 0.5m below 1st layer of struts | Thu Jul 26 08:00:00 IDT 2018 | Fri Aug 03 16:00:00 IDT 2018 | Tue Jun 26 08:00:00 IDT 2018 | Fri Jul 06 16:00:00 IDT 2018 |  | COMPLETED
2086 | TT_TASK | DPT /Zone A (Southern Section) - Install 1st layer of struts | Thu Aug 02 08:00:00 IDT 2018 | Thu Aug 16 16:00:00 IDT 2018 | Thu Jul 05 08:00:00 IDT 2018 | Mon Aug 13 16:00:00 IDT 2018 |  | COMPLETED
2087 | TT_TASK | DPT /Zone A (Southern Section) - Excavate to 0.5m below 2nd layer of struts | Fri Sep 07 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Thu Aug 09 08:00:00 IDT 2018 | Sat Aug 25 16:00:00 IDT 2018 |  | COMPLETED
2088 | TT_TASK | DPT /Zone A (Southern Section) - Install 2nd layer of struts | Mon Aug 27 08:00:00 IDT 2018 | Thu Sep 20 16:00:00 IDT 2018 | Sat Aug 25 08:00:00 IDT 2018 | Fri Oct 05 16:00:00 IDT 2018 |  | COMPLETED
2089 | TT_TASK | DPT /Zone A (Southern Section) - Excavate to final excavation level -1.4 mPD | Mon Nov 26 08:00:00 IST 2018 | Tue Dec 04 16:00:00 IST 2018 | Mon Sep 24 08:00:00 IDT 2018 | Tue Oct 16 16:00:00 IDT 2018 |  | COMPLETED
2090 | TT_TASK | DPT /Zone A (Southern Section) - Cast base slab | Mon Nov 26 08:00:00 IST 2018 | Tue Dec 04 16:00:00 IST 2018 | Mon Oct 15 08:00:00 IDT 2018 | Thu Nov 08 16:00:00 IST 2018 |  | COMPLETED
2091 | TT_TASK | DPT /Zone A (Southern Section) - Remove 2nd layer of struts | Sat Dec 01 08:00:00 IST 2018 | Mon Dec 10 16:00:00 IST 2018 | Thu Oct 25 08:00:00 IDT 2018 | Fri Nov 16 16:00:00 IST 2018 |  | COMPLETED
2092 | TT_TASK | DPT /Zone A (Southern Section) - Install Cooling Water Pipe (39 nos.) | Mon Nov 26 08:00:00 IST 2018 | Sat Dec 22 16:00:00 IST 2018 | Sat Nov 03 08:00:00 IST 2018 | Mon Dec 31 16:00:00 IST 2018 |  | COMPLETED
2093 | TT_TASK | DPT /Zone A (Southern Section) - Testing to Cooling Water Pipe (TBC) | Wed Jan 01 08:00:00 IST 2020 | Fri Jan 10 16:00:00 IST 2020 | Tue Jan 01 08:00:00 IST 2019 | Tue Jan 01 08:00:00 IST 2019 |  | COMPLETED
2094 | TT_TASK | DPT /Zone A (Southern Section) - Backfill to 0.5m below 1st layer of struts | Sat Feb 23 08:00:00 IST 2019 | Thu Feb 28 16:00:00 IST 2019 | Mon Dec 17 08:00:00 IST 2018 | Sat Dec 22 16:00:00 IST 2018 |  | COMPLETED
2095 | TT_TASK | DPT /Zone A (Southern Section) - Concrete surround | Sat Feb 02 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Sat Dec 01 08:00:00 IST 2018 | Sat Dec 15 16:00:00 IST 2018 |  | COMPLETED
2096 | TT_TASK | DPT /Zone A (Southern Section) - Remove 1st layer of struts | Mon Feb 18 08:00:00 IST 2019 | Sat Mar 02 16:00:00 IST 2019 | Fri Dec 28 08:00:00 IST 2018 | Mon Dec 31 16:00:00 IST 2018 |  | COMPLETED
2097 | TT_TASK | DPT /Zone A (Southern Section) - Trim down sheet pile 2m | Fri Mar 01 08:00:00 IST 2019 | Thu Mar 07 16:00:00 IST 2019 | Sun Dec 30 08:00:00 IST 2018 | Wed Jan 02 16:00:00 IST 2019 |  | COMPLETED
2098 | TT_TASK | DPT /Zone A (Southern Section) - Backfill and form slope to the formation of Generator Transformer | Mon Mar 11 08:00:00 IST 2019 | Mon Mar 11 08:00:00 IST 2019 | Fri Dec 28 08:00:00 IST 2018 | Wed Jan 02 16:00:00 IST 2019 |  | COMPLETED
2099 | TT_TASK | DPT /Zone B (Middle Section) - Grouting to the eastern side of double pipe trench | Mon Sep 25 08:00:00 IDT 2017 | Thu Nov 02 16:00:00 IST 2017 | Sat Sep 23 08:00:00 IDT 2017 | Wed Feb 07 16:00:00 IST 2018 |  | COMPLETED
2100 | TT_TASK | DPT /Zone B (Middle Section) - Grouting to the western side of double pipe trench | Tue Oct 03 08:00:00 IDT 2017 | Mon Nov 06 16:00:00 IST 2017 | Mon Oct 02 00:00:00 IDT 2017 | Wed Feb 07 16:00:00 IST 2018 |  | COMPLETED
2102 | TT_TASK | DPT/ Zone B Central - Open cut excavation | Sat Jan 26 08:00:00 IST 2019 | Thu Feb 14 16:00:00 IST 2019 | Thu Nov 29 00:00:00 IST 2018 | Tue Dec 18 16:00:00 IST 2018 |  | COMPLETED
2103 | TT_TASK | DPT/ Zone B South (i.e. Zone A Interface) - Open cut excavation | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 08 16:00:00 IST 2019 | Mon Dec 31 00:00:00 IST 2018 | Sat Jan 12 16:00:00 IST 2019 |  | COMPLETED
2104 | TT_TASK | DPT/ Zone B North (i.e. KSS Interface) - Open cut excavation | Sat Jan 26 08:00:00 IST 2019 | Wed Feb 06 16:00:00 IST 2019 | Thu Jan 24 00:00:00 IST 2019 | Fri Feb 08 16:00:00 IST 2019 |  | COMPLETED
2105 | TT_TASK | DPT/ Zone B North (i.e. KSS Crane Access) - Open cut excavation | Mon Apr 01 08:00:00 IDT 2019 | Thu Apr 11 16:00:00 IDT 2019 | Sat Mar 09 08:00:00 IST 2019 | Mon Mar 11 16:00:00 IST 2019 |  | COMPLETED
2107 | TT_TASK | DPT/ Zone B Central - Base slab | Sat Jan 26 08:00:00 IST 2019 | Thu Jan 31 16:00:00 IST 2019 | Tue Dec 18 08:00:00 IST 2018 | Sat Dec 22 16:00:00 IST 2018 |  | COMPLETED
2108 | TT_TASK | DPT/ Zone B South (i.e. Zone A Interface) - Base slab | Sat Jan 26 08:00:00 IST 2019 | Wed Jan 30 16:00:00 IST 2019 | Sun Jan 13 08:00:00 IST 2019 | Thu Jan 17 16:00:00 IST 2019 |  | COMPLETED
2109 | TT_TASK | DPT/ Zone B North (i.e. KSS Interface) - Base slab | Mon Apr 01 08:00:00 IDT 2019 | Thu Apr 04 16:00:00 IDT 2019 | Sat Feb 09 08:00:00 IST 2019 | Tue Feb 12 16:00:00 IST 2019 |  | COMPLETED
2110 | TT_TASK | DPT/ Zone B North (i.e. KSS Crane Access) - Base slab | Mon Apr 01 08:00:00 IDT 2019 | Thu Apr 04 16:00:00 IDT 2019 | Wed Mar 13 08:00:00 IST 2019 | Fri Mar 15 16:00:00 IST 2019 |  | COMPLETED
2112 | TT_TASK | DPT/ Zone B Central - CW pipe installation | Sat Jan 26 08:00:00 IST 2019 | Tue Feb 05 16:00:00 IST 2019 | Mon Dec 24 08:00:00 IST 2018 | Thu Jan 03 16:00:00 IST 2019 |  | COMPLETED
2113 | TT_TASK | DPT/ Zone B South (i.e. Zone A Interface) - CW pipe installation | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 01 16:00:00 IST 2019 | Thu Jan 17 00:00:00 IST 2019 | Wed Jan 23 16:00:00 IST 2019 |  | COMPLETED
2114 | TT_TASK | DPT/ Zone B North (i.e. KSS Interface) - CW pipe installation | Sun Mar 31 08:00:00 IDT 2019 | Mon Apr 01 16:00:00 IDT 2019 | Wed Feb 13 08:00:00 IST 2019 | Fri Feb 15 16:00:00 IST 2019 |  | COMPLETED
2115 | TT_TASK | DPT/ Zone B North (i.e. KSS Crane Access) - CW pipe installation | Sun Mar 31 08:00:00 IDT 2019 | Fri Apr 05 16:00:00 IDT 2019 | Sat Mar 16 08:00:00 IST 2019 | Thu Mar 21 16:00:00 IST 2019 |  | COMPLETED
2116 | TT_TASK | DPT /Zone B (Middle Section) - Testing to Cooling Water Pipe (TBC) | Wed Jan 01 08:00:00 IST 2020 | Sat Jan 11 16:00:00 IST 2020 | Wed Apr 03 08:00:00 IDT 2019 | Wed Apr 03 08:00:00 IDT 2019 |  | COMPLETED
2118 | TT_TASK | DPT/ Zone B Central - Concrete surround & backfill | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 08 16:00:00 IST 2019 | Mon Jan 07 08:00:00 IST 2019 | Sat Jan 19 16:00:00 IST 2019 |  | COMPLETED
2119 | TT_TASK | DPT/ Zone B South (i.e. Zone A Interface) - Concrete surround & backfill | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 08 16:00:00 IST 2019 | Thu Jan 17 08:00:00 IST 2019 | Wed Jan 30 16:00:00 IST 2019 |  | COMPLETED
2120 | TT_TASK | DPT/ Zone B North (i.e. KSS Interface) - Concrete surround & backfill | Tue Apr 02 08:00:00 IDT 2019 | Wed Apr 17 16:00:00 IDT 2019 | Sat Feb 16 08:00:00 IST 2019 | Mon Feb 25 16:00:00 IST 2019 |  | COMPLETED
2121 | TT_TASK | DPT/ Zone B North (i.e. KSS Crane Access) - Concrete surround & backfill | Sat Apr 06 08:00:00 IDT 2019 | Sat Apr 27 16:00:00 IDT 2019 | Fri Mar 15 08:00:00 IST 2019 | Tue Apr 02 16:00:00 IDT 2019 |  | COMPLETED
2122 | TT_TASK | DPT /Zone C (Northern Section) - Pipe Piles adjoining Shaft F (13 nos) | Mon Apr 23 08:00:00 IDT 2018 | Sat May 05 16:00:00 IDT 2018 | Sat Mar 03 08:00:00 IST 2018 | Tue Mar 13 16:00:00 IST 2018 |  | COMPLETED
2123 | TT_TASK | DPT /Zone C (Northern Section) - Remaining Eastern Pipe Pile (60 nos) | Mon May 07 08:00:00 IDT 2018 | Mon Jun 25 16:00:00 IDT 2018 | Wed Mar 14 08:00:00 IST 2018 | Wed May 02 16:00:00 IDT 2018 |  | COMPLETED
2124 | TT_TASK | DPT /Zone C (Northern Section) - Remaining Western Pipe Pile (50 nos) | Wed Jun 13 08:00:00 IDT 2018 | Tue Jul 24 16:00:00 IDT 2018 | Sat Apr 07 08:00:00 IDT 2018 | Sat Apr 28 16:00:00 IDT 2018 |  | COMPLETED
2125 | TT_TASK | DPT /Zone C (Northern Section) - Grout Curtain East | Sat May 26 08:00:00 IDT 2018 | Sat Jun 30 16:00:00 IDT 2018 | Fri Apr 27 08:00:00 IDT 2018 | Thu Jun 07 16:00:00 IDT 2018 |  | COMPLETED
2126 | TT_TASK | DPT /Zone C (Northern Section) - Grout Curtain West | Sat Jun 16 08:00:00 IDT 2018 | Thu Jul 19 16:00:00 IDT 2018 | Fri Apr 27 08:00:00 IDT 2018 | Thu Jun 07 16:00:00 IDT 2018 |  | COMPLETED
2127 | TT_TASK | DPT /Zone C (Northern Section) - Pumping Test and Report Submission | Thu May 02 08:00:00 IDT 2019 | Wed May 22 16:00:00 IDT 2019 | Fri Apr 26 08:00:00 IDT 2019 | Wed Jul 03 16:00:00 IDT 2019 |  | COMPLETED
2128 | TT_TASK | DPT /Zone C (Northern Section) - BD Consent for Commencement of Excavation & ELS | Wed Aug 21 08:00:00 IDT 2019 | Tue Sep 17 16:00:00 IDT 2019 | Tue Jun 25 08:00:00 IDT 2019 | Mon Jul 22 16:00:00 IDT 2019 |  | COMPLETED
2129 | TT_TASK | DPT /Zone C (Northern Section) - Excavation to 0.5m below 1st layer struts | Thu Aug 01 08:00:00 IDT 2019 | Wed Aug 14 16:00:00 IDT 2019 | Fri Jul 12 08:00:00 IDT 2019 | Mon Jul 22 16:00:00 IDT 2019 |  | COMPLETED
2130 | TT_TASK | DPT /Zone C (Northern Section) - Install 1st layer of struts | Thu Aug 15 08:00:00 IDT 2019 | Wed Aug 28 16:00:00 IDT 2019 | Mon Jul 22 08:00:00 IDT 2019 | Sat Jul 27 16:00:00 IDT 2019 |  | COMPLETED
2131 | TT_TASK | DPT /Zone C (Northern Section) - Excavation to 0.5m below 2nd layer struts | Thu Aug 01 08:00:00 IDT 2019 | Wed Aug 14 16:00:00 IDT 2019 | Wed Jul 31 08:00:00 IDT 2019 | Sat Aug 24 16:00:00 IDT 2019 |  | COMPLETED
2132 | TT_TASK | DPT /Zone C (Northern Section) - Install 2nd layer of struts | Sun Sep 15 08:00:00 IDT 2019 | Sat Sep 21 16:00:00 IDT 2019 | Thu Aug 22 08:00:00 IDT 2019 | Tue Sep 03 16:00:00 IDT 2019 |  | COMPLETED
2133 | TT_TASK | DPT /Zone C (Northern Section) - Excavation to formation level | Mon Nov 04 08:00:00 IST 2019 | Sun Nov 10 16:00:00 IST 2019 | Wed Sep 04 08:00:00 IDT 2019 | Thu Sep 12 16:00:00 IDT 2019 |  | COMPLETED
2134 | TT_TASK | DPT /Zone C (Northern Section) - Plate load test x2 sets | Fri Nov 01 08:00:00 IST 2019 | Wed Nov 06 16:00:00 IST 2019 | Fri Sep 13 08:00:00 IDT 2019 | Mon Sep 16 16:00:00 IDT 2019 |  | COMPLETED
2135 | TT_TASK | DPT /Zone C (Northern Section) - Install Cooling Water Pipe | Tue Sep 17 08:00:00 IDT 2019 | Sat Oct 05 16:00:00 IDT 2019 | Sat Aug 24 08:00:00 IDT 2019 | Tue Oct 15 16:00:00 IDT 2019 |  | COMPLETED
2136 | TT_TASK | DPT /Zone C (Northern Section) - Testing to Cooling Water Pipe | Wed Jan 01 08:00:00 IST 2020 | Wed Jan 01 08:00:00 IST 2020 | Wed Oct 16 08:00:00 IDT 2019 | Wed Oct 16 08:00:00 IDT 2019 |  | COMPLETED
2137 | TT_TASK | DPT /Zone C (Northern Section) - Break Shaft F pipe pile wall at the supply pipeline interface | Wed Jan 01 08:00:00 IST 2020 | Fri Jan 03 16:00:00 IST 2020 | Sat Dec 14 08:00:00 IST 2019 | Mon Dec 16 16:00:00 IST 2019 |  | COMPLETED
2138 | TT_TASK | DPT /Zone C (Northern Section) - Connect CW supply pipeline to Shaft F | Mon Jan 13 08:00:00 IST 2020 | Wed Jan 15 16:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Mon Dec 23 16:00:00 IST 2019 |  | COMPLETED
2139 | TT_TASK | DPT /Seal Pit - Stitch connection of Seal Pit between Shaft F and Zone C | Mon Feb 24 08:00:00 IST 2020 | Fri Mar 06 16:00:00 IST 2020 | Sun Dec 08 08:00:00 IST 2019 | Sun Dec 22 16:00:00 IST 2019 |  | COMPLETED
2140 | TT_TASK | DPT /Zone C (Northern Section) - Trim top 2m pipe piles | Mon Jan 13 08:00:00 IST 2020 | Sat Jan 18 16:00:00 IST 2020 | Mon Jan 13 08:00:00 IST 2020 | Sat Jan 18 16:00:00 IST 2020 |  | COMPLETED
2141 | TT_TASK | DPT /Zone C (Northern Section) - Backfill and reinstate to ground level | Mon Jan 20 08:00:00 IST 2020 | Wed Feb 05 16:00:00 IST 2020 | Mon Jan 20 08:00:00 IST 2020 | Wed Feb 05 16:00:00 IST 2020 |  | COMPLETED
2142 | TT_TASK | DPT /Seal Pit - Construct parts of structure within Zone C | Wed Jan 01 08:00:00 IST 2020 | Sun Feb 23 16:00:00 IST 2020 | Thu Sep 19 08:00:00 IDT 2019 | Thu Dec 19 16:00:00 IST 2019 |  | COMPLETED
2143 | TT_TASK | DPT /Seal Pit - Connect CW pipes to the discharge line at Zone C | Wed Jan 01 08:00:00 IST 2020 | Mon Jan 06 16:00:00 IST 2020 | Tue Nov 26 08:00:00 IST 2019 | Tue Nov 26 16:00:00 IST 2019 |  | COMPLETED
2144 | TT_TASK | DPT /Seal Pit - Construct balance of structure in Shaft F / Zone C | Wed Jan 01 08:00:00 IST 2020 | Tue Jan 21 16:00:00 IST 2020 | Sat Dec 07 08:00:00 IST 2019 | Sat Dec 07 16:00:00 IST 2019 |  | COMPLETED
2145 | TT_TASK | DPT /Seal Pit - ABWF | Mon Jan 13 08:00:00 IST 2020 | Thu Jan 30 16:00:00 IST 2020 | Mon Jan 13 08:00:00 IST 2020 | Thu Jan 30 16:00:00 IST 2020 |  | COMPLETED
2146 | TT_TASK | DPT /Seal Pit - Building Services Installation | Mon Jan 13 08:00:00 IST 2020 | Thu Jan 30 16:00:00 IST 2020 | Mon Jan 13 08:00:00 IST 2020 | Thu Jan 30 16:00:00 IST 2020 |  | COMPLETED
2147 | TT_TASK | Event 006 - Unchartered UU found at Zone A (slow down pre-boring progress) | Mon Oct 23 08:00:00 IDT 2017 | Mon Oct 23 16:00:00 IDT 2017 | Thu Nov 09 08:00:00 IST 2017 | Fri Dec 29 16:00:00 IST 2017 |  | COMPLETED
2149 | TT_TASK | Event 012ZA - Settlement Assessment - Report preparation and submission to BD | Mon Apr 23 08:00:00 IDT 2018 | Sat Apr 28 16:00:00 IDT 2018 | Mon Mar 05 08:00:00 IST 2018 | Thu May 17 16:00:00 IDT 2018 |  | COMPLETED
2150 | TT_TASK | Event 012ZA - Settlement Assessment - Report review and comment by BD | Sun Apr 29 08:00:00 IDT 2018 | Sat May 12 16:00:00 IDT 2018 | Fri Mar 16 08:00:00 IST 2018 | Fri Jun 22 16:00:00 IDT 2018 |  | COMPLETED
2152 | TT_TASK | Event 012ZA - Request and Issue of ROI for Post Grouting to Transformer Rd and other precautionary measures | Sun Apr 29 08:00:00 IDT 2018 | Thu May 03 16:00:00 IDT 2018 | Thu Mar 08 08:00:00 IST 2018 | Sun Mar 18 16:00:00 IST 2018 |  | COMPLETED
2153 | TT_TASK | Event 012ZA - Settlement Assessment - Post remedial grouting to Transformer Rd (36 nos. +4 SPT) | Sat May 05 08:00:00 IDT 2018 | Fri May 25 16:00:00 IDT 2018 | Mon Mar 19 08:00:00 IST 2018 | Wed Apr 04 16:00:00 IDT 2018 |  | COMPLETED
2154 | TT_TASK | Event 012ZA - Settlement Assessment - Instruction of additional remedial grouting (24 nos. - ROI #72) | Sat May 05 08:00:00 IDT 2018 | Thu May 10 16:00:00 IDT 2018 | Thu Apr 05 08:00:00 IDT 2018 | Wed Apr 11 16:00:00 IDT 2018 |  | COMPLETED
2155 | TT_TASK | Event 012ZA - Settlement Assessment - Post remedial grouting to Transformer Rd (24 nos.) | Sat May 05 08:00:00 IDT 2018 | Wed May 16 16:00:00 IDT 2018 | Thu Apr 12 08:00:00 IDT 2018 | Mon Apr 23 16:00:00 IDT 2018 |  | COMPLETED
2156 | TT_TASK | Event 012ZA - Settlement Assessment - Awaiting confirmation on locations of 2 nos,. additional SPT | Sun May 27 08:00:00 IDT 2018 | Fri Jun 01 16:00:00 IDT 2018 | Tue Apr 24 08:00:00 IDT 2018 | Wed Apr 25 16:00:00 IDT 2018 |  | COMPLETED
2157 | TT_TASK | Event 012ZA - Settlement Assessment - 2 nos. additional SPT | Sat Jun 02 08:00:00 IDT 2018 | Fri Jun 08 16:00:00 IDT 2018 | Thu Apr 26 08:00:00 IDT 2018 | Sat May 05 16:00:00 IDT 2018 |  | COMPLETED
2158 | TT_TASK | Event 012ZA - Settlement Assessment - Preparation and submission of supplementary information | Sat May 26 08:00:00 IDT 2018 | Fri Jun 08 16:00:00 IDT 2018 | Sun May 06 08:00:00 IDT 2018 | Thu May 17 16:00:00 IDT 2018 |  | COMPLETED
2162 | TT_TASK | Event 021(ZA) - AAA amendment for Zone A {4b1-alt A-2} [WITHDRAWN] | Sat May 26 08:00:00 IDT 2018 | Sun Jun 24 16:00:00 IDT 2018 | Fri Mar 16 08:00:00 IST 2018 | Wed Apr 04 16:00:00 IDT 2018 |  | COMPLETED
2163 | TT_TASK | Event 021(ZA) - AAA amendment for Zone A {4b1-alt A-2(r1)} [WITHDRAWN] | Sat May 26 08:00:00 IDT 2018 | Sun Jun 24 16:00:00 IDT 2018 | Tue Apr 24 08:00:00 IDT 2018 | Fri May 18 16:00:00 IDT 2018 |  | COMPLETED
2164 | TT_TASK | Event 021(ZA) - AAA amendment for Zone A {4b1-alt A-2(r2)} | Sat May 26 08:00:00 IDT 2018 | Sun Jun 24 16:00:00 IDT 2018 | Fri May 18 08:00:00 IDT 2018 | Fri Jun 22 16:00:00 IDT 2018 |  | COMPLETED
2165 | TT_TASK | Event 039(ZA) - Transformer Generator resequencing amendment (Part 1) | Thu Jul 26 08:00:00 IDT 2018 | Fri Aug 24 16:00:00 IDT 2018 | Fri Jun 29 08:00:00 IDT 2018 | Fri Jul 27 16:00:00 IDT 2018 |  | COMPLETED
2166 | TT_TASK | Event 039(ZA) - Transformer Generator resequencing amendment (Part 2) | Sun Aug 26 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Fri Aug 24 08:00:00 IDT 2018 | Thu Sep 20 16:00:00 IDT 2018 |  | COMPLETED
2167 | TT_TASK | Event 042 - Zone B FEL amendment (Type II) | Sat Jan 26 08:00:00 IST 2019 | Sun Feb 24 16:00:00 IST 2019 | Fri Nov 30 08:00:00 IST 2018 | Fri Dec 28 16:00:00 IST 2018 |  | COMPLETED
2168 | TT_TASK | Event 042 - BA8 consent for Zone B FEL amendment | Sat Jan 26 08:00:00 IST 2019 | Sun Feb 24 16:00:00 IST 2019 | Fri Nov 30 08:00:00 IST 2018 | Fri Dec 28 16:00:00 IST 2018 |  | COMPLETED
2169 | TT_TASK | Event 045 - Shaft F / Zone C Re-sequencing - Additional pipe piles | Sat Jan 26 08:00:00 IST 2019 | Sat Jan 26 16:00:00 IST 2019 | Fri Jan 11 00:00:00 IST 2019 | Wed Jan 23 16:00:00 IST 2019 |  | COMPLETED
2170 | TT_TASK | Event 045 - Shaft F / Zone C Re-sequencing - Additional TAM grout | Mon Apr 01 08:00:00 IDT 2019 | Sat Apr 13 16:00:00 IDT 2019 | Sat Mar 23 08:00:00 IST 2019 | Mon Apr 01 16:00:00 IDT 2019 |  | COMPLETED
2174 | TT_TASK | Event 011D - Install trial jet grout | Thu Jul 26 08:00:00 IDT 2018 | Sat Jul 28 16:00:00 IDT 2018 | Wed Jul 25 08:00:00 IDT 2018 | Sat Jul 28 16:00:00 IDT 2018 |  | COMPLETED
2175 | TT_TASK | Event 017D - Shaft D Advanced Precautionary Grouting (32 out of 53) | Wed Jun 06 08:00:00 IDT 2018 | Thu Jul 05 16:00:00 IDT 2018 | Sat May 05 08:00:00 IDT 2018 | Sat Jun 09 16:00:00 IDT 2018 |  | COMPLETED
2176 | TT_TASK | Event 017D - Shaft D Advanced Precautionary Grouting (1 out of 53) | Thu Jul 26 08:00:00 IDT 2018 | Thu Jul 26 16:00:00 IDT 2018 | Thu Jun 21 08:00:00 IDT 2018 | Fri Jun 22 16:00:00 IDT 2018 |  | COMPLETED
2177 | TT_TASK | Event 017D - Shaft D Advanced Precautionary Grouting (9 out of 53) | Thu Jul 26 08:00:00 IDT 2018 | Thu Jul 26 16:00:00 IDT 2018 | Tue Jun 26 08:00:00 IDT 2018 | Tue Jul 03 16:00:00 IDT 2018 |  | COMPLETED
2178 | TT_TASK | Event 017D - Shaft D Advanced Precautionary Grouting (11 out of 53) | Sun Aug 26 08:00:00 IDT 2018 | Thu Aug 30 16:00:00 IDT 2018 | Sun Jul 29 08:00:00 IDT 2018 | Thu Aug 02 16:00:00 IDT 2018 |  | COMPLETED
2179 | TT_TASK | Event 021D - Shaft D AAA amendment (Type II) / submission & approval | Tue Jun 26 08:00:00 IDT 2018 | Wed Jul 25 16:00:00 IDT 2018 | Wed May 30 08:00:00 IDT 2018 | Tue Jul 03 16:00:00 IDT 2018 |  | COMPLETED
2180 | TT_TASK | Event 021D - Shaft D AAA amendment / consent for APG & trial jet grout | Thu Jul 26 08:00:00 IDT 2018 | Wed Aug 22 16:00:00 IDT 2018 | Mon Jun 18 08:00:00 IDT 2018 | Wed Jul 25 16:00:00 IDT 2018 |  | COMPLETED
2182 | TT_TASK | Event 031D - Works suspended after FS main stirke in Diversion Culvet works area | Thu Jul 26 08:00:00 IDT 2018 | Thu Jul 26 16:00:00 IDT 2018 | Wed Jul 04 00:00:00 IDT 2018 | Mon Jul 09 16:00:00 IDT 2018 |  | COMPLETED
2183 | TT_TASK | Event 032D - Works suspension instructed to await BD consent | Thu Jul 26 08:00:00 IDT 2018 | Thu Jul 26 16:00:00 IDT 2018 | Thu Jul 12 08:00:00 IDT 2018 | Mon Jul 23 16:00:00 IDT 2018 |  | COMPLETED
2186 | TT_TASK | Shaft D - Utilities Diversion | Mon Apr 23 08:00:00 IDT 2018 | Thu Jun 14 16:00:00 IDT 2018 | Wed Mar 07 08:00:00 IST 2018 | Wed Jun 20 16:00:00 IDT 2018 |  | COMPLETED
2187 | TT_TASK | Grouting and Welding to CWP between Shaft E and Shaft F (Part 1 of 2) | Wed Jan 01 08:00:00 IST 2020 | Thu Jan 09 16:00:00 IST 2020 | Thu Oct 31 08:00:00 IST 2019 | Fri Nov 08 16:00:00 IST 2019 |  | COMPLETED
2191 | TT_TASK | Event 011E - Install trial get grout ( x3 nos.) | Mon Aug 27 08:00:00 IDT 2018 | Thu Aug 30 16:00:00 IDT 2018 | Sat Aug 04 08:00:00 IDT 2018 | Tue Aug 07 16:00:00 IDT 2018 |  | COMPLETED
2192 | TT_TASK | Event 011E - Permeability Test + Core sample after 21 days from grout installed | Thu Dec 06 08:00:00 IST 2018 | Wed Dec 19 16:00:00 IST 2018 | Fri Sep 07 08:00:00 IDT 2018 | Thu Sep 20 16:00:00 IDT 2018 |  | COMPLETED
2193 | TT_TASK | Event 011E - Test to early achievement of 28 day strength | Thu Dec 06 08:00:00 IST 2018 | Sat Dec 08 16:00:00 IST 2018 | Thu Sep 13 08:00:00 IDT 2018 | Fri Sep 21 16:00:00 IDT 2018 |  | COMPLETED
2194 | TT_TASK | Event 011E - Curing and cube test to backfill grout | Thu Dec 06 08:00:00 IST 2018 | Wed Jan 02 16:00:00 IST 2019 | Fri Sep 21 08:00:00 IDT 2018 | Thu Oct 18 16:00:00 IDT 2018 |  | COMPLETED
2195 | TT_TASK | Event 011E - Formal test report issued for submission in 7 calendar days | Thu Dec 06 08:00:00 IST 2018 | Wed Dec 12 16:00:00 IST 2018 | Sat Nov 03 08:00:00 IST 2018 | Tue Dec 04 16:00:00 IST 2018 |  | COMPLETED
2196 | TT_TASK | Event 011E - Shaft E - BA8 for full scale grout block and excav below -1.6 mPD | Sat Jan 05 08:00:00 IST 2019 | Fri Feb 01 16:00:00 IST 2019 | Fri Nov 30 08:00:00 IST 2018 | Mon Dec 24 16:00:00 IST 2018 |  | COMPLETED
2197 | TT_TASK | Event 017E - Shaft E - Preventive Grouting | Wed Jun 06 08:00:00 IDT 2018 | Thu Jul 05 16:00:00 IDT 2018 | Thu May 10 08:00:00 IDT 2018 | Fri May 25 16:00:00 IDT 2018 |  | COMPLETED
2198 | TT_TASK | Event 021E - AAA amendment (and cofferdam enlargement) for Shaft E | Thu Jul 26 08:00:00 IDT 2018 | Fri Aug 24 16:00:00 IDT 2018 | Fri Jun 29 08:00:00 IDT 2018 | Fri Jul 27 16:00:00 IDT 2018 |  | COMPLETED
2199 | TT_TASK | Event 021E - Consent for pipe piles (incl' APG) and grout curtain further to AAA amendment | Sun Aug 26 08:00:00 IDT 2018 | Wed Sep 05 16:00:00 IDT 2018 | Fri Jul 27 08:00:00 IDT 2018 | Mon Aug 06 16:00:00 IDT 2018 |  | COMPLETED
2201 | TT_TASK | Event 034 - ROI #113 Crest Wall Removal / method statement, mobilize subcon, etc | Thu Jul 26 08:00:00 IDT 2018 | Fri Aug 24 16:00:00 IDT 2018 | Tue Jul 17 08:00:00 IDT 2018 | Tue Aug 14 16:00:00 IDT 2018 |  | COMPLETED
2202 | TT_TASK | Event 034 - ROI #113 Crest Wall Removal / site works | Sat Sep 15 08:00:00 IDT 2018 | Fri Oct 05 16:00:00 IDT 2018 | Wed Aug 15 08:00:00 IDT 2018 | Mon Sep 10 16:00:00 IDT 2018 |  | COMPLETED
2203 | TT_TASK | Event 060E - Probing test to jet grout block | Sat Jun 01 08:00:00 IDT 2019 | Sun Jun 02 16:00:00 IDT 2019 | Thu May 16 08:00:00 IDT 2019 | Thu May 16 16:00:00 IDT 2019 |  | COMPLETED
2204 | TT_TASK | Shaft E - Utilities Diversion | Fri May 04 08:00:00 IDT 2018 | Mon Jun 25 16:00:00 IDT 2018 | Mon Mar 19 08:00:00 IST 2018 | Wed May 30 16:00:00 IDT 2018 |  | COMPLETED
2206 | TT_TASK | Shaft E - Grout Block (at lunching area) | Wed Apr 10 08:00:00 IDT 2019 | Sat May 11 16:00:00 IDT 2019 | Tue Feb 12 08:00:00 IST 2019 | Sat Mar 16 16:00:00 IST 2019 |  | COMPLETED
2208 | TT_TASK | Shaft E /Grout Block - Core sample | Fri May 17 08:00:00 IDT 2019 | Thu Jun 06 16:00:00 IDT 2019 | Wed Feb 27 08:00:00 IST 2019 | Fri Mar 15 16:00:00 IST 2019 |  | COMPLETED
2209 | TT_TASK | Shaf E /Grout Block - Test to early achievement of 28 day strength | Mon Apr 29 08:00:00 IDT 2019 | Wed May 01 16:00:00 IDT 2019 | Tue Mar 12 08:00:00 IST 2019 | Fri Mar 29 16:00:00 IDT 2019 |  | COMPLETED
2210 | TT_TASK | Shaft E/ Grout Block - Jet grout assessment report (AF TBC) | Sat May 04 08:00:00 IDT 2019 | Fri May 10 16:00:00 IDT 2019 | Sat Mar 30 08:00:00 IDT 2019 | Tue Apr 23 16:00:00 IDT 2019 |  | COMPLETED
2211 | TT_TASK | Shaft E - BA8 consent for pile wall opening | Sat May 04 08:00:00 IDT 2019 | Fri May 31 16:00:00 IDT 2019 | Thu Apr 18 08:00:00 IDT 2019 | Wed Jun 12 16:00:00 IDT 2019 |  | COMPLETED
2212 | TT_TASK | Shaft E - 610 Dia. Pipe Pile Wall @ 750 c/c (52 nos) | Tue Jul 03 08:00:00 IDT 2018 | Wed Sep 12 16:00:00 IDT 2018 | Mon Jun 04 08:00:00 IDT 2018 | Fri Nov 16 16:00:00 IST 2018 |  | COMPLETED
2213 | TT_TASK | Shaft E - BD Consent for Excavation & ELS above +4.7 mPD | Wed Dec 26 08:00:00 IST 2018 | Tue Jan 22 16:00:00 IST 2019 | Tue Dec 18 08:00:00 IST 2018 | Mon Feb 25 16:00:00 IST 2019 |  | COMPLETED
2214 | TT_TASK | Shaft E - Grout Curtain (behind pipe pile wall) (total drilling 1490m) | Mon Nov 26 08:00:00 IST 2018 | Mon Dec 17 16:00:00 IST 2018 | Tue Nov 20 08:00:00 IST 2018 | Mon Dec 10 16:00:00 IST 2018 |  | COMPLETED
2215 | TT_TASK | Shaft E - Pumping Test and Report Submission | Wed Dec 26 08:00:00 IST 2018 | Tue Jan 15 16:00:00 IST 2019 | Sat Dec 15 08:00:00 IST 2018 | Mon Jan 28 16:00:00 IST 2019 |  | COMPLETED
2216 | TT_TASK | Shaft E - BD Consent for Excavation & ELS from +4.7 to -1.6 mPD | Tue Apr 02 08:00:00 IDT 2019 | Mon Apr 29 16:00:00 IDT 2019 | Tue Jan 29 08:00:00 IST 2019 | Mon Feb 25 16:00:00 IST 2019 |  | COMPLETED
2217 | TT_TASK | Shaft E - Excavate to 0.5m below 1st layer of struts / Install lagging plate | Wed Feb 13 08:00:00 IST 2019 | Tue Feb 19 16:00:00 IST 2019 | Tue Jan 15 08:00:00 IST 2019 | Sat Jan 19 16:00:00 IST 2019 |  | COMPLETED
2218 | TT_TASK | Shaft E - Install 1st layer of struts (22 t) | Wed Feb 20 08:00:00 IST 2019 | Sat Feb 23 16:00:00 IST 2019 | Sun Jan 20 08:00:00 IST 2019 | Wed Jan 23 16:00:00 IST 2019 |  | COMPLETED
2219 | TT_TASK | Shaft E - Excavate to below 2nd layer of strut | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 05 16:00:00 IDT 2019 | Fri Mar 01 08:00:00 IST 2019 | Tue Mar 05 16:00:00 IST 2019 |  | COMPLETED
2220 | TT_TASK | Shaft E - Intstall lagging plates and 2nd layer of strut | Tue Apr 02 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Sat Mar 02 08:00:00 IST 2019 | Fri Mar 08 16:00:00 IST 2019 |  | COMPLETED
2221 | TT_TASK | Shaft E - Excavate to below 3rd layer of strut | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 05 16:00:00 IDT 2019 | Sat Mar 09 08:00:00 IST 2019 | Sun Mar 10 16:00:00 IST 2019 |  | COMPLETED
2222 | TT_TASK | Shaft E - Intstall lagging plates and 3rd layer of strut | Tue Apr 02 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Mon Mar 11 08:00:00 IST 2019 | Fri Mar 15 16:00:00 IST 2019 |  | COMPLETED
2223 | TT_TASK | Shaft E - Excavate to below 4th layer of strut | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 05 16:00:00 IDT 2019 | Sat Mar 16 08:00:00 IST 2019 | Sun Mar 17 16:00:00 IST 2019 |  | COMPLETED
2224 | TT_TASK | Shaft E - Intstall lagging plates and 4th layer of strut | Tue Apr 02 08:00:00 IDT 2019 | Sat Apr 06 16:00:00 IDT 2019 | Sun Mar 17 08:00:00 IST 2019 | Tue Mar 26 16:00:00 IST 2019 |  | COMPLETED
2225 | TT_TASK | Shaft E - Excavate to below 5th layer of strut | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 05 16:00:00 IDT 2019 | Wed Mar 27 08:00:00 IST 2019 | Thu Mar 28 16:00:00 IST 2019 |  | COMPLETED
2226 | TT_TASK | Shaft E - Intstall lagging plates and 5th layer of strut | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 05 16:00:00 IDT 2019 | Thu Mar 28 08:00:00 IST 2019 | Tue Apr 02 16:00:00 IDT 2019 |  | COMPLETED
2227 | TT_TASK | Shaft E - Excavate to below 6th layer of strut | Wed May 01 08:00:00 IDT 2019 | Mon May 06 16:00:00 IDT 2019 | Wed Apr 03 08:00:00 IDT 2019 | Fri Apr 05 16:00:00 IDT 2019 |  | COMPLETED
2228 | TT_TASK | Shaft E - Intstall lagging plates and 6th layer of strut | Thu May 02 08:00:00 IDT 2019 | Tue May 07 16:00:00 IDT 2019 | Sat Apr 06 08:00:00 IDT 2019 | Tue Apr 09 16:00:00 IDT 2019 |  | COMPLETED
2229 | TT_TASK | Shaft E - Excavate to below 7th layer of strut | Wed May 08 08:00:00 IDT 2019 | Mon May 13 16:00:00 IDT 2019 | Thu Apr 11 08:00:00 IDT 2019 | Sat Apr 13 16:00:00 IDT 2019 |  | COMPLETED
2230 | TT_TASK | Shaft E - Intstall lagging plates and 7th layer of strut | Wed May 01 08:00:00 IDT 2019 | Mon May 06 16:00:00 IDT 2019 | Sun Apr 14 08:00:00 IDT 2019 | Wed Apr 24 16:00:00 IDT 2019 |  | COMPLETED
2231 | TT_TASK | Shaft E - Excavate to below 8th layer of strut | Wed May 01 08:00:00 IDT 2019 | Mon May 06 16:00:00 IDT 2019 | Thu Apr 25 08:00:00 IDT 2019 | Wed May 01 16:00:00 IDT 2019 |  | COMPLETED
2232 | TT_TASK | Shaft E - Intstall lagging plates and 8th layer of strut | Mon Jun 03 08:00:00 IDT 2019 | Thu Jun 06 16:00:00 IDT 2019 | Thu May 02 08:00:00 IDT 2019 | Sun May 05 16:00:00 IDT 2019 |  | COMPLETED
2233 | TT_TASK | Shaft E - Excavate to final excavation level -18 mPD /install lagging plate/ S9 at FEL | Sat Jun 01 08:00:00 IDT 2019 | Wed Jun 12 16:00:00 IDT 2019 | Mon May 06 08:00:00 IDT 2019 | Wed May 22 16:00:00 IDT 2019 |  | COMPLETED
2234 | TT_TASK | Shaft E - Cast base slab /skin wall | Mon Jun 03 08:00:00 IDT 2019 | Wed Jun 12 16:00:00 IDT 2019 | Sun May 19 08:00:00 IDT 2019 | Tue Jun 11 16:00:00 IDT 2019 |  | COMPLETED
2235 | TT_TASK | Shaft E - Cast-in bottom layers of struts with base slab | Sat Jun 01 08:00:00 IDT 2019 | Sat Jun 01 16:00:00 IDT 2019 | Wed May 22 08:00:00 IDT 2019 | Wed May 22 16:00:00 IDT 2019 |  | COMPLETED
2236 | TT_TASK | Shaft E - Break through the pipe pile wall for launching TBM | Mon Aug 05 08:00:00 IDT 2019 | Thu Aug 15 16:00:00 IDT 2019 | Wed Jun 12 08:00:00 IDT 2019 | Thu Jun 27 16:00:00 IDT 2019 |  | COMPLETED
2237 | TT_TASK | Shaft E - Set up and launch TBM to Shaft F | Thu Aug 01 08:00:00 IDT 2019 | Sun Aug 25 16:00:00 IDT 2019 | Wed Jun 12 08:00:00 IDT 2019 | Fri Aug 16 16:00:00 IDT 2019 |  | COMPLETED
2238 | TT_TASK | Shaft E - Micro tunneling and pipe jacking to Shaft F (Part 1 of 2) | Wed Sep 18 08:00:00 IDT 2019 | Wed Oct 02 16:00:00 IDT 2019 | Sat Aug 17 08:00:00 IDT 2019 | Wed Sep 18 16:00:00 IDT 2019 |  | COMPLETED
2239 | TT_TASK | Shaft E - Remove jacking frame, thrust block and etc | Wed Jan 01 08:00:00 IST 2020 | Wed Jan 01 16:00:00 IST 2020 | Wed Oct 30 08:00:00 IST 2019 | Tue Nov 12 16:00:00 IST 2019 |  | COMPLETED
2240 | TT_TASK | Shaft E - Install CW pipe to 0.5m above 7th layer of strut and mass fill | Wed Jan 01 08:00:00 IST 2020 | Thu Jan 02 16:00:00 IST 2020 | Wed Nov 13 08:00:00 IST 2019 | Sat Nov 16 16:00:00 IST 2019 |  | COMPLETED
2241 | TT_TASK | Shaft E - Install CW pipe to 0.5m above 6th layer of strut and mass fill | Fri Jan 03 08:00:00 IST 2020 | Sat Jan 04 16:00:00 IST 2020 | Mon Nov 18 08:00:00 IST 2019 | Wed Nov 20 16:00:00 IST 2019 |  | COMPLETED
2242 | TT_TASK | Shaft E - Install CW pipe to 0.5m above 5th layer of strut and mass fill | Wed Jan 01 08:00:00 IST 2020 | Thu Jan 02 16:00:00 IST 2020 | Thu Nov 21 08:00:00 IST 2019 | Fri Nov 22 16:00:00 IST 2019 |  | COMPLETED
2243 | TT_TASK | Shaft E - Install CW pipe to 0.5m above 4th layer of strut and mass fill | Fri Jan 03 08:00:00 IST 2020 | Sat Jan 04 16:00:00 IST 2020 | Sat Nov 23 08:00:00 IST 2019 | Sat Nov 23 16:00:00 IST 2019 |  | COMPLETED
2244 | TT_TASK | Shaft E - Install CW pipe to 0.5m above 3rd layer of strut and mass fill | Sun Jan 05 08:00:00 IST 2020 | Mon Jan 06 16:00:00 IST 2020 | Sun Nov 24 08:00:00 IST 2019 | Tue Nov 26 16:00:00 IST 2019 |  | COMPLETED
2245 | TT_TASK | Shaft E - Install CW pipe to 0.5m above 2nd layer of strut and mass fill | Tue Jan 07 08:00:00 IST 2020 | Wed Jan 08 16:00:00 IST 2020 | Wed Nov 27 08:00:00 IST 2019 | Thu Nov 28 16:00:00 IST 2019 |  | COMPLETED
2246 | TT_TASK | Testing to CWP between Shaft E and Shaft F (Part 1 of 2) | Wed Jan 01 08:00:00 IST 2020 | Tue Jan 07 16:00:00 IST 2020 | Fri Nov 29 08:00:00 IST 2019 | Fri Nov 29 08:00:00 IST 2019 |  | COMPLETED
2247 | TT_TASK | Shaft E - Connect CW pipe to Discharge Culvert | Sun Jan 12 08:00:00 IST 2020 | Mon Jan 13 16:00:00 IST 2020 | Tue Dec 10 08:00:00 IST 2019 | Wed Dec 18 16:00:00 IST 2019 |  | COMPLETED
2248 | TT_TASK | Shaft E - Trim pipe piles | Wed Jan 01 08:00:00 IST 2020 | Sat Jan 04 16:00:00 IST 2020 | Wed Jan 01 08:00:00 IST 2020 | Sat Jan 04 16:00:00 IST 2020 |  | COMPLETED
2249 | TT_TASK | Shaft E - Backfill and reinstate to ground level | Sun Jan 05 08:00:00 IST 2020 | Fri Jan 10 16:00:00 IST 2020 | Sun Jan 05 08:00:00 IST 2020 | Fri Jan 10 16:00:00 IST 2020 |  | COMPLETED
2252 | TT_TASK | Discharge Culvert - Utilities Diversion along Sea Bank Road | Fri May 04 08:00:00 IDT 2018 | Mon Jun 25 16:00:00 IDT 2018 | Wed Apr 25 08:00:00 IDT 2018 | Wed Jun 20 16:00:00 IDT 2018 |  | COMPLETED
2253 | TT_TASK | Discharge Culvert /Zone A (Eastern Section) - Pipe Pile (PPS080-240, PPS330-490 excl' 1800 culvert) | Wed Dec 05 08:00:00 IST 2018 | Thu Jan 17 16:00:00 IST 2019 | Tue Aug 28 08:00:00 IDT 2018 | Mon Nov 12 16:00:00 IST 2018 |  | COMPLETED
2254 | TT_TASK | Discharge Culvert /Zone A (Eastern Section) - Grout curtain behind pile wall - excl' 1800 drainage area | Mon Nov 26 08:00:00 IST 2018 | Tue Jan 08 16:00:00 IST 2019 | Wed Sep 19 00:00:00 IDT 2018 | Sat Jan 12 16:00:00 IST 2019 |  | COMPLETED
2255 | TT_TASK | Discharge Culvert /Zone A (Eastern Section) - all remaining works held up by the issue of 1800 culvert | Sun Mar 31 08:00:00 IDT 2019 | Fri Jun 28 16:00:00 IDT 2019 | Sat Jan 26 08:00:00 IST 2019 | Wed Jul 10 16:00:00 IDT 2019 |  | COMPLETED
2256 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - Pumping Test & Assessment Report to BD | Wed May 01 08:00:00 IDT 2019 | Tue May 21 16:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Wed May 22 16:00:00 IDT 2019 |  | COMPLETED
2257 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - BD Consent for Commencement of Excavation & ELS | Sun Jun 09 08:00:00 IDT 2019 | Sat Jul 06 16:00:00 IDT 2019 | Thu May 16 08:00:00 IDT 2019 | Wed Jun 12 16:00:00 IDT 2019 |  | COMPLETED
2258 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - Excavate to 0.5m below 1st layer of struts | Thu Aug 01 08:00:00 IDT 2019 | Sat Aug 03 16:00:00 IDT 2019 | Sun May 26 08:00:00 IDT 2019 | Tue May 28 16:00:00 IDT 2019 |  | COMPLETED
2259 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - Install 1st layer of struts | Mon Aug 05 08:00:00 IDT 2019 | Fri Aug 09 16:00:00 IDT 2019 | Wed May 29 08:00:00 IDT 2019 | Sat Jun 01 16:00:00 IDT 2019 |  | COMPLETED
2260 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - Excavate below 1st layer of struts to FEL | Thu Aug 01 08:00:00 IDT 2019 | Sat Aug 10 16:00:00 IDT 2019 | Fri Jun 14 08:00:00 IDT 2019 | Mon Jun 24 16:00:00 IDT 2019 |  | COMPLETED
2261 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - Lagging plate below 1st layer of struts to FEL | Thu Aug 01 08:00:00 IDT 2019 | Mon Aug 05 16:00:00 IDT 2019 | Tue Jun 25 08:00:00 IDT 2019 | Thu Jul 04 16:00:00 IDT 2019 |  | COMPLETED
2262 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - Blinding concrete | Thu Aug 01 08:00:00 IDT 2019 | Tue Aug 06 16:00:00 IDT 2019 | Fri Jul 05 08:00:00 IDT 2019 | Tue Jul 09 16:00:00 IDT 2019 |  | COMPLETED
2263 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - Cast base slab and kicker | Thu Aug 01 08:00:00 IDT 2019 | Thu Aug 22 16:00:00 IDT 2019 | Wed Jul 10 08:00:00 IDT 2019 | Wed Jul 17 16:00:00 IDT 2019 |  | COMPLETED
2264 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - Construct manholes | Thu Jan 02 08:00:00 IST 2020 | Wed Jan 22 16:00:00 IST 2020 | Mon Aug 26 08:00:00 IDT 2019 | Thu Nov 14 16:00:00 IST 2019 |  | COMPLETED
2265 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - Install drainage pipes | Thu Jan 23 08:00:00 IST 2020 | Wed Feb 05 16:00:00 IST 2020 | Mon Aug 26 08:00:00 IDT 2019 | Thu Nov 14 16:00:00 IST 2019 |  | COMPLETED
2266 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - Cast side walls and top slab | Mon Aug 12 08:00:00 IDT 2019 | Mon Sep 02 16:00:00 IDT 2019 | Wed Jul 17 08:00:00 IDT 2019 | Tue Aug 06 16:00:00 IDT 2019 |  | COMPLETED
2267 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - Backfill to 0.5m below 1st layer of struts | Thu Jan 02 08:00:00 IST 2020 | Sat Jan 04 16:00:00 IST 2020 | Wed Aug 07 08:00:00 IDT 2019 | Sat Aug 10 16:00:00 IDT 2019 |  | COMPLETED
2268 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - Remove 1st layer of struts | Mon Jan 06 08:00:00 IST 2020 | Mon Jan 06 16:00:00 IST 2020 | Mon Aug 12 08:00:00 IDT 2019 | Mon Aug 12 16:00:00 IDT 2019 |  | COMPLETED
2269 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - Trim pipe piles | Tue Jan 07 08:00:00 IST 2020 | Mon Jan 13 16:00:00 IST 2020 | Tue Aug 13 08:00:00 IDT 2019 | Tue Aug 20 16:00:00 IDT 2019 |  | COMPLETED
2270 | TT_TASK | Discharge Culvert /Zone A1 (Eastern Section) - Backfill and reinstate to ground level | Tue Jan 14 08:00:00 IST 2020 | Mon Jan 20 16:00:00 IST 2020 | Mon Nov 18 08:00:00 IST 2019 | Sat Nov 23 16:00:00 IST 2019 |  | COMPLETED
2271 | TT_TASK | Discharge Culvert /Zone B(&A3) (Western Section) - Pipe Pile (PPS001-079, PPS491-570) - excl' 1800 drainage area | Fri Jan 18 08:00:00 IST 2019 | Wed Mar 06 16:00:00 IST 2019 | Mon Oct 22 08:00:00 IDT 2018 | Thu Nov 29 16:00:00 IST 2018 |  | COMPLETED
2272 | TT_TASK | Discharge Culvert / Grout Curtain (as a temporary cut off from Zone A2) | Tue May 07 08:00:00 IDT 2019 | Fri May 17 16:00:00 IDT 2019 | Wed Mar 06 08:00:00 IST 2019 | Tue Mar 19 16:00:00 IST 2019 |  | COMPLETED
2273 | TT_TASK | Discharge Culvert /Zone B(&A3) (Western Section) - Grout curtain behind pipe pile wall | Sat Jan 26 08:00:00 IST 2019 | Mon Mar 04 16:00:00 IST 2019 | Wed Nov 21 08:00:00 IST 2018 | Thu Jan 10 16:00:00 IST 2019 |  | COMPLETED
2274 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - Pumping Test & Assessment Report to BD | Sat Jun 01 08:00:00 IDT 2019 | Fri Jun 21 16:00:00 IDT 2019 | Mon May 27 08:00:00 IDT 2019 | Wed Jun 12 16:00:00 IDT 2019 |  | COMPLETED
2275 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - BD Consent for Commencement of Excavation & ELS | Thu Aug 01 08:00:00 IDT 2019 | Wed Aug 28 16:00:00 IDT 2019 | Thu Jun 06 08:00:00 IDT 2019 | Wed Jul 03 16:00:00 IDT 2019 |  | COMPLETED
2276 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - Excavate to 0.5m below 1st layer of struts | Thu Aug 01 08:00:00 IDT 2019 | Sat Aug 03 16:00:00 IDT 2019 | Thu Jul 18 08:00:00 IDT 2019 | Sat Jul 20 16:00:00 IDT 2019 |  | COMPLETED
2277 | TT_TASK | Discharge Culvert /Zone B (Shaft E Interface Section) - Pumping Test & Assessment Report to BD | Thu Aug 01 08:00:00 IDT 2019 | Wed Aug 21 16:00:00 IDT 2019 | Tue Jun 11 08:00:00 IDT 2019 | Wed Jun 26 16:00:00 IDT 2019 |  | COMPLETED
2278 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - Install 1st layer of struts | Thu Aug 01 08:00:00 IDT 2019 | Mon Aug 05 16:00:00 IDT 2019 | Mon Jul 22 08:00:00 IDT 2019 | Fri Jul 26 16:00:00 IDT 2019 |  | COMPLETED
2279 | TT_TASK | Discharge Culvert /Zone B (Shaft E Interface Section) - BD Consent for Commencement of Excavation & ELS | Wed Jan 01 08:00:00 IST 2020 | Tue Jan 28 16:00:00 IST 2020 | Fri Nov 15 08:00:00 IST 2019 | Thu Dec 12 16:00:00 IST 2019 |  | COMPLETED
2280 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - Excavate below 1st layer of struts to FEL | Thu Aug 01 08:00:00 IDT 2019 | Sat Aug 10 16:00:00 IDT 2019 | Sat Jul 27 08:00:00 IDT 2019 | Tue Aug 06 16:00:00 IDT 2019 |  | COMPLETED
2281 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - Lagging plate below 1st layer of struts to FEL | Mon Sep 09 08:00:00 IDT 2019 | Fri Sep 13 16:00:00 IDT 2019 | Thu Aug 08 08:00:00 IDT 2019 | Mon Aug 12 16:00:00 IDT 2019 |  | COMPLETED
2282 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - Blinding concrete | Thu Jan 02 08:00:00 IST 2020 | Tue Jan 07 16:00:00 IST 2020 | Tue Nov 12 08:00:00 IST 2019 | Tue Nov 12 16:00:00 IST 2019 |  | COMPLETED
2283 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - Cast base slab and kicker | Wed Jan 08 08:00:00 IST 2020 | Thu Jan 16 16:00:00 IST 2020 | Wed Nov 13 08:00:00 IST 2019 | Wed Nov 20 16:00:00 IST 2019 |  | COMPLETED
2284 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - Construct manholes | Thu Jan 02 08:00:00 IST 2020 | Wed Jan 22 16:00:00 IST 2020 | Mon Dec 16 08:00:00 IST 2019 | Fri Jan 24 16:00:00 IST 2020 |  | COMPLETED
2285 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - Install drainage pipes | Thu Jan 16 08:00:00 IST 2020 | Wed Jan 22 16:00:00 IST 2020 | Mon Dec 16 08:00:00 IST 2019 | Fri Jan 24 16:00:00 IST 2020 |  | COMPLETED
2286 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - Cast side walls and top slab | Fri Jan 17 08:00:00 IST 2020 | Sat Feb 01 16:00:00 IST 2020 | Thu Nov 21 08:00:00 IST 2019 | Sun Dec 15 16:00:00 IST 2019 |  | COMPLETED
2287 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - Backfill to 0.5m below 1st layer of struts | Thu Jan 02 08:00:00 IST 2020 | Sat Jan 04 16:00:00 IST 2020 | Mon Dec 16 08:00:00 IST 2019 | Wed Dec 18 16:00:00 IST 2019 |  | COMPLETED
2288 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - Remove 1st layer of struts | Mon Jan 06 08:00:00 IST 2020 | Mon Jan 06 16:00:00 IST 2020 | Thu Dec 19 08:00:00 IST 2019 | Thu Dec 19 16:00:00 IST 2019 |  | COMPLETED
2289 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - Trim pipe piles | Tue Jan 07 08:00:00 IST 2020 | Mon Jan 13 16:00:00 IST 2020 | Fri Dec 20 08:00:00 IST 2019 | Sat Dec 28 16:00:00 IST 2019 |  | COMPLETED
2290 | TT_TASK | Discharge Culvert /Zone A3 (Western Section) - Backfill and reinstate to ground level | Sat Feb 01 08:00:00 IST 2020 | Fri Feb 07 16:00:00 IST 2020 | Sat Feb 01 08:00:00 IST 2020 | Fri Feb 07 16:00:00 IST 2020 |  | COMPLETED
2291 | TT_TASK | Discharge Culvert /Zone B (Shaft E Interface Section) - 1st layer excavation and ELS | Wed Jan 01 08:00:00 IST 2020 | Tue Jan 07 16:00:00 IST 2020 | Mon Nov 18 08:00:00 IST 2019 | Thu Nov 21 16:00:00 IST 2019 |  | COMPLETED
2292 | TT_TASK | Discharge Culvert /Zone B (Shaft E Interface Section) - Excavation below 1st layer of strut to FEL | Wed Jan 08 08:00:00 IST 2020 | Sat Jan 11 16:00:00 IST 2020 | Fri Nov 22 08:00:00 IST 2019 | Tue Nov 26 16:00:00 IST 2019 |  | COMPLETED
2293 | TT_TASK | Discharge Culvert /Shaft E Interface - Install CW pipe between Shaft E and Discharge Culvert | Fri Jan 03 08:00:00 IST 2020 | Sat Jan 11 16:00:00 IST 2020 | Fri Dec 06 08:00:00 IST 2019 | Sun Dec 15 16:00:00 IST 2019 |  | COMPLETED
2294 | TT_TASK | Discharge Culvert /Zone B (Shaft E Interface Section) - Remaining drainage works and backfill | Wed Jan 01 08:00:00 IST 2020 | Thu Jan 30 16:00:00 IST 2020 | Thu Dec 19 08:00:00 IST 2019 | Fri Jan 24 16:00:00 IST 2020 |  | COMPLETED
2295 | TT_TASK | Discharge Culvert /Zone B (Shaft E Interface Section) - RC works | Sun Jan 12 08:00:00 IST 2020 | Sun Jan 26 16:00:00 IST 2020 | Wed Nov 27 08:00:00 IST 2019 | Sun Dec 15 16:00:00 IST 2019 |  | COMPLETED
2296 | TT_TASK | Discharge Culvert /Zone B (Shaft E Interface Section) - Strip internal space | Sun Jan 12 08:00:00 IST 2020 | Tue Jan 14 16:00:00 IST 2020 | Tue Dec 17 08:00:00 IST 2019 | Wed Dec 18 16:00:00 IST 2019 |  | COMPLETED
2297 | TT_TASK | Discharge Culvert /Zone A2 (1800 Drainage Section) - Remaining drainage works and backfill | Wed Jan 01 08:00:00 IST 2020 | Thu Jan 30 16:00:00 IST 2020 | Tue Nov 26 08:00:00 IST 2019 | Fri Jan 24 16:00:00 IST 2020 |  | COMPLETED
2299 | TT_TASK | Event 017S - Sea Bank Road (Zone A and Zone B excl' 1800 culvert) - Advanced Precautionary Grouting | Sat Jun 02 08:00:00 IDT 2018 | Tue Jul 31 16:00:00 IDT 2018 | Fri May 25 08:00:00 IDT 2018 | Thu Aug 30 16:00:00 IDT 2018 |  | COMPLETED
2300 | TT_TASK | Event 017S - Sea Bank Road (Zone C) - Advanced Precautionary Grouting inside creast wall | Mon Nov 26 08:00:00 IST 2018 | Fri Nov 30 16:00:00 IST 2018 | Tue Sep 04 08:00:00 IDT 2018 | Sat Sep 08 16:00:00 IDT 2018 |  | COMPLETED
2301 | TT_TASK | Event 017S - Sea Bank Road (Zone C) - Advanced Precautionary Grouting outside creast wall | Mon Nov 26 08:00:00 IST 2018 | Fri Nov 30 16:00:00 IST 2018 | Tue Oct 16 08:00:00 IDT 2018 | Sat Oct 20 16:00:00 IDT 2018 |  | COMPLETED
2303 | TT_TASK | Event 025S - Preventive grouting stopped as it's being legalized via AAA amendment | Wed Jun 27 08:00:00 IDT 2018 | Thu Aug 02 16:00:00 IDT 2018 | Fri Jun 22 08:00:00 IDT 2018 | Sun Jul 29 16:00:00 IDT 2018 |  | COMPLETED
2304 | TT_TASK | Event 037a - Discharge Culvert / Zone A & B amendment (Type II) | Sat Jan 26 08:00:00 IST 2019 | Sun Feb 24 16:00:00 IST 2019 | Wed Jan 02 08:00:00 IST 2019 | Thu Jan 31 16:00:00 IST 2019 |  | COMPLETED
2305 | TT_TASK | Event 037b - Discharge Culvert / 1800 drainage amendment (Type II) | Sat Jan 26 08:00:00 IST 2019 | Sun Feb 24 16:00:00 IST 2019 | Wed Jan 02 08:00:00 IST 2019 | Thu Jan 31 16:00:00 IST 2019 |  | COMPLETED
2306 | TT_TASK | Event 037d - Discharge Culvert / 1800 drainage & TBM alignment (Type II) | Sun Mar 31 08:00:00 IDT 2019 | Mon Apr 29 16:00:00 IDT 2019 | Tue Mar 26 08:00:00 IST 2019 | Tue Apr 30 16:00:00 IDT 2019 |  | COMPLETED
2307 | TT_TASK | Event 044 - Set up and conduct plate load test PL4 at SBR Zone A3 | Fri Nov 01 08:00:00 IST 2019 | Wed Nov 06 16:00:00 IST 2019 | Fri Sep 06 08:00:00 IDT 2019 | Mon Sep 09 16:00:00 IDT 2019 |  | COMPLETED
2308 | TT_TASK | Event 055 - 1800 drainage pipe at SBR / Pumping test and assessment report to BD (Zone A2) | Thu Aug 01 08:00:00 IDT 2019 | Sat Aug 17 16:00:00 IDT 2019 | Wed Jul 17 08:00:00 IDT 2019 | Fri Jul 26 16:00:00 IDT 2019 |  | COMPLETED
2309 | TT_TASK | Event 055 - 1800 drainage pipe at SBR / Excavation consent (Zone A2) | Sun Aug 11 08:00:00 IDT 2019 | Sat Sep 07 16:00:00 IDT 2019 | Wed Jul 31 08:00:00 IDT 2019 | Wed Aug 28 16:00:00 IDT 2019 |  | COMPLETED
2310 | TT_TASK | Event 055 - 1800 drainage pipe at SBR / Excavation and construction of Discharge Culvert (Zone A2) | Fri Nov 01 08:00:00 IST 2019 | Mon Jan 27 16:00:00 IST 2020 | Sat Sep 07 08:00:00 IDT 2019 | Mon Nov 25 16:00:00 IST 2019 |  | COMPLETED
2311 | TT_TASK | Event 062 - Construct temporary mucking pit at SBR Zone A3 | Sat Sep 14 08:00:00 IDT 2019 | Wed Sep 18 16:00:00 IDT 2019 | Tue Aug 13 08:00:00 IDT 2019 | Sat Aug 17 16:00:00 IDT 2019 |  | COMPLETED
2313 | TT_TASK | Outfall Apron Modif - Bulkhead Installation | Wed Apr 18 08:00:00 IDT 2018 | Sat Apr 21 16:00:00 IDT 2018 | Thu Feb 22 08:00:00 IST 2018 | Sun Feb 25 16:00:00 IST 2018 |  | COMPLETED
2314 | TT_TASK | Outfall Apron Modif - Bulkhead Modification (fixing method) - during CNY shutdown | Sun Mar 31 08:00:00 IDT 2019 | Wed Apr 03 16:00:00 IDT 2019 | Fri Feb 08 08:00:00 IST 2019 | Sat Feb 09 16:00:00 IST 2019 |  | COMPLETED
2315 | TT_TASK | Event 036 - Dicharge Culvert / Outfall portion amendment (Type II) | Mon Nov 26 08:00:00 IST 2018 | Tue Dec 25 16:00:00 IST 2018 | Wed Sep 12 08:00:00 IDT 2018 | Wed Oct 10 16:00:00 IDT 2018 |  | COMPLETED
2316 | TT_TASK | Event 056 - Bulkhead Modification (fixing method) - pre CNY | Sat Jan 26 08:00:00 IST 2019 | Sat Jan 26 16:00:00 IST 2019 | Thu Jan 24 08:00:00 IST 2019 | Wed Jan 30 16:00:00 IST 2019 |  | COMPLETED
2317 | TT_TASK | Event 059 - Discharge Culvert / Zone C /Plate Load Test | Thu May 30 08:00:00 IDT 2019 | Wed Jun 05 16:00:00 IDT 2019 | Sat Mar 02 08:00:00 IST 2019 | Mon Mar 18 16:00:00 IST 2019 |  | COMPLETED
2318 | TT_TASK | Outfall Apron Modif /behind the crest wall - Remove rock armour and crest wall | Mon Aug 27 08:00:00 IDT 2018 | Mon Sep 03 16:00:00 IDT 2018 | Mon Oct 08 08:00:00 IDT 2018 | Wed Oct 10 00:00:00 IDT 2018 |  | COMPLETED
2319 | TT_TASK | Outfall Apron Modif /behind the crest wall - Rock fill to +5.7mPD to form temporary working platform | Mon Aug 27 08:00:00 IDT 2018 | Thu Aug 30 16:00:00 IDT 2018 | Wed Oct 10 00:00:00 IDT 2018 | Fri Oct 12 16:00:00 IDT 2018 |  | COMPLETED
2320 | TT_TASK | Outfall Apron Modif /behind the crest wall - Pipe Piles (PPS271-280) | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Mon Oct 22 08:00:00 IDT 2018 | Wed Oct 24 00:00:00 IDT 2018 |  | COMPLETED
2321 | TT_TASK | Outfall Apron Modif /on Sea Bank Road - Pile Piles (PPS241-270, PPS281-329) | Thu Nov 29 08:00:00 IST 2018 | Tue Dec 04 16:00:00 IST 2018 | Mon Sep 17 08:00:00 IDT 2018 | Wed Oct 03 00:00:00 IDT 2018 |  | COMPLETED
2322 | TT_TASK | Outfall Apron Modif /behind the crest wall - Grout Curtain | Mon Nov 26 08:00:00 IST 2018 | Tue Dec 04 16:00:00 IST 2018 | Sat Oct 27 08:00:00 IDT 2018 | Mon Nov 05 16:00:00 IST 2018 |  | COMPLETED
2323 | TT_TASK | Outfall Apron Modif /on Sea Bank Road - Grout Curtain | Wed Dec 05 08:00:00 IST 2018 | Wed Dec 12 16:00:00 IST 2018 | Thu Oct 04 08:00:00 IDT 2018 | Mon Nov 05 16:00:00 IST 2018 |  | COMPLETED
2324 | TT_TASK | Outfall Apron Modif - Grout Curtain (as temporary cut off from Zone B and behind Outfall side wall) | Mon Nov 26 08:00:00 IST 2018 | Mon Dec 03 16:00:00 IST 2018 | Thu Oct 25 08:00:00 IDT 2018 | Thu Nov 01 16:00:00 IST 2018 |  | COMPLETED
2325 | TT_TASK | Outfall Apron Modif - Pumping Test and assessment report to BD | Mon Nov 26 08:00:00 IST 2018 | Thu Dec 13 16:00:00 IST 2018 | Thu Nov 08 08:00:00 IST 2018 | Fri Dec 21 16:00:00 IST 2018 |  | COMPLETED
2326 | TT_TASK | Outfall Apron Modif - BD Consent for Commencement of Excavation & ELS | Sun Jan 27 08:00:00 IST 2019 | Sat Feb 23 16:00:00 IST 2019 | Fri Dec 21 08:00:00 IST 2018 | Fri Feb 01 16:00:00 IST 2019 |  | COMPLETED
2327 | TT_TASK | Outfall Apron Modif - Excavate to 0.5m below the shoring layer | Sat Jan 26 08:00:00 IST 2019 | Mon Jan 28 16:00:00 IST 2019 | Fri Jan 04 08:00:00 IST 2019 | Sat Jan 12 16:00:00 IST 2019 |  | COMPLETED
2328 | TT_TASK | Outfall Apron Modif - Install the shoring | Tue Jan 29 08:00:00 IST 2019 | Thu Jan 31 16:00:00 IST 2019 | Mon Jan 14 08:00:00 IST 2019 | Tue Jan 22 16:00:00 IST 2019 |  | COMPLETED
2329 | TT_TASK | Outfall Apron Modif - Excavate to final excavation level +1.5 mPD (Zone C) | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 02 16:00:00 IDT 2019 | Thu Feb 14 08:00:00 IST 2019 | Fri Mar 01 16:00:00 IST 2019 |  | COMPLETED
2330 | TT_TASK | Outfall Apron Modif - Construct the box culvert section in Zone C | Sat Jun 01 08:00:00 IDT 2019 | Sat Jun 29 16:00:00 IDT 2019 | Wed May 08 08:00:00 IDT 2019 | Mon Aug 12 16:00:00 IDT 2019 |  | COMPLETED
2331 | TT_TASK | Outfall Apron Modif - Construct the box culvert to 0.5 m below the shoring | Fri Nov 01 08:00:00 IST 2019 | Thu Nov 14 16:00:00 IST 2019 | Sat Aug 24 08:00:00 IDT 2019 | Mon Sep 02 16:00:00 IDT 2019 |  | COMPLETED
2332 | TT_TASK | Outfall Apron Modif - Form the designed opening on apron wing wall (after stop logs installed) | Fri Nov 01 08:00:00 IST 2019 | Mon Nov 04 16:00:00 IST 2019 | Fri Sep 06 08:00:00 IDT 2019 | Tue Sep 24 16:00:00 IDT 2019 |  | COMPLETED
2333 | TT_TASK | Outfall Apron Modif - Backfill to 0.5m below the shoring | Thu Jan 02 08:00:00 IST 2020 | Fri Jan 03 16:00:00 IST 2020 | Thu Oct 31 08:00:00 IST 2019 | Fri Nov 01 16:00:00 IST 2019 |  | COMPLETED
2334 | TT_TASK | Outfall Apron Modif - Remove the shoring | Sat Jan 04 08:00:00 IST 2020 | Sat Jan 04 16:00:00 IST 2020 | Sat Nov 02 08:00:00 IST 2019 | Mon Nov 04 16:00:00 IST 2019 |  | COMPLETED
2335 | TT_TASK | Outfall Apron Modif - Construct the remaining box culvert structure | Tue Nov 05 08:00:00 IST 2019 | Mon Nov 11 16:00:00 IST 2019 | Wed Sep 25 08:00:00 IDT 2019 | Wed Oct 30 16:00:00 IST 2019 |  | COMPLETED
2336 | TT_TASK | Outfall Apron Modif - Trim pipe pile | Mon Jan 13 08:00:00 IST 2020 | Tue Jan 14 16:00:00 IST 2020 | Sat Nov 02 08:00:00 IST 2019 | Mon Nov 04 16:00:00 IST 2019 |  | COMPLETED
2337 | TT_TASK | Outfall Apron Modif - Backfill and reinstate crest wall and rock armour | Wed Jan 15 08:00:00 IST 2020 | Tue Jan 21 16:00:00 IST 2020 | Tue Nov 05 08:00:00 IST 2019 | Sat Nov 09 16:00:00 IST 2019 |  | COMPLETED
2343 | TT_TASK | Turbine Table - Further excavate from +4.1 to +3.0 | Fri Aug 04 08:00:00 IDT 2017 | Tue Aug 22 16:00:00 IDT 2017 | Fri Aug 04 08:00:00 IDT 2017 | Mon Aug 28 16:00:00 IDT 2017 |  | COMPLETED
2344 | TT_TASK | Turbine Table - Cast blinding concrete | Mon Nov 27 08:00:00 IST 2017 | Tue Nov 28 16:00:00 IST 2017 | Mon Oct 23 08:00:00 IDT 2017 | Tue Oct 24 16:00:00 IDT 2017 |  | COMPLETED
2345 | TT_TASK | Turbine Table TT1 - Trim pile and prepare pile head | Mon Sep 25 08:00:00 IDT 2017 | Fri Sep 29 16:00:00 IDT 2017 | Mon Sep 25 08:00:00 IDT 2017 | Fri Sep 29 16:00:00 IDT 2017 |  | COMPLETED
2346 | TT_TASK | Turbine Table TT1 - Capping plate and rebar starter | Sat Sep 30 08:00:00 IDT 2017 | Sat Oct 07 16:00:00 IDT 2017 | Sat Sep 30 08:00:00 IDT 2017 | Sat Oct 07 16:00:00 IDT 2017 |  | COMPLETED
2347 | TT_TASK | Turbine Table TT1 Bottom Half - Erect side formwork (if any) | Thu Oct 26 08:00:00 IDT 2017 | Fri Oct 27 16:00:00 IDT 2017 | Thu Oct 26 08:00:00 IDT 2017 | Fri Oct 27 16:00:00 IDT 2017 |  | COMPLETED
2348 | TT_TASK | Turbine Table TT1 Bottom Half - Fix rebar | Mon Oct 30 08:00:00 IST 2017 | Wed Nov 01 16:00:00 IST 2017 | Mon Oct 30 08:00:00 IST 2017 | Wed Nov 01 16:00:00 IST 2017 |  | COMPLETED
2349 | TT_TASK | Turbine Table TT1 Bottom Half - Close formwork (if any) | Thu Nov 02 08:00:00 IST 2017 | Thu Nov 02 16:00:00 IST 2017 | Thu Nov 02 08:00:00 IST 2017 | Thu Nov 02 16:00:00 IST 2017 |  | COMPLETED
2350 | TT_TASK | Turbine Table TT1 Bottom Half - Pour concrete (mono pour) | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 |  | COMPLETED
2351 | TT_TASK | Turbine Table TT1 - Install cast-in / embed items | Fri Nov 03 08:00:00 IST 2017 | Mon Nov 06 16:00:00 IST 2017 | Fri Nov 03 08:00:00 IST 2017 | Mon Nov 06 16:00:00 IST 2017 |  | COMPLETED
2352 | TT_TASK | Turbine Table TT1 Upper Half - Fix rebar | Sat Nov 04 08:00:00 IST 2017 | Tue Nov 07 16:00:00 IST 2017 | Sat Nov 04 08:00:00 IST 2017 | Tue Nov 07 16:00:00 IST 2017 |  | COMPLETED
2353 | TT_TASK | Turbine Table TT1 Upper Half - Close formwork (if any) | Wed Nov 08 08:00:00 IST 2017 | Wed Nov 08 16:00:00 IST 2017 | Wed Nov 08 08:00:00 IST 2017 | Wed Nov 08 16:00:00 IST 2017 |  | COMPLETED
2354 | TT_TASK | Turbine Table TT1 Upper Half - Pour concrete (mono pour) | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 |  | COMPLETED
2355 | TT_TASK | Turbine Table TT1 - Construct Plinth PL1, PL2 with cast-in / embed items | Fri Dec 29 08:00:00 IST 2017 | Fri Jan 19 16:00:00 IST 2018 | Wed Dec 20 08:00:00 IST 2017 | Thu Jan 25 16:00:00 IST 2018 |  | COMPLETED
2356 | TT_TASK | Turbine Table TT2 - Trim pile and prepare pile head | Sat Sep 30 08:00:00 IDT 2017 | Sat Oct 07 16:00:00 IDT 2017 | Sat Sep 30 08:00:00 IDT 2017 | Sat Oct 07 16:00:00 IDT 2017 |  | COMPLETED
2357 | TT_TASK | Turbine Table TT2 - Capping plate and rebar starter | Mon Oct 09 08:00:00 IDT 2017 | Fri Oct 13 16:00:00 IDT 2017 | Mon Oct 09 08:00:00 IDT 2017 | Fri Oct 13 16:00:00 IDT 2017 |  | COMPLETED
2358 | TT_TASK | Turbine Table TT2 Bottom Half - Erect side formwork (if any) | Fri Nov 03 08:00:00 IST 2017 | Sat Nov 04 16:00:00 IST 2017 | Fri Nov 03 08:00:00 IST 2017 | Sat Nov 04 16:00:00 IST 2017 |  | COMPLETED
2359 | TT_TASK | Turbine Table TT2 Bottom Half - Fix rebar | Mon Nov 06 08:00:00 IST 2017 | Wed Nov 08 16:00:00 IST 2017 | Mon Nov 06 08:00:00 IST 2017 | Wed Nov 08 16:00:00 IST 2017 |  | COMPLETED
2360 | TT_TASK | Turbine Table TT2 Bottom Half - Close formwork (if any) | Thu Nov 09 08:00:00 IST 2017 | Thu Nov 09 16:00:00 IST 2017 | Thu Nov 09 08:00:00 IST 2017 | Thu Nov 09 16:00:00 IST 2017 |  | COMPLETED
2361 | TT_TASK | Turbine Table TT2 Bottom Half - Pour concrete (mono pour) | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 |  | COMPLETED
2362 | TT_TASK | Turbine Table TT2 - Install cast-in / embed items | Fri Nov 10 08:00:00 IST 2017 | Mon Nov 13 16:00:00 IST 2017 | Fri Nov 10 08:00:00 IST 2017 | Mon Nov 13 16:00:00 IST 2017 |  | COMPLETED
2363 | TT_TASK | Turbine Table TT2 Upper Half - Fix rebar | Sat Nov 11 08:00:00 IST 2017 | Tue Nov 14 16:00:00 IST 2017 | Sat Nov 11 08:00:00 IST 2017 | Tue Nov 14 16:00:00 IST 2017 |  | COMPLETED
2364 | TT_TASK | Turbine Table TT2 Upper Half - Close formwork (if any) | Wed Nov 15 08:00:00 IST 2017 | Wed Nov 15 16:00:00 IST 2017 | Wed Nov 15 08:00:00 IST 2017 | Wed Nov 15 16:00:00 IST 2017 |  | COMPLETED
2365 | TT_TASK | Turbine Table TT2 Upper Half - Pour concrete (mono pour) | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 |  | COMPLETED
2366 | TT_TASK | Turbine Table TT2 - Construct Plinth PL3 with cast-in / embed items | Wed Feb 28 08:00:00 IST 2018 | Thu Mar 15 16:00:00 IST 2018 | Fri Dec 29 08:00:00 IST 2017 | Mon Jan 29 16:00:00 IST 2018 |  | COMPLETED
2367 | TT_TASK | Turbine Table TT3 - Trim pile and prepare pile head | Mon Oct 09 08:00:00 IDT 2017 | Fri Oct 13 16:00:00 IDT 2017 | Mon Oct 09 08:00:00 IDT 2017 | Fri Oct 13 16:00:00 IDT 2017 |  | COMPLETED
2368 | TT_TASK | Turbine Table TT3 - Capping plate and rebar starter | Sat Oct 14 08:00:00 IDT 2017 | Thu Oct 19 16:00:00 IDT 2017 | Sat Oct 14 08:00:00 IDT 2017 | Thu Oct 19 16:00:00 IDT 2017 |  | COMPLETED
2369 | TT_TASK | Turbine Table TT3 Bottom Half - Erect side formwork (if any) | Fri Nov 10 08:00:00 IST 2017 | Sat Nov 11 16:00:00 IST 2017 | Fri Nov 10 08:00:00 IST 2017 | Sat Nov 11 16:00:00 IST 2017 |  | COMPLETED
2370 | TT_TASK | Turbine Table TT3 Bottom Half - Fix rebar | Mon Nov 13 08:00:00 IST 2017 | Wed Nov 15 16:00:00 IST 2017 | Mon Nov 13 08:00:00 IST 2017 | Wed Nov 15 16:00:00 IST 2017 |  | COMPLETED
2371 | TT_TASK | Turbine Table TT3 Bottom Half - Close formwork (if any) | Thu Nov 16 08:00:00 IST 2017 | Thu Nov 16 16:00:00 IST 2017 | Thu Nov 16 08:00:00 IST 2017 | Thu Nov 16 16:00:00 IST 2017 |  | COMPLETED
2372 | TT_TASK | Turbine Table TT3 Bottom Half - Pour concrete (mono pour) | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 |  | COMPLETED
2373 | TT_TASK | Turbine Table TT3 - Install cast-in / embed items | Fri Nov 17 08:00:00 IST 2017 | Mon Nov 20 16:00:00 IST 2017 | Fri Nov 17 08:00:00 IST 2017 | Mon Nov 20 16:00:00 IST 2017 |  | COMPLETED
2374 | TT_TASK | Turbine Table TT3 Upper Half - Fix rebar | Sat Nov 18 08:00:00 IST 2017 | Tue Nov 21 16:00:00 IST 2017 | Sat Nov 18 08:00:00 IST 2017 | Tue Nov 21 16:00:00 IST 2017 |  | COMPLETED
2375 | TT_TASK | Turbine Table TT3 Upper Half - Close formwork (if any) | Wed Nov 22 08:00:00 IST 2017 | Wed Nov 22 16:00:00 IST 2017 | Wed Nov 22 08:00:00 IST 2017 | Wed Nov 22 16:00:00 IST 2017 |  | COMPLETED
2376 | TT_TASK | Turbine Table TT3 Upper Half - Pour concrete (mono pour) | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 |  | COMPLETED
2377 | TT_TASK | Turbine Table TT3 - Construct Plinth PL4, 5, 6, 7, 8, 8a with cast-in / embed items | Wed Feb 28 08:00:00 IST 2018 | Tue Mar 27 16:00:00 IDT 2018 | Fri Dec 29 08:00:00 IST 2017 | Fri Apr 20 16:00:00 IDT 2018 |  | COMPLETED
2378 | TT_TASK | Turbine Table TT4 - Trim pile and prepare pile head | Sat Oct 14 08:00:00 IDT 2017 | Thu Oct 19 16:00:00 IDT 2017 | Sat Oct 14 08:00:00 IDT 2017 | Thu Oct 19 16:00:00 IDT 2017 |  | COMPLETED
2379 | TT_TASK | Turbine Table TT4 - Capping plate and rebar starter | Fri Oct 20 08:00:00 IDT 2017 | Tue Oct 24 16:00:00 IDT 2017 | Fri Oct 20 08:00:00 IDT 2017 | Mon Oct 23 16:00:00 IDT 2017 |  | COMPLETED
2380 | TT_TASK | Turbine Table TT4 - Erect side formwork (if any) | Fri Nov 24 08:00:00 IST 2017 | Sat Nov 25 16:00:00 IST 2017 | Fri Nov 24 08:00:00 IST 2017 | Sat Nov 25 16:00:00 IST 2017 |  | COMPLETED
2381 | TT_TASK | Turbine Table TT4 - Fix rebar and cast-in / embed items | Wed Nov 29 08:00:00 IST 2017 | Fri Dec 01 16:00:00 IST 2017 | Wed Nov 29 08:00:00 IST 2017 | Fri Dec 01 16:00:00 IST 2017 |  | COMPLETED
2382 | TT_TASK | Turbine Table TT4 - Close formwork (if any) | Fri Dec 01 08:00:00 IST 2017 | Fri Dec 01 16:00:00 IST 2017 | Fri Dec 01 08:00:00 IST 2017 | Fri Dec 01 16:00:00 IST 2017 |  | COMPLETED
2383 | TT_TASK | Turbine Table TT4 - Pour concrete (mono pour) | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 |  | COMPLETED
2384 | TT_TASK | Turbine Table TT4 - Construct Plinth CEPL1, CEPL2 with cast-in / embed items | Fri Mar 16 08:00:00 IST 2018 | Tue Mar 27 16:00:00 IDT 2018 | Tue Jan 16 08:00:00 IST 2018 | Sat Jan 27 16:00:00 IST 2018 |  | COMPLETED
2385 | TT_TASK | Turbine Table TT5 - Trim pile and prepare pile head | Fri Oct 20 08:00:00 IDT 2017 | Tue Oct 24 16:00:00 IDT 2017 | Fri Oct 20 08:00:00 IDT 2017 | Tue Oct 24 16:00:00 IDT 2017 |  | COMPLETED
2386 | TT_TASK | Turbine Table TT5 - Capping plate and rebar starter | Thu Oct 26 08:00:00 IDT 2017 | Tue Oct 31 16:00:00 IST 2017 | Thu Oct 26 08:00:00 IDT 2017 | Tue Oct 31 16:00:00 IST 2017 |  | COMPLETED
2387 | TT_TASK | Turbine Table TT5 Bottom Half - Erect side formwork (if any) | Fri Nov 17 08:00:00 IST 2017 | Sat Nov 18 16:00:00 IST 2017 | Fri Nov 17 08:00:00 IST 2017 | Sat Nov 18 16:00:00 IST 2017 |  | COMPLETED
2388 | TT_TASK | Turbine Table TT5 Bottom Half - Fix rebar | Mon Nov 20 08:00:00 IST 2017 | Wed Nov 22 16:00:00 IST 2017 | Mon Nov 20 08:00:00 IST 2017 | Wed Nov 22 16:00:00 IST 2017 |  | COMPLETED
2389 | TT_TASK | Turbine Table TT5 Bottom Half - Close formwork (if any) | Thu Nov 23 08:00:00 IST 2017 | Thu Nov 23 16:00:00 IST 2017 | Thu Nov 23 08:00:00 IST 2017 | Thu Nov 23 16:00:00 IST 2017 |  | COMPLETED
2390 | TT_TASK | Turbine Table TT5 Bottom Half - Pour concrete (mono pour) | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 |  | COMPLETED
2391 | TT_TASK | Turbine Table TT5 - Install cast-in / embed items | Fri Nov 24 08:00:00 IST 2017 | Mon Nov 27 16:00:00 IST 2017 | Fri Nov 24 08:00:00 IST 2017 | Wed Nov 29 16:00:00 IST 2017 |  | COMPLETED
2392 | TT_TASK | Turbine Table TT5 Upper Half - Fix rebar | Sat Nov 25 08:00:00 IST 2017 | Tue Nov 28 16:00:00 IST 2017 | Sat Nov 25 08:00:00 IST 2017 | Thu Nov 30 16:00:00 IST 2017 |  | COMPLETED
2393 | TT_TASK | Turbine Table TT5 Upper Half - Close formwork (if any) | Wed Nov 29 08:00:00 IST 2017 | Wed Nov 29 16:00:00 IST 2017 | Wed Nov 29 08:00:00 IST 2017 | Wed Nov 29 16:00:00 IST 2017 |  | COMPLETED
2394 | TT_TASK | Turbine Table TT5 Upper Half - Pour concrete (mono pour) | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 | Sat Dec 02 08:00:00 IST 2017 | Sat Dec 02 16:00:00 IST 2017 |  | COMPLETED
2395 | TT_TASK | Turbine Table TT5 - Construct Plinth PL9, 10, 11, 12, 13 with cast-in / embed items | Wed Mar 28 08:00:00 IDT 2018 | Tue Apr 17 16:00:00 IDT 2018 | Fri Jan 19 08:00:00 IST 2018 | Sat Feb 10 16:00:00 IST 2018 |  | COMPLETED
2397 | TT_TASK | Ground Slab TH1 - Blinding to the profile of pile caps and ground beams | Fri Oct 06 08:00:00 IDT 2017 | Mon Oct 09 16:00:00 IDT 2017 | Fri Sep 08 08:00:00 IDT 2017 | Mon Dec 04 16:00:00 IST 2017 |  | COMPLETED
2398 | TT_TASK | Ground Slab TH1 - Trim pile and prepare pile head | Tue Oct 10 08:00:00 IDT 2017 | Sat Oct 14 16:00:00 IDT 2017 | Tue Sep 05 08:00:00 IDT 2017 | Fri Oct 06 16:00:00 IDT 2017 |  | COMPLETED
2399 | TT_TASK | Ground Slab TH1 - Capping plate and rebar starter | Mon Sep 25 08:00:00 IDT 2017 | Sat Oct 07 16:00:00 IDT 2017 | Thu Sep 14 08:00:00 IDT 2017 | Sat Oct 07 16:00:00 IDT 2017 |  | COMPLETED
2400 | TT_TASK | Ground Slab TH1 - Erect side formwork | Mon Oct 09 08:00:00 IDT 2017 | Tue Oct 10 16:00:00 IDT 2017 | Fri Sep 22 08:00:00 IDT 2017 | Tue Feb 13 16:00:00 IST 2018 |  | COMPLETED
2401 | TT_TASK | Ground Slab TH1 - Fix rebar for pile caps and ground beams and install cast-in / embed items | Thu Oct 12 08:00:00 IDT 2017 | Mon Oct 16 16:00:00 IDT 2017 | Wed Sep 20 08:00:00 IDT 2017 | Tue Feb 13 16:00:00 IST 2018 |  | COMPLETED
2402 | TT_TASK | Ground Slab TH1 - Pour caps and beams to the level of ground floor slab underside | Tue Oct 17 08:00:00 IDT 2017 | Tue Oct 17 16:00:00 IDT 2017 | Sat Sep 23 08:00:00 IDT 2017 | Wed Feb 14 16:00:00 IST 2018 |  | COMPLETED
2403 | TT_TASK | Ground Slab TH1 - Prepare CJ | Thu Mar 15 08:00:00 IST 2018 | Thu Mar 15 16:00:00 IST 2018 | Thu Feb 08 08:00:00 IST 2018 | Tue Feb 13 16:00:00 IST 2018 |  | COMPLETED
2404 | TT_TASK | Ground Slab TH1 - Fix ground floor slab rebar | Fri Mar 16 08:00:00 IST 2018 | Wed Mar 21 16:00:00 IST 2018 | Thu Feb 08 08:00:00 IST 2018 | Tue Feb 13 16:00:00 IST 2018 |  | COMPLETED
2405 | TT_TASK | Ground Slab TH1 - Pour ground slab | Thu Mar 22 08:00:00 IST 2018 | Thu Mar 22 16:00:00 IST 2018 | Wed Feb 14 08:00:00 IST 2018 | Wed Feb 14 16:00:00 IST 2018 |  | COMPLETED
2406 | TT_TASK | Ground Slab TH1 - Strike formwork (if any) | Fri Mar 23 08:00:00 IDT 2018 | Fri Mar 23 16:00:00 IDT 2018 | Tue Feb 20 08:00:00 IST 2018 | Wed Feb 21 16:00:00 IST 2018 |  | COMPLETED
2407 | TT_TASK | Ground Slab TH2 - Blinding to the profile of pile caps and ground beams | Mon Mar 19 08:00:00 IST 2018 | Wed Mar 21 16:00:00 IST 2018 | Thu Jan 18 08:00:00 IST 2018 | Sat Jan 20 16:00:00 IST 2018 |  | COMPLETED
2408 | TT_TASK | Ground Slab TH2 - Trim pile and prepare pile head | Tue Oct 10 08:00:00 IDT 2017 | Sat Oct 14 16:00:00 IDT 2017 | Tue Sep 05 08:00:00 IDT 2017 | Mon Jan 15 16:00:00 IST 2018 |  | COMPLETED
2409 | TT_TASK | Ground Slab TH2 - Capping plate and rebar starter | Wed Mar 14 08:00:00 IST 2018 | Sat Mar 17 16:00:00 IST 2018 | Sat Jan 13 08:00:00 IST 2018 | Wed Jan 17 16:00:00 IST 2018 |  | COMPLETED
2410 | TT_TASK | Ground Slab TH2 - Erect side formwork | Thu Mar 22 08:00:00 IST 2018 | Fri Mar 23 16:00:00 IDT 2018 | Fri Feb 02 08:00:00 IST 2018 | Sat Mar 03 16:00:00 IST 2018 |  | COMPLETED
2411 | TT_TASK | Ground Slab TH2 - Fix rebar for pile caps and ground beams install cast-in / embed items | Fri Mar 02 08:00:00 IST 2018 | Wed Mar 07 16:00:00 IST 2018 | Fri Feb 02 08:00:00 IST 2018 | Sat Mar 03 16:00:00 IST 2018 |  | COMPLETED
2412 | TT_TASK | Ground Slab TH2 - Pour caps and beams to the level of ground floor slab underside | Thu May 03 08:00:00 IDT 2018 | Thu May 03 16:00:00 IDT 2018 | Mon Mar 05 08:00:00 IST 2018 | Mon Mar 05 16:00:00 IST 2018 |  | COMPLETED
2413 | TT_TASK | Ground Slab TH2 - Prepare CJ | Tue Mar 06 08:00:00 IST 2018 | Wed Mar 07 16:00:00 IST 2018 | Sat Feb 24 08:00:00 IST 2018 | Sat Mar 03 16:00:00 IST 2018 |  | COMPLETED
2414 | TT_TASK | Ground Slab TH2 - Fix ground floor slab rebar | Mon Feb 26 08:00:00 IST 2018 | Thu Mar 08 16:00:00 IST 2018 | Sat Feb 24 08:00:00 IST 2018 | Sat Mar 03 16:00:00 IST 2018 |  | COMPLETED
2415 | TT_TASK | Ground Slab TH2 - Pour ground slab | Thu May 03 08:00:00 IDT 2018 | Thu May 03 16:00:00 IDT 2018 | Mon Mar 05 08:00:00 IST 2018 | Mon Mar 05 16:00:00 IST 2018 |  | COMPLETED
2416 | TT_TASK | Ground Slab TH2 - Strike formwork (if any) | Fri May 04 08:00:00 IDT 2018 | Fri May 04 16:00:00 IDT 2018 | Tue Mar 06 08:00:00 IST 2018 | Tue Mar 06 16:00:00 IST 2018 |  | COMPLETED
2417 | TT_TASK | Ground Slab TH3 - Blinding to the profile of pile caps and ground beams | Mon Oct 16 08:00:00 IDT 2017 | Thu Oct 19 16:00:00 IDT 2017 | Fri Sep 08 08:00:00 IDT 2017 | Mon Dec 04 16:00:00 IST 2017 |  | COMPLETED
2418 | TT_TASK | Ground Slab TH3 - Trim pile and prepare pile head | Fri Oct 20 08:00:00 IDT 2017 | Tue Oct 24 16:00:00 IDT 2017 | Tue Sep 05 08:00:00 IDT 2017 | Fri Oct 13 16:00:00 IDT 2017 |  | COMPLETED
2419 | TT_TASK | Ground Slab TH3 - Capping plate and rebar starter | Tue Oct 10 08:00:00 IDT 2017 | Sat Oct 14 16:00:00 IDT 2017 | Tue Oct 10 08:00:00 IDT 2017 | Sat Oct 14 16:00:00 IDT 2017 |  | COMPLETED
2420 | TT_TASK | Ground Slab TH3 - Erect side formwork | Wed Dec 27 08:00:00 IST 2017 | Sat Dec 30 16:00:00 IST 2017 | Tue Dec 05 08:00:00 IST 2017 | Tue Feb 13 16:00:00 IST 2018 |  | COMPLETED
2421 | TT_TASK | Ground Slab TH3 - Fix rebar for pile caps and ground beams install cast-in / embed items | Tue Jan 02 08:00:00 IST 2018 | Mon Jan 08 16:00:00 IST 2018 | Sat Dec 09 08:00:00 IST 2017 | Tue Feb 13 16:00:00 IST 2018 |  | COMPLETED
2422 | TT_TASK | Ground Slab TH3 - Pour caps and beams to the level of ground floor slab underside | Wed Mar 14 08:00:00 IST 2018 | Wed Mar 14 16:00:00 IST 2018 | Sat Jan 20 08:00:00 IST 2018 | Wed Feb 14 16:00:00 IST 2018 |  | COMPLETED
2423 | TT_TASK | Ground Slab TH3 - Prepare CJ | Thu Mar 15 08:00:00 IST 2018 | Thu Mar 15 16:00:00 IST 2018 | Thu Feb 08 08:00:00 IST 2018 | Tue Feb 13 16:00:00 IST 2018 |  | COMPLETED
2424 | TT_TASK | Ground Slab TH3 - Fix ground floor slab rebar | Fri Mar 16 08:00:00 IST 2018 | Wed Mar 21 16:00:00 IST 2018 | Thu Feb 08 08:00:00 IST 2018 | Tue Feb 13 16:00:00 IST 2018 |  | COMPLETED
2425 | TT_TASK | Ground Slab TH3 - Pour ground slab | Thu Mar 22 08:00:00 IST 2018 | Thu Mar 22 16:00:00 IST 2018 | Wed Feb 14 08:00:00 IST 2018 | Wed Feb 14 16:00:00 IST 2018 |  | COMPLETED
2426 | TT_TASK | Ground Slab TH3 - Strike formwork (if any) | Fri Mar 23 08:00:00 IDT 2018 | Fri Mar 23 16:00:00 IDT 2018 | Tue Feb 20 08:00:00 IST 2018 | Wed Feb 21 16:00:00 IST 2018 |  | COMPLETED
2427 | TT_TASK | Ground Slab TH4 - Backfill the interface area between Turbine Table to +4.2 mPD | Thu Dec 06 08:00:00 IST 2018 | Sat Dec 08 16:00:00 IST 2018 | Fri Sep 07 08:00:00 IDT 2018 | Sun Sep 09 16:00:00 IDT 2018 |  | COMPLETED
2428 | TT_TASK | Ground Slab TH4 - Blinding to the profile of pile caps and ground beams | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Fri Sep 07 08:00:00 IDT 2018 | Sun Sep 09 16:00:00 IDT 2018 |  | COMPLETED
2429 | TT_TASK | Ground Slab TH4 - Trim pile and prepare pile head | Wed Dec 27 08:00:00 IST 2017 | Sat Dec 30 16:00:00 IST 2017 | Mon Dec 18 08:00:00 IST 2017 | Thu Dec 21 16:00:00 IST 2017 |  | COMPLETED
2430 | TT_TASK | Ground Slab TH4 - Capping plate and rebar starter | Thu Dec 28 08:00:00 IST 2017 | Tue Jan 02 16:00:00 IST 2018 | Tue Dec 19 08:00:00 IST 2017 | Fri Dec 22 16:00:00 IST 2017 |  | COMPLETED
2431 | TT_TASK | Ground Slab TH4 - Erect side formwork | Mon Nov 26 08:00:00 IST 2018 | Tue Nov 27 16:00:00 IST 2018 | Mon Sep 10 08:00:00 IDT 2018 | Sat Sep 29 16:00:00 IDT 2018 |  | COMPLETED
2432 | TT_TASK | Ground Slab TH4 - Fix rebar for pile caps and ground beams install cast-in / embed items | Mon Nov 26 08:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 | Mon Sep 10 08:00:00 IDT 2018 | Sat Sep 29 16:00:00 IDT 2018 |  | COMPLETED
2433 | TT_TASK | Ground Slab TH4 - Pour caps and beams to the level of ground floor slab underside | Wed Dec 05 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 | Sun Sep 30 08:00:00 IDT 2018 | Sun Sep 30 16:00:00 IDT 2018 |  | COMPLETED
2434 | TT_TASK | Ground Slab TH4 - Prepare CJ | Fri Nov 30 08:00:00 IST 2018 | Fri Nov 30 16:00:00 IST 2018 | Sun Sep 30 08:00:00 IDT 2018 | Sun Sep 30 16:00:00 IDT 2018 |  | COMPLETED
2435 | TT_TASK | Ground Slab TH4 - Fix ground floor slab rebar | Sat Dec 01 08:00:00 IST 2018 | Tue Dec 04 16:00:00 IST 2018 | Mon Sep 10 08:00:00 IDT 2018 | Sat Sep 29 16:00:00 IDT 2018 |  | COMPLETED
2436 | TT_TASK | Ground Slab TH4 - Pour ground slab | Wed Dec 05 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 | Sun Sep 30 08:00:00 IDT 2018 | Sun Sep 30 16:00:00 IDT 2018 |  | COMPLETED
2437 | TT_TASK | Ground Slab TH5 - Blinding to the profile of pile caps and ground beams | Mon Oct 09 08:00:00 IDT 2017 | Thu Oct 12 16:00:00 IDT 2017 | Fri Sep 08 08:00:00 IDT 2017 | Tue Feb 06 16:00:00 IST 2018 |  | COMPLETED
2438 | TT_TASK | Ground Slab TH5 - Trim pile and prepare pile head | Fri Oct 13 08:00:00 IDT 2017 | Tue Oct 17 16:00:00 IDT 2017 | Tue Sep 05 08:00:00 IDT 2017 | Fri Oct 20 16:00:00 IDT 2017 |  | COMPLETED
2439 | TT_TASK | Ground Slab TH5 - Capping plate and rebar starter | Tue Oct 17 08:00:00 IDT 2017 | Sat Oct 21 16:00:00 IDT 2017 | Tue Oct 17 08:00:00 IDT 2017 | Sat Oct 21 16:00:00 IDT 2017 |  | COMPLETED
2440 | TT_TASK | Ground Slab TH5 - Erect side formwork | Tue Mar 06 08:00:00 IST 2018 | Fri Mar 09 16:00:00 IST 2018 | Wed Feb 07 08:00:00 IST 2018 | Tue Mar 06 16:00:00 IST 2018 |  | COMPLETED
2441 | TT_TASK | Ground Slab TH5 - Fix rebar for pile caps and ground beams install cast-in / embed items | Fri Mar 02 08:00:00 IST 2018 | Fri Mar 09 16:00:00 IST 2018 | Wed Feb 07 08:00:00 IST 2018 | Tue Mar 06 16:00:00 IST 2018 |  | COMPLETED
2442 | TT_TASK | Ground Slab TH5 - Pour caps and beams to the level of ground floor slab underside | Tue May 08 08:00:00 IDT 2018 | Tue May 08 16:00:00 IDT 2018 | Wed Mar 07 08:00:00 IST 2018 | Wed Mar 07 16:00:00 IST 2018 |  | COMPLETED
2443 | TT_TASK | Ground Slab TH5 - Prepare CJ | Mon Apr 23 08:00:00 IDT 2018 | Fri May 04 16:00:00 IDT 2018 | Mon Feb 26 08:00:00 IST 2018 | Tue Mar 06 16:00:00 IST 2018 |  | COMPLETED
2444 | TT_TASK | Ground Slab TH5 - Fix ground floor slab rebar | Tue Apr 24 08:00:00 IDT 2018 | Fri May 04 16:00:00 IDT 2018 | Tue Feb 27 08:00:00 IST 2018 | Tue Mar 06 16:00:00 IST 2018 |  | COMPLETED
2445 | TT_TASK | Ground Slab TH5 - Pour ground slab | Tue May 08 08:00:00 IDT 2018 | Tue May 08 16:00:00 IDT 2018 | Wed Mar 07 08:00:00 IST 2018 | Wed Mar 07 16:00:00 IST 2018 |  | COMPLETED
2446 | TT_TASK | Ground Slab TH5 - Strike formwork (if any) | Thu May 10 08:00:00 IDT 2018 | Thu May 10 16:00:00 IDT 2018 | Thu Mar 08 08:00:00 IST 2018 | Thu Mar 08 16:00:00 IST 2018 |  | COMPLETED
2447 | TT_TASK | Ground Slab TH6 - Backfill the interface area between Turbine Table to +4.2 mPD | Thu Dec 06 08:00:00 IST 2018 | Sat Dec 08 16:00:00 IST 2018 | Fri Sep 07 08:00:00 IDT 2018 | Sun Sep 09 16:00:00 IDT 2018 |  | COMPLETED
2448 | TT_TASK | Ground Slab TH6 - Blinding to the profile of pile caps and ground beams | Thu Nov 29 08:00:00 IST 2018 | Sat Dec 01 16:00:00 IST 2018 | Fri Sep 07 08:00:00 IDT 2018 | Sun Sep 09 16:00:00 IDT 2018 |  | COMPLETED
2449 | TT_TASK | Ground Slab TH6 - Trim pile and prepare pile head | Wed Dec 27 08:00:00 IST 2017 | Sat Dec 30 16:00:00 IST 2017 | Mon Dec 11 08:00:00 IST 2017 | Thu Dec 14 16:00:00 IST 2017 |  | COMPLETED
2450 | TT_TASK | Ground Slab TH6 - Capping plate and rebar starter | Thu Dec 28 08:00:00 IST 2017 | Tue Jan 02 16:00:00 IST 2018 | Tue Dec 12 08:00:00 IST 2017 | Fri Dec 15 16:00:00 IST 2017 |  | COMPLETED
2451 | TT_TASK | Ground Slab TH6 - Erect side formwork | Mon Nov 26 08:00:00 IST 2018 | Tue Nov 27 16:00:00 IST 2018 | Mon Sep 10 08:00:00 IDT 2018 | Sat Sep 29 16:00:00 IDT 2018 |  | COMPLETED
2452 | TT_TASK | Ground Slab TH6 - Fix rebar for pile caps and ground beams install cast-in / embed items | Mon Nov 26 08:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 | Mon Sep 10 08:00:00 IDT 2018 | Sat Sep 29 16:00:00 IDT 2018 |  | COMPLETED
2453 | TT_TASK | Ground Slab TH6 - Pour caps and beams to the level of ground floor slab underside | Wed Dec 05 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 | Sun Sep 30 08:00:00 IDT 2018 | Sun Sep 30 16:00:00 IDT 2018 |  | COMPLETED
2454 | TT_TASK | Ground Slab TH6 - Prepare CJ | Fri Nov 30 08:00:00 IST 2018 | Fri Nov 30 16:00:00 IST 2018 | Sun Sep 30 08:00:00 IDT 2018 | Sun Sep 30 16:00:00 IDT 2018 |  | COMPLETED
2455 | TT_TASK | Ground Slab TH6 - Fix ground floor slab rebar | Sat Dec 01 08:00:00 IST 2018 | Tue Dec 04 16:00:00 IST 2018 | Mon Sep 10 08:00:00 IDT 2018 | Sun Sep 30 16:00:00 IDT 2018 |  | COMPLETED
2456 | TT_TASK | Ground Slab TH6 - Pour ground slab | Wed Dec 05 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 | Sun Sep 30 08:00:00 IDT 2018 | Sun Sep 30 16:00:00 IDT 2018 |  | COMPLETED
2457 | TT_TASK | Ground Slab TH7 - Blinding to the profile of pile caps and ground beams | Fri Mar 02 08:00:00 IST 2018 | Mon Mar 05 16:00:00 IST 2018 | Thu Feb 22 08:00:00 IST 2018 | Sat Feb 24 16:00:00 IST 2018 |  | COMPLETED
2458 | TT_TASK | Ground Slab TH7 - Trim pile and prepare pile head | Sat Oct 21 08:00:00 IDT 2017 | Fri Oct 27 16:00:00 IDT 2017 | Sat Oct 21 08:00:00 IDT 2017 | Wed Jan 10 16:00:00 IST 2018 |  | COMPLETED
2459 | TT_TASK | Ground Slab TH7 - Capping plate and rebar starter | Tue Mar 06 08:00:00 IST 2018 | Fri Mar 09 16:00:00 IST 2018 | Mon Jan 08 08:00:00 IST 2018 | Wed Feb 21 16:00:00 IST 2018 |  | COMPLETED
2460 | TT_TASK | Ground Slab TH7 - Erect side formwork | Tue Mar 06 08:00:00 IST 2018 | Wed Mar 07 16:00:00 IST 2018 | Wed Feb 07 08:00:00 IST 2018 | Fri Apr 27 16:00:00 IDT 2018 |  | COMPLETED
2461 | TT_TASK | Ground Slab TH7 - Fix rebar for pile caps and ground beams install cast-in / embed items | Tue Mar 06 08:00:00 IST 2018 | Fri Mar 09 16:00:00 IST 2018 | Wed Feb 07 08:00:00 IST 2018 | Fri Apr 27 16:00:00 IDT 2018 |  | COMPLETED
2462 | TT_TASK | Ground Slab TH7 - Pour caps and beams to the level of ground floor slab underside | Tue May 29 08:00:00 IDT 2018 | Tue May 29 16:00:00 IDT 2018 | Thu Mar 29 08:00:00 IDT 2018 | Sat Apr 28 16:00:00 IDT 2018 |  | COMPLETED
2463 | TT_TASK | Ground Slab TH7 - Prepare CJ | Mon Apr 23 08:00:00 IDT 2018 | Mon Apr 30 16:00:00 IDT 2018 | Tue Apr 17 08:00:00 IDT 2018 | Fri Apr 27 16:00:00 IDT 2018 |  | COMPLETED
2464 | TT_TASK | Ground Slab TH7 - Fix ground floor slab rebar | Mon Apr 23 08:00:00 IDT 2018 | Mon Apr 30 16:00:00 IDT 2018 | Tue Apr 17 08:00:00 IDT 2018 | Fri Apr 27 16:00:00 IDT 2018 |  | COMPLETED
2465 | TT_TASK | Ground Slab TH7 - Pour ground slab | Tue May 29 08:00:00 IDT 2018 | Tue May 29 16:00:00 IDT 2018 | Sat Apr 28 08:00:00 IDT 2018 | Sat Apr 28 16:00:00 IDT 2018 |  | COMPLETED
2466 | TT_TASK | Ground Slab TH7 - Strike formwork (if any) | Thu May 31 08:00:00 IDT 2018 | Thu May 31 16:00:00 IDT 2018 | Mon Apr 30 08:00:00 IDT 2018 | Mon Apr 30 16:00:00 IDT 2018 |  | COMPLETED
2468 | TT_TASK | Ground Slab TH8 - Blinding to the profile of pile caps and ground beams | Tue Mar 20 08:00:00 IST 2018 | Thu Mar 22 16:00:00 IST 2018 | Fri Jan 19 08:00:00 IST 2018 | Mon Jan 22 16:00:00 IST 2018 |  | COMPLETED
2469 | TT_TASK | Ground Slab TH8 - Trim pile and prepare pile head | Wed Mar 14 08:00:00 IST 2018 | Sat Mar 17 16:00:00 IST 2018 | Sat Jan 13 08:00:00 IST 2018 | Wed Jan 17 16:00:00 IST 2018 |  | COMPLETED
2470 | TT_TASK | Ground Slab TH8 - Capping plate and rebar starter | Thu Mar 15 08:00:00 IST 2018 | Mon Mar 19 16:00:00 IST 2018 | Mon Jan 15 08:00:00 IST 2018 | Thu Jan 18 16:00:00 IST 2018 |  | COMPLETED
2471 | TT_TASK | Ground Slab TH8 - Erect side formwork | Mon Apr 23 08:00:00 IDT 2018 | Sat May 12 16:00:00 IDT 2018 | Mon Feb 26 08:00:00 IST 2018 | Fri Mar 23 16:00:00 IDT 2018 |  | COMPLETED
2472 | TT_TASK | Ground Slab TH8 - Fix rebar for pile caps and ground beams install cast-in / embed items | Mon Apr 23 08:00:00 IDT 2018 | Sat May 12 16:00:00 IDT 2018 | Mon Feb 26 08:00:00 IST 2018 | Fri Mar 23 16:00:00 IDT 2018 |  | COMPLETED
2473 | TT_TASK | Ground Slab TH8 - Pour caps and beams to the level of ground floor slab underside | Mon May 14 08:00:00 IDT 2018 | Mon May 14 16:00:00 IDT 2018 | Sat Mar 24 08:00:00 IDT 2018 | Sat Mar 24 16:00:00 IDT 2018 |  | COMPLETED
2474 | TT_TASK | Ground Slab TH8 - Prepare CJ | Mon May 07 08:00:00 IDT 2018 | Sat May 12 16:00:00 IDT 2018 | Wed Mar 14 08:00:00 IST 2018 | Fri Mar 23 16:00:00 IDT 2018 |  | COMPLETED
2475 | TT_TASK | Ground Slab TH8 - Fix ground floor slab rebar | Mon May 07 08:00:00 IDT 2018 | Sat May 12 16:00:00 IDT 2018 | Wed Mar 14 08:00:00 IST 2018 | Fri Mar 23 16:00:00 IDT 2018 |  | COMPLETED
2476 | TT_TASK | Ground Slab TH8 - Pour ground slab | Mon May 14 08:00:00 IDT 2018 | Mon May 14 16:00:00 IDT 2018 | Sat Mar 24 08:00:00 IDT 2018 | Sat Mar 24 16:00:00 IDT 2018 |  | COMPLETED
2477 | TT_TASK | Ground Slab TH8 - Strike formwork (if any) | Tue May 15 08:00:00 IDT 2018 | Tue May 15 16:00:00 IDT 2018 | Sun Mar 25 08:00:00 IDT 2018 | Sun Mar 25 16:00:00 IDT 2018 |  | COMPLETED
2479 | TT_TASK | Ground Slab TH9 - Blinding to the profile of pile caps and ground beams | Tue Mar 20 08:00:00 IST 2018 | Thu Mar 22 16:00:00 IST 2018 | Fri Jan 19 08:00:00 IST 2018 | Mon Jan 22 16:00:00 IST 2018 |  | COMPLETED
2480 | TT_TASK | Ground Slab TH9 - Trim pile and prepare pile head | Wed Mar 14 08:00:00 IST 2018 | Sat Mar 17 16:00:00 IST 2018 | Sat Jan 13 08:00:00 IST 2018 | Wed Jan 17 16:00:00 IST 2018 |  | COMPLETED
2481 | TT_TASK | Ground Slab TH9 - Capping plate and rebar starter | Thu Mar 15 08:00:00 IST 2018 | Mon Mar 19 16:00:00 IST 2018 | Mon Jan 15 08:00:00 IST 2018 | Thu Jan 18 16:00:00 IST 2018 |  | COMPLETED
2482 | TT_TASK | Ground Slab TH9 - Erect side formwork | Mon Apr 23 08:00:00 IDT 2018 | Sat May 12 16:00:00 IDT 2018 | Mon Feb 26 08:00:00 IST 2018 | Fri Mar 23 16:00:00 IDT 2018 |  | COMPLETED
2483 | TT_TASK | Ground Slab TH9 - Fix rebar for pile caps and ground beams install cast-in / embed items | Mon Apr 23 08:00:00 IDT 2018 | Sat May 12 16:00:00 IDT 2018 | Mon Feb 26 08:00:00 IST 2018 | Fri Mar 23 16:00:00 IDT 2018 |  | COMPLETED
2484 | TT_TASK | Ground Slab TH9 - Pour caps and beams to the level of ground floor slab underside | Mon May 14 08:00:00 IDT 2018 | Mon May 14 16:00:00 IDT 2018 | Sat Mar 24 08:00:00 IDT 2018 | Sat Mar 24 16:00:00 IDT 2018 |  | COMPLETED
2485 | TT_TASK | Ground Slab TH9 - Prepare CJ | Mon May 07 08:00:00 IDT 2018 | Sat May 12 16:00:00 IDT 2018 | Wed Mar 14 08:00:00 IST 2018 | Fri Mar 23 16:00:00 IDT 2018 |  | COMPLETED
2486 | TT_TASK | Ground Slab TH9 - Fix ground floor slab rebar | Mon May 07 08:00:00 IDT 2018 | Sat May 12 16:00:00 IDT 2018 | Wed Mar 14 08:00:00 IST 2018 | Fri Mar 23 16:00:00 IDT 2018 |  | COMPLETED
2487 | TT_TASK | Ground Slab TH9 - Pour ground slab | Mon May 14 08:00:00 IDT 2018 | Mon May 14 16:00:00 IDT 2018 | Sat Mar 24 08:00:00 IDT 2018 | Sat Mar 24 16:00:00 IDT 2018 |  | COMPLETED
2488 | TT_TASK | Ground Slab TH9 - Strike formwork (if any) | Mon Nov 26 08:00:00 IST 2018 | Mon Nov 26 16:00:00 IST 2018 | Sun Mar 25 08:00:00 IDT 2018 | Sun Mar 25 16:00:00 IDT 2018 |  | COMPLETED
2489 | TT_TASK | Ground Slab TH10 - Backfill the interface area between Cond.Polishing Pit | Thu Dec 06 08:00:00 IST 2018 | Sat Dec 08 16:00:00 IST 2018 | Fri Sep 07 08:00:00 IDT 2018 | Sun Sep 09 16:00:00 IDT 2018 |  | COMPLETED
2490 | TT_TASK | Ground Slab TH10 - Blinding to the profile of pile caps and ground beams | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Fri Sep 07 08:00:00 IDT 2018 | Sun Sep 09 16:00:00 IDT 2018 |  | COMPLETED
2491 | TT_TASK | Ground Slab TH10 - Trim pile and prepare pile head | Wed Dec 27 08:00:00 IST 2017 | Sat Dec 30 16:00:00 IST 2017 | Mon Dec 04 08:00:00 IST 2017 | Thu Dec 07 16:00:00 IST 2017 |  | COMPLETED
2492 | TT_TASK | Ground Slab TH10 - Capping plate and rebar starter | Thu Dec 28 08:00:00 IST 2017 | Tue Jan 02 16:00:00 IST 2018 | Tue Dec 05 08:00:00 IST 2017 | Fri Dec 08 16:00:00 IST 2017 |  | COMPLETED
2493 | TT_TASK | Ground Slab TH10 - Erect side formwork | Mon Nov 26 08:00:00 IST 2018 | Tue Nov 27 16:00:00 IST 2018 | Mon Sep 10 08:00:00 IDT 2018 | Sat Sep 29 16:00:00 IDT 2018 |  | COMPLETED
2494 | TT_TASK | Ground Slab TH10 - Fix rebar for pile caps and ground beams install cast-in / embed items | Mon Nov 26 08:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 | Mon Sep 10 08:00:00 IDT 2018 | Sat Sep 29 16:00:00 IDT 2018 |  | COMPLETED
2495 | TT_TASK | Ground Slab TH10 - Pour caps and beams to the level of ground floor slab underside | Wed Dec 05 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 | Sun Sep 30 08:00:00 IDT 2018 | Sun Sep 30 16:00:00 IDT 2018 |  | COMPLETED
2496 | TT_TASK | Ground Slab TH10 - Prepare CJ | Mon Nov 26 08:00:00 IST 2018 | Mon Nov 26 16:00:00 IST 2018 | Sun Sep 30 08:00:00 IDT 2018 | Sun Sep 30 16:00:00 IDT 2018 |  | COMPLETED
2497 | TT_TASK | Ground Slab TH10 - Fix ground floor slab rebar | Sat Dec 01 08:00:00 IST 2018 | Tue Dec 04 16:00:00 IST 2018 | Mon Sep 10 08:00:00 IDT 2018 | Sat Sep 29 16:00:00 IDT 2018 |  | COMPLETED
2498 | TT_TASK | Ground Slab TH10 - Pour ground slab | Wed Dec 05 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 | Sun Sep 30 08:00:00 IDT 2018 | Sun Sep 30 16:00:00 IDT 2018 |  | COMPLETED
2499 | TT_TASK | Ground Slab TH10 - Strike formwork (if any) | Tue Nov 27 08:00:00 IST 2018 | Tue Nov 27 16:00:00 IST 2018 | Tue Oct 02 08:00:00 IDT 2018 | Tue Oct 02 16:00:00 IDT 2018 |  | COMPLETED
2501 | TT_TASK | Condensate Pit - Further excavate from +4.1 mPD to the pit formation level | Mon Feb 26 08:00:00 IST 2018 | Tue Feb 27 16:00:00 IST 2018 | Mon Jan 15 08:00:00 IST 2018 | Sat Jan 27 16:00:00 IST 2018 |  | COMPLETED
2502 | TT_TASK | Condensate Pit - Sheet piling adjoining Turbine Table | Thu Sep 28 08:00:00 IDT 2017 | Tue Oct 24 16:00:00 IDT 2017 | Sat Sep 30 08:00:00 IDT 2017 | Sat Oct 21 16:00:00 IDT 2017 |  | COMPLETED
2503 | TT_TASK | Condensate Pit - Sheet piling for the sump pit | Wed Dec 27 08:00:00 IST 2017 | Mon Jan 08 16:00:00 IST 2018 | Thu Dec 21 08:00:00 IST 2017 | Sun Jan 14 16:00:00 IST 2018 |  | COMPLETED
2504 | TT_TASK | Condensate Pit - Excavation and construct the sump pit to the underside level of pit slab | Mon Nov 26 08:00:00 IST 2018 | Tue Dec 04 16:00:00 IST 2018 | Mon Oct 08 08:00:00 IDT 2018 | Fri Nov 09 16:00:00 IST 2018 |  | COMPLETED
2505 | TT_TASK | Condensate Pit - Trim sheet pile head (pump pit) | Wed Dec 05 08:00:00 IST 2018 | Thu Dec 06 16:00:00 IST 2018 | Mon Jun 25 08:00:00 IDT 2018 | Thu Jul 05 16:00:00 IDT 2018 |  | COMPLETED
2506 | TT_TASK | Condensate Pit - Complete the slab around the sump pit (previosuly left out) | Fri Dec 07 08:00:00 IST 2018 | Mon Dec 10 16:00:00 IST 2018 | Mon Nov 12 08:00:00 IST 2018 | Thu Nov 22 16:00:00 IST 2018 |  | COMPLETED
2507 | TT_TASK | Condensate Pit - Trim pile and prepare pile head | Wed Feb 28 08:00:00 IST 2018 | Thu Mar 01 16:00:00 IST 2018 | Mon Jan 29 08:00:00 IST 2018 | Sat Jun 16 16:00:00 IDT 2018 |  | COMPLETED
2508 | TT_TASK | Condensate Pit - Capping plate and rebar starter | Thu Mar 01 08:00:00 IST 2018 | Sat Mar 03 16:00:00 IST 2018 | Tue Jan 30 08:00:00 IST 2018 | Tue Jun 19 16:00:00 IDT 2018 |  | COMPLETED
2509 | TT_TASK | Condensate Pit - Vertical blinding to the profile of pile caps, ground beams and shallow pits | Sat May 12 08:00:00 IDT 2018 | Tue May 15 16:00:00 IDT 2018 | Tue Mar 13 08:00:00 IST 2018 | Sat Jul 14 16:00:00 IDT 2018 |  | COMPLETED
2510 | TT_TASK | Condensate Pit - Install waterproofing | Tue May 15 08:00:00 IDT 2018 | Tue May 15 16:00:00 IDT 2018 | Tue Mar 20 08:00:00 IST 2018 | Fri Jul 27 16:00:00 IDT 2018 |  | COMPLETED
2511 | TT_TASK | Condensate Pit - Fix rebar for pile caps, ground beams and shallow pits | Fri May 18 08:00:00 IDT 2018 | Mon May 21 16:00:00 IDT 2018 | Wed Mar 21 08:00:00 IST 2018 | Mon Aug 06 16:00:00 IDT 2018 |  | COMPLETED
2512 | TT_TASK | Condensate Pit - Close formwork | Thu May 24 08:00:00 IDT 2018 | Thu May 24 16:00:00 IDT 2018 | Mon Apr 16 08:00:00 IDT 2018 | Mon Aug 06 16:00:00 IDT 2018 |  | COMPLETED
2513 | TT_TASK | Condensate Pit - Pour caps, beams and shallow pits to the underside level of pit slab | Fri May 25 08:00:00 IDT 2018 | Fri May 25 16:00:00 IDT 2018 | Wed Apr 18 08:00:00 IDT 2018 | Tue Aug 07 16:00:00 IDT 2018 |  | COMPLETED
2514 | TT_TASK | Condensate Pit - Prepare CJ | Sat May 26 08:00:00 IDT 2018 | Sat May 26 16:00:00 IDT 2018 | Thu Apr 19 08:00:00 IDT 2018 | Fri Aug 10 16:00:00 IDT 2018 |  | COMPLETED
2515 | TT_TASK | Condensate Pit - Fix pit slab rebar | Mon May 28 08:00:00 IDT 2018 | Tue May 29 16:00:00 IDT 2018 | Wed Mar 21 08:00:00 IST 2018 | Mon Aug 06 16:00:00 IDT 2018 |  | COMPLETED
2516 | TT_TASK | Condensate Pit - Pour pit slab and kicker | Thu May 31 08:00:00 IDT 2018 | Thu May 31 16:00:00 IDT 2018 | Wed Apr 18 08:00:00 IDT 2018 | Tue Aug 07 16:00:00 IDT 2018 |  | COMPLETED
2517 | TT_TASK | Condensate Pit - Erect wall formwork | Fri Jun 01 08:00:00 IDT 2018 | Sat Jun 02 16:00:00 IDT 2018 | Thu Apr 19 08:00:00 IDT 2018 | Fri Aug 31 16:00:00 IDT 2018 |  | COMPLETED
2518 | TT_TASK | Condensate Pit - Fix wall and column rebar | Mon Jun 04 08:00:00 IDT 2018 | Thu Jun 07 16:00:00 IDT 2018 | Thu Apr 19 08:00:00 IDT 2018 | Fri Aug 31 16:00:00 IDT 2018 |  | COMPLETED
2519 | TT_TASK | Condensate Pit - Close wall formwork | Thu Jun 07 08:00:00 IDT 2018 | Thu Jun 07 16:00:00 IDT 2018 | Sun Apr 22 08:00:00 IDT 2018 | Sun Sep 02 00:00:00 IDT 2018 |  | COMPLETED
2520 | TT_TASK | Condensate Pit - Pour walls and columns to the underside of Turbine Hall ground slab | Tue Jul 31 08:00:00 IDT 2018 | Tue Jul 31 16:00:00 IDT 2018 | Fri May 04 08:00:00 IDT 2018 | Mon Sep 03 16:00:00 IDT 2018 |  | COMPLETED
2521 | TT_TASK | Condensate Pit - Curing | Sun Dec 02 08:00:00 IST 2018 | Tue Dec 04 16:00:00 IST 2018 | Tue Sep 04 08:00:00 IDT 2018 | Thu Sep 06 16:00:00 IDT 2018 |  | COMPLETED
2522 | TT_TASK | Condensate Pit - Apply waterproofing to the external face of pit wall | Mon Nov 26 08:00:00 IST 2018 | Tue Nov 27 16:00:00 IST 2018 | Fri Sep 07 08:00:00 IDT 2018 | Fri Sep 07 16:00:00 IDT 2018 |  | COMPLETED
2523 | TT_TASK | Condensate Pit - Backfill againt basement wall | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Fri Sep 07 08:00:00 IDT 2018 | Sun Sep 09 16:00:00 IDT 2018 |  | COMPLETED
2525 | TT_TASK | Cond.Polishing Pit - Further excavate from +4.1 mPD to the pit formation level | Mon Feb 26 08:00:00 IST 2018 | Fri Mar 02 16:00:00 IST 2018 | Mon Jan 15 08:00:00 IST 2018 | Sat Jan 27 16:00:00 IST 2018 |  | COMPLETED
2526 | TT_TASK | Cond.Polishing Pit - Trim pile and prepare pile head | Sat Mar 03 08:00:00 IST 2018 | Mon Mar 05 16:00:00 IST 2018 | Mon Jan 29 08:00:00 IST 2018 | Mon May 21 16:00:00 IDT 2018 |  | COMPLETED
2527 | TT_TASK | Cond.Polishing Pit - Capping plate and rebar starter | Mon Mar 05 08:00:00 IST 2018 | Wed Mar 07 16:00:00 IST 2018 | Tue Jan 30 08:00:00 IST 2018 | Tue May 22 16:00:00 IDT 2018 |  | COMPLETED
2528 | TT_TASK | Cond.Polishing Pit - Vertical blinding to the profile of pile caps, ground beams and shallow pits | Mon May 14 08:00:00 IDT 2018 | Thu May 17 16:00:00 IDT 2018 | Thu Apr 12 08:00:00 IDT 2018 | Thu May 31 16:00:00 IDT 2018 |  | COMPLETED
2529 | TT_TASK | Cond.Polishing Pit - Install waterproofing | Fri May 18 08:00:00 IDT 2018 | Fri May 18 16:00:00 IDT 2018 | Mon Apr 16 08:00:00 IDT 2018 | Thu Jul 26 16:00:00 IDT 2018 |  | COMPLETED
2530 | TT_TASK | Cond.Polishing Pit - Fix rebar for pile caps, ground beams and shallow pits | Fri Jun 01 08:00:00 IDT 2018 | Mon Jun 04 16:00:00 IDT 2018 | Thu May 03 08:00:00 IDT 2018 | Fri Jun 22 16:00:00 IDT 2018 |  | COMPLETED
2531 | TT_TASK | Cond.Polishing Pit - Close formwork | Mon Jun 04 08:00:00 IDT 2018 | Mon Jun 04 16:00:00 IDT 2018 | Wed May 23 08:00:00 IDT 2018 | Sat Jun 30 16:00:00 IDT 2018 |  | COMPLETED
2532 | TT_TASK | Cond.Polishing Pit - Pour caps, beams and shallow pits to the underside level of pit slab | Tue Jun 05 08:00:00 IDT 2018 | Tue Jun 05 16:00:00 IDT 2018 | Thu May 24 08:00:00 IDT 2018 | Sun Jul 01 16:00:00 IDT 2018 |  | COMPLETED
2533 | TT_TASK | Cond.Polishing Pit - Prepare CJ | Thu Jun 07 08:00:00 IDT 2018 | Thu Jun 07 16:00:00 IDT 2018 | Fri May 25 08:00:00 IDT 2018 | Wed Jul 04 16:00:00 IDT 2018 |  | COMPLETED
2534 | TT_TASK | Cond.Polishing Pit - Fix pit slab rebar | Thu Jul 05 08:00:00 IDT 2018 | Fri Jul 06 16:00:00 IDT 2018 | Tue May 22 08:00:00 IDT 2018 | Fri Jun 22 16:00:00 IDT 2018 |  | COMPLETED
2535 | TT_TASK | Cond.Polishing Pit - Pour pit slab | Sat Jun 30 08:00:00 IDT 2018 | Sat Jun 30 16:00:00 IDT 2018 | Thu May 24 08:00:00 IDT 2018 | Sun Jul 01 16:00:00 IDT 2018 |  | COMPLETED
2536 | TT_TASK | Cond.Polishing Pit - Erect wall formwork | Tue Jul 03 08:00:00 IDT 2018 | Sat Jul 07 16:00:00 IDT 2018 | Tue Jun 12 08:00:00 IDT 2018 | Wed Jul 18 16:00:00 IDT 2018 |  | COMPLETED
2537 | TT_TASK | Cond.Polishing Pit - Fix wall and column rebar | Tue Jun 26 08:00:00 IDT 2018 | Tue Jul 17 16:00:00 IDT 2018 | Sat Jun 09 08:00:00 IDT 2018 | Tue Jul 24 16:00:00 IDT 2018 |  | COMPLETED
2538 | TT_TASK | Cond.Polishing Pit - Close wall formwork | Sat Jun 30 08:00:00 IDT 2018 | Thu Jul 19 16:00:00 IDT 2018 | Tue Jun 12 08:00:00 IDT 2018 | Sat Aug 04 16:00:00 IDT 2018 |  | COMPLETED
2539 | TT_TASK | Cond.Polishing Pit - Pour walls and columns to the underside of Turbine Hall ground slab | Thu Jul 26 08:00:00 IDT 2018 | Fri Aug 10 16:00:00 IDT 2018 | Sun Jul 01 08:00:00 IDT 2018 | Tue Aug 07 16:00:00 IDT 2018 |  | COMPLETED
2540 | TT_TASK | Cond.Polishing Pit - Curing | Sun Sep 09 08:00:00 IDT 2018 | Tue Sep 11 16:00:00 IDT 2018 | Wed Aug 08 08:00:00 IDT 2018 | Fri Aug 10 16:00:00 IDT 2018 |  | COMPLETED
2541 | TT_TASK | Cond.Polishing Pit - Apply waterproofing to the external face of pit wall | Mon Sep 10 08:00:00 IDT 2018 | Tue Sep 11 16:00:00 IDT 2018 | Thu Aug 09 08:00:00 IDT 2018 | Fri Aug 10 16:00:00 IDT 2018 |  | COMPLETED
2542 | TT_TASK | Cond.Polishing Pit - Backfill againt basement wall | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Fri Sep 07 08:00:00 IDT 2018 | Sun Sep 09 16:00:00 IDT 2018 |  | COMPLETED
2550 | TT_TASK | Turbine Hall GL1~5 - Erect steel columns SC1(SC2) (w/ Overhead Crane support columns) at GL.1-5 /H | Mon Apr 23 08:00:00 IDT 2018 | Thu May 10 16:00:00 IDT 2018 | Thu Mar 29 08:00:00 IDT 2018 | Fri Apr 13 16:00:00 IDT 2018 |  | COMPLETED
2551 | TT_TASK | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.1 /G2-C | Sat Apr 28 08:00:00 IDT 2018 | Mon May 07 16:00:00 IDT 2018 | Sat Mar 31 08:00:00 IDT 2018 | Sat Apr 07 16:00:00 IDT 2018 |  | COMPLETED
2552 | TT_TASK | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /G | Tue May 08 08:00:00 IDT 2018 | Wed May 09 16:00:00 IDT 2018 | Mon Apr 09 08:00:00 IDT 2018 | Tue Apr 10 16:00:00 IDT 2018 |  | COMPLETED
2553 | TT_TASK | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /F | Tue May 08 08:00:00 IDT 2018 | Wed May 09 16:00:00 IDT 2018 | Mon Apr 09 08:00:00 IDT 2018 | Tue Apr 10 16:00:00 IDT 2018 |  | COMPLETED
2554 | TT_TASK | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /E | Sat May 26 08:00:00 IDT 2018 | Sat May 26 16:00:00 IDT 2018 | Thu May 03 08:00:00 IDT 2018 | Thu May 03 16:00:00 IDT 2018 |  | COMPLETED
2555 | TT_TASK | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /D | Mon May 28 08:00:00 IDT 2018 | Mon May 28 16:00:00 IDT 2018 | Sat May 05 08:00:00 IDT 2018 | Sat May 05 16:00:00 IDT 2018 |  | COMPLETED
2556 | TT_TASK | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /C | Tue May 29 08:00:00 IDT 2018 | Tue May 29 16:00:00 IDT 2018 | Mon May 07 08:00:00 IDT 2018 | Mon May 07 16:00:00 IDT 2018 |  | COMPLETED
2557 | TT_TASK | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.1 /B | Mon Jun 04 08:00:00 IDT 2018 | Mon Jun 04 16:00:00 IDT 2018 | Wed May 02 08:00:00 IDT 2018 | Wed May 02 16:00:00 IDT 2018 |  | COMPLETED
2558 | TT_TASK | Turbine Hall GL1~5 - Erect steel columns SC1(SC2)(w/ Overhead Crane support columns) at GL.1-4 /A | Tue Jun 05 08:00:00 IDT 2018 | Fri Jun 08 16:00:00 IDT 2018 | Thu May 03 08:00:00 IDT 2018 | Tue May 08 16:00:00 IDT 2018 |  | COMPLETED
2559 | TT_TASK | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /A | Sat Jun 09 08:00:00 IDT 2018 | Wed Jun 13 16:00:00 IDT 2018 | Wed May 09 08:00:00 IDT 2018 | Sat May 12 16:00:00 IDT 2018 |  | COMPLETED
2560 | TT_TASK | Turbine Hall GL.1-5 /H-G2/G1 (Bay 1a) - Connect erected columns by beams and bracing to +37.26 | Fri May 11 08:00:00 IDT 2018 | Mon May 14 16:00:00 IDT 2018 | Sat Apr 14 08:00:00 IDT 2018 | Tue Apr 17 16:00:00 IDT 2018 |  | COMPLETED
2561 | TT_TASK | Turbine Hall GL.1-5 /G2/G1-G (Bay 2a) - Connect erected columns by beams and bracing to +37.26 | Mon May 14 08:00:00 IDT 2018 | Wed May 16 16:00:00 IDT 2018 | Tue Apr 17 08:00:00 IDT 2018 | Thu Apr 19 16:00:00 IDT 2018 |  | COMPLETED
2562 | TT_TASK | Turbine Hall GL.1-5 /G-F (Bay 3a) - Connect erected columns by beams and bracing to +37.26 | Wed May 16 08:00:00 IDT 2018 | Fri May 18 16:00:00 IDT 2018 | Thu Apr 19 08:00:00 IDT 2018 | Sat Apr 21 16:00:00 IDT 2018 |  | COMPLETED
2563 | TT_TASK | Turbine Hall GL.1-5 /F-E (Bay 4a) - Connect erected columns by beams and bracing to +37.26 | Mon May 28 08:00:00 IDT 2018 | Wed May 30 16:00:00 IDT 2018 | Sat May 05 08:00:00 IDT 2018 | Tue May 08 16:00:00 IDT 2018 |  | COMPLETED
2564 | TT_TASK | Turbine Hall GL.1-5 /E-D (Bay 5a) - Connect erected columns by beams and bracing to +37.26 | Wed May 30 08:00:00 IDT 2018 | Sat Jun 02 16:00:00 IDT 2018 | Tue May 08 08:00:00 IDT 2018 | Thu May 10 16:00:00 IDT 2018 |  | COMPLETED
2565 | TT_TASK | Turbine Hall GL.1-5 /D-C (Bay 6a) - Connect erected columns by beams and bracing to +37.26 | Sat Jun 02 08:00:00 IDT 2018 | Tue Jun 05 16:00:00 IDT 2018 | Thu May 10 08:00:00 IDT 2018 | Sat May 12 16:00:00 IDT 2018 |  | COMPLETED
2566 | TT_TASK | Turbine Hall GL.1-5 /C-B (Bay 7a) - Connect erected columns by beams and bracing to +37.26 | Tue Jun 05 08:00:00 IDT 2018 | Thu Jun 07 16:00:00 IDT 2018 | Sat May 12 08:00:00 IDT 2018 | Tue May 15 16:00:00 IDT 2018 |  | COMPLETED
2567 | TT_TASK | Turbine Hall GL.1-5 /B-A (Bay 8a) - Connect erected columns by beams and bracing to +37.26 | Thu Jun 14 08:00:00 IDT 2018 | Sat Jun 16 16:00:00 IDT 2018 | Tue May 15 08:00:00 IDT 2018 | Thu May 17 16:00:00 IDT 2018 |  | COMPLETED
2568 | TT_TASK | Turbine Hall GL.1-5 - Install main beams to the steel columns at GL.1-5 /H, +37.26 | Tue May 15 08:00:00 IDT 2018 | Wed May 16 16:00:00 IDT 2018 | Wed Apr 18 08:00:00 IDT 2018 | Thu Apr 19 16:00:00 IDT 2018 |  | COMPLETED
2569 | TT_TASK | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /G2-G1, +37.26 | Thu May 17 08:00:00 IDT 2018 | Fri May 18 16:00:00 IDT 2018 | Thu Apr 12 08:00:00 IDT 2018 | Fri Apr 13 16:00:00 IDT 2018 |  | COMPLETED
2570 | TT_TASK | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /G, +37.26 | Sat May 19 08:00:00 IDT 2018 | Mon May 21 16:00:00 IDT 2018 | Tue Apr 17 08:00:00 IDT 2018 | Wed Apr 18 16:00:00 IDT 2018 |  | COMPLETED
2571 | TT_TASK | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /F, +37.26 | Sat May 26 08:00:00 IDT 2018 | Mon May 28 16:00:00 IDT 2018 | Mon Apr 23 08:00:00 IDT 2018 | Tue Apr 24 16:00:00 IDT 2018 |  | COMPLETED
2572 | TT_TASK | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /E, +37.26 | Mon Jun 04 08:00:00 IDT 2018 | Tue Jun 05 16:00:00 IDT 2018 | Fri May 11 08:00:00 IDT 2018 | Sat May 12 16:00:00 IDT 2018 |  | COMPLETED
2573 | TT_TASK | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /D, +37.26 | Wed Jun 06 08:00:00 IDT 2018 | Thu Jun 07 16:00:00 IDT 2018 | Mon May 14 08:00:00 IDT 2018 | Tue May 15 16:00:00 IDT 2018 |  | COMPLETED
2574 | TT_TASK | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /C, +37.26 | Fri Jun 08 08:00:00 IDT 2018 | Sat Jun 09 16:00:00 IDT 2018 | Wed May 16 08:00:00 IDT 2018 | Thu May 17 16:00:00 IDT 2018 |  | COMPLETED
2575 | TT_TASK | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /B, +37.26 | Sat Jun 16 08:00:00 IDT 2018 | Tue Jun 19 16:00:00 IDT 2018 | Thu May 17 08:00:00 IDT 2018 | Fri May 18 16:00:00 IDT 2018 |  | COMPLETED
2576 | TT_TASK | Turbine Hall GL.1-5 - Install main beams to the steel columns at GL.1-5 /A, +37.26 | Tue Jun 19 08:00:00 IDT 2018 | Wed Jun 20 16:00:00 IDT 2018 | Fri May 18 08:00:00 IDT 2018 | Sat May 19 16:00:00 IDT 2018 |  | COMPLETED
2577 | TT_TASK | Turbine Hall GL.1-5 /H-G2/G1 (Bay 1a) - Connect installed trusses by secondary beams and bracing | Sat May 26 08:00:00 IDT 2018 | Tue May 29 16:00:00 IDT 2018 | Mon Apr 23 08:00:00 IDT 2018 | Wed Apr 25 16:00:00 IDT 2018 |  | COMPLETED
2578 | TT_TASK | Turbine Hall GL.1-5 /G2/G1-G (Bay 2a) - Connect installed trusses by secondary beams and bracing | Sat May 26 08:00:00 IDT 2018 | Tue May 29 16:00:00 IDT 2018 | Mon Apr 23 08:00:00 IDT 2018 | Wed Apr 25 16:00:00 IDT 2018 |  | COMPLETED
2579 | TT_TASK | Turbine Hall GL.1-5 /G-F (Bay 3a) - Connect installed trusses by secondary beams and bracing | Tue May 29 08:00:00 IDT 2018 | Thu May 31 16:00:00 IDT 2018 | Wed Apr 25 08:00:00 IDT 2018 | Fri Apr 27 16:00:00 IDT 2018 |  | COMPLETED
2580 | TT_TASK | Turbine Hall GL.1-5 /F-E (Bay 4a) - Connect installed trusses by secondary beams and bracing | Wed Jun 06 08:00:00 IDT 2018 | Fri Jun 08 16:00:00 IDT 2018 | Mon May 14 08:00:00 IDT 2018 | Wed May 16 16:00:00 IDT 2018 |  | COMPLETED
2581 | TT_TASK | Turbine Hall GL.1-5 /E-D (Bay 5a) - Connect installed trusses by secondary beams and bracing | Fri Jun 08 08:00:00 IDT 2018 | Mon Jun 11 16:00:00 IDT 2018 | Wed May 16 08:00:00 IDT 2018 | Fri May 18 16:00:00 IDT 2018 |  | COMPLETED
2582 | TT_TASK | Turbine Hall GL.1-5 /D-C (Bay 6a) - Connect installed trusses by secondary beams and bracing | Mon Jun 11 08:00:00 IDT 2018 | Wed Jun 13 16:00:00 IDT 2018 | Fri May 18 08:00:00 IDT 2018 | Mon May 21 16:00:00 IDT 2018 |  | COMPLETED
2583 | TT_TASK | Turbine Hall GL.1-5 /C-B (Bay 7a) - Connect installed trusses by secondary beams and bracing [Deferred Works] | Thu Jan 02 08:00:00 IST 2020 | Thu Jan 02 08:00:00 IST 2020 | Sat May 19 08:00:00 IDT 2018 | Sat May 19 08:00:00 IDT 2018 |  | COMPLETED
2584 | TT_TASK | Turbine Hall GL.1-5 /B-A (Bay 8a) - Connect installed trusses by secondary beams and bracing | Thu Jun 21 08:00:00 IDT 2018 | Sat Jun 23 16:00:00 IDT 2018 | Mon May 21 08:00:00 IDT 2018 | Thu May 24 16:00:00 IDT 2018 |  | COMPLETED
2585 | TT_TASK | Turbine Hall GL.2-4 /G2/G1-G (Bay 2a) - Install upper roof steel structure | Wed May 30 08:00:00 IDT 2018 | Thu May 31 16:00:00 IDT 2018 | Thu Apr 26 08:00:00 IDT 2018 | Fri Apr 27 16:00:00 IDT 2018 |  | COMPLETED
2586 | TT_TASK | Turbine Hall GL.2-4 /G-F (Bay 3a) - Install upper roof steel structure | Sat Jun 02 08:00:00 IDT 2018 | Mon Jun 04 16:00:00 IDT 2018 | Sat Apr 28 08:00:00 IDT 2018 | Mon Apr 30 16:00:00 IDT 2018 |  | COMPLETED
2587 | TT_TASK | Turbine Hall GL.2-4 /F-E (Bay 4a) - Install upper roof steel structure | Tue Jun 05 08:00:00 IDT 2018 | Wed Jun 06 16:00:00 IDT 2018 | Wed May 02 08:00:00 IDT 2018 | Thu May 03 16:00:00 IDT 2018 |  | COMPLETED
2588 | TT_TASK | Turbine Hall GL.2-4 /E-D (Bay 5a) - Install upper roof steel structure | Tue Jun 12 08:00:00 IDT 2018 | Wed Jun 13 16:00:00 IDT 2018 | Sat May 19 08:00:00 IDT 2018 | Mon May 21 16:00:00 IDT 2018 |  | COMPLETED
2589 | TT_TASK | Turbine Hall GL.2-4 /D-C (Bay 6a) - Install upper roof steel structure | Thu Jun 14 08:00:00 IDT 2018 | Fri Jun 15 16:00:00 IDT 2018 | Wed May 23 08:00:00 IDT 2018 | Thu May 24 16:00:00 IDT 2018 |  | COMPLETED
2590 | TT_TASK | Turbine Hall GL.2-4 /C-B (Bay 7a) - Install upper roof steel structure [Deferred Works] | Thu Jan 02 08:00:00 IST 2020 | Thu Jan 02 08:00:00 IST 2020 | Sat May 19 08:00:00 IDT 2018 | Sat May 19 08:00:00 IDT 2018 |  | COMPLETED
2594 | TT_TASK | Turbine Hall GL5-7 - Erect steel columns SC3(SC2) at GL.6-7 /H | Tue Jun 26 08:00:00 IDT 2018 | Wed Jun 27 16:00:00 IDT 2018 | Mon Jun 11 08:00:00 IDT 2018 | Sat Jun 16 16:00:00 IDT 2018 |  | COMPLETED
2595 | TT_TASK | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /G2-G1 | Thu Jun 28 08:00:00 IDT 2018 | Sat Jun 30 16:00:00 IDT 2018 | Thu Jun 14 08:00:00 IDT 2018 | Wed Jun 20 08:00:00 IDT 2018 |  | COMPLETED
2596 | TT_TASK | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /F1 | Mon Nov 26 08:00:00 IST 2018 | Mon Nov 26 16:00:00 IST 2018 | Wed Sep 26 08:00:00 IDT 2018 | Wed Sep 26 16:00:00 IDT 2018 |  | COMPLETED
2597 | TT_TASK | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /F | Mon Nov 26 08:00:00 IST 2018 | Mon Nov 26 16:00:00 IST 2018 | Thu Sep 27 08:00:00 IDT 2018 | Thu Sep 27 16:00:00 IDT 2018 |  | COMPLETED
2598 | TT_TASK | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /E | Tue Nov 27 08:00:00 IST 2018 | Tue Nov 27 16:00:00 IST 2018 | Fri Sep 28 08:00:00 IDT 2018 | Fri Sep 28 16:00:00 IDT 2018 |  | COMPLETED
2599 | TT_TASK | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /D | Wed Nov 28 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Sat Sep 29 08:00:00 IDT 2018 | Sat Sep 29 16:00:00 IDT 2018 |  | COMPLETED
2600 | TT_TASK | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /C | Thu Nov 29 08:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 | Tue Oct 02 08:00:00 IDT 2018 | Tue Oct 02 16:00:00 IDT 2018 |  | COMPLETED
2601 | TT_TASK | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /B | Fri Nov 30 08:00:00 IST 2018 | Fri Nov 30 16:00:00 IST 2018 | Wed Oct 03 08:00:00 IDT 2018 | Wed Oct 03 16:00:00 IDT 2018 |  | COMPLETED
2602 | TT_TASK | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /A | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Thu Oct 04 08:00:00 IDT 2018 | Sat Oct 06 16:00:00 IDT 2018 |  | COMPLETED
2603 | TT_TASK | Turbine Hall GL5-7 /H-G1 (Bay 1b) - Connect erected columns by beams and bracing to +32.26 | Tue Jun 26 08:00:00 IDT 2018 | Thu Jun 28 16:00:00 IDT 2018 | Thu Jun 21 08:00:00 IDT 2018 | Sat Jun 23 16:00:00 IDT 2018 |  | COMPLETED
2604 | TT_TASK | Turbine Hall GL5-7 /G1 -F (Bay 2b) - Connect erected columns by beams and bracing to +32.26 | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Fri Sep 28 08:00:00 IDT 2018 | Tue Oct 02 16:00:00 IDT 2018 |  | COMPLETED
2605 | TT_TASK | Turbine Hall GL5-7 /F-E (Bay 3b) - Connect erected columns by beams and bracing to +32.26 | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Wed Oct 03 08:00:00 IDT 2018 | Fri Oct 05 00:00:00 IDT 2018 |  | COMPLETED
2606 | TT_TASK | Turbine Hall GL5-7 /E-D (Bay 4b) - Connect erected columns by beams and bracing to +32.26 | Thu Nov 29 08:00:00 IST 2018 | Sat Dec 01 16:00:00 IST 2018 | Sat Oct 06 08:00:00 IDT 2018 | Tue Oct 09 16:00:00 IDT 2018 |  | COMPLETED
2607 | TT_TASK | Turbine Hall GL5-7 /D-C (Bay 5b) - Connect erected columns by beams and bracing to +32.26 | Mon Dec 03 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 | Wed Oct 10 08:00:00 IDT 2018 | Fri Oct 12 16:00:00 IDT 2018 |  | COMPLETED
2608 | TT_TASK | Turbine Hall GL5-7 /C-B (Bay 6b) - Connect erected columns by beams and bracing to +32.26 | Thu Dec 06 08:00:00 IST 2018 | Sat Dec 08 16:00:00 IST 2018 | Sat Oct 13 08:00:00 IDT 2018 | Tue Oct 16 16:00:00 IDT 2018 |  | COMPLETED
2609 | TT_TASK | Turbine Hall GL5-7 /B-A (Bay 7b) - Connect erected columns by beams and bracing to +32.26 | Mon Dec 10 08:00:00 IST 2018 | Wed Dec 12 16:00:00 IST 2018 | Wed Oct 17 00:00:00 IDT 2018 | Tue Oct 23 16:00:00 IDT 2018 |  | COMPLETED
2610 | TT_TASK | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /H, +32.26 | Tue Jul 03 08:00:00 IDT 2018 | Tue Jul 03 16:00:00 IDT 2018 | Mon Jun 25 08:00:00 IDT 2018 | Mon Jun 25 16:00:00 IDT 2018 |  | COMPLETED
2611 | TT_TASK | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /G1, +32.26 | Mon Nov 26 08:00:00 IST 2018 | Mon Nov 26 16:00:00 IST 2018 | Wed Oct 03 08:00:00 IDT 2018 | Wed Oct 03 16:00:00 IDT 2018 |  | COMPLETED
2612 | TT_TASK | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /F, +32.26 | Thu Nov 29 08:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 | Sat Oct 06 08:00:00 IDT 2018 | Sat Oct 06 16:00:00 IDT 2018 |  | COMPLETED
2613 | TT_TASK | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /E, +32.26 | Mon Dec 03 08:00:00 IST 2018 | Mon Dec 03 16:00:00 IST 2018 | Wed Oct 10 08:00:00 IDT 2018 | Wed Oct 10 16:00:00 IDT 2018 |  | COMPLETED
2614 | TT_TASK | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /D, +32.26 | Thu Dec 06 08:00:00 IST 2018 | Thu Dec 06 16:00:00 IST 2018 | Sat Oct 13 08:00:00 IDT 2018 | Sat Oct 13 16:00:00 IDT 2018 |  | COMPLETED
2615 | TT_TASK | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /C, +32.26 | Mon Dec 10 08:00:00 IST 2018 | Mon Dec 10 16:00:00 IST 2018 | Wed Oct 17 00:00:00 IDT 2018 | Wed Oct 17 00:00:00 IDT 2018 |  | COMPLETED
2616 | TT_TASK | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /B, +32.26 | Thu Dec 13 08:00:00 IST 2018 | Thu Dec 13 16:00:00 IST 2018 | Wed Oct 24 08:00:00 IDT 2018 | Wed Oct 24 16:00:00 IDT 2018 |  | COMPLETED
2617 | TT_TASK | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /A, +32.26 | Thu Dec 13 08:00:00 IST 2018 | Thu Dec 13 16:00:00 IST 2018 | Thu Oct 25 08:00:00 IDT 2018 | Thu Oct 25 16:00:00 IDT 2018 |  | COMPLETED
2618 | TT_TASK | Turbine Hall GL5-7 /H-G1 (Bay 1b) - Connect installed trusses by secondary beams and bracing (Event 046 - ROI #199) | Mon Nov 26 08:00:00 IST 2018 | Mon Nov 26 08:00:00 IST 2018 | Tue Oct 30 08:00:00 IST 2018 | Sat Nov 03 16:00:00 IST 2018 |  | COMPLETED
2619 | TT_TASK | Turbine Hall GL5-7 /G1 -F (Bay 2b) - Connect installed trusses by secondary beams and bracing | Mon Nov 26 08:00:00 IST 2018 | Tue Nov 27 16:00:00 IST 2018 | Mon Oct 08 08:00:00 IDT 2018 | Tue Oct 09 16:00:00 IDT 2018 |  | COMPLETED
2620 | TT_TASK | Turbine Hall GL5-7 /F-E (Bay 3b) - Connect installed trusses by secondary beams and bracing | Wed Nov 28 08:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 | Thu Oct 11 08:00:00 IDT 2018 | Fri Oct 12 16:00:00 IDT 2018 |  | COMPLETED
2621 | TT_TASK | Turbine Hall GL5-7 /E-D (Bay 4b) - Connect installed trusses by secondary beams and bracing | Fri Nov 30 08:00:00 IST 2018 | Sat Dec 01 16:00:00 IST 2018 | Mon Oct 15 08:00:00 IDT 2018 | Tue Oct 16 16:00:00 IDT 2018 |  | COMPLETED
2622 | TT_TASK | Turbine Hall GL5-7 /D-C (Bay 5b) - Connect installed trusses by secondary beams and bracing | Mon Dec 03 08:00:00 IST 2018 | Tue Dec 04 16:00:00 IST 2018 | Thu Oct 18 08:00:00 IDT 2018 | Fri Oct 19 16:00:00 IDT 2018 |  | COMPLETED
2623 | TT_TASK | Turbine Hall GL5-7 /C-B (Bay 6b) - Connect installed trusses by 2ndary beams & bracing [DEF_WK07 not required] | Mon Nov 26 08:00:00 IST 2018 | Tue Nov 27 16:00:00 IST 2018 | Thu Oct 25 08:00:00 IDT 2018 | Fri Oct 26 16:00:00 IDT 2018 |  | COMPLETED
2624 | TT_TASK | Turbine Hall GL5-7 /B-A (Bay 7b) - Connect installed trusses by secondary beams and bracing | Fri Dec 14 08:00:00 IST 2018 | Sat Dec 15 16:00:00 IST 2018 | Sat Oct 27 08:00:00 IDT 2018 | Mon Oct 29 16:00:00 IST 2018 |  | COMPLETED
2627 | TT_TASK | Turbine Hall GL.7-10 (Bay 1c) - Erect steel columns and bracing SC4 at GL.7-10 /K1-G1 | Thu Jun 28 08:00:00 IDT 2018 | Sat Jun 30 16:00:00 IDT 2018 | Thu Jun 21 08:00:00 IDT 2018 | Tue Jul 10 16:00:00 IDT 2018 |  | COMPLETED
2628 | TT_TASK | Turbine Hall GL.7-10 (Bay 2c) - Erect steel columns and bracing SC4 at GL.7-10 /G1-F | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Fri Sep 28 08:00:00 IDT 2018 | Tue Oct 02 16:00:00 IDT 2018 |  | COMPLETED
2629 | TT_TASK | Turbine Hall GL.7-10 (Bay 3c) - Erect steel columns and bracing SC4 at GL.7-10 /F-C | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Tue Oct 30 08:00:00 IST 2018 | Thu Nov 01 16:00:00 IST 2018 |  | COMPLETED
2630 | TT_TASK | Turbine Hall GL.7-10 (Bay 4c) - Erect steel columns and bracing SC4 at GL.7-10 /C-A | Thu Nov 29 08:00:00 IST 2018 | Sat Dec 01 16:00:00 IST 2018 | Tue Nov 06 08:00:00 IST 2018 | Thu Nov 08 16:00:00 IST 2018 |  | COMPLETED
2631 | TT_TASK | Turbine Hall GL.7-10 (Bay 1c) - Install steel main and secondary beams at level +10.8 | Tue Jul 03 08:00:00 IDT 2018 | Thu Jul 05 16:00:00 IDT 2018 | Mon Jun 25 08:00:00 IDT 2018 | Thu Jul 12 16:00:00 IDT 2018 |  | COMPLETED
2632 | TT_TASK | Turbine Hall GL.7-10 (Bay 2c) - Install steel main and secondary beams at to level +10.8 | Thu Dec 06 08:00:00 IST 2018 | Sat Dec 08 16:00:00 IST 2018 | Wed Oct 03 08:00:00 IDT 2018 | Fri Oct 05 16:00:00 IDT 2018 |  | COMPLETED
2633 | TT_TASK | Turbine Hall GL.7-10 (Bay 3c) - Install steel main and secondary beams at to level +10.8 | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Fri Nov 02 08:00:00 IST 2018 | Mon Nov 05 16:00:00 IST 2018 |  | COMPLETED
2634 | TT_TASK | Turbine Hall GL.7-10 (Bay 1c) - Construct floor slab at level +10.8 | Mon Aug 27 08:00:00 IDT 2018 | Wed Aug 29 16:00:00 IDT 2018 | Mon Jul 23 08:00:00 IDT 2018 | Thu Sep 06 16:00:00 IDT 2018 |  | COMPLETED
2635 | TT_TASK | Turbine Hall GL.7-10 (Bay 2c) - Construct floor slab at to level +10.8 | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Fri Nov 02 08:00:00 IST 2018 | Sun Nov 18 16:00:00 IST 2018 |  | COMPLETED
2636 | TT_TASK | Turbine Hall GL.7-10 (Bay 3c) - Construct floor slab at level +10.8 | Sat Jan 26 08:00:00 IST 2019 | Wed Feb 13 16:00:00 IST 2019 | Wed Nov 28 08:00:00 IST 2018 | Fri Dec 14 16:00:00 IST 2018 |  | COMPLETED
2638 | TT_TASK | Turbine Hall GL.7-10 (Bay 1c) - Install steel beams and bracing at level +14.85 | Thu Jul 26 08:00:00 IDT 2018 | Wed Aug 08 16:00:00 IDT 2018 | Fri Jun 29 08:00:00 IDT 2018 | Sat Jul 14 16:00:00 IDT 2018 |  | COMPLETED
2639 | TT_TASK | Turbine Hall GL.7-10 (Bay 2c) - Install steel beams and bracing at level +14.85 | Thu Dec 13 08:00:00 IST 2018 | Mon Dec 17 16:00:00 IST 2018 | Sat Oct 06 08:00:00 IDT 2018 | Wed Oct 10 16:00:00 IDT 2018 |  | COMPLETED
2640 | TT_TASK | Turbine Hall GL.7-10 (Bay 3c) - Install steel beams and bracing at level +14.85 | Mon Nov 26 08:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 | Fri Nov 09 08:00:00 IST 2018 | Tue Nov 13 16:00:00 IST 2018 |  | COMPLETED
2641 | TT_TASK | Turbine Hall GL.7-10 (Bay 4c) - Install steel beams and bracing at level +14.85 | Fri Nov 30 08:00:00 IST 2018 | Tue Dec 04 16:00:00 IST 2018 | Wed Nov 14 08:00:00 IST 2018 | Mon Nov 19 16:00:00 IST 2018 |  | COMPLETED
2642 | TT_TASK | Turbine Hall GL.7-10 (Bay 1c) - Construct roof slab at level +14.85 | Mon Nov 26 08:00:00 IST 2018 | Tue Dec 18 16:00:00 IST 2018 | Thu Sep 27 08:00:00 IDT 2018 | Tue Oct 23 16:00:00 IDT 2018 |  | COMPLETED
2643 | TT_TASK | Turbine Hall GL.7-10 (Bay 2c) - Construct roof slab at level +14.85 | Sat Jan 26 08:00:00 IST 2019 | Wed Feb 13 16:00:00 IST 2019 | Sat Nov 24 08:00:00 IST 2018 | Fri Dec 14 16:00:00 IST 2018 |  | COMPLETED
2644 | TT_TASK | Turbine Hall GL.7-10 (Bay 3c) - Construct roof slab at level +14.85 | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 15 16:00:00 IST 2019 | Sun Dec 16 08:00:00 IST 2018 | Sat Dec 29 16:00:00 IST 2018 |  | COMPLETED
2649 | TT_TASK | DW01 - Construct Roof of Turbine Hall (GL.B~C /1-5) after installation of main OH crane | Thu Jul 26 08:00:00 IDT 2018 | Fri Aug 31 16:00:00 IDT 2018 | Mon Jul 23 08:00:00 IDT 2018 | Sun Aug 05 16:00:00 IDT 2018 |  | COMPLETED
2651 | TT_TASK | Turbine Hall GL.1-5 /H-G2/G1 (Bay 1a) - Kalbau | Tue Jun 26 08:00:00 IDT 2018 | Thu Jun 28 16:00:00 IDT 2018 | Thu Jun 07 08:00:00 IDT 2018 | Tue Jun 26 16:00:00 IDT 2018 |  | COMPLETED
2652 | TT_TASK | Turbine Hall GL.1-5 /G2/G1-G (Bay 2a) - Kalbau | Fri Jun 29 08:00:00 IDT 2018 | Tue Jul 03 16:00:00 IDT 2018 | Wed Jun 20 08:00:00 IDT 2018 | Fri Jun 29 16:00:00 IDT 2018 |  | COMPLETED
2653 | TT_TASK | Turbine Hall GL.1-5 /G-F (Bay 3a) - Kalbau | Tue Jul 31 08:00:00 IDT 2018 | Thu Aug 02 16:00:00 IDT 2018 | Fri Jun 29 08:00:00 IDT 2018 | Tue Jul 03 16:00:00 IDT 2018 |  | COMPLETED
2654 | TT_TASK | Turbine Hall GL.1-5 /F-E (Bay 4a) - Kalbau | Sat Aug 04 08:00:00 IDT 2018 | Tue Aug 07 16:00:00 IDT 2018 | Tue Jul 03 08:00:00 IDT 2018 | Sat Jul 07 16:00:00 IDT 2018 |  | COMPLETED
2655 | TT_TASK | Turbine Hall GL.1-5 /E-D (Bay 5a) - Kalbau | Wed Aug 08 08:00:00 IDT 2018 | Fri Aug 10 16:00:00 IDT 2018 | Sat Jul 07 08:00:00 IDT 2018 | Mon Jul 09 16:00:00 IDT 2018 |  | COMPLETED
2656 | TT_TASK | Turbine Hall GL.1-5 /D-C (Bay 6a) - Kalbau | Sat Aug 11 08:00:00 IDT 2018 | Tue Aug 14 16:00:00 IDT 2018 | Mon Jul 09 08:00:00 IDT 2018 | Tue Jul 10 16:00:00 IDT 2018 |  | COMPLETED
2657 | TT_TASK | Turbine Hall GL.1-5 /C-B (Bay 7a) - Install standing seam roof cladding [Deferred Works] | Thu Jan 02 08:00:00 IST 2020 | Thu Jan 02 08:00:00 IST 2020 | Sat May 19 08:00:00 IDT 2018 | Sat May 19 08:00:00 IDT 2018 |  | COMPLETED
2658 | TT_TASK | Turbine Hall GL.1-5 /B-A (Bay 8a) - Kalbau | Thu Jul 19 08:00:00 IDT 2018 | Sat Jul 21 16:00:00 IDT 2018 | Wed Jun 13 08:00:00 IDT 2018 | Thu Jul 12 16:00:00 IDT 2018 |  | COMPLETED
2661 | TT_TASK | Turbine Hall GL.1-5 - Vapour barrier & ST clips | Mon Nov 26 08:00:00 IST 2018 | Fri Dec 28 16:00:00 IST 2018 | Sat Oct 27 08:00:00 IDT 2018 | Wed Nov 14 16:00:00 IST 2018 |  | COMPLETED
2662 | TT_TASK | Turbine Hall GL.1-5 - Insulation & Kalzip | Mon Nov 26 08:00:00 IST 2018 | Wed Dec 12 16:00:00 IST 2018 | Fri Nov 23 08:00:00 IST 2018 | Sat Dec 29 16:00:00 IST 2018 |  | COMPLETED
2663 | TT_TASK | Turbine Hall GL.1-5 - Remaining works related to dog houses | Thu May 02 08:00:00 IDT 2019 | Wed May 22 16:00:00 IDT 2019 | Mon Feb 11 08:00:00 IST 2019 | Fri Jun 14 16:00:00 IDT 2019 |  | COMPLETED
2666 | TT_TASK | DW08 - Construct Roof of Turbine Hall(GL.F~G1 /5-7) after equip.installation on platfrom at +12.15 | Sat Jun 01 08:00:00 IDT 2019 | Sat Jun 29 16:00:00 IDT 2019 | Sat May 04 08:00:00 IDT 2019 | Mon Sep 09 16:00:00 IDT 2019 |  | COMPLETED
2667 | TT_TASK | Turbine Hall GL5-7 - Cleats, purlins, bridging, bracing, etc | Tue Jul 03 08:00:00 IDT 2018 | Thu Aug 23 16:00:00 IDT 2018 | Mon Jun 25 08:00:00 IDT 2018 | Sun Dec 09 16:00:00 IST 2018 |  | COMPLETED
2668 | TT_TASK | Turbine Hall GL5-7 /H-G1 (Bay 1b) - Kalbau | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Sat Nov 10 08:00:00 IST 2018 | Wed Dec 12 16:00:00 IST 2018 |  | COMPLETED
2669 | TT_TASK | Turbine Hall GL5-7 /F-E (Bay 3b) - Kalbau | Thu Nov 29 08:00:00 IST 2018 | Sat Dec 01 16:00:00 IST 2018 | Mon Nov 12 08:00:00 IST 2018 | Wed Nov 14 16:00:00 IST 2018 |  | COMPLETED
2670 | TT_TASK | Turbine Hall GL5-7 /E-D (Bay 4b) - Kalbau | Thu Nov 29 08:00:00 IST 2018 | Sat Dec 01 16:00:00 IST 2018 | Wed Nov 14 08:00:00 IST 2018 | Fri Nov 16 16:00:00 IST 2018 |  | COMPLETED
2671 | TT_TASK | Turbine Hall GL5-7 /D-C (Bay 5b) - Kalbau | Mon Dec 03 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 | Fri Nov 16 08:00:00 IST 2018 | Mon Nov 19 16:00:00 IST 2018 |  | COMPLETED
2672 | TT_TASK | Turbine Hall GL5-7 /C-B (Bay 6b) - Kalbau (DEF_WK07 confirmed not required) | Sat Jan 26 08:00:00 IST 2019 | Tue Jan 29 16:00:00 IST 2019 | Thu Dec 13 08:00:00 IST 2018 | Sat Dec 15 16:00:00 IST 2018 |  | COMPLETED
2673 | TT_TASK | Turbine Hall GL5-7 /B-A (Bay 7b) - Kalbau | Tue Jan 29 08:00:00 IST 2019 | Thu Jan 31 16:00:00 IST 2019 | Sun Dec 16 08:00:00 IST 2018 | Tue Dec 18 16:00:00 IST 2018 |  | COMPLETED
2675 | TT_TASK | West Elevation / GL.7 / Gutter subframe | Mon Apr 01 08:00:00 IDT 2019 | Sun May 05 16:00:00 IDT 2019 | Fri Mar 22 08:00:00 IST 2019 | Wed Sep 04 16:00:00 IDT 2019 |  | COMPLETED
2676 | TT_TASK | West Elevation / GL.7 / Gutter Installation | Wed Jul 10 08:00:00 IDT 2019 | Sat Jul 27 16:00:00 IDT 2019 | Wed May 15 08:00:00 IDT 2019 | Fri Oct 25 16:00:00 IDT 2019 |  | COMPLETED
2678 | TT_TASK | Turbine Hall GL.5-7 - Vapour barrier & ST clips | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 15 16:00:00 IST 2019 | Sun Dec 23 08:00:00 IST 2018 | Sat Jan 12 16:00:00 IST 2019 |  | COMPLETED
2679 | TT_TASK | Turbine Hall GL.5-7 - Insulation & Kalzip | Sat Feb 02 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Fri Jan 04 08:00:00 IST 2019 | Tue Jan 15 16:00:00 IST 2019 |  | COMPLETED
2682 | TT_TASK | Air Intake & Bus Duct Installation / Construction period | Sat Jan 26 08:00:00 IST 2019 | Thu Apr 25 16:00:00 IDT 2019 | Sun Jan 20 08:00:00 IST 2019 | Sun Sep 08 16:00:00 IDT 2019 |  | COMPLETED
2683 | TT_TASK | Turbine Hall GL.7-10 - Cleats, purlins, bridging, etc | Sat Jan 26 08:00:00 IST 2019 | Tue Mar 05 16:00:00 IST 2019 | Thu Nov 15 08:00:00 IST 2018 | Sat Jan 19 16:00:00 IST 2019 |  | COMPLETED
2684 | TT_TASK | Turbine Hall GL.7-10 (Bay 1c) - embeds and subframe | Sun Sep 01 08:00:00 IDT 2019 | Sat Sep 07 16:00:00 IDT 2019 | Mon Aug 05 08:00:00 IDT 2019 | Sun Aug 11 16:00:00 IDT 2019 |  | COMPLETED
2685 | TT_TASK | Turbine Hall GL.7-10 (Bay 2c) - Embeds and subframe | Sat Sep 07 08:00:00 IDT 2019 | Fri Sep 13 16:00:00 IDT 2019 | Sun Aug 11 08:00:00 IDT 2019 | Sat Aug 17 16:00:00 IDT 2019 |  | COMPLETED
2686 | TT_TASK | Turbine Hall GL.7-10 (Bay 3c) - Embeds and subframe | Wed Jan 01 08:00:00 IST 2020 | Fri Jan 31 16:00:00 IST 2020 | Mon Sep 09 08:00:00 IDT 2019 | Fri Oct 04 16:00:00 IDT 2019 |  | COMPLETED
2687 | TT_TASK | Turbine Hall GL.7-10 (Bay 4c) - Kalbau | Wed Mar 06 08:00:00 IST 2019 | Fri Mar 22 16:00:00 IST 2019 | Sat Jan 12 08:00:00 IST 2019 | Sat Jan 19 16:00:00 IST 2019 |  | COMPLETED
2689 | TT_TASK | Turbine Hall GL.7-10 (Bay 4c) - Deferred Opening | Thu Aug 01 08:00:00 IDT 2019 | Fri Aug 16 16:00:00 IDT 2019 | Fri Mar 01 08:00:00 IST 2019 | Sat Mar 16 16:00:00 IST 2019 |  | COMPLETED
2690 | TT_TASK | Turbine Hall GL.7-10 (Bay 4c) - Kalzip | Thu Aug 01 08:00:00 IDT 2019 | Tue Aug 20 16:00:00 IDT 2019 | Wed Mar 06 08:00:00 IST 2019 | Mon Mar 25 16:00:00 IST 2019 |  | COMPLETED
2692 | TT_TASK | Turbine Hall GL.7-10 / F-K - Kalbau/ VB/ ST clip/ Insul./ Kalzip | Sun Sep 01 08:00:00 IDT 2019 | Tue Sep 17 16:00:00 IDT 2019 | Wed Aug 14 08:00:00 IDT 2019 | Wed Sep 25 16:00:00 IDT 2019 |  | COMPLETED
2693 | TT_TASK | Turbine Hall GL.7-10 / A-F - Kalbau/ VB/ ST clip/ Insul./ Kalzip | Sat Feb 01 08:00:00 IST 2020 | Fri Feb 21 16:00:00 IST 2020 | Sat Oct 05 08:00:00 IDT 2019 | Mon Oct 21 16:00:00 IDT 2019 |  | COMPLETED
2694 | TT_TASK | West Elevation / GL.10, K -E / Gutter subframe | Mon May 06 08:00:00 IDT 2019 | Fri May 10 16:00:00 IDT 2019 | Thu Mar 28 08:00:00 IST 2019 | Thu May 09 16:00:00 IDT 2019 |  | COMPLETED
2695 | TT_TASK | West Elevation / GL. 10, E -A / Gutter subframe | Mon Apr 08 08:00:00 IDT 2019 | Fri Apr 12 16:00:00 IDT 2019 | Thu Mar 28 08:00:00 IST 2019 | Thu May 09 16:00:00 IDT 2019 |  | COMPLETED
2696 | TT_TASK | West Elevation / GL. 10, K -E / Gutter Installation | Fri Sep 13 08:00:00 IDT 2019 | Fri Sep 27 16:00:00 IDT 2019 | Mon Jun 17 08:00:00 IDT 2019 | Sat Jul 27 16:00:00 IDT 2019 |  | COMPLETED
2697 | TT_TASK | West Elevation / GL. 10, E -A / Gutter Installation | Fri Sep 13 08:00:00 IDT 2019 | Fri Sep 27 16:00:00 IDT 2019 | Mon Jun 17 08:00:00 IDT 2019 | Sat Jul 27 16:00:00 IDT 2019 |  | COMPLETED
2699 | TT_TASK | East Elevation / GL.1, A-E / Gutter subframe | Thu May 02 08:00:00 IDT 2019 | Wed May 08 16:00:00 IDT 2019 | Thu Apr 04 08:00:00 IDT 2019 | Tue May 14 16:00:00 IDT 2019 |  | COMPLETED
2700 | TT_TASK | East Elevation / GL.1, E -K / Gutter subframe | Thu May 09 08:00:00 IDT 2019 | Wed May 15 16:00:00 IDT 2019 | Thu Apr 04 08:00:00 IDT 2019 | Tue May 14 16:00:00 IDT 2019 |  | COMPLETED
2701 | TT_TASK | East Elevation / GL. 1, A-E / Gutter Installation | Wed Jun 19 08:00:00 IDT 2019 | Tue Jul 02 16:00:00 IDT 2019 | Fri May 17 08:00:00 IDT 2019 | Sat Jun 22 16:00:00 IDT 2019 |  | COMPLETED
2702 | TT_TASK | East Elevation / GL. 1, E-K / Gutter Installation | Wed Jun 19 08:00:00 IDT 2019 | Tue Jul 02 16:00:00 IDT 2019 | Fri May 17 08:00:00 IDT 2019 | Sat Jun 22 16:00:00 IDT 2019 |  | COMPLETED
2703 | TT_TASK | West Elevation / GL.5, A-E / Gutter subframe | Mon Apr 01 08:00:00 IDT 2019 | Mon Apr 15 16:00:00 IDT 2019 | Tue Mar 26 08:00:00 IST 2019 | Wed May 15 16:00:00 IDT 2019 |  | COMPLETED
2704 | TT_TASK | West Elevation / GL.5, E-K / Gutter subframe | Thu May 02 08:00:00 IDT 2019 | Tue May 14 16:00:00 IDT 2019 | Tue Mar 26 08:00:00 IST 2019 | Wed May 15 16:00:00 IDT 2019 |  | COMPLETED
2705 | TT_TASK | West Elevation / GL.5, A-E / Gutter Installation | Sat Jun 01 08:00:00 IDT 2019 | Sat Jun 15 16:00:00 IDT 2019 | Sat May 11 08:00:00 IDT 2019 | Sat Aug 10 16:00:00 IDT 2019 |  | COMPLETED
2706 | TT_TASK | West Elevation / GL.5, E-K / Gutter Installation | Sat Jun 01 08:00:00 IDT 2019 | Sat Jun 15 16:00:00 IDT 2019 | Sat May 11 08:00:00 IDT 2019 | Sat Aug 10 16:00:00 IDT 2019 |  | COMPLETED
2709 | TT_TASK | DW03 - Construct Walls of Turbine Hall below +12.0(GL.K /5-7) after erection of Condensate Pipe Rack & associated equip | Mon Apr 01 08:00:00 IDT 2019 | Sat Jun 01 16:00:00 IDT 2019 | Wed Nov 07 08:00:00 IST 2018 | Wed Nov 14 16:00:00 IST 2018 |  | COMPLETED
2710 | TT_TASK | Perimeter RC Wall / North Elevation - GL.1 -5 | Tue Oct 30 08:00:00 IST 2018 | Fri Nov 09 16:00:00 IST 2018 | Mon Jul 02 00:00:00 IDT 2018 | Thu Jul 19 16:00:00 IDT 2018 |  | COMPLETED
2711 | TT_TASK | Perimeter RC Wall / North Elevation - GL.7 -10 | Tue Aug 21 08:00:00 IDT 2018 | Fri Aug 24 16:00:00 IDT 2018 | Thu Apr 12 08:00:00 IDT 2018 | Sat May 12 16:00:00 IDT 2018 |  | COMPLETED
2712 | TT_TASK | Perimeter RC Wall / East Elevation - GL.A -C | Thu Jul 12 08:00:00 IDT 2018 | Mon Jul 16 16:00:00 IDT 2018 | Thu Jun 21 08:00:00 IDT 2018 | Fri Jul 27 16:00:00 IDT 2018 |  | COMPLETED
2713 | TT_TASK | Perimeter RC Wall / East Elevation - GL.C -E | Sat Jul 07 08:00:00 IDT 2018 | Wed Jul 11 16:00:00 IDT 2018 | Thu Jun 21 08:00:00 IDT 2018 | Fri Jul 27 16:00:00 IDT 2018 |  | COMPLETED
2714 | TT_TASK | Perimeter RC Wall / East Elevation - GL.E -G | Sat Jun 30 08:00:00 IDT 2018 | Thu Jul 05 16:00:00 IDT 2018 | Sat Jun 02 08:00:00 IDT 2018 | Sat Jun 16 16:00:00 IDT 2018 |  | COMPLETED
2715 | TT_TASK | Perimeter RC Wall / East Elevation - GL.G -K | Tue Jun 26 08:00:00 IDT 2018 | Fri Jun 29 16:00:00 IDT 2018 | Sat Jun 02 08:00:00 IDT 2018 | Sat Jun 16 16:00:00 IDT 2018 |  | COMPLETED
2716 | TT_TASK | Perimeter RC Wall / South Elevation - GL.10 -7 | Mon Nov 26 08:00:00 IST 2018 | Fri Nov 30 16:00:00 IST 2018 | Fri Oct 19 08:00:00 IDT 2018 | Sun Oct 28 00:00:00 IDT 2018 |  | COMPLETED
2717 | TT_TASK | Perimeter RC Wall / South Elevation - GL.7 -5 [Deferred Works] | Mon Nov 26 08:00:00 IST 2018 | Mon Nov 26 08:00:00 IST 2018 | Fri Oct 19 08:00:00 IDT 2018 | Sun Oct 28 00:00:00 IDT 2018 |  | COMPLETED
2718 | TT_TASK | Perimeter RC Wall / South Elevation - GL.5 -2 | Mon Aug 27 08:00:00 IDT 2018 | Fri Aug 31 16:00:00 IDT 2018 | Wed Jul 11 08:00:00 IDT 2018 | Wed Jul 25 16:00:00 IDT 2018 |  | COMPLETED
2719 | TT_TASK | Perimeter RC Wall / West Elevation - GL.K -G | Mon Aug 06 08:00:00 IDT 2018 | Thu Aug 09 16:00:00 IDT 2018 | Thu Apr 12 08:00:00 IDT 2018 | Sat May 12 16:00:00 IDT 2018 |  | COMPLETED
2720 | TT_TASK | Perimeter RC Wall / West Elevation - GL.G -E | Mon Nov 26 08:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 | Sat Oct 20 08:00:00 IDT 2018 | Sat Nov 24 16:00:00 IST 2018 |  | COMPLETED
2721 | TT_TASK | Perimeter RC Wall / West Elevation - GL.E -C | Fri Nov 30 08:00:00 IST 2018 | Tue Dec 04 16:00:00 IST 2018 | Sat Oct 20 08:00:00 IDT 2018 | Sun Nov 04 00:00:00 IST 2018 |  | COMPLETED
2722 | TT_TASK | Perimeter RC Wall / West Elevation - GL.C -A | Mon Nov 26 08:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 | Fri Oct 19 08:00:00 IDT 2018 | Sun Oct 28 00:00:00 IDT 2018 |  | COMPLETED
2724 | TT_TASK | DW05 - Construct Int.Structural Steel Members of Turbine Hall below +23.9 (GL.A-C/11) | Thu Aug 01 08:00:00 IDT 2019 | Fri Aug 30 16:00:00 IDT 2019 | Thu Apr 18 08:00:00 IDT 2019 | Thu May 16 16:00:00 IDT 2019 |  | COMPLETED
2725 | TT_TASK | DW11 - Capping of all cladding openings required by / following the installation of all items of plant and equip (TBC) | Sat Jun 01 08:00:00 IDT 2019 | Thu Aug 15 16:00:00 IDT 2019 | Mon May 13 08:00:00 IDT 2019 | Fri Jan 24 16:00:00 IST 2020 |  | COMPLETED
2726 | TT_TASK | Lift No.1 - Glazing panel to lift shaft | Thu May 02 08:00:00 IDT 2019 | Wed May 29 16:00:00 IDT 2019 | Wed Mar 27 08:00:00 IST 2019 | Wed May 15 16:00:00 IDT 2019 |  | COMPLETED
2727 | TT_TASK | North Elevation GL.1-5 / Cleats, purlins, bridging, bracing, etc | Mon Nov 26 08:00:00 IST 2018 | Sat Dec 08 16:00:00 IST 2018 | Thu Sep 27 08:00:00 IDT 2018 | Tue Jan 15 16:00:00 IST 2019 |  | COMPLETED
2728 | TT_TASK | North Elevation GL.1-5 / Kalbau | Sat Feb 23 08:00:00 IST 2019 | Sat Mar 09 16:00:00 IST 2019 | Tue Dec 25 08:00:00 IST 2018 | Sat Jan 19 16:00:00 IST 2019 |  | COMPLETED
2729 | TT_TASK | North Elevation GL.1-5 / Vapour barrier & ST clips | Fri Feb 01 08:00:00 IST 2019 | Thu Feb 28 16:00:00 IST 2019 | Mon Jan 14 08:00:00 IST 2019 | Thu Jan 24 16:00:00 IST 2019 |  | COMPLETED
2730 | TT_TASK | East Elevation at GL.1 / Mullion & transom | Sat Jan 26 08:00:00 IST 2019 | Sat Mar 09 16:00:00 IST 2019 | Thu Dec 13 08:00:00 IST 2018 | Thu Feb 14 16:00:00 IST 2019 |  | COMPLETED
2731 | TT_TASK | East Elevation at GL.1 / Glazing panels | Mon Mar 11 08:00:00 IST 2019 | Thu May 02 16:00:00 IDT 2019 | Thu Jan 24 08:00:00 IST 2019 | Sun Mar 03 16:00:00 IST 2019 |  | COMPLETED
2732 | TT_TASK | East Elevation at GL.1 / Subframe for aluminum features | Thu Apr 04 08:00:00 IDT 2019 | Wed Apr 24 16:00:00 IDT 2019 | Mon Feb 11 08:00:00 IST 2019 | Fri May 31 16:00:00 IDT 2019 |  | COMPLETED
2733 | TT_TASK | South Elevation GL.1-5 / Cleats, purlins, bridging, bracing, etc | Mon Nov 26 08:00:00 IST 2018 | Sat Feb 23 16:00:00 IST 2019 | Wed Oct 03 08:00:00 IDT 2018 | Wed Jan 16 16:00:00 IST 2019 |  | COMPLETED
2734 | TT_TASK | South Elevation GL.1-5 / Kalbau | Mon Feb 25 08:00:00 IST 2019 | Sat Mar 23 16:00:00 IST 2019 | Tue Nov 20 08:00:00 IST 2018 | Thu Jan 31 16:00:00 IST 2019 |  | COMPLETED
2735 | TT_TASK | South Elevation GL.1-5 / Vapour barrier & ST clips | Thu Jan 31 08:00:00 IST 2019 | Wed Feb 27 16:00:00 IST 2019 | Wed Jan 02 08:00:00 IST 2019 | Thu Feb 28 16:00:00 IST 2019 |  | COMPLETED
2736 | TT_TASK | South Elevation GL.1-5 / Insulation & Kalzip | Mon Apr 15 08:00:00 IDT 2019 | Thu May 02 16:00:00 IDT 2019 | Wed Feb 13 08:00:00 IST 2019 | Thu Feb 28 16:00:00 IST 2019 |  | COMPLETED
2737 | TT_TASK | West Elevation at GL.5 / Mullion & transom | Sat Jan 26 08:00:00 IST 2019 | Tue Feb 12 16:00:00 IST 2019 | Mon Jan 07 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 |  | COMPLETED
2738 | TT_TASK | West Elevation at GL.5 / Glazing panels | Sat Apr 27 08:00:00 IDT 2019 | Thu May 02 16:00:00 IDT 2019 | Wed Feb 20 08:00:00 IST 2019 | Thu Feb 28 16:00:00 IST 2019 |  | COMPLETED
2739 | TT_TASK | West Elevation at GL.5 / Subframe for aluminum features | Thu May 02 08:00:00 IDT 2019 | Mon May 20 16:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Sat Aug 10 16:00:00 IDT 2019 |  | COMPLETED
2740 | TT_TASK | West Elevation at GL.5 / Aluminum featured claddings | Fri Aug 16 08:00:00 IDT 2019 | Wed Aug 28 16:00:00 IDT 2019 | Wed Jul 03 08:00:00 IDT 2019 | Thu Aug 15 16:00:00 IDT 2019 |  | COMPLETED
2741 | TT_TASK | North Elevation GL.1-5 / Insulation & Kalzip | Sat Feb 02 08:00:00 IST 2019 | Fri Mar 01 16:00:00 IST 2019 | Mon Jan 21 08:00:00 IST 2019 | Tue Jan 29 16:00:00 IST 2019 |  | COMPLETED
2742 | TT_TASK | North Elevation GL.5-10 / Cleats, purlins, bridging, bracing, etc | Sat Jan 26 08:00:00 IST 2019 | Mon Mar 04 16:00:00 IST 2019 | Fri Nov 23 08:00:00 IST 2018 | Mon Dec 24 16:00:00 IST 2018 |  | COMPLETED
2743 | TT_TASK | North Elevation GL.5-10 / Kalbau | Fri Feb 22 08:00:00 IST 2019 | Mon Mar 04 16:00:00 IST 2019 | Mon Dec 17 08:00:00 IST 2018 | Sat Jan 19 16:00:00 IST 2019 |  | COMPLETED
2744 | TT_TASK | East Elevation at GL.1 / Aluminum featured claddings | Thu Aug 01 08:00:00 IDT 2019 | Mon Aug 19 16:00:00 IDT 2019 | Tue Jun 25 08:00:00 IDT 2019 | Sat Nov 30 16:00:00 IST 2019 |  | COMPLETED
2745 | TT_TASK | East Elevation at GL.1 / Cleats, purlins, bridging, bracing, etc | Mon Nov 26 08:00:00 IST 2018 | Sat Jan 12 16:00:00 IST 2019 | Fri Aug 31 08:00:00 IDT 2018 | Sat Oct 20 16:00:00 IDT 2018 |  | COMPLETED
2746 | TT_TASK | East Elevation at GL.1 / Subframe for wall claddings | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 01 16:00:00 IST 2019 | Fri Nov 30 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 |  | COMPLETED
2747 | TT_TASK | Eest Elevation at GL.1 / Remaining cleats, purlins, bracing, etc. | Sat Feb 02 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Mon Dec 03 08:00:00 IST 2018 | Sun Dec 09 16:00:00 IST 2018 |  | COMPLETED
2748 | TT_TASK | South Elevation GL.5-10 / Cleats, purlins, bridging, bracing, etc | Sat Jan 26 08:00:00 IST 2019 | Fri Mar 15 16:00:00 IST 2019 | Wed Nov 28 08:00:00 IST 2018 | Wed Mar 13 16:00:00 IST 2019 |  | COMPLETED
2749 | TT_TASK | South Elevation GL.5-10 / Kalbau | Sat Mar 02 08:00:00 IST 2019 | Fri Mar 15 16:00:00 IST 2019 | Mon Jan 07 08:00:00 IST 2019 | Thu Mar 14 16:00:00 IST 2019 |  | COMPLETED
2750 | TT_TASK | South Elevation GL.5-10 / Vapour barrier & ST clips | Sat May 04 08:00:00 IDT 2019 | Sat May 25 16:00:00 IDT 2019 | Fri Mar 08 08:00:00 IST 2019 | Sun Mar 31 16:00:00 IDT 2019 |  | COMPLETED
2751 | TT_TASK | South Elevation GL.5-10 / Insulation & Kalzip | Mon May 20 08:00:00 IDT 2019 | Sat Jun 01 16:00:00 IDT 2019 | Fri Mar 15 08:00:00 IST 2019 | Fri Mar 29 16:00:00 IDT 2019 |  | COMPLETED
2752 | TT_TASK | West Elevation at GL.7 / Mullion & transom | Mon Apr 01 08:00:00 IDT 2019 | Sat May 04 16:00:00 IDT 2019 | Fri Feb 15 08:00:00 IST 2019 | Wed Mar 20 16:00:00 IST 2019 |  | COMPLETED
2753 | TT_TASK | West Elevation at GL.7 / Glazing panels | Mon Apr 29 08:00:00 IDT 2019 | Sat May 11 16:00:00 IDT 2019 | Tue Mar 12 08:00:00 IST 2019 | Sat Mar 30 16:00:00 IDT 2019 |  | COMPLETED
2755 | TT_TASK | West Elevation at GL.7 / Erect PERI bridge over scaffold [EVENT063] | Thu Aug 01 08:00:00 IDT 2019 | Thu Aug 15 16:00:00 IDT 2019 | Sat Jul 20 08:00:00 IDT 2019 | Sat Aug 03 16:00:00 IDT 2019 |  | COMPLETED
2756 | TT_TASK | West Elevation at GL.7 / Complete remaining glazing [EVENT063] | Thu Sep 05 08:00:00 IDT 2019 | Sat Sep 28 16:00:00 IDT 2019 | Mon Aug 05 08:00:00 IDT 2019 | Wed Aug 28 16:00:00 IDT 2019 |  | COMPLETED
2757 | TT_TASK | West Elevation at GL.7 / Subframe for aluminum features | Thu May 02 08:00:00 IDT 2019 | Mon May 13 16:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Sat Oct 12 16:00:00 IDT 2019 |  | COMPLETED
2758 | TT_TASK | West Elevation at GL.7 / Aluminum featured claddings | Fri Aug 23 08:00:00 IDT 2019 | Mon Sep 02 16:00:00 IDT 2019 | Mon Jul 15 08:00:00 IDT 2019 | Fri Oct 25 16:00:00 IDT 2019 |  | COMPLETED
2759 | TT_TASK | West Elevation at GL.7 / Cleats, purlins, bridging, bracing, etc | Sat Jan 26 08:00:00 IST 2019 | Sat Apr 27 16:00:00 IDT 2019 | Thu Nov 29 08:00:00 IST 2018 | Thu Mar 28 16:00:00 IST 2019 |  | COMPLETED
2760 | TT_TASK | West Elevation at GL.7 / Kalbau | Thu Apr 25 08:00:00 IDT 2019 | Fri May 10 16:00:00 IDT 2019 | Thu Mar 21 08:00:00 IST 2019 | Sun Mar 31 16:00:00 IDT 2019 |  | COMPLETED
2762 | TT_TASK | West Elevation at GL.7 / KSS mounting vent pipe onto support frame [EVENT] | Thu Jan 02 08:00:00 IST 2020 | Tue Jan 14 16:00:00 IST 2020 | Thu Sep 05 08:00:00 IDT 2019 | Fri Sep 27 16:00:00 IDT 2019 |  | COMPLETED
2763 | TT_TASK | West Elevation at GL.7 / KSS place vent pipe and support frame in position, bolt fixing by LCAL [EVENT / ROI] | Wed Jan 15 08:00:00 IST 2020 | Wed Jan 15 16:00:00 IST 2020 | Sat Sep 28 08:00:00 IDT 2019 | Sat Sep 28 16:00:00 IDT 2019 |  | COMPLETED
2764 | TT_TASK | West Elevation at GL.7 / Vapour barrier & ST clips | Thu May 02 08:00:00 IDT 2019 | Fri May 24 16:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Thu Oct 03 16:00:00 IDT 2019 |  | COMPLETED
2765 | TT_TASK | West Elevation at GL.7 / Insulation & Kalzip | Sat May 18 08:00:00 IDT 2019 | Fri May 31 16:00:00 IDT 2019 | Mon Apr 29 08:00:00 IDT 2019 | Thu Oct 10 16:00:00 IDT 2019 |  | COMPLETED
2766 | TT_TASK | North Elevation GL.5-10 / Vapour barrier & ST clips | Mon Dec 31 08:00:00 IST 2018 | Mon Jan 14 16:00:00 IST 2019 | Mon Dec 31 08:00:00 IST 2018 | Thu Mar 28 16:00:00 IST 2019 |  | COMPLETED
2767 | TT_TASK | North Elevation GL.5-10 / Insulation & Kalzip | Sat Feb 02 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Tue Jan 08 08:00:00 IST 2019 | Mon Apr 01 16:00:00 IDT 2019 |  | COMPLETED
2769 | TT_TASK | East Elevation at GL.1 / Kalbau | Mon Nov 26 08:00:00 IST 2018 | Sat Dec 29 16:00:00 IST 2018 | Fri Nov 09 08:00:00 IST 2018 | Sun Dec 09 16:00:00 IST 2018 |  | COMPLETED
2770 | TT_TASK | East Elevation at GL.1 / Vapour barrier & ST clips | Mon Apr 01 08:00:00 IDT 2019 | Thu Apr 25 16:00:00 IDT 2019 | Thu Mar 28 08:00:00 IST 2019 | Sat Apr 20 16:00:00 IDT 2019 |  | COMPLETED
2771 | TT_TASK | East Elevation at GL.1 / Insulation & Kalzip | Tue May 07 08:00:00 IDT 2019 | Tue May 28 16:00:00 IDT 2019 | Sat Apr 20 08:00:00 IDT 2019 | Tue Apr 30 16:00:00 IDT 2019 |  | COMPLETED
2772 | TT_TASK | East Elevation at GL.1 / Louvres (incl' those at the Loft) | Fri Apr 12 08:00:00 IDT 2019 | Thu May 16 16:00:00 IDT 2019 | Wed Jan 16 08:00:00 IST 2019 | Fri Mar 01 16:00:00 IST 2019 |  | COMPLETED
2775 | TT_TASK | North Elevation GL.1-10 / Aluminum features claddings | Mon Sep 02 08:00:00 IDT 2019 | Fri Oct 18 16:00:00 IDT 2019 | Fri Aug 16 08:00:00 IDT 2019 | Sat Nov 16 16:00:00 IST 2019 |  | COMPLETED
2776 | TT_TASK | South Elevation GL.1-10 / Aluminum features claddings | Thu Jan 02 08:00:00 IST 2020 | Mon Feb 03 16:00:00 IST 2020 | Tue Sep 24 08:00:00 IDT 2019 | Mon Oct 21 16:00:00 IDT 2019 |  | COMPLETED
2777 | TT_TASK | West Elevation at GL.10 / Mullion & transom | Mon Apr 01 08:00:00 IDT 2019 | Mon Apr 08 16:00:00 IDT 2019 | Mon Mar 18 08:00:00 IST 2019 | Mon Mar 25 16:00:00 IST 2019 |  | COMPLETED
2778 | TT_TASK | West Elevation at GL.10 / Glazing panels | Tue Apr 09 08:00:00 IDT 2019 | Mon Apr 15 16:00:00 IDT 2019 | Mon Mar 25 08:00:00 IST 2019 | Sat Mar 30 16:00:00 IDT 2019 |  | COMPLETED
2779 | TT_TASK | West Elevation at GL.10 / Subframe for aluminum features | Thu May 02 08:00:00 IDT 2019 | Sat May 18 16:00:00 IDT 2019 | Mon Mar 25 08:00:00 IST 2019 | Thu Aug 15 16:00:00 IDT 2019 |  | COMPLETED
2780 | TT_TASK | West Elevation at GL.10 / Aluminum featured claddings | Fri Aug 16 08:00:00 IDT 2019 | Thu Aug 29 16:00:00 IDT 2019 | Thu Jul 18 08:00:00 IDT 2019 | Thu Aug 22 16:00:00 IDT 2019 |  | COMPLETED
2781 | TT_TASK | West Elevation at GL.10 / Cleats, purlins, bridging, bracing, etc | Sat Jun 01 08:00:00 IDT 2019 | Sat Jun 15 16:00:00 IDT 2019 | Thu May 02 08:00:00 IDT 2019 | Thu Jul 18 16:00:00 IDT 2019 |  | COMPLETED
2782 | TT_TASK | West Elevation at GL.10 / Aluminum wall cladding | Thu Aug 22 08:00:00 IDT 2019 | Tue Sep 03 16:00:00 IDT 2019 | Thu May 23 08:00:00 IDT 2019 | Thu Oct 31 16:00:00 IST 2019 |  | COMPLETED
2783 | TT_TASK | West Elevation at GL.10 / Louvres to 1st floor rooms | Thu May 02 08:00:00 IDT 2019 | Tue May 14 16:00:00 IDT 2019 | Sat Apr 27 08:00:00 IDT 2019 | Thu Jun 13 16:00:00 IDT 2019 |  | COMPLETED
2784 | TT_TASK | West Elevation at GL.10 / Louvres to ground floor rooms | Wed May 15 08:00:00 IDT 2019 | Fri May 24 16:00:00 IDT 2019 | Sat Apr 27 08:00:00 IDT 2019 | Sat Oct 19 16:00:00 IDT 2019 |  | COMPLETED
2785 | TT_TASK | North Elevation GL.1-10 / Louvres | Thu May 02 08:00:00 IDT 2019 | Sat Jul 13 16:00:00 IDT 2019 | Thu Apr 04 08:00:00 IDT 2019 | Wed Sep 25 16:00:00 IDT 2019 |  | COMPLETED
2786 | TT_TASK | South Elevation GL.1-10 / Louvres | Mon Apr 01 08:00:00 IDT 2019 | Sat Jun 15 16:00:00 IDT 2019 | Mon Mar 11 08:00:00 IST 2019 | Sat Apr 20 16:00:00 IDT 2019 |  | COMPLETED
2788 | TT_TASK | Crane Walkway, Steel Platforms and Staircases | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Mon Aug 13 08:00:00 IDT 2018 | Tue Mar 19 16:00:00 IST 2019 |  | COMPLETED
2789 | TT_TASK | GMS grating at Loft Level at +37.8 | Thu Aug 01 08:00:00 IDT 2019 | Sun Sep 29 16:00:00 IDT 2019 | Thu Jun 20 08:00:00 IDT 2019 | Wed Sep 11 16:00:00 IDT 2019 |  | COMPLETED
2791 | TT_TASK | Lube Oil Module - Construct 1m high bund wall | Tue Oct 16 08:00:00 IDT 2018 | Fri Oct 26 16:00:00 IDT 2018 | Wed Aug 15 08:00:00 IDT 2018 | Fri Aug 24 16:00:00 IDT 2018 |  | COMPLETED
2792 | TT_TASK | Switchgear Block - Construct internal concrete wall G/F | Sat Oct 27 08:00:00 IDT 2018 | Fri Nov 16 16:00:00 IST 2018 | Thu May 10 08:00:00 IDT 2018 | Tue Jan 08 00:00:00 IST 2019 |  | COMPLETED
2793 | TT_TASK | Switchgear Block - Construct internal concrete wall 1/F | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Wed Oct 24 08:00:00 IDT 2018 | Sat Jan 12 16:00:00 IST 2019 |  | COMPLETED
2794 | TT_TASK | Turbine Building (GL001) - ABWF works | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Sat Sep 01 08:00:00 IDT 2018 | Thu Feb 27 16:00:00 IST 2020 |  | COMPLETED
2795 | TT_TASK | Condensate Polishing Plant (GL002) - ABWF works | Sat Feb 23 08:00:00 IST 2019 | Fri Mar 01 16:00:00 IST 2019 | Fri Dec 07 08:00:00 IST 2018 | Thu Feb 27 16:00:00 IST 2020 |  | COMPLETED
2796 | TT_TASK | Switchgear Block G/F - ABWF works | Sat Jan 26 08:00:00 IST 2019 | Fri Mar 01 16:00:00 IST 2019 | Thu Oct 04 08:00:00 IDT 2018 | Sat Mar 30 16:00:00 IDT 2019 |  | COMPLETED
2797 | TT_TASK | Switchgear Block 1/F - ABWF works | Sat Jan 26 08:00:00 IST 2019 | Fri Mar 01 16:00:00 IST 2019 | Wed Nov 28 08:00:00 IST 2018 | Sat Mar 30 16:00:00 IDT 2019 |  | COMPLETED
2798 | TT_TASK | Raised floor to Electronic Equipment and Control Room | Thu May 02 08:00:00 IDT 2019 | Fri May 17 16:00:00 IDT 2019 | Mon Apr 08 08:00:00 IDT 2019 | Sat May 11 16:00:00 IDT 2019 |  | COMPLETED
2799 | TT_TASK | Suespended ceiling to Control Room and ELV Room [descoped; TBC] | Thu May 02 08:00:00 IDT 2019 | Fri May 17 16:00:00 IDT 2019 | Mon Apr 08 08:00:00 IDT 2019 | Sat May 11 16:00:00 IDT 2019 |  | COMPLETED
2800 | TT_TASK | Doors, louvre, roller shutters, handrails, etc | Mon Apr 01 08:00:00 IDT 2019 | Tue Aug 13 16:00:00 IDT 2019 | Mon Mar 18 08:00:00 IST 2019 | Thu Feb 27 16:00:00 IST 2020 |  | COMPLETED
2801 | TT_TASK | Finishes to perimeter concrete walls (i.e. tiling) | Thu Jan 02 08:00:00 IST 2020 | Tue Feb 25 16:00:00 IST 2020 | Wed Nov 06 08:00:00 IST 2019 | Tue Dec 24 16:00:00 IST 2019 |  | COMPLETED
2803 | TT_TASK | Overhead Crane - Unpack and Checking | Tue May 01 08:00:00 IDT 2018 | Mon May 14 16:00:00 IDT 2018 | Mon Jan 08 08:00:00 IST 2018 | Fri Jan 19 16:00:00 IST 2018 |  | COMPLETED
2804 | TT_TASK | Overhead Crane - Pre-assembly at Green Lawn | Mon Apr 23 08:00:00 IDT 2018 | Wed May 23 16:00:00 IDT 2018 | Fri Mar 02 08:00:00 IST 2018 | Thu Mar 29 16:00:00 IDT 2018 |  | COMPLETED
2806 | TT_TASK | Overhead Crane / Event - Bolt inspection and handover | Tue Jun 26 08:00:00 IDT 2018 | Fri Jun 29 16:00:00 IDT 2018 | Sat May 26 08:00:00 IDT 2018 | Tue May 29 16:00:00 IDT 2018 |  | COMPLETED
2807 | TT_TASK | Overhead Crane / Event - Rail installation / Weld on ground | Tue Jun 26 08:00:00 IDT 2018 | Tue Jul 10 16:00:00 IDT 2018 | Wed May 30 08:00:00 IDT 2018 | Wed Jun 13 16:00:00 IDT 2018 |  | COMPLETED
2808 | TT_TASK | Overhead Crane / Event - Rail installation / Lift-up | Tue Jun 26 08:00:00 IDT 2018 | Fri Jun 29 16:00:00 IDT 2018 | Thu Jun 14 08:00:00 IDT 2018 | Sun Jun 17 16:00:00 IDT 2018 |  | COMPLETED
2809 | TT_TASK | Overhead Crane / Event - Rail installation / Re-delivery of bolts | Tue Jun 26 08:00:00 IDT 2018 | Wed Jul 04 16:00:00 IDT 2018 | Mon Jun 18 00:00:00 IDT 2018 | Tue Jun 26 16:00:00 IDT 2018 |  | COMPLETED
2810 | TT_TASK | Overhead Crane / Event - Rail installation / Clip down | Thu Jul 26 08:00:00 IDT 2018 | Sun Aug 05 16:00:00 IDT 2018 | Wed Jun 27 08:00:00 IDT 2018 | Fri Jul 13 16:00:00 IDT 2018 |  | COMPLETED
2811 | TT_TASK | Overhead Crane - Lift up and sit on position 1 of 2 | Mon Aug 06 08:00:00 IDT 2018 | Wed Aug 08 16:00:00 IDT 2018 | Sat Jul 14 08:00:00 IDT 2018 | Mon Jul 16 16:00:00 IDT 2018 |  | COMPLETED
2812 | TT_TASK | Overhead Crane - Lift up and sit on position 2 of 2 | Wed Aug 08 08:00:00 IDT 2018 | Fri Aug 10 16:00:00 IDT 2018 | Tue Jul 17 08:00:00 IDT 2018 | Thu Jul 19 16:00:00 IDT 2018 |  | COMPLETED
2813 | TT_TASK | Overhead Crane - E&M Fit-out and T&C | Thu Jul 26 08:00:00 IDT 2018 | Tue Sep 04 16:00:00 IDT 2018 | Fri Jul 20 08:00:00 IDT 2018 | Fri Aug 31 16:00:00 IDT 2018 |  | COMPLETED
2816 | TT_TASK | Turbine Hall Area - Lightning Pit and Earth Pit | Thu Jan 02 08:00:00 IST 2020 | Mon Jan 20 16:00:00 IST 2020 | Mon Jul 22 08:00:00 IDT 2019 | Wed Dec 18 16:00:00 IST 2019 |  | COMPLETED
2818 | TT_TASK | Turbine Hall Area (GL.1-5) - Cable containment (Elect) | Thu Jun 06 08:00:00 IDT 2019 | Mon Jul 08 16:00:00 IDT 2019 | Mon Mar 18 08:00:00 IST 2019 | Thu Nov 07 16:00:00 IST 2019 |  | COMPLETED
2819 | TT_TASK | Turbine Hall Area (GL.5-7) - Cable containment (Elect) | Sat Jun 22 08:00:00 IDT 2019 | Mon Jul 15 16:00:00 IDT 2019 | Mon Apr 22 08:00:00 IDT 2019 | Thu Nov 21 16:00:00 IST 2019 |  | COMPLETED
2820 | TT_TASK | Turbine Hall Area (GL.8-10) - Cable containment (Elect) | Thu Jul 04 08:00:00 IDT 2019 | Mon Jul 22 16:00:00 IDT 2019 | Mon May 27 08:00:00 IDT 2019 | Thu Oct 31 16:00:00 IST 2019 |  | COMPLETED
2821 | TT_TASK | Turbine Hall Area (High/ Roof Level) - Cable containmen (Elect) | Tue Oct 09 08:00:00 IDT 2018 | Mon Oct 15 16:00:00 IDT 2018 | Mon May 28 08:00:00 IDT 2018 | Thu Oct 17 16:00:00 IDT 2019 |  | COMPLETED
2822 | TT_TASK | Turbine Hall Area (incl' Switchgear Block) - Major Electrical Equipment on site | Sat Jun 01 08:00:00 IDT 2019 | Sun Jun 30 16:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 30 16:00:00 IDT 2019 |  | COMPLETED
2823 | TT_TASK | Switchgear Block - Installation of LV Switchboard, Transformers, UPS, DBs, etc | Tue Jul 02 08:00:00 IDT 2019 | Tue Aug 27 16:00:00 IDT 2019 | Mon Nov 12 08:00:00 IST 2018 | Fri May 31 16:00:00 IDT 2019 |  | COMPLETED
2824 | TT_TASK | Turbine Hall Area (GL.1-5) - Light fitting, power point, earting point incl. final termination | Thu Jan 02 08:00:00 IST 2020 | Sat Feb 22 16:00:00 IST 2020 | Fri Nov 08 08:00:00 IST 2019 | Fri Feb 07 16:00:00 IST 2020 |  | COMPLETED
2825 | TT_TASK | Turbine Hall Area (GL.5-7) - Light fitting, power point, earthing point incl. final termination | Thu Jan 02 08:00:00 IST 2020 | Sat Feb 22 16:00:00 IST 2020 | Fri Dec 06 08:00:00 IST 2019 | Fri Feb 07 16:00:00 IST 2020 |  | COMPLETED
2826 | TT_TASK | Turbine Hall Area (GL.8-10) - Light fitting, power point, earthing point incl. final termination | Tue Jan 21 08:00:00 IST 2020 | Thu Mar 12 16:00:00 IST 2020 | Fri Nov 01 08:00:00 IST 2019 | Fri Feb 07 16:00:00 IST 2020 |  | COMPLETED
2827 | TT_TASK | Turbine Hall Area / Roof Level - Installation of Photovoltaic Power System | Thu Jan 02 08:00:00 IST 2020 | Wed Mar 04 16:00:00 IST 2020 | Sat Oct 12 08:00:00 IDT 2019 | Thu Nov 14 16:00:00 IST 2019 |  | COMPLETED
2831 | TT_TASK | Turbine Hall Area / GL.1-5 - Ductwork and fan installation (ACMV) | Sat Jun 01 08:00:00 IDT 2019 | Wed Jun 26 16:00:00 IDT 2019 | Thu May 02 08:00:00 IDT 2019 | Fri Nov 29 16:00:00 IST 2019 |  | COMPLETED
2832 | TT_TASK | Turbine Hall Area / GL.5-7 - Ductwork and fan installation (ACMV) | Mon Sep 02 08:00:00 IDT 2019 | Thu Nov 07 16:00:00 IST 2019 | Mon Aug 26 08:00:00 IDT 2019 | Fri Dec 06 16:00:00 IST 2019 |  | COMPLETED
2837 | TT_TASK | Switchgear Block - Installation of Indoor Unit (VEUs) | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 26 16:00:00 IDT 2019 | Mon Feb 04 08:00:00 IST 2019 | Sat Mar 30 16:00:00 IDT 2019 |  | COMPLETED
2838 | TT_TASK | Switchgear Block (Turbine Hall Roof Level GL.7-10) - Installation of Outdoor Unit (VCUs) | Mon Sep 02 08:00:00 IDT 2019 | Tue Oct 15 16:00:00 IDT 2019 | Mon Aug 19 08:00:00 IDT 2019 | Fri Nov 15 16:00:00 IST 2019 |  | COMPLETED
2839 | TT_TASK | Turbine Hall Area / Loft Level - Installation of Roof Extraction Fan | Mon Sep 02 08:00:00 IDT 2019 | Mon Oct 28 16:00:00 IST 2019 | Thu Aug 15 08:00:00 IDT 2019 | Fri Nov 01 16:00:00 IST 2019 |  | COMPLETED
2840 | TT_TASK | Turbine Hall Area - Final ductwork and air grille / diffuser | Thu Jan 02 08:00:00 IST 2020 | Wed Feb 19 16:00:00 IST 2020 | Sat Oct 26 08:00:00 IDT 2019 | Fri Dec 06 16:00:00 IST 2019 |  | COMPLETED
2844 | TT_TASK | Turbine Hall - Installation of fire alarm panels | Thu Jan 02 08:00:00 IST 2020 | Wed Jan 15 16:00:00 IST 2020 | Fri Nov 01 08:00:00 IST 2019 | Thu Nov 14 16:00:00 IST 2019 |  | COMPLETED
2845 | TT_TASK | Turbine Hall - Installation of detectors incl' wiring and termination | Thu Jan 02 08:00:00 IST 2020 | Wed Jan 15 16:00:00 IST 2020 | Fri Nov 01 08:00:00 IST 2019 | Thu Nov 14 16:00:00 IST 2019 |  | COMPLETED
2846 | TT_TASK | Turbine Hall - Lift No.1 detector installation | Thu Jan 02 08:00:00 IST 2020 | Wed Jan 15 16:00:00 IST 2020 | Fri Nov 01 08:00:00 IST 2019 | Thu Nov 14 16:00:00 IST 2019 |  | COMPLETED
2847 | TT_TASK | Turbine Hall - Loft Platform detector installation | Thu Jan 02 08:00:00 IST 2020 | Wed Jan 15 16:00:00 IST 2020 | Fri Nov 01 08:00:00 IST 2019 | Thu Nov 14 16:00:00 IST 2019 |  | COMPLETED
2848 | TT_TASK | Turbine Hall - Installation of portable fire fighting equipment | Wed Jan 08 08:00:00 IST 2020 | Thu Jan 09 16:00:00 IST 2020 | Mon Mar 09 08:00:00 IST 2020 | Tue Mar 10 16:00:00 IST 2020 |  | COMPLETED
2849 | TT_TASK | Turbine Hall - Testing and Commisisoning to FS installation | Thu Jan 16 08:00:00 IST 2020 | Wed Jan 22 16:00:00 IST 2020 | Fri Nov 15 08:00:00 IST 2019 | Thu Nov 21 16:00:00 IST 2019 |  | COMPLETED
2854 | TT_TASK | Lift No.1 - Lift Installation incl' T&C | Fri Nov 01 08:00:00 IST 2019 | Wed Jan 01 16:00:00 IST 2020 | Mon Sep 23 08:00:00 IDT 2019 | Tue Dec 31 16:00:00 IST 2019 |  | COMPLETED
2855 | TT_TASK | Lift No.1 - Submit Form LE5 and EMSD Inspection | Thu Jan 02 08:00:00 IST 2020 | Tue Jan 21 16:00:00 IST 2020 | Wed Feb 19 08:00:00 IST 2020 | Wed Mar 04 16:00:00 IST 2020 |  | COMPLETED
2856 | TT_TASK | Lift No.1 - Obtain Use Permit | Wed Jan 22 08:00:00 IST 2020 | Thu Jan 30 16:00:00 IST 2020 | Thu Mar 05 08:00:00 IST 2020 | Thu Mar 12 16:00:00 IST 2020 |  | COMPLETED
2860 | TT_TASK | Exhaust Stack - Further excavation from +4.2 mPD to the required formation level | Thu Nov 16 08:00:00 IST 2017 | Fri Nov 17 16:00:00 IST 2017 | Thu Nov 16 08:00:00 IST 2017 | Fri Nov 17 16:00:00 IST 2017 |  | COMPLETED
2861 | TT_TASK | Exhaust Stack - Cast blinding concrete | Wed Jan 10 08:00:00 IST 2018 | Sat Jan 13 16:00:00 IST 2018 | Wed Dec 13 08:00:00 IST 2017 | Thu Dec 14 16:00:00 IST 2017 |  | COMPLETED
2862 | TT_TASK | Exhaust Stack - Trim pile and prepare pile head | Fri Sep 29 08:00:00 IDT 2017 | Thu Oct 12 16:00:00 IDT 2017 | Tue Sep 26 08:00:00 IDT 2017 | Sun Nov 19 00:00:00 IST 2017 |  | COMPLETED
2863 | TT_TASK | Exhaust Stack - Capping plate and rebar starter | Tue Nov 21 08:00:00 IST 2017 | Wed Nov 29 16:00:00 IST 2017 | Tue Nov 21 08:00:00 IST 2017 | Fri Dec 08 16:00:00 IST 2017 |  | COMPLETED
2864 | TT_TASK | Exhaust Stack - Erect side formwork | Sat Jan 06 08:00:00 IST 2018 | Fri Jan 12 16:00:00 IST 2018 | Thu Dec 21 08:00:00 IST 2017 | Sat Jan 06 16:00:00 IST 2018 |  | COMPLETED
2865 | TT_TASK | Exhaust Stack - Fix rebar and install cast-in /embed items | Mon Jan 15 08:00:00 IST 2018 | Sat Jan 27 16:00:00 IST 2018 | Thu Dec 21 08:00:00 IST 2017 | Wed Jan 10 16:00:00 IST 2018 |  | COMPLETED
2866 | TT_TASK | Exhaust Stack - Pour pile cap (incl' Lift Pit No.2) | Mon Mar 12 08:00:00 IST 2018 | Mon Mar 12 16:00:00 IST 2018 | Fri Jan 12 08:00:00 IST 2018 | Fri Jan 12 16:00:00 IST 2018 |  | COMPLETED
2867 | TT_TASK | Exhaust Stack - Strike formwork | Tue Mar 13 08:00:00 IST 2018 | Tue Mar 13 16:00:00 IST 2018 | Sat Jan 13 08:00:00 IST 2018 | Sat Jan 13 16:00:00 IST 2018 |  | COMPLETED
2869 | TT_TASK | HRSG - Cast vertical blinding to the profile of caps and beams | Thu Dec 28 08:00:00 IST 2017 | Tue Jan 02 16:00:00 IST 2018 | Sat Dec 02 08:00:00 IST 2017 | Fri Dec 08 16:00:00 IST 2017 |  | COMPLETED
2870 | TT_TASK | HRSG - Trim pile and prepare pile head | Fri Nov 24 08:00:00 IST 2017 | Tue Dec 12 16:00:00 IST 2017 | Tue Sep 26 08:00:00 IDT 2017 | Sun Nov 19 00:00:00 IST 2017 |  | COMPLETED
2871 | TT_TASK | HRSG - Capping plate and rebar starter | Sat Nov 25 08:00:00 IST 2017 | Wed Dec 13 16:00:00 IST 2017 | Fri Sep 29 08:00:00 IDT 2017 | Thu Nov 30 16:00:00 IST 2017 |  | COMPLETED
2872 | TT_TASK | HRSG - Fix rebar and install cast-in /embed items (Part 1 of 2) | Wed Jan 03 08:00:00 IST 2018 | Fri Jan 12 16:00:00 IST 2018 | Sat Dec 02 08:00:00 IST 2017 | Sat Jan 13 16:00:00 IST 2018 |  | COMPLETED
2873 | TT_TASK | HRSG - Pour pile cap (Part 1 of 2) | Tue Mar 13 08:00:00 IST 2018 | Tue Mar 13 16:00:00 IST 2018 | Mon Jan 15 08:00:00 IST 2018 | Mon Jan 15 16:00:00 IST 2018 |  | COMPLETED
2874 | TT_TASK | HRSG - Fix rebar and install cast-in /embed items (Part 2 of 2) | Tue Mar 13 08:00:00 IST 2018 | Wed Mar 14 16:00:00 IST 2018 | Wed Jan 24 08:00:00 IST 2018 | Tue Jan 30 16:00:00 IST 2018 |  | COMPLETED
2875 | TT_TASK | HRSG - Pour pile cap (Part 2 of 2) | Thu Mar 15 08:00:00 IST 2018 | Thu Mar 15 16:00:00 IST 2018 | Wed Jan 31 08:00:00 IST 2018 | Wed Jan 31 16:00:00 IST 2018 |  | COMPLETED
2882 | TT_TASK | Pipe Rack 01 - Foundation and Plinths | Tue Apr 09 08:00:00 IDT 2019 | Tue May 07 16:00:00 IDT 2019 | Sat Feb 23 08:00:00 IST 2019 | Thu Mar 07 16:00:00 IST 2019 |  | COMPLETED
2884 | TT_TASK | DW06 - Construct Metal Fence and Removal Shelter at Transformer Area | Fri Jan 10 08:00:00 IST 2020 | Tue Mar 10 16:00:00 IST 2020 | Tue Oct 15 08:00:00 IDT 2019 | Fri Dec 20 16:00:00 IST 2019 |  | COMPLETED
2885 | TT_TASK | Event 039(TX) - Power Island Phase 4 /5 resequencing amendment | Mon Nov 26 08:00:00 IST 2018 | Tue Dec 25 16:00:00 IST 2018 | Mon Oct 15 08:00:00 IDT 2018 | Mon Nov 12 16:00:00 IST 2018 |  | COMPLETED
2886 | TT_TASK | Event 039(TX) - BA8 consent for Phase 5 excavation [APPROVAL DEEMED] | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Tue Dec 11 08:00:00 IST 2018 | Mon Jan 07 16:00:00 IST 2019 |  | COMPLETED
2887 | TT_TASK | Event 039(TX) - MV Aux.TX / open cut to the required formation level w/ a berm 5m wide at Zone A north PPW | Sat Jan 26 08:00:00 IST 2019 | Wed Jan 30 16:00:00 IST 2019 | Fri Nov 30 08:00:00 IST 2018 | Sun Dec 02 16:00:00 IST 2018 |  | COMPLETED
2888 | TT_TASK | Event 039(TX) - MV Aux.TX / conduct plate load test PL4 | Thu Jan 31 08:00:00 IST 2019 | Fri Feb 15 16:00:00 IST 2019 | Mon Dec 03 08:00:00 IST 2018 | Thu Dec 13 16:00:00 IST 2018 |  | COMPLETED
2889 | TT_TASK | Event 039(TX) - MV Aux.TX / construct foundation CT11-FT1 (Part 1 of 2) | Sat Feb 16 08:00:00 IST 2019 | Tue Feb 26 16:00:00 IST 2019 | Fri Dec 14 08:00:00 IST 2018 | Sat Jan 12 16:00:00 IST 2019 |  | COMPLETED
2890 | TT_TASK | Event 039(TX) - MV Aux.TX / construct pit wall to +6.15 and plinth PL3 | Wed Feb 27 08:00:00 IST 2019 | Fri Mar 08 16:00:00 IST 2019 | Sun Jan 13 08:00:00 IST 2019 | Thu Jan 24 16:00:00 IST 2019 |  | COMPLETED
2891 | TT_TASK | Event 039(TX) - MV Aux.TX / construct fire wall to +11.55 and corbels at G.L.AA | Thu Jan 31 08:00:00 IST 2019 | Wed Feb 20 16:00:00 IST 2019 | Fri Jan 25 08:00:00 IST 2019 | Mon Feb 04 16:00:00 IST 2019 |  | COMPLETED
2892 | TT_TASK | Event 039(TX) - MV Aux.TX / apply hardener | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 02 16:00:00 IDT 2019 | Sat Feb 16 08:00:00 IST 2019 | Mon Feb 18 16:00:00 IST 2019 |  | COMPLETED
2894 | TT_TASK | Event 039(TX) - Start-up TX / backfill to the required formation | Thu Jan 31 08:00:00 IST 2019 | Mon Feb 04 16:00:00 IST 2019 | Wed Jan 02 08:00:00 IST 2019 | Mon Jan 07 16:00:00 IST 2019 |  | COMPLETED
2895 | TT_TASK | Event 039(TX) - Start-up TX / construct foundation CT12-FT1 | Sat Jan 26 08:00:00 IST 2019 | Tue Feb 12 16:00:00 IST 2019 | Sat Jan 12 08:00:00 IST 2019 | Tue Jan 22 16:00:00 IST 2019 |  | COMPLETED
2896 | TT_TASK | Event 039(TX) - Start-up TX / construct plinth PL1 & PL2 | Wed Feb 13 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Thu Jan 24 08:00:00 IST 2019 | Wed Jan 30 16:00:00 IST 2019 |  | COMPLETED
2897 | TT_TASK | Event 039(TX) - Start-up TX / apply hardener | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 02 16:00:00 IDT 2019 | Tue Feb 12 08:00:00 IST 2019 | Wed Feb 13 16:00:00 IST 2019 |  | COMPLETED
2899 | TT_TASK | Generator TX - Further excavate from +4.2 to the required formation level | Mon Feb 04 08:00:00 IST 2019 | Tue Feb 12 16:00:00 IST 2019 | Mon Jan 07 08:00:00 IST 2019 | Mon Jan 07 16:00:00 IST 2019 |  | COMPLETED
2900 | TT_TASK | Generator TX - Cast vertical blinding | Mon Feb 04 08:00:00 IST 2019 | Thu Feb 14 16:00:00 IST 2019 | Sat Jan 05 08:00:00 IST 2019 | Mon Jan 07 16:00:00 IST 2019 |  | COMPLETED
2901 | TT_TASK | Generator TX - Construct base slabs | Fri Feb 15 08:00:00 IST 2019 | Thu Feb 28 16:00:00 IST 2019 | Tue Jan 08 08:00:00 IST 2019 | Sat Jan 12 16:00:00 IST 2019 |  | COMPLETED
2902 | TT_TASK | Generator TX - Construct equipment plinths | Mon Feb 04 08:00:00 IST 2019 | Wed Feb 13 16:00:00 IST 2019 | Sun Jan 13 08:00:00 IST 2019 | Fri Jan 25 16:00:00 IST 2019 |  | COMPLETED
2903 | TT_TASK | Generator TX - Construct concrete blast walls | Mon Feb 04 08:00:00 IST 2019 | Wed Feb 20 16:00:00 IST 2019 | Tue Jan 22 08:00:00 IST 2019 | Tue Feb 12 16:00:00 IST 2019 |  | COMPLETED
2905 | TT_TASK | M&E Works by Others #8 - Erect Transformers and dress out (indicative only) | Thu May 02 08:00:00 IDT 2019 | Sat Aug 31 16:00:00 IDT 2019 | Mon Mar 11 08:00:00 IST 2019 | Mon Oct 14 16:00:00 IDT 2019 |  | COMPLETED
2907 | TT_TASK | Duct Bank between Switchgear Blk & Gen.TX - Construct drawpit BS01, BS03, BS04, BS05 | Fri Mar 08 08:00:00 IST 2019 | Thu Mar 14 16:00:00 IST 2019 | Fri Oct 12 08:00:00 IDT 2018 | Fri Jan 25 16:00:00 IST 2019 |  | COMPLETED
2908 | TT_TASK | Duct Bank between Switchgear Blk & Gen.TX - Install cable ducting with concrete surround | Fri Mar 15 08:00:00 IST 2019 | Thu Mar 28 16:00:00 IST 2019 | Tue Nov 06 08:00:00 IST 2018 | Tue Feb 12 16:00:00 IST 2019 |  | COMPLETED
2910 | TT_TASK | Boiler Blow Down Pit - Further excavate from +4.2 to the final formation level | Tue Jun 26 08:00:00 IDT 2018 | Thu Jun 28 16:00:00 IDT 2018 | Mon May 28 08:00:00 IDT 2018 | Sat Jun 02 16:00:00 IDT 2018 |  | COMPLETED
2911 | TT_TASK | Boiler Blow Down Pit - Cast vertical blinding to the profile of base slab and shallow ppit | Thu Aug 02 08:00:00 IDT 2018 | Mon Aug 06 16:00:00 IDT 2018 | Wed Jul 04 08:00:00 IDT 2018 | Sat Jul 14 16:00:00 IDT 2018 |  | COMPLETED
2912 | TT_TASK | Boiler Blow Down Pit - Install waterproofing | Thu Jul 26 08:00:00 IDT 2018 | Fri Jul 27 16:00:00 IDT 2018 | Thu Jul 12 08:00:00 IDT 2018 | Sat Jul 14 16:00:00 IDT 2018 |  | COMPLETED
2913 | TT_TASK | Boiler Blow Down Pit - Fix bottom layer rebar | Sat Jul 28 08:00:00 IDT 2018 | Tue Aug 07 16:00:00 IDT 2018 | Mon Jul 16 08:00:00 IDT 2018 | Sat Jul 21 16:00:00 IDT 2018 |  | COMPLETED
2914 | TT_TASK | Boiler Blow Down Pit - Close formwork (if any) | Mon Sep 03 08:00:00 IDT 2018 | Mon Sep 03 16:00:00 IDT 2018 | Thu Aug 09 08:00:00 IDT 2018 | Thu Aug 09 16:00:00 IDT 2018 |  | COMPLETED
2915 | TT_TASK | Boiler Blow Down Pit - Pour base slab and shallow pit | Tue Sep 04 08:00:00 IDT 2018 | Tue Sep 04 16:00:00 IDT 2018 | Fri Aug 10 08:00:00 IDT 2018 | Fri Aug 10 16:00:00 IDT 2018 |  | COMPLETED
2916 | TT_TASK | Boiler Blow Down Pit - Prepare CJ | Thu Sep 06 08:00:00 IDT 2018 | Thu Sep 06 16:00:00 IDT 2018 | Sat Aug 11 08:00:00 IDT 2018 | Sat Aug 11 16:00:00 IDT 2018 |  | COMPLETED
2917 | TT_TASK | Boiler Blow Down Pit - Erect wall and column formwork | Mon Aug 27 08:00:00 IDT 2018 | Thu Aug 30 16:00:00 IDT 2018 | Thu Jul 26 08:00:00 IDT 2018 | Sat Jul 28 16:00:00 IDT 2018 |  | COMPLETED
2918 | TT_TASK | Boiler Blow Down Pit - Fix upper layer rebar | Thu Aug 30 08:00:00 IDT 2018 | Sat Sep 01 16:00:00 IDT 2018 | Sat Aug 04 08:00:00 IDT 2018 | Tue Aug 07 16:00:00 IDT 2018 |  | COMPLETED
2919 | TT_TASK | Boiler Blow Down Pit - Close wall formwork | Fri Aug 31 08:00:00 IDT 2018 | Mon Sep 03 16:00:00 IDT 2018 | Mon Aug 06 08:00:00 IDT 2018 | Thu Aug 09 16:00:00 IDT 2018 |  | COMPLETED
2920 | TT_TASK | Boiler Blow Down Pit- Pour walls and columns to the underside of Feedwater Platform slab | Tue Sep 04 08:00:00 IDT 2018 | Tue Sep 04 16:00:00 IDT 2018 | Fri Aug 10 08:00:00 IDT 2018 | Fri Aug 10 16:00:00 IDT 2018 |  | COMPLETED
2921 | TT_TASK | Boiler Blow Down Pit - Curing | Wed Sep 05 08:00:00 IDT 2018 | Tue Sep 11 16:00:00 IDT 2018 | Sat Aug 11 08:00:00 IDT 2018 | Fri Aug 17 16:00:00 IDT 2018 |  | COMPLETED
2922 | TT_TASK | Boiler Blow Down Pit - Apply waterproofing to the external face of pit wall | Tue Aug 21 08:00:00 IDT 2018 | Thu Aug 23 16:00:00 IDT 2018 | Thu Jul 12 08:00:00 IDT 2018 | Sat Jul 14 16:00:00 IDT 2018 |  | COMPLETED
2923 | TT_TASK | Boiler Blow Down Pit - Backfill againt basement wall | Thu Jul 26 08:00:00 IDT 2018 | Fri Jul 27 16:00:00 IDT 2018 | Sat Jun 30 08:00:00 IDT 2018 | Tue Jul 03 16:00:00 IDT 2018 |  | COMPLETED
2925 | TT_TASK | Event 015 - HRSG West occupied by M&E Contract for HRSG Erection | Mon Apr 23 08:00:00 IDT 2018 | Sun Jun 03 16:00:00 IDT 2018 | Wed Mar 07 08:00:00 IST 2018 | Fri May 25 16:00:00 IDT 2018 |  | COMPLETED
2926 | TT_TASK | Event 015 - Remob, excavation, earthing, backfill to formation levels, set-up for plate load test | Tue Jun 26 08:00:00 IDT 2018 | Tue Jul 10 16:00:00 IDT 2018 | Sat May 26 08:00:00 IDT 2018 | Sat Jun 09 16:00:00 IDT 2018 |  | COMPLETED
2927 | TT_TASK | Event 015 - Clarification on plate load test requirements and invitation for BD inspection | Tue Jun 26 08:00:00 IDT 2018 | Tue Jun 26 16:00:00 IDT 2018 | Sun Jun 10 08:00:00 IDT 2018 | Wed Jun 20 16:00:00 IDT 2018 |  | COMPLETED
2928 | TT_TASK | Event 019 - Plate Load Test Set Up | Wed Feb 28 08:00:00 IST 2018 | Tue Mar 06 16:00:00 IST 2018 | Fri Feb 09 08:00:00 IST 2018 | Tue Feb 13 16:00:00 IST 2018 |  | COMPLETED
2930 | TT_TASK | Event 019 - Plate Load Test ( x2 nos) | Wed Aug 01 08:00:00 IDT 2018 | Tue Aug 14 16:00:00 IDT 2018 | Thu Jun 21 08:00:00 IDT 2018 | Mon Jun 25 16:00:00 IDT 2018 |  | COMPLETED
2931 | TT_TASK | Event 019 - Photo records for foundation dimension set-out | Thu Jul 26 08:00:00 IDT 2018 | Sun Jul 29 16:00:00 IDT 2018 | Tue Jun 26 08:00:00 IDT 2018 | Fri Jun 29 16:00:00 IDT 2018 |  | COMPLETED
2932 | TT_TASK | Event 035 - CLP allocated space for relocation of rebar yard | Thu Jul 26 08:00:00 IDT 2018 | Thu Jul 26 16:00:00 IDT 2018 | Mon Jul 16 08:00:00 IDT 2018 | Wed Jul 25 16:00:00 IDT 2018 |  | COMPLETED
2935 | TT_TASK | FW Platform - Construct base slab GL.K-S (= Pipe Bridge) | Thu Jul 26 08:00:00 IDT 2018 | Thu Sep 27 16:00:00 IDT 2018 | Sat Jun 30 08:00:00 IDT 2018 | Thu Aug 23 16:00:00 IDT 2018 |  | COMPLETED
2936 | TT_TASK | FW Platform - Construct base slab GL.S-V (= Feedwater Platform) | Fri Aug 31 08:00:00 IDT 2018 | Thu Oct 11 16:00:00 IDT 2018 | Mon Jul 30 08:00:00 IDT 2018 | Mon Oct 08 16:00:00 IDT 2018 |  | COMPLETED
2937 | TT_TASK | FW Platform - Construct plinths for FW Pump, Con.Recirculation Pump, Sampling Skid, Amonnia & Phosphate Dosing Container | Mon Aug 27 08:00:00 IDT 2018 | Thu Sep 13 16:00:00 IDT 2018 | Fri Aug 24 08:00:00 IDT 2018 | Sat Oct 27 16:00:00 IDT 2018 |  | COMPLETED
2938 | TT_TASK | FW Platform - Construct of remaining Feedwater Platform foundation and plinth | Mon Nov 26 08:00:00 IST 2018 | Sat Dec 15 16:00:00 IST 2018 | Thu Nov 15 08:00:00 IST 2018 | Mon Dec 31 16:00:00 IST 2018 |  | COMPLETED
2941 | TT_TASK | LV Aux. Power TX - Construct 600mm deep foundation | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 09 16:00:00 IDT 2019 | Tue Jan 29 08:00:00 IST 2019 | Mon Feb 04 16:00:00 IST 2019 |  | COMPLETED
2943 | TT_TASK | RW Collection Pump Rm - Stratum Requirement (ROI#182) | Mon Nov 26 08:00:00 IST 2018 | Wed Dec 12 16:00:00 IST 2018 | Wed Oct 10 08:00:00 IDT 2018 | Fri Oct 26 16:00:00 IDT 2018 |  | COMPLETED
2944 | TT_TASK | RW Collection Pump Rm - Install re-prop below S1 as per Zone A (4th) amendment | Sat Feb 16 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Wed Dec 05 08:00:00 IST 2018 | Sat Dec 15 16:00:00 IST 2018 |  | COMPLETED
2946 | TT_TASK | RW Collection Pump Rm - Vertical blinding to the profile of base slab and shallow sump pit | Mon Nov 26 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Wed Oct 31 00:00:00 IST 2018 | Wed Oct 31 00:00:00 IST 2018 |  | COMPLETED
2947 | TT_TASK | RW Collection Pump Rm - Install waterproofing [confirmed not required] | Mon Nov 26 08:00:00 IST 2018 | Tue Nov 27 16:00:00 IST 2018 | Wed Oct 31 08:00:00 IST 2018 | Wed Oct 31 16:00:00 IST 2018 |  | COMPLETED
2948 | TT_TASK | RW Collection Pump Rm - Fix rebar for base slab and shallow pits | Wed Nov 28 08:00:00 IST 2018 | Sat Dec 01 16:00:00 IST 2018 | Thu Nov 01 08:00:00 IST 2018 | Wed Nov 07 16:00:00 IST 2018 |  | COMPLETED
2949 | TT_TASK | RW Collection Pump Rm - Close formwork (if any) | Mon Dec 03 08:00:00 IST 2018 | Mon Dec 03 16:00:00 IST 2018 | Sat Nov 03 08:00:00 IST 2018 | Wed Nov 07 16:00:00 IST 2018 |  | COMPLETED
2950 | TT_TASK | RW Collection Pump Rm - Pour base slab and shallow pit | Tue Dec 04 08:00:00 IST 2018 | Tue Dec 04 16:00:00 IST 2018 | Thu Nov 08 08:00:00 IST 2018 | Thu Nov 08 16:00:00 IST 2018 |  | COMPLETED
2951 | TT_TASK | RW Collection Pump Rm - Prepare CJ | Wed Nov 28 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 | Fri Nov 09 08:00:00 IST 2018 | Fri Nov 09 16:00:00 IST 2018 |  | COMPLETED
2952 | TT_TASK | RW Collection Pump Rm - Erect formwork for basement wall and staircase (Part 1 of 2) | Thu Nov 29 08:00:00 IST 2018 | Mon Dec 03 16:00:00 IST 2018 | Wed Nov 14 08:00:00 IST 2018 | Fri Nov 16 16:00:00 IST 2018 |  | COMPLETED
2953 | TT_TASK | RW Collection Pump Rm - Fix rebar for basement wall and staircase (Part 1 of 2) | Sat Dec 01 08:00:00 IST 2018 | Wed Dec 05 16:00:00 IST 2018 | Fri Nov 16 08:00:00 IST 2018 | Thu Nov 22 16:00:00 IST 2018 |  | COMPLETED
2954 | TT_TASK | RW Collection Pump Rm - Close wall formwork (Part 1 of 2) | Mon Nov 26 08:00:00 IST 2018 | Mon Nov 26 16:00:00 IST 2018 | Fri Nov 23 08:00:00 IST 2018 | Wed Nov 28 16:00:00 IST 2018 |  | COMPLETED
2955 | TT_TASK | RW Collection Pump Rm - Pour basement wall and staircase (Part 1 of 2) | Mon Jan 28 08:00:00 IST 2019 | Mon Jan 28 16:00:00 IST 2019 | Thu Nov 29 08:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 |  | COMPLETED
2956 | TT_TASK | RW Collection Pump Rm - Erect formwork for basement wall and staircase (Part 2 of 2) | Fri Feb 15 08:00:00 IST 2019 | Tue Feb 19 16:00:00 IST 2019 | Sun Dec 16 08:00:00 IST 2018 | Sun Dec 23 16:00:00 IST 2018 |  | COMPLETED
2957 | TT_TASK | RW Collection Pump Rm - Fix rebar for basement wall and staircase (Part 2 of 2) | Mon Feb 18 08:00:00 IST 2019 | Thu Feb 21 16:00:00 IST 2019 | Fri Dec 21 08:00:00 IST 2018 | Sat Jan 05 16:00:00 IST 2019 |  | COMPLETED
2958 | TT_TASK | RW Collection Pump Rm - Close wall formwork (Part 2 of 2) | Thu Feb 21 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Fri Jan 04 08:00:00 IST 2019 | Sun Jan 06 16:00:00 IST 2019 |  | COMPLETED
2959 | TT_TASK | RW Collection Pump Rm - Pour basement wall and staircase (Part 2 of 2) | Sat Feb 23 08:00:00 IST 2019 | Sat Feb 23 16:00:00 IST 2019 | Mon Jan 07 08:00:00 IST 2019 | Mon Jan 07 16:00:00 IST 2019 |  | COMPLETED
2960 | TT_TASK | RW Collection Pump Rm - Curing | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 01 16:00:00 IST 2019 | Tue Jan 08 08:00:00 IST 2019 | Mon Jan 14 16:00:00 IST 2019 |  | COMPLETED
2961 | TT_TASK | RW Collection Pump Rm - Apply waterproofing to the external face of basement wall [confirmed not required] | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 02 16:00:00 IDT 2019 | Thu Nov 29 16:00:00 IST 2018 | Thu Nov 29 16:00:00 IST 2018 |  | COMPLETED
2962 | TT_TASK | RW Collection Pump Rm - Backfill againt basement wall | Mon Feb 04 08:00:00 IST 2019 | Thu Feb 14 16:00:00 IST 2019 | Mon Dec 17 08:00:00 IST 2018 | Sat Dec 22 16:00:00 IST 2018 |  | COMPLETED
2963 | TT_TASK | RW Collection Pump Rm - Construct Irrigation Tank and Rainwater Collection Tank structure | Mon Apr 01 08:00:00 IDT 2019 | Mon May 27 16:00:00 IDT 2019 | Sat Mar 09 08:00:00 IST 2019 | Sat Aug 17 16:00:00 IDT 2019 |  | COMPLETED
2964 | TT_TASK | RW Collection Pump Rm - Falsework and formwork to top slab | Sat Mar 16 08:00:00 IST 2019 | Mon Mar 18 16:00:00 IST 2019 | Sun Dec 16 08:00:00 IST 2018 | Sun Dec 23 16:00:00 IST 2018 |  | COMPLETED
2965 | TT_TASK | RW Collection Pump Rm - Fix rebar | Tue Mar 19 08:00:00 IST 2019 | Thu Mar 21 16:00:00 IST 2019 | Fri Dec 21 08:00:00 IST 2018 | Sat Jan 05 16:00:00 IST 2019 |  | COMPLETED
2966 | TT_TASK | RW Collection Pump Rm - Pour top slab | Fri Mar 22 08:00:00 IST 2019 | Fri Mar 22 16:00:00 IST 2019 | Mon Jan 07 08:00:00 IST 2019 | Mon Jan 07 16:00:00 IST 2019 |  | COMPLETED
2967 | TT_TASK | RW Collection Pump Rm - Construct remaining staircase structure abovehground | Mon Sep 16 08:00:00 IDT 2019 | Mon Oct 14 16:00:00 IDT 2019 | Mon Aug 19 08:00:00 IDT 2019 | Tue Sep 24 16:00:00 IDT 2019 |  | COMPLETED
2968 | TT_TASK | RW Collection Pump Rm - Construct footing for Emergency Power Generator on top slab (relocated to adj. Shaft F) | Mon Apr 01 08:00:00 IDT 2019 | Thu Apr 18 16:00:00 IDT 2019 | Mon Mar 18 08:00:00 IST 2019 | Tue Jul 02 16:00:00 IDT 2019 |  | COMPLETED
2969 | TT_TASK | RW Collection Pump Rm - ABWF works to pump room and water tanks | Thu Jan 02 08:00:00 IST 2020 | Mon Feb 17 16:00:00 IST 2020 | Wed Sep 25 08:00:00 IDT 2019 | Tue Dec 31 16:00:00 IST 2019 |  | COMPLETED
2970 | TT_TASK | RW Collection Pump Rm - Building Services installation | Thu Jan 02 08:00:00 IST 2020 | Mon Feb 17 16:00:00 IST 2020 | Thu Aug 22 08:00:00 IDT 2019 | Fri Jan 24 16:00:00 IST 2020 |  | COMPLETED
2972 | TT_TASK | Irrigation System - Plant room installation inside RW Collection Pump Rm | Tue Feb 04 08:00:00 IST 2020 | Thu Mar 12 16:00:00 IST 2020 | Sun Oct 20 08:00:00 IDT 2019 | Fri Jan 24 16:00:00 IST 2020 |  | COMPLETED
2973 | TT_TASK | Irrigation System - Water supply pipeline from the water cabinet | Fri Aug 09 08:00:00 IDT 2019 | Thu Sep 05 16:00:00 IDT 2019 | Mon Apr 29 08:00:00 IDT 2019 | Mon Sep 30 16:00:00 IDT 2019 |  | COMPLETED
2974 | TT_TASK | Irrigation System - Distribution pipeline installation along the east perimeter of HRSG Area | Thu Jan 02 08:00:00 IST 2020 | Wed Jan 15 16:00:00 IST 2020 | Thu Dec 19 08:00:00 IST 2019 | Fri Jan 17 16:00:00 IST 2020 |  | COMPLETED
2975 | TT_TASK | Irrigation System - Distribution pipeline installation along the perimeter of Turbine Hall | Wed Feb 19 08:00:00 IST 2020 | Tue Mar 03 16:00:00 IST 2020 | Mon Jul 22 08:00:00 IDT 2019 | Wed Dec 18 16:00:00 IST 2019 |  | COMPLETED
2976 | TT_TASK | Irrigation System - Distribution pipeline installation to the northern side of HRSG Area | Wed Jan 15 08:00:00 IST 2020 | Fri Jan 24 16:00:00 IST 2020 | Wed Jan 15 08:00:00 IST 2020 | Fri Jan 24 16:00:00 IST 2020 |  | COMPLETED
2978 | TT_TASK | Event 041 - Crane access for KSS (original thought was three months) | Mon Nov 26 08:00:00 IST 2018 | Sat Feb 23 16:00:00 IST 2019 | Fri Sep 07 08:00:00 IDT 2018 | Mon Apr 15 16:00:00 IDT 2019 |  | COMPLETED
2979 | TT_TASK | Gas Final Filter Equip - Construct 1.1m deep foundation | Thu May 02 08:00:00 IDT 2019 | Mon May 27 16:00:00 IDT 2019 | Thu Apr 18 08:00:00 IDT 2019 | Sat May 04 16:00:00 IDT 2019 |  | COMPLETED
2980 | TT_TASK | Gas Final Filter Equip - Construct 1m high bund wall all around | Wed Jun 05 08:00:00 IDT 2019 | Thu Jun 20 16:00:00 IDT 2019 | Mon May 06 08:00:00 IDT 2019 | Mon Sep 02 16:00:00 IDT 2019 |  | COMPLETED
2981 | TT_TASK | Gas Final Filter Equip - Erect wire mesh security fence after filter install | Thu Jan 02 08:00:00 IST 2020 | Wed Jan 15 16:00:00 IST 2020 | Sat Oct 12 08:00:00 IDT 2019 | Fri Oct 18 16:00:00 IDT 2019 |  | COMPLETED
2983 | TT_TASK | Close Cooling Water Structure - Construct foundation and plinths | Tue Apr 09 08:00:00 IDT 2019 | Mon Apr 29 16:00:00 IDT 2019 | Mon Feb 25 08:00:00 IST 2019 | Mon Mar 04 16:00:00 IST 2019 |  | COMPLETED
2987 | TT_TASK | Outdoor Pipe Trench - Construct pipe trench | Mon Apr 01 08:00:00 IDT 2019 | Sat Apr 13 16:00:00 IDT 2019 | Sat Feb 02 08:00:00 IST 2019 | Thu Feb 14 16:00:00 IST 2019 |  | COMPLETED
2991 | TT_TASK | Construct footings of False Start & GT Water Tank to the South of HRSG | Mon Apr 01 08:00:00 IDT 2019 | Sat May 18 16:00:00 IDT 2019 | Wed Mar 20 08:00:00 IST 2019 | Fri Apr 12 16:00:00 IDT 2019 |  | COMPLETED
2992 | TT_TASK | Construct footings of Urea Decomposition Chamber to the East of HRSG | Thu Aug 01 08:00:00 IDT 2019 | Mon Aug 26 16:00:00 IDT 2019 | Mon Jun 03 08:00:00 IDT 2019 | Sat Jun 29 16:00:00 IDT 2019 |  | COMPLETED
2996 | TT_TASK | Fuel Gas Purger Air, GRS & Fuel Gas Blending - Underground drainage | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 15 16:00:00 IST 2019 | Sat Jan 05 08:00:00 IST 2019 | Wed Jan 16 16:00:00 IST 2019 |  | COMPLETED
2997 | TT_TASK | Fuel Gas Purge Air System - Construct foundation | Sat Feb 16 08:00:00 IST 2019 | Fri Mar 01 16:00:00 IST 2019 | Thu Jan 17 08:00:00 IST 2019 | Tue Jan 29 16:00:00 IST 2019 |  | COMPLETED
2998 | TT_TASK | Gas Receiving & Fuel Gas Blending Station - Construct foundation | Mon Jan 28 08:00:00 IST 2019 | Sat Feb 09 16:00:00 IST 2019 | Thu Jan 17 08:00:00 IST 2019 | Tue Jan 29 16:00:00 IST 2019 |  | COMPLETED
2999 | TT_TASK | Gas Receiving & Fuel Gas Blending Station - Construct fire wall | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 08 16:00:00 IST 2019 | Thu Jan 17 08:00:00 IST 2019 | Tue Jan 29 16:00:00 IST 2019 |  | COMPLETED
3000 | TT_TASK | Gas Receiving & Fuel Gas Blending Station - Erect wire mech fence | Thu Jan 02 08:00:00 IST 2020 | Sat Jan 11 16:00:00 IST 2020 | Mon Oct 28 08:00:00 IST 2019 | Wed Oct 30 16:00:00 IST 2019 |  | COMPLETED
3003 | TT_TASK | Event 049 / Urea Facilities / Set up and conduct plate load test no. PL1 | Sat Jan 26 08:00:00 IST 2019 | Sat Jan 26 16:00:00 IST 2019 | Sun Dec 09 08:00:00 IST 2018 | Thu Dec 13 16:00:00 IST 2018 |  | COMPLETED
3004 | TT_TASK | Construct footings for Chemical Unloading Bay and Urea Factilities | Sat Jan 26 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Fri Dec 14 08:00:00 IST 2018 | Fri Jan 11 16:00:00 IST 2019 |  | COMPLETED
3007 | TT_TASK | Works in Existing Central Control Room in Control Block Building and Associated Works (indicative only, TBC) | Mon Feb 03 08:00:00 IST 2020 | Sat Feb 22 16:00:00 IST 2020 | Mon Feb 03 08:00:00 IST 2020 | Sat Feb 22 16:00:00 IST 2020 |  | COMPLETED
3009 | TT_TASK | DW09 - Construct UG Neutralization Tank | Mon Nov 26 08:00:00 IST 2018 | Mon Dec 31 16:00:00 IST 2018 | Thu Nov 15 08:00:00 IST 2018 | Mon Dec 31 16:00:00 IST 2018 |  | COMPLETED
3010 | TT_TASK | DW10 - Final Reinstatement of Access Roads and Pavement at Turbine Hall and HRSG Area (i.e. wearing course) | Sat May 23 08:00:00 IDT 2020 | Thu May 28 16:00:00 IDT 2020 | Sat May 23 08:00:00 IDT 2020 | Thu May 28 16:00:00 IDT 2020 |  | COMPLETED
3013 | TT_TASK | Provide/Extend/Relocate Sitewide Drainage System | Mon Apr 01 08:00:00 IDT 2019 | Tue Aug 13 16:00:00 IDT 2019 | Mon Jul 16 08:00:00 IDT 2018 | Fri Jan 24 16:00:00 IST 2020 |  | COMPLETED
3019 | TT_TASK | Roadworks - Concrete Pavements | Thu Aug 01 08:00:00 IDT 2019 | Fri Sep 20 16:00:00 IDT 2019 | Mon Jul 22 08:00:00 IDT 2019 | Mon Sep 09 16:00:00 IDT 2019 |  | COMPLETED
3020 | TT_TASK | Roadworks - Road Marking and signs | Thu Jun 04 08:00:00 IDT 2020 | Thu Jun 11 16:00:00 IDT 2020 | Thu Jun 04 08:00:00 IDT 2020 | Thu Jun 11 16:00:00 IDT 2020 |  | COMPLETED
3021 | TT_TASK | Roadworks - Install Directonal Signage | Fri Jun 12 08:00:00 IDT 2020 | Tue Jun 30 16:00:00 IDT 2020 | Fri Jun 12 08:00:00 IDT 2020 | Tue Jun 30 16:00:00 IDT 2020 |  | COMPLETED
3022 | TT_TASK | Roadworks - Install Street Furniture | Fri Jun 12 08:00:00 IDT 2020 | Tue Jun 30 16:00:00 IDT 2020 | Fri Jun 12 08:00:00 IDT 2020 | Tue Jun 30 16:00:00 IDT 2020 |  | COMPLETED
3026 | TT_TASK | Irrigation Points | Sat Feb 01 08:00:00 IST 2020 | Fri Feb 14 16:00:00 IST 2020 | Sat Feb 01 08:00:00 IST 2020 | Fri Feb 14 16:00:00 IST 2020 |  | COMPLETED
3027 | TT_TASK | Grasscrete Around Building | Thu Jan 02 08:00:00 IST 2020 | Wed Feb 12 16:00:00 IST 2020 | Mon Jul 22 08:00:00 IDT 2019 | Wed Dec 18 16:00:00 IST 2019 |  | COMPLETED
3031 | TT_TASK | Utility and Gas Trenches (as per drawing ref. BPB /OARU /GA /1 /VAA /D1 /161 Rev.4) | Sat Jan 26 08:00:00 IST 2019 | Sat Apr 13 16:00:00 IDT 2019 | Wed Dec 12 08:00:00 IST 2018 | Thu Feb 14 16:00:00 IST 2019 |  | COMPLETED
3032 | TT_TASK | Sleeperways (as per drawing ref. BPB /OARU /GA /1 /VAA /D1 /161 Rev.4) | Thu Aug 01 08:00:00 IDT 2019 | Tue Aug 20 16:00:00 IDT 2019 | Sat Jul 06 08:00:00 IDT 2019 | Thu Aug 22 16:00:00 IDT 2019 |  | COMPLETED
3257 | TT_TASK | Submission and Approval - Purchase Orders to Sub-contractors of Crane Barges (e.g. for lifts greater than 300t) | Thu Mar 01 08:00:00 IST 2018 | Fri Mar 16 10:00:00 IST 2018 | Tue Jan 30 08:00:00 IST 2018 | Wed Feb 14 18:00:00 IST 2018 |  | COMPLETED
3258 | TT_TASK | Submission and Approval - Purchase Orders to Sub-contractors of Land based cranes (e.g. for large lifts between 50-300t) | Thu Mar 01 08:00:00 IST 2018 | Fri Mar 16 10:00:00 IST 2018 | Tue Jan 30 08:00:00 IST 2018 | Fri Feb 09 18:00:00 IST 2018 |  | COMPLETED
3259 | TT_TASK | Submission and Approval - Insurance certificates and policy documentation | Thu Feb 01 08:00:00 IST 2018 | Wed Feb 21 13:00:00 IST 2018 | Wed Nov 01 08:00:00 IST 2017 | Fri Nov 17 18:00:00 IST 2017 |  | COMPLETED
3260 | TT_TASK | Submission and Approval - Construction Execution Plan | Thu Feb 01 08:00:00 IST 2018 | Wed Feb 21 13:00:00 IST 2018 | Fri Nov 17 08:00:00 IST 2017 | Mon Feb 26 18:00:00 IST 2018 |  | COMPLETED
3261 | TT_TASK | Submission and Approval - SHHE Plans | Thu Feb 01 08:00:00 IST 2018 | Wed Feb 21 13:00:00 IST 2018 | Fri Nov 17 08:00:00 IST 2017 | Mon Feb 26 18:00:00 IST 2018 |  | COMPLETED
3262 | TT_TASK | Submission and Approval - Material Management Plan | Thu Feb 01 08:00:00 IST 2018 | Wed Feb 21 13:00:00 IST 2018 | Sun Dec 17 08:00:00 IST 2017 | Sun Dec 17 18:00:00 IST 2017 |  | COMPLETED
3263 | TT_TASK | Submission and Approval - Project Quality Plan | Thu Feb 01 08:00:00 IST 2018 | Wed Feb 21 13:00:00 IST 2018 | Mon Jan 08 08:00:00 IST 2018 | Mon Jan 08 18:00:00 IST 2018 |  | COMPLETED
3264 | TT_TASK | Submission and Approval - Quality Assurance System Manual | Thu Feb 01 08:00:00 IST 2018 | Wed Feb 21 13:00:00 IST 2018 | Mon Jan 08 08:00:00 IST 2018 | Mon Jan 08 18:00:00 IST 2018 |  | COMPLETED
3361 | TT_TASK | Prepare RFQ Documentation | Wed Feb 28 08:00:00 IST 2018 | Wed Feb 28 18:00:00 IST 2018 | Wed Feb 28 08:00:00 IST 2018 | Tue Mar 20 18:00:00 IST 2018 |  | COMPLETED
3363 | TT_TASK | RFQ Process | Thu Mar 01 08:00:00 IST 2018 | Thu Mar 01 18:00:00 IST 2018 | Wed Feb 28 08:00:00 IST 2018 | Wed Feb 28 18:00:00 IST 2018 |  | COMPLETED
3364 | TT_TASK | Bid Technical Evaluation/Review Process | Thu Mar 01 08:00:00 IST 2018 | Thu Mar 01 18:00:00 IST 2018 | Wed Feb 28 08:00:00 IST 2018 | Wed Feb 28 18:00:00 IST 2018 |  | COMPLETED
3365 | TT_TASK | Negoitiations with Selected Sub-Contractor | Thu Mar 15 08:00:00 IST 2018 | Thu Mar 15 08:00:00 IST 2018 | Wed Feb 28 08:00:00 IST 2018 | Wed Feb 28 18:00:00 IST 2018 |  | COMPLETED
3367 | TT_TASK | Subcontractor Site Mobilization | Thu Mar 29 08:00:00 IDT 2018 | Thu Mar 29 18:00:00 IDT 2018 | Wed Feb 28 08:00:00 IST 2018 | Wed Feb 28 18:00:00 IST 2018 |  | COMPLETED
3368 | TT_TASK | Subcontractor Submittal/Approval of Required Documentation (QA/QC, Weld Procedures, HSE, Schedules) | Thu Mar 29 08:00:00 IDT 2018 | Thu Mar 29 18:00:00 IDT 2018 | Wed Feb 28 08:00:00 IST 2018 | Wed Feb 28 18:00:00 IST 2018 |  | COMPLETED
3371 | TT_TASK | Prepare RFQ Documentation | Thu Mar 01 08:00:00 IST 2018 | Wed Mar 21 18:00:00 IST 2018 | Wed Jan 24 08:00:00 IST 2018 | Tue Feb 13 18:00:00 IST 2018 |  | COMPLETED
3373 | TT_TASK | RFQ Process | Thu Mar 01 08:00:00 IST 2018 | Wed Mar 21 18:00:00 IST 2018 | Thu Feb 15 08:00:00 IST 2018 | Thu Mar 01 18:00:00 IST 2018 |  | COMPLETED
3374 | TT_TASK | Bid Technical Evaluation/Review Process | Thu Mar 22 08:00:00 IST 2018 | Mon Apr 09 18:00:00 IDT 2018 | Fri Mar 02 08:00:00 IST 2018 | Wed Mar 07 18:00:00 IST 2018 |  | COMPLETED
3375 | TT_TASK | Negoitiations with Selected Sub-Contractor | Tue Apr 10 08:00:00 IDT 2018 | Fri Apr 20 18:00:00 IDT 2018 | Thu Mar 08 08:00:00 IST 2018 | Mon Mar 12 18:00:00 IST 2018 |  | COMPLETED
3377 | TT_TASK | Subcontractor Site Mobilization | Tue Apr 24 08:00:00 IDT 2018 | Wed May 30 18:00:00 IDT 2018 | Wed Mar 14 08:00:00 IST 2018 | Sat Mar 31 06:00:00 IDT 2018 |  | COMPLETED
3378 | TT_TASK | Subcontractor Submittal/Approval of Required Documentation (QA/QC, Weld Procedures, HSE, Schedules) | Thu Mar 01 08:00:00 IST 2018 | Wed Mar 28 18:00:00 IDT 2018 | Wed Mar 14 08:00:00 IST 2018 | Wed Mar 28 18:00:00 IDT 2018 |  | COMPLETED
3381 | TT_TASK | Prepare RFQ Documentation | Thu Feb 01 08:00:00 IST 2018 | Sat Feb 24 18:00:00 IST 2018 | Mon Nov 06 08:00:00 IST 2017 | Fri Nov 24 18:00:00 IST 2017 |  | COMPLETED
3383 | TT_TASK | RFQ Process | Mon Feb 26 08:00:00 IST 2018 | Sat Mar 17 18:00:00 IST 2018 | Tue Nov 28 08:00:00 IST 2017 | Fri Dec 15 18:00:00 IST 2017 |  | COMPLETED
3384 | TT_TASK | Bid Technical Evaluation/Review Process | Tue Feb 13 08:00:00 IST 2018 | Thu Mar 01 18:00:00 IST 2018 | Mon Dec 18 08:00:00 IST 2017 | Wed Jan 03 18:00:00 IST 2018 |  | COMPLETED
3385 | TT_TASK | Negoitiations with Selected Sub-Contractor | Fri Mar 02 08:00:00 IST 2018 | Thu Mar 15 18:00:00 IST 2018 | Thu Jan 04 08:00:00 IST 2018 | Wed Jan 17 18:00:00 IST 2018 |  | COMPLETED
3387 | TT_TASK | HRSG Subcontractor Site Mobilization | Fri Mar 16 08:00:00 IST 2018 | Wed Mar 21 18:00:00 IST 2018 | Mon Feb 19 08:00:00 IST 2018 | Wed Mar 07 18:00:00 IST 2018 |  | COMPLETED
3388 | TT_TASK | HRSG Subcontractor Submittal/Approval of Required Documentation (QA/QC, Weld Procedures, HSE, Schedules) | Thu Feb 01 08:00:00 IST 2018 | Sat Mar 10 18:00:00 IST 2018 | Thu Jan 18 08:00:00 IST 2018 | Fri Mar 23 18:00:00 IDT 2018 |  | COMPLETED
3391 | TT_TASK | Site Mobilization (Pipe Fitter + Welder) | Wed Sep 05 08:00:00 IDT 2018 | Thu Oct 11 18:00:00 IDT 2018 | Thu Jun 28 08:00:00 IDT 2018 | Thu Jun 28 18:00:00 IDT 2018 |  | COMPLETED
3393 | TT_TASK | Prepare RFQ Documentation | Tue Jun 26 08:00:00 IDT 2018 | Tue Jul 17 18:00:00 IDT 2018 | Mon Apr 16 08:00:00 IDT 2018 | Sat Apr 21 18:00:00 IDT 2018 |  | COMPLETED
3395 | TT_TASK | RFQ Process | Wed Jul 18 08:00:00 IDT 2018 | Tue Aug 07 18:00:00 IDT 2018 | Mon Apr 23 08:00:00 IDT 2018 | Sat May 26 18:00:00 IDT 2018 |  | COMPLETED
3396 | TT_TASK | Bid Technical Evaluation/Review Process | Wed Aug 08 08:00:00 IDT 2018 | Tue Aug 21 18:00:00 IDT 2018 | Mon May 07 08:00:00 IDT 2018 | Wed May 16 18:00:00 IDT 2018 |  | COMPLETED
3397 | TT_TASK | Negotiations with Selected Sub-Contractor | Wed Aug 22 08:00:00 IDT 2018 | Tue Sep 04 18:00:00 IDT 2018 | Wed May 16 08:00:00 IDT 2018 | Sat May 26 18:00:00 IDT 2018 |  | COMPLETED
3399 | TT_TASK | Subcontractor Site Mobilization | Tue Oct 02 08:00:00 IDT 2018 | Mon Nov 05 18:00:00 IST 2018 | Wed Sep 26 00:00:00 IDT 2018 | Wed Oct 10 00:00:00 IDT 2018 |  | COMPLETED
3400 | TT_TASK | Subcontractor Submittal/Approval of Required Documentation (QA/QC, Weld Procedures, HSE, Schedules) | Thu Sep 06 13:00:00 IDT 2018 | Sat Oct 13 12:00:00 IDT 2018 | Wed Sep 05 00:00:00 IDT 2018 | Wed Dec 05 00:00:00 IST 2018 |  | COMPLETED
3403 | TT_TASK | Delivery of LV Transformer BFT01 (BHT) | Mon Dec 02 08:00:00 IST 2019 | Tue Dec 03 09:00:00 IST 2019 | Wed Mar 27 00:00:00 IST 2019 | Wed Mar 27 00:00:00 IST 2019 |  | COMPLETED
3404 | TT_TASK | Delivery of LV Transformer BFT02 (BHT) | Mon Dec 02 08:00:00 IST 2019 | Tue Dec 03 09:00:00 IST 2019 | Wed Mar 27 00:00:00 IST 2019 | Wed Mar 27 00:00:00 IST 2019 |  | COMPLETED
3405 | TT_TASK | Delivery of LV Transformer BFT03 | Mon Dec 02 08:00:00 IST 2019 | Tue Dec 03 09:00:00 IST 2019 | Wed Mar 27 00:00:00 IST 2019 | Wed Mar 27 00:00:00 IST 2019 |  | COMPLETED
3406 | TT_TASK | Delivery of LV Switchgear 10BFE/10BMA | Mon Dec 02 08:00:00 IST 2019 | Mon Dec 09 13:00:00 IST 2019 | Fri Apr 05 08:00:00 IDT 2019 | Wed Apr 10 08:00:00 IDT 2019 |  | COMPLETED
3407 | TT_TASK | Delivery of PCC UBA81 & Cabinet 10UBA Building | Mon Mar 30 08:00:00 IDT 2020 | Mon Apr 06 13:00:00 IDT 2020 | Sat Mar 28 08:00:00 IDT 2020 | Sat Mar 28 08:00:00 IDT 2020 |  | COMPLETED
3408 | TT_TASK | Delivery of SEE/ SFC Transformer | Thu Apr 26 08:00:00 IDT 2018 | Thu May 03 13:00:00 IDT 2018 | Thu Apr 26 08:00:00 IDT 2018 | Wed May 02 18:00:00 IDT 2018 |  | COMPLETED
3545 | TT_TASK | Mobilisation of the Crane Barge to Site | Tue Mar 13 08:00:00 IST 2018 | Tue Jul 10 12:00:00 IDT 2018 | Wed Feb 14 08:00:00 IST 2018 | Thu Mar 15 18:00:00 IST 2018 |  | COMPLETED
3546 | TT_TASK | Mobilisation of the Land based cranes to Site | Thu Mar 01 08:00:00 IST 2018 | Thu Mar 08 13:00:00 IST 2018 | Mon Mar 19 08:00:00 IST 2018 | Fri Mar 23 18:00:00 IDT 2018 |  | COMPLETED
3548 | TT_TASK | ITP for - (00BAW-01) Earthing Grid for back-energizing | Thu Aug 30 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Thu Aug 23 00:00:00 IDT 2018 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
3549 | TT_TASK | ITP for - (00BAW-02) Earthing Grid Complete | Thu Aug 30 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Thu Aug 23 00:00:00 IDT 2018 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
3550 | TT_TASK | ITP for - (00BAW-03) Lightening Protection | Thu Aug 30 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Thu Aug 23 00:00:00 IDT 2018 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
3551 | TT_TASK | ITP for - (10MA-01) HP-/ IP-/ LP-Turbine 10MAA/MAB/MAC | Mon Dec 02 08:00:00 IST 2019 | Wed Dec 25 16:00:00 IST 2019 | Tue May 07 08:00:00 IDT 2019 | Fri Jun 14 18:00:00 IDT 2019 |  | COMPLETED
3552 | TT_TASK | ITP for - (10MAN) ST Bypass System | Thu Aug 30 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Thu Jun 07 00:00:00 IDT 2018 | Wed Aug 29 00:00:00 IDT 2018 |  | COMPLETED
3553 | TT_TASK | ITP for - (10MAG) Condensing System | Tue Apr 10 15:00:00 IDT 2018 | Fri May 04 15:00:00 IDT 2018 | Wed Feb 28 08:00:00 IST 2018 | Fri Mar 23 18:00:00 IDT 2018 |  | COMPLETED
3554 | TT_TASK | ITP for - (10MAV) Lube and Lifting Oil System Incl. Generator and GT | Thu Jul 05 13:00:00 IDT 2018 | Tue Jul 31 13:00:00 IDT 2018 | Wed May 09 08:00:00 IDT 2018 | Wed May 30 18:00:00 IDT 2018 |  | COMPLETED
3555 | TT_TASK | ITP for - (10MAW) Gland / Leakage Steam System | Mon Sep 03 08:00:00 IDT 2018 | Wed Sep 26 16:00:00 IDT 2018 | Mon Jun 25 08:00:00 IDT 2018 | Tue Jul 17 18:00:00 IDT 2018 |  | COMPLETED
3556 | TT_TASK | ITP for - (10MAX) ST Hydraulic System | Mon Sep 03 08:00:00 IDT 2018 | Wed Sep 26 16:00:00 IDT 2018 | Mon Jun 25 08:00:00 IDT 2018 | Tue Jul 17 18:00:00 IDT 2018 |  | COMPLETED
3557 | TT_TASK | ITP for - (10MKA) Generator Incl. Bearing System 10 MKD | Mon Dec 02 08:00:00 IST 2019 | Wed Dec 25 16:00:00 IST 2019 | Tue May 08 08:00:00 IDT 2018 | Tue Jun 05 18:00:00 IDT 2018 |  | COMPLETED
3558 | TT_TASK | ITP for - (10MKF) Generator Primary Water Cooling System | Wed Jul 03 12:00:00 IDT 2019 | Mon Jul 29 12:00:00 IDT 2019 | Sat May 12 08:00:00 IDT 2018 | Tue Jun 05 18:00:00 IDT 2018 |  | COMPLETED
3559 | TT_TASK | ITP for - (10MKG) Gas Supply System | Wed Aug 01 09:00:00 IDT 2018 | Mon Aug 27 09:00:00 IDT 2018 | Sat May 12 08:00:00 IDT 2018 | Tue Jun 05 18:00:00 IDT 2018 |  | COMPLETED
3560 | TT_TASK | ITP for - (10MKQ) Waste Gas System | Wed Jul 03 12:00:00 IDT 2019 | Mon Jul 29 12:00:00 IDT 2019 | Thu May 31 08:00:00 IDT 2018 | Sat Jul 14 18:00:00 IDT 2018 |  | COMPLETED
3561 | TT_TASK | ITP for - (10MKW) Seal Oil Supply System | Mon Jul 02 09:00:00 IDT 2018 | Thu Jul 26 09:00:00 IDT 2018 | Fri May 11 08:00:00 IDT 2018 | Sat Jun 30 18:00:00 IDT 2018 |  | COMPLETED
3562 | TT_TASK | ITP for - (10MBA) GT Including Combustion Chamber | Mon Dec 02 08:00:00 IST 2019 | Wed Dec 25 16:00:00 IST 2019 | Tue May 08 08:00:00 IDT 2018 | Thu Jun 14 18:00:00 IDT 2018 |  | COMPLETED
3563 | TT_TASK | ITP for - (10MBX) GT Hydraulic Oil | Wed Jul 11 08:00:00 IDT 2018 | Fri Aug 03 16:00:00 IDT 2018 | Sat May 19 08:00:00 IDT 2018 | Thu Jun 28 18:00:00 IDT 2018 |  | COMPLETED
3564 | TT_TASK | ITP for - (10MBP) GT Natural Gas Incl. Draining System MBP40 | Wed Jul 03 12:00:00 IDT 2019 | Mon Jul 29 12:00:00 IDT 2019 | Fri Jun 01 08:00:00 IDT 2018 | Fri Jul 13 18:00:00 IDT 2018 |  | COMPLETED
3565 | TT_TASK | ITP for - (10MBN) GT Fuel Oil Injection System | Wed Jul 03 12:00:00 IDT 2019 | Mon Jul 29 12:00:00 IDT 2019 | Sat May 19 08:00:00 IDT 2018 | Mon Jul 16 18:00:00 IDT 2018 |  | COMPLETED
3566 | TT_TASK | ITP for - (10MBH) GT Cooling Air System | Thu Jul 05 13:00:00 IDT 2018 | Tue Jul 31 13:00:00 IDT 2018 | Sat May 19 08:00:00 IDT 2018 | Fri Jun 15 18:00:00 IDT 2018 |  | COMPLETED
3567 | TT_TASK | ITP for - (10MBA18) Compressor Cleaning Package | Mon Dec 02 08:00:00 IST 2019 | Wed Dec 25 16:00:00 IST 2019 | Wed Jun 13 08:00:00 IDT 2018 | Thu Jun 21 18:00:00 IDT 2018 |  | COMPLETED
3568 | TT_TASK | ITP for - (10MBA5x) GT Hydraulic Clearance Optimization Supply System | Mon Dec 02 08:00:00 IST 2019 | Wed Dec 25 16:00:00 IST 2019 | Sat Jun 02 08:00:00 IDT 2018 | Thu Jul 12 18:00:00 IDT 2018 |  | COMPLETED
3569 | TT_TASK | ITP for - (10MBX2x) GT Pneumatic System | Tue Jun 26 08:00:00 IDT 2018 | Thu Jul 19 16:00:00 IDT 2018 | Sat May 19 08:00:00 IDT 2018 | Thu Jun 28 18:00:00 IDT 2018 |  | COMPLETED
3570 | TT_TASK | ITP for - (10MBL) Air Intake System | Mon Dec 02 08:00:00 IST 2019 | Wed Dec 25 16:00:00 IST 2019 | Mon May 07 08:00:00 IDT 2018 | Thu Jun 14 18:00:00 IDT 2018 |  | COMPLETED
3571 | TT_TASK | ITP for - (10MBU) GT NOX Water Injection System | Mon Dec 02 08:00:00 IST 2019 | Wed Dec 25 16:00:00 IST 2019 | Sat May 19 08:00:00 IDT 2018 | Fri Jun 15 18:00:00 IDT 2018 |  | COMPLETED
3572 | TT_TASK | ITP for - (10LCA) Main Condensate Pumps and Supply System for Min. Flow Operation Incl. | Mon Sep 17 08:00:00 IDT 2018 | Wed Oct 10 16:00:00 IDT 2018 | Mon Jun 04 00:00:00 IDT 2018 | Mon Jul 16 00:00:00 IDT 2018 |  | COMPLETED
3573 | TT_TASK | ITP for - (10PGB) Closed Cooling Water System | Mon Dec 02 08:00:00 IST 2019 | Wed Dec 25 16:00:00 IST 2019 | Mon Jun 04 08:00:00 IDT 2018 | Thu Aug 09 00:00:00 IDT 2018 |  | COMPLETED
3574 | TT_TASK | ITP for - (10PCB) Service Cooling Water System Incl. 10PDB | Mon Nov 12 09:00:00 IST 2018 | Thu Dec 06 09:00:00 IST 2018 | Mon Jun 04 08:00:00 IDT 2018 | Mon Aug 06 00:00:00 IDT 2018 |  | COMPLETED
3575 | TT_TASK | ITP for - (10SGA) FF Indoor Hydrants 10SGA Inside 10ULA, 10UHA, 10UMC | Thu Nov 22 15:00:00 IST 2018 | Tue Dec 18 15:00:00 IST 2018 | Mon Jul 09 00:00:00 IDT 2018 | Fri Jul 27 00:00:00 IDT 2018 |  | COMPLETED
3576 | TT_TASK | ITP for - (10SGC-02) FF Spray Deluge System 10SGC for Lube Oil / Seal Oil System | Tue Nov 13 13:00:00 IST 2018 | Fri Dec 07 13:00:00 IST 2018 | Thu Jul 19 00:00:00 IDT 2018 | Fri Aug 03 00:00:00 IDT 2018 |  | COMPLETED
3577 | TT_TASK | ITP for - (10BAT) Main Transformer 10BAT01/10BBT01 | Thu Aug 30 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Thu Aug 16 00:00:00 IDT 2018 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
3578 | TT_TASK | ITP for - (10MKC) SEE/SFC Equipment Excitation Transformer MKC; SFC Transformer MBJ | Tue Nov 13 08:00:00 IST 2018 | Thu Dec 06 16:00:00 IST 2018 | Fri Aug 17 00:00:00 IDT 2018 | Tue Aug 28 00:00:00 IDT 2018 |  | COMPLETED
3579 | TT_TASK | ITP for - (10SGC-01) FF Spary Deluge System for BAT/ BBT SGC | Wed Mar 20 08:00:00 IST 2019 | Fri Apr 12 16:00:00 IDT 2019 | Thu Jul 19 08:00:00 IDT 2018 | Fri Aug 03 00:00:00 IDT 2018 |  | COMPLETED
3580 | TT_TASK | ITP for - (10LD) Condensate Polishing Plant | Thu Aug 30 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Mon Jun 04 00:00:00 IDT 2018 | Mon Jul 16 00:00:00 IDT 2018 |  | COMPLETED
3581 | TT_TASK | ITP for - (10LDK) Condensate Polishing System | Wed Aug 01 09:00:00 IDT 2018 | Mon Aug 27 09:00:00 IDT 2018 | Mon Jun 04 08:00:00 IDT 2018 | Mon Jul 16 18:00:00 IDT 2018 |  | COMPLETED
3582 | TT_TASK | ITP for - (00SGM) FF Protection System for UBN | Wed Nov 28 08:00:00 IST 2018 | Fri Dec 21 16:00:00 IST 2018 | Thu Jul 19 00:00:00 IDT 2018 | Wed Aug 01 00:00:00 IDT 2018 |  | COMPLETED
3583 | TT_TASK | ITP for - (10BFT01) LV-Transformer BFT01 (BHT) | Fri Jul 06 08:00:00 IDT 2018 | Tue Jul 31 16:00:00 IDT 2018 | Fri Jul 06 08:00:00 IDT 2018 | Wed Jul 18 00:00:00 IDT 2018 |  | COMPLETED
3584 | TT_TASK | ITP for - (10BFT02) LV-Transformer BFT02 (BHT) | Tue Nov 27 08:00:00 IST 2018 | Thu Dec 20 16:00:00 IST 2018 | Fri Aug 03 00:00:00 IDT 2018 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
3585 | TT_TASK | ITP for - (00BBT) MV Transformer BBT01 | Tue Nov 27 08:00:00 IST 2018 | Thu Dec 20 16:00:00 IST 2018 | Wed Aug 29 00:00:00 IDT 2018 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
3586 | TT_TASK | ITP for - (10MBR) Exhaust Gas System | Fri Aug 10 08:00:00 IDT 2018 | Tue Sep 04 16:00:00 IDT 2018 | Fri May 11 08:00:00 IDT 2018 | Tue Jun 05 18:00:00 IDT 2018 |  | COMPLETED
3587 | TT_TASK | ITP for - (10EK) Fuel Gas Supply System for GT10 | Wed Jul 11 08:00:00 IDT 2018 | Fri Aug 03 16:00:00 IDT 2018 | Fri Jun 22 08:00:00 IDT 2018 | Tue Jul 31 00:00:00 IDT 2018 |  | COMPLETED
3588 | TT_TASK | ITP for - (10HAD10) HRSG HP Steam | Wed Oct 17 08:00:00 IDT 2018 | Fri Nov 09 16:00:00 IST 2018 | Fri Feb 23 00:00:00 IST 2018 | Thu Jun 28 00:00:00 IDT 2018 |  | COMPLETED
3589 | TT_TASK | ITP for - (10HAD50) HRSG IP Steam | Wed Oct 17 08:00:00 IDT 2018 | Fri Nov 09 16:00:00 IST 2018 | Fri Feb 23 00:00:00 IST 2018 | Thu Jun 28 00:00:00 IDT 2018 |  | COMPLETED
3590 | TT_TASK | ITP for - (10HAD80) HRSG LP Steam | Wed Oct 17 08:00:00 IDT 2018 | Fri Nov 09 16:00:00 IST 2018 | Fri Feb 23 00:00:00 IST 2018 | Thu Jun 28 00:00:00 IDT 2018 |  | COMPLETED
3591 | TT_TASK | ITP for - (10HBK) HRSG Exhaust Gas System | Thu Aug 30 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Mon Mar 12 00:00:00 IST 2018 | Thu Jun 28 00:00:00 IDT 2018 |  | COMPLETED
3592 | TT_TASK | ITP for - (10LCL) HRSG Drains System | Wed Aug 15 08:00:00 IDT 2018 | Fri Sep 07 16:00:00 IDT 2018 | Mon Jun 04 08:00:00 IDT 2018 | Thu Jun 28 00:00:00 IDT 2018 |  | COMPLETED
3593 | TT_TASK | ITP for - (10LCA-02) Condensate Supply System incl. Preheater 10HAA10 | Wed Aug 01 09:00:00 IDT 2018 | Mon Aug 27 09:00:00 IDT 2018 | Sat Jun 02 08:00:00 IDT 2018 | Mon Jul 16 00:00:00 IDT 2018 |  | COMPLETED
3594 | TT_TASK | ITP for - (10LAC) Feedwater Pump | Wed Jul 03 12:00:00 IDT 2019 | Mon Jul 29 12:00:00 IDT 2019 | Sat Jun 02 08:00:00 IDT 2018 | Mon Jul 30 00:00:00 IDT 2018 |  | COMPLETED
3595 | TT_TASK | ITP for - (10QCB) Hydrazine Dosing QC | Wed Sep 19 08:00:00 IDT 2018 | Fri Oct 12 16:00:00 IDT 2018 | Fri Jun 29 00:00:00 IDT 2018 | Tue Aug 07 00:00:00 IDT 2018 |  | COMPLETED
3596 | TT_TASK | ITP for - (10QCC) Trisodium Phosphate Dosing QC | Wed Sep 19 08:00:00 IDT 2018 | Fri Oct 12 16:00:00 IDT 2018 | Fri Jun 29 00:00:00 IDT 2018 | Tue Aug 07 00:00:00 IDT 2018 |  | COMPLETED
3597 | TT_TASK | ITP for - (10QCD) Ammonia Dosing QC | Thu Oct 11 08:00:00 IDT 2018 | Mon Nov 05 16:00:00 IST 2018 | Fri Jun 29 00:00:00 IDT 2018 | Tue Aug 07 00:00:00 IDT 2018 |  | COMPLETED
3598 | TT_TASK | ITP for - (10QU) Sampling Container QC | Wed Sep 19 08:00:00 IDT 2018 | Fri Oct 12 16:00:00 IDT 2018 | Mon Aug 20 00:00:00 IDT 2018 | Tue Sep 11 00:00:00 IDT 2018 |  | COMPLETED
3599 | TT_TASK | ITP for - (00LBG) Auxiliary Steam System | Thu Aug 30 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Tue Jul 03 00:00:00 IDT 2018 | Wed Aug 08 00:00:00 IDT 2018 |  | COMPLETED
3600 | TT_TASK | ITP for - (10PAH) Condenser Tube Cleaning System | Wed Aug 01 09:00:00 IDT 2018 | Mon Aug 27 09:00:00 IDT 2018 | Sat May 12 08:00:00 IDT 2018 | Wed Jun 06 18:00:00 IDT 2018 |  | COMPLETED
3601 | TT_TASK | ITP for - (10PAB-01) Circulating Water System incl. Cooling Water Pumps | Tue Jun 26 08:00:00 IDT 2018 | Thu Jul 19 16:00:00 IDT 2018 | Mon Jun 04 08:00:00 IDT 2018 | Tue Jul 17 18:00:00 IDT 2018 |  | COMPLETED
3602 | TT_TASK | ITP for - (00PAA) Cooling Water Screening Plant | Thu Aug 30 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Fri Aug 03 00:00:00 IDT 2018 | Fri Aug 10 00:00:00 IDT 2018 |  | COMPLETED
3603 | TT_TASK | ITP for - (00PUR) Cathodic Protection System for Cooling Water Inlet | Wed Sep 12 08:00:00 IDT 2018 | Fri Oct 05 16:00:00 IDT 2018 | Fri Jun 01 08:00:00 IDT 2018 | Fri Jul 13 18:00:00 IDT 2018 |  | COMPLETED
3604 | TT_TASK | ITP for - (10PUR) Cathodic Protection System for Cooling Water Side of Condenser | Wed Sep 12 08:00:00 IDT 2018 | Fri Oct 05 16:00:00 IDT 2018 | Fri Jun 01 08:00:00 IDT 2018 | Fri Jul 13 18:00:00 IDT 2018 |  | COMPLETED
3605 | TT_TASK | ITP for - (00MBU) NOX Water Forwarding System incl. Supply Lines to GT Skid | Mon Aug 06 08:00:00 IDT 2018 | Wed Aug 29 16:00:00 IDT 2018 | Sat May 19 08:00:00 IDT 2018 | Fri Jun 15 18:00:00 IDT 2018 |  | COMPLETED
3606 | TT_TASK | ITP for - (00STG) Laboratory Container STG | Wed Aug 01 09:00:00 IDT 2018 | Mon Aug 27 09:00:00 IDT 2018 | Mon Jun 04 08:00:00 IDT 2018 | Tue Jul 17 18:00:00 IDT 2018 |  | COMPLETED
3607 | TT_TASK | ITP for - (10SGC-02) FF Spray Deluge Systems for 00UEH/UEJ/UEK Area | Tue Nov 13 13:00:00 IST 2018 | Fri Dec 07 13:00:00 IST 2018 | Thu Jul 19 00:00:00 IDT 2018 | Fri Aug 03 00:00:00 IDT 2018 |  | COMPLETED
3608 | TT_TASK | ITP for - (00EG-01) Fuel Oil Forwarding Station and Storage Tank | Wed Sep 12 08:00:00 IDT 2018 | Fri Oct 05 16:00:00 IDT 2018 | Fri May 25 08:00:00 IDT 2018 | Thu Jun 14 00:00:00 IDT 2018 |  | COMPLETED
3609 | TT_TASK | ITP for - (00EG-02) Fuel Oil Forwarding System incl. Supply Lines up to Fuel Oil | Tue Jun 26 08:00:00 IDT 2018 | Thu Jul 19 16:00:00 IDT 2018 | Fri May 25 08:00:00 IDT 2018 | Wed Jul 25 18:00:00 IDT 2018 |  | COMPLETED
3610 | TT_TASK | ITP for - (10MAD) ST Bearing System | Thu Aug 30 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Mon May 07 00:00:00 IDT 2018 | Wed Aug 29 00:00:00 IDT 2018 |  | COMPLETED
3611 | TT_TASK | ITP for - (10HAA) HRSG | Fri Feb 09 08:00:00 IST 2018 | Tue Mar 06 16:00:00 IST 2018 | Wed Jan 10 08:00:00 IST 2018 | Fri Mar 23 18:00:00 IDT 2018 |  | COMPLETED
3613 | TT_TASK | Method Statement - (10MAN) ST Bypass System | Thu Aug 30 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Fri Jun 08 00:00:00 IDT 2018 | Mon Aug 06 00:00:00 IDT 2018 |  | COMPLETED
3614 | TT_TASK | Method Statement - (10MAG) Condensing System | Tue Apr 10 15:00:00 IDT 2018 | Fri May 04 15:00:00 IDT 2018 | Fri Mar 02 08:00:00 IST 2018 | Fri Mar 30 18:00:00 IDT 2018 |  | COMPLETED
3615 | TT_TASK | Method Statement - (10MKA) Generator Incl. Bearing System 10 MKD | Thu Jul 26 08:00:00 IDT 2018 | Mon Aug 20 16:00:00 IDT 2018 | Mon Jun 11 00:00:00 IDT 2018 | Tue Jun 26 00:00:00 IDT 2018 |  | COMPLETED
3616 | TT_TASK | Method Statement - (10HBK) HRSG Exhaust Gas System | Thu Aug 30 08:00:00 IDT 2018 | Mon Sep 24 16:00:00 IDT 2018 | Mon Jul 02 00:00:00 IDT 2018 | Sat Jul 14 00:00:00 IDT 2018 |  | COMPLETED
3617 | TT_TASK | Method Statement - (10HAA) HRSG | Fri Feb 09 08:00:00 IST 2018 | Thu Feb 22 16:00:00 IST 2018 | Wed Jan 10 08:00:00 IST 2018 | Wed Mar 07 18:00:00 IST 2018 |  | COMPLETED
3619 | TT_TASK | Erect Annex Hall D5/D9/D12 Secondary Steel Structure | Mon Jan 21 08:00:00 IST 2019 | Fri Mar 22 18:00:00 IST 2019 | Mon Jan 21 08:00:00 IST 2019 | Wed May 15 00:00:00 IDT 2019 |  | COMPLETED
3667 | TT_TASK | HP/IP - Clean HP Turbine and Prepare for Assembly | Thu Oct 04 08:00:00 IDT 2018 | Tue Oct 09 18:00:00 IDT 2018 | Wed Sep 12 00:00:00 IDT 2018 | Tue Sep 18 00:00:00 IDT 2018 |  | COMPLETED
3668 | TT_TASK | HP/IP - Set Down Turbine on Bearing Pedestals & Provisionaly Align | Wed Oct 10 08:00:00 IDT 2018 | Thu Oct 18 18:00:00 IDT 2018 | Tue Sep 18 00:00:00 IDT 2018 | Fri Oct 12 00:00:00 IDT 2018 |  | COMPLETED
3669 | TT_TASK | HP/IP - Establish the Radial & Axial Check Dimensions for the Shaft in Bearing Pedestals | Tue Oct 09 08:00:00 IDT 2018 | Tue Oct 09 17:00:00 IDT 2018 | Sat Sep 29 00:00:00 IDT 2018 | Fri Oct 12 19:00:00 IDT 2018 |  | COMPLETED
3670 | TT_TASK | HP/IP - Clean Main & Auxiliary Bearings, Prepare for Assembly & Install | Tue Dec 11 16:00:00 IST 2018 | Thu Dec 13 15:00:00 IST 2018 | Mon Nov 26 00:00:00 IST 2018 | Fri Dec 07 00:00:00 IST 2018 |  | COMPLETED
3671 | TT_TASK | HP/IP - Set Down Shaft in Bearings & Align Shaft | Mon Dec 03 08:00:00 IST 2018 | Tue Dec 11 18:00:00 IST 2018 | Sat Dec 08 00:00:00 IST 2018 | Mon Dec 17 19:00:00 IST 2018 |  | COMPLETED
3672 | TT_TASK | HP/IP Perform Radial & Axial Clearance Checks on Turbine | Wed Dec 12 08:00:00 IST 2018 | Thu Dec 13 18:00:00 IST 2018 | Sat Dec 22 00:00:00 IST 2018 | Tue Jan 15 00:00:00 IST 2019 |  | COMPLETED
3674 | TT_TASK | Clean Turbine & Generator Foundations & Confirm Survey Acceptance | Wed Aug 08 08:00:00 IDT 2018 | Fri Aug 10 18:00:00 IDT 2018 | Mon Jul 23 08:00:00 IDT 2018 | Thu Jul 26 18:00:00 IDT 2018 |  | COMPLETED
3675 | TT_TASK | Markout Reference Points for Turbine Floor Elev., Longitudinal & Transverse Axis | Tue Aug 14 08:00:00 IDT 2018 | Thu Aug 16 18:00:00 IDT 2018 | Mon Jul 16 08:00:00 IDT 2018 | Thu Jul 26 18:00:00 IDT 2018 |  | COMPLETED
3676 | TT_TASK | Install Anchor Bolts - Front HP Bearing Pedestal | Fri Aug 17 08:00:00 IDT 2018 | Fri Aug 17 18:00:00 IDT 2018 | Mon Jul 23 08:00:00 IDT 2018 | Wed Jul 25 18:00:00 IDT 2018 |  | COMPLETED
3677 | TT_TASK | Clean Front HP Bearing Pedestal, Prepare for Assembly and Set Down on Adjusting Screws | Fri Aug 17 08:00:00 IDT 2018 | Mon Aug 20 18:00:00 IDT 2018 | Mon Jul 23 08:00:00 IDT 2018 | Thu Jul 26 18:00:00 IDT 2018 |  | COMPLETED
3678 | TT_TASK | Install Anchor Bolts - Rear HP Bearing Pedestal | Fri Aug 17 08:00:00 IDT 2018 | Fri Aug 17 18:00:00 IDT 2018 | Mon Jul 23 08:00:00 IDT 2018 | Wed Jul 25 18:00:00 IDT 2018 |  | COMPLETED
3679 | TT_TASK | Clean Rear HP Bearing Pedestal, Prepare for Assembly and Set Down on Adjusting Screws | Fri Aug 17 13:03:00 IDT 2018 | Fri Aug 24 08:03:00 IDT 2018 | Mon Jul 23 08:00:00 IDT 2018 | Thu Jul 26 18:00:00 IDT 2018 |  | COMPLETED
3680 | TT_TASK | Install Anchor Bolts - Rear LP-1 Bearing Pedestal | Fri Aug 17 08:00:00 IDT 2018 | Fri Aug 17 18:00:00 IDT 2018 | Mon Jul 23 08:00:00 IDT 2018 | Thu Jul 26 18:00:00 IDT 2018 |  | COMPLETED
3681 | TT_TASK | Clean Rear LP-1 Bearing Pedestal, Prepare for Assembly and Set Down on Adjusting Screws | Thu Jul 26 08:00:00 IDT 2018 | Wed Aug 01 12:00:00 IDT 2018 | Mon Jul 23 08:00:00 IDT 2018 | Fri Aug 24 00:00:00 IDT 2018 |  | COMPLETED
3682 | TT_TASK | Align Front & Rear HP Bearing Pedestals | Wed Aug 01 13:00:00 IDT 2018 | Mon Aug 06 11:00:00 IDT 2018 | Wed Aug 01 13:00:00 IDT 2018 | Mon Aug 06 11:00:00 IDT 2018 |  | COMPLETED
3683 | TT_TASK | Align Rear LP-1 Bearing Pedestals | Thu Aug 30 08:00:00 IDT 2018 | Tue Sep 04 12:00:00 IDT 2018 | Fri Aug 10 00:00:00 IDT 2018 | Fri Aug 24 00:00:00 IDT 2018 |  | COMPLETED
3684 | TT_TASK | Set-up Formwork for Grouting Front & Rear HP Bearing Pedestals | Mon Aug 06 11:00:00 IDT 2018 | Wed Aug 08 10:00:00 IDT 2018 | Mon Aug 06 11:00:00 IDT 2018 | Wed Aug 08 10:00:00 IDT 2018 |  | COMPLETED
3685 | TT_TASK | Set-up Formwork for Grouting Rear LP-1 Bearing Pedestal | Tue Sep 04 13:00:00 IDT 2018 | Fri Sep 07 18:00:00 IDT 2018 | Fri Aug 17 00:00:00 IDT 2018 | Fri Aug 24 00:00:00 IDT 2018 |  | COMPLETED
3686 | TT_TASK | Align Check of Pedestals before Grouting | Sat Aug 25 08:00:00 IDT 2018 | Tue Aug 28 18:00:00 IDT 2018 | Sat Aug 25 08:00:00 IDT 2018 | Mon Aug 27 00:00:00 IDT 2018 |  | COMPLETED
3687 | TT_TASK | Grout Pedestals | Wed Sep 12 08:00:00 IDT 2018 | Fri Sep 14 16:00:00 IDT 2018 | Sat Aug 25 00:00:00 IDT 2018 | Thu Aug 30 00:00:00 IDT 2018 |  | COMPLETED
3688 | TT_TASK | Align Check of Bearing Casings & Baseplates After Grouting | Thu Aug 23 08:00:00 IDT 2018 | Sat Aug 25 18:00:00 IDT 2018 | Thu Aug 23 08:00:00 IDT 2018 | Fri Aug 24 00:00:00 IDT 2018 |  | COMPLETED
3689 | TT_TASK | Install & Prealign Steel Bars for LP-1 Casing Centering Guiders in Foundation | Sat Sep 29 08:00:00 IDT 2018 | Mon Oct 08 11:00:00 IDT 2018 | Sat Sep 08 00:00:00 IDT 2018 | Fri Oct 19 00:00:00 IDT 2018 |  | COMPLETED
3690 | TT_TASK | Fill in Voids in Casing Centering Guides with Grout | Mon Oct 08 11:00:00 IDT 2018 | Wed Oct 10 09:00:00 IDT 2018 | Mon Oct 08 11:00:00 IDT 2018 | Fri Oct 19 00:00:00 IDT 2018 |  | COMPLETED
3692 | TT_TASK | Install & Prealign Steel Bar for LP-1 Casing Guider in Foundation | Wed Oct 10 09:00:00 IDT 2018 | Thu Oct 11 18:00:00 IDT 2018 | Sat Sep 08 00:00:00 IDT 2018 | Fri Oct 19 00:00:00 IDT 2018 |  | COMPLETED
3693 | TT_TASK | LP-1 - Clean LP1 Side Casing & End Walls, Prepare for Assembly | Fri Oct 12 08:00:00 IDT 2018 | Mon Oct 15 16:00:00 IDT 2018 | Sat Oct 06 00:00:00 IDT 2018 | Fri Oct 19 00:00:00 IDT 2018 |  | COMPLETED
3694 | TT_TASK | LP-1 - LP1 Side End Walls on Supporting Arms, Align & Secure, Prepare for Assembly | Mon Oct 15 16:00:00 IDT 2018 | Wed Oct 17 14:00:00 IDT 2018 | Mon Oct 22 00:00:00 IDT 2018 | Tue Oct 23 00:00:00 IDT 2018 |  | COMPLETED
3695 | TT_TASK | LP-1 - Fit Bottom Plate, Align & Tack Weld | Wed Oct 17 14:00:00 IDT 2018 | Mon Oct 22 09:00:00 IDT 2018 | Fri Oct 26 00:00:00 IDT 2018 | Tue Oct 30 15:00:00 IST 2018 |  | COMPLETED
3696 | TT_TASK | LP-1 - Prepare & Install Side Wall | Wed Oct 31 08:00:00 IST 2018 | Sat Nov 03 15:00:00 IST 2018 | Mon Oct 22 00:00:00 IDT 2018 | Sat Oct 27 00:00:00 IDT 2018 |  | COMPLETED
3697 | TT_TASK | LP-1 - Fit & Weld Bracing Pipes for LP-1 Casing | Tue Nov 06 08:00:00 IST 2018 | Tue Nov 13 11:00:00 IST 2018 | Tue Nov 13 00:00:00 IST 2018 | Mon Nov 26 00:00:00 IST 2018 |  | COMPLETED
3698 | TT_TASK | LP-1 - Align, Mount & Bolt Down the LP-1 Casing | Sat Nov 10 14:00:00 IST 2018 | Thu Nov 15 14:00:00 IST 2018 | Sat Nov 24 00:00:00 IST 2018 | Fri Dec 21 00:00:00 IST 2018 |  | COMPLETED
3699 | TT_TASK | LP-1 - Weld Entire LP-1 Outer Casing | Mon Dec 03 08:00:00 IST 2018 | Wed Dec 12 18:00:00 IST 2018 | Fri Nov 30 00:00:00 IST 2018 | Wed Dec 12 19:00:00 IST 2018 |  | COMPLETED
3700 | TT_TASK | LP-1 - Remove Top Half Outer Casing, Clean, Weld & Finish Joints on Joint Plane | Thu Dec 13 08:00:00 IST 2018 | Mon Dec 31 18:00:00 IST 2018 | Fri Dec 14 00:00:00 IST 2018 | Fri Dec 14 00:00:00 IST 2018 |  | COMPLETED
3701 | TT_TASK | LP-1 - Align Bottom Half Outer Casing to Longitunal & Transverse Axes & Vertically | Fri Dec 14 17:00:00 IST 2018 | Thu Jan 03 17:00:00 IST 2019 | Mon Nov 05 00:00:00 IST 2018 | Wed Nov 21 00:00:00 IST 2018 |  | COMPLETED
3702 | TT_TASK | LP-1 - Align Steel Bar for Outer Casing Guider & Fill Voids w/ Grout | Thu Jan 03 17:00:00 IST 2019 | Mon Jan 07 14:00:00 IST 2019 | Sat Nov 24 00:00:00 IST 2018 | Fri Dec 21 00:00:00 IST 2018 |  | COMPLETED
3703 | TT_TASK | LP-1 - Provisionally Mount Exp. Joints for Supporting Arm & Centering Guide | Thu Jan 03 17:00:00 IST 2019 | Wed Jan 09 11:00:00 IST 2019 | Sat Dec 15 00:00:00 IST 2018 | Sat Dec 29 00:00:00 IST 2018 |  | COMPLETED
3704 | TT_TASK | LP-1 - Set Down Bottom Half Inner Casing in Bottom Outer Casing | Wed Jan 09 11:00:00 IST 2019 | Mon Jan 14 11:00:00 IST 2019 | Fri Dec 21 00:00:00 IST 2018 | Fri Dec 21 00:00:00 IST 2018 |  | COMPLETED
3705 | TT_TASK | LP-1 - Align Elevation & Centerline of Bottom Half of Inner Casing | Mon Jan 14 11:00:00 IST 2019 | Fri Jan 18 11:00:00 IST 2019 | Sat Dec 22 00:00:00 IST 2018 | Fri Dec 28 00:00:00 IST 2018 |  | COMPLETED
3706 | TT_TASK | LP-1 - Fix the Inner Casing Radially & Axially, Check Guide Rods | Wed Jan 02 17:00:00 IST 2019 | Tue Jan 08 16:00:00 IST 2019 | Wed Dec 26 00:00:00 IST 2018 | Wed Jan 02 00:00:00 IST 2019 |  | COMPLETED
3707 | TT_TASK | LP-1 - Clean Botton Half Shaft Seal Casing & Attach to Bearing Pedestal | Tue Jan 22 08:00:00 IST 2019 | Wed Jan 23 18:00:00 IST 2019 | Mon Dec 31 00:00:00 IST 2018 | Mon Dec 31 00:00:00 IST 2018 |  | COMPLETED
3708 | TT_TASK | LP-1 - Clean LP-1 Shaft & Prepare for Assembly | Fri Jan 18 11:00:00 IST 2019 | Mon Jan 21 18:00:00 IST 2019 | Sat Dec 29 00:00:00 IST 2018 | Tue Jan 15 00:00:00 IST 2019 |  | COMPLETED
3709 | TT_TASK | LP-1 - Clean Main & Auxiliary Bearing, Prepare for Assembly & Install | Thu Jan 24 08:00:00 IST 2019 | Fri Jan 25 16:00:00 IST 2019 | Mon Dec 31 00:00:00 IST 2018 | Mon Dec 31 00:00:00 IST 2018 |  | COMPLETED
3710 | TT_TASK | LP-1 - Slide Bellow Type Expansion Joints onto LP-1 Shaft | Wed Jan 02 17:00:00 IST 2019 | Sat Jan 05 14:00:00 IST 2019 | Sat Dec 29 00:00:00 IST 2018 | Sat Dec 29 00:00:00 IST 2018 |  | COMPLETED
3711 | TT_TASK | LP-1 - Install Turbine Shaft in Main & Auxiliary Bearings & Align | Sat Jan 05 14:00:00 IST 2019 | Tue Jan 08 12:00:00 IST 2019 | Fri Jan 04 00:00:00 IST 2019 | Sat Jan 05 00:00:00 IST 2019 |  | COMPLETED
3712 | TT_TASK | LP-1 - Take Actual Radial & Axial Shaft Dimensions in the Bearing Pedestals | Tue Jan 08 13:00:00 IST 2019 | Thu Jan 10 10:00:00 IST 2019 | Tue Jan 08 13:00:00 IST 2019 | Mon Jan 14 00:00:00 IST 2019 |  | COMPLETED
3713 | TT_TASK | LP-1 - Provisionally Align Lower Section of Shaft Seal Casing to Shaft | Thu Jan 10 10:00:00 IST 2019 | Sat Jan 12 10:00:00 IST 2019 | Mon Jan 14 00:00:00 IST 2019 | Tue Jan 22 18:00:00 IST 2019 |  | COMPLETED
3714 | TT_TASK | LP-1 - Radially & Axially Align Bottom Half Inner Casing to Turbine Shaft | Sat Jan 12 08:00:00 IST 2019 | Fri Jan 18 18:00:00 IST 2019 | Mon Jan 14 00:00:00 IST 2019 | Mon Jan 21 00:00:00 IST 2019 |  | COMPLETED
3715 | TT_TASK | LP-1 - Perform Radially & Axially Blading Clearance Checks | Sat Jan 19 08:00:00 IST 2019 | Wed Jan 23 18:00:00 IST 2019 | Mon Jan 14 00:00:00 IST 2019 | Mon Jan 21 00:00:00 IST 2019 |  | COMPLETED
3716 | TT_TASK | LP-1 - Install Guide Blade Carrier & Stationary Blade Ring Upper Part | Thu Jan 24 08:00:00 IST 2019 | Sat Jan 26 18:00:00 IST 2019 | Sun Jan 20 00:00:00 IST 2019 | Mon Jan 21 00:00:00 IST 2019 |  | COMPLETED
3717 | TT_TASK | LP-1 - Mount Outer Shell of Inner Casing & Tighten Casing Joint Bolts | Mon Jan 21 08:00:00 IST 2019 | Thu Jan 24 18:00:00 IST 2019 | Fri Feb 15 00:00:00 IST 2019 | Sun Mar 17 00:00:00 IST 2019 |  | COMPLETED
3718 | TT_TASK | LP-1 - Check Axial Displacement of Inner Casing | Mon Apr 01 08:00:00 IDT 2019 | Mon Apr 01 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Mon Apr 01 18:00:00 IDT 2019 |  | COMPLETED
3719 | TT_TASK | LP-1 - Drill & Ream Holes for Fitting Bolts in Joint Plane of Outer Casing | Mon Apr 01 08:00:00 IDT 2019 | Wed Apr 03 18:00:00 IDT 2019 | Sat Mar 09 00:00:00 IST 2019 | Sun Mar 17 00:00:00 IST 2019 |  | COMPLETED
3720 | TT_TASK | LP-1 - Install Atmospheric Relief Diaphragm into Top Half Outer Casing | Mon Feb 18 16:00:00 IST 2019 | Fri Feb 22 15:00:00 IST 2019 | Thu Dec 13 00:00:00 IST 2018 | Fri Dec 14 00:00:00 IST 2018 |  | COMPLETED
3721 | TT_TASK | LP-1 - Mount Top Half Cover & Tighten Casing Joint Bolts | Thu Apr 04 09:00:00 IDT 2019 | Tue Apr 09 18:00:00 IDT 2019 | Wed Mar 20 00:00:00 IST 2019 | Thu Sep 12 00:00:00 IDT 2019 |  | COMPLETED
3722 | TT_TASK | LP-1 - Pre-assemble Cross Over Pipe | Mon Apr 01 08:00:00 IDT 2019 | Mon Apr 29 17:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Mon Sep 02 10:12:00 IDT 2019 |  | COMPLETED
3723 | TT_TASK | LP-1 - Assemble Cross Over Pipe | Thu Jun 20 11:48:00 IDT 2019 | Mon Jun 24 10:48:00 IDT 2019 | Thu Jun 20 11:48:00 IDT 2019 | Thu Sep 19 09:24:00 IDT 2019 |  | COMPLETED
3724 | TT_TASK | LP-1 - Insulate Cross Over Pipe & Turbine | Sat Aug 31 08:00:00 IDT 2019 | Fri Sep 20 18:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 | Fri Oct 04 00:00:00 IDT 2019 |  | COMPLETED
3726 | TT_TASK | Perform Preliminary Alignment of Shaft Assembly in Operating Position | Mon Jan 28 08:00:00 IST 2019 | Thu Jan 31 18:00:00 IST 2019 | Wed Jan 09 00:00:00 IST 2019 | Sat Jan 12 00:00:00 IST 2019 |  | COMPLETED
3727 | TT_TASK | Alignment - Generator to Steam Turbine/Gas Turbine to Generator | Fri Feb 01 08:00:00 IST 2019 | Fri Feb 08 18:00:00 IST 2019 | Mon Jan 14 00:00:00 IST 2019 | Fri Apr 12 00:00:00 IDT 2019 |  | COMPLETED
3728 | TT_TASK | Assembly of Shifting Clutch | Sat Jan 26 09:00:00 IST 2019 | Wed Jan 30 09:00:00 IST 2019 | Wed Jan 30 00:00:00 IST 2019 | Fri Feb 01 18:00:00 IST 2019 |  | COMPLETED
3729 | TT_TASK | Common Coupling Alignment at Steam Turbine/Generator/Gas Turbine | Wed Jan 30 09:00:00 IST 2019 | Fri Feb 08 15:00:00 IST 2019 | Mon Feb 11 00:00:00 IST 2019 | Wed Apr 03 13:30:00 IDT 2019 |  | COMPLETED
3730 | TT_TASK | Draw Together HP/LP Coupling, Ream & Hone Coupling Holes, Finish Grind Coupling Holes | Fri Feb 08 15:00:00 IST 2019 | Thu Feb 14 09:00:00 IST 2019 | Mon Feb 18 00:00:00 IST 2019 | Sat Mar 02 00:00:00 IST 2019 |  | COMPLETED
3731 | TT_TASK | Couple HP & LP1 Shafts Checking Radial Run-Out of Coupling Flanges | Thu Feb 14 09:00:00 IST 2019 | Sat Feb 16 09:00:00 IST 2019 | Sat Mar 02 00:00:00 IST 2019 | Thu Mar 07 00:00:00 IST 2019 |  | COMPLETED
3732 | TT_TASK | Check The Radial Clearance of the LP1 Inner Casing by Means of Adjusting Screws | Wed Jan 30 15:00:00 IST 2019 | Fri Feb 01 15:00:00 IST 2019 | Wed Jan 30 15:00:00 IST 2019 | Thu Apr 04 15:18:00 IDT 2019 |  | COMPLETED
3733 | TT_TASK | Check Radial Run-Out of FInal Stage of Outer Shell of LP Casing | Fri Feb 01 15:00:00 IST 2019 | Sat Feb 02 15:00:00 IST 2019 | Sat Mar 09 00:00:00 IST 2019 | Mon Mar 11 00:00:00 IST 2019 |  | COMPLETED
3734 | TT_TASK | Correct the Alignment of LP Inner Casing if Necessary & Mount Fitted Keys for Casing Support | Fri Feb 01 15:00:00 IST 2019 | Sat Feb 09 15:00:00 IST 2019 | Fri Feb 01 15:00:00 IST 2019 | Tue Apr 09 08:54:00 IDT 2019 |  | COMPLETED
3735 | TT_TASK | Align LP1 Bottom Half Shaft Seal Casing to Coupled Shaft Assembly | Sat Feb 09 15:00:00 IST 2019 | Tue Feb 12 15:00:00 IST 2019 | Wed Mar 20 00:00:00 IST 2019 | Thu Apr 11 08:54:00 IDT 2019 |  | COMPLETED
3736 | TT_TASK | Check Radial Clearance of LP1 Shaft Seal | Tue Apr 30 08:00:00 IDT 2019 | Tue Apr 30 18:00:00 IDT 2019 | Wed Apr 10 00:00:00 IDT 2019 | Wed Apr 24 00:00:00 IDT 2019 |  | COMPLETED
3737 | TT_TASK | Place Cover on LP Shaft Seal Casing Ready for Operations - Fabricate to Size & Insert Fitted Keys | Thu May 02 08:00:00 IDT 2019 | Mon May 06 18:00:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Wed Aug 21 00:00:00 IDT 2019 |  | COMPLETED
3738 | TT_TASK | If Necessary - Realign HP Casing to Coupled Shaft Assembly, Level off Brack Supports | Wed Apr 17 08:54:00 IDT 2019 | Sat Apr 20 08:54:00 IDT 2019 | Wed Apr 17 08:54:00 IDT 2019 | Wed Apr 24 08:54:00 IDT 2019 |  | COMPLETED
3739 | TT_TASK | Install & Align Shaft Turning Gear (Electric Motor) | Tue May 07 08:00:00 IDT 2019 | Wed May 08 18:00:00 IDT 2019 | Mon Apr 29 00:00:00 IDT 2019 | Tue Apr 30 00:00:00 IDT 2019 |  | COMPLETED
3740 | TT_TASK | Machine to Size & Install Fitted Keys for HP Casing Guide | Tue May 07 08:00:00 IDT 2019 | Thu May 09 18:00:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Fri Jun 28 00:00:00 IDT 2019 |  | COMPLETED
3741 | TT_TASK | Machine to Size & Install Shim Plates for HP Turbine Bracket & Support | Fri May 10 08:00:00 IDT 2019 | Sat May 11 18:00:00 IDT 2019 | Fri May 10 08:00:00 IDT 2019 | Sat Aug 31 00:00:00 IDT 2019 |  | COMPLETED
3742 | TT_TASK | Establish Clearance @ Front HP Bearing Pedestal | Mon May 13 08:00:00 IDT 2019 | Tue May 14 18:00:00 IDT 2019 | Mon May 13 08:00:00 IDT 2019 | Tue May 14 18:00:00 IDT 2019 |  | COMPLETED
3743 | TT_TASK | Install Vibration Sensors in Bearing Pedestals | Thu Aug 01 16:39:00 IDT 2019 | Fri Aug 16 18:00:00 IDT 2019 | Fri Jul 19 00:00:00 IDT 2019 | Tue Aug 27 00:00:00 IDT 2019 |  | COMPLETED
3744 | TT_TASK | Install Sealing Rings in Front/Rear HP & Rear LP1 Bearing Pedestals | Mon May 20 08:00:00 IDT 2019 | Thu May 23 18:00:00 IDT 2019 | Tue Apr 30 00:00:00 IDT 2019 | Thu May 02 00:00:00 IDT 2019 |  | COMPLETED
3745 | TT_TASK | Prepare Front/Rear HP & Rear LP1 Bearing Pedestals for Flushing | Thu Apr 25 10:00:00 IDT 2019 | Fri May 03 10:00:00 IDT 2019 | Thu Apr 25 10:00:00 IDT 2019 | Tue May 07 18:00:00 IDT 2019 |  | COMPLETED
3747 | TT_TASK | Steam Turbine Ready for Oil FLushing | Fri Jun 07 08:00:00 IDT 2019 | Fri Jun 07 18:00:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 |  | COMPLETED
3748 | TT_TASK | Steam Turbine Lube Oil Flushing | Sat Jun 08 08:00:00 IDT 2019 | Tue Jul 02 18:00:00 IDT 2019 | Wed May 29 00:00:00 IDT 2019 | Fri Jun 21 00:00:00 IDT 2019 |  | COMPLETED
3749 | TT_TASK | Re-assembly after Lube Oil Flush | Mon Jun 17 08:00:00 IDT 2019 | Wed Jun 26 18:00:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 | Sat Jul 06 00:00:00 IDT 2019 |  | COMPLETED
3750 | TT_TASK | Closing of Bearing Pedestals | Tue Jul 09 11:36:00 IDT 2019 | Fri Jul 19 11:36:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 | Tue Aug 27 00:00:00 IDT 2019 |  | COMPLETED
3751 | TT_TASK | E & IC Installation | Mon Jun 03 08:00:00 IDT 2019 | Sat Jul 13 18:00:00 IDT 2019 | Mon May 13 00:00:00 IDT 2019 | Sat Sep 07 18:00:00 IDT 2019 |  | COMPLETED
3752 | TT_TASK | Pre-Commissioning - (10MA-01) HP/IP/LP Turbine | Mon Sep 09 08:00:00 IDT 2019 | Tue Sep 17 18:00:00 IDT 2019 | Fri Sep 06 00:00:00 IDT 2019 | Sat Nov 16 00:00:00 IST 2019 |  | COMPLETED
3754 | TT_TASK | Install Equipment/Skids/Pumps | Sat Sep 29 08:00:00 IDT 2018 | Thu Oct 11 18:00:00 IDT 2018 | Fri Sep 14 00:00:00 IDT 2018 | Sun Sep 30 00:00:00 IDT 2018 |  | COMPLETED
3755 | TT_TASK | Set Lube Oil Module into Position - Skid | Sat Sep 29 08:00:00 IDT 2018 | Fri Oct 05 18:00:00 IDT 2018 | Fri Sep 14 00:00:00 IDT 2018 | Sun Sep 30 00:00:00 IDT 2018 |  | COMPLETED
3756 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Sat Jan 12 08:00:00 IST 2019 | Fri Mar 08 18:00:00 IST 2019 | Mon Jan 07 00:00:00 IST 2019 | Tue Apr 30 00:00:00 IDT 2019 |  | COMPLETED
3757 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Fri Feb 08 08:00:00 IST 2019 | Mon Apr 01 12:00:00 IDT 2019 | Fri Feb 08 08:00:00 IST 2019 | Thu May 23 00:00:00 IDT 2019 |  | COMPLETED
3758 | TT_TASK | NDE | Fri Mar 01 08:00:00 IST 2019 | Wed Apr 10 11:00:00 IDT 2019 | Fri Mar 01 08:00:00 IST 2019 | Tue May 28 00:00:00 IDT 2019 |  | COMPLETED
3759 | TT_TASK | EC+I | Wed Jun 05 08:00:00 IDT 2019 | Tue Jul 02 10:00:00 IDT 2019 | Tue May 21 00:00:00 IDT 2019 | Fri Sep 06 00:00:00 IDT 2019 |  | COMPLETED
3760 | TT_TASK | Line Inspection | Fri May 31 08:00:00 IDT 2019 | Tue Jun 04 18:00:00 IDT 2019 | Wed Jun 12 00:00:00 IDT 2019 | Sat Jun 15 18:00:00 IDT 2019 |  | COMPLETED
3761 | TT_TASK | Hydro Test | Sat Jun 29 08:00:00 IDT 2019 | Tue Jul 02 18:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 | Mon Aug 19 00:00:00 IDT 2019 |  | COMPLETED
3763 | TT_TASK | Painting/Insulation | Sat Jun 08 08:00:00 IDT 2019 | Tue Jun 18 18:00:00 IDT 2019 | Wed May 08 00:00:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
3764 | TT_TASK | Pre-Commissioning | Sat Aug 31 13:00:00 IDT 2019 | Thu Sep 12 12:00:00 IDT 2019 | Tue Aug 20 00:00:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
3766 | TT_TASK | Install Equipment/Skids/Pumps | Wed Oct 31 08:00:00 IST 2018 | Mon Nov 05 18:00:00 IST 2018 | Wed Oct 03 00:00:00 IDT 2018 | Fri Oct 05 00:00:00 IDT 2018 |  | COMPLETED
3767 | TT_TASK | Flush ST Hydraulic Piping | Mon Sep 09 08:00:00 IDT 2019 | Mon Sep 16 18:00:00 IDT 2019 | Mon Sep 09 08:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
3768 | TT_TASK | Reconfigure ST Hydraulic Piping after Flushing] | Mon Sep 30 08:00:00 IDT 2019 | Tue Oct 08 18:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 |  | COMPLETED
3769 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Fri Feb 08 15:00:00 IST 2019 | Fri Mar 15 15:00:00 IST 2019 | Sat Dec 15 00:00:00 IST 2018 | Thu Apr 25 00:00:00 IDT 2019 |  | COMPLETED
3770 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Mon Apr 08 14:00:00 IDT 2019 | Fri May 17 17:00:00 IDT 2019 | Mon Apr 08 14:00:00 IDT 2019 | Wed Sep 04 00:00:00 IDT 2019 |  | COMPLETED
3771 | TT_TASK | NDE | Mon Apr 08 14:00:00 IDT 2019 | Fri May 17 17:00:00 IDT 2019 | Wed Apr 17 00:00:00 IDT 2019 | Mon Sep 16 00:00:00 IDT 2019 |  | COMPLETED
3772 | TT_TASK | EC+I | Tue Apr 30 08:00:00 IDT 2019 | Sat Jun 08 11:00:00 IDT 2019 | Tue May 07 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
3773 | TT_TASK | Line Inspection | Wed Jul 31 15:00:00 IDT 2019 | Mon Aug 05 15:00:00 IDT 2019 | Mon Aug 26 00:00:00 IDT 2019 | Thu Aug 29 00:00:00 IDT 2019 |  | COMPLETED
3774 | TT_TASK | Hydro Test | Wed Sep 04 08:00:00 IDT 2019 | Sat Sep 07 18:00:00 IDT 2019 | Wed Sep 04 08:00:00 IDT 2019 | Sat Sep 07 18:00:00 IDT 2019 |  | COMPLETED
3775 | TT_TASK | Painting/Insulation | Tue Jun 11 11:00:00 IDT 2019 | Sat Jun 29 11:00:00 IDT 2019 | Tue May 07 00:00:00 IDT 2019 | Sat Nov 09 00:00:00 IST 2019 |  | COMPLETED
3776 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Tue Sep 24 08:00:00 IDT 2019 | Sat Sep 28 18:00:00 IDT 2019 | Tue Sep 24 08:00:00 IDT 2019 | Sat Nov 09 18:00:00 IST 2019 |  | COMPLETED
3778 | TT_TASK | Install & Align Main Stop & Control Valves | Thu Apr 04 17:00:00 IDT 2019 | Wed Apr 24 14:00:00 IDT 2019 | Tue Apr 09 00:00:00 IDT 2019 | Mon Jun 17 09:30:00 IDT 2019 |  | COMPLETED
3779 | TT_TASK | Install & Align RH Stop & Control Valves | Sat Apr 13 14:00:00 IDT 2019 | Sat May 04 10:00:00 IDT 2019 | Sat Apr 13 14:00:00 IDT 2019 | Fri Jun 21 11:00:00 IDT 2019 |  | COMPLETED
3780 | TT_TASK | Install & Align Steam Supply Valves & Bolt | Mon Jun 10 11:00:00 IDT 2019 | Fri Jun 28 18:00:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 |  | COMPLETED
3781 | TT_TASK | Installation of all Actuators for MS, RH, LP | Tue Jun 18 08:00:00 IDT 2019 | Mon Jul 15 10:00:00 IDT 2019 | Tue Jun 11 00:00:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 |  | COMPLETED
3782 | TT_TASK | E&IC Installation ST Stop and Control Valves | Wed Jun 26 10:00:00 IDT 2019 | Mon Aug 05 10:00:00 IDT 2019 | Fri Jun 21 00:00:00 IDT 2019 | Sat Aug 31 00:00:00 IDT 2019 |  | COMPLETED
3783 | TT_TASK | Pre-Commissioning | Sat Aug 31 08:00:00 IDT 2019 | Wed Sep 11 18:00:00 IDT 2019 | Mon Sep 02 00:00:00 IDT 2019 | Wed Sep 11 18:00:00 IDT 2019 |  | COMPLETED
3785 | TT_TASK | Attach Spring Supports for By Pass Valve | Fri May 31 08:00:00 IDT 2019 | Wed Jun 05 18:00:00 IDT 2019 | Mon Jun 10 00:00:00 IDT 2019 | Fri Jun 21 00:00:00 IDT 2019 |  | COMPLETED
3786 | TT_TASK | Install By Pass Valves | Thu Jun 06 08:00:00 IDT 2019 | Fri Jun 14 18:00:00 IDT 2019 | Fri Jun 21 00:00:00 IDT 2019 | Sat Aug 31 00:00:00 IDT 2019 |  | COMPLETED
3787 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Thu Apr 25 08:00:00 IDT 2019 | Fri May 24 18:00:00 IDT 2019 | Thu Apr 25 08:00:00 IDT 2019 | Sat Aug 31 00:00:00 IDT 2019 |  | COMPLETED
3788 | TT_TASK | NDE | Tue Apr 30 08:00:00 IDT 2019 | Wed May 29 18:00:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
3789 | TT_TASK | EC+I | Fri Jun 07 08:00:00 IDT 2019 | Sat Jul 06 18:00:00 IDT 2019 | Fri May 24 00:00:00 IDT 2019 | Wed Sep 25 00:00:00 IDT 2019 |  | COMPLETED
3790 | TT_TASK | Line Inspection & Preparation for Neutral Float Welds | Fri Aug 02 08:00:00 IDT 2019 | Fri Aug 09 18:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
3791 | TT_TASK | Neutral Float & Final Weld Connections to Bypass Control Valves | Thu Jul 11 08:00:00 IDT 2019 | Wed Jul 24 18:00:00 IDT 2019 | Mon Jul 22 00:00:00 IDT 2019 | Sat Aug 31 00:00:00 IDT 2019 |  | COMPLETED
3792 | TT_TASK | Hydro Test | Wed Aug 21 14:24:00 IDT 2019 | Mon Sep 02 14:24:00 IDT 2019 | Sat Aug 31 00:00:00 IDT 2019 | Sat Sep 07 10:15:00 IDT 2019 |  | COMPLETED
3793 | TT_TASK | Close-out Insulation after Neutral Float Welds | Sat Sep 07 10:15:00 IDT 2019 | Wed Sep 18 10:15:00 IDT 2019 | Sat Sep 07 10:15:00 IDT 2019 | Thu Nov 07 18:00:00 IST 2019 |  | COMPLETED
3794 | TT_TASK | Painting/Insulation | Sat Jun 29 08:00:00 IDT 2019 | Sat Jul 20 18:00:00 IDT 2019 | Tue Jun 25 00:00:00 IDT 2019 | Sat Oct 26 00:00:00 IDT 2019 |  | COMPLETED
3795 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Wed Sep 18 10:15:00 IDT 2019 | Mon Sep 30 10:15:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 | Sat Oct 26 00:00:00 IDT 2019 |  | COMPLETED
3797 | TT_TASK | Install Gland Steam Condenser (MAW) | Mon Apr 01 08:00:00 IDT 2019 | Thu Apr 04 18:00:00 IDT 2019 | Fri Apr 12 00:00:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 |  | COMPLETED
3798 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Wed Sep 11 08:00:00 IDT 2019 | Thu Sep 19 18:00:00 IDT 2019 | Wed Sep 11 08:00:00 IDT 2019 | Tue Nov 12 00:00:00 IST 2019 |  | COMPLETED
3799 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Tue Apr 30 11:36:00 IDT 2019 | Sat May 11 17:36:00 IDT 2019 | Fri May 10 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
3800 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Thu Apr 18 08:00:00 IDT 2019 | Thu May 23 18:00:00 IDT 2019 | Thu Apr 18 08:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
3801 | TT_TASK | NDE | Sat May 25 17:06:00 IDT 2019 | Tue Jun 18 17:06:00 IDT 2019 | Tue May 14 00:00:00 IDT 2019 | Tue Sep 24 00:00:00 IDT 2019 |  | COMPLETED
3802 | TT_TASK | EC+I | Wed Jun 05 11:36:00 IDT 2019 | Thu Jul 11 11:36:00 IDT 2019 | Thu Jun 27 00:00:00 IDT 2019 | Tue Sep 24 00:00:00 IDT 2019 |  | COMPLETED
3803 | TT_TASK | Line Inpsection | Wed Aug 14 08:00:00 IDT 2019 | Wed Aug 21 18:00:00 IDT 2019 | Fri Aug 23 00:00:00 IDT 2019 | Fri Aug 30 00:00:00 IDT 2019 |  | COMPLETED
3804 | TT_TASK | Hydro Test | Thu Aug 22 08:00:00 IDT 2019 | Thu Aug 29 18:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 | Sat Aug 31 18:00:00 IDT 2019 |  | COMPLETED
3805 | TT_TASK | Painting/Insulation | Wed Jun 05 11:36:00 IDT 2019 | Sat Jun 22 11:36:00 IDT 2019 | Tue Jun 18 00:00:00 IDT 2019 | Tue Nov 12 00:00:00 IST 2019 |  | COMPLETED
3807 | TT_TASK | Install Steam Turbine Drain Module (MAL00Y) | Wed Oct 24 08:00:00 IDT 2018 | Mon Oct 29 18:00:00 IST 2018 | Wed Aug 01 00:00:00 IDT 2018 | Sat Sep 22 00:00:00 IDT 2018 |  | COMPLETED
3808 | TT_TASK | Resolution of Foundation Embedment problem (Civil Issue) | Sat Sep 29 08:00:00 IDT 2018 | Tue Oct 23 18:00:00 IDT 2018 | Sat Sep 29 08:00:00 IDT 2018 | Sat Oct 20 00:00:00 IDT 2018 |  | COMPLETED
3809 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Sat Apr 06 08:00:00 IDT 2019 | Sat May 11 18:00:00 IDT 2019 | Tue Apr 09 00:00:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
3810 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Sat Apr 27 08:00:00 IDT 2019 | Sat Jun 01 18:00:00 IDT 2019 | Sat Apr 27 08:00:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
3811 | TT_TASK | NDE | Tue May 28 11:36:00 IDT 2019 | Wed Jun 26 11:36:00 IDT 2019 | Tue May 21 00:00:00 IDT 2019 | Wed Sep 25 00:00:00 IDT 2019 |  | COMPLETED
3812 | TT_TASK | EC+I | Wed Jun 12 08:00:00 IDT 2019 | Wed Jul 03 18:00:00 IDT 2019 | Wed Jun 12 08:00:00 IDT 2019 | Fri Sep 27 00:00:00 IDT 2019 |  | COMPLETED
3813 | TT_TASK | Line Inspection | Sat Aug 31 08:00:00 IDT 2019 | Wed Sep 04 18:00:00 IDT 2019 | Tue Sep 10 00:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
3814 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 04 18:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
3815 | TT_TASK | Painting/Insulation | Wed Jun 05 15:18:00 IDT 2019 | Fri Jul 19 15:18:00 IDT 2019 | Thu May 23 00:00:00 IDT 2019 | Tue Nov 12 00:00:00 IST 2019 |  | COMPLETED
3816 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Tue Sep 10 08:00:00 IDT 2019 | Thu Sep 19 18:00:00 IDT 2019 | Tue Sep 10 08:00:00 IDT 2019 | Tue Nov 12 00:00:00 IST 2019 |  | COMPLETED
3818 | TT_TASK | Install Equipment/Skids/Pumps | Sat Apr 06 13:30:00 IDT 2019 | Sat Apr 13 13:30:00 IDT 2019 | Mon Apr 08 00:00:00 IDT 2019 | Fri Jun 07 00:00:00 IDT 2019 |  | COMPLETED
3819 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Sat Apr 13 13:30:00 IDT 2019 | Wed May 08 13:30:00 IDT 2019 | Mon Apr 15 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
3820 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue Apr 23 13:30:00 IDT 2019 | Fri May 17 13:30:00 IDT 2019 | Tue Apr 23 13:30:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
3821 | TT_TASK | NDE | Sat May 11 08:00:00 IDT 2019 | Fri Jun 07 18:00:00 IDT 2019 | Sat May 11 08:00:00 IDT 2019 | Wed Sep 25 00:00:00 IDT 2019 |  | COMPLETED
3822 | TT_TASK | EC+I | Tue May 28 08:00:00 IDT 2019 | Wed Jun 19 18:00:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
3823 | TT_TASK | Line Inspection | Wed Aug 14 08:00:00 IDT 2019 | Tue Aug 20 18:00:00 IDT 2019 | Wed Aug 21 00:00:00 IDT 2019 | Sat Aug 31 00:00:00 IDT 2019 |  | COMPLETED
3824 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Tue Oct 08 18:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 |  | COMPLETED
3825 | TT_TASK | Painting/Insulation | Fri Jun 14 08:00:00 IDT 2019 | Fri Jun 28 18:00:00 IDT 2019 | Mon Jun 17 00:00:00 IDT 2019 | Thu Nov 07 00:00:00 IST 2019 |  | COMPLETED
3826 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Wed Sep 11 14:24:00 IDT 2019 | Thu Sep 19 14:24:00 IDT 2019 | Wed Sep 11 14:24:00 IDT 2019 | Thu Nov 07 00:00:00 IST 2019 |  | COMPLETED
3829 | TT_TASK | Set up and Check Condenser Foundations | Wed Apr 18 16:00:00 IDT 2018 | Sat Apr 21 12:00:00 IDT 2018 | Mon Apr 16 08:00:00 IDT 2018 | Wed Apr 18 18:00:00 IDT 2018 |  | COMPLETED
3830 | TT_TASK | Placing and Alignment of Support Plates | Tue Apr 02 08:00:00 IDT 2019 | Thu Apr 04 17:00:00 IDT 2019 | Tue Apr 02 08:00:00 IDT 2019 | Thu Apr 04 17:00:00 IDT 2019 |  | COMPLETED
3831 | TT_TASK | Fitting and Welding of Fixing and Guide Points | Mon May 07 08:00:00 IDT 2018 | Wed May 09 18:00:00 IDT 2018 | Sat Apr 28 08:00:00 IDT 2018 | Fri May 04 06:00:00 IDT 2018 |  | COMPLETED
3832 | TT_TASK | Placing Hotwell | Mon May 07 08:00:00 IDT 2018 | Mon May 07 18:00:00 IDT 2018 | Sat May 05 08:00:00 IDT 2018 | Sat May 19 06:00:00 IDT 2018 |  | COMPLETED
3833 | TT_TASK | Assembly and Welding of Condensate Drain Tank | Mon Jun 04 08:00:00 IDT 2018 | Fri Jun 08 12:00:00 IDT 2018 | Sat Jun 02 08:00:00 IDT 2018 | Tue Jun 05 18:00:00 IDT 2018 |  | COMPLETED
3834 | TT_TASK | Placing Steam Shell (lower part) and Connection Weld | Wed May 23 08:00:00 IDT 2018 | Sat Jun 02 18:00:00 IDT 2018 | Tue May 22 08:00:00 IDT 2018 | Wed May 23 06:00:00 IDT 2018 |  | COMPLETED
3835 | TT_TASK | Placing, Aligning and Grouting of Vacuum Pumps | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 12 18:00:00 IDT 2019 | Thu Apr 04 00:00:00 IDT 2019 | Fri Jun 07 00:00:00 IDT 2019 |  | COMPLETED
3836 | TT_TASK | Installing Protective Covers for Cooling Tubes | Thu Jul 26 08:00:00 IDT 2018 | Sat Jul 28 18:00:00 IDT 2018 | Mon Jun 11 00:00:00 IDT 2018 | Wed Jun 13 00:00:00 IDT 2018 |  | COMPLETED
3837 | TT_TASK | Alignment of Condenser Steam Shell | Thu Aug 16 16:00:00 IDT 2018 | Fri Aug 17 16:00:00 IDT 2018 | Tue May 22 08:00:00 IDT 2018 | Fri May 25 06:00:00 IDT 2018 |  | COMPLETED
3839 | TT_TASK | Assembly and Welding of Condenser Neck | Fri Aug 17 16:00:00 IDT 2018 | Thu Sep 13 16:00:00 IDT 2018 | Fri Jun 15 08:00:00 IDT 2018 | Fri Aug 31 11:25:00 IDT 2018 |  | COMPLETED
3840 | TT_TASK | Fitting and Welding of Guide Bolts and Stiffening Plates | Thu Sep 13 16:00:00 IDT 2018 | Wed Sep 26 16:00:00 IDT 2018 | Sun Jun 17 08:00:00 IDT 2018 | Mon Jan 21 00:00:00 IST 2019 |  | COMPLETED
3841 | TT_TASK | Installing and Wedling of Seismic Tie Down | Thu Apr 04 17:00:00 IDT 2019 | Tue Apr 09 17:00:00 IDT 2019 | Thu Apr 04 17:00:00 IDT 2019 | Wed Apr 10 17:00:00 IDT 2019 |  | COMPLETED
3842 | TT_TASK | Assemble and Weld Nozzles into Steam Dome | Sat Sep 29 08:00:00 IDT 2018 | Sat Oct 13 09:00:00 IDT 2018 | Mon Sep 03 00:00:00 IDT 2018 | Mon Oct 15 00:00:00 IDT 2018 |  | COMPLETED
3843 | TT_TASK | Vacuum Test Water Side | Mon Dec 31 08:00:00 IST 2018 | Wed Jan 02 17:00:00 IST 2019 | Tue Dec 11 00:00:00 IST 2018 | Wed Jan 09 00:00:00 IST 2019 |  | COMPLETED
3844 | TT_TASK | Check Corrosion Protection on CW Side | Wed Jan 02 17:00:00 IST 2019 | Sat Jan 19 17:00:00 IST 2019 | Mon Jan 14 00:00:00 IST 2019 | Mon Jan 21 00:00:00 IST 2019 |  | COMPLETED
3845 | TT_TASK | Fitting and Bolting of Front and Rear Coverwith Seal | Fri Oct 12 10:00:00 IDT 2018 | Sat Oct 20 10:00:00 IDT 2018 | Sun Jun 03 08:00:00 IDT 2018 | Wed Jun 13 18:00:00 IDT 2018 |  | COMPLETED
3846 | TT_TASK | Connection and Welding of Rear Cover | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 09 18:00:00 IDT 2019 | Wed Apr 03 00:00:00 IDT 2019 | Thu Apr 11 18:00:00 IDT 2019 |  | COMPLETED
3848 | TT_TASK | Fitting of Condenser to LP Turbine | Wed Jan 30 08:00:00 IST 2019 | Mon Feb 18 18:00:00 IST 2019 | Wed Jan 30 08:00:00 IST 2019 | Sat May 04 13:30:00 IDT 2019 |  | COMPLETED
3849 | TT_TASK | Welding of Condenser to LP Turbine | Tue Feb 19 08:00:00 IST 2019 | Fri Feb 22 18:00:00 IST 2019 | Tue Feb 19 08:00:00 IST 2019 | Fri Feb 22 18:00:00 IST 2019 |  | COMPLETED
3850 | TT_TASK | Floating of Bypass Station | Fri May 31 08:00:00 IDT 2019 | Tue Jun 11 18:00:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
3851 | TT_TASK | Assembly and Welding of Condenser Neck Structure | Mon Sep 03 08:00:00 IDT 2018 | Thu Sep 13 18:00:00 IDT 2018 | Fri Jun 15 00:00:00 IDT 2018 | Mon Jul 30 00:00:00 IDT 2018 |  | COMPLETED
3852 | TT_TASK | Grouting of Condenser Shell Support Structure Seismic Tie | Sat Feb 02 17:00:00 IST 2019 | Tue Feb 12 17:00:00 IST 2019 | Tue Mar 26 00:00:00 IST 2019 | Thu Apr 11 11:30:00 IDT 2019 |  | COMPLETED
3853 | TT_TASK | Final Works and Cleaning | Thu Apr 11 11:30:00 IDT 2019 | Tue Apr 16 11:30:00 IDT 2019 | Thu Apr 11 11:30:00 IDT 2019 | Sat Jun 29 16:12:00 IDT 2019 |  | COMPLETED
3854 | TT_TASK | Final Inspection | Fri Jul 12 16:12:00 IDT 2019 | Mon Jul 15 16:12:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 |  | COMPLETED
3855 | TT_TASK | Insulation Condenser | Mon Jul 15 16:12:00 IDT 2019 | Sat Aug 24 16:12:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 | Thu Nov 14 00:00:00 IST 2019 |  | COMPLETED
3856 | TT_TASK | Placing and Alignment of Sliding Supports | Sat Jan 26 08:00:00 IST 2019 | Tue Jan 29 18:00:00 IST 2019 | Fri Mar 15 00:00:00 IST 2019 | Fri May 03 08:54:00 IDT 2019 |  | COMPLETED
3857 | TT_TASK | Piping Installation MAG | Sat May 04 13:30:00 IDT 2019 | Sat Jun 08 13:30:00 IDT 2019 | Sat May 04 13:30:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
3858 | TT_TASK | Prepare ground to South of Condenser for 750T crane | Wed Apr 25 16:00:00 IDT 2018 | Thu May 03 18:00:00 IDT 2018 | Thu Apr 26 08:00:00 IDT 2018 | Thu May 03 06:00:00 IDT 2018 |  | COMPLETED
3861 | TT_TASK | Pressure Test Condenser | Fri Oct 18 08:00:00 IDT 2019 | Tue Oct 29 18:00:00 IST 2019 | Fri Oct 18 08:00:00 IDT 2019 | Tue Oct 29 00:00:00 IST 2019 |  | COMPLETED
3864 | TT_TASK | Installation of Condensate Extraction Pump - Skid | Wed Jan 02 08:00:00 IST 2019 | Sat Jan 12 18:00:00 IST 2019 | Thu Jan 10 00:00:00 IST 2019 | Mon May 06 18:00:00 IDT 2019 |  | COMPLETED
3865 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Aug 31 15:45:00 IDT 2019 | Wed Sep 11 15:45:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 | Thu Dec 05 00:00:00 IST 2019 |  | COMPLETED
3866 | TT_TASK | Install Condensate Recirculation Pump Skid (LCA50Y Module) | Thu Feb 28 08:00:00 IST 2019 | Wed Mar 13 18:00:00 IST 2019 | Wed Feb 27 00:00:00 IST 2019 | Thu Feb 28 00:00:00 IST 2019 |  | COMPLETED
3867 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Sat Jan 12 08:00:00 IST 2019 | Wed Apr 03 18:00:00 IDT 2019 | Sat Jan 12 08:00:00 IST 2019 | Wed Jul 17 00:00:00 IDT 2019 |  | COMPLETED
3868 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue Apr 30 08:00:00 IDT 2019 | Wed Jun 05 17:00:00 IDT 2019 | Mon May 06 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
3869 | TT_TASK | NDE | Tue Apr 30 08:00:00 IDT 2019 | Wed Jun 05 18:00:00 IDT 2019 | Mon Apr 08 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
3870 | TT_TASK | E &IC Erection Cond Recirc Pump | Mon Apr 01 08:00:00 IDT 2019 | Fri May 17 18:00:00 IDT 2019 | Mon Apr 15 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
3871 | TT_TASK | Line Inspection | Sat Aug 03 15:56:00 IDT 2019 | Tue Aug 13 15:56:00 IDT 2019 | Mon Aug 05 00:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
3872 | TT_TASK | Hydro Test | Tue Aug 13 15:56:00 IDT 2019 | Fri Aug 23 15:56:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
3873 | TT_TASK | Painting/Insulation | Wed Jun 19 15:45:00 IDT 2019 | Mon Jul 08 15:45:00 IDT 2019 | Fri Jun 07 00:00:00 IDT 2019 | Thu Dec 05 00:00:00 IST 2019 |  | COMPLETED
3875 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 01 08:00:00 IDT 2019 | Wed May 08 17:00:00 IDT 2019 | Tue Apr 02 00:00:00 IDT 2019 | Mon Jun 10 00:00:00 IDT 2019 |  | COMPLETED
3876 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Fri Mar 22 16:00:00 IST 2019 | Sat Jun 29 16:00:00 IDT 2019 | Mon Jan 07 00:00:00 IST 2019 | Wed Jul 24 00:00:00 IDT 2019 |  | COMPLETED
3877 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Fri Jun 21 13:55:00 IDT 2019 | Tue Jul 16 13:55:00 IDT 2019 | Tue May 07 00:00:00 IDT 2019 | Thu Jul 25 00:00:00 IDT 2019 |  | COMPLETED
3878 | TT_TASK | NDE | Mon Jul 08 13:55:00 IDT 2019 | Tue Jul 16 13:55:00 IDT 2019 | Mon May 13 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
3879 | TT_TASK | EC+I | Mon May 27 08:00:00 IDT 2019 | Thu Jun 06 18:00:00 IDT 2019 | Fri Apr 26 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
3880 | TT_TASK | Line Inspection | Wed Jul 31 08:00:00 IDT 2019 | Sat Aug 10 18:00:00 IDT 2019 | Fri Jul 05 00:00:00 IDT 2019 | Sat Aug 10 18:00:00 IDT 2019 |  | COMPLETED
3881 | TT_TASK | Hydro Test | Mon Aug 12 08:00:00 IDT 2019 | Thu Aug 22 18:00:00 IDT 2019 | Thu Aug 15 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
3882 | TT_TASK | Painting/Insulation | Fri May 31 08:00:00 IDT 2019 | Sat Jun 29 18:00:00 IDT 2019 | Tue Jun 18 00:00:00 IDT 2019 | Mon Nov 11 00:00:00 IST 2019 |  | COMPLETED
3883 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Sep 07 10:15:00 IDT 2019 | Fri Sep 20 10:15:00 IDT 2019 | Sat Sep 07 10:15:00 IDT 2019 | Mon Nov 11 00:00:00 IST 2019 |  | COMPLETED
3885 | TT_TASK | Install Equipment/Skids/Pumps | Sat Feb 16 08:00:00 IST 2019 | Fri Mar 22 18:00:00 IST 2019 | Mon Mar 25 00:00:00 IST 2019 | Tue Apr 30 00:00:00 IDT 2019 |  | COMPLETED
3886 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Tue Apr 16 08:00:00 IDT 2019 | Thu Jun 06 18:00:00 IDT 2019 | Tue Apr 16 08:00:00 IDT 2019 | Wed Jul 24 00:00:00 IDT 2019 |  | COMPLETED
3887 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Wed May 15 08:00:00 IDT 2019 | Sat Jun 29 18:00:00 IDT 2019 | Fri Apr 26 00:00:00 IDT 2019 | Wed Jul 24 00:00:00 IDT 2019 |  | COMPLETED
3888 | TT_TASK | NDE | Fri May 10 08:00:00 IDT 2019 | Wed Jun 26 18:00:00 IDT 2019 | Fri May 10 08:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
3889 | TT_TASK | EC+I | Wed Jul 03 08:00:00 IDT 2019 | Thu Jul 25 18:00:00 IDT 2019 | Tue Apr 30 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
3890 | TT_TASK | Line Inspection | Wed Aug 14 10:42:00 IDT 2019 | Thu Aug 22 10:42:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
3891 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 04 18:00:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 |  | COMPLETED
3892 | TT_TASK | Painting/Insulation | Wed Jul 10 08:00:00 IDT 2019 | Wed Aug 07 18:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 | Mon Dec 09 00:00:00 IST 2019 |  | COMPLETED
3893 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Thu Sep 12 11:52:00 IDT 2019 | Sat Sep 21 11:52:00 IDT 2019 | Thu Sep 12 11:52:00 IDT 2019 | Mon Dec 09 00:00:00 IST 2019 |  | COMPLETED
3895 | TT_TASK | Install Equipment/Skids/Pumps | Sat Feb 16 08:00:00 IST 2019 | Mon Mar 04 17:00:00 IST 2019 | Mon Mar 25 00:00:00 IST 2019 | Mon Apr 15 16:15:00 IDT 2019 |  | COMPLETED
3896 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 15 16:15:00 IDT 2019 | Fri May 31 16:15:00 IDT 2019 | Mon Apr 15 16:15:00 IDT 2019 | Mon Jul 22 00:00:00 IDT 2019 |  | COMPLETED
3897 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Wed May 29 08:00:00 IDT 2019 | Fri Jun 28 14:00:00 IDT 2019 | Tue May 14 00:00:00 IDT 2019 | Mon Jul 22 00:00:00 IDT 2019 |  | COMPLETED
3898 | TT_TASK | NDE | Thu May 30 14:00:00 IDT 2019 | Sat Jul 06 14:00:00 IDT 2019 | Thu May 16 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
3899 | TT_TASK | EC+I | Fri Jun 21 15:29:00 IDT 2019 | Fri Aug 02 15:29:00 IDT 2019 | Fri Jun 14 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
3900 | TT_TASK | Line Inspection | Mon Aug 05 14:51:00 IDT 2019 | Tue Aug 13 14:51:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 | Thu Sep 12 00:00:00 IDT 2019 |  | COMPLETED
3901 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 04 18:00:00 IDT 2019 | Fri Oct 25 00:00:00 IDT 2019 | Mon Nov 04 00:00:00 IST 2019 |  | COMPLETED
3902 | TT_TASK | Painting/Insulation | Thu Jul 18 14:51:00 IDT 2019 | Mon Aug 05 14:51:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 | Tue Nov 26 00:00:00 IST 2019 |  | COMPLETED
3903 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Sep 21 10:20:00 IDT 2019 | Mon Sep 30 10:20:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 | Tue Nov 26 00:00:00 IST 2019 |  | COMPLETED
3906 | TT_TASK | Pre-assemble of Air Intake System | Fri Feb 15 11:00:00 IST 2019 | Mon Mar 04 11:00:00 IST 2019 | Mon Mar 25 00:00:00 IST 2019 | Fri Apr 26 00:00:00 IDT 2019 |  | COMPLETED
3907 | TT_TASK | Installation of Air Inlet Duct (Inlet Plenum Damper and Transition piece) | Wed May 15 16:12:00 IDT 2019 | Thu Jun 06 16:12:00 IDT 2019 | Mon May 13 00:00:00 IDT 2019 | Sat Jun 22 08:54:00 IDT 2019 |  | COMPLETED
3908 | TT_TASK | Set Air Inlet Duct Lower Plenum on Foundation MBL | Mon Apr 15 09:48:00 IDT 2019 | Sat Apr 27 09:48:00 IDT 2019 | Mon Apr 15 09:48:00 IDT 2019 | Fri May 03 09:48:00 IDT 2019 |  | COMPLETED
3909 | TT_TASK | Installation of Air Inlet Duct (Remaining) | Thu Jun 06 16:12:00 IDT 2019 | Tue Jul 02 16:12:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Sat Aug 31 00:00:00 IDT 2019 |  | COMPLETED
3910 | TT_TASK | Installation of Air Intake Cone and Filters | Sat Jun 01 09:48:00 IDT 2019 | Wed Jun 26 09:48:00 IDT 2019 | Sat Apr 20 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
3911 | TT_TASK | Insulation Anti Icing MBL | Fri Jul 12 08:54:00 IDT 2019 | Tue Aug 06 08:54:00 IDT 2019 | Mon Jun 03 00:00:00 IDT 2019 | Wed Jul 24 00:00:00 IDT 2019 |  | COMPLETED
3912 | TT_TASK | E&IC MBL | Mon Apr 29 08:00:00 IDT 2019 | Fri Jun 14 18:00:00 IDT 2019 | Mon Apr 29 08:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
3913 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Aug 31 10:53:00 IDT 2019 | Thu Sep 19 10:53:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
3914 | TT_TASK | Install Filter House Support Steel | Mon Apr 01 08:00:00 IDT 2019 | Fri May 10 18:00:00 IDT 2019 | Wed Jan 23 00:00:00 IST 2019 | Thu Feb 28 00:00:00 IST 2019 |  | COMPLETED
3915 | TT_TASK | Install Filter House | Mon Apr 01 08:00:00 IDT 2019 | Fri May 10 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
3916 | TT_TASK | Installation of Inlet Air Duct Support Platform | Mon Apr 01 08:00:00 IDT 2019 | Thu Apr 18 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Tue Jun 11 14:24:00 IDT 2019 |  | COMPLETED
3917 | TT_TASK | Lower Half Secondary Air Piping | Sat Apr 27 09:48:00 IDT 2019 | Sat May 04 09:48:00 IDT 2019 | Sat Apr 27 09:48:00 IDT 2019 | Mon May 06 15:18:00 IDT 2019 |  | COMPLETED
3918 | TT_TASK | Set Exhaust Manifold | Fri Oct 26 08:00:00 IDT 2018 | Wed Oct 31 18:00:00 IST 2018 | Wed Sep 05 00:00:00 IDT 2018 | Thu Sep 27 00:00:00 IDT 2018 |  | COMPLETED
3919 | TT_TASK | Complete Steel Work for Inlet Air System | Mon Apr 01 08:00:00 IDT 2019 | Sat Apr 27 18:00:00 IDT 2019 | Fri Mar 01 00:00:00 IST 2019 | Mon May 06 16:12:00 IDT 2019 |  | COMPLETED
3921 | TT_TASK | Check Foundation | Thu Aug 30 08:00:00 IDT 2018 | Mon Sep 03 18:00:00 IDT 2018 | Wed Aug 08 00:00:00 IDT 2018 | Sat Sep 08 00:00:00 IDT 2018 |  | COMPLETED
3922 | TT_TASK | Lower Support Block Centering Guide to Foundation Pit | Thu Oct 11 08:00:00 IDT 2018 | Mon Oct 15 18:00:00 IDT 2018 | Sat Sep 15 00:00:00 IDT 2018 | Sat Sep 15 00:00:00 IDT 2018 |  | COMPLETED
3923 | TT_TASK | Install & Grout Compressor Supports | Tue Oct 16 08:00:00 IDT 2018 | Sat Oct 20 18:00:00 IDT 2018 | Thu Sep 13 00:00:00 IDT 2018 | Sat Sep 29 00:00:00 IDT 2018 |  | COMPLETED
3924 | TT_TASK | Position Support Bridge | Wed Oct 17 08:00:00 IDT 2018 | Wed Oct 17 18:00:00 IDT 2018 | Mon Sep 17 00:00:00 IDT 2018 | Sat Sep 29 00:00:00 IDT 2018 |  | COMPLETED
3925 | TT_TASK | Install & Grout Turbine Supports Blocks | Mon Oct 22 08:00:00 IDT 2018 | Fri Oct 26 18:00:00 IDT 2018 | Mon Sep 17 00:00:00 IDT 2018 | Sat Sep 29 00:00:00 IDT 2018 |  | COMPLETED
3926 | TT_TASK | Install Turbine Supports | Tue Oct 23 08:00:00 IDT 2018 | Wed Oct 24 18:00:00 IDT 2018 | Mon Sep 17 00:00:00 IDT 2018 | Sat Sep 29 00:00:00 IDT 2018 |  | COMPLETED
3927 | TT_TASK | Set Combustion Turbine | Sat Nov 03 08:00:00 IST 2018 | Wed Nov 07 17:00:00 IST 2018 | Wed Oct 03 00:00:00 IDT 2018 | Sat Oct 06 00:00:00 IDT 2018 |  | COMPLETED
3928 | TT_TASK | GT Enclosure Installation | Mon Jan 21 08:00:00 IST 2019 | Tue Apr 16 18:00:00 IDT 2019 | Mon Jan 21 08:00:00 IST 2019 | Thu Nov 21 00:00:00 IST 2019 |  | COMPLETED
3929 | TT_TASK | Align Support Block Centering Guide | Wed Nov 07 17:00:00 IST 2018 | Fri Nov 09 15:00:00 IST 2018 | Fri Sep 14 00:00:00 IDT 2018 | Sat Sep 15 00:00:00 IDT 2018 |  | COMPLETED
3930 | TT_TASK | Grout Support Block Centering Guide | Fri Nov 09 15:00:00 IST 2018 | Mon Nov 12 12:00:00 IST 2018 | Tue Oct 09 00:00:00 IDT 2018 | Wed Oct 10 00:00:00 IDT 2018 |  | COMPLETED
3931 | TT_TASK | Align Combustion Turbine to Foundation Axis | Mon Nov 12 13:00:00 IST 2018 | Thu Nov 15 18:00:00 IST 2018 | Sat Oct 06 00:00:00 IDT 2018 | Wed Oct 10 00:00:00 IDT 2018 |  | COMPLETED
3933 | TT_TASK | Install Weld Support Bridge & Clamps for Fuel Gas Manifolds | Sat Apr 27 09:48:00 IDT 2019 | Fri May 03 09:48:00 IDT 2019 | Sat Apr 20 00:00:00 IDT 2019 | Wed Jun 26 00:00:00 IDT 2019 |  | COMPLETED
3934 | TT_TASK | Install Intermediate Shaft & Center to Combustion Turbine | Fri Dec 28 08:00:00 IST 2018 | Mon Dec 31 18:00:00 IST 2018 | Fri Nov 16 00:00:00 IST 2018 | Wed Nov 21 00:00:00 IST 2018 |  | COMPLETED
3935 | TT_TASK | Install Clamps for Fuel Gas Manifolds | Fri Dec 28 08:00:00 IST 2018 | Fri Jan 04 11:00:00 IST 2019 | Fri Oct 26 00:00:00 IDT 2018 | Thu Nov 15 00:00:00 IST 2018 |  | COMPLETED
3936 | TT_TASK | Install Secondary Air Piping System | Thu Apr 18 08:00:00 IDT 2019 | Sat Apr 27 18:00:00 IDT 2019 | Fri Nov 30 00:00:00 IST 2018 | Sat Jan 12 00:00:00 IST 2019 |  | COMPLETED
3937 | TT_TASK | Install Fuel Gas Manifold Pilot Gas | Fri Jan 04 11:00:00 IST 2019 | Wed Jan 09 17:00:00 IST 2019 | Tue Nov 06 00:00:00 IST 2018 | Fri Nov 16 00:00:00 IST 2018 |  | COMPLETED
3939 | TT_TASK | Install Fuel Gas Manifold Stages A/B/C/D | Wed Jan 09 17:00:00 IST 2019 | Tue Jan 15 16:00:00 IST 2019 | Tue Nov 06 00:00:00 IST 2018 | Fri Nov 16 00:00:00 IST 2018 |  | COMPLETED
3940 | TT_TASK | E & IC Erection of GT | Tue Apr 02 15:00:00 IDT 2019 | Thu Jun 06 15:00:00 IDT 2019 | Fri Mar 22 00:00:00 IST 2019 | Wed Sep 11 00:00:00 IDT 2019 |  | COMPLETED
3941 | TT_TASK | Common Coupling Alignment GT/GEN/ST | Sat Apr 27 09:48:00 IDT 2019 | Fri May 10 09:48:00 IDT 2019 | Tue Mar 05 00:00:00 IST 2019 | Fri Apr 12 00:00:00 IDT 2019 |  | COMPLETED
3942 | TT_TASK | Align & Welding Spur of the Support Block of Centering Guide | Wed Jan 30 11:00:00 IST 2019 | Fri Feb 01 18:00:00 IST 2019 | Wed Oct 10 00:00:00 IDT 2018 | Thu Oct 11 00:00:00 IDT 2018 |  | COMPLETED
3943 | TT_TASK | Insulate Compressor Vane Carrier | Wed Jul 31 08:00:00 IDT 2019 | Tue Aug 06 18:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 | Tue Sep 03 11:36:00 IDT 2019 |  | COMPLETED
3944 | TT_TASK | Weld Lugs of Compressor Supports | Mon Apr 01 08:00:00 IDT 2019 | Mon Apr 08 18:00:00 IDT 2019 | Tue Mar 26 00:00:00 IST 2019 | Mon Apr 08 15:18:00 IDT 2019 |  | COMPLETED
3945 | TT_TASK | Weld & Pretension Turbine Supports | Mon Apr 08 15:18:00 IDT 2019 | Thu Apr 11 15:18:00 IDT 2019 | Mon Apr 08 15:18:00 IDT 2019 | Thu Apr 11 15:18:00 IDT 2019 |  | COMPLETED
3946 | TT_TASK | Connect Exhaust Gas Line to Exhaust Gas Diffuser | Thu Apr 11 15:18:00 IDT 2019 | Tue Apr 16 15:18:00 IDT 2019 | Fri Mar 15 00:00:00 IST 2019 | Sat Mar 23 00:00:00 IST 2019 |  | COMPLETED
3947 | TT_TASK | Install Actuators for Vane Pitch Controllers (IGV/VGv1/2/3) | Fri Jun 07 16:39:00 IDT 2019 | Fri Jun 14 11:39:00 IDT 2019 | Wed Jun 12 00:00:00 IDT 2019 | Thu Jul 25 00:00:00 IDT 2019 |  | COMPLETED
3948 | TT_TASK | Check Alignment of Shaft Assembly | Thu Apr 11 15:18:00 IDT 2019 | Mon Apr 15 14:18:00 IDT 2019 | Mon Mar 25 00:00:00 IST 2019 | Thu Apr 11 17:54:00 IDT 2019 |  | COMPLETED
3949 | TT_TASK | Complete Insulation Installation | Tue Apr 30 08:00:00 IDT 2019 | Tue Jul 23 18:00:00 IDT 2019 | Fri May 24 00:00:00 IDT 2019 | Thu Sep 12 00:00:00 IDT 2019 |  | COMPLETED
3950 | TT_TASK | Position & Align Coupling Flanges, Bore Out & Hone Bolt Holes | Fri Apr 12 08:00:00 IDT 2019 | Tue Apr 23 18:00:00 IDT 2019 | Fri Apr 12 08:00:00 IDT 2019 | Fri Apr 26 18:00:00 IDT 2019 |  | COMPLETED
3951 | TT_TASK | Install Compressor Bearing Cover & Shaft Turning Gear Unit | Sat Apr 27 13:30:00 IDT 2019 | Tue Apr 30 11:30:00 IDT 2019 | Tue Mar 26 00:00:00 IST 2019 | Sat Aug 31 00:00:00 IDT 2019 |  | COMPLETED
3952 | TT_TASK | Install Shaft Position Sensors for HCO System | Wed Jul 31 09:42:00 IDT 2019 | Thu Aug 01 09:42:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
3953 | TT_TASK | Install Speed Measuring Facilities | Thu Aug 01 09:42:00 IDT 2019 | Fri Aug 02 09:42:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 | Sat Aug 31 18:00:00 IDT 2019 |  | COMPLETED
3954 | TT_TASK | Install Vibration Sensors | Fri Aug 02 09:42:00 IDT 2019 | Mon Aug 05 09:42:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
3955 | TT_TASK | GT Encl E&IC Installation Incl Lighting | Mon May 20 17:00:00 IDT 2019 | Thu Jun 06 17:00:00 IDT 2019 | Mon May 20 17:00:00 IDT 2019 | Thu Sep 12 00:00:00 IDT 2019 |  | COMPLETED
3956 | TT_TASK | Gas Turbine FInal Check | Thu Oct 03 11:36:00 IDT 2019 | Sat Oct 12 11:36:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
3957 | TT_TASK | Completion of Gas Turbine | Sat Oct 26 10:42:00 IDT 2019 | Mon Nov 04 10:42:00 IST 2019 | Sat Sep 28 00:00:00 IDT 2019 | Thu Nov 21 13:12:00 IST 2019 |  | COMPLETED
3959 | TT_TASK | Installation of Exhaust Gas Support /Steelwork | Fri Mar 01 08:00:00 IST 2019 | Sat Mar 23 18:00:00 IST 2019 | Fri Mar 01 08:00:00 IST 2019 | Tue Apr 23 18:00:00 IDT 2019 |  | COMPLETED
3960 | TT_TASK | Installation of Exhaust Gas System Diffuser Casing & Transition Piece | Mon May 06 16:12:00 IDT 2019 | Thu May 30 16:12:00 IDT 2019 | Thu May 16 00:00:00 IDT 2019 | Tue Jul 23 00:00:00 IDT 2019 |  | COMPLETED
3961 | TT_TASK | Final Installation of Exhaust Gas Diffuser Expansion Jt (After Final Train Alignment) | Thu Apr 18 08:00:00 IDT 2019 | Tue May 28 18:00:00 IDT 2019 | Mon Mar 18 00:00:00 IST 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
3962 | TT_TASK | Grout Exhaust Gas Diffuser Supports | Sat Aug 31 08:00:00 IDT 2019 | Wed Sep 04 18:00:00 IDT 2019 | Tue Sep 24 00:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 |  | COMPLETED
3964 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 09 14:00:00 IDT 2019 | Mon Apr 08 00:00:00 IDT 2019 | Mon Jun 10 00:00:00 IDT 2019 |  | COMPLETED
3965 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 01 08:00:00 IDT 2019 | Mon May 06 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Fri Sep 06 00:00:00 IDT 2019 |  | COMPLETED
3966 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Thu May 09 14:24:00 IDT 2019 | Sat Jun 01 14:24:00 IDT 2019 | Thu May 09 14:24:00 IDT 2019 | Fri Sep 06 00:00:00 IDT 2019 |  | COMPLETED
3967 | TT_TASK | NDE | Wed May 15 14:24:00 IDT 2019 | Thu Jun 13 14:24:00 IDT 2019 | Wed May 15 14:24:00 IDT 2019 | Thu Sep 12 00:00:00 IDT 2019 |  | COMPLETED
3968 | TT_TASK | EC+I | Mon Jun 24 08:00:00 IDT 2019 | Mon Jul 15 18:00:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Fri Sep 13 00:00:00 IDT 2019 |  | COMPLETED
3969 | TT_TASK | Line Inspection | Fri Sep 06 09:48:00 IDT 2019 | Wed Sep 11 09:48:00 IDT 2019 | Mon Sep 16 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
3970 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 04 18:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 | Fri Oct 04 18:00:00 IDT 2019 |  | COMPLETED
3971 | TT_TASK | Painting/Insulation | Fri Aug 16 08:00:00 IDT 2019 | Wed Aug 21 18:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Fri Nov 29 00:00:00 IST 2019 |  | COMPLETED
3972 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Tue Sep 17 09:48:00 IDT 2019 | Mon Sep 23 09:48:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 | Fri Nov 29 00:00:00 IST 2019 |  | COMPLETED
3974 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 08 08:00:00 IDT 2019 | Thu Apr 25 12:00:00 IDT 2019 | Sat Apr 06 08:00:00 IDT 2019 | Fri Jun 07 00:00:00 IDT 2019 |  | COMPLETED
3975 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Jan 21 08:00:00 IST 2019 | Mon Mar 11 18:00:00 IST 2019 | Mon Jan 21 08:00:00 IST 2019 | Mon Apr 22 00:00:00 IDT 2019 |  | COMPLETED
3976 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Mon Apr 01 08:00:00 IDT 2019 | Mon May 06 18:00:00 IDT 2019 | Thu Apr 04 00:00:00 IDT 2019 | Tue Sep 03 00:00:00 IDT 2019 |  | COMPLETED
3977 | TT_TASK | NDE | Tue Apr 23 08:00:00 IDT 2019 | Wed May 22 18:00:00 IDT 2019 | Tue Apr 23 08:00:00 IDT 2019 | Tue Sep 17 00:00:00 IDT 2019 |  | COMPLETED
3978 | TT_TASK | EC+I | Tue Apr 30 08:00:00 IDT 2019 | Tue Jun 04 18:00:00 IDT 2019 | Wed May 08 00:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
3979 | TT_TASK | Line Inspection | Wed Sep 04 08:00:00 IDT 2019 | Sat Sep 07 18:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 | Thu Sep 19 18:00:00 IDT 2019 |  | COMPLETED
3980 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 04 18:00:00 IDT 2019 | Sat Oct 26 00:00:00 IDT 2019 | Sat Oct 26 00:00:00 IDT 2019 |  | COMPLETED
3981 | TT_TASK | Painting/Insulation | Fri Jun 21 08:00:00 IDT 2019 | Wed Jul 10 18:00:00 IDT 2019 | Thu Jun 13 00:00:00 IDT 2019 | Wed Nov 06 00:00:00 IST 2019 |  | COMPLETED
3982 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Tue Sep 17 11:36:00 IDT 2019 | Tue Sep 24 11:36:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 | Wed Nov 06 11:36:00 IST 2019 |  | COMPLETED
3984 | TT_TASK | Install Fuel Gas Equipment/Skids | Sat Apr 06 08:00:00 IDT 2019 | Thu Apr 25 15:00:00 IDT 2019 | Tue Apr 09 00:00:00 IDT 2019 | Tue Jul 23 00:00:00 IDT 2019 |  | COMPLETED
3985 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Thu May 23 16:30:00 IDT 2019 | Wed Jun 19 08:30:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Thu Jul 25 00:00:00 IDT 2019 |  | COMPLETED
3986 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Fri Jun 07 08:30:00 IDT 2019 | Wed Jun 26 15:30:00 IDT 2019 | Fri May 24 00:00:00 IDT 2019 | Thu Jul 25 00:00:00 IDT 2019 |  | COMPLETED
3987 | TT_TASK | NDE | Wed May 22 15:30:00 IDT 2019 | Wed Jun 26 15:30:00 IDT 2019 | Wed May 22 15:30:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
3988 | TT_TASK | EC+I | Tue Jun 25 09:00:00 IDT 2019 | Fri Jul 19 09:00:00 IDT 2019 | Mon Jun 24 00:00:00 IDT 2019 | Thu Sep 12 00:00:00 IDT 2019 |  | COMPLETED
3989 | TT_TASK | Line Inspection | Sat Sep 07 14:24:00 IDT 2019 | Thu Sep 12 14:24:00 IDT 2019 | Tue Sep 17 00:00:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 |  | COMPLETED
3990 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 04 18:00:00 IDT 2019 | Tue Oct 22 00:00:00 IDT 2019 | Thu Oct 24 00:00:00 IDT 2019 |  | COMPLETED
3991 | TT_TASK | Painting/Insulation | Tue Jun 25 09:00:00 IDT 2019 | Sat Jul 13 09:00:00 IDT 2019 | Thu Jun 13 00:00:00 IDT 2019 | Thu Nov 21 00:00:00 IST 2019 |  | COMPLETED
3992 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Wed Sep 18 14:24:00 IDT 2019 | Tue Sep 24 14:24:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 | Thu Nov 21 00:00:00 IST 2019 |  | COMPLETED
3994 | TT_TASK | Set Equipment/Skids/Pumps | Mon Apr 08 08:00:00 IDT 2019 | Tue Apr 09 09:00:00 IDT 2019 | Sat Apr 06 08:00:00 IDT 2019 | Wed Jun 05 00:00:00 IDT 2019 |  | COMPLETED
3995 | TT_TASK | Final nstall Equipment/Skids/Pumps | Fri Jun 14 11:39:00 IDT 2019 | Tue Jun 18 13:39:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Fri Jul 26 00:00:00 IDT 2019 |  | COMPLETED
3996 | TT_TASK | Final Pipe Connections to Skid | Mon Jun 17 11:39:00 IDT 2019 | Wed Jun 19 13:39:00 IDT 2019 | Mon Jun 17 11:39:00 IDT 2019 | Tue Sep 03 13:30:00 IDT 2019 |  | COMPLETED
3997 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 01 08:00:00 IDT 2019 | Sat Apr 27 18:00:00 IDT 2019 | Tue Apr 02 00:00:00 IDT 2019 | Wed Sep 04 00:00:00 IDT 2019 |  | COMPLETED
3998 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue Apr 23 08:00:00 IDT 2019 | Fri May 17 18:00:00 IDT 2019 | Tue Apr 23 08:00:00 IDT 2019 | Fri Sep 06 00:00:00 IDT 2019 |  | COMPLETED
3999 | TT_TASK | NDE | Tue Apr 16 08:00:00 IDT 2019 | Mon May 13 18:00:00 IDT 2019 | Tue Apr 16 08:00:00 IDT 2019 | Tue Sep 10 00:00:00 IDT 2019 |  | COMPLETED
4000 | TT_TASK | EC+I | Fri May 31 08:00:00 IDT 2019 | Wed Jun 26 18:00:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4001 | TT_TASK | Line Inspection | Mon Aug 12 16:17:00 IDT 2019 | Fri Aug 16 16:17:00 IDT 2019 | Tue Aug 27 00:00:00 IDT 2019 | Wed Sep 04 00:00:00 IDT 2019 |  | COMPLETED
4002 | TT_TASK | Hydro Test | Fri Aug 16 16:17:00 IDT 2019 | Wed Aug 28 16:17:00 IDT 2019 | Thu Aug 29 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4003 | TT_TASK | Painting/Insulation | Tue Apr 30 08:00:00 IDT 2019 | Fri May 24 12:00:00 IDT 2019 | Mon May 06 00:00:00 IDT 2019 | Fri Sep 13 00:00:00 IDT 2019 |  | COMPLETED
4004 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Wed Aug 28 16:17:00 IDT 2019 | Wed Sep 11 16:17:00 IDT 2019 | Sat Aug 31 00:00:00 IDT 2019 | Fri Sep 13 00:00:00 IDT 2019 |  | COMPLETED
4006 | TT_TASK | Set GT Lube Oil Package into Position - Skid | Sat Sep 29 08:00:00 IDT 2018 | Sat Sep 29 18:00:00 IDT 2018 | Fri Sep 14 00:00:00 IDT 2018 | Sat Sep 29 18:00:00 IDT 2018 |  | COMPLETED
4007 | TT_TASK | Install Equipment/Skids/Pumps | Fri Nov 30 08:00:00 IST 2018 | Fri Dec 07 10:00:00 IST 2018 | Wed Oct 10 00:00:00 IDT 2018 | Thu Oct 11 00:00:00 IDT 2018 |  | COMPLETED
4008 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Tue Feb 19 08:00:00 IST 2019 | Wed May 08 10:00:00 IDT 2019 | Mon Jan 07 00:00:00 IST 2019 | Thu Jun 20 00:00:00 IDT 2019 |  | COMPLETED
4009 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Fri Feb 08 08:00:00 IST 2019 | Tue Mar 26 18:00:00 IST 2019 | Mon Mar 18 00:00:00 IST 2019 | Sat May 25 18:00:00 IDT 2019 |  | COMPLETED
4010 | TT_TASK | NDE | Wed Apr 03 08:00:00 IDT 2019 | Thu Apr 25 18:00:00 IDT 2019 | Wed Apr 03 08:00:00 IDT 2019 | Tue Jun 25 00:00:00 IDT 2019 |  | COMPLETED
4011 | TT_TASK | EC+I | Mon May 27 08:00:00 IDT 2019 | Tue Jun 18 18:00:00 IDT 2019 | Mon May 27 08:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4012 | TT_TASK | Line Inspection | Mon Jun 10 08:00:00 IDT 2019 | Thu Jun 13 18:00:00 IDT 2019 | Tue Jun 04 00:00:00 IDT 2019 | Sat Jun 08 00:00:00 IDT 2019 |  | COMPLETED
4013 | TT_TASK | Painting/Insulation | Fri May 31 08:00:00 IDT 2019 | Tue Jun 18 18:00:00 IDT 2019 | Tue May 21 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4015 | TT_TASK | GT Lube Oil/Lifting Flush & Restore | Fri May 31 08:00:00 IDT 2019 | Sat Jun 22 18:00:00 IDT 2019 | Thu Jun 20 00:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 |  | COMPLETED
4016 | TT_TASK | Pre-Commissioning/Cleaning | Fri Sep 06 14:24:00 IDT 2019 | Tue Sep 17 14:24:00 IDT 2019 | Fri Sep 06 14:24:00 IDT 2019 | Sat Oct 12 09:48:00 IDT 2019 |  | COMPLETED
4018 | TT_TASK | Set Pneumatic Skid Package into Position | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 02 09:00:00 IDT 2019 | Wed Apr 03 00:00:00 IDT 2019 | Tue Jun 11 00:00:00 IDT 2019 |  | COMPLETED
4019 | TT_TASK | Install Equipment/Skids/Pumps | Mon Jun 03 08:00:00 IDT 2019 | Tue Jun 11 14:00:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Thu Jul 25 00:00:00 IDT 2019 |  | COMPLETED
4020 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Tue Apr 02 08:00:00 IDT 2019 | Tue Apr 30 18:00:00 IDT 2019 | Tue Apr 02 08:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4021 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue Apr 09 08:00:00 IDT 2019 | Wed May 08 18:00:00 IDT 2019 | Tue Apr 09 08:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4022 | TT_TASK | NDE | Sat May 25 16:39:00 IDT 2019 | Wed Jun 12 16:39:00 IDT 2019 | Sat May 25 16:39:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4023 | TT_TASK | EC+I | Mon Jun 24 16:39:00 IDT 2019 | Wed Jul 24 16:39:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4024 | TT_TASK | Line Inspection | Wed Sep 04 15:45:00 IDT 2019 | Mon Sep 09 15:45:00 IDT 2019 | Wed Sep 04 15:45:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 |  | COMPLETED
4025 | TT_TASK | Hydro Test | Mon Sep 09 15:45:00 IDT 2019 | Tue Sep 17 15:45:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 | Fri Sep 27 18:00:00 IDT 2019 |  | COMPLETED
4026 | TT_TASK | Painting/Insulation | Tue Jul 16 15:45:00 IDT 2019 | Thu Aug 08 15:45:00 IDT 2019 | Fri Jul 26 00:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
4027 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Tue Sep 17 15:45:00 IDT 2019 | Tue Sep 24 15:45:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 | Fri Oct 11 18:00:00 IDT 2019 |  | COMPLETED
4029 | TT_TASK | Set Hydraulic Clearance Optimization Package into Position | Mon Apr 08 08:00:00 IDT 2019 | Tue Apr 09 09:00:00 IDT 2019 | Sat Apr 06 08:00:00 IDT 2019 | Mon May 06 15:45:00 IDT 2019 |  | COMPLETED
4030 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 08 08:00:00 IDT 2019 | Tue Apr 16 14:00:00 IDT 2019 | Mon Apr 08 00:00:00 IDT 2019 | Sat May 04 10:42:00 IDT 2019 |  | COMPLETED
4031 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Sat Apr 13 08:00:00 IDT 2019 | Tue May 07 18:00:00 IDT 2019 | Sat Apr 13 08:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4032 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Sat Apr 13 08:00:00 IDT 2019 | Tue May 07 18:00:00 IDT 2019 | Sat Apr 13 08:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4033 | TT_TASK | NDE | Fri May 10 14:24:00 IDT 2019 | Tue May 28 14:24:00 IDT 2019 | Fri May 10 14:24:00 IDT 2019 | Tue Aug 27 00:00:00 IDT 2019 |  | COMPLETED
4034 | TT_TASK | EC+I | Tue May 21 14:24:00 IDT 2019 | Thu Jun 13 14:24:00 IDT 2019 | Tue May 21 14:24:00 IDT 2019 | Fri Sep 13 00:00:00 IDT 2019 |  | COMPLETED
4035 | TT_TASK | Line Inspection | Sat Aug 31 08:00:00 IDT 2019 | Wed Sep 04 18:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 |  | COMPLETED
4036 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Tue Oct 15 09:00:00 IDT 2019 | Mon Sep 30 08:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 |  | COMPLETED
4037 | TT_TASK | Painting/Insulation | Sat Jun 01 14:24:00 IDT 2019 | Wed Jun 26 14:24:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4038 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Thu Sep 19 09:00:00 IDT 2019 | Wed Oct 09 09:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4040 | TT_TASK | Install Equipment/Skids/Pumps | Mon Dec 31 08:00:00 IST 2018 | Tue Jan 15 10:00:00 IST 2019 | Mon Dec 31 08:00:00 IST 2018 | Fri Jan 11 18:00:00 IST 2019 |  | COMPLETED
4041 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 23 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Wed Jul 10 00:00:00 IDT 2019 |  | COMPLETED
4042 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Wed May 15 08:00:00 IDT 2019 | Sat May 25 18:00:00 IDT 2019 | Wed May 15 08:00:00 IDT 2019 | Wed Jul 10 00:00:00 IDT 2019 |  | COMPLETED
4043 | TT_TASK | NDE | Tue May 21 08:00:00 IDT 2019 | Fri May 31 18:00:00 IDT 2019 | Tue May 21 00:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 |  | COMPLETED
4044 | TT_TASK | EC+I | Wed Jul 10 08:00:00 IDT 2019 | Sat Jul 20 18:00:00 IDT 2019 | Wed Jul 10 08:00:00 IDT 2019 | Sat Jul 20 18:00:00 IDT 2019 |  | COMPLETED
4045 | TT_TASK | Line Inspection | Mon Jul 22 08:00:00 IDT 2019 | Wed Jul 31 18:00:00 IDT 2019 | Mon Jul 22 08:00:00 IDT 2019 | Wed Jul 31 18:00:00 IDT 2019 |  | COMPLETED
4046 | TT_TASK | Hydro Test | Wed Jul 31 08:00:00 IDT 2019 | Fri Aug 09 18:00:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 |  | COMPLETED
4047 | TT_TASK | Painting/Insulation | Wed Jul 10 08:00:00 IDT 2019 | Tue Jul 30 16:00:00 IDT 2019 | Sat May 11 00:00:00 IDT 2019 | Tue Jul 23 00:00:00 IDT 2019 |  | COMPLETED
4048 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Aug 10 08:00:00 IDT 2019 | Tue Aug 20 18:00:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 | Thu Aug 22 00:00:00 IDT 2019 |  | COMPLETED
4050 | TT_TASK | Install Equipment/Skids/Pumps | Thu Jan 24 08:00:00 IST 2019 | Fri Feb 08 10:00:00 IST 2019 | Sat Dec 15 00:00:00 IST 2018 | Thu Dec 20 00:00:00 IST 2018 |  | COMPLETED
4051 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Feb 18 17:00:00 IST 2019 | Fri Apr 12 11:00:00 IDT 2019 | Tue Feb 12 00:00:00 IST 2019 | Sat Jul 06 18:00:00 IDT 2019 |  | COMPLETED
4052 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Mon May 27 08:00:00 IDT 2019 | Fri Jun 21 10:00:00 IDT 2019 | Mon May 27 00:00:00 IDT 2019 | Mon Jul 08 08:00:00 IDT 2019 |  | COMPLETED
4053 | TT_TASK | NDE | Mon Jun 10 10:00:00 IDT 2019 | Fri Jun 21 10:00:00 IDT 2019 | Tue May 28 00:00:00 IDT 2019 | Sat Jul 13 18:00:00 IDT 2019 |  | COMPLETED
4054 | TT_TASK | E&IC Installation MBU | Mon Jul 08 08:00:00 IDT 2019 | Thu Jul 18 18:00:00 IDT 2019 | Mon Jul 08 08:00:00 IDT 2019 | Thu Jul 18 18:00:00 IDT 2019 |  | COMPLETED
4055 | TT_TASK | Line Inspection | Wed Jul 31 08:00:00 IDT 2019 | Thu Aug 08 18:00:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Sat Jun 08 00:00:00 IDT 2019 |  | COMPLETED
4056 | TT_TASK | Hydro Test | Fri Aug 09 08:00:00 IDT 2019 | Mon Aug 19 18:00:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 |  | COMPLETED
4057 | TT_TASK | Painting/Insulation | Wed Jul 31 08:00:00 IDT 2019 | Thu Aug 08 18:00:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Sat Jun 08 00:00:00 IDT 2019 |  | COMPLETED
4058 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Tue Aug 20 08:00:00 IDT 2019 | Fri Aug 30 18:00:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 |  | COMPLETED
4060 | TT_TASK | Install Equipment/Skids/Pumps | Fri Mar 01 08:00:00 IST 2019 | Tue Apr 02 12:00:00 IDT 2019 | Sat Dec 15 00:00:00 IST 2018 | Tue Apr 23 18:00:00 IDT 2019 |  | COMPLETED
4061 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Wed Apr 24 08:00:00 IDT 2019 | Tue May 14 15:00:00 IDT 2019 | Wed Apr 24 08:00:00 IDT 2019 | Sat Jul 06 18:00:00 IDT 2019 |  | COMPLETED
4062 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Thu Apr 25 15:00:00 IDT 2019 | Thu May 16 15:00:00 IDT 2019 | Thu Apr 25 15:00:00 IDT 2019 | Mon Jul 08 08:00:00 IDT 2019 |  | COMPLETED
4063 | TT_TASK | NDE | Fri May 10 14:13:00 IDT 2019 | Wed May 15 14:13:00 IDT 2019 | Fri May 10 14:13:00 IDT 2019 | Wed Jul 10 16:12:00 IDT 2019 |  | COMPLETED
4064 | TT_TASK | EC+I | Mon Jul 08 08:00:00 IDT 2019 | Wed Jul 24 18:00:00 IDT 2019 | Mon Jul 08 08:00:00 IDT 2019 | Wed Jul 24 18:00:00 IDT 2019 |  | COMPLETED
4065 | TT_TASK | Line Inspection | Wed Jul 10 16:12:00 IDT 2019 | Sat Jul 20 16:12:00 IDT 2019 | Wed Jul 10 16:12:00 IDT 2019 | Fri Jul 12 00:00:00 IDT 2019 |  | COMPLETED
4066 | TT_TASK | Hydro Test | Sat Jul 20 16:12:00 IDT 2019 | Fri Aug 02 16:12:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 | Wed Jul 17 00:00:00 IDT 2019 |  | COMPLETED
4067 | TT_TASK | Painting/Insulation | Fri Jul 05 08:00:00 IDT 2019 | Sat Jul 13 18:00:00 IDT 2019 | Fri Jul 05 08:00:00 IDT 2019 | Wed Jul 24 00:00:00 IDT 2019 |  | COMPLETED
4068 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Wed Jul 31 08:00:00 IDT 2019 | Tue Aug 13 18:00:00 IDT 2019 | Sat Jun 08 00:00:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 |  | COMPLETED
4070 | TT_TASK | Set Compressor Cleaning Package into Position -Skid | Wed Oct 31 08:00:00 IST 2018 | Mon Nov 05 16:00:00 IST 2018 | Fri Oct 26 00:00:00 IDT 2018 | Tue Oct 30 00:00:00 IST 2018 |  | COMPLETED
4071 | TT_TASK | Final Align Compressor Cleaning Package and final pipe connections | Tue Jun 18 09:48:00 IDT 2019 | Wed Jun 26 15:48:00 IDT 2019 | Sat Jun 08 00:00:00 IDT 2019 | Thu Oct 03 11:36:00 IDT 2019 |  | COMPLETED
4072 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 01 08:00:00 IDT 2019 | Mon May 06 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Thu Sep 05 00:00:00 IDT 2019 |  | COMPLETED
4073 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue Apr 23 08:00:00 IDT 2019 | Wed May 22 18:00:00 IDT 2019 | Tue Apr 23 08:00:00 IDT 2019 | Thu Sep 05 00:00:00 IDT 2019 |  | COMPLETED
4074 | TT_TASK | NDE | Mon May 06 14:24:00 IDT 2019 | Wed May 29 14:24:00 IDT 2019 | Mon May 06 14:24:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4075 | TT_TASK | EC+I | Wed May 29 14:24:00 IDT 2019 | Wed Jun 12 14:24:00 IDT 2019 | Thu May 23 00:00:00 IDT 2019 | Wed Sep 11 00:00:00 IDT 2019 |  | COMPLETED
4076 | TT_TASK | Line Inspection | Wed Sep 04 08:00:00 IDT 2019 | Thu Sep 05 18:00:00 IDT 2019 | Mon Sep 16 00:00:00 IDT 2019 | Wed Sep 18 00:00:00 IDT 2019 |  | COMPLETED
4077 | TT_TASK | Hydro Test | Fri Sep 06 08:00:00 IDT 2019 | Mon Sep 09 18:00:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4078 | TT_TASK | Painting/Insulation | Wed May 29 14:24:00 IDT 2019 | Mon Jun 03 14:24:00 IDT 2019 | Thu May 23 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4079 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Tue Sep 10 08:00:00 IDT 2019 | Thu Sep 12 18:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4081 | TT_TASK | Install Equipment/Skids/Pumps | Sat Jun 29 08:00:00 IDT 2019 | Fri Jul 05 18:00:00 IDT 2019 | Sat Jun 29 08:00:00 IDT 2019 | Fri Jul 05 18:00:00 IDT 2019 |  | COMPLETED
4082 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Sat May 04 14:00:00 IDT 2019 | Sat Jun 22 14:00:00 IDT 2019 | Wed Jan 02 00:00:00 IST 2019 | Sat Jul 06 00:00:00 IDT 2019 |  | COMPLETED
4083 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Thu Jul 04 08:00:00 IDT 2019 | Wed Jul 17 18:00:00 IDT 2019 | Thu Jul 04 08:00:00 IDT 2019 | Wed Jul 17 18:00:00 IDT 2019 |  | COMPLETED
4084 | TT_TASK | NDE | Wed Jul 10 08:00:00 IDT 2019 | Wed Jul 17 18:00:00 IDT 2019 | Wed Jul 10 08:00:00 IDT 2019 | Fri Jul 19 00:00:00 IDT 2019 |  | COMPLETED
4085 | TT_TASK | EC+I | Thu Jul 18 08:00:00 IDT 2019 | Fri Aug 09 18:00:00 IDT 2019 | Wed Jul 10 00:00:00 IDT 2019 | Sat Jul 27 00:00:00 IDT 2019 |  | COMPLETED
4086 | TT_TASK | Line Inspection | Wed Jul 10 08:00:00 IDT 2019 | Wed Jul 17 18:00:00 IDT 2019 | Wed Jul 10 08:00:00 IDT 2019 | Wed Jul 17 18:00:00 IDT 2019 |  | COMPLETED
4087 | TT_TASK | Hydro Test | Wed Jul 31 08:00:00 IDT 2019 | Sat Aug 03 18:00:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 | Sat Jun 29 00:00:00 IDT 2019 |  | COMPLETED
4088 | TT_TASK | Painting/Insulation | Sat Jul 13 08:00:00 IDT 2019 | Fri Jul 26 18:00:00 IDT 2019 | Sat Jul 13 08:00:00 IDT 2019 | Fri Jul 26 18:00:00 IDT 2019 |  | COMPLETED
4089 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Mon Aug 05 08:00:00 IDT 2019 | Mon Aug 12 18:00:00 IDT 2019 | Sat Jun 29 00:00:00 IDT 2019 | Tue Nov 12 00:00:00 IST 2019 |  | COMPLETED
4091 | TT_TASK | Installation of Ventilation System for Gas Turbine Enclosure and Skid Enclosures | Tue Apr 30 08:00:00 IDT 2019 | Fri Jun 28 16:00:00 IDT 2019 | Thu May 09 00:00:00 IDT 2019 | Thu Sep 26 00:00:00 IDT 2019 |  | COMPLETED
4093 | TT_TASK | Installation of Fire Detection System for GT Noise Enclosure MPB | Mon Jul 01 08:00:00 IDT 2019 | Wed Sep 11 16:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 | Wed Jan 08 00:00:00 IST 2020 |  | COMPLETED
4096 | TT_TASK | Set on Base Boiler Blowdown Vessel | Tue Nov 13 08:00:00 IST 2018 | Tue Nov 13 17:00:00 IST 2018 | Tue Nov 06 00:00:00 IST 2018 | Thu Nov 08 00:00:00 IST 2018 |  | COMPLETED
4097 | TT_TASK | Tie In Works to BD Vessel | Mon May 06 08:00:00 IDT 2019 | Tue May 28 18:00:00 IDT 2019 | Mon May 06 08:00:00 IDT 2019 | Thu Jun 13 18:00:00 IDT 2019 |  | COMPLETED
4098 | TT_TASK | Erection Main Piperack Structure (UMY00Y Modules) | Tue Nov 20 08:00:00 IST 2018 | Fri Dec 07 17:00:00 IST 2018 | Wed Nov 07 00:00:00 IST 2018 | Fri Nov 30 00:00:00 IST 2018 |  | COMPLETED
4099 | TT_TASK | Erection of Boiler Platforms and Ladders | Wed Oct 17 08:00:00 IDT 2018 | Fri Dec 28 17:00:00 IST 2018 | Sat Sep 15 00:00:00 IDT 2018 | Mon Mar 25 00:00:00 IST 2019 |  | COMPLETED
4100 | TT_TASK | Erection of Inlet Duct | Thu Oct 11 08:00:00 IDT 2018 | Wed Jan 09 18:00:00 IST 2019 | Tue Oct 16 00:00:00 IDT 2018 | Fri Mar 29 00:00:00 IST 2019 |  | COMPLETED
4101 | TT_TASK | Pressure Test Walkdowns and Prep | Fri Jun 14 08:00:00 IDT 2019 | Thu Jun 27 17:00:00 IDT 2019 | Tue May 14 00:00:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 |  | COMPLETED
4102 | TT_TASK | PWHT HRSG Casing roof beams | Tue Jun 26 08:00:00 IDT 2018 | Thu Jul 12 18:00:00 IDT 2018 | Sat Jun 23 08:00:00 IDT 2018 | Sat Jul 14 18:00:00 IDT 2018 |  | COMPLETED
4103 | TT_TASK | Completion Works at Roof Beams - NDE, Roof Beam Seam Welds, Painting, Insulation + Liner Plates, Modify | Mon Jul 09 08:00:00 IDT 2018 | Thu Jul 19 18:00:00 IDT 2018 | Sun Jul 15 08:00:00 IDT 2018 | Thu Jul 26 18:00:00 IDT 2018 |  | COMPLETED
4104 | TT_TASK | Installation of Main Steel Structure HRSG (Main Frame / Casing) without PWHT of roof beams | Tue Apr 03 08:00:00 IDT 2018 | Wed Jun 13 09:00:00 IDT 2018 | Fri Apr 06 08:00:00 IDT 2018 | Fri Jun 22 18:00:00 IDT 2018 |  | COMPLETED
4105 | TT_TASK | Preparation of Foundations and installation of Sole Plates | Tue Mar 06 08:00:00 IST 2018 | Thu Mar 15 18:00:00 IST 2018 | Mon Mar 12 08:00:00 IST 2018 | Mon Apr 23 00:00:00 IDT 2018 |  | COMPLETED
4107 | TT_TASK | Alignment and Installation of Modules (Heating Surfaces) | Fri Jul 20 08:00:00 IDT 2018 | Mon Aug 20 18:00:00 IDT 2018 | Fri Jul 27 08:00:00 IDT 2018 | Sat Sep 08 00:00:00 IDT 2018 |  | COMPLETED
4108 | TT_TASK | Resolve Row 2 Support Beam Issue / SPMT Working on Stack Delivery | Thu Aug 30 08:00:00 IDT 2018 | Sat Sep 15 18:00:00 IDT 2018 | Sat Aug 18 00:00:00 IDT 2018 | Fri Aug 31 00:00:00 IDT 2018 |  | COMPLETED
4109 | TT_TASK | Installation of Supports & Drums of HRSG | Mon Oct 15 08:00:00 IDT 2018 | Thu Oct 25 18:00:00 IDT 2018 | Thu Sep 20 00:00:00 IDT 2018 | Sat Oct 27 00:00:00 IDT 2018 |  | COMPLETED
4111 | TT_TASK | Modules Welding | Tue Nov 06 08:00:00 IST 2018 | Wed Nov 28 18:00:00 IST 2018 | Thu Nov 01 00:00:00 IST 2018 | Fri Nov 30 00:00:00 IST 2018 |  | COMPLETED
4114 | TT_TASK | Erect Stair Towers | Sat May 26 08:00:00 IDT 2018 | Thu Jul 19 18:00:00 IDT 2018 | Mon Jun 11 08:00:00 IDT 2018 | Mon Oct 29 00:00:00 IST 2018 |  | COMPLETED
4116 | TT_TASK | Installation of HRSG Piping | Tue Nov 06 08:00:00 IST 2018 | Mon May 13 16:00:00 IDT 2019 | Wed Nov 07 00:00:00 IST 2018 | Tue May 28 00:00:00 IDT 2019 |  | COMPLETED
4117 | TT_TASK | Reconfigure Post Hydro Test | Wed Oct 02 09:42:00 IDT 2019 | Thu Oct 24 09:42:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 | Fri Nov 29 00:00:00 IST 2019 |  | COMPLETED
4118 | TT_TASK | Completion of the HRSG ready to start Piping | Fri Oct 19 08:00:00 IDT 2018 | Wed Oct 24 14:00:00 IDT 2018 | Fri Oct 12 00:00:00 IDT 2018 | Wed Oct 24 14:00:00 IDT 2018 |  | COMPLETED
4120 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Dec 10 08:00:00 IST 2018 | Fri Apr 05 11:00:00 IDT 2019 | Fri Nov 23 00:00:00 IST 2018 | Sat May 25 00:00:00 IDT 2019 |  | COMPLETED
4121 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Thu Feb 21 08:00:00 IST 2019 | Tue May 07 18:00:00 IDT 2019 | Thu Feb 21 08:00:00 IST 2019 | Fri Jun 14 16:12:00 IDT 2019 |  | COMPLETED
4122 | TT_TASK | NDE | Fri Jan 25 09:00:00 IST 2019 | Tue May 07 18:00:00 IDT 2019 | Fri Nov 23 00:00:00 IST 2018 | Tue Jun 18 00:00:00 IDT 2019 |  | COMPLETED
4123 | TT_TASK | EC+I | Sat Jun 15 13:30:00 IDT 2019 | Mon Jul 22 13:30:00 IDT 2019 | Sat May 18 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4124 | TT_TASK | Line Inspection | Fri Jun 07 15:24:00 IDT 2019 | Wed Jun 12 15:24:00 IDT 2019 | Mon May 13 00:00:00 IDT 2019 | Fri May 17 00:00:00 IDT 2019 |  | COMPLETED
4125 | TT_TASK | Hydro Test with HRSG | Thu Jun 27 17:00:00 IDT 2019 | Thu Jul 04 17:00:00 IDT 2019 | Sat May 18 00:00:00 IDT 2019 | Sat May 25 00:00:00 IDT 2019 |  | COMPLETED
4126 | TT_TASK | Painting/Insulation | Sat Jun 15 13:30:00 IDT 2019 | Wed Jul 17 13:30:00 IDT 2019 | Sat May 18 00:00:00 IDT 2019 | Fri Nov 22 00:00:00 IST 2019 |  | COMPLETED
4127 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Wed Sep 25 11:24:00 IDT 2019 | Wed Oct 09 11:24:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 | Fri Nov 22 00:00:00 IST 2019 |  | COMPLETED
4129 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Dec 10 08:00:00 IST 2018 | Fri Apr 05 11:00:00 IDT 2019 | Fri Nov 09 00:00:00 IST 2018 | Wed May 22 00:00:00 IDT 2019 |  | COMPLETED
4130 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue Feb 12 08:00:00 IST 2019 | Fri Apr 26 18:00:00 IDT 2019 | Fri Nov 09 00:00:00 IST 2018 | Fri Jun 14 16:12:00 IDT 2019 |  | COMPLETED
4131 | TT_TASK | NDE | Tue Mar 05 08:00:00 IST 2019 | Wed Apr 24 18:00:00 IDT 2019 | Fri Nov 09 00:00:00 IST 2018 | Tue Jun 18 00:00:00 IDT 2019 |  | COMPLETED
4132 | TT_TASK | EC+I | Sat Jun 15 13:30:00 IDT 2019 | Sat Jul 27 13:30:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4133 | TT_TASK | Line Inspection | Sat Jun 15 09:48:00 IDT 2019 | Tue Jun 25 09:48:00 IDT 2019 | Sat Jun 15 09:48:00 IDT 2019 | Tue Jun 25 09:48:00 IDT 2019 |  | COMPLETED
4134 | TT_TASK | Hydro Test with HRSG | Fri Jun 28 15:18:00 IDT 2019 | Sat Jul 13 15:18:00 IDT 2019 | Fri Jun 21 00:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 |  | COMPLETED
4135 | TT_TASK | Painting/Insulation | Sat Jun 15 13:30:00 IDT 2019 | Wed Jul 17 13:30:00 IDT 2019 | Mon May 13 00:00:00 IDT 2019 | Fri Nov 22 00:00:00 IST 2019 |  | COMPLETED
4136 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Fri Sep 06 09:48:00 IDT 2019 | Sat Sep 21 09:48:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 | Fri Nov 22 00:00:00 IST 2019 |  | COMPLETED
4138 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Dec 10 08:00:00 IST 2018 | Tue Apr 30 10:00:00 IDT 2019 | Thu Nov 08 00:00:00 IST 2018 | Fri May 17 00:00:00 IDT 2019 |  | COMPLETED
4139 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Sat Feb 23 08:00:00 IST 2019 | Fri Apr 26 18:00:00 IDT 2019 | Thu Nov 08 00:00:00 IST 2018 | Tue May 14 00:00:00 IDT 2019 |  | COMPLETED
4140 | TT_TASK | NDE | Fri Feb 01 08:00:00 IST 2019 | Fri Mar 22 18:00:00 IST 2019 | Tue Apr 30 00:00:00 IDT 2019 | Mon May 20 18:00:00 IDT 2019 |  | COMPLETED
4141 | TT_TASK | EC+I | Sat Jun 15 08:00:00 IDT 2019 | Sat Jul 20 18:00:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4142 | TT_TASK | Line Inspection | Thu Jun 27 11:36:00 IDT 2019 | Tue Jul 16 11:36:00 IDT 2019 | Thu Jun 27 00:00:00 IDT 2019 | Sat Jul 06 00:00:00 IDT 2019 |  | COMPLETED
4143 | TT_TASK | Hydro Test with HRSG | Mon Sep 02 08:00:00 IDT 2019 | Thu Sep 12 18:00:00 IDT 2019 | Fri Aug 30 00:00:00 IDT 2019 | Sat Oct 26 00:00:00 IDT 2019 |  | COMPLETED
4144 | TT_TASK | Painting/Insulation | Fri May 31 08:00:00 IDT 2019 | Sat Jun 29 18:00:00 IDT 2019 | Fri May 31 08:00:00 IDT 2019 | Fri Nov 22 00:00:00 IST 2019 |  | COMPLETED
4145 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Thu Oct 24 09:42:00 IDT 2019 | Tue Nov 05 09:42:00 IST 2019 | Sat Oct 05 00:00:00 IDT 2019 | Fri Nov 22 00:00:00 IST 2019 |  | COMPLETED
4147 | TT_TASK | Install Equipment/Skids/Pumps | Fri May 24 08:00:00 IDT 2019 | Tue Jun 04 15:00:00 IDT 2019 | Thu May 23 16:00:00 IDT 2019 | Mon Jun 10 00:00:00 IDT 2019 |  | COMPLETED
4148 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Dec 10 08:00:00 IST 2018 | Sat Feb 02 18:00:00 IST 2019 | Mon Dec 10 08:00:00 IST 2018 | Tue May 21 00:00:00 IDT 2019 |  | COMPLETED
4149 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Wed Apr 17 09:02:00 IDT 2019 | Tue May 28 08:02:00 IDT 2019 | Thu Jan 17 00:00:00 IST 2019 | Tue Jun 25 16:36:00 IDT 2019 |  | COMPLETED
4150 | TT_TASK | NDE | Wed Apr 17 09:02:00 IDT 2019 | Tue May 28 08:02:00 IDT 2019 | Mon Dec 10 00:00:00 IST 2018 | Thu Jun 27 00:00:00 IDT 2019 |  | COMPLETED
4151 | TT_TASK | EC+I | Fri Jun 28 08:00:00 IDT 2019 | Mon Jul 22 18:00:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4152 | TT_TASK | Line Inspection | Tue Jun 25 16:36:00 IDT 2019 | Mon Jul 08 16:36:00 IDT 2019 | Tue Jun 25 16:36:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4153 | TT_TASK | Hydro Test | Thu Jul 11 08:00:00 IDT 2019 | Wed Jul 24 18:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4154 | TT_TASK | Painting/Insulation | Fri Jun 28 08:00:00 IDT 2019 | Tue Jul 23 18:00:00 IDT 2019 | Fri May 17 00:00:00 IDT 2019 | Mon Nov 11 00:00:00 IST 2019 |  | COMPLETED
4155 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Tue Sep 17 08:00:00 IDT 2019 | Mon Sep 30 18:00:00 IDT 2019 | Mon Sep 09 00:00:00 IDT 2019 | Mon Nov 11 00:00:00 IST 2019 |  | COMPLETED
4157 | TT_TASK | Insulation of Stack + Complete Outlet Duct | Tue Apr 30 08:00:00 IDT 2019 | Tue Aug 06 14:00:00 IDT 2019 | Mon May 13 00:00:00 IDT 2019 | Thu Nov 21 00:00:00 IST 2019 |  | COMPLETED
4158 | TT_TASK | Erection of Stack | Mon Oct 15 08:00:00 IDT 2018 | Mon Apr 15 18:00:00 IDT 2019 | Fri Aug 31 00:00:00 IDT 2018 | Thu Jun 20 00:00:00 IDT 2019 |  | COMPLETED
4160 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Fri Feb 08 08:00:00 IST 2019 | Mon May 06 18:00:00 IDT 2019 | Fri Feb 08 08:00:00 IST 2019 | Sat Jul 27 00:00:00 IDT 2019 |  | COMPLETED
4161 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Mon Mar 04 08:00:00 IST 2019 | Thu May 30 18:00:00 IDT 2019 | Mon Mar 04 08:00:00 IST 2019 | Thu Jul 25 00:00:00 IDT 2019 |  | COMPLETED
4162 | TT_TASK | NDE | Mon Mar 25 17:00:00 IST 2019 | Tue Jun 11 17:00:00 IDT 2019 | Mon Mar 25 17:00:00 IST 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4163 | TT_TASK | EC+I | Tue Jun 18 08:00:00 IDT 2019 | Tue Jul 23 18:00:00 IDT 2019 | Sat Jun 08 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4164 | TT_TASK | Line Inspection | Mon Jul 08 08:24:00 IDT 2019 | Wed Jul 17 08:24:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 | Wed Aug 07 18:00:00 IDT 2019 |  | COMPLETED
4165 | TT_TASK | Hydro Test | Mon Aug 05 08:00:00 IDT 2019 | Thu Aug 15 18:00:00 IDT 2019 | Mon Aug 05 00:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4166 | TT_TASK | Painting/Insulation | Tue May 21 13:30:00 IDT 2019 | Sat Jun 22 14:30:00 IDT 2019 | Tue May 21 13:30:00 IDT 2019 | Fri Nov 15 00:00:00 IST 2019 |  | COMPLETED
4167 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Thu Sep 05 09:57:00 IDT 2019 | Wed Sep 18 09:57:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 | Fri Nov 15 00:00:00 IST 2019 |  | COMPLETED
4169 | TT_TASK | Skid/Panels/Cabinets Installation | Tue Jun 18 08:00:00 IDT 2019 | Fri Jul 05 18:00:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Fri Jun 14 15:45:00 IDT 2019 |  | COMPLETED
4170 | TT_TASK | Cable Raceway | Thu Mar 28 08:00:00 IST 2019 | Thu Apr 18 17:00:00 IDT 2019 | Fri Mar 15 00:00:00 IST 2019 | Thu Jun 20 13:15:00 IDT 2019 |  | COMPLETED
4171 | TT_TASK | Cable | Thu Jun 20 13:15:00 IDT 2019 | Tue Jul 09 13:15:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Mon Jun 10 00:00:00 IDT 2019 |  | COMPLETED
4172 | TT_TASK | Tubing | Fri Jun 14 15:45:00 IDT 2019 | Sat Jul 06 15:45:00 IDT 2019 | Fri Jun 14 15:45:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4173 | TT_TASK | Instrumentation | Wed Jul 31 10:15:00 IDT 2019 | Mon Aug 19 10:15:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 |  | COMPLETED
4174 | TT_TASK | Installation CEMS equiptment on Stack | Fri Jun 14 15:45:00 IDT 2019 | Fri Jul 26 15:45:00 IDT 2019 | Fri Jun 14 15:45:00 IDT 2019 | Fri Sep 06 00:00:00 IDT 2019 |  | COMPLETED
4176 | TT_TASK | Installation of Cable Support Structure for HRSG | Wed Apr 24 15:00:00 IDT 2019 | Sat Jul 20 15:00:00 IDT 2019 | Wed Apr 24 15:00:00 IDT 2019 | Sat Jun 29 00:00:00 IDT 2019 |  | COMPLETED
4177 | TT_TASK | Installation & Termination of Power & Control Cable for HRSG | Fri May 24 15:00:00 IDT 2019 | Mon Aug 12 15:00:00 IDT 2019 | Fri May 24 15:00:00 IDT 2019 | Wed Jun 26 00:00:00 IDT 2019 |  | COMPLETED
4178 | TT_TASK | Installation of Distribution Panel & Control Panel and Racks for HRSG | Wed Apr 24 08:00:00 IDT 2019 | Mon Jun 10 18:00:00 IDT 2019 | Wed Apr 24 08:00:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 |  | COMPLETED
4179 | TT_TASK | Installation of Instrumentation for HRSG | Mon Apr 01 08:00:00 IDT 2019 | Mon Jun 10 18:00:00 IDT 2019 | Mon Apr 22 00:00:00 IDT 2019 | Fri Jun 28 08:00:00 IDT 2019 |  | COMPLETED
4180 | TT_TASK | Installation & Termination of Cable for Lighting Fittings for HRSG | Mon Feb 25 09:00:00 IST 2019 | Wed Apr 24 09:00:00 IDT 2019 | Mon Jan 14 00:00:00 IST 2019 | Thu Jun 27 00:00:00 IDT 2019 |  | COMPLETED
4184 | TT_TASK | Set Up Equipment on Site | Sat Sep 29 08:00:00 IDT 2018 | Mon Oct 08 18:00:00 IDT 2018 | Mon Aug 20 00:00:00 IDT 2018 | Wed Aug 22 00:00:00 IDT 2018 |  | COMPLETED
4185 | TT_TASK | Check and Prep of Foundation | Thu Aug 30 08:00:00 IDT 2018 | Wed Sep 12 18:00:00 IDT 2018 | Wed Aug 22 00:00:00 IDT 2018 | Thu Aug 23 00:00:00 IDT 2018 |  | COMPLETED
4186 | TT_TASK | Prepare Generator and Lower onto Foundation | Tue Oct 23 08:00:00 IDT 2018 | Mon Oct 29 18:00:00 IST 2018 | Sat Sep 22 00:00:00 IDT 2018 | Mon Sep 24 00:00:00 IDT 2018 |  | COMPLETED
4188 | TT_TASK | Shift Generator into Position | Tue Oct 23 08:00:00 IDT 2018 | Wed Oct 24 16:00:00 IDT 2018 | Wed Sep 26 00:00:00 IDT 2018 | Thu Oct 04 00:00:00 IDT 2018 |  | COMPLETED
4189 | TT_TASK | Recording the Axial Adjustment of the Shaft System | Mon Dec 31 08:00:00 IST 2018 | Thu Jan 17 18:00:00 IST 2019 | Mon Jan 14 00:00:00 IST 2019 | Thu Feb 28 00:00:00 IST 2019 |  | COMPLETED
4190 | TT_TASK | Installation and Coupling of Collector Rotor, Swing Check, Decoupling | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 12 18:00:00 IDT 2019 | Fri Apr 05 00:00:00 IDT 2019 | Sat Apr 27 18:00:00 IDT 2019 |  | COMPLETED
4192 | TT_TASK | EC&I | Sat Apr 13 08:00:00 IDT 2019 | Sat May 25 18:00:00 IDT 2019 | Mon Apr 15 00:00:00 IDT 2019 | Wed Sep 04 00:00:00 IDT 2019 |  | COMPLETED
4195 | TT_TASK | Install Isophase Supports | Mon Dec 31 08:00:00 IST 2018 | Tue Jan 08 18:00:00 IST 2019 | Thu Jan 03 00:00:00 IST 2019 | Tue Jan 08 18:00:00 IST 2019 |  | COMPLETED
4196 | TT_TASK | Install Bushings | Wed Jan 09 08:00:00 IST 2019 | Sat Jan 19 18:00:00 IST 2019 | Mon Jan 21 00:00:00 IST 2019 | Fri Feb 01 00:00:00 IST 2019 |  | COMPLETED
4198 | TT_TASK | Removal of Transport Covers, Installation of Frame Covers | Sat Mar 16 13:00:00 IST 2019 | Tue Mar 19 10:00:00 IST 2019 | Sat Oct 20 00:00:00 IDT 2018 | Thu Oct 25 00:00:00 IDT 2018 |  | COMPLETED
4199 | TT_TASK | Install H2 Shaft Seals | Wed Nov 07 08:00:00 IST 2018 | Sat Nov 24 14:00:00 IST 2018 | Mon Nov 19 00:00:00 IST 2018 | Thu Dec 20 00:00:00 IST 2018 |  | COMPLETED
4200 | TT_TASK | Common Coupling Alignment GT/Gen/ST (with Installed Clutch) | Sat Feb 02 15:00:00 IST 2019 | Wed Mar 13 15:00:00 IST 2019 | Mon Jan 14 00:00:00 IST 2019 | Fri Apr 12 00:00:00 IDT 2019 |  | COMPLETED
4201 | TT_TASK | Fix Generator into Position | Mon Feb 11 08:00:00 IST 2019 | Thu Feb 21 18:00:00 IST 2019 | Mon Feb 11 08:00:00 IST 2019 | Thu Feb 21 18:00:00 IST 2019 |  | COMPLETED
4202 | TT_TASK | Grouting the Generator Foundation Beams | Mon Feb 25 14:00:00 IST 2019 | Wed Mar 06 14:00:00 IST 2019 | Thu Mar 07 00:00:00 IST 2019 | Thu Mar 07 00:00:00 IST 2019 |  | COMPLETED
4203 | TT_TASK | Coupling of Collector Rotor | Fri Feb 22 08:00:00 IST 2019 | Mon Feb 25 18:00:00 IST 2019 | Fri Feb 15 00:00:00 IST 2019 | Tue Apr 09 00:00:00 IDT 2019 |  | COMPLETED
4205 | TT_TASK | Assembling of Collector | Wed Apr 10 13:30:00 IDT 2019 | Fri Apr 26 13:30:00 IDT 2019 | Wed Apr 10 13:30:00 IDT 2019 | Fri Apr 12 00:00:00 IDT 2019 |  | COMPLETED
4206 | TT_TASK | Removal of Dessicant Bags (Timing to Start - TBE) | Sat Aug 31 08:00:00 IDT 2019 | Mon Sep 02 18:00:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 |  | COMPLETED
4207 | TT_TASK | Generator Leak Test | Fri Oct 04 08:00:00 IDT 2019 | Tue Oct 08 18:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4208 | TT_TASK | Install Bearing Bracket Oil Seals TE/EE | Fri May 03 08:00:00 IDT 2019 | Mon May 06 18:00:00 IDT 2019 | Fri May 03 08:00:00 IDT 2019 | Mon May 06 18:00:00 IDT 2019 |  | COMPLETED
4209 | TT_TASK | Install Grounding Brushes | Tue May 07 08:00:00 IDT 2019 | Tue May 07 18:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
4210 | TT_TASK | Install Coupling Cover | Mon Jun 03 17:06:00 IDT 2019 | Tue Jun 04 16:06:00 IDT 2019 | Tue Jun 25 00:00:00 IDT 2019 | Tue Oct 08 18:00:00 IDT 2019 |  | COMPLETED
4211 | TT_TASK | Pre-Commissioning/Cleaning | Wed Oct 09 08:00:00 IDT 2019 | Wed Oct 16 18:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 | Fri Oct 25 00:00:00 IDT 2019 |  | COMPLETED
4213 | TT_TASK | Install Equipment/Skids/Pumps | Sat Dec 15 17:00:00 IST 2018 | Mon Dec 24 17:00:00 IST 2018 | Fri Oct 19 00:00:00 IDT 2018 | Fri Oct 26 00:00:00 IDT 2018 |  | COMPLETED
4214 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Wed Mar 06 08:00:00 IST 2019 | Thu Mar 28 18:00:00 IST 2019 | Mon Oct 15 00:00:00 IDT 2018 | Thu May 23 18:00:00 IDT 2019 |  | COMPLETED
4215 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue Apr 16 14:24:00 IDT 2019 | Fri May 10 14:24:00 IDT 2019 | Wed Mar 20 00:00:00 IST 2019 | Sat Apr 13 09:48:00 IDT 2019 |  | COMPLETED
4216 | TT_TASK | NDE | Tue Apr 30 08:00:00 IDT 2019 | Tue May 14 09:00:00 IDT 2019 | Thu Apr 11 00:00:00 IDT 2019 | Thu May 23 00:00:00 IDT 2019 |  | COMPLETED
4217 | TT_TASK | EC+I | Sat Apr 13 08:00:00 IDT 2019 | Fri Apr 26 09:00:00 IDT 2019 | Sat Apr 13 08:00:00 IDT 2019 | Wed Aug 07 00:00:00 IDT 2019 |  | COMPLETED
4218 | TT_TASK | Line Inspection | Fri May 31 08:00:00 IDT 2019 | Mon Jun 03 18:00:00 IDT 2019 | Mon Jun 03 00:00:00 IDT 2019 | Sat Jun 29 00:00:00 IDT 2019 |  | COMPLETED
4219 | TT_TASK | Hydro Test | Wed Jul 31 08:00:00 IDT 2019 | Mon Aug 05 18:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4220 | TT_TASK | Painting/Insulation | Wed Jun 12 15:00:00 IDT 2019 | Fri Jun 21 12:00:00 IDT 2019 | Mon May 13 00:00:00 IDT 2019 | Mon Aug 26 00:00:00 IDT 2019 |  | COMPLETED
4221 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Mon Sep 30 08:00:00 IDT 2019 | Wed Oct 16 18:00:00 IDT 2019 | Mon Sep 30 08:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 |  | COMPLETED
4223 | TT_TASK | Install Equipment/Skids/Pumps | Wed Oct 31 08:00:00 IST 2018 | Wed Nov 07 18:00:00 IST 2018 | Tue Oct 02 00:00:00 IDT 2018 | Wed Oct 10 00:00:00 IDT 2018 |  | COMPLETED
4224 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Thu Jan 31 08:00:00 IST 2019 | Sat Mar 16 18:00:00 IST 2019 | Mon Oct 15 00:00:00 IDT 2018 | Sun May 26 00:00:00 IDT 2019 |  | COMPLETED
4225 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue May 07 15:00:00 IDT 2019 | Thu Jun 06 15:00:00 IDT 2019 | Wed Mar 20 00:00:00 IST 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4226 | TT_TASK | NDE | Sat Jun 01 08:00:00 IDT 2019 | Sat Jul 06 18:00:00 IDT 2019 | Wed May 22 00:00:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 |  | COMPLETED
4227 | TT_TASK | EC+I | Tue Jun 25 08:00:00 IDT 2019 | Tue Jul 23 18:00:00 IDT 2019 | Fri May 17 00:00:00 IDT 2019 | Wed Sep 18 00:00:00 IDT 2019 |  | COMPLETED
4228 | TT_TASK | Line Inspection | Mon Aug 19 11:36:00 IDT 2019 | Sat Aug 24 11:36:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4229 | TT_TASK | Hydro Test | Tue Oct 15 08:00:00 IDT 2019 | Fri Oct 18 18:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4230 | TT_TASK | Painting/Insulation | Thu Jun 13 08:00:00 IDT 2019 | Wed Jul 03 18:00:00 IDT 2019 | Thu Jun 27 00:00:00 IDT 2019 | Mon Oct 28 00:00:00 IST 2019 |  | COMPLETED
4231 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Tue Oct 22 08:00:00 IDT 2019 | Fri Oct 25 18:00:00 IDT 2019 | Mon Oct 28 00:00:00 IST 2019 | Wed Nov 20 13:57:00 IST 2019 |  | COMPLETED
4233 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 09 18:00:00 IDT 2019 | Mon Apr 08 00:00:00 IDT 2019 | Tue Jun 11 00:00:00 IDT 2019 |  | COMPLETED
4234 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Thu Mar 14 08:00:00 IST 2019 | Sat Apr 06 18:00:00 IDT 2019 | Mon Jan 07 00:00:00 IST 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
4235 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Thu Apr 25 08:00:00 IDT 2019 | Mon May 20 18:00:00 IDT 2019 | Wed Mar 20 00:00:00 IST 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
4236 | TT_TASK | NDE | Tue Apr 09 15:48:00 IDT 2019 | Sat Apr 20 15:48:00 IDT 2019 | Tue Apr 09 15:48:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 |  | COMPLETED
4237 | TT_TASK | EC+I | Wed Apr 24 08:00:00 IDT 2019 | Wed May 08 18:00:00 IDT 2019 | Wed Apr 24 08:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4238 | TT_TASK | Line Inspection | Sat Aug 31 10:42:00 IDT 2019 | Mon Sep 09 10:42:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 | Tue Sep 17 00:00:00 IDT 2019 |  | COMPLETED
4239 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Sat Oct 05 18:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 | Fri Oct 11 18:00:00 IDT 2019 |  | COMPLETED
4240 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Tue Oct 08 08:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 | Mon Oct 07 00:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 |  | COMPLETED
4242 | TT_TASK | Install Equipment/Skids/Pumps | Thu Nov 01 08:00:00 IST 2018 | Mon Nov 12 18:00:00 IST 2018 | Wed Oct 17 00:00:00 IDT 2018 | Sat Oct 27 00:00:00 IDT 2018 |  | COMPLETED
4243 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 01 08:00:00 IDT 2019 | Tue May 07 18:00:00 IDT 2019 | Thu Nov 01 00:00:00 IST 2018 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4244 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Wed May 08 08:00:00 IDT 2019 | Tue Jun 04 10:00:00 IDT 2019 | Mon Nov 05 00:00:00 IST 2018 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4245 | TT_TASK | NDE | Tue Apr 30 13:00:00 IDT 2019 | Fri May 24 12:00:00 IDT 2019 | Fri May 17 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4246 | TT_TASK | EC+I | Tue Apr 30 08:00:00 IDT 2019 | Thu May 23 18:00:00 IDT 2019 | Fri May 17 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4247 | TT_TASK | Line Inspection | Wed Aug 07 14:35:00 IDT 2019 | Mon Aug 12 14:35:00 IDT 2019 | Mon Aug 05 00:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4248 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Wed Oct 09 18:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 |  | COMPLETED
4249 | TT_TASK | Painting/Insulation | Thu Jul 04 08:54:00 IDT 2019 | Sat Jul 27 08:54:00 IDT 2019 | Wed Jul 24 00:00:00 IDT 2019 | Fri Nov 01 00:00:00 IST 2019 |  | COMPLETED
4250 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Thu Oct 10 08:00:00 IDT 2019 | Fri Oct 18 18:00:00 IDT 2019 | Mon Oct 14 00:00:00 IDT 2019 | Fri Nov 01 00:00:00 IST 2019 |  | COMPLETED
4254 | TT_TASK | Preparation of Feed Water Pump Foundations | Mon Feb 11 08:00:00 IST 2019 | Thu Feb 14 18:00:00 IST 2019 | Tue Jan 29 00:00:00 IST 2019 | Thu Feb 07 00:00:00 IST 2019 |  | COMPLETED
4255 | TT_TASK | Install Feedwater Pump Skid (LAC10Y) | Fri Feb 15 08:00:00 IST 2019 | Thu Feb 28 17:00:00 IST 2019 | Fri Feb 15 08:00:00 IST 2019 | Wed May 08 17:30:00 IDT 2019 |  | COMPLETED
4256 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Sat Apr 13 08:00:00 IDT 2019 | Tue Jun 04 18:00:00 IDT 2019 | Sat Apr 13 08:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4257 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Thu May 23 09:48:00 IDT 2019 | Fri Jul 05 08:48:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4258 | TT_TASK | NDE | Thu May 16 08:48:00 IDT 2019 | Fri Jul 05 08:48:00 IDT 2019 | Thu May 16 08:48:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 |  | COMPLETED
4259 | TT_TASK | EC+I | Mon Jun 10 09:48:00 IDT 2019 | Tue Jul 16 09:48:00 IDT 2019 | Wed May 22 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4260 | TT_TASK | Line Inspection | Thu Jul 04 14:18:00 IDT 2019 | Fri Jul 12 14:18:00 IDT 2019 | Sat Jul 27 00:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4261 | TT_TASK | Hydro Test | Sat Aug 31 08:00:00 IDT 2019 | Sat Sep 07 18:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4262 | TT_TASK | Painting/Insulation | Thu Jun 27 10:57:00 IDT 2019 | Tue Jul 16 10:57:00 IDT 2019 | Fri Jun 21 00:00:00 IDT 2019 | Thu Nov 14 00:00:00 IST 2019 |  | COMPLETED
4263 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Mon Sep 30 08:00:00 IDT 2019 | Thu Oct 17 17:00:00 IDT 2019 | Thu Oct 03 00:00:00 IDT 2019 | Thu Nov 14 00:00:00 IST 2019 |  | COMPLETED
4265 | TT_TASK | Install Equipment/Skids/Pumps/ | Mon Apr 01 08:00:00 IDT 2019 | Wed May 08 18:00:00 IDT 2019 | Fri Mar 01 00:00:00 IST 2019 | Tue Jun 18 00:00:00 IDT 2019 |  | COMPLETED
4266 | TT_TASK | Insulation of FInal Weld Connections | Sat Aug 31 13:30:00 IDT 2019 | Tue Sep 17 13:30:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 | Thu Nov 14 00:00:00 IST 2019 |  | COMPLETED
4267 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Thu Feb 28 17:00:00 IST 2019 | Fri May 10 11:00:00 IDT 2019 | Thu Feb 28 17:00:00 IST 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4268 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue May 14 17:03:00 IDT 2019 | Sat Jun 22 09:03:00 IDT 2019 | Tue May 14 17:03:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4269 | TT_TASK | NDE | Sat May 04 10:03:00 IDT 2019 | Sat Jun 22 09:03:00 IDT 2019 | Sat May 04 10:03:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4270 | TT_TASK | EC+I | Fri May 31 17:03:00 IDT 2019 | Sat Jul 06 17:03:00 IDT 2019 | Fri May 24 00:00:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 |  | COMPLETED
4271 | TT_TASK | Line Inspection & Preparation for Neutral Float Welds | Mon Jun 10 14:12:00 IDT 2019 | Fri Jun 21 14:12:00 IDT 2019 | Tue Jun 18 00:00:00 IDT 2019 | Sat Jul 27 00:00:00 IDT 2019 |  | COMPLETED
4272 | TT_TASK | Neural Float & Final Weld Connections to FW Pump | Sat Jun 29 08:00:00 IDT 2019 | Thu Jul 11 18:00:00 IDT 2019 | Sat Jul 27 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4273 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 | Wed Oct 02 00:00:00 IDT 2019 | Tue Oct 08 00:00:00 IDT 2019 |  | COMPLETED
4274 | TT_TASK | Insulation of Pipework Prior to Neutral Float | Fri Jun 07 14:12:00 IDT 2019 | Tue Jul 02 14:12:00 IDT 2019 | Fri Jun 14 00:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4275 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Mon Oct 14 08:00:00 IDT 2019 | Thu Oct 24 18:00:00 IDT 2019 | Thu Oct 03 00:00:00 IDT 2019 | Thu Nov 14 00:00:00 IST 2019 |  | COMPLETED
4277 | TT_TASK | Install Make-up Water/NOx Pumps & Pressure System (Tank/Controls) | Mon Jan 21 08:00:00 IST 2019 | Thu Feb 21 18:00:00 IST 2019 | Tue Jan 15 00:00:00 IST 2019 | Tue May 07 18:00:00 IDT 2019 |  | COMPLETED
4278 | TT_TASK | Install NOx Piping from Existing Demin Tank to GT NOx Control Pump including Recir Line | Wed Apr 24 08:00:00 IDT 2019 | Tue Jul 16 18:00:00 IDT 2019 | Wed Apr 24 08:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4279 | TT_TASK | Install Make-up Water Piping from Existing Demin Tank to Connection Points of New CCGT | Tue Apr 30 08:00:00 IDT 2019 | Mon Jul 22 18:00:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4280 | TT_TASK | NDE | Sat Jun 22 08:00:00 IDT 2019 | Mon Jul 29 18:00:00 IDT 2019 | Tue May 14 00:00:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 |  | COMPLETED
4281 | TT_TASK | EC+I | Tue Jul 23 08:00:00 IDT 2019 | Fri Sep 06 17:00:00 IDT 2019 | Thu May 23 00:00:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 |  | COMPLETED
4282 | TT_TASK | Line Inspection | Sat Jul 20 13:30:00 IDT 2019 | Mon Jul 29 13:30:00 IDT 2019 | Thu Jul 11 00:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 |  | COMPLETED
4283 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Wed Oct 09 18:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 |  | COMPLETED
4284 | TT_TASK | Painting/Insulation | Tue Aug 13 08:16:00 IDT 2019 | Fri Sep 20 08:16:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Tue Oct 15 00:00:00 IDT 2019 |  | COMPLETED
4285 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Tue Oct 15 16:12:00 IDT 2019 | Wed Oct 23 15:12:00 IDT 2019 | Tue Oct 15 16:12:00 IDT 2019 | Mon Nov 04 00:00:00 IST 2019 |  | COMPLETED
4289 | TT_TASK | Install Equipment/Skids/Pumps | Mon Feb 18 17:00:00 IST 2019 | Wed Mar 06 16:00:00 IST 2019 | Sat Sep 15 00:00:00 IDT 2018 | Tue Sep 25 00:00:00 IDT 2018 |  | COMPLETED
4290 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Wed Mar 06 16:00:00 IST 2019 | Fri May 03 09:00:00 IDT 2019 | Sat Sep 15 00:00:00 IDT 2018 | Sat Jul 27 00:00:00 IDT 2019 |  | COMPLETED
4291 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Wed Apr 03 09:57:00 IDT 2019 | Fri May 03 09:57:00 IDT 2019 | Fri Apr 05 00:00:00 IDT 2019 | Sat Jul 27 00:00:00 IDT 2019 |  | COMPLETED
4292 | TT_TASK | EC+I | Mon Jun 10 08:00:00 IDT 2019 | Thu Jul 04 17:00:00 IDT 2019 | Fri May 10 00:00:00 IDT 2019 | Fri Sep 27 00:00:00 IDT 2019 |  | COMPLETED
4293 | TT_TASK | Line Inspection | Tue Jul 23 10:36:00 IDT 2019 | Mon Aug 05 10:36:00 IDT 2019 | Wed Jul 24 00:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4294 | TT_TASK | Hydro Test | Wed Aug 07 11:24:00 IDT 2019 | Wed Aug 21 11:24:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4295 | TT_TASK | Painting/Insulation | Fri May 03 09:57:00 IDT 2019 | Sat Jun 15 08:57:00 IDT 2019 | Fri May 03 09:57:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4296 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Mon Sep 16 08:36:00 IDT 2019 | Mon Sep 30 08:36:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Fri Nov 08 13:24:00 IST 2019 |  | COMPLETED
4298 | TT_TASK | Install Equipment/Skids/Pumps | Fri Feb 15 08:00:00 IST 2019 | Fri Mar 01 16:00:00 IST 2019 | Sat Sep 15 00:00:00 IDT 2018 | Tue Sep 25 00:00:00 IDT 2018 |  | COMPLETED
4299 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Fri Nov 16 08:00:00 IST 2018 | Mon Jan 28 18:00:00 IST 2019 | Sat Sep 01 00:00:00 IDT 2018 | Tue May 21 00:00:00 IDT 2019 |  | COMPLETED
4300 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Mon Jun 10 09:00:00 IDT 2019 | Mon Jul 08 09:00:00 IDT 2019 | Fri May 10 00:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4301 | TT_TASK | EC+I | Thu Jul 04 08:00:00 IDT 2019 | Wed Jul 17 16:00:00 IDT 2019 | Sat Jun 08 00:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4302 | TT_TASK | Line Inspection | Tue Jul 02 09:21:00 IDT 2019 | Mon Jul 15 09:21:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 | Sat Jul 27 00:00:00 IDT 2019 |  | COMPLETED
4303 | TT_TASK | Hydro Test | Wed Jul 31 08:00:00 IDT 2019 | Wed Aug 14 18:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4304 | TT_TASK | Painting/Insulation | Thu Jul 04 08:00:00 IDT 2019 | Fri Jul 26 18:00:00 IDT 2019 | Tue Jun 04 00:00:00 IDT 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
4305 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Aug 31 08:00:00 IDT 2019 | Fri Sep 13 18:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
4309 | TT_TASK | Install Equipment/Skids/Pumps | Fri May 31 08:00:00 IDT 2019 | Tue Jun 18 16:00:00 IDT 2019 | Mon Jun 10 00:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4310 | TT_TASK | Install Pipe/Valves/Supports (Inside+Outside) | Sat Apr 06 14:24:00 IDT 2019 | Mon May 13 14:24:00 IDT 2019 | Sat Apr 06 14:24:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4311 | TT_TASK | EC+I | Wed Jul 03 08:00:00 IDT 2019 | Thu Jul 25 16:00:00 IDT 2019 | Wed May 22 00:00:00 IDT 2019 | Wed Sep 25 00:00:00 IDT 2019 |  | COMPLETED
4312 | TT_TASK | Line Inspection | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 18 18:00:00 IDT 2019 | Thu Oct 03 00:00:00 IDT 2019 | Fri Oct 18 00:00:00 IDT 2019 |  | COMPLETED
4313 | TT_TASK | Hydro Test | Sat Oct 19 08:00:00 IDT 2019 | Wed Oct 30 18:00:00 IST 2019 | Sat Oct 19 08:00:00 IDT 2019 | Mon Oct 21 00:00:00 IDT 2019 |  | COMPLETED
4314 | TT_TASK | Painting/Insulation | Sat Jun 08 08:54:00 IDT 2019 | Thu Jul 04 08:54:00 IDT 2019 | Thu May 16 00:00:00 IDT 2019 | Tue Dec 10 00:00:00 IST 2019 |  | COMPLETED
4315 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Thu Oct 31 08:00:00 IST 2019 | Mon Nov 11 18:00:00 IST 2019 | Tue Oct 08 00:00:00 IDT 2019 | Tue Dec 10 00:00:00 IST 2019 |  | COMPLETED
4316 | TT_TASK | Install Fuel Gas Piping from Plant to Tie-in to Existing Line | Thu Aug 30 08:00:00 IDT 2018 | Wed Oct 17 18:00:00 IDT 2018 | Mon Aug 13 00:00:00 IDT 2018 | Mon May 06 00:00:00 IDT 2019 |  | COMPLETED
4318 | TT_TASK | Erection of Blending Station | Tue Apr 30 08:00:00 IDT 2019 | Wed May 22 18:00:00 IDT 2019 | Sat May 25 00:00:00 IDT 2019 | Sat Jul 27 00:00:00 IDT 2019 |  | COMPLETED
4319 | TT_TASK | Install Equipment/Skids/Pumps | Tue Apr 30 08:00:00 IDT 2019 | Wed Jun 05 16:00:00 IDT 2019 | Tue May 07 00:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4320 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Wed Apr 03 08:00:00 IDT 2019 | Thu Jun 06 18:00:00 IDT 2019 | Fri Mar 01 00:00:00 IST 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4321 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Sat Apr 06 08:00:00 IDT 2019 | Thu May 16 17:00:00 IDT 2019 | Wed Apr 10 00:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4322 | TT_TASK | NDE | Wed May 08 08:00:00 IDT 2019 | Sat Jun 15 17:00:00 IDT 2019 | Wed May 08 08:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4323 | TT_TASK | EC+I | Thu May 23 08:00:00 IDT 2019 | Fri Jul 05 17:00:00 IDT 2019 | Thu May 23 08:00:00 IDT 2019 | Thu Sep 26 00:00:00 IDT 2019 |  | COMPLETED
4324 | TT_TASK | Line Inspection | Mon Sep 02 08:09:00 IDT 2019 | Wed Sep 11 08:09:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Thu Oct 17 00:00:00 IDT 2019 |  | COMPLETED
4325 | TT_TASK | Hydro Test | Thu Oct 10 09:48:00 IDT 2019 | Sat Oct 19 09:48:00 IDT 2019 | Mon Oct 21 00:00:00 IDT 2019 | Fri Oct 25 00:00:00 IDT 2019 |  | COMPLETED
4326 | TT_TASK | Painting/Insulation | Fri Jul 26 08:00:00 IDT 2019 | Tue Aug 06 18:00:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 | Mon Dec 16 00:00:00 IST 2019 |  | COMPLETED
4327 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Oct 19 09:48:00 IDT 2019 | Thu Oct 31 09:48:00 IST 2019 | Mon Oct 07 00:00:00 IDT 2019 | Mon Dec 16 00:00:00 IST 2019 |  | COMPLETED
4329 | TT_TASK | Install Equipment/Skids/Pumps | Tue Apr 30 08:00:00 IDT 2019 | Wed Jun 05 16:00:00 IDT 2019 | Wed May 08 00:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4330 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Tue Apr 30 08:00:00 IDT 2019 | Wed Jun 05 18:00:00 IDT 2019 | Mon May 06 00:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4331 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Mon May 13 08:00:00 IDT 2019 | Fri Jun 07 09:00:00 IDT 2019 | Mon May 13 08:00:00 IDT 2019 | Thu Sep 12 00:00:00 IDT 2019 |  | COMPLETED
4332 | TT_TASK | EC+I | Tue Apr 30 08:00:00 IDT 2019 | Wed Jun 05 16:00:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Fri Sep 27 00:00:00 IDT 2019 |  | COMPLETED
4333 | TT_TASK | Line Inspection | Mon Sep 09 13:30:00 IDT 2019 | Mon Sep 16 13:30:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Wed Oct 16 00:00:00 IDT 2019 |  | COMPLETED
4334 | TT_TASK | Hydro Test | Sat Oct 05 13:30:00 IDT 2019 | Tue Oct 15 13:30:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 | Wed Oct 16 00:00:00 IDT 2019 |  | COMPLETED
4335 | TT_TASK | Painting/Insulation | Tue Jun 25 15:18:00 IDT 2019 | Wed Jul 17 15:18:00 IDT 2019 | Fri Jun 14 00:00:00 IDT 2019 | Wed Nov 27 00:00:00 IST 2019 |  | COMPLETED
4336 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Tue Oct 15 13:30:00 IDT 2019 | Wed Oct 23 13:30:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 | Wed Nov 27 00:00:00 IST 2019 |  | COMPLETED
4337 | TT_TASK | NDE | Wed May 08 08:00:00 IDT 2019 | Thu Jun 13 16:00:00 IDT 2019 | Wed May 08 08:00:00 IDT 2019 | Wed Oct 02 13:30:00 IDT 2019 |  | COMPLETED
4341 | TT_TASK | Install Equipment - Skid | Sat Jun 22 08:00:00 IDT 2019 | Sat Jul 06 18:00:00 IDT 2019 | Sat May 18 00:00:00 IDT 2019 | Thu Oct 17 00:00:00 IDT 2019 |  | COMPLETED
4342 | TT_TASK | Installation of Bar Screen - Skid | Wed Jul 31 08:00:00 IDT 2019 | Thu Aug 22 18:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 | Tue Oct 15 00:00:00 IDT 2019 |  | COMPLETED
4343 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Jul 22 08:00:00 IDT 2019 | Fri Aug 09 18:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 |  | COMPLETED
4344 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Sat Aug 10 08:00:00 IDT 2019 | Thu Aug 29 14:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 | Wed Oct 23 00:00:00 IDT 2019 |  | COMPLETED
4345 | TT_TASK | NDE | Thu Aug 15 08:00:00 IDT 2019 | Sat Aug 31 18:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 | Sat Oct 26 00:00:00 IDT 2019 |  | COMPLETED
4346 | TT_TASK | EC+I | Mon Sep 02 08:00:00 IDT 2019 | Tue Sep 17 18:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 | Wed Nov 20 00:00:00 IST 2019 |  | COMPLETED
4347 | TT_TASK | Line Inspection | Wed Oct 30 08:00:00 IST 2019 | Mon Nov 04 18:00:00 IST 2019 | Wed Oct 30 08:00:00 IST 2019 | Mon Nov 04 18:00:00 IST 2019 |  | COMPLETED
4348 | TT_TASK | Hydro Test | Tue Nov 05 08:00:00 IST 2019 | Fri Nov 08 18:00:00 IST 2019 | Tue Nov 05 08:00:00 IST 2019 | Fri Nov 15 00:00:00 IST 2019 |  | COMPLETED
4349 | TT_TASK | Painting/Insulation | Sat Sep 21 15:51:00 IDT 2019 | Mon Sep 30 15:51:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Tue Dec 10 00:00:00 IST 2019 |  | COMPLETED
4350 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Nov 30 08:00:00 IST 2019 | Sat Dec 07 18:00:00 IST 2019 | Sat Nov 30 08:00:00 IST 2019 | Tue Dec 10 00:00:00 IST 2019 |  | COMPLETED
4352 | TT_TASK | Install Cooling Water Piperack (UPY00Y Module) | Mon Apr 01 08:00:00 IDT 2019 | Mon Apr 15 17:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Tue Jul 23 00:00:00 IDT 2019 |  | COMPLETED
4353 | TT_TASK | Install Large Bore Pipe/Valves/Supports from Civil U/G TP to Condenser | Thu May 09 15:36:00 IDT 2019 | Thu Jun 06 15:36:00 IDT 2019 | Thu May 09 15:36:00 IDT 2019 | Mon Nov 04 16:12:00 IST 2019 |  | COMPLETED
4354 | TT_TASK | Install Small Bore Pipe/Valves/Supports from Civil U/G TP to Condenser | Mon Apr 01 08:00:00 IDT 2019 | Tue Jun 04 18:00:00 IDT 2019 | Tue Apr 09 00:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 |  | COMPLETED
4355 | TT_TASK | NDE | Mon Jun 24 09:00:00 IDT 2019 | Tue Jul 02 18:00:00 IDT 2019 | Tue Jun 04 00:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 |  | COMPLETED
4356 | TT_TASK | EC+I | Fri Jun 28 13:00:00 IDT 2019 | Tue Jul 30 12:00:00 IDT 2019 | Thu Jun 13 00:00:00 IDT 2019 | Tue Nov 05 16:34:00 IST 2019 |  | COMPLETED
4357 | TT_TASK | Line Inspection | Sat Oct 26 08:00:00 IDT 2019 | Thu Oct 31 18:00:00 IST 2019 | Fri Oct 04 00:00:00 IDT 2019 | Tue Oct 22 00:00:00 IDT 2019 |  | COMPLETED
4358 | TT_TASK | Hydro Test | Mon Nov 04 16:12:00 IST 2019 | Wed Nov 13 16:12:00 IST 2019 | Mon Nov 04 16:12:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
4359 | TT_TASK | Painting/Insulation | Tue Oct 15 16:00:00 IDT 2019 | Tue Oct 29 16:00:00 IST 2019 | Wed Sep 25 00:00:00 IDT 2019 | Mon Dec 16 00:00:00 IST 2019 |  | COMPLETED
4360 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Wed Dec 04 14:24:00 IST 2019 | Tue Dec 10 14:24:00 IST 2019 | Wed Dec 04 14:24:00 IST 2019 | Mon Dec 16 00:00:00 IST 2019 |  | COMPLETED
4362 | TT_TASK | Install Circulating Water Pumps | Mon Jul 08 08:00:00 IDT 2019 | Mon Jul 22 16:00:00 IDT 2019 | Sat Jul 06 14:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4363 | TT_TASK | Prepare Circulating Water Pumps Foundations | Fri May 31 08:00:00 IDT 2019 | Fri Jun 14 09:00:00 IDT 2019 | Sat Jun 29 00:00:00 IDT 2019 | Fri Jul 19 00:00:00 IDT 2019 |  | COMPLETED
4364 | TT_TASK | Install Large Bore Pipe/Valves/Supports from CW Pumps to U/G Piping Terminal Point | Thu Jul 11 17:00:00 IDT 2019 | Mon Aug 05 16:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 | Fri Oct 25 18:00:00 IDT 2019 |  | COMPLETED
4365 | TT_TASK | Install Small Bore Pipe/Valves/Supports from CW Pump to U/G Piping Terminal Point | Mon Jul 15 17:00:00 IDT 2019 | Wed Aug 07 17:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 | Fri Oct 25 00:00:00 IDT 2019 |  | COMPLETED
4366 | TT_TASK | NDE | Fri Aug 09 08:00:00 IDT 2019 | Tue Aug 20 18:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 | Fri Oct 25 00:00:00 IDT 2019 |  | COMPLETED
4367 | TT_TASK | EC+I | Mon Sep 02 11:00:00 IDT 2019 | Thu Oct 03 11:00:00 IDT 2019 | Mon Sep 02 11:00:00 IDT 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
4368 | TT_TASK | Line Inspection | Sat Nov 30 08:00:00 IST 2019 | Wed Dec 04 18:00:00 IST 2019 | Sat Nov 30 08:00:00 IST 2019 | Sun Dec 01 00:00:00 IST 2019 |  | COMPLETED
4369 | TT_TASK | Hydro Test | Mon Mar 30 08:00:00 IDT 2020 | Thu Apr 02 18:00:00 IDT 2020 | Mon Dec 02 08:00:00 IST 2019 | Fri Dec 06 18:00:00 IST 2019 |  | COMPLETED
4370 | TT_TASK | Painting/Insulation | Thu Sep 26 08:00:00 IDT 2019 | Sat Oct 05 18:00:00 IDT 2019 | Thu Sep 26 08:00:00 IDT 2019 | Thu Dec 12 00:00:00 IST 2019 |  | COMPLETED
4371 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Fri Apr 03 08:00:00 IDT 2020 | Wed Apr 08 18:00:00 IDT 2020 | Sat Dec 07 08:00:00 IST 2019 | Thu Dec 12 08:00:00 IST 2019 |  | COMPLETED
4373 | TT_TASK | Install Closed Cooling/Service Water Pump Module (PXB00Y) | Tue Apr 30 08:00:00 IDT 2019 | Thu Jun 06 18:00:00 IDT 2019 | Fri May 03 00:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4374 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Wed Apr 03 08:00:00 IDT 2019 | Thu Jun 27 14:00:00 IDT 2019 | Thu Oct 18 00:00:00 IDT 2018 | Mon Sep 02 08:00:00 IDT 2019 |  | COMPLETED
4375 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue Apr 16 08:00:00 IDT 2019 | Sat May 25 18:00:00 IDT 2019 | Fri Mar 08 00:00:00 IST 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4376 | TT_TASK | NDE | Wed May 15 14:24:00 IDT 2019 | Sat Jul 06 14:24:00 IDT 2019 | Wed May 15 14:24:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4377 | TT_TASK | EC+I | Sat Jul 13 17:12:00 IDT 2019 | Mon Aug 12 17:12:00 IDT 2019 | Thu Jun 06 00:00:00 IDT 2019 | Thu Sep 26 00:00:00 IDT 2019 |  | COMPLETED
4378 | TT_TASK | Line Inspection | Thu Aug 08 17:12:00 IDT 2019 | Fri Aug 16 17:12:00 IDT 2019 | Sat Jun 29 00:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 |  | COMPLETED
4379 | TT_TASK | Hydro Test | Thu Aug 22 13:45:00 IDT 2019 | Fri Aug 30 13:45:00 IDT 2019 | Wed Jul 10 00:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 |  | COMPLETED
4380 | TT_TASK | Painting/Insulation | Sat Jul 13 17:12:00 IDT 2019 | Tue Aug 06 17:12:00 IDT 2019 | Sat Jun 08 00:00:00 IDT 2019 | Thu Oct 17 00:00:00 IDT 2019 |  | COMPLETED
4381 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Fri Oct 11 08:00:00 IDT 2019 | Fri Oct 18 17:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
4384 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Fri Jul 26 11:36:00 IDT 2019 | Wed Aug 28 11:36:00 IDT 2019 | Fri Jul 12 00:00:00 IDT 2019 | Wed Sep 04 16:12:00 IDT 2019 |  | COMPLETED
4385 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Wed Jul 24 11:36:00 IDT 2019 | Mon Aug 19 11:36:00 IDT 2019 | Thu Jul 11 00:00:00 IDT 2019 | Tue Sep 03 09:48:00 IDT 2019 |  | COMPLETED
4386 | TT_TASK | NDE | Tue Aug 06 08:00:00 IDT 2019 | Mon Aug 12 18:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Thu Oct 03 00:00:00 IDT 2019 |  | COMPLETED
4387 | TT_TASK | EC+I | Sat Aug 10 11:36:00 IDT 2019 | Tue Aug 20 11:36:00 IDT 2019 | Mon Jul 15 00:00:00 IDT 2019 | Wed Sep 25 00:00:00 IDT 2019 |  | COMPLETED
4388 | TT_TASK | Line Inspection | Mon Sep 30 10:42:00 IDT 2019 | Tue Oct 08 10:42:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 | Sat Nov 09 00:00:00 IST 2019 |  | COMPLETED
4389 | TT_TASK | Hydro Test | Fri Nov 01 08:00:00 IST 2019 | Fri Nov 08 18:00:00 IST 2019 | Mon Nov 25 00:00:00 IST 2019 | Fri Nov 29 00:00:00 IST 2019 |  | COMPLETED
4390 | TT_TASK | Painting/Insulation | Tue Aug 20 14:24:00 IDT 2019 | Mon Sep 02 14:24:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 | Fri Nov 15 00:00:00 IST 2019 |  | COMPLETED
4391 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Nov 09 08:00:00 IST 2019 | Fri Nov 15 18:00:00 IST 2019 | Sat Nov 09 08:00:00 IST 2019 | Fri Nov 15 18:00:00 IST 2019 |  | COMPLETED
4393 | TT_TASK | Install Equipment/Skids/Pumps | Tue Feb 19 08:00:00 IST 2019 | Mon Feb 25 16:00:00 IST 2019 | Thu Nov 15 00:00:00 IST 2018 | Tue Nov 20 00:00:00 IST 2018 |  | COMPLETED
4394 | TT_TASK | Install Control Cabinet & Junction Box for Tube Cleaning Systen | Fri May 31 08:00:00 IDT 2019 | Mon Jun 03 16:00:00 IDT 2019 | Tue Jun 25 00:00:00 IDT 2019 | Wed Jul 17 00:00:00 IDT 2019 |  | COMPLETED
4395 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Sat Apr 06 13:30:00 IDT 2019 | Thu May 09 11:30:00 IDT 2019 | Sat Apr 06 13:30:00 IDT 2019 | Tue Sep 03 00:00:00 IDT 2019 |  | COMPLETED
4396 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Fri Apr 26 11:30:00 IDT 2019 | Tue May 14 11:30:00 IDT 2019 | Fri Apr 26 11:30:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4397 | TT_TASK | NDE | Thu May 23 14:30:00 IDT 2019 | Wed Jun 05 14:30:00 IDT 2019 | Thu May 23 14:30:00 IDT 2019 | Fri Sep 27 00:00:00 IDT 2019 |  | COMPLETED
4398 | TT_TASK | EC+I | Thu May 30 08:06:00 IDT 2019 | Sat Jun 29 08:06:00 IDT 2019 | Tue May 21 00:00:00 IDT 2019 | Thu Sep 26 00:00:00 IDT 2019 |  | COMPLETED
4399 | TT_TASK | Line Inspection | Wed Sep 04 11:47:00 IDT 2019 | Tue Sep 17 11:47:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Sat Oct 05 18:00:00 IDT 2019 |  | COMPLETED
4400 | TT_TASK | Hydro Test | Sat Mar 28 08:00:00 IDT 2020 | Thu Apr 02 18:00:00 IDT 2020 | Wed Dec 04 08:00:00 IST 2019 | Mon Dec 09 18:00:00 IST 2019 |  | COMPLETED
4401 | TT_TASK | Painting/Insulation | Mon Sep 23 11:47:00 IDT 2019 | Thu Oct 10 11:47:00 IDT 2019 | Mon Sep 23 11:47:00 IDT 2019 | Tue Dec 17 18:00:00 IST 2019 |  | COMPLETED
4402 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Wed Apr 01 09:00:00 IDT 2020 | Wed Apr 08 18:00:00 IDT 2020 | Tue Dec 10 09:00:00 IST 2019 | Tue Dec 17 18:00:00 IST 2019 |  | COMPLETED
4404 | TT_TASK | Install Equipment/Skids/Pumps - Skid | Wed May 22 08:00:00 IDT 2019 | Sat Jun 01 18:00:00 IDT 2019 | Tue Apr 23 00:00:00 IDT 2019 | Tue Sep 10 00:00:00 IDT 2019 |  | COMPLETED
4405 | TT_TASK | Install Containers - Skid | Sat Jun 08 13:30:00 IDT 2019 | Thu Jun 13 11:30:00 IDT 2019 | Thu Jun 27 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4406 | TT_TASK | Install Interconnection Lines to Process | Fri Aug 02 17:30:00 IDT 2019 | Wed Aug 07 17:30:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
4407 | TT_TASK | Install Pipe/Valves/Supports - Skid | Sat Jun 08 13:30:00 IDT 2019 | Sat Jul 06 13:30:00 IDT 2019 | Fri Jun 14 00:00:00 IDT 2019 | Wed Oct 02 09:21:00 IDT 2019 |  | COMPLETED
4408 | TT_TASK | EC+I | Tue Aug 20 08:54:00 IDT 2019 | Thu Aug 29 08:54:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
4409 | TT_TASK | Line Inspection | Wed Oct 30 08:43:00 IST 2019 | Fri Nov 08 08:43:00 IST 2019 | Wed Oct 30 08:43:00 IST 2019 | Fri Nov 08 08:43:00 IST 2019 |  | COMPLETED
4410 | TT_TASK | Hydro Test/Leak Test | Fri Nov 01 08:43:00 IST 2019 | Mon Nov 11 08:43:00 IST 2019 | Fri Nov 01 08:43:00 IST 2019 | Mon Nov 11 08:43:00 IST 2019 |  | COMPLETED
4411 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Mon Nov 11 08:43:00 IST 2019 | Wed Nov 20 08:43:00 IST 2019 | Mon Nov 11 08:43:00 IST 2019 | Wed Nov 20 08:43:00 IST 2019 |  | COMPLETED
4412 | TT_TASK | NDE | Tue Jul 16 08:00:00 IDT 2019 | Mon Jul 29 18:00:00 IDT 2019 | Tue Jul 16 08:00:00 IDT 2019 | Thu Oct 03 00:00:00 IDT 2019 |  | COMPLETED
4414 | TT_TASK | Anode Installation | Mon Sep 02 08:00:00 IDT 2019 | Wed Sep 11 18:00:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 | Fri Oct 04 00:00:00 IDT 2019 |  | COMPLETED
4415 | TT_TASK | Rectifier Installation | Sat Sep 07 08:00:00 IDT 2019 | Wed Sep 18 18:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 | Thu Oct 10 15:18:00 IDT 2019 |  | COMPLETED
4416 | TT_TASK | Junction Box Installion | Fri Sep 13 08:00:00 IDT 2019 | Tue Sep 24 18:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 |  | COMPLETED
4417 | TT_TASK | Test Station | Fri Sep 20 08:00:00 IDT 2019 | Mon Sep 30 18:00:00 IDT 2019 | Fri Sep 20 08:00:00 IDT 2019 | Wed Oct 30 13:03:00 IST 2019 |  | COMPLETED
4418 | TT_TASK | Cable Pulling/Termination | Wed Oct 02 08:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 | Wed Oct 30 17:06:00 IST 2019 |  | COMPLETED
4419 | TT_TASK | Precommissioning | Wed Oct 30 08:00:00 IST 2019 | Sat Nov 09 18:00:00 IST 2019 | Wed Oct 30 08:00:00 IST 2019 | Sat Nov 09 18:00:00 IST 2019 |  | COMPLETED
4421 | TT_TASK | Anode Installation | Mon Sep 02 08:00:00 IDT 2019 | Tue Sep 10 18:00:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 |  | COMPLETED
4422 | TT_TASK | Rectifier Installation | Wed Sep 11 08:00:00 IDT 2019 | Sat Sep 21 18:00:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
4423 | TT_TASK | Junction Box Installion | Mon Sep 23 08:00:00 IDT 2019 | Wed Oct 02 18:00:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 |  | COMPLETED
4424 | TT_TASK | Test Station | Thu Oct 03 08:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 | Wed Oct 30 11:36:00 IST 2019 |  | COMPLETED
4425 | TT_TASK | Cable Pulling/Termination | Mon Oct 14 08:00:00 IDT 2019 | Tue Oct 22 18:00:00 IDT 2019 | Wed Sep 18 00:00:00 IDT 2019 | Wed Oct 30 16:12:00 IST 2019 |  | COMPLETED
4426 | TT_TASK | Precommissioning | Wed Oct 30 16:12:00 IST 2019 | Fri Nov 08 16:12:00 IST 2019 | Wed Oct 30 16:12:00 IST 2019 | Fri Nov 08 16:12:00 IST 2019 |  | COMPLETED
4430 | TT_TASK | Install Equipment/Skids/Pumps | Fri Mar 15 08:00:00 IST 2019 | Wed Apr 17 17:00:00 IDT 2019 | Fri Mar 15 08:00:00 IST 2019 | Sat Jun 22 00:00:00 IDT 2019 |  | COMPLETED
4431 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 01 08:00:00 IDT 2019 | Fri May 10 18:00:00 IDT 2019 | Wed Apr 03 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4432 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Sat Apr 13 08:00:00 IDT 2019 | Thu May 23 17:00:00 IDT 2019 | Sat Apr 13 08:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4433 | TT_TASK | NDE | Wed May 29 11:47:00 IDT 2019 | Mon Jun 17 11:47:00 IDT 2019 | Tue May 07 00:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4434 | TT_TASK | EC+I | Wed Jun 05 10:20:00 IDT 2019 | Fri Jun 28 10:20:00 IDT 2019 | Fri May 17 00:00:00 IDT 2019 | Thu Sep 26 00:00:00 IDT 2019 |  | COMPLETED
4435 | TT_TASK | Line Inspection | Thu Aug 01 11:30:00 IDT 2019 | Mon Aug 05 11:30:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4436 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Thu Oct 03 18:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 | Wed Oct 09 18:00:00 IDT 2019 |  | COMPLETED
4437 | TT_TASK | Painting/Insulation | Mon Jun 24 11:36:00 IDT 2019 | Wed Jul 03 11:36:00 IDT 2019 | Mon Jun 03 00:00:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 |  | COMPLETED
4438 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Fri Oct 04 08:00:00 IDT 2019 | Tue Oct 08 18:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 | Wed Oct 30 17:06:00 IST 2019 |  | COMPLETED
4440 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Wed Apr 17 17:00:00 IDT 2019 | Mon Jun 10 17:00:00 IDT 2019 | Fri Mar 15 00:00:00 IST 2019 | Thu Sep 19 00:00:00 IDT 2019 |  | COMPLETED
4441 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Wed Apr 24 09:48:00 IDT 2019 | Thu Jun 06 09:48:00 IDT 2019 | Wed Apr 24 09:48:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 |  | COMPLETED
4442 | TT_TASK | NDE | Fri May 31 08:00:00 IDT 2019 | Sat Jun 08 17:00:00 IDT 2019 | Wed Jun 05 00:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4443 | TT_TASK | EC+I | Tue Apr 30 08:00:00 IDT 2019 | Mon Jun 10 18:00:00 IDT 2019 | Wed May 08 00:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4444 | TT_TASK | Line Inspection | Fri Aug 02 15:51:00 IDT 2019 | Sat Aug 10 15:51:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 | Wed Sep 18 00:00:00 IDT 2019 |  | COMPLETED
4445 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 04 18:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 | Thu Oct 10 18:00:00 IDT 2019 |  | COMPLETED
4446 | TT_TASK | Painting | Fri Jun 21 08:00:00 IDT 2019 | Sat Jul 20 18:00:00 IDT 2019 | Mon Jun 03 00:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
4447 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Oct 05 08:00:00 IDT 2019 | Fri Oct 11 18:00:00 IDT 2019 | Sat Oct 05 08:00:00 IDT 2019 | Fri Oct 11 18:00:00 IDT 2019 |  | COMPLETED
4449 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Feb 18 17:00:00 IST 2019 | Tue May 14 12:00:00 IDT 2019 | Wed Jan 02 00:00:00 IST 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4450 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Wed May 08 14:36:00 IDT 2019 | Fri Jun 14 13:36:00 IDT 2019 | Wed May 08 14:36:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 |  | COMPLETED
4451 | TT_TASK | NDE | Mon Apr 01 08:00:00 IDT 2019 | Mon Jun 17 17:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4452 | TT_TASK | EC+I | Sat Jun 29 08:24:00 IDT 2019 | Wed Jul 24 08:24:00 IDT 2019 | Mon Jun 03 00:00:00 IDT 2019 | Thu Sep 26 00:00:00 IDT 2019 |  | COMPLETED
4453 | TT_TASK | Line Inspection | Mon Aug 12 08:01:00 IDT 2019 | Tue Aug 20 08:01:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 | Thu Sep 19 13:21:00 IDT 2019 |  | COMPLETED
4454 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 04 18:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 | Thu Oct 17 00:00:00 IDT 2019 |  | COMPLETED
4455 | TT_TASK | Painting/Insulation | Sat Jun 29 08:24:00 IDT 2019 | Wed Jul 24 08:24:00 IDT 2019 | Tue Jun 04 00:00:00 IDT 2019 | Fri Nov 15 00:00:00 IST 2019 |  | COMPLETED
4456 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Oct 05 08:00:00 IDT 2019 | Mon Oct 14 18:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
4460 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 01 08:00:00 IDT 2019 | Mon Apr 15 17:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4461 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 15 17:00:00 IDT 2019 | Sat May 25 17:00:00 IDT 2019 | Mon Apr 15 17:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4462 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue Jun 18 10:11:00 IDT 2019 | Mon Jul 08 10:11:00 IDT 2019 | Wed Jun 05 00:00:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 |  | COMPLETED
4463 | TT_TASK | EC+I | Mon Jul 08 10:11:00 IDT 2019 | Fri Jul 19 10:11:00 IDT 2019 | Thu Jun 06 00:00:00 IDT 2019 | Tue Oct 08 00:00:00 IDT 2019 |  | COMPLETED
4464 | TT_TASK | Line Inspection | Mon Sep 30 08:00:00 IDT 2019 | Wed Oct 09 17:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 | Thu Nov 07 00:00:00 IST 2019 |  | COMPLETED
4465 | TT_TASK | Hydro Test | Thu Dec 05 08:00:00 IST 2019 | Tue Dec 17 18:00:00 IST 2019 | Fri Nov 08 00:00:00 IST 2019 | Tue Nov 19 00:00:00 IST 2019 |  | COMPLETED
4466 | TT_TASK | Painting/Insulation | Wed Jul 03 10:11:00 IDT 2019 | Sat Jul 20 10:11:00 IDT 2019 | Fri Jun 07 00:00:00 IDT 2019 | Tue Nov 19 00:00:00 IST 2019 |  | COMPLETED
4467 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Wed Oct 23 13:30:00 IDT 2019 | Tue Oct 29 13:30:00 IST 2019 | Sat Oct 12 00:00:00 IDT 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
4469 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 01 08:00:00 IDT 2019 | Mon Apr 15 17:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4470 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 15 17:00:00 IDT 2019 | Sat May 25 17:00:00 IDT 2019 | Mon Apr 15 17:00:00 IDT 2019 | Tue Oct 08 00:00:00 IDT 2019 |  | COMPLETED
4471 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Mon Jun 24 10:12:00 IDT 2019 | Fri Jul 12 10:12:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
4472 | TT_TASK | EC+I | Wed Jun 05 10:12:00 IDT 2019 | Fri Jul 05 16:00:00 IDT 2019 | Fri Jun 07 00:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
4473 | TT_TASK | Line Inspection | Mon Sep 30 15:45:00 IDT 2019 | Fri Oct 11 14:45:00 IDT 2019 | Tue Oct 08 00:00:00 IDT 2019 | Thu Oct 31 14:12:00 IST 2019 |  | COMPLETED
4474 | TT_TASK | Hydro Test | Fri Dec 06 08:00:00 IST 2019 | Fri Dec 13 18:00:00 IST 2019 | Fri Nov 01 00:00:00 IST 2019 | Fri Nov 08 00:00:00 IST 2019 |  | COMPLETED
4475 | TT_TASK | Painting/Insulation | Sat Jul 06 10:12:00 IDT 2019 | Wed Jul 24 10:12:00 IDT 2019 | Fri Jun 14 00:00:00 IDT 2019 | Fri Nov 08 00:00:00 IST 2019 |  | COMPLETED
4476 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Tue Dec 10 08:00:00 IST 2019 | Fri Dec 13 18:00:00 IST 2019 | Wed Nov 20 00:00:00 IST 2019 | Mon Nov 25 00:00:00 IST 2019 |  | COMPLETED
4478 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 12 17:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4479 | TT_TASK | Install Large Bore Pipe/Valves/Supports (Inside+Outside) | Mon Mar 11 08:00:00 IST 2019 | Tue Apr 30 18:00:00 IDT 2019 | Fri Mar 22 00:00:00 IST 2019 | Tue Oct 08 00:00:00 IDT 2019 |  | COMPLETED
4480 | TT_TASK | Install Small Bore Pipe/Valves/Supports (Inside+Outside) | Fri May 17 16:12:00 IDT 2019 | Tue Jun 11 16:12:00 IDT 2019 | Fri May 17 16:12:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
4481 | TT_TASK | EC+I | Wed Jun 12 13:48:00 IDT 2019 | Mon Jul 08 11:48:00 IDT 2019 | Wed Jun 12 13:48:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
4482 | TT_TASK | Line Inspection | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 04 18:00:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 | Wed Oct 30 14:24:00 IST 2019 |  | COMPLETED
4483 | TT_TASK | Hydro Test | Fri Dec 06 08:00:00 IST 2019 | Tue Dec 10 18:00:00 IST 2019 | Fri Nov 01 00:00:00 IST 2019 | Fri Nov 08 00:00:00 IST 2019 |  | COMPLETED
4484 | TT_TASK | Painting/Insulation | Mon Jun 10 15:36:00 IDT 2019 | Fri Jul 05 14:36:00 IDT 2019 | Mon Jun 03 00:00:00 IDT 2019 | Fri Nov 08 00:00:00 IST 2019 |  | COMPLETED
4485 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Fri Dec 06 08:00:00 IST 2019 | Tue Dec 10 18:00:00 IST 2019 | Wed Nov 20 00:00:00 IST 2019 | Mon Nov 25 00:00:00 IST 2019 |  | COMPLETED
4486 | TT_TASK | NDE | Fri May 24 16:12:00 IDT 2019 | Tue Jun 18 16:12:00 IDT 2019 | Fri May 24 16:12:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4488 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 12 17:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4489 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Tue Feb 26 17:00:00 IST 2019 | Wed Apr 24 10:00:00 IDT 2019 | Fri Feb 22 00:00:00 IST 2019 | Wed Oct 09 00:00:00 IDT 2019 |  | COMPLETED
4490 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue May 07 10:51:00 IDT 2019 | Wed Jun 12 09:51:00 IDT 2019 | Tue May 07 10:51:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
4491 | TT_TASK | EC+I | Wed Jul 10 11:51:00 IDT 2019 | Mon Jul 22 11:51:00 IDT 2019 | Wed Jun 12 00:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
4492 | TT_TASK | Line Inspection | Fri Oct 04 13:30:00 IDT 2019 | Thu Oct 10 13:30:00 IDT 2019 | Fri Oct 18 00:00:00 IDT 2019 | Tue Oct 22 18:00:00 IDT 2019 |  | COMPLETED
4493 | TT_TASK | Hydro Test | Sat Nov 30 08:00:00 IST 2019 | Tue Dec 03 18:00:00 IST 2019 | Fri Nov 01 00:00:00 IST 2019 | Fri Nov 08 00:00:00 IST 2019 |  | COMPLETED
4494 | TT_TASK | Painting/Insulation | Sat Jun 29 14:39:00 IDT 2019 | Wed Jul 24 13:39:00 IDT 2019 | Fri Jun 14 00:00:00 IDT 2019 | Fri Nov 08 00:00:00 IST 2019 |  | COMPLETED
4495 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Mon Oct 14 13:30:00 IDT 2019 | Fri Oct 18 13:30:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 | Mon Nov 25 00:00:00 IST 2019 |  | COMPLETED
4496 | TT_TASK | NDE | Tue Apr 30 08:00:00 IDT 2019 | Wed Jun 12 16:00:00 IDT 2019 | Wed May 22 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4499 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Thu Feb 21 08:00:00 IST 2019 | Sat Apr 06 17:00:00 IDT 2019 | Wed Oct 31 00:00:00 IST 2018 | Fri Jun 07 00:00:00 IDT 2019 |  | COMPLETED
4500 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Mon Jun 17 08:00:00 IDT 2019 | Mon Jun 24 17:00:00 IDT 2019 | Wed May 08 00:00:00 IDT 2019 | Sat Jun 08 08:36:00 IDT 2019 |  | COMPLETED
4501 | TT_TASK | EC+I | Sat Jun 22 08:00:00 IDT 2019 | Tue Jul 23 17:00:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4502 | TT_TASK | Line Inspection | Fri May 31 08:00:00 IDT 2019 | Tue Jun 11 18:00:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Mon Jun 17 00:00:00 IDT 2019 |  | COMPLETED
4503 | TT_TASK | Hydro Test | Thu Jun 20 08:00:00 IDT 2019 | Tue Jun 25 18:00:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 | Fri Jul 05 00:00:00 IDT 2019 |  | COMPLETED
4504 | TT_TASK | Painting/Insulation | Mon Jun 24 17:00:00 IDT 2019 | Fri Jul 12 17:00:00 IDT 2019 | Thu May 16 00:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4505 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Mon Sep 02 08:00:00 IDT 2019 | Fri Sep 06 18:00:00 IDT 2019 | Mon Sep 02 08:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4507 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 01 08:00:00 IDT 2019 | Fri May 10 18:00:00 IDT 2019 | Sun Feb 17 00:00:00 IST 2019 | Thu Feb 28 00:00:00 IST 2019 |  | COMPLETED
4508 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 01 08:00:00 IDT 2019 | Fri May 10 18:00:00 IDT 2019 | Sat Feb 16 00:00:00 IST 2019 | Wed May 15 17:06:00 IDT 2019 |  | COMPLETED
4509 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Mon Apr 08 08:00:00 IDT 2019 | Tue Apr 23 15:00:00 IDT 2019 | Mon Apr 08 08:00:00 IDT 2019 | Wed May 08 15:16:00 IDT 2019 |  | COMPLETED
4510 | TT_TASK | EC+I | Wed May 15 17:06:00 IDT 2019 | Sat Jun 08 17:06:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 |  | COMPLETED
4511 | TT_TASK | Line Inspection | Wed May 08 15:16:00 IDT 2019 | Mon May 13 15:16:00 IDT 2019 | Wed May 08 15:16:00 IDT 2019 | Mon May 13 15:16:00 IDT 2019 |  | COMPLETED
4512 | TT_TASK | Hydro Test | Mon May 13 15:16:00 IDT 2019 | Fri May 17 15:16:00 IDT 2019 | Mon May 13 15:16:00 IDT 2019 | Thu May 23 00:00:00 IDT 2019 |  | COMPLETED
4513 | TT_TASK | Painting/Insulation | Wed May 15 17:06:00 IDT 2019 | Sat Jun 01 17:06:00 IDT 2019 | Wed May 15 17:06:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4514 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Aug 31 08:00:00 IDT 2019 | Wed Sep 04 18:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4516 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 12 17:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Mon Jun 10 00:00:00 IDT 2019 |  | COMPLETED
4517 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Fri Feb 22 10:00:00 IST 2019 | Fri Mar 29 10:00:00 IDT 2019 | Wed Oct 31 00:00:00 IST 2018 | Tue Apr 30 00:00:00 IDT 2019 |  | COMPLETED
4518 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Sat Apr 27 08:00:00 IDT 2019 | Fri Jun 07 18:00:00 IDT 2019 | Sat Apr 27 08:00:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 |  | COMPLETED
4519 | TT_TASK | EC+I | Wed Jun 05 13:30:00 IDT 2019 | Sat Jun 22 13:30:00 IDT 2019 | Fri Jun 07 00:00:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 |  | COMPLETED
4520 | TT_TASK | Line Inspection | Thu Jun 13 09:48:00 IDT 2019 | Tue Jun 25 09:48:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 | Wed Jul 10 18:00:00 IDT 2019 |  | COMPLETED
4521 | TT_TASK | Hydro Test | Thu Jul 11 08:00:00 IDT 2019 | Mon Jul 22 18:00:00 IDT 2019 | Wed Jul 24 00:00:00 IDT 2019 | Sat Aug 10 18:00:00 IDT 2019 |  | COMPLETED
4522 | TT_TASK | Painting/Insulation | Thu Jun 13 09:48:00 IDT 2019 | Tue Jul 02 09:48:00 IDT 2019 | Thu Jun 13 09:48:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4523 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Mon Aug 12 08:00:00 IDT 2019 | Wed Aug 21 18:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4527 | TT_TASK | Install Containers | Mon Apr 01 08:00:00 IDT 2019 | Mon Apr 08 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Thu Sep 12 00:00:00 IDT 2019 |  | COMPLETED
4528 | TT_TASK | Install Interconnecting Lines To Process | Tue Apr 09 08:00:00 IDT 2019 | Thu Jun 27 18:00:00 IDT 2019 | Tue Apr 09 08:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
4529 | TT_TASK | Hydro/Leak Test | Fri Sep 13 17:06:00 IDT 2019 | Thu Oct 10 17:06:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Tue Oct 08 11:14:00 IDT 2019 |  | COMPLETED
4530 | TT_TASK | EC+I | Mon Jul 08 15:45:00 IDT 2019 | Wed Aug 07 15:45:00 IDT 2019 | Tue Jun 04 00:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
4531 | TT_TASK | Precommissioning | Mon Oct 21 13:41:00 IDT 2019 | Thu Nov 07 13:41:00 IST 2019 | Fri Oct 18 00:00:00 IDT 2019 | Sun Jan 19 18:00:00 IST 2020 |  | COMPLETED
4533 | TT_TASK | Install Containers | Wed Feb 13 16:00:00 IST 2019 | Wed Feb 20 15:00:00 IST 2019 | Tue Feb 26 00:00:00 IST 2019 | Fri May 03 17:30:00 IDT 2019 |  | COMPLETED
4534 | TT_TASK | Install Interconnecting Lines To Process | Fri Jun 07 17:30:00 IDT 2019 | Tue Jul 09 17:30:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 |  | COMPLETED
4535 | TT_TASK | Hydro/Leak Test | Thu Sep 05 17:06:00 IDT 2019 | Mon Sep 30 17:06:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
4536 | TT_TASK | EC+I | Tue Jul 09 17:30:00 IDT 2019 | Thu Aug 01 17:30:00 IDT 2019 | Sat Jun 08 00:00:00 IDT 2019 | Tue Oct 08 00:00:00 IDT 2019 |  | COMPLETED
4537 | TT_TASK | Precommissioning | Sat Oct 05 13:41:00 IDT 2019 | Sat Oct 26 13:41:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 | Mon Dec 02 18:00:00 IST 2019 |  | COMPLETED
4539 | TT_TASK | Install Containers | Mon Mar 11 08:00:00 IST 2019 | Sat Mar 16 17:00:00 IST 2019 | Tue Mar 26 00:00:00 IST 2019 | Fri May 03 00:00:00 IDT 2019 |  | COMPLETED
4540 | TT_TASK | Install Interconnecting Lines To Process | Thu Jun 20 17:30:00 IDT 2019 | Sat Jul 20 16:30:00 IDT 2019 | Fri May 10 00:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
4541 | TT_TASK | Hydro/Leak Test | Thu Sep 05 15:36:00 IDT 2019 | Mon Sep 30 15:36:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Thu Oct 10 15:36:00 IDT 2019 |  | COMPLETED
4542 | TT_TASK | EC+I | Thu Jun 27 14:48:00 IDT 2019 | Fri Jul 26 14:48:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 | Fri Oct 11 13:48:00 IDT 2019 |  | COMPLETED
4543 | TT_TASK | Precommissioning | Fri Oct 11 13:48:00 IDT 2019 | Mon Nov 04 13:48:00 IST 2019 | Fri Oct 18 00:00:00 IDT 2019 | Mon Dec 02 18:00:00 IST 2019 |  | COMPLETED
4545 | TT_TASK | Install Containers | Mon Apr 01 08:00:00 IDT 2019 | Thu Apr 18 18:00:00 IDT 2019 | Tue Mar 26 00:00:00 IST 2019 | Mon Oct 07 00:00:00 IDT 2019 |  | COMPLETED
4546 | TT_TASK | Install Interconnecting Lines To Process | Fri May 31 08:00:00 IDT 2019 | Tue Jul 23 18:00:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
4547 | TT_TASK | Hydro/Leak Test | Wed Sep 11 08:00:00 IDT 2019 | Tue Sep 24 18:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4548 | TT_TASK | EC+I | Tue Apr 30 08:00:00 IDT 2019 | Sat Jun 08 18:00:00 IDT 2019 | Thu May 09 00:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
4549 | TT_TASK | Precommissioning | Fri Oct 04 08:54:00 IDT 2019 | Mon Oct 21 08:54:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 | Tue Nov 26 00:00:00 IST 2019 |  | COMPLETED
4551 | TT_TASK | Install Containers | Mon Mar 11 08:00:00 IST 2019 | Sat Mar 16 17:00:00 IST 2019 | Tue Apr 30 00:00:00 IDT 2019 | Fri May 24 17:30:00 IDT 2019 |  | COMPLETED
4552 | TT_TASK | Install Interconnecting Lines To Process | Fri May 31 08:00:00 IDT 2019 | Sat Jul 06 18:00:00 IDT 2019 | Mon Jun 03 00:00:00 IDT 2019 | Tue Oct 08 00:00:00 IDT 2019 |  | COMPLETED
4553 | TT_TASK | Hydro/Leak Test | Tue Sep 10 15:45:00 IDT 2019 | Mon Sep 16 14:45:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4554 | TT_TASK | EC+I | Mon Jul 08 08:00:00 IDT 2019 | Tue Aug 13 17:00:00 IDT 2019 | Tue Jun 04 00:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
4555 | TT_TASK | Precommissioning | Thu Oct 03 09:56:00 IDT 2019 | Tue Oct 22 09:56:00 IDT 2019 | Thu Oct 17 00:00:00 IDT 2019 | Tue Dec 10 00:00:00 IST 2019 |  | COMPLETED
4558 | TT_TASK | Installation Aux. System Pipe Racks (UMCM1Y Modules) | Tue Nov 06 08:00:00 IST 2018 | Fri Dec 07 16:00:00 IST 2018 | Thu Oct 18 00:00:00 IDT 2018 | Tue Nov 20 00:00:00 IST 2018 |  | COMPLETED
4559 | TT_TASK | Installation Water System Pipe Racks (UMCL1Y Modules) | Tue Feb 12 08:00:00 IST 2019 | Fri Feb 22 16:00:00 IST 2019 | Mon Jan 21 00:00:00 IST 2019 | Sat May 11 18:00:00 IDT 2019 |  | COMPLETED
4561 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Mar 11 08:00:00 IST 2019 | Tue Apr 30 18:00:00 IDT 2019 | Mon Mar 11 08:00:00 IST 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4562 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue Apr 16 16:12:00 IDT 2019 | Mon Jun 03 16:12:00 IDT 2019 | Tue Apr 16 16:12:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4563 | TT_TASK | NDE | Tue Apr 16 16:12:00 IDT 2019 | Sat Jun 08 16:12:00 IDT 2019 | Tue Apr 16 16:12:00 IDT 2019 | Fri Sep 27 00:00:00 IDT 2019 |  | COMPLETED
4564 | TT_TASK | EC+I | Mon May 20 16:12:00 IDT 2019 | Tue Jun 18 16:12:00 IDT 2019 | Mon May 20 16:12:00 IDT 2019 | Thu Sep 26 00:00:00 IDT 2019 |  | COMPLETED
4565 | TT_TASK | Line Inspection | Wed Sep 04 14:24:00 IDT 2019 | Tue Sep 17 14:24:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Mon Oct 21 00:00:00 IDT 2019 |  | COMPLETED
4566 | TT_TASK | Hydro Test | Tue Oct 22 08:00:00 IDT 2019 | Sat Oct 26 18:00:00 IDT 2019 | Tue Oct 22 08:00:00 IDT 2019 | Fri Oct 25 00:00:00 IDT 2019 |  | COMPLETED
4567 | TT_TASK | Painting/Insulation of Pipework | Mon May 20 16:12:00 IDT 2019 | Tue Jun 25 16:12:00 IDT 2019 | Mon May 20 16:12:00 IDT 2019 | Mon Nov 04 00:00:00 IST 2019 |  | COMPLETED
4568 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Thu Oct 17 08:00:00 IDT 2019 | Tue Oct 22 18:00:00 IDT 2019 | Sat Oct 26 00:00:00 IDT 2019 | Mon Nov 04 18:00:00 IST 2019 |  | COMPLETED
4570 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Thu Feb 28 08:00:00 IST 2019 | Thu May 09 12:00:00 IDT 2019 | Mon Mar 11 00:00:00 IST 2019 | Thu Sep 05 00:00:00 IDT 2019 |  | COMPLETED
4571 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Thu May 09 09:36:00 IDT 2019 | Mon Jun 17 11:36:00 IDT 2019 | Thu May 09 09:36:00 IDT 2019 | Tue Sep 03 16:41:00 IDT 2019 |  | COMPLETED
4572 | TT_TASK | NDE | Thu Apr 04 11:00:00 IDT 2019 | Mon Jun 10 10:00:00 IDT 2019 | Thu Apr 04 11:00:00 IDT 2019 | Thu Sep 26 00:00:00 IDT 2019 |  | COMPLETED
4573 | TT_TASK | EC+I | Mon May 27 09:36:00 IDT 2019 | Tue Jul 02 09:36:00 IDT 2019 | Tue May 14 00:00:00 IDT 2019 | Tue Sep 24 00:00:00 IDT 2019 |  | COMPLETED
4574 | TT_TASK | Insulation of Pipework Prior to Neutral Float | Mon Jun 17 16:45:00 IDT 2019 | Thu Jul 11 16:45:00 IDT 2019 | Mon Jun 17 16:45:00 IDT 2019 | Wed Sep 25 00:00:00 IDT 2019 |  | COMPLETED
4575 | TT_TASK | Line Inspection & Preparation for Neutral Float | Thu Aug 01 16:41:00 IDT 2019 | Tue Aug 13 16:41:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Mon Aug 26 00:00:00 IDT 2019 |  | COMPLETED
4576 | TT_TASK | Neutral Float of LBA and FInal Weld to Turbine Stop Valve | Fri Jul 26 17:30:00 IDT 2019 | Wed Aug 07 17:30:00 IDT 2019 | Wed Jul 17 00:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4577 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 04 18:00:00 IDT 2019 | Wed Oct 23 00:00:00 IDT 2019 | Sat Oct 26 18:00:00 IDT 2019 |  | COMPLETED
4578 | TT_TASK | Insulation of Neutral Float Weld | Sat Oct 05 08:00:00 IDT 2019 | Fri Oct 11 18:00:00 IDT 2019 | Sat Oct 05 08:00:00 IDT 2019 | Wed Oct 30 18:00:00 IST 2019 |  | COMPLETED
4579 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Oct 12 08:00:00 IDT 2019 | Thu Oct 17 18:00:00 IDT 2019 | Sat Oct 26 00:00:00 IDT 2019 | Tue Nov 05 13:30:00 IST 2019 |  | COMPLETED
4581 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Mar 11 08:00:00 IST 2019 | Tue May 07 18:00:00 IDT 2019 | Mon Mar 11 08:00:00 IST 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4582 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Wed May 08 14:24:00 IDT 2019 | Sat Jun 15 16:24:00 IDT 2019 | Wed May 08 14:24:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4583 | TT_TASK | NDE | Thu May 09 16:24:00 IDT 2019 | Sat Jun 15 16:24:00 IDT 2019 | Thu May 09 16:24:00 IDT 2019 | Thu Sep 26 00:00:00 IDT 2019 |  | COMPLETED
4584 | TT_TASK | EC+I | Sat May 25 14:24:00 IDT 2019 | Fri Jul 12 14:24:00 IDT 2019 | Sat May 25 14:24:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4585 | TT_TASK | Insulation of Pipework Prior to Neutral Float | Thu Jun 20 09:21:00 IDT 2019 | Wed Jul 03 09:21:00 IDT 2019 | Thu Jun 20 09:21:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4586 | TT_TASK | Line Inspection & Preparation for Neutral Float | Sat Aug 03 09:48:00 IDT 2019 | Thu Aug 15 09:48:00 IDT 2019 | Sat Aug 03 09:48:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
4587 | TT_TASK | Neutral Float of LBB and FInal Weld to Turbine Stop Valve | Fri Jul 19 11:36:00 IDT 2019 | Thu Aug 01 11:36:00 IDT 2019 | Thu Jul 18 00:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 |  | COMPLETED
4588 | TT_TASK | Hydro Test | Mon Sep 30 13:57:00 IDT 2019 | Wed Oct 16 13:57:00 IDT 2019 | Tue Sep 24 00:00:00 IDT 2019 | Fri Oct 25 00:00:00 IDT 2019 |  | COMPLETED
4589 | TT_TASK | Insulation of Neutral Float Weld | Mon Sep 30 08:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 | Fri Oct 04 00:00:00 IDT 2019 | Sat Nov 02 13:30:00 IST 2019 |  | COMPLETED
4590 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Wed Oct 16 13:57:00 IDT 2019 | Wed Oct 30 13:57:00 IST 2019 | Sat Oct 26 00:00:00 IDT 2019 | Fri Nov 15 10:42:00 IST 2019 |  | COMPLETED
4592 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Feb 18 17:00:00 IST 2019 | Sat Apr 27 17:00:00 IDT 2019 | Mon Jan 14 00:00:00 IST 2019 | Thu Sep 05 00:00:00 IDT 2019 |  | COMPLETED
4593 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue Apr 30 17:33:00 IDT 2019 | Mon Jun 10 09:33:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4594 | TT_TASK | NDE | Fri May 03 09:33:00 IDT 2019 | Mon Jun 10 09:33:00 IDT 2019 | Fri May 03 09:33:00 IDT 2019 | Wed Sep 25 00:00:00 IDT 2019 |  | COMPLETED
4595 | TT_TASK | EC+I | Sat May 18 17:33:00 IDT 2019 | Sat Jun 22 17:33:00 IDT 2019 | Sat May 18 17:33:00 IDT 2019 | Wed Sep 25 00:00:00 IDT 2019 |  | COMPLETED
4596 | TT_TASK | Insulation of Pipework Prior to Neutral Float | Mon Jun 17 17:24:00 IDT 2019 | Fri Jun 28 17:24:00 IDT 2019 | Mon Jun 17 17:24:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4597 | TT_TASK | Line Inspection & Preparation for Neutral Float | Mon Aug 05 16:12:00 IDT 2019 | Fri Aug 09 16:12:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
4598 | TT_TASK | Neutral Float of LBC and FInal Weld to Turbine Stop Valve | Fri Aug 09 16:12:00 IDT 2019 | Thu Aug 15 16:12:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
4599 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 04 18:00:00 IDT 2019 | Fri Oct 18 00:00:00 IDT 2019 | Fri Oct 25 00:00:00 IDT 2019 |  | COMPLETED
4600 | TT_TASK | Insulation of Neutral Float Weld | Sat Oct 05 08:00:00 IDT 2019 | Fri Oct 11 18:00:00 IDT 2019 | Sat Oct 05 08:00:00 IDT 2019 | Thu Oct 31 18:00:00 IST 2019 |  | COMPLETED
4601 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Oct 05 08:00:00 IDT 2019 | Fri Oct 11 18:00:00 IDT 2019 | Sat Oct 26 00:00:00 IDT 2019 | Mon Nov 04 13:30:00 IST 2019 |  | COMPLETED
4603 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 01 08:00:00 IDT 2019 | Sat May 04 18:00:00 IDT 2019 | Thu Apr 04 00:00:00 IDT 2019 | Thu Jul 25 00:00:00 IDT 2019 |  | COMPLETED
4604 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Fri May 24 10:42:00 IDT 2019 | Wed Jun 19 10:42:00 IDT 2019 | Fri May 24 10:42:00 IDT 2019 | Fri Jul 26 00:00:00 IDT 2019 |  | COMPLETED
4605 | TT_TASK | NDE | Sat Jun 08 10:42:00 IDT 2019 | Wed Jun 26 10:42:00 IDT 2019 | Thu May 09 00:00:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 |  | COMPLETED
4606 | TT_TASK | EC+I | Fri May 24 10:42:00 IDT 2019 | Fri Jun 21 10:42:00 IDT 2019 | Fri May 24 00:00:00 IDT 2019 | Thu Sep 26 00:00:00 IDT 2019 |  | COMPLETED
4607 | TT_TASK | Line Inspection | Wed Jul 31 08:00:00 IDT 2019 | Sat Aug 10 18:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Sat Aug 31 00:00:00 IDT 2019 |  | COMPLETED
4608 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 | Mon Oct 07 00:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
4609 | TT_TASK | Insulation | Mon Jun 24 11:36:00 IDT 2019 | Fri Jul 12 11:36:00 IDT 2019 | Fri Jun 14 00:00:00 IDT 2019 | Fri Nov 08 00:00:00 IST 2019 |  | COMPLETED
4610 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Mon Oct 14 08:00:00 IDT 2019 | Thu Oct 24 18:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 | Fri Nov 08 13:30:00 IST 2019 |  | COMPLETED
4612 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 01 08:00:00 IDT 2019 | Thu Apr 04 18:00:00 IDT 2019 | Mon Apr 08 00:00:00 IDT 2019 | Tue Jun 11 00:00:00 IDT 2019 |  | COMPLETED
4613 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 15 08:00:00 IDT 2019 | Wed Jun 12 18:00:00 IDT 2019 | Mon Apr 15 08:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4614 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Fri May 31 15:29:00 IDT 2019 | Sat Jun 29 15:29:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4615 | TT_TASK | NDE | Sat Jun 22 13:30:00 IDT 2019 | Thu Jul 11 13:30:00 IDT 2019 | Sat Jun 08 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4616 | TT_TASK | EC+I | Tue Jun 18 15:29:00 IDT 2019 | Thu Jul 18 15:29:00 IDT 2019 | Fri May 17 00:00:00 IDT 2019 | Thu Sep 26 00:00:00 IDT 2019 |  | COMPLETED
4617 | TT_TASK | Line Inspection | Wed Jul 31 08:00:00 IDT 2019 | Sat Aug 10 18:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Mon Sep 02 13:30:00 IDT 2019 |  | COMPLETED
4618 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 | Mon Oct 07 00:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
4619 | TT_TASK | Insulation | Tue Jul 09 08:00:00 IDT 2019 | Thu Aug 01 18:00:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 | Wed Nov 06 00:00:00 IST 2019 |  | COMPLETED
4620 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Mon Oct 14 08:00:00 IDT 2019 | Fri Oct 25 18:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 | Wed Nov 06 10:42:00 IST 2019 |  | COMPLETED
4623 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 01 08:00:00 IDT 2019 | Mon Apr 15 17:00:00 IDT 2019 | Wed Apr 10 00:00:00 IDT 2019 | Wed Jul 17 00:00:00 IDT 2019 |  | COMPLETED
4624 | TT_TASK | Erection of Oil Separator Pumps GM - Skid | Fri Jun 07 13:00:00 IDT 2019 | Mon Jun 17 12:00:00 IDT 2019 | Fri Jun 07 13:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4625 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 15 17:00:00 IDT 2019 | Sat May 25 17:00:00 IDT 2019 | Mon Apr 15 17:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4626 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue Apr 30 08:00:00 IDT 2019 | Fri May 24 18:00:00 IDT 2019 | Wed May 08 00:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4627 | TT_TASK | E&IC of Oil Separator Pumps GM | Sat May 25 14:00:00 IDT 2019 | Thu Jun 13 14:00:00 IDT 2019 | Sat May 25 14:00:00 IDT 2019 | Wed Aug 07 00:00:00 IDT 2019 |  | COMPLETED
4628 | TT_TASK | Line Inspection | Thu Aug 01 08:27:00 IDT 2019 | Tue Aug 06 08:27:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 | Tue Sep 03 11:36:00 IDT 2019 |  | COMPLETED
4629 | TT_TASK | Hydro Test | Tue Sep 03 11:36:00 IDT 2019 | Tue Sep 10 11:36:00 IDT 2019 | Wed Sep 25 00:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 |  | COMPLETED
4630 | TT_TASK | Painting/Insulation | Sat May 25 08:00:00 IDT 2019 | Tue Jun 04 18:00:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Thu Oct 31 16:12:00 IST 2019 |  | COMPLETED
4631 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Thu Oct 31 16:12:00 IST 2019 | Thu Nov 07 16:12:00 IST 2019 | Thu Oct 10 00:00:00 IDT 2019 | Mon Nov 04 09:48:00 IST 2019 |  | COMPLETED
4633 | TT_TASK | Install Equipment/Skids/Pumps | Wed Apr 17 08:00:00 IDT 2019 | Thu May 02 18:00:00 IDT 2019 | Fri Apr 19 00:00:00 IDT 2019 | Wed Jul 10 00:00:00 IDT 2019 |  | COMPLETED
4634 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Tue May 14 08:27:00 IDT 2019 | Fri Jun 07 08:27:00 IDT 2019 | Tue May 14 08:27:00 IDT 2019 | Tue Jul 23 00:00:00 IDT 2019 |  | COMPLETED
4635 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Fri Jun 07 08:27:00 IDT 2019 | Wed Jun 19 08:27:00 IDT 2019 | Tue May 21 00:00:00 IDT 2019 | Thu Jul 25 00:00:00 IDT 2019 |  | COMPLETED
4636 | TT_TASK | EC+I | Tue May 14 08:27:00 IDT 2019 | Sat Jun 01 08:27:00 IDT 2019 | Tue May 14 08:27:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4637 | TT_TASK | Line Inspection | Wed Jul 31 08:00:00 IDT 2019 | Wed Aug 07 17:00:00 IDT 2019 | Wed Jul 10 00:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4638 | TT_TASK | Hydro Test | Mon Sep 02 10:53:00 IDT 2019 | Thu Sep 12 10:53:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Sat Oct 05 13:30:00 IDT 2019 |  | COMPLETED
4639 | TT_TASK | Painting/Insulation | Sat Jun 08 08:00:00 IDT 2019 | Thu Jun 20 08:27:00 IDT 2019 | Tue May 21 00:00:00 IDT 2019 | Thu Mar 26 18:00:00 IST 2020 |  | COMPLETED
4640 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Sat Oct 05 13:30:00 IDT 2019 | Tue Oct 15 13:30:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 | Thu Mar 26 18:00:00 IST 2020 |  | COMPLETED
4643 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 15 08:00:00 IDT 2019 | Sat May 11 18:00:00 IDT 2019 | Mon Apr 15 08:00:00 IDT 2019 | Tue Jul 09 00:00:00 IDT 2019 |  | COMPLETED
4644 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Tue Apr 30 08:00:00 IDT 2019 | Fri May 24 18:00:00 IDT 2019 | Thu May 09 00:00:00 IDT 2019 | Tue Jul 23 00:00:00 IDT 2019 |  | COMPLETED
4645 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Tue May 14 08:00:00 IDT 2019 | Wed Jun 05 18:00:00 IDT 2019 | Tue May 14 08:00:00 IDT 2019 | Wed Jul 24 00:00:00 IDT 2019 |  | COMPLETED
4646 | TT_TASK | EC+I | Fri May 24 15:18:00 IDT 2019 | Mon Jun 17 15:18:00 IDT 2019 | Fri May 24 15:18:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4647 | TT_TASK | Line Inspection | Fri Aug 02 08:00:00 IDT 2019 | Tue Aug 06 18:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4648 | TT_TASK | Hydro Test | Sat Aug 31 11:36:00 IDT 2019 | Mon Sep 09 11:36:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Fri Oct 04 13:30:00 IDT 2019 |  | COMPLETED
4649 | TT_TASK | Painting/Insulation | Mon May 13 08:00:00 IDT 2019 | Tue Jun 11 18:00:00 IDT 2019 | Mon May 13 08:00:00 IDT 2019 | Tue Nov 05 09:48:00 IST 2019 |  | COMPLETED
4650 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Fri Oct 04 13:30:00 IDT 2019 | Mon Oct 14 11:30:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 | Tue Nov 05 09:48:00 IST 2019 |  | COMPLETED
4652 | TT_TASK | Install Effluent Transfer Pump Station incl Canopy | Mon Jun 17 08:00:00 IDT 2019 | Thu Jun 27 18:00:00 IDT 2019 | Fri Jun 14 00:00:00 IDT 2019 | Thu Jul 11 18:00:00 IDT 2019 |  | COMPLETED
4653 | TT_TASK | Install Large Bore Pipe/Valves on Sleepers | Fri Jun 07 08:27:00 IDT 2019 | Wed Jul 03 08:27:00 IDT 2019 | Wed Jun 19 00:00:00 IDT 2019 | Mon Jul 08 11:36:00 IDT 2019 |  | COMPLETED
4654 | TT_TASK | Install Small Bore Pipe/Valves on Sleepers | Thu Jun 20 08:27:00 IDT 2019 | Mon Jul 15 08:27:00 IDT 2019 | Wed Jun 05 00:00:00 IDT 2019 | Wed Jul 10 00:00:00 IDT 2019 |  | COMPLETED
4655 | TT_TASK | EC+I | Wed Jun 12 17:06:00 IDT 2019 | Tue Jul 02 17:06:00 IDT 2019 | Tue May 21 00:00:00 IDT 2019 | Fri Jul 12 00:00:00 IDT 2019 |  | COMPLETED
4656 | TT_TASK | Line Inspection | Wed Jul 31 08:00:00 IDT 2019 | Thu Aug 08 18:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4657 | TT_TASK | Hydro Test | Sat Aug 31 16:12:00 IDT 2019 | Fri Sep 06 16:12:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Thu Oct 03 13:30:00 IDT 2019 |  | COMPLETED
4658 | TT_TASK | Painting/Insulation | Sat Jun 15 16:12:00 IDT 2019 | Fri Jul 05 16:12:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Thu Jul 11 14:24:00 IDT 2019 |  | COMPLETED
4659 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Thu Oct 03 13:30:00 IDT 2019 | Sat Oct 12 11:30:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 | Mon Feb 10 00:00:00 IST 2020 |  | COMPLETED
4660 | TT_TASK | Install Effluent Tanks incl Stairs/Platforms - Skid | Tue Apr 30 08:00:00 IDT 2019 | Sat May 18 18:00:00 IDT 2019 | Mon May 13 00:00:00 IDT 2019 | Wed Jun 26 00:00:00 IDT 2019 |  | COMPLETED
4661 | TT_TASK | Install Effluent Treatment Dispossal to Existing Station | Wed Oct 30 08:00:00 IST 2019 | Mon Dec 09 18:00:00 IST 2019 | Mon Oct 14 00:00:00 IDT 2019 | Sat Nov 23 18:00:00 IST 2019 |  | COMPLETED
4662 | TT_TASK | Install Sump Pumps | Mon Apr 01 08:00:00 IDT 2019 | Thu May 23 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Fri Jun 28 15:45:00 IDT 2019 |  | COMPLETED
4663 | TT_TASK | Install Piping Support Steelwork at Effluent Plant | Sat Apr 13 08:00:00 IDT 2019 | Thu Apr 25 18:00:00 IDT 2019 | Sat Apr 13 08:00:00 IDT 2019 | Wed Jul 10 00:00:00 IDT 2019 |  | COMPLETED
4664 | TT_TASK | Install Effluent Chemical (Caustic/Sulfuric Acid) Equipment | Tue Apr 30 08:00:00 IDT 2019 | Fri May 17 17:00:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Thu Jun 27 00:00:00 IDT 2019 |  | COMPLETED
4665 | TT_TASK | Install Large Bore Pipe/Valves - Remaining Sections to Pumps & U/G TP | Sat May 25 17:06:00 IDT 2019 | Wed Jun 19 17:06:00 IDT 2019 | Sat May 25 17:06:00 IDT 2019 | Thu Jun 27 00:00:00 IDT 2019 |  | COMPLETED
4666 | TT_TASK | Install Small Bore Pipe/Valves - Remaining Sections to Pumps & U/G TP | Sat May 25 17:06:00 IDT 2019 | Wed Jun 19 17:06:00 IDT 2019 | Sat May 25 17:06:00 IDT 2019 | Fri Jul 12 00:00:00 IDT 2019 |  | COMPLETED
4668 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 15 08:00:00 IDT 2019 | Mon May 06 18:00:00 IDT 2019 | Mon Apr 15 08:00:00 IDT 2019 | Wed Jul 17 00:00:00 IDT 2019 |  | COMPLETED
4669 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Tue Apr 02 08:00:00 IDT 2019 | Mon May 06 18:00:00 IDT 2019 | Tue Apr 02 08:00:00 IDT 2019 | Wed Jul 24 00:00:00 IDT 2019 |  | COMPLETED
4670 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Mon May 27 14:35:00 IDT 2019 | Wed Jun 05 13:35:00 IDT 2019 | Thu May 16 00:00:00 IDT 2019 | Tue Jul 23 00:00:00 IDT 2019 |  | COMPLETED
4671 | TT_TASK | Line Inspection | Wed Jul 31 08:00:00 IDT 2019 | Wed Aug 07 18:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Mon Sep 02 15:18:00 IDT 2019 |  | COMPLETED
4672 | TT_TASK | Hydro Test | Mon Sep 02 15:18:00 IDT 2019 | Tue Sep 10 15:18:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Fri Oct 04 13:30:00 IDT 2019 |  | COMPLETED
4673 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Fri Oct 04 13:30:00 IDT 2019 | Thu Oct 10 13:30:00 IDT 2019 | Tue Oct 08 00:00:00 IDT 2019 | Thu Oct 31 14:24:00 IST 2019 |  | COMPLETED
4676 | TT_TASK | Install Equipment/Skids/Pumps | Mon Apr 15 08:00:00 IDT 2019 | Mon May 06 18:00:00 IDT 2019 | Wed Apr 17 00:00:00 IDT 2019 | Tue Jul 09 00:00:00 IDT 2019 |  | COMPLETED
4677 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Tue Apr 30 08:00:00 IDT 2019 | Thu May 23 18:00:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4678 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Mon May 13 08:00:00 IDT 2019 | Tue May 21 17:00:00 IDT 2019 | Mon May 13 08:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4679 | TT_TASK | EC+I | Tue May 21 17:00:00 IDT 2019 | Tue Jun 04 17:00:00 IDT 2019 | Tue May 21 17:00:00 IDT 2019 | Fri Sep 27 00:00:00 IDT 2019 |  | COMPLETED
4680 | TT_TASK | Line Inspection | Wed Jul 31 11:33:00 IDT 2019 | Thu Aug 08 11:33:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4681 | TT_TASK | Hydro Test | Sat Aug 31 15:18:00 IDT 2019 | Mon Sep 09 15:18:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 |  | COMPLETED
4682 | TT_TASK | Painting/Insulation | Thu Jul 04 09:24:00 IDT 2019 | Fri Jul 12 09:24:00 IDT 2019 | Thu Jul 25 00:00:00 IDT 2019 | Wed Dec 18 00:00:00 IST 2019 |  | COMPLETED
4683 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Fri Oct 04 13:30:00 IDT 2019 | Mon Oct 14 13:30:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 | Wed Dec 18 00:00:00 IST 2019 |  | COMPLETED
4685 | TT_TASK | Install Equipment/Skids/Pumps | Tue Apr 16 08:00:00 IDT 2019 | Tue Apr 30 18:00:00 IDT 2019 | Thu Apr 18 00:00:00 IDT 2019 | Wed Jul 10 00:00:00 IDT 2019 |  | COMPLETED
4686 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Tue Apr 30 08:00:00 IDT 2019 | Tue May 21 18:00:00 IDT 2019 | Tue May 14 00:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4687 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Fri May 10 08:00:00 IDT 2019 | Fri May 31 18:00:00 IDT 2019 | Fri May 10 08:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4688 | TT_TASK | EC+I | Wed May 22 08:00:00 IDT 2019 | Sat Jun 01 18:00:00 IDT 2019 | Wed May 22 08:00:00 IDT 2019 | Fri Sep 27 00:00:00 IDT 2019 |  | COMPLETED
4689 | TT_TASK | Hydro Test | Sat Mar 28 08:00:00 IDT 2020 | Thu Apr 02 18:00:00 IDT 2020 | Sun Aug 04 00:00:00 IDT 2019 | Fri Aug 09 00:00:00 IDT 2019 |  | COMPLETED
4690 | TT_TASK | Painting/Insulation | Wed May 22 08:00:00 IDT 2019 | Sat Jun 01 18:00:00 IDT 2019 | Wed May 22 08:00:00 IDT 2019 | Thu Oct 03 00:00:00 IDT 2019 |  | COMPLETED
4691 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Fri Apr 03 08:00:00 IDT 2020 | Wed Apr 08 18:00:00 IDT 2020 | Sat Aug 10 00:00:00 IDT 2019 | Thu Aug 15 00:00:00 IDT 2019 |  | COMPLETED
4694 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 01 08:00:00 IDT 2019 | Sat Apr 27 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Tue Sep 03 00:00:00 IDT 2019 |  | COMPLETED
4695 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Sat Apr 13 08:00:00 IDT 2019 | Tue May 07 18:00:00 IDT 2019 | Sat Apr 13 08:00:00 IDT 2019 | Tue Sep 03 00:00:00 IDT 2019 |  | COMPLETED
4696 | TT_TASK | NDE | Sat Apr 13 08:00:00 IDT 2019 | Fri May 10 18:00:00 IDT 2019 | Sat Apr 13 08:00:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 |  | COMPLETED
4697 | TT_TASK | EC+I | Wed May 22 14:24:00 IDT 2019 | Fri Jun 14 14:24:00 IDT 2019 | Wed May 22 14:24:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4698 | TT_TASK | Line Inspection | Tue Sep 03 11:36:00 IDT 2019 | Mon Sep 09 11:36:00 IDT 2019 | Thu Sep 26 00:00:00 IDT 2019 | Tue Oct 08 00:00:00 IDT 2019 |  | COMPLETED
4699 | TT_TASK | Hydro Test | Fri Oct 04 08:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 | Mon Sep 30 00:00:00 IDT 2019 | Fri Oct 04 00:00:00 IDT 2019 |  | COMPLETED
4700 | TT_TASK | Painting/Insulation | Mon Jul 29 08:00:00 IDT 2019 | Wed Aug 14 18:00:00 IDT 2019 | Fri Jul 26 00:00:00 IDT 2019 | Mon Aug 12 18:00:00 IDT 2019 |  | COMPLETED
4701 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Mon Oct 21 15:45:00 IDT 2019 | Tue Oct 29 15:45:00 IST 2019 | Sat Oct 05 00:00:00 IDT 2019 | Mon Oct 14 18:00:00 IDT 2019 |  | COMPLETED
4703 | TT_TASK | Install Large Bore Pipe/Valves/Supports | Mon Apr 01 08:00:00 IDT 2019 | Thu May 02 10:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Fri Jul 26 00:00:00 IDT 2019 |  | COMPLETED
4704 | TT_TASK | Install Small Bore Pipe/Valves/Supports | Wed Mar 13 09:00:00 IST 2019 | Sat Apr 06 09:00:00 IDT 2019 | Fri Mar 01 00:00:00 IST 2019 | Thu Jul 25 00:00:00 IDT 2019 |  | COMPLETED
4705 | TT_TASK | NDE | Tue Apr 02 11:00:00 IDT 2019 | Tue May 07 10:00:00 IDT 2019 | Tue Apr 02 11:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4706 | TT_TASK | EC+I | Tue May 14 10:24:00 IDT 2019 | Thu Jun 06 10:24:00 IDT 2019 | Tue May 14 10:24:00 IDT 2019 | Wed Sep 25 00:00:00 IDT 2019 |  | COMPLETED
4707 | TT_TASK | Line Inspection | Sat Aug 03 15:48:00 IDT 2019 | Mon Aug 12 15:48:00 IDT 2019 | Thu Aug 22 00:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4708 | TT_TASK | Hydro Test | Mon Sep 30 08:00:00 IDT 2019 | Wed Oct 09 18:00:00 IDT 2019 | Fri Oct 18 00:00:00 IDT 2019 | Tue Oct 22 18:00:00 IDT 2019 |  | COMPLETED
4709 | TT_TASK | Painting/Insulation | Tue May 14 10:24:00 IDT 2019 | Thu Jun 06 18:00:00 IDT 2019 | Tue May 14 10:24:00 IDT 2019 | Mon Dec 23 18:00:00 IST 2019 |  | COMPLETED
4710 | TT_TASK | Pre-Commissioning/Flushing/Cleaning | Thu Oct 03 11:36:00 IDT 2019 | Sat Oct 12 11:36:00 IDT 2019 | Fri Oct 25 00:00:00 IDT 2019 | Mon Dec 23 18:00:00 IST 2019 |  | COMPLETED
4714 | TT_TASK | Cable Raceway | Mon Apr 01 08:00:00 IDT 2019 | Thu Apr 25 16:00:00 IDT 2019 | Wed Apr 03 00:00:00 IDT 2019 | Thu May 02 16:12:00 IDT 2019 |  | COMPLETED
4715 | TT_TASK | Precommissioning | Fri Aug 02 14:24:00 IDT 2019 | Wed Aug 14 14:24:00 IDT 2019 | Mon Aug 12 00:00:00 IDT 2019 | Mon Aug 19 00:00:00 IDT 2019 |  | COMPLETED
4716 | TT_TASK | BAT Transformer Installation Programme | Thu Feb 21 08:00:00 IST 2019 | Mon May 20 18:00:00 IDT 2019 | Wed Feb 06 00:00:00 IST 2019 | Wed Jun 26 13:30:00 IDT 2019 |  | COMPLETED
4717 | TT_TASK | Install, grout 30 Support Plates in Foundation | Tue Apr 30 08:00:00 IDT 2019 | Mon May 06 18:00:00 IDT 2019 | Tue Apr 30 08:00:00 IDT 2019 | Tue May 07 08:00:00 IDT 2019 |  | COMPLETED
4718 | TT_TASK | Cable Pulling | Thu May 02 16:12:00 IDT 2019 | Thu Jun 06 16:12:00 IDT 2019 | Thu May 02 16:12:00 IDT 2019 | Wed Jun 26 13:30:00 IDT 2019 |  | COMPLETED
4719 | TT_TASK | Cable Termination | Sat May 25 16:12:00 IDT 2019 | Thu Jun 06 16:12:00 IDT 2019 | Tue May 14 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4720 | TT_TASK | Hi Pot Testing | Wed Jun 26 13:30:00 IDT 2019 | Sat Jul 06 13:30:00 IDT 2019 | Sat Jun 29 00:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4722 | TT_TASK | Cable Raceway | Tue Apr 02 08:00:00 IDT 2019 | Tue Apr 16 16:00:00 IDT 2019 | Tue Apr 02 08:00:00 IDT 2019 | Tue Apr 16 18:00:00 IDT 2019 |  | COMPLETED
4723 | TT_TASK | SFC Transformer Installation Programme | Mon Mar 25 09:00:00 IST 2019 | Thu Apr 11 09:00:00 IDT 2019 | Wed Mar 27 00:00:00 IST 2019 | Tue Jun 04 00:00:00 IDT 2019 |  | COMPLETED
4724 | TT_TASK | Cable Pulling | Thu Apr 11 09:00:00 IDT 2019 | Wed May 15 09:00:00 IDT 2019 | Mon Mar 11 00:00:00 IST 2019 | Mon Jun 17 00:00:00 IDT 2019 |  | COMPLETED
4725 | TT_TASK | Cable Termination | Wed Jun 05 14:24:00 IDT 2019 | Mon Jun 17 14:24:00 IDT 2019 | Sat May 25 00:00:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 |  | COMPLETED
4726 | TT_TASK | Hi Pot Testing | Fri Jun 28 13:30:00 IDT 2019 | Thu Jul 04 13:30:00 IDT 2019 | Tue Jun 25 00:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4727 | TT_TASK | Precommissioning | Sat Aug 03 16:12:00 IDT 2019 | Thu Aug 15 16:12:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4729 | TT_TASK | BBT Transformer Installation Programme | Mon Mar 11 08:00:00 IST 2019 | Tue Apr 30 18:00:00 IDT 2019 | Wed Mar 20 00:00:00 IST 2019 | Mon Jun 03 09:48:00 IDT 2019 |  | COMPLETED
4730 | TT_TASK | Cable Raceway | Tue Apr 02 08:00:00 IDT 2019 | Tue Apr 16 16:00:00 IDT 2019 | Tue Apr 02 08:00:00 IDT 2019 | Fri May 03 09:48:00 IDT 2019 |  | COMPLETED
4731 | TT_TASK | Cable Termination | Tue May 07 16:12:00 IDT 2019 | Fri May 24 16:12:00 IDT 2019 | Tue May 07 16:12:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 |  | COMPLETED
4732 | TT_TASK | Cable Pulling | Mon Mar 25 09:00:00 IST 2019 | Fri Apr 26 09:00:00 IDT 2019 | Mon Mar 11 00:00:00 IST 2019 | Fri Jun 07 00:00:00 IDT 2019 |  | COMPLETED
4733 | TT_TASK | Hi Pot Testing | Thu Jun 06 16:17:00 IDT 2019 | Thu Jun 20 16:17:00 IDT 2019 | Fri Jun 28 00:00:00 IDT 2019 | Sat Aug 10 18:00:00 IDT 2019 |  | COMPLETED
4734 | TT_TASK | Precommissioning | Mon Aug 12 08:00:00 IDT 2019 | Mon Aug 26 18:00:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
4736 | TT_TASK | Cable Raceway | Tue Apr 02 08:00:00 IDT 2019 | Tue Apr 16 16:00:00 IDT 2019 | Tue Apr 02 08:00:00 IDT 2019 | Tue May 14 14:24:00 IDT 2019 |  | COMPLETED
4737 | TT_TASK | SEE Transformer Installation Programme | Mon Mar 25 09:00:00 IST 2019 | Thu Apr 11 09:00:00 IDT 2019 | Wed Mar 27 00:00:00 IST 2019 | Tue Jun 04 00:00:00 IDT 2019 |  | COMPLETED
4738 | TT_TASK | Cable Pulling | Thu Apr 11 09:00:00 IDT 2019 | Sat May 25 12:00:00 IDT 2019 | Mon Mar 11 00:00:00 IST 2019 | Thu Jun 27 00:00:00 IDT 2019 |  | COMPLETED
4739 | TT_TASK | Cable Termination | Tue Jun 25 09:48:00 IDT 2019 | Thu Jul 11 09:48:00 IDT 2019 | Fri May 10 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
4740 | TT_TASK | Hi Pot Testing | Mon Jul 08 09:48:00 IDT 2019 | Wed Jul 17 09:48:00 IDT 2019 | Tue Jul 16 00:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4741 | TT_TASK | Precommissioning | Mon Sep 02 10:20:00 IDT 2019 | Fri Sep 13 10:20:00 IDT 2019 | Mon Sep 02 10:20:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 |  | COMPLETED
4743 | TT_TASK | Cable Raceway | Fri Feb 22 08:00:00 IST 2019 | Fri Mar 15 16:00:00 IST 2019 | Fri Mar 01 00:00:00 IST 2019 | Wed Mar 13 00:00:00 IST 2019 |  | COMPLETED
4744 | TT_TASK | LV Transformer Installation Programme (7 days x 4 transformers) | Mon Mar 11 08:00:00 IST 2019 | Wed Apr 03 18:00:00 IDT 2019 | Wed Mar 27 00:00:00 IST 2019 | Wed Jun 12 13:30:00 IDT 2019 |  | COMPLETED
4745 | TT_TASK | Cable Pulling | Thu Apr 18 08:00:00 IDT 2019 | Thu May 16 18:00:00 IDT 2019 | Wed Mar 13 00:00:00 IST 2019 | Wed Mar 20 00:00:00 IST 2019 |  | COMPLETED
4746 | TT_TASK | Cable Termination | Fri May 03 08:54:00 IDT 2019 | Mon May 13 08:54:00 IDT 2019 | Fri May 03 08:54:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4747 | TT_TASK | Hi Pot Testing | Sat Jun 15 10:42:00 IDT 2019 | Thu Jun 27 10:42:00 IDT 2019 | Sat Jun 15 10:42:00 IDT 2019 | Tue Jul 23 00:00:00 IDT 2019 |  | COMPLETED
4748 | TT_TASK | Precommissioning | Wed Jul 31 11:36:00 IDT 2019 | Mon Aug 12 11:36:00 IDT 2019 | Wed Jul 24 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4750 | TT_TASK | Install Generator Circuit Breaker (GCB) onto Support Steel | Tue Jun 18 08:00:00 IDT 2019 | Thu Jul 04 18:00:00 IDT 2019 | Tue May 14 00:00:00 IDT 2019 | Fri Jul 26 00:00:00 IDT 2019 |  | COMPLETED
4751 | TT_TASK | Install Control Panel | Fri Jul 05 08:00:00 IDT 2019 | Thu Jul 11 18:00:00 IDT 2019 | Mon May 06 00:00:00 IDT 2019 | Sat Jul 27 00:00:00 IDT 2019 |  | COMPLETED
4752 | TT_TASK | Precommissioning | Wed Jul 31 08:00:00 IDT 2019 | Sat Aug 10 18:00:00 IDT 2019 | Sat Jul 27 00:00:00 IDT 2019 | Thu Aug 01 00:00:00 IDT 2019 |  | COMPLETED
4753 | TT_TASK | Test | Mon Aug 12 08:00:00 IDT 2019 | Thu Aug 22 18:00:00 IDT 2019 | Fri Aug 02 00:00:00 IDT 2019 | Tue Sep 03 00:00:00 IDT 2019 |  | COMPLETED
4755 | TT_TASK | Installation of IPB Cabinet (Neut. Grd, Sec CT, Earthing, Pressure Red., H2 Purge) | Mon May 13 08:00:00 IDT 2019 | Wed May 29 17:00:00 IDT 2019 | Mon May 13 08:00:00 IDT 2019 | Wed Nov 06 18:00:00 IST 2019 |  | COMPLETED
4756 | TT_TASK | IPB Connection to Generator & Generator Breaker after HI Voltage Test | Fri Jul 12 15:45:00 IDT 2019 | Tue Jul 16 15:45:00 IDT 2019 | Mon May 13 00:00:00 IDT 2019 | Thu Nov 07 18:00:00 IST 2019 |  | COMPLETED
4757 | TT_TASK | IPB Connection at Main Transformer & Auxiliary Transformers after HI Voltage Test | Thu Aug 29 09:00:00 IDT 2019 | Sat Aug 31 18:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 | Thu Oct 24 00:00:00 IDT 2019 |  | COMPLETED
4758 | TT_TASK | Installation of Surge Arrestor | Thu Jul 18 14:24:00 IDT 2019 | Tue Jul 23 13:24:00 IDT 2019 | Sat Jul 06 00:00:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
4759 | TT_TASK | IPB Connection at ExcitationTransformer & SFC Transformer after HI Voltage Test | Mon Sep 02 08:00:00 IDT 2019 | Wed Sep 04 17:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 | Thu Nov 07 18:00:00 IST 2019 |  | COMPLETED
4760 | TT_TASK | IPB Connection at Main Transformer & Auxiliary Transformers after HI Voltage Test | Mon Sep 02 08:00:00 IDT 2019 | Wed Sep 04 17:00:00 IDT 2019 | Thu Aug 15 00:00:00 IDT 2019 | Thu Nov 07 18:00:00 IST 2019 |  | COMPLETED
4761 | TT_TASK | Close Inspection Cover | Fri Nov 08 08:00:00 IST 2019 | Fri Nov 08 18:00:00 IST 2019 | Fri Nov 08 08:00:00 IST 2019 | Fri Nov 08 18:00:00 IST 2019 |  | COMPLETED
4762 | TT_TASK | Air Leakage Test | Tue Sep 10 14:54:00 IDT 2019 | Fri Sep 13 14:54:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 | Wed Sep 25 00:00:00 IDT 2019 |  | COMPLETED
4763 | TT_TASK | Precommissioning | Sat Nov 09 08:00:00 IST 2019 | Tue Nov 12 18:00:00 IST 2019 | Sat Nov 09 08:00:00 IST 2019 | Tue Nov 12 18:00:00 IST 2019 |  | COMPLETED
4764 | TT_TASK | Install Steel Structure @ Generator Area | Mon Apr 01 08:00:00 IDT 2019 | Thu May 23 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Tue Jul 23 00:00:00 IDT 2019 |  | COMPLETED
4765 | TT_TASK | Install/Align/Weld IPB | Sat Jun 01 15:45:00 IDT 2019 | Wed Jul 03 15:45:00 IDT 2019 | Thu May 16 00:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4766 | TT_TASK | NDE | Tue Jun 04 15:45:00 IDT 2019 | Wed Jul 10 15:45:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4767 | TT_TASK | Install Support Steel Transformer Area | Fri Apr 26 08:00:00 IDT 2019 | Fri May 10 17:00:00 IDT 2019 | Fri Apr 26 08:00:00 IDT 2019 | Wed Jul 24 00:00:00 IDT 2019 |  | COMPLETED
4768 | TT_TASK | Install Air Piping from Pressure Reducing Cubicle to Taps @ IPB Enclosure | Tue May 14 10:39:00 IDT 2019 | Wed May 22 09:39:00 IDT 2019 | Tue May 14 10:39:00 IDT 2019 | Thu Nov 07 18:00:00 IST 2019 |  | COMPLETED
4769 | TT_TASK | Install Air Piping from Pressure Reducing Cubicle to Taps @ IPB Enclosure | Thu Jul 18 14:24:00 IDT 2019 | Mon Jul 22 14:24:00 IDT 2019 | Sat Jul 27 00:00:00 IDT 2019 | Thu Nov 07 18:00:00 IST 2019 |  | COMPLETED
4770 | TT_TASK | Installation of Short Circuit Devise | Wed Jun 26 15:18:00 IDT 2019 | Wed Jul 03 15:18:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 |  | COMPLETED
4771 | TT_TASK | Hi Potential Test | Mon Sep 02 13:30:00 IDT 2019 | Sat Sep 07 13:30:00 IDT 2019 | Mon Sep 02 13:30:00 IDT 2019 | Sat Sep 07 13:30:00 IDT 2019 |  | COMPLETED
4773 | TT_TASK | Set Generator Protection Panel, Align & Bolt | Tue Apr 30 17:00:00 IDT 2019 | Wed May 08 16:00:00 IDT 2019 | Tue Apr 30 17:00:00 IDT 2019 | Mon May 06 00:00:00 IDT 2019 |  | COMPLETED
4774 | TT_TASK | Install Generator Protection Panel Relays | Tue Jun 04 14:24:00 IDT 2019 | Tue Jun 11 14:24:00 IDT 2019 | Tue May 07 00:00:00 IDT 2019 | Wed Jul 24 00:00:00 IDT 2019 |  | COMPLETED
4775 | TT_TASK | Install Cable Tray | Tue Apr 30 17:00:00 IDT 2019 | Sat May 25 17:00:00 IDT 2019 | Tue Apr 30 17:00:00 IDT 2019 | Mon May 13 13:30:00 IDT 2019 |  | COMPLETED
4776 | TT_TASK | Cable Pulling & Terminations | Sat May 25 17:00:00 IDT 2019 | Sat Jun 15 17:00:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Fri Aug 02 00:00:00 IDT 2019 |  | COMPLETED
4777 | TT_TASK | Hi Pot | Thu Jun 13 15:18:00 IDT 2019 | Thu Jun 20 15:18:00 IDT 2019 | Wed Jun 26 00:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4778 | TT_TASK | Precommissioning | Fri Aug 02 08:54:00 IDT 2019 | Mon Aug 12 08:54:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 | Fri Aug 30 00:00:00 IDT 2019 |  | COMPLETED
4780 | TT_TASK | Set Excitation Control & Circuit Breaker Panels, Align & Bolt | Tue Jun 04 14:24:00 IDT 2019 | Wed Jun 12 13:24:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Wed Jul 17 00:00:00 IDT 2019 |  | COMPLETED
4781 | TT_TASK | Install Relays | Wed Jun 12 13:24:00 IDT 2019 | Wed Jun 19 13:24:00 IDT 2019 | Tue May 21 00:00:00 IDT 2019 | Fri Jul 26 00:00:00 IDT 2019 |  | COMPLETED
4782 | TT_TASK | Install Cable Tray | Tue Jun 04 14:24:00 IDT 2019 | Sat Jun 22 14:24:00 IDT 2019 | Tue May 07 00:00:00 IDT 2019 | Tue May 21 00:00:00 IDT 2019 |  | COMPLETED
4783 | TT_TASK | Cable Puling & Terminations | Sat Jun 22 14:24:00 IDT 2019 | Wed Jul 17 14:24:00 IDT 2019 | Wed May 22 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4784 | TT_TASK | Hi Pot | Tue Jun 18 08:00:00 IDT 2019 | Mon Jun 24 18:00:00 IDT 2019 | Thu Jun 27 00:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4785 | TT_TASK | Precommissioning | Sat Aug 03 08:00:00 IDT 2019 | Thu Aug 08 18:00:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
4787 | TT_TASK | Set Static Start-up Panel & Switichgear, Align & Bolt | Mon Apr 15 16:00:00 IDT 2019 | Thu Apr 25 16:00:00 IDT 2019 | Wed Mar 27 00:00:00 IST 2019 | Tue Jul 23 00:00:00 IDT 2019 |  | COMPLETED
4788 | TT_TASK | Install Relays | Mon Jun 17 15:12:00 IDT 2019 | Mon Jun 24 15:12:00 IDT 2019 | Tue May 14 00:00:00 IDT 2019 | Fri Jul 26 00:00:00 IDT 2019 |  | COMPLETED
4789 | TT_TASK | Install Cable Tray | Fri May 03 16:00:00 IDT 2019 | Sat May 25 15:00:00 IDT 2019 | Mon Mar 11 00:00:00 IST 2019 | Wed May 08 00:00:00 IDT 2019 |  | COMPLETED
4790 | TT_TASK | Cable Puling & Terminations | Sat May 25 15:00:00 IDT 2019 | Mon Jun 17 15:00:00 IDT 2019 | Mon Mar 11 00:00:00 IST 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4791 | TT_TASK | Hi Pot | Wed Jul 10 17:06:00 IDT 2019 | Wed Jul 17 17:06:00 IDT 2019 | Wed Jul 17 00:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4792 | TT_TASK | Precommissioning | Tue Aug 06 11:57:00 IDT 2019 | Sat Aug 10 11:57:00 IDT 2019 | Tue Aug 06 11:57:00 IDT 2019 | Tue Oct 08 00:00:00 IDT 2019 |  | COMPLETED
4796 | TT_TASK | Switchgear Cubicles Installation/ Bolting | Mon Apr 08 08:00:00 IDT 2019 | Thu May 16 09:00:00 IDT 2019 | Wed Apr 10 00:00:00 IDT 2019 | Thu May 09 13:30:00 IDT 2019 |  | COMPLETED
4797 | TT_TASK | Cable Raceway | Tue Apr 02 08:00:00 IDT 2019 | Tue Apr 16 18:00:00 IDT 2019 | Fri Mar 01 00:00:00 IST 2019 | Tue Apr 30 18:00:00 IDT 2019 |  | COMPLETED
4798 | TT_TASK | Protection Panel | Thu May 09 13:30:00 IDT 2019 | Fri May 24 16:30:00 IDT 2019 | Thu May 09 13:30:00 IDT 2019 | Fri May 24 16:30:00 IDT 2019 |  | COMPLETED
4799 | TT_TASK | UPS/DC Cable Pulling | Fri May 24 16:30:00 IDT 2019 | Mon Jun 10 09:30:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Fri Jul 26 00:00:00 IDT 2019 |  | COMPLETED
4800 | TT_TASK | Distribution Panel | Mon Jun 10 09:30:00 IDT 2019 | Tue Jun 25 13:30:00 IDT 2019 | Tue May 14 00:00:00 IDT 2019 | Thu May 16 00:00:00 IDT 2019 |  | COMPLETED
4801 | TT_TASK | Bus Torquing/Connection | Tue Jun 25 13:30:00 IDT 2019 | Tue Jul 09 13:30:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4802 | TT_TASK | Hi Pot Testing | Tue Jul 16 11:36:00 IDT 2019 | Wed Jul 31 11:36:00 IDT 2019 | Tue Jul 16 11:36:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4804 | TT_TASK | Switchgear Cubicles Installation/ Bolting | Mon Apr 08 08:00:00 IDT 2019 | Fri May 03 16:00:00 IDT 2019 | Wed Apr 10 00:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4805 | TT_TASK | Cable Raceway | Wed Feb 27 08:00:00 IST 2019 | Thu Mar 21 18:00:00 IST 2019 | Mon Feb 11 00:00:00 IST 2019 | Sat Apr 27 18:00:00 IDT 2019 |  | COMPLETED
4806 | TT_TASK | Protection Panel | Sat May 11 08:00:00 IDT 2019 | Wed May 15 18:00:00 IDT 2019 | Sat May 11 08:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4807 | TT_TASK | UPS/DC Cable Pulling | Thu May 16 08:00:00 IDT 2019 | Sat Jun 01 18:00:00 IDT 2019 | Thu May 16 08:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4808 | TT_TASK | Distribution Panel | Mon Jun 03 08:00:00 IDT 2019 | Thu Jun 06 17:00:00 IDT 2019 | Sun May 12 00:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4809 | TT_TASK | Bus Torquing/Connection | Thu Jun 06 17:00:00 IDT 2019 | Tue Jun 11 17:00:00 IDT 2019 | Fri May 17 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4810 | TT_TASK | Hi Pot Testing | Mon Jul 22 15:45:00 IDT 2019 | Fri Jul 26 15:45:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 | Sat Aug 03 16:12:00 IDT 2019 |  | COMPLETED
4812 | TT_TASK | Switchgear Cubicles Installation/ Bolting | Tue Apr 02 08:00:00 IDT 2019 | Fri May 24 16:00:00 IDT 2019 | Sun Mar 10 00:00:00 IST 2019 | Fri May 03 18:00:00 IDT 2019 |  | COMPLETED
4813 | TT_TASK | Cable Raceway | Tue Apr 02 08:00:00 IDT 2019 | Sat Apr 06 17:00:00 IDT 2019 | Fri Mar 01 00:00:00 IST 2019 | Wed Apr 17 00:00:00 IDT 2019 |  | COMPLETED
4814 | TT_TASK | Protection Panel | Tue Apr 16 17:00:00 IDT 2019 | Sat Apr 20 17:00:00 IDT 2019 | Tue Apr 16 17:00:00 IDT 2019 | Sat May 04 09:48:00 IDT 2019 |  | COMPLETED
4815 | TT_TASK | UPS/DC Cable Pulling | Sat May 04 09:48:00 IDT 2019 | Thu May 09 09:48:00 IDT 2019 | Sat May 04 09:48:00 IDT 2019 | Fri May 17 00:00:00 IDT 2019 |  | COMPLETED
4816 | TT_TASK | Distribution Panel | Thu May 09 09:48:00 IDT 2019 | Tue May 14 09:48:00 IDT 2019 | Thu May 09 09:48:00 IDT 2019 | Tue May 14 09:48:00 IDT 2019 |  | COMPLETED
4817 | TT_TASK | Bus Torquing/Connection | Tue May 14 09:48:00 IDT 2019 | Sat May 18 09:48:00 IDT 2019 | Tue May 14 09:48:00 IDT 2019 | Sat May 18 09:48:00 IDT 2019 |  | COMPLETED
4818 | TT_TASK | Hi Pot Testing | Sat May 18 09:48:00 IDT 2019 | Thu May 23 09:48:00 IDT 2019 | Sat May 18 09:48:00 IDT 2019 | Sat May 25 00:00:00 IDT 2019 |  | COMPLETED
4820 | TT_TASK | Switchgear Cubicles Installation/ Bolting | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 26 16:00:00 IDT 2019 | Sun Mar 10 00:00:00 IST 2019 | Thu May 02 18:00:00 IDT 2019 |  | COMPLETED
4821 | TT_TASK | Cable Raceway | Mon Apr 01 08:00:00 IDT 2019 | Thu Apr 18 18:00:00 IDT 2019 | Fri Mar 01 00:00:00 IST 2019 | Tue May 14 13:30:00 IDT 2019 |  | COMPLETED
4822 | TT_TASK | Protection Panel | Mon Apr 15 08:00:00 IDT 2019 | Thu May 02 18:00:00 IDT 2019 | Mon Apr 15 08:00:00 IDT 2019 | Thu May 09 18:00:00 IDT 2019 |  | COMPLETED
4823 | TT_TASK | UPS/DC Cable Pulling | Sat Apr 13 13:30:00 IDT 2019 | Fri May 03 13:30:00 IDT 2019 | Sat Apr 13 13:30:00 IDT 2019 | Sat Jul 27 00:00:00 IDT 2019 |  | COMPLETED
4824 | TT_TASK | Bus Torquing | Mon Apr 29 13:30:00 IDT 2019 | Wed May 08 13:30:00 IDT 2019 | Mon Apr 29 13:30:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 |  | COMPLETED
4825 | TT_TASK | Hi Pot Testing | Tue Jun 18 09:48:00 IDT 2019 | Wed Jul 03 09:48:00 IDT 2019 | Tue Jun 04 00:00:00 IDT 2019 | Sat Jul 13 00:00:00 IDT 2019 |  | COMPLETED
4826 | TT_TASK | Install & Test 6.6kV Switchgear Panel x 2 | Thu Mar 01 08:00:00 IST 2018 | Tue Mar 06 12:00:00 IST 2018 | Thu Feb 22 08:00:00 IST 2018 | Mon Feb 26 18:00:00 IST 2018 |  | COMPLETED
4828 | TT_TASK | Pull Temp. MV Cable from Existing Station MV | Wed Jul 31 08:00:00 IDT 2019 | Tue Aug 20 18:00:00 IDT 2019 | Mon Jun 03 00:00:00 IDT 2019 | Tue Aug 20 00:00:00 IDT 2019 |  | COMPLETED
4830 | TT_TASK | Installation of Gas Insulated Line - GIL | Mon Apr 08 08:00:00 IDT 2019 | Fri May 03 16:00:00 IDT 2019 | Wed Apr 10 00:00:00 IDT 2019 | Mon May 20 18:00:00 IDT 2019 |  | COMPLETED
4831 | TT_TASK | Cable Raceway | Tue May 21 08:00:00 IDT 2019 | Fri May 24 17:00:00 IDT 2019 | Tue May 14 00:00:00 IDT 2019 | Thu Jun 20 17:45:00 IDT 2019 |  | COMPLETED
4832 | TT_TASK | Protection Panel | Tue Jun 18 09:00:00 IDT 2019 | Sat Jun 22 09:00:00 IDT 2019 | Fri May 17 00:00:00 IDT 2019 | Fri May 24 00:00:00 IDT 2019 |  | COMPLETED
4833 | TT_TASK | UPS/DC Cable Pulling | Sat Jun 22 09:00:00 IDT 2019 | Thu Jun 27 09:00:00 IDT 2019 | Wed May 22 00:00:00 IDT 2019 | Wed Jul 31 09:48:00 IDT 2019 |  | COMPLETED
4834 | TT_TASK | Bus Torquing | Thu Jun 27 09:00:00 IDT 2019 | Wed Jul 03 09:00:00 IDT 2019 | Thu May 23 00:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4835 | TT_TASK | Hi Pot Testing | Thu Jun 27 11:21:00 IDT 2019 | Wed Jul 03 11:21:00 IDT 2019 | Thu Jun 27 11:21:00 IDT 2019 | Fri Aug 02 14:24:00 IDT 2019 |  | COMPLETED
4836 | TT_TASK | Connection of HV Cable to 400Kv Building | Thu Jun 20 08:00:00 IDT 2019 | Sat Jun 29 17:00:00 IDT 2019 | Thu Jun 20 08:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4838 | TT_TASK | Switchgear Cubicles Installation/ Bolting | Mon Apr 01 08:00:00 IDT 2019 | Wed Apr 17 16:00:00 IDT 2019 | Tue Apr 09 00:00:00 IDT 2019 | Wed May 08 18:00:00 IDT 2019 |  | COMPLETED
4839 | TT_TASK | Cable Raceway | Tue Apr 30 08:00:00 IDT 2019 | Mon May 13 18:00:00 IDT 2019 | Tue Apr 30 08:00:00 IDT 2019 | Mon May 13 18:00:00 IDT 2019 |  | COMPLETED
4840 | TT_TASK | Protection Panel | Sat Apr 13 08:00:00 IDT 2019 | Wed Apr 17 18:00:00 IDT 2019 | Sat Apr 13 08:00:00 IDT 2019 | Fri May 17 09:48:00 IDT 2019 |  | COMPLETED
4841 | TT_TASK | UPS/DC Cable Pulling | Tue May 14 08:00:00 IDT 2019 | Thu May 30 18:00:00 IDT 2019 | Tue May 14 08:00:00 IDT 2019 | Wed Jul 24 00:00:00 IDT 2019 |  | COMPLETED
4842 | TT_TASK | Distribution Panel | Fri May 31 08:00:00 IDT 2019 | Tue Jun 04 18:00:00 IDT 2019 | Tue May 21 00:00:00 IDT 2019 | Fri May 24 00:00:00 IDT 2019 |  | COMPLETED
4843 | TT_TASK | Bus Torquing/Connection | Wed Jun 05 17:00:00 IDT 2019 | Wed Jun 12 17:00:00 IDT 2019 | Tue May 21 00:00:00 IDT 2019 | Sat Jul 20 18:00:00 IDT 2019 |  | COMPLETED
4844 | TT_TASK | Hi Pot Testing | Wed Jun 12 17:00:00 IDT 2019 | Sat Jun 15 17:00:00 IDT 2019 | Thu May 23 00:00:00 IDT 2019 | Thu Jul 25 18:00:00 IDT 2019 |  | COMPLETED
4845 | TT_TASK | Installation of Batteries, Battery Charger, Converter & Inverter and UPS System | Thu May 09 08:00:00 IDT 2019 | Wed Jun 05 17:00:00 IDT 2019 | Thu May 09 08:00:00 IDT 2019 | Tue Jun 18 13:45:00 IDT 2019 |  | COMPLETED
4849 | TT_TASK | Install Cabling | Tue Jun 18 17:00:00 IDT 2019 | Sat Jul 13 17:00:00 IDT 2019 | Fri May 24 00:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
4850 | TT_TASK | Install Accessories/Supports | Mon Apr 01 08:00:00 IDT 2019 | Tue Apr 23 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Sat May 18 18:00:00 IDT 2019 |  | COMPLETED
4851 | TT_TASK | Install equipment | Mon May 20 08:00:00 IDT 2019 | Sat Jun 08 18:00:00 IDT 2019 | Mon May 13 00:00:00 IDT 2019 | Sat Jun 29 00:00:00 IDT 2019 |  | COMPLETED
4852 | TT_TASK | Install Primary Containment | Mon Jun 10 08:00:00 IDT 2019 | Thu Jun 13 17:00:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 | Tue Jul 16 00:00:00 IDT 2019 |  | COMPLETED
4853 | TT_TASK | Install Secondary Containment | Thu Jun 13 17:00:00 IDT 2019 | Tue Jun 18 17:00:00 IDT 2019 | Fri May 24 00:00:00 IDT 2019 | Wed Jul 17 00:00:00 IDT 2019 |  | COMPLETED
4854 | TT_TASK | Test | Fri Aug 02 08:54:00 IDT 2019 | Wed Aug 07 08:54:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4856 | TT_TASK | Lay the Earthing Conductors from the Equipment to Designated Earth Pit | Mon Jun 17 08:00:00 IDT 2019 | Tue Jul 23 18:00:00 IDT 2019 | Tue May 21 00:00:00 IDT 2019 | Tue Jul 23 00:00:00 IDT 2019 |  | COMPLETED
4857 | TT_TASK | Install Accessories/Supports/Mounting Fitting | Mon Apr 01 08:00:00 IDT 2019 | Fri Apr 12 17:00:00 IDT 2019 | Wed Apr 10 00:00:00 IDT 2019 | Fri May 10 15:24:00 IDT 2019 |  | COMPLETED
4858 | TT_TASK | Install equipment | Fri Apr 12 17:00:00 IDT 2019 | Sat Apr 27 16:00:00 IDT 2019 | Fri Apr 12 17:00:00 IDT 2019 | Wed Jun 19 00:00:00 IDT 2019 |  | COMPLETED
4859 | TT_TASK | Install Secondary Containment | Fri May 31 08:00:00 IDT 2019 | Fri Jul 05 18:00:00 IDT 2019 | Wed May 22 00:00:00 IDT 2019 | Thu Jul 18 00:00:00 IDT 2019 |  | COMPLETED
4860 | TT_TASK | Install Primary Containment | Thu May 23 08:12:00 IDT 2019 | Thu Jun 27 17:12:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4861 | TT_TASK | Test | Tue Sep 10 11:36:00 IDT 2019 | Mon Sep 16 11:36:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4862 | TT_TASK | Complete all Terminations | Thu Jun 06 08:00:00 IDT 2019 | Sat Jun 29 18:00:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
4864 | TT_TASK | Install Cabling | Fri May 31 08:00:00 IDT 2019 | Mon Jun 24 18:00:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 | Thu Sep 12 00:00:00 IDT 2019 |  | COMPLETED
4865 | TT_TASK | Install Accessories/Supports/Mounting/Fittings | Mon Apr 01 08:00:00 IDT 2019 | Mon May 06 18:00:00 IDT 2019 | Mon Apr 08 00:00:00 IDT 2019 | Fri May 17 00:00:00 IDT 2019 |  | COMPLETED
4866 | TT_TASK | Install Equipment | Wed May 15 08:00:00 IDT 2019 | Sat Jun 15 16:00:00 IDT 2019 | Wed May 15 08:00:00 IDT 2019 | Wed Jul 03 00:00:00 IDT 2019 |  | COMPLETED
4867 | TT_TASK | Install Primary Containment | Wed May 29 16:00:00 IDT 2019 | Thu Jun 27 16:00:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Tue Jul 16 00:00:00 IDT 2019 |  | COMPLETED
4868 | TT_TASK | Install Secondary Containment | Sat Jun 15 16:00:00 IDT 2019 | Wed Jul 10 16:00:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4869 | TT_TASK | Test | Fri Aug 09 11:36:00 IDT 2019 | Wed Aug 14 11:36:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 | Tue Oct 08 00:00:00 IDT 2019 |  | COMPLETED
4870 | TT_TASK | Install All Termination Rods | Fri Jun 21 16:00:00 IDT 2019 | Sat Jul 06 16:00:00 IDT 2019 | Thu May 23 00:00:00 IDT 2019 | Wed Jul 31 14:24:00 IDT 2019 |  | COMPLETED
4871 | TT_TASK | Install Downcomers | Fri May 31 08:00:00 IDT 2019 | Thu Jun 27 18:00:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 | Thu Aug 22 00:00:00 IDT 2019 |  | COMPLETED
4875 | TT_TASK | Installation of Gas Detection and System | Tue Apr 30 08:00:00 IDT 2019 | Mon Jun 03 18:00:00 IDT 2019 | Tue May 07 00:00:00 IDT 2019 | Wed May 22 00:00:00 IDT 2019 |  | COMPLETED
4876 | TT_TASK | Installation of instrument, equipment and cable for gas detection system for Gas Turbine & Auxiliaries | Thu May 23 16:00:00 IDT 2019 | Sat Jun 15 16:00:00 IDT 2019 | Thu May 23 16:00:00 IDT 2019 | Thu Oct 17 00:00:00 IDT 2019 |  | COMPLETED
4877 | TT_TASK | Installation of Gas Detection System for BOP | Tue Apr 30 08:00:00 IDT 2019 | Thu Aug 01 12:00:00 IDT 2019 | Thu Mar 07 00:00:00 IST 2019 | Wed Jan 08 00:00:00 IST 2020 |  | COMPLETED
4879 | TT_TASK | Lighting and Small Power Installation & Commissioning FW Area | Fri May 31 15:07:00 IDT 2019 | Wed Jun 12 15:07:00 IDT 2019 | Fri May 31 15:07:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
4880 | TT_TASK | Installation Lighting and Small Power | Mon Apr 01 08:00:00 IDT 2019 | Sat May 04 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
4881 | TT_TASK | Remaining Lighting and Small Power Finished | Mon Sep 30 08:00:00 IDT 2019 | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4882 | TT_TASK | Lighting and Small Power Installation (10UBA) | Sat Jun 22 08:00:00 IDT 2019 | Wed Jul 10 17:00:00 IDT 2019 | Wed May 22 00:00:00 IDT 2019 | Tue Sep 24 00:00:00 IDT 2019 |  | COMPLETED
4884 | TT_TASK | Install Accessories/Supports | Thu Aug 22 08:00:00 IDT 2019 | Sat Sep 07 18:00:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Wed Jul 03 00:00:00 IDT 2019 |  | COMPLETED
4885 | TT_TASK | Install Primary Containment | Mon Sep 09 08:00:00 IDT 2019 | Thu Oct 03 18:00:00 IDT 2019 | Wed Jul 03 00:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
4886 | TT_TASK | Install Secondary Containment | Fri Oct 04 08:00:00 IDT 2019 | Fri Oct 25 18:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
4887 | TT_TASK | Install Cabling | Fri Oct 04 08:00:00 IDT 2019 | Fri Nov 01 18:00:00 IST 2019 | Wed Aug 14 00:00:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
4890 | TT_TASK | Install Accessories/Supports | Mon Sep 30 08:00:00 IDT 2019 | Wed Oct 16 18:00:00 IDT 2019 | Mon Oct 07 00:00:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 |  | COMPLETED
4891 | TT_TASK | Install Primary Containment | Tue Oct 08 08:00:00 IDT 2019 | Tue Oct 22 18:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 | Thu Oct 17 00:00:00 IDT 2019 |  | COMPLETED
4892 | TT_TASK | Install Secondary Containment | Fri Oct 11 08:00:00 IDT 2019 | Tue Oct 22 18:00:00 IDT 2019 | Fri Oct 11 08:00:00 IDT 2019 | Thu Oct 17 00:00:00 IDT 2019 |  | COMPLETED
4893 | TT_TASK | Install Cabling | Thu Oct 17 08:00:00 IDT 2019 | Mon Oct 28 18:00:00 IST 2019 | Fri Oct 11 00:00:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 |  | COMPLETED
4895 | TT_TASK | Install Accessories/Supports | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 18 18:00:00 IDT 2019 | Tue Jul 02 00:00:00 IDT 2019 | Tue Jul 30 00:00:00 IDT 2019 |  | COMPLETED
4896 | TT_TASK | Install Primary Containment | Fri Oct 11 08:00:00 IDT 2019 | Mon Oct 28 18:00:00 IST 2019 | Tue Jul 02 00:00:00 IDT 2019 | Tue Jul 30 00:00:00 IDT 2019 |  | COMPLETED
4897 | TT_TASK | Install Secondary Containment | Mon Oct 21 08:00:00 IDT 2019 | Sat Nov 09 18:00:00 IST 2019 | Mon Sep 23 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4898 | TT_TASK | Install Cabling | Tue Nov 05 08:00:00 IST 2019 | Mon Nov 25 18:00:00 IST 2019 | Thu Oct 03 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4900 | TT_TASK | Install Accessories/Supports | Tue Oct 15 09:00:00 IDT 2019 | Sat Oct 26 09:00:00 IDT 2019 | Sat Oct 05 00:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
4901 | TT_TASK | Install Secondary Containment | Sat Oct 26 09:00:00 IDT 2019 | Sat Nov 09 09:00:00 IST 2019 | Sat Oct 05 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4902 | TT_TASK | Install Cabling | Sat Nov 09 09:00:00 IST 2019 | Sat Nov 23 09:00:00 IST 2019 | Sat Oct 05 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4904 | TT_TASK | Install Accessories/Supports | Mon Sep 30 08:00:00 IDT 2019 | Mon Oct 14 18:00:00 IDT 2019 | Fri Oct 04 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4905 | TT_TASK | Install Primary Containment | Wed Oct 09 08:00:00 IDT 2019 | Fri Oct 25 18:00:00 IDT 2019 | Fri Oct 04 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4906 | TT_TASK | Install Secondary Containment | Mon Oct 21 08:00:00 IDT 2019 | Wed Nov 06 18:00:00 IST 2019 | Fri Oct 04 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4907 | TT_TASK | Install Cabling | Thu Nov 07 08:00:00 IST 2019 | Tue Nov 26 18:00:00 IST 2019 | Fri Oct 04 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4909 | TT_TASK | Install Accessories/Supports | Mon Sep 30 08:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 | Wed Oct 02 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4910 | TT_TASK | Install Secondary Containment | Thu Oct 03 08:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 | Wed Oct 02 00:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 |  | COMPLETED
4911 | TT_TASK | Install Cabling | Sat Oct 05 08:00:00 IDT 2019 | Tue Oct 15 18:00:00 IDT 2019 | Wed Oct 02 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
4914 | TT_TASK | Installation of Emergency Diesel Generator Set ( XKA) | Tue Jul 16 08:00:00 IDT 2019 | Thu Aug 01 16:00:00 IDT 2019 | Mon Jul 22 00:00:00 IDT 2019 | Wed Oct 02 13:30:00 IDT 2019 |  | COMPLETED
4915 | TT_TASK | Install Pipework | Wed Jun 26 08:00:00 IDT 2019 | Wed Jul 17 18:00:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 |  | COMPLETED
4916 | TT_TASK | Cable Raceway | Fri Jul 12 08:00:00 IDT 2019 | Mon Jul 29 18:00:00 IDT 2019 | Tue Jun 04 00:00:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 |  | COMPLETED
4917 | TT_TASK | Pull Cables & Terminate | Thu Jul 18 08:00:00 IDT 2019 | Sat Aug 03 18:00:00 IDT 2019 | Thu Jun 06 00:00:00 IDT 2019 | Sat Nov 30 13:03:00 IST 2019 |  | COMPLETED
4918 | TT_TASK | Precommissioning | Sat Oct 05 16:12:00 IDT 2019 | Fri Oct 18 16:12:00 IDT 2019 | Tue Oct 15 00:00:00 IDT 2019 | Tue Nov 26 00:00:00 IST 2019 |  | COMPLETED
4921 | TT_TASK | ET200 Cabinet Installation including Supports | Sat Apr 13 08:00:00 IDT 2019 | Thu Apr 25 18:00:00 IDT 2019 | Sat Apr 13 08:00:00 IDT 2019 | Fri May 10 00:00:00 IDT 2019 |  | COMPLETED
4922 | TT_TASK | Grounding Supports | Mon Apr 01 08:00:00 IDT 2019 | Thu Apr 11 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4923 | TT_TASK | AC/DC Installation | Fri Jun 07 08:00:00 IDT 2019 | Mon Jun 24 18:00:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4924 | TT_TASK | Cable Installation | Tue May 28 08:00:00 IDT 2019 | Tue Jun 11 18:00:00 IDT 2019 | Tue May 28 08:00:00 IDT 2019 | Wed Aug 07 00:00:00 IDT 2019 |  | COMPLETED
4925 | TT_TASK | Communication Cable Installation | Tue May 28 08:00:00 IDT 2019 | Fri Jun 07 18:00:00 IDT 2019 | Tue May 28 08:00:00 IDT 2019 | Wed Aug 07 00:00:00 IDT 2019 |  | COMPLETED
4926 | TT_TASK | Primary and Secondary Containment Installation | Fri May 10 08:00:00 IDT 2019 | Mon May 27 18:00:00 IDT 2019 | Fri May 10 08:00:00 IDT 2019 | Wed Jul 10 00:00:00 IDT 2019 |  | COMPLETED
4927 | TT_TASK | Test System | Fri Aug 02 13:30:00 IDT 2019 | Fri Aug 16 13:30:00 IDT 2019 | Mon Aug 12 00:00:00 IDT 2019 | Wed Aug 14 00:00:00 IDT 2019 |  | COMPLETED
4929 | TT_TASK | ET200 Cabinet Installation including Supports | Mon Apr 01 08:00:00 IDT 2019 | Thu Apr 11 18:00:00 IDT 2019 | Fri Apr 05 00:00:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 |  | COMPLETED
4930 | TT_TASK | Grounding Supports | Sat Apr 13 08:00:00 IDT 2019 | Wed Apr 24 18:00:00 IDT 2019 | Sat Apr 13 08:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
4931 | TT_TASK | AC/DC Installation | Thu May 16 08:00:00 IDT 2019 | Mon May 27 18:00:00 IDT 2019 | Thu May 16 08:00:00 IDT 2019 | Wed Aug 07 00:00:00 IDT 2019 |  | COMPLETED
4932 | TT_TASK | Cable Installation | Thu May 16 08:00:00 IDT 2019 | Mon May 27 18:00:00 IDT 2019 | Thu May 16 08:00:00 IDT 2019 | Thu Aug 08 00:00:00 IDT 2019 |  | COMPLETED
4933 | TT_TASK | Communication Cable Installation | Tue May 28 08:00:00 IDT 2019 | Fri Jun 07 18:00:00 IDT 2019 | Tue May 28 08:00:00 IDT 2019 | Thu Aug 08 00:00:00 IDT 2019 |  | COMPLETED
4934 | TT_TASK | Primary and Secondary Containment Installation | Sat Apr 13 08:00:00 IDT 2019 | Wed Apr 24 18:00:00 IDT 2019 | Sat Apr 13 08:00:00 IDT 2019 | Wed Jul 10 00:00:00 IDT 2019 |  | COMPLETED
4935 | TT_TASK | Test System | Mon Aug 05 08:00:00 IDT 2019 | Thu Aug 15 18:00:00 IDT 2019 | Fri Aug 09 00:00:00 IDT 2019 | Tue Aug 13 00:00:00 IDT 2019 |  | COMPLETED
4937 | TT_TASK | ET200 Cabinet Installation including Supports | Wed Apr 17 08:00:00 IDT 2019 | Sat Apr 27 18:00:00 IDT 2019 | Wed Apr 17 08:00:00 IDT 2019 | Wed May 15 00:00:00 IDT 2019 |  | COMPLETED
4938 | TT_TASK | Grounding Supports | Fri Apr 26 08:00:00 IDT 2019 | Thu May 02 18:00:00 IDT 2019 | Fri Apr 26 08:00:00 IDT 2019 | Fri Aug 09 00:00:00 IDT 2019 |  | COMPLETED
4939 | TT_TASK | AC/DC Installation | Sat May 11 08:00:00 IDT 2019 | Wed May 22 18:00:00 IDT 2019 | Sat May 11 08:00:00 IDT 2019 | Fri Aug 23 00:00:00 IDT 2019 |  | COMPLETED
4940 | TT_TASK | Cable Installation | Thu May 23 08:00:00 IDT 2019 | Mon Jun 03 18:00:00 IDT 2019 | Thu May 23 08:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4941 | TT_TASK | Communication Cable Installation | Thu May 23 08:00:00 IDT 2019 | Mon Jun 03 18:00:00 IDT 2019 | Thu May 23 08:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
4942 | TT_TASK | Primary and Secondary Containment Installation | Mon May 06 08:00:00 IDT 2019 | Thu May 16 18:00:00 IDT 2019 | Mon May 06 08:00:00 IDT 2019 | Wed Jul 10 00:00:00 IDT 2019 |  | COMPLETED
4943 | TT_TASK | Test System | Mon Aug 05 13:30:00 IDT 2019 | Fri Aug 16 13:30:00 IDT 2019 | Tue Aug 06 00:00:00 IDT 2019 | Sat Aug 17 00:00:00 IDT 2019 |  | COMPLETED
4945 | TT_TASK | ET200 Cabinet Installation including Supports | Sat Aug 31 08:00:00 IDT 2019 | Sat Sep 07 18:00:00 IDT 2019 | Tue Aug 06 00:00:00 IDT 2019 | Tue Aug 13 00:00:00 IDT 2019 |  | COMPLETED
4946 | TT_TASK | Grounding Supports | Fri May 31 08:00:00 IDT 2019 | Tue Jun 11 18:00:00 IDT 2019 | Mon May 20 00:00:00 IDT 2019 | Thu May 30 00:00:00 IDT 2019 |  | COMPLETED
4947 | TT_TASK | AC/DC Installation | Wed Sep 04 08:00:00 IDT 2019 | Tue Sep 10 18:00:00 IDT 2019 | Wed Aug 14 00:00:00 IDT 2019 | Tue Aug 20 00:00:00 IDT 2019 |  | COMPLETED
4948 | TT_TASK | Cable Installation | Sat Aug 31 08:00:00 IDT 2019 | Fri Sep 06 18:00:00 IDT 2019 | Thu Aug 22 00:00:00 IDT 2019 | Fri Aug 23 00:00:00 IDT 2019 |  | COMPLETED
4949 | TT_TASK | Communication Cable Installation | Sat Aug 31 08:00:00 IDT 2019 | Fri Sep 06 18:00:00 IDT 2019 | Thu Aug 22 00:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
4950 | TT_TASK | Primary and Secondary Containment Installation | Sat Aug 31 08:00:00 IDT 2019 | Fri Sep 06 18:00:00 IDT 2019 | Tue Aug 06 00:00:00 IDT 2019 | Tue Aug 13 00:00:00 IDT 2019 |  | COMPLETED
4951 | TT_TASK | Test System | Sat Aug 31 08:00:00 IDT 2019 | Tue Sep 03 18:00:00 IDT 2019 | Mon Aug 26 00:00:00 IDT 2019 | Mon Aug 26 00:00:00 IDT 2019 |  | COMPLETED
4953 | TT_TASK | ET200 Cabinet Installation including Supports | Mon Sep 30 08:00:00 IDT 2019 | Thu Oct 10 18:00:00 IDT 2019 | Thu Jul 25 00:00:00 IDT 2019 | Wed Jul 31 00:00:00 IDT 2019 |  | COMPLETED
4954 | TT_TASK | Grounding Supports | Mon Sep 30 08:00:00 IDT 2019 | Thu Oct 10 18:00:00 IDT 2019 | Thu Jul 25 00:00:00 IDT 2019 | Wed Jul 31 00:00:00 IDT 2019 |  | COMPLETED
4955 | TT_TASK | AC/DC Installation | Thu Oct 03 08:00:00 IDT 2019 | Wed Oct 09 18:00:00 IDT 2019 | Wed Jul 31 00:00:00 IDT 2019 | Wed Aug 07 00:00:00 IDT 2019 |  | COMPLETED
4956 | TT_TASK | Cable Installation | Mon Sep 30 08:00:00 IDT 2019 | Wed Oct 09 18:00:00 IDT 2019 | Thu Aug 01 00:00:00 IDT 2019 | Fri Aug 09 00:00:00 IDT 2019 |  | COMPLETED
4957 | TT_TASK | Communication Cable Installation | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 11 18:00:00 IDT 2019 | Thu Aug 01 00:00:00 IDT 2019 | Fri Aug 09 00:00:00 IDT 2019 |  | COMPLETED
4958 | TT_TASK | Primary and Secondary Containment Installation | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 11 18:00:00 IDT 2019 | Thu Jul 25 00:00:00 IDT 2019 | Wed Jul 31 00:00:00 IDT 2019 |  | COMPLETED
4959 | TT_TASK | Test System | Mon Sep 30 08:00:00 IDT 2019 | Tue Oct 08 18:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 | Tue Aug 13 00:00:00 IDT 2019 |  | COMPLETED
4963 | TT_TASK | Erection Cable Trays Between UEY/UGY01 to UGD/USG/UGA/UGC/UEN | Mon Apr 01 08:00:00 IDT 2019 | Thu May 23 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Wed Jun 05 13:30:00 IDT 2019 |  | COMPLETED
4964 | TT_TASK | Erection Cable Trays Between 10UBA Building to UEY/10UEN | Mon Jan 21 08:00:00 IST 2019 | Wed Feb 27 18:00:00 IST 2019 | Mon Jan 21 08:00:00 IST 2019 | Wed May 08 00:00:00 IDT 2019 |  | COMPLETED
4965 | TT_TASK | Erection Cable Trays UMC to Generator (1f) | Wed Jan 02 08:00:00 IST 2019 | Fri Feb 22 18:00:00 IST 2019 | Tue Nov 13 00:00:00 IST 2018 | Wed May 15 00:00:00 IDT 2019 |  | COMPLETED
4966 | TT_TASK | Erection Cable Trays 10UBA Building to UBX/UBE/UBF | Wed Jan 02 08:00:00 IST 2019 | Wed Feb 20 18:00:00 IST 2019 | Mon Oct 22 00:00:00 IDT 2018 | Wed May 15 18:00:00 IDT 2019 |  | COMPLETED
4967 | TT_TASK | Cable Support Installation | Mon Apr 01 08:00:00 IDT 2019 | Thu Jun 27 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Wed Jun 19 00:00:00 IDT 2019 |  | COMPLETED
4968 | TT_TASK | Erection Cable Trays 10UBA Building to USA01-03 | Mon Apr 01 08:00:00 IDT 2019 | Thu May 23 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Fri Jun 14 00:00:00 IDT 2019 |  | COMPLETED
4969 | TT_TASK | Erection Cable Trays UMC to ST AND PUMPS (1d) | Mon Apr 01 08:00:00 IDT 2019 | Fri May 17 18:00:00 IDT 2019 | Mon Apr 01 08:00:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 |  | COMPLETED
4970 | TT_TASK | Erection Cable Trays UMC to GT (1e) | Tue Feb 12 15:00:00 IST 2019 | Mon Mar 25 15:00:00 IST 2019 | Tue Jan 15 00:00:00 IST 2019 | Tue May 21 00:00:00 IDT 2019 |  | COMPLETED
4972 | TT_TASK | Cabling From 10UBA Building to UCA / UYC | Mon Jun 03 08:00:00 IDT 2019 | Tue Jul 02 18:00:00 IDT 2019 | Fri May 03 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4973 | TT_TASK | Cabling From 10UBA Building to UAA | Tue Apr 30 08:00:00 IDT 2019 | Tue Jun 04 18:00:00 IDT 2019 | Mon May 06 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4974 | TT_TASK | Cabling 10UBA Building to 00UGD/UGA/UGC | Mon May 27 13:30:00 IDT 2019 | Tue Jul 02 13:30:00 IDT 2019 | Thu May 02 00:00:00 IDT 2019 | Fri May 31 00:00:00 IDT 2019 |  | COMPLETED
4975 | TT_TASK | Cabling 10UBA Building to USG | Tue Apr 30 08:00:00 IDT 2019 | Tue Jun 04 18:00:00 IDT 2019 | Wed May 08 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4976 | TT_TASK | Cabling 10UBA Building to UEL/UEH/UEJ | Tue Apr 30 08:00:00 IDT 2019 | Mon Jun 10 18:00:00 IDT 2019 | Fri May 03 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4977 | TT_TASK | Cabling From 10UBA (Switchgear) Building to 10UBN Diesel Generator | Thu Jul 18 08:00:00 IDT 2019 | Wed Aug 21 18:00:00 IDT 2019 | Sat Jun 01 00:00:00 IDT 2019 | Fri Sep 06 00:00:00 IDT 2019 |  | COMPLETED
4978 | TT_TASK | Cabling From 10UBA Building to ULA (FW Pumps)/UHA (HRSG) AND UHW (Blow Down Tank) | Fri May 24 08:00:00 IDT 2019 | Wed Jul 10 18:00:00 IDT 2019 | Fri May 24 08:00:00 IDT 2019 | Fri Sep 06 00:00:00 IDT 2019 |  | COMPLETED
4979 | TT_TASK | Cabling From 10UBA Building to UST | Mon Apr 01 08:00:00 IDT 2019 | Mon May 06 18:00:00 IDT 2019 | Mon Apr 08 00:00:00 IDT 2019 | Thu Sep 05 00:00:00 IDT 2019 |  | COMPLETED
4980 | TT_TASK | Cabling From 10UBA (Switchgear) Building to UBX/UBE/UBF (Transformers) | Tue Apr 16 08:00:00 IDT 2019 | Mon May 27 18:00:00 IDT 2019 | Tue Apr 16 08:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4981 | TT_TASK | Cabling Between 10UBA Building | Thu Feb 14 08:00:00 IST 2019 | Mon Mar 18 18:00:00 IST 2019 | Wed Feb 20 00:00:00 IST 2019 | Fri May 31 00:00:00 IDT 2019 |  | COMPLETED
4982 | TT_TASK | MV and LV Cable Pulling | Tue Apr 30 08:00:00 IDT 2019 | Sat Sep 21 18:00:00 IDT 2019 | Fri May 10 00:00:00 IDT 2019 | Mon Sep 09 00:00:00 IDT 2019 |  | COMPLETED
4983 | TT_TASK | Cabling 10UBA (Switchgear) Building to 10UEN (Gas Filter/Preheating) | Mon Jun 17 13:30:00 IDT 2019 | Fri Jul 12 13:30:00 IDT 2019 | Fri May 17 00:00:00 IDT 2019 | Mon Sep 02 11:09:00 IDT 2019 |  | COMPLETED
4984 | TT_TASK | Cabling From 10UBA Building to USA01-03 | Wed Jun 05 13:30:00 IDT 2019 | Thu Jul 11 13:30:00 IDT 2019 | Fri Jun 14 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
4987 | TT_TASK | Erection Security Other Buildings (Except UCA) | Sat Nov 30 08:00:00 IST 2019 | Sat Dec 28 18:00:00 IST 2019 | Mon Nov 04 00:00:00 IST 2019 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
4988 | TT_TASK | Install Equipment | Sat Aug 31 08:00:00 IDT 2019 | Mon Sep 30 18:00:00 IDT 2019 | Tue Aug 20 00:00:00 IDT 2019 | Mon Jan 13 18:00:00 IST 2020 |  | COMPLETED
4989 | TT_TASK | EC+I | Wed Sep 25 08:00:00 IDT 2019 | Sat Oct 19 18:00:00 IDT 2019 | Tue Aug 20 00:00:00 IDT 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
4990 | TT_TASK | Precommissioning | Sat Apr 04 08:00:00 IDT 2020 | Wed Apr 08 18:00:00 IDT 2020 | Tue Jan 14 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
4994 | TT_TASK | Install Skids/Euipment (Firehouse) | Mon Sep 30 08:00:00 IDT 2019 | Thu Oct 17 18:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 |  | COMPLETED
4995 | TT_TASK | Install LB Pipework/Valves/Supports (Firehouse) | Fri Oct 18 08:00:00 IDT 2019 | Tue Oct 29 18:00:00 IST 2019 | Wed Oct 09 00:00:00 IDT 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
4996 | TT_TASK | Install SB Pipework/Valves/Supports (Firehouse) | Thu Oct 24 08:00:00 IDT 2019 | Mon Nov 04 18:00:00 IST 2019 | Fri Oct 11 00:00:00 IDT 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
4997 | TT_TASK | Install Ring Main | Sat Feb 09 08:00:00 IST 2019 | Thu Jun 13 18:00:00 IDT 2019 | Tue Jan 15 00:00:00 IST 2019 | Fri Jan 17 00:00:00 IST 2020 |  | COMPLETED
4998 | TT_TASK | Install all Hydrants/Supports | Mon Oct 14 08:00:00 IDT 2019 | Wed Oct 30 18:00:00 IST 2019 | Mon Oct 14 08:00:00 IDT 2019 | Mon Jan 06 00:00:00 IST 2020 |  | COMPLETED
4999 | TT_TASK | EC+I | Sat Oct 12 08:00:00 IDT 2019 | Wed Nov 06 18:00:00 IST 2019 | Wed Oct 09 00:00:00 IDT 2019 | Fri Oct 18 00:00:00 IDT 2019 |  | COMPLETED
5000 | TT_TASK | Hydro Test | Thu Apr 02 13:30:00 IDT 2020 | Tue Apr 14 13:30:00 IDT 2020 | Tue Jan 07 00:00:00 IST 2020 | Fri Jan 17 00:00:00 IST 2020 |  | COMPLETED
5001 | TT_TASK | Precommissioning/Flush/Clean | Wed Apr 08 13:30:00 IDT 2020 | Tue Apr 14 13:30:00 IDT 2020 | Sun Jan 12 00:00:00 IST 2020 | Fri Jan 17 00:00:00 IST 2020 |  | COMPLETED
5002 | TT_TASK | Paint | Tue Nov 05 08:00:00 IST 2019 | Fri Nov 15 18:00:00 IST 2019 | Sat Oct 12 00:00:00 IDT 2019 | Fri Jan 17 00:00:00 IST 2020 |  | COMPLETED
5004 | TT_TASK | Install Deluge Pipework/Valves/Sprinklers | Wed Jul 31 08:00:00 IDT 2019 | Wed Aug 28 18:00:00 IDT 2019 | Mon Aug 05 00:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
5005 | TT_TASK | Install Supports | Thu Aug 29 08:00:00 IDT 2019 | Mon Sep 09 18:00:00 IDT 2019 | Wed Aug 07 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
5006 | TT_TASK | Hydro Test | Fri Oct 25 13:30:00 IDT 2019 | Wed Oct 30 13:30:00 IST 2019 | Thu Oct 10 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
5007 | TT_TASK | Precommissioning/Flush/Clean | Wed Oct 30 13:30:00 IST 2019 | Mon Nov 04 13:30:00 IST 2019 | Thu Oct 10 00:00:00 IDT 2019 | Mon Oct 14 00:00:00 IDT 2019 |  | COMPLETED
5008 | TT_TASK | Spray Test | Mon Nov 04 13:30:00 IST 2019 | Fri Nov 08 13:30:00 IST 2019 | Sat Oct 12 00:00:00 IDT 2019 | Tue Jan 14 00:00:00 IST 2020 |  | COMPLETED
5010 | TT_TASK | Install Deluge Pipework/Valves/Sprinklers | Thu Aug 08 08:00:00 IDT 2019 | Wed Aug 28 18:00:00 IDT 2019 | Thu Aug 08 08:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
5011 | TT_TASK | Install Supports | Wed Jul 31 08:00:00 IDT 2019 | Tue Aug 20 18:00:00 IDT 2019 | Mon Aug 05 00:00:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 |  | COMPLETED
5012 | TT_TASK | Hydro Test | Thu Oct 17 13:30:00 IDT 2019 | Sat Oct 26 13:30:00 IDT 2019 | Tue Oct 08 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
5013 | TT_TASK | Precommissioning/Flush/Clean | Sat Oct 26 13:30:00 IDT 2019 | Tue Nov 05 13:30:00 IST 2019 | Fri Oct 11 00:00:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 |  | COMPLETED
5014 | TT_TASK | Spray Test | Tue Mar 31 08:00:00 IDT 2020 | Wed Apr 08 18:00:00 IDT 2020 | Sat Jan 04 00:00:00 IST 2020 | Tue Jan 14 08:00:00 IST 2020 |  | COMPLETED
5015 | TT_TASK | Provide TEMP Fire Water Supply | Sat Nov 30 08:00:00 IST 2019 | Fri Dec 20 18:00:00 IST 2019 | Wed Nov 20 00:00:00 IST 2019 | Fri Jan 03 00:00:00 IST 2020 |  | COMPLETED
5017 | TT_TASK | Install LB Pipework/Valves/Supports | Mon Sep 30 08:00:00 IDT 2019 | Thu Oct 24 18:00:00 IDT 2019 | Tue Sep 17 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
5018 | TT_TASK | Install SB Pipework/Valves/Supports | Mon Sep 30 08:00:00 IDT 2019 | Fri Oct 18 18:00:00 IDT 2019 | Tue Sep 17 00:00:00 IDT 2019 | Mon Oct 14 13:30:00 IDT 2019 |  | COMPLETED
5019 | TT_TASK | Install all Hydrants/Supports | Mon Sep 30 08:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 | Tue Sep 17 00:00:00 IDT 2019 | Thu Oct 10 18:00:00 IDT 2019 |  | COMPLETED
5020 | TT_TASK | Hydro Test | Mon Oct 14 13:30:00 IDT 2019 | Fri Oct 18 13:30:00 IDT 2019 | Mon Oct 14 13:30:00 IDT 2019 | Fri Oct 18 13:30:00 IDT 2019 |  | COMPLETED
5021 | TT_TASK | Precommissioning/Flush/Clean | Fri Oct 18 13:30:00 IDT 2019 | Wed Oct 23 13:30:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 | Fri Jan 17 00:00:00 IST 2020 |  | COMPLETED
5022 | TT_TASK | Provide TEMP Fire Water Supply | Sat Nov 30 08:00:00 IST 2019 | Wed Dec 11 18:00:00 IST 2019 | Wed Nov 20 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5024 | TT_TASK | Install Pipework/Valves/Sprinklers | Tue Oct 08 08:00:00 IDT 2019 | Tue Nov 05 18:00:00 IST 2019 | Thu May 23 00:00:00 IDT 2019 | Sat Oct 12 18:00:00 IDT 2019 |  | COMPLETED
5025 | TT_TASK | Install Supports | Sat Oct 19 08:00:00 IDT 2019 | Mon Nov 11 18:00:00 IST 2019 | Thu May 23 00:00:00 IDT 2019 | Thu Oct 10 18:00:00 IDT 2019 |  | COMPLETED
5026 | TT_TASK | Hydro Test | Fri Oct 11 08:00:00 IDT 2019 | Tue Oct 15 18:00:00 IDT 2019 | Fri Oct 11 08:00:00 IDT 2019 | Tue Oct 15 18:00:00 IDT 2019 |  | COMPLETED
5027 | TT_TASK | Precommissioning/Flush/Clean | Wed Oct 16 08:00:00 IDT 2019 | Sat Oct 19 18:00:00 IDT 2019 | Wed Oct 16 08:00:00 IDT 2019 | Sat Oct 19 18:00:00 IDT 2019 |  | COMPLETED
5028 | TT_TASK | Spray Test | Sat Mar 28 08:00:00 IDT 2020 | Wed Apr 01 18:00:00 IDT 2020 | Sat Mar 07 00:00:00 IST 2020 | Thu Mar 12 00:00:00 IST 2020 |  | COMPLETED
5030 | TT_TASK | Install Deluge Pipework/Valves/Sprinklers | Fri Oct 25 08:00:00 IDT 2019 | Sat Nov 16 18:00:00 IST 2019 | Mon Aug 19 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
5031 | TT_TASK | Install Supports | Mon Sep 30 08:00:00 IDT 2019 | Thu Oct 24 18:00:00 IDT 2019 | Mon May 27 00:00:00 IDT 2019 | Thu Oct 17 18:00:00 IDT 2019 |  | COMPLETED
5032 | TT_TASK | Hydro Test | Fri Nov 01 08:00:00 IST 2019 | Tue Nov 05 18:00:00 IST 2019 | Wed Oct 09 00:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
5033 | TT_TASK | Precommissioning/Flush/Clean | Wed Nov 06 08:00:00 IST 2019 | Sat Nov 09 18:00:00 IST 2019 | Sat Oct 12 00:00:00 IDT 2019 | Thu Oct 17 00:00:00 IDT 2019 |  | COMPLETED
5034 | TT_TASK | Spray Test | Thu Apr 09 08:00:00 IDT 2020 | Mon Apr 13 18:00:00 IDT 2020 | Sat Mar 14 00:00:00 IST 2020 | Tue Mar 17 00:00:00 IST 2020 |  | COMPLETED
5036 | TT_TASK | Install Skid+Auxiliaries | Mon Sep 30 08:00:00 IDT 2019 | Tue Oct 15 18:00:00 IDT 2019 | Tue Oct 08 00:00:00 IDT 2019 | Sat Oct 19 00:00:00 IDT 2019 |  | COMPLETED
5037 | TT_TASK | Install all pipepwork and Supports | Wed Jul 31 08:00:00 IDT 2019 | Thu Sep 12 18:00:00 IDT 2019 | Fri Jul 05 00:00:00 IDT 2019 | Sat Oct 12 13:30:00 IDT 2019 |  | COMPLETED
5038 | TT_TASK | EC+I | Wed Oct 16 08:00:00 IDT 2019 | Tue Nov 12 18:00:00 IST 2019 | Mon Oct 14 00:00:00 IDT 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5039 | TT_TASK | Hydro Test | Sat Mar 28 08:00:00 IDT 2020 | Mon Apr 06 18:00:00 IDT 2020 | Thu Dec 26 00:00:00 IST 2019 | Sat Jan 04 00:00:00 IST 2020 |  | COMPLETED
5040 | TT_TASK | Precommissioning/Flush/Clean | Sat Mar 28 08:00:00 IDT 2020 | Mon Apr 06 18:00:00 IDT 2020 | Thu Dec 26 00:00:00 IST 2019 | Sat Jan 04 00:00:00 IST 2020 |  | COMPLETED
5042 | TT_TASK | Installation of Fire Fighting CO2 System for PCC 10SGJ | Fri Oct 11 08:00:00 IDT 2019 | Wed Nov 27 14:00:00 IST 2019 | Fri Jul 05 00:00:00 IDT 2019 | Sun Jan 05 00:00:00 IST 2020 |  | COMPLETED
5044 | TT_TASK | Installation Fire Detection System (SGY) | Fri Feb 15 08:00:00 IST 2019 | Wed Jun 19 18:00:00 IDT 2019 | Fri Feb 15 08:00:00 IST 2019 | Mon Jan 20 00:00:00 IST 2020 |  | COMPLETED
5048 | TT_TASK | Equipment Installation | Mon Apr 01 08:00:00 IDT 2019 | Wed Apr 17 18:00:00 IDT 2019 | Tue Apr 16 00:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
5049 | TT_TASK | Cable Raceways | Tue Apr 23 08:00:00 IDT 2019 | Sat May 18 18:00:00 IDT 2019 | Tue Apr 23 08:00:00 IDT 2019 | Thu Jun 27 00:00:00 IDT 2019 |  | COMPLETED
5050 | TT_TASK | Cable Pulling | Fri Jun 07 13:57:00 IDT 2019 | Wed Jul 03 13:57:00 IDT 2019 | Thu May 30 00:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
5051 | TT_TASK | Cable Termination | Fri Jul 12 14:24:00 IDT 2019 | Mon Aug 05 14:24:00 IDT 2019 | Wed Jun 12 00:00:00 IDT 2019 | Mon Sep 02 18:00:00 IDT 2019 |  | COMPLETED
5052 | TT_TASK | Precommissioning | Tue Sep 03 08:00:00 IDT 2019 | Fri Sep 13 18:00:00 IDT 2019 | Tue Sep 03 08:00:00 IDT 2019 | Wed Nov 20 00:00:00 IST 2019 |  | COMPLETED
5054 | TT_TASK | Erection Telecommunication Other Buildings (Except UCA) | Wed Apr 24 16:00:00 IDT 2019 | Thu May 30 16:00:00 IDT 2019 | Wed Apr 24 16:00:00 IDT 2019 | Sat Aug 03 00:00:00 IDT 2019 |  | COMPLETED
5055 | TT_TASK | Cable Raceways | Thu Jun 06 16:00:00 IDT 2019 | Mon Jul 08 16:00:00 IDT 2019 | Sat May 25 00:00:00 IDT 2019 | Wed Jun 26 00:00:00 IDT 2019 |  | COMPLETED
5056 | TT_TASK | Cable Pulling | Tue Jun 18 13:30:00 IDT 2019 | Fri Jul 12 13:30:00 IDT 2019 | Thu Jun 13 00:00:00 IDT 2019 | Sat Aug 10 00:00:00 IDT 2019 |  | COMPLETED
5057 | TT_TASK | Cable Termination | Sat Jun 29 13:30:00 IDT 2019 | Wed Jul 24 13:30:00 IDT 2019 | Sat Jun 29 13:30:00 IDT 2019 | Thu Sep 05 00:00:00 IDT 2019 |  | COMPLETED
5058 | TT_TASK | Precommissioning | Sat Aug 31 16:12:00 IDT 2019 | Thu Sep 12 16:12:00 IDT 2019 | Fri Sep 06 00:00:00 IDT 2019 | Sat Jan 18 08:00:00 IST 2020 |  | COMPLETED
5061 | TT_TASK | Cable Tray Installation (Under Floor) | Tue Nov 06 08:00:00 IST 2018 | Tue Dec 04 18:00:00 IST 2018 | Tue Nov 20 00:00:00 IST 2018 | Thu Jan 31 14:36:00 IST 2019 |  | COMPLETED
5062 | TT_TASK | Printer Installation | Sat Jun 01 08:00:00 IDT 2019 | Tue Jun 04 18:00:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 | Sat Jul 20 00:00:00 IDT 2019 |  | COMPLETED
5063 | TT_TASK | Install Floor | Mon Apr 01 08:00:00 IDT 2019 | Sat Apr 13 18:00:00 IDT 2019 | Wed Apr 03 00:00:00 IDT 2019 | Tue May 07 18:00:00 IDT 2019 |  | COMPLETED
5064 | TT_TASK | I/O Cabinet Installation | Tue Jan 29 14:00:00 IST 2019 | Fri Mar 01 14:00:00 IST 2019 | Wed Oct 10 00:00:00 IDT 2018 | Mon Mar 04 14:36:00 IST 2019 |  | COMPLETED
5065 | TT_TASK | Control Cabinet Installation | Wed Feb 27 09:00:00 IST 2019 | Fri Mar 15 09:00:00 IST 2019 | Wed Oct 10 00:00:00 IDT 2018 | Tue Mar 12 14:36:00 IST 2019 |  | COMPLETED
5066 | TT_TASK | Engineer Work Station Installation | Tue Mar 12 14:36:00 IST 2019 | Tue Mar 26 14:36:00 IST 2019 | Fri Mar 15 00:00:00 IST 2019 | Tue May 21 18:00:00 IDT 2019 |  | COMPLETED
5067 | TT_TASK | Operator Work Station Installation | Sat Jun 29 08:00:00 IDT 2019 | Thu Jul 04 18:00:00 IDT 2019 | Thu Jul 04 00:00:00 IDT 2019 | Thu Jul 25 00:00:00 IDT 2019 |  | COMPLETED
5068 | TT_TASK | Network/Cabinet Installation | Tue Jun 18 08:00:00 IDT 2019 | Fri Jun 21 18:00:00 IDT 2019 | Fri May 10 00:00:00 IDT 2019 | Tue Jun 25 00:00:00 IDT 2019 |  | COMPLETED
5069 | TT_TASK | AC/DC System Installation | Tue Jun 18 08:00:00 IDT 2019 | Thu Jun 20 18:00:00 IDT 2019 | Tue May 14 00:00:00 IDT 2019 | Fri Jun 28 00:00:00 IDT 2019 |  | COMPLETED
5070 | TT_TASK | Hardwire Switches Installation | Fri Jun 07 16:12:00 IDT 2019 | Thu Jun 13 16:12:00 IDT 2019 | Sat Jun 22 00:00:00 IDT 2019 | Thu Jun 27 18:00:00 IDT 2019 |  | COMPLETED
5071 | TT_TASK | Furniture Installation | Sat Mar 09 17:00:00 IST 2019 | Thu Mar 14 17:00:00 IST 2019 | Fri Mar 15 00:00:00 IST 2019 | Mon Apr 29 00:00:00 IDT 2019 |  | COMPLETED
5072 | TT_TASK | Control Room Equipment Installation | Fri Jun 14 11:36:00 IDT 2019 | Wed Jun 26 11:36:00 IDT 2019 | Tue May 07 00:00:00 IDT 2019 | Sat Jul 06 18:00:00 IDT 2019 |  | COMPLETED
5073 | TT_TASK | Installation of Telecommunication System | Sat Jun 22 08:00:00 IDT 2019 | Tue Jul 02 18:00:00 IDT 2019 | Mon May 13 00:00:00 IDT 2019 | Sat Jul 06 14:24:00 IDT 2019 |  | COMPLETED
5074 | TT_TASK | Cable Laying of Local Control Room | Thu Apr 18 08:00:00 IDT 2019 | Tue May 14 18:00:00 IDT 2019 | Thu Apr 18 08:00:00 IDT 2019 | Wed Jun 26 16:12:00 IDT 2019 |  | COMPLETED
5077 | TT_TASK | Equipment Installation | Tue Apr 16 08:00:00 IDT 2019 | Sat Apr 27 18:00:00 IDT 2019 | Wed Apr 17 00:00:00 IDT 2019 | Wed Jul 24 00:00:00 IDT 2019 |  | COMPLETED
5078 | TT_TASK | EC+I | Tue Jul 16 08:09:00 IDT 2019 | Thu Jul 25 08:09:00 IDT 2019 | Thu Jun 13 00:00:00 IDT 2019 | Sat Jul 27 00:00:00 IDT 2019 |  | COMPLETED
5079 | TT_TASK | Precommissioning | Wed Jul 31 08:00:00 IDT 2019 | Fri Aug 09 17:00:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
5080 | TT_TASK | Booster Pump Install | Tue Jun 11 11:09:00 IDT 2019 | Thu Jun 20 11:09:00 IDT 2019 | Tue Jun 11 11:09:00 IDT 2019 | Tue Jul 23 00:00:00 IDT 2019 |  | COMPLETED
5081 | TT_TASK | Auto Wash Strainer Install | Sat Jun 15 11:09:00 IDT 2019 | Wed Jun 26 10:09:00 IDT 2019 | Sat Jun 15 11:09:00 IDT 2019 | Fri Jul 26 00:00:00 IDT 2019 |  | COMPLETED
5082 | TT_TASK | Chlorinated Cell Module Install | Thu Jun 20 11:09:00 IDT 2019 | Tue Jul 02 10:09:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 | Sat Jul 27 00:00:00 IDT 2019 |  | COMPLETED
5083 | TT_TASK | Fresh Air Blower Install | Wed Jun 26 10:09:00 IDT 2019 | Sat Jul 06 10:09:00 IDT 2019 | Wed Jun 12 00:00:00 IDT 2019 | Tue Jul 23 00:00:00 IDT 2019 |  | COMPLETED
5084 | TT_TASK | XXX and Contineous Dosing Install | Tue Jul 02 10:09:00 IDT 2019 | Fri Jul 12 09:09:00 IDT 2019 | Tue Jun 11 00:00:00 IDT 2019 | Wed Jul 24 14:36:00 IDT 2019 |  | COMPLETED
5085 | TT_TASK | Fume Scrubber Install | Mon Jul 08 09:09:00 IDT 2019 | Wed Jul 17 09:09:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 | Fri Jul 26 00:00:00 IDT 2019 |  | COMPLETED
5086 | TT_TASK | Acid Tank and Acid Cleaning Install | Mon Jul 15 09:09:00 IDT 2019 | Thu Jul 25 08:09:00 IDT 2019 | Sat Jun 15 00:00:00 IDT 2019 | Fri Jul 26 00:00:00 IDT 2019 |  | COMPLETED
5087 | TT_TASK | Sump Pump Install | Wed Jul 10 09:09:00 IDT 2019 | Sat Jul 20 08:09:00 IDT 2019 | Thu Jun 13 00:00:00 IDT 2019 | Thu Jul 25 00:00:00 IDT 2019 |  | COMPLETED
5090 | TT_TASK | Equipment Installation | Fri Dec 06 08:00:00 IST 2019 | Fri Dec 13 18:00:00 IST 2019 | Mon Nov 04 00:00:00 IST 2019 | Tue Nov 19 00:00:00 IST 2019 |  | COMPLETED
5091 | TT_TASK | EC+I | Mon Dec 09 08:00:00 IST 2019 | Mon Dec 16 18:00:00 IST 2019 | Mon Nov 04 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5092 | TT_TASK | Precommissioning | Fri Dec 06 08:00:00 IST 2019 | Sat Dec 14 18:00:00 IST 2019 | Mon Nov 25 00:00:00 IST 2019 | Sat Jan 18 08:00:00 IST 2020 |  | COMPLETED
5093 | TT_TASK | Function Test | Fri Apr 03 08:00:00 IDT 2020 | Sat Apr 11 18:00:00 IDT 2020 | Sat Jan 11 08:00:00 IST 2020 | Sat Jan 18 08:00:00 IST 2020 |  | COMPLETED
5102 | TT_TASK | LUN to CLP for Energisation of Electrical cabinet 10GHC10GH001/2 on 30-Aug | Wed Aug 28 08:00:00 IDT 2019 | Mon Sep 02 12:00:00 IDT 2019 | Wed Aug 28 08:00:00 IDT 2019 | Thu Aug 29 08:00:00 IDT 2019 |  | COMPLETED
5103 | TT_TASK | Energisation of Electrical Cabinet 10GHC10GH001/2 | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Sep 03 00:00:00 IDT 2019 | Tue Sep 03 00:00:00 IDT 2019 |  | COMPLETED
5104 | TT_TASK | Cold Commissioning of Electrical Cabinet and Pump Motors | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Sep 04 00:00:00 IDT 2019 | Sat Sep 07 12:00:00 IDT 2019 |  | COMPLETED
5105 | TT_TASK | Preparation for System Flushing | Wed Sep 04 08:00:00 IDT 2019 | Mon Sep 09 12:00:00 IDT 2019 | Wed Sep 04 08:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
5106 | TT_TASK | System flushing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Sep 09 00:00:00 IDT 2019 | Mon Sep 09 00:00:00 IDT 2019 |  | COMPLETED
5107 | TT_TASK | System restoration post flush | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Sep 10 00:00:00 IDT 2019 | Sat Sep 14 00:00:00 IDT 2019 |  | COMPLETED
5111 | TT_TASK | System Commissioning | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Sep 16 00:00:00 IDT 2019 | Mon Sep 16 00:00:00 IDT 2019 |  | COMPLETED
5112 | TT_TASK | Draining of system for finalising the tie-in works for dosing system | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Nov 13 00:00:00 IST 2019 | Fri Nov 22 12:00:00 IST 2019 |  | COMPLETED
5116 | TT_TASK | Rotation checks and motor solo runs incl re-coupling in preparation for flushing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Sep 30 00:00:00 IDT 2019 | Mon Sep 30 00:00:00 IDT 2019 |  | COMPLETED
5117 | TT_TASK | Investigation works on elevated vibrations during motor solo runs for PGB11&12AP001 | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 02 00:00:00 IDT 2019 | Wed Oct 02 00:00:00 IDT 2019 |  | COMPLETED
5118 | TT_TASK | Prep for additional grouting works for baseframe of PGB11&12AP001 | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 03 00:00:00 IDT 2019 | Thu Oct 03 00:00:00 IDT 2019 |  | COMPLETED
5119 | TT_TASK | Additional grouting works for baseframe of PGB11&12AP001 | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Oct 04 00:00:00 IDT 2019 | Fri Oct 04 00:00:00 IDT 2019 |  | COMPLETED
5120 | TT_TASK | Re-testing of motor solo run after grouting | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 |  | COMPLETED
5121 | TT_TASK | Coupling of pump & setup for initial pump operation | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
5122 | TT_TASK | Filling of baseframe with concrete and preparation for final grouting | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
5123 | TT_TASK | Curing time for concrete grouting ongoing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 14 00:00:00 IDT 2019 | Mon Oct 14 00:00:00 IDT 2019 |  | COMPLETED
5124 | TT_TASK | Motor solo run and coupling / fist flushing operation | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Oct 15 00:00:00 IDT 2019 | Tue Oct 15 00:00:00 IDT 2019 |  | COMPLETED
5125 | TT_TASK | System flushing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 16 00:00:00 IDT 2019 | Thu Oct 24 00:00:00 IDT 2019 |  | COMPLETED
5126 | TT_TASK | Oil draining | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 24 00:00:00 IDT 2019 | Mon Oct 28 00:00:00 IST 2019 |  | COMPLETED
5127 | TT_TASK | Restoration ongoing, prepare for filling | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Oct 29 00:00:00 IST 2019 | Wed Nov 13 00:00:00 IST 2019 |  | COMPLETED
5128 | TT_TASK | Refilling System, adjusting flowrates (pending finalization of reinstatements) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Nov 12 00:00:00 IST 2019 | Sat Nov 16 00:00:00 IST 2019 |  | COMPLETED
5129 | TT_TASK | Refilling System, adjusting flowrates (pending finalization of reinstatements) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Nov 19 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5130 | TT_TASK | System in operation, adjusting flowrates | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 27 00:00:00 IST 2019 | Sat Nov 30 08:00:00 IST 2019 |  | COMPLETED
5131 | TT_TASK | System in service for flushing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5136 | TT_TASK | Loading of APs for ST | Tue Aug 20 08:00:00 IDT 2019 | Tue Aug 20 18:00:00 IDT 2019 | Tue Aug 20 08:00:00 IDT 2019 | Tue Aug 20 18:00:00 IDT 2019 |  | COMPLETED
5137 | TT_TASK | Cold Commissioning | Tue Sep 03 08:00:00 IDT 2019 | Sat Sep 07 12:00:00 IDT 2019 | Tue Sep 03 08:00:00 IDT 2019 | Mon Sep 09 00:00:00 IDT 2019 |  | COMPLETED
5138 | TT_TASK | cold commissioning MA-01 | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Nov 21 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5141 | TT_TASK | Preparation for Loop checking | Wed Aug 21 08:00:00 IDT 2019 | Mon Aug 26 12:00:00 IDT 2019 | Wed Aug 21 08:00:00 IDT 2019 | Sat Aug 24 18:00:00 IDT 2019 |  | COMPLETED
5142 | TT_TASK | Loop Checking | Mon Aug 26 08:00:00 IDT 2019 | Fri Aug 30 12:00:00 IDT 2019 | Mon Aug 26 08:00:00 IDT 2019 | Thu Sep 05 00:00:00 IDT 2019 |  | COMPLETED
5143 | TT_TASK | Preparation for flushing | Tue Sep 03 08:00:00 IDT 2019 | Sat Sep 07 12:00:00 IDT 2019 | Tue Sep 03 08:00:00 IDT 2019 | Thu Sep 05 00:00:00 IDT 2019 |  | COMPLETED
5146 | TT_TASK | Turning gear operation & adjustment of oil system tosupport GT turning gear | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5147 | TT_TASK | Topping up of main oil tank to normal operation Level | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5148 | TT_TASK | System offline for HCO inspection | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Mon Jan 06 00:00:00 IST 2020 |  | COMPLETED
5149 | TT_TASK | Setup for Commissioning Oil Flushing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Sep 06 00:00:00 IDT 2019 | Sat Sep 07 00:00:00 IDT 2019 |  | COMPLETED
5150 | TT_TASK | Commissioning Oil flushing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Sep 10 00:00:00 IDT 2019 | Fri Sep 13 12:00:00 IDT 2019 |  | COMPLETED
5151 | TT_TASK | Connection of DC Lube Oil Pump for flushing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Sep 12 00:00:00 IDT 2019 | Thu Sep 12 00:00:00 IDT 2019 |  | COMPLETED
5152 | TT_TASK | Electrical commissioning of DC oil pump | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Sep 13 00:00:00 IDT 2019 | Tue Sep 17 00:00:00 IDT 2019 |  | COMPLETED
5153 | TT_TASK | Preparation for installation of new feeder for MAV24AP001 | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Sep 30 00:00:00 IDT 2019 | Mon Sep 30 00:00:00 IDT 2019 |  | COMPLETED
5154 | TT_TASK | Removal of current feeder & Preparation for installation of new feeder MAV24AP001 | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 02 00:00:00 IDT 2019 | Fri Oct 04 00:00:00 IDT 2019 |  | COMPLETED
5155 | TT_TASK | Finalisation of Cabling Works for new feeder for DC Pump | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
5156 | TT_TASK | Test Run of MAV24AP001 after feeder exchange | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 14 00:00:00 IDT 2019 | Mon Oct 14 00:00:00 IDT 2019 |  | COMPLETED
5157 | TT_TASK | Preparation works for draining oil from main lube oil tank (construction activity) | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Oct 15 00:00:00 IDT 2019 | Tue Oct 15 00:00:00 IDT 2019 |  | COMPLETED
5158 | TT_TASK | Continuation of oil draining from tank (construction) | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 16 00:00:00 IDT 2019 | Fri Oct 18 00:00:00 IDT 2019 |  | COMPLETED
5159 | TT_TASK | Preparation for inspection/cleaning works (Construction) | Mon Oct 21 08:00:00 IDT 2019 | Fri Oct 25 12:00:00 IDT 2019 | Mon Oct 21 08:00:00 IDT 2019 | Tue Oct 22 00:00:00 IDT 2019 |  | COMPLETED
5160 | TT_TASK | Inspection of Oil tank | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 23 00:00:00 IDT 2019 | Fri Oct 25 00:00:00 IDT 2019 |  | COMPLETED
5161 | TT_TASK | Oil Tank refilling, pending cleanliness inspection | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 28 00:00:00 IST 2019 | Mon Oct 28 00:00:00 IST 2019 |  | COMPLETED
5162 | TT_TASK | Oil Tank cleanliness inspection | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Oct 29 00:00:00 IST 2019 | Tue Oct 29 00:00:00 IST 2019 |  | COMPLETED
5163 | TT_TASK | Oil Tank refilling ongoing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 30 00:00:00 IST 2019 | Thu Oct 31 00:00:00 IST 2019 |  | COMPLETED
5164 | TT_TASK | Normalization of system | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Sat Nov 02 00:00:00 IST 2019 | Sat Nov 02 00:00:00 IST 2019 |  | COMPLETED
5165 | TT_TASK | lube oil flushing ongoing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Nov 04 00:00:00 IST 2019 | Wed Nov 13 00:00:00 IST 2019 |  | COMPLETED
5166 | TT_TASK | Restoration ongoing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Nov 13 00:00:00 IST 2019 | Sat Nov 16 08:00:00 IST 2019 |  | COMPLETED
5167 | TT_TASK | System operation | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 13 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5169 | TT_TASK | System setup for lube oil flushing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Sep 05 00:00:00 IDT 2019 | Tue Sep 10 12:00:00 IDT 2019 |  | COMPLETED
5173 | TT_TASK | Pneumatic valve commissioning | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Nov 14 00:00:00 IST 2019 | Mon Nov 18 12:00:00 IST 2019 |  | COMPLETED
5174 | TT_TASK | Valve commissioning | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Sat Nov 30 12:00:00 IST 2019 |  | COMPLETED
5175 | TT_TASK | Seal steam commissioning | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Jan 16 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5179 | TT_TASK | Loading of APs for GT | Tue Aug 20 08:00:00 IDT 2019 | Sat Aug 24 12:00:00 IDT 2019 | Tue Aug 20 08:00:00 IDT 2019 | Thu Aug 22 18:00:00 IDT 2019 |  | COMPLETED
5180 | TT_TASK | Cold Commissioning | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Sep 03 00:00:00 IDT 2019 | Wed Oct 02 00:00:00 IDT 2019 |  | COMPLETED
5181 | TT_TASK | Engineering updates for GT system | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 03 00:00:00 IDT 2019 | Fri Oct 04 00:00:00 IDT 2019 |  | COMPLETED
5182 | TT_TASK | cold commissioning (MBP/MBA) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5183 | TT_TASK | cold commissioning (VGV/IGV) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5184 | TT_TASK | cold commissioning MBA50 | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5186 | TT_TASK | Energisation of motor & loop checks to support construction flushing | Mon Aug 26 08:00:00 IDT 2019 | Fri Aug 30 12:00:00 IDT 2019 | Mon Aug 26 08:00:00 IDT 2019 | Tue Aug 27 00:00:00 IDT 2019 |  | COMPLETED
5187 | TT_TASK | Cold commissioning in preparation for first pressurization | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 21 00:00:00 IDT 2019 | Tue Oct 29 00:00:00 IST 2019 |  | COMPLETED
5189 | TT_TASK | Initial pressurization of system, valve commissioning | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Nov 05 00:00:00 IST 2019 | Fri Nov 08 12:00:00 IST 2019 |  | COMPLETED
5191 | TT_TASK | System setup for lube oil flushing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Sep 05 00:00:00 IDT 2019 | Mon Sep 09 12:00:00 IDT 2019 |  | COMPLETED
5193 | TT_TASK | Operation of lifting oil system to support construction works | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Sep 16 00:00:00 IDT 2019 | Thu Sep 19 12:00:00 IDT 2019 |  | COMPLETED
5194 | TT_TASK | Commissioning of turning gear system | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Nov 21 00:00:00 IST 2019 | Sat Dec 14 00:00:00 IST 2019 |  | COMPLETED
5195 | TT_TASK | First GT turning Gear | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Sat Nov 23 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5196 | TT_TASK | System in operation for air leak test ( if required) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 16 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5198 | TT_TASK | IGV/VGV comissioning | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Nov 05 00:00:00 IST 2019 | Fri Nov 08 12:00:00 IST 2019 |  | COMPLETED
5200 | TT_TASK | IGV/VGV | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 13 00:00:00 IST 2019 | Sat Nov 16 00:00:00 IST 2019 |  | COMPLETED
5201 | TT_TASK | IGV/VGV | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 20 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5202 | TT_TASK | Commissioning of HCO system | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5203 | TT_TASK | Commissioning of HCO system - system restored | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Thu Jan 09 00:00:00 IST 2020 |  | COMPLETED
5204 | TT_TASK | GT protection testing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Wed Jan 08 00:00:00 IST 2020 |  | COMPLETED
5207 | TT_TASK | Pneumatic valve commisioning | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Nov 14 00:00:00 IST 2019 | Tue Nov 19 12:00:00 IST 2019 |  | COMPLETED
5211 | TT_TASK | Motor rotation checks | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 17 00:00:00 IDT 2019 | Fri Oct 18 00:00:00 IDT 2019 |  | COMPLETED
5213 | TT_TASK | Initial filling & flushing of system | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 28 00:00:00 IST 2019 | Thu Nov 07 00:00:00 IST 2019 |  | COMPLETED
5214 | TT_TASK | Flushing on HOLD | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Nov 08 00:00:00 IST 2019 | Wed Nov 13 12:00:00 IST 2019 |  | COMPLETED
5215 | TT_TASK | System flushing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 11 00:00:00 IST 2019 | Wed Nov 13 12:00:00 IST 2019 |  | COMPLETED
5216 | TT_TASK | System flushing pending filter delivery | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 20 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5217 | TT_TASK | System flushing pending filter delivery | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 27 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5218 | TT_TASK | System restoration | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Wed Dec 11 00:00:00 IST 2019 |  | COMPLETED
5222 | TT_TASK | Prep of Pumps for Construction oil flushing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 |  | COMPLETED
5223 | TT_TASK | Support prep for Construction oil flushing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Sep 23 00:00:00 IDT 2019 | Thu Sep 26 00:00:00 IDT 2019 |  | COMPLETED
5224 | TT_TASK | Restoration Works after Construction Flushing completion | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Sep 27 00:00:00 IDT 2019 | Fri Oct 04 12:00:00 IDT 2019 |  | COMPLETED
5228 | TT_TASK | Initial pressurizing of compressed air skid | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
5229 | TT_TASK | Preparation for piping service test and air blow | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 |  | COMPLETED
5230 | TT_TASK | System operation and preparation for air blow of system piping | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 14 00:00:00 IDT 2019 | Mon Oct 14 00:00:00 IDT 2019 |  | COMPLETED
5232 | TT_TASK | Preparation for air blow out | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Oct 22 00:00:00 IDT 2019 | Wed Oct 23 00:00:00 IDT 2019 |  | COMPLETED
5233 | TT_TASK | Initial air blow out @12.00 | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 24 00:00:00 IDT 2019 | Fri Oct 25 00:00:00 IDT 2019 |  | COMPLETED
5234 | TT_TASK | Service test completed, system normalised | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 28 00:00:00 IST 2019 | Thu Oct 31 12:00:00 IST 2019 |  | COMPLETED
5236 | TT_TASK | Rotation check and motor solo run for vibration check (LCA51/52AP001) | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Oct 15 00:00:00 IDT 2019 | Fri Oct 18 12:00:00 IDT 2019 |  | COMPLETED
5238 | TT_TASK | cold commissioning, preparation for oil flushing (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 20 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5239 | TT_TASK | cold commissioning, preparation for oil flushing (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 27 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5240 | TT_TASK | System in service for flushing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Fri Dec 13 00:00:00 IST 2019 |  | COMPLETED
5243 | TT_TASK | Cold commissioning | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Nov 05 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5244 | TT_TASK | Check of interlocks, commissioning of components | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Nov 07 00:00:00 IST 2019 | Mon Nov 11 08:00:00 IST 2019 |  | COMPLETED
5246 | TT_TASK | Blow out of sysem branch lines, service test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Nov 12 00:00:00 IST 2019 | Wed Nov 13 00:00:00 IST 2019 |  | COMPLETED
5250 | TT_TASK | system commissioning, leakage check and air blow | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Oct 31 00:00:00 IST 2019 | Sat Nov 02 00:00:00 IST 2019 |  | COMPLETED
5251 | TT_TASK | system commissioning, leakage check and air blow | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Nov 12 00:00:00 IST 2019 | Sat Nov 16 00:00:00 IST 2019 |  | COMPLETED
5254 | TT_TASK | system commissioning, leakage check and air blow (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 11 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5255 | TT_TASK | system commissioning, leakage check and air blow (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Nov 26 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5256 | TT_TASK | System blow out | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Tue Dec 10 00:00:00 IST 2019 |  | COMPLETED
5265 | TT_TASK | Acid Filling UBA-0104 | Tue Aug 20 08:00:00 IDT 2019 | Tue Aug 20 18:00:00 IDT 2019 | Tue Aug 20 08:00:00 IDT 2019 | Tue Aug 20 18:00:00 IDT 2019 |  | COMPLETED
5266 | TT_TASK | Battery charging (First Bank) | Wed Aug 21 08:00:00 IDT 2019 | Mon Aug 26 12:00:00 IDT 2019 | Wed Aug 21 08:00:00 IDT 2019 | Thu Aug 22 18:00:00 IDT 2019 |  | COMPLETED
5267 | TT_TASK | Preparation for Battery charging (Second Bank) | Mon Aug 26 08:00:00 IDT 2019 | Fri Aug 30 12:00:00 IDT 2019 | Mon Aug 26 08:00:00 IDT 2019 | Mon Aug 26 18:00:00 IDT 2019 |  | COMPLETED
5268 | TT_TASK | Battery charging (Second Bank) | Tue Aug 27 08:00:00 IDT 2019 | Wed Aug 28 18:00:00 IDT 2019 | Tue Aug 27 08:00:00 IDT 2019 | Wed Aug 28 18:00:00 IDT 2019 |  | COMPLETED
5269 | TT_TASK | Discharge test from 1st Bank | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 |  | COMPLETED
5270 | TT_TASK | Preparation for 2nd Discharge test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
5271 | TT_TASK | 2nd Discharge test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 | Wed Oct 16 12:00:00 IDT 2019 |  | COMPLETED
5275 | TT_TASK | Cold Commissioning | Mon Jul 29 08:00:00 IDT 2019 | Fri Aug 02 12:00:00 IDT 2019 | Mon Jul 29 08:00:00 IDT 2019 | Sat Aug 24 00:00:00 IDT 2019 |  | COMPLETED
5276 | TT_TASK | Initial Interlock testing | Mon Aug 26 08:00:00 IDT 2019 | Fri Aug 30 12:00:00 IDT 2019 | Mon Aug 26 08:00:00 IDT 2019 | Wed Aug 28 00:00:00 IDT 2019 |  | COMPLETED
5277 | TT_TASK | Interlock testing with CLP | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Aug 30 00:00:00 IDT 2019 | Fri Aug 30 00:00:00 IDT 2019 |  | COMPLETED
5278 | TT_TASK | Feeder commissioning | Tue Sep 03 08:00:00 IDT 2019 | Sat Sep 07 12:00:00 IDT 2019 | Tue Sep 03 08:00:00 IDT 2019 | Tue Sep 10 00:00:00 IDT 2019 |  | COMPLETED
5280 | TT_TASK | Feeder commissioning - 10MBU25AP001 | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 21 00:00:00 IDT 2019 | Fri Oct 25 12:00:00 IDT 2019 |  | COMPLETED
5281 | TT_TASK | Feeder commissioning - 10LCB11/12AP001 | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 28 00:00:00 IST 2019 | Mon Nov 04 00:00:00 IST 2019 |  | COMPLETED
5282 | TT_TASK | Rotation check - 10MBU25AP001 | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 31 00:00:00 IST 2019 | Thu Oct 31 00:00:00 IST 2019 |  | COMPLETED
5283 | TT_TASK | De-energization of BBA for LCAL works inside MV room | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Nov 05 00:00:00 IST 2019 | Tue Nov 12 00:00:00 IST 2019 |  | COMPLETED
5284 | TT_TASK | Primary injection start planned at 9am | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Nov 13 00:00:00 IST 2019 | Thu Nov 14 00:00:00 IST 2019 |  | COMPLETED
5285 | TT_TASK | MV feeder commissioning | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Nov 15 00:00:00 IST 2019 | Wed Nov 20 12:00:00 IST 2019 |  | COMPLETED
5286 | TT_TASK | Feeder commissioning 10LAC11/12AP001,10PAC11/12AP001 | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Sat Nov 30 12:00:00 IST 2019 |  | COMPLETED
5287 | TT_TASK | Supporting MV motor test runs | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Sat Dec 14 00:00:00 IST 2019 |  | COMPLETED
5288 | TT_TASK | De-energization of BBB for civil completion works inside room 206 | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Tue Jan 07 00:00:00 IST 2020 |  | COMPLETED
5289 | TT_TASK | Re-energization of BBB busbar | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Jan 08 00:00:00 IST 2020 | Wed Jan 08 00:00:00 IST 2020 |  | COMPLETED
5292 | TT_TASK | Cold Commissioning | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Sep 10 00:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
5293 | TT_TASK | Cold Commissioning - PGB Signal checks | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Sep 30 00:00:00 IDT 2019 | Fri Oct 04 12:00:00 IDT 2019 |  | COMPLETED
5294 | TT_TASK | I&C Commissioning EK,EG and PA System | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 16 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5295 | TT_TASK | I&C Commissioning EK,EG and PA System | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5296 | TT_TASK | I&C Commissioning EK,EG and PA System | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 13 00:00:00 IST 2020 | Thu Jan 16 00:00:00 IST 2020 |  | COMPLETED
5300 | TT_TASK | Commissioning Works | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Sep 18 00:00:00 IDT 2019 | Mon Sep 23 12:00:00 IDT 2019 |  | COMPLETED
5301 | TT_TASK | Energization | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 | Tue Sep 24 12:00:00 IDT 2019 |  | COMPLETED
5304 | TT_TASK | Prep for Energisation (Final checks) | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Sep 30 00:00:00 IDT 2019 | Mon Sep 30 00:00:00 IDT 2019 |  | COMPLETED
5305 | TT_TASK | Energisation | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 02 00:00:00 IDT 2019 | Sat Oct 05 12:00:00 IDT 2019 |  | COMPLETED
5308 | TT_TASK | Preparation for Energization | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
5309 | TT_TASK | Energization | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 | Wed Oct 16 12:00:00 IDT 2019 |  | COMPLETED
5312 | TT_TASK | Review of Interlcok with CLP / ARUP | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 14 00:00:00 IDT 2019 | Mon Oct 14 18:00:00 IDT 2019 |  | COMPLETED
5313 | TT_TASK | Energization of BFT04 & BFT05 | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Oct 15 00:00:00 IDT 2019 | Tue Oct 15 00:00:00 IDT 2019 |  | COMPLETED
5314 | TT_TASK | De-Energization of BFT04 & BFT05 for completion of | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 16 00:00:00 IDT 2019 | Wed Oct 16 00:00:00 IDT 2019 |  | COMPLETED
5315 | TT_TASK | BFT04 / BFT05 Energized | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 17 00:00:00 IDT 2019 | Thu Oct 17 00:00:00 IDT 2019 |  | COMPLETED
5321 | TT_TASK | System Commissioning & Energisation of Components (UBA-0204,0205) | Tue Aug 20 08:00:00 IDT 2019 | Sat Aug 24 12:00:00 IDT 2019 | Tue Aug 20 08:00:00 IDT 2019 | Fri Aug 23 18:00:00 IDT 2019 |  | COMPLETED
5322 | TT_TASK | Prep work for LV Board Energization via BMT01 | Tue Sep 03 08:00:00 IDT 2019 | Sat Sep 07 12:00:00 IDT 2019 | Tue Sep 03 08:00:00 IDT 2019 | Thu Sep 05 00:00:00 IDT 2019 |  | COMPLETED
5325 | TT_TASK | Energisation of first components upon requirements | Mon Nov 18 08:00:00 IST 2019 | Sat Dec 21 12:00:00 IST 2019 | Mon Nov 18 08:00:00 IST 2019 | Sat Dec 21 12:00:00 IST 2019 |  | COMPLETED
5326 | TT_TASK | Energisation of first components upon requirements | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 08:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5329 | TT_TASK | Partial draining of oil for inspection at bushings | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 |  | COMPLETED
5330 | TT_TASK | Inspection of Internal bushing connection to Phase B | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Sep 20 00:00:00 IDT 2019 | Sat Sep 21 00:00:00 IDT 2019 |  | COMPLETED
5331 | TT_TASK | Preparation for rectification works | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Sep 23 00:00:00 IDT 2019 | Fri Sep 27 00:00:00 IDT 2019 |  | COMPLETED
5332 | TT_TASK | Inspection with Client Consultant Engineer | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Sep 25 00:00:00 IDT 2019 | Sat Sep 28 00:00:00 IDT 2019 |  | COMPLETED
5333 | TT_TASK | FRA Test with STGZ | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Sep 30 00:00:00 IDT 2019 | Mon Sep 30 00:00:00 IDT 2019 |  | COMPLETED
5334 | TT_TASK | Prep Work - awaiting material delivery confirmation) | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 02 00:00:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 |  | COMPLETED
5335 | TT_TASK | Start Rectification Works - exchange of insulation boards and installaiton of spacer | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 |  | COMPLETED
5336 | TT_TASK | Exchange of flange on neutral bushing & preparation for transformer testing prior to final close up | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Oct 11 00:00:00 IDT 2019 | Sat Oct 12 00:00:00 IDT 2019 |  | COMPLETED
5337 | TT_TASK | Vacuum pulling ongoing in preparation for oil filling | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 14 00:00:00 IDT 2019 | Wed Oct 16 18:00:00 IDT 2019 |  | COMPLETED
5338 | TT_TASK | 24hr vacuum hold prior to oil filling | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 17 00:00:00 IDT 2019 | Fri Oct 18 00:00:00 IDT 2019 |  | COMPLETED
5339 | TT_TASK | Oil Circulation and sampling | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 21 00:00:00 IDT 2019 | Wed Oct 23 00:00:00 IDT 2019 |  | COMPLETED
5340 | TT_TASK | Cool down of oil in preparation for testing - Dirana test scheduled | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 24 00:00:00 IDT 2019 | Fri Oct 25 00:00:00 IDT 2019 |  | COMPLETED
5341 | TT_TASK | Continuation of transformer testing - Winding resistance test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 28 00:00:00 IST 2019 | Mon Oct 28 00:00:00 IST 2019 |  | COMPLETED
5342 | TT_TASK | Dirana Test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Oct 29 00:00:00 IST 2019 | Wed Oct 30 00:00:00 IST 2019 |  | COMPLETED
5343 | TT_TASK | Signal checks | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 30 00:00:00 IST 2019 | Sat Nov 02 00:00:00 IST 2019 |  | COMPLETED
5344 | TT_TASK | Finalization of commissioning | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Nov 04 00:00:00 IST 2019 | Mon Nov 04 00:00:00 IST 2019 |  | COMPLETED
5345 | TT_TASK | Preparation for primary injection test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Nov 05 00:00:00 IST 2019 | Sat Nov 09 12:00:00 IST 2019 |  | COMPLETED
5346 | TT_TASK | Final check for readiness | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Nov 11 00:00:00 IST 2019 | Mon Nov 11 00:00:00 IST 2019 |  | COMPLETED
5347 | TT_TASK | Ready for Primary injection test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Nov 12 00:00:00 IST 2019 | Tue Nov 12 00:00:00 IST 2019 |  | COMPLETED
5348 | TT_TASK | Primary injection planned at 9am | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Nov 13 00:00:00 IST 2019 | Wed Nov 13 00:00:00 IST 2019 |  | COMPLETED
5349 | TT_TASK | Signal checks oil analyzer (DGA) | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Nov 15 00:00:00 IST 2019 | Tue Nov 19 18:00:00 IST 2019 |  | COMPLETED
5350 | TT_TASK | 400V Injection from GIS side (pending release from CLP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Tue Nov 19 18:00:00 IST 2019 |  | COMPLETED
5351 | TT_TASK | final check for readiness for BE / walkdown | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Nov 28 08:00:00 IST 2019 | Fri Nov 29 00:00:00 IST 2019 |  | COMPLETED
5352 | TT_TASK | Outage works | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Dec 11 08:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5353 | TT_TASK | DGA Signal exchange CCR-LDC | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Nov 19 00:00:00 IST 2019 | Thu Nov 21 12:00:00 IST 2019 |  | COMPLETED
5354 | TT_TASK | Interlock/Intertrip for BE | Tue Nov 19 08:00:00 IST 2019 | Sat Nov 23 12:00:00 IST 2019 | Wed Nov 20 08:00:00 IST 2019 | Fri Nov 22 12:00:00 IST 2019 |  | COMPLETED
5355 | TT_TASK | Re-Energization | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Sat Dec 14 08:00:00 IST 2019 | Sun Dec 15 00:00:00 IST 2019 |  | COMPLETED
5356 | TT_TASK | Re-Energization | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Sat Dec 21 08:00:00 IST 2019 | Sun Dec 22 00:00:00 IST 2019 |  | COMPLETED
5357 | TT_TASK | final check for readiness for BE | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Nov 21 08:00:00 IST 2019 | Fri Nov 22 12:00:00 IST 2019 |  | COMPLETED
5360 | TT_TASK | Cold Commissioning (Software loading) | Thu Sep 26 08:00:00 IDT 2019 | Wed Oct 02 12:00:00 IDT 2019 | Thu Sep 26 08:00:00 IDT 2019 | Mon Sep 30 18:00:00 IDT 2019 |  | COMPLETED
5361 | TT_TASK | Preparation for Interlock testing | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Sep 30 00:00:00 IDT 2019 | Wed Oct 02 00:00:00 IDT 2019 |  | COMPLETED
5362 | TT_TASK | Interlock testing & prep for sec injection | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 03 00:00:00 IDT 2019 | Fri Oct 04 00:00:00 IDT 2019 |  | COMPLETED
5363 | TT_TASK | Interlock testing & sec injection | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 | Fri Oct 18 00:00:00 IDT 2019 |  | COMPLETED
5364 | TT_TASK | Signal exchange SCB | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 21 00:00:00 IDT 2019 | Mon Oct 21 00:00:00 IDT 2019 |  | COMPLETED
5365 | TT_TASK | Preparation for primary injection test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Nov 11 00:00:00 IST 2019 | Tue Nov 12 00:00:00 IST 2019 |  | COMPLETED
5366 | TT_TASK | Primary injection test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Nov 13 00:00:00 IST 2019 | Thu Nov 14 00:00:00 IST 2019 |  | COMPLETED
5367 | TT_TASK | Implementing requested changes from CLP | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Nov 15 00:00:00 IST 2019 | Tue Nov 19 18:00:00 IST 2019 |  | COMPLETED
5368 | TT_TASK | Interlock/Intertrip for BE | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Sat Nov 23 18:00:00 IST 2019 |  | COMPLETED
5375 | TT_TASK | Fans/Pumps cold commissioning | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 23 00:00:00 IDT 2019 | Wed Oct 23 00:00:00 IDT 2019 |  | COMPLETED
5376 | TT_TASK | Signal checks | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 24 00:00:00 IDT 2019 | Thu Oct 31 00:00:00 IST 2019 |  | COMPLETED
5377 | TT_TASK | Commissioning test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Nov 01 00:00:00 IST 2019 | Sat Nov 02 00:00:00 IST 2019 |  | COMPLETED
5378 | TT_TASK | Finalization of Commissioning | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Nov 04 00:00:00 IST 2019 | Mon Nov 04 00:00:00 IST 2019 |  | COMPLETED
5379 | TT_TASK | Preparation for primary injection test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Nov 05 00:00:00 IST 2019 | Sat Nov 09 12:00:00 IST 2019 |  | COMPLETED
5380 | TT_TASK | Final check for readiness | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Nov 11 00:00:00 IST 2019 | Mon Nov 11 00:00:00 IST 2019 |  | COMPLETED
5381 | TT_TASK | Ready for Primary injection test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Tue Nov 12 00:00:00 IST 2019 | Tue Nov 12 00:00:00 IST 2019 |  | COMPLETED
5382 | TT_TASK | Primary injection test planned at 9am | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Nov 13 00:00:00 IST 2019 | Wed Nov 13 00:00:00 IST 2019 |  | COMPLETED
5383 | TT_TASK | 400V Injection from GIS side (pending release from CLP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Tue Nov 19 18:00:00 IST 2019 |  | COMPLETED
5384 | TT_TASK | final check for readiness for BE | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Nov 21 08:00:00 IST 2019 | Fri Nov 22 12:00:00 IST 2019 |  | COMPLETED
5385 | TT_TASK | final check for readiness for BE / walkdown | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Nov 28 08:00:00 IST 2019 | Fri Nov 29 00:00:00 IST 2019 |  | COMPLETED
5386 | TT_TASK | Outage works | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Dec 11 08:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5389 | TT_TASK | Cold commissioning | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 28 00:00:00 IST 2019 | Thu Oct 31 18:00:00 IST 2019 |  | COMPLETED
5390 | TT_TASK | Cold commissioning - primary injection test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Nov 13 00:00:00 IST 2019 | Sat Nov 16 18:00:00 IST 2019 |  | COMPLETED
5391 | TT_TASK | First SFC test runs | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Jan 15 00:00:00 IST 2020 | Thu Jan 16 00:00:00 IST 2020 |  | COMPLETED
5394 | TT_TASK | Cold comm - energization of cabinet | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 30 00:00:00 IST 2019 | Fri Nov 01 00:00:00 IST 2019 |  | COMPLETED
5395 | TT_TASK | Cold comm - isolation test, ratio test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Sat Nov 02 00:00:00 IST 2019 | Sat Nov 02 00:00:00 IST 2019 |  | COMPLETED
5396 | TT_TASK | Cold comm - current trafo test, voltage trafo test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Nov 04 00:00:00 IST 2019 | Wed Nov 06 00:00:00 IST 2019 |  | COMPLETED
5397 | TT_TASK | Finalizing cold comm - torquing of connections | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Nov 07 00:00:00 IST 2019 | Thu Nov 07 00:00:00 IST 2019 |  | COMPLETED
5398 | TT_TASK | Ready for primary injection test | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Fri Nov 08 00:00:00 IST 2019 | Tue Nov 12 00:00:00 IST 2019 |  | COMPLETED
5399 | TT_TASK | Primary injection test planned at 9am | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Nov 13 00:00:00 IST 2019 | Thu Nov 14 00:00:00 IST 2019 |  | COMPLETED
5402 | TT_TASK | CLP Training on the job & commissioning of CKA-03 | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Mon Nov 18 00:00:00 IST 2019 |  | COMPLETED
5404 | TT_TASK | Back Engergization | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sun Dec 01 00:00:00 IST 2019 | Sun Dec 01 00:00:00 IST 2019 |  | COMPLETED
5410 | TT_TASK | Cold commissioning, rotation checks, commossioning of components | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Nov 11 00:00:00 IST 2019 | Thu Nov 14 00:00:00 IST 2019 |  | COMPLETED
5417 | TT_TASK | Server Commissioning CCR (CRY-01) | Tue Aug 20 08:00:00 IDT 2019 | Sat Aug 24 12:00:00 IDT 2019 | Tue Aug 20 08:00:00 IDT 2019 | Fri Aug 23 12:00:00 IDT 2019 |  | COMPLETED
5418 | TT_TASK | Server Commissioning LCR UBA-0202 (CRY-02) | Tue Aug 20 08:00:00 IDT 2019 | Sat Aug 24 12:00:00 IDT 2019 | Tue Aug 20 08:00:00 IDT 2019 | Fri Aug 23 12:00:00 IDT 2019 |  | COMPLETED
5419 | TT_TASK | Simulator Commissioning (CRQ) | Tue Aug 20 08:00:00 IDT 2019 | Sat Aug 24 12:00:00 IDT 2019 | Tue Aug 20 08:00:00 IDT 2019 | Fri Aug 23 12:00:00 IDT 2019 |  | COMPLETED
5422 | TT_TASK | Initial commissioning of LV Busbars | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Sep 12 00:00:00 IDT 2019 | Thu Sep 19 00:00:00 IDT 2019 |  | COMPLETED
5423 | TT_TASK | Commissioning of LV Busbars | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Sep 23 00:00:00 IDT 2019 | Fri Sep 27 12:00:00 IDT 2019 |  | COMPLETED
5424 | TT_TASK | Feeder commissioning - BFTGT002 | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 09 00:00:00 IDT 2019 | Mon Oct 14 12:00:00 IDT 2019 |  | COMPLETED
5425 | TT_TASK | Testing of automatic transfer system (ATS) | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 14 00:00:00 IDT 2019 | Thu Oct 17 12:00:00 IDT 2019 |  | COMPLETED
5426 | TT_TASK | Energisation of first components upon requirements | Mon Nov 18 08:00:00 IST 2019 | Sat Dec 21 12:00:00 IST 2019 | Mon Nov 18 08:00:00 IST 2019 | Sat Dec 21 12:00:00 IST 2019 |  | COMPLETED
5428 | TT_TASK | Preparation for system flushing, rotation check of water transfer pumps | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 10 00:00:00 IDT 2019 | Mon Oct 14 00:00:00 IDT 2019 |  | COMPLETED
5430 | TT_TASK | Finalisation of piping by Wai Leun to complete last flushing step | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 16 00:00:00 IDT 2019 | Wed Oct 16 00:00:00 IDT 2019 |  | COMPLETED
5431 | TT_TASK | System flushing (discharge piping) | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Thu Oct 17 00:00:00 IDT 2019 | Fri Oct 18 00:00:00 IDT 2019 |  | COMPLETED
5433 | TT_TASK | Borescope inspection of piping system | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Mon Oct 28 00:00:00 IST 2019 | Tue Oct 29 00:00:00 IST 2019 |  | COMPLETED
5434 | TT_TASK | Blow out of gas ring lines | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Oct 30 00:00:00 IST 2019 | Mon Nov 04 12:00:00 IST 2019 |  | COMPLETED
5435 | TT_TASK | Valve commissioning | Sat Aug 31 08:00:00 IDT 2019 | Thu Sep 05 12:00:00 IDT 2019 | Wed Nov 06 00:00:00 IST 2019 | Mon Nov 11 12:00:00 IST 2019 |  | COMPLETED
5437 | TT_TASK | Valve commissioning | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 13 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5439 | TT_TASK | System line up | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Jan 15 00:00:00 IST 2020 | Fri Jan 17 00:00:00 IST 2020 |  | COMPLETED
5441 | TT_TASK | Ammonia dosing system line up and chemical filling | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 13 00:00:00 IST 2020 | Wed Jan 15 00:00:00 IST 2020 |  | COMPLETED
5443 | TT_TASK | Outage initiation post chem clean, setup of all system isolations | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Dec 19 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5444 | TT_TASK | Preparation and line up of all systems for first fire | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Fri Jan 17 00:00:00 IST 2020 | Sun Jan 19 00:00:00 IST 2020 |  | COMPLETED
5446 | TT_TASK | cold commissioning of hydraulic flaps incl system flushing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Dec 17 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5447 | TT_TASK | preparation for filling of PAB system | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Dec 19 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5448 | TT_TASK | preparation for filling of PAB system at condenser | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Jan 07 00:00:00 IST 2020 | Wed Jan 08 00:00:00 IST 2020 |  | COMPLETED
5449 | TT_TASK | system final line up & first pump operation | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Jan 09 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5450 | TT_TASK | PAB System commissioning | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Jan 14 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5451 | TT_TASK | PAB System - First 2 pump operation | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Jan 16 00:00:00 IST 2020 | Thu Jan 16 00:00:00 IST 2020 |  | COMPLETED
5453 | TT_TASK | Energization of cabinets/components and I&C checks | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Sat Dec 14 00:00:00 IST 2019 |  | COMPLETED
5454 | TT_TASK | cold commissioning of intake system | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 16 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5455 | TT_TASK | testing of PAC chamber stoplog - dry and wet testing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Dec 18 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5456 | TT_TASK | cold commissioning of intake system | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5457 | TT_TASK | flooding of cooling water intake structure and removal of stoplogs | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Jan 07 00:00:00 IST 2020 | Wed Jan 08 00:00:00 IST 2020 |  | COMPLETED
5458 | TT_TASK | wet commissioning of intake systems | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Jan 08 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5459 | TT_TASK | wet commissioning of intake systems | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Jan 15 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5461 | TT_TASK | Support motor solo runs in fuel oil pumphouse | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Thu Dec 12 00:00:00 IST 2019 |  | COMPLETED
5462 | TT_TASK | Finalisation of temporary piping works and system line up for flushing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Dec 18 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5463 | TT_TASK | Finalisation of temporary piping works and system line up for flushing (after FSD inspection) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Jan 09 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5464 | TT_TASK | Finalisation of temporary piping works and system line up for flushing (after FSD inspection) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Jan 16 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5466 | TT_TASK | Filling, Service test | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Fri Nov 29 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5467 | TT_TASK | Flushing/Chem clean as per schedule | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Dec 10 00:00:00 IST 2019 | Thu Dec 12 00:00:00 IST 2019 |  | COMPLETED
5468 | TT_TASK | Chem clean as per schedule | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Dec 17 00:00:00 IST 2019 | Wed Dec 18 00:00:00 IST 2019 |  | COMPLETED
5469 | TT_TASK | Steam rinsing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Dec 17 00:00:00 IST 2019 | Wed Dec 18 00:00:00 IST 2019 |  | COMPLETED
5470 | TT_TASK | initial inspections post chem clean | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Dec 19 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5472 | TT_TASK | Spray deluge test for UBE/UBF/UBG | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Mon Nov 18 00:00:00 IST 2019 |  | COMPLETED
5473 | TT_TASK | final paint check and touch up where required | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Tue Nov 26 00:00:00 IST 2019 |  | COMPLETED
5475 | TT_TASK | Hot commissioning of Aux Boilers and safety valve testing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5476 | TT_TASK | ready for operation, pending operational licence | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5477 | TT_TASK | Operation for heating up during chemical clean | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Dec 12 00:00:00 IST 2019 | Sat Dec 14 00:00:00 IST 2019 |  | COMPLETED
5478 | TT_TASK | Operation for heating up during chemical clean | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 16 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5480 | TT_TASK | High velocity flushing as per schedule incl heat up and Chem Clean | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Wed Dec 18 00:00:00 IST 2019 |  | COMPLETED
5481 | TT_TASK | Chemical cleaning as per schedule | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 16 00:00:00 IST 2019 | Wed Dec 18 00:00:00 IST 2019 |  | COMPLETED
5482 | TT_TASK | Inspections post chem clean | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Thu Jan 09 00:00:00 IST 2020 |  | COMPLETED
5483 | TT_TASK | I&C commissionin of components restored after chem clean | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5484 | TT_TASK | System line up for filling | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Jan 09 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5485 | TT_TASK | System line up for filling (with QCD) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 13 00:00:00 IST 2020 | Wed Jan 15 00:00:00 IST 2020 |  | COMPLETED
5486 | TT_TASK | Re-filling of HRSG/Water steam | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Jan 16 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5487 | TT_TASK | I&C commissionin of components restored after chem clean | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 13 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5489 | TT_TASK | cold commissioning/system line up for chemical cleaning | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5490 | TT_TASK | initial I&C commissioning | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 20 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5491 | TT_TASK | initial I&C commissioning | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5492 | TT_TASK | cold commissioning/system line up for chemical cleaning | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5493 | TT_TASK | High velocity flushing as per schedule incl heat up and Chem Clean | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Sun Dec 15 00:00:00 IST 2019 |  | COMPLETED
5494 | TT_TASK | Chemical cleaning as per schedule | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 16 00:00:00 IST 2019 | Wed Dec 18 00:00:00 IST 2019 |  | COMPLETED
5495 | TT_TASK | Inspections post chem clean | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Thu Jan 09 00:00:00 IST 2020 |  | COMPLETED
5496 | TT_TASK | I&C commissionin of components restored after chem clean | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5497 | TT_TASK | HRSG protection testing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Jan 09 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5498 | TT_TASK | System line up for filling | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Jan 09 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5499 | TT_TASK | System line up for filling (with QCD) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 13 00:00:00 IST 2020 | Wed Jan 15 00:00:00 IST 2020 |  | COMPLETED
5500 | TT_TASK | Re-filling of HRSG/Water steam | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Jan 16 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5501 | TT_TASK | I&C commissionin of components restored after chem clean | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 13 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5503 | TT_TASK | Cold commissioning, I&C checks with vendor TFA | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Dec 17 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5504 | TT_TASK | Cold commissioning, I&C checks with vendor TFA | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Jan 07 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5505 | TT_TASK | Cold commissioning, I&C checks with vendor TFA | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 13 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5506 | TT_TASK | System line up for purging/gas charging | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Jan 16 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5508 | TT_TASK | TOP Walkdowns as per IFIs | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Nov 19 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5509 | TT_TASK | TOP Walkdowns as per IFIs | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5510 | TT_TASK | TOP Walkdowns as per IFIs | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Sat Dec 14 00:00:00 IST 2019 |  | COMPLETED
5511 | TT_TASK | TOP Walkdowns as per IFIs | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 16 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5512 | TT_TASK | TOP Walkdowns as per IFIs | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5513 | TT_TASK | TOP Walkdowns as per IFIs | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 13 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5515 | TT_TASK | Continuatuion of air leak testing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Dec 17 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5517 | TT_TASK | System operation to support GT turning gear | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 20 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5518 | TT_TASK | System operation to support GT turning gear | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 27 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5519 | TT_TASK | System operation to support GT turning gear and fact finding on MKW12AP001 | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Sat Dec 14 00:00:00 IST 2019 |  | COMPLETED
5520 | TT_TASK | System operation to support GT turning gear and fact finding on MKW12AP001 | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 16 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5522 | TT_TASK | Preparation and system line up for CO2 purging | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Jan 09 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5523 | TT_TASK | Preparation and system line up for CO2 purging | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 13 00:00:00 IST 2020 | Tue Jan 14 00:00:00 IST 2020 |  | COMPLETED
5524 | TT_TASK | H2 Charging (Date TBC) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Sat Jan 18 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5526 | TT_TASK | cold commissioning and first filling | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5527 | TT_TASK | cold commissioning and first filling | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5528 | TT_TASK | Condenser cleaning | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Wed Jan 08 00:00:00 IST 2020 |  | COMPLETED
5529 | TT_TASK | Condenser protection testing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Tue Jan 07 00:00:00 IST 2020 |  | COMPLETED
5530 | TT_TASK | Condenser filling | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Jan 15 00:00:00 IST 2020 | Wed Jan 15 00:00:00 IST 2020 |  | COMPLETED
5531 | TT_TASK | First vacuum pulling | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Jan 16 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5533 | TT_TASK | Initial cold commissioning - signal checks | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 20 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5534 | TT_TASK | Initial cold commissioning, signal checks, system line up for aux. Steam blow (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 27 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5535 | TT_TASK | Aux. Steam Blow | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Sat Nov 30 00:00:00 IST 2019 | Sun Dec 01 00:00:00 IST 2019 |  | COMPLETED
5536 | TT_TASK | System restoration after steam blow | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Wed Dec 11 00:00:00 IST 2019 |  | COMPLETED
5537 | TT_TASK | System operation for heat up prior to chemical cleaning | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Dec 12 00:00:00 IST 2019 | Sat Dec 14 00:00:00 IST 2019 |  | COMPLETED
5538 | TT_TASK | System restoration after steam blow | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 16 00:00:00 IST 2019 | Wed Dec 18 00:00:00 IST 2019 |  | COMPLETED
5539 | TT_TASK | System restoration | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Wed Jan 08 00:00:00 IST 2020 |  | COMPLETED
5540 | TT_TASK | System operation with Aux Boiler for seal steam comm | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Jan 16 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5542 | TT_TASK | cold commissioning and system setup for filling of condenser | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 20 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5543 | TT_TASK | cold commissioning and system setup for filling of condenser (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 27 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5545 | TT_TASK | TOP pending - cold commissioning | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Oct 30 00:00:00 IST 2019 | Thu Oct 31 00:00:00 IST 2019 |  | COMPLETED
5546 | TT_TASK | cold commissioning (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 11 00:00:00 IST 2019 | Sat Nov 16 00:00:00 IST 2019 |  | COMPLETED
5547 | TT_TASK | cold commissioning incl motor solo runs incl first pump operation | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5548 | TT_TASK | cold commissioning incl motor solo runs incl first pump operation | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5549 | TT_TASK | System in service for flushing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Sat Dec 14 00:00:00 IST 2019 |  | COMPLETED
5550 | TT_TASK | System in service | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Dec 17 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5552 | TT_TASK | min flow run (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Fri Nov 15 00:00:00 IST 2019 | Sat Nov 16 00:00:00 IST 2019 |  | COMPLETED
5553 | TT_TASK | min flow run (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Fri Nov 22 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5554 | TT_TASK | preparation for min flow run, cold comissioning (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 11 00:00:00 IST 2019 | Thu Nov 14 00:00:00 IST 2019 |  | COMPLETED
5555 | TT_TASK | preparation for min flow run, cold comissioning (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Thu Nov 21 00:00:00 IST 2019 |  | COMPLETED
5556 | TT_TASK | preparation for min flow run, cold comissioning (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Thu Nov 28 00:00:00 IST 2019 |  | COMPLETED
5557 | TT_TASK | min flow run (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Nov 28 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5558 | TT_TASK | Pump operation for high velocity flushing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Sat Dec 14 00:00:00 IST 2019 |  | COMPLETED
5560 | TT_TASK | cold commissioning, preparation for oil flushing (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Nov 12 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5561 | TT_TASK | cold commissioning, oil flushing, motor rotation checks, motor solo run | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5562 | TT_TASK | First FWP operation | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Fri Jan 17 00:00:00 IST 2020 | Sat Jan 18 00:00:00 IST 2020 |  | COMPLETED
5564 | TT_TASK | Commissioning of GM-01 system (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Thu Nov 14 00:00:00 IST 2019 | Sat Nov 16 00:00:00 IST 2019 |  | COMPLETED
5565 | TT_TASK | Commissioning of GM-01 system (pending TOP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Nov 19 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5566 | TT_TASK | Commissioning of GM-01 system | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Tue Dec 10 00:00:00 IST 2019 |  | COMPLETED
5568 | TT_TASK | Initial electrical cold commissioning | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Nov 19 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5569 | TT_TASK | Synchronization tests | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Thu Dec 12 00:00:00 IST 2019 |  | COMPLETED
5570 | TT_TASK | Synchronization tests | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 16 00:00:00 IST 2019 | Thu Dec 19 00:00:00 IST 2019 |  | COMPLETED
5571 | TT_TASK | UVTS internal testing/logic checks | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Tue Jan 14 00:00:00 IST 2020 |  | COMPLETED
5572 | TT_TASK | Initial ATS internal testing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Sat Jan 11 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5573 | TT_TASK | ATS official testing | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Jan 14 00:00:00 IST 2020 | Wed Jan 15 00:00:00 IST 2020 |  | COMPLETED
5574 | TT_TASK | ATS Test | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Jan 14 00:00:00 IST 2020 | Tue Jan 14 00:00:00 IST 2020 |  | COMPLETED
5576 | TT_TASK | pressurisation of bus duct (pressure test for constrcution) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Nov 19 00:00:00 IST 2019 | Thu Nov 21 00:00:00 IST 2019 |  | COMPLETED
5577 | TT_TASK | pressurisation of bus duct (pressure test for constrcution) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Wed Nov 27 00:00:00 IST 2019 |  | COMPLETED
5579 | TT_TASK | End- to End test: D1 - LDC | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Nov 20 00:00:00 IST 2019 | Fri Nov 22 00:00:00 IST 2019 |  | COMPLETED
5581 | TT_TASK | 400V Injection from GIS side (pending release from CLP) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Tue Nov 19 00:00:00 IST 2019 |  | COMPLETED
5582 | TT_TASK | Exchange of gasket on GIL & refilling of SF6 | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Nov 19 00:00:00 IST 2019 | Wed Nov 20 00:00:00 IST 2019 |  | COMPLETED
5583 | TT_TASK | Exchange of gasket on GIL & refilling of SF6 | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Nov 26 00:00:00 IST 2019 | Wed Nov 27 00:00:00 IST 2019 |  | COMPLETED
5585 | TT_TASK | MEP System Commissioining | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Sat Nov 23 00:00:00 IST 2019 |  | COMPLETED
5586 | TT_TASK | MEP System Commissioining | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Sat Nov 30 00:00:00 IST 2019 |  | COMPLETED
5587 | TT_TASK | MEP System Commissioining | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Sat Dec 14 00:00:00 IST 2019 |  | COMPLETED
5588 | TT_TASK | MEP System Commissioining | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 16 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5589 | TT_TASK | MEP System Commissioining | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Sat Jan 11 00:00:00 IST 2020 |  | COMPLETED
5590 | TT_TASK | MEP System Commissioining | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 13 00:00:00 IST 2020 | Sun Jan 19 00:00:00 IST 2020 |  | COMPLETED
5593 | TT_TASK | Station interface walkdowns for all upcoming terminal points (flushing/cleaning preparation) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Fri Nov 22 00:00:00 IST 2019 |  | COMPLETED
5594 | TT_TASK | 400kV Backfeed @ 1/12 02:00 | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Sun Dec 01 00:00:00 IST 2019 | Sun Dec 01 00:00:00 IST 2019 |  | COMPLETED
5596 | TT_TASK | Backfeed Coordination (HV injection & interlock/intertrip tests) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Thu Nov 21 00:00:00 IST 2019 |  | COMPLETED
5597 | TT_TASK | Backfeed Coordination (Document review) | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Fri Nov 29 00:00:00 IST 2019 |  | COMPLETED
5598 | TT_TASK | Issue for BAT re-energization after outage | Mon Dec 09 08:00:00 IST 2019 | Fri Dec 13 12:00:00 IST 2019 | Tue Dec 10 00:00:00 IST 2019 | Fri Dec 13 00:00:00 IST 2019 |  | COMPLETED
5599 | TT_TASK | Issue for BAT re-energization after outage | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Dec 17 00:00:00 IST 2019 | Fri Dec 20 00:00:00 IST 2019 |  | COMPLETED
5600 | TT_TASK | Transformer re-energization work | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Sun Dec 22 00:00:00 IST 2019 | Sun Dec 22 00:00:00 IST 2019 |  | COMPLETED
5602 | TT_TASK | Fresh water fire fight system preparation and spray test | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 18 00:00:00 IST 2019 | Mon Nov 18 00:00:00 IST 2019 |  | COMPLETED
5603 | TT_TASK | Fire Fighting System flushing coordination | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 13 00:00:00 IST 2020 | Fri Jan 17 00:00:00 IST 2020 |  | COMPLETED
5605 | TT_TASK | GHD Tie-in work coordination | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Tue Nov 19 00:00:00 IST 2019 | Fri Nov 22 00:00:00 IST 2019 |  | COMPLETED
5606 | TT_TASK | GHD Tie-in work coordination | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Tue Nov 26 00:00:00 IST 2019 |  | COMPLETED
5608 | TT_TASK | QJA10 / QJA20 Tie-in work coordination | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Fri Nov 29 00:00:00 IST 2019 |  | COMPLETED
5609 | TT_TASK | QJA10 / QJA20 Tie-in work coordination | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Fri Dec 13 00:00:00 IST 2019 |  | COMPLETED
5610 | TT_TASK | QJA10 / QJA20 Tie-in work coordination | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 16 00:00:00 IST 2019 | Fri Dec 20 00:00:00 IST 2019 |  | COMPLETED
5612 | TT_TASK | EG Tie-in work coordination | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Nov 25 00:00:00 IST 2019 | Fri Nov 29 00:00:00 IST 2019 |  | COMPLETED
5613 | TT_TASK | EG Tie-in work coordination | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 09 00:00:00 IST 2019 | Fri Dec 13 00:00:00 IST 2019 |  | COMPLETED
5614 | TT_TASK | EG Tie-in work coordination | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 16 00:00:00 IST 2019 | Fri Dec 20 00:00:00 IST 2019 |  | COMPLETED
5615 | TT_TASK | EG Tie-in work coordination | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Fri Jan 10 00:00:00 IST 2020 |  | COMPLETED
5616 | TT_TASK | EG Tie-in work coordination | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 13 00:00:00 IST 2020 | Fri Jan 17 00:00:00 IST 2020 |  | COMPLETED
5618 | TT_TASK | Rotation checks & motor solo runs for Fuel oil forwarding pumps | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Wed Dec 11 00:00:00 IST 2019 | Thu Dec 12 00:00:00 IST 2019 |  | COMPLETED
5620 | TT_TASK | Chemical clean effluent coordination | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Dec 16 00:00:00 IST 2019 | Sat Dec 21 00:00:00 IST 2019 |  | COMPLETED
5622 | TT_TASK | EK purging procedure review | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Fri Jan 10 00:00:00 IST 2020 |  | COMPLETED
5623 | TT_TASK | EK purging procedure review | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 13 00:00:00 IST 2020 | Fri Jan 17 00:00:00 IST 2020 |  | COMPLETED
5625 | TT_TASK | Primary protection test discussion | Thu Jul 02 08:00:00 IDT 2020 | Tue Jul 07 12:00:00 IDT 2020 | Mon Jan 06 00:00:00 IST 2020 | Mon Jan 06 00:00:00 IST 2020 |  | COMPLETED
5699 | TT_TASK | Unit on Load | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Mon Apr 27 00:00:00 IDT 2020 | Thu Apr 30 00:00:00 IDT 2020 |  | COMPLETED
5700 | TT_TASK | Vibration trip test | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Fri May 01 00:00:00 IDT 2020 | Fri May 01 00:00:00 IDT 2020 |  | COMPLETED
5701 | TT_TASK | Unit Shutdown | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sat May 02 00:00:00 IDT 2020 | Sun May 03 00:00:00 IDT 2020 |  | COMPLETED
5702 | TT_TASK | Unit on Load | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Mon May 04 00:00:00 IDT 2020 | Mon May 04 00:00:00 IDT 2020 |  | COMPLETED
5703 | TT_TASK | Unit CC Base Load | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Tue May 05 00:00:00 IDT 2020 | Sun May 10 00:00:00 IDT 2020 |  | COMPLETED
5704 | TT_TASK | Unit Trip @ 16 MW | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Mon May 11 00:00:00 IDT 2020 | Mon May 11 00:00:00 IDT 2020 |  | COMPLETED
5705 | TT_TASK | Unit CC Base Load | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Mon May 11 00:00:00 IDT 2020 | Tue May 12 00:00:00 IDT 2020 |  | COMPLETED
5706 | TT_TASK | Shut down outage for FSD Inspection | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Wed May 13 00:00:00 IDT 2020 | Thu Jun 04 00:00:00 IDT 2020 |  | COMPLETED
5707 | TT_TASK | Fuel Gas Line flushing Outage (Flushing cleaning I/P) | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Fri Jun 05 00:00:00 IDT 2020 | Sun Jun 14 00:00:00 IDT 2020 |  | COMPLETED
5708 | TT_TASK | Cold start / Load / shutdown | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Mon Jun 15 00:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 |  | COMPLETED
5709 | TT_TASK | Hot start / Load / SCR system testing / shutdown | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Tue Jun 16 00:00:00 IDT 2020 | Wed Jun 17 00:00:00 IDT 2020 |  | COMPLETED
5710 | TT_TASK | Shutdown (GT Offline Washing ) | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Thu Jun 18 00:00:00 IDT 2020 | Thu Jun 18 00:00:00 IDT 2020 |  | COMPLETED
5711 | TT_TASK | Offline washing / Warm start / Trip test/ Hot start/ Shutdown | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Fri Jun 19 00:00:00 IDT 2020 | Fri Jun 19 00:00:00 IDT 2020 |  | COMPLETED
5712 | TT_TASK | Hot start / shutdown / Hot start on the fly | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Sat Jun 20 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
5713 | TT_TASK | Unit on Load / shutdown | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Sun Jun 21 00:00:00 IDT 2020 | Sun Jun 21 00:00:00 IDT 2020 |  | COMPLETED
5714 | TT_TASK | Hot start/ Unit on Load | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Mon Jun 22 00:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 |  | COMPLETED
5715 | TT_TASK | Unit Minimum Load Operation | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Tue Jun 23 00:00:00 IDT 2020 | Tue Jun 23 00:00:00 IDT 2020 |  | COMPLETED
5716 | TT_TASK | Unit on Load / Excitation Test | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Wed Jun 24 00:00:00 IDT 2020 | Wed Jun 24 00:00:00 IDT 2020 |  | COMPLETED
5717 | TT_TASK | Unit on Load / Emergency Shutdown (FF Ring main water leak inside turbine hall) | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Thu Jun 25 00:00:00 IDT 2020 | Fri Jun 26 00:00:00 IDT 2020 |  | COMPLETED
5718 | TT_TASK | Warm Test / Excitation Test | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Sat Jun 27 00:00:00 IDT 2020 | Sat Jun 27 00:00:00 IDT 2020 |  | COMPLETED
5719 | TT_TASK | Unit on Load / Excitation test/ SCR Load Testing | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Sun Jun 28 00:00:00 IDT 2020 | Sun Jun 28 00:00:00 IDT 2020 |  | COMPLETED
5720 | TT_TASK | Load / SCR Load Testing | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Mon Jun 29 00:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 |  | COMPLETED
5721 | TT_TASK | SCR Load Testing | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Thu Jul 02 00:00:00 IDT 2020 | Thu Jul 02 00:00:00 IDT 2020 |  | COMPLETED
5722 | TT_TASK | Shutdown | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Thu Jul 02 00:00:00 IDT 2020 | Thu Jul 02 00:00:00 IDT 2020 |  | COMPLETED
5723 | TT_TASK | Automatic Hot Start on the Fly and verification of SCR system | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Fri Jul 03 00:00:00 IDT 2020 | Fri Jul 03 00:00:00 IDT 2020 |  | COMPLETED
5724 | TT_TASK | Unit on Load / Emissiong QAL2 Test | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Sat Jul 04 00:00:00 IDT 2020 | Sat Jul 04 00:00:00 IDT 2020 |  | COMPLETED
5725 | TT_TASK | Unit on Load / Emissiong QAL2 Test / Operational Reliability test Running | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Sun Jul 05 00:00:00 IDT 2020 | Tue Jul 07 00:00:00 IDT 2020 |  | COMPLETED
5726 | TT_TASK | shutdown for defect clearance before contractual RTR | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Wed Jul 08 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
5727 | TT_TASK | Cold Start / Load | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Sat Jul 11 00:00:00 IDT 2020 | Sat Jul 11 00:00:00 IDT 2020 |  | COMPLETED
5728 | TT_TASK | Unit on Load | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Sun Jul 12 00:00:00 IDT 2020 | Sun Jul 12 00:00:00 IDT 2020 |  | COMPLETED
5729 | TT_TASK | Contractual Reliability test Running | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Mon Jul 13 00:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 |  | COMPLETED
5730 | TT_TASK | Forced Outage - SCR Blower failure | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Fri Jul 24 00:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 |  | COMPLETED
5731 | TT_TASK | Phase 1 - Cold Start / Contractual Reliability test Running - (Start) | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Sun Jul 26 00:00:00 IDT 2020 | Sun Jul 26 00:00:00 IDT 2020 |  | COMPLETED
5732 | TT_TASK | Phase 1 - Contractual Reliability test Running | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Mon Jul 27 00:00:00 IDT 2020 | Tue Jul 28 00:00:00 IDT 2020 |  | COMPLETED
5733 | TT_TASK | Phase 1 - Contractual Reliability test Running / AGC test | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Wed Jul 29 00:00:00 IDT 2020 | Thu Jul 30 00:00:00 IDT 2020 |  | COMPLETED
5734 | TT_TASK | Phase 1 - Contractual Reliability test Running - (Complete) | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Fri Jul 31 00:00:00 IDT 2020 | Wed Aug 05 00:00:00 IDT 2020 |  | COMPLETED
5735 | TT_TASK | Phase 2 - Contractual Reliability test Running - (Start) | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Thu Aug 06 00:00:00 IDT 2020 | Wed Aug 12 00:00:00 IDT 2020 |  | COMPLETED
5736 | TT_TASK | Phase 2 - Contractual Reliability test Running / shutdown - (Complete) | Mon Sep 27 08:00:00 IDT 2021 | Fri Oct 01 16:00:00 IDT 2021 | Thu Aug 13 00:00:00 IDT 2020 | Thu Aug 13 00:00:00 IDT 2020 |  | COMPLETED
5737 | TT_TASK | Shutdown - defect clearance | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Fri Aug 14 00:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 |  | COMPLETED
5738 | TT_TASK | Shutdown - IGV cleaning / calibration | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sun Aug 16 00:00:00 IDT 2020 | Sun Aug 16 00:00:00 IDT 2020 |  | COMPLETED
5739 | TT_TASK | Shutdown - defect clearance | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Mon Aug 17 00:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 |  | COMPLETED
5740 | TT_TASK | Phase 3 - Cold Start / Contractual Reliability test Running (Start) | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Tue Aug 18 00:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 |  | COMPLETED
5741 | TT_TASK | Phase 3 - Contractual Reliability test Running / internal Performance Test | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Wed Aug 19 00:00:00 IDT 2020 | Thu Aug 20 00:00:00 IDT 2020 |  | COMPLETED
5742 | TT_TASK | Phase 3 - Contractual Reliability test Running / Contracual Performance Test | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Fri Aug 21 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
5743 | TT_TASK | Phase 3 - Contractual Reliability test Running | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sun Aug 23 00:00:00 IDT 2020 | Sun Jun 27 00:00:00 IDT 2021 |  | COMPLETED
5744 | TT_TASK | Phase 3 - Contractual Reliability test Running / shutdown (complete) | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Fri Aug 28 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
5745 | TT_TASK | Shutdown - defect clearance | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sat Aug 29 00:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
5746 | TT_TASK | Cold start test, internal Pefromance Test @ 50%CC | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Tue Sep 01 00:00:00 IDT 2020 | Tue Sep 01 00:00:00 IDT 2020 |  | COMPLETED
5747 | TT_TASK | Hot start on YOC Gas / shutdown | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Wed Sep 02 00:00:00 IDT 2020 | Fri Sep 04 00:00:00 IDT 2020 |  | COMPLETED
5748 | TT_TASK | Shutdown | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sat Sep 05 00:00:00 IDT 2020 | Sat Sep 05 00:00:00 IDT 2020 |  | COMPLETED
5749 | TT_TASK | Shutdown / Preparation for Performance Test | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sun Sep 06 00:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 |  | COMPLETED
5750 | TT_TASK | Shutdown | Tue Jun 08 08:00:00 IDT 2021 | Mon Jun 14 16:00:00 IDT 2021 | Thu Sep 10 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
5751 | TT_TASK | Offline washing / cold start | Tue Jun 15 08:00:00 IDT 2021 | Mon Jun 21 16:00:00 IDT 2021 | Sat Sep 12 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
5752 | TT_TASK | Unit on Load / internal Performance Test | Tue Jun 22 08:00:00 IDT 2021 | Mon Jun 28 16:00:00 IDT 2021 | Sun Sep 13 00:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 |  | COMPLETED
5753 | TT_TASK | Unit on Load / Contractual Performance Test | Tue Jun 29 08:00:00 IDT 2021 | Mon Jul 05 16:00:00 IDT 2021 | Tue Sep 15 00:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 |  | COMPLETED
5754 | TT_TASK | Shutdown / hot start / Contractual Performance Test | Tue Jul 06 08:00:00 IDT 2021 | Mon Jul 12 16:00:00 IDT 2021 | Thu Sep 17 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
5755 | TT_TASK | Unit on Load / Contractual Performance Test | Tue Jul 13 08:00:00 IDT 2021 | Mon Jul 19 16:00:00 IDT 2021 | Fri Sep 18 00:00:00 IDT 2020 | Fri Sep 18 00:00:00 IDT 2020 |  | COMPLETED
5756 | TT_TASK | Unit Load / Contractual Performance Test / shutdown | Tue Jul 20 08:00:00 IDT 2021 | Mon Jul 26 16:00:00 IDT 2021 | Sat Sep 19 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
5757 | TT_TASK | Shutdown | Tue Jul 27 08:00:00 IDT 2021 | Mon Aug 02 16:00:00 IDT 2021 | Sun Sep 20 00:00:00 IDT 2020 | Sun Sep 20 00:00:00 IDT 2020 |  | COMPLETED
5758 | TT_TASK | Cold Start / YOC gas commissioning | Tue Aug 03 08:00:00 IDT 2021 | Mon Aug 09 16:00:00 IDT 2021 | Mon Sep 21 00:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 |  | COMPLETED
5759 | TT_TASK | YOC gas commissioning | Tue Aug 10 08:00:00 IDT 2021 | Mon Aug 16 16:00:00 IDT 2021 | Tue Sep 22 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
5761 | TT_TASK | Unit under Operation Control | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Mon Sep 28 00:00:00 IDT 2020 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
5763 | TT_TASK | Unit Cool down | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
5764 | TT_TASK | Unit offline and Issue PTW's | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sun Feb 21 00:00:00 IST 2021 | Sun Feb 21 00:00:00 IST 2021 |  | COMPLETED
5765 | TT_TASK | TB2 Handover to Siemens | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
5767 | TT_TASK | TB2 Blade Rectification Works outage | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
5768 | TT_TASK | GT Fuel Oil Barrel / Bucket testing | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sun Mar 14 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
5769 | TT_TASK | H/O to Commissioning Team - GT TGO | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
5772 | TT_TASK | Unit Start -up Verification on fuel gas operation incl initial testing of SCR System | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
5773 | TT_TASK | SCR Testing | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
5774 | TT_TASK | SCR Testing -RTR Phase 1- Fuel Gas emissions (Nox & NH3) and noise testing @ HRSG (with plant instrumentation) | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
5775 | TT_TASK | SCR Testing - RTR Phase 1 | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
5778 | TT_TASK | Fuel oil commissioning - Water purge testing | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
5779 | TT_TASK | Fuel oil commissioning - Start up Testing & Initial Change over testing @20% | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
5780 | TT_TASK | Fuel oil commissioning - Partload combustion tuning (incl NoX Water Tuning) | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Sun Apr 11 00:00:00 IDT 2021 |  | COMPLETED
5781 | TT_TASK | Fuel oil commissioning - Baseload combustion tuning (incl NoX Water Tuning) | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
5782 | TT_TASK | Fuel oil commissioning - inspection after initial Fuel Oil preparation (burner filters, MBN,MBU,EG) | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
5783 | TT_TASK | Fuel oil commissioning - Start up testing & Initial Change over testing @ 20% | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
5784 | TT_TASK | Fuel oil commissioning - Start up testing & Initial Change over testing @ 30% | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
5785 | TT_TASK | Fuel oil commissioning - Change over testing @ 40% | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
5786 | TT_TASK | Fuel oil commissioning - Change over testing @ 50% | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
5787 | TT_TASK | Fuel oil commissioning - Change over testing @ 60% | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sun Apr 18 00:00:00 IDT 2021 | Sun Apr 18 00:00:00 IDT 2021 |  | COMPLETED
5788 | TT_TASK | Fuel oil commissioning - Change over testing @ 70% | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
5789 | TT_TASK | Fuel oil commissioning - Change over testing @ 70% | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
5790 | TT_TASK | Fuel oil commissioning - Inspection of Fuel oil System | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
5791 | TT_TASK | Fuel oil commissioning - Start-up optimisation - high load transfer testing | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
5792 | TT_TASK | Fuel oil commissioning - GT Fuel Gas Baseload operation and automatic changeover to fuel oil operation | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
5793 | TT_TASK | Fuel oil commissioning - Unit Start up and loading to baseload | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
5794 | TT_TASK | Fuel oil commissioning - Phase - C 910 Automatic Start-up of the unit with secondary fuel | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
5795 | TT_TASK | Fuel oil commissioning - Phase - C 932 Load change rates of unit with secondary fuel | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
5796 | TT_TASK | Fuel oil commissioning - Phase - C 966 Fuel changeover in combined cycle mode | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
5797 | TT_TASK | Fuel oil commissioning - Unit Shutdown | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
5798 | TT_TASK | Fuel oil commissioning - Phase - C 910 Automatic Start-up of the unit with secondary fuel | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sun May 02 00:00:00 IDT 2021 | Sun May 02 00:00:00 IDT 2021 |  | COMPLETED
5799 | TT_TASK | Fuel oil commissioning - Phase - C 932 Load change rates of unit with secondary fuel | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
5800 | TT_TASK | Fuel oil commissioning - Phase - C 966 Fuel changeover in combined cycle mode | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
5801 | TT_TASK | Performance Test on Oil - Phase - C 956 maximum caoacity of the unit with secondary fuel | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
5802 | TT_TASK | S/D outage - PT and FO Burner Removal | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
5803 | TT_TASK | S/U for PT - Fuel Oil Performance Testing (@100%) | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
5804 | TT_TASK | Restart of Unit - Start SCR RTR - Phase 2 | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
5806 | TT_TASK | SCR RTR Phase 2 | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Sat May 22 00:00:00 IDT 2021 |  | COMPLETED
5807 | TT_TASK | SCR RTR Phase 3 | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Sun May 23 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
5808 | TT_TASK | SCR RTR Phase 3 - Handover tp CPL - Section 6 part 2 | Tue Jun 01 08:00:00 IDT 2021 | Mon Jun 07 16:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
303 | TT_TASK | MSFT Issue DRB #1 for Review | Tue May 26 07:00:00 IDT 2020 | Mon Jun 01 17:00:00 IDT 2020 | Tue May 19 00:00:00 IDT 2020 | Mon Jul 20 00:00:00 IDT 2020 |  | COMPLETED
306 | TT_TASK | Lead Time for PEMB | Wed Feb 19 08:00:00 IST 2020 | Thu Jun 18 17:00:00 IDT 2020 | Mon Feb 24 00:00:00 IST 2020 | Thu Jun 18 00:00:00 IDT 2020 |  | COMPLETED
307 | TT_TASK | Lead Time for Rebar (Footings & Walls) | Mon Apr 27 08:00:00 IDT 2020 | Sun May 31 17:00:00 IDT 2020 | Mon Mar 30 00:00:00 IDT 2020 | Tue Apr 21 00:00:00 IDT 2020 |  | COMPLETED
308 | TT_TASK | Lead Time for COLO 1 Structural Interior Steel | Mon Aug 10 08:00:00 IDT 2020 | Sat Oct 31 17:00:00 IST 2020 | Tue Jun 30 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
309 | TT_TASK | Lead Time for Wall & Roof Metal Panels | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Mon Jun 29 00:00:00 IDT 2020 |  | COMPLETED
310 | TT_TASK | Lead Time for Admin/COLO 1 Yard Steel | Mon Aug 31 08:00:00 IDT 2020 | Sun Oct 18 17:00:00 IDT 2020 | Tue Jun 30 00:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 |  | COMPLETED
311 | TT_TASK | Lead Time for HM Ext. frames | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
312 | TT_TASK | Lead time for Drywall/Framing | Mon Aug 10 08:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Mon Aug 10 08:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
592 | TT_TASK | MV Ductbanks Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | Mon Sep 14 08:00:00 IDT 2020 | Sun Sep 20 17:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 | Sun Sep 06 00:00:00 IDT 2020 |  | COMPLETED
593 | TT_TASK | MV Wire Procurement DRB#1 JAZ to UMS/URS & UPM to UMS | Wed Aug 12 08:00:00 IDT 2020 | Tue Nov 03 17:00:00 IST 2020 | Tue Aug 04 00:00:00 IDT 2020 | Mon Oct 26 00:00:00 IST 2020 |  | COMPLETED
594 | TT_TASK | UMS Vault Procurement DRB#1 | Mon Sep 28 08:00:00 IDT 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
595 | TT_TASK | DRB#1 BIM Modeling & Coordination DRB#1 JAZ to UMS/URS & UPM to UMS | Mon Aug 10 08:00:00 IDT 2020 | Sun Aug 23 17:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
596 | TT_TASK | Site- Neher Mcgrath Study DRB#1 JAZ to UMS/URS & UPM to UMS | Tue Aug 11 08:00:00 IDT 2020 | Mon Aug 24 17:00:00 IDT 2020 | Tue Aug 04 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
597 | TT_TASK | JAZ Riser Support DRB#1 Procurement/ Jaz Foundations/Construction | Mon Aug 10 08:00:00 IDT 2020 | Sun Oct 18 17:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
598 | TT_TASK | UPM to UMS Vaults Procurement DRB#1 | Tue Sep 08 08:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
600 | TT_TASK | MV Ductbanks Procurement | Wed Aug 12 08:00:00 IDT 2020 | Thu Aug 20 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
601 | TT_TASK | Telecom DuctBank / Vaults Procurement | Thu May 14 08:00:00 IDT 2020 | Mon May 18 17:00:00 IDT 2020 | Wed May 06 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
602 | TT_TASK | MV Wire Procurement | Wed Aug 12 08:00:00 IDT 2020 | Tue Nov 03 17:00:00 IST 2020 | Tue Jul 21 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
603 | TT_TASK | Off-Site BIM Modeling & Coordination | Mon Apr 27 08:00:00 IDT 2020 | Sun May 24 17:00:00 IDT 2020 | Tue Apr 14 00:00:00 IDT 2020 | Tue May 05 00:00:00 IDT 2020 |  | COMPLETED
604 | TT_TASK | Neher Mcgrath Study | Thu Jul 02 08:00:00 IDT 2020 | Thu Aug 06 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Fri Jul 24 00:00:00 IDT 2020 |  | COMPLETED
605 | TT_TASK | URS Vault Procurement | Mon Sep 28 08:00:00 IDT 2020 | Wed Nov 11 17:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
607 | TT_TASK | Site Temp Power Procurement & Infrastructure | Mon Jun 29 08:00:00 IDT 2020 | Mon Aug 31 08:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
609 | TT_TASK | Underground Grounding Procurement | Mon Apr 27 08:00:00 IDT 2020 | Sun May 17 17:00:00 IDT 2020 | Tue Apr 07 00:00:00 IDT 2020 | Tue Apr 28 00:00:00 IDT 2020 |  | COMPLETED
610 | TT_TASK | BIM Modeling (Under ground) | Tue May 05 08:00:00 IDT 2020 | Mon Jun 08 17:00:00 IDT 2020 | Tue May 05 08:00:00 IDT 2020 | Mon Jun 08 00:00:00 IDT 2020 |  | COMPLETED
611 | TT_TASK | Electrical Long Lead Equipment Procurement (Cablebus, Panel Boards) | Mon Apr 27 08:00:00 IDT 2020 | Sun Jun 21 17:00:00 IDT 2020 | Mon Apr 27 08:00:00 IDT 2020 | Mon Aug 31 00:00:00 IDT 2020 |  | COMPLETED
612 | TT_TASK | BIM Modeling (Above ground) | Sun Aug 02 08:00:00 IDT 2020 | Wed Sep 30 17:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
615 | TT_TASK | Design / Lead Time for Electrical/Telecom (OFCI Telecom BOM Materials) | Mon Aug 10 08:00:00 IDT 2020 | Sat Nov 07 17:00:00 IST 2020 | Wed Jul 01 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
616 | TT_TASK | Design / Lead Time for Busway (OFCI Starline BOM Materials) | Thu Nov 26 08:00:00 IST 2020 | Thu Jan 14 17:00:00 IST 2021 | Mon Sep 21 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
619 | TT_TASK | Water treatment Skids Procurement ( sourcing materials and Materail approval only) | Mon Apr 27 08:00:00 IDT 2020 | Fri Nov 06 12:00:00 IST 2020 | Tue Apr 07 00:00:00 IDT 2020 | Mon Jul 06 00:00:00 IDT 2020 |  | COMPLETED
620 | TT_TASK | Design / Lead Time for M&P overhead | Mon Jun 29 08:00:00 IDT 2020 | Tue Jul 28 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
621 | TT_TASK | Design / Lead Time for Fire Protection | Mon Aug 31 08:00:00 IDT 2020 | Tue Sep 29 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
622 | TT_TASK | Design / Lead Time for Fire Alarm | Mon Jun 29 08:00:00 IDT 2020 | Thu Aug 27 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
628 | TT_TASK | URS/UMS Concrete Anchor and Vault Design | Mon Aug 10 07:00:00 IDT 2020 | Wed Aug 26 17:00:00 IDT 2020 | Wed Aug 05 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
629 | TT_TASK | URS/UMS Vault Submiital Review by EOR | Mon Sep 14 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Fri Sep 25 00:00:00 IDT 2020 |  | COMPLETED
632 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-2 PSR(10/13) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sat Dec 12 17:00:00 IST 2020 | Tue Oct 13 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
633 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-3 PSR(9/28) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Mon Dec 28 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
634 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-4 PSR (10/28) to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Fri Nov 27 16:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
635 | TT_TASK | Delay in UPM Delivery (Duration = Colo1 Cell-1 PSR (9/19) to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Tue Dec 15 17:00:00 IST 2020 | Sat Sep 19 00:00:00 IDT 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
637 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-1 11/25 to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Fri Oct 09 17:00:00 IDT 2020 | Wed Nov 25 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
638 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-2 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sun Nov 15 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
639 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-4 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Fri Nov 06 16:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
640 | TT_TASK | Delay in UPM Delivery (Duration = Colo2 Cell-3 11/25 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Sun Nov 15 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
642 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-1 PSR 11/23 to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Wed Oct 14 17:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
643 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-2 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
644 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-4 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Wed Nov 11 16:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Sun Jan 03 00:00:00 IST 2021 |  | COMPLETED
645 | TT_TASK | Delay in UPM Delivery (Duration = Colo3 Cell-3 11/23 to MSFT delivery) | Mon Nov 02 08:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Sun Jan 03 00:00:00 IST 2021 |  | COMPLETED
647 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-1 12/7 to MSFT delivery) | Sat Jan 09 08:00:00 IST 2021 | Sat Jan 09 08:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
648 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-2 12/7 to MSFT delivery) | Tue Jan 05 08:00:00 IST 2021 | Tue Jan 05 08:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
649 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-4 12/18 to MSFT delivery) | Sat Jan 09 08:00:00 IST 2021 | Sat Jan 09 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
650 | TT_TASK | Delay in UPM Delivery (Duration = Colo4 Cell-3 12/18 to MSFT delivery) | Thu Jan 14 08:00:00 IST 2021 | Thu Jan 14 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
653 | TT_TASK | Review Fluid Cooler wiring and devices buyout with Stetner | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Wed Sep 23 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
654 | TT_TASK | Change order release for fluid cooler wiring devices | Mon Oct 19 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 | Mon Oct 26 00:00:00 IST 2020 |  | COMPLETED
657 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
658 | TT_TASK | Fluid Cooler RI in place | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
659 | TT_TASK | Fluid Cooler Wire install and Term | Fri Mar 05 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
661 | TT_TASK | Fluid Cooler Panel installation | Tue Mar 23 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
662 | TT_TASK | Fluid Cooler RI in place | Thu Mar 18 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
663 | TT_TASK | Fluid Cooler Wire install and Term | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 |  | COMPLETED
665 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 15 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
666 | TT_TASK | Fluid Cooler RI in place | Fri Feb 19 07:00:00 IST 2021 | Thu Feb 25 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
667 | TT_TASK | Fluid Cooler Wire install and Term | Thu Mar 18 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
669 | TT_TASK | Fluid Cooler Panel installation | Thu Mar 18 07:00:00 IST 2021 | Mon Mar 22 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
670 | TT_TASK | Fluid Cooler RI in place | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
671 | TT_TASK | Fluid Cooler Wire install and Term | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
674 | TT_TASK | Fluid Cooler Panel installation | Mon Mar 29 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
675 | TT_TASK | Fluid Cooler RI in place | Thu Mar 25 07:00:00 IST 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
676 | TT_TASK | Fluid Cooler Wire install and Term | Thu Apr 01 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
678 | TT_TASK | Fluid Cooler Panel installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
679 | TT_TASK | Fluid Cooler RI in place | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
680 | TT_TASK | Fluid Cooler Wire install and Term | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
682 | TT_TASK | Fluid Cooler Panel installation | Thu Apr 01 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Sat Mar 27 00:00:00 IDT 2021 |  | COMPLETED
683 | TT_TASK | Fluid Cooler RI in place | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
684 | TT_TASK | Fluid Cooler Wire install and Term | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
687 | TT_TASK | Fluid Cooler Panel installation | Tue May 04 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
688 | TT_TASK | Fluid Cooler RI in place | Fri May 07 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
689 | TT_TASK | Fluid Cooler Wire install and Term | Fri May 14 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
691 | TT_TASK | Fluid Cooler Panel installation | Mon May 17 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
692 | TT_TASK | Fluid Cooler RI in place | Thu May 20 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
693 | TT_TASK | Fluid Cooler Wire install and Term | Fri May 28 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
695 | TT_TASK | Fluid Cooler Panel installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
696 | TT_TASK | Fluid Cooler RI in place | Fri Jun 04 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
697 | TT_TASK | Fluid Cooler Wire install and Term | Fri Jun 11 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
700 | TT_TASK | Fluid Cooler Panel installation | Tue Jun 08 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
701 | TT_TASK | Fluid Cooler RI in place | Fri Jun 11 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
702 | TT_TASK | Fluid Cooler Wire install and Term | Sat Jun 19 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
704 | TT_TASK | Fluid Cooler Panel installation | Fri Jun 11 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
705 | TT_TASK | Fluid Cooler RI in place | Sat Jun 19 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
706 | TT_TASK | Fluid Cooler Wire install and Term | Sat Jun 26 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
708 | TT_TASK | Fluid Cooler Panel installation | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
709 | TT_TASK | Fluid Cooler RI in place | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
710 | TT_TASK | Fluid Cooler Wire install and Term | Tue Jul 13 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
712 | TT_TASK | Fluid Cooler Panel installation | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
713 | TT_TASK | Fluid Cooler RI in place | Tue Jul 13 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
714 | TT_TASK | Fluid Cooler Wire install and Term | Tue Jul 20 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
718 | TT_TASK | ADMIN Overhead Rough-in (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
719 | TT_TASK | ADMIN Electrical Room Build out (DRB#2) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
720 | TT_TASK | ADMIN Lighting installation (DRB#2) | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
742 | TT_TASK | Water Treatmant Skid Fabrication | Mon Sep 14 08:00:00 IDT 2020 | Mon Dec 07 17:00:00 IST 2020 | Tue Aug 25 00:00:00 IDT 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
743 | TT_TASK | L&I approval process | Mon Sep 14 08:00:00 IDT 2020 | Tue Oct 13 17:00:00 IDT 2020 | Tue Aug 25 00:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 |  | COMPLETED
745 | TT_TASK | Water treatment delivery COLO-1 | Mon Dec 21 08:00:00 IST 2020 | Sun Dec 27 17:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
750 | TT_TASK | Submit and approve Shop drawings for UPM junstion box | Mon Oct 19 08:00:00 IDT 2020 | Sun Nov 08 17:00:00 IST 2020 | Fri Oct 09 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
751 | TT_TASK | Lead time for junction box | Mon Nov 02 08:00:00 IST 2020 | Sun Dec 13 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
752 | TT_TASK | Fabrication and Delivery of PEMB pentrations support steel | Mon Nov 09 08:00:00 IST 2020 | Fri Nov 13 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
756 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
757 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Tue Dec 15 00:00:00 IST 2020 |  | COMPLETED
758 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
760 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
761 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
762 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Feb 13 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
763 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
764 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Mar 05 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
765 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
768 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
769 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
770 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Feb 08 08:00:00 IST 2021 | Thu Feb 11 08:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
772 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
773 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
774 | TT_TASK | Install additional Cable bus (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
775 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
776 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Mar 02 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
777 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
780 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
781 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Tue Dec 15 00:00:00 IST 2020 |  | COMPLETED
782 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
784 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
785 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
786 | TT_TASK | Install additional Cable bus (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
787 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
788 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Mar 06 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
789 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
792 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Dec 04 07:00:00 IST 2020 | Wed Dec 09 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 18 00:00:00 IST 2020 |  | COMPLETED
793 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
794 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 23 00:00:00 IST 2021 |  | COMPLETED
796 | TT_TASK | Install MER Supply duct | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
797 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
798 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 03 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
799 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
800 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Thu Mar 04 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
801 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
803 | TT_TASK | COLO-1 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon Mar 22 07:00:00 IST 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
804 | TT_TASK | COLO-1 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon Apr 05 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
805 | TT_TASK | COLO-1 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
806 | TT_TASK | COLO-1 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
810 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Sat Jan 02 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
811 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
812 | TT_TASK | Install added DRB#3 Tray and conduit | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
814 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
815 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
816 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
817 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
818 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
819 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
822 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
823 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Thu Feb 11 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
824 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Mar 26 07:00:00 IDT 2021 | Mon Mar 29 17:00:00 IDT 2021 | Sat Feb 27 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
826 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
827 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
828 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
829 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
830 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
831 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
834 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
835 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
836 | TT_TASK | Install added DRB#3 Tray and conduit | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
838 | TT_TASK | Install MER Supply duct | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Sat Mar 27 00:00:00 IDT 2021 |  | COMPLETED
839 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 |  | COMPLETED
840 | TT_TASK | Install additional Cable bus (DRB#3) | Mon May 03 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
841 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
842 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue May 04 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
843 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
846 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
847 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Thu Feb 11 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
848 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 02 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
850 | TT_TASK | Install MER Supply duct | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
851 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri May 07 07:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
852 | TT_TASK | Install additional Cable bus (DRB#3) | Fri Apr 30 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
853 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue May 04 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
854 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
855 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 |  | COMPLETED
857 | TT_TASK | COLO-2 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Fri Apr 30 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
858 | TT_TASK | COLO-2 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
859 | TT_TASK | COLO-2 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 03 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
860 | TT_TASK | COLO-2 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
864 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
865 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
866 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
868 | TT_TASK | Install MER Supply duct | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
869 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
870 | TT_TASK | Install Roxtec block sealing and Install added tray cable (DRB#3) | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
871 | TT_TASK | Install additional Cable bus (DRB#3) | Tue May 18 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
872 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
873 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
876 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
877 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
878 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
880 | TT_TASK | Install MER Supply duct | Mon May 24 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
881 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
882 | TT_TASK | Install additional Cable bus (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
883 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 |  | COMPLETED
884 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Sat Aug 14 07:00:00 IDT 2021 | Sat Aug 14 17:00:00 IDT 2021 |  | COMPLETED
885 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Fri Sep 03 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Thu Aug 26 00:00:00 IDT 2021 |  | COMPLETED
888 | TT_TASK | Sure steel - PEMB MER penetration framing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
889 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 |  | COMPLETED
890 | TT_TASK | Install added DRB#3 Tray and conduit | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
892 | TT_TASK | Install MER Supply duct | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
893 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 |  | COMPLETED
894 | TT_TASK | Install additional Cable bus (DRB#3) | Sat May 29 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
895 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
896 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 |  | COMPLETED
897 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Mon Aug 09 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
900 | TT_TASK | Sure steel - PEMB MER penetration framing | Fri Feb 05 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
901 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Mon Mar 01 07:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
902 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
904 | TT_TASK | Install MER Supply duct | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
905 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
906 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jun 05 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
907 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
908 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
909 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
911 | TT_TASK | COLO-3 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
912 | TT_TASK | COLO-3 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 |  | COMPLETED
913 | TT_TASK | COLO-3 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
914 | TT_TASK | COLO-3 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
918 | TT_TASK | Sure steel - PEMB MER penetration framing | Thu Feb 11 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
919 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
920 | TT_TASK | Install added DRB#3 Tray and conduit | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
922 | TT_TASK | Install MER Supply duct | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
923 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Thu Jul 08 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
924 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
925 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
926 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
927 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
930 | TT_TASK | Sure steel - PEMB MER penetration framing | Tue Feb 16 07:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
931 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
932 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
934 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
935 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
936 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
937 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Fri Sep 03 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 |  |  | 400.0 | NOT_STARTED
938 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
939 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Sat Oct 02 07:00:00 IDT 2021 | Fri Oct 08 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
942 | TT_TASK | Sure steel - PEMB MER penetration framing | Thu Feb 11 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
943 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
944 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
946 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
947 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Thu Jul 08 07:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 |  | COMPLETED
948 | TT_TASK | Install additional Cable bus (DRB#3) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Jul 28 00:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 |  | COMPLETED
949 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
950 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
951 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
954 | TT_TASK | Sure steel - PEMB MER penetration framing | Tue Feb 16 07:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
955 | TT_TASK | Wall Penetration installation rough-in (Install Roxtec frame) (DRB#3) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
956 | TT_TASK | Install added DRB#3 Tray and conduit | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Thu Jul 08 00:00:00 IDT 2021 |  | COMPLETED
958 | TT_TASK | Install MER Supply duct | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
959 | TT_TASK | Install Roxtec blocks and Install tray/conduit from Roxtec to MER (DRB#3) | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
960 | TT_TASK | Install additional Cable bus (DRB#3) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
961 | TT_TASK | Install additional Cable bus feeder (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
962 | TT_TASK | Install additional Electrical Feeders for Mech equipment additional Term (DRB#3) | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 |  | COMPLETED
963 | TT_TASK | Install Roxtec block sealing and install added tray cable (DRB#3) | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
965 | TT_TASK | COLO-4 Cell-1 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Thu Sep 09 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
966 | TT_TASK | COLO-4 Cell-3 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Wed Aug 18 00:00:00 IDT 2021 |  |  | IN_PROGRESS
967 | TT_TASK | COLO-4 Cell-4 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
968 | TT_TASK | COLO-4 Cell-2 Late start to Pulling PDU Feeders due to Space constraint in MER (ADP in front of MSB) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Sat Aug 07 00:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
970 | TT_TASK | Site Shut Down - 9/9/2020 | Mon Sep 14 07:00:00 IDT 2020 | Mon Sep 14 17:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 | Wed Sep 09 00:00:00 IDT 2020 |  | COMPLETED
971 | TT_TASK | Site Shut Down - 9/10/2020 | Tue Sep 15 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Thu Sep 10 00:00:00 IDT 2020 | Thu Sep 10 00:00:00 IDT 2020 |  | COMPLETED
972 | TT_TASK | Site Shut Down - 9/11/2020 | Wed Sep 16 07:00:00 IDT 2020 | Wed Sep 16 17:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
973 | TT_TASK | Site Shut Down - 9/12/2020 | Thu Sep 17 07:00:00 IDT 2020 | Thu Sep 17 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 |  | COMPLETED
974 | TT_TASK | Site Shut Down - 9/14/2020 | Mon Sep 28 07:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 | Mon Sep 14 00:00:00 IDT 2020 |  | COMPLETED
975 | TT_TASK | Site Shut Down - 9/15/2020 | Tue Sep 29 07:00:00 IDT 2020 | Tue Sep 29 17:00:00 IDT 2020 | Tue Sep 15 00:00:00 IDT 2020 | Tue Sep 15 00:00:00 IDT 2020 |  | COMPLETED
976 | TT_TASK | Site Shut Down - 9/16/2020 | Wed Sep 30 07:00:00 IDT 2020 | Wed Sep 30 17:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 | Wed Sep 16 00:00:00 IDT 2020 |  | COMPLETED
979 | TT_TASK | Complete Remaining IWW piping to tie-in point | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 29 17:00:00 IST 2020 | Mon Sep 21 00:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
980 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
982 | TT_TASK | Complete Remaining Sanitary piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
983 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
985 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
986 | TT_TASK | Complete Remaining Fire Main piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
988 | TT_TASK | Complete Remaining ITW piping to tie-in point | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
989 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
991 | TT_TASK | Complete Remaining Telecom Duct Back (excluding Tie-in) | Mon Sep 21 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Mon Sep 21 07:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
992 | TT_TASK | Clayco Waiting on Overhead Powerlines to be grounded | Mon Sep 14 07:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Sat Sep 12 00:00:00 IDT 2020 | Thu Sep 17 00:00:00 IDT 2020 |  | COMPLETED
995 | TT_TASK | Delay in COLO-1- Cell-1 MER Delivery (Duration = COLO1 Cell-1 PSR(11/6/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sat Jan 30 17:00:00 IST 2021 | Fri Nov 06 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
996 | TT_TASK | Delay in COLO-1- Cell-2 MER Delivery (Duration = COLO1 Cell-2 PSR(11/13/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Fri Jan 29 17:00:00 IST 2021 | Fri Nov 13 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
997 | TT_TASK | Delay in COLO-1- Cell-3 MER Delivery (Duration = COLO1 Cell-3 PSR(11/20/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Feb 04 17:00:00 IST 2021 | Fri Nov 20 00:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 |  | COMPLETED
998 | TT_TASK | Delay in COLO-1- Cell-4 MER Delivery (Duration = COLO1 Cell-4 PSR(11/30/20) to MSFT delivery) | Mon Feb 01 08:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1000 | TT_TASK | Delay in COLO-2- Cell-1 MER Delivery (Duration = Colo1 Cell-1 PSR(12/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Feb 11 10:00:00 IST 2021 | Tue Dec 15 00:00:00 IST 2020 | Wed Feb 03 00:00:00 IST 2021 |  | COMPLETED
1001 | TT_TASK | Delay in COLO-2- Cell-2 MER Delivery (Duration = COLO 2 Cell-2 PSR(12/22/20) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1002 | TT_TASK | Delay in COLO-2- Cell-3 MER Delivery (Duration = COLO 2- Cell-3 PSR(12/28/20) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1003 | TT_TASK | Delay in COLO-2- Cell-4 MER Delivery (Duration = COLO 2- Cell-4 PSR(1/5/21) to MSFT delivery) | Mon Feb 01 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Jan 05 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1005 | TT_TASK | Delay in COLO-3- Cell-1 MER Delivery (Duration = COLO-3 Cell-1 PSR(1/29/21) to MSFT delivery) | Sun Jan 31 08:00:00 IST 2021 | Sat Apr 03 17:00:00 IDT 2021 | Fri Jan 29 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1006 | TT_TASK | Delay in COLO-3- Cell-2 MER Delivery (Duration = COLO-3 Cell-2 PSR(2/5/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 05 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1007 | TT_TASK | Delay in COLO-3 Cell-3 MER Delivery (Duration = COLO-3 Cell-3 PSR(2/12/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Feb 12 00:00:00 IST 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1008 | TT_TASK | Delay in COLO-3 Cell-4 MER Delivery (Duration = COLO-3 Cell-4 PSR(2/19/21) to MSFT delivery) | Sun Feb 28 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Thu Apr 22 00:00:00 IDT 2021 |  | COMPLETED
1010 | TT_TASK | Delay in COLO-4- Cell-1 MER Delivery (Duration= COLO-4 Cell-1 PSR(3/12/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Mar 12 00:00:00 IST 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
1011 | TT_TASK | Delay in COLO-4- Cell-2 MER Delivery (Duration = COLO-4 Cell-2 PSR(3/19/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1012 | TT_TASK | Delay in COLO-4- Cell-3 MER Delivery (Duration = COLO-4 Cell-3 PSR(3/26/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1013 | TT_TASK | Delay in COLO-4- Cell-4 MER Delivery (Duration = COLO-4 Cell-4 PSR(4/2/21) to MSFT delivery) | Mon Apr 26 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 | Sun May 09 00:00:00 IDT 2021 |  | COMPLETED
1015 | TT_TASK | Wire Mesh Procurement | Mon Nov 16 08:00:00 IST 2020 | Wed Dec 23 12:00:00 IST 2020 | Thu Sep 24 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
1016 | TT_TASK | Wire Mesh Submittal Approval | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Wed Sep 16 00:00:00 IDT 2020 | Wed Sep 23 00:00:00 IDT 2020 |  | COMPLETED
1017 | TT_TASK | Wire Mesh Procurement Delay | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Sat Oct 24 00:00:00 IDT 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1019 | TT_TASK | Complete Remaining Telecom Duct Back tie-in Install to MWH02 | Mon Dec 21 07:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1020 | TT_TASK | Clayco waiting on MSOW Approval | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Tue Dec 01 00:00:00 IST 2020 |  | COMPLETED
1021 | TT_TASK | Clayco MSOW Submited for approval | Mon Nov 16 07:00:00 IST 2020 | Tue Nov 17 17:00:00 IST 2020 | Fri Oct 16 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
1022 | TT_TASK | MSFT Stand down/ Additional Hydro excavation | Mon Dec 21 07:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
1024 | TT_TASK | Delay in UMS delivery (Duration = (9/19) to MSFT delivery) | Mon Sep 28 08:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Thu Nov 19 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
1027 | TT_TASK | Delay In COLO-1 Cell-1 Generator (Duration= COLO-1 Cell-1 PSR(9/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Tue Jan 19 17:00:00 IST 2021 | Tue Sep 15 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1028 | TT_TASK | Delay In COLO-1 Cell-2 Generator (Duration= COLO-1 Cell-2 PSR(9/15/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sat Feb 06 17:00:00 IST 2021 | Tue Sep 15 00:00:00 IDT 2020 | Mon Nov 02 00:00:00 IST 2020 |  | COMPLETED
1029 | TT_TASK | Delay In COLO-1 Cell-4 Generator (Duration= COLO-1 Cell-4 PSR(9/29/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Tue Jan 12 17:00:00 IST 2021 | Tue Sep 29 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1030 | TT_TASK | Delay In COLO-1 Cell-3 Generator (Duration= COLO-1 Cell-3 PSR(9/29/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Wed Feb 03 17:00:00 IST 2021 | Tue Sep 29 00:00:00 IDT 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1032 | TT_TASK | Delay In COLO-2 Cell-1 Generator (Duration= COLO-2 Cell-1 PSR(10/12/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sun Mar 07 17:00:00 IST 2021 | Mon Oct 12 00:00:00 IDT 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1033 | TT_TASK | Delay In COLO-2 Cell-2 Generator (Duration= COLO-2 Cell-2 PSR(11/6/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Sun Feb 21 17:00:00 IST 2021 | Fri Nov 06 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
1034 | TT_TASK | Delay In COLO-2 Cell-4 Generator (Duration= COLO-2 Cell-4 PSR(11/21/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Fri Feb 19 17:00:00 IST 2021 | Sat Nov 21 00:00:00 IST 2020 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
1035 | TT_TASK | Delay In COLO-2 Cell-3 Generator (Duration= COLO-2 Cell-3 PSR(10/22/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Thu Mar 18 17:00:00 IST 2021 | Thu Oct 22 00:00:00 IDT 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1037 | TT_TASK | 6.1.39.1- COLO-3 CEll-1 GEN Belly tank Failed pressure test | Mon Mar 15 07:00:00 IST 2021 | Fri Apr 09 17:00:00 IDT 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
1038 | TT_TASK | 6.1.39.2- COLO-3 Cell-1 Replace Belly Tank and Set GEN | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1039 | TT_TASK | Delay In COLO-3 Cell-1 Generator (Duration= COLO-3 Cell-1 PSR(10/12/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Sat May 08 17:00:00 IDT 2021 | Mon Nov 09 00:00:00 IST 2020 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1040 | TT_TASK | Delay In COLO-3 Cell-2 Generator (Duration= COLO-3 Cell-2 PSR(11/6/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Tue Mar 30 17:00:00 IDT 2021 | Sat Nov 21 00:00:00 IST 2020 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
1041 | TT_TASK | Delay In COLO-3 Cell-4 Generator (Duration= COLO-3 Cell-4 PSR(11/21/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Mar 18 17:00:00 IST 2021 | Wed Dec 09 00:00:00 IST 2020 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
1042 | TT_TASK | Delay In COLO-3 Cell-3 Generator (Duration= COLO-3 Cell-3 PSR(10/22/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Apr 29 17:00:00 IDT 2021 | Thu Nov 05 00:00:00 IST 2020 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1044 | TT_TASK | Delay In COLO-4 Cell-1 Generator (Duration= COLO-4 Cell-1 PSR(10/12/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Sat Jun 05 17:00:00 IDT 2021 | Mon Nov 09 00:00:00 IST 2020 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
1045 | TT_TASK | Delay In COLO-4 Cell-2 Generator (Duration= COLO-4 Cell-2 PSR(11/6/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Thu Apr 01 17:00:00 IDT 2021 | Wed Dec 09 00:00:00 IST 2020 | Thu Mar 11 00:00:00 IST 2021 |  | COMPLETED
1046 | TT_TASK | Delay In COLO-4 Cell-4 Generator (Duration= COLO-4 Cell-4 PSR(11/21/20) to MSFT delivery) | Mon Dec 21 08:00:00 IST 2020 | Wed Apr 14 17:00:00 IDT 2021 | Mon Nov 30 00:00:00 IST 2020 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
1047 | TT_TASK | Delay In COLO-4 Cell-3 Generator (Duration= COLO-4 Cell-3 PSR(10/22/20) to MSFT delivery) | Thu Dec 31 08:00:00 IST 2020 | Tue May 11 17:00:00 IDT 2021 | Fri Nov 20 00:00:00 IST 2020 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1050 | TT_TASK | COLO1 CELL1 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1051 | TT_TASK | COLO1 CELL3 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
1052 | TT_TASK | COLO1 CELL2 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1053 | TT_TASK | COLO1 CELL4 MER Security/Telecom Missing Raceway installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
1058 | TT_TASK | COLO-1 Cell-1 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1059 | TT_TASK | COLO1 CELL1 Interior MER conduit installation utility side | Fri Mar 05 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1060 | TT_TASK | COLO-1 Cell-1 Interior MER conduit installation building side Complete March1st (MER discovery Corrections & Signoff) | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1063 | TT_TASK | COLO-1 CELL3 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1064 | TT_TASK | COLO1 CELL3 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1065 | TT_TASK | COLO-1 CELL3 Interior MER conduit installation building side | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
1068 | TT_TASK | COLO-1 CELL2 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1069 | TT_TASK | COLO1 CELL2 Interior MER conduit installation utility side | Sat Mar 06 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1070 | TT_TASK | COLO-1 CELL2 Interior MER conduit installation building side | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1073 | TT_TASK | COLO-1 CELL4 Rearrange Roxtec blocks per coordination layout | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1074 | TT_TASK | COLO1 CELL4 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1075 | TT_TASK | COLO-1 CELL4 Interior MER conduit installation building side | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
1079 | TT_TASK | COLO-2 Cell-1 Rearrange Roxtec blocks per coordination layout | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1080 | TT_TASK | COLO2 CELL1 Interior MER conduit installation utility side | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1081 | TT_TASK | COLO-2 Cell-1 Interior MER conduit installation building side | Mon Apr 05 07:00:00 IDT 2021 | Mon Apr 19 17:00:00 IDT 2021 | Fri Mar 05 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1089 | TT_TASK | COLO-1 Cell-1 MER Flex Conduit fixes | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1090 | TT_TASK | COLO-1 Cell-3 MER Flex Conduit fixes | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1091 | TT_TASK | COLO-1 Cell-2 MER Flex Conduit fixes | Tue Mar 02 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1092 | TT_TASK | COLO-1 Cell-4 MER Flex Conduit fixes | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1095 | TT_TASK | Safety Stop work due to failed Starline Hangers | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 01 07:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
1096 | TT_TASK | Lead time for replacement hangers from Starline | Mon Feb 01 08:00:00 IST 2021 | Sun Feb 07 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
1097 | TT_TASK | COLO-1 Cell-1 Remove/ Replace busway & hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1098 | TT_TASK | COLO-1 Cell-3 Remove/ Replace busway & hangers | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1099 | TT_TASK | COLO-1 Cell-2 Remove/ Replace busway & hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1100 | TT_TASK | COLO-1 Cell-4 Remove/ Replace busway & hangers | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1101 | TT_TASK | Determined Startline hanger Design Issue & Approve replacement hangers | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
1102 | TT_TASK | COLO-2 Cell-1 Remove/ Replace busway & hangers | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1103 | TT_TASK | COLO-2 Cell-2 Remove/ Replace busway & hangers | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1105 | TT_TASK | Lead time for missing Admin Gen Bussing | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 |  | COMPLETED
1106 | TT_TASK | Admin Gen Bussing Install | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1107 | TT_TASK | Awaiting DCE approval of Non NEMA standard Lugs | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1108 | TT_TASK | Awaiting Phase conductor lugs from NC power as per RFI#412 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 |  | COMPLETED
1109 | TT_TASK | 6.1.41 - Incorrect Lugs for Admin Gen Main Bussing | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1112 | TT_TASK | COLO-1 Cell-4 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
1113 | TT_TASK | COLO-1 Cell-3 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Thu Mar 11 00:00:00 IST 2021 |  | COMPLETED
1114 | TT_TASK | COLO-1 Cell-2 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 04 00:00:00 IST 2021 |  | COMPLETED
1115 | TT_TASK | COLO-1 Cell-1 SE Install UPS batteries in cabinet | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1117 | TT_TASK | COLO-2 Cell-1 SE Install UPS batteries in cabinet | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
1118 | TT_TASK | COLO-2 Cell-2 SE Install UPS batteries in cabinet | Fri Apr 30 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
1119 | TT_TASK | COLO-2 Cell-3 SE Install UPS batteries in cabinet | Sat May 08 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1120 | TT_TASK | COLO-2 Cell-4 SE Install UPS batteries in cabinet | Sat May 15 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 |  | COMPLETED
1122 | TT_TASK | COLO-3 Cell-1 SE Install UPS batteries in cabinet | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1123 | TT_TASK | COLO-3 Cell-2 SE Install UPS batteries in cabinet | Tue May 25 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1124 | TT_TASK | COLO-3 Cell-3 SE Install UPS batteries in cabinet | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1125 | TT_TASK | COLO-3 Cell-4 SE Install UPS batteries in cabinet | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1127 | TT_TASK | COLO-4 Cell-1 SE Install UPS batteries in cabinet | Tue Sep 14 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1128 | TT_TASK | COLO-4 Cell-2 SE Install UPS batteries in cabinet | Wed Sep 29 07:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  | 320.0 | IN_PROGRESS
1129 | TT_TASK | COLO-4 Cell-3 SE Install UPS batteries in cabinet | Tue Sep 07 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
1130 | TT_TASK | COLO-4 Cell-4 SE Install UPS batteries in cabinet | Tue Sep 21 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
1132 | TT_TASK | COLO-2 CEll-2 Awaiting SE Revised tool Come along for MER Lift & Set | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
1133 | TT_TASK | COLO-2 CEll-3 Awaiting SE Revised tool Come along for MER Lift & Set | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1134 | TT_TASK | MER shipping split connection Safety Standown & RCA Review | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1137 | TT_TASK | COLO-2 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Mon Mar 22 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1138 | TT_TASK | RFI#432 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
1139 | TT_TASK | Lead time for tube steel | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
1140 | TT_TASK | COLO-2 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1141 | TT_TASK | COLO-2 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Thu Apr 01 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1142 | TT_TASK | COLO-2 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Mar 02 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1144 | TT_TASK | COLO-3 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Fri May 07 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 |  | COMPLETED
1145 | TT_TASK | COLO-3 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Wed May 19 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed May 19 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 |  | COMPLETED
1146 | TT_TASK | COLO-3 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Thu May 13 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Thu May 13 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 |  | COMPLETED
1147 | TT_TASK | COLO-3 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Wed May 26 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Wed May 26 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 |  | COMPLETED
1149 | TT_TASK | COLO-4 Cell-1 Install Tube steel & Cable tray transition per RFI#432 | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1150 | TT_TASK | COLO-4 Cell-3 Install Tube steel & Cable tray transition per RFI#432 | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1151 | TT_TASK | COLO-4 Cell-2 Install Tube steel & Cable tray transition per RFI#432 | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1152 | TT_TASK | COLO-4 Cell-4 Install Tube steel & Cable tray transition per RFI#432 | Mon Jun 14 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1154 | TT_TASK | All Construction activities -Safety Standown due to Admin Gen unplanned Energization | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
1156 | TT_TASK | COLO-1 Cell-1 Field Modification of tray | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Mon Feb 15 00:00:00 IST 2021 |  | COMPLETED
1157 | TT_TASK | COLO-1 Cell-2 Field Modification of tray | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 31 17:00:00 IDT 2021 | Thu Jan 21 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
1160 | TT_TASK | #3. Snow- 1/27/2021(one full day) | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 | Wed Jan 27 00:00:00 IST 2021 |  | COMPLETED
1161 | TT_TASK | #4. Extreme Heat - 6/28/21- 7/2/21(Effecting COLO-4 Yard work) | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
1162 | TT_TASK | #5 Extreme heat -production loss in Yards 7/1/21 through 7/14/21 (11 half days of loss) | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 09 00:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
1163 | TT_TASK | #6 Extreme heat - Production loss in Yards 7/15/21 through 7/31/21 (3 half days) | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
1164 | TT_TASK | #1. Rain And High Winds- 10/13/2020(half day only) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Tue Oct 13 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1165 | TT_TASK | #2. Snow -12/30/20 (one full day) | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 17:00:00 IST 2021 | Wed Dec 30 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
1168 | TT_TASK | COLO-1 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Mon Jan 11 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
1169 | TT_TASK | COLO-1 CELL-3 WA State L&I onsite inspection & Approval to Connect to MER | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1170 | TT_TASK | COLO-1 CELL-2 WA State L&I onsite inspection & Approval to Connect to MER | Sat Jan 23 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1171 | TT_TASK | COLO-1 CELL-4 WA State L&I onsite inspection & Approval to Connect to MER | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1173 | TT_TASK | COLO-2 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Fri Mar 12 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1174 | TT_TASK | COLO-2 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Tue Mar 23 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1175 | TT_TASK | COLO-2 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
1176 | TT_TASK | COLO-2 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Fri Apr 09 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1178 | TT_TASK | COLO-3 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Sat May 08 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1179 | TT_TASK | COLO-3 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Fri May 14 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1180 | TT_TASK | COLO-3 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1181 | TT_TASK | COLO-3 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1183 | TT_TASK | COLO-4 Cell-1 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 |  | COMPLETED
1184 | TT_TASK | COLO-4 Cell-2 WA State L&I onsite inspection & Approval to Connect to MER | Sat Jun 19 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1185 | TT_TASK | COLO-4 Cell-3 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
1186 | TT_TASK | COLO-4 Cell-4 WA State L&I onsite inspection & Approval to Connect to MER | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 |  | COMPLETED
1189 | TT_TASK | 6.1.36 Rework for Addtional circuits for UMS URS Battery charger feed upsize | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1190 | TT_TASK | 6.1.34.1 COLO-1 Cell-1 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1191 | TT_TASK | 6.1.34.2 COLO-1 Cell-2 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1192 | TT_TASK | 6.1.34.3 COLO-1 Cell-3 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 |  | COMPLETED
1193 | TT_TASK | 6.1.34.4 COLO-1 Cell-4 Rework on ATS Input conductors | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 |  | COMPLETED
1194 | TT_TASK | 6.1.01.0 Awaiting MER 10A HRG's (lead time= 8 weeks from 2/2/2021) | Mon Mar 01 07:00:00 IST 2021 | Mon Apr 12 17:00:00 IDT 2021 | Tue Feb 02 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
1195 | TT_TASK | 6.1.09 Awaiting Rev-D for Coordination study (DRB3/SCCS/ Submittal Breaker verification) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
1196 | TT_TASK | 6.1.26.1 L2/L3 Scripts SE MER overall Script | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
1197 | TT_TASK | 6.1.33 URS UMS Ground Buss hole Pattern | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1198 | TT_TASK | 6.1.35 UPS battery IR Scanning | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
1199 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-1 Cell-1 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1200 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-1 Cell-4 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1201 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-1 Cell-3 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1202 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-1 Cell-2 | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1203 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-2 Cell-1 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1204 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-2 Cell-2 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1205 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-2 Cell-3 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1206 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-2 Cell-4 | Tue Jul 06 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue Jul 13 00:00:00 IDT 2021 | Mon Jul 19 00:00:00 IDT 2021 |  | COMPLETED
1207 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-3 Cell-1 | Tue Aug 31 07:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
1208 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-3 Cell-4 | Tue Sep 07 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  |  | 10.0 | NOT_STARTED
1209 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-3 Cell-3 | Tue Sep 07 07:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  |  | 10.0 | NOT_STARTED
1210 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-3 Cell-2 | Thu Sep 09 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1211 | TT_TASK | 6.1.01.1 MER 10A HRG Retrofit COLO-4 Cell-1 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1212 | TT_TASK | 6.1.01.4 MER 10A HRG Retrofit COLO-4 Cell-4 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1213 | TT_TASK | 6.1.01.3 MER 10A HRG Retrofit COLO-4 Cell-3 | Mon Oct 18 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1214 | TT_TASK | 6.1.01.2 MER 10A HRG Retrofit COLO-4 Cell-2 | Thu Oct 07 07:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1216 | TT_TASK | 6.1.37- 6.2.01- Ground Fault setting on COLO-2 Gen MCB01 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Wed Apr 28 17:00:00 IDT 2021 |  | COMPLETED
1218 | TT_TASK | 6.1.38 PDU MCB01 LOTO Provisions | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
1220 | TT_TASK | 6.1.11 Awaiting BAS Backplanes from Siemens to VECA for Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
1221 | TT_TASK | 6.1.26.2 L2/L3 Scripts Siemens BAS SAT Scripts | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1222 | TT_TASK | 6.1.11 Awaiting Liftstation #3 BAS Backplanes from Siemens to VECA for Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1223 | TT_TASK | 6.1.11 Liftstation #3 BAS Install / Pull wire / term Backplanes | Mon May 17 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 |  | COMPLETED
1226 | TT_TASK | COLO-2 Cell-1 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Dec 29 00:00:00 IST 2020 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1227 | TT_TASK | COLO-2 Cell-2 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sun Jan 10 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1228 | TT_TASK | COLO-2 Cell-3 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Wed Jan 20 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1229 | TT_TASK | COLO-2 Cell-4 Install Missing Raceway & Bussing within generator | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sat Jan 23 00:00:00 IST 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
1231 | TT_TASK | COLO-3 Cell-1 Install Missing Raceway & Bussing within generator | Mon Apr 26 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1232 | TT_TASK | COLO-3 Cell-2 Install Missing Raceway & Bussing within generator | Thu Apr 29 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1233 | TT_TASK | COLO-3 Cell-3 Install Missing Raceway & Bussing within generator | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
1234 | TT_TASK | COLO-3 Cell-4 Install Missing Raceway & Bussing within generator | Tue May 04 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 |  | COMPLETED
1236 | TT_TASK | COLO-4 Cell-1 Install Missing Raceway & Bussing within generator | Tue May 25 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
1237 | TT_TASK | COLO-4 Cell-2 Install Missing Raceway & Bussing within generator | Tue May 11 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1238 | TT_TASK | COLO-4 Cell-3 Install Missing Raceway & Bussing within generator | Thu May 20 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1239 | TT_TASK | COLO-4 Cell-4 Install Missing Raceway & Bussing within generator | Mon May 17 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
1242 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
1243 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 2weeks- fab and ship | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Mon Apr 05 00:00:00 IDT 2021 |  | COMPLETED
1244 | TT_TASK | 6.1.43- Updates to Rev D SCCS - Reprint Arc Flash Labels- 1 week to install | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
1245 | TT_TASK | 6.1.44- MER Battery Monitoring Software Â– Constraint to EPMS checkouts/Point Â– Point(needed by 4/23) | Mon Mar 15 07:00:00 IST 2021 | Mon Jun 07 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Aug 07 07:00:00 IDT 2021 |  | COMPLETED
1246 | TT_TASK | 6.1.46- Site UPM Inspections | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
1247 | TT_TASK | 6.1.47- COLO-1 Cell-2 UPS01- Factory Test thermal event | Mon Mar 15 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
1249 | TT_TASK | 6.1.40- 480V house power to Gen Enclousure is Fed OH vs UG | Mon Mar 15 07:00:00 IST 2021 | Sat Apr 17 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
1254 | TT_TASK | Downtime awaiting solution for safety space constraint | Mon Apr 26 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1256 | TT_TASK | NOPC-18 Remove COLO-1 Cell-1 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
1257 | TT_TASK | Rubicon MSB inspection complete (ready for transformer reinstall) | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Mon Apr 26 07:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1258 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-1 transformer | Tue May 25 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1260 | TT_TASK | NOPC-18 Remove COLO-1 Cell-2 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
1261 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1262 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-2 transformer | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1264 | TT_TASK | NOPC-18 Remove COLO-1 Cell-3 transformer | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Mon Apr 26 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 |  | COMPLETED
1265 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1266 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-3 transformer | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1268 | TT_TASK | NOPC-18 Remove COLO-1 Cell-4 transformer | Mon May 17 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1269 | TT_TASK | MSB inspection complete (ready for transformer reinstall) | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
1270 | TT_TASK | NOPC-18 Reinstall COLO-1 Cell-4 transformer | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1273 | TT_TASK | NOPC-18 Remove COLO-2 Cell-1 transformer | Tue Jun 01 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Tue Jun 08 00:00:00 IDT 2021 |  | COMPLETED
1274 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-1 transformer | Thu Jul 22 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1276 | TT_TASK | NOPC-18 Remove COLO-2 Cell-2 transformer | Wed Jun 02 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
1277 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-2 transformer | Fri Jul 23 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
1279 | TT_TASK | NOPC-18 Remove COLO-2 Cell-3 transformer | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 |  | COMPLETED
1280 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-3 transformer | Thu Jul 29 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1282 | TT_TASK | NOPC-18 Remove COLO-2 Cell-4 transformer | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1283 | TT_TASK | NOPC-18 Reinstall COLO-2 Cell-4 transformer | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Jul 09 00:00:00 IDT 2021 | Mon Jul 12 00:00:00 IDT 2021 |  | COMPLETED
1286 | TT_TASK | NOPC-18 Remove COLO-3 Cell-1 transformer | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
1287 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-1 transformer | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 22 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1289 | TT_TASK | NOPC-18 Remove COLO-3 Cell-2 transformer | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jul 24 07:00:00 IDT 2021 | Sat Jul 24 17:00:00 IDT 2021 |  | COMPLETED
1290 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-2 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
1292 | TT_TASK | NOPC-18 Remove COLO-3 Cell-3 transformer | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Thu Aug 19 07:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1293 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-3 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1295 | TT_TASK | NOPC-18 Remove COLO-3 Cell-4 transformer | Tue Aug 31 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1296 | TT_TASK | NOPC-18 Reinstall COLO-3 Cell-4 transformer | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1299 | TT_TASK | NOPC-18 Remove COLO-4 Cell-1 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1300 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-1 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1302 | TT_TASK | NOPC-18 Remove COLO-4 Cell-2 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1303 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-2 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1305 | TT_TASK | NOPC-18 Remove COLO-4 Cell-3 transformer | Wed Sep 29 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1306 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-3 transformer | Sat Oct 09 07:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1308 | TT_TASK | NOPC-18 Remove COLO-4 Cell-4 transformer | Sat Sep 18 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1309 | TT_TASK | NOPC-18 Reinstall COLO-4 Cell-4 transformer | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
1311 | TT_TASK | PDU termination crew downtime due to COVID-19 | Sat Apr 24 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Sat Apr 24 07:00:00 IDT 2021 |  | COMPLETED
1314 | TT_TASK | 6.2.03- Replace ADP01 faulty trip units | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1315 | TT_TASK | 6.1.51-COLO-1 Cell-1,2 Factory conductors not terminated per drawings | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1316 | TT_TASK | 6.1.49 - COLO-1 Cell-1 Awaiting Ground Lug solution, procurement, installation of labelling ATS 01-06 | Fri Apr 30 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
1317 | TT_TASK | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
1318 | TT_TASK | 6.1.53-COLO-1 Cell-1,2 UPS01, PNL01 awaiting missing breakers | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
1319 | TT_TASK | 6.1.53-COLO-1 Cell-1,2,3,4 UPS01, PNL01 Install/ term Missing breakers | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1320 | TT_TASK | 6.1.59 (6.1.51 carryover) -COLO-1 Cell-1,2 Factory conductors exertherm corrections | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
1321 | TT_TASK | 6.1.50- SCCS Revision#10 (RFI-540) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1325 | TT_TASK | 6.1.54- TCM Awaiting Admin Siemens Break tank parts | Mon May 17 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1326 | TT_TASK | 6.1.54- Install Breaktank parts | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1328 | TT_TASK | 6.2.03- Replace Damaged UPM in COLO-4 Cell-4 | Thu May 06 07:00:00 IDT 2021 | Sat May 08 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1330 | TT_TASK | 6.1.55-COLO-1 - FC Factoy Re-wire (RFI-502) | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1331 | TT_TASK | 6.1.55-COLO-2 - FC Factoy Re-wire (RFI-502) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1332 | TT_TASK | 6.1.55-COLO-3 - FC Factoy Re-wire (RFI-502) | Sat Jun 05 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1333 | TT_TASK | 6.1.55-COLO-4 - FC Factoy Re-wire (RFI-502) | Thu Jun 10 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1335 | TT_TASK | 6.1.57 -Awaiting revised coordination study #9 | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
1336 | TT_TASK | Reprint revised panel 3,4 Arc flash labels | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1337 | TT_TASK | Print new DC Arc flash labels for Admin ELP | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1340 | TT_TASK | 6.1.58-RFI-528- COLO-1 - SF/RF Circuitry & terminal block rework | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
1341 | TT_TASK | 6.1.63- COLO1-UPS01-PNL01 Compass Issues Constraining L3Â’s | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
1342 | TT_TASK | 6.1.56 - COLO-1 Awaiting MSB/ADP Ground Lug replacements, Installation of labelling | Fri Apr 30 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
1349 | TT_TASK | All trades stand down | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
1350 | TT_TASK | Veca standown | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
1353 | TT_TASK | COLO-1 Cell-1 MER-UPS Battery Disconnect modifications rework | Wed Jun 16 07:00:00 IDT 2021 | Sat Jun 19 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1354 | TT_TASK | COLO-1 Cell-2 MER-UPS Battery Disconnect modifications rework | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1355 | TT_TASK | COLO-1 Cell-3 MER-UPS Battery Disconnect modifications rework | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
1356 | TT_TASK | COLO-1 Cell-4 MER-UPS Battery Disconnect modifications rework | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
1357 | TT_TASK | RFI-548 COLO MSB to UPS Battery disconnect solution approval | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1358 | TT_TASK | ADMIN-UPS Battery Disconnect modifications rework | Wed Jun 16 07:00:00 IDT 2021 | Sat Jun 19 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1359 | TT_TASK | RFI-552 Admin MSB to UPS Battery disconnect solution approval | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
1361 | TT_TASK | COLO-2 Cell-2 MER-UPS Battery Disconnect modifications rework | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 |  | COMPLETED
1362 | TT_TASK | COLO-2 Cell-1 MER-UPS Battery Disconnect modifications rework | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  | COMPLETED
1363 | TT_TASK | COLO-2 Cell-3 MER-UPS Battery Disconnect modifications rework | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  | COMPLETED
1364 | TT_TASK | COLO-2 Cell-4 MER-UPS Battery Disconnect modifications rework | Fri Jul 02 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 23 07:00:00 IDT 2021 |  | COMPLETED
1366 | TT_TASK | COLO-3 Cell-1 MER-UPS Battery Disconnect modifications rework | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 |  | COMPLETED
1367 | TT_TASK | COLO-3 Cell-2 MER-UPS Battery Disconnect modifications rework | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1368 | TT_TASK | COLO-3 Cell-3 MER-UPS Battery Disconnect modifications rework | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
1369 | TT_TASK | COLO-3 Cell-4 MER-UPS Battery Disconnect modifications rework | Sat Sep 11 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Mon Aug 16 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
1371 | TT_TASK | COLO-4 Cell-1 MER-UPS Battery Disconnect modifications rework | Thu Sep 16 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Fri Aug 20 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
1372 | TT_TASK | COLO-4 Cell-2 MER-UPS Battery Disconnect modifications rework | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
1373 | TT_TASK | COLO-4 Cell-3 MER-UPS Battery Disconnect modifications rework | Mon Sep 27 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1374 | TT_TASK | COLO-4 Cell-4 MER-UPS Battery Disconnect modifications rework | Fri Sep 03 07:00:00 IDT 2021 | Thu Sep 09 17:00:00 IDT 2021 |  |  | 270.0 | NOT_STARTED
1377 | TT_TASK | COLO-3 Cell-3 Remove inaccessible tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 04 00:00:00 IDT 2021 |  | COMPLETED
1378 | TT_TASK | COLO-3 CEll-3 Reinstall tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
1379 | TT_TASK | COLO-3 Cell-4 Remove inaccessible tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Sat Jun 12 00:00:00 IDT 2021 |  | COMPLETED
1380 | TT_TASK | COLO-3 Cell-4 Reinstall tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1381 | TT_TASK | COLO-4 Cell-1 Remove inaccessible tray in MER | Mon Jul 12 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Sat Jun 12 00:00:00 IDT 2021 |  | COMPLETED
1382 | TT_TASK | COLO-4 Cell-1 Reinstall tray in MER | Tue Aug 03 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
1383 | TT_TASK | COLO-4 Cell-2 Remove inaccessible tray in MER | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
1384 | TT_TASK | COLO-4 Cell-2 Reinstall tray in MER | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1385 | TT_TASK | COLO-4 Cell-3 Remove inaccessible tray in MER | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Thu Jul 15 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
1386 | TT_TASK | COLO-4 Cell-3 Reinstall tray in MER | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
1387 | TT_TASK | COLO-4 Cell-4 Remove inaccessible tray in MER4 | Wed Aug 04 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
1388 | TT_TASK | COLO-4 Cell-4 Reinstall tray in MER | Fri Sep 03 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Mon Aug 09 07:00:00 IDT 2021 | Thu Aug 12 00:00:00 IDT 2021 |  | COMPLETED
1389 | TT_TASK | COLO-3 Cell-1 Remove inaccessible tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 |  | COMPLETED
1390 | TT_TASK | COLO-3 CEll-1 Reinstall tray in MER | Mon Jun 28 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 |  | COMPLETED
1391 | TT_TASK | COLO-3 Cell-2 Remove inaccessible tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1392 | TT_TASK | COLO-3 Cell-2 Reinstall tray in MER | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
1395 | TT_TASK | COLO-3 Cell-3 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 14 00:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1397 | TT_TASK | COLO-4 Cell-1 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Fri Jul 23 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1398 | TT_TASK | COLO-4 Cell-2 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
1399 | TT_TASK | COLO-4 Cell-3 Conduit rework | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 |  | COMPLETED
1400 | TT_TASK | COLO-4 Cell-4 Conduit rework | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
1404 | TT_TASK | 6.1-88 COLO-1 MER awaiting updated UPS L3 test script approval | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 31 07:00:00 IDT 2021 |  | COMPLETED
1405 | TT_TASK | 6.1-89 RFI574- COLO-1 Relocating MSB EPMS device to different cabinet | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1406 | TT_TASK | 6.1-92 COLO-1 SF/ RF startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
1407 | TT_TASK | 6.1-93 COLO-1 HVAC minisplits startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
1409 | TT_TASK | 6.2-08 COLO-2 Cell- 1,2 MER equipment Phenolic labelling | Wed Jul 14 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
1410 | TT_TASK | 6.2-08 COLO-2 Cell- 3,4 MER equipment Phenolic labelling | Wed Jul 14 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Mon Aug 02 00:00:00 IDT 2021 |  | COMPLETED
1411 | TT_TASK | 6.2-12 COLO-2 All Cells- Factory connection Torque verification | Wed Jul 14 07:00:00 IDT 2021 | Wed Jul 21 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
1413 | TT_TASK | 6.1-95 COLO-1 ATS's L3 startup delay (vendor schedule availability) | Wed Jul 14 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  | COMPLETED
1415 | TT_TASK | 6.1-96 COLO-1 PDU - EPMS L3 startup delay (vendor schedule availability) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Mon Aug 02 07:00:00 IDT 2021 |  | COMPLETED
1420 | TT_TASK | COLO-2 Cell-1 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1421 | TT_TASK | COLO-2 Cell-2 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1422 | TT_TASK | COLO-2 Cell-3 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 |  | COMPLETED
1423 | TT_TASK | COLO-2 Cell-4 UPS PNL01 Compass issues Preventing CYT | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Tue Aug 17 00:00:00 IDT 2021 |  | COMPLETED
1429 | TT_TASK | 6.1-98 Admin/COLO-1 ASCO EPMS Connectivity Issues | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1430 | TT_TASK | 6.1-88 Admin/ COLO-1 MER/ADMIN UPS L3 Testing (includes shutdown to move PQM's & PQM data post proccessing) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 31 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1431 | TT_TASK | 6.1-106 COLO-1 Cell-2 UPS01 Power module failure | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 27 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1433 | TT_TASK | COLO-2 Cell-1 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1434 | TT_TASK | COLO-2 Cell-3 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1435 | TT_TASK | COLO-2 Cell-4 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1437 | TT_TASK | COLO-3 Delay in SE uploading QC Checkilst | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Fri Aug 06 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1439 | TT_TASK | COLO-2 Cell-2 Open Issues preventing Yellow tags MER Equipment | Tue Aug 31 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  |  | IN_PROGRESS
1442 | TT_TASK | Mobilization | Mon Apr 27 07:00:00 IDT 2020 | Wed May 20 17:00:00 IDT 2020 | Mon Apr 06 00:00:00 IDT 2020 | Sat May 02 17:00:00 IDT 2020 |  | COMPLETED
1444 | TT_TASK | Establish Access Roads / Laydown / Craft Parking / Temp Utilities | Thu May 14 07:00:00 IDT 2020 | Fri Jun 19 17:00:00 IDT 2020 | Fri Apr 24 00:00:00 IDT 2020 | Sat May 23 00:00:00 IDT 2020 |  | COMPLETED
1446 | TT_TASK | Site Sanitary | Mon May 11 07:00:00 IDT 2020 | Fri Jul 24 17:00:00 IDT 2020 | Tue May 05 00:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 |  | COMPLETED
1447 | TT_TASK | Remaining Site Sanitary | Mon May 11 07:00:00 IDT 2020 | Fri Jul 24 17:00:00 IDT 2020 | Tue Aug 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
1448 | TT_TASK | IWW System | Tue May 26 07:00:00 IDT 2020 | Sat Aug 08 17:00:00 IDT 2020 | Mon May 18 00:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 |  | COMPLETED
1449 | TT_TASK | Remaining IWW System | Tue May 26 07:00:00 IDT 2020 | Sat Aug 08 17:00:00 IDT 2020 | Tue Aug 11 00:00:00 IDT 2020 | Fri Sep 11 00:00:00 IDT 2020 |  | COMPLETED
1450 | TT_TASK | Site Water / Fire Loop | Fri Jul 24 07:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1451 | TT_TASK | Site Storm | Mon Jun 29 07:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Mon Jun 15 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
1454 | TT_TASK | Telecom-Communications Site Loop/Ductbank | Mon Jun 29 08:00:00 IDT 2020 | Thu Oct 01 08:00:00 IDT 2020 | Thu Jun 25 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1455 | TT_TASK | Telecom-RNG Fiber Underground installation | Mon Feb 01 07:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
1456 | TT_TASK | Telecom-RNG Fiber CNR buildout | Mon Oct 05 07:00:00 IDT 2020 | Tue Dec 08 17:00:00 IST 2020 | Mon Oct 05 07:00:00 IDT 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
1461 | TT_TASK | Temp Power/ Telecom duct bank | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Thu Aug 27 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1462 | TT_TASK | Vault- set 1st Vault Along UMS Duct bank run | Thu Sep 03 07:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1463 | TT_TASK | Vault- Set 2nd vault Along UMS Duct Run near COLO-2 | Tue Sep 08 07:00:00 IDT 2020 | Thu Sep 10 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1464 | TT_TASK | Vault- Set vault along URS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1465 | TT_TASK | Vault- Set vault along UMS to JAZ run | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1466 | TT_TASK | Set URS Vault | Mon Nov 16 08:00:00 IST 2020 | Wed Nov 25 08:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1467 | TT_TASK | Set UMS vault | Wed Nov 25 08:00:00 IST 2020 | Tue Dec 08 08:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1469 | TT_TASK | Vault- Set North vault- Along UPM to Vault | Fri Oct 09 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1470 | TT_TASK | Vault - Set North Vault Along Vault to URS run | Fri Oct 23 07:00:00 IDT 2020 | Tue Oct 27 17:00:00 IST 2020 | Thu Aug 20 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1471 | TT_TASK | Vault - Set South Vault Along Vault to URS run | Sat Nov 07 07:00:00 IST 2020 | Tue Nov 10 17:00:00 IST 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1472 | TT_TASK | Vault - Set South Vault along UPM to Vault | Mon Nov 23 07:00:00 IST 2020 | Wed Nov 25 17:00:00 IST 2020 | Thu Aug 20 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1475 | TT_TASK | Duct bank- COLO-1 UPM to north vault | Mon Oct 19 07:00:00 IDT 2020 | Tue Oct 20 17:00:00 IDT 2020 | Fri Oct 02 00:00:00 IDT 2020 | Mon Oct 05 00:00:00 IDT 2020 |  | COMPLETED
1476 | TT_TASK | Duct bank- COLO-2 UPM to north Valut | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Mon Oct 05 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1477 | TT_TASK | Duct Bank- Building to URS - 1st Half | Sat Sep 26 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 07:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
1478 | TT_TASK | Duct Bank- Building to URS(upto horse shoe) - 2nd Half | Wed Sep 30 07:00:00 IDT 2020 | Thu Oct 08 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
1479 | TT_TASK | Duct Bank - JAZ to vault- UMS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Thu Oct 29 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1480 | TT_TASK | Duct Bank - Vault to Vault along UMS duct Run - horseshoe | Mon Oct 26 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
1481 | TT_TASK | Duct Bank - COLO-3 UPM to Vault UMS Run | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1482 | TT_TASK | Duct Bank - URS to vault - URS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1483 | TT_TASK | Duct Bank - Vault To JAZ - URS to JAZ run | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 09 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1484 | TT_TASK | Duct Bank - Vault to UMS- UMS to JAZ run | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1485 | TT_TASK | Duct Bank - south vault (along UMS duct run) to UMS | Sat Nov 21 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1486 | TT_TASK | Duct Bank - COLO-4 UPM to UMS | Mon Nov 23 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
1488 | TT_TASK | Duct Bank - COLO1- UPM to UPM | Mon Aug 10 07:00:00 IDT 2020 | Thu Aug 13 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1489 | TT_TASK | Duct Bank - COLO2- UPM to UPM | Mon Aug 31 07:00:00 IDT 2020 | Thu Sep 03 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
1490 | TT_TASK | Duct Bank - North Crossover (URS to west Vault Run) | Mon Sep 14 07:00:00 IDT 2020 | Sat Sep 26 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
1491 | TT_TASK | Duct Bank - South Cross over (URS to west Vault Run) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Fri Oct 09 00:00:00 IDT 2020 |  | COMPLETED
1492 | TT_TASK | Duct Bank - COLO-3 UPM to UPM | Fri Nov 06 07:00:00 IST 2020 | Tue Nov 10 17:00:00 IST 2020 | Sat Oct 10 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1493 | TT_TASK | Duct Bank - COLO-4 UPM to UPM | Wed Nov 25 07:00:00 IST 2020 | Wed Dec 02 17:00:00 IST 2020 | Sat Oct 10 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1495 | TT_TASK | Duct Bank Admin UPM to COLO-1 UPM | Thu Sep 24 07:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 |  | COMPLETED
1496 | TT_TASK | Duct Back- Admin UPM to Vault | Fri Oct 23 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Mon Aug 24 00:00:00 IDT 2020 | Fri Aug 28 00:00:00 IDT 2020 |  | COMPLETED
1497 | TT_TASK | Duct Bank COLO-2 UPM to Vault | Mon Oct 19 07:00:00 IDT 2020 | Thu Oct 22 17:00:00 IDT 2020 | Mon Sep 28 00:00:00 IDT 2020 | Thu Oct 01 00:00:00 IDT 2020 |  | COMPLETED
1498 | TT_TASK | Duct Bank - Building to North Vault URS run | Fri Oct 23 07:00:00 IDT 2020 | Sat Oct 31 17:00:00 IST 2020 | Fri Oct 02 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1499 | TT_TASK | Duct Bank - Builing to South Vault- URS Run | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 09 17:00:00 IST 2020 | Fri Oct 02 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1500 | TT_TASK | Duct Bank - Vault to COLO-3 UPM | Tue Nov 10 07:00:00 IST 2020 | Fri Nov 13 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1501 | TT_TASK | Duct Bank - Vault to COLO-4 UPM | Mon Nov 16 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1503 | TT_TASK | Set MV Gear (URS) | Mon Nov 23 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1504 | TT_TASK | Set MV Gear (UMS) | Mon Dec 21 07:00:00 IST 2020 | Mon Dec 28 17:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
1506 | TT_TASK | Pull UPM to UPM COLO-1 - CELL-1 to Cell-3 | Tue Jan 05 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1507 | TT_TASK | Pul UPM to UPM COLO-2- CELL-1 to Cell-3 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Sat Jan 02 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
1508 | TT_TASK | Pull UPM to UPM COLO-3 - CELL-1 to Cell-3 | Fri Jan 15 07:00:00 IST 2021 | Mon Jan 18 17:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1509 | TT_TASK | Pull UPM to UPM COLO-4 - CELL-1 to Cell-3 | Wed Feb 03 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
1511 | TT_TASK | Pull UPM to UPM Admin to COLO-1 Cell -2 | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1512 | TT_TASK | Pull UPM to UPM COLO-1 Cell 2- Cell - 4 | Thu Jan 07 07:00:00 IST 2021 | Fri Jan 08 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1513 | TT_TASK | Pull UPM to UPM COLO-2 Cell 2- Cell - 4 | Wed Feb 03 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1514 | TT_TASK | Pull UPM to UPM COLO-3 Cell 2- Cell - 4 | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1515 | TT_TASK | Pull UPM to UPM COLO-4 Cell 2- Cell - 4 | Thu Feb 11 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1517 | TT_TASK | Pull Cross Overs- COLO-1 CELL-3 to CELL-4 | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1518 | TT_TASK | Pull Cross Overs- COLO-2 CELL-3 to CELL-4 | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1519 | TT_TASK | Pull Cross Overs- COLO-3 CELL-3 to CELL-4 | Tue Feb 09 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1520 | TT_TASK | Pull Cross Overs- COLO-4 CELL-3 to CELL-4 | Sat Feb 13 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1522 | TT_TASK | PULL- URS to Admin | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Sat Dec 05 00:00:00 IST 2020 |  | COMPLETED
1523 | TT_TASK | PULL- URS to COLO-2 | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
1524 | TT_TASK | PULL- URS to COLO-3 | Tue Jan 12 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1525 | TT_TASK | PULL- URS to COLO-4 | Mon Jan 18 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1527 | TT_TASK | Pull- UMS to COLO-1,2,3 | Tue Jan 12 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Jan 11 17:00:00 IST 2021 |  | COMPLETED
1528 | TT_TASK | Pull- UMS to COLO-4 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 |  | COMPLETED
1530 | TT_TASK | Pull - JAZ to URS | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
1531 | TT_TASK | Pull - JAZ to UMS | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1534 | TT_TASK | Term COLO -1 Cell-3 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1535 | TT_TASK | Term COLO -2 Cell-3 UPM | Thu Mar 04 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1536 | TT_TASK | Term COLO -3 Cell-3 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 |  | COMPLETED
1537 | TT_TASK | Term COLO -4 Cell-3 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1538 | TT_TASK | Term COLO -1 Cell-1 UPM | Wed Feb 10 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1539 | TT_TASK | Term COLO -2 Cell-1 UPM | Sat Feb 13 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1540 | TT_TASK | Term COLO -3 Cell-1 UPM | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1541 | TT_TASK | Term COLO -4 Cell-1 UPM | Thu Mar 11 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
1543 | TT_TASK | Term COLO -1 Cell-4 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
1544 | TT_TASK | Term COLO -2 Cell-4 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1545 | TT_TASK | Term COLO -3 Cell-4 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1546 | TT_TASK | Term COLO -4 Cell-4 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1547 | TT_TASK | Term Admin - UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1548 | TT_TASK | Term COLO -1 Cell-2 UPM | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
1549 | TT_TASK | Term COLO -2 Cell-2 UPM | Fri Feb 05 07:00:00 IST 2021 | Tue Feb 09 17:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1550 | TT_TASK | Term COLO -3 Cell-2 UPM | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 |  | COMPLETED
1551 | TT_TASK | Term COLO -4 Cell-2 UPM | Fri Mar 05 07:00:00 IST 2021 | Mon Mar 08 17:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1553 | TT_TASK | Battery Station Yellow tagging / EPMS Checkouts | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
1554 | TT_TASK | GCPUD NORTH Mobile substation maintance & Mobile Sub re-energization 4/1 Â– 4/3 | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1555 | TT_TASK | GCPUD SOUTH Mobile substation maintance & Mobile Sub re-energization 4/1 Â– 4/3 | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1556 | TT_TASK | Term- UMS- Line Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1557 | TT_TASK | Term- JAZ to Structure- (Incl Stress Cones) from ums | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1558 | TT_TASK | Term- UMS- Load side | Wed Feb 10 07:00:00 IST 2021 | Tue Feb 23 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1559 | TT_TASK | Yellow Tagging for UMS (includes GC, vendor Lvl-2) | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
1560 | TT_TASK | UMS Control Power Available CYT | Wed Feb 10 07:00:00 IST 2021 | Wed Feb 17 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
1562 | TT_TASK | Term URS- Line Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
1563 | TT_TASK | Term- JAS to URS- (Incl Stress Cones) | Wed Feb 03 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1564 | TT_TASK | TERM- URS- Load Side | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1565 | TT_TASK | Yellow Tagging for URS | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
1566 | TT_TASK | URS Control Power Available CYT | Wed Feb 10 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
1568 | TT_TASK | Aggregate Road Base | Mon Oct 19 07:00:00 IDT 2020 | Tue Nov 24 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
1569 | TT_TASK | Plant shutdown for winter | Mon Nov 30 07:00:00 IST 2020 | Tue Apr 06 17:00:00 IDT 2021 | Mon Nov 23 00:00:00 IST 2020 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
1570 | TT_TASK | Curb & Gutter | Mon Nov 30 07:00:00 IST 2020 | Sat Jan 09 17:00:00 IST 2021 | Mon Nov 02 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1571 | TT_TASK | Pave HMA | Mon Apr 05 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Sat Nov 07 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1572 | TT_TASK | Site Lighting | Mon May 03 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 |  | 120.0 | IN_PROGRESS
1575 | TT_TASK | Landscape and Site Specialties | Mon May 17 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  |  | IN_PROGRESS
1581 | TT_TASK | Perimeter Foundations - Excavate/FRP | Mon Apr 27 07:00:00 IDT 2020 | Thu May 14 17:00:00 IDT 2020 | Wed Apr 22 00:00:00 IDT 2020 | Wed May 20 00:00:00 IDT 2020 |  | COMPLETED
1582 | TT_TASK | Perimeter Foundations - Waterproof/Backfill | Mon Jun 01 07:00:00 IDT 2020 | Thu Jun 04 17:00:00 IDT 2020 | Wed May 27 00:00:00 IDT 2020 | Fri Jun 05 00:00:00 IDT 2020 |  | COMPLETED
1583 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Fri Jun 05 07:00:00 IDT 2020 | Tue Jun 16 17:00:00 IDT 2020 | Tue Jun 02 00:00:00 IDT 2020 | Fri Jun 12 00:00:00 IDT 2020 |  | COMPLETED
1585 | TT_TASK | Erect PEMB Steel | Mon Jun 29 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Mon Jun 22 00:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 |  | COMPLETED
1586 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Thu Jul 02 00:00:00 IDT 2020 | Fri Jul 10 00:00:00 IDT 2020 |  | COMPLETED
1588 | TT_TASK | MEP Undeground Rough-In (Interior) | Tue Aug 18 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1589 | TT_TASK | Aggregate Base Course | Mon Aug 31 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 |  | COMPLETED
1590 | TT_TASK | Slab on Grade | Mon Sep 14 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1592 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Aug 18 07:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 |  | COMPLETED
1593 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Tue Jul 14 00:00:00 IDT 2020 | Tue Jul 21 00:00:00 IDT 2020 |  | COMPLETED
1594 | TT_TASK | Downspouts & Gutters | Tue Aug 18 07:00:00 IDT 2020 | Sat Aug 29 17:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 |  | COMPLETED
1604 | TT_TASK | Perimeter Foundations - Excavate/FRP | Fri May 15 07:00:00 IDT 2020 | Wed Jun 03 17:00:00 IDT 2020 | Mon May 04 00:00:00 IDT 2020 | Fri May 15 00:00:00 IDT 2020 |  | COMPLETED
1605 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Sat Jun 13 07:00:00 IDT 2020 | Thu Jun 25 17:00:00 IDT 2020 | Tue Jun 02 00:00:00 IDT 2020 | Fri Jun 12 00:00:00 IDT 2020 |  | COMPLETED
1606 | TT_TASK | Perimeter Foundations - Waterproof Backfill | Tue May 26 07:00:00 IDT 2020 | Sat Jun 06 17:00:00 IDT 2020 | Tue May 26 07:00:00 IDT 2020 | Wed Jun 17 00:00:00 IDT 2020 |  | COMPLETED
1608 | TT_TASK | Erect PEMB Steel | Mon Jun 29 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Fri Jun 26 00:00:00 IDT 2020 | Mon Jul 06 00:00:00 IDT 2020 |  | COMPLETED
1609 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Wed Jul 01 00:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 |  | COMPLETED
1610 | TT_TASK | Erect Interior Structural Steel | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
1612 | TT_TASK | MEP Undeground Rough-In (Interior) | Fri Aug 14 07:00:00 IDT 2020 | Tue Sep 01 17:00:00 IDT 2020 | Mon Aug 03 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1613 | TT_TASK | Aggregate Base Course | Sat Sep 05 07:00:00 IDT 2020 | Fri Sep 11 17:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 |  | COMPLETED
1614 | TT_TASK | Slab on Grade | Mon Sep 14 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1618 | TT_TASK | Exterior Insulated Metal Panels Installation - East Elevation | Tue Aug 18 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Mon Jul 13 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1621 | TT_TASK | Exterior Insulated Metal Panels Installation - West Elevation | Tue Aug 18 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Mon Jul 13 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1623 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 |  | COMPLETED
1624 | TT_TASK | Downspouts & Gutters | Tue Aug 18 07:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Mon Jul 27 00:00:00 IDT 2020 | Wed Aug 12 00:00:00 IDT 2020 |  | COMPLETED
1629 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jun 22 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Mon May 11 00:00:00 IDT 2020 | Tue Jun 16 00:00:00 IDT 2020 |  | COMPLETED
1630 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Wed Jul 08 07:00:00 IDT 2020 | Mon Jul 20 17:00:00 IDT 2020 | Tue Jun 09 00:00:00 IDT 2020 | Sat Jun 20 00:00:00 IDT 2020 |  | COMPLETED
1632 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Tue Jul 07 00:00:00 IDT 2020 | Wed Jul 22 00:00:00 IDT 2020 |  | COMPLETED
1633 | TT_TASK | Secondary Steel | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 17 17:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 | Tue Aug 04 00:00:00 IDT 2020 |  | COMPLETED
1634 | TT_TASK | Erect Interior Structural Steel | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1636 | TT_TASK | MEP Undeground Rough-In (Interior) | Mon Aug 31 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Wed Aug 19 00:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 |  | COMPLETED
1637 | TT_TASK | Aggregate Base Course | Mon Oct 19 07:00:00 IDT 2020 | Mon Oct 26 17:00:00 IST 2020 | Thu Oct 01 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1638 | TT_TASK | Slab on Grade | Mon Oct 19 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
1640 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Aug 18 07:00:00 IDT 2020 | Tue Sep 01 17:00:00 IDT 2020 | Fri Jul 31 00:00:00 IDT 2020 | Thu Aug 13 00:00:00 IDT 2020 |  | COMPLETED
1641 | TT_TASK | Roof Panels Installation | Mon Aug 10 07:00:00 IDT 2020 | Wed Aug 26 17:00:00 IDT 2020 | Fri Jul 31 00:00:00 IDT 2020 | Fri Aug 14 00:00:00 IDT 2020 |  | COMPLETED
1642 | TT_TASK | Downspouts & Gutters | Sat Sep 05 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Mon Aug 10 00:00:00 IDT 2020 | Mon Aug 17 00:00:00 IDT 2020 |  | COMPLETED
1647 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Wed Jul 08 07:00:00 IDT 2020 | Mon Jul 20 17:00:00 IDT 2020 | Wed Jun 24 00:00:00 IDT 2020 | Thu Jul 09 00:00:00 IDT 2020 |  | COMPLETED
1648 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jun 22 07:00:00 IDT 2020 | Thu Jul 09 17:00:00 IDT 2020 | Tue Jun 16 00:00:00 IDT 2020 | Sat Jul 18 00:00:00 IDT 2020 |  | COMPLETED
1650 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Thu Jul 23 00:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 |  | COMPLETED
1651 | TT_TASK | Secondary Steel | Mon Aug 31 07:00:00 IDT 2020 | Sat Sep 05 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 |  | COMPLETED
1652 | TT_TASK | Erect Interior Structural Steel | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1654 | TT_TASK | MEP Undeground Rough-In (Interior) | Mon Oct 19 07:00:00 IDT 2020 | Thu Nov 05 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1655 | TT_TASK | Aggregate Base Course | Fri Nov 06 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1656 | TT_TASK | Slab on Grade | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Wed Oct 28 00:00:00 IST 2020 |  | COMPLETED
1658 | TT_TASK | Exterior Insulated Metal Panels Installation | Tue Sep 08 07:00:00 IDT 2020 | Tue Sep 22 17:00:00 IDT 2020 | Sat Aug 15 00:00:00 IDT 2020 | Sat Aug 22 00:00:00 IDT 2020 |  | COMPLETED
1659 | TT_TASK | Roof Panels Installation | Tue Sep 08 07:00:00 IDT 2020 | Thu Sep 24 17:00:00 IDT 2020 | Tue Aug 18 00:00:00 IDT 2020 | Tue Sep 01 00:00:00 IDT 2020 |  | COMPLETED
1660 | TT_TASK | Downspouts & Gutters | Wed Sep 16 07:00:00 IDT 2020 | Tue Sep 22 17:00:00 IDT 2020 | Wed Sep 02 00:00:00 IDT 2020 | Mon Oct 12 00:00:00 IDT 2020 |  | COMPLETED
1670 | TT_TASK | Perimeter Foundations - Excavate/FRP/Backfill | Mon Jul 06 07:00:00 IDT 2020 | Thu Jul 23 17:00:00 IDT 2020 | Tue Jun 23 00:00:00 IDT 2020 | Thu Jul 30 00:00:00 IDT 2020 |  | COMPLETED
1671 | TT_TASK | Interior Footings - Excavate/FRP/Backfill | Sat Aug 29 07:00:00 IDT 2020 | Thu Sep 10 17:00:00 IDT 2020 | Sat Jul 25 00:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 |  | COMPLETED
1673 | TT_TASK | Erect PEMB Steel | Mon Aug 10 07:00:00 IDT 2020 | Tue Aug 25 17:00:00 IDT 2020 | Sat Aug 08 00:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 |  | COMPLETED
1674 | TT_TASK | Secondary Steel | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 08 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 |  | COMPLETED
1675 | TT_TASK | Erect Interior Structural Steel | Mon Dec 21 07:00:00 IST 2020 | Tue Dec 29 17:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
1677 | TT_TASK | MEP Undeground Rough-In (Interior) | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Oct 05 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1678 | TT_TASK | Aggregate Base Course | Wed Nov 11 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Thu Oct 15 00:00:00 IDT 2020 | Thu Oct 29 00:00:00 IST 2020 |  | COMPLETED
1679 | TT_TASK | Slab on Grade | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1681 | TT_TASK | Exterior Insulated Metal Panels Installation | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Mon Aug 24 00:00:00 IDT 2020 | Wed Sep 30 00:00:00 IDT 2020 |  | COMPLETED
1682 | TT_TASK | Roof Panels Installation | Thu Sep 03 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Thu Aug 27 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1683 | TT_TASK | Downspouts & Gutters | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Sep 07 00:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1693 | TT_TASK | Hang Wall Partitions | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1694 | TT_TASK | Hang Wall Partitions- Early Walls | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1695 | TT_TASK | MEP Rough-In / Wall & Ceiling | Mon Oct 19 07:00:00 IDT 2020 | Mon Nov 02 17:00:00 IST 2020 | Thu Oct 01 00:00:00 IDT 2020 | Tue Nov 17 00:00:00 IST 2020 |  | COMPLETED
1697 | TT_TASK | Early Room - Finishes | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1699 | TT_TASK | Loading Dock Equipment & Dock Doors | Wed May 05 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
1700 | TT_TASK | MEP Overhead | Mon Oct 19 07:00:00 IDT 2020 | Tue Nov 17 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1701 | TT_TASK | Ceilings / Ligthing / FA Devices | Mon Mar 01 07:00:00 IST 2021 | Tue Apr 13 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
1702 | TT_TASK | Concrete Floor Sealing/Epoxy | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
1706 | TT_TASK | Generator Term | Fri Mar 05 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
1707 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Wed Aug 26 00:00:00 IDT 2020 | Fri Sep 25 00:00:00 IDT 2020 |  | COMPLETED
1708 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 17:00:00 IST 2020 | Fri Sep 18 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
1709 | TT_TASK | Set Exterior Electrical OFCI Equipment | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1710 | TT_TASK | Admin -Electrical Underground Rough-In | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 31 17:00:00 IDT 2020 | Fri Aug 07 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
1711 | TT_TASK | Generator & Utility Power Pull-Test | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1712 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Jan 18 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1713 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1715 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Oct 19 07:00:00 IDT 2020 | Mon Nov 02 17:00:00 IST 2020 | Fri Oct 09 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1716 | TT_TASK | Set Exterior Mechanical CFCI Equipment (remaning mini splits) | Fri Nov 06 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1717 | TT_TASK | Mechanical Underground Rough-In | Mon Aug 10 07:00:00 IDT 2020 | Mon Aug 31 17:00:00 IDT 2020 | Sat Aug 08 00:00:00 IDT 2020 | Tue Aug 25 00:00:00 IDT 2020 |  | COMPLETED
1718 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1721 | TT_TASK | Fire Alarm Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1722 | TT_TASK | Controls Installation | Tue Feb 16 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
1724 | TT_TASK | Set Electrical Equipment incl. OH raceways | Mon Nov 23 07:00:00 IST 2020 | Wed Jan 13 17:00:00 IST 2021 | Mon Nov 16 00:00:00 IST 2020 | Tue Dec 29 00:00:00 IST 2020 |  | COMPLETED
1725 | TT_TASK | Electrical Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1727 | TT_TASK | Domestic Water Piping | Mon Nov 23 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1728 | TT_TASK | Plumbing Devices & Trim | Mon Jul 26 15:00:00 IDT 2021 | Tue Aug 17 15:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
1730 | TT_TASK | Security Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
1732 | TT_TASK | Mechanical Ductwork Installation | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1733 | TT_TASK | Set Mechanical Equipment | Mon Nov 23 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
1734 | TT_TASK | Mechanical Devices & Trim | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1739 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1740 | TT_TASK | Overhead MEPFP Rough-In | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 11 17:00:00 IST 2020 | Wed Oct 14 00:00:00 IDT 2020 | Sat Oct 17 00:00:00 IDT 2020 |  | COMPLETED
1741 | TT_TASK | Early Topout | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1743 | TT_TASK | Sprinkler Test | Mon Dec 21 07:00:00 IST 2020 | Tue Dec 22 17:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1744 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1747 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
1748 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1749 | TT_TASK | Early Topout | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Tue Nov 10 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1751 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Nov 30 07:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1754 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 02 07:00:00 IST 2020 | Fri Nov 06 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 |  | COMPLETED
1755 | TT_TASK | Overhead MEPFP Rough-In | Sat Oct 31 07:00:00 IST 2020 | Wed Nov 11 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 16 00:00:00 IDT 2020 |  | COMPLETED
1756 | TT_TASK | Early Topout | Mon Nov 16 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 |  | COMPLETED
1758 | TT_TASK | Datahall Finishes- Ceiling Grid | Thu Dec 03 07:00:00 IST 2020 | Tue Dec 15 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1761 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
1762 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1763 | TT_TASK | Early Topout | Thu Nov 19 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Tue Nov 10 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1765 | TT_TASK | Datahall Finishes- Ceiling Grid | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 | Wed Nov 25 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
1768 | TT_TASK | Remaining MER raceway across Mech chase | Tue Dec 01 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1769 | TT_TASK | Electrical OH Below Mechanical Piping | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1770 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1771 | TT_TASK | OverHead MEPFP Rough-In ( Add TCM Cross over piping HRA Level-3) | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1772 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Nov 07 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1774 | TT_TASK | Mechanical Corridor Finishes | Mon Nov 16 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1777 | TT_TASK | Remaining MER raceway across Mech chase | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1778 | TT_TASK | Electrical OH Below Mechanical Piping | Wed Jan 20 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1779 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 11 00:00:00 IST 2020 |  | COMPLETED
1780 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1781 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1783 | TT_TASK | Mechanical Corridor Finishes | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1786 | TT_TASK | Remaining MER raceway across Mech chase | Tue Dec 01 07:00:00 IST 2020 | Thu Dec 10 17:00:00 IST 2020 | Tue Jan 05 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1787 | TT_TASK | Electrical OH Below Mechanical Piping | Mon Jan 04 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
1788 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
1789 | TT_TASK | OverHead MEPFP Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
1790 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1792 | TT_TASK | Mechanical Corridor Finishes | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 |  | COMPLETED
1795 | TT_TASK | Remaining MER raceway across Mech chase | Fri Feb 05 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1796 | TT_TASK | Electrical OH Below Mechanical Piping | Wed Jan 20 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
1797 | TT_TASK | Frame & Top out | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Wed Nov 11 00:00:00 IST 2020 |  | COMPLETED
1798 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Tue Oct 20 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
1799 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 |  | COMPLETED
1801 | TT_TASK | Mechanical Corridor Finishes | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Tue Nov 17 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
1805 | TT_TASK | Generator & Utility Power Term | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1806 | TT_TASK | Remaining Mechanical Equipment (ADP01) Termimations | Thu Mar 18 07:00:00 IST 2021 | Tue Mar 23 17:00:00 IST 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1807 | TT_TASK | Electrical Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 14 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1808 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1809 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1810 | TT_TASK | Exterior Equipment Pads - Electrical | Thu Sep 03 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Sat Oct 10 00:00:00 IDT 2020 |  | COMPLETED
1811 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Oct 12 07:00:00 IDT 2020 | Mon Oct 26 17:00:00 IST 2020 | Mon Oct 12 07:00:00 IDT 2020 | Thu Oct 15 00:00:00 IDT 2020 |  | COMPLETED
1812 | TT_TASK | Lift & Set MER in Place | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Wed Dec 16 00:00:00 IST 2020 | Wed Dec 16 17:00:00 IST 2020 |  | COMPLETED
1813 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
1814 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 13 17:00:00 IST 2021 | Thu Dec 17 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1815 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Jan 11 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Tue Jan 05 00:00:00 IST 2021 | Sat Jan 16 00:00:00 IST 2021 |  | COMPLETED
1816 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1817 | TT_TASK | Generator & Utility Power Pull | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1819 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1820 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1821 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1822 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1823 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Sat Dec 05 00:00:00 IST 2020 | Mon Dec 07 00:00:00 IST 2020 |  | COMPLETED
1824 | TT_TASK | Mechanical Equipment Piping Connections | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1825 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
1828 | TT_TASK | Fire Alarm Installation | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
1829 | TT_TASK | Controls Installation | Fri Mar 05 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1832 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 22 07:00:00 IST 2021 | Tue Mar 30 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1833 | TT_TASK | Electrical Underground Rough-In | Thu Sep 03 07:00:00 IDT 2020 | Fri Sep 18 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1834 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1835 | TT_TASK | Set Electrical Equipment-UPM Cell -3 | Fri Dec 11 07:00:00 IST 2020 | Tue Dec 15 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1836 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
1837 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1838 | TT_TASK | Lift & Set MER in Place | Mon Jan 11 08:00:00 IST 2021 | Mon Jan 18 08:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1839 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 18 08:00:00 IST 2021 | Fri Jan 22 08:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Wed Jan 13 00:00:00 IST 2021 |  | COMPLETED
1840 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
1841 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 |  | COMPLETED
1842 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Thu Mar 04 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
1843 | TT_TASK | Generator & Utility Power Pull | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
1845 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1846 | TT_TASK | Exterior Equipment Pads - Mechanical | Fri Oct 16 07:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Sat Sep 19 00:00:00 IDT 2020 | Wed Oct 14 00:00:00 IDT 2020 |  | COMPLETED
1847 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1848 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1849 | TT_TASK | Set Exterior Water Treatment equipment | Mon Dec 07 07:00:00 IST 2020 | Tue Dec 08 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1850 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1851 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 15 07:00:00 IST 2021 | Mon Mar 22 17:00:00 IST 2021 | Wed Feb 17 00:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 |  | COMPLETED
1854 | TT_TASK | Fire Alarm Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1855 | TT_TASK | Controls Installation | Tue Mar 09 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1858 | TT_TASK | Generator & Utility Power Pull | Tue Feb 02 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Feb 26 07:00:00 IST 2021 |  | COMPLETED
1859 | TT_TASK | Remaining Mechanical Equipment (ADP01) Termimations | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1860 | TT_TASK | Electrical Underground Rough-In | Fri Aug 14 07:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Thu Aug 06 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1861 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 05 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1862 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1863 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Sep 05 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Fri Oct 02 00:00:00 IDT 2020 |  | COMPLETED
1864 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Oct 26 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Tue Oct 13 00:00:00 IDT 2020 |  | COMPLETED
1865 | TT_TASK | Lift & Set MER in Place | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
1866 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 11 08:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1867 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1868 | TT_TASK | GEN & UPM to MER Cable Bus Install | Wed Jan 20 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
1869 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
1870 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1872 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Aug 31 07:00:00 IDT 2020 | Tue Sep 15 17:00:00 IDT 2020 | Fri Aug 21 00:00:00 IDT 2020 | Tue Sep 08 00:00:00 IDT 2020 |  | COMPLETED
1873 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Oct 05 07:00:00 IDT 2020 | Sat Oct 17 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Mon Oct 19 00:00:00 IDT 2020 |  | COMPLETED
1874 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
1875 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1876 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
1877 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1878 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 08 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Tue Feb 09 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1881 | TT_TASK | Fire Alarm Installation | Thu Feb 18 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Apr 01 00:00:00 IDT 2021 |  | COMPLETED
1882 | TT_TASK | Controls Installation | Sat Mar 06 07:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
1885 | TT_TASK | Generator & Utility Power Pull | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
1886 | TT_TASK | Electrical Underground Rough-In | Sat Sep 05 07:00:00 IDT 2020 | Mon Sep 21 17:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Sep 19 00:00:00 IDT 2020 |  | COMPLETED
1887 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Sep 28 07:00:00 IDT 2020 | Thu Oct 01 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Thu Sep 24 00:00:00 IDT 2020 |  | COMPLETED
1888 | TT_TASK | Set Electrical Equipment-UPM | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 | Tue Nov 24 00:00:00 IST 2020 |  | COMPLETED
1889 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Mon Sep 21 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1890 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Thu Oct 22 00:00:00 IDT 2020 |  | COMPLETED
1891 | TT_TASK | Lift & Set MER in Place | Mon Jan 11 08:00:00 IST 2021 | Mon Jan 18 08:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
1892 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jan 11 08:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Jan 11 08:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
1893 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jan 11 08:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1894 | TT_TASK | GEN & UPM to MER Cable Bus Install | Thu Feb 04 07:00:00 IST 2021 | Sat Feb 13 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
1895 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Wed Apr 07 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Wed Mar 24 00:00:00 IST 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
1896 | TT_TASK | Generator & Utility Power Test-Term | Mon Mar 15 07:00:00 IST 2021 | Wed Mar 17 17:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
1898 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Sep 14 07:00:00 IDT 2020 | Sat Sep 26 17:00:00 IDT 2020 | Mon Sep 14 07:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 |  | COMPLETED
1899 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 12 17:00:00 IDT 2020 | Tue Sep 22 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
1900 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Thu Nov 12 00:00:00 IST 2020 |  | COMPLETED
1901 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1902 | TT_TASK | Set Exterior Water Treatment equipment | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
1903 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
1904 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 06 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 |  | COMPLETED
1907 | TT_TASK | Fire Alarm Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1908 | TT_TASK | Controls Installation | Thu Apr 15 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1911 | TT_TASK | VFD'S Installation & wirepull | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1912 | TT_TASK | Ligthing Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 |  | COMPLETED
1914 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Thu Nov 26 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
1915 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1917 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1919 | TT_TASK | Fire Riser Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1920 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1921 | TT_TASK | Controls Installation | Fri Mar 26 07:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1924 | TT_TASK | VFD'S Installation & Wiring | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
1925 | TT_TASK | Ligthing Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
1927 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
1928 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1930 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1932 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1933 | TT_TASK | Controls Installation | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1936 | TT_TASK | VFD'S Installation & Wiring | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
1937 | TT_TASK | Ligthing Installation | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 |  | COMPLETED
1939 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Nov 23 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
1940 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
1942 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1944 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1945 | TT_TASK | Controls Installation | Tue Apr 13 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed May 26 00:00:00 IDT 2021 |  | COMPLETED
1948 | TT_TASK | VFD'S Installation & Wiring | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
1949 | TT_TASK | Ligthing Installation | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jul 29 00:00:00 IDT 2021 |  | COMPLETED
1951 | TT_TASK | AHU/DOAS Equipment Setting | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
1952 | TT_TASK | Hydronic Piping Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1954 | TT_TASK | Floor Drain System Installation | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
1956 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
1957 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1961 | TT_TASK | HAC Installation | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Tue Dec 22 00:00:00 IST 2020 |  | COMPLETED
1962 | TT_TASK | Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1963 | TT_TASK | Power Bus Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
1964 | TT_TASK | PDU's Installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
1965 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Apr 05 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1966 | TT_TASK | Light Fixtures Installation | Wed May 05 07:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
1967 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
1969 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
1970 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1971 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1972 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon May 17 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1974 | TT_TASK | Security Devices & Trim | Mon May 17 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
1975 | TT_TASK | Controls Installation | Fri Mar 26 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1976 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1979 | TT_TASK | HAC Installation | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
1980 | TT_TASK | Cable Tray Installation | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 16 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
1981 | TT_TASK | Power Bus Installation | Tue Mar 02 07:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
1982 | TT_TASK | PDU's Installation | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
1983 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Apr 26 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
1984 | TT_TASK | Light Fixtures Installation | Wed May 12 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
1985 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Apr 26 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
1987 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
1988 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1989 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
1990 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Thu Jul 01 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1992 | TT_TASK | Security Devices & Trim | Mon Jun 07 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
1993 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
1994 | TT_TASK | Fire Alarm System | Tue May 04 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
1997 | TT_TASK | HAC Installation | Mon Jan 04 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
1998 | TT_TASK | Cable Tray Installation | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 23 00:00:00 IST 2020 | Mon Jan 18 00:00:00 IST 2021 |  | COMPLETED
1999 | TT_TASK | Power Bus Installation | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
2000 | TT_TASK | PDU's Installation | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Sat Feb 06 00:00:00 IST 2021 |  | COMPLETED
2001 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Apr 01 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Mon Mar 29 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2002 | TT_TASK | Light Fixtures Installation | Tue May 11 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 |  | COMPLETED
2003 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 23 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 17 00:00:00 IDT 2021 |  | COMPLETED
2005 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2006 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2007 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2008 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed May 19 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2010 | TT_TASK | Security Devices & Trim | Mon May 17 07:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2011 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2012 | TT_TASK | Fire Alarm System | Thu May 06 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2015 | TT_TASK | HAC Installation | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2016 | TT_TASK | Cable Tray Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2017 | TT_TASK | Power Bus Installation | Fri Mar 12 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2018 | TT_TASK | PDU's Installation | Mon Mar 08 07:00:00 IST 2021 | Wed Mar 10 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2019 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon May 03 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 |  | COMPLETED
2020 | TT_TASK | Light Fixtures Installation | Fri May 21 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2021 | TT_TASK | Pull/term/Test PDU to Power bus | Mon May 03 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2023 | TT_TASK | IDF Backbone Install | Mon Mar 22 07:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2024 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2025 | TT_TASK | BMS Pull Wire / Term / Test | Thu Apr 01 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Mar 13 00:00:00 IST 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2026 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed May 19 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2028 | TT_TASK | Security Devices & Trim | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 |  | COMPLETED
2029 | TT_TASK | Controls Installation | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2030 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2036 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 16 07:00:00 IST 2020 | Fri Nov 20 17:00:00 IST 2020 | Mon Nov 16 07:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2037 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
2038 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2040 | TT_TASK | Datahall Finishes - Ceiling Grid | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2043 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2044 | TT_TASK | Overhead MEPFP Rough-In | Fri Nov 06 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2045 | TT_TASK | Hang drywall / Mud / Tape | Wed Jan 06 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2047 | TT_TASK | Datahall Finishes - Ceiling Grid | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2050 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2051 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 12 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 |  | COMPLETED
2052 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2054 | TT_TASK | Datahall Finishes - Ceiling Grid | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2057 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Nov 23 07:00:00 IST 2020 | Tue Dec 01 17:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2058 | TT_TASK | Overhead MEPFP Rough-In | Fri Nov 06 07:00:00 IST 2020 | Wed Nov 18 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2059 | TT_TASK | Hang drywall / Mud / Tape | Wed Jan 06 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2061 | TT_TASK | Datahall Finishes - Ceiling Grid | Mon Jan 11 07:00:00 IST 2021 | Wed Jan 20 17:00:00 IST 2021 | Thu Dec 31 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2064 | TT_TASK | Remaining Post MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2065 | TT_TASK | Frame & Top out | Mon Nov 23 07:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2066 | TT_TASK | OverHead MEPFP Rough-In | Thu Nov 19 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2067 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Dec 12 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2069 | TT_TASK | Mechanical Corridor Finishes | Mon Jan 11 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2072 | TT_TASK | Remaining MER raceway across Mech chase | Thu Mar 25 07:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2073 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2074 | TT_TASK | OverHead MEPFP Rough-In | Tue Dec 08 07:00:00 IST 2020 | Mon Dec 21 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2075 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Dec 14 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2077 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2080 | TT_TASK | Remaining MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 |  | COMPLETED
2081 | TT_TASK | Frame & Top out | Mon Nov 30 07:00:00 IST 2020 | Wed Dec 09 17:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2082 | TT_TASK | OverHead MEPFP Rough-In | Sat Dec 19 07:00:00 IST 2020 | Thu Jan 07 17:00:00 IST 2021 | Mon Oct 26 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2083 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Sat Dec 12 07:00:00 IST 2020 | Thu Dec 17 17:00:00 IST 2020 | Mon Nov 16 00:00:00 IST 2020 | Wed Nov 25 00:00:00 IST 2020 |  | COMPLETED
2085 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2088 | TT_TASK | Remaining MER raceway across Mech chase | Mon Mar 22 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Mar 12 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2089 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Tue Jan 12 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2090 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2091 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Nov 30 07:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Fri Nov 20 00:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 |  | COMPLETED
2093 | TT_TASK | Mechanical Corridor Finishes | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 28 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 |  | COMPLETED
2097 | TT_TASK | Generator & Utility Power Pull | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
2098 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
2099 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2100 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 08 00:00:00 IST 2020 | Tue Dec 08 00:00:00 IST 2020 |  | COMPLETED
2101 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Dec 14 07:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 | Tue Nov 17 00:00:00 IST 2020 |  | COMPLETED
2102 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Tue Dec 29 00:00:00 IST 2020 |  | COMPLETED
2103 | TT_TASK | Lift & Set MER in Place | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2104 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Fri Feb 12 00:00:00 IST 2021 |  | COMPLETED
2105 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Wed Feb 10 00:00:00 IST 2021 |  | COMPLETED
2106 | TT_TASK | GEN & UPM to MER Cable Bus Install | Mon Mar 22 07:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Fri Mar 05 00:00:00 IST 2021 | Sat Mar 13 00:00:00 IST 2021 |  | COMPLETED
2107 | TT_TASK | Generator & Utility Power Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2108 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2110 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Wed Oct 07 00:00:00 IDT 2020 |  | COMPLETED
2111 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 08 17:00:00 IST 2021 | Mon Nov 02 00:00:00 IST 2020 | Fri Nov 06 00:00:00 IST 2020 |  | COMPLETED
2112 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2113 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC) | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2114 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2115 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2116 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2119 | TT_TASK | Fire Alarm Installation | Tue May 11 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2120 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2123 | TT_TASK | Generator & Utility Power Pull | Tue May 11 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 |  | COMPLETED
2124 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 21 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2125 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 09 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2126 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Wed Dec 16 00:00:00 IST 2020 | Thu Dec 17 00:00:00 IST 2020 |  | COMPLETED
2127 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Dec 14 07:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Nov 14 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2128 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2129 | TT_TASK | Lift & Set MER in Place | Tue Mar 23 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Tue Mar 02 00:00:00 IST 2021 |  | COMPLETED
2130 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Mar 29 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2131 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Mar 29 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2132 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Fri Apr 16 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 25 00:00:00 IST 2021 |  | COMPLETED
2133 | TT_TASK | Generator & Utility Power Test-Term | Thu May 06 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 13 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2134 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 |  | COMPLETED
2136 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2137 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Dec 21 07:00:00 IST 2020 | Fri Jan 08 17:00:00 IST 2021 | Mon Nov 16 00:00:00 IST 2020 | Thu Nov 19 00:00:00 IST 2020 |  | COMPLETED
2138 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2139 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2140 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 | Tue Jan 19 00:00:00 IST 2021 |  | COMPLETED
2141 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2142 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Tue Mar 16 00:00:00 IST 2021 |  | COMPLETED
2145 | TT_TASK | Fire Alarm Installation | Wed May 26 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2146 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2149 | TT_TASK | Generator & Utility Power Pull | Fri Mar 26 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 |  | COMPLETED
2150 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2151 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Wed Nov 04 00:00:00 IST 2020 |  | COMPLETED
2152 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Wed Nov 04 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2153 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Tue Nov 03 00:00:00 IST 2020 |  | COMPLETED
2154 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 | Sat Jan 09 00:00:00 IST 2021 |  | COMPLETED
2155 | TT_TASK | Lift & Set MER in Place | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Mar 01 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2156 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Mar 27 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2157 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Mar 27 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Tue Mar 02 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2158 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Thu Mar 25 07:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
2159 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2160 | TT_TASK | Generator & Utility Power Test-Term | Tue Apr 06 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Tue Apr 06 07:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2162 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2163 | TT_TASK | Exterior Equipment Pads - Mechanical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Fri Nov 13 00:00:00 IST 2020 |  | COMPLETED
2164 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 |  | COMPLETED
2165 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2166 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Fri Jan 15 07:00:00 IST 2021 | Fri Jan 29 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2167 | TT_TASK | Set Exterior Water Treatment equipment | Mon Feb 01 07:00:00 IST 2021 | Tue Feb 02 17:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
2168 | TT_TASK | Mechanical Equipment Piping Connections | Mon Mar 22 07:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
2171 | TT_TASK | Fire Alarm Installation | Tue May 11 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2172 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2175 | TT_TASK | Generator & Utility Power Pull | Thu May 13 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2176 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2177 | TT_TASK | Exterior Equipment Pads - for UPM's | Mon Nov 30 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Nov 02 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2178 | TT_TASK | Set Electrical Equipment-UPM | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Thu Dec 10 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2179 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Thu Nov 05 00:00:00 IST 2020 |  | COMPLETED
2180 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 | Fri Jan 22 00:00:00 IST 2021 |  | COMPLETED
2181 | TT_TASK | Lift & Set MER in Place | Mon Mar 22 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Mar 08 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
2182 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Sat Mar 27 07:00:00 IDT 2021 | Wed Mar 31 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2183 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Sat Mar 27 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Mon Mar 29 00:00:00 IDT 2021 |  | COMPLETED
2184 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Thu Apr 15 07:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Apr 08 00:00:00 IDT 2021 |  | COMPLETED
2185 | TT_TASK | Generator & Utility Power Test-Term | Tue May 18 07:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2186 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Apr 30 07:00:00 IDT 2021 | Tue May 25 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2188 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Sep 28 00:00:00 IDT 2020 | Tue Oct 06 00:00:00 IDT 2020 |  | COMPLETED
2189 | TT_TASK | Set Gen Stack / Exhaust duct | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2192 | TT_TASK | Fire Alarm Installation | Wed May 12 07:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2193 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2196 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Mon Jun 07 00:00:00 IDT 2021 |  | COMPLETED
2197 | TT_TASK | Ligthing Installation | Fri Jul 23 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2199 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2200 | TT_TASK | Hydronic Piping Installation | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2202 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2203 | TT_TASK | Toilet Piping Installation / DW | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2205 | TT_TASK | Fire Riser Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2206 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2207 | TT_TASK | Controls Installation | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue Jun 08 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2210 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2211 | TT_TASK | Ligthing Installation | Sat Aug 07 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2213 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
2214 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2216 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2217 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2219 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2220 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
2223 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2224 | TT_TASK | Ligthing Installation | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2226 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
2227 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2229 | TT_TASK | Toilet Piping Installation / DW | Mon May 03 07:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2230 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2232 | TT_TASK | Fire Alarm System | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2233 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Fri Jul 09 08:12:00 IDT 2021 |  | COMPLETED
2236 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2237 | TT_TASK | Ligthing Installation | Wed Aug 04 07:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2239 | TT_TASK | AHU/DOAS Equipment Setting | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
2240 | TT_TASK | Hydronic Piping Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
2242 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2243 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2245 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2246 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2249 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Mar 31 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2250 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2251 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 | Mon Feb 22 00:00:00 IST 2021 |  | COMPLETED
2252 | TT_TASK | Power Bus Installation | Fri Mar 26 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 |  | COMPLETED
2253 | TT_TASK | PDU's Installation | Fri Mar 26 07:00:00 IDT 2021 | Mon Mar 29 17:00:00 IDT 2021 | Fri Mar 19 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
2254 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2255 | TT_TASK | Light Fixtures Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2256 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 02 07:00:00 IDT 2021 | Wed Jun 23 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
2258 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Jun 10 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2259 | TT_TASK | BMS Pull Wire / Term / Test | Thu Jun 10 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2260 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Jul 23 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2262 | TT_TASK | Fire Alarm System | Tue May 04 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2263 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2266 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2267 | TT_TASK | HAC Installation | Wed Feb 03 07:00:00 IST 2021 | Wed Feb 17 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Wed Feb 03 00:00:00 IST 2021 |  | COMPLETED
2268 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 | Mon Mar 08 00:00:00 IST 2021 |  | COMPLETED
2269 | TT_TASK | Power Bus Installation | Mon Mar 22 07:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2270 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2271 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Tue Jun 08 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2272 | TT_TASK | Light Fixtures Installation | Wed Jun 23 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 |  | COMPLETED
2273 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2275 | TT_TASK | EPMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 |  | COMPLETED
2276 | TT_TASK | BMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 |  | COMPLETED
2277 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon Aug 09 07:00:00 IDT 2021 | Wed Sep 01 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2279 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2280 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2283 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2284 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2285 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Mon Feb 08 00:00:00 IST 2021 | Tue Feb 23 00:00:00 IST 2021 |  | COMPLETED
2286 | TT_TASK | Power Bus Installation | Fri Mar 26 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2287 | TT_TASK | PDU's Installation | Mon Mar 22 07:00:00 IST 2021 | Wed Mar 24 17:00:00 IST 2021 | Fri Mar 19 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2288 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jun 03 07:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2289 | TT_TASK | Light Fixtures Installation | Fri Jun 18 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Jun 18 07:00:00 IDT 2021 | Thu Jul 01 00:00:00 IDT 2021 |  | COMPLETED
2290 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 02 07:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Wed Jun 02 00:00:00 IDT 2021 |  | COMPLETED
2292 | TT_TASK | EPMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2293 | TT_TASK | BMS Pull Wire / Term / Test | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2294 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Jul 30 07:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2296 | TT_TASK | Fire Alarm System | Mon May 10 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon May 10 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 |  | COMPLETED
2297 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2300 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Thu Apr 22 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Mar 22 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2301 | TT_TASK | HAC Installation | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
2302 | TT_TASK | Cable Tray Installation | Mon Mar 01 07:00:00 IST 2021 | Sat Mar 13 17:00:00 IST 2021 | Wed Feb 24 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2303 | TT_TASK | Power Bus Installation | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2304 | TT_TASK | PDU's Installation | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2305 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Jun 09 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed May 26 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2306 | TT_TASK | Light Fixtures Installation | Wed Jun 23 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2307 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Jun 08 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2309 | TT_TASK | EPMS Pull Wire / Term / Test | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2310 | TT_TASK | BMS Pull Wire / Term / Test | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2311 | TT_TASK | ` | Tue Aug 24 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Thu Aug 19 17:00:00 IDT 2021 |  | COMPLETED
2313 | TT_TASK | Fire Alarm System | Fri May 21 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 |  | COMPLETED
2314 | TT_TASK | Controls Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2319 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2320 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Tue Jan 26 00:00:00 IST 2021 |  | COMPLETED
2321 | TT_TASK | Hang drywall / Mud / Tape | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2323 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2326 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
2327 | TT_TASK | Overhead MEPFP Rough-In | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 21 07:00:00 IST 2020 | Wed Jan 06 17:00:00 IST 2021 |  | COMPLETED
2328 | TT_TASK | Hang drywall / Mud / Tape | Thu Jan 14 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2330 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2333 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Fri Dec 11 00:00:00 IST 2020 | Fri Dec 18 00:00:00 IST 2020 |  | COMPLETED
2334 | TT_TASK | Overhead MEPFP Rough-In | Mon Nov 16 07:00:00 IST 2020 | Mon Nov 30 17:00:00 IST 2020 | Wed Oct 28 00:00:00 IST 2020 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2335 | TT_TASK | Hang drywall / Mud / Tape | Fri Jan 08 07:00:00 IST 2021 | Mon Jan 18 17:00:00 IST 2021 | Tue Dec 22 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2337 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Wed Jan 06 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2340 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Sat Dec 19 00:00:00 IST 2020 | Thu Dec 24 00:00:00 IST 2020 |  | COMPLETED
2341 | TT_TASK | Overhead MEPFP Rough-In | Fri Jan 15 07:00:00 IST 2021 | Wed Jan 27 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2342 | TT_TASK | Hang drywall / Mud / Tape | Thu Jan 14 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
2344 | TT_TASK | Datahall Finishes | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 25 17:00:00 IST 2021 | Fri Jan 08 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2347 | TT_TASK | Remaining MER raceway across Mech chase | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2348 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
2349 | TT_TASK | OverHead MEPFP Rough-In | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 14 17:00:00 IST 2020 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2350 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Thu Jan 21 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Thu Jan 21 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 |  | COMPLETED
2352 | TT_TASK | Mechanical Corridor Finishes | Fri Mar 05 07:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2355 | TT_TASK | Remaining MER raceway across Mech chase | Thu Jun 17 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2356 | TT_TASK | Frame & Top out | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2357 | TT_TASK | OverHead MEPFP Rough-In | Wed Jan 13 07:00:00 IST 2021 | Wed Jan 27 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2358 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 | Thu Feb 11 00:00:00 IST 2021 |  | COMPLETED
2360 | TT_TASK | Mechanical Corridor Finishes | Wed Feb 03 07:00:00 IST 2021 | Wed Feb 24 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2363 | TT_TASK | Remaining MER raceway across Mech chase | Mon May 03 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2364 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Sat Dec 12 00:00:00 IST 2020 |  | COMPLETED
2365 | TT_TASK | OverHead MEPFP Rough-In | Tue Jan 12 07:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Mon Nov 23 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2366 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Thu Jan 28 00:00:00 IST 2021 |  | COMPLETED
2368 | TT_TASK | Mechanical Corridor Finishes | Tue Feb 02 07:00:00 IST 2021 | Tue Feb 23 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2371 | TT_TASK | Remaining MER raceway across Mech chase | Thu Jun 17 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
2372 | TT_TASK | Frame & Top out | Tue Jan 12 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2373 | TT_TASK | OverHead MEPFP Rough-In | Fri Jan 08 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Mon Dec 28 00:00:00 IST 2020 |  | COMPLETED
2374 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 05 17:00:00 IST 2021 | Mon Jan 25 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
2376 | TT_TASK | Mechanical Corridor Finishes | Tue Feb 23 07:00:00 IST 2021 | Tue Mar 16 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2380 | TT_TASK | Generator & Utility Power Pull | Wed May 19 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2381 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
2382 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2383 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 29 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
2384 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Sat Jan 02 07:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Mon Nov 30 00:00:00 IST 2020 |  | COMPLETED
2385 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2386 | TT_TASK | Lift & Set MER in Place | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 | Sat Apr 03 00:00:00 IDT 2021 |  | COMPLETED
2387 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Apr 26 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
2388 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon May 03 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Apr 05 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2389 | TT_TASK | GEN & UPM to MER Cable Bus Install | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2390 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2391 | TT_TASK | Generator & Utility Power Test-Term | Wed Jun 02 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Thu May 20 00:00:00 IDT 2021 | Mon May 31 00:00:00 IDT 2021 |  | COMPLETED
2393 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Wed Oct 21 00:00:00 IDT 2020 |  | COMPLETED
2394 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2395 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 30 00:00:00 IST 2020 |  | COMPLETED
2396 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2397 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2398 | TT_TASK | Set Exterior Water Treatment equipment | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 01 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2399 | TT_TASK | Mechanical Equipment Piping Connections | Fri Apr 30 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2402 | TT_TASK | Fire Alarm Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2403 | TT_TASK | Controls Installation | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2406 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Sat Jun 19 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2407 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
2408 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2409 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2410 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 02 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2411 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 15 08:00:00 IST 2021 | Mon Mar 22 08:00:00 IST 2021 | Fri Mar 05 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2412 | TT_TASK | Lift & Set MER in Place | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2413 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon May 17 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2414 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Fri May 07 07:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Fri Apr 16 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2415 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat Jun 05 00:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2416 | TT_TASK | Generator & Utility Power Test-Term | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2417 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Jun 08 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Tue Jun 08 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2419 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 24 00:00:00 IDT 2020 |  | COMPLETED
2420 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
2423 | TT_TASK | Fire Alarm Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Mon Jun 28 07:00:00 IDT 2021 | Thu Jul 15 07:00:00 IDT 2021 |  | COMPLETED
2424 | TT_TASK | Controls Installation | Tue Jun 29 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 29 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2427 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2428 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2429 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2430 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 08:00:00 IST 2021 | Tue Jan 12 08:00:00 IST 2021 | Fri Dec 18 00:00:00 IST 2020 | Sat Dec 19 00:00:00 IST 2020 |  | COMPLETED
2431 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Fri Nov 27 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2432 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
2433 | TT_TASK | Lift & Set MER in Place | Mon Apr 26 07:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 |  | COMPLETED
2434 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2435 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon May 03 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Sat Apr 10 00:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 |  | COMPLETED
2436 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Mon May 17 07:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Mon May 17 00:00:00 IDT 2021 |  | COMPLETED
2437 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Thu Jun 10 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2438 | TT_TASK | Generator & Utility Power Test-Term | Thu Jun 03 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
2440 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2441 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Nov 30 00:00:00 IST 2020 | Wed Dec 02 00:00:00 IST 2020 |  | COMPLETED
2442 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2443 | TT_TASK | Set Gen Stack / Exhaust duct | Mon Apr 26 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 | Tue Apr 06 00:00:00 IDT 2021 |  | COMPLETED
2444 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Thu Apr 08 00:00:00 IDT 2021 | Thu Apr 22 00:00:00 IDT 2021 |  | COMPLETED
2445 | TT_TASK | Set Exterior Water Treatment equipment | Mon Apr 26 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Fri Apr 09 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2446 | TT_TASK | Mechanical Equipment Piping Connections | Mon May 03 07:00:00 IDT 2021 | Sat May 08 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2449 | TT_TASK | Fire Alarm Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 |  | COMPLETED
2450 | TT_TASK | Controls Installation | Fri Jun 25 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2453 | TT_TASK | Generator & Utility Power Pull | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 04 17:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2454 | TT_TASK | Electrical Underground Rough-In | Tue Nov 17 07:00:00 IST 2020 | Thu Dec 03 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2455 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Fri Dec 04 00:00:00 IST 2020 | Wed Dec 09 00:00:00 IST 2020 |  | COMPLETED
2456 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2457 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Wed Dec 02 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2458 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Mar 01 07:00:00 IST 2021 | Fri Mar 05 17:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 | Fri Feb 26 00:00:00 IST 2021 |  | COMPLETED
2459 | TT_TASK | Lift & Set MER in Place | Fri May 07 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2460 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2461 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2462 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2463 | TT_TASK | Generator & Utility Power Test-Term | Tue Jul 06 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 | Thu Jul 15 12:00:00 IDT 2021 |  | COMPLETED
2464 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Sat Jun 05 07:00:00 IDT 2021 | Tue Jun 29 00:00:00 IDT 2021 |  | COMPLETED
2466 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Fri Dec 04 07:00:00 IST 2020 | Fri Dec 18 17:00:00 IST 2020 | Fri Oct 23 00:00:00 IDT 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
2467 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Thu Dec 03 00:00:00 IST 2020 | Fri Dec 11 00:00:00 IST 2020 |  | COMPLETED
2468 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Feb 01 07:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2469 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2470 | TT_TASK | Set Exterior Water Treatment equipment | Fri Apr 30 07:00:00 IDT 2021 | Mon May 03 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 |  | COMPLETED
2471 | TT_TASK | Set Gen Stack / Exhaust duct | Fri Apr 30 07:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 | Wed Apr 07 00:00:00 IDT 2021 |  | COMPLETED
2472 | TT_TASK | Mechanical Equipment Piping Connections | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2475 | TT_TASK | Fire Alarm Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jul 07 07:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2476 | TT_TASK | Controls Installation | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
2479 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2480 | TT_TASK | Ligthing Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2482 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
2483 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2485 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 00:00:00 IDT 2021 |  | COMPLETED
2486 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2488 | TT_TASK | Fire Riser Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2489 | TT_TASK | Fire Alarm System | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2490 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Tue May 25 00:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2493 | TT_TASK | VFD'S Installation & Wiring | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2494 | TT_TASK | Ligthing Installation | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
2496 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Tue Mar 23 00:00:00 IST 2021 |  | COMPLETED
2497 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2499 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2500 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2502 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2503 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2506 | TT_TASK | VFD'S Installation & Wiring | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2507 | TT_TASK | Ligthing Installation | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
2509 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 15 00:00:00 IST 2021 |  | COMPLETED
2510 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2512 | TT_TASK | Floor Drain System Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2513 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2515 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2516 | TT_TASK | Controls Installation | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
2519 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 16 07:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Wed Jun 16 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
2520 | TT_TASK | Ligthing Installation | Mon Aug 30 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2522 | TT_TASK | AHU/DOAS Equipment Setting | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Tue Mar 16 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
2523 | TT_TASK | Hydronic Piping Installation | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Apr 23 00:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 |  | COMPLETED
2525 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2526 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 16 00:00:00 IDT 2021 |  | COMPLETED
2528 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2529 | TT_TASK | Controls Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2532 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 |  | COMPLETED
2533 | TT_TASK | HAC Installation | Wed Mar 31 07:00:00 IDT 2021 | Fri Apr 02 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2534 | TT_TASK | Cable Tray Installation | Sat Apr 03 07:00:00 IDT 2021 | Sat Apr 17 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Mon Mar 22 00:00:00 IST 2021 |  | COMPLETED
2535 | TT_TASK | Power Bus Installation | Fri Apr 30 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2536 | TT_TASK | PDU's Installation | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2537 | TT_TASK | Pull/term/Test PDU to Power bus | Sat Jun 19 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2538 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
2539 | TT_TASK | Light Fixtures Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 |  | COMPLETED
2541 | TT_TASK | EPMS Pull Wire / Term / Test | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2542 | TT_TASK | BMS Pull Wire / Term / Test | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2543 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Aug 20 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Jul 07 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2545 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2546 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
2549 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2550 | TT_TASK | HAC Installation | Wed Apr 07 07:00:00 IDT 2021 | Fri Apr 09 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2551 | TT_TASK | Cable Tray Installation | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Mar 23 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2552 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
2553 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
2554 | TT_TASK | Pull/term/Test PDU to Power bus | Fri Jul 02 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Fri Jul 02 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
2555 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Mon Aug 16 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Thu Jul 08 00:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2556 | TT_TASK | Light Fixtures Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2558 | TT_TASK | EPMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2559 | TT_TASK | BMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2560 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2562 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2563 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2566 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 |  | COMPLETED
2567 | TT_TASK | HAC Installation | Sat Apr 03 07:00:00 IDT 2021 | Tue Apr 06 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2568 | TT_TASK | Cable Tray Installation | Wed Apr 07 07:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Thu Mar 11 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2569 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat May 08 00:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 |  | COMPLETED
2570 | TT_TASK | PDU's Installation | Fri May 07 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2571 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Sat Jul 24 00:00:00 IDT 2021 |  | COMPLETED
2572 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 23 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2573 | TT_TASK | Light Fixtures Installation | Wed Jul 21 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2575 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2576 | TT_TASK | BMS Pull Wire / Term / Test | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2577 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Fri Aug 20 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2579 | TT_TASK | Fire Alarm System | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2580 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2583 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2584 | TT_TASK | HAC Installation | Mon Apr 12 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2585 | TT_TASK | Cable Tray Installation | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Thu Mar 25 00:00:00 IST 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2586 | TT_TASK | Power Bus Installation | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Mon Apr 19 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
2587 | TT_TASK | PDU's Installation | Mon Jun 14 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Thu Apr 29 00:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 |  | COMPLETED
2588 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 | Mon Jul 12 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
2589 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2590 | TT_TASK | Light Fixtures Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2592 | TT_TASK | EPMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2593 | TT_TASK | BMS Pull Wire / Term / Test | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2594 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed Sep 15 07:00:00 IDT 2021 | Fri Oct 08 17:00:00 IDT 2021 | Sat Jul 17 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2596 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
2597 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
2602 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2603 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2604 | TT_TASK | Early Topout | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2606 | TT_TASK | Datahall Finishes | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
2609 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Jan 18 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2610 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2611 | TT_TASK | Early Topout | Mon Feb 01 07:00:00 IST 2021 | Wed Feb 03 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
2613 | TT_TASK | Datahall Finishes | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2616 | TT_TASK | Frame wall & MEPFP In wall roughin | Sat Jan 02 07:00:00 IST 2021 | Thu Jan 07 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2617 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2618 | TT_TASK | Early Topout | Tue Feb 09 07:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Thu Jan 14 00:00:00 IST 2021 |  | COMPLETED
2620 | TT_TASK | Datahall Finishes | Wed Mar 31 07:00:00 IDT 2021 | Wed Apr 14 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Sat Feb 27 00:00:00 IST 2021 |  | COMPLETED
2623 | TT_TASK | Frame wall & MEPFP In wall roughin | Mon Jan 18 07:00:00 IST 2021 | Fri Jan 22 17:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 |  | COMPLETED
2624 | TT_TASK | Overhead MEPFP Rough-In | Mon Feb 01 07:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Fri Jan 15 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2625 | TT_TASK | Early Topout | Mon Feb 08 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Thu Jan 21 00:00:00 IST 2021 |  | COMPLETED
2627 | TT_TASK | Datahall Finishes | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Mon Mar 01 00:00:00 IST 2021 |  | COMPLETED
2630 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 18 00:00:00 IDT 2021 |  | COMPLETED
2631 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Fri Jan 08 00:00:00 IST 2021 |  | COMPLETED
2632 | TT_TASK | OverHead MEPFP Rough-In | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Feb 19 00:00:00 IST 2021 | Sat Mar 06 00:00:00 IST 2021 |  | COMPLETED
2633 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 15 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Tue Feb 16 00:00:00 IST 2021 | Thu Feb 18 00:00:00 IST 2021 |  | COMPLETED
2635 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Sat Jan 09 00:00:00 IST 2021 | Mon Feb 01 00:00:00 IST 2021 |  | COMPLETED
2638 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 |  | COMPLETED
2639 | TT_TASK | Frame & Top out | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Sat Jan 09 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
2640 | TT_TASK | OverHead MEPFP Rough-In | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2641 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Tue Mar 30 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Thu Feb 18 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2643 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 29 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Thu Jan 21 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
2646 | TT_TASK | Remaining MER raceway across Mech chase | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 |  | COMPLETED
2647 | TT_TASK | Frame & Top out | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 28 00:00:00 IST 2020 | Tue Feb 02 00:00:00 IST 2021 |  | COMPLETED
2648 | TT_TASK | OverHead MEPFP Rough-In | Fri Apr 30 07:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Feb 05 00:00:00 IST 2021 | Sat Feb 20 00:00:00 IST 2021 |  | COMPLETED
2649 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Mon Mar 15 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 | Thu Feb 04 00:00:00 IST 2021 |  | COMPLETED
2651 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 15 07:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Thu Feb 25 00:00:00 IST 2021 |  | COMPLETED
2654 | TT_TASK | Remaining MER raceway across Mech chase | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
2655 | TT_TASK | Frame & Top out | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 08 17:00:00 IDT 2021 | Wed Feb 03 00:00:00 IST 2021 | Sat Feb 13 00:00:00 IST 2021 |  | COMPLETED
2656 | TT_TASK | OverHead MEPFP Rough-In | Sat May 15 07:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 00:00:00 IST 2021 | Tue Mar 09 00:00:00 IST 2021 |  | COMPLETED
2657 | TT_TASK | Electrical surface mounted Rough-in Above AHU | Tue Mar 30 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Fri Feb 12 00:00:00 IST 2021 | Fri Feb 19 00:00:00 IST 2021 |  | COMPLETED
2659 | TT_TASK | Mechanical Corridor Finishes | Thu Apr 29 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2663 | TT_TASK | Generator & Utility Power Pull | Wed Jul 28 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Sat Jun 26 00:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2664 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2665 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2666 | TT_TASK | Set Electrical Equipment-UPM | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Wed Dec 30 00:00:00 IST 2020 | Thu Dec 31 00:00:00 IST 2020 |  | COMPLETED
2667 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2668 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Apr 26 08:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2669 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 |  | COMPLETED
2670 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2671 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue Apr 27 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2672 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Fri Jun 25 00:00:00 IDT 2021 |  | COMPLETED
2673 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2674 | TT_TASK | Generator & Utility Power Test-Term | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Wed Jul 28 17:00:00 IDT 2021 |  | COMPLETED
2676 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 12 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2677 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2678 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2679 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Feb 15 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2680 | TT_TASK | Set Exterior Water Treatment equipment | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 01 17:00:00 IDT 2021 | Wed Mar 03 00:00:00 IST 2021 | Wed Mar 03 00:00:00 IST 2021 |  | COMPLETED
2681 | TT_TASK | Mechanical Equipment Piping Connections | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2682 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2685 | TT_TASK | Fire Alarm Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
2686 | TT_TASK | Controls Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2689 | TT_TASK | Generator & Utility Power Pull | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Mon Jul 19 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
2690 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2691 | TT_TASK | Exterior Equipment Pads - for UPM's | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Tue Dec 01 00:00:00 IST 2020 | Fri Dec 04 00:00:00 IST 2020 |  | COMPLETED
2692 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2693 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 07 00:00:00 IST 2020 | Thu Dec 10 00:00:00 IST 2020 |  | COMPLETED
2694 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Mon Apr 26 08:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2695 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2696 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2697 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
2698 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sat Jul 10 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2699 | TT_TASK | Generator & Utility Power Test-Term | Fri Jul 16 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jul 28 07:00:00 IDT 2021 | Sat Aug 07 17:00:00 IDT 2021 |  | COMPLETED
2700 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2702 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 19 00:00:00 IDT 2020 | Fri Oct 23 00:00:00 IDT 2020 |  | COMPLETED
2703 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 09 07:00:00 IST 2021 | Sat Jan 23 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2704 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2705 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Thu Apr 01 00:00:00 IDT 2021 | Wed Apr 14 00:00:00 IDT 2021 |  | COMPLETED
2706 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2707 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2708 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2711 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
2712 | TT_TASK | Controls Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Tue Aug 17 07:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
2715 | TT_TASK | Generator & Utility Power Pull | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 | Thu Aug 05 09:30:00 IDT 2021 |  | COMPLETED
2716 | TT_TASK | Electrical Underground Rough-In | Mon Nov 02 07:00:00 IST 2020 | Mon Nov 16 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2717 | TT_TASK | Exterior Equipment Pads - for UPM's | Sat Jan 02 07:00:00 IST 2021 | Wed Jan 06 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2718 | TT_TASK | Set Electrical Equipment-UPM | Mon Jan 11 07:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 |  | COMPLETED
2719 | TT_TASK | Exterior Equipment Pads - Electrical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2720 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2721 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2722 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Thu May 06 00:00:00 IDT 2021 |  | COMPLETED
2723 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2724 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu Jul 15 00:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2725 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2726 | TT_TASK | Generator & Utility Power Test-Term | Fri Sep 03 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
2728 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Mon Nov 09 07:00:00 IST 2020 | Mon Nov 23 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2729 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2730 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2731 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2732 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2733 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2734 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Fri Apr 02 00:00:00 IDT 2021 |  | COMPLETED
2737 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2738 | TT_TASK | Controls Installation | Wed Sep 01 07:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Thu Aug 26 07:00:00 IDT 2021 |  | 1210.0 | IN_PROGRESS
2741 | TT_TASK | Generator & Utility Power Pull | Fri Aug 06 07:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Thu Jul 29 00:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
2742 | TT_TASK | Electrical Underground Rough-In | Sat Nov 07 07:00:00 IST 2020 | Sat Nov 21 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2743 | TT_TASK | Exterior Equipment Pads - for UPM's | Thu Jan 07 07:00:00 IST 2021 | Mon Jan 11 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2744 | TT_TASK | Set Electrical Equipment-UPM | Mon Mar 01 07:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Thu Jan 07 00:00:00 IST 2021 |  | COMPLETED
2745 | TT_TASK | Exterior Equipment Pads - Electrical | Mon Jan 18 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2746 | TT_TASK | Set Exterior Electrical OFCI Equipment - GEN | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 05 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2747 | TT_TASK | Lift & Set MER in Place | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2748 | TT_TASK | Steel Support for OH Conductors & Cable Tray Installation | Mon Jun 07 07:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2749 | TT_TASK | Assemble MER & Complete Shipping Split (SE) | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
2750 | TT_TASK | GEN & UPM to MER Cable Bus Instal | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Fri Jul 16 07:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2751 | TT_TASK | Generator & Utility Power Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2752 | TT_TASK | Electrical Feeders to Mechanical Equipment Pull-Test-Term | Tue Aug 31 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 |  | COMPLETED
2754 | TT_TASK | Mechanical/Plumbing Underground Rough-In | Tue Nov 24 07:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Mon Oct 26 00:00:00 IST 2020 | Sat Nov 07 00:00:00 IST 2020 |  | COMPLETED
2755 | TT_TASK | Exterior Equipment Pads - Mechanical | Sat Jan 02 07:00:00 IST 2021 | Fri Jan 15 17:00:00 IST 2021 | Mon Dec 14 00:00:00 IST 2020 | Wed Dec 16 00:00:00 IST 2020 |  | COMPLETED
2756 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Feb 01 00:00:00 IST 2021 | Fri Feb 05 00:00:00 IST 2021 |  | COMPLETED
2757 | TT_TASK | Set Exterior Mechanical OFCI Equipment (FC / WTE / Pumps) | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 |  | COMPLETED
2758 | TT_TASK | Set Exterior Water Treatment equipment | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 |  | COMPLETED
2759 | TT_TASK | Mechanical Equipment Piping Connections | Fri Jul 02 07:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
2760 | TT_TASK | Set Gen Stack / Exhaust duct | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2763 | TT_TASK | Fire Alarm Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
2764 | TT_TASK | Controls Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
2767 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2768 | TT_TASK | Ligthing Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2770 | TT_TASK | AHU/DOAS Equipment Setting | Sat May 15 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed Mar 10 00:00:00 IST 2021 | Wed Mar 10 00:00:00 IST 2021 |  | COMPLETED
2771 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2773 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2774 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2776 | TT_TASK | Fire Riser Installation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Wed May 19 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2777 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2778 | TT_TASK | Controls Installation | Sat Jul 31 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2781 | TT_TASK | VFD'S Installation & Wiring | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
2782 | TT_TASK | Ligthing Installation | Thu Sep 16 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
2784 | TT_TASK | AHU/DOAS Equipment Setting | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Thu Mar 18 00:00:00 IST 2021 | Thu Mar 18 00:00:00 IST 2021 |  | COMPLETED
2785 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2787 | TT_TASK | Floor Drain System Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2788 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2790 | TT_TASK | Fire Alarm System | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2791 | TT_TASK | Controls Installation | Mon Aug 23 07:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2794 | TT_TASK | VFD'S Installation & Wiring | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
2795 | TT_TASK | Lighting Installation | Sat Sep 11 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Mon Aug 16 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 |  | COMPLETED
2797 | TT_TASK | AHU/DOAS Equipment Setting | Sat May 15 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Wed Mar 17 00:00:00 IST 2021 | Wed Mar 17 00:00:00 IST 2021 |  | COMPLETED
2798 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2800 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2801 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2803 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2804 | TT_TASK | Controls Installation | Mon Aug 16 07:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 |  | COMPLETED
2807 | TT_TASK | VFD'S Installation & Wiring | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2808 | TT_TASK | Ligthing Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
2810 | TT_TASK | AHU/DOAS Equipment Setting | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sat Mar 20 00:00:00 IST 2021 | Sat Mar 20 00:00:00 IST 2021 |  | COMPLETED
2811 | TT_TASK | Hydronic Piping Installation | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 |  | COMPLETED
2813 | TT_TASK | Floor Drain System Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2814 | TT_TASK | Toilet Piping Installation / DW | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
2816 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2817 | TT_TASK | Controls Installation | Wed Sep 08 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2820 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 09 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2821 | TT_TASK | HAC Installation | Thu Apr 15 07:00:00 IDT 2021 | Wed Apr 28 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2822 | TT_TASK | Cable Tray Installation | Tue May 04 07:00:00 IDT 2021 | Mon May 17 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2823 | TT_TASK | Power Bus Installation | Mon Jun 07 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
2824 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2825 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 27 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2826 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Aug 25 07:00:00 IDT 2021 | Sat Sep 18 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2827 | TT_TASK | Light Fixtures Installation | Sat Aug 21 07:00:00 IDT 2021 | Fri Aug 27 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
2829 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2830 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
2831 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Mon Sep 27 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2833 | TT_TASK | Fire Alarm System | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2834 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Tue Jul 20 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2837 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 16 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2838 | TT_TASK | HAC Installation | Thu Apr 29 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2839 | TT_TASK | Cable Tray Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Apr 21 00:00:00 IDT 2021 | Tue May 04 00:00:00 IDT 2021 |  | COMPLETED
2840 | TT_TASK | Power Bus Installation | Tue Jun 01 07:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Wed Jun 23 07:00:00 IDT 2021 |  | COMPLETED
2841 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Fri Jun 25 07:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2842 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Fri Sep 03 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2843 | TT_TASK | Pull/term/Test PDU to Power bus | Fri Sep 03 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  |  | 210.0 | NOT_STARTED
2844 | TT_TASK | Light Fixtures Installation | Fri Oct 01 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2846 | TT_TASK | EPMS Pull Wire / Term / Test | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2847 | TT_TASK | BMS Pull Wire / Term / Test | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
2848 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Thu Oct 21 07:00:00 IDT 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  | 801.0 | NOT_STARTED
2850 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2851 | TT_TASK | Controls Installation | Tue Sep 14 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Thu Aug 12 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2854 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 16 07:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 | Fri May 21 00:00:00 IDT 2021 |  | COMPLETED
2855 | TT_TASK | HAC Installation | Thu Apr 29 07:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2856 | TT_TASK | Cable Tray Installation | Thu May 06 07:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Mon Apr 12 00:00:00 IDT 2021 | Sat Apr 24 00:00:00 IDT 2021 |  | COMPLETED
2857 | TT_TASK | Power Bus Installation | Mon Jun 14 07:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
2858 | TT_TASK | PDU's Installation | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2859 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Sep 01 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2860 | TT_TASK | Pull/term/Test PDU to Power bus | Wed Aug 25 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Thu Jul 29 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2861 | TT_TASK | Light Fixtures Installation | Mon Aug 30 07:00:00 IDT 2021 | Tue Sep 07 08:00:00 IDT 2021 | Mon Aug 30 07:00:00 IDT 2021 |  | 89.0 | IN_PROGRESS
2863 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2864 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 170.0 | NOT_STARTED
2865 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Sat Oct 09 07:00:00 IDT 2021 | Tue Nov 02 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2867 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2868 | TT_TASK | Controls Installation | Mon Jun 14 07:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Mon Jun 14 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
2871 | TT_TASK | Below Ceiling Branch Conduit Rough-in | Fri Jul 23 07:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 |  | COMPLETED
2872 | TT_TASK | HAC Installation | Fri May 07 07:00:00 IDT 2021 | Thu May 20 17:00:00 IDT 2021 | Tue Mar 09 00:00:00 IST 2021 | Fri Mar 26 00:00:00 IST 2021 |  | COMPLETED
2873 | TT_TASK | Cable Tray Installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2874 | TT_TASK | Power Bus Installation | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Thu Jun 24 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2875 | TT_TASK | PDU's Installation | Mon Jun 07 07:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Wed Jul 14 00:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
2876 | TT_TASK | Pull / Term / Test Conductors ( MER to PDU) | Wed Sep 01 07:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 25 00:00:00 IDT 2021 |  |  | IN_PROGRESS
2877 | TT_TASK | Pull/term/Test PDU to Power bus | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 22 17:00:00 IDT 2021 | Wed Aug 25 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2878 | TT_TASK | Light Fixtures Installation | Tue Aug 31 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
2880 | TT_TASK | EPMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2881 | TT_TASK | BMS Pull Wire / Term / Test | Thu Sep 02 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 300.0 | NOT_STARTED
2882 | TT_TASK | Install/Dress/Test Production Fiber (Includes MOR rack set & Fiber runner) | Wed Nov 03 07:00:00 IST 2021 | Tue Nov 30 17:00:00 IST 2021 |  |  | 691.0 | NOT_STARTED
2884 | TT_TASK | Fire Alarm System | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2885 | TT_TASK | Controls Installation | Mon Jun 28 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jul 27 00:00:00 IDT 2021 | Tue Aug 24 13:00:00 IDT 2021 |  | COMPLETED
2889 | TT_TASK | ATS Equipment Yellow Tagging (S2 from MER) | Mon May 17 07:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 |  | COMPLETED
2890 | TT_TASK | Control Power Available | Fri Apr 30 07:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Fri Apr 30 07:00:00 IDT 2021 | Fri May 28 00:00:00 IDT 2021 |  | COMPLETED
2891 | TT_TASK | Power available for Start up | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
2892 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2893 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 |  | COMPLETED
2895 | TT_TASK | Admin - NETA test validation Inpections- VECA-EPS-RTS Admin | Mon Mar 01 07:00:00 IST 2021 | Wed Mar 03 17:00:00 IST 2021 | Thu Mar 11 00:00:00 IST 2021 | Fri Mar 12 00:00:00 IST 2021 |  | COMPLETED
2896 | TT_TASK | Electrical Equipment Yellow Tagging | Mon Apr 26 07:00:00 IDT 2021 | Mon May 10 17:00:00 IDT 2021 | Wed Apr 28 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2897 | TT_TASK | Admin/Colo-1 Network Startup | Mon May 17 07:00:00 IDT 2021 | Mon May 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri May 07 00:00:00 IDT 2021 |  | COMPLETED
2898 | TT_TASK | EPMS Checkout / Point to Point | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2902 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2903 | TT_TASK | UPM Yellow tagging - Admin & COLO-1 CELL-1 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2904 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
2905 | TT_TASK | SE- Completed L2 QC Checklist | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 |  | COMPLETED
2906 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-1 | Sat Apr 17 07:00:00 IDT 2021 | Tue Apr 20 17:00:00 IDT 2021 | Mon Mar 15 00:00:00 IST 2021 | Wed Mar 24 00:00:00 IST 2021 |  | COMPLETED
2907 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jun 01 07:00:00 IDT 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2908 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2909 | TT_TASK | Network Startup | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 |  | COMPLETED
2910 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2911 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2912 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2914 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2915 | TT_TASK | Power available for Start up | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2916 | TT_TASK | SE- Completed L2 QC Checklist | Mon Jun 14 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
2917 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Jul 13 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2918 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-3 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2919 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-3 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Wed May 12 00:00:00 IDT 2021 | Fri May 14 00:00:00 IDT 2021 |  | COMPLETED
2920 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Thu Jun 10 07:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Sat May 29 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2921 | TT_TASK | Network Startup | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 |  | COMPLETED
2922 | TT_TASK | EPMS Checkout / Point to Point | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jul 06 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2923 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2924 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2926 | TT_TASK | Control Power Available | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 22 00:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2927 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2928 | TT_TASK | SE- Completed L2 QC Checklist | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Thu Jun 17 00:00:00 IDT 2021 |  | COMPLETED
2929 | TT_TASK | Mechanical Equipment Yellow Tag | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Fri Jun 11 00:00:00 IDT 2021 |  | COMPLETED
2930 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-2 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2931 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-2 | Tue Jun 01 07:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Mon May 03 00:00:00 IDT 2021 | Wed May 05 00:00:00 IDT 2021 |  | COMPLETED
2932 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jun 01 07:00:00 IDT 2021 | Fri Jun 11 17:00:00 IDT 2021 | Wed May 19 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2933 | TT_TASK | Network Startup | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2934 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2935 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
2936 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Tue Jul 06 07:00:00 IDT 2021 | Tue Jul 20 15:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2938 | TT_TASK | Control Power Available | Tue Jun 22 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue Jun 22 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
2939 | TT_TASK | Power available for Start up | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
2940 | TT_TASK | SE- Completed L2 QC Checklist | Mon Jun 14 07:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Wed Jun 23 00:00:00 IDT 2021 |  | COMPLETED
2941 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Jul 02 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Mon Jun 14 00:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
2942 | TT_TASK | UPM Yellow tagging - COLO-1 CELL-4 | Wed Mar 31 07:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Thu Apr 15 00:00:00 IDT 2021 |  | COMPLETED
2943 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-1 Cell-4 | Wed Jun 30 07:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Thu Jun 03 00:00:00 IDT 2021 |  | COMPLETED
2944 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Jul 07 07:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Jun 21 00:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
2945 | TT_TASK | Network Startup | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2946 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Mon Jul 26 15:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 |  | COMPLETED
2947 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
2948 | TT_TASK | EPMS Checkout / Point to Point | Tue Jul 06 07:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
2950 | TT_TASK | GEN SCR testing and Burnins | Wed Jul 14 07:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jul 14 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
2951 | TT_TASK | Admin GEN SCR testing and Burnins | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
2952 | TT_TASK | ATS- Lvl 3 Testing & Start up (Electrical Equipment) | Sat Jul 10 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Jul 10 07:00:00 IDT 2021 |  | 100.0 | IN_PROGRESS
2953 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Tue Jul 13 11:00:00 IDT 2021 | Wed Jul 28 11:00:00 IDT 2021 | Tue Jul 13 11:00:00 IDT 2021 | Wed Jul 28 11:00:00 IDT 2021 |  | COMPLETED
2954 | TT_TASK | Cooling Automation | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2955 | TT_TASK | BAS Prefunctional Testing on Construction Server | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 | Sat Aug 28 00:00:00 IDT 2021 |  | COMPLETED
2956 | TT_TASK | Additional Go-Back loadbanking (ASCO) | Fri Sep 10 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2957 | TT_TASK | Load Bank & IR Scan | Wed Sep 15 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2958 | TT_TASK | Level 3 Cx - ADMIN AND COLO1 | Fri Sep 17 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2959 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Sat Oct 02 07:00:00 IDT 2021 | Sat Oct 02 07:00:00 IDT 2021 |  |  |  | NOT_STARTED
2961 | TT_TASK | COLO 1 Level 4 & Level 5 IST | Sat Oct 02 08:00:00 IDT 2021 | Fri Oct 29 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2962 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Sat Oct 30 08:00:00 IDT 2021 | Mon Nov 08 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2963 | TT_TASK | Security Commissioning (level3 DCPS) | Tue Nov 09 08:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2964 | TT_TASK | Punch List - Admin/COLO 1 | Sat Oct 30 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2965 | TT_TASK | MST Ready for Network Install | Sat Oct 02 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2966 | TT_TASK | Final Clean/ ready for lock down | Sat Nov 13 07:00:00 IST 2021 | Mon Nov 22 17:00:00 IST 2021 |  |  |  | NOT_STARTED
2970 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 18 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2971 | TT_TASK | Power available for Start up | Sat Sep 11 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2972 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 09 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2973 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  | 20.0 | IN_PROGRESS
2974 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-1 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 04 17:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2975 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-1 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2976 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Aug 04 07:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Wed Jul 21 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2977 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2978 | TT_TASK | EPMS Checkout / Point to Point | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 200.0 | NOT_STARTED
2979 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Thu Sep 16 07:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 |  |  | 20.0 | NOT_STARTED
2980 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Thu Sep 16 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  | 50.0 | NOT_STARTED
2982 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2983 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2984 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2985 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2986 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-3 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Fri Jul 30 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2987 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-3 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
2988 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 | Thu Aug 05 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2989 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2990 | TT_TASK | EPMS Checkout / Point to Point | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
2991 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2992 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2994 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2995 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
2996 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
2997 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
2998 | TT_TASK | UPM Yellow tagging - COLO-2 CELL-2 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
2999 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-2 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
3000 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Jul 13 07:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3001 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3002 | TT_TASK | EPMS Checkout / Point to Point | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3003 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3004 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Wed Sep 22 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3006 | TT_TASK | Control Power Available | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3007 | TT_TASK | Power available for Start up | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3008 | TT_TASK | SE- Completed L2 QC Checklist | Wed Jul 14 07:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 |  | COMPLETED
3009 | TT_TASK | Mechanical Equipment Yellow Tag | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 01 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3010 | TT_TASK | UPM Yellow tagging -COLO-2 CELL-4 | Wed Jun 30 07:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
3011 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-2 Cell-4 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Tue Jul 27 07:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
3012 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Aug 18 07:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Mon Jul 26 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3013 | TT_TASK | Network Startup | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3014 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3015 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3016 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Sat Sep 18 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  | 30.0 | NOT_STARTED
3018 | TT_TASK | GEN SCR testing and Burnins | Sat Sep 18 07:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  |  | 150.0 | NOT_STARTED
3019 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Mon Sep 27 07:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3020 | TT_TASK | Cooling Automation | Mon Oct 11 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3021 | TT_TASK | BAS Prefunctional Testing on Construction Server | Thu Oct 07 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3022 | TT_TASK | Load Bank & IR Scan | Tue Oct 26 07:00:00 IDT 2021 | Tue Nov 16 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3023 | TT_TASK | Level 3 Cx- COLO-2 | Wed Nov 17 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3024 | TT_TASK | Weather (5 Days) - 0 remaining Check Delay #14 for updates | Sat Dec 04 07:00:00 IST 2021 | Sat Dec 04 07:00:00 IST 2021 |  |  |  | NOT_STARTED
3026 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Mon Dec 27 07:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3027 | TT_TASK | Security Commissioning (level3 DCPS) | Tue Jan 11 07:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3028 | TT_TASK | COLO 2 Level 4 & Level 5 IST | Sat Dec 04 08:00:00 IST 2021 | Fri Dec 24 17:00:00 IST 2021 |  |  | 16.0 | NOT_STARTED
3029 | TT_TASK | Punch List COLO-2 | Mon Dec 27 08:00:00 IST 2021 | Sun Jan 09 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3030 | TT_TASK | MST Ready for Network Install | Sat Dec 04 07:00:00 IST 2021 | Thu Dec 09 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3031 | TT_TASK | Final Clean/ ready for lock down | Mon Jan 10 08:00:00 IST 2022 | Fri Jan 21 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3035 | TT_TASK | Control Power Available | Thu Sep 09 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3036 | TT_TASK | Power available for Start up | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3037 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 06 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3038 | TT_TASK | Mechanical Equipment Yellow Tag | Wed Sep 22 07:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3039 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-1 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3040 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-1 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3041 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3042 | TT_TASK | Network Startup | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3043 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3044 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3045 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Tue Oct 05 07:00:00 IDT 2021 | Tue Oct 19 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3047 | TT_TASK | Control Power Available | Tue Sep 21 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3048 | TT_TASK | Power available for Start up | Mon Oct 04 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3049 | TT_TASK | SE- Completed L2 QC Checklist | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3050 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Oct 05 07:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3051 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-3 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 160.0 | NOT_STARTED
3052 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-3 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3053 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3054 | TT_TASK | Network Startup | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3055 | TT_TASK | EPMS Checkout / Point to Point | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3056 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3057 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Oct 18 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3059 | TT_TASK | Control Power Available | Thu Sep 09 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3060 | TT_TASK | Power available for Start up | Tue Sep 21 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3061 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 10 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3062 | TT_TASK | Mechanical Equipment Yellow Tag | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3063 | TT_TASK | UPM Yellow tagging -COLO-3 CELL-2 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3064 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-2 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3065 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Fri Aug 13 07:00:00 IDT 2021 | Wed Aug 25 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3066 | TT_TASK | Network Startup | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3067 | TT_TASK | EPMS Checkout / Point to Point | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3068 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3069 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Sep 27 07:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  |  | 170.0 | NOT_STARTED
3071 | TT_TASK | Control Power Available | Tue Sep 21 07:00:00 IDT 2021 | Sat Oct 02 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3072 | TT_TASK | Power available for Start up | Mon Oct 04 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3073 | TT_TASK | SE- Completed L2 QC Checklist | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3074 | TT_TASK | Mechanical Equipment Yellow Tag | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3075 | TT_TASK | UPM Yellow tagging COLO-3 CELL-4 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 |  |  | 160.0 | NOT_STARTED
3076 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-3 Cell-4 | Tue Aug 31 07:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
3077 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Sep 14 07:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3078 | TT_TASK | Network Startup | Mon Sep 27 07:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3079 | TT_TASK | EPMS Checkout / Point to Point | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 60.0 | NOT_STARTED
3080 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3081 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Oct 08 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  |  | 70.0 | NOT_STARTED
3083 | TT_TASK | GEN SCR testing and Burnins | Fri Oct 08 07:00:00 IDT 2021 | Tue Oct 26 17:00:00 IDT 2021 |  |  | 320.0 | NOT_STARTED
3084 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Fri Oct 22 07:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3085 | TT_TASK | Cooling Automation | Fri Nov 05 07:00:00 IST 2021 | Fri Nov 19 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3086 | TT_TASK | BAS Prefunctional Testing on Construction Server | Mon Nov 01 07:00:00 IST 2021 | Wed Nov 24 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3087 | TT_TASK | Load Bank & IR Scan | Wed Dec 08 07:00:00 IST 2021 | Mon Jan 03 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3088 | TT_TASK | Level 3 Cx- COLO-3 | Tue Jan 04 07:00:00 IST 2022 | Tue Jan 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3089 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Wed Jan 19 07:00:00 IST 2022 | Wed Jan 19 07:00:00 IST 2022 |  |  |  | NOT_STARTED
3091 | TT_TASK | COLO 3 Level 4 & Level 5 IST | Wed Jan 19 08:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3092 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Wed Feb 09 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3093 | TT_TASK | Security Commissioning (level3 DCPS) | Sat Feb 19 08:00:00 IST 2022 | Wed Feb 23 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3094 | TT_TASK | Punch List COLO-3 | Wed Feb 09 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3095 | TT_TASK | MST Ready for Network Install | Wed Jan 19 08:00:00 IST 2022 | Tue Jan 25 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3096 | TT_TASK | Final Clean/ ready for lock down | Wed Feb 23 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3100 | TT_TASK | Control Power Available | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3101 | TT_TASK | Power available for Start up | Tue Nov 02 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3102 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3103 | TT_TASK | Mechanical Equipment Yellow Tag | Mon Oct 18 07:00:00 IDT 2021 | Thu Oct 28 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3104 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-1 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
3105 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-1 | Fri Sep 17 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
3106 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3107 | TT_TASK | Network Startup | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3108 | TT_TASK | EPMS Checkout / Point to Point | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  | 40.0 | NOT_STARTED
3109 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3110 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3112 | TT_TASK | Control Power Available | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3113 | TT_TASK | Power available for Start up | Mon Nov 15 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3114 | TT_TASK | SE- Completed L2 QC Checklist | Sat Oct 23 07:00:00 IDT 2021 | Wed Nov 03 17:00:00 IST 2021 |  |  | 20.0 | NOT_STARTED
3115 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Oct 29 07:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 |  |  | 70.0 | NOT_STARTED
3116 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-3 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Wed Aug 04 07:00:00 IDT 2021 | Mon Aug 16 00:00:00 IDT 2021 |  | COMPLETED
3117 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-3 | Tue Sep 28 07:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  |  | 200.0 | NOT_STARTED
3118 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3119 | TT_TASK | Network Startup | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3120 | TT_TASK | EPMS Checkout / Point to Point | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3121 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3122 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3124 | TT_TASK | Control Power Available | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3125 | TT_TASK | Power available for Start up | Tue Nov 02 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3126 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3127 | TT_TASK | Mechanical Equipment Yellow Tag | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3128 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-2 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Fri Aug 13 07:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3129 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-2 | Fri Sep 17 07:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 |  |  | 180.0 | NOT_STARTED
3130 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  |  | NOT_STARTED
3131 | TT_TASK | Network Startup | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3132 | TT_TASK | EPMS Checkout / Point to Point | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3133 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3134 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  |  | 100.0 | NOT_STARTED
3136 | TT_TASK | Control Power Available | Tue Nov 02 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3137 | TT_TASK | Power available for Start up | Mon Nov 15 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3138 | TT_TASK | SE- Completed L2 QC Checklist | Wed Oct 13 07:00:00 IDT 2021 | Mon Oct 25 17:00:00 IDT 2021 |  |  | 100.0 | NOT_STARTED
3139 | TT_TASK | Mechanical Equipment Yellow Tag | Thu Oct 21 07:00:00 IDT 2021 | Mon Nov 01 17:00:00 IST 2021 |  |  | 140.0 | NOT_STARTED
3140 | TT_TASK | UPM Yellow tagging -COLO-4 CELL-4 | Tue Aug 31 07:00:00 IDT 2021 | Mon Sep 13 17:00:00 IDT 2021 | Tue Aug 24 07:00:00 IDT 2021 |  |  | IN_PROGRESS
3141 | TT_TASK | NETA test validation Inpections- VECA-EPS-RTS COLO-4 Cell-4 | Sat Sep 18 07:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 |  |  | 270.0 | NOT_STARTED
3142 | TT_TASK | Electrical Equipment Yellow Tagging (Field Terminated equipment) | Tue Oct 26 07:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3143 | TT_TASK | Network Startup | Mon Nov 08 07:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3144 | TT_TASK | EPMS Checkout / Point to Point | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3145 | TT_TASK | OFCI Lvl 3 Testing & Start up (Electrical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3146 | TT_TASK | OFCI Lvl 3 Testing & Start up (Mechanical Equipment) | Fri Nov 19 07:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3148 | TT_TASK | GEN SCR testing and Burnins | Fri Nov 19 07:00:00 IST 2021 | Thu Dec 09 17:00:00 IST 2021 |  |  | 310.0 | NOT_STARTED
3149 | TT_TASK | Hydronic Pipe Flush (Open and closed Loop) | Tue Nov 30 07:00:00 IST 2021 | Mon Dec 13 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3150 | TT_TASK | Cooling Automation | Tue Dec 14 07:00:00 IST 2021 | Thu Dec 30 17:00:00 IST 2021 |  |  |  | NOT_STARTED
3151 | TT_TASK | BAS Prefunctional Testing on Construction Server | Tue Dec 07 07:00:00 IST 2021 | Tue Jan 04 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3152 | TT_TASK | Load Bank & IR Scan | Sat Jan 22 07:00:00 IST 2022 | Sat Feb 12 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3153 | TT_TASK | Level 3 Cx - COLO-4 | Mon Feb 14 07:00:00 IST 2022 | Sat Feb 26 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3154 | TT_TASK | Weather (5 Days) - 3 remaining Check Delay #14 for updates | Mon Feb 28 07:00:00 IST 2022 | Mon Feb 28 07:00:00 IST 2022 |  |  |  | NOT_STARTED
3156 | TT_TASK | COLO 4 Level 4 & Level 5 IST | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 20 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3157 | TT_TASK | Security Commissioning (level2 with Corp net after IST) | Mon Mar 21 08:00:00 IST 2022 | Wed Mar 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3158 | TT_TASK | Security Commissioning (level3 DCPS) | Thu Mar 31 08:00:00 IDT 2022 | Mon Apr 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3159 | TT_TASK | Punch List COLO-4 | Mon Mar 21 08:00:00 IST 2022 | Sat Apr 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3160 | TT_TASK | MST Ready for Network Install | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3161 | TT_TASK | Final Clean/ ready for lock down | Sun Apr 03 08:00:00 IDT 2022 | Wed Apr 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3163 | TT_TASK | CSA Punchlist - COLO-1 | Sat Jul 31 07:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Mon Jul 26 00:00:00 IDT 2021 | Tue Aug 03 07:00:00 IDT 2021 |  | COMPLETED
3164 | TT_TASK | CSA Punchlist - COLO-2 | Fri Oct 08 07:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  |  | 220.0 | NOT_STARTED
3165 | TT_TASK | CSA Punchlist - COLO-3 | Mon Nov 01 07:00:00 IST 2021 | Fri Nov 12 17:00:00 IST 2021 |  |  | 360.0 | NOT_STARTED
3166 | TT_TASK | CSA Punchlist - COLO-4 | Sat Dec 11 07:00:00 IST 2021 | Thu Dec 23 17:00:00 IST 2021 |  |  | 380.0 | NOT_STARTED
3167 | TT_TASK | MEP Punchlist - COLO-1 | Tue Sep 07 07:00:00 IDT 2021 | Fri Sep 17 17:00:00 IDT 2021 |  |  | 110.0 | NOT_STARTED
3168 | TT_TASK | MEP Punchlist - COLO-2 | Wed Nov 17 07:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 |  |  | 20.0 | NOT_STARTED
3169 | TT_TASK | MEP Punchlist - COLO-3 | Tue Jan 04 07:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  |  | 20.0 | NOT_STARTED
3170 | TT_TASK | MEP Punchlist - COLO-4 | Mon Feb 14 07:00:00 IST 2022 | Thu Feb 24 17:00:00 IST 2022 |  |  | 20.0 | NOT_STARTED
3171 | TT_TASK | AE/Owner Punchlist - COLO-1 | Sat Oct 30 07:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  |  | 60.0 | NOT_STARTED
3172 | TT_TASK | AE/Owner Punchlist - COLO-2 | Mon Dec 27 07:00:00 IST 2021 | Mon Jan 03 17:00:00 IST 2022 |  |  | 41.0 | NOT_STARTED
3173 | TT_TASK | AE/Owner Punchlist - COLO-3 | Wed Feb 09 07:00:00 IST 2022 | Mon Feb 14 17:00:00 IST 2022 |  |  | 71.0 | NOT_STARTED
3174 | TT_TASK | AE/Owner Punchlist - COLO-4 | Mon Mar 21 07:00:00 IST 2022 | Fri Mar 25 17:00:00 IDT 2022 |  |  | 70.0 | NOT_STARTED
3182 | TT_TASK | UMS - ROJ COLO-2 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3183 | TT_TASK | UMS - ROJ COLO-3 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3184 | TT_TASK | UMS - ROJ COLO-4 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3185 | TT_TASK | MSFT Delivery -UMS -COLO 4 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3186 | TT_TASK | MSFT Delivery -UMS -COLO 3 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3187 | TT_TASK | MSFT Delivery -UMS -COLO 2 ROJ | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3190 | TT_TASK | TCO COLO 2 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3191 | TT_TASK | Weather Tight | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3192 | TT_TASK | Duct Bank - UMS01 to UPM COLO-1 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3193 | TT_TASK | Duct Bank - UMS02 to UPM COLO-2 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3194 | TT_TASK | Duct Bank - UMS03 to UPM COLO-3 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3195 | TT_TASK | Duct Bank - UMS04 to UPM COLO-4 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3196 | TT_TASK | PAD- COLO-1 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3197 | TT_TASK | PAD- COLO-2 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3198 | TT_TASK | PAD- COLO-3 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3199 | TT_TASK | PAD- COLO-4 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3200 | TT_TASK | Pull- UMS01- UPM COLO-1 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3201 | TT_TASK | Pull- UMS02- UPM COLO-2 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3202 | TT_TASK | Pull- UMS03- UPM COLO-3 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3203 | TT_TASK | Pull- UMS04- UPM COLO-4 Cell-1 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3204 | TT_TASK | Set- COLO-1 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3205 | TT_TASK | Set- COLO-2 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3206 | TT_TASK | Set- COLO-3 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3207 | TT_TASK | Set- COLO-4 UMS | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3208 | TT_TASK | Term Admin - UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3209 | TT_TASK | Term COLO -1 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3210 | TT_TASK | Term COLO -1 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3211 | TT_TASK | Term COLO -2 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3212 | TT_TASK | Term COLO -2 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3213 | TT_TASK | Term COLO -3 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3214 | TT_TASK | Term COLO -3 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3215 | TT_TASK | Term COLO -4 Cell-4 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3216 | TT_TASK | Term COLO -4 Cell-3 UPM | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3217 | TT_TASK | Term- UMS01- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3218 | TT_TASK | Term- UMS02- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3219 | TT_TASK | Term- UMS03- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3220 | TT_TASK | Term- UMS04- Load side | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3221 | TT_TASK | Yellow Tagging for UMS01 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3222 | TT_TASK | Yellow Tagging for UMS02 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3223 | TT_TASK | Yellow Tagging for UMS03 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3224 | TT_TASK | Yellow Tagging for UMS04 | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3225 | TT_TASK | URS Vault design and Approval | Mon Aug 31 07:00:00 IDT 2020 | Mon Aug 31 07:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 | Sat Aug 29 00:00:00 IDT 2020 |  | COMPLETED
3227 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Thu Oct 22 07:00:00 IDT 2020 | Thu Oct 22 07:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3228 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3229 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jan 23 07:00:00 IST 2021 | Sat Jan 23 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3230 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Thu Oct 22 07:00:00 IDT 2020 | Thu Oct 22 07:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3231 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3232 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jan 23 07:00:00 IST 2021 | Sat Jan 23 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3233 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Nov 04 07:00:00 IST 2020 | Wed Nov 04 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3234 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3235 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Feb 04 07:00:00 IST 2021 | Thu Feb 04 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3236 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Nov 04 07:00:00 IST 2020 | Wed Nov 04 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3237 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3238 | TT_TASK | COLO Lighting installation (DRB#2) | Mon Feb 08 07:00:00 IST 2021 | Mon Feb 08 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3239 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Dec 17 07:00:00 IST 2020 | Thu Dec 17 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3240 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Dec 02 07:00:00 IST 2020 | Wed Dec 02 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3241 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Mar 11 07:00:00 IST 2021 | Thu Mar 11 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3242 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Tue Dec 29 07:00:00 IST 2020 | Tue Dec 29 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3243 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Wed Dec 02 07:00:00 IST 2020 | Wed Dec 02 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3244 | TT_TASK | COLO Lighting installation (DRB#2) | Thu Mar 11 07:00:00 IST 2021 | Thu Mar 11 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3245 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Dec 18 07:00:00 IST 2020 | Fri Dec 18 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3246 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Dec 15 07:00:00 IST 2020 | Tue Dec 15 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3247 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Mar 26 07:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3248 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Dec 15 07:00:00 IST 2020 | Tue Dec 15 07:00:00 IST 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3249 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Mar 26 07:00:00 IDT 2021 | Fri Mar 26 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3250 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Jan 07 07:00:00 IST 2021 | Thu Jan 07 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3251 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3252 | TT_TASK | COLO Lighting installation (DRB#2) | Tue Apr 27 07:00:00 IDT 2021 | Tue Apr 27 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3253 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Thu Jan 14 07:00:00 IST 2021 | Thu Jan 14 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3254 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3255 | TT_TASK | COLO Lighting installation (DRB#2) | Mon May 03 07:00:00 IDT 2021 | Mon May 03 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3256 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Fri Feb 12 07:00:00 IST 2021 | Fri Feb 12 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3257 | TT_TASK | COLO Lighting installation (DRB#2) | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3258 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Jan 29 07:00:00 IST 2021 | Fri Jan 29 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3259 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Fri Feb 12 07:00:00 IST 2021 | Fri Feb 12 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3260 | TT_TASK | COLO Lighting installation (DRB#2) | Wed May 12 07:00:00 IDT 2021 | Wed May 12 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3261 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3262 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Mar 09 07:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3263 | TT_TASK | COLO Lighting installation (DRB#2) | Wed Jun 09 07:00:00 IDT 2021 | Wed Jun 09 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3264 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Fri Feb 05 07:00:00 IST 2021 | Fri Feb 05 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3265 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Tue Mar 09 07:00:00 IST 2021 | Tue Mar 09 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3266 | TT_TASK | COLO Lighting installation (DRB#2) | Fri Jun 04 07:00:00 IDT 2021 | Fri Jun 04 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3267 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Sat Feb 20 07:00:00 IST 2021 | Sat Feb 20 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3268 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Mon Mar 22 07:00:00 IST 2021 | Mon Mar 22 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3269 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jun 19 07:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3270 | TT_TASK | COLO Fluid Cooler Heat Trace Installation (DRB#2) | Sat Feb 20 07:00:00 IST 2021 | Sat Feb 20 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3271 | TT_TASK | Overhead Rough-in Additional Lighting and Branch (DRB#2) | Mon Mar 22 07:00:00 IST 2021 | Mon Mar 22 07:00:00 IST 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3272 | TT_TASK | COLO Lighting installation (DRB#2) | Sat Jun 19 07:00:00 IDT 2021 | Sat Jun 19 07:00:00 IDT 2021 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3273 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3274 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3275 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3276 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3277 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3278 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3279 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3280 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3281 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3282 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3283 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3284 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3285 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3286 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3287 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3288 | TT_TASK | Install Added Overhead Rough In MER MECH EQ (DRB#3) | Mon Sep 28 07:00:00 IDT 2020 | Mon Oct 05 17:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 | Sat Sep 26 00:00:00 IDT 2020 |  | COMPLETED
3290 | TT_TASK | Steel Supports for Exterior Mechanical Equipment (Fluid Cooler Steel & Pipe Steel Supports) | Mon Nov 02 07:00:00 IST 2020 | Thu Nov 05 17:00:00 IST 2020 | Fri Oct 30 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3291 | TT_TASK | Mechanical Equipment Piping Connections | Tue Nov 03 07:00:00 IST 2020 | Tue Nov 17 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3292 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3293 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3294 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3295 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3296 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3297 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 30 07:00:00 IST 2020 | Mon Dec 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3298 | TT_TASK | Fluid Cooler RI prefabrication | Mon Nov 02 07:00:00 IST 2020 | Sat Nov 07 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3299 | TT_TASK | Fluid Cooler RI prefabrication | Thu Dec 10 07:00:00 IST 2020 | Wed Dec 16 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3300 | TT_TASK | Fluid Cooler RI prefabrication | Wed Dec 16 07:00:00 IST 2020 | Tue Dec 22 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3301 | TT_TASK | Fluid Cooler RI prefabrication | Wed Dec 23 07:00:00 IST 2020 | Mon Jan 04 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3302 | TT_TASK | Fluid Cooler RI prefabrication | Thu Jan 07 07:00:00 IST 2021 | Wed Jan 13 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3303 | TT_TASK | Fluid Cooler RI prefabrication | Thu Jan 14 07:00:00 IST 2021 | Thu Jan 21 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3304 | TT_TASK | Fluid Cooler RI prefabrication | Fri Jan 22 07:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3305 | TT_TASK | Fluid Cooler RI prefabrication | Tue Jan 26 07:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3306 | TT_TASK | Submit and approve shop drawing for PEMB penetrations | Mon Oct 19 08:00:00 IDT 2020 | Sun Nov 08 17:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 | Sat Oct 31 00:00:00 IST 2020 |  | COMPLETED
3308 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3309 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3310 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3311 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3312 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3313 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3314 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3315 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3316 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3317 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3318 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3319 | TT_TASK | Fire Riser Installation | Mon Nov 30 07:00:00 IST 2020 | Mon Nov 30 07:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 | Sat Nov 28 00:00:00 IST 2020 |  | COMPLETED
3321 | TT_TASK | Yellow Tagging for COLO-2 UPM's | Fri Jan 29 07:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3322 | TT_TASK | Yellow Tagging for COLO-3 UPM's | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 |  | COMPLETED
3323 | TT_TASK | Yellow Tagging for COLO-4 UPM's | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 | Sat Jan 30 07:00:00 IST 2021 | Sat Jan 30 17:00:00 IST 2021 |  | COMPLETED
3324 | TT_TASK | Pull/term/Test PDU to Power bus | Mon Jan 11 07:00:00 IST 2021 | Mon Jan 11 07:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3326 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3327 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 01 07:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3328 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Mar 10 07:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3329 | TT_TASK | Fluid Cooler QAQC and Cx | Mon Mar 08 07:00:00 IST 2021 | Tue Mar 09 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3330 | TT_TASK | Fluid Cooler QAQC and Cx | Thu Mar 18 07:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3331 | TT_TASK | Fluid Cooler QAQC and Cx | Fri Apr 02 07:00:00 IDT 2021 | Sat Apr 03 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3332 | TT_TASK | Fluid Cooler QAQC and Cx | Fri Mar 26 07:00:00 IDT 2021 | Sat Mar 27 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3333 | TT_TASK | Fluid Cooler QAQC and Cx | Tue Apr 06 07:00:00 IDT 2021 | Wed Apr 07 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3334 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 14 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3335 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 21 07:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3336 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 14 07:00:00 IDT 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3337 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 28 07:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3338 | TT_TASK | Fluid Cooler QAQC and Cx | Wed Apr 21 07:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3339 | TT_TASK | Fluid Cooler QAQC and Cx | Thu May 06 07:00:00 IDT 2021 | Fri May 07 17:00:00 IDT 2021 | Sun Feb 28 00:00:00 IST 2021 | Sun Feb 28 00:00:00 IST 2021 |  | COMPLETED
3341 | TT_TASK | COLO-2 CELL3 Rearrange Roxtec blocks per coordination layout | Wed Mar 31 07:00:00 IDT 2021 | Wed Mar 31 07:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3342 | TT_TASK | COLO2 CELL3 Interior MER conduit installation utility side | Tue Apr 06 07:00:00 IDT 2021 | Tue Apr 06 07:00:00 IDT 2021 | Fri Mar 26 00:00:00 IST 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3343 | TT_TASK | COLO-2 CELL3 Interior MER conduit installation building side | Tue Apr 20 07:00:00 IDT 2021 | Tue Apr 20 07:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 | Tue Mar 30 00:00:00 IDT 2021 |  | COMPLETED
3345 | TT_TASK | COLO-2 Cell-4 Rearrange Roxtec blocks per coordination layout | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3346 | TT_TASK | COLO2 CELL4 Interior MER conduit installation utility side | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3347 | TT_TASK | COLO2 CELL4 Interior MER conduit installation building side | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3350 | TT_TASK | COLO-2 Cell-1 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3351 | TT_TASK | COLO-2 Cell-2 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3352 | TT_TASK | COLO-2 Cell-3 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3353 | TT_TASK | COLO-2 Cell-4 MER Flex Conduit fixes | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3354 | TT_TASK | COLO2 CELL1 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3355 | TT_TASK | COLO2 CELL2 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3356 | TT_TASK | COLO2 CELL3 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3357 | TT_TASK | COLO2 CELL4 MER Security/Telecom Missing Raceway installation | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 | Wed Mar 31 00:00:00 IDT 2021 |  | COMPLETED
3360 | TT_TASK | Concrete interior - Create Punch list | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Jan 04 00:00:00 IST 2021 | Mon Jan 11 00:00:00 IST 2021 |  | COMPLETED
3361 | TT_TASK | Concrete interior - Complete Punch List | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 | Wed Jan 20 00:00:00 IST 2021 |  | COMPLETED
3362 | TT_TASK | Garco Steel (Mezz steel, Yard) - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3363 | TT_TASK | Garco Steel (Mezz steel, Yard) - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3364 | TT_TASK | Sure Steel (Building, Mezz, Ceiling) - Create Punch list | Sat Jan 02 07:00:00 IST 2021 | Mon Jan 04 17:00:00 IST 2021 | Mon Dec 21 00:00:00 IST 2020 | Wed Dec 23 00:00:00 IST 2020 |  | COMPLETED
3365 | TT_TASK | Sure Steel (Building, Mezz, Ceiling) - Complete Punch List | Mon Feb 01 07:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Mon Jan 18 00:00:00 IST 2021 | Fri Jan 29 00:00:00 IST 2021 |  | COMPLETED
3366 | TT_TASK | Advantage - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3367 | TT_TASK | Advantage - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3368 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3369 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3370 | TT_TASK | VECA - Create Punch list | Tue Sep 07 07:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3371 | TT_TASK | VECA - Complete Punch List | Thu Sep 09 07:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3372 | TT_TASK | LINX - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3373 | TT_TASK | LINX - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3374 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3375 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3376 | TT_TASK | TCM- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3377 | TT_TASK | TCM - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3378 | TT_TASK | Cascade- Create Punch list | Mon Apr 26 07:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Mon Jan 11 00:00:00 IST 2021 | Tue Jan 12 00:00:00 IST 2021 |  | COMPLETED
3379 | TT_TASK | Cascade - Complete Punch List | Wed Apr 28 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Mon Jan 18 00:00:00 IST 2021 | Sat Jan 30 00:00:00 IST 2021 |  | COMPLETED
3380 | TT_TASK | Submit GC Punch List to A/E | Tue Sep 21 07:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3381 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Sep 22 07:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3382 | TT_TASK | Complete A/E Punchlist | Thu Sep 30 07:00:00 IDT 2021 | Wed Oct 13 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3383 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3384 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3385 | TT_TASK | VECA - Create Punch list | Fri Oct 29 07:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3386 | TT_TASK | VECA - Complete Punch List | Mon Nov 01 07:00:00 IST 2021 | Mon Nov 08 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3387 | TT_TASK | LINX - Create Punch list | Mon Aug 16 07:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3388 | TT_TASK | LINX - Complete Punch List | Wed Aug 18 07:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3389 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3390 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3391 | TT_TASK | TCM- Create Punch list | Wed Sep 22 07:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3392 | TT_TASK | TCM - Complete Punch List | Fri Sep 24 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3393 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3394 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3395 | TT_TASK | Submit GC Punch List to A/E | Tue Nov 09 07:00:00 IST 2021 | Tue Nov 09 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3396 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Nov 10 07:00:00 IST 2021 | Tue Nov 16 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3397 | TT_TASK | Complete A/E Punchlist | Wed Nov 17 07:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3398 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3399 | TT_TASK | PCI - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3400 | TT_TASK | VECA - Create Punch list | Tue Dec 14 07:00:00 IST 2021 | Wed Dec 15 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3401 | TT_TASK | VECA - Complete Punch List | Thu Dec 16 07:00:00 IST 2021 | Thu Dec 23 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3402 | TT_TASK | LINX - Create Punch list | Wed Oct 13 07:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3403 | TT_TASK | LINX - Complete Punch List | Fri Oct 15 07:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3404 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3405 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3406 | TT_TASK | TCM- Create Punch list | Wed Sep 22 07:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3407 | TT_TASK | TCM - Complete Punch List | Fri Sep 24 07:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3408 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3409 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3410 | TT_TASK | Submit GC Punch List to A/E | Mon Dec 27 07:00:00 IST 2021 | Mon Dec 27 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3411 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Tue Dec 28 07:00:00 IST 2021 | Wed Jan 05 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3412 | TT_TASK | Complete A/E Punchlist | Thu Jan 06 07:00:00 IST 2022 | Thu Jan 20 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3413 | TT_TASK | PCI - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Sat Jul 31 07:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3414 | TT_TASK | PCI - Complete Punch List | Sat Jul 31 07:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3415 | TT_TASK | VECA - Create Punch list | Fri Jan 28 07:00:00 IST 2022 | Mon Jan 31 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3416 | TT_TASK | VECA - Complete Punch List | Tue Feb 01 07:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3417 | TT_TASK | LINX - Create Punch list | Fri Nov 19 07:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3418 | TT_TASK | LINX - Complete Punch List | Mon Nov 22 07:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3419 | TT_TASK | Convergent - Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3420 | TT_TASK | Convergent - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3421 | TT_TASK | TCM- Create Punch list | Thu Nov 04 07:00:00 IST 2021 | Fri Nov 05 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3422 | TT_TASK | TCM - Complete Punch List | Mon Nov 08 07:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3423 | TT_TASK | Cascade- Create Punch list | Sat Jul 31 07:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3424 | TT_TASK | Cascade - Complete Punch List | Tue Aug 03 07:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3425 | TT_TASK | Submit GC Punch List to A/E | Tue Feb 08 07:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3426 | TT_TASK | A/E & Owner-Rep Punchlist Walk | Wed Feb 09 07:00:00 IST 2022 | Tue Feb 15 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3427 | TT_TASK | Complete A/E Punchlist | Wed Feb 16 07:00:00 IST 2022 | Tue Mar 01 17:00:00 IST 2022 | Fri Jul 30 00:00:00 IDT 2021 | Fri Jul 30 00:00:00 IDT 2021 |  | COMPLETED
3428 | TT_TASK | COLO-2 Cell2 Rearrange Roxtec blocks per coordination layout (delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
3429 | TT_TASK | COLO2 CELL2 Interior MER conduit installation utility side(delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 | Sun May 30 00:00:00 IDT 2021 |  | COMPLETED
3430 | TT_TASK | COLO-2 CELL2 Interior MER conduit installation building (delete) | Tue Jun 01 07:00:00 IDT 2021 | Tue Jun 01 07:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 | Fri Apr 30 00:00:00 IDT 2021 |  | COMPLETED
3432 | TT_TASK | 6.1.50- ADP01- FCB23/FCB24 Two wire circuit design change and potential SCCS change(delete) | Fri Apr 30 07:00:00 IDT 2021 | Wed May 05 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Sat May 15 00:00:00 IDT 2021 |  | COMPLETED
3433 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3434 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3435 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
3436 | TT_TASK | Toilet Piping Installation / DW | Wed Jun 30 07:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 | Tue Jun 01 00:00:00 IDT 2021 |  | COMPLETED
2 | TT_TASK | PILING/PILE TRIMMING WORKS (CLP SCOPE) | Fri Jan 15 08:00:00 IST 2021 | Sun May 30 17:00:00 IDT 2021 | Fri Jan 15 08:00:00 IST 2021 | Sun May 30 17:00:00 IDT 2021 |  | COMPLETED
7 | TT_TASK | PULLING HV CABLES TO GIL BY CUSTOMER | Thu Dec 15 08:00:00 IST 2022 | Wed Jan 25 17:00:00 IST 2023 |  |  |  | NOT_STARTED
8 | TT_TASK | HV CABLE CONNECTION BY CUSTOMER | Sat Jan 28 08:00:00 IST 2023 | Fri Feb 17 17:00:00 IST 2023 |  |  |  | NOT_STARTED
9 | TT_TASK | CONNECTION TO TP BY CLIENT TP-E7 | Fri Mar 03 08:00:00 IST 2023 | Thu Mar 16 17:00:00 IST 2023 |  |  | 2320.0 | NOT_STARTED
10 | TT_TASK | CONNECTION TO TP BY CLIENT TP-E8 | Mon Oct 17 08:00:00 IDT 2022 | Sun Oct 30 17:00:00 IST 2022 |  |  | 3416.0 | NOT_STARTED
16 | TT_TASK | CONSTRUCTION PIT UBS(Additional Pit) | Fri Jun 03 08:00:00 IDT 2022 | Thu Jun 16 17:00:00 IDT 2022 |  |  | 1208.0 | NOT_STARTED
18 | TT_TASK | BASIC BUILDING DESIGN INCL. 3D MODEL 20UEZ02 (CLP Scope) | Mon Dec 21 08:00:00 IST 2020 | Sat Jan 16 17:00:00 IST 2021 | Mon Dec 21 08:00:00 IST 2020 | Sat Jan 16 17:00:00 IST 2021 |  | COMPLETED
19 | TT_TASK | DETAIL DESIGN CONCRETE STRUCTURE 20UEZ02 (CLP Scope) | Sun Jan 17 08:00:00 IST 2021 | Sat Feb 20 17:00:00 IST 2021 | Sun Jan 17 08:00:00 IST 2021 | Sat Feb 20 17:00:00 IST 2021 |  | COMPLETED
20 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS 20UEZ02 (CLP Scope) | Sun Feb 07 08:00:00 IST 2021 | Sat Feb 20 17:00:00 IST 2021 | Sun Feb 07 08:00:00 IST 2021 | Sat Feb 20 17:00:00 IST 2021 |  | COMPLETED
21 | TT_TASK | BD - SUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE - 20UEZ02 (CLP Scope) | Sun Feb 21 08:00:00 IST 2021 | Wed Apr 21 17:00:00 IDT 2021 | Sun Feb 21 08:00:00 IST 2021 | Wed Apr 21 17:00:00 IDT 2021 |  | COMPLETED
22 | TT_TASK | BD - CONSENT LETTER - DESIGN 20UEZ02 (CLP Scope) | Thu Apr 22 08:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Thu Apr 22 08:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 |  | COMPLETED
24 | TT_TASK | DETAIL DESIGN BARBENDING STRUCTURE 20UEZ02 (CLP Scope) | Thu Apr 29 08:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Thu Apr 29 08:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 |  | COMPLETED
27 | TT_TASK | WORK PREPARATION, EXCAVATION 20UEZ02 (CLP Scope) | Thu May 20 08:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Thu May 20 08:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 |  | COMPLETED
28 | TT_TASK | CONSTRUCTION FOUNDATION 20UEZ02 (CLP Scope) | Thu Jun 03 08:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Thu Jun 03 08:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
31 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS 20ULZ02 (CLP Scope) | Wed Jan 13 08:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Wed Jan 13 08:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 |  | COMPLETED
32 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20ULZ02 (CLP Scope) | Wed Jan 27 08:00:00 IST 2021 | Sat Feb 20 17:00:00 IST 2021 | Wed Jan 27 08:00:00 IST 2021 | Sat Feb 20 17:00:00 IST 2021 |  | COMPLETED
33 | TT_TASK | BD - SUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE - 20ULZ02 (CLP Scope) | Sun Feb 21 08:00:00 IST 2021 | Wed Apr 21 17:00:00 IDT 2021 | Sun Feb 21 08:00:00 IST 2021 | Wed Apr 21 17:00:00 IDT 2021 |  | COMPLETED
34 | TT_TASK | BD - CONSENT LETTER - DESIGN 20ULZ02 (CLP Scope) | Thu Apr 22 08:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Thu Apr 22 08:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 |  | COMPLETED
36 | TT_TASK | DETAIL DESIGN BARBENDING STRUCTURE 20ULZ02 (CLP Scope) | Thu Apr 29 08:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 | Thu Apr 29 08:00:00 IDT 2021 | Wed May 19 17:00:00 IDT 2021 |  | COMPLETED
39 | TT_TASK | BASIC BUILDING DESIGN INCL. 3D MODEL 20ULZ02 (CLP Scope) | Thu Nov 12 08:00:00 IST 2020 | Tue Dec 08 17:00:00 IST 2020 | Thu Nov 12 08:00:00 IST 2020 | Tue Dec 08 17:00:00 IST 2020 |  | COMPLETED
40 | TT_TASK | DETAIL DESIGN CONCRETE STRUCTURE 20ULZ02 (CLP Scope) | Wed Dec 09 08:00:00 IST 2020 | Tue Jan 26 17:00:00 IST 2021 | Wed Dec 09 08:00:00 IST 2020 | Tue Jan 26 17:00:00 IST 2021 |  | COMPLETED
41 | TT_TASK | WORK PREPARATION, EXCAVATION 20ULZ02 (CLP Scope) | Thu May 20 08:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 | Thu May 20 08:00:00 IDT 2021 | Wed Jun 02 17:00:00 IDT 2021 |  | COMPLETED
42 | TT_TASK | CONSTRUCTION FOUNDATION 20ULZ02 (CLP Scope) | Thu Jun 03 08:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Thu Jun 03 08:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
54 | TT_TASK | FABRICATION MEDIUM LEAD SUPPORT ITEMS (100%) | Sat Jul 24 08:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Sat Jul 24 08:00:00 IDT 2021 | Fri Oct 01 00:00:00 IDT 2021 |  | COMPLETED
60 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CONTROL VALVE | Sat Oct 09 08:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 | Sat Oct 09 08:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  | COMPLETED
61 | TT_TASK | TRANSPORT MEDIUM LEAD SUPPORT ITEMS (100%) | Sat Oct 02 08:00:00 IDT 2021 | Fri Nov 19 17:00:00 IST 2021 | Sat Oct 02 08:00:00 IDT 2021 | Fri Nov 19 00:00:00 IST 2021 |  | COMPLETED
63 | TT_TASK | DESIGN PHASE PIPING LARGE BORE & SUPPORTS LOT4 | Fri May 21 08:00:00 IDT 2021 | Mon Jul 05 17:00:00 IDT 2021 | Fri May 21 08:00:00 IDT 2021 | Mon Jul 05 17:00:00 IDT 2021 |  | COMPLETED
65 | TT_TASK | DESIGN PHASE PIPING GRP & PLASTIC MATERIAL LOT7 | Fri Jun 04 08:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 | Fri Jun 04 08:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 |  | COMPLETED
66 | TT_TASK | PIPE SUPPORTS DOCUMENTATION OFF RACK LOT7 | Wed Jul 21 08:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 | Wed Jul 21 08:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
67 | TT_TASK | PIPE SUPPORTS DOCUMENTATION OFF RACK LOT6 | Tue Aug 31 08:00:00 IDT 2021 | Mon Oct 18 17:00:00 IDT 2021 | Tue Aug 31 08:00:00 IDT 2021 | Mon Oct 18 17:00:00 IDT 2021 |  | COMPLETED
69 | TT_TASK | DESIGN PHASE PIPING LARGE BORE & SUPPORTS LOT 5 | Fri Jun 11 08:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Fri Jun 11 08:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
70 | TT_TASK | PIPE SUPPORTS DOCUMENTATION ON RACK LOT2 | Fri Aug 06 08:00:00 IDT 2021 | Wed Sep 01 17:00:00 IDT 2021 | Fri Aug 06 08:00:00 IDT 2021 | Wed Sep 01 17:00:00 IDT 2021 |  | COMPLETED
71 | TT_TASK | PIPE SUPPORTS DOCUMENTATION ON RACK LOT1 | Tue Jul 20 08:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Tue Jul 20 08:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 |  | COMPLETED
72 | TT_TASK | DESIGN PHASE PIPING SMALL BORE & SUPPORTS LOT 6 | Fri Jun 11 08:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Fri Jun 11 08:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
88 | TT_TASK | FABRICATION ISOMETRICS ON RACK LOT1 | Fri Jul 09 08:00:00 IDT 2021 | Sun Aug 01 17:00:00 IDT 2021 | Fri Jul 09 08:00:00 IDT 2021 | Sun Aug 01 17:00:00 IDT 2021 |  | COMPLETED
94 | TT_TASK | FABRICATION ISOMETRICS ON RACK LOT2 | Fri Aug 06 08:00:00 IDT 2021 | Wed Sep 01 17:00:00 IDT 2021 | Fri Aug 06 08:00:00 IDT 2021 | Wed Sep 01 17:00:00 IDT 2021 |  | COMPLETED
100 | TT_TASK | PIPE SUPPORTS DOCUMENTATION ON RACK LOT3 | Fri Sep 03 08:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Sep 03 08:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 |  | COMPLETED
101 | TT_TASK | FABRICATION ISOMETRICS ON RACK LOT3 | Fri Sep 03 08:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Fri Sep 03 08:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 |  | COMPLETED
102 | TT_TASK | DESIGN PHASE PIPING & SUPPORTS ON RACK LOT1 | Fri Jun 11 08:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri Jun 11 08:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
103 | TT_TASK | DESIGN PHASE PIPING & SUPPORTS ON RACK LOT2 | Fri Jul 09 08:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jul 09 08:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
104 | TT_TASK | DESIGN PHASE PIPING & SUPPORTS ON RACK LOT3 | Fri Aug 06 08:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Fri Aug 06 08:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 |  | COMPLETED
105 | TT_TASK | PIPE SUPPORTS DOCUMENTATION OFF RACK LOT4 | Tue Jul 06 08:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 06 08:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
106 | TT_TASK | FABRICATION ISOMETRICS OFF RACK LOT 7 | Wed Jul 21 08:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 | Wed Jul 21 08:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
107 | TT_TASK | FABRICATION ISOMETRICS OFF RACK LOT4 | Tue Jul 06 08:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 06 08:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
108 | TT_TASK | PIPE SUPPORTS DOCUMENTATION OFF RACK LOT5 | Wed Jul 28 08:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Jul 28 08:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 |  | COMPLETED
109 | TT_TASK | FABRICATION ISOMETRICS OFF RACK LOT 6 | Wed Jul 28 08:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 | Wed Jul 28 08:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  | COMPLETED
110 | TT_TASK | FABRICATION ISOMETRICS OFF RACK LOT 5 | Wed Jul 28 08:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 | Wed Jul 28 08:00:00 IDT 2021 | Tue Sep 14 17:00:00 IDT 2021 |  | COMPLETED
111 | TT_TASK | PREFABRICATION ON SITE ALL SYSTEMS - LOT 4 | Sat May 21 08:00:00 IDT 2022 | Sat Jun 11 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
112 | TT_TASK | UNPACKING & SORTING PIPING LOT 4 | Sat Apr 30 08:00:00 IDT 2022 | Fri May 20 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
113 | TT_TASK | UNPACKING & SORTING PIPING LOT 5 | Sat May 21 08:00:00 IDT 2022 | Fri Jun 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
114 | TT_TASK | UNPACKING & SORTING PIPING LOT 6 | Sat Sep 17 08:00:00 IDT 2022 | Fri Oct 07 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
115 | TT_TASK | PREFABRICATION ON SITE ALL SYSTEMS - TEMP. PIPING | Sat Oct 08 08:00:00 IDT 2022 | Fri Nov 04 17:00:00 IST 2022 |  |  | 1128.0 | NOT_STARTED
122 | TT_TASK | PREFABRICATION ON SITE ALL SYSTEMS LOT 5 | Sat May 28 08:00:00 IDT 2022 | Fri Jun 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
127 | TT_TASK | GENERAL BUILDING PLAN PREPARATION - FIRST DRAFT | Sat Oct 31 08:00:00 IST 2020 | Fri Jan 15 17:00:00 IST 2021 | Sat Oct 31 08:00:00 IST 2020 | Fri Jan 15 17:00:00 IST 2021 |  | COMPLETED
128 | TT_TASK | CLIENT - REVIEW - GENERAL BUILDING PLAN | Sat Jan 16 08:00:00 IST 2021 | Tue Feb 09 17:00:00 IST 2021 | Sat Jan 16 08:00:00 IST 2021 | Tue Feb 09 17:00:00 IST 2021 |  | COMPLETED
129 | TT_TASK | 1 -BD (BUILDING DEPARTMENT) - GBP 1st DRAFT SUBMISSION (INCL. WITHDRAW & RESUBMIT) | Sat Jan 16 08:00:00 IST 2021 | Thu Apr 15 17:00:00 IDT 2021 | Sat Jan 16 08:00:00 IST 2021 | Thu Apr 15 17:00:00 IDT 2021 |  | COMPLETED
130 | TT_TASK | BD - APPROVAL LETTER AWARD FOR GBP | Fri Apr 16 08:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Fri Apr 16 08:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 |  | COMPLETED
131 | TT_TASK | (MS2) LOADING DATA COMPILATION FOR PILE CAP DESIGN | Sat Aug 01 08:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 | Sat Aug 01 08:00:00 IDT 2020 | Fri Oct 30 17:00:00 IST 2020 |  | COMPLETED
132 | TT_TASK | PILE CAP & FOUNDATION DESIGN (WITH PREL. DESIGN FOR ALL AREAS) | Sat Aug 01 08:00:00 IDT 2020 | Sun Feb 28 17:00:00 IST 2021 | Sat Aug 01 08:00:00 IDT 2020 | Sun Feb 28 17:00:00 IST 2021 |  | COMPLETED
133 | TT_TASK | 1(a) - BD - GBP 2ND AMENDMENT SUBMISSION (INCL. MIC UNITS) - CONSENT LETTER | Fri May 14 08:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Fri May 14 08:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 |  | COMPLETED
134 | TT_TASK | NOISE PROTECTION CONCEPT REVIEW / COMMENTS BY CUSTOMER | Tue Mar 02 08:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 | Tue Mar 02 08:00:00 IST 2021 | Fri Mar 26 17:00:00 IDT 2021 |  | COMPLETED
135 | TT_TASK | NOISE PROTECTION CONCEPT FINALISATION | Sat Mar 27 08:00:00 IDT 2021 | Sat Apr 10 17:00:00 IDT 2021 | Sat Mar 27 08:00:00 IDT 2021 | Sat Apr 10 17:00:00 IDT 2021 |  | COMPLETED
136 | TT_TASK | SENDING / RECEIVING / REVIEWING OFFERS ERECTION CONTRACTOR (MECHANICAL) | Fri Mar 19 08:00:00 IST 2021 | Mon Jul 12 17:00:00 IDT 2021 | Fri Mar 19 08:00:00 IST 2021 | Mon Jul 12 17:00:00 IDT 2021 |  | COMPLETED
137 | TT_TASK | SENDING / RECEIVING / REVIEWING OFFERS ERECTION (E and I&C) | Fri Mar 19 08:00:00 IST 2021 | Mon Jul 12 17:00:00 IDT 2021 | Fri Mar 19 08:00:00 IST 2021 | Mon Jul 12 17:00:00 IDT 2021 |  | COMPLETED
138 | TT_TASK | REVISE RFQ DOCUMENTS / AUDIT / CHECK REVISED OFFERS ERECTION CONTRACTOR (MECHANICAL) | Tue Jul 13 08:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 13 08:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
139 | TT_TASK | REVISE RFQ DOCUMENTS / AUDIT / CHECK REVISED OFFERS ERECTION CONTRACTOR (E and I&C) | Tue Jul 13 08:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Tue Jul 13 08:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
140 | TT_TASK | CONTRACT NEGOTIATION / AWARD ERECTION CONTRACTOR (MECHANICAL) | Tue Aug 03 08:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 | Tue Aug 03 08:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  | COMPLETED
141 | TT_TASK | CONTRACT NEGOTIATION / AWARD ERECTION CONTRACTOR (E and I&C) | Tue Aug 03 08:00:00 IDT 2021 | Thu Dec 02 17:00:00 IST 2021 | Tue Aug 03 08:00:00 IDT 2021 | Thu Dec 02 17:00:00 IST 2021 |  | COMPLETED
142 | TT_TASK | 55 - BD - SUBMISSION - MiC PRE-ACCEPTANCE | Tue Apr 20 08:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Tue Apr 20 08:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 |  | COMPLETED
146 | TT_TASK | PREPARATION PREL. OPERATING MANUAL (BHB) | Sat Feb 11 08:00:00 IST 2023 | Sat Jun 10 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
148 | TT_TASK | REVISION OF OPERATING MANUAL (BHB) ON SITE | Mon Oct 09 08:00:00 IDT 2023 | Thu Dec 07 17:00:00 IST 2023 |  |  | 192.0 | NOT_STARTED
160 | TT_TASK | REVIEW CLIENT KKS PLANT LABELLING | Sat Dec 18 08:00:00 IST 2021 | Tue Jan 11 17:00:00 IST 2022 | Sat Dec 18 08:00:00 IST 2021 | Tue Jan 11 17:00:00 IST 2022 |  | COMPLETED
161 | TT_TASK | PREPARATION RFQ DOCUMENTS FOR ERECTION CONTRACTOR (MECHANICAL) | Fri Jan 15 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 |  | COMPLETED
162 | TT_TASK | PREPARATION RFQ DOCUMENTS FOR ERECTION CONTRACTOR (E and I&C) | Fri Jan 15 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 |  | COMPLETED
163 | TT_TASK | NOISE PROTECTION CONCEPT | Sun Jan 17 08:00:00 IST 2021 | Sat Feb 27 17:00:00 IST 2021 | Sun Jan 17 08:00:00 IST 2021 | Sat Feb 27 17:00:00 IST 2021 |  | COMPLETED
165 | TT_TASK | QUOTATION STAGE KKS PLANT LABELLING | Wed Jan 12 08:00:00 IST 2022 | Wed Mar 30 17:00:00 IDT 2022 | Wed Jan 12 08:00:00 IST 2022 |  |  | IN_PROGRESS
166 | TT_TASK | QUOTATION STAGE ERECTION CONTRACTOR (MECHANICAL) | Fri Mar 19 08:00:00 IST 2021 | Fri Jul 09 17:00:00 IDT 2021 | Fri Mar 19 08:00:00 IST 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
167 | TT_TASK | QUOTATION STAGE ERECTION CONTRACTOR (E and I&C) | Fri Mar 19 08:00:00 IST 2021 | Fri Jul 09 17:00:00 IDT 2021 | Fri Mar 19 08:00:00 IST 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
171 | TT_TASK | DESIGN,PREFABRICATION, TRANSPORT KKS PLANT LABELLING | Fri Sep 09 08:00:00 IDT 2022 | Thu Jan 26 17:00:00 IST 2023 |  |  |  | NOT_STARTED
172 | TT_TASK | ERECTION KKS PLANT LABELLING (REQUIRED FOR BACK ENERGISING) | Fri Jan 27 08:00:00 IST 2023 | Thu Mar 23 17:00:00 IST 2023 |  |  |  | NOT_STARTED
173 | TT_TASK | ERECTION KKS PLANT LABELLING (REQUIRED FOR 1ST FIRE) | Fri Jan 27 08:00:00 IST 2023 | Thu Jun 15 17:00:00 IDT 2023 |  |  | 64.0 | NOT_STARTED
174 | TT_TASK | ERECTION KKS PLANT LABELLING (REQUIRED FOR REM. PLANT) | Wed Apr 19 08:00:00 IDT 2023 | Tue Sep 05 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
176 | TT_TASK | MOBILISATION ERECTION CONTRACTOR (MECHANICAL) | Sun Nov 07 08:00:00 IST 2021 | Fri Jan 28 17:00:00 IST 2022 | Sun Nov 07 08:00:00 IST 2021 | Fri Jan 28 17:00:00 IST 2022 |  | COMPLETED
178 | TT_TASK | MOBILISATION ERECTION CONTRACTOR (E AND I&C) | Sat Feb 26 08:00:00 IST 2022 | Wed Apr 13 17:00:00 IDT 2022 | Sat Feb 26 08:00:00 IST 2022 |  |  | IN_PROGRESS
179 | TT_TASK | BD - SUBMISSION & APPROVAL - SUPPORTING FRAME FOR MODULES LOT 1 (UMY00Y/ULY00Y) | Thu Jun 17 08:00:00 IDT 2021 | Wed Sep 01 17:00:00 IDT 2021 | Thu Jun 17 08:00:00 IDT 2021 | Wed Sep 01 00:00:00 IDT 2021 |  | COMPLETED
180 | TT_TASK | BD - SUBMISSION & APPROVAL - SUPPORTING FRAME FOR MODULES LOT 2 (UMCM1Y/UMCL1Y) | Mon Jul 05 08:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Mon Jul 05 08:00:00 IDT 2021 | Thu Sep 02 00:00:00 IDT 2021 |  | COMPLETED
181 | TT_TASK | BD - SUBMISSION & APPROVAL - SUPPORTING FRAME FOR MODULES LOT 3 (UEY01Y/UEY02Y/UPY00Y) | Tue Aug 03 08:00:00 IDT 2021 | Fri Oct 01 17:00:00 IDT 2021 | Tue Aug 03 08:00:00 IDT 2021 | Fri Oct 01 00:00:00 IDT 2021 |  | COMPLETED
182 | TT_TASK | BD - CONSENT LETTER - SUPPORTING FRAME FOR MODULES LOT 1 | Thu Sep 02 08:00:00 IDT 2021 | Mon Nov 29 17:00:00 IST 2021 | Thu Sep 02 08:00:00 IDT 2021 | Tue Nov 30 08:00:00 IST 2021 |  | COMPLETED
183 | TT_TASK | BD - CONSENT LETTER - SUPPORTING FRAME FOR MODULES LOT 2 - UMCL1 | Sat Apr 23 08:00:00 IDT 2022 | Fri May 20 17:00:00 IDT 2022 |  |  | 56.0 | NOT_STARTED
184 | TT_TASK | BD - CONSENT LETTER - SUPPORTING FRAME FOR MODULES LOT 3 (UEY02) | Sat Oct 02 08:00:00 IDT 2021 | Sun Mar 27 17:00:00 IDT 2022 | Sat Oct 02 08:00:00 IDT 2021 |  | 8.0 | IN_PROGRESS
185 | TT_TASK | BD - REJECTION & REWORK- SUPPORTING FRAME FOR MODULES LOT 1 | Tue Nov 30 08:00:00 IST 2021 | Sun Dec 19 17:00:00 IST 2021 | Tue Nov 30 08:00:00 IST 2021 | Sun Dec 19 17:00:00 IST 2021 |  | COMPLETED
186 | TT_TASK | BD - RESUBMISSION - SUPPORTING FRAME FOR MODULES LOT 1 | Mon Dec 20 08:00:00 IST 2021 | Mon Feb 14 17:00:00 IST 2022 | Mon Dec 20 08:00:00 IST 2021 | Mon Feb 14 17:00:00 IST 2022 |  | COMPLETED
187 | TT_TASK | BD - RESUBMISSION & APPROVAL - PIPE RACK UEY | Fri Mar 04 08:00:00 IST 2022 | Mon May 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
188 | TT_TASK | BD - RESUBMISSION & APPROVAL - PIPERACK UPY | Mon Feb 21 08:00:00 IST 2022 | Thu Apr 21 17:00:00 IDT 2022 | Mon Feb 21 08:00:00 IST 2022 |  |  | IN_PROGRESS
189 | TT_TASK | BD - CONSENT LETTER - PIPE RACK UEY | Tue May 03 08:00:00 IDT 2022 | Mon May 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
191 | TT_TASK | BD - CONSENT LETTER - PIPERACK UPY | Fri Apr 22 08:00:00 IDT 2022 | Thu May 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
193 | TT_TASK | BD - RESUBMISSION & APPROVAL - SUPPORTING FRAME FOR MODULES LOT 2 (UMCL1Y) | Tue Feb 22 08:00:00 IST 2022 | Fri Apr 22 17:00:00 IDT 2022 | Tue Feb 22 08:00:00 IST 2022 |  |  | IN_PROGRESS
194 | TT_TASK | BD - CONSENT LETTER - SUPPORTING FRAME FOR MODULES LOT 2 - UMCM1 | Fri Apr 29 08:00:00 IDT 2022 | Thu May 26 17:00:00 IDT 2022 |  |  | 8.0 | NOT_STARTED
195 | TT_TASK | BD - RESUBMISSION & APPROVAL - SUPPORTING FRAME FOR MODULES LOT 2 (UMCM1Y) | Mon Feb 28 08:00:00 IST 2022 | Thu Apr 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
197 | TT_TASK | PROJECT SPECIFIC ADAPTION OF GENERAL TCCs | Sat Aug 01 08:00:00 IDT 2020 | Fri Aug 21 17:00:00 IDT 2020 | Sat Aug 01 08:00:00 IDT 2020 | Fri Aug 21 17:00:00 IDT 2020 |  | COMPLETED
205 | TT_TASK | KICK OFF PROCESS ENGINEERING | Sat Aug 01 08:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 | Sat Aug 01 08:00:00 IDT 2020 | Fri Aug 28 17:00:00 IDT 2020 |  | COMPLETED
207 | TT_TASK | INTERCONNECTION ENGINEERING, CMI, FUP | Fri Apr 30 08:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 | Fri Apr 30 08:00:00 IDT 2021 | Mon Jul 12 17:00:00 IDT 2021 |  | COMPLETED
208 | TT_TASK | APPROVAL SINGLE LINE DIAGRAM | Fri Jan 15 08:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Fri Feb 19 17:00:00 IST 2021 |  | COMPLETED
212 | TT_TASK | M2 ORDERABILITY PID FOR COMPLETE SYSTEMS (Building Block Scope only) | Sat Aug 01 08:00:00 IDT 2020 | Fri Oct 23 17:00:00 IDT 2020 | Sat Aug 01 08:00:00 IDT 2020 | Fri Oct 23 17:00:00 IDT 2020 |  | COMPLETED
216 | TT_TASK | PREPARATION OF SPECIFICATION BLACK BOXES (LET) & LV-MOTORS | Fri Jan 22 08:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Fri Jan 22 08:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 |  | COMPLETED
218 | TT_TASK | SSM OFFICE ERECTION | Sat May 01 08:00:00 IDT 2021 | Tue Jun 08 17:00:00 IDT 2021 | Sat May 01 00:00:00 IDT 2021 | Tue Jun 08 00:00:00 IDT 2021 |  | COMPLETED
220 | TT_TASK | CONSTRUCTION OF SIEMENS SITE CONTRACTOR OFFICE AREA | Thu Jul 01 08:00:00 IDT 2021 | Mon Sep 27 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Tue Sep 28 00:00:00 IDT 2021 |  | COMPLETED
221 | TT_TASK | INSTALLATION OF POTABLE WATER AND WASTE WATER SYSTEM (TP availability needed?) | Thu Jul 01 08:00:00 IDT 2021 | Fri Aug 27 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Fri Aug 27 17:00:00 IDT 2021 |  | COMPLETED
222 | TT_TASK | PREPARATION OF AREA AT SIEMENS INDUCTION-EHS / FIRST AID STATION / GATE HOUSE | Thu Jul 01 08:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
223 | TT_TASK | PREPARATION OF LAYDOWN AREAS AND SIEMENS STORAGE | Thu Jul 01 08:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Mon Aug 16 17:00:00 IDT 2021 |  | COMPLETED
224 | TT_TASK | PREPARATION OF CONTRACTORS VILLAGE AREA | Thu Jul 01 08:00:00 IDT 2021 | Fri Aug 27 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Fri Aug 27 17:00:00 IDT 2021 |  | COMPLETED
225 | TT_TASK | INSTALLATION OF TEMPORARY ROADS AT LAYDOWN AREA | Wed Sep 15 08:00:00 IDT 2021 | Tue Nov 02 17:00:00 IST 2021 | Wed Sep 15 08:00:00 IDT 2021 | Tue Nov 02 17:00:00 IST 2021 |  | COMPLETED
226 | TT_TASK | INSTALLATION OF SIEMENS WAREHOUSE | Mon Aug 30 08:00:00 IDT 2021 | Fri Dec 03 17:00:00 IST 2021 | Mon Aug 30 08:00:00 IDT 2021 | Fri Dec 03 17:00:00 IST 2021 |  | COMPLETED
227 | TT_TASK | SITE POWER - SDB1.1 - DISMANTLE AND RELOCATE TO NEW LOCATION | Thu Jul 01 08:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
228 | TT_TASK | SITE POWER - SDB1.2.1 - INSTALLATION | Thu Jul 01 08:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 |  | COMPLETED
229 | TT_TASK | SITE POWER - SDB1.4 - INSTALLATION | Thu Jul 01 08:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
230 | TT_TASK | SITE POWER - SDB1.5 / SDB1.6 - INSTALLATION | Thu Jul 01 08:00:00 IDT 2021 | Wed Jul 21 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Wed Jul 21 17:00:00 IDT 2021 |  | COMPLETED
231 | TT_TASK | SITE POWER - GATE HOUSE/INDUCTION ROOM/FIRST AID/LCM&PTW OFFICE - INSTALLATION POWER SUPPLY | Thu Jul 01 08:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Fri Aug 20 17:00:00 IDT 2021 |  | COMPLETED
232 | TT_TASK | SITE POWER - WAREHOUSE/DAY ACCOMODATION BUILDINGS - INSTALLATION POWER SUPPLY | Thu Jul 01 08:00:00 IDT 2021 | Fri Nov 26 17:00:00 IST 2021 | Thu Jul 01 08:00:00 IDT 2021 | Sat Nov 27 08:00:00 IST 2021 |  | COMPLETED
233 | TT_TASK | SITE POWER - ABLUTION AND SHOWR CONTAINERS - INSTALLATION POWER SUPPLY | Thu Jul 01 08:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Fri Oct 22 17:00:00 IDT 2021 |  | COMPLETED
234 | TT_TASK | SITE POWER - AS PER IT CONCEPT - INSTALLATION OF FIBER OPTIC/LAN CABLES | Thu Jul 01 08:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
235 | TT_TASK | SITE POWER - SDB1.7 - INSTALLATION | Thu Jul 01 08:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
238 | TT_TASK | QUOTATION STAGE SITE INFRASTRUCTURE | Fri Jan 29 08:00:00 IST 2021 | Tue Apr 13 17:00:00 IDT 2021 | Fri Jan 29 08:00:00 IST 2021 | Tue Apr 13 17:00:00 IDT 2021 |  | COMPLETED
239 | TT_TASK | PREPARATION KICK OFF SITE INFRASTRUCTURE | Wed Apr 14 08:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Wed Apr 14 08:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 |  | COMPLETED
241 | TT_TASK | DETAIL DESIGN SITE INFRASTRUCTURE (by subcontractor) | Wed Apr 14 08:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 | Wed Apr 14 08:00:00 IDT 2021 | Tue Apr 27 17:00:00 IDT 2021 |  | COMPLETED
242 | TT_TASK | REVIEW OF DETAIL DESIGN SITE INFRASTRUCTURE (by Siemens) | Wed Apr 28 08:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 28 08:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 |  | COMPLETED
243 | TT_TASK | PREPARE RFQ MAIN CIVIL WORKS | Sun Dec 13 08:00:00 IST 2020 | Sun Jan 31 17:00:00 IST 2021 | Sun Dec 13 08:00:00 IST 2020 | Sun Jan 31 17:00:00 IST 2021 |  | COMPLETED
244 | TT_TASK | EVALUATION/NEGOTIATION MAIN CIVIL WORKS | Fri Apr 09 08:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 | Fri Apr 09 08:00:00 IDT 2021 | Thu May 13 17:00:00 IDT 2021 |  | COMPLETED
245 | TT_TASK | PREPARATION KICK OFF MAIN CIVIL WORKS | Fri May 14 08:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Fri May 14 08:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 |  | COMPLETED
248 | TT_TASK | PREPARATION ROOM MODEL | Sun Apr 18 08:00:00 IDT 2021 | Sat May 01 17:00:00 IDT 2021 | Sun Apr 18 08:00:00 IDT 2021 | Sat May 01 17:00:00 IDT 2021 |  | COMPLETED
252 | TT_TASK | QUOTATION STAGE MAIN CIVIL WORKS | Mon Feb 01 08:00:00 IST 2021 | Thu May 13 17:00:00 IDT 2021 | Mon Feb 01 08:00:00 IST 2021 | Thu May 13 17:00:00 IDT 2021 |  | COMPLETED
254 | TT_TASK | PREPARE MAINTENANCE CONCEPT | Sat Jul 31 08:00:00 IDT 2021 | Fri Aug 27 17:00:00 IDT 2021 | Sat Jul 31 08:00:00 IDT 2021 | Fri Aug 27 17:00:00 IDT 2021 |  | COMPLETED
255 | TT_TASK | QUOTATION STAGE STEELWORK & CLADDING | Fri Jan 29 08:00:00 IST 2021 | Thu May 13 17:00:00 IDT 2021 | Fri Jan 29 08:00:00 IST 2021 | Thu May 13 17:00:00 IDT 2021 |  | COMPLETED
256 | TT_TASK | PREPARATION KICK OFF STEELWORK & CLADDING | Fri May 14 08:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Fri May 14 08:00:00 IDT 2021 | Thu May 27 00:00:00 IDT 2021 |  | COMPLETED
259 | TT_TASK | QUOTATION STAGE PAB PIPING SUPPLY | Sat Jan 30 08:00:00 IST 2021 | Sun Mar 14 17:00:00 IST 2021 | Sat Jan 30 08:00:00 IST 2021 | Sun Mar 14 17:00:00 IST 2021 |  | COMPLETED
260 | TT_TASK | PREPARATION RFQ PAB PIPING SUPPLY | Fri Jan 15 08:00:00 IST 2021 | Fri Jan 29 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Fri Jan 29 17:00:00 IST 2021 |  | COMPLETED
262 | TT_TASK | MOBILISATION OF CONTRACTOR (MAIN CIVIL WORKS) | Tue Jun 01 08:00:00 IDT 2021 | Thu Jul 01 08:16:00 IDT 2021 | Tue Jun 01 08:00:00 IDT 2021 | Thu Jul 01 08:16:00 IDT 2021 |  | COMPLETED
273 | TT_TASK | DETAIL DESIGN CABLE ROUTING | Fri Oct 01 08:00:00 IDT 2021 | Sun Dec 19 17:00:00 IST 2021 | Fri Oct 01 08:00:00 IDT 2021 | Sun Dec 19 17:00:00 IST 2021 |  | COMPLETED
278 | TT_TASK | BASIC DESIGN CABLE - OVERALL CABLE ROUTING DWG YD16 - FIRST SUBMISSION | Sat Mar 20 08:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 | Sat Mar 20 08:00:00 IST 2021 | Fri Apr 02 17:00:00 IDT 2021 |  | COMPLETED
281 | TT_TASK | PROJECT SPECIFIC ADAPTION OF ELECTRICAL REQUIREMENTS FOR HRSG | Thu Aug 13 08:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 | Thu Aug 13 08:00:00 IDT 2020 | Wed Oct 07 17:00:00 IDT 2020 |  | COMPLETED
282 | TT_TASK | CABLE SPIDER | Fri Feb 05 08:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Fri Feb 05 08:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 |  | COMPLETED
284 | TT_TASK | BASIC DESIGN CABLE - OVERALL CABLE ROUTING DWG YD16 - FINAL SUBMISSION | Sat Apr 03 08:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 | Sat Apr 03 08:00:00 IDT 2021 | Fri Apr 16 17:00:00 IDT 2021 |  | COMPLETED
285 | TT_TASK | DETAIL DESIGN CABLE ROUTING ELECTRICAL SCOPE | Fri Oct 01 08:00:00 IDT 2021 | Mon Feb 14 17:00:00 IST 2022 | Fri Oct 01 08:00:00 IDT 2021 | Mon Feb 14 17:00:00 IST 2022 |  | COMPLETED
286 | TT_TASK | DETAIL DESIGN CABLE ROUTING I&C SCOPE | Tue Feb 08 08:00:00 IST 2022 | Fri Apr 08 17:00:00 IDT 2022 | Tue Feb 08 08:00:00 IST 2022 |  |  | IN_PROGRESS
287 | TT_TASK | DETAIL DESIGN CABLE ROUTING BLACK BOXES | Sat Mar 19 08:00:00 IST 2022 | Fri Apr 15 17:00:00 IDT 2022 |  |  | 56.0 | NOT_STARTED
291 | TT_TASK | PULLING DATA PREPARATION ON SITE (BOP SYSTEMS) | Sat Apr 09 08:00:00 IDT 2022 | Fri Apr 22 17:00:00 IDT 2022 |  |  | 632.0 | NOT_STARTED
293 | TT_TASK | BASIC DESIGN / SPECIFICATION IPB BAA | Fri Jan 15 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 |  | COMPLETED
297 | TT_TASK | QUOTATION STAGE IPB BAA | Fri Mar 19 08:00:00 IST 2021 | Sat May 01 17:00:00 IDT 2021 | Fri Mar 19 08:00:00 IST 2021 | Sat May 01 17:00:00 IDT 2021 |  | COMPLETED
299 | TT_TASK | AUDIT AT IPB MANUFACTURER | Sun May 02 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Sun May 02 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 |  | COMPLETED
301 | TT_TASK | BASIC DESIGN / SPECIFICATION GEN. CIRCUIT BREAKER BAC | Fri Jan 29 08:00:00 IST 2021 | Thu May 06 17:00:00 IDT 2021 | Fri Jan 29 08:00:00 IST 2021 | Thu May 06 17:00:00 IDT 2021 |  | COMPLETED
304 | TT_TASK | QUOTATION STAGE GEN. CIRCUIT BREAKER BAC | Fri May 07 08:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri May 07 08:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
307 | TT_TASK | PREPARATION VEL (before ELV2) | Fri Feb 05 08:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 | Fri Feb 05 08:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 |  | COMPLETED
308 | TT_TASK | PREPARATION VEL (before ELV3) | Tue Mar 16 08:00:00 IST 2021 | Mon Jun 14 17:00:00 IDT 2021 | Tue Mar 16 08:00:00 IST 2021 | Mon Jun 14 17:00:00 IDT 2021 |  | COMPLETED
310 | TT_TASK | PREPARATION VEL (after ELV3) | Thu Jul 01 08:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
311 | TT_TASK | SPECIFICATION GROUNDING & LIGHTNING PROTECTION | Tue May 18 08:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Tue May 18 08:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 |  | COMPLETED
312 | TT_TASK | GROUNDING MEASUREMENT / GROUNDING DESIGN REPORT | Fri Feb 26 08:00:00 IST 2021 | Thu Apr 22 17:00:00 IDT 2021 | Fri Feb 26 08:00:00 IST 2021 | Thu Apr 22 17:00:00 IDT 2021 |  | COMPLETED
315 | TT_TASK | QUOTATION STAGE IN- / OUTDOOR GROUNDING BAW | Sun Dec 19 08:00:00 IST 2021 | Sat Jan 29 17:00:00 IST 2022 | Sun Dec 19 08:00:00 IST 2021 | Sat Jan 29 17:00:00 IST 2022 |  | COMPLETED
317 | TT_TASK | FINALIZE VEL INPUT DATA (before ELV3) | Fri Jun 18 08:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Fri Jun 18 08:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 |  | COMPLETED
318 | TT_TASK | BASIC DESIGN IN-/ OUTDOOR GROUNDING | Tue Jun 29 08:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Tue Jun 29 08:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
319 | TT_TASK | DETAIL DESIGN OUTDOOR GROUNDING-ATKINS | Tue Aug 10 08:00:00 IDT 2021 | Tue Dec 14 17:00:00 IST 2021 | Tue Aug 10 08:00:00 IDT 2021 | Tue Dec 14 17:00:00 IST 2021 |  | COMPLETED
320 | TT_TASK | DETAIL DESIGN INDOOR GROUNDING-SE | Sat Nov 27 08:00:00 IST 2021 | Fri Jan 07 17:00:00 IST 2022 | Sat Nov 27 08:00:00 IST 2021 | Fri Jan 07 17:00:00 IST 2022 |  | COMPLETED
321 | TT_TASK | MANUFACTURING / SHOP TEST IN- / OUTDOOR GROUNDING BAW | Sun Jan 30 08:00:00 IST 2022 | Wed May 04 17:00:00 IDT 2022 | Sun Jan 30 08:00:00 IST 2022 |  |  | IN_PROGRESS
324 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION IN- / OUTDOOR GROUNDING BAW | Thu May 05 08:00:00 IDT 2022 | Wed Jun 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
325 | TT_TASK | TRANSPORT IN- / OUTDOOR GROUNDING BAW (THAILAND) | Thu Jun 02 08:00:00 IDT 2022 | Fri Jul 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
327 | TT_TASK | EARTHING MEASUREMENT | Mon May 10 08:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Mon May 10 08:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 |  | COMPLETED
331 | TT_TASK | BASIC DESIGN / SPECIFICATION MV SWITCHGEAR 20/90BBA/BBB | Fri Feb 05 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 05 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
333 | TT_TASK | QUOTATION STAGE MV SWITCHGEAR 20/90BBA/BBB | Sat May 01 08:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Sat May 01 08:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
335 | TT_TASK | BASIC DESIGN / SPECIFICATION LV SWITCHGEAR FOR HRSG BFF/BMF | Fri Apr 02 08:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Fri Apr 02 08:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 |  | COMPLETED
337 | TT_TASK | QUOTATION STAGE LV SWITCHGEAR FOR HRSG BFF/BMF | Fri May 28 08:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri May 28 08:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
340 | TT_TASK | DETAIL DESIGN / CLARIFICATION TYPICAL OF LV SWITCHGEAR FOR HRSG 20BFF/BMF | Fri Jul 30 08:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Fri Jul 30 08:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 |  | COMPLETED
342 | TT_TASK | BASIC DESIGN / SPECIFICATION LV-TRANSFORMERS BFT | Tue May 18 08:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 | Tue May 18 08:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
345 | TT_TASK | QUOTATION STAGE LV-TRANSFORMERS BFT | Fri Jul 30 08:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 | Fri Jul 30 08:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 |  | COMPLETED
348 | TT_TASK | COMMISSIONING LV TRANSFORMER 20BFT03 | Mon May 22 08:00:00 IDT 2023 | Sun May 28 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
350 | TT_TASK | COMMISSIONING LV TRANSFORMER 20BFT04 | Mon May 22 08:00:00 IDT 2023 | Sun May 28 17:00:00 IDT 2023 |  |  | 8.0 | NOT_STARTED
351 | TT_TASK | TRANSPORT LV TRANSFORMER 20BFT03/04 | Fri Sep 09 08:00:00 IDT 2022 | Thu Nov 03 17:00:00 IST 2022 |  |  |  | NOT_STARTED
353 | TT_TASK | PLACING LV TRANSFORMER 20BFT03/04 | Fri Nov 18 08:00:00 IST 2022 | Fri Nov 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
354 | TT_TASK | ERECTION LV TRANSFORMER 20BFT03/04 | Sat Nov 19 08:00:00 IST 2022 | Thu Dec 15 17:00:00 IST 2022 |  |  |  | NOT_STARTED
356 | TT_TASK | COMMISSIONING 20BTA/BTL | Tue Feb 14 08:00:00 IST 2023 | Mon Feb 20 17:00:00 IST 2023 |  |  |  | NOT_STARTED
360 | TT_TASK | PREPARATION OF 1ST LENGTH MATRIX | Sun May 02 08:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 | Sun May 02 08:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
361 | TT_TASK | BASIC DESIGN / SPECIFICATION MV/LV CABLES BZK | Tue Jul 27 08:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Tue Jul 27 08:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 |  | COMPLETED
364 | TT_TASK | PREPARATION OF FINAL LENGTH MATRIX | Sun May 16 08:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Sun May 16 08:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
367 | TT_TASK | QUOTATION MV/LV CABLES BZK | Tue Aug 24 08:00:00 IDT 2021 | Sat Jan 29 17:00:00 IST 2022 | Tue Aug 24 08:00:00 IDT 2021 | Sat Jan 29 17:00:00 IST 2022 |  | COMPLETED
369 | TT_TASK | BASIC DESIGN / SPECIFICATION I&C CABLES BZK | Thu Aug 26 08:00:00 IDT 2021 | Wed Sep 22 17:00:00 IDT 2021 | Thu Aug 26 08:00:00 IDT 2021 | Wed Sep 22 17:00:00 IDT 2021 |  | COMPLETED
370 | TT_TASK | QUOTATION I&C CABLES BZK | Thu Sep 23 08:00:00 IDT 2021 | Wed Dec 01 17:00:00 IST 2021 | Thu Sep 23 08:00:00 IDT 2021 | Wed Dec 01 17:00:00 IST 2021 |  | COMPLETED
373 | TT_TASK | MANUFACTURING / SHOP TEST MV/LV CABLE 20/00BZK (LOT2) | Sat Mar 26 08:00:00 IDT 2022 | Wed Sep 07 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
376 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MV/LV CABLE 20/00BZK (LOT2) | Thu Sep 08 08:00:00 IDT 2022 | Wed Oct 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
377 | TT_TASK | TRANSPORT MV/LV CABLE 20/00BZK (LOT2) (THAILAND) | Thu Oct 06 08:00:00 IDT 2022 | Wed Oct 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
380 | TT_TASK | BASIC DESIGN / SPECIFICATION / PLANTLAYOUT DWG / BOQ LIGHTING & SMALL POWER BZL | Thu Feb 04 08:00:00 IST 2021 | Wed Apr 28 17:00:00 IDT 2021 | Thu Feb 04 08:00:00 IST 2021 | Wed Apr 28 17:00:00 IDT 2021 |  | COMPLETED
382 | TT_TASK | QUOTATION STAGE LIGHTING & SMALL POWER BZL | Thu May 13 08:00:00 IDT 2021 | Wed Dec 15 17:00:00 IST 2021 | Thu May 13 08:00:00 IDT 2021 | Wed Dec 15 17:00:00 IST 2021 |  | COMPLETED
384 | TT_TASK | BASIC DESIGN, SPECIFICATION LIGHTING/SMALL POWER BZL - not done by BHI | Sat Feb 20 08:00:00 IST 2021 | Fri May 14 17:00:00 IDT 2021 | Sat Feb 20 08:00:00 IST 2021 | Fri May 14 17:00:00 IDT 2021 |  | COMPLETED
386 | TT_TASK | CHECK OF BASIC DESIGN WITH ATKINS | Thu Apr 29 08:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Thu Apr 29 08:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 |  | COMPLETED
387 | TT_TASK | DETAIL DESIGN, SPECIFICATION LIGHTING/SMALL POWER BZL HRSG | Thu May 05 08:00:00 IDT 2022 | Mon Jul 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
388 | TT_TASK | QUOTATION STAGE LIGHTING/SMALL POWER BZL HRSG | Tue Feb 01 08:00:00 IST 2022 | Wed Mar 02 17:00:00 IST 2022 | Tue Feb 01 08:00:00 IST 2022 |  |  | IN_PROGRESS
389 | TT_TASK | MANUFACTURING LIGHTING/SMALL POWER BZL HRSG | Tue Jul 05 08:00:00 IDT 2022 | Mon Sep 26 17:00:00 IDT 2022 |  |  | 1016.0 | NOT_STARTED
390 | TT_TASK | BASIC DESIGN, SPECIFICATION LIGHTING/SMALL POWER BZL HRSG | Thu Mar 03 08:00:00 IST 2022 | Wed Apr 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
391 | TT_TASK | REVIEW & COMMENTING BD SPECIFICATION LIGHTING/SMALL POWER BZL HRSG | Thu Apr 14 08:00:00 IDT 2022 | Wed May 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
392 | TT_TASK | MANUFACTURING /SHOP TEST LIGHTING & SMALL POWER BZL HIGHBAY, 20UMC | Sat Mar 19 08:00:00 IST 2022 | Thu Apr 07 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
395 | TT_TASK | DETAIL DESIGN LIGHTING & SMALL POWER BZL HIGHBAY, 20UMC | Thu Dec 16 08:00:00 IST 2021 | Fri Mar 18 17:00:00 IST 2022 | Thu Dec 16 08:00:00 IST 2021 |  |  | IN_PROGRESS
396 | TT_TASK | MANUFACTURING /SHOP TEST LIGHTING & SMALL POWER BZL COMPLETE PLANT | Sat May 28 08:00:00 IDT 2022 | Thu Jun 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
399 | TT_TASK | DETAIL DESIGN LIGHTING & SMALL POWER BZL COMPLETE PLANT | Thu Dec 16 08:00:00 IST 2021 | Fri May 27 17:00:00 IDT 2022 | Thu Dec 16 08:00:00 IST 2021 |  |  | IN_PROGRESS
400 | TT_TASK | TRANSPORT LIGHTING & SMALL POWER BZL HIGHBAY, 20UMC | Fri Apr 15 08:00:00 IDT 2022 | Sun Apr 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
403 | TT_TASK | TRANSPORT LIGHTING & SMALL POWER BZL COMPLETE PLANT | Fri Jul 01 08:00:00 IDT 2022 | Sun Jul 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
406 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM 20ULA (FIRST SUBMISSION) | Sun Dec 05 08:00:00 IST 2021 | Sun Dec 19 17:00:00 IST 2021 | Sun Dec 05 08:00:00 IST 2021 | Sun Dec 19 17:00:00 IST 2021 |  | COMPLETED
407 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UEY/00UEN/20UMX (FIRST SUBMISSION) | Sat Dec 04 08:00:00 IST 2021 | Sat Dec 18 17:00:00 IST 2021 | Sat Dec 04 08:00:00 IST 2021 | Sat Dec 18 17:00:00 IST 2021 |  | COMPLETED
408 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM 20URA/20URD AREA(FIRST SUBMISSION) | Sat Jan 01 08:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 | Sat Jan 01 08:00:00 IST 2022 | Sat Jan 15 17:00:00 IST 2022 |  | COMPLETED
409 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UBY05/UBZ03/ULZ02/UBZ02 (FIRST SUBMISSION) | Sat Jan 08 08:00:00 IST 2022 | Sat Jan 22 17:00:00 IST 2022 | Sat Jan 08 08:00:00 IST 2022 | Sat Jan 22 17:00:00 IST 2022 |  | COMPLETED
410 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UEZ02/20UQY0102/03/20UQX/20UQZ (FIRST SUBMISSION) | Sat Jan 15 08:00:00 IST 2022 | Sat Jan 29 17:00:00 IST 2022 | Sat Jan 15 08:00:00 IST 2022 | Sat Jan 29 17:00:00 IST 2022 |  | COMPLETED
411 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UBN (FIRST SUBMISSION) | Sat Jan 29 08:00:00 IST 2022 | Sat Feb 12 17:00:00 IST 2022 | Sat Jan 29 08:00:00 IST 2022 | Sat Feb 12 17:00:00 IST 2022 |  | COMPLETED
412 | TT_TASK | PREPARATION TENDER BOQ CABLE SUPPORT SYSTEM BZP | Wed Jul 14 08:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 | Wed Jul 14 08:00:00 IDT 2021 | Tue Aug 10 17:00:00 IDT 2021 |  | COMPLETED
413 | TT_TASK | BASIC DESIGN / SPECIFICATION CABLE SUPPORT SYSTEM BZP | Wed Jun 16 08:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 16 08:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
414 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM BZP | Sat Jan 08 08:00:00 IST 2022 | Fri Apr 01 17:00:00 IDT 2022 | Sat Jan 08 08:00:00 IST 2022 |  |  | IN_PROGRESS
416 | TT_TASK | QUOTATION STAGE FOR CABLE SUPPORT SYSTEM BZP | Wed Aug 11 08:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Wed Aug 11 08:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  | COMPLETED
420 | TT_TASK | ADJUSTMENT OF CABLE SUPPORT ACC. TO MANUFACTURER STANDARD | Thu Sep 30 08:00:00 IDT 2021 | Wed Nov 24 17:00:00 IST 2021 | Thu Sep 30 08:00:00 IDT 2021 | Wed Nov 24 17:00:00 IST 2021 |  | COMPLETED
422 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UBF AREA (FIRST SUBMISSION) | Thu Aug 12 08:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 | Thu Aug 12 08:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
423 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UBA71 (FIRST SUBMISSION) | Fri Oct 22 08:00:00 IDT 2021 | Sun Dec 05 17:00:00 IST 2021 | Fri Oct 22 08:00:00 IDT 2021 | Sun Dec 05 17:00:00 IST 2021 |  | COMPLETED
424 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UBA11 (FIRST SUBMISSION) | Thu Sep 23 08:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 | Thu Sep 23 08:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  | COMPLETED
425 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UBA81 (FIRST SUBMISSION) | Fri Oct 29 08:00:00 IDT 2021 | Tue Jan 04 17:00:00 IST 2022 | Fri Oct 29 08:00:00 IDT 2021 | Tue Jan 04 17:00:00 IST 2022 |  | COMPLETED
426 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM 90UBA10 (FIRST SUBMISSION) | Fri Oct 08 08:00:00 IDT 2021 | Thu Oct 21 17:00:00 IDT 2021 | Fri Oct 08 08:00:00 IDT 2021 | Thu Oct 21 17:00:00 IDT 2021 |  | COMPLETED
427 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UMC (FIRST SUBMISSION) | Fri Dec 24 08:00:00 IST 2021 | Fri Jan 07 17:00:00 IST 2022 | Fri Dec 24 08:00:00 IST 2021 | Fri Jan 07 17:00:00 IST 2022 |  | COMPLETED
428 | TT_TASK | DETAIL DESIGN CABLE SUPPORT SYSTEM 20UMY (FIRST SUBMISSION) | Fri Nov 05 08:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 | Fri Nov 05 08:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  | COMPLETED
429 | TT_TASK | MANUFACTURING / SHOP TEST CABLE SUPPORT SYSTEM BZP (LOT 1) | Sat Jan 15 08:00:00 IST 2022 | Fri Mar 18 17:00:00 IST 2022 | Sat Jan 15 08:00:00 IST 2022 |  |  | IN_PROGRESS
430 | TT_TASK | MANUFACTURING / SHOP TEST CABLE SUPPORT SYSTEM BZP (LOT 2) | Sun May 08 08:00:00 IDT 2022 | Wed Jun 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
435 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CABLE SUPPORT SYSTEM BZP (LOT 1) | Sat Mar 19 08:00:00 IST 2022 | Fri Apr 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
436 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CABLE SUPPORT SYSTEM BZP (LOT 2) | Thu Jun 23 08:00:00 IDT 2022 | Mon Jul 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
437 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION LIGHTING & SMALL POWER BZL HIGHBAY, 20UMC | Fri Apr 08 08:00:00 IDT 2022 | Thu Apr 14 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
438 | TT_TASK | TRANSPORT CABLE SUPPORT SYSTEM BZP (LOT 1) (SOUTH KOREA) | Sat Apr 02 08:00:00 IDT 2022 | Fri Apr 15 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
439 | TT_TASK | TRANSPORT CABLE SUPPORT SYSTEM BZP (LOT 2) | Tue Jul 19 08:00:00 IDT 2022 | Mon Aug 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
440 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION LIGHTING & SMALL POWER BZL COMPLETE PLANT | Fri Jun 24 08:00:00 IDT 2022 | Thu Jun 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
444 | TT_TASK | TECHNICAL CLARIFICATION BOP I&C | Fri Jan 15 08:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 |  | COMPLETED
446 | TT_TASK | ENGINEERING CLOSED LOOP CONTROLS | Fri Sep 03 08:00:00 IDT 2021 | Sun Jan 16 17:00:00 IST 2022 | Fri Sep 03 08:00:00 IDT 2021 | Sun Jan 16 17:00:00 IST 2022 |  | COMPLETED
447 | TT_TASK | ENGINEERING FUP'S UNIT COORDINATION | Mon Feb 07 08:00:00 IST 2022 | Mon Aug 01 17:00:00 IDT 2022 | Mon Feb 07 08:00:00 IST 2022 |  |  | IN_PROGRESS
448 | TT_TASK | DESIGN REVIEW I&C AUTOMATION HMI | Mon Jan 17 08:00:00 IST 2022 | Sun Feb 06 17:00:00 IST 2022 | Mon Jan 17 08:00:00 IST 2022 | Sun Feb 06 17:00:00 IST 2022 |  | COMPLETED
449 | TT_TASK | IMPLEMENTATION HARDWARE PROXIES FUPs & OM COMBINED CYCLE | Mon Jan 31 08:00:00 IST 2022 | Sun Feb 27 17:00:00 IST 2022 | Mon Jan 31 08:00:00 IST 2022 | Sun Feb 27 17:00:00 IST 2022 |  | COMPLETED
450 | TT_TASK | REVISION I&C DOCUMENTS | Mon Feb 07 08:00:00 IST 2022 | Sun Feb 27 17:00:00 IST 2022 | Mon Feb 07 08:00:00 IST 2022 | Sun Feb 27 17:00:00 IST 2022 |  | COMPLETED
454 | TT_TASK | BOP I&C SCOPE CALCULATION | Fri Feb 26 08:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 | Fri Feb 26 08:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 |  | COMPLETED
456 | TT_TASK | HW ENGINEERING BOP I&C | Fri Apr 09 08:00:00 IDT 2021 | Fri Dec 17 17:00:00 IST 2021 | Fri Apr 09 08:00:00 IDT 2021 | Fri Dec 17 17:00:00 IST 2021 |  | COMPLETED
459 | TT_TASK | SW ENGINEERING BOP I&C, T3000 DB MERGING Fail Safe | Sun Sep 19 08:00:00 IDT 2021 | Sun Jan 16 17:00:00 IST 2022 | Sun Sep 19 08:00:00 IDT 2021 | Sun Jan 16 17:00:00 IST 2022 |  | COMPLETED
461 | TT_TASK | SW ENGINEERING BOP I&C, T3000 DB MERGING, PROXIE GENERATION | Tue Aug 02 08:00:00 IDT 2022 | Mon Sep 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
462 | TT_TASK | Filling Meas/Consumer list IC tasks | Fri Mar 26 08:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Mar 26 08:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
463 | TT_TASK | SW ENGINEERING BOP I&C, T3000 DB MERGING non Fail Safe | Mon Feb 07 08:00:00 IST 2022 | Sun Jul 03 17:00:00 IDT 2022 | Mon Feb 07 08:00:00 IST 2022 |  | 232.0 | IN_PROGRESS
469 | TT_TASK | Order of BOP I&C CABLES (PREPARATION RFQ/QUOTATION STAGE) | Sat Aug 28 08:00:00 IDT 2021 | Fri Dec 10 17:00:00 IST 2021 | Sat Aug 28 08:00:00 IDT 2021 | Fri Dec 10 17:00:00 IST 2021 |  | COMPLETED
472 | TT_TASK | DETAIL DESIGN / MANUFACTURING/ SHOP TEST CCR FURNITURE AND HMI EQUIPMENT | Fri Jun 04 08:00:00 IDT 2021 | Mon Apr 04 17:00:00 IDT 2022 | Fri Jun 04 08:00:00 IDT 2021 |  |  | IN_PROGRESS
473 | TT_TASK | DETAIL DESIGN / MANUFACTURING/ SHOP TEST FOR BOP I&C FIELD DEVICES | Sat May 15 08:00:00 IDT 2021 | Tue Mar 15 17:00:00 IST 2022 | Sat May 15 08:00:00 IDT 2021 |  |  | IN_PROGRESS
476 | TT_TASK | DEVELOPMENT CENTRAL CONTROL ROOM & I&C EQUIPMENT CONCEPT PLAN | Fri Jan 15 08:00:00 IST 2021 | Fri May 14 17:00:00 IDT 2021 | Fri Jan 15 08:00:00 IST 2021 | Fri May 14 17:00:00 IDT 2021 |  | COMPLETED
477 | TT_TASK | DETAIL DESIGN / LAYOUT FOR CCR / CONNECTION TO EXISTING CCR / REVIEW / APPROVAL | Sat May 15 08:00:00 IDT 2021 | Thu Dec 09 17:00:00 IST 2021 | Sat May 15 08:00:00 IDT 2021 | Thu Dec 09 17:00:00 IST 2021 |  | COMPLETED
478 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION BOP I&C FIELD DEVICES | Wed Mar 16 08:00:00 IST 2022 | Tue Apr 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
479 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CCR FURNITURE AND HMI EQUIPMENT | Tue Apr 05 08:00:00 IDT 2022 | Mon May 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
480 | TT_TASK | OPTIMIZATION AUTOMATIC SEQUENCE CONTROL 20 | Mon Jun 19 08:00:00 IDT 2023 | Wed Jun 21 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
481 | TT_TASK | BASIC DESIGN / SPECIFICATION PROT./SYNCHR./METERING CHA/CHY | Sat May 01 08:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Sat May 01 08:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 |  | COMPLETED
483 | TT_TASK | QUOTATION STAGE PPROT./SYNCHR./METERING CHA/CHY | Wed Jun 23 08:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 | Wed Jun 23 08:00:00 IDT 2021 | Wed Sep 08 17:00:00 IDT 2021 |  | COMPLETED
485 | TT_TASK | PROJECT DEFINITION / SYSTEM DESCRIPTION FOR THE CUSTOMER | Thu Jun 24 08:00:00 IDT 2021 | Wed Jul 21 17:00:00 IDT 2021 | Thu Jun 24 08:00:00 IDT 2021 | Wed Jul 21 17:00:00 IDT 2021 |  | COMPLETED
488 | TT_TASK | DETAILED PLANNING THERMODYN. DIAGN. | Thu Jul 22 08:00:00 IDT 2021 | Wed Oct 13 17:00:00 IDT 2021 | Thu Jul 22 08:00:00 IDT 2021 | Wed Oct 13 17:00:00 IDT 2021 |  | COMPLETED
489 | TT_TASK | SYSTEM SETUP THERMODYN. DIAGN. AT PLANT SHOP TEST FIELD | Thu Oct 14 08:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 | Thu Oct 14 08:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 |  | COMPLETED
490 | TT_TASK | PRELIMINARY PRODUCT MANUAL THERMODYN. DIAGN. | Thu Oct 21 08:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 | Thu Oct 21 08:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 |  | COMPLETED
491 | TT_TASK | SERVER CHECK WITHIN PRECOMMISSIONING (PLANT SHOP TEST) | Mon Mar 21 08:00:00 IST 2022 | Sun Mar 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
492 | TT_TASK | TRANSPORT THERMODYN. DIAGNOSIS SERVER | Sun Feb 05 08:00:00 IST 2023 | Sat Apr 01 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
493 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION THERMODYN. DIAGNOSIS SERVER | Sun Jan 08 08:00:00 IST 2023 | Sat Feb 04 17:00:00 IST 2023 |  |  |  | NOT_STARTED
494 | TT_TASK | ERECTION THERMODYNAMIC SERVER | Sun Apr 02 08:00:00 IDT 2023 | Sat Apr 08 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
495 | TT_TASK | DETAIL DESIGN / MANUFACTURING/ SHOP TEST FOR BOP I&C FIELD CABINETS | Fri Jul 30 08:00:00 IDT 2021 | Fri May 20 17:00:00 IDT 2022 | Fri Jul 30 08:00:00 IDT 2021 |  |  | IN_PROGRESS
498 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION BOP I&C FIELD CABINETS | Sat May 21 08:00:00 IDT 2022 | Fri Jun 17 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
499 | TT_TASK | TRANSPORT BOP I&C FIELD CABINETS | Thu Aug 11 08:00:00 IDT 2022 | Wed Oct 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
500 | TT_TASK | TRANSPORT BOP I&C FIELD DEVICES | Thu Aug 11 08:00:00 IDT 2022 | Wed Oct 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
501 | TT_TASK | TRANSPORT CCR FURNITURE AND HMI EQUIPMENT | Tue May 03 08:00:00 IDT 2022 | Mon Jun 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
503 | TT_TASK | BASIC DESIGN / SPECIFICATION / PLANTLAYOUT DWGS BOQ CCTV SYSTEM CYP | Sun Sep 12 08:00:00 IDT 2021 | Thu Jan 27 17:00:00 IST 2022 | Sun Sep 12 08:00:00 IDT 2021 | Thu Jan 27 17:00:00 IST 2022 |  | COMPLETED
505 | TT_TASK | QUOTATION STAGE CCTV SYSTEM CYP | Sat Mar 05 08:00:00 IST 2022 | Sat Apr 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
514 | TT_TASK | MANUFACTURING / SHOP TEST CCTV SYSTEM CYP | Sun May 01 08:00:00 IDT 2022 | Sun Oct 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
517 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CCTV SYSTEM CYP | Mon Oct 03 08:00:00 IDT 2022 | Tue Nov 01 17:00:00 IST 2022 |  |  |  | NOT_STARTED
518 | TT_TASK | TRANSPORT CCTV SYSTEM CYP | Wed Nov 02 08:00:00 IST 2022 | Thu Dec 01 17:00:00 IST 2022 |  |  |  | NOT_STARTED
520 | TT_TASK | ERECTION CCTV SYSTEM IN OTHER BUILDINGS (EXCEPT UMC) | Fri Feb 24 08:00:00 IST 2023 | Thu Apr 20 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
522 | TT_TASK | COMMISSIONING TELECOMMUNICATION ENTIRE PLANT | Sat May 27 08:00:00 IDT 2023 | Fri Jun 16 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
531 | TT_TASK | BASIC DESIGN / PREP. RFQ GAS FINAL FILTER/ PREHEATER 20EKG | Tue Feb 02 08:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Tue Feb 02 08:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 |  | COMPLETED
532 | TT_TASK | BASIC DESIGN / PREP. RFQ FUEL GAS RECEIVING AND MIXING SYSTEM EK | Tue Jan 26 08:00:00 IST 2021 | Tue Mar 30 17:00:00 IDT 2021 | Tue Jan 26 08:00:00 IST 2021 | Tue Mar 30 17:00:00 IDT 2021 |  | COMPLETED
533 | TT_TASK | QUOTATION STAGE GAS FINAL FILTER/ PREHEATER 20EKG | Fri Mar 26 08:00:00 IDT 2021 | Sun Jun 27 17:00:00 IDT 2021 | Fri Mar 26 08:00:00 IDT 2021 | Sun Jun 27 17:00:00 IDT 2021 |  | COMPLETED
534 | TT_TASK | QUOTATION STAGE FUEL GAS RECEIVING AND MIXING SYSTEM EK | Wed Mar 31 08:00:00 IDT 2021 | Sun Jun 27 17:00:00 IDT 2021 | Wed Mar 31 08:00:00 IDT 2021 | Sun Jun 27 17:00:00 IDT 2021 |  | COMPLETED
542 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION GAS FINAL FILTER/ PREHEATER 20EKG | Wed Jul 20 08:00:00 IDT 2022 | Tue Aug 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
544 | TT_TASK | ENGINEERING P&ID'S G-SYSTEMS | Fri Jan 29 08:00:00 IST 2021 | Sat May 29 17:00:00 IDT 2021 | Fri Jan 29 08:00:00 IST 2021 | Sat May 29 17:00:00 IDT 2021 |  | COMPLETED
546 | TT_TASK | REVISION P&ID'S AFTER 3D DRV G-SYSTEMS | Sun Jul 11 08:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Sun Jul 11 08:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 |  | COMPLETED
547 | TT_TASK | DESIGN DATA SHEETS G-COMPONENTS | Sat Oct 17 08:00:00 IDT 2020 | Fri Jan 29 17:00:00 IST 2021 | Sat Oct 17 08:00:00 IDT 2020 | Fri Jan 29 17:00:00 IST 2021 |  | COMPLETED
551 | TT_TASK | DESIGN REVIEW INCL. SIL-STUDY G-SYSTEMS | Sun May 30 08:00:00 IDT 2021 | Sat Jul 03 17:00:00 IDT 2021 | Sun May 30 08:00:00 IDT 2021 | Sat Jul 03 17:00:00 IDT 2021 |  | COMPLETED
553 | TT_TASK | HARA / SIL-STUDY ASSESSMENT OF NONSTANDARD SYSTEMS | Sun Feb 28 08:00:00 IST 2021 | Sat Jul 03 17:00:00 IDT 2021 | Sun Feb 28 08:00:00 IST 2021 | Sat Jul 03 17:00:00 IDT 2021 |  | COMPLETED
554 | TT_TASK | HARA / SIL-STUDY ASSESSMENT OF NONSTANDARD SYSTEMS | Sun Jul 04 08:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 | Sun Jul 04 08:00:00 IDT 2021 | Sat Jul 10 17:00:00 IDT 2021 |  | COMPLETED
555 | TT_TASK | DATA MANAGEMENT G-SYSTEMS | Sun Jul 04 08:00:00 IDT 2021 | Sat Sep 04 17:00:00 IDT 2021 | Sun Jul 04 08:00:00 IDT 2021 | Sat Sep 04 17:00:00 IDT 2021 |  | COMPLETED
557 | TT_TASK | I&C SW ENGINEERING FUPS & HMI'S G-SYSTEM | Wed Sep 01 08:00:00 IDT 2021 | Wed Jun 29 17:00:00 IDT 2022 | Wed Sep 01 08:00:00 IDT 2021 |  | 1216.0 | IN_PROGRESS
559 | TT_TASK | SYSTEM DESCRIPTION G-SYSTEMS | Fri Jan 29 08:00:00 IST 2021 | Sat Feb 27 17:00:00 IST 2021 | Fri Jan 29 08:00:00 IST 2021 | Sat Feb 27 17:00:00 IST 2021 |  | COMPLETED
560 | TT_TASK | PREPARATION P&ID'S G-SYSTEMS (INPUT FOR M1) | Mon Jan 04 08:00:00 IST 2021 | Sun Feb 14 17:00:00 IST 2021 | Mon Jan 04 08:00:00 IST 2021 | Sun Feb 14 17:00:00 IST 2021 |  | COMPLETED
567 | TT_TASK | CONTRACT REVIEW / PREP. RFQ SUMP PUMP GM | Tue May 04 08:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue May 04 08:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 |  | COMPLETED
568 | TT_TASK | QUOTATION STAGE SUMP PUMP GM | Sat May 15 08:00:00 IDT 2021 | Wed Oct 13 17:00:00 IDT 2021 | Sat May 15 08:00:00 IDT 2021 | Wed Oct 13 17:00:00 IDT 2021 |  | COMPLETED
570 | TT_TASK | DESIGN DATA SHEETS SUMP PUMP GM | Sat Jan 30 08:00:00 IST 2021 | Mon May 03 17:00:00 IDT 2021 | Sat Jan 30 08:00:00 IST 2021 | Mon May 03 17:00:00 IDT 2021 |  | COMPLETED
573 | TT_TASK | MANUFACTURING / SHOP TEST SUMP PUMP GM | Thu Oct 14 08:00:00 IDT 2021 | Mon Apr 25 17:00:00 IDT 2022 | Thu Oct 14 08:00:00 IDT 2021 |  |  | IN_PROGRESS
576 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION SUMP PUMP GM | Tue Apr 26 08:00:00 IDT 2022 | Mon May 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
577 | TT_TASK | TRANSPORT SUMP PUMP GM | Tue May 24 08:00:00 IDT 2022 | Mon Jul 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
579 | TT_TASK | I&C SW ENGINEERING FUPS & HMI'S HRSG-SYSTEM | Wed Sep 01 08:00:00 IDT 2021 | Wed Jun 29 17:00:00 IDT 2022 | Wed Sep 01 08:00:00 IDT 2021 |  | 1216.0 | IN_PROGRESS
580 | TT_TASK | PREPARATION P&ID'S HRSG - SYSTEMS (INPUT FOR M1) | Sat Dec 12 08:00:00 IST 2020 | Fri Jan 29 17:00:00 IST 2021 | Sat Dec 12 08:00:00 IST 2020 | Fri Jan 29 17:00:00 IST 2021 |  | COMPLETED
581 | TT_TASK | TECHNICAL CLARIFICATION HRSG | Sat Aug 01 08:00:00 IDT 2020 | Wed Dec 30 17:00:00 IST 2020 | Sat Aug 01 08:00:00 IDT 2020 | Wed Dec 30 17:00:00 IST 2020 |  | COMPLETED
583 | TT_TASK | HRSG ENGINEERING / PREPARATION BD SUBMISSION - STACK / MAINFRAME | Wed Jan 27 08:00:00 IST 2021 | Sat May 15 17:00:00 IDT 2021 | Wed Jan 27 08:00:00 IST 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
584 | TT_TASK | HRSG ENGINEERING / PREPARATION BD SUBMISSION - PLATFORMS/STEELWORK | Sun May 16 08:00:00 IDT 2021 | Fri Feb 25 17:00:00 IST 2022 | Sun May 16 08:00:00 IDT 2021 | Fri Feb 25 17:00:00 IST 2022 |  | COMPLETED
587 | TT_TASK | DESIGN REVIEW INCL. SIL-STUDY HRSG-SYSTEMS | Fri Mar 19 08:00:00 IST 2021 | Thu Apr 22 17:00:00 IDT 2021 | Fri Mar 19 08:00:00 IST 2021 | Thu Apr 22 17:00:00 IDT 2021 |  | COMPLETED
590 | TT_TASK | PREPARATION PROCESS DOCUMENTS FOR RFQ HRSG | Sat Aug 01 08:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 | Sat Aug 01 08:00:00 IDT 2020 | Fri Sep 04 17:00:00 IDT 2020 |  | COMPLETED
594 | TT_TASK | PROJECT SPECIFIC ADAPTION OF HRSG SPECIFICATION | Sat Aug 01 08:00:00 IDT 2020 | Fri Aug 14 17:00:00 IDT 2020 | Sat Aug 01 08:00:00 IDT 2020 | Fri Aug 14 17:00:00 IDT 2020 |  | COMPLETED
595 | TT_TASK | OFFER PREPARATION BY HRSG SUPPLIER | Tue Nov 03 08:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 | Tue Nov 03 08:00:00 IST 2020 | Fri Dec 04 17:00:00 IST 2020 |  | COMPLETED
599 | TT_TASK | TECHNIAL CLARIFICATION WITH HRSG SUPPLIERS | Fri Dec 18 08:00:00 IST 2020 | Thu Jan 14 17:00:00 IST 2021 | Fri Dec 18 08:00:00 IST 2020 | Thu Jan 14 17:00:00 IST 2021 |  | COMPLETED
602 | TT_TASK | FINAL NEGOTIATION HRSG | Fri Jan 15 08:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Tue Jan 26 17:00:00 IST 2021 |  | COMPLETED
614 | TT_TASK | PROJECT SPEC. PREL. PIPE ROUTING AND SUPPORT CONCEPT HRSG | Sat Oct 31 08:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 | Sat Oct 31 08:00:00 IST 2020 | Fri Dec 11 17:00:00 IST 2020 |  | COMPLETED
616 | TT_TASK | STRESS ANALYSIS BY MTEC FOR HRSG-SYSTEMS LAB/LBA10/LBB/C | Sat Dec 12 08:00:00 IST 2020 | Fri Jan 22 17:00:00 IST 2021 | Sat Dec 12 08:00:00 IST 2020 | Fri Jan 22 17:00:00 IST 2021 |  | COMPLETED
617 | TT_TASK | REVIEW PIPE STRESS CALCULATION FOR HRSG-SYSTEMS LAB/LBA10/LBB/C | Sat Jan 23 08:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 | Sat Jan 23 08:00:00 IST 2021 | Fri Feb 12 17:00:00 IST 2021 |  | COMPLETED
624 | TT_TASK | BASIC / DETAIL DESIGN / ORDERING / DELIVERY / MANUFACTURING PIPING HRSG20_Last Part (SB | Thu Jan 28 08:00:00 IST 2021 | Wed Apr 06 17:00:00 IDT 2022 | Thu Jan 28 08:00:00 IST 2021 |  |  | IN_PROGRESS
625 | TT_TASK | BASIC / DETAIL DESIGN / ORDERING / DELIVERY / MANUFACTURING PIPING HRSG20_1st part (LB CARBON STEEL) | Thu Jan 28 08:00:00 IST 2021 | Thu Feb 24 17:00:00 IST 2022 | Thu Jan 28 08:00:00 IST 2021 | Thu Feb 24 17:00:00 IST 2022 |  | COMPLETED
626 | TT_TASK | BASIC / DETAIL DESIGN / ORDERING / DELIVERY / MANUFACTURING PIPING HRSG20_2nd part (LB HIGH ALLOY STEEL) | Thu Jan 28 08:00:00 IST 2021 | Thu Mar 03 17:00:00 IST 2022 | Thu Jan 28 08:00:00 IST 2021 |  |  | IN_PROGRESS
627 | TT_TASK | BASIC / DETAIL DESIGN / ORDERING / DELIVERY / MANUFACTURING PIPING HRSG20 INTERNALPIPING | Thu Jan 28 08:00:00 IST 2021 | Thu Feb 24 17:00:00 IST 2022 | Thu Jan 28 08:00:00 IST 2021 | Thu Feb 24 17:00:00 IST 2022 |  | COMPLETED
629 | TT_TASK | BASIC DESIGN MAIN STEEL STRUCTURE HRSG (Main Frame) | Thu Nov 05 08:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 | Thu Nov 05 08:00:00 IST 2020 | Wed Dec 30 17:00:00 IST 2020 |  | COMPLETED
630 | TT_TASK | BD - HRSG PACKAGES SUBMISSION & APPROVAL | Sun May 16 08:00:00 IDT 2021 | Mon Aug 02 17:00:00 IDT 2021 | Sun May 16 00:00:00 IDT 2021 | Tue Aug 03 08:00:00 IDT 2021 |  | COMPLETED
632 | TT_TASK | BD - HRSG PACKAGES SUBMISSION & APPROVAL -RESUBMISSION/WITHDRAWN STACK | Wed Nov 03 08:00:00 IST 2021 | Wed Nov 03 17:00:00 IST 2021 | Wed Nov 03 08:00:00 IST 2021 | Thu Nov 04 00:00:00 IST 2021 |  | COMPLETED
633 | TT_TASK | BD - HRSG PACKAGES SUBMISSION & APPROVAL -RESUBMISSION 2 STACK | Fri Nov 12 08:00:00 IST 2021 | Tue Jan 18 17:00:00 IST 2022 | Fri Nov 12 08:00:00 IST 2021 | Wed Jan 19 00:00:00 IST 2022 |  | COMPLETED
634 | TT_TASK | BD - CONSENT LETTER STACK - BA8 | Thu Feb 24 08:00:00 IST 2022 | Wed Mar 23 17:00:00 IST 2022 | Thu Feb 24 08:00:00 IST 2022 |  |  | IN_PROGRESS
635 | TT_TASK | BD - HRSG PACKAGES SUBMISSION & APPROVAL -RESUBMISSION1 MAIN FRAME+ STACK | Tue Sep 14 08:00:00 IDT 2021 | Tue Nov 02 17:00:00 IST 2021 | Tue Sep 14 00:00:00 IDT 2021 | Wed Nov 03 00:00:00 IST 2021 |  | COMPLETED
637 | TT_TASK | BD - HRSG PACKAGES SUBMISSION & APPROVAL -RESUBMISSION2 MAIN FRAME | Mon Nov 08 08:00:00 IST 2021 | Thu Jan 06 17:00:00 IST 2022 | Mon Nov 08 08:00:00 IST 2021 | Thu Jan 06 17:00:00 IST 2022 |  | COMPLETED
638 | TT_TASK | BD - HRSG PACKAGES SUBMISSION & APPROVAL -RESUBMISSION3 MAIN FRAME | Mon Jan 10 08:00:00 IST 2022 | Thu Mar 10 17:00:00 IST 2022 | Mon Jan 10 08:00:00 IST 2022 |  |  | IN_PROGRESS
639 | TT_TASK | BD - COMMENCEMENT OF WORK STACK- BA10 | Thu Mar 24 08:00:00 IST 2022 | Wed Mar 30 17:00:00 IDT 2022 |  |  | 160.0 | NOT_STARTED
640 | TT_TASK | BD - HRSG PACKAGES SUBMISSION & APPROVAL-11th AMMENDMENT (PILE); 4th AMMENDMENT (PILE CAP) | Sun Jan 23 08:00:00 IST 2022 | Wed Feb 23 17:00:00 IST 2022 | Sun Jan 23 08:00:00 IST 2022 | Wed Feb 23 17:00:00 IST 2022 |  | COMPLETED
641 | TT_TASK | BD - CONSENT LETTER HRSG PACKAGES-BA8 | Fri Mar 11 08:00:00 IST 2022 | Thu Mar 31 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
642 | TT_TASK | BD - HRSG PLATFORMS SUBMISSION & APPROVAL(Lower platform, piperack, Maintenance Staircase) | Sat Feb 26 08:00:00 IST 2022 | Tue Apr 26 17:00:00 IDT 2022 | Sat Feb 26 08:00:00 IST 2022 |  |  | IN_PROGRESS
643 | TT_TASK | BD - HRSG PLATFORMS SUBMISSION & APPROVAL(Side platforms and roof canopy) | Sat Mar 12 08:00:00 IST 2022 | Tue May 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
644 | TT_TASK | BD - CONSENT LETTER HRSG PLATFORMS(Side platforms and roof canopy) | Wed May 11 08:00:00 IDT 2022 | Tue Jun 07 17:00:00 IDT 2022 |  |  | 808.0 | NOT_STARTED
645 | TT_TASK | BD - CONSENT LETTER HRSG PLATFORMS | Tue Mar 01 08:00:00 IST 2022 | Mon Mar 28 17:00:00 IDT 2022 |  |  | 248.0 | NOT_STARTED
646 | TT_TASK | BD - COMMENCEMENT OF WORK-BA10 | Fri Mar 25 08:00:00 IDT 2022 | Thu Mar 31 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
655 | TT_TASK | BASIC DESIGN STACK HRSG incl. OUTLET DUCT | Fri Dec 04 08:00:00 IST 2020 | Thu Jan 14 17:00:00 IST 2021 | Fri Dec 04 08:00:00 IST 2020 | Thu Jan 14 17:00:00 IST 2021 |  | COMPLETED
657 | TT_TASK | QUOTATION STAGE / ORDERING STACK HRSG incl. OUTLET DUCT | Fri Jan 01 08:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Fri Jan 01 08:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 |  | COMPLETED
658 | TT_TASK | DETAIL DESIGN MAIN STEEL STRUCTURE HRSG | Wed Jan 27 08:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Wed Jan 27 08:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 |  | COMPLETED
659 | TT_TASK | DESIGN SECONDARY STEEL STRUCTURE HRSG | Sat Mar 13 08:00:00 IST 2021 | Thu Jul 15 17:00:00 IDT 2021 | Sat Mar 13 08:00:00 IST 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
660 | TT_TASK | PREPARATION P&ID'S L-SYSTEMS (INPUT FOR M1) | Sun Nov 29 08:00:00 IST 2020 | Mon Feb 15 17:00:00 IST 2021 | Sun Nov 29 08:00:00 IST 2020 | Mon Feb 15 17:00:00 IST 2021 |  | COMPLETED
661 | TT_TASK | ENGINEERING P&ID'S L-SYSTEMS | Sat Dec 12 08:00:00 IST 2020 | Fri Jan 29 17:00:00 IST 2021 | Sat Dec 12 08:00:00 IST 2020 | Fri Jan 29 17:00:00 IST 2021 |  | COMPLETED
662 | TT_TASK | DESIGN REVIEW INTERFACE ST / L-SYSTEMS | Mon Apr 12 08:00:00 IDT 2021 | Sun May 02 17:00:00 IDT 2021 | Mon Apr 12 08:00:00 IDT 2021 | Sun May 02 17:00:00 IDT 2021 |  | COMPLETED
663 | TT_TASK | DATA MANAGEMENT L- SYSTEMS | Wed May 05 08:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed May 05 08:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
664 | TT_TASK | I&C SW ENGINEERING FUPS & HMI'S L-SYSTEM | Wed Sep 01 08:00:00 IDT 2021 | Wed Jun 29 17:00:00 IDT 2022 | Wed Sep 01 08:00:00 IDT 2021 |  | 1216.0 | IN_PROGRESS
665 | TT_TASK | REVISION P&ID'S AFTER 3D DRV L SYSTEMS | Wed May 12 08:00:00 IDT 2021 | Sun Jun 20 17:00:00 IDT 2021 | Wed May 12 08:00:00 IDT 2021 | Sun Jun 20 17:00:00 IDT 2021 |  | COMPLETED
666 | TT_TASK | DESIGN DATA SHEETS L-COMPONENTS | Sun Nov 29 08:00:00 IST 2020 | Sat Feb 06 17:00:00 IST 2021 | Sun Nov 29 08:00:00 IST 2020 | Sat Feb 06 17:00:00 IST 2021 |  | COMPLETED
672 | TT_TASK | DESIGN REVIEW INCL. SIL-STUDY L-SYSTEMS | Wed Mar 31 08:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Mar 31 08:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 |  | COMPLETED
673 | TT_TASK | HARA / SIL-STUDY ASSESSMENT OF NONSTANDARD SYSTEMS | Mon Jan 11 08:00:00 IST 2021 | Tue May 04 17:00:00 IDT 2021 | Mon Jan 11 08:00:00 IST 2021 | Tue May 04 17:00:00 IDT 2021 |  | COMPLETED
676 | TT_TASK | HARA / SIL-STUDY ASSESSMENT OF STANDARD SYSTEMS | Wed May 05 08:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Wed May 05 08:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 |  | COMPLETED
677 | TT_TASK | SYSTEM DESCRIPTION L-SYSTEMS | Sat Jan 30 08:00:00 IST 2021 | Sun Feb 28 17:00:00 IST 2021 | Sat Jan 30 08:00:00 IST 2021 | Sun Feb 28 17:00:00 IST 2021 |  | COMPLETED
684 | TT_TASK | CONTRACT REVIEW, PREPARATION RFQ BYPASS STATION 20LBF | Wed Dec 02 08:00:00 IST 2020 | Tue Dec 29 17:00:00 IST 2020 | Wed Dec 02 08:00:00 IST 2020 | Tue Dec 29 17:00:00 IST 2020 |  | COMPLETED
685 | TT_TASK | QUOTATION STAGE BYPASS STATION 20LBF | Wed Dec 30 08:00:00 IST 2020 | Tue Jan 26 17:00:00 IST 2021 | Wed Dec 30 08:00:00 IST 2020 | Tue Jan 26 17:00:00 IST 2021 |  | COMPLETED
689 | TT_TASK | BASIC DESIGN / QUOTATION STAGE / ORDERING BLOW DOWN TANK LBH | Wed Nov 18 08:00:00 IST 2020 | Tue Jan 26 17:00:00 IST 2021 | Wed Nov 18 08:00:00 IST 2020 | Tue Jan 26 17:00:00 IST 2021 |  | COMPLETED
696 | TT_TASK | TECHNICAL CLARIFCATION / PREP. RFQ CONDENSATE EXTRACTION PUMPS LCB | Fri Jan 15 08:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 |  | COMPLETED
697 | TT_TASK | QUOTATION STAGE CONDENSATE EXTRACTION PUMP LCB | Fri Feb 05 08:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 | Fri Feb 05 08:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 |  | COMPLETED
702 | TT_TASK | PREPARATION RFQ CONDENSATE POLISHING PLANT 20LD | Wed Mar 03 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 | Wed Mar 03 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 |  | COMPLETED
705 | TT_TASK | BASIC DESIGN / PREPARATION P&ID'S CONDENSATE POLISHING PLANT 20LD | Wed Feb 03 08:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Wed Feb 03 08:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 |  | COMPLETED
706 | TT_TASK | QUOTATION STAGE CONDENSATE POLISHING PLANT 20LD | Fri Mar 19 08:00:00 IST 2021 | Tue May 18 17:00:00 IDT 2021 | Fri Mar 19 08:00:00 IST 2021 | Tue May 18 17:00:00 IDT 2021 |  | COMPLETED
710 | TT_TASK | PREPARATION RFQ LOGISTICS CONTRACT | Fri Feb 26 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 | Fri Feb 26 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 |  | COMPLETED
711 | TT_TASK | QUOTATION STAGE LOGISTICS CONTRACT | Fri Mar 19 08:00:00 IST 2021 | Thu Apr 15 17:00:00 IDT 2021 | Fri Mar 19 08:00:00 IST 2021 | Thu Apr 15 17:00:00 IDT 2021 |  | COMPLETED
712 | TT_TASK | REVIEW OF QUOTATIONS & PREPARATION OF BID COMPARISON SHEET LOGISTICS CONTRACT | Fri Apr 16 08:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Fri Apr 16 08:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 |  | COMPLETED
714 | TT_TASK | CONTRACTUAL CLARIFICATION, QUALIFICATION AND FINAL EVALUATION | Fri May 07 08:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Fri May 07 08:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 |  | COMPLETED
715 | TT_TASK | CONTRACT AWARD LOGISTICS CONTRACT (SOURCING BOARD / FINAL CONTRACT DOCUMENTS) | Fri May 28 08:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Fri May 28 08:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 |  | COMPLETED
718 | TT_TASK | PREPARATION PERIOD FOR LOGISTICS CONTRACTOR (HEAVY LOADS) | Fri Jun 11 08:00:00 IDT 2021 | Tue Dec 07 17:00:00 IST 2021 | Fri Jun 11 08:00:00 IDT 2021 | Tue Dec 07 17:00:00 IST 2021 |  | COMPLETED
725 | TT_TASK | CLIENT TERMINAL POINTS DOCUMENTS | Fri Jan 15 08:00:00 IST 2021 | Sat Apr 10 17:00:00 IDT 2021 | Fri Jan 15 08:00:00 IST 2021 | Sat Apr 10 17:00:00 IDT 2021 |  | COMPLETED
726 | TT_TASK | PREPARATION P&ID'S P-SYSTEMS (INPUT FOR M1) | Sun Nov 08 08:00:00 IST 2020 | Sun Feb 14 17:00:00 IST 2021 | Sun Nov 08 08:00:00 IST 2020 | Sun Feb 14 17:00:00 IST 2021 |  | COMPLETED
727 | TT_TASK | ENGINEERING P&ID'S P-SYSTEMS | Fri Jan 01 08:00:00 IST 2021 | Thu Feb 18 17:00:00 IST 2021 | Fri Jan 01 08:00:00 IST 2021 | Thu Feb 18 17:00:00 IST 2021 |  | COMPLETED
728 | TT_TASK | DATA MANAGEMENT P SYSTEMS | Wed May 05 08:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 | Wed May 05 08:00:00 IDT 2021 | Tue Jul 06 17:00:00 IDT 2021 |  | COMPLETED
729 | TT_TASK | I&C SW ENGINEERING FUPS & HMI'S P-SYSTEM | Wed Sep 01 08:00:00 IDT 2021 | Wed Jun 29 17:00:00 IDT 2022 | Wed Sep 01 08:00:00 IDT 2021 |  | 1216.0 | IN_PROGRESS
730 | TT_TASK | REVISION P&ID'S AFTER 3D DRV P SYSTEMS | Fri Jan 15 08:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Thu Feb 11 17:00:00 IST 2021 |  | COMPLETED
731 | TT_TASK | DESIGN DATA SHEETS P-COMPONENTS | Tue Nov 03 08:00:00 IST 2020 | Tue Mar 02 17:00:00 IST 2021 | Tue Nov 03 08:00:00 IST 2020 | Tue Mar 02 17:00:00 IST 2021 |  | COMPLETED
737 | TT_TASK | DESIGN REVIEW INCL. SIL-STUDY P-SYSTEMS | Wed Mar 31 08:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Mar 31 08:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 |  | COMPLETED
738 | TT_TASK | HARA / SIL-STUDY ASSESSMENT OF NONSTANDARD SYSTEMS | Wed Jan 13 08:00:00 IST 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Jan 13 08:00:00 IST 2021 | Tue May 04 17:00:00 IDT 2021 |  | COMPLETED
740 | TT_TASK | HARA / SIL-STUDY ASSESSMENT OF STANDARD SYSTEMS | Wed May 05 08:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Wed May 05 08:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 |  | COMPLETED
742 | TT_TASK | SYSTEM DESCRIPTION P-SYSTEMS | Tue Jan 26 08:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 | Tue Jan 26 08:00:00 IST 2021 | Mon Mar 01 17:00:00 IST 2021 |  | COMPLETED
744 | TT_TASK | BASIC DESIGN OF PIPING / ROUTING PAB | Fri Jan 15 08:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Feb 08 17:00:00 IST 2021 |  | COMPLETED
746 | TT_TASK | 3D MODEL PAB | Tue Feb 02 08:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Tue Feb 02 08:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 |  | COMPLETED
747 | TT_TASK | FINALIZE BASIC DESIGN PAB | Mon Feb 15 08:00:00 IST 2021 | Sun Mar 14 17:00:00 IST 2021 | Mon Feb 15 08:00:00 IST 2021 | Sun Mar 14 17:00:00 IST 2021 |  | COMPLETED
754 | TT_TASK | CONTRACT REVIEW / PREP. CIRC. CW PUMP PAC | Sat Dec 19 08:00:00 IST 2020 | Fri Jan 29 17:00:00 IST 2021 | Sat Dec 19 08:00:00 IST 2020 | Fri Jan 29 17:00:00 IST 2021 |  | COMPLETED
755 | TT_TASK | QUOTATION STAGE CIRC. CW PUMP PAC | Sat Jan 30 08:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 | Sat Jan 30 08:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 |  | COMPLETED
757 | TT_TASK | DESIGN DATA SHEETS CIRC. CW PUMP PAC | Sat Jan 16 08:00:00 IST 2021 | Fri Jan 29 17:00:00 IST 2021 | Sat Jan 16 08:00:00 IST 2021 | Fri Jan 29 17:00:00 IST 2021 |  | COMPLETED
759 | TT_TASK | MANUFACTURING / SHOP TEST CIRC. CW PUMP 20PAC | Fri Apr 09 08:00:00 IDT 2021 | Sun May 01 17:00:00 IDT 2022 | Fri Apr 09 08:00:00 IDT 2021 |  |  | IN_PROGRESS
763 | TT_TASK | BASIC DESIGN / PREP. RFQ COOLING TOWER EQUIPMENT PAD (GFK) | Sun Nov 01 08:00:00 IST 2020 | Sat Dec 19 17:00:00 IST 2020 | Sun Nov 01 08:00:00 IST 2020 | Sat Dec 19 17:00:00 IST 2020 |  | COMPLETED
764 | TT_TASK | QUOTATION STAGE COOLING TOWER EQUIPMENT PAD (GFK) | Sun Dec 20 08:00:00 IST 2020 | Thu Feb 18 17:00:00 IST 2021 | Sun Dec 20 08:00:00 IST 2020 | Thu Feb 18 17:00:00 IST 2021 |  | COMPLETED
775 | TT_TASK | TRANSPORT PARTS EMB. INTO RISERES 20PAD | Fri Aug 13 08:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 | Fri Aug 13 08:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  | COMPLETED
777 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - PARTS EMB. INTO RISERES 20PAD | Tue Jul 13 08:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Tue Jul 13 08:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
778 | TT_TASK | CONTRACT REVIEW / PREP. RFQ SERVICE COOLING WATER BOOSTER PUMP PCB | Sun Jan 10 08:00:00 IST 2021 | Sat Feb 06 17:00:00 IST 2021 | Sun Jan 10 08:00:00 IST 2021 | Sat Feb 06 17:00:00 IST 2021 |  | COMPLETED
780 | TT_TASK | QUOTATION STAGE SERVICE COOLING WATER BOOSTER PUMP PCB | Sun Feb 07 08:00:00 IST 2021 | Tue Mar 30 17:00:00 IDT 2021 | Sun Feb 07 08:00:00 IST 2021 | Tue Mar 30 17:00:00 IDT 2021 |  | COMPLETED
789 | TT_TASK | CONCEPT DESIGN HVAC SYSTEM SA | Fri Jan 15 08:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Thu Mar 04 17:00:00 IST 2021 |  | COMPLETED
792 | TT_TASK | BASIC DESIGN before DF (part I) HVAC SYSTEM SA | Fri Mar 05 08:00:00 IST 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Mar 05 08:00:00 IST 2021 | Thu Apr 29 17:00:00 IDT 2021 |  | COMPLETED
793 | TT_TASK | BASIC DESIGN after DF (part II) HVAC SYSTEM SA | Fri Apr 30 08:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 | Fri Apr 30 08:00:00 IDT 2021 | Thu May 06 17:00:00 IDT 2021 |  | COMPLETED
800 | TT_TASK | PREPARATION FIRE-/ EXPLOSION PROTECTION CONCEPT | Tue Sep 01 08:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 | Tue Sep 01 08:00:00 IDT 2020 | Mon Sep 28 17:00:00 IDT 2020 |  | COMPLETED
801 | TT_TASK | PREPARATION OF FIRE PROTECTION CONCEPT FOR SUBMISSION TO BD | Fri Jan 15 08:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 |  | COMPLETED
802 | TT_TASK | PREPARATION OF EXPLOSION PROTECTION CONCEPT FOR SUBMISSION TO BD | Fri Jan 15 08:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Fri Mar 19 17:00:00 IST 2021 |  | COMPLETED
803 | TT_TASK | BD - SUBMISSON & APPROVAL - FIRE PROTECTION CONCEPT | Fri Feb 05 08:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 | Fri Feb 05 08:00:00 IST 2021 | Mon Apr 05 17:00:00 IDT 2021 |  | COMPLETED
804 | TT_TASK | UPDATE OF FIRE PROTECTION CONCEPT AFTER BD ALIGNMENT | Tue Apr 06 08:00:00 IDT 2021 | Mon Apr 19 17:00:00 IDT 2021 | Tue Apr 06 08:00:00 IDT 2021 | Mon Apr 19 17:00:00 IDT 2021 |  | COMPLETED
805 | TT_TASK | SUPPLIER P&ID's PREPARATION / FRIST DESIGN DWGS (ISOMETRICS) | Sat Jul 24 08:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Sat Jul 24 08:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 |  | COMPLETED
806 | TT_TASK | BASIC DESIGN FIRE FIGHTING SYSTEMS SG- | Tue Mar 16 08:00:00 IST 2021 | Mon Apr 19 17:00:00 IDT 2021 | Tue Mar 16 08:00:00 IST 2021 | Mon Apr 19 17:00:00 IDT 2021 |  | COMPLETED
807 | TT_TASK | BASIC DESIGN DWGS FIRE FIGHTING SYSTEMS SG- (incl. Design Review) | Tue Apr 20 08:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Tue Apr 20 08:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
808 | TT_TASK | BASIC DESIGN FIRE FIGHTING RING MAIN SGA (prel. LH020) | Mon May 31 08:00:00 IDT 2021 | Sun Jul 11 17:00:00 IDT 2021 | Mon May 31 08:00:00 IDT 2021 | Sun Jul 11 17:00:00 IDT 2021 |  | COMPLETED
811 | TT_TASK | P&ID, FINALIZE RING MAIN CONCEPT | Fri Jan 15 08:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Thu Feb 04 17:00:00 IST 2021 |  | COMPLETED
812 | TT_TASK | PLANNING 3D MODELLING OF F/F RING MAIN OUTSIDE BUILDING | Fri Jan 29 08:00:00 IST 2021 | Thu Feb 18 17:00:00 IST 2021 | Fri Jan 29 08:00:00 IST 2021 | Thu Feb 18 17:00:00 IST 2021 |  | COMPLETED
814 | TT_TASK | UPDATE RING MAIN DESIGN | Wed Mar 31 08:00:00 IDT 2021 | Tue Apr 13 17:00:00 IDT 2021 | Wed Mar 31 08:00:00 IDT 2021 | Tue Apr 13 17:00:00 IDT 2021 |  | COMPLETED
815 | TT_TASK | FINALIZE RING MAIN BASIC DESIGN | Wed Apr 14 08:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Wed Apr 14 08:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 |  | COMPLETED
817 | TT_TASK | INTERMEDIATE FIRE- & EXPLOSION PROTECTION CONCEPT | Tue Sep 29 08:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 | Tue Sep 29 08:00:00 IDT 2020 | Mon Oct 19 17:00:00 IDT 2020 |  | COMPLETED
818 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN FIRE MAIN RING | Fri Aug 06 08:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 | Fri Aug 06 08:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
819 | TT_TASK | BD - SUBMISSION & APPROVAL - HYDRAULIC SUBMISSION APPROVAL (FSI/314 SCHEMATIC DWGS SUBMISSION) | Tue Aug 31 08:00:00 IDT 2021 | Sun Dec 05 17:00:00 IST 2021 | Tue Aug 31 08:00:00 IDT 2021 | Sun Dec 05 17:00:00 IST 2021 |  | COMPLETED
820 | TT_TASK | BD - CONSENT LETTER - HYDRAULIC SUBMISSION APPROVAL (FSI/314 SCHEMATIC DWGS SUBMISSION) | Mon Dec 06 08:00:00 IST 2021 | Sun Jan 02 17:00:00 IST 2022 | Mon Dec 06 08:00:00 IST 2021 | Sun Jan 02 17:00:00 IST 2022 |  | COMPLETED
821 | TT_TASK | PREPARATION FINAL FIRE PROTECTION CONCEPT & ESCAPE ROUTE AND FIRE PROTECTION DWGS | Sun Jun 06 08:00:00 IDT 2021 | Sat Jul 03 17:00:00 IDT 2021 | Sun Jun 06 08:00:00 IDT 2021 | Sat Jul 03 17:00:00 IDT 2021 |  | COMPLETED
823 | TT_TASK | PREP. RFQ FIRE FIGHTING SYSTEMS SG- | Fri Jul 02 08:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Jul 02 08:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
826 | TT_TASK | QUOTATION STAGE FIRE FIGHTING SYSTEMS SG- | Fri Jul 16 08:00:00 IDT 2021 | Thu Sep 09 17:00:00 IDT 2021 | Fri Jul 16 08:00:00 IDT 2021 | Thu Sep 09 17:00:00 IDT 2021 |  | COMPLETED
828 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN FIRE FIGHTING | Tue Apr 20 08:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 20 08:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 |  | COMPLETED
829 | TT_TASK | FINALIZATION OF FIRE FIGHTING DESIGN | Sat May 15 08:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 | Sat May 15 08:00:00 IDT 2021 | Fri Jun 18 17:00:00 IDT 2021 |  | COMPLETED
830 | TT_TASK | BD - REVIEW & APPROVAL - FIRE FIGHTING DESIGN | Fri May 28 08:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 | Fri May 28 08:00:00 IDT 2021 | Fri Jul 23 17:00:00 IDT 2021 |  | COMPLETED
831 | TT_TASK | DETAIL DESIGN FIRE MAIN RING / OVERALL FIRE WATER DEMAND MINIMUM CALCULATION | Fri Jun 25 08:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Fri Jun 25 08:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
832 | TT_TASK | FIRE PROTECTION CONCEPT FOR CLIENT REVIEW | Tue Apr 20 08:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 | Tue Apr 20 08:00:00 IDT 2021 | Fri May 14 17:00:00 IDT 2021 |  | COMPLETED
833 | TT_TASK | UPDATED FIRE PROTECTION CONCEPT AFTER ALIGNMENT WITH CLIENT | Sat May 15 08:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 | Sat May 15 08:00:00 IDT 2021 | Fri May 21 17:00:00 IDT 2021 |  | COMPLETED
834 | TT_TASK | FIRE PROTECTION CONCEPT FOR FSD APPROVAL | Sat May 22 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Sat May 22 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 |  | COMPLETED
835 | TT_TASK | UPDATED FIRE PROTECTION CONCEPT AFTER ALIGNMENT WITH FSD | Sun May 30 08:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 | Sun May 30 08:00:00 IDT 2021 | Sat Jun 05 17:00:00 IDT 2021 |  | COMPLETED
836 | TT_TASK | UPDATE FIRE MAIN RING MAIN P&ID's | Wed Mar 03 08:00:00 IST 2021 | Tue Mar 16 17:00:00 IST 2021 | Wed Mar 03 08:00:00 IST 2021 | Tue Mar 16 17:00:00 IST 2021 |  | COMPLETED
838 | TT_TASK | EXPLOSION PROTECTION CONCEPT FOR CLIENT REVIEW | Sat Mar 20 08:00:00 IST 2021 | Tue Apr 13 17:00:00 IDT 2021 | Sat Mar 20 08:00:00 IST 2021 | Tue Apr 13 17:00:00 IDT 2021 |  | COMPLETED
839 | TT_TASK | UPDATED EXPLOSION PROTECTION CONCEPT AFTER ALIGNMENT WITH CLIENT | Wed Apr 14 08:00:00 IDT 2021 | Tue Apr 20 17:00:00 IDT 2021 | Wed Apr 14 08:00:00 IDT 2021 | Tue Apr 20 17:00:00 IDT 2021 |  | COMPLETED
840 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST FIRE FIGHTING RING MAIN SGA | Tue Nov 23 08:00:00 IST 2021 | Sun Jul 10 17:00:00 IDT 2022 | Tue Nov 23 08:00:00 IST 2021 |  |  | IN_PROGRESS
843 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION FIRE FIGHTING RING MAIN SGA | Mon Jun 06 08:00:00 IDT 2022 | Sun Jul 03 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
844 | TT_TASK | TRANSPORT FIRE FIGHTING RING MAIN SGA (HONGKONG) | Mon Jul 04 08:00:00 IDT 2022 | Sun Jul 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
846 | TT_TASK | ERECTION FIRE FIGHTING EXTINGUISHERS SGM | Sun Sep 25 08:00:00 IDT 2022 | Sat Oct 22 17:00:00 IDT 2022 |  |  | 312.0 | NOT_STARTED
849 | TT_TASK | CONTRACT REVIEW / PREP. RFQ CRANE 20SMM01/02 FOR 20UMC | Fri Jan 15 08:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Feb 01 17:00:00 IST 2021 |  | COMPLETED
850 | TT_TASK | QUOTATION STAGE CRANES 20SMM01/02 FOR 20UMC | Tue Feb 02 08:00:00 IST 2021 | Mon Mar 29 17:00:00 IDT 2021 | Tue Feb 02 08:00:00 IST 2021 | Mon Mar 29 17:00:00 IDT 2021 |  | COMPLETED
854 | TT_TASK | CONTRACT REVIEW / PREP. RFQ CRANE 20SMM03 FOR 20UMC | Tue Mar 30 08:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 | Tue Mar 30 08:00:00 IDT 2021 | Mon Apr 12 17:00:00 IDT 2021 |  | COMPLETED
855 | TT_TASK | QUOTATION STAGE CRANES 20SMM03 FOR 20UMC | Tue Apr 13 08:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 | Tue Apr 13 08:00:00 IDT 2021 | Mon Apr 26 17:00:00 IDT 2021 |  | COMPLETED
859 | TT_TASK | BASIC DESIGN PLANT LAYOUT POWER BLOCK AREA (UMC,UPY,UTG01/05,UHA,UVM01,UEY01,UMX,UMY,UHW,UHX,UBA11,ULA,ULY01) | Fri Jan 29 08:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Fri Jan 29 08:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 |  | COMPLETED
861 | TT_TASK | BASIC DESIGN PLANT LAYOUT TRANSFORMER AREA | Fri Feb 26 08:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 | Fri Feb 26 08:00:00 IST 2021 | Wed Apr 07 17:00:00 IDT 2021 |  | COMPLETED
865 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBA8110/20 | Thu Jun 24 08:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Thu Jun 24 00:00:00 IDT 2021 | Fri Sep 03 00:00:00 IDT 2021 |  | COMPLETED
866 | TT_TASK | BD - SUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE - 20UBA8110/20 | Mon Dec 13 08:00:00 IST 2021 | Tue Feb 08 17:00:00 IST 2022 | Mon Dec 13 08:00:00 IST 2021 | Tue Feb 08 17:00:00 IST 2022 |  | COMPLETED
867 | TT_TASK | BD - RESUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE - 20UBA8110/20 | Fri Mar 04 08:00:00 IST 2022 | Mon May 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
868 | TT_TASK | BD - CONSENT LETTER - DESIGN 20UBA8110/20 | Tue May 03 08:00:00 IDT 2022 | Mon May 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
869 | TT_TASK | BD - SUBMISSION & APPROVAL - STEEL STRUCTURE 20UBA8110/20 | Sat Feb 26 08:00:00 IST 2022 | Tue Apr 26 17:00:00 IDT 2022 | Sat Feb 26 08:00:00 IST 2022 |  |  | IN_PROGRESS
870 | TT_TASK | BD - CONSENT LETTER - STEEL STRUCTURE 20UBA8110/20 | Wed Apr 27 08:00:00 IDT 2022 | Tue May 24 17:00:00 IDT 2022 |  |  | 584.0 | NOT_STARTED
871 | TT_TASK | BD - SUBMISSION & APPROVAL - STEEL STRUCTURE 20UBA7910/20 | Mon Feb 28 08:00:00 IST 2022 | Thu Apr 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
872 | TT_TASK | BD - CONSENT LETTER - STEEL STRUCTURE 20UBA7910/20 | Fri Apr 29 08:00:00 IDT 2022 | Thu May 26 17:00:00 IDT 2022 |  |  | 576.0 | NOT_STARTED
873 | TT_TASK | DETAIL DESIGN BARBENDING STRUCTURE UBA7xxx | Fri Oct 01 08:00:00 IDT 2021 | Thu Oct 21 17:00:00 IDT 2021 | Fri Oct 01 08:00:00 IDT 2021 | Thu Oct 21 17:00:00 IDT 2021 |  | COMPLETED
875 | TT_TASK | DETAIL DESIGN BARBENDING STRUCTURE UBA7910/7920 | Wed Mar 16 08:00:00 IST 2022 | Tue Apr 05 17:00:00 IDT 2022 |  |  | 112.0 | NOT_STARTED
877 | TT_TASK | BD - AMENDMENT SUBMISSION - DETAIL DESIGN CONCRETE - UBA7xxx | Mon Dec 13 08:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 | Mon Dec 13 08:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 |  | COMPLETED
878 | TT_TASK | BD - RESUBMISSION AND APPROVAL - STEEL STRUCTURE 20UBA7xxx | Mon Dec 06 08:00:00 IST 2021 | Mon Feb 28 17:00:00 IST 2022 | Mon Dec 06 08:00:00 IST 2021 |  |  | IN_PROGRESS
879 | TT_TASK | DETAIL DESIGN CONCRETE STRUCTURE UBA7xxx REVISED | Tue Jul 27 08:00:00 IDT 2021 | Wed Jan 12 17:00:00 IST 2022 | Tue Jul 27 08:00:00 IDT 2021 | Wed Jan 12 17:00:00 IST 2022 |  | COMPLETED
881 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS UBA7910/7920 | Mon Aug 09 08:00:00 IDT 2021 | Sun Aug 22 17:00:00 IDT 2021 | Mon Aug 09 08:00:00 IDT 2021 | Sun Aug 22 17:00:00 IDT 2021 |  | COMPLETED
883 | TT_TASK | BASIC BUILDING DESIGN INCL. 3D MODEL UBA7xxx | Fri Apr 16 08:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 | Fri Apr 16 08:00:00 IDT 2021 | Fri May 28 17:00:00 IDT 2021 |  | COMPLETED
884 | TT_TASK | DETAIL DESIGN CONCRETE STRUCTURE UBA7xxx | Sat May 29 08:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Sat May 29 08:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
885 | TT_TASK | DETAIL DESIGN CONCRETE STRUCTURE UBA7910/7920 | Thu Jun 24 08:00:00 IDT 2021 | Fri Jan 07 17:00:00 IST 2022 | Thu Jun 24 08:00:00 IDT 2021 | Fri Jan 07 17:00:00 IST 2022 |  | COMPLETED
887 | TT_TASK | BASIC BUILDING DESIGN INCL. 3D MODEL UBA7910/7920 | Thu May 20 08:00:00 IDT 2021 | Wed Jun 23 17:00:00 IDT 2021 | Thu May 20 08:00:00 IDT 2021 | Wed Jun 23 17:00:00 IDT 2021 |  | COMPLETED
888 | TT_TASK | BD - SUBMISSION & APPROVAL - STEEL STRUCTURE 20UBA7xxx | Mon Aug 02 08:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Mon Aug 02 08:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  | COMPLETED
889 | TT_TASK | BD - CONSENT LETTER - STEEL STRUCTURE 20UBA7xxx | Tue Mar 01 09:57:00 IST 2022 | Tue Mar 29 09:57:00 IDT 2022 |  |  |  | NOT_STARTED
890 | TT_TASK | CLIENT - REVIEW - STEELWORK - 20UBX/20UBG | Mon Feb 21 08:00:00 IST 2022 | Thu Mar 17 17:00:00 IST 2022 | Mon Feb 21 08:00:00 IST 2022 |  | 136.0 | IN_PROGRESS
891 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - UBA7xxx | Wed Jul 28 08:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Wed Jul 28 08:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
892 | TT_TASK | BD - SUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION UBA7xxx(2NDPACKAGE) | Mon May 24 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
893 | TT_TASK | BD - CONSENT LETTER - DESIGN UBA7xxx | Tue Jun 15 08:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 |  | COMPLETED
894 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - UBA7910/7920 | Mon Aug 23 08:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Mon Aug 23 08:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 |  | COMPLETED
895 | TT_TASK | BD - SUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE - UBA7910/7920 | Sat Jan 15 08:00:00 IST 2022 | Tue Mar 15 17:00:00 IST 2022 | Sat Jan 15 08:00:00 IST 2022 |  |  | IN_PROGRESS
896 | TT_TASK | BD - CONSENT LETTER - DESIGN UBA7910/7920 | Wed Mar 16 08:00:00 IST 2022 | Tue Apr 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
899 | TT_TASK | BASIC DESIGN STEEL STRUCTURE UBA7xxx | Fri May 28 08:00:00 IDT 2021 | Wed Jun 23 17:00:00 IDT 2021 | Fri May 28 08:00:00 IDT 2021 | Wed Jun 23 17:00:00 IDT 2021 |  | COMPLETED
900 | TT_TASK | DETAIL DESIGN STEEL STRUCTURE UBA7xxx | Thu Jun 24 08:00:00 IDT 2021 | Sun Aug 01 17:00:00 IDT 2021 | Thu Jun 24 08:00:00 IDT 2021 | Sun Aug 01 17:00:00 IDT 2021 |  | COMPLETED
901 | TT_TASK | HANDRAILS AND GRATING DWGS & CONNECTION FORCE REPORT UBA7xxx | Tue Jan 11 08:00:00 IST 2022 | Mon Jan 31 17:00:00 IST 2022 | Tue Jan 11 08:00:00 IST 2022 | Mon Jan 31 17:00:00 IST 2022 |  | COMPLETED
902 | TT_TASK | DETAIL DESIGN STEEL STRUCTURE 20UBA7910/20 | Wed Sep 01 08:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 | Wed Sep 01 08:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  | COMPLETED
903 | TT_TASK | HANDRAILS AND GRATING DWGS & CONNECTION FORCE REPORT 20UBA7910/20 | Sat Sep 25 08:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 | Sat Sep 25 08:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  | COMPLETED
904 | TT_TASK | DETAIL DESIGN STEEL STRUCTURE 20UBA8110/20 | Tue Sep 21 08:00:00 IDT 2021 | Mon Dec 06 17:00:00 IST 2021 | Tue Sep 21 08:00:00 IDT 2021 | Mon Dec 06 17:00:00 IST 2021 |  | COMPLETED
906 | TT_TASK | HANDRAILS AND GRATING DWGS & CONNECTION FORCE REPORT 20UBA8110/20 | Tue Nov 16 08:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 | Tue Nov 16 08:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  | COMPLETED
912 | TT_TASK | BASIC DESIGN / CONCEPTUAL DESIGN & SPECIFICATION ELECTRICAL MODULES UBA | Fri Nov 13 08:00:00 IST 2020 | Sun Feb 28 17:00:00 IST 2021 | Fri Nov 13 08:00:00 IST 2020 | Sun Feb 28 17:00:00 IST 2021 |  | COMPLETED
914 | TT_TASK | QUOTATION STAGE ELECTRICAL MODULES UBA | Mon Mar 01 08:00:00 IST 2021 | Tue May 18 17:00:00 IDT 2021 | Mon Mar 01 08:00:00 IST 2021 | Tue May 18 00:00:00 IDT 2021 |  | COMPLETED
921 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS UBF/UBE | Tue Jul 27 08:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Tue Jul 27 08:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
923 | TT_TASK | DETAIL DESIGN CONCRETE STRUCTURE 20UBE/UBF | Tue Jun 22 08:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Tue Jun 22 08:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
924 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - 20UBE/UBF | Tue Aug 10 08:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Tue Aug 10 08:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 |  | COMPLETED
925 | TT_TASK | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL 20UBE/UBF | Sun Jun 06 08:00:00 IDT 2021 | Mon Jun 21 17:00:00 IDT 2021 | Sun Jun 06 08:00:00 IDT 2021 | Mon Jun 21 17:00:00 IDT 2021 |  | COMPLETED
926 | TT_TASK | PREPARATION TRANSFORMER YARD DWGS BAT/BBT | Fri Feb 26 08:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Fri Feb 26 08:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 |  | COMPLETED
928 | TT_TASK | BD - SUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION 20UBE/UBF(2NDPACKAGES) | Mon May 24 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
929 | TT_TASK | BD - CONSENT LETTER DESIGN 20UBE/UBF | Tue Jun 15 08:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 |  | COMPLETED
930 | TT_TASK | BD - SUBMISSION & APPROVAL - GEN TRAFO PLATFORM 20UBF | Fri Dec 03 08:00:00 IST 2021 | Mon Jan 31 17:00:00 IST 2022 | Fri Dec 03 08:00:00 IST 2021 | Mon Jan 31 17:00:00 IST 2022 |  | COMPLETED
931 | TT_TASK | BD - CONSENT LETTER GEN TRAFO PLATFORM 20UBF | Tue Feb 01 08:00:00 IST 2022 | Mon Feb 28 17:00:00 IST 2022 | Tue Feb 01 08:00:00 IST 2022 |  | 376.0 | IN_PROGRESS
932 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS 20UBG01/02 | Mon Jan 17 08:00:00 IST 2022 | Sun Jan 30 17:00:00 IST 2022 | Mon Jan 17 08:00:00 IST 2022 | Sun Jan 30 17:00:00 IST 2022 |  | COMPLETED
933 | TT_TASK | DETAIL DESIGN BARBENDING 20UBE/UBF | Thu Sep 23 08:00:00 IDT 2021 | Thu Oct 28 17:00:00 IDT 2021 | Thu Sep 23 08:00:00 IDT 2021 | Thu Oct 28 17:00:00 IDT 2021 |  | COMPLETED
934 | TT_TASK | BASIC DESIGN STEEL STRUCTURE INCL. 3D MODEL 20UBE/UBF | Sun Jun 06 08:00:00 IDT 2021 | Mon Jun 21 17:00:00 IDT 2021 | Sun Jun 06 08:00:00 IDT 2021 | Mon Jun 21 17:00:00 IDT 2021 |  | COMPLETED
935 | TT_TASK | BD - AMENDMENT SUBMISSION - DETAIL DESIGN CONCRETE | Mon Dec 13 08:00:00 IST 2021 | Sun Jan 09 17:00:00 IST 2022 | Mon Dec 13 08:00:00 IST 2021 | Sun Jan 09 17:00:00 IST 2022 |  | COMPLETED
936 | TT_TASK | BD - RESUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE - TABLE + WALL | Fri Mar 18 08:00:00 IST 2022 | Mon May 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
937 | TT_TASK | BD - CONSENT LETTER | Tue May 17 08:00:00 IDT 2022 | Wed Jun 15 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
943 | TT_TASK | DETAIL DESIGN STEEL STRUCTURE UBF/UBE | Tue Jun 22 08:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Tue Jun 22 08:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
945 | TT_TASK | HANDRAILS AND GRATING DWGS & CONNECTION FORCE REPORT 20UBE/UBF | Tue Jul 20 08:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Tue Jul 20 08:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
947 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS 20UBX/20UBG03 | Thu Oct 21 08:00:00 IDT 2021 | Mon Dec 06 17:00:00 IST 2021 | Thu Oct 21 08:00:00 IDT 2021 | Mon Dec 06 17:00:00 IST 2021 |  | COMPLETED
950 | TT_TASK | BASIC DESIGN PLANT LAYOUT COOLING TOWER | Tue Feb 23 08:00:00 IST 2021 | Fri Apr 16 17:00:00 IDT 2021 | Tue Feb 23 08:00:00 IST 2021 | Fri Apr 16 17:00:00 IDT 2021 |  | COMPLETED
956 | TT_TASK | BASIC DESIGN PLANT LAYOUT FUEL GAS AREA | Sat Mar 06 08:00:00 IST 2021 | Fri Apr 16 17:00:00 IDT 2021 | Sat Mar 06 08:00:00 IST 2021 | Fri Apr 16 17:00:00 IDT 2021 |  | COMPLETED
958 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS 20UEN | Thu Sep 02 08:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Thu Sep 02 08:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  | COMPLETED
964 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS UHA | Fri Jul 16 08:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 | Fri Jul 16 08:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
966 | TT_TASK | DETAIL DESIGN CONCRETE STRUCTURE UHA | Mon May 31 08:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 | Mon May 31 08:00:00 IDT 2021 | Thu Jul 29 17:00:00 IDT 2021 |  | COMPLETED
968 | TT_TASK | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL UHA | Mon May 10 08:00:00 IDT 2021 | Sun May 30 17:00:00 IDT 2021 | Mon May 10 08:00:00 IDT 2021 | Sun May 30 17:00:00 IDT 2021 |  | COMPLETED
969 | TT_TASK | BD - SUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION 20UHA(2ND PACKAGE) | Mon May 24 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
970 | TT_TASK | CLIENT - REVIEW - HRSG DETAIL DESIGN CONCRETE 20UHA | Fri Jul 30 08:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 | Fri Jul 30 08:00:00 IDT 2021 | Mon Aug 23 17:00:00 IDT 2021 |  | COMPLETED
971 | TT_TASK | BD - CONSENT LETTER HRSG DETAIL DESIGN CONCRETE 20UHA | Tue Jun 15 08:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Tue Jun 15 08:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 |  | COMPLETED
972 | TT_TASK | DETAIL DESIGN BARBENDING UHA (BY MCW) | Wed Aug 04 08:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 | Wed Aug 04 08:00:00 IDT 2021 | Tue Aug 31 17:00:00 IDT 2021 |  | COMPLETED
973 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS 20ULA | Sat Jun 19 08:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Sat Jun 19 08:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
975 | TT_TASK | DETAIL DESIGN CONCRETE STRUCTURE 20ULA | Wed May 19 08:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 | Wed May 19 08:00:00 IDT 2021 | Fri Jul 02 17:00:00 IDT 2021 |  | COMPLETED
976 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20ULA | Sat Jul 03 08:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Sat Jul 03 08:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
978 | TT_TASK | BASIC DESIGN / BASIC BUILDING DESIGN INCL. 3D MODEL 20ULA | Wed May 05 08:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 | Wed May 05 08:00:00 IDT 2021 | Tue May 18 17:00:00 IDT 2021 |  | COMPLETED
979 | TT_TASK | BD - SUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE RESUBMISSION 20ULA(2NDPACKES) | Mon May 24 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
980 | TT_TASK | BD - CONSENT LETTER DETAIL DESIGN CONCRETE 20ULA | Tue Jun 15 08:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Tue Jun 15 00:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 |  | COMPLETED
981 | TT_TASK | DETAIL DESIGN BARBENDING STRUCTURE 20ULA | Tue Aug 17 08:00:00 IDT 2021 | Mon Sep 06 17:00:00 IDT 2021 | Tue Aug 17 08:00:00 IDT 2021 | Mon Sep 06 17:00:00 IDT 2021 |  | COMPLETED
984 | TT_TASK | BD - AMENDMENT SUBMISSION - DETAIL DESIGN CONCRETE RESUBMISSION 20ULA /20UHW / 20UMY (left side) | Mon Dec 13 08:00:00 IST 2021 | Sun Jan 09 17:00:00 IST 2022 | Mon Dec 13 08:00:00 IST 2021 | Sun Jan 09 17:00:00 IST 2022 |  | COMPLETED
988 | TT_TASK | BASIC BUILDING DESIGN CONCRETE TS FOUNDATION - PRELIMINARY - 20UMC | Fri Jan 15 08:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 |  | COMPLETED
989 | TT_TASK | DETAIL DESIGN CONCRETE TS FOUNDATION - PRELIMINARY - 20UMC | Fri Jan 29 08:00:00 IST 2021 | Thu Apr 15 17:00:00 IDT 2021 | Fri Jan 29 08:00:00 IST 2021 | Thu Apr 15 17:00:00 IDT 2021 |  | COMPLETED
990 | TT_TASK | BD - SUBMISSION & APPROVAL-DETAIL DESIGN- TURBOSET 1ST SUBMISSION (2NDPACKAGE) | Tue Apr 20 08:00:00 IDT 2021 | Wed May 12 17:00:00 IDT 2021 | Tue Apr 20 00:00:00 IDT 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
991 | TT_TASK | BD - RESUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE - 2ND AMMENDMENT (PILE CAP) | Thu Sep 09 08:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 | Thu Sep 09 00:00:00 IDT 2021 | Fri Oct 08 00:00:00 IDT 2021 |  | COMPLETED
992 | TT_TASK | BD - SUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE - RESUBMISSION CEP/LDK - PIT(1STPACKAGE) | Mon May 24 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
993 | TT_TASK | BD - SUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE - SUPERSTRUCTURE TUPC PLINGTHS | Fri Dec 17 08:00:00 IST 2021 | Thu Jan 13 17:00:00 IST 2022 | Fri Dec 17 08:00:00 IST 2021 | Thu Jan 13 17:00:00 IST 2022 |  | COMPLETED
994 | TT_TASK | BD - AMENDMENT - DETAIL DESIGN CONCRETE CEP/LDK PIT (SCREEN WALL) | Mon Dec 13 08:00:00 IST 2021 | Sun Jan 02 17:00:00 IST 2022 | Mon Dec 13 08:00:00 IST 2021 | Sun Jan 02 17:00:00 IST 2022 |  | COMPLETED
995 | TT_TASK | BD - SUBMISSION OF AMENDMENT(2nd) - SUPERSTRUCTURE TUPC PLINGTHS | Mon Feb 07 08:00:00 IST 2022 | Sat Mar 05 17:00:00 IST 2022 | Mon Feb 07 08:00:00 IST 2022 |  |  | IN_PROGRESS
996 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS TS FOUND. 20UMC | Thu Apr 08 08:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 | Thu Apr 08 08:00:00 IDT 2021 | Wed Apr 21 17:00:00 IDT 2021 |  | COMPLETED
998 | TT_TASK | DETAIL DESIGN CONCRETE STRUCTURE TS FOUND. 20UMC | Sat Feb 06 08:00:00 IST 2021 | Wed Apr 21 17:00:00 IDT 2021 | Sat Feb 06 08:00:00 IST 2021 | Wed Apr 21 17:00:00 IDT 2021 |  | COMPLETED
999 | TT_TASK | CLIENT - REVIEW - TURBOSET DETAIL DESIGN CONCRETE 20UMC | Thu Apr 22 08:00:00 IDT 2021 | Sun May 16 17:00:00 IDT 2021 | Thu Apr 22 08:00:00 IDT 2021 | Sun May 16 17:00:00 IDT 2021 |  | COMPLETED
1001 | TT_TASK | BD - SUBMISSION & APPROVAL - TURBOSET DETAIL DESIGN CONCRETE - 1ST AMMENDMENT (PILE CAP) | Mon Jun 28 08:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 |  | COMPLETED
1002 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN CONCRETE - CEP/LDK - PIT 20UMC | Fri Feb 19 08:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 | Fri Feb 19 08:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 |  | COMPLETED
1003 | TT_TASK | BD - SUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE - 1ST SUBMISSION CEP/LDK - PIT (1STPACKAGE) | Tue Mar 16 08:00:00 IST 2021 | Wed May 12 17:00:00 IDT 2021 | Tue Mar 16 08:00:00 IST 2021 | Thu May 13 00:00:00 IDT 2021 |  | COMPLETED
1004 | TT_TASK | BD - CONSENT LETTER DETAIL DESIGN CONCRETE CEP/LDK PIT (1ST PACKAGE) | Mon Jun 28 08:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 |  | COMPLETED
1005 | TT_TASK | BD - CONSENT LETTER DETAIL DESIGN CONCRETE TURBOSET 2NDPACKAGE | Thu Jun 10 08:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 |  | COMPLETED
1006 | TT_TASK | DETAIL DESIGN BARBENDING TS FOUND. 20UMC | Thu Jun 10 08:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Thu Jun 10 08:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
1007 | TT_TASK | DETAIL DESIGN BARBENDING UMC BUILDING 20UMC | Thu Jul 22 08:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Thu Jul 22 08:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 |  | COMPLETED
1008 | TT_TASK | DETAIL DESIGN BARBENDING CEP/LDK 20UMC | Thu Jun 17 08:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Thu Jun 17 08:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1010 | TT_TASK | BD - SUBMISSION & APPROVAL-DETAIL DESIGN CONCRETE TURBOSET RESUBMISSION 1ST AND 2ND PACKAGES | Mon May 24 08:00:00 IDT 2021 | Wed Jun 09 17:00:00 IDT 2021 | Mon May 24 00:00:00 IDT 2021 | Thu Jun 10 00:00:00 IDT 2021 |  | COMPLETED
1014 | TT_TASK | BD - CONSENT LETTER DETAIL DESIGN CONCRETE TURBOSET 20UMC PACKAGE 1&2 - RESUBMISSION | Wed Jun 30 08:00:00 IDT 2021 | Thu Jul 22 17:00:00 IDT 2021 | Wed Jun 30 00:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 |  | COMPLETED
1015 | TT_TASK | BD - SUBMISSION & APPROVAL - TURBOSET DETAIL DESIGN CONCRET - 2ND AMMENDMENT (PILE CAP) | Fri Jul 23 08:00:00 IDT 2021 | Sun Aug 01 17:00:00 IDT 2021 | Fri Jul 23 00:00:00 IDT 2021 | Mon Aug 02 00:00:00 IDT 2021 |  | COMPLETED
1018 | TT_TASK | BD - RESUBMISSION & APPROVAL - STANDING SEAM ROOF/WALL/PANELS - CLADDING 20UMC | Mon Jan 17 08:00:00 IST 2022 | Thu Mar 17 17:00:00 IST 2022 | Mon Jan 17 08:00:00 IST 2022 |  |  | IN_PROGRESS
1019 | TT_TASK | BD - WITHDRAWAL & REWORK STEEL PLATFORMS LOT1 20UMC | Fri Dec 24 08:00:00 IST 2021 | Thu Jan 13 17:00:00 IST 2022 | Fri Dec 24 08:00:00 IST 2021 | Thu Jan 13 17:00:00 IST 2022 |  | COMPLETED
1020 | TT_TASK | BD - RESUBMISSION & APPROVAL STEEL PLATFORMS LOT1 20UMC | Fri Jan 14 08:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 | Fri Jan 14 08:00:00 IST 2022 | Tue Feb 08 17:00:00 IST 2022 |  | COMPLETED
1021 | TT_TASK | BD - SUBMISSION OF AMENDMENT(2nd)- UMC MAIN FRAME incl. CRANE WALKWAY HVAC PLATFORM | Fri Dec 17 08:00:00 IST 2021 | Thu Jan 13 17:00:00 IST 2022 | Fri Dec 17 08:00:00 IST 2021 | Thu Jan 13 17:00:00 IST 2022 |  | COMPLETED
1022 | TT_TASK | BD - SUBMISSION OF AMENDMENT(3rd) STEEL PLATFORMS CEP/LDK 20UMC | Sun Mar 06 08:00:00 IST 2022 | Sat Apr 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1023 | TT_TASK | BD - SUBMISSION OF AMENDMENT(3rd)- SUPERSTRUCTURE UMC MAIN HALL,CEP/LDK,& CRANE WALKWAY,STAIR TOWER | Sun Mar 06 08:00:00 IST 2022 | Sat Apr 02 17:00:00 IDT 2022 |  |  | 272.0 | NOT_STARTED
1025 | TT_TASK | BD - CONSENT LETTER STEEL ST AND GENO. 20UMC | Fri Apr 01 08:00:00 IDT 2022 | Thu Apr 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1026 | TT_TASK | BD - RESUBMISSION & APPROVAL STEEL PLATFORMS ST AND GENO 20UMC | Fri Mar 04 08:00:00 IST 2022 | Thu Mar 31 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1027 | TT_TASK | BD - RESUBMISSION & APPROVAL - STEEL PLATFORMS LOT2 20UMC Misc. platform on generator,ST,other misc. | Fri Apr 01 08:00:00 IDT 2022 | Mon May 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1028 | TT_TASK | BASIC DESIGN / STEEL COLUMN ANCHORING DWG, STATIC ANALYSIS 20UMC | Sun Jan 24 08:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 | Sun Jan 24 08:00:00 IST 2021 | Tue Mar 02 17:00:00 IST 2021 |  | COMPLETED
1030 | TT_TASK | DETAIL DESIGN STEEL STRUCTURE / CRANE 20UMC | Wed Mar 03 08:00:00 IST 2021 | Sun May 16 17:00:00 IDT 2021 | Wed Mar 03 08:00:00 IST 2021 | Sun May 16 17:00:00 IDT 2021 |  | COMPLETED
1031 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN - STEEL STRUCTURE 20UMC | Mon May 17 08:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 | Mon May 17 08:00:00 IDT 2021 | Thu Jun 10 17:00:00 IDT 2021 |  | COMPLETED
1033 | TT_TASK | HANDRAILS AND GRATING DWGS & CONNECTION FORCE REPORT 20UMC | Mon Apr 26 08:00:00 IDT 2021 | Sun May 16 17:00:00 IDT 2021 | Mon Apr 26 08:00:00 IDT 2021 | Sun May 16 17:00:00 IDT 2021 |  | COMPLETED
1034 | TT_TASK | BD - SUBMISSION & APPROVAL - STEEL STRUCTURE 20UMC (Incl. Crane Walkawy) | Mon May 17 08:00:00 IDT 2021 | Sun Jul 11 17:00:00 IDT 2021 | Mon May 17 08:00:00 IDT 2021 | Mon Jul 12 00:00:00 IDT 2021 |  | COMPLETED
1036 | TT_TASK | BD - RESUBMISSION & APPROVAL - UMC PACKAGES(Steel,topslab,CEP/LDK screen wall,turbine plinth/wall) | Mon Jul 12 08:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 | Mon Jul 12 08:00:00 IDT 2021 | Fri Aug 27 00:00:00 IDT 2021 |  | COMPLETED
1037 | TT_TASK | BD -CONSENT LETTER UMC PACKAGES(Steel,topslab,CEP/LDK screen wall,turbine plinth/wall) 20UMC | Wed Aug 18 08:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 | Wed Aug 18 00:00:00 IDT 2021 | Thu Oct 21 00:00:00 IDT 2021 |  | COMPLETED
1038 | TT_TASK | DETAIL DESIGN CLADDING 20UMC | Tue Jun 15 08:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 | Tue Jun 15 08:00:00 IDT 2021 | Fri Aug 13 17:00:00 IDT 2021 |  | COMPLETED
1039 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN - CLADDING 20UMC | Sat Aug 14 08:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Sat Aug 14 08:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 |  | COMPLETED
1040 | TT_TASK | BD - SUBMISSION & APPROVAL - STANDING SEAM ROOF/WALL/PANELS - CLADDING 20UMC | Wed Nov 17 08:00:00 IST 2021 | Thu Nov 25 17:00:00 IST 2021 | Wed Nov 17 08:00:00 IST 2021 | Fri Nov 26 00:00:00 IST 2021 |  | COMPLETED
1042 | TT_TASK | BD - CONSENT LETTER - STANDING SEAM ROOF/WALL/PANELS - CLADDING 20UMC | Fri Mar 18 08:00:00 IST 2022 | Thu Apr 14 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1043 | TT_TASK | BD - SUBMISSION & APPROVAL - STEEL PLATFORMS LOT1 20UMC GENO & ST | Thu Jul 15 08:00:00 IDT 2021 | Sat Nov 06 17:00:00 IST 2021 | Thu Jul 15 08:00:00 IDT 2021 | Sat Nov 06 17:00:00 IST 2021 |  | COMPLETED
1044 | TT_TASK | BD - CONSENT LETTER STEEL CEP/LDK 20UMC | Sun Apr 03 08:00:00 IDT 2022 | Sat Apr 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1045 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN - STEEL STRUCTURE LOT1 20UMC | Thu Jun 17 08:00:00 IDT 2021 | Sun Jul 11 17:00:00 IDT 2021 | Thu Jun 17 08:00:00 IDT 2021 | Sun Jul 11 17:00:00 IDT 2021 |  | COMPLETED
1046 | TT_TASK | BD - SUBMISSION & APPROVAL - LOUVRES - CLADDING 20UMC | Wed Nov 17 08:00:00 IST 2021 | Thu Nov 25 17:00:00 IST 2021 | Wed Nov 17 08:00:00 IST 2021 | Fri Nov 26 00:00:00 IST 2021 |  | COMPLETED
1047 | TT_TASK | BD - CONSENT LETTER - LOUVRES - CLADDING 20UMC | Tue Nov 30 08:00:00 IST 2021 | Mon Jan 24 17:00:00 IST 2022 | Tue Nov 30 08:00:00 IST 2021 | Mon Jan 24 17:00:00 IST 2022 |  | COMPLETED
1049 | TT_TASK | DETAIL DESIGN STEEL STRUCTURE / CRANE (AFTER RECEIVING FINAL MS3) 20UMC | Tue Jun 08 08:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 | Tue Jun 08 08:00:00 IDT 2021 | Fri Aug 06 17:00:00 IDT 2021 |  | COMPLETED
1050 | TT_TASK | BD - RESUBMISSION & APPROVAL-1st Amendment UMC PACKAGES(topslab-trenches,CEP/LDK wall,Turbine plinght/wall) | Wed Nov 17 08:00:00 IST 2021 | Wed Jan 12 17:00:00 IST 2022 | Wed Nov 17 08:00:00 IST 2021 | Wed Jan 12 17:00:00 IST 2022 |  | COMPLETED
1051 | TT_TASK | BASIC DESIGN / STEEL AFTER FINAL MS3 INPUT 20UMC | Tue May 18 08:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Tue May 18 08:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 |  | COMPLETED
1052 | TT_TASK | BD - SUBMISSION & APPROVAL - STEEL PLATFORMS LOT2 20UMC | Wed Aug 18 08:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 | Wed Aug 18 08:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  | COMPLETED
1053 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN - STEEL STRUCTURE LOT2 20UMC | Fri Jul 16 08:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 | Fri Jul 16 08:00:00 IDT 2021 | Mon Aug 09 17:00:00 IDT 2021 |  | COMPLETED
1054 | TT_TASK | BD - CONSENT LETTER STEEL PLATFORMS LOT2 20UMC platform on Misc. platform on generator,ST,other misc. | Tue May 31 08:00:00 IDT 2022 | Mon Jun 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1055 | TT_TASK | BD - SUBMISSION & APPROVAL - STEEL PLATFORMS LOT1 20UMC CEP/LDK/CRANE WALKWAY STAIRCASE | Fri Jul 02 08:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 | Fri Jul 02 08:00:00 IDT 2021 | Fri Nov 05 17:00:00 IST 2021 |  | COMPLETED
1057 | TT_TASK | DETAIL DESIGN STEEL PLATFORMS LOT1 20UMC | Mon May 03 08:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 |  | COMPLETED
1058 | TT_TASK | HANDRAILS AND GRATING DWGS & CONNECTION FORCE REPORT LOT1 20UMC | Thu May 27 08:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 | Thu May 27 08:00:00 IDT 2021 | Wed Jun 16 17:00:00 IDT 2021 |  | COMPLETED
1060 | TT_TASK | BASIC DESIGN STEEL PLATFORMS LOT1 20UMC | Tue Mar 30 08:00:00 IDT 2021 | Sun May 02 17:00:00 IDT 2021 | Tue Mar 30 08:00:00 IDT 2021 | Sun May 02 17:00:00 IDT 2021 |  | COMPLETED
1062 | TT_TASK | BASIC DESIGN STEEL PLATFORMS LOT2 20UMC | Wed Apr 28 08:00:00 IDT 2021 | Mon May 31 17:00:00 IDT 2021 | Wed Apr 28 08:00:00 IDT 2021 | Mon May 31 17:00:00 IDT 2021 |  | COMPLETED
1063 | TT_TASK | DETAIL DESIGN STEEL PLATFORMS LOT2 20UMC | Tue Jun 01 08:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Tue Jun 01 08:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
1064 | TT_TASK | HANDRAILS AND GRATING DWGS & CONNECTION FORCE REPORT LOT2 20UMC | Fri Jun 25 08:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Fri Jun 25 08:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
1069 | TT_TASK | DETAIL DESIGN CONCRETE STRUCTURE CEP/LDK PIT 20UMC | Fri Jan 29 08:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 | Fri Jan 29 08:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 |  | COMPLETED
1071 | TT_TASK | BASIC DESIGN CEP/LDK PIT 20UMC | Fri Jan 01 08:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Fri Jan 01 08:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 |  | COMPLETED
1072 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS CEP/LDK PIT 20UMC | Tue Mar 02 08:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 | Tue Mar 02 08:00:00 IST 2021 | Mon Mar 15 17:00:00 IST 2021 |  | COMPLETED
1075 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS UMX-To be deleted | Fri Aug 27 08:00:00 IDT 2021 | Thu Sep 09 17:00:00 IDT 2021 | Fri Aug 27 08:00:00 IDT 2021 | Thu Sep 09 17:00:00 IDT 2021 |  | COMPLETED
1076 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20UMX-To be deleted | Fri Sep 10 08:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 | Fri Sep 10 08:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 |  | COMPLETED
1078 | TT_TASK | BD - SUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE 20UMX-deleted | Fri Sep 10 08:00:00 IDT 2021 | Mon Nov 08 17:00:00 IST 2021 | Fri Sep 10 08:00:00 IDT 2021 | Mon Nov 08 17:00:00 IST 2021 |  | COMPLETED
1079 | TT_TASK | DETAIL DESIGN CONCRETE STRUCTURE UMX-To be deleted | Tue Jul 27 08:00:00 IDT 2021 | Thu Sep 09 17:00:00 IDT 2021 | Tue Jul 27 08:00:00 IDT 2021 | Thu Sep 09 17:00:00 IDT 2021 |  | COMPLETED
1081 | TT_TASK | BASIC BUILDING DESIGN INCL. 3D MODEL UMX-Deleted | Wed Jun 30 08:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 | Wed Jun 30 08:00:00 IDT 2021 | Mon Jul 26 17:00:00 IDT 2021 |  | COMPLETED
1082 | TT_TASK | BD - CONSENT LETTER - DETAIL DESIGN CONCRETE 20UMX-deleted | Tue Nov 09 08:00:00 IST 2021 | Mon Nov 15 17:00:00 IST 2021 | Tue Nov 09 08:00:00 IST 2021 | Mon Nov 15 17:00:00 IST 2021 |  | COMPLETED
1083 | TT_TASK | DETAIL DESIGN BARBENDING STRUCTURE UMX-deleted | Tue Nov 09 08:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 | Tue Nov 09 08:00:00 IST 2021 | Mon Nov 29 17:00:00 IST 2021 |  | COMPLETED
1085 | TT_TASK | DETAIL DESIGN CONCRETE STRUCTURE 20ULY/UMY | Sun May 30 08:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sun May 30 08:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
1088 | TT_TASK | BASIC BUILDING DESIGN INCL. 3D MODEL 20ULY/UMY | Sun May 09 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Sun May 09 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 |  | COMPLETED
1089 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS 20ULY/UMY | Wed Jun 30 08:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 30 08:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
1090 | TT_TASK | DETAIL DESIGN BARBENDING STRUCTURE 20ULY/UMY | Tue Nov 16 08:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 | Tue Nov 16 08:00:00 IST 2021 | Mon Dec 06 17:00:00 IST 2021 |  | COMPLETED
1094 | TT_TASK | BASIC DESIGN PLANT LAYOUT COOLING TOWER | Sun Dec 20 08:00:00 IST 2020 | Fri Apr 16 17:00:00 IDT 2021 | Sun Dec 20 08:00:00 IST 2020 | Fri Apr 16 17:00:00 IDT 2021 |  | COMPLETED
1096 | TT_TASK | COORDINATION ATKINS - CPT / INCL. EMBEDDED PARTS - SUBSTRUCTURE 20URA/URD | Fri Aug 06 08:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 | Fri Aug 06 08:00:00 IDT 2021 | Thu Sep 02 17:00:00 IDT 2021 |  | COMPLETED
1100 | TT_TASK | BD - RESUBMISSION APPROVAL SUBSTRUCTURE 2ND AMENDMENT 20URA/URD | Wed Sep 22 08:00:00 IDT 2021 | Sat Nov 13 17:00:00 IST 2021 | Wed Sep 22 08:00:00 IDT 2021 | Sun Nov 14 00:00:00 IST 2021 |  | COMPLETED
1102 | TT_TASK | BD - CONSENT LETTER RESUBMISSION2 SUBSTRUCTURE 20URA/URD | Wed Oct 27 08:00:00 IDT 2021 | Mon Nov 08 17:00:00 IST 2021 | Wed Oct 27 00:00:00 IDT 2021 | Tue Nov 09 00:00:00 IST 2021 |  | COMPLETED
1104 | TT_TASK | BD - CONSENT LETTER RESUBMISSION3 SUBSTRUCTURE 20URA/URD | Mon Nov 15 08:00:00 IST 2021 | Thu Nov 18 17:00:00 IST 2021 | Mon Nov 15 00:00:00 IST 2021 | Fri Nov 19 00:00:00 IST 2021 |  | COMPLETED
1105 | TT_TASK | BD - AMENDMENT SUBMISSION - CAPS 20URA/URD | Mon Dec 13 08:00:00 IST 2021 | Sun Jan 09 17:00:00 IST 2022 | Mon Dec 13 08:00:00 IST 2021 | Sun Jan 09 17:00:00 IST 2022 |  | COMPLETED
1108 | TT_TASK | ATKINS DD DETAIL DESIGN SUPERSTRUCTURE -20URA/URD | Sun May 30 08:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Sun May 30 08:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 |  | COMPLETED
1110 | TT_TASK | BASIC DESIGN COOLING TOWER FOUNDATION 20URA To be used/cancel xx | Tue Feb 02 08:00:00 IST 2021 | Mon Mar 29 17:00:00 IDT 2021 | Tue Feb 02 08:00:00 IST 2021 | Mon Mar 29 17:00:00 IDT 2021 |  | COMPLETED
1111 | TT_TASK | PREPARATION FOUNDATION GROUNDING DWGS 20URA/URD | Fri Jun 11 08:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 | Fri Jun 11 08:00:00 IDT 2021 | Thu Jun 24 17:00:00 IDT 2021 |  | COMPLETED
1113 | TT_TASK | CLIENT REVIEW DETAIL DESIGN SUBSTRUCTURE AND CATHODIC PROTECTION-20URA/URD | Mon Jul 26 08:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 | Mon Jul 26 08:00:00 IDT 2021 | Thu Aug 05 17:00:00 IDT 2021 |  | COMPLETED
1114 | TT_TASK | BD - SUBMISSION APPROVAL SUBSTRUCTURE AMENDMENT SUBMISSION 20URA/URD- | Thu Jul 22 08:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Thu Jul 22 00:00:00 IDT 2021 | Thu Aug 12 00:00:00 IDT 2021 |  | COMPLETED
1115 | TT_TASK | BD - CONSENT LETTER SUBSTRUCTURE -20URA/URD(1STPACKAGE) | Mon Jun 28 08:00:00 IDT 2021 | Tue Jul 20 17:00:00 IDT 2021 | Mon Jun 28 00:00:00 IDT 2021 | Wed Jul 21 00:00:00 IDT 2021 |  | COMPLETED
1116 | TT_TASK | BD - CONSENT LETTER SUPERSTRUCTURE 20URA/URD | Mon Nov 22 08:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 | Mon Nov 22 08:00:00 IST 2021 | Fri Dec 03 17:00:00 IST 2021 |  | COMPLETED
1117 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN CONCRETE SUPERSTRUCTURE 20URA-To be used/cancel xx | Fri Jun 25 08:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 | Fri Jun 25 08:00:00 IDT 2021 | Mon Jul 19 17:00:00 IDT 2021 |  | COMPLETED
1119 | TT_TASK | BARBENDING AND DRAWINGS SUBSTRUCTURE-20URA/URD | Fri Sep 03 08:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Fri Sep 03 08:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  | COMPLETED
1120 | TT_TASK | ATKINS REDESIGN DD SUPERSTRUCTURE-20URA/URD | Wed Aug 25 08:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 | Wed Aug 25 08:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 |  | COMPLETED
1121 | TT_TASK | BD - SUBMISSION APPROVAL SUPERSTRUCTURE- RESUBMISSION 20URA/URD | Wed Sep 15 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 | Wed Sep 15 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 |  | COMPLETED
1122 | TT_TASK | BARBENDING AND DRAWINGS SUPERSTRUCTURE-20URA/URD | Thu Oct 14 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 | Thu Oct 14 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 |  | COMPLETED
1123 | TT_TASK | ATKINS REDESIGN DD SUBSTRUCTURE-20URA/URD | Tue Jun 15 08:00:00 IDT 2021 | Wed Jul 21 17:00:00 IDT 2021 | Tue Jun 15 08:00:00 IDT 2021 | Thu Jul 22 00:00:00 IDT 2021 |  | COMPLETED
1124 | TT_TASK | FOUNDATION GROUNDING DWGS RELEASED FOR EXEC. 20URD xx | Wed Jun 30 08:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Wed Jun 30 08:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
1126 | TT_TASK | DETAIL DESIGN CONCRETE STRUCTURE 20URD xx | Sun May 30 08:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Sun May 30 08:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
1127 | TT_TASK | CLIENT - REVIEW - DETAIL DESIGN CONCRETE 20URD xx | Wed Jul 14 08:00:00 IDT 2021 | Sat Aug 07 17:00:00 IDT 2021 | Wed Jul 14 08:00:00 IDT 2021 | Sat Aug 07 17:00:00 IDT 2021 |  | COMPLETED
1130 | TT_TASK | BASIC BUILDING DESIGN INCL. 3D MODEL 20URD xx | Sun May 02 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 | Sun May 02 08:00:00 IDT 2021 | Sat May 29 17:00:00 IDT 2021 |  | COMPLETED
1131 | TT_TASK | BD - SUBMISSION & APPROVAL - DETAIL DESIGN CONCRETE 20URD xxxx | Wed Jul 14 08:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 | Wed Jul 14 08:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  | COMPLETED
1132 | TT_TASK | BD - CONSENT LETTER DETAIL DESIGN CONCRETE 20URD xx | Sat May 15 08:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 | Sat May 15 08:00:00 IDT 2021 | Fri Jun 25 17:00:00 IDT 2021 |  | COMPLETED
1133 | TT_TASK | DETAIL DESIGN BARBENDING 20URD xx | Wed Aug 25 08:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 | Wed Aug 25 08:00:00 IDT 2021 | Tue Sep 21 17:00:00 IDT 2021 |  | COMPLETED
1135 | TT_TASK | PREPARATION RFQ CHEMICAL CLEANING | Sat May 21 08:00:00 IDT 2022 | Fri Jun 17 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1136 | TT_TASK | QUOTATION STAGE CHEMICAL CLEANING | Sat Jun 18 08:00:00 IDT 2022 | Fri Aug 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1140 | TT_TASK | PREPARATION RFQ CHEMICAL CLEANING SYSTEM ZTA | Tue Nov 30 08:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 | Tue Nov 30 08:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 |  | COMPLETED
1141 | TT_TASK | QUOTATION STAGE CHEMICAL CLEANING SYSTEM ZTA | Sat Jun 18 08:00:00 IDT 2022 | Fri Aug 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1143 | TT_TASK | DESIGN, PROCUREMENT CHEMICAL CLEANING | Sat Aug 13 08:00:00 IDT 2022 | Fri Nov 11 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1145 | TT_TASK | DESIGN, PROC. TEMP. PIPING / VALVES FOR CHEMICAL CLEANING SYSTEM ZTA | Sat Aug 13 08:00:00 IDT 2022 | Mon Dec 12 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1148 | TT_TASK | TRANSPORT, MOBILIZATION CHEMICAL CLEANING EQUIPMENT | Sun Jan 01 08:00:00 IST 2023 | Sat Feb 25 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1149 | TT_TASK | TRANSPORT EQUIPMENT/ MOBILIZATION CHEMICAL CLEANING SYSTEM ZTA | Sun Jan 15 08:00:00 IST 2023 | Sat Mar 11 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1151 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - TEMP. PIPING / VALVES FOR CHEMICAL CLEANING SYSTEM ZTA | Tue Dec 13 08:00:00 IST 2022 | Mon Jan 09 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1152 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - CHEMICAL CLEANING | Sun Dec 04 08:00:00 IST 2022 | Sat Dec 31 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1154 | TT_TASK | INTEGRATION OF ACID CLEANING SYSTEM ZTB | Thu Apr 15 08:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 | Thu Apr 15 08:00:00 IDT 2021 | Wed May 26 17:00:00 IDT 2021 |  | COMPLETED
1156 | TT_TASK | DESIGN, PROC. PIPING / VALVES FOR STEAM BLOWING SYSTEM ZTB | Thu May 27 08:00:00 IDT 2021 | Wed Feb 09 17:00:00 IST 2022 | Thu May 27 08:00:00 IDT 2021 | Wed Feb 09 17:00:00 IST 2022 |  | COMPLETED
1158 | TT_TASK | TRANSPORT PIPING FOR STEAM BLOWING SYSTEM ZTB | Sun Jan 01 08:00:00 IST 2023 | Sat Feb 25 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1160 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - PIPING / VALVES FOR STEAM BLOWING SYSTEM ZTB | Sun Dec 04 08:00:00 IST 2022 | Sat Dec 31 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1242 | TT_TASK | 20 - HOARDING PLAN AMENDMENT & RENEWAL OF HOARDING PLAN | Thu Apr 01 08:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 | Thu Apr 01 08:00:00 IDT 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
1244 | TT_TASK | 20(a) - HOARDING PLAN AMENDMENT & RENEWAL OF HOARDING PLAN | Thu Jun 10 08:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 | Thu Jun 10 08:00:00 IDT 2021 | Fri Jul 09 17:00:00 IDT 2021 |  | COMPLETED
1298 | TT_TASK | 103 - DESTINATION CONTROL STATEMENT: FIREWALL IMPORT LICENSE | Mon Dec 20 08:00:00 IST 2021 | Wed Jan 19 17:00:00 IST 2022 | Mon Dec 20 08:00:00 IST 2021 | Wed Jan 19 17:00:00 IST 2022 |  | COMPLETED
1299 | TT_TASK | 104 - LICENSE ISSUE | Thu Jan 20 08:00:00 IST 2022 | Thu May 19 17:00:00 IDT 2022 | Thu Jan 20 08:00:00 IST 2022 |  | 728.0 | IN_PROGRESS
1300 | TT_TASK | 105 - IMPORT LICENSE FOR RADIOACTIVE SUBSTANCE | Thu Jan 20 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 | Thu Jan 20 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 |  | COMPLETED
1301 | TT_TASK | 106 - RADIOACTIVE SUBSTANCE LICENSE (BPPS) | Thu Jan 20 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 | Thu Jan 20 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 |  | COMPLETED
1302 | TT_TASK | 107 - WSD FORM 542 SUBMISSION (TOWN WATER DOMESTIC WATER SUPPLY) | Wed Jun 16 08:00:00 IDT 2021 | Sun Dec 12 17:00:00 IST 2021 | Wed Jun 16 08:00:00 IDT 2021 | Sun Dec 12 17:00:00 IST 2021 |  | COMPLETED
1303 | TT_TASK | 108 - APPROVAL OF WSD FORM 542 SUBMISSION (TOWN WATER DOMESTIC WATER SUPPLY) | Mon Dec 13 08:00:00 IST 2021 | Mon Dec 13 17:00:00 IST 2021 | Mon Dec 13 08:00:00 IST 2021 | Mon Dec 13 17:00:00 IST 2021 |  | COMPLETED
1304 | TT_TASK | 109 - WSD FORM 46 PART1/2 (TOWN WATER DOMESTIC WATER SUPPLY) | Mon Aug 22 08:00:00 IDT 2022 | Sat Nov 19 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1305 | TT_TASK | 110 - WSD FORM 46 PART 3 (TOWN WATER DOMESTIC WATER SUPPLY) | Sun Nov 20 08:00:00 IST 2022 | Sun Nov 20 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1306 | TT_TASK | 111 - WSD FINAL AMENDMENT PLAN SUBMISSION (TOWN WATER DOMESTIC WATER SUPPLY) | Tue Dec 14 08:00:00 IST 2021 | Fri Feb 11 17:00:00 IST 2022 | Tue Dec 14 08:00:00 IST 2021 | Fri Feb 11 17:00:00 IST 2022 |  | COMPLETED
1307 | TT_TASK | 112 - APPROVAL OF WSD FINAL AMENDMENT PLAN SUBMISSION (TOWN WATER DOMESTIC WATER SUPPLY) | Sat Feb 12 08:00:00 IST 2022 | Sat Feb 12 17:00:00 IST 2022 | Sat Feb 12 08:00:00 IST 2022 | Sat Feb 12 17:00:00 IST 2022 |  | COMPLETED
1308 | TT_TASK | 113 - WSD FORM 46 PART 4 (TOWN WATER DOMESTIC WATER SUPPLY) | Wed Jan 25 08:00:00 IST 2023 | Mon Apr 24 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1309 | TT_TASK | 114 - WSD FORM 46 PART 5 (TOWN WATER DOMESTIC WATER SUPPLY) | Tue Apr 25 08:00:00 IDT 2023 | Fri Jun 23 17:00:00 IDT 2023 |  |  | 136.0 | NOT_STARTED
1310 | TT_TASK | 115 - WSD FORM 542 SUBMISSION (TOWN WATER SERVICES SYSTEM) | Wed Jun 16 08:00:00 IDT 2021 | Sun Dec 12 17:00:00 IST 2021 | Wed Jun 16 08:00:00 IDT 2021 | Sun Dec 12 17:00:00 IST 2021 |  | COMPLETED
1311 | TT_TASK | 116 - APPROVAL OF WSD FORM 542 SUBMISSION (TOWN WATER SERVICES SYSTEM) | Mon Dec 13 08:00:00 IST 2021 | Mon Dec 13 17:00:00 IST 2021 | Mon Dec 13 08:00:00 IST 2021 | Mon Dec 13 17:00:00 IST 2021 |  | COMPLETED
1312 | TT_TASK | 117 - WSD FORM 46 PART 1/2 (TOWN WATER SERVICES SYSTEM) | Tue Apr 26 08:00:00 IDT 2022 | Sun Jul 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1313 | TT_TASK | 118 - WSD FORM 46 PART 3 (TOWN WATER SERVICES SYSTEM) | Mon Jul 25 08:00:00 IDT 2022 | Mon Jul 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1314 | TT_TASK | 119 - WSD FINAL AMENDMENT PLAN SUBMISSION (TOWN WATER SERVICES SYSTEM) | Thu Jul 07 08:00:00 IDT 2022 | Sun Sep 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1315 | TT_TASK | 120 - APPROVAL OF WSD FINAL AMENDMENT PLAN SUBMISSION (TOWN WATER SERVICES SYSTEM) | Mon Sep 05 08:00:00 IDT 2022 | Mon Sep 05 17:00:00 IDT 2022 |  |  | 3856.0 | NOT_STARTED
1316 | TT_TASK | 121 - WSD FORM 46 PART 4 (TOWN WATER SERVICES SYSTEM) | Wed Jan 25 08:00:00 IST 2023 | Mon Apr 24 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1317 | TT_TASK | 122 - WSD FORM 46 PART 5 (TOWN WATER SERVICES SYSTEM) | Tue Apr 25 08:00:00 IDT 2023 | Fri Jun 23 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1318 | TT_TASK | 123 - WSD FORM 542 SUBMISSION (FRESH FIRE WATER SUPPLY) | Wed Aug 18 08:00:00 IDT 2021 | Sun Feb 13 17:00:00 IST 2022 | Wed Aug 18 08:00:00 IDT 2021 | Sun Feb 13 17:00:00 IST 2022 |  | COMPLETED
1319 | TT_TASK | 124 - APPROVAL OF WSD FORM 542 SUBMISSION (FRESH FIRE WATER SUPPLY) | Mon Feb 14 08:00:00 IST 2022 | Mon Feb 14 17:00:00 IST 2022 | Mon Feb 14 08:00:00 IST 2022 | Mon Feb 14 17:00:00 IST 2022 |  | COMPLETED
1320 | TT_TASK | 125 - WSD FORM 46 PART 1/2 (FRESH FIRE WATER SUPPLY) | Tue Feb 15 08:00:00 IST 2022 | Fri Apr 15 17:00:00 IDT 2022 | Tue Feb 15 08:00:00 IST 2022 |  |  | IN_PROGRESS
1321 | TT_TASK | 126 - WSD FORM 46 PART 3 (FRESH FIRE WATER SUPPLY) | Sat Apr 16 08:00:00 IDT 2022 | Sat Apr 16 17:00:00 IDT 2022 |  |  | 136.0 | NOT_STARTED
1322 | TT_TASK | 127 - WSD FINAL AMENDMENT PLAN SUBMISSION (FRESH FIRE WATER SUPPLY) | Thu Jul 07 08:00:00 IDT 2022 | Sun Sep 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1323 | TT_TASK | 128 - APPROVAL OF WSD FINAL AMENDMENT PLAN SUBMISSION (FRESH FIRE WATER SUPPLY) | Mon Sep 05 08:00:00 IDT 2022 | Mon Sep 05 17:00:00 IDT 2022 |  |  | 1000.0 | NOT_STARTED
1324 | TT_TASK | 129 - WSD FORM 46 PART 4 (FRESH FIRE WATER SUPPLY) | Mon Jan 09 08:00:00 IST 2023 | Sat Apr 08 17:00:00 IDT 2023 |  |  | 128.0 | NOT_STARTED
1325 | TT_TASK | 130 - WSD FORM 46 PART 5 (FRESH FIRE WATER SUPPLY) | Tue Apr 25 08:00:00 IDT 2023 | Fri Jun 23 17:00:00 IDT 2023 |  |  | 72.0 | NOT_STARTED
1326 | TT_TASK | 131 - FORM BA14 - CERTIFICATE ON COMPLETION OF BUILDING WORKS (PILE FOUNDATION) | Mon May 31 08:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Mon May 31 08:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 |  | COMPLETED
1328 | TT_TASK | 133 - CERTIFICATE OF COMPLETION OF DRAIN TESTS | Wed Dec 07 08:00:00 IST 2022 | Thu Jan 05 17:00:00 IST 2023 |  |  | 1168.0 | NOT_STARTED
1330 | TT_TASK | 136 - FORM FSI/314 SUBMISSION OF AS-BUILT DWGS | Thu Jan 12 08:00:00 IST 2023 | Fri Feb 10 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1331 | TT_TASK | 137 - FORM FS/314 SUBMISSION TO REQUEST FSD INSPECTION | Thu Jan 12 08:00:00 IST 2023 | Wed Jan 25 17:00:00 IST 2023 |  |  | 608.0 | NOT_STARTED
1332 | TT_TASK | 138 - FIRE SERVICES WATER COMPLIANCE ADVICE | Thu Jan 05 08:00:00 IST 2023 | Sun Mar 05 17:00:00 IST 2023 |  |  | 56.0 | NOT_STARTED
1333 | TT_TASK | 139 - ISSUE FIRE SERVICE CERTIFICATE FOR OP (F.S.172) | Thu Jan 12 08:00:00 IST 2023 | Tue Apr 11 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1334 | TT_TASK | 140 - AP UNDERTAKING LETTERS | Wed Apr 12 08:00:00 IDT 2023 | Tue Apr 25 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1335 | TT_TASK | 141 - FORM BA13 - APPLICATION OF OP | Wed Apr 12 08:00:00 IDT 2023 | Mon Jul 10 17:00:00 IDT 2023 |  |  | 112.0 | NOT_STARTED
1336 | TT_TASK | 142 - MASTER LAYOUT PLAN REVISION | Tue Jun 01 08:00:00 IDT 2021 | Sun Aug 29 17:00:00 IDT 2021 | Tue Jun 01 08:00:00 IDT 2021 | Sun Aug 29 17:00:00 IDT 2021 |  | COMPLETED
1337 | TT_TASK | 142a - LANDSCAPE MASTER PLAN REVISION | Thu Jan 12 08:00:00 IST 2023 | Tue Apr 11 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1338 | TT_TASK | 144 - BPPS APCL - AMENDMENT TO EXISTING LICENSE | Fri Jul 08 08:00:00 IDT 2022 | Tue Jan 03 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1339 | TT_TASK | 145 - AIR MODEL TEST | Wed Jul 14 08:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Wed Jul 14 08:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
1340 | TT_TASK | 146 - LICENSE OBTAINED | Thu Jul 15 08:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Thu Jul 15 08:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
1341 | TT_TASK | 147 - BPPS WPCL - AMENDMENT TO EXISTING LICENSE | Wed Jan 04 08:00:00 IST 2023 | Wed Jan 04 17:00:00 IST 2023 |  |  | 2888.0 | NOT_STARTED
1342 | TT_TASK | 148 - EFFLUENT DISCHARGE PLAN | Sat Jan 28 08:00:00 IST 2023 | Thu Apr 27 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1343 | TT_TASK | CHEMICAL WASTE WATER DISCHARGE LICENSE | Fri Jan 13 08:00:00 IST 2023 | Mon Mar 13 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1344 | TT_TASK | 64 - TEMPORARY EXCAVATION AND LATERAL SUPPORT (ELS) WORKS | Sat Apr 17 08:00:00 IDT 2021 | Sun May 16 17:00:00 IDT 2021 | Sat Apr 17 08:00:00 IDT 2021 | Sun May 16 17:00:00 IDT 2021 |  | COMPLETED
1345 | TT_TASK | 64a - TEMPORARY EXCAVATION AND LATERAL SUPPORT (ELS) WORKS | Thu Jun 17 08:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 | Thu Jun 17 08:00:00 IDT 2021 | Fri Jul 16 17:00:00 IDT 2021 |  | COMPLETED
1346 | TT_TASK | 143 - MASTER LAYOUT PLAN REVISION | Tue Jun 01 08:00:00 IDT 2021 | Sun Aug 29 17:00:00 IDT 2021 | Tue Jun 01 08:00:00 IDT 2021 | Sun Aug 29 17:00:00 IDT 2021 |  | COMPLETED
1347 | TT_TASK | 143b - LANDSCAPE MASTER PLAN REVISION | Thu Jan 12 08:00:00 IST 2023 | Tue Apr 11 17:00:00 IDT 2023 |  |  | 2112.0 | NOT_STARTED
1348 | TT_TASK | 149 - FURTHER ENVIRONMENTAL PERMIT | Sat May 15 08:00:00 IDT 2021 | Sun May 30 17:00:00 IDT 2021 | Sat May 15 08:00:00 IDT 2021 | Sun May 30 17:00:00 IDT 2021 |  | COMPLETED
1349 | TT_TASK | 83a - ISSUE OF LICENCES | Mon Jul 10 08:00:00 IDT 2023 | Thu Sep 07 17:00:00 IDT 2023 |  |  | 920.0 | NOT_STARTED
1350 | TT_TASK | 81a- ISSUE OF FIRE SAFETY REQUIREMENTS FOR STORAGE/USE OF DG UNDER DANGEROUS GOODS ORDINANCE | Wed Nov 09 08:00:00 IST 2022 | Mon Feb 06 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1351 | TT_TASK | UPDATE OF PROCESS & OPERATIONAL SAFETY MEASURES | Sun Jan 01 08:00:00 IST 2023 | Sat Jan 21 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1352 | TT_TASK | PREPARE PILOT SCHEME FOR CT | Sat Apr 17 08:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 | Sat Apr 17 08:00:00 IDT 2021 | Sat May 15 17:00:00 IDT 2021 |  | COMPLETED
1353 | TT_TASK | CALCULATION OF OVERALL FIRE WATER DEMAND / UPDATE OF INSPECTION PROCEDURES/PREPARATION SCHEMATIC DWGS | Mon Jul 11 08:00:00 IDT 2022 | Sun Aug 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1354 | TT_TASK | PREPARATION OF AS-BUILT DRAWINGS / MATERIAL TEST RECORDS FOR DG APPLICATION | Wed Nov 09 08:00:00 IST 2022 | Sun Jan 15 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1355 | TT_TASK | PREPARATION FOR LICENSE FOR STORAGE OF DG (CONSTRUCTION WORKS) | Wed May 19 08:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed May 19 08:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
1356 | TT_TASK | PREPARATION DOCUMENTATION PRESSURE VESSELS (CONSTRUCTION WORKS) | Mon May 31 08:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Mon May 31 08:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1357 | TT_TASK | PREPARATION CERTIFICATIONS FOR LIFTING APPLIANCES | Thu Jun 02 08:00:00 IDT 2022 | Wed Jun 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1358 | TT_TASK | PREPARATION CERTIFICATIONS FOR PRESSURE VESSELS | Thu Dec 22 08:00:00 IST 2022 | Mon Feb 20 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1359 | TT_TASK | PREPARATION OF FOREIGN WORKER VISA / JUSTIFICATION FOR FOREIGN EMPLOYMENT | Fri Feb 12 08:00:00 IST 2021 | Mon May 31 17:00:00 IDT 2021 | Fri Feb 12 08:00:00 IST 2021 | Mon May 31 17:00:00 IDT 2021 |  | COMPLETED
1360 | TT_TASK | Preparation of NOTIFICATION OF CONSTRUCTION WORKS AND WORKER REGISTRATION | Fri May 14 08:00:00 IDT 2021 | Mon May 31 17:00:00 IDT 2021 | Fri May 14 08:00:00 IDT 2021 | Mon May 31 17:00:00 IDT 2021 |  | COMPLETED
1361 | TT_TASK | PREPARATION OF DOCUMENTS FOR SUBMISSIONS 90/92/94/95 | Tue May 04 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue May 04 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
1362 | TT_TASK | PREPARATION OF SUBMISSIONS TO CIC/PCFB | Fri May 14 08:00:00 IDT 2021 | Mon May 31 17:00:00 IDT 2021 | Fri May 14 08:00:00 IDT 2021 | Mon May 31 17:00:00 IDT 2021 |  | COMPLETED
1363 | TT_TASK | PREPARATION OF SUBMISSIONS FOR FORM 3 - COMPLETION OF CONSTRUCTION WORKS | Sun Dec 17 08:00:00 IST 2023 | Sat Dec 30 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1364 | TT_TASK | PREPARATION OF SUBMISSION FOR FIREWALL IMPORT LICENSE | Fri Nov 19 08:00:00 IST 2021 | Sun Dec 19 17:00:00 IST 2021 | Fri Nov 19 08:00:00 IST 2021 | Sun Dec 19 17:00:00 IST 2021 |  | COMPLETED
1365 | TT_TASK | PREPARATION OF SUBMISSION FOR 104/105/106 | Mon Dec 20 08:00:00 IST 2021 | Wed Jan 19 17:00:00 IST 2022 | Mon Dec 20 08:00:00 IST 2021 | Wed Jan 19 17:00:00 IST 2022 |  | COMPLETED
1366 | TT_TASK | PREPARATION OF FORM 542 SUBMISSION (TOWN WATER DOMESTIC WATER SUPPLY) | Wed Jun 02 08:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Jun 02 08:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
1367 | TT_TASK | PREPARATION OF FORM 542 SUBMISSION (TOWN WATER SERVICES SYSTEM) | Wed Jun 02 08:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 | Wed Jun 02 08:00:00 IDT 2021 | Tue Jun 15 17:00:00 IDT 2021 |  | COMPLETED
1368 | TT_TASK | PREPARATION OF FORM 542 SUBMISSION (FRESH FIRE WATER SUPPLY) | Fri Jul 16 08:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 | Fri Jul 16 08:00:00 IDT 2021 | Tue Aug 17 17:00:00 IDT 2021 |  | COMPLETED
1369 | TT_TASK | DRAIN TESTS AND REPORTS | Sat Oct 15 08:00:00 IDT 2022 | Tue Dec 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1370 | TT_TASK | PREPARATION OF AS-BUILT DOCUMENTATION FOR FSI/314 & FSI 501 SUBMISSION | Thu Dec 01 08:00:00 IST 2022 | Wed Jan 11 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1371 | TT_TASK | PREPARATION OF DOCUMENTATION FOR OP SUBMISSION | Thu Jan 12 08:00:00 IST 2023 | Tue Apr 11 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1372 | TT_TASK | PREPARATION OF LAYOUT/LANDSCAPING PLAN | Sat Apr 17 08:00:00 IDT 2021 | Mon May 31 17:00:00 IDT 2021 | Sat Apr 17 08:00:00 IDT 2021 | Mon May 31 17:00:00 IDT 2021 |  | COMPLETED
1373 | TT_TASK | PREPARATION OF LAYOUT/LANDSCAPING PLAN - REVISED/FINAL | Thu Dec 01 08:00:00 IST 2022 | Wed Jan 11 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1374 | TT_TASK | PREPARATION OF BPPS APCL SUBMISSION | Fri May 27 08:00:00 IDT 2022 | Thu Jul 07 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1375 | TT_TASK | PREPARATION OF FINAL SUBMISSION DOCUMENTATION (TOWN WATER DOMESTIC WATER SUPPLY/TOWN WATER SERVICE) | Thu Dec 01 08:00:00 IST 2022 | Tue Jan 24 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1376 | TT_TASK | PREPARATION OF FINAL SUBMISSION DOCUMENTATION ( FRESH FIRE WATER) | Thu Dec 01 08:00:00 IST 2022 | Sun Jan 08 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1377 | TT_TASK | 65 - CONSTRUCTION APPROVAL (CA) APPLICATION | Tue Oct 05 08:00:00 IDT 2021 | Fri Dec 03 17:00:00 IST 2021 | Tue Oct 05 08:00:00 IDT 2021 | Fri Dec 03 17:00:00 IST 2021 |  | COMPLETED
1378 | TT_TASK | 66 - USE APPROVAL (UA) APPLICATION | Sun Jan 22 08:00:00 IST 2023 | Fri Apr 21 17:00:00 IDT 2023 |  |  | 248.0 | NOT_STARTED
1379 | TT_TASK | 67 - PILOT SCHEME FOR COOLING TOWER APPROVED TO EMSD | Sun May 16 08:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Sun May 16 08:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
1380 | TT_TASK | 68 - HELPDESK SUBMISSION OF CONCEPTUAL DESIGN | Tue Jun 15 08:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 | Tue Jun 15 08:00:00 IDT 2021 | Wed Jul 14 17:00:00 IDT 2021 |  | COMPLETED
1381 | TT_TASK | 69 - SPRINKLER LOCAL APPLICATION | Fri Oct 28 08:00:00 IDT 2022 | Fri Feb 24 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1382 | TT_TASK | 70 - AFA DETECTION ALARM | Fri Oct 28 08:00:00 IDT 2022 | Mon Dec 26 17:00:00 IST 2022 |  |  | 1304.0 | NOT_STARTED
1383 | TT_TASK | 73 - OVERALL FIRE WATER DEMAND MAXIMUM DEMAND CALCULATION | Mon Aug 22 08:00:00 IDT 2022 | Tue Sep 20 17:00:00 IDT 2022 |  |  | 1672.0 | NOT_STARTED
1384 | TT_TASK | 75 - INSPECTION PROCEDURES AND SEQUENCING (TESTING STANDARDS FOR ALL SYSTEMS) | Mon Aug 22 08:00:00 IDT 2022 | Tue Sep 20 17:00:00 IDT 2022 |  |  | 1672.0 | NOT_STARTED
1385 | TT_TASK | 76 - HYDRAULIC SUBMISSION APPROVAL (FSI/314 SCHEMATIC DRAWINGS SUBMISSION) | Fri Oct 28 08:00:00 IDT 2022 | Sat Nov 26 17:00:00 IST 2022 |  |  | 1136.0 | NOT_STARTED
1386 | TT_TASK | 77 - FSI/314 SCHEMATIC DRAWINGS (VAC/AFA/FSI APPROVAL) | Mon Aug 22 08:00:00 IDT 2022 | Fri Feb 17 17:00:00 IST 2023 |  |  | 472.0 | NOT_STARTED
1387 | TT_TASK | 78 - SEAWATER DIVERSION OF OUTDDOR FIRE HYDRANTS | Fri Oct 28 08:00:00 IDT 2022 | Sat Nov 26 17:00:00 IST 2022 |  |  | 1136.0 | NOT_STARTED
1388 | TT_TASK | 79 - EM LOCK (ELECTROMAGNETIC DOOR LOCK) | Fri Oct 28 08:00:00 IDT 2022 | Sat Nov 26 17:00:00 IST 2022 |  |  | 1136.0 | NOT_STARTED
1389 | TT_TASK | 80 - LICENSE FOR STORAGE OF DANGEROUS GOODS | Wed Jun 16 08:00:00 IDT 2021 | Sat Aug 14 17:00:00 IDT 2021 | Wed Jun 16 08:00:00 IDT 2021 | Sat Aug 14 17:00:00 IDT 2021 |  | COMPLETED
1390 | TT_TASK | 81- APPLICATION FOR STORAGE/USE/MANUF. OF DANGEROUS GOODS UNDER DG ORDINACE FOR ISSUANCE OF FIRE SAFETY REQUIREMENTS | Sat Nov 19 08:00:00 IST 2022 | Thu Feb 16 17:00:00 IST 2023 |  |  | 464.0 | NOT_STARTED
1391 | TT_TASK | 82 - DANGEROUS GOODS LICENSE INSPECTION APPLICATIONS | Mon Jan 16 08:00:00 IST 2023 | Thu Mar 16 17:00:00 IST 2023 |  |  | 2320.0 | NOT_STARTED
1392 | TT_TASK | 83 - REPORT OF COMPLIANCE | Fri Mar 24 08:00:00 IDT 2023 | Sat Apr 22 17:00:00 IDT 2023 |  |  | 240.0 | NOT_STARTED
1393 | TT_TASK | 84 - PRESSURE VESSELS (FOR CONSTRUCTION WORKS) | Thu Jul 01 08:00:00 IDT 2021 | Sun Aug 29 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Sun Aug 29 17:00:00 IDT 2021 |  | COMPLETED
1394 | TT_TASK | 85 - CERTIFICATES FOR LIFTING APPLIANCES, LIFTING GEARS | Thu Jun 23 08:00:00 IDT 2022 | Sun Aug 21 17:00:00 IDT 2022 |  |  | 3976.0 | NOT_STARTED
1395 | TT_TASK | 86 - CERTIFICATES FOR BOILERS, PRESSURE VESSELS | Tue Feb 21 08:00:00 IST 2023 | Fri Apr 21 17:00:00 IDT 2023 |  |  | 56.0 | NOT_STARTED
1396 | TT_TASK | 87 - NOTIFICATION OF CONSTRUCTION WORKS AND REGISTRATION OF WORKERS TO LD | Tue Jun 01 08:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 | Tue Jun 01 08:00:00 IDT 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1397 | TT_TASK | 88 - IMPORTATION OF WORKERS AND WORKING VISA APPLICATION TO IMMD | Tue Jun 01 08:00:00 IDT 2021 | Sat Nov 27 17:00:00 IST 2021 | Tue Jun 01 08:00:00 IDT 2021 | Sat Nov 27 17:00:00 IST 2021 |  | COMPLETED
1398 | TT_TASK | 89 - BILLING ACCOUNT FOR CONSTRUCTION WASTE DISPOSAL | Tue Mar 16 08:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 | Tue Mar 16 08:00:00 IST 2021 | Wed Apr 14 17:00:00 IDT 2021 |  | COMPLETED
1399 | TT_TASK | 90 - CONSTRUCTION NOISE PERMIT | Wed Jun 02 08:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 | Wed Jun 02 08:00:00 IDT 2021 | Thu Jul 01 17:00:00 IDT 2021 |  | COMPLETED
1400 | TT_TASK | 91 - WASTE WATER DISCHARGE LICENSE | Fri Apr 09 08:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 | Fri Apr 09 08:00:00 IDT 2021 | Mon Jun 07 17:00:00 IDT 2021 |  | COMPLETED
1401 | TT_TASK | 92 - WASTE CHEMICAL DISPOSAL | Wed Jun 02 08:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Wed Jun 02 08:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
1402 | TT_TASK | 94 - SITE SUPERVISION PLANS UNDER AP/RSE/RGE STREAMS | Wed Jun 02 08:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Wed Jun 02 08:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 |  | COMPLETED
1403 | TT_TASK | 95 - SITE SUPERVISION PLANS UNDER RGBC/RSC STREAM | Wed Jun 02 08:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 | Wed Jun 02 08:00:00 IDT 2021 | Tue Jun 22 17:00:00 IDT 2021 |  | COMPLETED
1404 | TT_TASK | 96 - NOTICE OF COMMENCEMENT OF CONSTRUCTION WORKS (FORM1) TO CIC | Tue Jun 01 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue Jun 01 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
1405 | TT_TASK | 97 - NOTICE OF INTERIM PAYMENT (FORM2) TO CIC | Tue Jun 01 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue Jun 01 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
1406 | TT_TASK | 98 - NOTICE OF FINAL PAYMENT (FORM2) TO CIC | Tue Jun 01 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue Jun 01 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
1407 | TT_TASK | 99 - NOTICE TO COMPLETION OF CONSTRUCTION WORKS (FORM3) TO CIC | Sun Dec 31 08:00:00 IST 2023 | Sun Dec 31 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1408 | TT_TASK | 100 - NOTICE OF COMMENCEMENT OF CONSTRUCTION OPERATIONS (FORM1B) TO PCFB | Tue Jun 01 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue Jun 01 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
1409 | TT_TASK | 101 - NOTICE OF INTERIM PAYMENT (FORM2B) TO PCFB | Tue Jun 01 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue Jun 01 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
1410 | TT_TASK | 102 - NOTICE OF FINAL PAYMENT (FORM3B) TO PCFB | Tue Jun 01 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Tue Jun 01 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
1412 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION INSULATION FOR ALL SYSTEMS | Sat Sep 03 08:00:00 IDT 2022 | Fri Sep 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1423 | TT_TASK | ROAD DESIGN STRUCTURAL & FINAL HYDRAULIC CALCULATIONS | Mon Jan 25 08:00:00 IST 2021 | Sun Feb 21 17:00:00 IST 2021 | Mon Jan 25 08:00:00 IST 2021 | Sun Feb 21 17:00:00 IST 2021 |  | COMPLETED
1425 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2B-20UZA01-Excavation /Stripping | Mon Feb 14 08:00:00 IST 2022 | Tue Mar 15 17:00:00 IST 2022 | Mon Feb 14 08:00:00 IST 2022 |  |  | IN_PROGRESS
1426 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2B-20UZA01-Laying base course and compaction | Wed Mar 02 08:00:00 IST 2022 | Sat Mar 19 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1427 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2B-20UZA01-Laying sub base and compaction | Sun Mar 20 08:00:00 IST 2022 | Wed Apr 06 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1428 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2B-20UZA01-Sub Finishing | Thu Apr 07 08:00:00 IDT 2022 | Wed Apr 13 17:00:00 IDT 2022 |  |  | 424.0 | NOT_STARTED
1430 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2C-20UZA01-Excavation /Stripping | Mon Mar 28 08:00:00 IDT 2022 | Tue Apr 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1431 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2C-20UZA01-Laying base course and compaction | Wed Apr 27 08:00:00 IDT 2022 | Mon May 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1432 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2C-20UZA01-Sub Finishing | Tue May 17 08:00:00 IDT 2022 | Sun Jun 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1433 | TT_TASK | COMPOSITE DRAWING RING ROAD INCL. UNDERGROUND (U/G) DRAINAGE PART 2 | Mon Feb 22 08:00:00 IST 2021 | Sat May 29 17:00:00 IDT 2021 | Mon Feb 22 08:00:00 IST 2021 | Sat May 29 17:00:00 IDT 2021 |  | COMPLETED
1434 | TT_TASK | CONCEPT COMPOSITE DRAWING RING ROAD INCL. UNDERGROUND (U/G) DRAINAGE | Fri Jan 15 08:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Thu Jan 28 17:00:00 IST 2021 |  | COMPLETED
1436 | TT_TASK | CLIENT - REVIEW - RING ROAD INCL. UNDERGROUND (U/G) DRAINAGE | Sun May 30 08:00:00 IDT 2021 | Wed Jun 23 17:00:00 IDT 2021 | Sun May 30 08:00:00 IDT 2021 | Wed Jun 23 17:00:00 IDT 2021 |  | COMPLETED
1437 | TT_TASK | BD - SUBMISSION & APPROVAL - RING ROAD | Fri May 21 08:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 | Fri May 21 08:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1438 | TT_TASK | BD - SUBMISSION & APPROVAL -UNDERGROUND (U/G) DRAINAGE RC PLANS | Fri May 21 08:00:00 IDT 2021 | Sun Oct 10 17:00:00 IDT 2021 | Fri May 21 08:00:00 IDT 2021 | Sun Oct 10 17:00:00 IDT 2021 |  | COMPLETED
1439 | TT_TASK | BD - CONSENT LETTER UNDERGROUND (U/G) DRAINAGE | Mon Oct 11 08:00:00 IDT 2021 | Sun Nov 07 17:00:00 IST 2021 | Mon Oct 11 08:00:00 IDT 2021 | Sun Nov 07 17:00:00 IST 2021 |  | COMPLETED
1443 | TT_TASK | SUMMARY SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 3 | Mon Jun 06 08:00:00 IDT 2022 | Mon Aug 15 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1445 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1A-20UZA03-Excavation /Stripping | Mon Oct 11 08:00:00 IDT 2021 | Sun Nov 28 17:00:00 IST 2021 | Mon Oct 11 08:00:00 IDT 2021 | Sun Nov 28 17:00:00 IST 2021 |  | COMPLETED
1446 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1A-20UZA03- base course | Thu Oct 21 08:00:00 IDT 2021 | Thu Dec 02 17:00:00 IST 2021 | Thu Oct 21 08:00:00 IDT 2021 | Thu Dec 02 17:00:00 IST 2021 |  | COMPLETED
1447 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1A-20UZA03- sub base | Mon Oct 25 08:00:00 IDT 2021 | Mon Dec 06 17:00:00 IST 2021 | Mon Oct 25 08:00:00 IDT 2021 | Mon Dec 06 17:00:00 IST 2021 |  | COMPLETED
1448 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1A-20UZA03-Road base | Fri Nov 05 08:00:00 IST 2021 | Thu Dec 16 17:00:00 IST 2021 | Fri Nov 05 08:00:00 IST 2021 | Thu Dec 16 17:00:00 IST 2021 |  | COMPLETED
1449 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1A-20UZA03-drainage | Fri Feb 18 08:00:00 IST 2022 | Thu Apr 07 17:00:00 IDT 2022 | Fri Feb 18 08:00:00 IST 2022 |  | 3896.0 | IN_PROGRESS
1451 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1B-20UZA02-Excavation /Stripping | Mon Mar 28 08:00:00 IDT 2022 | Mon Apr 11 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1452 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1B-20UZA02-Laying base course and compaction | Tue Apr 12 08:00:00 IDT 2022 | Thu Apr 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1453 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1B-20UZA02-Laying sub base and compaction | Fri Apr 22 08:00:00 IDT 2022 | Sun May 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1454 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1B-20UZA02-Sub Finishing | Mon May 02 08:00:00 IDT 2022 | Sun May 08 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1456 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1C-20UZA04-Excavation /Stripping | Mon May 02 08:00:00 IDT 2022 | Mon May 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1457 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1C-20UZA04-Laying base course and compaction | Tue May 17 08:00:00 IDT 2022 | Thu May 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1458 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1C-20UZA04-Laying sub base and compaction | Fri May 27 08:00:00 IDT 2022 | Sun Jun 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1459 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART1C-20UZA04-Sub Finishing | Mon Jun 06 08:00:00 IDT 2022 | Sun Jun 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1461 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2A-20UZA01-Excavation /Stripping | Mon Feb 28 08:00:00 IST 2022 | Mon Mar 07 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1462 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2A-20UZA01-Laying base course and compaction | Tue Mar 08 08:00:00 IST 2022 | Mon Mar 14 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1463 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2A-20UZA01-Laying sub base and compaction | Tue Mar 15 08:00:00 IST 2022 | Mon Mar 21 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1464 | TT_TASK | SUBBASE RING ROAD INCL.(U/G) SYSTEM - PART 2A-20UZA01-Sub Finishing | Tue Mar 22 08:00:00 IST 2022 | Sun Mar 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1465 | TT_TASK | INSULATION PIPES / VALVES FOR STEAM SYSTEM 20LBA10 | Wed Feb 08 08:00:00 IST 2023 | Tue Mar 14 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1466 | TT_TASK | ERECTION, NDT PIPE / VALVES 11LBA10 (TURBOSET) | Thu Dec 08 08:00:00 IST 2022 | Wed Jan 25 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1489 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION OFFRACK / YARD LOT 4 | Sun Apr 24 08:00:00 IDT 2022 | Sat Apr 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1490 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION OFFRACK / YARD LOT 5 | Sun Apr 24 08:00:00 IDT 2022 | Sat Apr 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1491 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION OFFRACK / YARD LOT 6 | Mon Aug 15 08:00:00 IDT 2022 | Sat Aug 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1492 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION GT SPECIAL TOOLS 20MB- | Sat Apr 02 08:00:00 IDT 2022 | Fri Apr 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1493 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION GT INTERMEDIATE SHAFT 20MB- | Sat Apr 09 08:00:00 IDT 2022 | Fri Apr 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1494 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION OFFRACK / YARD LOT 7 | Tue May 24 08:00:00 IDT 2022 | Mon May 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1495 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION PIPING CA/WA06 | Fri Mar 04 08:00:00 IST 2022 | Thu Mar 10 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1496 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION PIPING TP04A/10A | Fri Mar 04 08:00:00 IST 2022 | Thu Mar 10 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1497 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION PIPING PUS | Thu Mar 24 08:00:00 IST 2022 | Wed Mar 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1498 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION PIPING SPARE MATERIAL | Mon Feb 28 08:00:00 IST 2022 | Sun Mar 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1499 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MATERIAL FOR SB PIPING & SUPPORTS | Fri Apr 08 08:00:00 IDT 2022 | Thu Apr 14 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1500 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MODULES LOT 1 | Fri Apr 15 08:00:00 IDT 2022 | Thu Apr 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1501 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MODULES LOT 2 | Sun May 15 08:00:00 IDT 2022 | Sat May 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1502 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MODULES LOT 3 | Fri Jun 24 08:00:00 IDT 2022 | Thu Jun 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1503 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION LOOSE STEEL FOR MODULES LOT 2 (20UMCL1Y/20UMCM1Y) | Sun May 01 08:00:00 IDT 2022 | Sat May 07 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1504 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION LOOSE STEEL FOR MODULES LOT 1 (20UMY00Y/20ULY00Y) | Thu Mar 31 08:00:00 IDT 2022 | Wed Apr 06 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1505 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION ASSEMBLED STEEL FOR MODULES LOT 3 (20UEY1Y) | Sun May 15 08:00:00 IDT 2022 | Sat May 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1506 | TT_TASK | ERECTION, NDT, PT / VALVES INTERCON. PIPING 20EK/MB/AUX. SYSTEM | Mon Oct 17 08:00:00 IDT 2022 | Sun Jan 01 17:00:00 IST 2023 |  |  | 408.0 | NOT_STARTED
1511 | TT_TASK | PREPARATION CHEMICAL CLEANING HRSG20 | Sat Apr 15 08:00:00 IDT 2023 | Fri May 12 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1512 | TT_TASK | CHEMICAL CLEANING HRSG20 STEAM LINES TO ST | Sat May 13 08:00:00 IDT 2023 | Fri Jun 02 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1514 | TT_TASK | COLD COMMISSIONING FOR CHEMICAL CLEANING HRSG | Sat Apr 22 08:00:00 IDT 2023 | Fri May 12 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1515 | TT_TASK | PREPARATION CHEMICAL CLEANING WSC | Sat Apr 15 08:00:00 IDT 2023 | Fri May 12 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1517 | TT_TASK | COLD COMMISSIONING FOR CHEMICAL CLEANING WSC | Sat Apr 22 08:00:00 IDT 2023 | Fri May 12 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1522 | TT_TASK | QUOTATION STAGE GIL 400kV 20ACA | Fri Mar 26 08:00:00 IDT 2021 | Thu Jun 17 17:00:00 IDT 2021 | Fri Mar 26 08:00:00 IDT 2021 | Thu Jun 17 17:00:00 IDT 2021 |  | COMPLETED
1528 | TT_TASK | BASIC DESIGN / SPECIFICATION GIL 400kV 20ACA | Sun Feb 14 08:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 | Sun Feb 14 08:00:00 IST 2021 | Thu Mar 25 17:00:00 IST 2021 |  | COMPLETED
1529 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST GIL 400kV 20ACA | Fri Jun 18 08:00:00 IDT 2021 | Sat Jun 11 17:00:00 IDT 2022 | Fri Jun 18 08:00:00 IDT 2021 |  |  | IN_PROGRESS
1531 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION GIL 400kV 20ACA | Sun Jun 12 08:00:00 IDT 2022 | Sat Jul 09 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1533 | TT_TASK | TRANSPORT GIL 400kV 20ACA | Sun Jul 10 08:00:00 IDT 2022 | Sat Sep 03 17:00:00 IDT 2022 |  |  | 240.0 | NOT_STARTED
1534 | TT_TASK | PLACEMENT GIL 400kV 20ACA | Tue Oct 04 08:00:00 IDT 2022 | Wed Oct 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1535 | TT_TASK | ERECTION GIL 400kV 20ACA | Thu Oct 06 08:00:00 IDT 2022 | Wed Nov 30 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1536 | TT_TASK | ERECTION,TESTING GIL BEFORE HV CABLE CONNECTION 400kV 20ACA GIL COMMISIONING | Thu Dec 01 08:00:00 IST 2022 | Wed Dec 14 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1537 | TT_TASK | DEGASING OF GIL FOR CABLE CONNECTION COMPARTMENT | Thu Jan 26 08:00:00 IST 2023 | Fri Jan 27 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1539 | TT_TASK | SF6 GASING FOR HV CABLE TESTING | Sat Feb 18 08:00:00 IST 2023 | Sun Feb 19 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1540 | TT_TASK | DEGASING OF GIL - INSTALL LINKS BETWEEN CABLE TO GIL CONDUCTOR | Mon Feb 20 08:00:00 IST 2023 | Sun Mar 05 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1541 | TT_TASK | GASING OF CABLE CONNECTION COMPARTMENT | Mon Mar 06 08:00:00 IST 2023 | Tue Mar 07 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1542 | TT_TASK | FLANGE LEAKAGE TEST GIL | Wed Mar 08 08:00:00 IST 2023 | Thu Mar 09 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1546 | TT_TASK | COMMISSIONING GIL 400kV 20ACA - INTERFACE GRID PLANT | Fri Mar 10 08:00:00 IST 2023 | Thu Mar 23 17:00:00 IST 2023 |  |  | 144.0 | NOT_STARTED
1550 | TT_TASK | COMMISSIONING ELECTRICAL MODULES 20UBA1110 | Tue Apr 11 08:00:00 IDT 2023 | Mon Apr 24 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1552 | TT_TASK | COMMISSIONING LIGHTING AND SMALL POWER 20UEN | Sun Mar 26 08:00:00 IDT 2023 | Sat Apr 08 17:00:00 IDT 2023 |  |  | 664.0 | NOT_STARTED
1554 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST IPB 20BAA | Sun May 30 08:00:00 IDT 2021 | Mon Jun 06 17:00:00 IDT 2022 | Sun May 30 08:00:00 IDT 2021 |  |  | IN_PROGRESS
1557 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST IPB FIRST PARTS / SADDLES 20BAA | Tue Oct 05 08:00:00 IDT 2021 | Mon May 30 17:00:00 IDT 2022 | Tue Oct 05 08:00:00 IDT 2021 |  |  | IN_PROGRESS
1558 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION IPB 20BAA | Tue Jun 07 08:00:00 IDT 2022 | Mon Jul 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1559 | TT_TASK | TRANSPORT IPB IPB 20BAA | Tue Jul 05 08:00:00 IDT 2022 | Mon Aug 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1561 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION IPB FIRST PARTS / SADDLES 20BAA | Tue May 31 08:00:00 IDT 2022 | Mon Jun 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1562 | TT_TASK | TRANSPORT IPB IPB FIRST PARTS / SADDLES 20BAA | Tue Jun 28 08:00:00 IDT 2022 | Mon Aug 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1564 | TT_TASK | ERECTION CURRENT TRANSFORMER 20BAA | Mon Sep 26 08:00:00 IDT 2022 | Sun Oct 09 17:00:00 IDT 2022 |  |  | 1576.0 | NOT_STARTED
1565 | TT_TASK | ERECTION IPB PART 1 - 20BAT TO 20BAC | Tue Sep 27 08:00:00 IDT 2022 | Mon Nov 14 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1566 | TT_TASK | CLOSING BUSDUCT AND LEAKAGE TEST 20BAA | Fri Feb 03 08:00:00 IST 2023 | Thu Feb 09 17:00:00 IST 2023 |  |  | 144.0 | NOT_STARTED
1567 | TT_TASK | HIGH VOLTAGE/PRESSURE TEST IPB 20BAA | Tue Jan 24 08:00:00 IST 2023 | Mon Jan 30 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1568 | TT_TASK | ERECTION IPB PART 2 - 20BAC TO 20MKA | Tue Nov 15 08:00:00 IST 2022 | Mon Jan 23 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1569 | TT_TASK | PLACEMENT BAA BELOW AIR FILTER HOUSE OUTER PART 20BAA | Tue Aug 23 08:00:00 IDT 2022 | Mon Aug 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1570 | TT_TASK | CALIBRATING OF CKA SYSTEM (SUPERVISOR) | Tue Jan 31 08:00:00 IST 2023 | Thu Feb 02 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1571 | TT_TASK | BASIC DESIGN / SPECIFICATION CT / GROUNDING CUBICLE 20BAB | Wed Feb 17 08:00:00 IST 2021 | Wed Jun 30 17:00:00 IDT 2021 | Wed Feb 17 08:00:00 IST 2021 | Wed Jun 30 17:00:00 IDT 2021 |  | COMPLETED
1572 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CT / GROUNDING CUBICLE 20BAB | Sat Apr 30 08:00:00 IDT 2022 | Fri May 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1574 | TT_TASK | QUOTATION STAGE CT / GROUNDING CUBICLE 20BAB | Thu Jul 01 08:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 | Thu Jul 01 08:00:00 IDT 2021 | Thu Jul 15 17:00:00 IDT 2021 |  | COMPLETED
1578 | TT_TASK | DESIGN / MANUFACTURING CT / GROUNDING CUBICLE 20BAB | Fri May 14 08:00:00 IDT 2021 | Wed Apr 13 17:00:00 IDT 2022 | Fri May 14 08:00:00 IDT 2021 |  |  | IN_PROGRESS
1582 | TT_TASK | TRANSPORT CT / GROUNDING CUBICLE 20BAB | Mon May 30 08:00:00 IDT 2022 | Mon Aug 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1583 | TT_TASK | ERECTION CT / GROUNDING CUBICLE 20BAB | Tue Aug 23 08:00:00 IDT 2022 | Mon Sep 05 17:00:00 IDT 2022 |  |  | 1848.0 | NOT_STARTED
1584 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST GEN. CIRCUIT BREAKER 20BAC | Fri Jul 16 08:00:00 IDT 2021 | Thu Apr 28 17:00:00 IDT 2022 | Fri Jul 16 08:00:00 IDT 2021 |  |  | IN_PROGRESS
1586 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION GEN. CIRCUIT BREAKER 20BAC | Mon May 23 08:00:00 IDT 2022 | Sun Jun 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1587 | TT_TASK | TRANSPORT GEN. CIRCUIT BREAKER 20BAC | Mon Jun 20 08:00:00 IDT 2022 | Sun Aug 14 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1589 | TT_TASK | PLACING GEN. CIRCUIT BREAKER 20BAC | Mon Sep 26 08:00:00 IDT 2022 | Mon Sep 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1590 | TT_TASK | ERECTION GEN. CIRCUIT BREAKER 20BAC | Fri Oct 07 08:00:00 IDT 2022 | Thu Oct 13 17:00:00 IDT 2022 |  |  | 104.0 | NOT_STARTED
1591 | TT_TASK | COMMISSIONING CIRCUIT BREAKER/ ISOLATED GEN BUSDUCT | Tue Mar 07 08:00:00 IST 2023 | Mon Mar 13 17:00:00 IST 2023 |  |  | 112.0 | NOT_STARTED
1593 | TT_TASK | BASIC DESIGN / SPECIFICATION MAIN TRANSFORMERS BAT/BBT | Fri Jan 15 08:00:00 IST 2021 | Thu Feb 25 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Thu Feb 25 17:00:00 IST 2021 |  | COMPLETED
1596 | TT_TASK | QUOTATION STAGE MAIN TRANSFORMERS BAT/BBT | Fri Feb 26 08:00:00 IST 2021 | Mon May 10 17:00:00 IDT 2021 | Fri Feb 26 08:00:00 IST 2021 | Mon May 10 00:00:00 IDT 2021 |  | COMPLETED
1600 | TT_TASK | AUDIT AT TRANSFORMER MANUFACTURER | Wed Apr 07 08:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 | Wed Apr 07 08:00:00 IDT 2021 | Tue May 04 17:00:00 IDT 2021 |  | COMPLETED
1601 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST MAIN TRANSFORMERS 20BAT | Wed May 05 08:00:00 IDT 2021 | Wed Jun 15 17:00:00 IDT 2022 | Wed May 05 08:00:00 IDT 2021 |  |  | IN_PROGRESS
1608 | TT_TASK | PLACEMENT ON FOUNDATION TRANSFORMER 20BAT | Wed Aug 10 08:00:00 IDT 2022 | Tue Aug 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1609 | TT_TASK | TRANSPORT MAIN TRANSFORMERS 20BAT | Thu Jul 14 08:00:00 IDT 2022 | Thu Jul 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1610 | TT_TASK | TRANSPORT TRANSFORMER OIL FOR 20BAT (PURCHASED LOCALLY) | Sun Aug 28 08:00:00 IDT 2022 | Sun Sep 11 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1611 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MAIN TRANSFORMERS 20BAT | Thu Jun 16 08:00:00 IDT 2022 | Wed Jul 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1612 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION TRANSFORMER OIL FOR 20BAT | Sun Jul 31 08:00:00 IDT 2022 | Sat Aug 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1613 | TT_TASK | INSTALLATION GRATING 20UBE/UBF | Wed Aug 17 08:00:00 IDT 2022 | Fri Aug 19 17:00:00 IDT 2022 |  |  | 1424.0 | NOT_STARTED
1614 | TT_TASK | ERECTION GENERATOR TRANSFORMER 20BAT | Tue Aug 30 08:00:00 IDT 2022 | Mon Oct 03 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1616 | TT_TASK | OIL FILLING GENERATOR TRANSFORMER 20BAT | Mon Sep 12 08:00:00 IDT 2022 | Sun Sep 18 17:00:00 IDT 2022 |  |  | 48.0 | NOT_STARTED
1617 | TT_TASK | ELECTRICAL ERECTION SURGE ARRESTORS (BUILT IN GIL) | Thu Nov 24 08:00:00 IST 2022 | Wed Nov 30 17:00:00 IST 2022 |  |  | 600.0 | NOT_STARTED
1619 | TT_TASK | COMMISSIONING MAIN TRANSFORMER 20BAT | Tue Feb 21 08:00:00 IST 2023 | Mon Mar 06 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1620 | TT_TASK | RFQ FOR LIGHTNING PROTECTION(Not applicable) | Sat Dec 04 08:00:00 IST 2021 | Sun Jan 30 17:00:00 IST 2022 | Sat Dec 04 08:00:00 IST 2021 | Sun Jan 30 17:00:00 IST 2022 |  | COMPLETED
1621 | TT_TASK | QUOTATION PHASE FOR LIGHTNING PROTECTION(Notapplicable) | Sat Dec 11 08:00:00 IST 2021 | Sun Jan 30 17:00:00 IST 2022 | Sat Dec 11 08:00:00 IST 2021 | Sun Jan 30 17:00:00 IST 2022 |  | COMPLETED
1622 | TT_TASK | DETAIL DESIGN LIGHTNING PROTECTION BLDGS | Thu May 06 08:00:00 IDT 2021 | Fri Dec 03 17:00:00 IST 2021 | Thu May 06 08:00:00 IDT 2021 | Fri Dec 03 17:00:00 IST 2021 |  | COMPLETED
1625 | TT_TASK | MANUFACTURING,TRANSPORT MATERIAL LIGHTNING PROTECTION | Mon Jun 27 08:00:00 IDT 2022 | Sun Aug 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1626 | TT_TASK | ERECTION LIGHTNING PROTECTION 20UBE / UBF | Tue Oct 04 08:00:00 IDT 2022 | Mon Nov 14 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1628 | TT_TASK | ERECTION LIGHTNING PROTECTION 20UHA | Mon Sep 12 08:00:00 IDT 2022 | Sun Oct 09 17:00:00 IDT 2022 |  |  | 1008.0 | NOT_STARTED
1629 | TT_TASK | ERECTION OUTDOOR EARTHING 20UBF AREA | Mon Dec 05 08:00:00 IST 2022 | Sun Feb 12 17:00:00 IST 2023 |  |  | 328.0 | NOT_STARTED
1630 | TT_TASK | ERECTION OUTDOOR EARTHING/LIGHTNING BOP AREA | Tue Aug 16 08:00:00 IDT 2022 | Wed Nov 23 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1631 | TT_TASK | ERECTION OUTDOOR EARTHING 20UMC AREA | Sun Jan 22 08:00:00 IST 2023 | Sat Feb 18 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1633 | TT_TASK | ERECTION LIGHTNING PROTECTION 20UMC | Mon Aug 22 08:00:00 IDT 2022 | Sun Oct 16 17:00:00 IDT 2022 |  |  | 2072.0 | NOT_STARTED
1634 | TT_TASK | ERECTION OUTDOOR EARTHING/LIGHTNING 00UEN03/04 AREA | Thu Aug 25 08:00:00 IDT 2022 | Wed Oct 05 17:00:00 IDT 2022 |  |  | 1368.0 | NOT_STARTED
1635 | TT_TASK | ERECTION INDOOR EARTHING 20UMC | Sun Aug 28 08:00:00 IDT 2022 | Sat Oct 22 17:00:00 IDT 2022 |  |  | 1232.0 | NOT_STARTED
1636 | TT_TASK | ERECTION OUTDOOR EARTHING/LIGHTNING 20URA/URD AREA | Sat Jul 02 08:00:00 IDT 2022 | Sun Oct 09 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1637 | TT_TASK | ERECTION LIGHTNING PROTECTION BOP | Thu Oct 27 08:00:00 IDT 2022 | Wed Nov 23 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1638 | TT_TASK | ERECTION LIGHTNING PROTECTION COOLING TOWER AREA (20URA/URD/UBA8110/20/UBD03/04) | Fri Mar 24 08:00:00 IDT 2023 | Wed May 24 17:00:00 IDT 2023 |  |  | 312.0 | NOT_STARTED
1639 | TT_TASK | ERECTION OUTDOOR EARTHING/LIGHTNING 20ULA/UHA AREA | Sun Sep 11 08:00:00 IDT 2022 | Sat Nov 05 17:00:00 IST 2022 |  |  | 1120.0 | NOT_STARTED
1640 | TT_TASK | ERECTION INDOOR EARTHING 20URD | Tue Jun 21 08:00:00 IDT 2022 | Mon Aug 15 17:00:00 IDT 2022 |  |  | 2568.0 | NOT_STARTED
1641 | TT_TASK | ERECTION LIGHTNING PROTECTION 00UEN | Thu Oct 27 08:00:00 IDT 2022 | Wed Nov 23 17:00:00 IST 2022 |  |  | 1384.0 | NOT_STARTED
1646 | TT_TASK | COMMISSIONING ELECTRICAL INTERFACE GRID/PLANT (6.6kV MV CONNECTION) | Thu Mar 23 08:00:00 IST 2023 | Wed Mar 29 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1647 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST MV SWITCHGEAR 20/01BBA/BBB | Sat Aug 14 08:00:00 IDT 2021 | Mon Mar 07 17:00:00 IST 2022 | Sat Aug 14 08:00:00 IDT 2021 |  |  | IN_PROGRESS
1648 | TT_TASK | TRANSPORT TO WORKSHOP MV SWITCHGEAR 20/01BBA/BBB (TO ST. INGBERT-INSTALL INTO ELECTRICAL MODULES) | Tue Mar 08 08:00:00 IST 2022 | Mon Mar 14 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1649 | TT_TASK | COMMISSIONING MV SWITCHGEAR FEEDER 1 FOR MV + PROTECTION LINK C STATION TO D2 STATION 90BBA01 | Wed Mar 08 08:00:00 IST 2023 | Wed Mar 22 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1651 | TT_TASK | COMMISSIONING MV SWITCHGEAR FEEDER 1 FOR MV + PROTECTION LINK D2 STATION 90BBA02 IN 01UBA9010/20 TO D1 STATION 10BBA05 | Thu Mar 30 08:00:00 IDT 2023 | Wed Apr 12 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1653 | TT_TASK | COMMISSIONING MV SWITCHGEAR FEEDER 2 FOR MV + PROTECTION LINK C STATION TO D2 STATION 90BBB01 | Tue May 23 08:00:00 IDT 2023 | Tue Jun 06 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1655 | TT_TASK | COMMISSIONING MV SWITCHGEAR FEEDER 2 FOR MV + PROTECTION LINK D2 STATION 90BBB02 IN 01UBA9010/20 TO D1 STATION 10BBA06 | Wed Jun 07 08:00:00 IDT 2023 | Tue Jun 20 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1658 | TT_TASK | COMMISSIONING MV SWITCHGEAR 20BBB | Thu Mar 30 08:00:00 IDT 2023 | Wed Apr 12 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1659 | TT_TASK | FEEDER COMMISSIONING MV SWITCHGEAR 20BBB | Thu Apr 13 08:00:00 IDT 2023 | Wed May 31 17:00:00 IDT 2023 |  |  | 16.0 | NOT_STARTED
1660 | TT_TASK | COMMISSIONING MV SWITCHGEAR 20BBA | Wed Feb 22 08:00:00 IST 2023 | Tue Mar 07 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1661 | TT_TASK | FEEDER COMMISSIONING MV SWITCHGEAR 20BBA | Thu Mar 30 08:00:00 IDT 2023 | Wed May 17 17:00:00 IDT 2023 |  |  | 96.0 | NOT_STARTED
1670 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST AUX. TRANSFORMER 20BBT | Wed May 05 08:00:00 IDT 2021 | Wed Jun 15 17:00:00 IDT 2022 | Wed May 05 08:00:00 IDT 2021 |  |  | IN_PROGRESS
1672 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION AUX. TRANSFORMER 20BBT | Thu Jun 16 08:00:00 IDT 2022 | Wed Jul 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1673 | TT_TASK | TRANSPORT AUX. TRANSFORMER 20BBT | Thu Jul 14 08:00:00 IDT 2022 | Thu Jul 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1675 | TT_TASK | PLACEMENT AUX. TRANSFORMER 20BBT | Wed Aug 17 08:00:00 IDT 2022 | Sun Aug 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1676 | TT_TASK | ERECTION AUX. TRANSFORMER 20BBT | Mon Aug 22 08:00:00 IDT 2022 | Sun Sep 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1677 | TT_TASK | COMMISSIONING AUX. TRANSFORMER 20BBT01 | Tue Mar 07 08:00:00 IST 2023 | Mon Mar 13 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1679 | TT_TASK | COMMISSIONING LV SWITCHGEAR BFF/BMF (HRSG) | Tue Apr 11 08:00:00 IDT 2023 | Mon Apr 17 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1680 | TT_TASK | FEEDER COMMISSIONING LV SWITCHGEAR BFF/BMF | Tue Apr 18 08:00:00 IDT 2023 | Mon Jun 05 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1681 | TT_TASK | BASIC DESIGN / SPECIFICATION LV- / DC-SWITCHGEAR BFA/BFB/BMA/BUA/BUB/BUC | Fri Feb 12 08:00:00 IST 2021 | Thu May 13 17:00:00 IDT 2021 | Fri Feb 12 08:00:00 IST 2021 | Thu May 13 17:00:00 IDT 2021 |  | COMPLETED
1682 | TT_TASK | DETAIL DESIGN / CLARIFICATION TYPICAL OF LV- / DC-SWITCHGEAR BFA/BFB/BMA/BUA/BUB/BUC | Fri Jul 30 08:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Fri Jul 30 08:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 |  | COMPLETED
1684 | TT_TASK | QUOTATION STAGE LV- / DC-SWITCHGEAR BFA/BFB/BMA/BUA/BUB/BUC | Fri May 14 08:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 | Fri May 14 08:00:00 IDT 2021 | Tue Jun 29 17:00:00 IDT 2021 |  | COMPLETED
1687 | TT_TASK | MANUFACTURING / SHOP TEST LV- / DC-SWITCHGEAR BFA/BFB/BMA/BUA/BUB/BUC | Wed Sep 08 08:00:00 IDT 2021 | Tue Feb 15 17:00:00 IST 2022 | Wed Sep 08 08:00:00 IDT 2021 | Tue Feb 15 17:00:00 IST 2022 |  | COMPLETED
1689 | TT_TASK | TRANSPORT TO WORKSHOP LV- / DC-SWITCHGEAR BFA/BFB/BMA/BUA/BUB/BUC (TO ST. INGBERT-INSTALL INTO ELECTRICAL MODULES) | Wed Feb 16 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 | Wed Feb 16 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 |  | COMPLETED
1691 | TT_TASK | COMMISSIONING LV SWITCHGEAR 20BFA / BMA / BFB | Tue Feb 07 08:00:00 IST 2023 | Mon Feb 13 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1692 | TT_TASK | FEEDER COMMISSIONING LV SWITCHGEAR 20BFA / BMA / BFB | Tue Apr 11 08:00:00 IDT 2023 | Mon May 29 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1694 | TT_TASK | BASIC DESIGN / SPECIFICATION LV- / DC-SWITCHGEAR 20BFC/BFD | Fri Apr 02 08:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 | Fri Apr 02 08:00:00 IDT 2021 | Thu May 27 17:00:00 IDT 2021 |  | COMPLETED
1696 | TT_TASK | QUOTATION STAGE LV- / DC-SWITCHGEAR 20BFC/BFD | Fri May 28 08:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 | Fri May 28 08:00:00 IDT 2021 | Thu Jul 08 17:00:00 IDT 2021 |  | COMPLETED
1699 | TT_TASK | DETAIL DESIGN / CLARIFICATION TYPICAL OF LV- / DC-SWITCHGEAR 20BFC/BFD | Fri Jul 30 08:00:00 IDT 2021 | Tue Dec 07 17:00:00 IST 2021 | Fri Jul 30 08:00:00 IDT 2021 | Tue Dec 07 17:00:00 IST 2021 |  | COMPLETED
1700 | TT_TASK | MANUFACTURING / SHOP TEST LV- / DC-SWITCHGEAR 20BFC/BFD | Wed Feb 16 08:00:00 IST 2022 | Tue Jun 14 17:00:00 IDT 2022 | Wed Feb 16 08:00:00 IST 2022 |  |  | IN_PROGRESS
1701 | TT_TASK | TRANSPORT TO WORKSHOP LV- / DC-SWITCHGEAR 20BFC/BFD (only as ELECTRICAL MODULES) | Wed Jun 15 08:00:00 IDT 2022 | Tue Jun 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1703 | TT_TASK | COMMISSIONING LV SWITCHGEAR 20BFC/BFD | Tue Apr 18 08:00:00 IDT 2023 | Mon May 01 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1704 | TT_TASK | MANUFACTURING / SHOP TEST LV SWITCHGEAR FOR HRSG 20BFF/BMF | Tue Feb 15 08:00:00 IST 2022 | Mon Jun 13 17:00:00 IDT 2022 | Tue Feb 15 08:00:00 IST 2022 |  |  | IN_PROGRESS
1706 | TT_TASK | TRANSPORT LV SWITCHGEAR FOR HRSG 20BFF/BMFF TO WORKSHOP OF ELECTRICAL MODULES MANUFACTURER | Tue Jun 14 08:00:00 IDT 2022 | Wed Jun 15 17:00:00 IDT 2022 |  |  | 448.0 | NOT_STARTED
1708 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST LV-TRANSFORMERS BFT | Wed Sep 22 08:00:00 IDT 2021 | Thu Mar 31 17:00:00 IDT 2022 | Wed Sep 22 08:00:00 IDT 2021 |  |  | IN_PROGRESS
1711 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION LV-TRANSFORMERS BFT | Fri Apr 01 08:00:00 IDT 2022 | Thu Apr 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1712 | TT_TASK | TRANSPORT LV-TRANSFORMERS 20BFT01/02 | Fri Apr 29 08:00:00 IDT 2022 | Thu Jun 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1716 | TT_TASK | ERECTION LV-TRANSFORMERS 20BFT01/02 | Thu Aug 11 08:00:00 IDT 2022 | Wed Aug 31 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1717 | TT_TASK | PLACING LV-TRANSFORMERS 20BFT01/02 | Thu Jun 30 08:00:00 IDT 2022 | Thu Jun 30 17:00:00 IDT 2022 |  |  | 328.0 | NOT_STARTED
1719 | TT_TASK | COMMISSIONING LV-TRANSFORMERS 20BFT01 | Wed Feb 22 08:00:00 IST 2023 | Tue Mar 07 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1721 | TT_TASK | COMMISSIONING LV-TRANSFORMERS 20BFT02 | Tue Mar 28 08:00:00 IDT 2023 | Mon Apr 10 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1725 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST INVERTER 20BRU20 | Thu Sep 30 08:00:00 IDT 2021 | Fri Feb 11 17:00:00 IST 2022 | Thu Sep 30 08:00:00 IDT 2021 | Fri Feb 11 17:00:00 IST 2022 |  | COMPLETED
1726 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST AC-DC CONVERTER BUK | Thu Sep 30 08:00:00 IDT 2021 | Fri Feb 18 17:00:00 IST 2022 | Thu Sep 30 08:00:00 IDT 2021 | Fri Feb 18 17:00:00 IST 2022 |  | COMPLETED
1727 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST INVERTER 20BRU10 | Thu Sep 30 08:00:00 IDT 2021 | Fri May 13 17:00:00 IDT 2022 | Thu Sep 30 08:00:00 IDT 2021 |  |  | IN_PROGRESS
1728 | TT_TASK | TRANSPORT TO WORKSHOP INVERTER BRU (TO ST. INGBERT-INSTALL INTO ELECTRICAL MODULES) | Sat Feb 12 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 | Sat Feb 12 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 |  | COMPLETED
1730 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION INVERTER 20BRU10 (TO SITE) | Sat May 14 08:00:00 IDT 2022 | Fri Jun 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1732 | TT_TASK | TRANSPORT INVERTER 20BRU10 (TO SITE) | Sat Jun 11 08:00:00 IDT 2022 | Fri Aug 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1734 | TT_TASK | INSTALL 20BRU10 INTO PCC 20UBA7710 | Sat Aug 06 08:00:00 IDT 2022 | Mon Aug 08 17:00:00 IDT 2022 |  |  | 1024.0 | NOT_STARTED
1735 | TT_TASK | BASIC DESIGN / SPECIFICATION BATTERIES & RACKS BTA | Wed Jun 30 08:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 | Wed Jun 30 08:00:00 IDT 2021 | Wed Aug 11 17:00:00 IDT 2021 |  | COMPLETED
1737 | TT_TASK | QUOTATION STAGE BATTERIES & RACKS BTA | Thu Aug 12 08:00:00 IDT 2021 | Wed Nov 17 17:00:00 IST 2021 | Thu Aug 12 08:00:00 IDT 2021 | Wed Nov 17 17:00:00 IST 2021 |  | COMPLETED
1739 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST BATTERIES RACKS BTA | Thu Nov 18 08:00:00 IST 2021 | Sun Feb 20 17:00:00 IST 2022 | Thu Nov 18 08:00:00 IST 2021 | Sun Feb 20 17:00:00 IST 2022 |  | COMPLETED
1740 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST BATTERIES BTA | Thu Nov 18 08:00:00 IST 2021 | Wed May 18 17:00:00 IDT 2022 | Thu Nov 18 08:00:00 IST 2021 |  |  | IN_PROGRESS
1741 | TT_TASK | PLACEMENT OF BATTERIES INTO RACKS BATTERIES BTA | Thu Dec 15 08:00:00 IST 2022 | Wed Dec 21 17:00:00 IST 2022 |  |  | 176.0 | NOT_STARTED
1742 | TT_TASK | TRANSPORT TO WORKSHOP BATTERY RACKS BTA (TO ST. INGBERT-INSTALL INTO ELECTRICAL MODULES) | Mon Feb 21 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 | Mon Feb 21 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 |  | COMPLETED
1743 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST BATTERY CHARGER BTL | Thu Sep 30 08:00:00 IDT 2021 | Fri Feb 11 17:00:00 IST 2022 | Thu Sep 30 08:00:00 IDT 2021 | Fri Feb 11 17:00:00 IST 2022 |  | COMPLETED
1744 | TT_TASK | TRANSPORT TO WORKSHOP BATTERY CHARGER BTL (TO ST. INGBERT-INSTALL INTO ELECTRICAL MODULES) | Sat Feb 12 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 | Sat Feb 12 08:00:00 IST 2022 | Fri Feb 18 17:00:00 IST 2022 |  | COMPLETED
1745 | TT_TASK | TRANSPORT TO WORKSHOP AC-DC CONVERTER BUK (TO ST. INGBERT-INSTALL INTO ELECTRICAL MODULES) | Sat Feb 19 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 | Sat Feb 19 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 |  | COMPLETED
1746 | TT_TASK | COMMISSIONING DC SYSTEM 20BU/BRU | Tue Feb 14 08:00:00 IST 2023 | Mon Feb 20 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1747 | TT_TASK | BASIC DESIGN / SPECIFICATION INVERTER,CONVERTER,BATTERY CHARGER BRU/BTL | Fri Jul 30 08:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 | Fri Jul 30 08:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 |  | COMPLETED
1749 | TT_TASK | QUOTATION STAGE INVERTER, CONVERTER, BATTERY CHARGER BRU/BTL | Thu Aug 19 08:00:00 IDT 2021 | Mon Sep 20 17:00:00 IDT 2021 | Thu Aug 19 08:00:00 IDT 2021 | Tue Sep 21 00:00:00 IDT 2021 |  | COMPLETED
1752 | TT_TASK | MANUFACTURING / SHOP TEST MV/LV CABLES20/00BZK (LOT 1) | Sun Jan 30 08:00:00 IST 2022 | Sun May 29 17:00:00 IDT 2022 | Sun Jan 30 08:00:00 IST 2022 |  |  | IN_PROGRESS
1755 | TT_TASK | MANUFACTURING / SHOP TEST I&C CABLES BZK (LOT 1) | Thu Dec 02 08:00:00 IST 2021 | Tue Apr 19 17:00:00 IDT 2022 | Thu Dec 02 08:00:00 IST 2021 |  |  | IN_PROGRESS
1758 | TT_TASK | MANUFACTURING / SHOP TEST I&C CABLES BZK (LOT 2) | Sat Mar 26 08:00:00 IDT 2022 | Tue Aug 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1761 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MV/LV CABLES20/00BZK (LOT 1) | Mon May 30 08:00:00 IDT 2022 | Sun Jun 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1762 | TT_TASK | TRANSPORT MV/LV CABLES20/00BZK (LOT 1) (THAILAND) | Mon Jun 27 08:00:00 IDT 2022 | Tue Jul 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1764 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION I&C CABLES BZK (LOT 1) | Wed Apr 20 08:00:00 IDT 2022 | Tue May 17 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1765 | TT_TASK | TRANSPORT I&C CABLES BZK (LOT 1) | Wed May 18 08:00:00 IDT 2022 | Tue Jul 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1767 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION I&C CABLES BZK (LOT 2) | Wed Aug 03 08:00:00 IDT 2022 | Tue Aug 30 17:00:00 IDT 2022 |  |  | 8.0 | NOT_STARTED
1768 | TT_TASK | TRANSPORT I&C CABLES BZK (LOT 2) | Thu Sep 01 08:00:00 IDT 2022 | Wed Oct 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1770 | TT_TASK | ELECTRICAL ERECTION STACK HRSG20_3rd part INCL. CABLES / HEATED PROBE FOR EMISSION MONITORING | Sat Sep 03 08:00:00 IDT 2022 | Mon Sep 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1771 | TT_TASK | ERECTION CABLING 20UBA1110 TO HRSG (AFTER ELECTRICAL MODULES INSTALLATION) | Sat Dec 17 08:00:00 IST 2022 | Fri Feb 17 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1772 | TT_TASK | ERECTION CABLING HRSG TO CCR | Wed Nov 02 08:00:00 IST 2022 | Tue Nov 22 17:00:00 IST 2022 |  |  | 400.0 | NOT_STARTED
1773 | TT_TASK | CABLING TO 20UBA1110 AND ULA FROM EXTERNAL | Sat Dec 17 08:00:00 IST 2022 | Fri Jan 13 17:00:00 IST 2023 |  |  | 696.0 | NOT_STARTED
1774 | TT_TASK | CABLING ULA INTERNAL TO 20UBA1110 | Sat Dec 17 08:00:00 IST 2022 | Fri Dec 30 17:00:00 IST 2022 |  |  | 808.0 | NOT_STARTED
1775 | TT_TASK | 10BBA06 - FEEDER 2: MV + CONTROL CABLE CONN. C STATION / D1 STATION TO BE REMOVED FROM CABLE TRAY | Tue Apr 11 08:00:00 IDT 2023 | Mon May 08 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1776 | TT_TASK | 10BBA06 - FEEDER 2: MV + CONTROL CABLE CONN. D1 STATION FROM 10BBA06 TO D2 STATION 90BBB01 INSTALLED ON CABLE TRAY | Tue May 09 08:00:00 IDT 2023 | Mon May 22 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1778 | TT_TASK | CABLING (LATS) ST 20 | Thu Nov 10 08:00:00 IST 2022 | Wed Dec 21 17:00:00 IST 2022 |  |  | 288.0 | NOT_STARTED
1779 | TT_TASK | 10BBA05 - FEEDER 1: MV + CONTROL CABLE CONN. C STATION / D1 STATION TO BE REMOVED FROM CABLE TRAY | Sun Jan 15 08:00:00 IST 2023 | Sat Feb 11 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1780 | TT_TASK | 10BBA05 - FEEDER 1: MV + CONTROL CABLE CONN. D1 STATION FROM 10BBA05 TO D2 STATION 90BBA01 INSTALLED ON CABLE TRAY | Sun Feb 12 08:00:00 IST 2023 | Sat Feb 25 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1781 | TT_TASK | CABLING GENERATOR INTERNAL / GEN. AUXILIARIES | Mon Sep 26 08:00:00 IDT 2022 | Sun Oct 16 17:00:00 IDT 2022 |  |  | 904.0 | NOT_STARTED
1782 | TT_TASK | CABLING LV /MV CABLES GT INTERNAL / TO AUXILIARIES 20UMC | Thu Oct 13 08:00:00 IDT 2022 | Tue Dec 06 17:00:00 IST 2022 |  |  | 56.0 | NOT_STARTED
1783 | TT_TASK | CABLING (E AND I&C CABLES) GENERATOR 20 | Mon Oct 10 08:00:00 IDT 2022 | Sun Nov 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1784 | TT_TASK | CABLING ELECTRICAL MODULES 20UBA (10x) TO TRANSFORMER AREA (BAT/BBT/BAC/GIL) | Thu Oct 27 08:00:00 IDT 2022 | Wed Dec 14 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1785 | TT_TASK | CABLING GT TO AIR INTAKE 20MBL | Sun Dec 11 08:00:00 IST 2022 | Sat Dec 17 17:00:00 IST 2022 |  |  | 1040.0 | NOT_STARTED
1786 | TT_TASK | CABLING GIS TO D2 | Thu Dec 15 08:00:00 IST 2022 | Wed Jan 11 17:00:00 IST 2023 |  |  | 712.0 | NOT_STARTED
1787 | TT_TASK | CABLING 20UMC TO UBA7x | Sun Dec 11 08:00:00 IST 2022 | Sat Jan 14 17:00:00 IST 2023 |  |  | 184.0 | NOT_STARTED
1788 | TT_TASK | CABLING TO GT FROM 20UBA7x | Sun Dec 11 08:00:00 IST 2022 | Sat Dec 17 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1789 | TT_TASK | INTERCONNECTING I&C CABLING TO EXISTING DCS IN 00UCA (D1) -D2 TO D1 CONTROL ROOM | Tue Nov 15 08:00:00 IST 2022 | Mon Dec 19 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1790 | TT_TASK | CABLING FROM 20UBA (10x) TO 20UBA8110/20 AND URD | Fri Dec 16 08:00:00 IST 2022 | Thu Feb 02 17:00:00 IST 2023 |  |  | 96.0 | NOT_STARTED
1791 | TT_TASK | LV/CONTROL CABLE WORKS IN 00UCA | Wed Nov 02 08:00:00 IST 2022 | Tue Nov 29 17:00:00 IST 2022 |  |  | 608.0 | NOT_STARTED
1792 | TT_TASK | CABLING WORKS 20UBA (10x) to 20UMX02/01UEN | Fri Dec 30 08:00:00 IST 2022 | Thu Jan 26 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1793 | TT_TASK | INTERCONNECTING I&C CABLING TO EXISTING DCS IN 00UCA (D1) - 20UBA90xx TO UCA(C) / D1 | Tue Nov 15 08:00:00 IST 2022 | Sat May 13 17:00:00 IDT 2023 |  |  | 384.0 | NOT_STARTED
1794 | TT_TASK | CABLING FROM 20UBA (10x) TO 20UBN | Sun Dec 04 08:00:00 IST 2022 | Sat Jan 28 17:00:00 IST 2023 |  |  | 72.0 | NOT_STARTED
1795 | TT_TASK | INTERCONNECTING CABLING WITH D1 (LBG/LDK) | Tue Nov 15 08:00:00 IST 2022 | Mon Mar 20 17:00:00 IST 2023 |  |  | 168.0 | NOT_STARTED
1796 | TT_TASK | INSTALLATION OF I&C CABINETS | Thu Aug 04 08:00:00 IDT 2022 | Wed Aug 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1797 | TT_TASK | INSTALLATION OF CCR EQUIPMENT | Thu Aug 11 08:00:00 IDT 2022 | Wed Aug 17 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1798 | TT_TASK | INSTALLATION OF NEW MIMIC PANELS | Sat Jul 30 08:00:00 IDT 2022 | Wed Aug 03 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1799 | TT_TASK | RELOCATION OF TABLES | Fri Jul 08 08:00:00 IDT 2022 | Sun Jul 17 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1800 | TT_TASK | SHIFTING OF BOARDS AND MIMICS | Mon Jul 18 08:00:00 IDT 2022 | Fri Jul 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1801 | TT_TASK | INSTALLATION OF NEW TABLES | Sat Jul 23 08:00:00 IDT 2022 | Fri Jul 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1802 | TT_TASK | CABLING FROM 00UCA TO D2 STATION | Wed Nov 02 08:00:00 IST 2022 | Tue Dec 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1803 | TT_TASK | CABLING FROM 00UCA TO 400kV SUBSTATION | Wed Dec 07 08:00:00 IST 2022 | Tue Jan 03 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1804 | TT_TASK | RELOCATION C4 | Thu Apr 15 08:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Thu Apr 15 08:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 |  | COMPLETED
1805 | TT_TASK | RELOCATION C1 | Mon Dec 06 08:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 | Mon Dec 06 08:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  | COMPLETED
1806 | TT_TASK | RELOCATION C2 / C3 | Tue Feb 01 08:00:00 IST 2022 | Thu Feb 10 17:00:00 IST 2022 | Tue Feb 01 08:00:00 IST 2022 | Thu Feb 10 17:00:00 IST 2022 |  | COMPLETED
1807 | TT_TASK | CABLING DEMIN. WATER AREA | Fri Dec 16 08:00:00 IST 2022 | Thu Dec 29 17:00:00 IST 2022 |  |  | 1144.0 | NOT_STARTED
1808 | TT_TASK | CABLING TO / INSIDE WATER INTAKE | Fri Mar 24 08:00:00 IDT 2023 | Thu Apr 06 17:00:00 IDT 2023 |  |  | 368.0 | NOT_STARTED
1809 | TT_TASK | CABLING MV COUPLING 20BBA - 90BBA & 20BBB - 90BBB | Thu Oct 27 08:00:00 IDT 2022 | Wed Nov 23 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1810 | TT_TASK | CABLING (LATS) GENERATOR 20 | Sun Feb 26 08:00:00 IST 2023 | Sat Mar 11 17:00:00 IST 2023 |  |  | 80.0 | NOT_STARTED
1811 | TT_TASK | CABLING ST/ST AUXILIARIES | Thu Oct 06 08:00:00 IDT 2022 | Wed Dec 21 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1812 | TT_TASK | CABLING TO ST FROM 20UBA7x | Thu Oct 06 08:00:00 IDT 2022 | Wed Nov 16 17:00:00 IST 2022 |  |  | 1216.0 | NOT_STARTED
1815 | TT_TASK | CABLING FROM 20UBA (10x) TO 01UBA9010/20 | Thu Dec 01 08:00:00 IST 2022 | Wed Jan 25 17:00:00 IST 2023 |  |  | 8.0 | NOT_STARTED
1816 | TT_TASK | CABLING 20UMC ST TO LDK | Mon Oct 10 08:00:00 IDT 2022 | Mon Jan 02 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1817 | TT_TASK | CABLING MODULES IN UMC BUILDING | Sun Dec 11 08:00:00 IST 2022 | Sat Jan 07 17:00:00 IST 2023 |  |  | 800.0 | NOT_STARTED
1818 | TT_TASK | CABLING TO OIL MODULE | Sun Dec 11 08:00:00 IST 2022 | Sat Dec 31 17:00:00 IST 2022 |  |  | 416.0 | NOT_STARTED
1819 | TT_TASK | CABLING 20UBA (10x) to 20UEN AND DOSING | Sun Feb 05 08:00:00 IST 2023 | Sat Feb 25 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1820 | TT_TASK | CABLING (E AND I&C CABLES) GT20 | Sun Jan 08 08:00:00 IST 2023 | Sat Feb 18 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1821 | TT_TASK | CABLING TO GENERATOR 20MKA | Thu Oct 13 08:00:00 IDT 2022 | Wed Nov 09 17:00:00 IST 2022 |  |  | 1328.0 | NOT_STARTED
1822 | TT_TASK | CABLING GT TO EMERGENCY DIESEL | Sat Oct 22 08:00:00 IDT 2022 | Fri Nov 04 17:00:00 IST 2022 |  |  | 1624.0 | NOT_STARTED
1823 | TT_TASK | CABLING STREET AREA | Thu May 11 08:00:00 IDT 2023 | Wed May 24 17:00:00 IDT 2023 |  |  | 296.0 | NOT_STARTED
1824 | TT_TASK | CABLING GT LATS GT20 | Sun Dec 18 08:00:00 IST 2022 | Sat Feb 25 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1825 | TT_TASK | LIGHTING AND SMALL POWER INSTALLATION STREET LIGHTING 20UZA | Tue Aug 16 08:00:00 IDT 2022 | Tue Dec 13 17:00:00 IST 2022 |  |  | 3064.0 | NOT_STARTED
1827 | TT_TASK | LIGHTING AND SMALL POWER INSTALLATION UBF/UBN | Thu Dec 15 08:00:00 IST 2022 | Wed Jan 11 17:00:00 IST 2023 |  |  | 712.0 | NOT_STARTED
1828 | TT_TASK | LIGHTING AND SMALL POWER INSTALLATION 20UBA76xx/77xx/7410/73xx/7210/7110/7920/10 | Mon Sep 26 08:00:00 IDT 2022 | Sun Oct 16 17:00:00 IDT 2022 |  |  | 1408.0 | NOT_STARTED
1829 | TT_TASK | LIGHTING AND SMALL POWER INSTALLATION 20UEX01/20UBN | Sat Sep 17 08:00:00 IDT 2022 | Fri Oct 14 17:00:00 IDT 2022 |  |  | 56.0 | NOT_STARTED
1830 | TT_TASK | EXTERNAL LIGHTING AND SMALL POWER INSTALLATION 01UBA9010/20 | Tue Oct 04 08:00:00 IDT 2022 | Mon Oct 17 17:00:00 IDT 2022 |  |  | 1032.0 | NOT_STARTED
1831 | TT_TASK | EXTERNAL LIGHTING AND SMALL POWER INSTALLATION 20UBA1110 | Sat Dec 17 08:00:00 IST 2022 | Fri Dec 30 17:00:00 IST 2022 |  |  | 808.0 | NOT_STARTED
1832 | TT_TASK | LIGHTING AND SMALL POWER INSTALLATION 20ULA AREA | Sat Sep 03 08:00:00 IDT 2022 | Tue Nov 01 17:00:00 IST 2022 |  |  | 912.0 | NOT_STARTED
1833 | TT_TASK | LIGHTING AND SMALL POWER 20UEN | Sun Mar 12 08:00:00 IST 2023 | Sat Mar 25 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1834 | TT_TASK | EXTERNAL LIGHTING AND SMALL POWER INSTALLATION 20UBA8110/20 | Fri Dec 16 08:00:00 IST 2022 | Thu Dec 29 17:00:00 IST 2022 |  |  | 816.0 | NOT_STARTED
1835 | TT_TASK | LIGHTING AND SMALL POWER INSTALLATION 20URD | Thu Jul 28 08:00:00 IDT 2022 | Wed Sep 07 17:00:00 IDT 2022 |  |  | 1352.0 | NOT_STARTED
1836 | TT_TASK | LIGHTING AND SMALL POWER INSTALLATION 20URA FIRST 4 CELLS | Fri Feb 24 08:00:00 IST 2023 | Thu Mar 16 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1837 | TT_TASK | LIGHTING AND SMALL POWER INSTALLATION 20URA LAST 4 CELLS | Thu Apr 13 08:00:00 IDT 2023 | Wed May 03 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1838 | TT_TASK | LIGHTING AND SMALL POWER INSTALLATION 01UEN | Thu Dec 08 08:00:00 IST 2022 | Wed Dec 21 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1839 | TT_TASK | LIGHTING AND SMALL POWER INSTALLATION 20UMC - HIGH BAY | Tue Jun 07 08:00:00 IDT 2022 | Mon Jun 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1840 | TT_TASK | LIGHTING AND SMALL POWER INSTALLATION IN ENCLOSURE 20UMC | Fri Sep 23 08:00:00 IDT 2022 | Thu Oct 06 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1841 | TT_TASK | LIGHTING AND SMALL POWER INSTALLATION 20UMC - REMAINING | Mon Aug 22 08:00:00 IDT 2022 | Sun Feb 19 17:00:00 IST 2023 |  |  | 344.0 | NOT_STARTED
1842 | TT_TASK | LIGHTING AND SMALL POWER INSTALLATION HRSG20 | Wed Feb 01 08:00:00 IST 2023 | Tue Apr 18 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1844 | TT_TASK | COMMISSIONING LIGHTING/SMALL POWER 20UHA AREA | Wed Apr 19 08:00:00 IDT 2023 | Tue Apr 25 17:00:00 IDT 2023 |  |  | 192.0 | NOT_STARTED
1846 | TT_TASK | COMMISSIONING LIGHTING/SMALL POWER IN UBA/UBF/UBE | Tue Apr 11 08:00:00 IDT 2023 | Mon Apr 17 17:00:00 IDT 2023 |  |  | 1320.0 | NOT_STARTED
1848 | TT_TASK | COMMISSIONING LIGHTING/SMALL POWER INSIDE 20UMC | Tue Apr 18 08:00:00 IDT 2023 | Mon Apr 24 17:00:00 IDT 2023 |  |  | 408.0 | NOT_STARTED
1849 | TT_TASK | COMMISSIONING HIGH BAY LIGHTING INSIDE 20UMC | Tue Apr 11 08:00:00 IDT 2023 | Mon Apr 17 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1850 | TT_TASK | COMMISSIONING LIGHTING/SMALL POWER INSIDE 20UMC | Tue Apr 18 08:00:00 IDT 2023 | Mon Apr 24 17:00:00 IDT 2023 |  |  | 464.0 | NOT_STARTED
1851 | TT_TASK | ENERGIZATION FOR LIGHTING AND SMALL POWER 20UMC HIGH BAY (FROM TEMP POWER SUPPLY) | Tue Jun 28 08:00:00 IDT 2022 | Mon Jul 04 17:00:00 IDT 2022 |  |  | 384.0 | NOT_STARTED
1852 | TT_TASK | SYSTEM COMMISSIONING AND ENERGIZATION FOR LIGHTING AND SMALL POWER 20UMC (FR.TEMP POWER SUPPLY) | Tue Apr 04 08:00:00 IDT 2023 | Mon Apr 10 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1854 | TT_TASK | COMMISSIONING LIGHTING/SMALL POWER IN 20URD/URA/UGJ | Thu May 04 08:00:00 IDT 2023 | Wed May 10 17:00:00 IDT 2023 |  |  | 288.0 | NOT_STARTED
1856 | TT_TASK | COMMISSIONING LIGHTING/SMALL POWER IN 01UEN | Thu Dec 22 08:00:00 IST 2022 | Wed Dec 28 17:00:00 IST 2022 |  |  | 944.0 | NOT_STARTED
1857 | TT_TASK | ERECTION CABLE TRAYS 20UMC GT AREA | Thu Sep 29 08:00:00 IDT 2022 | Wed Oct 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1858 | TT_TASK | ERECTION CABLE TRAYS ON 20ULZ01 | Tue Jul 26 08:00:00 IDT 2022 | Mon Aug 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1859 | TT_TASK | ERECTION CABLE TRAYS 20UMC ST AREA | Mon Sep 26 08:00:00 IDT 2022 | Wed Oct 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1860 | TT_TASK | ERECTION CABLE TRAYS ON 20ULY01 | Sun Oct 09 08:00:00 IDT 2022 | Sat Oct 15 17:00:00 IDT 2022 |  |  | 240.0 | NOT_STARTED
1861 | TT_TASK | ERECTION CABLE TRAYS ON 20UBY02 INCL.UBN | Sun Aug 28 08:00:00 IDT 2022 | Thu Sep 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1862 | TT_TASK | ERECTION CABLE TRAYS HRSG20 | Thu Jun 30 08:00:00 IDT 2022 | Wed Jul 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1863 | TT_TASK | ERECTION CABLE TRAYS FOR 20ULA | Sat Aug 13 08:00:00 IDT 2022 | Fri Sep 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1864 | TT_TASK | ERECTION CABLE TRAY FOR LATs GT 20UMC | Thu Oct 13 08:00:00 IDT 2022 | Wed Oct 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1865 | TT_TASK | ERECTION CABLE TRAYS FOR 20URA AREA PART 1 | Fri Feb 24 08:00:00 IST 2023 | Thu Mar 23 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1866 | TT_TASK | ERECTION CABLE TRAYS AIR INTAKE SYSTEM 20MBL | Sun Nov 27 08:00:00 IST 2022 | Sat Dec 10 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1867 | TT_TASK | ERECTION CABLE TRAYS FOR 20URA AREA PART 2 | Thu Mar 30 08:00:00 IDT 2023 | Wed Apr 12 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1868 | TT_TASK | ERECTION CABLE TRAYS BELOW ELECTRICAL MODULES 20UBA76xx/77xx/7410/73xx/7210/7110 | Thu Jun 02 08:00:00 IDT 2022 | Wed Jul 06 17:00:00 IDT 2022 |  |  | 160.0 | NOT_STARTED
1869 | TT_TASK | ERECTION CABLE TRAYS ON 20UQZ | Thu Oct 27 08:00:00 IDT 2022 | Wed Nov 09 17:00:00 IST 2022 |  |  | 656.0 | NOT_STARTED
1870 | TT_TASK | ERECTION CABLE TRAYS BEFORE LIFTING OF MODULE 20UEY02 | Thu Aug 04 08:00:00 IDT 2022 | Wed Aug 17 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1871 | TT_TASK | ERECTION LOOSE STEEL SUPPORTS FOR CABLE TRAYS BEFORE LIFTING OF MODULE 20UEY01 | Sat Jun 11 08:00:00 IDT 2022 | Fri Jun 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1872 | TT_TASK | ERECTION LOOSE STEEL SUPPORTS FOR CABLE TRAYS BEFORE LIFTING OF MODULE 20UEY02 | Thu Jul 21 08:00:00 IDT 2022 | Wed Aug 03 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1873 | TT_TASK | ERECTION CABLE TRAYS ON 20UEY04/05 | Fri Jul 15 08:00:00 IDT 2022 | Sun Jul 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1874 | TT_TASK | ERECTION CABLE TRAYS ON 20UEZ01 | Mon Jul 25 08:00:00 IDT 2022 | Sun Aug 07 17:00:00 IDT 2022 |  |  | 1136.0 | NOT_STARTED
1875 | TT_TASK | ERECTION CABLE TRAYS ON 20ULZ02 | Tue Jul 26 08:00:00 IDT 2022 | Mon Aug 08 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1876 | TT_TASK | ERECTION CABLE TRAYS FOR GENERATOR AREA 20MKA | Mon Sep 05 08:00:00 IDT 2022 | Sun Sep 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1877 | TT_TASK | ERECTION CABLE TRAYS ON 20UBZ04 | Fri Sep 02 08:00:00 IDT 2022 | Thu Sep 15 17:00:00 IDT 2022 |  |  | 288.0 | NOT_STARTED
1878 | TT_TASK | ERECTION CABLE TRAYS 20UMC ST TO LDK | Mon Sep 26 08:00:00 IDT 2022 | Sun Oct 09 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1879 | TT_TASK | ERECTION JUNCTION BOXES & INSTRUMENTATION HRSG20 | Thu Jul 28 08:00:00 IDT 2022 | Wed Sep 14 17:00:00 IDT 2022 |  |  | 384.0 | NOT_STARTED
1880 | TT_TASK | ERECTION JUNCTION BOXES & INSTRUMENTATION IN ULA | Sat Sep 03 08:00:00 IDT 2022 | Fri Sep 30 17:00:00 IDT 2022 |  |  | 256.0 | NOT_STARTED
1881 | TT_TASK | ERECTION CABLE TRAYS ON 20UBZ03 | Wed Aug 24 08:00:00 IDT 2022 | Fri Sep 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1882 | TT_TASK | ERECTION CABLE TRAYS ON 20UEZ02 | Mon Oct 31 08:00:00 IST 2022 | Wed Nov 09 17:00:00 IST 2022 |  |  | 656.0 | NOT_STARTED
1883 | TT_TASK | ERECTION CABLE TRAYS ON 20UEY03 | Tue Jul 05 08:00:00 IDT 2022 | Thu Jul 14 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1884 | TT_TASK | ERECTION STACK CABLE TRAYS FOR EMISSION MONITORING PART 1 (parallel to Pre-assembly stack part 1) | Sun Jun 19 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  | 168.0 | NOT_STARTED
1885 | TT_TASK | ERECTION STACK CABLE TRAYS FOR EMISSION MONITORING PART 2 (parallel to Pre-assembly stack part 2) | Sun Jun 19 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  | 168.0 | NOT_STARTED
1886 | TT_TASK | ERECTION CABLE TRAYS ON 20UBY05 | Thu Nov 10 08:00:00 IST 2022 | Mon Nov 14 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1887 | TT_TASK | ERECTION CABLE TRAYS ON 10UEY01 | Wed Jun 22 08:00:00 IDT 2022 | Tue Jul 19 17:00:00 IDT 2022 |  |  | 280.0 | NOT_STARTED
1888 | TT_TASK | ERECTION CABLE TRAYS 20UMC SOUTH / WEST CORNER | Thu Jun 02 08:00:00 IDT 2022 | Wed Jun 29 17:00:00 IDT 2022 |  |  | 696.0 | NOT_STARTED
1889 | TT_TASK | ADAPTION CABLE TRAYS ON 10UBS04/05 /10UBA | Sat Apr 16 08:00:00 IDT 2022 | Fri May 13 17:00:00 IDT 2022 |  |  | 312.0 | NOT_STARTED
1890 | TT_TASK | ERECTION CABLE TRAYS 20UMY | Thu May 12 08:00:00 IDT 2022 | Wed Jun 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1891 | TT_TASK | ERECTION LOOSE STEEL SUPPORTS FOR CABLE TRAYS BEFORE LIFTING OF MODULE 20UEY01 | Tue Nov 30 08:00:00 IST 2021 | Mon Dec 13 17:00:00 IST 2021 | Tue Nov 30 00:00:00 IST 2021 |  | 1096.0 | IN_PROGRESS
1893 | TT_TASK | ERECTION CABLE TRAYS ON 20UBY03 | Wed Jul 27 08:00:00 IDT 2022 | Tue Aug 02 17:00:00 IDT 2022 |  |  | 680.0 | NOT_STARTED
1894 | TT_TASK | ERECTION CABLE TRAYS ON 20UBZ02 | Fri Jun 10 08:00:00 IDT 2022 | Thu Jun 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1895 | TT_TASK | ERECTION CABLE TRAYS BELOW ELECTRICAL MODULES 01UBA9010/20 | Wed Aug 24 08:00:00 IDT 2022 | Tue Sep 06 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1896 | TT_TASK | ERECTION CABLE TRAYS ON 20UBY04 | Sat Sep 03 08:00:00 IDT 2022 | Fri Sep 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1897 | TT_TASK | ERECTION CABLE TRAYS BELOW ELECTRICAL MODULES 20UBA7920/7910 | Sun Aug 14 08:00:00 IDT 2022 | Sat Aug 20 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1898 | TT_TASK | ERECTION CABLE TRAYS ON 20UQY01 | Thu Oct 27 08:00:00 IDT 2022 | Wed Nov 09 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1899 | TT_TASK | ERECTION CABLE TRAYS BELOW ELECTRICAL MODULES 20UBA1110 | Tue Sep 27 08:00:00 IDT 2022 | Mon Oct 10 17:00:00 IDT 2022 |  |  | 304.0 | NOT_STARTED
1900 | TT_TASK | ERECTION CABLE TRAYS ON 20UQY02 | Mon Aug 15 08:00:00 IDT 2022 | Sun Aug 21 17:00:00 IDT 2022 |  |  | 1296.0 | NOT_STARTED
1901 | TT_TASK | ERECTION CABLE TRAYS ON 20UQY03 | Mon Aug 22 08:00:00 IDT 2022 | Sun Sep 04 17:00:00 IDT 2022 |  |  | 448.0 | NOT_STARTED
1902 | TT_TASK | ERECTION CABLE TRAYS BEFORE LIFTING OF MODULE 20UEY01 | Sat Jun 25 08:00:00 IDT 2022 | Fri Jul 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1903 | TT_TASK | ERECTION CABLE TRAYS FOR 20UBA to UBX/UBE/UBF | Mon Sep 26 08:00:00 IDT 2022 | Sun Oct 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1904 | TT_TASK | ERECTION CABLE TRAYS BELOW ELECTRICAL MODULES 20UBA8110/20 | Sat Aug 13 08:00:00 IDT 2022 | Fri Aug 19 17:00:00 IDT 2022 |  |  | 712.0 | NOT_STARTED
1905 | TT_TASK | ERECTION CABLE TRAYS ON 20UBY01 | Tue Jul 12 08:00:00 IDT 2022 | Mon Jul 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1906 | TT_TASK | ERECTION CABLE TRAYS FOR 20 URD AREA | Thu Aug 11 08:00:00 IDT 2022 | Mon Aug 15 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1908 | TT_TASK | INSTALLATION OF CABLE TRAYS FOR EXTERNAL CONNECTION IN CONTROL BUILDING UCA | Wed Oct 12 08:00:00 IDT 2022 | Tue Nov 01 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1909 | TT_TASK | INSTALLATION OF CABLE TRAYS FOR D2 PLANT TO SUBSTATION BRANCH | Mon Jun 27 08:00:00 IDT 2022 | Sun Jul 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1910 | TT_TASK | INSTALLATION OF CABLE TRAYS C-STATION TO SUBSTATION BRANCH | Mon Jul 18 08:00:00 IDT 2022 | Sun Aug 14 17:00:00 IDT 2022 |  |  | 632.0 | NOT_STARTED
1911 | TT_TASK | INSTALLATION OF CABLE TRAY BRANCH TO SUBSTATION | Mon May 16 08:00:00 IDT 2022 | Sun Jun 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1912 | TT_TASK | INSTALLATION OF CABLE TRAYS INSIDE SUBSTATION | Mon Jun 06 08:00:00 IDT 2022 | Sun Jul 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1913 | TT_TASK | FINALIZE CABLE TRAYS ON 20UEY01 | Sun Aug 07 08:00:00 IDT 2022 | Sat Aug 13 17:00:00 IDT 2022 |  |  | 640.0 | NOT_STARTED
1914 | TT_TASK | FINALIZE CABLE TRAYS ON 20UEY02 | Mon Aug 22 08:00:00 IDT 2022 | Sun Aug 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1915 | TT_TASK | INSTALLATION OF I&C EQUIPMENT & ET200 FOR LATS GT | Thu Oct 20 08:00:00 IDT 2022 | Wed Nov 16 17:00:00 IST 2022 |  |  | 472.0 | NOT_STARTED
1916 | TT_TASK | INSTALLATION OF I&C EQUIPMENT & ET200 FOR LATS ST20 | Thu Oct 06 08:00:00 IDT 2022 | Wed Nov 09 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1917 | TT_TASK | ERECTION I&C-EQUIPMENT 20UMC | Mon Oct 24 08:00:00 IDT 2022 | Sun Dec 04 17:00:00 IST 2022 |  |  | 136.0 | NOT_STARTED
1918 | TT_TASK | ERECTION JUNCTION BOXES / INSTRUMENTATION | Mon Sep 26 08:00:00 IDT 2022 | Sun Nov 06 17:00:00 IST 2022 |  |  | 224.0 | NOT_STARTED
1920 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST FOR EMISSION MONITORING SYSTEM 20CFE | Thu Jun 10 08:00:00 IDT 2021 | Thu Aug 04 17:00:00 IDT 2022 | Thu Jun 10 08:00:00 IDT 2021 |  |  | IN_PROGRESS
1923 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - EMISSION MONITORING SYSTEM 20CFE | Fri Aug 05 08:00:00 IDT 2022 | Thu Sep 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1924 | TT_TASK | TRANSPORT TO SITE EMISSION MONITORING SYSTEM 20CFE | Fri Sep 02 08:00:00 IDT 2022 | Thu Oct 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1926 | TT_TASK | ERECTION CONTINIOUS EMISSION MONITORING SYSTEM HRSG20 | Fri Nov 18 08:00:00 IST 2022 | Thu Dec 01 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1927 | TT_TASK | CABLING CONTINIOUS EMISSION MONITORING/ STACK HRSG20 | Sat Feb 18 08:00:00 IST 2023 | Fri Mar 10 17:00:00 IST 2023 |  |  | 776.0 | NOT_STARTED
1929 | TT_TASK | COMMISSIONING CONTINIOUS EMISSION MONITORING SYSTEM (2) (CALIBRATION) HRSG20 | Tue Jul 11 08:00:00 IDT 2023 | Mon Jul 17 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1930 | TT_TASK | COMMISSIONING CONTINIOUS EMISSION MONITORING SYSTEM (1) HRSG20 | Fri Jun 16 08:00:00 IDT 2023 | Thu Jun 22 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1931 | TT_TASK | COMMISSIONING UNIT PROTECTION 20CHA (GENERATOR) | Fri Jun 09 08:00:00 IDT 2023 | Thu Jun 22 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1932 | TT_TASK | COMMISSIONING ELECTRICAL INTERFACE GRID/PLANT (GT20) | Tue Mar 28 08:00:00 IDT 2023 | Mon Apr 10 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1934 | TT_TASK | COMMISSIONING UNIT PROTECTION FOR BAT/BBT 20CHA/CHY | Tue Mar 14 08:00:00 IST 2023 | Mon Mar 27 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1935 | TT_TASK | COMMISSIONING UNIT PROTECTION FOR BBA | Thu Mar 09 08:00:00 IST 2023 | Wed Mar 22 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1936 | TT_TASK | DETAIL DESIGN /MANUFACTURING / SHOP TEST PROT./ SYNCHR./METERING 20CHA/CHY/CJN | Thu Sep 09 08:00:00 IDT 2021 | Tue Mar 22 17:00:00 IST 2022 | Thu Sep 09 08:00:00 IDT 2021 |  |  | IN_PROGRESS
1937 | TT_TASK | MANUFACTURING / SHOP TEST HRSG PROTECTION CABINET FOR PRECOM TEST-20CJF01 | Thu Sep 09 08:00:00 IDT 2021 | Fri Feb 25 17:00:00 IST 2022 | Thu Sep 09 08:00:00 IDT 2021 | Fri Feb 25 17:00:00 IST 2022 |  | COMPLETED
1938 | TT_TASK | TRANSPORT TO WORKSHOP PROT./ SYNCHR./METERING 20CHA/CHY (TO ST. INGBERT-INSTALL INTO ELECTRICAL MODULES) | Wed Mar 23 08:00:00 IST 2022 | Tue Mar 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1939 | TT_TASK | TRANSPORT TO TESTING FACILITY HRSG PROTECTION CABINET (PRECOMMISSIONING TEST)-20CJF01 | Sat Feb 26 08:00:00 IST 2022 | Thu Mar 03 17:00:00 IST 2022 | Sat Feb 26 08:00:00 IST 2022 |  |  | IN_PROGRESS
1943 | TT_TASK | DETAIL DESIGN HW ENGINEERING HRSG I&C CABINETS FOR ELECTRICAL MODULES's AND OM EQUIP. FOR PRECOMMISSIONING TEST | Mon Apr 26 08:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Mon Apr 26 00:00:00 IDT 2021 | Sun Jul 18 00:00:00 IDT 2021 |  | COMPLETED
1944 | TT_TASK | DETAIL DESIGN HW ENGINEERING BOP I&C CABINETS FOR ELECTRICAL MODULES 20UBA20UBA7310/30 | Mon Apr 26 08:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 | Mon Apr 26 08:00:00 IDT 2021 | Mon Aug 30 17:00:00 IDT 2021 |  | COMPLETED
1945 | TT_TASK | MANUFACTURING I&C CABINETS AND OM EQUIP.-20CPC21 | Tue Aug 31 08:00:00 IDT 2021 | Mon Jan 31 17:00:00 IST 2022 | Tue Aug 31 08:00:00 IDT 2021 | Mon Jan 31 17:00:00 IST 2022 |  | COMPLETED
1946 | TT_TASK | MANUFACTURING BOP AP Server + PLC/CS3000 - Cabinets (Protection)-20CPC41 | Tue Aug 31 08:00:00 IDT 2021 | Wed Feb 16 17:00:00 IST 2022 | Tue Aug 31 08:00:00 IDT 2021 | Wed Feb 16 17:00:00 IST 2022 |  | COMPLETED
1947 | TT_TASK | MANUFACTURING BOP I&C CABINETS FOR ELECTRICAL MODULES 20UBA7310-20CPC01+20CPC11 | Tue Aug 31 08:00:00 IDT 2021 | Thu Nov 11 17:00:00 IST 2021 | Tue Aug 31 08:00:00 IDT 2021 | Thu Nov 11 17:00:00 IST 2021 |  | COMPLETED
1948 | TT_TASK | MANUFACTURING BOP I&C CABINETS FOR ELECTRICAL MODULES 20UBA7320-20CJC01+20CRY02 | Sat Oct 16 08:00:00 IDT 2021 | Tue Jan 04 17:00:00 IST 2022 | Sat Oct 16 08:00:00 IDT 2021 | Tue Jan 04 17:00:00 IST 2022 |  | COMPLETED
1949 | TT_TASK | TRANSPORT TO HEGELE BOP I&C CABINETS FOR ELECTRICAL MODULESÂ´S-20CPC41+20CPC21 | Thu Feb 17 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 | Thu Feb 17 08:00:00 IST 2022 | Tue Feb 22 17:00:00 IST 2022 |  | COMPLETED
1950 | TT_TASK | TRANSPORT TO HEGELE BOP I&C CABINETS FOR ELECTRICAL MODULES 20UBA7310/30-20CPC01+20CPC11 | Fri Nov 12 08:00:00 IST 2021 | Wed Nov 17 17:00:00 IST 2021 | Fri Nov 12 08:00:00 IST 2021 | Wed Nov 17 17:00:00 IST 2021 |  | COMPLETED
1952 | TT_TASK | COMMISSIONING AUTOMATION SYSTEM 20UBA | Tue Feb 21 08:00:00 IST 2023 | Mon Mar 06 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1953 | TT_TASK | BASIC DESIGN /QUOTATION STAGE/ ODERING ELECTRICAL / I&C EQUIPMENT HRSG | Fri Jan 22 08:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 | Fri Jan 22 08:00:00 IST 2021 | Thu Apr 01 17:00:00 IDT 2021 |  | COMPLETED
1955 | TT_TASK | DETAIL DESIGN / MANUFACTURING ELECTRICAL / I&C EQUIPMENT HRSG20 | Fri Apr 02 08:00:00 IDT 2021 | Thu Apr 21 17:00:00 IDT 2022 | Fri Apr 02 08:00:00 IDT 2021 |  |  | IN_PROGRESS
1958 | TT_TASK | TRANSPORT ELECTRICAL / I&C EQUIPMENT HRSG20 | Fri May 20 08:00:00 IDT 2022 | Sat Jun 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1960 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION ELECTRICAL / I&C EQUIPMENT HRSG20 | Fri Apr 22 08:00:00 IDT 2022 | Thu May 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1961 | TT_TASK | COLD COMMISSIONING SFC CUBICLE 20CJT | Thu Mar 30 08:00:00 IDT 2023 | Wed Apr 12 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1962 | TT_TASK | COLD COMMISSIONING SEE CUBICLE 20CJT | Tue Mar 14 08:00:00 IST 2023 | Mon Mar 27 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1964 | TT_TASK | COMMISSIONING ET200 STATIONS GT/WSC 20CP/CJ | Tue Feb 28 08:00:00 IST 2023 | Mon Mar 13 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1965 | TT_TASK | I&C FIELD COMMISSIONING GT20 | Tue Feb 28 08:00:00 IST 2023 | Mon May 01 17:00:00 IDT 2023 |  |  | 296.0 | NOT_STARTED
1967 | TT_TASK | COMMISSIONING ET200 STATIONS ST CJJ | Tue Apr 11 08:00:00 IDT 2023 | Mon Apr 17 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1968 | TT_TASK | I&C FIELD COMMISSIONING ST | Tue Apr 18 08:00:00 IDT 2023 | Mon Jun 19 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1970 | TT_TASK | COMMISSIONING ET200 STATIONS HRSG20 CPC | Tue Apr 11 08:00:00 IDT 2023 | Mon Apr 17 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1971 | TT_TASK | COMMISSIONING ET200 STATIONS CPC | Tue Feb 28 08:00:00 IST 2023 | Mon Mar 13 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1973 | TT_TASK | I&C FIELD COMMISSIONING HRSG20 CPC | Tue Apr 18 08:00:00 IDT 2023 | Mon May 15 17:00:00 IDT 2023 |  |  | 32.0 | NOT_STARTED
1974 | TT_TASK | I&C FIELD COMMISSIONING WSC (1) CPC | Tue Apr 11 08:00:00 IDT 2023 | Mon May 08 17:00:00 IDT 2023 |  |  | 32.0 | NOT_STARTED
1975 | TT_TASK | I&C FIELD COMMISSIONING WSC (2) CPC | Sat Jun 03 08:00:00 IDT 2023 | Fri Jun 23 17:00:00 IDT 2023 |  |  | 56.0 | NOT_STARTED
1977 | TT_TASK | I&C FIELD COMMISSIONING AUX. POWER (90BBA) | Tue Mar 14 08:00:00 IST 2023 | Mon Mar 27 17:00:00 IDT 2023 |  |  | 16.0 | NOT_STARTED
1978 | TT_TASK | COMMISSIONING ET200 STATIONS AUXILIARY/ANCILLIARY CPD (BAT) | Tue Feb 28 08:00:00 IST 2023 | Mon Mar 13 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1979 | TT_TASK | I&C FIELD COMMISSIONING AUX. POWER (BAT) | Tue Mar 14 08:00:00 IST 2023 | Mon Mar 27 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1981 | TT_TASK | COMMISSIONING CONTROL ROOM EQUIPMENT | Tue Feb 21 08:00:00 IST 2023 | Mon Mar 06 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1983 | TT_TASK | ERECTION CCTV SYSTEM CYP IN UMC | Wed Dec 28 08:00:00 IST 2022 | Tue Feb 14 17:00:00 IST 2023 |  |  |  | NOT_STARTED
1984 | TT_TASK | COMMISSIONING TELECOMMUNICATION UCA | Sat May 13 08:00:00 IDT 2023 | Fri Jun 02 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
1986 | TT_TASK | QUOTATION STAGE SIREN SYSTEM CYC | Sat Mar 05 08:00:00 IST 2022 | Sat Apr 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1989 | TT_TASK | BASIC DESIGN / SPECIFICATION / PLANTLAYOUT DWGS BOQ SIREN SYSTEM CYC | Mon Nov 01 08:00:00 IST 2021 | Thu Jan 27 17:00:00 IST 2022 | Mon Nov 01 08:00:00 IST 2021 | Thu Jan 27 17:00:00 IST 2022 |  | COMPLETED
1992 | TT_TASK | MANUFACTURING / SHOP TEST SIREN SYSTEM CYC | Sun May 01 08:00:00 IDT 2022 | Sun Oct 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
1993 | TT_TASK | TRANSPORT SIREN SYSTEM CYC | Wed Nov 02 08:00:00 IST 2022 | Thu Dec 01 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1995 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION SIREN SYSTEM CYC | Mon Oct 03 08:00:00 IDT 2022 | Tue Nov 01 17:00:00 IST 2022 |  |  |  | NOT_STARTED
1996 | TT_TASK | ERECTION SIREN SYSTEM CYC IN UMC | Fri Dec 02 08:00:00 IST 2022 | Thu Jan 19 17:00:00 IST 2023 |  |  | 280.0 | NOT_STARTED
1997 | TT_TASK | ERECTION SIREN SYSTEM IN OTHER BUILDINGS (EXCEPT UMC) | Fri Feb 24 08:00:00 IST 2023 | Thu Apr 20 17:00:00 IDT 2023 |  |  | 288.0 | NOT_STARTED
1998 | TT_TASK | COMMISSIONING SIREN SYSTEM CYC | Sat May 27 08:00:00 IDT 2023 | Fri Jun 16 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2001 | TT_TASK | QUOTATION STAGE ACCESS DOOR CONTROL SYSTEM CYD | Sat Mar 05 08:00:00 IST 2022 | Sat Apr 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2004 | TT_TASK | BASIC DESIGN / SPECIFICATION / PLANTLAYOUT DWGS BOQ ACCESS DOOR CONTROL SYSTEM CYC | Mon Nov 01 08:00:00 IST 2021 | Thu Jan 27 17:00:00 IST 2022 | Mon Nov 01 08:00:00 IST 2021 | Thu Jan 27 17:00:00 IST 2022 |  | COMPLETED
2007 | TT_TASK | MANUFACTURING / SHOP TEST ACCESS DOOR CONTROL SYSTEM CYD | Sun May 01 08:00:00 IDT 2022 | Sun Oct 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2008 | TT_TASK | TRANSPORT ACCESS DOOR CONTROL SYSTEM CYD | Wed Nov 02 08:00:00 IST 2022 | Thu Dec 01 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2010 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION ACCESS DOOR CONTROL SYSTEM CYD | Mon Oct 03 08:00:00 IDT 2022 | Tue Nov 01 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2011 | TT_TASK | ERECTION ACCESS DOOR CONTROL SYSTEM CYD IN UMC | Fri Dec 02 08:00:00 IST 2022 | Thu Jan 19 17:00:00 IST 2023 |  |  | 280.0 | NOT_STARTED
2012 | TT_TASK | ERECTION ACCESS DOOR CONTROL SYSTEM IN OTHER BUILDINGS (EXCEPT UMC) | Fri Feb 24 08:00:00 IST 2023 | Thu Apr 20 17:00:00 IDT 2023 |  |  | 288.0 | NOT_STARTED
2013 | TT_TASK | COMMISSIONING ACCESS DOOR CONTROL SYSTEM CYD | Sat May 27 08:00:00 IDT 2023 | Fri Jun 16 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2018 | TT_TASK | COLD COMMISSIONING GAS DETECTION SYSTEM 20CYQ | Tue May 23 08:00:00 IDT 2023 | Mon May 29 17:00:00 IDT 2023 |  |  | 256.0 | NOT_STARTED
2020 | TT_TASK | QUOTATION STAGE RADIO SYSTEM CYS | Sat Mar 05 08:00:00 IST 2022 | Sat Apr 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2023 | TT_TASK | BASIC DESIGN / SPECIFICATION / PLANTLAYOUT DWGS BOQ RADIO SYSTEM CYS | Mon Nov 01 08:00:00 IST 2021 | Thu Jan 27 17:00:00 IST 2022 | Mon Nov 01 08:00:00 IST 2021 | Thu Jan 27 17:00:00 IST 2022 |  | COMPLETED
2026 | TT_TASK | MANUFACTURING / SHOP TEST RADIO SYSTEM CYS | Sun May 01 08:00:00 IDT 2022 | Sun Oct 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2027 | TT_TASK | TRANSPORT RADIO SYSTEM CYS | Wed Nov 02 08:00:00 IST 2022 | Thu Dec 01 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2029 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION RADIO SYSTEM CYS | Mon Oct 03 08:00:00 IDT 2022 | Tue Nov 01 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2030 | TT_TASK | ERECTION RADIO SYSTEM CYS IN UMC | Fri Dec 02 08:00:00 IST 2022 | Thu Jan 19 17:00:00 IST 2023 |  |  | 280.0 | NOT_STARTED
2031 | TT_TASK | ERECTION RADIO SYSTEM IN OTHER BUILDINGS (EXCEPT UMC) | Fri Feb 24 08:00:00 IST 2023 | Thu Apr 20 17:00:00 IDT 2023 |  |  | 288.0 | NOT_STARTED
2032 | TT_TASK | COMMISSIONING RADIO SYSTEM CYS | Sat May 27 08:00:00 IDT 2023 | Fri Jun 16 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2035 | TT_TASK | QUOTATION STAGE LAN SYSTEM CYX | Sat Mar 05 08:00:00 IST 2022 | Sat Apr 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2038 | TT_TASK | BASIC DESIGN / SPECIFICATION / PLANTLAYOUT DWGS BOQ LAN SYSTEM CYX | Mon Nov 01 08:00:00 IST 2021 | Thu Jan 27 17:00:00 IST 2022 | Mon Nov 01 08:00:00 IST 2021 | Thu Jan 27 17:00:00 IST 2022 |  | COMPLETED
2041 | TT_TASK | MANUFACTURING / SHOP TEST LAN SYSTEM CYX | Sun May 01 08:00:00 IDT 2022 | Sun Oct 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2042 | TT_TASK | TRANSPORT LAN SYSTEM CYX | Wed Nov 02 08:00:00 IST 2022 | Thu Dec 01 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2044 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION LAN SYSTEM CYX | Mon Oct 03 08:00:00 IDT 2022 | Tue Nov 01 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2045 | TT_TASK | ERECTION LAN SYSTEM CYX IN UMC | Fri Dec 02 08:00:00 IST 2022 | Thu Jan 19 17:00:00 IST 2023 |  |  | 280.0 | NOT_STARTED
2046 | TT_TASK | ERECTION LAN SYSTEM IN OTHER BUILDINGS (EXCEPT UMC) | Fri Feb 24 08:00:00 IST 2023 | Thu Apr 20 17:00:00 IDT 2023 |  |  | 288.0 | NOT_STARTED
2047 | TT_TASK | COMMISSIONING LAN SYSTEM CYX | Sat May 27 08:00:00 IDT 2023 | Fri Jun 16 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2060 | TT_TASK | DETAIL DESIGN / MANUFACTURING / SHOP TEST FUEL OIL DAY TANK EGx | Fri Dec 17 08:00:00 IST 2021 | Wed Jun 15 17:00:00 IDT 2022 | Fri Dec 17 08:00:00 IST 2021 |  |  | IN_PROGRESS
2061 | TT_TASK | TRANSPORT FUEL OIL DAY TANK EGx | Thu Jul 14 08:00:00 IDT 2022 | Wed Sep 07 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2063 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION FUEL OIL DAY TANK EGx | Thu Jun 16 08:00:00 IDT 2022 | Wed Jul 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2064 | TT_TASK | ERECTION / PIPING FUEL OIL DAY TANK EGx | Sat Sep 17 08:00:00 IDT 2022 | Fri Oct 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2065 | TT_TASK | DESIGN / MANUFACTURING / PRE ERECTION / SHOP TEST GAS FINAL FILTER/ PREHEATER 20EKG | Mon Jun 28 08:00:00 IDT 2021 | Tue Jul 19 17:00:00 IDT 2022 | Mon Jun 28 08:00:00 IDT 2021 |  |  | IN_PROGRESS
2066 | TT_TASK | DETAIL DESIGN FUEL GAS RECEIVING AND MIXING SYSTEM 01EK | Mon Jun 28 08:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 | Mon Jun 28 08:00:00 IDT 2021 | Thu Aug 12 17:00:00 IDT 2021 |  | COMPLETED
2069 | TT_TASK | MANUFACTURING / SHOP TEST FUEL GAS RECEIVING AND MIXING SYSTEM 01EK | Fri Aug 13 08:00:00 IDT 2021 | Thu May 26 17:00:00 IDT 2022 | Fri Aug 13 08:00:00 IDT 2021 |  |  | IN_PROGRESS
2073 | TT_TASK | TRANSPORT GAS FINAL FILTER/ PREHEATER 20EKG | Sun Nov 06 08:00:00 IST 2022 | Sat Dec 31 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2074 | TT_TASK | TRANSPORT (FROM GERMANY) FUEL GAS RECEIVING AND MIXING SYSTEM 01EK (AUSTRIA) | Sat Jun 25 08:00:00 IDT 2022 | Thu Aug 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2077 | TT_TASK | TRANSPORT CONDENSATE TANK 01EK (AUSTRIA) | Sat Jun 25 08:00:00 IDT 2022 | Thu Aug 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2079 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION FUEL GAS RECEIVING AND MIXING SYSTEM 01EK | Fri May 27 08:00:00 IDT 2022 | Thu Jun 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2080 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CONDENSATE TANK 01EK | Fri May 27 08:00:00 IDT 2022 | Thu Jun 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2081 | TT_TASK | ERECTION GAS FINAL FILTER/ PREHEATER 20EKG | Sun Jan 01 08:00:00 IST 2023 | Sat Feb 11 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2082 | TT_TASK | MECHANICAL ERECTION FUEL GAS RECEIVING AND MIXING SYSTEM 01EK | Thu Aug 25 08:00:00 IDT 2022 | Wed Oct 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2083 | TT_TASK | MECHANICAL ERECTION CONDENSATE TANK 01EK | Fri Aug 19 08:00:00 IDT 2022 | Thu Aug 25 17:00:00 IDT 2022 |  |  | 2104.0 | NOT_STARTED
2086 | TT_TASK | TEMPORARY PLACEMENT OF CRANE ON 20UEN FOR INSTALLATION WORKS ON 20UEN | Fri Mar 18 08:00:00 IST 2022 | Sat Nov 26 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2087 | TT_TASK | ELECTRICAL ERECTION FUEL GAS COMPONENTS 20EK- | Thu Oct 20 08:00:00 IDT 2022 | Wed Nov 23 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2088 | TT_TASK | E- AND I&C-ERECTION 20UEN | Sun Feb 12 08:00:00 IST 2023 | Sat Feb 25 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2090 | TT_TASK | ELECTRICAL ERECTION / VALVES 20EKG | Fri Mar 17 08:00:00 IST 2023 | Thu Mar 30 17:00:00 IDT 2023 |  |  | 352.0 | NOT_STARTED
2091 | TT_TASK | ELECTRICAL ERECTION / VALVES 20EKG70 | Sun Feb 26 08:00:00 IST 2023 | Sat Mar 11 17:00:00 IST 2023 |  |  | 152.0 | NOT_STARTED
2093 | TT_TASK | COLD COMMISSIONING FUEL GAS COMPONENTS FOR GT20 | Tue May 23 08:00:00 IDT 2023 | Mon Jun 19 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2094 | TT_TASK | FORWARDING NATURAL GAS TO GT20 | Tue Jun 20 08:00:00 IDT 2023 | Sat Jun 24 17:00:00 IDT 2023 |  |  | 8.0 | NOT_STARTED
2096 | TT_TASK | COLD COMMISSIONING FUEL GAS METERING SYSTEM FOR GT20 | Tue May 23 08:00:00 IDT 2023 | Mon Jun 19 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2099 | TT_TASK | ERECTION, NDT, PT (PT & PIGGING) PIPES / VALVES 20EKG70 (20UEN - GT FUEL GAS PURGE SKID) | Sun Jan 08 08:00:00 IST 2023 | Sat Feb 11 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2100 | TT_TASK | ERECTION, NDT, PT (PT & PIGGING) PIPES / VALVES 00EKG (TP-M1A/B - 00UEN03/04) | Fri Aug 19 08:00:00 IDT 2022 | Wed Nov 16 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2101 | TT_TASK | ERECTION, NDT, PT (PT & PIGGING) PIPES / VALVES 20EKG (00UEN03/04 - 20UEN VIA UEYxx) | Thu Sep 29 08:00:00 IDT 2022 | Sat Feb 25 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2102 | TT_TASK | ERECTION, NDT, PT PIPES - 20EKG | Thu Jan 05 08:00:00 IST 2023 | Thu Mar 23 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2103 | TT_TASK | INSULATION PIPES 20EKG | Sun Feb 12 08:00:00 IST 2023 | Sat Mar 04 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2104 | TT_TASK | ERECTION, NDT, PT PIPES - CONDENSER PREHEATING PIPE 20EKT | Tue Jan 10 08:00:00 IST 2023 | Mon Feb 13 17:00:00 IST 2023 |  |  | 40.0 | NOT_STARTED
2106 | TT_TASK | ERECTION, NDT, PT / VALVES / PT DEMIN WATER 20GHC | Tue Oct 04 08:00:00 IDT 2022 | Mon Dec 05 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2107 | TT_TASK | ERECTION, NDT, PT / VALVES DEMIN WATER GHC COMMON HEADER | Mon Aug 29 08:00:00 IDT 2022 | Sun Sep 25 17:00:00 IDT 2022 |  |  | 64.0 | NOT_STARTED
2108 | TT_TASK | ELECTRICAL ERECTION / VALVES DEMIN WATER 20GHC | Tue Nov 15 08:00:00 IST 2022 | Mon Dec 05 17:00:00 IST 2022 |  |  | 920.0 | NOT_STARTED
2109 | TT_TASK | ERECTION, NDT, PT / VALVES DEMIN WATER 20GHC IN UHY (UNDER HRSG INLET DUCT) | Tue Nov 15 08:00:00 IST 2022 | Mon Nov 28 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2110 | TT_TASK | COMMISSIONING PIPES / VALVES DEMIN WATER 00GHC | Fri Apr 07 08:00:00 IDT 2023 | Fri Apr 21 17:00:00 IDT 2023 |  |  | 168.0 | NOT_STARTED
2112 | TT_TASK | PRE-ERECTION / PT PIPES GHD FOR UGD TO UMC | Tue Jul 05 08:00:00 IDT 2022 | Mon Jul 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2113 | TT_TASK | ERECTION / PT PIPES GHD FOR UGD IN UMC | Tue Jul 26 08:00:00 IDT 2022 | Mon Sep 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2114 | TT_TASK | ELECTRICAL ERECTION PIPES GHD FOR UGD IN UMC | Tue Jan 03 08:00:00 IST 2023 | Mon Jan 09 17:00:00 IST 2023 |  |  | 824.0 | NOT_STARTED
2116 | TT_TASK | COLD COMMISSIONING SERVICE WATER DISTRIBUTION SYSTEM GHD | Tue Apr 25 08:00:00 IDT 2023 | Sat Apr 29 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2117 | TT_TASK | FINAL COLD COMMISSIONING SERVICE WATER DISTRIBUTION SYSTEM GHD | Sun Apr 30 08:00:00 IDT 2023 | Thu May 04 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2119 | TT_TASK | ERECTION / PT IN UMC 20GKB-PIPES | Wed Jan 18 08:00:00 IST 2023 | Tue Feb 21 17:00:00 IST 2023 |  |  | 16.0 | NOT_STARTED
2120 | TT_TASK | ERECTION / PT PIPES 00GKB FOR UGD TO UMC | Mon Nov 21 08:00:00 IST 2022 | Sun Jan 22 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2122 | TT_TASK | COLD COMMISSIONING DRINKING WATER DISTRIBUTION SYSTEM GKB | Sat Apr 29 08:00:00 IDT 2023 | Fri May 05 17:00:00 IDT 2023 |  |  | 456.0 | NOT_STARTED
2123 | TT_TASK | M-ERECTION SUMP PUMPS GM FOR UBF | Tue Jul 19 08:00:00 IDT 2022 | Mon Aug 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2125 | TT_TASK | M-ERECTION SUMP PUMPS/OIL SEPARATOR GM FOR 20UBH01 | Thu Jul 21 08:00:00 IDT 2022 | Wed Aug 03 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2127 | TT_TASK | ERECTION PIPES DRAINAGE SYSTEM 20GM BOILER/STEAM TURBINE | Mon Aug 22 08:00:00 IDT 2022 | Sun Oct 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2128 | TT_TASK | ERECTION PIPES DRAINAGE SYSTEM 00GM FROM WATER TRETAMENT TO UBH02 | Thu Jul 28 08:00:00 IDT 2022 | Wed Sep 07 17:00:00 IDT 2022 |  |  | 1752.0 | NOT_STARTED
2129 | TT_TASK | ERECTION PIPES DRAINAGE SYSTEM 00GM FROM GAS TURBINE TO UBH01 | Mon Oct 24 08:00:00 IDT 2022 | Sun Dec 04 17:00:00 IST 2022 |  |  | 1048.0 | NOT_STARTED
2130 | TT_TASK | ERECTION PIPES DRAINAGE SYSTEM 00GM FROM STEAM TURBINE / HRSG TO UBH02 | Sat Aug 13 08:00:00 IDT 2022 | Fri Sep 23 17:00:00 IDT 2022 |  |  | 1624.0 | NOT_STARTED
2131 | TT_TASK | ERECTION PIPES STORM SYSTEM 00GM | Thu Jul 28 08:00:00 IDT 2022 | Wed Sep 07 17:00:00 IDT 2022 |  |  | 1752.0 | NOT_STARTED
2132 | TT_TASK | ELECTRICAL ERECTION SUMP PUMPS/OIL SEPARATOR GM FOR 20UBH01 | Thu Aug 04 08:00:00 IDT 2022 | Wed Aug 10 17:00:00 IDT 2022 |  |  | 256.0 | NOT_STARTED
2133 | TT_TASK | ELECTRICAL ERECTION SUMP PUMPS GM FOR UBF | Tue Aug 02 08:00:00 IDT 2022 | Mon Aug 08 17:00:00 IDT 2022 |  |  | 272.0 | NOT_STARTED
2135 | TT_TASK | COLD COMMISSIONING PLANT DRAINAGE SYSTEM GM FOR UBF | Tue Feb 14 08:00:00 IST 2023 | Mon Feb 20 17:00:00 IST 2023 |  |  | 72.0 | NOT_STARTED
2136 | TT_TASK | COLD COMMISSIONING PLANT DRAINAGE SYSTEM FOR 20ULA GM | Thu Mar 30 08:00:00 IDT 2023 | Wed Apr 05 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2138 | TT_TASK | COLD COMMISSIONING PLANT DRAINAGE SYSTEM GM | Sat Apr 22 08:00:00 IDT 2023 | Fri Apr 28 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2156 | TT_TASK | DETAIL DESIGN / MANUFACTURING HEATING SURFACES HRSG20 MODULE 1,2,3,4,5,6 | Thu Jan 28 08:00:00 IST 2021 | Tue Mar 01 17:00:00 IST 2022 | Thu Jan 28 08:00:00 IST 2021 |  |  | IN_PROGRESS
2158 | TT_TASK | DETAIL DESIGN DRUMS HRSG20 | Thu Jan 28 08:00:00 IST 2021 | Sat Feb 27 17:00:00 IST 2021 | Thu Jan 28 08:00:00 IST 2021 | Sat Feb 27 17:00:00 IST 2021 |  | COMPLETED
2159 | TT_TASK | MANUFACTURING DRUMS HRSG20 | Sun Feb 28 08:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 | Sun Feb 28 08:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 |  | COMPLETED
2160 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST HRSG REMAINING MATERIAL | Thu May 27 08:00:00 IDT 2021 | Wed Mar 02 17:00:00 IST 2022 | Thu May 27 08:00:00 IDT 2021 |  |  | IN_PROGRESS
2162 | TT_TASK | DETAIL DESIGN, MANUFACTURING INSULATION MATERIAL HRSG20 (OUTLET DUCT & SEALING AREAS STACK) | Tue Oct 26 08:00:00 IDT 2021 | Mon Jan 31 17:00:00 IST 2022 | Tue Oct 26 08:00:00 IDT 2021 | Mon Jan 31 17:00:00 IST 2022 |  | COMPLETED
2163 | TT_TASK | DETAIL DESIGN, MANUFACTURING INSULATION MATERIAL HRSG20 (PIPES, DRUMS, VESSELS) | Sat Aug 20 08:00:00 IDT 2022 | Fri Nov 25 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2164 | TT_TASK | MANUFACTURING VALVES > 2 HRSG20 | Thu Jan 28 08:00:00 IST 2021 | Wed Jan 19 17:00:00 IST 2022 | Thu Jan 28 08:00:00 IST 2021 | Wed Jan 19 17:00:00 IST 2022 |  | COMPLETED
2167 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION HEATING SURFACES HRSG20 MODULE 2-6 | Wed Feb 09 08:00:00 IST 2022 | Thu Mar 03 17:00:00 IST 2022 | Wed Feb 09 08:00:00 IST 2022 |  |  | IN_PROGRESS
2168 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION DRUMS HRSG20 | Tue Jan 11 08:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 | Tue Jan 11 08:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 |  | COMPLETED
2169 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION PIPING HRSG20_1st Part (LB CARBON STEEL) | Thu Feb 10 08:00:00 IST 2022 | Wed Mar 09 17:00:00 IST 2022 | Thu Feb 10 08:00:00 IST 2022 |  |  | IN_PROGRESS
2170 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION PIPING HRSG20_Last Part (SB | Thu Apr 07 08:00:00 IDT 2022 | Wed May 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2171 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION PIPING HRSG20_2nd Part (LB HIGH ALLOY STEEL) | Fri Mar 04 08:00:00 IST 2022 | Thu Mar 31 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2172 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION VALVES > 2 HRSG20 | Thu Jan 20 08:00:00 IST 2022 | Wed Feb 16 17:00:00 IST 2022 | Thu Jan 20 08:00:00 IST 2022 | Wed Feb 16 17:00:00 IST 2022 |  | COMPLETED
2173 | TT_TASK | TRANSPORT PIPING HRSG20_1st Part (LB CARBON STEEL) | Mon Mar 21 08:00:00 IST 2022 | Tue Apr 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2174 | TT_TASK | TRANSPORT PIPING HRSG20_Last Part (SB | Thu May 05 08:00:00 IDT 2022 | Fri Jun 03 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2175 | TT_TASK | TRANSPORT PIPING HRSG20_2nd Part (LB HIGH ALLOY STEEL) | Fri Apr 01 08:00:00 IDT 2022 | Sat Apr 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2179 | TT_TASK | TRANSPORT INSULATION MATERIAL HRSG20 (PIPES, DRUMS, VESSELS) | Sat Jan 14 08:00:00 IST 2023 | Fri Feb 17 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2181 | TT_TASK | TRANSPORT INSULATION MATERIAL HRSG20 (OUTLET DUCT & SEALING AREAS STACK) | Fri May 13 08:00:00 IDT 2022 | Thu Jun 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2183 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION HEATING SURFACES HRSG20 MODULE 1 | Wed Mar 02 08:00:00 IST 2022 | Sun Mar 20 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2184 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION PIPING HRSG20 INTERNAL PIPING | Thu Feb 10 08:00:00 IST 2022 | Wed Mar 09 17:00:00 IST 2022 | Thu Feb 10 08:00:00 IST 2022 |  |  | IN_PROGRESS
2185 | TT_TASK | TRANSPORT PIPING HRSG20_INTERNAL PIPING | Mon Mar 21 08:00:00 IST 2022 | Sat Apr 09 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2187 | TT_TASK | TRANSPORT VALVES > 2 HRSG20 | Mon Mar 21 08:00:00 IST 2022 | Sat Apr 09 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2190 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - HRSG REMAINING MATERIAL | Thu Mar 03 08:00:00 IST 2022 | Wed Mar 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2192 | TT_TASK | TRANSPORT DRUMS HRSG20 | Mon Mar 21 08:00:00 IST 2022 | Wed Mar 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2194 | TT_TASK | TRANSPORT HRSG REMAINING MATERIAL | Thu Mar 31 08:00:00 IDT 2022 | Fri Apr 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2197 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - INSULATION MATERIAL HRSG20 (OUTLET DUCT & SEALING AREAS STACK) | Fri Apr 15 08:00:00 IDT 2022 | Thu May 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2199 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - INSULATION MATERIAL HRSG20 (PIPES, DRUMS, VESSELS) | Sat Nov 26 08:00:00 IST 2022 | Fri Dec 23 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2200 | TT_TASK | TRANSPORT HEATING SURFACES HRSG20 MODULE 2-6 | Mon Mar 21 08:00:00 IST 2022 | Wed Mar 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2207 | TT_TASK | TRANSPORT HEATING SURFACES HRSG20 MODULE1 | Mon Mar 21 08:00:00 IST 2022 | Wed Mar 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2211 | TT_TASK | PREPARATION PRESSURE TEST HRSG20 | Tue Mar 07 08:00:00 IST 2023 | Mon Apr 03 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2212 | TT_TASK | ERECTION INTERNAL BAFFLE HRSG20 | Mon Jun 20 08:00:00 IDT 2022 | Sun Aug 21 17:00:00 IDT 2022 |  |  | 1616.0 | NOT_STARTED
2216 | TT_TASK | PRESSURE TEST HRSG20 | Sun Mar 12 08:00:00 IST 2023 | Fri Apr 14 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2220 | TT_TASK | INSULATION HRSG / PIPES HRSG20 FOR CHEMICAL CLEANING | Tue Mar 28 08:00:00 IDT 2023 | Mon Apr 24 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2222 | TT_TASK | INSULATION HRSG / PIPES HRSG20 AFTER CHEMICAL CLEANING | Sat Jun 03 08:00:00 IDT 2023 | Fri Jun 30 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2223 | TT_TASK | ERECTION AND LIFTING MODULE (INCLUDING ALIGNMENT) HRSG20 | Tue May 24 08:00:00 IDT 2022 | Thu Jun 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2225 | TT_TASK | Tilting Frame assemble | Sat May 21 08:00:00 IDT 2022 | Mon May 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2226 | TT_TASK | Erection of Module #3 | Tue May 24 08:00:00 IDT 2022 | Thu May 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2227 | TT_TASK | Erection of Module #4 | Fri May 27 08:00:00 IDT 2022 | Sun May 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2228 | TT_TASK | Erection of Module #5 | Mon May 30 08:00:00 IDT 2022 | Wed Jun 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2229 | TT_TASK | Erection of Module #6 | Thu Jun 02 08:00:00 IDT 2022 | Sat Jun 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2230 | TT_TASK | Erection of Module #2 | Sun Jun 05 08:00:00 IDT 2022 | Tue Jun 07 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2231 | TT_TASK | Install and welding the Bumper support at M2 | Wed Jun 08 08:00:00 IDT 2022 | Fri Jun 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2232 | TT_TASK | Erection of module #1 | Sat Jun 11 08:00:00 IDT 2022 | Mon Jun 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2233 | TT_TASK | Install and welding the Bumper support at M1 | Tue Jun 14 08:00:00 IDT 2022 | Thu Jun 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2234 | TT_TASK | PREPARATIONS FOR MODULE LOADING HRSG20 | Fri May 13 08:00:00 IDT 2022 | Thu May 19 17:00:00 IDT 2022 |  |  | 8.0 | NOT_STARTED
2237 | TT_TASK | ERECTION HP VESSEL / IP AND LP DRUM | Mon Jun 27 08:00:00 IDT 2022 | Sun Jul 03 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2238 | TT_TASK | Installation of drum support (Additional crane at south of HRSG) | Thu Jun 16 08:00:00 IDT 2022 | Sun Jun 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2239 | TT_TASK | Erect scaffolding working platform for drums installation | Thu Jun 16 08:00:00 IDT 2022 | Sun Jun 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2240 | TT_TASK | Installation of HP steam drum | Mon Jun 27 08:00:00 IDT 2022 | Tue Jun 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2241 | TT_TASK | Installation of IP steam drum | Wed Jun 29 08:00:00 IDT 2022 | Thu Jun 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2242 | TT_TASK | Installation of LP steam drum | Fri Jul 01 08:00:00 IDT 2022 | Sat Jul 02 17:00:00 IDT 2022 |  |  | 8.0 | NOT_STARTED
2243 | TT_TASK | ALIGNMENT HP VESSEL / IP AND LP DRUM | Mon Jun 27 08:00:00 IDT 2022 | Sun Jul 03 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2244 | TT_TASK | COLD COMMISSIONING DISTRIBUTION PANEL HRSG 20HA | Tue Apr 18 08:00:00 IDT 2023 | Mon Apr 24 17:00:00 IDT 2023 |  |  | 384.0 | NOT_STARTED
2246 | TT_TASK | FINAL COLD COMMISSIONING HRSG 20HAD/LBH | Mon Jun 12 08:00:00 IDT 2023 | Sun Jun 18 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2247 | TT_TASK | HRSG PROTECTION TESTS 20HA | Thu Jun 22 08:00:00 IDT 2023 | Fri Jun 23 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2248 | TT_TASK | STEAM BLOW (ABO) HRSG / WD 20 | Mon Jul 03 08:00:00 IDT 2023 | Sun Jul 09 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2251 | TT_TASK | COLD COMMISSIONING HRSG CONDENSATE RH SYS (FOR CHEM. CLEANING) 20HAA | Sat Apr 29 08:00:00 IDT 2023 | Fri May 12 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2253 | TT_TASK | COLD COMMISSIONING HRSG HP SYSTEM (FOR CHEMICAL CLEANING) 20HAD10 | Sat Apr 29 08:00:00 IDT 2023 | Fri May 12 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2255 | TT_TASK | COLD COMMISSIONING HRSG IP STEAM (FOR CHEM. CLEANING) 20HAD50 | Sat Apr 29 08:00:00 IDT 2023 | Fri May 12 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2257 | TT_TASK | COLD COMMISSIONING HRSG LP STEAM (FOR CHEM. CLEANING) 20HAD80 | Sat Apr 29 08:00:00 IDT 2023 | Fri May 12 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2258 | TT_TASK | MANUFACTURING MAIN STEEL STRUCTURE HRSG20 | Wed Apr 14 08:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 | Wed Apr 14 08:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 |  | COMPLETED
2261 | TT_TASK | MANUFACTURING CASING HRSG20 | Wed Apr 14 08:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 | Wed Apr 14 08:00:00 IDT 2021 | Wed Nov 10 17:00:00 IST 2021 |  | COMPLETED
2270 | TT_TASK | MANUFACTURING SECONDARY STEEL STRUCTURE HRSG20_1st Part | Sun Jun 06 08:00:00 IDT 2021 | Thu Dec 30 17:00:00 IST 2021 | Sun Jun 06 08:00:00 IDT 2021 | Thu Dec 30 17:00:00 IST 2021 |  | COMPLETED
2272 | TT_TASK | MANUFACTURING SECONDARY STEEL STRUCTURE HRSG20_Last Part | Fri Jul 16 08:00:00 IDT 2021 | Mon Jan 31 17:00:00 IST 2022 | Fri Jul 16 08:00:00 IDT 2021 | Mon Jan 31 17:00:00 IST 2022 |  | COMPLETED
2273 | TT_TASK | DETAIL DESIGN STACK HRSG 20 | Thu Jan 28 08:00:00 IST 2021 | Sat Apr 10 17:00:00 IDT 2021 | Thu Jan 28 08:00:00 IST 2021 | Sat Apr 10 17:00:00 IDT 2021 |  | COMPLETED
2274 | TT_TASK | MANUFACTURING STACK HRSG 20 | Sun Apr 11 08:00:00 IDT 2021 | Mon Jan 10 17:00:00 IST 2022 | Sun Apr 11 08:00:00 IDT 2021 | Mon Jan 10 17:00:00 IST 2022 |  | COMPLETED
2276 | TT_TASK | DETAIL DESIGN INLET DUCT HRSG20 | Sat Jan 30 08:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 | Sat Jan 30 08:00:00 IST 2021 | Fri Mar 12 17:00:00 IST 2021 |  | COMPLETED
2277 | TT_TASK | MANUFACTURING INLET DUCT HRSG20 | Wed May 12 08:00:00 IDT 2021 | Sun Dec 05 17:00:00 IST 2021 | Wed May 12 08:00:00 IDT 2021 | Sun Dec 05 17:00:00 IST 2021 |  | COMPLETED
2279 | TT_TASK | DETAIL DESIGN OUTLET DUCT HRSG 20 | Thu Jan 28 08:00:00 IST 2021 | Sat Feb 27 17:00:00 IST 2021 | Thu Jan 28 08:00:00 IST 2021 | Sat Feb 27 17:00:00 IST 2021 |  | COMPLETED
2280 | TT_TASK | MANUFACTURING OUTLET DUCT HRSG 20 | Sun Feb 28 08:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 | Sun Feb 28 08:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 |  | COMPLETED
2282 | TT_TASK | TRANSPORT MAIN STEEL STRUCTURE HRSG20 (MAIN FRAME / CASING) | Thu Dec 30 08:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 | Thu Dec 30 08:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 |  | COMPLETED
2288 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MAIN STEEL STRUCTURE HRSG20 | Thu Nov 11 08:00:00 IST 2021 | Wed Dec 29 17:00:00 IST 2021 | Thu Nov 11 08:00:00 IST 2021 | Wed Dec 29 17:00:00 IST 2021 |  | COMPLETED
2289 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION SECONDARY STEEL STRUCTURE HRSG20_1st Part incl. Drum Supports | Fri Dec 31 08:00:00 IST 2021 | Thu Jan 27 17:00:00 IST 2022 | Fri Dec 31 08:00:00 IST 2021 | Thu Jan 27 17:00:00 IST 2022 |  | COMPLETED
2290 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION SECONDARY STEEL STRUCTURE HRSG20_Last Part | Tue Feb 01 08:00:00 IST 2022 | Mon Feb 28 17:00:00 IST 2022 | Tue Feb 01 08:00:00 IST 2022 |  |  | IN_PROGRESS
2291 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION OUTLET DUCT HRSG 20 | Tue Jan 11 08:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 | Tue Jan 11 08:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 |  | COMPLETED
2292 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION STACK HRSG 20 | Tue Jan 11 08:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 | Tue Jan 11 08:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 |  | COMPLETED
2293 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION INLET DUCT HRSG20 | Mon Dec 06 08:00:00 IST 2021 | Sun Jan 02 17:00:00 IST 2022 | Mon Dec 06 08:00:00 IST 2021 | Sun Jan 02 17:00:00 IST 2022 |  | COMPLETED
2294 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CASING HRSG20 | Thu Nov 11 08:00:00 IST 2021 | Wed Dec 29 17:00:00 IST 2021 | Thu Nov 11 08:00:00 IST 2021 | Wed Dec 29 17:00:00 IST 2021 |  | COMPLETED
2295 | TT_TASK | TRANSPORT SECONDARY STEEL STRUCTURE HRSG20_1st Part incl. Drum Supports | Thu Feb 17 08:00:00 IST 2022 | Tue Mar 08 17:00:00 IST 2022 | Thu Feb 17 08:00:00 IST 2022 |  |  | IN_PROGRESS
2297 | TT_TASK | TRANSPORT SECONDARY STEEL STRUCTURE HRSG20_Last Part | Sat Mar 05 08:00:00 IST 2022 | Tue Mar 15 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2299 | TT_TASK | TRANSPORT STACK HRSG 20 | Mon Mar 21 08:00:00 IST 2022 | Sat Apr 09 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2301 | TT_TASK | TRANSPORT INLET DUCT HRSG20 | Thu Feb 17 08:00:00 IST 2022 | Tue Mar 08 17:00:00 IST 2022 | Thu Feb 17 08:00:00 IST 2022 |  |  | IN_PROGRESS
2303 | TT_TASK | TRANSPORT OUTLET DUCT HRSG 20 | Sat Mar 05 08:00:00 IST 2022 | Tue Mar 15 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2305 | TT_TASK | GROUTING MAIN STEEL incl. CURING HRSG20 | Sat May 14 08:00:00 IDT 2022 | Fri May 20 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2306 | TT_TASK | INSTALL PIPING HRSG20_Internal Large Bore | Sun Jun 05 08:00:00 IDT 2022 | Sat Aug 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2307 | TT_TASK | INSTALL PIPING HRSG20_External Large Bore - HRSG TP FOR PIPING AVAILABLE | Fri Jul 15 08:00:00 IDT 2022 | Wed Oct 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2308 | TT_TASK | PRE-ASSEMBLY PIPING HRSG20_Small Bore | Fri Jun 17 08:00:00 IDT 2022 | Thu Sep 08 17:00:00 IDT 2022 |  |  | 248.0 | NOT_STARTED
2309 | TT_TASK | STEEL ALIGNMENT AND BOLT TIGHTENING HRSG20 | Fri Apr 08 08:00:00 IDT 2022 | Wed Apr 20 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2310 | TT_TASK | Adjust alignment of main frame and panels | Tue Apr 05 08:00:00 IDT 2022 | Sat Apr 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2311 | TT_TASK | Bolt tightening of main frame | Tue Apr 05 08:00:00 IDT 2022 | Sat Apr 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2312 | TT_TASK | Grouting the casing columns (by others, ensure grouting should be completed in 4 days) | Tue Apr 19 08:00:00 IDT 2022 | Fri Apr 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2313 | TT_TASK | Install the internal gondola | Fri Apr 08 08:00:00 IDT 2022 | Tue Apr 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2314 | TT_TASK | MAIN CASING ERECTION & WELDING HRSG20 | Thu Apr 07 08:00:00 IDT 2022 | Thu May 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2315 | TT_TASK | External South Side seal welding work from M1 to M2 (Nightshift) | Fri Apr 08 08:00:00 IDT 2022 | Wed Apr 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2316 | TT_TASK | External North Side seal welding work from M1 to M2 (Nightshift) | Fri Apr 08 08:00:00 IDT 2022 | Wed Apr 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2317 | TT_TASK | External South Side seal welding work from M3 to M4 (Nightshift) | Fri Apr 08 08:00:00 IDT 2022 | Wed Apr 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2318 | TT_TASK | External North Side seal welding work from M3 to M4 (Nightshift) | Fri Apr 08 08:00:00 IDT 2022 | Wed Apr 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2319 | TT_TASK | NDT for External sides seal weld joint from M1 to M4 | Thu Apr 14 08:00:00 IDT 2022 | Tue Apr 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2320 | TT_TASK | External South Side seal welding work from M5 to M6 (Nightshift) | Thu Apr 14 08:00:00 IDT 2022 | Tue Apr 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2321 | TT_TASK | External North Side seal welding work from M5 to M6 (Nightshift) | Thu Apr 14 08:00:00 IDT 2022 | Tue Apr 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2322 | TT_TASK | External South Side seal welding work from M7 to M8 (Nightshift) | Thu Apr 14 08:00:00 IDT 2022 | Tue Apr 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2323 | TT_TASK | External North Side seal welding work from M7 to M8 (Nightshift) | Thu Apr 14 08:00:00 IDT 2022 | Tue Apr 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2324 | TT_TASK | NDT for External sides seal weld joint from M5 to M8 | Wed Apr 20 08:00:00 IDT 2022 | Fri Apr 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2325 | TT_TASK | Internal South side seal welding work from M1 to M4 | Wed Apr 20 08:00:00 IDT 2022 | Fri Apr 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2326 | TT_TASK | Internal North side seal welding work from M1 to M4 | Wed Apr 20 08:00:00 IDT 2022 | Fri Apr 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2327 | TT_TASK | NDT for Internal sides seal weld joint from M1 to M4 | Sat Apr 23 08:00:00 IDT 2022 | Mon Apr 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2328 | TT_TASK | Insulation and Liner plate installation at both sides from M1 to M4 (Nightshift) | Sat Apr 23 08:00:00 IDT 2022 | Thu Apr 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2329 | TT_TASK | Internal South side seal welding work from M5 to M8 | Sat Apr 23 08:00:00 IDT 2022 | Mon Apr 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2330 | TT_TASK | Internal North side seal welding work from M5 to M8 | Sat Apr 23 08:00:00 IDT 2022 | Mon Apr 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2331 | TT_TASK | NDT for Internal sides seal weld joint from M5 to M8 | Tue Apr 26 08:00:00 IDT 2022 | Thu Apr 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2332 | TT_TASK | Insulation and Liner plate installation at both sides from M5 to M8 (Nightshift) | Fri Apr 29 08:00:00 IDT 2022 | Wed May 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2333 | TT_TASK | External Bottom Panels seal welding work from M1 to M8 (Nightshift) | Sat Apr 23 08:00:00 IDT 2022 | Thu Apr 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2334 | TT_TASK | NDT for External Bottom Panels seal weld joint from M1 to M8 | Fri Apr 29 08:00:00 IDT 2022 | Sun May 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2335 | TT_TASK | Internal Bottom Panels seal welding work from M1 to M8 | Tue Apr 26 08:00:00 IDT 2022 | Sun May 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2336 | TT_TASK | NDT for Internal Bottom Panels seal weld joint from M1 to M8 | Mon May 02 08:00:00 IDT 2022 | Wed May 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2337 | TT_TASK | Insulation and Liner plates installaiton for Bottom panels from M1 to M8 (Dayshift and Nightshift) | Mon May 02 08:00:00 IDT 2022 | Fri May 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2338 | TT_TASK | Dismantle the gondola | Mon May 02 08:00:00 IDT 2022 | Fri May 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2339 | TT_TASK | Installation of stair tower (South) + Access platform | Wed Apr 20 08:00:00 IDT 2022 | Fri May 13 17:00:00 IDT 2022 |  |  | 56.0 | NOT_STARTED
2340 | TT_TASK | INSTALL PIPING HRSG20_Small Bore | Mon Aug 29 08:00:00 IDT 2022 | Tue Mar 21 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2341 | TT_TASK | ERECTION OUTLET DUCT HRSG20 | Mon Sep 05 08:00:00 IDT 2022 | Sun Sep 18 17:00:00 IDT 2022 |  |  | 584.0 | NOT_STARTED
2342 | TT_TASK | Erect scaffolding for outlet duct & expansion joint installation | Mon Sep 05 08:00:00 IDT 2022 | Thu Sep 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2343 | TT_TASK | Installation of outlet duct panel | Fri Sep 23 08:00:00 IDT 2022 | Tue Oct 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2344 | TT_TASK | Installation of outlet duct expansion joint | Wed Oct 05 08:00:00 IDT 2022 | Sun Oct 16 17:00:00 IDT 2022 |  |  | 360.0 | NOT_STARTED
2345 | TT_TASK | REMAINING EXTERNAL INSULATION FOR OUTLET DUCT HRSG20 | Thu Dec 01 08:00:00 IST 2022 | Wed Jan 11 17:00:00 IST 2023 |  |  | 768.0 | NOT_STARTED
2346 | TT_TASK | PRE-ASSEMBLY STACK INCL. INSULATION / SEC. STEEL HRSG20_1st/2nd part | Wed Apr 20 08:00:00 IDT 2022 | Tue May 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2347 | TT_TASK | ERECTION STACK DAMPER HRSG20 | Fri Jul 08 08:00:00 IDT 2022 | Sat Jul 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2348 | TT_TASK | ERECTION STACK HRSG20_1st part | Fri Jun 24 08:00:00 IDT 2022 | Thu Jun 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2349 | TT_TASK | PRE-ASSEMBLY STACK INCL. INSULATION / SEC. STEEL HRSG 3rd/4th part | Fri May 20 08:00:00 IDT 2022 | Thu Jun 23 17:00:00 IDT 2022 |  |  | 144.0 | NOT_STARTED
2350 | TT_TASK | ERECTION STACK HRSG20_3rd part | Sun Jul 17 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2351 | TT_TASK | REMAINING EXTERNAL INSULATION FOR STACK HRSG20 & COMPLETION PLATFORMS | Tue Sep 13 08:00:00 IDT 2022 | Mon Oct 10 17:00:00 IDT 2022 |  |  | 1512.0 | NOT_STARTED
2352 | TT_TASK | INSTALL PIPING SUPPORTS HRSG20 | Fri Jun 17 08:00:00 IDT 2022 | Mon May 01 17:00:00 IDT 2023 |  |  | 112.0 | NOT_STARTED
2353 | TT_TASK | ERECTION STACK HRSG20_2nd part | Fri Jul 01 08:00:00 IDT 2022 | Thu Jul 07 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2354 | TT_TASK | ERECTION STACK HRSG20_4th part | Sun Aug 14 08:00:00 IDT 2022 | Sat Aug 20 17:00:00 IDT 2022 |  |  | 184.0 | NOT_STARTED
2355 | TT_TASK | ERECTION STACK HRSG20_Basering | Fri Jun 17 08:00:00 IDT 2022 | Thu Jun 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2356 | TT_TASK | ERECTION STACK HRSG20_Flue Gas Silencer | Sun Jul 24 08:00:00 IDT 2022 | Sat Aug 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2357 | TT_TASK | INSTALL PIPING HRSG20_External Large Bore Second Part | Thu Oct 13 08:00:00 IDT 2022 | Thu Dec 15 17:00:00 IST 2022 |  |  | 128.0 | NOT_STARTED
2358 | TT_TASK | INSTALLATION COMPENSATORS | Thu Dec 01 08:00:00 IST 2022 | Wed Dec 21 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2359 | TT_TASK | ERECTION MAIN STEEL COLUMNS INCL. BOTTOM PANELS & TOP CROSS GIRDER HRSG20 | Fri Apr 01 08:00:00 IDT 2022 | Sat Apr 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2361 | TT_TASK | Install column panel CS04R, bottom panel CS34B & column panel CS04L | Fri Apr 01 08:00:00 IDT 2022 | Fri Apr 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2362 | TT_TASK | Install the top girder beams CS22T, CS23T | Sat Apr 02 08:00:00 IDT 2022 | Sat Apr 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2363 | TT_TASK | Install the column panel CS01R, CS01L, bottom panel CS31B & temporary bracings | Sun Apr 03 08:00:00 IDT 2022 | Sun Apr 03 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2364 | TT_TASK | Install the top girder beam CS21T and bottom panels CS32B, CS33B | Mon Apr 04 08:00:00 IDT 2022 | Mon Apr 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2365 | TT_TASK | Install the side panel CS03R, CS03L, CS02R & CS02L | Tue Apr 05 08:00:00 IDT 2022 | Tue Apr 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2366 | TT_TASK | Install the column panel CS05R & bottom girder beam CS35B | Wed Apr 06 08:00:00 IDT 2022 | Wed Apr 06 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2367 | TT_TASK | Install the column panel CS05L, top girder beam CS24T & CS25T | Thu Apr 07 08:00:00 IDT 2022 | Thu Apr 07 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2368 | TT_TASK | Install the bottom panel CS42B, side panel CS13R & CS13L | Fri Apr 08 08:00:00 IDT 2022 | Fri Apr 08 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2369 | TT_TASK | Install the side panels CS12R & CS12L | Sat Apr 09 08:00:00 IDT 2022 | Sat Apr 09 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2370 | TT_TASK | Install the column panel CS08R & CS08L, install the bottom panel CS38B | Sun Apr 10 08:00:00 IDT 2022 | Sun Apr 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2371 | TT_TASK | Install the top girder beam CS26T & CS27T | Mon Apr 11 08:00:00 IDT 2022 | Mon Apr 11 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2372 | TT_TASK | Install the bottom panels CS37B & CS36B, side panel CS07R & CS07L | Tue Apr 12 08:00:00 IDT 2022 | Tue Apr 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2373 | TT_TASK | Install the bottom panel CS41B, side panel CS06R & CS06L | Wed Apr 13 08:00:00 IDT 2022 | Wed Apr 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2374 | TT_TASK | Install the column panel CS11R, CS11L | Thu Apr 14 08:00:00 IDT 2022 | Thu Apr 14 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2375 | TT_TASK | Install the top girder beam CS28T, the bottom panels CS39B & CS40B | Fri Apr 15 08:00:00 IDT 2022 | Fri Apr 15 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2376 | TT_TASK | Install the side panels CS10R, CS10L, CS09R & CS09L | Sat Apr 16 08:00:00 IDT 2022 | Sat Apr 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2377 | TT_TASK | Install the top panels (CS45F > CS46F & CS49F > CS50F) | Thu May 05 08:00:00 IDT 2022 | Thu May 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2378 | TT_TASK | Install the top panels (CS41F > CS42F & CS51F > CS52F) | Fri May 06 08:00:00 IDT 2022 | Fri May 06 17:00:00 IDT 2022 |  |  | 328.0 | NOT_STARTED
2379 | TT_TASK | FOUNDATION SURVEY HRSG20 | Tue Dec 21 08:00:00 IST 2021 | Fri Dec 31 17:00:00 IST 2021 | Tue Dec 21 08:00:00 IST 2021 | Fri Dec 31 17:00:00 IST 2021 |  | COMPLETED
2380 | TT_TASK | PREPARATION WORKS HRSG STRUCTURE ERECTION HRSG20 | Wed Mar 16 08:00:00 IST 2022 | Thu Mar 31 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2382 | TT_TASK | REMAINING SECONDARY PLATFORMS LADDERS etc. HRSG20 | Mon Sep 19 08:00:00 IDT 2022 | Sun Dec 11 17:00:00 IST 2022 |  |  | 680.0 | NOT_STARTED
2383 | TT_TASK | ERECTION STAIRCASE 1 (STACK, SOUTH) HRSG20 | Thu Apr 21 08:00:00 IDT 2022 | Wed May 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2384 | TT_TASK | PRE-ASSEMBLY TOP PLATFORMS HRSG20 | Fri Apr 29 08:00:00 IDT 2022 | Thu May 19 17:00:00 IDT 2022 |  |  | 48.0 | NOT_STARTED
2385 | TT_TASK | ERECTION TOP PLATFORMS HRSG20 | Thu May 19 08:00:00 IDT 2022 | Wed Jun 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2386 | TT_TASK | ERECTION DRUM SUPPORT STEEL / ERECTION TOP PLATFORMS FOR DRUM INSTALL/ROOF PANELS | Fri Jun 17 08:00:00 IDT 2022 | Sun Jun 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2387 | TT_TASK | ERECTION STAIRCASE 2 (INLET DUCT, NORTH) HRSG20 | Mon Sep 05 08:00:00 IDT 2022 | Sun Sep 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2388 | TT_TASK | REMAINING INTERNAL INSULATION FOR INLET DUCT HRSG20 | Fri Sep 09 08:00:00 IDT 2022 | Thu Sep 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2389 | TT_TASK | ERECTION INLET DUCT HRSG20 | Mon Jul 04 08:00:00 IDT 2022 | Sun Jul 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2390 | TT_TASK | Erection of inlet duct main frame and panels | Mon Jul 04 08:00:00 IDT 2022 | Thu Jul 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2391 | TT_TASK | Erect scaffolding for inlet duct & expansion joint installation | Mon Jul 11 08:00:00 IDT 2022 | Wed Aug 03 17:00:00 IDT 2022 |  |  | 120.0 | NOT_STARTED
2392 | TT_TASK | Adjust alignment of main frame and panels | Tue Jul 26 08:00:00 IDT 2022 | Sun Jul 31 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2393 | TT_TASK | Bolt tightening of main frame | Mon Aug 01 08:00:00 IDT 2022 | Sat Aug 06 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2394 | TT_TASK | Erect internal scaffolding for panel welding and insulation installation | Wed Aug 10 08:00:00 IDT 2022 | Sat Aug 27 17:00:00 IDT 2022 |  |  | 24.0 | NOT_STARTED
2395 | TT_TASK | WELDING INLET DUCT | Fri Jul 08 08:00:00 IDT 2022 | Tue Aug 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2396 | TT_TASK | External seal welding of main frame and panels | Sun Aug 07 08:00:00 IDT 2022 | Thu Aug 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2397 | TT_TASK | Internal seal welding of panels | Fri Aug 19 08:00:00 IDT 2022 | Tue Aug 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2398 | TT_TASK | NDT for welding and touch up painting | Wed Aug 31 08:00:00 IDT 2022 | Sun Sep 11 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2399 | TT_TASK | Installation of insulation of casing | Mon Sep 12 08:00:00 IDT 2022 | Thu Sep 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2400 | TT_TASK | Installation of inlet duct expansion joint | Sun Sep 18 08:00:00 IDT 2022 | Thu Sep 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2403 | TT_TASK | COLD COMMISSIONING BOILER INLET, OUTLET DUCT, STACK HBK/HNE 20 | Tue Apr 18 08:00:00 IDT 2023 | Mon Apr 24 17:00:00 IDT 2023 |  |  | 144.0 | NOT_STARTED
2404 | TT_TASK | ERECTION DRUM END ENCLOSURE / CANOPY HRSG20 | Sat Sep 17 08:00:00 IDT 2022 | Fri Nov 25 17:00:00 IST 2022 |  |  | 808.0 | NOT_STARTED
2405 | TT_TASK | INSTALL BUMPERS HRSG20 | Fri Apr 22 08:00:00 IDT 2022 | Thu May 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2408 | TT_TASK | BASIC DESIGN SCR SKID HSJ/HSK | Wed Jan 27 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 | Wed Jan 27 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 |  | COMPLETED
2412 | TT_TASK | DESIGN, MANUFACTURING, SHOP TEST SCR SKID HSJ/HSK | Fri Sep 17 08:00:00 IDT 2021 | Mon May 09 17:00:00 IDT 2022 | Fri Sep 17 08:00:00 IDT 2021 |  |  | IN_PROGRESS
2415 | TT_TASK | DETAIL DESIGN DECOMP. CHAMBER / HOT AIR BLOWER SUPPORT FRAME | Thu Apr 29 08:00:00 IDT 2021 | Sun Jul 18 17:00:00 IDT 2021 | Thu Apr 29 08:00:00 IDT 2021 | Sun Jul 18 17:00:00 IDT 2021 |  | COMPLETED
2416 | TT_TASK | BD - SUBMISSION & APPROVAL - DECOMP. CHAMBER / HOT AIR BLOWER SUPPORT FRAME | Mon Jul 19 08:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 | Mon Jul 19 08:00:00 IDT 2021 | Thu Sep 16 17:00:00 IDT 2021 |  | COMPLETED
2417 | TT_TASK | DESIGN, MANUFACTURING, SHOP TEST SCR EQUIPMENT HSJ/HSK | Fri Sep 17 08:00:00 IDT 2021 | Wed Dec 08 17:00:00 IST 2021 | Fri Sep 17 08:00:00 IDT 2021 | Wed Dec 08 17:00:00 IST 2021 |  | COMPLETED
2420 | TT_TASK | TRANSPORT SCR SKID HSJ/HSK | Tue Jun 07 08:00:00 IDT 2022 | Mon Aug 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2422 | TT_TASK | TRANSPORT SCR CATALYST MODULES | Fri Apr 07 08:00:00 IDT 2023 | Thu Jun 01 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2424 | TT_TASK | TRANSPORT SCR SCR EQUIPMENT TO BE INSTALLED INSIDE HRSG CASING | Thu Dec 09 08:00:00 IST 2021 | Fri Jan 07 17:00:00 IST 2022 | Thu Dec 09 08:00:00 IST 2021 | Fri Jan 07 17:00:00 IST 2022 |  | COMPLETED
2425 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - SCR SKID HSJ/HSK | Tue May 10 08:00:00 IDT 2022 | Mon Jun 06 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2426 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - SCR CATALYST MODULES | Fri Mar 10 08:00:00 IST 2023 | Thu Apr 06 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2427 | TT_TASK | ERECTION SCR SKID HSJ/HSK | Tue Aug 30 08:00:00 IDT 2022 | Mon Oct 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2428 | TT_TASK | PREPARATION INSTALLATION SCR SKID HSJ/HSK | Tue Aug 02 08:00:00 IDT 2022 | Mon Aug 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2429 | TT_TASK | ERECTION AMMONIA STORAGE / SUPPLY SYTEM | Fri Jul 29 08:00:00 IDT 2022 | Thu Aug 11 17:00:00 IDT 2022 |  |  | 464.0 | NOT_STARTED
2430 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20HSJ | Tue Oct 11 08:00:00 IDT 2022 | Mon Jan 16 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2431 | TT_TASK | INSULATION PIPES / VALVES SCR SYSTEM 20HSJ | Tue Jan 17 08:00:00 IST 2023 | Mon Feb 20 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2432 | TT_TASK | ELECTRICAL ERECTION / VALVES SCR SYSTEM 20HSJ | Tue Feb 21 08:00:00 IST 2023 | Mon Feb 27 17:00:00 IST 2023 |  |  | 864.0 | NOT_STARTED
2434 | TT_TASK | COLD COMMISSIONING SCR AMMONIA STORAGE & SUPPLY HSJ/HSK | Fri Jun 16 08:00:00 IDT 2023 | Thu Jun 22 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2436 | TT_TASK | REMOVE PIPES (CHEMICAL CLEANING) 20 | Sat Jun 03 08:00:00 IDT 2023 | Fri Jun 30 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2437 | TT_TASK | COLD COMMISSIONING WATER SYSTEMS AFTER CHEMICAL CLEANING 20LAA/LCA30/EKT30 | Mon Jun 05 08:00:00 IDT 2023 | Sun Jun 11 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2438 | TT_TASK | REMOVAL INSERTS OF EMERGENCY STOP VALVES | Mon Jul 10 08:00:00 IDT 2023 | Fri Jul 14 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2439 | TT_TASK | INSTALLATION SCR MODULES IN HRSG | Mon Jul 10 08:00:00 IDT 2023 | Mon Jul 24 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2440 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20LAB | Mon Aug 29 08:00:00 IDT 2022 | Sun Dec 11 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2441 | TT_TASK | INSULATION PIPES / VALVES FEEDWATER SYSTEM 20LAB | Mon Dec 12 08:00:00 IST 2022 | Sun Jan 22 17:00:00 IST 2023 |  |  | 344.0 | NOT_STARTED
2442 | TT_TASK | ELECTRICAL ERECTION PIPES / VALVES 20LAB | Mon Dec 12 08:00:00 IST 2022 | Sun Dec 18 17:00:00 IST 2022 |  |  | 624.0 | NOT_STARTED
2446 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION FEEDWATER PUMP SKID 20LAC | Fri Mar 18 08:00:00 IST 2022 | Thu Apr 14 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2447 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MODULE 20LAC10Y (w/o Pump) | Sun May 15 08:00:00 IDT 2022 | Sat May 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2448 | TT_TASK | ERECTION FEEDWATER PUMP & MOTOR SKID 20LAC | Sat Jul 09 08:00:00 IDT 2022 | Fri Sep 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2449 | TT_TASK | ERECTION OF NOISE ENCLOSURE FEEDWATER PUMPS 20LAC | Sat Sep 03 08:00:00 IDT 2022 | Fri Nov 11 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2450 | TT_TASK | LIGHTING AND SMALL POWER INSIDE NOISE ENCLOSURE FEEDWATER PUMPS 20LAC | Sat Sep 17 08:00:00 IDT 2022 | Fri Oct 07 17:00:00 IDT 2022 |  |  | 1512.0 | NOT_STARTED
2452 | TT_TASK | ELECTRICAL ERECTION FEEDWATER PUMPS 20LAC | Sat Sep 03 08:00:00 IDT 2022 | Fri Oct 28 17:00:00 IDT 2022 |  |  | 112.0 | NOT_STARTED
2454 | TT_TASK | COLD COMMISSIONING FEEDWATER SYSTEM 20LAB/C | Sat Apr 15 08:00:00 IDT 2023 | Fri Apr 28 17:00:00 IDT 2023 |  |  | 112.0 | NOT_STARTED
2455 | TT_TASK | FIRST FEEDWATER SYSTEM MINIMUM FLOW OPERATION LAB/C | Mon Jun 12 08:00:00 IDT 2023 | Sun Jun 18 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2456 | TT_TASK | ERECTION, NDT PIPE / VALVES 10LBA10 (BOP) | Fri Aug 19 08:00:00 IDT 2022 | Sun Dec 11 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2457 | TT_TASK | INSULATION PIPES / VALVES FOR STEAM SYSTEM 20LBA10 | Thu Feb 09 08:00:00 IST 2023 | Wed Mar 22 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2458 | TT_TASK | PT, RE-INSTALLATION PIPES / VALVES LBA10 | Fri Feb 10 08:00:00 IST 2023 | Wed Feb 22 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2459 | TT_TASK | PT, RE-INSTALLATION PIPES / VALVES 11LBA10 (TURBOSET) | Thu Jan 26 08:00:00 IST 2023 | Tue Feb 07 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2460 | TT_TASK | ERECTION, NDT PIPE / VALVES 20LBA80 (BOP) | Mon Aug 22 08:00:00 IDT 2022 | Sun Dec 25 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2461 | TT_TASK | INSULATION PIPES / VALVES FOR STEAM SYSTEM 20LBA80 (BOP) | Thu Feb 09 08:00:00 IST 2023 | Wed Mar 15 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2462 | TT_TASK | PT, RE-INSTALLATION PIPES / VALVES 11LBA80 (TURBOSET) | Thu Feb 09 08:00:00 IST 2023 | Wed Feb 22 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2463 | TT_TASK | ERECTION, NDT PIPE / VALVES 11LBA80 (TURBOSET) | Thu Dec 22 08:00:00 IST 2022 | Wed Jan 25 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2464 | TT_TASK | INSULATION PIPES / VALVES FOR STEAM SYSTEM 11LBA80 (TURBOSET) | Thu Jan 26 08:00:00 IST 2023 | Wed Mar 01 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2465 | TT_TASK | PT, RE-INSTALLATION PIPES / VALVES 20LBA80 (BOP) | Mon Dec 26 08:00:00 IST 2022 | Sat Jan 07 17:00:00 IST 2023 |  |  | 776.0 | NOT_STARTED
2466 | TT_TASK | ELECTRICAL ERECTION PIPE / VALVES 20LBA10 | Thu Mar 16 08:00:00 IST 2023 | Wed Mar 22 17:00:00 IST 2023 |  |  | 208.0 | NOT_STARTED
2467 | TT_TASK | ELECTRICAL ERECTION PIPE / VALVES 20LBA10 | Wed Mar 08 08:00:00 IST 2023 | Tue Mar 14 17:00:00 IST 2023 |  |  | 272.0 | NOT_STARTED
2468 | TT_TASK | ELECTRICAL ERECTION / VALVES 20LBA80 | Thu Mar 09 08:00:00 IST 2023 | Wed Mar 15 17:00:00 IST 2023 |  |  | 208.0 | NOT_STARTED
2469 | TT_TASK | ELECTRICAL ERECTION / VALVES 11LBA80 | Thu Feb 23 08:00:00 IST 2023 | Wed Mar 01 17:00:00 IST 2023 |  |  | 376.0 | NOT_STARTED
2470 | TT_TASK | FINAL COLD COMMISSIONING STEAM SYSTEM 20LBA | Mon Jun 12 08:00:00 IDT 2023 | Sun Jun 18 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2472 | TT_TASK | COLD COMMISSIONING HP MAIN STEAM SYSTEM (FOR CHEM. CLEANING) LBA10 | Tue Apr 18 08:00:00 IDT 2023 | Mon May 01 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2474 | TT_TASK | COLD COMMISSIONING LP MAIN STEAM SYSTEM (FOR CHEM. CLEANING) LBA80 | Tue Apr 18 08:00:00 IDT 2023 | Mon May 01 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2475 | TT_TASK | ERECTION, NDT PIPE / VALVES 20LBB-LBC80 | Fri Aug 26 08:00:00 IDT 2022 | Thu Nov 10 17:00:00 IST 2022 |  |  | 728.0 | NOT_STARTED
2476 | TT_TASK | ERECTION, NDT PIPE / VALVES 20LBB-LBC80 | Thu Dec 15 08:00:00 IST 2022 | Wed Jan 25 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2477 | TT_TASK | INSULATION PIPES / VALVES FOR STEAM SYSTEM 20LBB-LBC80 | Thu Feb 23 08:00:00 IST 2023 | Wed Mar 29 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2478 | TT_TASK | INSULATION PIPES / VALVES FOR REHEAT SYSTEM 20LBB-LBC80 | Thu Feb 23 08:00:00 IST 2023 | Wed Mar 29 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2479 | TT_TASK | PT, RE-INSTALLATION PIPES / VALVES LBB-LBC80 | Fri Feb 10 08:00:00 IST 2023 | Wed Feb 22 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2480 | TT_TASK | ELECTRICAL ERECTION / VALVES 20LBB-LBC80 | Thu Mar 23 08:00:00 IST 2023 | Wed Mar 29 17:00:00 IDT 2023 |  |  | 152.0 | NOT_STARTED
2481 | TT_TASK | ELECTRICAL ERECTION / VALVES 20LBB-LBC80 | Thu Mar 23 08:00:00 IST 2023 | Wed Mar 29 17:00:00 IDT 2023 |  |  | 152.0 | NOT_STARTED
2482 | TT_TASK | COLD COMMISSIONING REHEAT SYSTEM (FOR CHEM. CLEANING) 20LBB | Tue Apr 18 08:00:00 IDT 2023 | Mon May 01 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2484 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST BYPASS STATION 20LBF | Wed Mar 17 08:00:00 IST 2021 | Sun Mar 06 17:00:00 IST 2022 | Wed Mar 17 08:00:00 IST 2021 |  |  | IN_PROGRESS
2487 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - BYPASS STATION 20LBF | Mon Mar 07 08:00:00 IST 2022 | Sun Apr 03 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2488 | TT_TASK | TRANSPORT BYPASS STATION 20LBF | Thu Jun 16 08:00:00 IDT 2022 | Fri Jul 15 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2490 | TT_TASK | ASSEMBLY / ERECTION, BYPASS STATION 20LBF | Sat Jul 30 08:00:00 IDT 2022 | Fri Aug 26 17:00:00 IDT 2022 |  |  | 16.0 | NOT_STARTED
2494 | TT_TASK | CONTRACT REVIEW / PREP. RFQ EL. SUPERHEATER LBG | Fri Feb 12 08:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 | Fri Feb 12 08:00:00 IST 2021 | Thu Mar 11 17:00:00 IST 2021 |  | COMPLETED
2495 | TT_TASK | QUOTATION STAGE EL. SUPERHEATER LBG | Fri Mar 12 08:00:00 IST 2021 | Sun Jun 06 17:00:00 IDT 2021 | Fri Mar 12 08:00:00 IST 2021 | Sun Jun 06 17:00:00 IDT 2021 |  | COMPLETED
2497 | TT_TASK | DESIGN DATA SHEETS EL. SUPERHEATER LBG | Fri Jan 29 08:00:00 IST 2021 | Thu Feb 18 17:00:00 IST 2021 | Fri Jan 29 08:00:00 IST 2021 | Thu Feb 18 17:00:00 IST 2021 |  | COMPLETED
2499 | TT_TASK | DETAIL DESIGN EL. SUPERHEATER 20LBG | Wed Aug 04 08:00:00 IDT 2021 | Tue Aug 24 17:00:00 IDT 2021 | Wed Aug 04 00:00:00 IDT 2021 | Wed Aug 25 00:00:00 IDT 2021 |  | COMPLETED
2500 | TT_TASK | PROCURMENT / PRE-FABRICATION EL.SUPERHEATER 20LBG | Thu Aug 26 08:00:00 IDT 2021 | Wed Jun 15 17:00:00 IDT 2022 | Thu Aug 26 08:00:00 IDT 2021 |  | 96.0 | IN_PROGRESS
2503 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION EL.SUPERHEATER 20LBG | Tue May 31 08:00:00 IDT 2022 | Mon Jun 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2504 | TT_TASK | TRANSPORT EL.SUPERHEATER 20LBG | Tue Jun 28 08:00:00 IDT 2022 | Mon Aug 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2506 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20LBG | Thu Jul 21 08:00:00 IDT 2022 | Wed Sep 28 17:00:00 IDT 2022 |  |  | 464.0 | NOT_STARTED
2507 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20LBG | Tue Aug 30 08:00:00 IDT 2022 | Mon Nov 07 17:00:00 IST 2022 |  |  | 224.0 | NOT_STARTED
2508 | TT_TASK | INSULATION PIPES / VALVES FOR STEAM SYSTEM 20LBG | Sat Nov 26 08:00:00 IST 2022 | Fri Jan 06 17:00:00 IST 2023 |  |  | 808.0 | NOT_STARTED
2509 | TT_TASK | INSULATION PIPES / VALVES FOR STEAM SYSTEM 20LBG | Tue Dec 06 08:00:00 IST 2022 | Mon Jan 02 17:00:00 IST 2023 |  |  | 840.0 | NOT_STARTED
2510 | TT_TASK | ERECTION EL.SUPERHEATER 20LBG | Tue Aug 23 08:00:00 IDT 2022 | Mon Sep 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2512 | TT_TASK | ELECTRICAL ERECTION / VALVES FOR STEAM SYSTEM 20LBG | Tue Dec 27 08:00:00 IST 2022 | Mon Jan 02 17:00:00 IST 2023 |  |  | 32.0 | NOT_STARTED
2513 | TT_TASK | ELECTRICAL ERECTION / VALVES FOR STEAM SYSTEM 20LBG | Tue Dec 27 08:00:00 IST 2022 | Mon Jan 02 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2514 | TT_TASK | E- AND I&C-ERECTION EL.SUPERHEATER 20LBG | Mon Oct 10 08:00:00 IDT 2022 | Sun Oct 16 17:00:00 IDT 2022 |  |  | 1464.0 | NOT_STARTED
2516 | TT_TASK | COLD COMMISSIONING AUXILIARY STEAM SYSTEM LBG | Tue May 02 08:00:00 IDT 2023 | Fri May 05 17:00:00 IDT 2023 |  |  | 56.0 | NOT_STARTED
2518 | TT_TASK | DETAIL DESIGN / MANUFACTURING BLOW DOWN TANK 20LBH | Thu Jan 28 08:00:00 IST 2021 | Wed Feb 09 17:00:00 IST 2022 | Thu Jan 28 08:00:00 IST 2021 | Wed Feb 09 17:00:00 IST 2022 |  | COMPLETED
2520 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION BLOW DOWN TANK 20LBH | Thu Feb 10 08:00:00 IST 2022 | Wed Mar 09 17:00:00 IST 2022 | Thu Feb 10 08:00:00 IST 2022 |  |  | IN_PROGRESS
2521 | TT_TASK | TRANSPORT BLOW DOWN TANK 20LBH | Mon Mar 21 08:00:00 IST 2022 | Mon Apr 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2523 | TT_TASK | ERECTION BLOW DOWN TANK 20LBH | Mon May 30 08:00:00 IDT 2022 | Tue Jun 28 17:00:00 IDT 2022 |  |  | 808.0 | NOT_STARTED
2524 | TT_TASK | PLACING BOILER BLOW DOWN TANK 20LBH | Tue Apr 19 08:00:00 IDT 2022 | Tue Apr 19 17:00:00 IDT 2022 |  |  | 304.0 | NOT_STARTED
2526 | TT_TASK | COLD COMMISSIONING BLOW DOWN TANK (FOR CHEM. CLEANING) 20LBH | Tue Apr 18 08:00:00 IDT 2023 | Mon Apr 24 17:00:00 IDT 2023 |  |  | 144.0 | NOT_STARTED
2529 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CONDENSATE RECIRC.PUMP 20LCA51 | Wed Oct 20 08:00:00 IDT 2021 | Tue Nov 16 17:00:00 IST 2021 | Wed Oct 20 08:00:00 IDT 2021 | Tue Nov 16 17:00:00 IST 2021 |  | COMPLETED
2530 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MODULE 20LCA50Y | Sun May 15 08:00:00 IDT 2022 | Sat May 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2531 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20LCA | Wed Aug 31 08:00:00 IDT 2022 | Mon Jan 23 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2532 | TT_TASK | ERECTION, NDT, PIPES / VALVES 20LCA - UNDER HRSG INLET DUCT | Wed Aug 17 08:00:00 IDT 2022 | Tue Aug 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2533 | TT_TASK | INSULATION PIPES / VALVES CONDENSATE SYSTEM 20LCA | Tue Jan 24 08:00:00 IST 2023 | Mon Feb 27 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2534 | TT_TASK | ERECTION, NDT, PIPES / VALVES 20LCA ON PIPE BRIDGES | Fri Jun 17 08:00:00 IDT 2022 | Thu Dec 22 17:00:00 IST 2022 |  |  | 680.0 | NOT_STARTED
2536 | TT_TASK | ELECTRICAL ERECTION / VALVES CONDENSATE SYSTEM 20LCA | Tue Feb 21 08:00:00 IST 2023 | Mon Feb 27 17:00:00 IST 2023 |  |  | 56.0 | NOT_STARTED
2538 | TT_TASK | COLD COMMISSIONING MAIN COND. SYSTEM IN MIN. FLOW OPERATION (FOR CHEM. CLEANING) LCA/LCB | Sat Apr 29 08:00:00 IDT 2023 | Sat May 06 17:00:00 IDT 2023 |  |  | 48.0 | NOT_STARTED
2540 | TT_TASK | DESIGN DATA SHEETS CONDENSATE EXTRACTION PUMPS LCB | Fri Jan 01 08:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Fri Jan 01 08:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 |  | COMPLETED
2541 | TT_TASK | MANUFACTURING / SHOP TEST CONDENSATE EXTRACTION PUMP 20LCB | Fri Apr 09 08:00:00 IDT 2021 | Wed Jun 08 17:00:00 IDT 2022 | Fri Apr 09 08:00:00 IDT 2021 |  |  | IN_PROGRESS
2544 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CONDENSATE EXTRACTION PUMP 20LCB | Thu May 12 08:00:00 IDT 2022 | Wed Jun 08 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2545 | TT_TASK | TRANSPORT CONDENSATE EXTRACTION PUMP 20LCB | Thu Jun 09 08:00:00 IDT 2022 | Wed Aug 03 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2547 | TT_TASK | PLACING CONDENSATE EXTRACTION PUMP 20LCB | Thu Aug 04 08:00:00 IDT 2022 | Fri Aug 05 17:00:00 IDT 2022 |  |  | 128.0 | NOT_STARTED
2548 | TT_TASK | ERECTION CONDENSATE EXTRACTION PUMP 20LCB | Mon Aug 22 08:00:00 IDT 2022 | Sun Sep 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2550 | TT_TASK | ELECTRICAL ERECTION CONDENSATE EXTRACTION PUMP 20LCB | Mon Oct 10 08:00:00 IDT 2022 | Sun Oct 23 17:00:00 IDT 2022 |  |  | 1496.0 | NOT_STARTED
2551 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20LCE | Sun Jun 12 08:00:00 IDT 2022 | Sat Oct 15 17:00:00 IDT 2022 |  |  | 248.0 | NOT_STARTED
2552 | TT_TASK | INSULATION PIPES / VALVES CONDENSATE 20LCE(Not appicable) | Sat Nov 26 08:00:00 IST 2022 | Fri Dec 30 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2553 | TT_TASK | ELECTRICAL ERECTION / VALVES CONDENSATE SYSTEM 20LCE | Sat Dec 31 08:00:00 IST 2022 | Fri Jan 06 17:00:00 IST 2023 |  |  | 896.0 | NOT_STARTED
2557 | TT_TASK | CONTRACT REVIEW / PREP. RFQ BOILER BLOWDOWN PUMP LCL | Fri Jan 15 08:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Mon Feb 22 17:00:00 IST 2021 |  | COMPLETED
2558 | TT_TASK | QUOTATION STAGE BOILER BLOWDOWN PUMP LCL | Tue Feb 23 08:00:00 IST 2021 | Sun May 02 17:00:00 IDT 2021 | Tue Feb 23 08:00:00 IST 2021 | Sun May 02 17:00:00 IDT 2021 |  | COMPLETED
2560 | TT_TASK | DESIGN DATA SHEETS BOILER BLOWDOWN PUMP LCL | Tue Feb 02 08:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 | Tue Feb 02 08:00:00 IST 2021 | Mon Feb 15 17:00:00 IST 2021 |  | COMPLETED
2563 | TT_TASK | DETAIL DESIGN / CLARIFICATION BOILER BLOWDOWN PUMP 20LCL | Mon May 03 08:00:00 IDT 2021 | Sun May 30 17:00:00 IDT 2021 | Mon May 03 08:00:00 IDT 2021 | Sun May 30 17:00:00 IDT 2021 |  | COMPLETED
2564 | TT_TASK | MANUFACTURING / SHOP TEST BOILER BLOWDOWN PUMP 20LCL | Mon May 31 08:00:00 IDT 2021 | Sat Apr 30 17:00:00 IDT 2022 | Mon May 31 08:00:00 IDT 2021 |  |  | IN_PROGRESS
2567 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION BOILER BLOWDOWN PUMP 20LCL | Sun May 01 08:00:00 IDT 2022 | Sat May 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2568 | TT_TASK | TRANSPORT BOILER BLOWDOWN PUMP 20LCL | Sun May 29 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2570 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20LCL | Sat Dec 03 08:00:00 IST 2022 | Fri Mar 17 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2571 | TT_TASK | INSULATION PIPES / VALVES STEAM GENERATOR DRAINS 20LCL | Sat Mar 18 08:00:00 IST 2023 | Fri Apr 14 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2572 | TT_TASK | ERECTION STEAM BOILER BLOWDOWN PUMP 20LCL | Sat Aug 06 08:00:00 IDT 2022 | Fri Sep 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2574 | TT_TASK | PLACING BOILER BLOWDOWN PUMP 20LCL | Fri Aug 05 08:00:00 IDT 2022 | Fri Aug 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2575 | TT_TASK | ELECTRICAL ERECTION / VALVES STEAM GENERATOR DRAINS 20LCL | Sat Apr 01 08:00:00 IDT 2023 | Fri Apr 14 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2576 | TT_TASK | ELECTRICAL ERECTION BOILER BLOWDOWN PUMP 20LCL | Sat Sep 03 08:00:00 IDT 2022 | Thu Sep 22 17:00:00 IDT 2022 |  |  | 1632.0 | NOT_STARTED
2578 | TT_TASK | COLD COMMISSIONING BOILER BLOWDOWN SYSTEM (FOR CHEM. CLEANING) 20LCL | Tue Apr 18 08:00:00 IDT 2023 | Mon Apr 24 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2579 | TT_TASK | FINAL COLD COMMISSIONING BOILER BLOWDOWN DRAIN PUMP 20LCL | Tue Apr 25 08:00:00 IDT 2023 | Mon May 01 17:00:00 IDT 2023 |  |  | 88.0 | NOT_STARTED
2580 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20LCW | Tue Nov 15 08:00:00 IST 2022 | Mon Jan 23 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2581 | TT_TASK | INSULATION PIPES / VALVES 20LCW | Tue Jan 24 08:00:00 IST 2023 | Mon Feb 20 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2582 | TT_TASK | ELECTRICAL ERECTION PIPES / VALVES 20LCW | Tue Feb 21 08:00:00 IST 2023 | Mon Mar 06 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2583 | TT_TASK | DETAIL DESIGN CONDENSATE POLISHING PLANT 20LD | Wed May 19 08:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 | Wed May 19 08:00:00 IDT 2021 | Tue Jul 27 17:00:00 IDT 2021 |  | COMPLETED
2585 | TT_TASK | MANUFACTURING/SHOP TEST CONDENSATE POLISHING PLANT 20LD | Wed Jul 28 08:00:00 IDT 2021 | Thu Apr 28 17:00:00 IDT 2022 | Wed Jul 28 08:00:00 IDT 2021 |  |  | IN_PROGRESS
2590 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CONDENSATE POLISHING PLANT 20LD | Fri Apr 29 08:00:00 IDT 2022 | Thu May 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2591 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CONDENSATE POLISHING PUMP 20LDK | Mon Sep 13 08:00:00 IDT 2021 | Sun Oct 10 17:00:00 IDT 2021 | Mon Sep 13 08:00:00 IDT 2021 | Sun Oct 10 17:00:00 IDT 2021 |  | COMPLETED
2592 | TT_TASK | TRANSPORT CONDENSATE POLISHING PLANT 20LD | Fri May 27 08:00:00 IDT 2022 | Thu Jul 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2594 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MODULE 20LDK00Y | Fri Apr 15 08:00:00 IDT 2022 | Thu Apr 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2595 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20LDK | Fri Aug 05 08:00:00 IDT 2022 | Wed Dec 28 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2596 | TT_TASK | INSULATION PIPES / VALVES 20LDK | Thu Dec 29 08:00:00 IST 2022 | Wed Feb 01 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2597 | TT_TASK | ERECTION CONDENSATE POLISHING PLANT 20LD | Fri Aug 05 08:00:00 IDT 2022 | Wed Nov 02 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2598 | TT_TASK | ELECTRICAL ERECTION CONDENSATE POLISHING PLANT 20LD | Thu Oct 20 08:00:00 IDT 2022 | Wed Nov 02 17:00:00 IST 2022 |  |  | 784.0 | NOT_STARTED
2600 | TT_TASK | LEAK TEST CONDENSATE POLISHING PLANT 20LD | Thu Feb 09 08:00:00 IST 2023 | Wed Feb 15 17:00:00 IST 2023 |  |  | 152.0 | NOT_STARTED
2601 | TT_TASK | ELECTRICAL ERECTION PIPES / VALVES 20LDK | Thu Feb 02 08:00:00 IST 2023 | Wed Feb 15 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2603 | TT_TASK | COLD COMMISSIONING CONDENSATE POLISHING PLANT (FOR BENSON BOILER) | Thu Mar 30 08:00:00 IDT 2023 | Wed May 03 17:00:00 IDT 2023 |  |  | 72.0 | NOT_STARTED
2605 | TT_TASK | ELECTRICAL ERECTION FOR MKC01/MBJ01 | Fri Sep 02 08:00:00 IDT 2022 | Thu Oct 20 17:00:00 IDT 2022 |  |  | 1096.0 | NOT_STARTED
2606 | TT_TASK | ELECTRICAL ERECTION FOR MKC02 | Mon Sep 26 08:00:00 IDT 2022 | Sun Oct 09 17:00:00 IDT 2022 |  |  | 1240.0 | NOT_STARTED
2607 | TT_TASK | COLD COMMISSIONING SEE TRANSFORMER 20MKC01 | Tue Mar 14 08:00:00 IST 2023 | Mon Mar 20 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2608 | TT_TASK | UV TEST (BLACK OUT) GT20 | Thu Jun 08 08:00:00 IDT 2023 | Wed Jun 14 17:00:00 IDT 2023 |  |  | 8.0 | NOT_STARTED
2609 | TT_TASK | COLD COMMISSIONING SFC TRANSFORMER 20MKC02 | Thu Apr 13 08:00:00 IDT 2023 | Wed Apr 19 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2610 | TT_TASK | UNDER VOLTAGE (UV) TEST (BLACK OUT) ST | Tue Jun 20 08:00:00 IDT 2023 | Mon Jun 26 17:00:00 IDT 2023 |  |  | 32.0 | NOT_STARTED
2611 | TT_TASK | COLD COMMISSIONING START UP TRANSFORMER 20MBJ01 | Tue Mar 14 08:00:00 IST 2023 | Mon Mar 20 17:00:00 IST 2023 |  |  | 168.0 | NOT_STARTED
2612 | TT_TASK | OPTIMIZING COMBINED CYCLE POWER PLANT | Sat Oct 21 08:00:00 IDT 2023 | Mon Dec 04 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2615 | TT_TASK | BYPASS OPERATION FOR ST 20 | Tue Jul 25 08:00:00 IDT 2023 | Mon Jul 31 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2617 | TT_TASK | COMBINED CYCLE POWER PLANT LOAD TESTS - MAIN GAS | Tue Aug 01 08:00:00 IDT 2023 | Fri Sep 29 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2618 | TT_TASK | COMBINED CYCLE POWER PLANT LOAD TESTS - 2ND & 3RD GAS | Sat Sep 30 08:00:00 IDT 2023 | Fri Oct 20 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2619 | TT_TASK | RELIABILITY RUN COMBINED CYCLE POWER PLANT | Sun Dec 17 08:00:00 IST 2023 | Sun Dec 31 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2620 | TT_TASK | PERFORMANCE TEST COMBINED CYCLE POWER PLANT | Tue Dec 05 08:00:00 IST 2023 | Sat Dec 16 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2621 | TT_TASK | TRANSPORT STEAM TURBINE (HI-L) | Sat Apr 30 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2623 | TT_TASK | TRANSPORT ST VALVES TO FABRICATOR | Wed Dec 22 08:00:00 IST 2021 | Fri Dec 31 17:00:00 IST 2021 | Wed Dec 22 08:00:00 IST 2021 | Fri Dec 31 17:00:00 IST 2021 |  | COMPLETED
2625 | TT_TASK | TRANSPORT ST HP/IP/LP VALVES | Sat Apr 30 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2627 | TT_TASK | TRANSPORT ST MAW VALVES (AIR FREIGHT) | Sat Apr 02 08:00:00 IDT 2022 | Wed Apr 06 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2629 | TT_TASK | GROUTING OF REAR LP1-BEARING PEDESTAL MA | Wed Jul 13 08:00:00 IDT 2022 | Wed Jul 20 17:00:00 IDT 2022 |  |  | 8.0 | NOT_STARTED
2630 | TT_TASK | GROUTING OF FRONT AND REAR HP-BEARING PEDESTALS MA | Thu Jul 07 08:00:00 IDT 2022 | Thu Jul 14 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2631 | TT_TASK | GROUTING OF STEEL BARS FOR LP1 CENTERING GUIDE MA | Thu Jul 21 08:00:00 IDT 2022 | Thu Jul 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2632 | TT_TASK | SET UP EQUIPMENT ON SITE, SET UP SITE STORES STEAM TURBINE MA | Tue May 24 08:00:00 IDT 2022 | Mon May 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2633 | TT_TASK | CHECK AND PREPARATION OF FOUNDATION STEAM TURBINE MA | Sat Jun 11 08:00:00 IDT 2022 | Fri Jun 17 17:00:00 IDT 2022 |  |  | 56.0 | NOT_STARTED
2634 | TT_TASK | PLACING BEARING CASINGS INCL. ANCHOR BOLTS MA | Sat Jun 25 08:00:00 IDT 2022 | Mon Jun 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2635 | TT_TASK | INSTALL. AND PREALIGNMENT OF STEEL BARS FOR LP1 CENTERING GUIDE MA | Wed Jul 13 08:00:00 IDT 2022 | Wed Jul 20 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2638 | TT_TASK | ALIGNMENT FRONT & REAR HP-BEARING PEDESTALS TO DRAWING AND DEFLECTION CURVE MA | Tue Jun 28 08:00:00 IDT 2022 | Wed Jul 06 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2639 | TT_TASK | ALIGNMENT REAR LP1-BEARING PEDESTAL TO DRAWING AND DEFLECTION CURVE MA | Mon Jul 04 08:00:00 IDT 2022 | Tue Jul 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2643 | TT_TASK | FINAL INSPECTIONS & CLOSING OF OPEN ITEMS BEFORE COMMISSIONING MA | Thu Feb 16 08:00:00 IST 2023 | Tue Mar 14 17:00:00 IST 2023 |  |  | 272.0 | NOT_STARTED
2646 | TT_TASK | ASSEMBLY OF TEMPORARY/FINAL HP/IP-VALVE SUPPORTS (OPTIONAL) | Fri Aug 05 08:00:00 IDT 2022 | Thu Aug 11 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2647 | TT_TASK | INSTALLATION HP-VALVE MAA | Fri Aug 12 08:00:00 IDT 2022 | Thu Aug 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2650 | TT_TASK | INSTALLATION AND ALIGNMENT REHEAT STOP AND CONTROL IP-VALVE MAB | Fri Aug 19 08:00:00 IDT 2022 | Thu Aug 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2652 | TT_TASK | INSTALLATION LP-FLAP (ERECTION ON PLATFORM) | Fri Nov 11 08:00:00 IST 2022 | Thu Nov 24 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2656 | TT_TASK | INSTALLATION ALL VALVE ACTUATORS FOR MAIN STEAM, REHEAT STOP AND CONTROL VALVES | Fri Aug 26 08:00:00 IDT 2022 | Thu Sep 22 17:00:00 IDT 2022 |  |  | 392.0 | NOT_STARTED
2661 | TT_TASK | CLEANING LP1-END WALLS AND PREPARATION OF ASSEMBLY STEAM TURBINE MA | Sun Jul 24 08:00:00 IDT 2022 | Mon Jul 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2662 | TT_TASK | PRE-ASSEMBLING/ ERECTION LP1-OUTER CASING MA | Wed Jul 27 08:00:00 IDT 2022 | Thu Aug 11 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2663 | TT_TASK | ALIGNMENT LP1-OUTER CASING TO LONGITUDINAL AND TRAVERSE AXES AND VERTICALY WITH DEFELCTION CURVE MA | Fri Aug 12 08:00:00 IDT 2022 | Sun Aug 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2664 | TT_TASK | WELDING ENTIRE LP1-OUTER CASING MA | Mon Aug 22 08:00:00 IDT 2022 | Mon Sep 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2665 | TT_TASK | FITTING/WELDING/ASSEMBLING CROSS OVER PIPE LP1 MA | Fri Oct 14 08:00:00 IDT 2022 | Thu Nov 03 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2666 | TT_TASK | SET DOWN AND ALIGNMENT LP1-BOTTOM HALF INNER CASING IN LP1-BOTTOM HALF OUTER CASING MA | Tue Sep 13 08:00:00 IDT 2022 | Fri Sep 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2668 | TT_TASK | PLACING LP1-TURBINE SHAFT IN BEARINGS MA | Sat Sep 17 08:00:00 IDT 2022 | Sun Sep 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2669 | TT_TASK | COMMON FINAL ALIGNMENT K-,LP-TURBINE AND GENERATOR | Thu Jan 12 08:00:00 IST 2023 | Sat Jan 21 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2670 | TT_TASK | PRELIMINARY ALIGNMENT LP1-TURBINE SHAFT AND LP1-SEALING CASING AND LP1-BOTTOM HALF INNER CASING MA | Mon Sep 19 08:00:00 IDT 2022 | Sun Sep 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2671 | TT_TASK | AXIAL AND RADIAL ALIGNMENT LP1-BOTTOM HALF INNER CASING TO SHAFT AND BLADING CLEARANCE MA | Mon Sep 26 08:00:00 IDT 2022 | Sun Oct 09 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2672 | TT_TASK | INSTALLING GUIDE BLADE RINGS AND LP1-TOP HALF INNER CASING AND LP1-TOP HALF OUTER CASING MA | Mon Sep 26 08:00:00 IDT 2022 | Thu Oct 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2673 | TT_TASK | FIT AND WELDING LP1-STEAM INLET LINES (incl. DISSASSEMBLING) MA | Fri Nov 04 08:00:00 IST 2022 | Thu Nov 24 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2675 | TT_TASK | PROVISIONALLY MOUNT OF EXPANSION JOINT FOR LP1-SUPPORTING ARM AND CENTERING GUIDE MA | Tue Sep 06 08:00:00 IDT 2022 | Mon Sep 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2676 | TT_TASK | PLACING LP1-TURBINE PEDESTALS MA | Mon Jun 27 08:00:00 IDT 2022 | Sun Jul 03 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2679 | TT_TASK | COMMON FINAL AXIAL MEASUREMENT TURBOSET | Thu Dec 22 08:00:00 IST 2022 | Wed Jan 11 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2680 | TT_TASK | FINISHING CASING ASSEMBLY MA | Fri Nov 25 08:00:00 IST 2022 | Thu Dec 29 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2681 | TT_TASK | CLEANING K-TURBINE AND PREPARATION OF ASSEMBLY MA | Tue Jul 26 08:00:00 IDT 2022 | Fri Jul 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2682 | TT_TASK | SET DOWN K-TURBINE ON BEARINGS AND PROVISIONALLY ALIGNMENT MA | Sat Jul 30 08:00:00 IDT 2022 | Sun Jul 31 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2683 | TT_TASK | CLEANING MAIN K-BEARING AND PLACING AUXILIARY K-BEARINGS MA | Mon Aug 01 08:00:00 IDT 2022 | Tue Aug 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2684 | TT_TASK | SET DOWN K-SHAFT IN BEARINGS AND ALIGNMENT OF SHAFT MA | Wed Aug 03 08:00:00 IDT 2022 | Tue Aug 09 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2685 | TT_TASK | PERFORM AXIAL AND RADIAL CLEARANCE CHECK OF K-TURBINE MA | Wed Aug 10 08:00:00 IDT 2022 | Thu Aug 11 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2686 | TT_TASK | COMPLETION OF BEARING PEDESTALS AND PREPARATION FOR FLUSHING MA | Sun Feb 05 08:00:00 IST 2023 | Tue Feb 14 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2687 | TT_TASK | ALIGNMENT AT CASING AND TURBINE BRACKETS MA | Sun Feb 05 08:00:00 IST 2023 | Fri Feb 17 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2689 | TT_TASK | INSTALLATION ST INSULATION MA | Wed Feb 22 08:00:00 IST 2023 | Tue Apr 04 17:00:00 IDT 2023 |  |  | 552.0 | NOT_STARTED
2691 | TT_TASK | HONE COUPLING HOLES AND COUPLING LP- AND GENERATOR-SHAFTS; CHECKING OF RADIAL RUN-OUT MA | Sun Jan 22 08:00:00 IST 2023 | Sat Jan 28 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2692 | TT_TASK | HONE COUPLING HOLES AND COUPLING OF K- AND LP-SHAFTS; CHECKING OF RADIAL RUN-OUT MA | Sun Jan 29 08:00:00 IST 2023 | Sat Feb 04 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2693 | TT_TASK | CLOSING BEARING PEDESTALS (READY FOR OPERATION) MA | Wed Mar 22 08:00:00 IST 2023 | Tue Apr 04 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2694 | TT_TASK | REASSEMBLY PIPING / TANK AFTER LUBE OIL FLUSHING MA | Wed Mar 15 08:00:00 IST 2023 | Tue Mar 21 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2695 | TT_TASK | INSTALLATION ST INSULATION (FIRST LAYER) MA | Fri Dec 02 08:00:00 IST 2022 | Thu Dec 29 17:00:00 IST 2022 |  |  | 224.0 | NOT_STARTED
2700 | TT_TASK | COLD COMMISSIONING LP-TURBINE 20MAB | Tue Apr 18 08:00:00 IDT 2023 | Mon Jun 19 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2704 | TT_TASK | COLD COMMISSIONING HP- / LP- VALVES -MAA/B | Mon Jul 10 08:00:00 IDT 2023 | Fri Jul 14 17:00:00 IDT 2023 |  |  | 80.0 | NOT_STARTED
2707 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES MAA-C | Mon Sep 26 08:00:00 IDT 2022 | Sun Nov 27 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2708 | TT_TASK | INSULATION PIPES / VALVES FOR STEAM SYSTEM MAA-C | Mon Nov 28 08:00:00 IST 2022 | Sun Jan 01 17:00:00 IST 2023 |  |  | 848.0 | NOT_STARTED
2709 | TT_TASK | ELECTRICAL ERECTION PIPES / VALVES MAA-C | Thu Dec 01 08:00:00 IST 2022 | Wed Dec 21 17:00:00 IST 2022 |  |  | 48.0 | NOT_STARTED
2710 | TT_TASK | TRANSPORT ST BEARINGS 20MAD | Fri Apr 08 08:00:00 IDT 2022 | Thu Jun 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2714 | TT_TASK | ELECTRICAL ERECTION ST BEARING CASINGS | Thu Oct 06 08:00:00 IDT 2022 | Wed Oct 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2716 | TT_TASK | COLD COMMISSIONING ST BEARING SYSTEM MAD | Wed Jun 07 08:00:00 IDT 2023 | Tue Jun 13 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2720 | TT_TASK | TRANSPORT ST CONDENSER 20MAG | Tue Apr 26 08:00:00 IDT 2022 | Tue May 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2721 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MODULE 20MAG50Y | Fri Apr 15 08:00:00 IDT 2022 | Thu Apr 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2722 | TT_TASK | GROUTING OF CONDENSER SHELL SUPPORT STRUCTURE SEISMIC TIE DOWNS MAG20 | Wed Sep 28 08:00:00 IDT 2022 | Sun Oct 02 17:00:00 IDT 2022 |  |  | 360.0 | NOT_STARTED
2723 | TT_TASK | SETTING UP OF ASSEMBLY AND CHECK FOUNDATION CONDENSER MAG20 | Wed May 11 08:00:00 IDT 2022 | Fri May 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2724 | TT_TASK | PLACING AND ALIGNMENT OF SUPPORT PLATES AND SLIDING SUPPORTS MAG20 | Sat May 14 08:00:00 IDT 2022 | Mon May 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2725 | TT_TASK | FITTING AND WELDING OF FIXING AND GUIDE POINTS MAG20 | Mon May 16 08:00:00 IDT 2022 | Wed May 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2727 | TT_TASK | INSTALLING PROTECTIVE COVER FOR COOLING TUBES IN THE STEAM SHELL (LOWER) MAG20 | Mon May 23 08:00:00 IDT 2022 | Wed May 25 17:00:00 IDT 2022 |  |  | 56.0 | NOT_STARTED
2728 | TT_TASK | INSTALLING PROTECTIVE COVER FOR COOLING TUBES IN THE STEAM SHELL (UPPER) MAG20 | Thu Jun 02 08:00:00 IDT 2022 | Sat Jun 04 17:00:00 IDT 2022 |  |  | 40.0 | NOT_STARTED
2729 | TT_TASK | PLACING STEAM SHELL (LOWER PART) AND CONNECTION/WELDING TO HOTWELL MAG20 | Mon May 23 08:00:00 IDT 2022 | Wed Jun 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2730 | TT_TASK | PLACING STEAM SHELL (UPPER PART) AND CONNECTION/WELDING TO LOWER PART MAG20 | Thu Jun 02 08:00:00 IDT 2022 | Wed Jun 15 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2731 | TT_TASK | ALIGNMENT OF CONDENSER STEAM SHELL MAG20 | Thu Jun 09 08:00:00 IDT 2022 | Thu Jun 09 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2733 | TT_TASK | FITTING/WELDING OF GUIDE BOLTS AND STIFFENING PLATES AND NOZZLES IN THE BOTTOM PLATE MAG20 | Fri Jun 10 08:00:00 IDT 2022 | Sun Jun 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2734 | TT_TASK | ASSEMBLING AND WELDING OF CONDENSER NECK WALLS AND NECK BRACING MAG20 | Fri Jun 10 08:00:00 IDT 2022 | Sat Jul 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2735 | TT_TASK | ASSEMBLING AND WELDING OF NOZZLES INTO THE STEAM DOME MAG20 | Sun Jul 10 08:00:00 IDT 2022 | Sat Jul 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2736 | TT_TASK | INSTALLING AND WELDING OF SEISMIC TIE-DOWNS MAG20 | Mon Jun 20 08:00:00 IDT 2022 | Thu Jun 23 17:00:00 IDT 2022 |  |  | 72.0 | NOT_STARTED
2737 | TT_TASK | VACUUM TEST WATER SIDE MAG20 | Sun Jul 03 08:00:00 IDT 2022 | Sat Jul 09 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2738 | TT_TASK | CHECKING THE CORROSION PROTECTION OF THE COOLING WATER SPACES MAG20 | Sun Jul 17 08:00:00 IDT 2022 | Tue Jul 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2739 | TT_TASK | CONNECTION AND WELDING OF REAR COVER MAG20 | Sat Jul 30 08:00:00 IDT 2022 | Fri Aug 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2741 | TT_TASK | FITTING AND BOLTING OF FRONT AND REAR COVER WITH SEAL MAG20 | Wed Jul 20 08:00:00 IDT 2022 | Fri Jul 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2742 | TT_TASK | ASSEMBLING AND WELDING OF THE CONDENSER NECK STRUCTURE ON BYPASS STEAM REGION MAG20 | Mon Aug 15 08:00:00 IDT 2022 | Wed Aug 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2743 | TT_TASK | CIRCULATING WATER SIDE LEAK TEST MAG20 | Sat Aug 06 08:00:00 IDT 2022 | Fri Aug 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2744 | TT_TASK | FITTING OF CONDENSER TO LP TURBINE MAG20 | Mon Aug 29 08:00:00 IDT 2022 | Sun Sep 11 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2745 | TT_TASK | WELDING OF CONDENSER TO LP TURBINE MAG20 | Mon Sep 12 08:00:00 IDT 2022 | Tue Sep 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2746 | TT_TASK | FINAL WORKS AND CLEANING MAG20 | Wed Sep 28 08:00:00 IDT 2022 | Sun Oct 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2747 | TT_TASK | FINAL INSPECTION MAG20 | Mon Oct 03 08:00:00 IDT 2022 | Wed Oct 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2748 | TT_TASK | INSULATION CONDENSER MAG20 | Thu Oct 06 08:00:00 IDT 2022 | Wed Nov 16 17:00:00 IST 2022 |  |  | 1216.0 | NOT_STARTED
2749 | TT_TASK | ELECTRICAL ERECTION CONDENSER MAG20 | Thu Oct 06 08:00:00 IDT 2022 | Wed Nov 02 17:00:00 IST 2022 |  |  | 1328.0 | NOT_STARTED
2751 | TT_TASK | PREPARATION OF BYPASS STATION INSTALLATION | Thu Jul 14 08:00:00 IDT 2022 | Fri Jul 15 17:00:00 IDT 2022 |  |  | 48.0 | NOT_STARTED
2752 | TT_TASK | ASSEMBLY AND WELDING OF CONDENSATE DRAIN TANK MAG | Thu May 19 08:00:00 IDT 2022 | Sun May 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2755 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES MAG | Fri Jun 17 08:00:00 IDT 2022 | Thu Dec 01 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2756 | TT_TASK | INSULATION PIPES / VALVES FOR CONDENSATION SYSTEM MAG | Fri Dec 02 08:00:00 IST 2022 | Thu Jan 05 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2757 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES MAG50 | Sun Jun 12 08:00:00 IDT 2022 | Sat Aug 20 17:00:00 IDT 2022 |  |  | 776.0 | NOT_STARTED
2758 | TT_TASK | INSULATION PIPES / VALVES FOR CONDENSATION SYSTEM MAG50 | Sat Nov 26 08:00:00 IST 2022 | Fri Dec 30 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2759 | TT_TASK | ELECTRICAL ERECTION / VALVES MAG | Fri Dec 30 08:00:00 IST 2022 | Thu Jan 05 17:00:00 IST 2023 |  |  | 816.0 | NOT_STARTED
2760 | TT_TASK | ELECTRICAL ERECTION / VALVES MAG50 | Sat Dec 24 08:00:00 IST 2022 | Fri Dec 30 17:00:00 IST 2022 |  |  | 864.0 | NOT_STARTED
2762 | TT_TASK | COLD COMMISSIONING CONDENSING/ ST DRAIN SYSTEM MAG/MAL | Wed Apr 26 08:00:00 IDT 2023 | Fri Apr 28 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2763 | TT_TASK | TRANSPORT AIR REMOVAL SYSTEM 20MAJ | Tue Mar 15 08:00:00 IST 2022 | Mon May 09 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2765 | TT_TASK | ERECTION VACUUM PUMP UNIT MAJ | Sun Jun 05 08:00:00 IDT 2022 | Sat Jun 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2766 | TT_TASK | PLACING, ALIGNMENT AND GROUTING MAJ-SKID (VACUUM-PUMPS) | Sun Jun 05 08:00:00 IDT 2022 | Tue Jun 07 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2768 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES MAJ | Sun Jun 12 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2769 | TT_TASK | INSULATION PIPES / VALVES FOR STEAM SYSTEM MAJ | Sun Jul 24 08:00:00 IDT 2022 | Sat Aug 27 17:00:00 IDT 2022 |  |  | 816.0 | NOT_STARTED
2770 | TT_TASK | ELECTRICAL ERECTION PIPES / VALVES MAJ | Thu Dec 08 08:00:00 IST 2022 | Wed Dec 21 17:00:00 IST 2022 |  |  | 936.0 | NOT_STARTED
2771 | TT_TASK | ELECTRICAL ERECTION VACUUM PUMP UNIT MAJ | Thu Dec 08 08:00:00 IST 2022 | Wed Dec 21 17:00:00 IST 2022 |  |  | 712.0 | NOT_STARTED
2773 | TT_TASK | COLD COMMISSIONING ST EVACUATION SYSTEM BEFORE TURNING GEAR MAJ | Wed Jun 07 08:00:00 IDT 2023 | Sun Jun 11 17:00:00 IDT 2023 |  |  | 64.0 | NOT_STARTED
2775 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MODULE 20MAL00YC | Fri Apr 15 08:00:00 IDT 2022 | Thu Apr 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2776 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES MAL | Mon Oct 10 08:00:00 IDT 2022 | Sun Nov 20 17:00:00 IST 2022 |  |  | 40.0 | NOT_STARTED
2777 | TT_TASK | INSULATION PIPES / VALVES FOR STEAM SYSTEM MAL | Sat Nov 26 08:00:00 IST 2022 | Fri Dec 30 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2778 | TT_TASK | ELECTRICAL ERECTION PIPES / VALVES MAL | Sat Dec 17 08:00:00 IST 2022 | Fri Dec 30 17:00:00 IST 2022 |  |  | 864.0 | NOT_STARTED
2780 | TT_TASK | COLD COMMISSIONING ST DRAIN SYSTEM MAL | Sun Jun 18 08:00:00 IDT 2023 | Mon Jun 26 17:00:00 IDT 2023 |  |  | 48.0 | NOT_STARTED
2781 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES MAM | Mon Sep 26 08:00:00 IDT 2022 | Sun Nov 06 17:00:00 IST 2022 |  |  | 152.0 | NOT_STARTED
2782 | TT_TASK | INSULATION PIPES / VALVES FOR STEAM SYSTEM MAM | Sat Nov 26 08:00:00 IST 2022 | Fri Dec 30 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2783 | TT_TASK | ELECTRICAL ERECTION PIPES / VALVES MAM | Sat Dec 31 08:00:00 IST 2022 | Fri Jan 13 17:00:00 IST 2023 |  |  | 752.0 | NOT_STARTED
2784 | TT_TASK | INSTALLATION BYPASS-STATION MAN (incl. VALVES AND PIPES) UmleitdampfeinfÃ¼hrung | Fri Jul 22 08:00:00 IDT 2022 | Thu Aug 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2785 | TT_TASK | FLOATING OF BYPASS STATION MAN Einschwimmen, etc. MAG20 | Fri Aug 05 08:00:00 IDT 2022 | Sun Aug 14 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2787 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES MAN | Thu Dec 01 08:00:00 IST 2022 | Wed Feb 08 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2788 | TT_TASK | INSULATION PIPES / VALVES MAN | Thu Feb 09 08:00:00 IST 2023 | Wed Mar 01 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2789 | TT_TASK | ELECTRICAL ERECTION PIPES / VALVES MAN | Thu Mar 02 08:00:00 IST 2023 | Wed Mar 22 17:00:00 IST 2023 |  |  | 208.0 | NOT_STARTED
2791 | TT_TASK | COLD COMMISSIONING ST BYPASS SYSTEM MAN | Sat Jun 17 08:00:00 IDT 2023 | Mon Jun 26 17:00:00 IDT 2023 |  |  | 224.0 | NOT_STARTED
2792 | TT_TASK | MANUFACTURING / SHOP TEST LUBE OIL 20MAV90 TANK | Mon Dec 13 08:00:00 IST 2021 | Sat Oct 15 17:00:00 IDT 2022 | Mon Dec 13 08:00:00 IST 2021 |  |  | IN_PROGRESS
2793 | TT_TASK | TRANSPORT LUBE OIL MODULE 20MAV | Sat Apr 30 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2794 | TT_TASK | TRANSPORT LUBE OIL 20MAV90 TANK | Mon Nov 21 08:00:00 IST 2022 | Sun Jan 15 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2795 | TT_TASK | ERECTION LUBE OIL MODULE UMC 20MAV | Thu Aug 04 08:00:00 IDT 2022 | Wed Aug 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2799 | TT_TASK | PREPARATION FOR PIPE CLEANING SYSTEM (ST) | Mon Nov 28 08:00:00 IST 2022 | Sun Dec 18 17:00:00 IST 2022 |  |  | 24.0 | NOT_STARTED
2800 | TT_TASK | ERECTION OF TEMPORARIES FOR LUBE OIL FLUSHING | Sun Feb 05 08:00:00 IST 2023 | Sat Feb 18 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2801 | TT_TASK | FILLING LUBE OIL TANK MAV | Sun Feb 19 08:00:00 IST 2023 | Tue Feb 21 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2802 | TT_TASK | TEST RUN OF LUBE OIL PUMPS | Wed Feb 22 08:00:00 IST 2023 | Thu Feb 23 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2803 | TT_TASK | ERECTION LUBE OIL 20MAV90 TANK | Mon Jan 16 08:00:00 IST 2023 | Wed Jan 18 17:00:00 IST 2023 |  |  | 1016.0 | NOT_STARTED
2804 | TT_TASK | LUBE OIL FLUSHING (INCL. PRESSURE TESTS) ST | Wed Feb 22 08:00:00 IST 2023 | Tue Mar 14 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2805 | TT_TASK | ERECTION, NDT PIPES / VALVES MAV | Mon Sep 26 08:00:00 IDT 2022 | Sun Nov 27 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2806 | TT_TASK | INSULATION PIPES / VALVES MAV | Mon Nov 28 08:00:00 IST 2022 | Sun Dec 25 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2807 | TT_TASK | ELECTRICAL ERECTION FOR MAV MODUL | Mon Oct 03 08:00:00 IDT 2022 | Sun Oct 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2808 | TT_TASK | CONSTR. POWER SUPPLY AVAIL. FOR LIFTING OIL SYSTEM 20MAV | Mon Oct 17 08:00:00 IDT 2022 | Sun Oct 30 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2809 | TT_TASK | ELECTRICAL ERECTION / VALVES MAV | Mon Dec 26 08:00:00 IST 2022 | Sun Jan 01 17:00:00 IST 2023 |  |  | 1184.0 | NOT_STARTED
2811 | TT_TASK | COLD COMMISSIONING LUBE AND LIFTING OIL SYSTEM INCL. GEN AND GT | Tue May 30 08:00:00 IDT 2023 | Mon Jun 19 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2814 | TT_TASK | TRANSPORT GLAND STEAM CONDENSER 20MAW | Tue May 03 08:00:00 IDT 2022 | Mon Jun 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2816 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MODULE MAW10Y | Fri Apr 15 08:00:00 IDT 2022 | Thu Apr 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2817 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MODULE 20MAW50Y | Fri Apr 15 08:00:00 IDT 2022 | Thu Apr 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2818 | TT_TASK | MECHANICAL ERECTION SEAL/LEAK STEAM SYSTEM MAW | Tue Jun 28 08:00:00 IDT 2022 | Mon Jul 11 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2820 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES MAW | Mon Sep 26 08:00:00 IDT 2022 | Sun Dec 18 17:00:00 IST 2022 |  |  | 488.0 | NOT_STARTED
2821 | TT_TASK | INSULATION PIPES / VALVES FOR STEAM SYSTEM MAW | Sat Feb 18 08:00:00 IST 2023 | Fri Mar 24 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2822 | TT_TASK | ELECTRICAL ERECTION SEAL/LEAK STEAM SYSTEM MAW | Thu Dec 08 08:00:00 IST 2022 | Wed Dec 21 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2823 | TT_TASK | ELECTRICAL ERECTION PIPES / VALVES MAW | Sat Mar 18 08:00:00 IST 2023 | Fri Mar 24 17:00:00 IDT 2023 |  |  | 176.0 | NOT_STARTED
2825 | TT_TASK | COLD COMMISSIONING ST GLAND/ LEAKAGE STEAM SYSTEM BEFORE TURNING GEAR MAW | Tue Apr 18 08:00:00 IDT 2023 | Fri May 05 17:00:00 IDT 2023 |  |  | 360.0 | NOT_STARTED
2826 | TT_TASK | TRANSPORT ST HYDRAULIC SYSTEM 20MAX | Sat Apr 30 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2828 | TT_TASK | ERECTION HYDRAULIC SYSTEM MAX | Fri Sep 09 08:00:00 IDT 2022 | Thu Sep 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2830 | TT_TASK | PIPE CLEANING CONTROL OIL SYSTEM MAX | Thu Feb 16 08:00:00 IST 2023 | Wed Feb 22 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2832 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES MAX | Thu Jan 12 08:00:00 IST 2023 | Wed Feb 15 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2833 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES MAX BEFORE ST CONNECTION AVAILABLE | Fri Nov 11 08:00:00 IST 2022 | Thu Dec 01 17:00:00 IST 2022 |  |  | 328.0 | NOT_STARTED
2834 | TT_TASK | INSULATION PIPES / VALVES MAX | Thu Feb 16 08:00:00 IST 2023 | Wed Mar 08 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2835 | TT_TASK | ELECTRICAL ERECTION HYDRAULIC SYSTEM MAX | Thu Dec 22 08:00:00 IST 2022 | Wed Jan 04 17:00:00 IST 2023 |  |  | 1224.0 | NOT_STARTED
2836 | TT_TASK | ELECTRICAL ERECTION PIPES / VALVES MAX | Thu Mar 09 08:00:00 IST 2023 | Wed Mar 15 17:00:00 IST 2023 |  |  | 664.0 | NOT_STARTED
2838 | TT_TASK | COLD COMMISSIONING ST HYDRAULIC SYSTEM MAX | Wed Jun 07 08:00:00 IDT 2023 | Fri Jun 16 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2840 | TT_TASK | ST PROTECTION | Thu Jun 15 08:00:00 IDT 2023 | Wed Jun 21 17:00:00 IDT 2023 |  |  | 40.0 | NOT_STARTED
2844 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION GAS TURBINE 20MB- | Sat Apr 09 08:00:00 IDT 2022 | Fri Apr 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2845 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - GT INTERCONNECTING PIPING 20MB- | Sat May 21 08:00:00 IDT 2022 | Fri Jun 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2846 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION GT ACCESSORY EQUIPMENT MB | Wed Jun 01 08:00:00 IDT 2022 | Tue Jun 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2847 | TT_TASK | TRANSFER / PREPARATION LIFT / SKID SYSTEM FOR GT20 | Sat Jul 23 08:00:00 IDT 2022 | Fri Jul 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2849 | TT_TASK | TRANSPORT INTERCONNECTING PIPING 20MB- | Sat Jun 11 08:00:00 IDT 2022 | Sun Jul 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2850 | TT_TASK | TRANSPORT GT ACCESSORY EQUIPMENT MB | Wed Jun 29 08:00:00 IDT 2022 | Tue Aug 23 17:00:00 IDT 2022 |  |  | 288.0 | NOT_STARTED
2854 | TT_TASK | PREPARATION FOUNDATION / INSTALL SUPPORT & BEAM GT20 | Sat Jul 16 08:00:00 IDT 2022 | Fri Jul 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2859 | TT_TASK | ERECTION GT AUXILIARIES 20MB- | Thu Aug 25 08:00:00 IDT 2022 | Wed Oct 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2862 | TT_TASK | FURTHER ASSEMBLY / PIPING / INSULATION GT20 | Thu Aug 04 08:00:00 IDT 2022 | Wed Sep 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2865 | TT_TASK | PRE-ALIGN AND FIX GT20 | Fri Aug 12 08:00:00 IDT 2022 | Thu Aug 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2866 | TT_TASK | INSULATION / COMPLETE ERECTION GT20 - BEFORE BURNERS INSTALLATION | Thu Sep 29 08:00:00 IDT 2022 | Wed Nov 02 17:00:00 IST 2022 |  |  | 8.0 | NOT_STARTED
2868 | TT_TASK | BURNERS INSTALLATION ERECTION GT20 | Mon Oct 17 08:00:00 IDT 2022 | Sun Nov 13 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2869 | TT_TASK | INSULATION / COMPLETE ERECTION GT20 - AFTER BURNERS INSTALLATION | Mon Nov 14 08:00:00 IST 2022 | Sun Dec 04 17:00:00 IST 2022 |  |  | 136.0 | NOT_STARTED
2870 | TT_TASK | FINAL INSPECTIONS & CLOSING OF OPEN ITEMS BEFORE COMMISSIONING GT20 MB | Wed Feb 01 08:00:00 IST 2023 | Tue Mar 14 17:00:00 IST 2023 |  |  | 344.0 | NOT_STARTED
2871 | TT_TASK | RESTORATION & PRESSURE TESTS AFTER OIL FLUSHING | Wed Mar 15 08:00:00 IST 2023 | Tue Apr 04 17:00:00 IDT 2023 |  |  | 576.0 | NOT_STARTED
2872 | TT_TASK | ERECTION, NDT, PT / VALVES 20MB (BOP) | Mon Oct 24 08:00:00 IDT 2022 | Sun Jan 01 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2873 | TT_TASK | INSULATION PIPES / VALVES 20MB (BOP) | Mon Jan 02 08:00:00 IST 2023 | Sun Jan 29 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2874 | TT_TASK | ELECTRICAL TEMPORARIES FOR OIL FLUSHING GT20 | Tue Feb 14 08:00:00 IST 2023 | Mon Feb 20 17:00:00 IST 2023 |  |  | 8.0 | NOT_STARTED
2875 | TT_TASK | INSTALLATION EMERGENCY PUSH BUTTON GT20 | Sun Feb 12 08:00:00 IST 2023 | Sat Feb 18 17:00:00 IST 2023 |  |  | 536.0 | NOT_STARTED
2876 | TT_TASK | INSTALLATION OF HEAT TRACING GT20 | Thu Sep 29 08:00:00 IDT 2022 | Wed Oct 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2877 | TT_TASK | ELECTRICAL ERECTION FOR PIPE CLEANING SYSTEM (GT20) | Thu Oct 20 08:00:00 IDT 2022 | Wed Nov 02 17:00:00 IST 2022 |  |  | 888.0 | NOT_STARTED
2878 | TT_TASK | ELECTRICAL ERECTION / VALVES 20MB (BOP) | Mon Jan 30 08:00:00 IST 2023 | Sun Feb 05 17:00:00 IST 2023 |  |  | 640.0 | NOT_STARTED
2879 | TT_TASK | ELECTRICAL ERECTION / VALVES 20MB | Mon Feb 06 08:00:00 IST 2023 | Sun Feb 19 17:00:00 IST 2023 |  |  | 528.0 | NOT_STARTED
2880 | TT_TASK | COLD COMMISSIONING GT AUXILIARIES 20MB- | Thu Jun 22 08:00:00 IDT 2023 | Wed Jun 28 17:00:00 IDT 2023 |  |  | 16.0 | NOT_STARTED
2883 | TT_TASK | COLD COMMISSIONING GT20 SYSTEMS MBA 20MBP | Thu May 18 08:00:00 IDT 2023 | Wed May 24 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2886 | TT_TASK | SAFETY VALVES TESTING, 1ST. BASELOAD GT20 | Mon Jul 03 08:00:00 IDT 2023 | Tue Jul 04 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2889 | TT_TASK | FULL SPEED NO LOAD GT20 | Sat Jul 01 08:00:00 IDT 2023 | Sat Jul 01 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2893 | TT_TASK | CONTRACT REVIEW / PREP. RFQ WASH WATER TANK 20MBA | Wed May 05 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 | Wed May 05 08:00:00 IDT 2021 | Tue Jun 01 17:00:00 IDT 2021 |  | COMPLETED
2894 | TT_TASK | QUOTATION STAGE WASH WATER TANK 20MBA | Wed Jun 02 08:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 | Wed Jun 02 08:00:00 IDT 2021 | Wed Sep 15 17:00:00 IDT 2021 |  | COMPLETED
2897 | TT_TASK | DETAIL DESIGN WASH WATER TANK 20MBA | Thu Sep 16 08:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Thu Sep 16 08:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  | COMPLETED
2900 | TT_TASK | PROCURMENT / PRE-FABRICATION WASH WATER TANK 20MBA | Sat Oct 09 08:00:00 IDT 2021 | Tue May 31 17:00:00 IDT 2022 | Sat Oct 09 08:00:00 IDT 2021 |  |  | IN_PROGRESS
2901 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION WASH WATER TANK 20MBA | Wed Jun 01 08:00:00 IDT 2022 | Tue Jun 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2902 | TT_TASK | TRANSPORT GT WASH WATER TANK 20MBA | Wed Jun 29 08:00:00 IDT 2022 | Thu Jul 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2903 | TT_TASK | TRANSPORT GAS TURBINE 20MB- | Sat Apr 30 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2904 | TT_TASK | TRANSPORT GT SUPPORTS 20MB- | Sat Apr 30 08:00:00 IDT 2022 | Fri Jun 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2906 | TT_TASK | TRANSPORT GT INSULATION PART 1 MB- (GERMANY) | Sat Apr 30 08:00:00 IDT 2022 | Fri Jun 24 17:00:00 IDT 2022 |  |  | 232.0 | NOT_STARTED
2907 | TT_TASK | TRANSPORT GT INSULATION PART 2 MB- (THAILAND) | Thu May 12 08:00:00 IDT 2022 | Fri Jun 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2908 | TT_TASK | LOWER, ALIGN & FIX GT20 / INST. INTERMEDIATE SHAFT | Thu Aug 04 08:00:00 IDT 2022 | Wed Aug 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2909 | TT_TASK | PRELIMINARY ALIGNMENT / COUPLING OF SHAFT GT20 | Fri Aug 26 08:00:00 IDT 2022 | Thu Sep 08 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2911 | TT_TASK | ERECTION, NDT, PT / VALVES 20MBA | Mon Oct 24 08:00:00 IDT 2022 | Sun Jan 01 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2912 | TT_TASK | INSULATION PIPES / VALVES 20MBA | Mon Jan 02 08:00:00 IST 2023 | Sun Feb 05 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2913 | TT_TASK | ERECTION WASH WATER TANK 20MBA | Mon Oct 17 08:00:00 IDT 2022 | Sun Oct 30 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2915 | TT_TASK | ERECTION, NDT, PT / VALVES HCO 20MBA51/54/MBV (BOP FOR LUBE OIL FLUSHING) | Mon Oct 17 08:00:00 IDT 2022 | Sun Nov 27 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2918 | TT_TASK | COLD COMMISSIONING GT20 INCLUDING COMBUSTION CHAMBER | Thu Apr 27 08:00:00 IDT 2023 | Wed Jun 21 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2922 | TT_TASK | COLD COMMISSIONING GT20 BLOW OFF SYSTEM MBA4x | Thu Jun 22 08:00:00 IDT 2023 | Wed Jun 28 17:00:00 IDT 2023 |  |  | 16.0 | NOT_STARTED
2923 | TT_TASK | AIR DISTRIBUTION TEST 20MKA | Sun Jul 02 08:00:00 IDT 2023 | Sun Jul 02 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2926 | TT_TASK | COLD COMMISSIONING TURBINE COOLING SYSTEM 20MBH | Thu Jun 22 08:00:00 IDT 2023 | Wed Jun 28 17:00:00 IDT 2023 |  |  | 16.0 | NOT_STARTED
2927 | TT_TASK | PLACING 20MKC01/20MBJ01-TRANSFORMER (on UBG01/02) | Wed Aug 31 08:00:00 IDT 2022 | Thu Sep 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2928 | TT_TASK | PLACING 20MKC02-TRANSFORMER (on UBG03) | Sat Jul 09 08:00:00 IDT 2022 | Sat Jul 09 17:00:00 IDT 2022 |  |  | 512.0 | NOT_STARTED
2929 | TT_TASK | TRANSPORT TURNING DEVICE 20MBK | Sat Apr 30 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2930 | TT_TASK | TRANSPORT AIR INTAKE SYSTEM 20MBL(Upper/Lower Cone, Silencer/Weatherhoods, Plenum, Filter Modules) (QUINGDAO) | Tue Apr 26 08:00:00 IDT 2022 | Mon May 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2931 | TT_TASK | TRANSPORT AIR INTAKE SYSTEM 20MBL (Supporting Struct, Staircase, Platforms) (SHANGHAI) | Thu Jul 14 08:00:00 IDT 2022 | Wed Aug 10 17:00:00 IDT 2022 |  |  | 152.0 | NOT_STARTED
2932 | TT_TASK | TRANSPORT AIR INTAKE SYSTEM 20MBL - Filters (Container) (TURKEY) | Thu Jun 02 08:00:00 IDT 2022 | Wed Jul 27 17:00:00 IDT 2022 |  |  | 472.0 | NOT_STARTED
2933 | TT_TASK | TRANSPORT AIR INTAKE SYSTEM 20MBL- Several Items (4 containers) (HAMBURG) | Thu May 12 08:00:00 IDT 2022 | Wed Jul 06 17:00:00 IDT 2022 |  |  | 640.0 | NOT_STARTED
2934 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION AIR INTAKE SYSTEM 20MBL (HAMBURG) | Thu Apr 28 08:00:00 IDT 2022 | Wed May 11 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2937 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION AIR INTAKE SYSTEM 20MBL (TURKEY) | Thu May 19 08:00:00 IDT 2022 | Wed Jun 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2939 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION AIR INTAKE SYSTEM 20MBL (Supporting Struct, Staircase, Platforms) (SHANGHAI) | Thu Jun 30 08:00:00 IDT 2022 | Wed Jul 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2940 | TT_TASK | PLACING GT AIR INTAKE LOWER PART 20MBL | Tue Jun 21 08:00:00 IDT 2022 | Thu Jun 23 17:00:00 IDT 2022 |  |  | 328.0 | NOT_STARTED
2941 | TT_TASK | PRE-ASSEMBLY GT AIR INTAKE MBL LOWER PART & INNER CONE BEFORE GT 20 | Tue May 24 08:00:00 IDT 2022 | Fri Jun 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2942 | TT_TASK | ERECTION AIR INTAKE DUCT INCL: SUPPORT STRUCTURE 20MBL | Tue Aug 30 08:00:00 IDT 2022 | Mon Oct 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2943 | TT_TASK | ERECTION FILTERHOUSE 20MBL | Sun Sep 25 08:00:00 IDT 2022 | Sat Nov 26 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2944 | TT_TASK | ERECTION AIR INTAKE SILENCER BAFFELS 20MBL | Sun Nov 27 08:00:00 IST 2022 | Sat Dec 10 17:00:00 IST 2022 |  |  | 88.0 | NOT_STARTED
2945 | TT_TASK | PREFABRICATION BEFORE ERECTION FILTERHOUSE 20MBL | Sun Jun 19 08:00:00 IDT 2022 | Sat Jul 09 17:00:00 IDT 2022 |  |  | 616.0 | NOT_STARTED
2946 | TT_TASK | E- AND I&C- ERECTION AIR INTAKE SYSTEM 20MBL | Sun Dec 11 08:00:00 IST 2022 | Sat Jan 07 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2948 | TT_TASK | COLD COMMISSIONING AIR INTAKE SYSTEM UNIT 20MBL | Thu Jun 08 08:00:00 IDT 2023 | Wed Jun 14 17:00:00 IDT 2023 |  |  | 8.0 | NOT_STARTED
2949 | TT_TASK | TRANSPORT GT FUEL GAS STRAINER SKID MBP | Sat Jun 25 08:00:00 IDT 2022 | Thu Aug 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2951 | TT_TASK | ERECTION FUEL GAS STRAINER SKID MBP | Thu Aug 25 08:00:00 IDT 2022 | Wed Sep 14 17:00:00 IDT 2022 |  |  | 864.0 | NOT_STARTED
2953 | TT_TASK | ERECTION, NDT, PT / VALVES IGN. GAS PIPES 20MBQ | Mon Jan 02 08:00:00 IST 2023 | Sun Mar 05 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2954 | TT_TASK | INSULATION PIPES / VALVES FOR STEAM SYSTEM 20MBQ | Mon Feb 27 08:00:00 IST 2023 | Sun Mar 26 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
2955 | TT_TASK | ELECTRICAL ERECTION / VALVES IGN. GAS PIPES 20MBQ | Mon Mar 20 08:00:00 IST 2023 | Sun Mar 26 17:00:00 IDT 2023 |  |  | 248.0 | NOT_STARTED
2956 | TT_TASK | BD - SUBMISSION & APPROVAL - EXHAUST DIFFUSER FRAME 20MBR | Wed Jul 14 08:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 | Wed Jul 14 08:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  | COMPLETED
2957 | TT_TASK | BD - APPROVAL AWARD EXHAUST DIFFUSER FRAME 20MBR | Sun Sep 12 08:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 | Sun Sep 12 08:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  | COMPLETED
2958 | TT_TASK | DETAIL DESIGN EXHAUST DIFFUSER FRAME 20MBR | Thu May 13 08:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 | Thu May 13 08:00:00 IDT 2021 | Tue Jul 13 17:00:00 IDT 2021 |  | COMPLETED
2959 | TT_TASK | TRANSPORT DIFFUSOR 20MBR | Wed Mar 23 08:00:00 IST 2022 | Thu Apr 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2961 | TT_TASK | TRANSPORT EXPANSION JOINT 20MBR | Wed Mar 23 08:00:00 IST 2022 | Wed Jun 15 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2963 | TT_TASK | ASSEMBLY MAIN PIECES PF DIFFUSER / WELDING SHELLS | Fri Apr 22 08:00:00 IDT 2022 | Thu Jun 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2964 | TT_TASK | INTERMEDIATE ALIGNMENT / PLACING AND WELDING EXPANSION JOINT TO DIFFUSER 20MBR | Fri Sep 09 08:00:00 IDT 2022 | Thu Sep 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2965 | TT_TASK | WELDING / INSULATION / TOUCH-UP DIFFUSOR 20MBR (before GT final position) | Fri Jun 03 08:00:00 IDT 2022 | Thu Jun 30 17:00:00 IDT 2022 |  |  | 448.0 | NOT_STARTED
2966 | TT_TASK | FINISH WORKS / INSULATION/ TOUCH-UP DIFFUSER 20MBR | Fri Sep 23 08:00:00 IDT 2022 | Thu Oct 06 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2967 | TT_TASK | INSTALLATION CABLE TRAYS DIFFUSER 20MBR | Fri Oct 07 08:00:00 IDT 2022 | Thu Oct 20 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2968 | TT_TASK | ELECTRICAL INSTALLATION OF EXHAUST GAS SYSTEM DIFFUSER 20MBR | Fri Oct 21 08:00:00 IDT 2022 | Thu Nov 03 17:00:00 IST 2022 |  |  | 1392.0 | NOT_STARTED
2970 | TT_TASK | COLD COMMISSIONING EXHAUST DIFFUSER 20MBR | Thu Jun 08 08:00:00 IDT 2023 | Wed Jun 14 17:00:00 IDT 2023 |  |  | 8.0 | NOT_STARTED
2973 | TT_TASK | BASIC DESIGN / PREP. LUBE OIL TRANSFER SYSTEMS MBV90 | Fri Feb 05 08:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 | Fri Feb 05 08:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 |  | COMPLETED
2974 | TT_TASK | QUOTATION STAGE LUBE OIL TRANSFER SYSTEMS MBV90 | Fri Apr 09 08:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 | Fri Apr 09 08:00:00 IDT 2021 | Thu Jun 03 17:00:00 IDT 2021 |  | COMPLETED
2978 | TT_TASK | DETAIL DESIGN LUBE OIL TRANSFER SYSTEMS MBV90 | Fri Jun 04 08:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 | Fri Jun 04 08:00:00 IDT 2021 | Wed Sep 29 17:00:00 IDT 2021 |  | COMPLETED
2980 | TT_TASK | MANUFACTURING / SHOP TEST LUBE OIL TRANSFER SYSTEMS MBV90 | Mon Dec 13 08:00:00 IST 2021 | Sun May 01 17:00:00 IDT 2022 | Mon Dec 13 08:00:00 IST 2021 |  |  | IN_PROGRESS
2981 | TT_TASK | BD - SUBMISSION & APPROVAL CLEAN / DIRTY OIL TANK MBV90 | Thu Sep 30 08:00:00 IDT 2021 | Sun Dec 12 17:00:00 IST 2021 | Thu Sep 30 08:00:00 IDT 2021 | Sun Dec 12 17:00:00 IST 2021 |  | COMPLETED
2983 | TT_TASK | TRANSPORT LUBE OIL TRANSFER SYSTEMS MBV90 | Mon May 30 08:00:00 IDT 2022 | Sun Jul 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2985 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION LUBE OIL TRANSFER SYSTEMS MBV90 | Mon May 02 08:00:00 IDT 2022 | Sun May 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
2986 | TT_TASK | MECHANICAL ERECTION CLEAN/DIRTY OIL TANK MBV90 | Mon Sep 12 08:00:00 IDT 2022 | Sun Nov 13 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2988 | TT_TASK | OIL FLUSHING GT20 | Wed Feb 22 08:00:00 IST 2023 | Tue Mar 14 17:00:00 IST 2023 |  |  |  | NOT_STARTED
2990 | TT_TASK | PREPARATION FOR PIPE CLEANING SYSTEM (GT20) | Mon Nov 21 08:00:00 IST 2022 | Sun Dec 11 17:00:00 IST 2022 |  |  | 576.0 | NOT_STARTED
2991 | TT_TASK | MECHANICAL ERECTION LUBE OIL TRANSFER PUMPS MBV90 | Mon Oct 10 08:00:00 IDT 2022 | Sun Nov 06 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2993 | TT_TASK | ERECTION,NDT,PT LUBE OIL TRANSFER PIPING MBV90 | Mon Oct 24 08:00:00 IDT 2022 | Sun Dec 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
2994 | TT_TASK | ELECTRICAL ERECTION CLEAN/DIRTY OIL TANK MBV90 | Mon Dec 05 08:00:00 IST 2022 | Sun Dec 11 17:00:00 IST 2022 |  |  | 1320.0 | NOT_STARTED
2995 | TT_TASK | ELECTRICAL ERECTION LUBE OIL TRANSFER PUMPS MBV90 | Mon Nov 07 08:00:00 IST 2022 | Sun Dec 04 17:00:00 IST 2022 |  |  | 1376.0 | NOT_STARTED
2996 | TT_TASK | ELECTRICAL ERECTION LUBE OIL TRANSFER PIPING MBV90 | Mon Dec 05 08:00:00 IST 2022 | Sun Jan 01 17:00:00 IST 2023 |  |  | 1152.0 | NOT_STARTED
2999 | TT_TASK | COLD COMMISSIONING LUBE OIL TRANSFER SYSTEM MBV90 | Fri May 26 08:00:00 IDT 2023 | Thu Jun 22 17:00:00 IDT 2023 |  |  | 64.0 | NOT_STARTED
3000 | TT_TASK | COLD COMMISSIONING OIL MODULE 20MBV (INCL: FLUSHING) | Thu Jun 01 08:00:00 IDT 2023 | Wed Jun 07 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3001 | TT_TASK | ERECTION MBX INSTRUMENT AIR SKID TANK | Thu Aug 25 08:00:00 IDT 2022 | Wed Sep 14 17:00:00 IDT 2022 |  |  | 1792.0 | NOT_STARTED
3002 | TT_TASK | TRANSPORT MBX INSTRUMENT AIR SKID TANK | Sat May 07 08:00:00 IDT 2022 | Sat Jul 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3003 | TT_TASK | ERECTION HYDRAULIC CLEARANCE OPTIMIZATION SKID MBA | Tue Aug 23 08:00:00 IDT 2022 | Mon Sep 12 17:00:00 IDT 2022 |  |  | 272.0 | NOT_STARTED
3004 | TT_TASK | ERECTION HYDRAULIC SKID MBX | Tue Aug 23 08:00:00 IDT 2022 | Mon Sep 12 17:00:00 IDT 2022 |  |  | 328.0 | NOT_STARTED
3006 | TT_TASK | COLD COMMISSIONING GT20 PNEUMATIC SYSTEM MBX21 | Thu Jun 22 08:00:00 IDT 2023 | Wed Jun 28 17:00:00 IDT 2023 |  |  | 16.0 | NOT_STARTED
3008 | TT_TASK | COLD COMMISSIONING GT HYDRAULIC OIL SYSTEM 20MBX | Tue May 09 08:00:00 IDT 2023 | Mon May 15 17:00:00 IDT 2023 |  |  | 16.0 | NOT_STARTED
3009 | TT_TASK | GT PROTECTION GT20 | Fri Jun 23 08:00:00 IDT 2023 | Sun Jun 25 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3010 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION SEAL OIL SYSTEM MKW | Thu Apr 21 08:00:00 IDT 2022 | Wed May 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3012 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CO2 EVAPORATOR MK | Wed May 18 08:00:00 IDT 2022 | Tue Jun 14 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3016 | TT_TASK | TRANSPORT CO2 EVAPORATOR MK | Wed Jun 15 08:00:00 IDT 2022 | Tue Aug 09 17:00:00 IDT 2022 |  |  | 352.0 | NOT_STARTED
3018 | TT_TASK | TRANSPORT GEN. 20MKA | Sat Jun 25 08:00:00 IDT 2022 | Thu Aug 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3020 | TT_TASK | TRANSPORT GENERATOR FOUNDATION PLATES 20MKA | Sat Apr 30 08:00:00 IDT 2022 | Fri Jun 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3022 | TT_TASK | FIRST GROUTING OF FIXATORS MKA | Thu Jul 14 08:00:00 IDT 2022 | Wed Jul 20 17:00:00 IDT 2022 |  |  | 232.0 | NOT_STARTED
3023 | TT_TASK | GROUTING ANCHOR BOLTS MKA | Tue Jan 24 08:00:00 IST 2023 | Mon Jan 30 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3024 | TT_TASK | GROUTING OF SLIPRING BASEPLATES MKA | Sat Feb 25 08:00:00 IST 2023 | Wed Mar 01 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3025 | TT_TASK | CHECK AND PREPARATION OF FOUNDATION MKA | Thu Jul 07 08:00:00 IDT 2022 | Wed Jul 20 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3030 | TT_TASK | FINAL ALIGNMENT OF SLIPRING SET MKA | Wed Feb 15 08:00:00 IST 2023 | Sun Feb 19 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3031 | TT_TASK | PREPARATION AND PLACING GENERATOR ON FOUNDATION MKA | Thu Jul 21 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  | 208.0 | NOT_STARTED
3032 | TT_TASK | ALIGNMENT OF GENERATOR AND SLIPRING SHAFT TO STEAM TURBINE MKA | Sat Aug 27 08:00:00 IDT 2022 | Thu Sep 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3033 | TT_TASK | FIXING OF GENERATOR IN POSITION MKA | Fri Sep 09 08:00:00 IDT 2022 | Thu Sep 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3039 | TT_TASK | SET UP EQUIPMENT ON SITE, SET UP SITE STORES GENERATOR MKA | Tue Jun 07 08:00:00 IDT 2022 | Mon Jun 13 17:00:00 IDT 2022 |  |  | 184.0 | NOT_STARTED
3041 | TT_TASK | GENERATOR COMPLETE ERECTION (SLIPRING, BEARINGS, SHAFT SEALING; BEARING BRACKET OIL SEALS; GROUNDING BRUSHES) MKA | Sun Mar 05 08:00:00 IST 2023 | Mon Apr 17 17:00:00 IDT 2023 |  |  | 56.0 | NOT_STARTED
3042 | TT_TASK | MEASUREMENT OF AXIAL ALIGNMENT OF SHAFT TO ST MKA | Sun Jan 22 08:00:00 IST 2023 | Mon Jan 23 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3043 | TT_TASK | ALIGNMENT OF GENERATOR TO GAS TURBINE MKA | Sat Aug 20 08:00:00 IDT 2022 | Thu Aug 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3044 | TT_TASK | MEASUREMENT OF AXIAL ALIGNMENT OF SHAFT TO GT MKA | Fri Aug 26 08:00:00 IDT 2022 | Sat Aug 27 17:00:00 IDT 2022 |  |  | 1192.0 | NOT_STARTED
3045 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20MKA | Mon Sep 05 08:00:00 IDT 2022 | Sun Dec 18 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3046 | TT_TASK | INSULATION PIPES / VALVES GENERATOR 20MKA | Mon Dec 19 08:00:00 IST 2022 | Sun Jan 22 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3047 | TT_TASK | INSTALLING OF HIGH VOLTAGE BUSHINGS MKA | Fri Sep 02 08:00:00 IDT 2022 | Sat Sep 03 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3048 | TT_TASK | PLACING OF GENERATOR SKIDS MKA | Fri Aug 19 08:00:00 IDT 2022 | Thu Sep 08 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3049 | TT_TASK | GENERATOR TO FIXATORS MKA | Fri Sep 02 08:00:00 IDT 2022 | Sun Sep 04 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3051 | TT_TASK | PREPARATION OF FOUNDATION FOR SLIPRING MKA | Sun Jul 24 08:00:00 IDT 2022 | Thu Jul 28 17:00:00 IDT 2022 |  |  | 56.0 | NOT_STARTED
3052 | TT_TASK | PREASSEMBLING OF SLIPRING BASEPLATE MKA | Fri Aug 12 08:00:00 IDT 2022 | Wed Aug 17 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3053 | TT_TASK | PREASSEMBLING OF SLIPRING SET MKA | Thu Aug 18 08:00:00 IDT 2022 | Mon Aug 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3055 | TT_TASK | FINAL COUPLING OF SLIPRING SHAFT MKA | Thu Mar 02 08:00:00 IST 2023 | Mon Mar 06 17:00:00 IST 2023 |  |  | 392.0 | NOT_STARTED
3056 | TT_TASK | FINAL ASSEMBLING OF SLIPRING SET MKA | Mon Feb 20 08:00:00 IST 2023 | Sat Mar 04 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3057 | TT_TASK | TEMPORARY COUPLING AND SWING CHECK OF SLIPRING SHAFT OF SLIPRING SET MKA | Fri Sep 02 08:00:00 IDT 2022 | Sat Sep 03 17:00:00 IDT 2022 |  |  | 1200.0 | NOT_STARTED
3058 | TT_TASK | ERECTION OF SLIPRING SET MKA | Tue Aug 23 08:00:00 IDT 2022 | Fri Aug 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3059 | TT_TASK | FINISH INSTALLATION OF SLIPRING SET MKA | Wed Feb 01 08:00:00 IST 2023 | Tue Feb 14 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3060 | TT_TASK | E- AND I&C- INSTALLATION (INCL.EARTHING / STARPOINT TRANSFORMER) GEN 20 | Mon Nov 07 08:00:00 IST 2022 | Sun Nov 27 17:00:00 IST 2022 |  |  | 1184.0 | NOT_STARTED
3063 | TT_TASK | ELECTRICAL ERECTION / VALVES GENERATOR 20MKA | Mon Jan 23 08:00:00 IST 2023 | Sun Jan 29 17:00:00 IST 2023 |  |  | 680.0 | NOT_STARTED
3065 | TT_TASK | COLD COMMISSIONING GENERATOR INCL. BEARING SYSTEM 20MKA/MKD | Tue May 02 08:00:00 IDT 2023 | Mon Jun 05 17:00:00 IDT 2023 |  |  | 80.0 | NOT_STARTED
3066 | TT_TASK | PREPARATION FOR VENTILATION TEST (COMM. DEPT.) MKA | Fri Jun 30 08:00:00 IDT 2023 | Sun Jul 02 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3067 | TT_TASK | VENTILATION TEST AT 3000 rpm (COMM. DEPT.) -after first ignition- MKA | Mon Jul 03 08:00:00 IDT 2023 | Tue Jul 04 17:00:00 IDT 2023 |  |  | 40.0 | NOT_STARTED
3068 | TT_TASK | INSPECTION AFTER VENTILATION TEST (COMM. DEPT.) MKA | Mon Jul 10 08:00:00 IDT 2023 | Thu Jul 13 17:00:00 IDT 2023 |  |  | 144.0 | NOT_STARTED
3069 | TT_TASK | AIR LEAKAGE TEST GENERATOR 20MKA | Fri Jun 16 08:00:00 IDT 2023 | Thu Jun 22 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3070 | TT_TASK | START UP TEST WITH MBJ 20MBA | Mon Jun 26 08:00:00 IDT 2023 | Wed Jun 28 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3071 | TT_TASK | GT GENERATOR PROTECTION TEST 20MKA | Sat Jul 01 08:00:00 IDT 2023 | Sun Jul 02 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3073 | TT_TASK | SYSTEM CHECKS 20MBA | Thu Jun 29 08:00:00 IDT 2023 | Fri Jun 30 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3075 | TT_TASK | TRANSPORT TRANSFORMERS 20MKC/MBJ | Sat Apr 30 08:00:00 IDT 2022 | Fri Jun 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3076 | TT_TASK | ERECTION MKC05 SLIP RING STRUCTURE MKC20 | Fri Sep 09 08:00:00 IDT 2022 | Thu Sep 22 17:00:00 IDT 2022 |  |  | 24.0 | NOT_STARTED
3080 | TT_TASK | ERECTION GENERATOR STATOR WATER SYSTEM 20MKF | Fri Oct 07 08:00:00 IDT 2022 | Thu Oct 20 17:00:00 IDT 2022 |  |  | 208.0 | NOT_STARTED
3081 | TT_TASK | PIPING ERECTION GENERATOR STATOR WATER SYSTEM 20MKF | Wed Nov 16 08:00:00 IST 2022 | Tue Jan 31 17:00:00 IST 2023 |  |  | 664.0 | NOT_STARTED
3083 | TT_TASK | TRANSPORT GAS COOLING SUPPLY SYSTEM 20MKG | Sat Apr 30 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3085 | TT_TASK | ERECTION GAS COOLING SUPPLY SYSTEM 20MKG | Fri Sep 23 08:00:00 IDT 2022 | Thu Oct 06 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3086 | TT_TASK | PIPING GAS COOLING SUPPLY SYSTEM 20MKG | Wed Oct 19 08:00:00 IDT 2022 | Tue Jan 03 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3088 | TT_TASK | TRANSPORT EXHAUST GAS SYSTEM FOR GENERATOR 20MKQ | Sat Apr 30 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3090 | TT_TASK | ERECTION EXHAUST GAS SYSTEM FOR GENERATOR 20MKQ | Fri Sep 09 08:00:00 IDT 2022 | Thu Sep 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3091 | TT_TASK | PIPING ERECTION EXHAUST GAS SYSTEM FOR GENERATOR 20MKQ | Fri Sep 23 08:00:00 IDT 2022 | Thu Dec 08 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3093 | TT_TASK | TRANSPORT SEAL OIL SYSTEM 20MKW | Sun May 29 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3095 | TT_TASK | TRANSPORT SEAL OIL TANK TO MODULE SKIDDER 20MKW | Fri Oct 29 08:00:00 IDT 2021 | Thu Dec 23 17:00:00 IST 2021 | Fri Oct 29 08:00:00 IDT 2021 | Thu Dec 23 17:00:00 IST 2021 |  | COMPLETED
3096 | TT_TASK | ERECTION SEAL OIL SYSTEM 20MKW | Fri Aug 19 08:00:00 IDT 2022 | Thu Sep 08 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3097 | TT_TASK | FINAL ERECTION MKW PIPING AFTER OIL FLUSHING MKW | Wed Mar 15 08:00:00 IST 2023 | Tue Mar 21 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3098 | TT_TASK | PIPING ERECTION SEAL OIL SYSTEM FOR GENERATOR 20MKW | Fri Sep 09 08:00:00 IDT 2022 | Thu Nov 03 17:00:00 IST 2022 |  |  | 1104.0 | NOT_STARTED
3100 | TT_TASK | COLD COMMISSIONING GEN SEAL OIL SYSTEM (COMM OIL FLUSHING) | Thu Jun 08 08:00:00 IDT 2023 | Wed Jun 14 17:00:00 IDT 2023 |  |  | 8.0 | NOT_STARTED
3101 | TT_TASK | TRANSPORT ENCLOSURE 20MPB | Sat May 28 08:00:00 IDT 2022 | Fri Jul 22 17:00:00 IDT 2022 |  |  | 608.0 | NOT_STARTED
3102 | TT_TASK | TRANSPORT STEEL WORK ENCLOSURE 20MPB | Thu Jul 14 08:00:00 IDT 2022 | Thu Sep 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3103 | TT_TASK | ERECTION OF ENCLOSURE 20MPB | Fri Oct 07 08:00:00 IDT 2022 | Thu Nov 24 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3104 | TT_TASK | ERECTION OF STEELWORK FOR ENCLOSURE 20MPB | Fri Sep 09 08:00:00 IDT 2022 | Thu Sep 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3105 | TT_TASK | ELECTRICAL ERECTION WORK FOR GT ENCLOSURE 20MPB / SAM | Fri Dec 09 08:00:00 IST 2022 | Thu Dec 22 17:00:00 IST 2022 |  |  | 1224.0 | NOT_STARTED
3106 | TT_TASK | PRESSURE TEST PAB / 20PAH | Sat Apr 08 08:00:00 IDT 2023 | Fri Apr 14 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3110 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION BACK WASH STRAINER 20PAA11 | Wed Jun 29 08:00:00 IDT 2022 | Tue Jul 26 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3112 | TT_TASK | ERECTION BACK WASH STRAINER 20PAA11 | Tue Oct 25 08:00:00 IDT 2022 | Mon Nov 21 17:00:00 IST 2022 |  |  | 336.0 | NOT_STARTED
3113 | TT_TASK | PREPARATION RFQ COOLING TOWER COARSE SCREEN 20PAA (MPA) | Wed Jul 14 08:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 | Wed Jul 14 08:00:00 IDT 2021 | Tue Aug 03 17:00:00 IDT 2021 |  | COMPLETED
3114 | TT_TASK | QUOTATION STAGE COOLING TOWER COARSE SCREEN 20PAA (MPA) | Wed Aug 04 08:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Wed Aug 04 08:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  | COMPLETED
3116 | TT_TASK | DETAIL DESIGN / MANUFACTURING COOLING TOWER COARSE SCREEN 20PAA (MPA) | Wed Sep 29 08:00:00 IDT 2021 | Tue May 31 17:00:00 IDT 2022 | Wed Sep 29 08:00:00 IDT 2021 |  |  | IN_PROGRESS
3119 | TT_TASK | TRANSPORT COOLING TOWER COARSE SCREEN 20PAA | Wed Jul 06 08:00:00 IDT 2022 | Tue Aug 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3121 | TT_TASK | TRANSPORT COOLING TOWER COARSE SCREEN TO PORT OF EXPORT 20PAA | Wed Jun 29 08:00:00 IDT 2022 | Tue Jul 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3122 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION COOLING TOWER COARSE SCREEN 20PAA | Wed Jun 01 08:00:00 IDT 2022 | Tue Jun 28 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3123 | TT_TASK | ERECTION COOLING TOWER COARSE SCREEN 20PAA | Wed Sep 07 08:00:00 IDT 2022 | Tue Oct 11 17:00:00 IDT 2022 |  |  | 1480.0 | NOT_STARTED
3124 | TT_TASK | COLD COMMISSIONING COOLING TOWER COARSE SCREEN AND STOPLOGS 20PAA | Sat Apr 15 08:00:00 IDT 2023 | Fri Apr 28 17:00:00 IDT 2023 |  |  | 152.0 | NOT_STARTED
3125 | TT_TASK | FABRICATION / DETAIL DESIGN PIPING SYSTEM (OUTSIDE) 20PAB | Mon Mar 15 08:00:00 IST 2021 | Sun Apr 11 17:00:00 IDT 2021 | Mon Mar 15 08:00:00 IST 2021 | Sun Apr 11 17:00:00 IDT 2021 |  | COMPLETED
3126 | TT_TASK | MANUFACTURING PIPING SYSTEM (OUTSIDE) 20PAB | Sun Mar 28 08:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 | Sun Mar 28 08:00:00 IDT 2021 | Sat Jun 26 17:00:00 IDT 2021 |  | COMPLETED
3127 | TT_TASK | TRANSPORT PIPING SYSTEM (OUTSIDE) 20PAB (FIRST DELIVERY) | Thu May 27 08:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 | Thu May 27 08:00:00 IDT 2021 | Wed Jul 07 17:00:00 IDT 2021 |  | COMPLETED
3128 | TT_TASK | TRANSPORT PIPING SYSTEM (OUTSIDE) 20PAB (LAST DELIVERY) | Sun Jun 27 08:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 | Sun Jun 27 08:00:00 IDT 2021 | Sat Aug 21 17:00:00 IDT 2021 |  | COMPLETED
3129 | TT_TASK | PRESSURE TEST 20PAB20-PIPES OUTSIDE | Sun Dec 19 08:00:00 IST 2021 | Sun Mar 13 17:00:00 IST 2022 | Sun Dec 19 08:00:00 IST 2021 |  |  | IN_PROGRESS
3130 | TT_TASK | BACKFILLING OF SHEET PILE PIPING SYSTEM (OUTSIDE) PAB UMC - URD | Sun Dec 19 08:00:00 IST 2021 | Mon Mar 14 17:00:00 IST 2022 | Sun Dec 19 08:00:00 IST 2021 |  | 840.0 | IN_PROGRESS
3135 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL1 | Sat Nov 13 08:00:00 IST 2021 | Mon Nov 15 17:00:00 IST 2021 | Sat Nov 13 08:00:00 IST 2021 | Mon Nov 15 17:00:00 IST 2021 |  | COMPLETED
3136 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL2,3 | Mon Sep 27 08:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Mon Sep 27 08:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  | COMPLETED
3137 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL4 | Thu Sep 23 08:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Thu Sep 23 00:00:00 IDT 2021 | Sat Sep 25 00:00:00 IDT 2021 |  | COMPLETED
3138 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL5 | Thu Sep 23 08:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Thu Sep 23 00:00:00 IDT 2021 | Fri Sep 24 00:00:00 IDT 2021 |  | COMPLETED
3139 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL6,7,8 | Sat Aug 07 08:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Sat Aug 07 08:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 |  | COMPLETED
3140 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL9 | Mon Sep 27 08:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 | Mon Sep 27 08:00:00 IDT 2021 | Tue Sep 28 17:00:00 IDT 2021 |  | COMPLETED
3141 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL10 | Wed Sep 29 08:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 | Wed Sep 29 08:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 |  | COMPLETED
3142 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL11 | Sat Oct 02 08:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 | Sat Oct 02 08:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 |  | COMPLETED
3143 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL12 | Thu Sep 30 08:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 | Thu Sep 30 08:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 |  | COMPLETED
3144 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL13 | Mon Sep 27 08:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 | Mon Sep 27 08:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 |  | COMPLETED
3145 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL14 INCLD. LAMINATION | Fri Oct 15 08:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 | Fri Oct 15 08:00:00 IDT 2021 | Wed Oct 20 17:00:00 IDT 2021 |  | COMPLETED
3146 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL16 | Thu Sep 30 08:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 | Thu Sep 30 08:00:00 IDT 2021 | Thu Oct 07 17:00:00 IDT 2021 |  | COMPLETED
3147 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL17 | Fri Oct 08 08:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 | Fri Oct 08 08:00:00 IDT 2021 | Sat Oct 09 17:00:00 IDT 2021 |  | COMPLETED
3148 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL18 | Mon Oct 11 08:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 | Mon Oct 11 08:00:00 IDT 2021 | Tue Oct 12 17:00:00 IDT 2021 |  | COMPLETED
3149 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL19 | Wed Oct 13 08:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 | Wed Oct 13 08:00:00 IDT 2021 | Thu Oct 14 17:00:00 IDT 2021 |  | COMPLETED
3150 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL20,21 | Fri Oct 15 08:00:00 IDT 2021 | Sat Oct 16 17:00:00 IDT 2021 | Fri Oct 15 08:00:00 IDT 2021 | Sat Oct 16 17:00:00 IDT 2021 |  | COMPLETED
3151 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL22,23 | Mon Oct 18 08:00:00 IDT 2021 | Tue Oct 19 17:00:00 IDT 2021 | Mon Oct 18 08:00:00 IDT 2021 | Tue Oct 19 17:00:00 IDT 2021 |  | COMPLETED
3152 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL24 | Wed Oct 20 08:00:00 IDT 2021 | Thu Oct 21 17:00:00 IDT 2021 | Wed Oct 20 08:00:00 IDT 2021 | Thu Oct 21 17:00:00 IDT 2021 |  | COMPLETED
3153 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL26 | Tue Nov 02 08:00:00 IST 2021 | Wed Nov 03 17:00:00 IST 2021 | Tue Nov 02 08:00:00 IST 2021 | Wed Nov 03 17:00:00 IST 2021 |  | COMPLETED
3154 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-SPOOL27,28,29 | Tue Nov 30 08:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 | Tue Nov 30 08:00:00 IST 2021 | Wed Dec 01 17:00:00 IST 2021 |  | COMPLETED
3155 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 01,02 | Wed Nov 03 08:00:00 IST 2021 | Sat Nov 27 17:00:00 IST 2021 | Wed Nov 03 08:00:00 IST 2021 | Sat Nov 27 17:00:00 IST 2021 |  | COMPLETED
3156 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 02,03 | Tue Aug 31 08:00:00 IDT 2021 | Wed Sep 01 17:00:00 IDT 2021 | Tue Aug 31 08:00:00 IDT 2021 | Wed Sep 01 17:00:00 IDT 2021 |  | COMPLETED
3157 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 06,07 | Fri Aug 06 08:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Fri Aug 06 08:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 |  | COMPLETED
3158 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 07,08 | Wed Aug 04 08:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 | Wed Aug 04 08:00:00 IDT 2021 | Fri Sep 10 17:00:00 IDT 2021 |  | COMPLETED
3159 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 20,21 | Wed Sep 29 08:00:00 IDT 2021 | Mon Oct 11 17:00:00 IDT 2021 | Wed Sep 29 08:00:00 IDT 2021 | Mon Oct 11 17:00:00 IDT 2021 |  | COMPLETED
3160 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 22,23 | Wed Sep 29 08:00:00 IDT 2021 | Mon Oct 11 17:00:00 IDT 2021 | Wed Sep 29 08:00:00 IDT 2021 | Mon Oct 11 17:00:00 IDT 2021 |  | COMPLETED
3161 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 25,26 | Tue Oct 12 08:00:00 IDT 2021 | Tue Nov 02 17:00:00 IST 2021 | Tue Oct 12 08:00:00 IDT 2021 | Tue Nov 02 17:00:00 IST 2021 |  | COMPLETED
3162 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 27-28 | Thu Oct 21 08:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 | Thu Oct 21 08:00:00 IDT 2021 | Thu Oct 28 00:00:00 IDT 2021 |  | COMPLETED
3163 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB41-LAMINATION SPOOL 28-29 | Thu Oct 21 08:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 | Thu Oct 21 00:00:00 IDT 2021 | Thu Oct 28 00:00:00 IDT 2021 |  | COMPLETED
3166 | TT_TASK | PAB BACKFILLING (APPROX. UP TO PIPE AXISOR PIPE CROWN LEVEL) | Sun Sep 05 08:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 | Sun Sep 05 08:00:00 IDT 2021 | Sat Oct 30 17:00:00 IDT 2021 |  | COMPLETED
3169 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL1 | Fri Nov 19 08:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 | Fri Nov 19 08:00:00 IST 2021 | Sat Nov 20 17:00:00 IST 2021 |  | COMPLETED
3170 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20 -SPOOL2,3,4 | Wed Aug 25 08:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 | Wed Aug 25 08:00:00 IDT 2021 | Thu Aug 26 17:00:00 IDT 2021 |  | COMPLETED
3171 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL5 | Mon Aug 30 08:00:00 IDT 2021 | Sat Sep 25 17:00:00 IDT 2021 | Mon Aug 30 08:00:00 IDT 2021 | Sat Sep 25 17:00:00 IDT 2021 |  | COMPLETED
3172 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL6 | Mon Aug 30 08:00:00 IDT 2021 | Sat Sep 25 17:00:00 IDT 2021 | Mon Aug 30 08:00:00 IDT 2021 | Sat Sep 25 17:00:00 IDT 2021 |  | COMPLETED
3173 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL7,8,9 | Fri Jul 30 08:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Fri Jul 30 08:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
3174 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL10 | Tue Aug 31 08:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 | Tue Aug 31 08:00:00 IDT 2021 | Fri Sep 03 17:00:00 IDT 2021 |  | COMPLETED
3175 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL11 | Thu Sep 02 08:00:00 IDT 2021 | Sat Sep 04 17:00:00 IDT 2021 | Thu Sep 02 08:00:00 IDT 2021 | Sat Sep 04 17:00:00 IDT 2021 |  | COMPLETED
3176 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL12 | Sat Sep 04 08:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 | Sat Sep 04 08:00:00 IDT 2021 | Tue Sep 07 17:00:00 IDT 2021 |  | COMPLETED
3177 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL13 | Sat Sep 04 08:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 | Sat Sep 04 08:00:00 IDT 2021 | Fri Sep 24 17:00:00 IDT 2021 |  | COMPLETED
3178 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL14 | Tue Sep 28 08:00:00 IDT 2021 | Sat Oct 16 17:00:00 IDT 2021 | Tue Sep 28 08:00:00 IDT 2021 | Sat Oct 16 17:00:00 IDT 2021 |  | COMPLETED
3179 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL15 INCLD. LAMINATION | Tue Oct 26 08:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 | Tue Oct 26 08:00:00 IDT 2021 | Thu Nov 04 17:00:00 IST 2021 |  | COMPLETED
3180 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL16 | Thu Oct 21 08:00:00 IDT 2021 | Sat Oct 23 17:00:00 IDT 2021 | Thu Oct 21 08:00:00 IDT 2021 | Mon Oct 25 00:00:00 IDT 2021 |  | COMPLETED
3181 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL17 | Wed Sep 29 08:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 | Wed Sep 29 08:00:00 IDT 2021 | Wed Oct 06 17:00:00 IDT 2021 |  | COMPLETED
3182 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL18 | Sat Oct 09 08:00:00 IDT 2021 | Mon Oct 11 17:00:00 IDT 2021 | Sat Oct 09 08:00:00 IDT 2021 | Mon Oct 11 17:00:00 IDT 2021 |  | COMPLETED
3183 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL19 | Tue Oct 12 08:00:00 IDT 2021 | Wed Oct 13 17:00:00 IDT 2021 | Tue Oct 12 08:00:00 IDT 2021 | Wed Oct 13 17:00:00 IDT 2021 |  | COMPLETED
3184 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL20 | Thu Oct 14 08:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 | Thu Oct 14 08:00:00 IDT 2021 | Fri Oct 15 17:00:00 IDT 2021 |  | COMPLETED
3185 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL21,22,23 | Fri Nov 12 08:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 | Fri Nov 12 08:00:00 IST 2021 | Sat Nov 13 17:00:00 IST 2021 |  | COMPLETED
3186 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL24 | Tue Oct 26 08:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 | Tue Oct 26 08:00:00 IDT 2021 | Wed Oct 27 17:00:00 IDT 2021 |  | COMPLETED
3187 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL25 INCLD. LAMINATION | Fri Nov 12 08:00:00 IST 2021 | Mon Nov 15 17:00:00 IST 2021 | Fri Nov 12 08:00:00 IST 2021 | Mon Nov 15 17:00:00 IST 2021 |  | COMPLETED
3188 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL29&31 | Mon Nov 29 08:00:00 IST 2021 | Tue Nov 30 17:00:00 IST 2021 | Mon Nov 29 08:00:00 IST 2021 | Tue Nov 30 17:00:00 IST 2021 |  | COMPLETED
3189 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL30 | Thu Dec 16 08:00:00 IST 2021 | Sat Dec 18 17:00:00 IST 2021 | Thu Dec 16 08:00:00 IST 2021 | Sat Dec 18 17:00:00 IST 2021 |  | COMPLETED
3190 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL32 | Mon Nov 29 08:00:00 IST 2021 | Tue Nov 30 17:00:00 IST 2021 | Mon Nov 29 08:00:00 IST 2021 | Tue Nov 30 17:00:00 IST 2021 |  | COMPLETED
3191 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL33 | Thu Dec 09 08:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 | Thu Dec 09 08:00:00 IST 2021 | Fri Dec 10 17:00:00 IST 2021 |  | COMPLETED
3192 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL1,2 | Fri Nov 19 08:00:00 IST 2021 | Fri Nov 26 17:00:00 IST 2021 | Fri Nov 19 08:00:00 IST 2021 | Fri Nov 26 17:00:00 IST 2021 |  | COMPLETED
3193 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 2,3 | Sat Aug 28 08:00:00 IDT 2021 | Mon Sep 27 17:00:00 IDT 2021 | Sat Aug 28 08:00:00 IDT 2021 | Mon Sep 27 17:00:00 IDT 2021 |  | COMPLETED
3194 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 3,4 | Sat Aug 28 08:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 | Sat Aug 28 08:00:00 IDT 2021 | Thu Sep 23 17:00:00 IDT 2021 |  | COMPLETED
3195 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 7,8 | Mon Jul 19 08:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Mon Jul 19 08:00:00 IDT 2021 | Mon Aug 30 00:00:00 IDT 2021 |  | COMPLETED
3196 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 8,9 | Sat Jul 24 08:00:00 IDT 2021 | Sat Aug 28 17:00:00 IDT 2021 | Sat Jul 24 08:00:00 IDT 2021 | Mon Aug 30 00:00:00 IDT 2021 |  | COMPLETED
3197 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 21,22 | Sat Oct 16 08:00:00 IDT 2021 | Tue Oct 19 17:00:00 IDT 2021 | Sat Oct 16 08:00:00 IDT 2021 | Tue Oct 19 17:00:00 IDT 2021 |  | COMPLETED
3198 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 22,23 | Fri Nov 05 08:00:00 IST 2021 | Thu Nov 11 17:00:00 IST 2021 | Fri Nov 05 08:00:00 IST 2021 | Thu Nov 11 17:00:00 IST 2021 |  | COMPLETED
3199 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-SPOOL26 INCLD. LAMINATION | Mon Nov 01 08:00:00 IST 2021 | Tue Nov 02 17:00:00 IST 2021 | Mon Nov 01 08:00:00 IST 2021 | Tue Nov 02 17:00:00 IST 2021 |  | COMPLETED
3200 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 29-31 | Fri Nov 12 08:00:00 IST 2021 | Sat Nov 27 17:00:00 IST 2021 | Fri Nov 12 08:00:00 IST 2021 | Sat Nov 27 17:00:00 IST 2021 |  | COMPLETED
3201 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 32-31 | Thu Dec 09 08:00:00 IST 2021 | Mon Dec 13 17:00:00 IST 2021 | Thu Dec 09 08:00:00 IST 2021 | Mon Dec 13 17:00:00 IST 2021 |  | COMPLETED
3202 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20-LAMINATION SPOOL 33-31 | Sat Dec 11 08:00:00 IST 2021 | Wed Dec 15 17:00:00 IST 2021 | Sat Dec 11 08:00:00 IST 2021 | Wed Dec 15 17:00:00 IST 2021 |  | COMPLETED
3203 | TT_TASK | BACKFILLING TO 0,5m BEFORE PAB INSTALLATION | Thu Jul 15 08:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 | Thu Jul 15 08:00:00 IDT 2021 | Sat Jul 31 17:00:00 IDT 2021 |  | COMPLETED
3204 | TT_TASK | ERECTION PIPING SYSTEM (OUTSIDE) 20PAB20- SPOOL 2/3/4 CONNECTION + ALIGN | Tue Sep 28 08:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 | Tue Sep 28 08:00:00 IDT 2021 | Tue Oct 05 17:00:00 IDT 2021 |  | COMPLETED
3205 | TT_TASK | PRESSURE TEST 20PAB41-PIPES OUTSIDE | Wed Dec 15 08:00:00 IST 2021 | Fri Jan 07 17:00:00 IST 2022 | Wed Dec 15 08:00:00 IST 2021 | Fri Jan 07 17:00:00 IST 2022 |  | COMPLETED
3206 | TT_TASK | ERECTION, NDT, PT / VALVES (MECHANICAL) 20PAB UMC | Sat Aug 13 08:00:00 IDT 2022 | Fri Sep 09 17:00:00 IDT 2022 |  |  | 72.0 | NOT_STARTED
3207 | TT_TASK | ERECTION, NDT, PT / VALVES (MECHANICAL) 20PAB URD | Thu Jun 30 08:00:00 IDT 2022 | Wed Aug 10 17:00:00 IDT 2022 |  |  | 992.0 | NOT_STARTED
3208 | TT_TASK | ERECTION, NDT, PT / VALVES (MECHANICAL) 20PAB01 TO PAC PUMPS | Thu Jun 30 08:00:00 IDT 2022 | Wed Aug 10 17:00:00 IDT 2022 |  |  | 768.0 | NOT_STARTED
3209 | TT_TASK | ELECTRICAL ERECTION / VALVES 20PAB | Tue Nov 15 08:00:00 IST 2022 | Mon Dec 12 17:00:00 IST 2022 |  |  | 984.0 | NOT_STARTED
3211 | TT_TASK | COLD COMMISSIONING COOLING WATER SYSTEMS PAB | Sat Apr 15 08:00:00 IDT 2023 | Fri May 19 17:00:00 IDT 2023 |  |  | 24.0 | NOT_STARTED
3214 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CIRC. CW PUMP 20PAC | Tue Apr 05 08:00:00 IDT 2022 | Mon May 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3215 | TT_TASK | TRANSPORT CIRC. CW PUMP 20PAC | Tue May 03 08:00:00 IDT 2022 | Wed Jun 01 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3217 | TT_TASK | ELECTRICAL ERECTION PAC/PSB-PUMPS | Fri Nov 18 08:00:00 IST 2022 | Thu Dec 15 17:00:00 IST 2022 |  |  | 784.0 | NOT_STARTED
3218 | TT_TASK | ERECTION CIRC. CW PUMP 20PAC | Thu Jun 16 08:00:00 IDT 2022 | Wed Aug 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3220 | TT_TASK | PROCUREMENT MATERIAL COOLING TOWER - FILL - 20PAD | Tue Jul 06 08:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 | Tue Jul 06 08:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 |  | COMPLETED
3221 | TT_TASK | PROCUREMENT MATERIAL COOLING TOWER - FRP - 20PAD | Tue Jul 06 08:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 | Tue Jul 06 08:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 |  | COMPLETED
3222 | TT_TASK | FABRICATION DESIGN COOLING TOWER - FILL - 20PAD | Tue Oct 05 08:00:00 IDT 2021 | Sun Jan 02 17:00:00 IST 2022 | Tue Oct 05 08:00:00 IDT 2021 | Sun Jan 02 17:00:00 IST 2022 |  | COMPLETED
3223 | TT_TASK | FABRICATION DESIGN COOLING TOWER - FRP - 20PAD | Tue Oct 05 08:00:00 IDT 2021 | Sun Jan 02 17:00:00 IST 2022 | Tue Oct 05 08:00:00 IDT 2021 | Sun Jan 02 17:00:00 IST 2022 |  | COMPLETED
3224 | TT_TASK | PROCUREMENT MATERIAL COOLING TOWER - NOISE ATT / PIPING / DRIFT ELIM - 20PAD | Tue Jul 06 08:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 | Tue Jul 06 08:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 |  | COMPLETED
3225 | TT_TASK | PROCUREMENT MATERIAL COOLING TOWER - WALKWAY - 20PAD | Tue Jul 06 08:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 | Tue Jul 06 08:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 |  | COMPLETED
3226 | TT_TASK | FABRICATION DESIGN COOLING TOWER - NOISE ATT / PIPING / DRIFT ELIM - 20PAD | Tue Oct 05 08:00:00 IDT 2021 | Mon Jan 03 17:00:00 IST 2022 | Tue Oct 05 08:00:00 IDT 2021 | Mon Jan 03 17:00:00 IST 2022 |  | COMPLETED
3227 | TT_TASK | FABRICATION DESIGN COOLING TOWER - WALKWAY - 20PAD | Tue Oct 05 08:00:00 IDT 2021 | Mon Jan 03 17:00:00 IST 2022 | Tue Oct 05 08:00:00 IDT 2021 | Mon Jan 03 17:00:00 IST 2022 |  | COMPLETED
3228 | TT_TASK | PROCUREMENT MATERIAL COOLING TOWER - DRY EQUIPMENT & ELECTRICAL - 20PAD | Tue Jul 06 08:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 | Tue Jul 06 08:00:00 IDT 2021 | Mon Oct 04 17:00:00 IDT 2021 |  | COMPLETED
3229 | TT_TASK | FABRICATION DESIGN COOLING TOWER - DRY EQUIPMENT & ELECTRICAL - 20PAD | Tue Oct 05 08:00:00 IDT 2021 | Mon Jan 03 17:00:00 IST 2022 | Tue Oct 05 08:00:00 IDT 2021 | Mon Jan 03 17:00:00 IST 2022 |  | COMPLETED
3230 | TT_TASK | PROCUREMENT MATERIAL COOLING TOWER - MECH. EQUIPMENT & FANSTACK - 20PAD | Tue Jul 06 08:00:00 IDT 2021 | Mon Nov 22 17:00:00 IST 2021 | Tue Jul 06 08:00:00 IDT 2021 | Mon Nov 22 17:00:00 IST 2021 |  | COMPLETED
3231 | TT_TASK | FABRICATION DESIGN COOLING TOWER - MECH. EQUIPMENT & FANSTACK - 20PAD | Tue Nov 23 08:00:00 IST 2021 | Mon Mar 28 17:00:00 IDT 2022 | Tue Nov 23 08:00:00 IST 2021 |  |  | IN_PROGRESS
3232 | TT_TASK | PROCUREMENT MATERIAL COOLING TOWER - VACUUM SKID & PIPING - 20PAD | Tue Jul 06 08:00:00 IDT 2021 | Mon Oct 18 17:00:00 IDT 2021 | Tue Jul 06 08:00:00 IDT 2021 | Mon Oct 18 17:00:00 IDT 2021 |  | COMPLETED
3233 | TT_TASK | FABRICATION DESIGN COOLING TOWER - VACUUM SKID & PIPING - 20PAD | Tue Oct 19 08:00:00 IDT 2021 | Mon Jan 31 17:00:00 IST 2022 | Tue Oct 19 08:00:00 IDT 2021 | Mon Jan 31 17:00:00 IST 2022 |  | COMPLETED
3236 | TT_TASK | MANUFACTURING COOLING TOWER - DRY EQUIPMENT & ELECTRICAL - 20PAD (EU) 20PAD DRY EQUIPMENT & ELECTRICAL BATCH 1 | Tue Jan 04 08:00:00 IST 2022 | Mon Sep 26 17:00:00 IDT 2022 | Tue Jan 04 08:00:00 IST 2022 |  |  | IN_PROGRESS
3237 | TT_TASK | MANUFACTURING COOLING TOWER - DRY EQUIPMENT & ELECTRICAL - (EU) 20PAD DRY EQUIPMENT BREAK BULK BATCH 2 | Tue Jan 04 08:00:00 IST 2022 | Mon Sep 26 17:00:00 IDT 2022 | Tue Jan 04 08:00:00 IST 2022 |  | 9728.0 | IN_PROGRESS
3238 | TT_TASK | DETAIL DESIGN COOLING TOWER EQUIPMENT 20PAD | Fri Feb 19 08:00:00 IST 2021 | Mon Jul 05 17:00:00 IDT 2021 | Fri Feb 19 08:00:00 IST 2021 | Mon Jul 05 17:00:00 IDT 2021 |  | COMPLETED
3241 | TT_TASK | MANUFACTURING COOLING TOWER - FILL - 20PAD | Mon Jan 03 08:00:00 IST 2022 | Sun Jun 26 17:00:00 IDT 2022 | Mon Jan 03 08:00:00 IST 2022 |  |  | IN_PROGRESS
3242 | TT_TASK | MANUFACTURING COOLING TOWER - FRP - 20PAD | Mon Jan 03 08:00:00 IST 2022 | Tue Jul 26 17:00:00 IDT 2022 | Mon Jan 03 08:00:00 IST 2022 |  |  | IN_PROGRESS
3243 | TT_TASK | MANUFACTURING COOLING TOWER - NOISE ATT / PIPING / DRIFT ELIM - 20PAD | Tue Jan 04 08:00:00 IST 2022 | Wed Jul 27 17:00:00 IDT 2022 | Tue Jan 04 08:00:00 IST 2022 |  |  | IN_PROGRESS
3244 | TT_TASK | MANUFACTURING COOLING TOWER - WALKWAY - 20PAD | Tue Jan 04 08:00:00 IST 2022 | Wed Jul 27 17:00:00 IDT 2022 | Tue Jan 04 08:00:00 IST 2022 |  |  | IN_PROGRESS
3245 | TT_TASK | MANUFACTURING COOLING TOWER - DRY EQUIPMENT & ELECTRICAL - 20PAD | Tue Jan 04 08:00:00 IST 2022 | Mon Sep 26 17:00:00 IDT 2022 | Tue Jan 04 08:00:00 IST 2022 |  |  | IN_PROGRESS
3246 | TT_TASK | MANUFACTURING COOLING TOWER - MECH. EQUIPMENT & FANSTACK - 20PAD | Tue Mar 29 08:00:00 IDT 2022 | Sun Nov 27 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3247 | TT_TASK | MANUFACTURING COOLING TOWER - VACUUM SKID & PIPING - 20PAD | Tue Feb 01 08:00:00 IST 2022 | Mon Sep 26 17:00:00 IDT 2022 | Tue Feb 01 08:00:00 IST 2022 |  |  | IN_PROGRESS
3275 | TT_TASK | TRANSPORT (EU) 20PAD FILL BATCH 1 | Sat Jun 11 08:00:00 IDT 2022 | Thu Aug 11 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3277 | TT_TASK | TRANSPORT (EU) 20PAD FILL BATCH 2 | Mon Jul 25 08:00:00 IDT 2022 | Sat Sep 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3279 | TT_TASK | TRANSPORT 20PAD FRP BATCH 1 | Sun Jul 24 08:00:00 IDT 2022 | Wed Aug 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3282 | TT_TASK | TRANSPORT 20PAD FRP BATCH 2 | Wed Aug 24 08:00:00 IDT 2022 | Sat Sep 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3284 | TT_TASK | TRANSPORT (EU) 20PAD NOISE ATT / PIPING / DRIFT ELIM BATCH 1 | Fri Jul 15 08:00:00 IDT 2022 | Wed Sep 14 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3285 | TT_TASK | TRANSPORT (EU) 20PAD NOISE ATT / PIPING / DRIFT ELIM BATCH 2 | Thu Aug 25 08:00:00 IDT 2022 | Tue Oct 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3288 | TT_TASK | TRANSPORT 20PAD WALKWAY BATCH 1 | Fri Jul 15 08:00:00 IDT 2022 | Wed Sep 14 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3290 | TT_TASK | TRANSPORT 20PAD WALKWAY BATCH 2 | Thu Aug 25 08:00:00 IDT 2022 | Tue Oct 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3293 | TT_TASK | TRANSPORT (EU) 20PAD DRY EQUIPMENT & ELECTRICAL BATCH 1 | Fri Sep 23 08:00:00 IDT 2022 | Wed Nov 23 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3294 | TT_TASK | TRANSPORT (EU) 20PAD DRY EQUIPMENT & ELECTRICAL BATCH 2 | Tue Oct 25 08:00:00 IDT 2022 | Sun Dec 25 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3295 | TT_TASK | TRANSPORT (EU) 20PAD MECH. EQUIPMENT & FANSTACK BATCH 1 | Thu Nov 24 08:00:00 IST 2022 | Tue Jan 24 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3296 | TT_TASK | TRANSPORT (EU) 20PAD MECH. EQUIPMENT & FANSTACK BATCH 2 | Mon Dec 26 08:00:00 IST 2022 | Sat Feb 25 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3300 | TT_TASK | TRANSPORT (EU) 20PAD VACUUM SKID & PIPING | Tue Oct 25 08:00:00 IDT 2022 | Sun Dec 25 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3301 | TT_TASK | TRANSPORT (EU) 20PAD DRY EQUIPMENT BREAK BULK BATCH 1 | Fri Sep 23 08:00:00 IDT 2022 | Fri Dec 16 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3302 | TT_TASK | TRANSPORT (EU) 20PAD DRY EQUIPMENT BREAK BULK BATCH 2 | Sat Oct 01 08:00:00 IDT 2022 | Sat Dec 24 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3305 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD FILL BATCH 1 | Sat May 14 08:00:00 IDT 2022 | Fri Jun 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3306 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD FILL BATCH 2 | Mon Jun 27 08:00:00 IDT 2022 | Sun Jul 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3307 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - 20PAD FRP BATCH 1 | Sun Jun 26 08:00:00 IDT 2022 | Sat Jul 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3308 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - 20PAD FRP BATCH 2 | Wed Jul 27 08:00:00 IDT 2022 | Tue Aug 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3309 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD NOISE ATT / PIPING / DRIFT ELIM BATCH 1 | Fri Jun 17 08:00:00 IDT 2022 | Thu Jul 14 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3310 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD NOISE ATT / PIPING / DRIFT ELIM BATCH 2 | Thu Jul 28 08:00:00 IDT 2022 | Wed Aug 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3311 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - 20PAD WALKWAY BATCH 1 | Fri Jun 17 08:00:00 IDT 2022 | Thu Jul 14 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3312 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - 20PAD WALKWAY BATCH 2 | Thu Jul 28 08:00:00 IDT 2022 | Wed Aug 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3313 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD DRY EQUIPMENT & ELECTRICAL BATCH 1 | Fri Aug 26 08:00:00 IDT 2022 | Thu Sep 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3314 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD DRY EQUIPMENT & ELECTRICAL BATCH 2 | Tue Sep 27 08:00:00 IDT 2022 | Mon Oct 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3315 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD MECH. EQUIPMENT & FANSTACK BATCH 1 | Thu Oct 27 08:00:00 IDT 2022 | Wed Nov 23 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3316 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD MECH. EQUIPMENT & FANSTACK BATCH 2 | Mon Nov 28 08:00:00 IST 2022 | Sun Dec 25 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3317 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD VACUUM SKID & PIPING | Tue Sep 27 08:00:00 IDT 2022 | Mon Oct 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3318 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD DRY EQUIPMENT BREAK BULK BATCH 1 | Fri Aug 26 08:00:00 IDT 2022 | Thu Sep 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3319 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - (EU) 20PAD DRY EQUIPMENT BREAK BULK BATCH 2 | Sat Sep 03 08:00:00 IDT 2022 | Fri Sep 30 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3320 | TT_TASK | MOBILISATION / MATERIAL UNLOADING | Fri Aug 12 08:00:00 IDT 2022 | Thu Aug 25 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3321 | TT_TASK | FILL PACK GLUEING FIRST 4 CELLS | Fri Aug 26 08:00:00 IDT 2022 | Thu Oct 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3322 | TT_TASK | DISTRIBUTION LATERAL PIPES FIRST 4 CELLS | Fri Oct 14 08:00:00 IDT 2022 | Thu Nov 17 17:00:00 IST 2022 |  |  | 168.0 | NOT_STARTED
3323 | TT_TASK | DRIFT ELIMINATION ASSEMBLY FIRST 4 CELLS | Fri Oct 14 08:00:00 IDT 2022 | Thu Nov 17 17:00:00 IST 2022 |  |  | 168.0 | NOT_STARTED
3324 | TT_TASK | INSTALLATION FILL PACKS SUPPORT FIRST 4 CELLS | Fri Sep 30 08:00:00 IDT 2022 | Thu Oct 20 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3325 | TT_TASK | AUXILIARY FRP STUCTURE INSTALLATION FIRST 4 CELLS | Fri Aug 26 08:00:00 IDT 2022 | Thu Sep 29 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3326 | TT_TASK | INSTALLATION OF FILL PACKS FIRST 4 CELLS | Fri Oct 21 08:00:00 IDT 2022 | Thu Dec 08 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3327 | TT_TASK | INSTALLATION OF DISTRIBUTION SYSTEM FIRST 4 CELLS | Fri Dec 09 08:00:00 IST 2022 | Thu Jan 26 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3328 | TT_TASK | INSTALLATION OF SOUND ABBATMENT SYSTEM FIRST 4 CELLS | Fri Oct 21 08:00:00 IDT 2022 | Thu Nov 24 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3329 | TT_TASK | INSTALLATION OF SUPPORT AND DRIFT ELIMINATOR FIRST 4 CELLS | Fri Jan 27 08:00:00 IST 2023 | Thu Mar 02 17:00:00 IST 2023 |  |  | 648.0 | NOT_STARTED
3330 | TT_TASK | INSTALLATION OF AIR MIX SYSTEM FIRST 4 CELLS | Fri Dec 09 08:00:00 IST 2022 | Thu Jan 26 17:00:00 IST 2023 |  |  | 928.0 | NOT_STARTED
3331 | TT_TASK | INSTALLATION OF INTERNAL WALKWAY FIRST 4 CELLS | Fri Dec 09 08:00:00 IST 2022 | Thu Jan 05 17:00:00 IST 2023 |  |  | 1096.0 | NOT_STARTED
3332 | TT_TASK | INSTALLATION OF MECHANICAL GROUP FIRST 4 CELLS | Fri Jan 27 08:00:00 IST 2023 | Thu Feb 23 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3333 | TT_TASK | INSTALLATION OF FAN STACK FIRST 4 CELLS | Fri Feb 17 08:00:00 IST 2023 | Thu Mar 23 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3334 | TT_TASK | INSTALLATION OF COIL BUNDLES AND SEALING FIRST 4 CELLS | Fri Nov 25 08:00:00 IST 2022 | Thu Dec 22 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3335 | TT_TASK | INSTALLATION OF VACUUM PIPE LINE FIRST 4 CELLS | Sat Jan 07 08:00:00 IST 2023 | Fri Feb 10 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3336 | TT_TASK | INSTALLATION OF VACUUM SKID FIRST 4 CELLS | Mon Dec 26 08:00:00 IST 2022 | Tue Dec 27 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3337 | TT_TASK | INSTALLATION OF DUMPERS WITH ACTUATORS FIRST 4 CELLS | Fri Dec 23 08:00:00 IST 2022 | Thu Jan 12 17:00:00 IST 2023 |  |  | 1040.0 | NOT_STARTED
3338 | TT_TASK | INSTALLATION OF PIPING DRY AREA FIRST 4 CELLS | Sat Feb 11 08:00:00 IST 2023 | Fri Mar 17 17:00:00 IST 2023 |  |  | 528.0 | NOT_STARTED
3341 | TT_TASK | FILL PACK GLUEING LAST 4 CELLS | Fri Sep 30 08:00:00 IDT 2022 | Thu Nov 17 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3342 | TT_TASK | AUXILIARY FRP STUCTURE INSTALLATION LAST 4 CELLS | Fri Sep 30 08:00:00 IDT 2022 | Thu Nov 03 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3344 | TT_TASK | INSTALLATION FILL PACKS SUPPORT LAST 4 CELLS | Fri Nov 04 08:00:00 IST 2022 | Thu Nov 24 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3345 | TT_TASK | DISTRIBUTION LATERAL PIPES LAST 4 CELLS | Fri Nov 18 08:00:00 IST 2022 | Thu Dec 22 17:00:00 IST 2022 |  |  | 168.0 | NOT_STARTED
3346 | TT_TASK | DRIFT ELIMINATION ASSEMBLY LAST 4 CELLS | Fri Nov 18 08:00:00 IST 2022 | Thu Dec 22 17:00:00 IST 2022 |  |  | 168.0 | NOT_STARTED
3347 | TT_TASK | INSTALLATION OF FILL PACKS LAST 4 CELLS | Fri Nov 25 08:00:00 IST 2022 | Thu Jan 12 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3348 | TT_TASK | INSTALLATION OF SOUND ABBATMENT SYSTEM LAST 4 CELLS | Fri Nov 25 08:00:00 IST 2022 | Thu Dec 29 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3349 | TT_TASK | INSTALLATION OF COIL BUNDLES AND SEALING LAST 4 CELLS | Fri Dec 30 08:00:00 IST 2022 | Thu Jan 26 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3350 | TT_TASK | INSTALLATION OF DISTRIBUTION SYSTEM LAST 4 CELLS | Fri Jan 13 08:00:00 IST 2023 | Thu Mar 02 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3351 | TT_TASK | INSTALLATION OF AIR MIX SYSTEM LAST 4 CELLS | Fri Jan 13 08:00:00 IST 2023 | Thu Mar 02 17:00:00 IST 2023 |  |  | 648.0 | NOT_STARTED
3352 | TT_TASK | INSTALLATION OF INTERNAL WALKWAY LAST 4 CELLS | Fri Jan 13 08:00:00 IST 2023 | Thu Feb 09 17:00:00 IST 2023 |  |  | 816.0 | NOT_STARTED
3353 | TT_TASK | INSTALLATION OF VACUUM PIPE LINE LAST 4 CELLS | Fri Jan 27 08:00:00 IST 2023 | Thu Mar 02 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3354 | TT_TASK | INSTALLATION OF DUMPERS WITH ACTUATORS LAST 4 CELLS | Fri Jan 27 08:00:00 IST 2023 | Thu Feb 16 17:00:00 IST 2023 |  |  | 760.0 | NOT_STARTED
3355 | TT_TASK | INSTALLATION OF PIPING DRY AREA LAST 4 CELLS | Fri Mar 03 08:00:00 IST 2023 | Thu Apr 06 17:00:00 IDT 2023 |  |  | 368.0 | NOT_STARTED
3356 | TT_TASK | INSTALLATION OF SUPPORT AND DRIFT ELIMINATOR LAST 4 CELLS | Fri Mar 03 08:00:00 IST 2023 | Thu Apr 06 17:00:00 IDT 2023 |  |  | 368.0 | NOT_STARTED
3357 | TT_TASK | INSTALLATION OF MECHANICAL GROUP LAST 4 CELLS | Fri Mar 03 08:00:00 IST 2023 | Thu Mar 30 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3358 | TT_TASK | INSTALLATION OF FAN STACK LAST 4 CELLS | Fri Mar 24 08:00:00 IDT 2023 | Thu Apr 27 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3360 | TT_TASK | E - AND I&C CABLING COOLING TOWER LAST 4 CELLS 20PAD | Tue Apr 25 08:00:00 IDT 2023 | Mon May 22 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3361 | TT_TASK | E - AND I&C CABLING COOLING TOWER FIRST 4 CELLS 20PAD INCL. RISER | Fri Mar 24 08:00:00 IDT 2023 | Thu Apr 20 17:00:00 IDT 2023 |  |  | 32.0 | NOT_STARTED
3363 | TT_TASK | FILLING OF COOLING WATER BASIN | Wed Jun 07 08:00:00 IDT 2023 | Tue Jun 13 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3364 | TT_TASK | COMMISSIONING COOLING WATER SYSTEM | Tue May 23 08:00:00 IDT 2023 | Mon Jun 26 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3365 | TT_TASK | FILLING OF COOLING WATER SYSTEM PAB | Wed Jun 07 08:00:00 IDT 2023 | Tue Jun 13 17:00:00 IDT 2023 |  |  | 136.0 | NOT_STARTED
3366 | TT_TASK | COMMISSIONING CATHODIC PROTECTION FOR COOLING TOWER 20PUR | Tue Apr 11 08:00:00 IDT 2023 | Mon Apr 24 17:00:00 IDT 2023 |  |  | 344.0 | NOT_STARTED
3367 | TT_TASK | COMMISSIONING CATHODIC PROTECTION FOR PAC & ELECTRICAL MODULES | Tue Apr 11 08:00:00 IDT 2023 | Mon Apr 24 17:00:00 IDT 2023 |  |  | 344.0 | NOT_STARTED
3368 | TT_TASK | COMMISSIONING CATHODIC PROTECTION FOR CONDENSER | Tue Apr 11 08:00:00 IDT 2023 | Mon Apr 24 17:00:00 IDT 2023 |  |  | 344.0 | NOT_STARTED
3372 | TT_TASK | PREPARATION RFQ CONDENSER TUBE CLEANING SYSTEM 20PAH | Fri Jan 15 08:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 | Fri Jan 15 08:00:00 IST 2021 | Wed Feb 10 17:00:00 IST 2021 |  | COMPLETED
3373 | TT_TASK | QUOTATION STAGE CONDENSER TUBE CLEANING SYSTEM 20PAH | Thu Feb 11 08:00:00 IST 2021 | Fri May 14 17:00:00 IDT 2021 | Thu Feb 11 08:00:00 IST 2021 | Fri May 14 17:00:00 IDT 2021 |  | COMPLETED
3377 | TT_TASK | DETAIL DESIGN CONDENSER TUBE CLEANING SYSTEM 20PAH | Sat May 15 08:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 | Sat May 15 08:00:00 IDT 2021 | Mon Jun 28 17:00:00 IDT 2021 |  | COMPLETED
3378 | TT_TASK | MANUFACTURING & SHOP TEST CONDENSER TUBE CLEANING SYSTEM 20PAH | Tue Jun 29 08:00:00 IDT 2021 | Sun Dec 26 17:00:00 IST 2021 | Tue Jun 29 08:00:00 IDT 2021 | Sun Dec 26 17:00:00 IST 2021 |  | COMPLETED
3383 | TT_TASK | TRANSPORT TO SKIDDER CONDENSER TUBE CLEANING SYSTEM (BALL STRAINER) 20PAH | Thu Jan 27 08:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 | Thu Jan 27 08:00:00 IST 2022 | Mon Feb 07 17:00:00 IST 2022 |  | COMPLETED
3385 | TT_TASK | TRANSPORT TO SITE CONDENSER TUBE CLEANING SYSTEM (REMAINING SYSTEM) 20PAH | Sat Jun 11 08:00:00 IDT 2022 | Fri Aug 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3387 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CONDENSER TUBE CLEANING SYSTEM 20PAH (BALL STRAINER) | Mon Nov 29 08:00:00 IST 2021 | Sun Dec 26 17:00:00 IST 2021 | Mon Nov 29 08:00:00 IST 2021 | Sun Dec 26 17:00:00 IST 2021 |  | COMPLETED
3388 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CONDENSER TUBE CLEANING SYSTEM 20PAH (REMAINING SYSTEM) | Sat May 14 08:00:00 IDT 2022 | Fri Jun 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3389 | TT_TASK | FEASIBLE PLACING CONDENSER CLEANING SCREEN | Mon Sep 19 08:00:00 IDT 2022 | Tue Sep 20 17:00:00 IDT 2022 |  |  | 184.0 | NOT_STARTED
3390 | TT_TASK | ERECTION CONDENSER TUBE CLEANING SYSTEM 20PAH | Mon Aug 22 08:00:00 IDT 2022 | Sun Sep 18 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3392 | TT_TASK | ERECTION, NDT, PT / VALVES 20PAH | Sat Dec 24 08:00:00 IST 2022 | Fri Feb 03 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3393 | TT_TASK | INSULATION PIPES / VALVES 20PAH | Sat Feb 04 08:00:00 IST 2023 | Fri Mar 03 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3394 | TT_TASK | E- AND I&C-ERECTION CONDENSER TUBE CLEANING SYSTEM 20PAH | Mon Oct 31 08:00:00 IST 2022 | Sun Nov 13 17:00:00 IST 2022 |  |  | 1432.0 | NOT_STARTED
3395 | TT_TASK | ELECTRICAL ERECTION / VALVES 20PAH | Sat Mar 04 08:00:00 IST 2023 | Fri Mar 10 17:00:00 IST 2023 |  |  | 280.0 | NOT_STARTED
3397 | TT_TASK | ERECTION, NDT, PT / VALVES (MECHANICAL) 20PAR MAKE UP WATER PIPES FOR COOLING TOWER | Tue Dec 06 08:00:00 IST 2022 | Mon Jan 16 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3398 | TT_TASK | INSULATION PIPES 20PAR MAKE UP WATER PIPES FOR COOLING TOWER | Tue Jan 17 08:00:00 IST 2023 | Mon Jan 30 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3399 | TT_TASK | ELECTRICAL ERECTION 10/20 PAR MAKE UP WATER PIPES FOR COOLING TOWER | Tue Jan 31 08:00:00 IST 2023 | Mon Feb 13 17:00:00 IST 2023 |  |  | 528.0 | NOT_STARTED
3401 | TT_TASK | QUOTATION STAGE, BASIC DESIGN CT MAKE-UP WATER PUMP PAS | Thu Mar 18 08:00:00 IST 2021 | Wed May 12 17:00:00 IDT 2021 | Thu Mar 18 08:00:00 IST 2021 | Wed May 12 17:00:00 IDT 2021 |  | COMPLETED
3403 | TT_TASK | PREPARATION RFQ CT MAKE-UP WATER PUMP PAS | Fri Feb 05 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 | Fri Feb 05 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 |  | COMPLETED
3407 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST CT MAKE-UP WATER PUMP /FRAME PAS | Tue Jun 15 08:00:00 IDT 2021 | Thu Jan 06 17:00:00 IST 2022 | Tue Jun 15 08:00:00 IDT 2021 | Thu Jan 06 17:00:00 IST 2022 |  | COMPLETED
3412 | TT_TASK | MANUFACTURING, PACKING CT MAKE-UP WATER PUMP PAS | Fri Jan 07 08:00:00 IST 2022 | Thu Apr 14 17:00:00 IDT 2022 | Fri Jan 07 08:00:00 IST 2022 |  |  | IN_PROGRESS
3413 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - FRAME PAS | Fri Jan 07 08:00:00 IST 2022 | Thu Feb 03 17:00:00 IST 2022 | Fri Jan 07 08:00:00 IST 2022 | Thu Feb 03 17:00:00 IST 2022 |  | COMPLETED
3414 | TT_TASK | TRANSPORT FRAME PAS | Fri Feb 04 08:00:00 IST 2022 | Thu Mar 31 17:00:00 IDT 2022 | Fri Feb 04 08:00:00 IST 2022 |  |  | IN_PROGRESS
3416 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - CT MAKE-UP WATER PUMP PAS | Fri Apr 15 08:00:00 IDT 2022 | Thu May 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3417 | TT_TASK | TRANSPORT CT MAKE-UP WATER PUMP PAS | Fri May 13 08:00:00 IDT 2022 | Thu Jul 07 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3419 | TT_TASK | ERECTION CT MAKE-UP WATER PUMP PAS | Tue Oct 25 08:00:00 IDT 2022 | Mon Oct 31 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3421 | TT_TASK | ERECTION CT MAKE-UP WATER PUMP FRAME PAS | Fri Apr 01 08:00:00 IDT 2022 | Thu Apr 07 17:00:00 IDT 2022 |  |  | 1600.0 | NOT_STARTED
3422 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20PBE/PBQ/PUN | Sat Jun 25 08:00:00 IDT 2022 | Fri Sep 30 17:00:00 IDT 2022 |  |  | 256.0 | NOT_STARTED
3423 | TT_TASK | INSULATION PIPES / VALVES COOLING WATER MAKE-UP SYSTEM 20PBE/PBQ/PUN(No Insulation) | Sat Nov 26 08:00:00 IST 2022 | Fri Dec 30 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3424 | TT_TASK | ELECTRICAL ERECTION / VALVES COOLING WATER MAKE-UP SYSTEM 20PBE/PBQ/PUN | Sat Dec 31 08:00:00 IST 2022 | Fri Jan 06 17:00:00 IST 2023 |  |  | 784.0 | NOT_STARTED
3426 | TT_TASK | DESIGN DATA SHEETS SERVICE COOLING WATER BOOSTER PUMP PCB | Thu Jan 07 08:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 | Thu Jan 07 08:00:00 IST 2021 | Thu Jan 14 17:00:00 IST 2021 |  | COMPLETED
3430 | TT_TASK | MANUFACTURING / SHOP TEST SERVICE COOLING WATER BOOSTER PUMP 20PCB | Wed Mar 31 08:00:00 IDT 2021 | Tue Oct 19 17:00:00 IDT 2021 | Wed Mar 31 08:00:00 IDT 2021 | Tue Oct 19 17:00:00 IDT 2021 |  | COMPLETED
3436 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION SERVICE COOLING WATER BOOSTER PUMP 20PCB | Wed Oct 20 08:00:00 IDT 2021 | Tue Nov 16 17:00:00 IST 2021 | Wed Oct 20 08:00:00 IDT 2021 | Tue Nov 16 17:00:00 IST 2021 |  | COMPLETED
3437 | TT_TASK | TRANSPORT TO SKIDDER SERVICE COOLING WATER PUMP 20PCB (AIR CARGO, needs to arrive at Skidder 30.12.21) | Wed Nov 17 08:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 | Wed Nov 17 08:00:00 IST 2021 | Mon Jan 10 17:00:00 IST 2022 |  | COMPLETED
3438 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MODULE 20PCB10Y | Sun May 15 08:00:00 IDT 2022 | Sat May 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3440 | TT_TASK | TRANSPORT MODULE 20PCB10Y | Sun May 22 08:00:00 IDT 2022 | Fri Jun 10 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3441 | TT_TASK | ERECTION, NDT, PT / VALVES SERVICE COOL.WATER 20PCB | Mon Aug 22 08:00:00 IDT 2022 | Sun Dec 04 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3442 | TT_TASK | INSULATION PIPES / VALVES SERVICE COOL.WATER 20PCB | Mon Dec 05 08:00:00 IST 2022 | Sun Jan 01 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3443 | TT_TASK | PIPING WORKS FOR PCB SYSTEM - INTERNAL PIPIES | Sat Jun 25 08:00:00 IDT 2022 | Fri Jul 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3444 | TT_TASK | ERECTION MODULE 20PCB10Y | Thu Jun 16 08:00:00 IDT 2022 | Wed Jun 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3446 | TT_TASK | ELECTRICAL ERECTION / VALVES SERVICE COOL.WATER 20PCB | Mon Jan 02 08:00:00 IST 2023 | Sun Jan 08 17:00:00 IST 2023 |  |  | 712.0 | NOT_STARTED
3447 | TT_TASK | ELECTRICAL ERECTION SERVICE COOLING WATER EXTRACTION PUMP PCB | Mon Oct 17 08:00:00 IDT 2022 | Sun Oct 30 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3449 | TT_TASK | COLD COMMISSIONING 20PCB | Fri May 12 08:00:00 IDT 2023 | Thu May 25 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3450 | TT_TASK | FINAL COLD COMMISSIONING 20PCB | Fri May 26 08:00:00 IDT 2023 | Thu Jun 15 17:00:00 IDT 2023 |  |  | 32.0 | NOT_STARTED
3451 | TT_TASK | PREPARATION RFQ SERVICE CW PUMPS PCC | Fri Feb 05 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 | Fri Feb 05 08:00:00 IST 2021 | Thu Mar 18 17:00:00 IST 2021 |  | COMPLETED
3452 | TT_TASK | QUOTATION STAGE, BASIC DESIGN SERVICE CW PUMPS PCC | Thu Mar 18 08:00:00 IST 2021 | Wed May 12 17:00:00 IDT 2021 | Thu Mar 18 08:00:00 IST 2021 | Wed May 12 17:00:00 IDT 2021 |  | COMPLETED
3457 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST SERVICE CW PUMPS PCC | Tue Jun 15 08:00:00 IDT 2021 | Tue Mar 08 17:00:00 IST 2022 | Tue Jun 15 08:00:00 IDT 2021 |  |  | IN_PROGRESS
3460 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - SERVICE CW PUMPS PCC | Wed Mar 09 08:00:00 IST 2022 | Tue Apr 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3461 | TT_TASK | TRANSPORT SERVICE CW PUMPS PCC | Wed Apr 06 08:00:00 IDT 2022 | Tue May 31 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3463 | TT_TASK | ERECTION OF STANDBY CW PUMPS (PCC) | Thu Aug 25 08:00:00 IDT 2022 | Wed Oct 05 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3466 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION DEBRIS FILTER 20PDB | Fri Dec 03 08:00:00 IST 2021 | Thu Dec 16 17:00:00 IST 2021 | Fri Dec 03 08:00:00 IST 2021 | Thu Dec 16 17:00:00 IST 2021 |  | COMPLETED
3472 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CCW PUMP 20PGB | Wed Oct 20 08:00:00 IDT 2021 | Tue Nov 16 17:00:00 IST 2021 | Wed Oct 20 08:00:00 IDT 2021 | Tue Nov 16 17:00:00 IST 2021 |  | COMPLETED
3473 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION HEAT EXCHANGER 20PGB | Mon Aug 16 08:00:00 IDT 2021 | Sun Sep 12 17:00:00 IDT 2021 | Mon Aug 16 08:00:00 IDT 2021 | Sun Sep 12 17:00:00 IDT 2021 |  | COMPLETED
3474 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CCW EXPANSION TANK 20PGB | Sun Oct 17 08:00:00 IDT 2021 | Sun Nov 14 17:00:00 IST 2021 | Sun Oct 17 08:00:00 IDT 2021 | Sun Nov 14 17:00:00 IST 2021 |  | COMPLETED
3475 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MODULE 20PGB10Y | Sun May 15 08:00:00 IDT 2022 | Sat May 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3476 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION MODULE 20PGB20Y | Sun May 15 08:00:00 IDT 2022 | Sat May 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3477 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20PGB | Thu Oct 13 08:00:00 IDT 2022 | Wed Dec 21 17:00:00 IST 2022 |  |  | 912.0 | NOT_STARTED
3478 | TT_TASK | INSULATION NDT, PT PIPES / VALVES 20PGB | Tue Feb 07 08:00:00 IST 2023 | Mon Feb 27 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3480 | TT_TASK | ELECTRICAL ERECTION PIPES / VALVES 20PGB | Tue Feb 14 08:00:00 IST 2023 | Mon Feb 27 17:00:00 IST 2023 |  |  | 368.0 | NOT_STARTED
3482 | TT_TASK | COLD COMMISSIONING CLOSED COOLING WATER SYSTEM FOR COMBINED CYCLE OPERATION PGB | Tue Apr 18 08:00:00 IDT 2023 | Mon May 08 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3483 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20PSB | Sat Jun 25 08:00:00 IDT 2022 | Fri Sep 30 17:00:00 IDT 2022 |  |  | 256.0 | NOT_STARTED
3484 | TT_TASK | INSULATION PIPES / VALVES COOLING WATER 20PSB(No Insulation) | Sat Nov 26 08:00:00 IST 2022 | Fri Dec 30 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3485 | TT_TASK | ELECTRICAL ERECTION / VALVES COOLING WATER 20PSB | Sat Dec 31 08:00:00 IST 2022 | Fri Jan 06 17:00:00 IST 2023 |  |  | 832.0 | NOT_STARTED
3486 | TT_TASK | PREPARATION RFQ CATHODIC PROTECTION 20PUR | Fri Feb 12 08:00:00 IST 2021 | Thu Apr 22 17:00:00 IDT 2021 | Fri Feb 12 08:00:00 IST 2021 | Thu Apr 22 17:00:00 IDT 2021 |  | COMPLETED
3487 | TT_TASK | QUOTATION STAGE CATHODIC PROTECTION 20PUR | Fri Apr 23 08:00:00 IDT 2021 | Sun May 23 17:00:00 IDT 2021 | Fri Apr 23 08:00:00 IDT 2021 | Sun May 23 17:00:00 IDT 2021 |  | COMPLETED
3489 | TT_TASK | CONCEPT REVIEW BY CLP / NEGOTIATION / AWARD CATHODIC PROTECTION 20URA xx | Fri Apr 02 08:00:00 IDT 2021 | Tue May 11 17:00:00 IDT 2021 | Fri Apr 02 08:00:00 IDT 2021 | Tue May 11 00:00:00 IDT 2021 |  | COMPLETED
3490 | TT_TASK | CP DESIGN & DRAWINGS SUBSTRUCTURE-20URA/URD | Fri Jun 11 08:00:00 IDT 2021 | Sun Jul 25 17:00:00 IDT 2021 | Fri Jun 11 08:00:00 IDT 2021 | Sun Jul 25 17:00:00 IDT 2021 |  | COMPLETED
3491 | TT_TASK | COORDINATION ATKINS - CPT / INCL. EMBEDDED PARTS - SUPERSTRUCTURE 20URA/URD | Mon Oct 11 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 | Mon Oct 11 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 |  | COMPLETED
3492 | TT_TASK | CP DESIGN & DRAWINGS SUPERSTRUCTURE-20URA/URD | Sat Jul 03 08:00:00 IDT 2021 | Sat Jul 24 17:00:00 IDT 2021 | Sat Jul 03 08:00:00 IDT 2021 | Sat Jul 24 17:00:00 IDT 2021 |  | COMPLETED
3493 | TT_TASK | CLIENT REVIEW DETAIL DESIGN SUPERSTRUCTURE AND CATHODIC PROTECTION-20URA/URD | Sun Jul 25 08:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 | Sun Jul 25 08:00:00 IDT 2021 | Wed Aug 18 17:00:00 IDT 2021 |  | COMPLETED
3494 | TT_TASK | CLIENT - REVIEW - CONCRETE SUPERSTRUCTURE CATHODIC PROTECTION 20URA-To be used/cancel xx | Wed Jun 30 08:00:00 IDT 2021 | Sat Jul 24 17:00:00 IDT 2021 | Wed Jun 30 08:00:00 IDT 2021 | Sat Jul 24 17:00:00 IDT 2021 |  | COMPLETED
3495 | TT_TASK | PROCUREMENT AND SHIPPING CATHODIC PROTECTION SUBSTRUCTURE-20URA/URD | Sun Aug 01 08:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 | Sun Aug 01 08:00:00 IDT 2021 | Thu Sep 30 17:00:00 IDT 2021 |  | COMPLETED
3496 | TT_TASK | PROCUREMENT AND SHIPPING CATHODIC PROTECTION SUPERSTRUCTURE-20URA/URD | Tue Jun 15 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 | Tue Jun 15 08:00:00 IDT 2021 | Fri Nov 12 17:00:00 IST 2021 |  | COMPLETED
3498 | TT_TASK | DETAIL DESIGN / MANUFACTURING CATHODIC PROTECTION 20PUR | Wed Oct 20 08:00:00 IDT 2021 | Sat Jul 16 17:00:00 IDT 2022 | Wed Oct 20 08:00:00 IDT 2021 |  |  | IN_PROGRESS
3500 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION CATHODIC PROTECTION 20PUR | Sun Jul 17 08:00:00 IDT 2022 | Sat Aug 13 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3501 | TT_TASK | TRANSPORT CATHODIC PROTECTION 20PUR | Sun Aug 14 08:00:00 IDT 2022 | Sat Oct 08 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3503 | TT_TASK | ELECTRICAL ERECTION CATHODIC PROTECTION CONDENSER | Sun Oct 23 08:00:00 IDT 2022 | Fri Jan 20 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3504 | TT_TASK | ELECTRICAL ERECTION CATHODIC PROTECTION PAC & ELECTRICAL MODULES | Sun Oct 23 08:00:00 IDT 2022 | Fri Jan 20 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3508 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20PUS | Sat Jun 25 08:00:00 IDT 2022 | Fri Sep 30 17:00:00 IDT 2022 |  |  | 256.0 | NOT_STARTED
3509 | TT_TASK | INSULATION PIPES / VALVES BIOCIDE GENERATION 20PUS(No Insulation) | Sat Nov 26 08:00:00 IST 2022 | Fri Dec 30 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3510 | TT_TASK | ELECTRICAL ERECTION / VALVES BIOCIDE GENERATION 20PUS | Sat Dec 31 08:00:00 IST 2022 | Fri Jan 06 17:00:00 IST 2023 |  |  | 832.0 | NOT_STARTED
3511 | TT_TASK | BASIC DESIGN / PREPARATION P&ID'S DOSING CONTAINER QC | Fri Mar 26 08:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Fri Mar 26 08:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 |  | COMPLETED
3515 | TT_TASK | PREPARATION RFQ DOSING CONTAINER QC | Fri Apr 23 08:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Apr 23 08:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 |  | COMPLETED
3516 | TT_TASK | QUOTATION STAGE DOSING CONTAINER QC | Fri Apr 30 08:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 | Fri Apr 30 08:00:00 IDT 2021 | Fri Jul 30 17:00:00 IDT 2021 |  | COMPLETED
3519 | TT_TASK | DETAIL DESIGN DOSING CONTAINER 20QC | Tue Aug 31 08:00:00 IDT 2021 | Mon Oct 18 17:00:00 IDT 2021 | Tue Aug 31 08:00:00 IDT 2021 | Mon Oct 18 17:00:00 IDT 2021 |  | COMPLETED
3520 | TT_TASK | MANUFACTURING DOSING CONTAINER 20QC | Mon Oct 25 08:00:00 IDT 2021 | Sat Jun 18 17:00:00 IDT 2022 | Mon Oct 25 08:00:00 IDT 2021 |  |  | IN_PROGRESS
3523 | TT_TASK | TRANSPORT DOSING CONTAINER 20QC | Sun Jul 17 08:00:00 IDT 2022 | Mon Aug 15 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3525 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION DOSING CONTAINER 20QC | Sun Jun 19 08:00:00 IDT 2022 | Sat Jul 16 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3526 | TT_TASK | ERECTION DOSING CONTAINER QC | Tue Aug 30 08:00:00 IDT 2022 | Mon Sep 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3528 | TT_TASK | ERECTION, NDT, PT / VALVES DOSING SYSTEM 20QC | Tue Sep 06 08:00:00 IDT 2022 | Mon Oct 03 17:00:00 IDT 2022 |  |  | 1512.0 | NOT_STARTED
3529 | TT_TASK | ERECTION, NDT, PT / VALVES DOSING 20QC | Thu Jan 26 08:00:00 IST 2023 | Wed Feb 22 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3530 | TT_TASK | ELECTRICAL ERECTION DOSING CONTAINER QC | Tue Sep 13 08:00:00 IDT 2022 | Mon Sep 19 17:00:00 IDT 2022 |  |  | 1624.0 | NOT_STARTED
3531 | TT_TASK | COLD COMMISSIONING DOSING / SAMPLING SYSTEMS QCD/QCL | Sun May 14 08:00:00 IDT 2023 | Sat May 27 17:00:00 IDT 2023 |  |  | 64.0 | NOT_STARTED
3533 | TT_TASK | COLD COMMISSIONING DOSING SYSTEMS REQUIRED FOR PGB-OPERATION QCB | Tue Apr 11 08:00:00 IDT 2023 | Mon Apr 17 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3536 | TT_TASK | ERECTION, NDT, PT / VALVES ST CONTROL AIR 20QFB | Wed Nov 02 08:00:00 IST 2022 | Tue Dec 27 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3537 | TT_TASK | ELECTRICAL ERECTION / VALVES ST CONTROL AIR 20QFB | Wed Dec 28 08:00:00 IST 2022 | Tue Jan 03 17:00:00 IST 2023 |  |  | 1184.0 | NOT_STARTED
3539 | TT_TASK | COLD COMMISSIONING ST CONTROL AIR SYSTEM QFB | Sat Jun 10 08:00:00 IDT 2023 | Wed Jun 14 17:00:00 IDT 2023 |  |  | 40.0 | NOT_STARTED
3540 | TT_TASK | BASIC DESIGN, SPECIFICATION CENTRAL GAS SUPPLY (H2,CO2) QJ_ | Sun Feb 14 08:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 | Sun Feb 14 08:00:00 IST 2021 | Sat Mar 27 17:00:00 IDT 2021 |  | COMPLETED
3541 | TT_TASK | QUOTATION STAGE CENTRAL GAS SUPPLY (H2,CO2) QJ_ | Sun Apr 11 08:00:00 IDT 2021 | Sat May 22 17:00:00 IDT 2021 | Sun Apr 11 08:00:00 IDT 2021 | Sat May 22 17:00:00 IDT 2021 |  | COMPLETED
3543 | TT_TASK | PREPARATION RFQ CENTRAL GAS SUPPLY (H2,CO2) QJ_ | Sun Mar 28 08:00:00 IDT 2021 | Sat Apr 10 17:00:00 IDT 2021 | Sun Mar 28 08:00:00 IDT 2021 | Sat Apr 10 17:00:00 IDT 2021 |  | COMPLETED
3544 | TT_TASK | DETAIL DESIGN, MANUFACTURING, SHOP TEST CENTRAL GAS SUPPLY (H2,CO2) QJ_ | Sun May 23 08:00:00 IDT 2021 | Wed Dec 08 17:00:00 IST 2021 | Sun May 23 08:00:00 IDT 2021 | Wed Dec 08 17:00:00 IST 2021 |  | COMPLETED
3547 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION - CENTRAL GAS SUPPLY (H2,CO2) QJ_ | Thu Dec 09 08:00:00 IST 2021 | Wed Jan 05 17:00:00 IST 2022 | Thu Dec 09 08:00:00 IST 2021 | Wed Jan 05 17:00:00 IST 2022 |  | COMPLETED
3548 | TT_TASK | TRANSPORT CENTRAL GAS SUPPLY (H2,CO2) QJ_ | Thu Jun 30 08:00:00 IDT 2022 | Wed Aug 24 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3550 | TT_TASK | ERECTION GAS SUPPLY BOTTLES FOR CO2 | Sat Nov 19 08:00:00 IST 2022 | Fri Nov 25 17:00:00 IST 2022 |  |  | 1200.0 | NOT_STARTED
3551 | TT_TASK | ERECTION GAS SUPPLY BOTTLES FOR H2 | Sat Oct 22 08:00:00 IDT 2022 | Fri Oct 28 17:00:00 IDT 2022 |  |  | 944.0 | NOT_STARTED
3554 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20QJA10 | Sat Jun 25 08:00:00 IDT 2022 | Fri Sep 30 17:00:00 IDT 2022 |  |  | 448.0 | NOT_STARTED
3555 | TT_TASK | INSULATION PIPES / VALVES GAS SUPPLY AND DISTRIBUTION QJA10(No Insulation) | Sat Nov 26 08:00:00 IST 2022 | Fri Dec 30 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3556 | TT_TASK | ERECTION, NDT, PT PIPES / VALVES 20QJA20 | Sat Jun 25 08:00:00 IDT 2022 | Fri Sep 30 17:00:00 IDT 2022 |  |  | 448.0 | NOT_STARTED
3557 | TT_TASK | INSULATION PIPES / VALVES GAS SUPPLY AND DISTRIBUTION QJA20(No Insulation) | Sat Nov 26 08:00:00 IST 2022 | Fri Dec 30 17:00:00 IST 2022 |  |  |  | NOT_STARTED
3558 | TT_TASK | ELECTRICAL ERECTION / VALVES GAS SUPPLY AND DISTRIBUTION QJA10 | Sat Dec 31 08:00:00 IST 2022 | Fri Jan 06 17:00:00 IST 2023 |  |  | 384.0 | NOT_STARTED
3559 | TT_TASK | ELECTRICAL ERECTION / VALVES GAS SUPPLY AND DISTRIBUTION QJA20 | Sat Dec 31 08:00:00 IST 2022 | Fri Jan 06 17:00:00 IST 2023 |  |  | 864.0 | NOT_STARTED
3560 | TT_TASK | BASIC DESIGN / PREPARATION P&ID'S DOSING CONTAINER 20QU | Fri Mar 26 08:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 | Fri Mar 26 08:00:00 IDT 2021 | Thu Apr 22 17:00:00 IDT 2021 |  | COMPLETED
3565 | TT_TASK | PREPARATION RFQ SAMPLING CONTAINER 20QU | Fri Apr 23 08:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 | Fri Apr 23 08:00:00 IDT 2021 | Thu Apr 29 17:00:00 IDT 2021 |  | COMPLETED
3566 | TT_TASK | QUOTATION STAGE SAMPLING CONTAINER 20QU | Fri Apr 30 08:00:00 IDT 2021 | Sat Jul 24 17:00:00 IDT 2021 | Fri Apr 30 08:00:00 IDT 2021 | Sat Jul 24 17:00:00 IDT 2021 |  | COMPLETED
3568 | TT_TASK | DETAIL DESIGN SAMPLING CONTAINER 20QU | Sun Jul 25 08:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 | Sun Jul 25 08:00:00 IDT 2021 | Sat Sep 11 17:00:00 IDT 2021 |  | COMPLETED
3569 | TT_TASK | MANUFACTURING SAMPLING CONTAINER 20QU | Sun Sep 12 08:00:00 IDT 2021 | Tue Feb 15 17:00:00 IST 2022 | Sun Sep 12 08:00:00 IDT 2021 | Tue Feb 15 17:00:00 IST 2022 |  | COMPLETED
3572 | TT_TASK | TRANSPORT SAMPLING CONTAINER 20QU | Tue Jun 28 08:00:00 IDT 2022 | Mon Aug 22 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3574 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION SAMPLING CONTAINER 20QU | Tue May 31 08:00:00 IDT 2022 | Mon Jun 27 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3575 | TT_TASK | ERECTION SAMPLING CONTAINER 20QU | Tue Sep 06 08:00:00 IDT 2022 | Mon Sep 19 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3577 | TT_TASK | ERECTION, NDT, PT / VALVES SAMPLING QU | Thu Jan 26 08:00:00 IST 2023 | Wed Mar 15 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3578 | TT_TASK | ELECTRICAL ERECTION SAMPLING CONTAINER 20QU | Tue Sep 20 08:00:00 IDT 2022 | Mon Sep 26 17:00:00 IDT 2022 |  |  | 1776.0 | NOT_STARTED
3579 | TT_TASK | ELECTRICAL ERECTION / VALVES DOSING SYSTEM 20QU | Thu Mar 16 08:00:00 IST 2023 | Wed Mar 22 17:00:00 IST 2023 |  |  | 416.0 | NOT_STARTED
3586 | TT_TASK | DETAIL DESIGN DUCTS HVAC SYSTEM UMC SA | Mon Aug 02 08:00:00 IDT 2021 | Sun Sep 26 17:00:00 IDT 2021 | Mon Aug 02 08:00:00 IDT 2021 | Sun Sep 26 17:00:00 IDT 2021 |  | COMPLETED
3589 | TT_TASK | COLD COMMISSIONING HVAC SYSTEM FOR 20UMC SAM | Tue Apr 11 08:00:00 IDT 2023 | Mon May 01 17:00:00 IDT 2023 |  |  | 256.0 | NOT_STARTED
3590 | TT_TASK | PREPARATION RFQ HVAC SYSTEM SA | Fri Mar 05 08:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 | Fri Mar 05 08:00:00 IST 2021 | Thu Apr 08 17:00:00 IDT 2021 |  | COMPLETED
3591 | TT_TASK | QUOTATION STAGE HVAC SYSTEM SA | Fri Apr 09 08:00:00 IDT 2021 | Sun Aug 01 17:00:00 IDT 2021 | Fri Apr 09 08:00:00 IDT 2021 | Sun Aug 01 17:00:00 IDT 2021 |  | COMPLETED
3597 | TT_TASK | MANUFACTURING DUCT FOR HVAC SYSTEM UMC 20SA | Fri Mar 11 08:00:00 IST 2022 | Thu Jun 23 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3598 | TT_TASK | MANUFACTURING SHOP TEST EQUIPMENT FOR HVAC SYSTEM UMC 20SA | Sun Nov 07 08:00:00 IST 2021 | Sat Mar 05 17:00:00 IST 2022 | Sun Nov 07 08:00:00 IST 2021 |  |  | IN_PROGRESS
3599 | TT_TASK | TRANSPORT DUCT FOR HVAC SYSTEM UMC 20SA | Fri Jul 22 08:00:00 IDT 2022 | Wed Oct 12 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3600 | TT_TASK | TRANSPORT EQUIPMENT FOR HVAC SYSTEM UMC 20SA | Sun Apr 03 08:00:00 IDT 2022 | Fri Jun 24 17:00:00 IDT 2022 |  |  | 880.0 | NOT_STARTED
3601 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION DUCT FOR HVAC SYSTEM UMC 20SA | Fri Jun 24 08:00:00 IDT 2022 | Thu Jul 21 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3602 | TT_TASK | LOGISTICS AND CUSTOMS PREPARATION EQUIPMENT FOR HVAC SYSTEM UMC 20SA | Sun Mar 06 08:00:00 IST 2022 | Sat Apr 02 17:00:00 IDT 2022 |  |  |  | NOT_STARTED
3603 | TT_TASK | ERECTION EQUIPMENT HVAC SYSTEM FOR UMC/USA 20SA | Mon Nov 07 08:00:00 IST 2022 | Sun Jan 01 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3604 | TT_TASK | ERECTION DUCTS FOR HVAC SYSTEM UMC | Mon Jan 02 08:00:00 IST 2023 | Sun Jan 15 17:00:00 IST 2023 |  |  |  | NOT_STARTED
3605 | TT_TASK | E- AND I&C- ERECTION HVAC SYSTEM 20SA | Mon Dec 05 08:00:00 IST 2022 | Sun Jan 15 17:00:00 IST 2023 |  |  | 680.0 | NOT_STARTED
3608 | TT_TASK | COLD COMMISSIONING HVAC FOR MPB NOISE ENCLOSURE | Thu May 25 08:00:00 IDT 2023 | Wed Jun 07 17:00:00 IDT 2023 |  |  |  | NOT_STARTED
3614 | TT_TASK | CONTRACT REVIEW / PREP. RFQ AIR COMPRESSOR SYSTEM SCA | Fri Feb 19 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 | Fri Feb 19 08:00:00 IST 2021 | Fri Apr 30 17:00:00 IDT 2021 |  | COMPLETED
3615 | TT_TASK | QUOTATION STAGE AIR COMPRESSOR SYSTEM SCA - ABORTED, DUE TO CLP DECISION TO CHANGE TO OIL FREE | Sat May 01 08:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 | Sat May 01 08:00:00 IDT 2021 | Sat Jul 17 17:00:00 IDT 2021 |  | COMPLETED
3617 | TT_TASK | DESIGN DATA SHEETS AIR COMPRESSOR SYSTEM SCA | Fri Feb 05 08:00:00 IST 2021 | Thu Feb 18 17:00:00 IST 2021 | Fri Feb 05 08:00:00 IST 2021 | Thu Feb 18 17:00:00 IST 2021 |  | COMPLETED