## Sheet1
ID | TaskType | Label | PlannedStart | PlannedEnd | ActualStart | ActualEnd | Float | Status
25 | TT_TASK | Access opening for the up track cut and cover tunnel at Tse Uk Tsuen Shaft | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 10 18:00:00 IST 2016 |  | COMPLETED
27 | TT_TASK | Close out the temporary access opening at Tse Uk Tsuen Shaft | Thu Mar 10 08:00:00 IST 2016 | Tue Apr 05 18:00:00 IDT 2016 | Thu Feb 11 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
307 | TT_TASK | Position crane for TBM retrieval (down track) | Wed Jul 02 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014 | Sat Aug 02 18:00:00 IDT 2014 |  | COMPLETED
308 | TT_TASK | TBM Break-in and Retrieval (down track) | Mon Aug 04 08:00:00 IDT 2014 | Sat Aug 30 18:00:00 IDT 2014 | Mon Aug 04 08:00:00 IDT 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
309 | TT_TASK | Position crane for TBM retrieval (up track) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 |  | COMPLETED
310 | TT_TASK | TBM Break-in and Retrieval (up track) | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
376 | TT_TASK | Supply Engineer with Survey Equipment [PS41.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
377 | TT_TASK | Provide Engineer with suitably qualified full time Survey Assistant - 4 nos. [PS41.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
378 | TT_TASK | Provide Engineer with site transportation as detailed in PS42.1 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 |  | COMPLETED
379 | TT_TASK | Submit details of qualified drivers to be assigned to the Engineer, for review [PS42.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 |  | COMPLETED
380 | TT_TASK | Install, service and maintain 10 container offices for use by the Engineer's Site Staff | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
381 | TT_TASK | Provide services and equipment for the Engineer | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
383 | TT_TASK | Master Programme - Prepare and submit for approval [GS4.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
384 | TT_TASK | Master Programme - Comments , Resubmission and Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
385 | TT_TASK | Time Chainage Programme - Prepare and submit for approval [GS4.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
386 | TT_TASK | Time Chainage Programme - Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
387 | TT_TASK | Implement and Maintain Programme Management System for 1st Audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
388 | TT_TASK | Implement and Maintain Programme Management System for 2nd Audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
389 | TT_TASK | Implement and Maintain Programme Management System for 3rd Audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
391 | TT_TASK | Environmental Management Plan - Prepare and submit for approval [GS5.1.10] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
392 | TT_TASK | Environmental Management Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
393 | TT_TASK | Quality Plan - Prepare and submit for approval [GS9.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
394 | TT_TASK | Quality Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
395 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 1st audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 |  | COMPLETED
396 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 2nd audit | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
397 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 3rd audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
398 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 4th audit | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
399 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 5th audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
400 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 6th audit | Tue Jul 02 08:00:00 IDT 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
401 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 7th audit | Thu Nov 28 08:00:00 IST 2013 | Thu Jun 05 18:00:00 IDT 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Jan 24 18:00:00 IST 2014 |  | COMPLETED
402 | TT_TASK | Health and Safety Plan - Prepare and submit [G3.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
403 | TT_TASK | System Assurance Plan - Prepare and submit for approval [PS Appendix P3.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
404 | TT_TASK | System Assurance Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
405 | TT_TASK | Design for Safety & Constructability Plan - Prepare and submit for approval [PS37.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
406 | TT_TASK | Design for Safety & Constructability Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
408 | TT_TASK | Methods of Construction - Prepare and submit for approval [GS12.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
409 | TT_TASK | Methods of Construction - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
410 | TT_TASK | Contractor's Submission Schedule - Prepare and submit for approval [GS12.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
411 | TT_TASK | Contractor's Submission Schedule - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
412 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) [PS13.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
413 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) - Approval period | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 |  | COMPLETED
414 | TT_TASK | Spoil Disposal Plan [PS17.7.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
415 | TT_TASK | Waste Management Plan [PS22.10.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
416 | TT_TASK | Independent Checking Engineer - Appoint and submit for approval [PS7.1.8] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
417 | TT_TASK | Independent Checking Engineer - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
418 | TT_TASK | Sub-contract Management Plan - Prepare and submit [PS34.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 |  | COMPLETED
419 | TT_TASK | Schedule of Utilities Services Arrangement [GS7.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
420 | TT_TASK | Site Safety Supervision Plan for Site Formation - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
421 | TT_TASK | Site Safety Supervision Plan for Site Formation - Approval period | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
422 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Prepare and Submit | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
423 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
424 | TT_TASK | Site Safety Supervision Plan for ELS - Prepare and Submit | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
425 | TT_TASK | Site Safety Supervision Plan for ELS - Approval Period | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
426 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Prepare and Submit | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
427 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Approval Period | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
428 | TT_TASK | Noise Management Plan [P22.3.9] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
429 | TT_TASK | Air Quality Management Plan [P22.4.3] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
430 | TT_TASK | Detailed Proposal for Water Pollution Control Measures and Proposed Monitoring [PS22.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
431 | TT_TASK | Groundwater Monitoring and Response Plan [PS22.5.2] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
432 | TT_TASK | Vibration Monitoring Plan [PS22.8.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 |  | COMPLETED
433 | TT_TASK | Proposed Outline TTM Scheme - Prepare & submit to the: Engineer for Review / SLG for Approval [PS19.3] | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 |  | COMPLETED
434 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Proposed TTM Scheme [PS19.4] | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 |  | COMPLETED
435 | TT_TASK | Resubmission of Proposed Outline TTM Scheme (if required) | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
436 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Resubmitted Proposed Outline TTM Scheme [PS19.4] | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 |  | COMPLETED
437 | TT_TASK | Notification Period of the Approved TTM Scheme prior to implementation [PS19.4] | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 |  | COMPLETED
440 | TT_TASK | Initial Site Survey (WA3.11) | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 |  | COMPLETED
441 | TT_TASK | Initial Site Survey Report (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 |  | COMPLETED
442 | TT_TASK | Initial Site Survey & Condition Survey (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
443 | TT_TASK | Initial Site Survey Report (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
444 | TT_TASK | Initial Site Survey & Condition Survey (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
445 | TT_TASK | Initial Site Survey Report (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
446 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 4.9 & 4.12A [PS4.2] | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
447 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 5.1 & 5.3 [PS4.2.3] | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 |  | COMPLETED
448 | TT_TASK | Proposal for Site Clearance Works [PS4.4.1] | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 |  | COMPLETED
449 | TT_TASK | Site Clearance / Site Formation Works (including demolition of EBS) | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
450 | TT_TASK | Backfill existing stream courses in Works Area 4.9, 4.10 and 4.11 [PS18.5.1] | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
451 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and submit to EPD for Approval (WA3.3 - Area M, I, L) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
452 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA3.3 - Area M, I, L) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
453 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
454 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
455 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.3 - Area M, I, L) | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
456 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA3.3 - Area M, I, L) | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
457 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA3.3 - Area M, I, L) | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
458 | TT_TASK | Remediation Report - Approval (WA3.3 - Area M, I, L) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
459 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and Submit to EPD for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
460 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
461 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
462 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.1, 3.2, 3.3, 3.3A) | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
463 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.1, 3.2, 3.3, 3.3A) | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 |  | COMPLETED
464 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 |  | COMPLETED
465 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
466 | TT_TASK | Remediation Report - Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
467 | TT_TASK | Conduct remediation for Area Q in accordance with method proposed in the approved Remediation Action Plan [PS22.9.2] | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 |  | COMPLETED
468 | TT_TASK | Remediation Report - Prepare and submit for Approval [PS22.9.2] (Area Q) | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 |  | COMPLETED
469 | TT_TASK | Remediation Report - Approval (Area Q) | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
470 | TT_TASK | Removal of contaminated soil at North Tunnels (Area N,O,P,Q,R,S) | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
471 | TT_TASK | Condition Survey EBS for presence of Asbestos and gather samples | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
472 | TT_TASK | Testing of gathered samples | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 |  | COMPLETED
473 | TT_TASK | Prepare and submit Asbestos Investigation Report (AIR) & Asbestos Abatement Plan (AAP) | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
474 | TT_TASK | Approval period of AIR & AAP | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
475 | TT_TASK | Notification period to Engineer and EPD prior to Asbestos abatement works | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
476 | TT_TASK | Asbestos abatement works | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
477 | TT_TASK | Demolition of EBS | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
478 | TT_TASK | Confirmation of tree survey | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 |  | COMPLETED
480 | TT_TASK | Installation of ground settlement markers | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 |  | COMPLETED
481 | TT_TASK | Settlement monitoring and submit report | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
482 | TT_TASK | Settlement monitoring and submit report | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 |  | COMPLETED
483 | TT_TASK | Settlement monitoring and submit report | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
484 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
485 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Wed Feb 26 18:00:00 IST 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Feb 21 18:00:00 IST 2014 |  | COMPLETED
486 | TT_TASK | Settlement monitoring and submit report | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 |  | COMPLETED
488 | TT_TASK | Permit Applications (incl. License to Search and Excavate Antiquities and Excavation Permit) | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 |  | COMPLETED
489 | TT_TASK | Check for underground utilities | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 |  | COMPLETED
490 | TT_TASK | Field walking and hand augering | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 |  | COMPLETED
491 | TT_TASK | Excavation of trial pits | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 |  | COMPLETED
492 | TT_TASK | Rescue excavation rescue works (if required) | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 |  | COMPLETED
494 | TT_TASK | Erection of Hoarding with Gate (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 |  | COMPLETED
495 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 3.1, 3.2, 3.3 and 3.3A [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
496 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 4.9, 4.10, 4.11, 4.12A~C, and 4.15 [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
497 | TT_TASK | Project Signboard Erection [PS4.6.8] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
498 | TT_TASK | Marine Survey at Barging Point [PS4.3] (before construction of barging facilities) | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 00:00:00 IST 2010 |  | COMPLETED
499 | TT_TASK | Construct barging facilities | Sat Oct 02 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Oct 02 00:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
500 | TT_TASK | Operation Plan for the Barging Facility - Prepare and Submit for Approval [PS17.1.9] | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
501 | TT_TASK | Operation Plan for the Barging Facility - Review and Approval Period | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 |  | COMPLETED
503 | TT_TASK | General and Special Attendance for Designated Contractors | Mon Dec 02 08:00:00 IST 2013 | Mon Aug 31 18:00:00 IDT 2015 | Tue Jul 02 08:00:00 IDT 2013 | Wed Mar 25 18:00:00 IST 2015 |  | COMPLETED
505 | TT_TASK | Prepare and Submit Detailed Interface Specification | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 |  | COMPLETED
506 | TT_TASK | Approval of Detailed Interface Plan | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
507 | TT_TASK | Prepare and Submit Detailed Interface Specification | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 |  | COMPLETED
508 | TT_TASK | Approval of Detailed Interface Plan | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
510 | TT_TASK | Prepare and Submit Draft Operation and Maintenance Manual [PS33.1] | Mon Aug 24 08:00:00 IDT 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jul 28 08:00:00 IDT 2014 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
511 | TT_TASK | Review and approval period of Draft Operation and Maintenance Manual | Wed Aug 10 08:00:00 IDT 2016 | Tue Sep 13 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
512 | TT_TASK | Prepare and Submit Final Operation and Maintenance Manual [PS33.1] | Wed Sep 14 08:00:00 IDT 2016 | Thu Feb 16 18:00:00 IST 2017 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
513 | TT_TASK | Provide Engineer with As-Built Drawing for the Whole of the Works [PS33.2] | Mon Nov 21 08:00:00 IST 2016 | Wed Dec 14 18:00:00 IST 2016 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
514 | TT_TASK | Provide Engineer with Asset Registration Information [PS33.3] | Fri May 19 08:00:00 IDT 2017 | Mon Jun 12 18:00:00 IDT 2017 |  |  |  | NOT_STARTED
517 | TT_TASK | Preliminary Design Programme - Prepare and Submit for Approval [PS7.1.8 - App. Z2.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
518 | TT_TASK | Preliminary Design Programme - Review and Approval Period [PS7.1.8 - App. Z2.2] | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 |  | COMPLETED
519 | TT_TASK | Preliminary Design Programme - Resubmission and Approval (if required) [PS7.1.8 - App. Z2.2] | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 |  | COMPLETED
520 | TT_TASK | Schedule of Designs - Prepare and Submit for Approval [PS7.1.8 - App. Z2.5] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
521 | TT_TASK | Detailed Proposal for Carrying Out the Cross Passage Works [PS11.5.2] | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
524 | TT_TASK | Design TBM and submit full details to the Engineer [PS7.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
525 | TT_TASK | TBM Design - Approval period | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 |  | COMPLETED
526 | TT_TASK | TBM Design - Resubmission and approval period | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 |  | COMPLETED
528 | TT_TASK | AIP Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
529 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 |  | COMPLETED
530 | TT_TASK | DDS Design - Prepare and Submit | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 |  | COMPLETED
531 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 |  | COMPLETED
532 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 |  | COMPLETED
533 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 |  | COMPLETED
534 | TT_TASK | Issue Completed Working Drawings | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
536 | TT_TASK | AIP Design - Prepare and Submit | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 |  | COMPLETED
537 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 |  | COMPLETED
538 | TT_TASK | AIP Design - Response to comments and Resubmit | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
539 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
540 | TT_TASK | DDS Design - Prepare and Submit | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
541 | TT_TASK | DDS Design - Review and Approval Period (by MTRC & related Government Authorities) | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 |  | COMPLETED
542 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 |  | COMPLETED
543 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 |  | COMPLETED
544 | TT_TASK | Issue Completed Working Drawings | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 |  | COMPLETED
546 | TT_TASK | DDS Design - Prepare and Submit | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 |  | COMPLETED
547 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 |  | COMPLETED
548 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 |  | COMPLETED
549 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 |  | COMPLETED
550 | TT_TASK | Issue Completed Working Drawings | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
552 | TT_TASK | AIP Design - Prepare and Submit | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 |  | COMPLETED
553 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
554 | TT_TASK | AIP Design - Response to comments and Resubmit | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 |  | COMPLETED
555 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
556 | TT_TASK | DDS Design - Prepare and Submit | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 |  | COMPLETED
557 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 |  | COMPLETED
558 | TT_TASK | DDS Design - Response to comments and Resubmit | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 |  | COMPLETED
559 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 |  | COMPLETED
560 | TT_TASK | Issue Completed Working Drawings | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 |  | COMPLETED
562 | TT_TASK | Prepare and Submit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 |  | COMPLETED
563 | TT_TASK | Review and Approval Period | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
564 | TT_TASK | Response to comments and Resubmit | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 |  | COMPLETED
565 | TT_TASK | Review and Approval Period (for resubmission) | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 |  | COMPLETED
568 | TT_TASK | DDS Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
569 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 |  | COMPLETED
570 | TT_TASK | DDS Design - Response to comments and Resubmit | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 |  | COMPLETED
571 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 |  | COMPLETED
572 | TT_TASK | Issue Completed Working Drawings | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
574 | TT_TASK | DDS Design - Prepare and Submit | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 |  | COMPLETED
575 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 |  | COMPLETED
576 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 |  | COMPLETED
577 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 |  | COMPLETED
578 | TT_TASK | Issue Completed Working Drawings | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 |  | COMPLETED
580 | TT_TASK | DDS Design - Prepare and Submit | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 |  | COMPLETED
581 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 |  | COMPLETED
582 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 |  | COMPLETED
583 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 |  | COMPLETED
584 | TT_TASK | Issue Completed Working Drawings | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 |  | COMPLETED
586 | TT_TASK | DDS Design - Prepare and Submit | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 |  | COMPLETED
587 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 |  | COMPLETED
588 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 |  | COMPLETED
589 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 |  | COMPLETED
590 | TT_TASK | Issue Completed Working Drawings | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 |  | COMPLETED
592 | TT_TASK | DDS Design - Prepare and Submit | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 |  | COMPLETED
593 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 |  | COMPLETED
594 | TT_TASK | DDS Design - Response to comments and Resubmit | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 |  | COMPLETED
595 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 |  | COMPLETED
596 | TT_TASK | Issue Completed Working Drawings | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
599 | TT_TASK | Formworks / Falsework - Prepare & Submit | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
600 | TT_TASK | Formworks / Falsework - Review & Approval Period (by MTRC) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
601 | TT_TASK | Formworks / Falsework - Response to comments and Resubmit | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 |  | COMPLETED
602 | TT_TASK | Formworks / Falsework - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
605 | TT_TASK | Layout of Site Hoarding - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
606 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (by MTRC) | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
607 | TT_TASK | Layout of Site Hoarding - Response to comments and Resubmit | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
608 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 |  | COMPLETED
610 | TT_TASK | Layout of Engineer's Accommodation - Prepare and Submit | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
611 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (by MTRC) | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 |  | COMPLETED
612 | TT_TASK | Layout of Engineer's Accommodation - Response to comments and Resubmit | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
613 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (for resubmit) (by MTRC & related Government Authorities | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
615 | TT_TASK | TTMS Assessment Report - Prepare and Submit | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 |  | COMPLETED
616 | TT_TASK | TTMS Assessment Report - Review and Approval Period (by MTRC) | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
617 | TT_TASK | TTMS Assessment Report - Response to comments and Resubmit | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 |  | COMPLETED
618 | TT_TASK | TTMS Assessment Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
619 | TT_TASK | Issue Completed Working Drawings | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 |  | COMPLETED
621 | TT_TASK | DIA Report - Prepare and Submit | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 |  | COMPLETED
622 | TT_TASK | DIA Report - Review and Approval Period (by MTRC) | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 |  | COMPLETED
623 | TT_TASK | DIA Report - Response to comments and Resubmit | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 |  | COMPLETED
624 | TT_TASK | DIA Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
625 | TT_TASK | Issue Completed Working Drawings | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 |  | COMPLETED
627 | TT_TASK | AIP Design - Prepare & Submit | Wed Sep 23 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 |  | COMPLETED
628 | TT_TASK | AIP Design - Review & Approval Period (by MTR) | Wed Oct 14 08:00:00 IDT 2015 | Wed Nov 11 18:00:00 IST 2015 | Mon Jun 08 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
629 | TT_TASK | AIP Design - Response to comments and Resubmit | Thu Nov 12 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Mon Jun 15 01:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
630 | TT_TASK | AIP Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jun 22 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
631 | TT_TASK | DDS Design - Prepare & Submit | Wed Jan 13 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Tue Sep 01 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 |  | COMPLETED
632 | TT_TASK | DDS Design - Review & Approval Period (by MTRC) | Fri Feb 26 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 12 18:00:00 IDT 2015 |  | COMPLETED
633 | TT_TASK | DDS Design - Response to comments & Resubmit | Tue Mar 29 08:00:00 IDT 2016 | Fri Apr 01 18:00:00 IDT 2016 | Mon Sep 14 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
634 | TT_TASK | DDS Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Apr 02 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 | Mon Sep 21 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
635 | TT_TASK | Issue Completed Working Drawings | Wed Jan 27 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
637 | TT_TASK | Layout of Barging Point - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
638 | TT_TASK | Layout of Barging Point - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
639 | TT_TASK | Layout of Barging Point - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
640 | TT_TASK | Layout of Barging Point - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
641 | TT_TASK | Loading Ramps - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
642 | TT_TASK | Loading Ramps - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
643 | TT_TASK | Loading Ramps - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
644 | TT_TASK | Loading Ramps - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
645 | TT_TASK | Weighbridge - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
646 | TT_TASK | Weighbridge - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
647 | TT_TASK | Weighbridge - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
648 | TT_TASK | Weighbridge - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
652 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
653 | TT_TASK | Pre-drill and guide wall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
654 | TT_TASK | D-wall construction (1084m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
655 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
656 | TT_TASK | Wang Toi Shan Shan Tsuen Road diversion works | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 |  | COMPLETED
658 | TT_TASK | Excavate up to +10.5mPD (369m3) | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 |  | COMPLETED
659 | TT_TASK | Install Strut S0 +11.0mPD | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 |  | COMPLETED
660 | TT_TASK | Excavate up to +8.0mPD (1525m3) | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 |  | COMPLETED
661 | TT_TASK | Install Strut S1 +8.5mPD | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 |  | COMPLETED
662 | TT_TASK | Excavate up to +4.5mPD (2135m3) | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 |  | COMPLETED
663 | TT_TASK | Install Strut S2 +5.0mPD | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 |  | COMPLETED
664 | TT_TASK | Excavate up to +0.5mPD (2440m3) | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 |  | COMPLETED
665 | TT_TASK | Install Strut S3 +1.0mPD | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 |  | COMPLETED
666 | TT_TASK | Excavate up to -6.5mPD (4340m3) | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 |  | COMPLETED
667 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
668 | TT_TASK | Construction of temporary slab and entrance seal (622m3) | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
672 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 08 18:00:00 IST 2014 | Fri Dec 05 08:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
673 | TT_TASK | Erect external formwork (Base Slab) | Tue Dec 09 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 08 08:00:00 IST 2014 | Tue Dec 09 18:00:00 IST 2014 |  | COMPLETED
674 | TT_TASK | Rebar fixing (Base Slab) | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 18:00:00 IST 2014 | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
675 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Dec 15 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Mon Dec 15 18:00:00 IST 2014 |  | COMPLETED
676 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Dec 17 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Tue Dec 16 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 |  | COMPLETED
677 | TT_TASK | Curing (Base Slab) | Thu Dec 18 08:00:00 IST 2014 | Sat Dec 27 18:00:00 IST 2014 | Wed Dec 17 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
678 | TT_TASK | Removal of formwork (Base Slab) | Fri Dec 19 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 24 18:00:00 IST 2014 |  | COMPLETED
679 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
680 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 | Mon Jun 22 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 |  | COMPLETED
681 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Jun 13 08:00:00 IDT 2015 | Mon Jun 15 18:00:00 IDT 2015 | Thu Jun 25 01:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
682 | TT_TASK | Concreting (Wall & Roof) (444m3) | Tue Jun 16 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
683 | TT_TASK | Curing (Wall & Roof) | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
684 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 |  | COMPLETED
685 | TT_TASK | Removal external formwork (Wall) | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
686 | TT_TASK | Side walkway and cable bracket (360m3) | Sat Jul 18 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Sat Jul 18 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
687 | TT_TASK | Access opening to DC (DC access period) | Tue Oct 06 08:00:00 IDT 2015 | Fri Mar 04 18:00:00 IST 2016 | Tue Oct 06 08:00:00 IDT 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
688 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Sat Dec 12 08:00:00 IST 2015 | Mon Jan 18 18:00:00 IST 2016 | Tue Nov 03 00:00:00 IST 2015 | Mon Nov 30 18:00:00 IST 2015 |  | COMPLETED
690 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 | Tue Apr 12 08:00:00 IDT 2016 | Wed Apr 13 18:00:00 IDT 2016 |  | COMPLETED
691 | TT_TASK | Erect external formwork (Base Slab) | Mon May 23 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Thu Apr 14 08:00:00 IDT 2016 | Fri Apr 15 18:00:00 IDT 2016 |  | COMPLETED
692 | TT_TASK | Rebar fixing (Base Slab) | Wed May 25 08:00:00 IDT 2016 | Fri May 27 18:00:00 IDT 2016 | Sat Apr 16 08:00:00 IDT 2016 | Tue Apr 19 18:00:00 IDT 2016 |  | COMPLETED
693 | TT_TASK | Erect internal kicker formwork (Base Slab) | Sat May 28 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 | Wed Apr 20 08:00:00 IDT 2016 | Thu Apr 21 18:00:00 IDT 2016 |  | COMPLETED
694 | TT_TASK | Concreting (Base Slab) (225m3) | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 | Fri Apr 22 08:00:00 IDT 2016 | Fri Apr 22 18:00:00 IDT 2016 |  | COMPLETED
695 | TT_TASK | Curing (Base Slab) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 08 18:00:00 IDT 2016 | Sat Apr 23 08:00:00 IDT 2016 | Fri Apr 29 18:00:00 IDT 2016 |  | COMPLETED
696 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Sat Apr 30 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
697 | TT_TASK | Removal of formwork (Base Slab) | Tue May 24 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Mon May 09 08:00:00 IDT 2016 | Tue May 10 18:00:00 IDT 2016 |  | COMPLETED
698 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed May 25 08:00:00 IDT 2016 | Sat May 28 18:00:00 IDT 2016 | Wed May 11 08:00:00 IDT 2016 | Mon May 16 18:00:00 IDT 2016 |  | COMPLETED
699 | TT_TASK | Rebar fixing (Wall & Roof) | Mon May 30 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 17 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 |  | COMPLETED
700 | TT_TASK | Erect external formwork (Wall & Roof) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 03 18:00:00 IDT 2016 | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 |  | COMPLETED
701 | TT_TASK | Concreting (Wall & Roof) (444m3) | Sat Jun 04 08:00:00 IDT 2016 | Sat Jun 04 18:00:00 IDT 2016 | Mon May 23 08:00:00 IDT 2016 | Mon May 23 18:00:00 IDT 2016 |  | COMPLETED
702 | TT_TASK | Curing (Wall & Roof) | Mon Jun 06 08:00:00 IDT 2016 | Tue Jun 14 18:00:00 IDT 2016 | Tue May 24 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 |  | COMPLETED
703 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 15 08:00:00 IDT 2016 | Wed Jun 15 18:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 |  | COMPLETED
704 | TT_TASK | Removal external formwork (Wall) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
705 | TT_TASK | Side walkway and cable bracket (102m3) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 |  | COMPLETED
706 | TT_TASK | Access opening to DC (DC access period) | Sat Jun 18 08:00:00 IDT 2016 | Thu Jul 14 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
707 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Fri Jul 15 08:00:00 IDT 2016 | Wed Aug 17 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
709 | TT_TASK | Backfilling between tunnels (2000m3) | Thu Sep 01 08:00:00 IDT 2016 | Sat Sep 17 18:00:00 IDT 2016 | Tue Sep 13 08:00:00 IDT 2016 | Fri Sep 30 18:00:00 IDT 2016 |  | COMPLETED
710 | TT_TASK | Remove Strut S2 | Mon Oct 03 08:00:00 IDT 2016 | Wed Oct 05 18:00:00 IDT 2016 | Mon Oct 03 08:00:00 IDT 2016 | Tue Oct 11 18:00:00 IDT 2016 |  | COMPLETED
711 | TT_TASK | Backfilling up top S1 Soffit | Thu Oct 06 08:00:00 IDT 2016 | Fri Oct 21 18:00:00 IDT 2016 | Fri Oct 28 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
712 | TT_TASK | Remove Strut S1 | Sat Oct 22 08:00:00 IDT 2016 | Mon Oct 24 18:00:00 IDT 2016 | Tue Oct 11 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
713 | TT_TASK | Backfilling up top S0 Soffit | Mon Nov 07 08:00:00 IST 2016 | Sat Nov 12 18:00:00 IST 2016 | Tue Nov 01 08:00:00 IST 2016 | Sat Nov 05 18:00:00 IST 2016 |  | COMPLETED
714 | TT_TASK | Remove Strut S0 | Mon Nov 14 08:00:00 IST 2016 | Tue Nov 15 18:00:00 IST 2016 | Mon Nov 07 08:00:00 IST 2016 | Tue Nov 08 18:00:00 IST 2016 |  | COMPLETED
715 | TT_TASK | Backfilling up to ground level | Wed Nov 16 08:00:00 IST 2016 | Fri Nov 18 18:00:00 IST 2016 | Wed Nov 09 08:00:00 IST 2016 | Fri Nov 11 18:00:00 IST 2016 |  | COMPLETED
719 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
720 | TT_TASK | Pre-drilling and guidewall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
721 | TT_TASK | D-wall construction (1451m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
722 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 |  | COMPLETED
724 | TT_TASK | Excavate from ground level to formation level -5.5mPD (4559m3) | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 |  | COMPLETED
725 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 |  | COMPLETED
726 | TT_TASK | Placing of blinding layer (South Bound) | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 |  | COMPLETED
727 | TT_TASK | Placing of blinding layer (North Bound) | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
729 | TT_TASK | Construction of Bay 2 to Bay 7a (3565m3) | Mon Jun 04 08:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 | Mon Jun 04 18:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 |  | COMPLETED
730 | TT_TASK | Side walkway and cable bracket (Southbound) | Fri Oct 02 08:00:00 IDT 2015 | Fri Nov 06 18:00:00 IST 2015 | Fri Oct 02 08:00:00 IDT 2015 | Sat Oct 31 18:00:00 IST 2015 |  | COMPLETED
731 | TT_TASK | Side walkway and cable bracket (Northbound) | Tue May 03 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 |  | COMPLETED
733 | TT_TASK | Backfilling (1344m3) | Wed Nov 07 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 | Wed Nov 07 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
736 | TT_TASK | Scheme Design, Mobilization, Site set up & Material delivery and Instrumentations | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
737 | TT_TASK | Downstream pipe pile wall construction (45 nos.) and grout curtain (45 nos.) | Mon Nov 12 08:00:00 IST 2012 | Fri Jan 25 18:00:00 IST 2013 | Mon Nov 12 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
738 | TT_TASK | Curtain Grout for cut slope (120 nos.) | Fri Jul 26 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
739 | TT_TASK | Drilling for ground improvement only (if require) | Mon Dec 10 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
740 | TT_TASK | If settlement reach the AAA alarm & action level TAM grouting will apply during excavation | Thu Apr 11 08:00:00 IDT 2013 | Thu May 16 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
741 | TT_TASK | Erection of temporary working platform for Up stream and Installation of Instrumentation System | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
742 | TT_TASK | Upstream pipe pile wall construction adjacent to WTSSTR, (17nos.) | Thu Dec 27 08:00:00 IST 2012 | Mon Jan 28 18:00:00 IST 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
743 | TT_TASK | Upstream pipe pile wall construction at Kam Tin River, 15m depth, 42nos. 1drill rig) | Tue Jan 29 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
744 | TT_TASK | Excavation and soil nail installation | Tue Apr 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
745 | TT_TASK | Excavation for rock and blinding layer | Sat Aug 24 08:00:00 IDT 2013 | Sat Sep 28 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
750 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
751 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
752 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
753 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
754 | TT_TASK | Concreting (164m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
755 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
756 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
757 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
758 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
759 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
760 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
761 | TT_TASK | Concreting (242m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
762 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
763 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
764 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
765 | TT_TASK | Removal internal falsework and formwork for roof | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
766 | TT_TASK | Side walkway and cable bracket (19m3) | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
770 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
771 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
772 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
773 | TT_TASK | Erect internal kicker formwork | Thu Nov 28 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 09 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
774 | TT_TASK | Concreting (121m3) | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
775 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
776 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
777 | TT_TASK | Removal of formwork | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
778 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
779 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
780 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
781 | TT_TASK | Concreting (121m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
782 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
783 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
784 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
785 | TT_TASK | Removal internal falsework and formwork for roof | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
786 | TT_TASK | Side walkway and cable bracket (38m3) | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
788 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
789 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
790 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
791 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
792 | TT_TASK | Concreting (240m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
793 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
794 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
795 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
796 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
797 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
798 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
799 | TT_TASK | Concreting (240m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
800 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
801 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
802 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
803 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
804 | TT_TASK | Side walkway and cable bracket | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
806 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
807 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
808 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
809 | TT_TASK | Concreting (222m3) | Wed Nov 06 08:00:00 IST 2013 | Wed Nov 06 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
810 | TT_TASK | Curing | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
811 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
812 | TT_TASK | Removal of formwork | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
815 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
816 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
817 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
818 | TT_TASK | Erect internal kicker formwork | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
819 | TT_TASK | Concreting (111m3) | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
820 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
821 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
822 | TT_TASK | Removal of formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
823 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
824 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
825 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
826 | TT_TASK | Concreting (220m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
827 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
828 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
829 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
830 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
831 | TT_TASK | Side walkway and cable bracket (38m3) | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 |  | COMPLETED
833 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
834 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
835 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
836 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
837 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
838 | TT_TASK | Curing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
839 | TT_TASK | Preparation of construction joint for base slab | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
840 | TT_TASK | Removal of formwork | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
841 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
842 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
843 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
844 | TT_TASK | Concreting (327m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
845 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
846 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
847 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
848 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
849 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
851 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 20 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
852 | TT_TASK | Rebar fixing | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
853 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 08:00:00 IDT 2013 |  | COMPLETED
854 | TT_TASK | Concreting (225m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
855 | TT_TASK | Curing | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
856 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
857 | TT_TASK | Removal of formwork | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
860 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 27 08:00:00 IST 2013 | Wed Nov 27 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
861 | TT_TASK | Erect external formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
862 | TT_TASK | Rebar fixing | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
863 | TT_TASK | Erect internal kicker formwork | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
864 | TT_TASK | Concreting (222m3) | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
865 | TT_TASK | Curing | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Mon Oct 28 18:00:00 IST 2013 |  | COMPLETED
866 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
867 | TT_TASK | Removal of formwork | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
868 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
869 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
870 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
871 | TT_TASK | Concreting (222m3) | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 |  | COMPLETED
872 | TT_TASK | Curing | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 07 18:00:00 IST 2014 |  | COMPLETED
873 | TT_TASK | Preparation of construction joint for wall and roof | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
874 | TT_TASK | Removal external and internal formwork for wall | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
875 | TT_TASK | Removal internal falsework and formwork for roof | Mon Feb 10 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
876 | TT_TASK | Side walkway and cable bracket (38m3) | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 |  | COMPLETED
878 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
879 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
880 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
881 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
882 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
883 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
884 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
885 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
886 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
887 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
888 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
889 | TT_TASK | Concreting (222m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
890 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
892 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
893 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
894 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
896 | TT_TASK | Placing of waterproof member T-lock & testing | Mon Nov 18 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
897 | TT_TASK | Rebar fixing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Wed Oct 23 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
898 | TT_TASK | Erect external formwork | Fri Nov 22 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
899 | TT_TASK | Concreting (222m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
900 | TT_TASK | Curing | Tue Nov 26 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
901 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
902 | TT_TASK | Removal of formwork | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
905 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
906 | TT_TASK | Erect external formwork | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
907 | TT_TASK | Rebar fixing | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
908 | TT_TASK | Erect internal kicker formwork | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
909 | TT_TASK | Concreting (330m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
910 | TT_TASK | Curing | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
911 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
912 | TT_TASK | Removal of formwork | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
913 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
914 | TT_TASK | Rebar fixing | Wed Nov 20 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
915 | TT_TASK | Erect external formwork | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
916 | TT_TASK | Concreting (330m3) | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
917 | TT_TASK | Curing | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
918 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
919 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
920 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
921 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
923 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
924 | TT_TASK | Erect external formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
925 | TT_TASK | Rebar fixing | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
926 | TT_TASK | Erect internal kicker formwork | Wed Dec 04 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
927 | TT_TASK | Concreting (240m3) | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
928 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
929 | TT_TASK | Preparation of construction joint for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
930 | TT_TASK | Removal of formwork | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
931 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
932 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
933 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
934 | TT_TASK | Concreting (240m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
935 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
936 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
937 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
938 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
939 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
941 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
942 | TT_TASK | Rebar fixing | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
943 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
944 | TT_TASK | Concreting (240m3) | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
945 | TT_TASK | Curing | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
946 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
947 | TT_TASK | Removal of formwork | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
950 | TT_TASK | Placing of waterproof member T-lock & testing | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
951 | TT_TASK | Erect external formwork | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
952 | TT_TASK | Rebar fixing | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
953 | TT_TASK | Erect internal kicker formwork | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
954 | TT_TASK | Concreting (200m3) | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
955 | TT_TASK | Curing | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
956 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
957 | TT_TASK | Removal of formwork | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
958 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 29 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
959 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
960 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
961 | TT_TASK | Concreting (200m3) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
962 | TT_TASK | Curing | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
963 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
964 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 13 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
965 | TT_TASK | Removal internal falsework and formwork for roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
966 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 |  | COMPLETED
968 | TT_TASK | Placing of waterproof member T-lock & testing | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
969 | TT_TASK | Erect external formwork | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
970 | TT_TASK | Rebar fixing | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
971 | TT_TASK | Erect internal kicker formwork | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
972 | TT_TASK | Concreting (220m3) | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
973 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
974 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
975 | TT_TASK | Removal of formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
976 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
977 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
978 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
979 | TT_TASK | Concreting (220m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
980 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
981 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
982 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
983 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
984 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
986 | TT_TASK | Placing of waterproof member T-lock & testing | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
987 | TT_TASK | Rebar fixing | Mon Nov 25 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
988 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
989 | TT_TASK | Concreting (222m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
990 | TT_TASK | Curing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
991 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
992 | TT_TASK | Removal of formwork | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
994 | TT_TASK | Removal of Temporary Nullah | Sat Mar 01 08:00:00 IST 2014 | Sat Jun 21 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
995 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (5218m3) | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 |  | COMPLETED
996 | TT_TASK | Reinstate the permenant Retaining wall of Nullah | Sat Mar 01 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Tue Mar 04 08:00:00 IST 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
997 | TT_TASK | Reinstate Nullah Base of original route | Tue Feb 25 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Tue Feb 25 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
998 | TT_TASK | Reinstate Nullah to original route | Sat Mar 29 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Sat Mar 29 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
999 | TT_TASK | Construction & connect East Box Culvert from Box 6B to KTR | Mon Apr 14 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Mon Feb 10 08:00:00 IST 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
1000 | TT_TASK | Reinstatement of Wang Toi Shan Shan Tsuen Road | Tue Dec 01 08:00:00 IST 2015 | Wed Jul 13 18:00:00 IDT 2016 | Tue Dec 01 08:00:00 IST 2015 | Mon Jul 18 18:00:00 IDT 2016 |  | COMPLETED
1003 | TT_TASK | Pre-drilling at Works Area 4.4 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
1004 | TT_TASK | Site Setup and guide wall | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1005 | TT_TASK | D-wall construction (3104m3) | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 |  | COMPLETED
1006 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
1008 | TT_TASK | Excavate up to +8.0mPD (775m3) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1009 | TT_TASK | Install Strut S1 +8.5mPD | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 |  | COMPLETED
1010 | TT_TASK | Excavate up to +4.5mPD (2713m3) | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 |  | COMPLETED
1011 | TT_TASK | Install Strut S2 +5.0mPD | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
1012 | TT_TASK | Excavate up to +0.5mPD (3100m3) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 |  | COMPLETED
1013 | TT_TASK | Install Strut S3 +1.0mPD | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1014 | TT_TASK | Excavate up to -3.0mPD (2713m3) | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1015 | TT_TASK | Install Strut S4 -2.5mPD | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 |  | COMPLETED
1016 | TT_TASK | Excavate up to -5.5mPD (4952m3) | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1017 | TT_TASK | Placing of blinding layer | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1021 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1022 | TT_TASK | Erect external formwork for base slab | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1023 | TT_TASK | Rebar fixing for base slab | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1024 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 26 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1025 | TT_TASK | Concreting for base slab (350m3) | Thu Jun 27 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1026 | TT_TASK | Curing for base slab | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1027 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1028 | TT_TASK | Removal of formwork for base slab | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1029 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1030 | TT_TASK | Removal strut S4 and S3 | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1032 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1033 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1034 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1035 | TT_TASK | Concreting for wall and roof (489m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1036 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1037 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1038 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1039 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1040 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1043 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1044 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1045 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1046 | TT_TASK | Curing for wall and roof | Sat Jun 22 08:00:00 IDT 2013 | Mon Jul 01 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1047 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1048 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1050 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Tue Dec 17 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1053 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1054 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1055 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1056 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1057 | TT_TASK | Concreting for base slab (350m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1058 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1059 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1060 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1061 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1062 | TT_TASK | Removal strut S4 and S3 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1064 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1065 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1066 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1067 | TT_TASK | Concreting for wall and roof (489m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1068 | TT_TASK | Curing for wall and roof | Wed Jun 12 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1069 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1070 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 14 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1071 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1072 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Feb 13 08:00:00 IST 2014 | Tue Feb 18 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1074 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1075 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1076 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1077 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1078 | TT_TASK | Curing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1079 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1080 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1081 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1082 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 16 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1084 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (2343m3) | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1085 | TT_TASK | Placing 0.5m thk concrete lateral support (+3.96mPD) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1086 | TT_TASK | Removal strut S2 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 23 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1088 | TT_TASK | Construction of Temporary Culvert (open channel) | Tue Jun 25 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1089 | TT_TASK | Temporary box culvert (At Box 6B Area) Saw Cut D-wall | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 |  | COMPLETED
1090 | TT_TASK | Erect 3m high block wall | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 |  | COMPLETED
1091 | TT_TASK | Connection to East Box Culvert (823B portion) | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 |  | COMPLETED
1092 | TT_TASK | Blinding | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
1093 | TT_TASK | Temporary box culvert (Outside Box 6B Area) Sheet piling | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 |  | COMPLETED
1094 | TT_TASK | ELS Works | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
1095 | TT_TASK | Blinding | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
1096 | TT_TASK | Removal of Temporary Culvert and Reinstatement | Fri May 16 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
1098 | TT_TASK | Reinstatement of TOA's | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 |  |  | IN_PROGRESS
1099 | TT_TASK | Hydroseeding works | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 | Wed Nov 30 18:00:00 IST 2016 |  | COMPLETED
1100 | TT_TASK | Tree Planting works | Thu Sep 01 08:00:00 IDT 2016 | Sat Dec 03 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
1101 | TT_TASK | Woodland Shrub Mix | Thu Sep 01 08:00:00 IDT 2016 | Fri Nov 18 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  | 200.0 | IN_PROGRESS
1104 | TT_TASK | Kam Tin River Diversion (Stage 1-3) | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1106 | TT_TASK | Concrete fill up to +8.0mPD near side A mass concrete wall | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 |  | COMPLETED
1107 | TT_TASK | Construction of mass concrete wall to +8.0mPD at side A (4 bay CH A80~A120) | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1108 | TT_TASK | Construction of base slab lining and low flow channel (4 bay A9~A10, B8~B9; LFC CH 80~110) | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1109 | TT_TASK | Construction of mass concrete wall to +8.0mPD of side B (3 bay CH B60~B90) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1110 | TT_TASK | Construction of T-shaped retaining wall (1 Bay CH B50~B60) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1111 | TT_TASK | Soil backfill at side A from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1112 | TT_TASK | Concrete backfill at side B from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1113 | TT_TASK | Removal strut at +8.5mPD near side A | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1114 | TT_TASK | Concrete fill up to +11.0mPD near side A mass concrete wall | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1115 | TT_TASK | Placing concrete block at side A from +8.0mPD to +11.0mpd at side A (4 bay CH A80~A120) | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1116 | TT_TASK | Soil backfill at side A from +8.0mPD to +11.0mPD | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1117 | TT_TASK | Removal strut at +8.5mPD near side B | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1118 | TT_TASK | Placing concrete block at side B from +8.0mPD to +11.0mPD (4 bay CH B60~B90) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1119 | TT_TASK | Concrete backfill at side B from +8.0mPD to +11.0mPD | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1121 | TT_TASK | Placing temporary concrete block to Up stream at CH30 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 |  | COMPLETED
1122 | TT_TASK | Placing temporary concrete block to Up stream at CH160 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1123 | TT_TASK | Excavation from GL to FL +5.0mPD Up stream (Low flow channel CH 30~60) | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1124 | TT_TASK | Excavation from GL to FL +5.0mPD Down stream (Low flow channel CH 130~160) | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1125 | TT_TASK | Construction of T-shaped retaining wall at Up stream of side B (2 Bay CH B30~B50) | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1126 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (3 bay CH B90~B120) | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1127 | TT_TASK | Construction of Up stream base slab lining and low flow channel (6 Bay A1~A4, B3~B4; Low flow channel CH 30~50) | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1128 | TT_TASK | Construction of Down stream base slab lining and low flow channel (5 Bay A14~A16, B14~B15; LFC CH 140~170) | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1129 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Up stream and saw cut D-wall | Fri Jun 14 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1130 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Down stream and saw cut D-wall | Wed Jun 19 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1131 | TT_TASK | Construction of remaining Up stream base slab lining and low flow channel (7 bay A5~A8, B5~B7; LFC CH 50~80) | Thu Jun 27 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1132 | TT_TASK | Construction of remaining Down stream base slab lining and low flow channel (7 bay A11~A13, B10~B13; LFC CH 110~140) | Wed Jul 03 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1134 | TT_TASK | Relocation of temporary concrete block at Up stream for construction of mass concrete wall at side B | Sat Jul 20 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1135 | TT_TASK | Relocation of temporary concrete block at Down stream for construction of mass concrete wall at side B | Tue Jul 23 08:00:00 IDT 2013 | Wed Jul 24 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1136 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Up stream of side B (3 bay CH B0~B30) | Tue Jul 23 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1137 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (4 bay CH B0~B30) | Thu Jul 25 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1141 | TT_TASK | Application of power supply, environmental permits and construction substation | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1142 | TT_TASK | Procurement and Confirmation of the order of 1st tunnel boring machine | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 |  | COMPLETED
1143 | TT_TASK | Prepare on-demand bond or bank guarantee for the procurement of TBM and submit to Engineer for approval | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 |  | COMPLETED
1144 | TT_TASK | TBM design and submission for approval | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
1145 | TT_TASK | TBM materials order and delivery to factory | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 |  | COMPLETED
1146 | TT_TASK | TBM equipments order and delivery to factory | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 |  | COMPLETED
1147 | TT_TASK | TBM Fabrication | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
1148 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 |  | COMPLETED
1149 | TT_TASK | TBM test Run | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 |  | COMPLETED
1150 | TT_TASK | TBM disassembly and packing for shipping to HK | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 |  | COMPLETED
1151 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
1152 | TT_TASK | Ground treatment for TBM lanching shaft | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 |  | COMPLETED
1153 | TT_TASK | Ground treatment for Cross Passage Tunnel | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1154 | TT_TASK | Box7A Setup TBM facilities, install noise enclosure and CNP application | Fri Jun 01 08:00:00 IDT 2012 | Sat Jan 26 18:00:00 IST 2013 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1155 | TT_TASK | Notice to Contract 824 the anticipated dates of break out TBM Shaft | Sat Jun 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1156 | TT_TASK | Fabrication of tunnel segment mould | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
1157 | TT_TASK | Fabrication 50% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1158 | TT_TASK | Fabrication 100% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
1159 | TT_TASK | Fabrication 30% of North Tunnel North Bound (Uptrack) Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1160 | TT_TASK | Fabrication 60% of North Tunnel North Bound (Uptrack) Precast Lining | Thu Oct 18 08:00:00 IST 2012 | Thu Feb 21 18:00:00 IST 2013 | Thu Oct 18 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1161 | TT_TASK | Fabrication 100% of North Tunnel North Bound (Uptrack) Precast Lining | Mon Aug 19 08:00:00 IDT 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Dec 03 08:00:00 IST 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1163 | TT_TASK | Assemble, T&C of TBM | Fri Jun 01 08:00:00 IDT 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Oct 16 00:00:00 IST 2012 |  | COMPLETED
1164 | TT_TASK | TBM drive & lining installation CH123+369 to CH123+283 Initial Drive (86m) | Sat Nov 03 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 | Wed Oct 17 00:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1165 | TT_TASK | Change Plant (Back-up cars) | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1166 | TT_TASK | TBM drive & lining installation CH123+283 to CH123+183 | Thu Jun 27 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1167 | TT_TASK | TBM drive & lining installation CH123+183 to CH123+083 | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1168 | TT_TASK | TBM drive & lining installation CH123+083 to CH122+983 | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1169 | TT_TASK | TBM drive & lining installation CH122+983 to CH122+883 | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1170 | TT_TASK | TBM drive & lining installation CH122+883 to CH122+783 | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Jun 13 08:00:00 IDT 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
1171 | TT_TASK | TBM drive & lining installation CH122+783 to CH122+683 | Sat Nov 02 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1172 | TT_TASK | TBM drive & lining installation CH122+683 to CH122+583 | Tue Dec 03 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Wed Feb 26 18:00:00 IST 2014 |  | COMPLETED
1173 | TT_TASK | TBM drive & lining installation CH122+583 to CH122+491 | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Feb 27 08:00:00 IST 2014 | Sat Aug 16 00:00:00 IDT 2014 |  | COMPLETED
1174 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1175 | TT_TASK | Dis-assemble TBM | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
1176 | TT_TASK | Invert slab, side walkway | Sat Oct 04 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 | Mon Sep 15 08:00:00 IDT 2014 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1177 | TT_TASK | Installation of cable bracket | Tue Dec 30 08:00:00 IST 2014 | Tue Jan 13 18:00:00 IST 2015 | Fri Sep 12 08:00:00 IDT 2014 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
1178 | TT_TASK | Provision of assess open for DC and modify of strut S1 and S2 at north bound | Tue Nov 04 11:12:00 IST 2014 | Thu Dec 04 11:12:00 IST 2014 | Wed Oct 01 08:00:00 IDT 2014 | Sat Oct 18 18:00:00 IDT 2014 |  | COMPLETED
1180 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Oct 06 13:00:00 IDT 2014 | Mon Oct 20 12:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
1181 | TT_TASK | Assemble, T&C of TBM | Mon Nov 03 08:00:00 IST 2014 | Fri Jan 02 18:00:00 IST 2015 | Sat Oct 04 08:00:00 IDT 2014 | Fri Nov 28 18:00:00 IST 2014 |  | COMPLETED
1182 | TT_TASK | Setup back-up plant for final drive | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
1183 | TT_TASK | Reinstate of noise enclosure | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Sat Nov 29 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1184 | TT_TASK | TBM drive & lining installation CH123+384 to CH123+284 (Initial Drive) | Sat Dec 06 08:00:00 IST 2014 | Thu Jan 22 18:00:00 IST 2015 | Tue Dec 02 00:00:00 IST 2014 | Tue Jan 20 18:00:00 IST 2015 |  | COMPLETED
1185 | TT_TASK | TBM drive & lining installation CH123+184 to CH123+084 | Wed Jan 21 08:00:00 IST 2015 | Wed Jan 28 18:00:00 IST 2015 | Wed Jan 21 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 |  | COMPLETED
1186 | TT_TASK | TBM drive & lining installation CH123+084 to CH122+984 | Wed Feb 04 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 | Thu Feb 12 08:00:00 IST 2015 | Thu Feb 26 18:00:00 IST 2015 |  | COMPLETED
1187 | TT_TASK | TBM drive & lining installation CH122+984 to CH122+884 | Thu Feb 12 08:00:00 IST 2015 | Tue Feb 24 18:00:00 IST 2015 | Fri Feb 27 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1188 | TT_TASK | TBM drive & lining installation CH122+884 to CH122+784 | Tue Mar 10 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Wed May 27 18:00:00 IDT 2015 |  | COMPLETED
1189 | TT_TASK | TBM drive & lining installation CH122+784 to CH122+684 | Wed May 06 08:00:00 IDT 2015 | Thu May 14 18:00:00 IDT 2015 | Thu May 28 08:00:00 IDT 2015 | Sat Jul 11 18:00:00 IDT 2015 |  | COMPLETED
1190 | TT_TASK | TBM drive & lining installation CH122+684 to CH122+584 | Fri Jul 03 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
1191 | TT_TASK | TBM drive & lining installation CH122+584 to CH122+506 | Tue Nov 03 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 |  | COMPLETED
1192 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 |  | COMPLETED
1193 | TT_TASK | Dis-assemble TBM | Wed Dec 16 08:00:00 IST 2015 | Fri Jan 22 18:00:00 IST 2016 | Sun Dec 13 08:00:00 IST 2015 | Sun Mar 13 18:00:00 IST 2016 |  | COMPLETED
1194 | TT_TASK | Invert slab, side walkway | Fri Apr 01 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 | Mon Mar 14 08:00:00 IST 2016 | Tue May 24 18:00:00 IDT 2016 |  | COMPLETED
1195 | TT_TASK | Installation of cable bracket | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Mar 15 18:00:00 IST 2016 |  | COMPLETED
1196 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Mon Feb 01 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 22 18:00:00 IST 2016 |  | COMPLETED
1199 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 1 (From Downtrack to Centre of CP) | Thu Apr 10 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Sat Jun 28 18:00:00 IDT 2014 |  | COMPLETED
1200 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Sun Nov 09 18:00:00 IST 2014 |  | COMPLETED
1201 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1202 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 18:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1203 | TT_TASK | Excavation 0-4mts with Shotcrete | Mon Feb 02 08:00:00 IST 2015 | Tue Feb 17 18:00:00 IST 2015 | Mon Feb 23 08:00:00 IST 2015 | Mon Mar 30 18:00:00 IDT 2015 |  | COMPLETED
1204 | TT_TASK | Invert Concrete | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1205 | TT_TASK | Wall and Roof concrete | Thu Apr 16 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 |  | COMPLETED
1206 | TT_TASK | Dismantle Temporary frame | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 |  | COMPLETED
1207 | TT_TASK | Install Door to Cross Passage (By contract 827) | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 |  | COMPLETED
1208 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 2 (From Centre of CP to Uptrack) | Sat Oct 17 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Sep 07 08:00:00 IDT 2015 | Tue Dec 01 18:00:00 IST 2015 |  | COMPLETED
1209 | TT_TASK | Probe/Grout | Thu Jun 25 08:00:00 IDT 2015 | Mon Jul 06 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Fri Apr 10 18:00:00 IDT 2015 |  | COMPLETED
1210 | TT_TASK | Coring of Segment | Tue Jul 07 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Sat Apr 11 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1211 | TT_TASK | Removal of segment | Sat Jul 11 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
1212 | TT_TASK | Excavation 0-4mts with Shotcrete | Wed Jul 15 08:00:00 IDT 2015 | Sat Jul 25 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1213 | TT_TASK | Invert Concrete | Sat Jul 18 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 | Thu May 07 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1214 | TT_TASK | Wall and Roof concrete | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1215 | TT_TASK | Dismantle Temporary frame | Tue Jan 19 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 04 18:00:00 IST 2016 |  | COMPLETED
1216 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Feb 22 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Fri Feb 05 08:00:00 IST 2016 | Sat Feb 06 18:00:00 IST 2016 |  | COMPLETED
1218 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 1 (From Downtrack to Centre of CP) | Tue Mar 11 08:00:00 IST 2014 | Wed Mar 26 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1219 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Wed Nov 12 18:00:00 IST 2014 |  | COMPLETED
1220 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Thu Nov 13 08:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1221 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Tue Nov 18 08:00:00 IST 2014 | Thu Nov 20 18:00:00 IST 2014 |  | COMPLETED
1222 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Sat Nov 22 08:00:00 IST 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1223 | TT_TASK | Invert Concrete | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
1224 | TT_TASK | Wall and Roof concrete | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1225 | TT_TASK | Dismantle Temporary frame | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1226 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1227 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 2 (From Centre of CP to Uptrack) | Thu May 21 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Mar 09 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1228 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Mon May 04 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1229 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
1230 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1231 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 22 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
1232 | TT_TASK | Invert Concrete | Sat Aug 08 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Wed Jul 08 18:00:00 IDT 2015 |  | COMPLETED
1233 | TT_TASK | Wall and Roof concrete | Tue Aug 25 08:00:00 IDT 2015 | Mon Sep 07 18:00:00 IDT 2015 | Thu Jul 09 08:00:00 IDT 2015 | Sat Aug 15 18:00:00 IDT 2015 |  | COMPLETED
1234 | TT_TASK | Dismantle Temporary frame | Tue Sep 22 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 | Mon Aug 17 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 |  | COMPLETED
1235 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1237 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 1 (From Downtrack to Centre of CP) | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Sat May 24 18:00:00 IDT 2014 |  | COMPLETED
1238 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
1239 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1240 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 |  | COMPLETED
1241 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Mon Nov 17 08:00:00 IST 2014 | Sat Nov 29 18:00:00 IST 2014 |  | COMPLETED
1242 | TT_TASK | Invert Concrete | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 |  | COMPLETED
1243 | TT_TASK | Wall and Roof concrete | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 |  | COMPLETED
1244 | TT_TASK | Dismantle Temporary frame | Tue Dec 30 08:00:00 IST 2014 | Wed Jan 07 18:00:00 IST 2015 | Tue Dec 30 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1245 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1246 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 2 (From Centre of CP to Uptrack) | Fri May 08 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 |  | COMPLETED
1247 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
1248 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
1249 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Thu May 07 18:00:00 IDT 2015 |  | COMPLETED
1250 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
1251 | TT_TASK | Invert Concrete | Wed Aug 05 08:00:00 IDT 2015 | Fri Aug 14 18:00:00 IDT 2015 | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
1252 | TT_TASK | Wall and Roof concrete | Tue Sep 15 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Wed Aug 26 18:00:00 IDT 2015 |  | COMPLETED
1253 | TT_TASK | Dismantle Temporary frame | Sat Oct 17 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Oct 08 18:00:00 IDT 2015 |  | COMPLETED
1254 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1258 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 |  | COMPLETED
1259 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1260 | TT_TASK | D-wall construction (1192m3) | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 |  | COMPLETED
1261 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1262 | TT_TASK | Construct capping beam, cobble, etc. (including bay 6 and 5) | Sat Oct 27 08:00:00 IST 2012 | Sat Feb 16 18:00:00 IST 2013 | Sat Oct 27 08:00:00 IST 2012 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1264 | TT_TASK | Excavate up to +22.0mPD (1860m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1265 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 |  | COMPLETED
1266 | TT_TASK | Excavate up to +16.5mPD (3410m3) | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 |  | COMPLETED
1267 | TT_TASK | Install Strut S2 +17.0mPD | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 |  | COMPLETED
1268 | TT_TASK | Excavate up to +11.0mPD (3410m3) | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 |  | COMPLETED
1269 | TT_TASK | Install Strut S3 +11.5mPD | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 |  | COMPLETED
1270 | TT_TASK | Excavate up to +7.0mPD (2480m3) | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 |  | COMPLETED
1271 | TT_TASK | Install Strut S4 +7.5mPD | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1272 | TT_TASK | Excavate up to +3.5mPD (2170m3) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 |  | COMPLETED
1273 | TT_TASK | Install Strut S5 +4.0mPD | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1274 | TT_TASK | Excavate up to formation (2294m3) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1275 | TT_TASK | Construct temp. 500mm thick plain concrete base slab | Thu Oct 18 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 |  | COMPLETED
1276 | TT_TASK | Removal of South Bound strut to +9.50mPD | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1277 | TT_TASK | Removal of North Bound strut to +9.50mPD | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 |  | COMPLETED
1278 | TT_TASK | Construct temp. 500mm thick TBM concrete base slab | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1279 | TT_TASK | Construction entrance seal for TBM at South Bound | Mon Nov 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1280 | TT_TASK | Construction entrance seal for TBM at North Bound | Sat Jul 20 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1281 | TT_TASK | Saw cut South Bound diaphragm wall | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1282 | TT_TASK | Saw cut North Bound diaphragm wall | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1286 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 05 18:00:00 IDT 2014 | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 |  | COMPLETED
1287 | TT_TASK | Erect external formwork (Base Slab) | Sat Sep 06 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 21 18:00:00 IDT 2014 |  | COMPLETED
1288 | TT_TASK | Rebar fixing (Base Slab) | Wed Sep 10 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Tue Jul 22 08:00:00 IDT 2014 | Sat Jul 26 18:00:00 IDT 2014 |  | COMPLETED
1289 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Sep 15 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Sun Jul 27 08:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1290 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Thu Aug 14 18:00:00 IDT 2014 |  | COMPLETED
1291 | TT_TASK | Concreting (Base Slab) (225m3) | Sat Aug 09 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Fri Aug 15 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
1292 | TT_TASK | Curing (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
1293 | TT_TASK | Removal of formwork (Base Slab) | Tue Aug 12 08:00:00 IDT 2014 | Tue Aug 12 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1294 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed Aug 13 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Mon Sep 15 18:00:00 IDT 2014 |  | COMPLETED
1295 | TT_TASK | Rebar fixing (Wall & Roof) | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 |  | COMPLETED
1296 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 |  | COMPLETED
1297 | TT_TASK | Clearing and inspection (Wall & Roof) | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
1298 | TT_TASK | Concreting (Wall & Roof) (450m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
1299 | TT_TASK | Curing (Wall & Roof) | Sat Oct 11 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
1300 | TT_TASK | Removal external formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1301 | TT_TASK | Removal internal falsework (Wall & Roof) | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 |  | COMPLETED
1302 | TT_TASK | Side walkway and cable bracket (102m3) | Sat Oct 18 08:00:00 IDT 2014 | Wed Oct 29 18:00:00 IST 2014 | Mon Sep 01 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1304 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Wed Nov 11 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Oct 19 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1305 | TT_TASK | Erect external formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 |  | COMPLETED
1306 | TT_TASK | Rebar fixing (Base Slab) | Mon Nov 16 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Tue Oct 27 08:00:00 IST 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1307 | TT_TASK | Erect internal kicker formwork (Base Slab) | Fri Nov 20 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Oct 31 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 |  | COMPLETED
1308 | TT_TASK | Clearing and inspection (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
1309 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1310 | TT_TASK | Curing (Base Slab) | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 |  | COMPLETED
1311 | TT_TASK | Removal of formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 |  | COMPLETED
1312 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
1313 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Dec 09 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
1314 | TT_TASK | Erect external formwork (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Thu Jan 07 18:00:00 IST 2016 |  | COMPLETED
1315 | TT_TASK | Clearing and inspection (Wall & Roof) | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Fri Jan 08 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
1316 | TT_TASK | Concreting (Wall & Roof) (450m3) | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
1317 | TT_TASK | Curing (Wall & Roof) | Tue Jan 12 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
1318 | TT_TASK | Removal external formwork (Wall ) | Thu Jan 14 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
1319 | TT_TASK | Removal internal falsework, formwork and reproping (Wall & Roof) | Thu Jan 28 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 |  | COMPLETED
1320 | TT_TASK | Side walkway and cable bracket (102m3) | Wed Dec 23 08:00:00 IST 2015 | Wed Jan 06 18:00:00 IST 2016 | Wed Nov 11 08:00:00 IST 2015 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
1322 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 |  | COMPLETED
1323 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 |  | COMPLETED
1324 | TT_TASK | Backfilling to 0.5m below S3 (+11.0mPD) (3486m3) | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 |  | COMPLETED
1325 | TT_TASK | Removal strut S3 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
1326 | TT_TASK | Backfilling to 0.5m below S2 (+16.5mPD) (3410m3) | Wed Mar 16 08:00:00 IST 2016 | Fri Apr 08 18:00:00 IDT 2016 | Wed Mar 16 08:00:00 IST 2016 | Tue Apr 12 18:00:00 IDT 2016 |  | COMPLETED
1327 | TT_TASK | Removal strut S2 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 |  | COMPLETED
1328 | TT_TASK | Backfilling to 0.5m below S1 (+22.0mPD) (3410m3) | Fri Apr 15 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 | Fri Apr 15 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
1329 | TT_TASK | Removal strut S1 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 |  | COMPLETED
1330 | TT_TASK | Backfilling to original ground level (approx. +25.0mPD) (1860m3) | Thu May 05 08:00:00 IDT 2016 | Tue May 17 18:00:00 IDT 2016 | Thu May 05 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
1333 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1334 | TT_TASK | D-wall construction (2844m3) | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1335 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1337 | TT_TASK | Excavate up to +22.0mPD (3720m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1338 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 |  | COMPLETED
1339 | TT_TASK | Excavate up to +16.5mPD (4880m3) | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 |  | COMPLETED
1340 | TT_TASK | Install Strut S2 +17.0mPD | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 |  | COMPLETED
1341 | TT_TASK | Excavate up to +11.0mPD (6820m3) | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
1342 | TT_TASK | Install Strut S3 +11.5mPD | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 |  | COMPLETED
1343 | TT_TASK | Excavate up to +7.0mPD (4960m3) | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 |  | COMPLETED
1344 | TT_TASK | Install Strut S4 +7.5mPD | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1345 | TT_TASK | Excavate up to +3.5mPD (4340m3) | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1346 | TT_TASK | Install Strut S5 +4.0mPD | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 |  | COMPLETED
1347 | TT_TASK | Excavate up to formation (4960m3) | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 |  | COMPLETED
1348 | TT_TASK | Construct temp. 500mm thick plain concrete base slab at Bay 5 & 6 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1349 | TT_TASK | Excavation to formation and place blinding Bay 4a | Thu Oct 18 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1350 | TT_TASK | Excavation to formation and place blinding Bay 4b | Fri Jun 21 08:00:00 IDT 2013 | Fri Jul 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1351 | TT_TASK | Excavation to formation and place blinding Bay3 | Sat Jul 13 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1352 | TT_TASK | Excavation to formation and place blinding Bay2 to Bay1 | Wed Jul 24 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1356 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 |  | COMPLETED
1357 | TT_TASK | Erect external formwork for base slab | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 |  | COMPLETED
1358 | TT_TASK | Rebar fixing for base slab | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1359 | TT_TASK | Erect internal kicker formwork for base slab | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1360 | TT_TASK | Concreting for base slab (363m3) | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1361 | TT_TASK | Curing for base slab | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1362 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1363 | TT_TASK | Removal of formwork for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1364 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1365 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 27 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1366 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1367 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1368 | TT_TASK | Curing for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1369 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1370 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 10 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1371 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 19 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jan 24 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1372 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 08 08:00:00 IST 2015 | Tue Jan 13 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1374 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 |  | COMPLETED
1375 | TT_TASK | Erect external formwork for base slab | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1376 | TT_TASK | Rebar fixing for base slab | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1377 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 |  | COMPLETED
1378 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1379 | TT_TASK | Curing for base slab | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1380 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1381 | TT_TASK | Removal of formwork for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1382 | TT_TASK | Rebar fixing for central slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1383 | TT_TASK | Erect external formwork for central slab | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1384 | TT_TASK | Concreting for central slab (450m3) | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1385 | TT_TASK | Curing for central slab | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1386 | TT_TASK | Preparation of construction joint for central slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1387 | TT_TASK | Removal of formwork for central slab | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1388 | TT_TASK | Removal strut S5 and S4 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1389 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1390 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1391 | TT_TASK | Erect external formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1392 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1393 | TT_TASK | Curing for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1394 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1395 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 08 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1396 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1397 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Nov 19 08:00:00 IST 2015 | Tue Nov 24 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 |  | COMPLETED
1400 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1401 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1402 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1403 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1404 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1405 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1406 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1407 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1408 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1409 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1410 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 10 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1411 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1412 | TT_TASK | Curing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1413 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1414 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1415 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1416 | TT_TASK | Side walkway and cable bracket | Fri Jan 02 08:00:00 IST 2015 | Wed Jan 07 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1418 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1419 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1420 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1421 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1422 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1423 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1424 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1425 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1426 | TT_TASK | Rebar fixing for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1427 | TT_TASK | Erect external formwork for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1428 | TT_TASK | Concreting for central slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1429 | TT_TASK | Curing for central slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1430 | TT_TASK | Preparation of construction joint for central slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1431 | TT_TASK | Removal of formwork for central slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 21 18:00:00 IST 2012 |  | COMPLETED
1432 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1433 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1434 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1435 | TT_TASK | Erect external formwork for wall | Mon Jul 15 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1436 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1437 | TT_TASK | Curing for wall and roof | Sun Jul 21 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1438 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1439 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 22 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1440 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 31 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1441 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Sep 16 08:00:00 IDT 2015 | Mon Sep 21 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1443 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1444 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1445 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1446 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1447 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1448 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1449 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1450 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1451 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1452 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1453 | TT_TASK | Erect external formwork for wall | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1454 | TT_TASK | Concreting for wall and roof (444m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1455 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1456 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1457 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Sat Feb 09 18:00:00 IST 2013 |  | COMPLETED
1458 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Nov 09 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Tue Oct 06 08:00:00 IDT 2015 | Sat Oct 10 18:00:00 IDT 2015 |  | COMPLETED
1461 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1462 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1463 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1464 | TT_TASK | Erect internal kicker formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1465 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1466 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1467 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1468 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1469 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1470 | TT_TASK | Curing | Wed Jun 12 08:00:00 IDT 2013 | Wed Jun 12 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1471 | TT_TASK | Removal strut S5 and S4 | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1473 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1474 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1475 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1476 | TT_TASK | Concreting for wall and roof (450m3) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1477 | TT_TASK | Curing for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1478 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1479 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1480 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 29 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1481 | TT_TASK | Side walkway and cable bracket | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1483 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1484 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1485 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1486 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1487 | TT_TASK | Curing for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1488 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1489 | TT_TASK | Removal external wall formwork for wall | Wed Jun 26 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1490 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1491 | TT_TASK | Side walkway and cable bracket | Fri Sep 04 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
1494 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1495 | TT_TASK | Erect external formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1496 | TT_TASK | Rebar fixing for base slab | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1497 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1498 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 |  | COMPLETED
1499 | TT_TASK | Curing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1500 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1501 | TT_TASK | Removal of formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1502 | TT_TASK | Shear beam | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1503 | TT_TASK | Curing | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1504 | TT_TASK | Removal strut S5 and S4 | Wed Jun 19 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1506 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 24 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1507 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1508 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1509 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1510 | TT_TASK | Curing for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1511 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1512 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1513 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1514 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
1516 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1517 | TT_TASK | Rebar fixing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1518 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1519 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1520 | TT_TASK | Curing for wall and roof | Sun Jun 23 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1521 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1522 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 25 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1523 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 03 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1524 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Aug 29 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1527 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1528 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Sat Dec 22 18:00:00 IST 2012 |  | COMPLETED
1529 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1530 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1531 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1532 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1533 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1534 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Fri Jan 11 18:00:00 IST 2013 |  | COMPLETED
1535 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Jan 12 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1536 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1537 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1539 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1540 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1541 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1542 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1543 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1544 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1545 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1546 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1547 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 |  | COMPLETED
1549 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1550 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Mon Feb 25 18:00:00 IST 2013 |  | COMPLETED
1551 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1552 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1553 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1554 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1555 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1556 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1557 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Aug 24 08:00:00 IDT 2015 | Fri Aug 28 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1560 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1561 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1562 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1563 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1564 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1565 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1566 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1567 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1568 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1569 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1570 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1572 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1573 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1574 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1575 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1576 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1577 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1578 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1579 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1580 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
1582 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1583 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1584 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1585 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1586 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1587 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1588 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1589 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1590 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Aug 18 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1593 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1594 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1595 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1596 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1597 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1598 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1599 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1600 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1601 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1602 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1603 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1605 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 31 18:00:00 IDT 2013 |  | COMPLETED
1606 | TT_TASK | Rebar fixing for wall and roof | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 |  | COMPLETED
1607 | TT_TASK | Erect external formwork for wall and roof | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 | Fri Sep 06 08:00:00 IDT 2013 | Thu Sep 12 18:00:00 IDT 2013 |  | COMPLETED
1608 | TT_TASK | Concreting for wall and roof (450m3) | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 |  | COMPLETED
1609 | TT_TASK | Curing for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1610 | TT_TASK | Preparation of construction joint for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1611 | TT_TASK | Removal external and internal formwork for wall | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Wed Sep 25 18:00:00 IDT 2013 |  | COMPLETED
1612 | TT_TASK | Removal internal falsework and formwork for roof | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1613 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 08 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1615 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 20 18:00:00 IST 2013 |  | COMPLETED
1616 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1617 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1618 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1619 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1620 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1621 | TT_TASK | Removal external wall formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1622 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1623 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Aug 12 08:00:00 IDT 2015 | Mon Aug 17 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1626 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1627 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1628 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Feb 14 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1629 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1630 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Mon Feb 18 18:00:00 IST 2013 |  | COMPLETED
1631 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1632 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1633 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1634 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1635 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1636 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1638 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jul 12 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1639 | TT_TASK | Rebar fixing for wall and roof | Wed Jul 17 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1640 | TT_TASK | Erect external formwork for wall and roof | Wed Aug 14 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1641 | TT_TASK | Concreting for wall and roof (450m3) | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1642 | TT_TASK | Curing for wall and roof | Sun Aug 11 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1643 | TT_TASK | Preparation of construction joint for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1644 | TT_TASK | Removal external and internal formwork for wall | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1645 | TT_TASK | Removal internal falsework and formwork for roof | Wed Aug 21 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1646 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 03 08:00:00 IST 2014 | Fri Mar 07 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1648 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1649 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1650 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Apr 09 08:00:00 IDT 2013 | Thu Apr 11 18:00:00 IDT 2013 |  | COMPLETED
1651 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1652 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1653 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1654 | TT_TASK | Removal external wall formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1655 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
1656 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Aug 06 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Mon Jul 27 08:00:00 IDT 2015 | Fri Jul 31 18:00:00 IDT 2015 |  | COMPLETED
1658 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Sep 12 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1659 | TT_TASK | Rebar fixing for roof | Tue Sep 17 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1660 | TT_TASK | Erect external formwork for roof | Thu Sep 19 08:00:00 IDT 2013 | Thu Sep 19 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1661 | TT_TASK | Concreting for roof (444m3) | Sat Sep 21 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1662 | TT_TASK | Curing for roof | Sun Sep 22 08:00:00 IDT 2013 | Tue Oct 01 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1663 | TT_TASK | Preparation of construction joint for roof | Mon Sep 23 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1664 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1665 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1668 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1669 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1670 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1671 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1672 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1673 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1674 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1675 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1676 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1677 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1678 | TT_TASK | Removal strut S5 and S4 | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1680 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Thu Apr 25 18:00:00 IDT 2013 |  | COMPLETED
1681 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri May 03 08:00:00 IDT 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
1682 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Thu May 16 08:00:00 IDT 2013 | Thu May 23 18:00:00 IDT 2013 |  | COMPLETED
1683 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1684 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1685 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1686 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Wed May 29 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1687 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1688 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 19 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1690 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Fri Apr 19 18:00:00 IDT 2013 |  | COMPLETED
1691 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1692 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Apr 25 08:00:00 IDT 2013 | Sat Apr 27 18:00:00 IDT 2013 |  | COMPLETED
1693 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1694 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1695 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1696 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1697 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1698 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 02 08:00:00 IDT 2015 | Sat Apr 11 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Feb 27 18:00:00 IST 2015 |  | COMPLETED
1700 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1701 | TT_TASK | Rebar fixing for roof | Tue Aug 06 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1702 | TT_TASK | Erect external formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1703 | TT_TASK | Concreting for roof (444m3) | Fri Aug 09 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 |  | COMPLETED
1704 | TT_TASK | Curing for roof | Thu Aug 01 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1705 | TT_TASK | Preparation of construction joint for roof | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 |  | COMPLETED
1706 | TT_TASK | Removal internal falsework and formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1707 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 09 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1710 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Wed Feb 20 18:00:00 IST 2013 |  | COMPLETED
1711 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1712 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1713 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1714 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1715 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1716 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1717 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1718 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1719 | TT_TASK | Curing | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1720 | TT_TASK | Removal strut S5 and S4 | Mon Jun 24 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1722 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1723 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1724 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Wed Jul 10 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1725 | TT_TASK | Concreting for wall and roof (450m3) | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1726 | TT_TASK | Curing for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1727 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1728 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 |  | COMPLETED
1729 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 |  | COMPLETED
1730 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1732 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1733 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1734 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1735 | TT_TASK | Concreting for wall and roof (450m3) | Tue Sep 03 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1736 | TT_TASK | Curing for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1737 | TT_TASK | Preparation of construction joint for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 |  | COMPLETED
1738 | TT_TASK | Removal external and internal formwork for wall | Thu Sep 05 08:00:00 IDT 2013 | Fri Sep 06 18:00:00 IDT 2013 | Thu Aug 22 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1739 | TT_TASK | Removal internal falsework and formwork for roof | Sat Sep 14 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 |  | COMPLETED
1740 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 05 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1742 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1743 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1744 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1745 | TT_TASK | Concreting for roof (363m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1746 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Sun Oct 20 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1747 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1748 | TT_TASK | Removal internal falsework and formwork for roof | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1749 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Dec 24 13:00:00 IST 2013 | Thu Jan 02 12:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1752 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1753 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1754 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1755 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Apr 12 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1756 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1757 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1758 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1759 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1760 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1761 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1762 | TT_TASK | Removal strut S5 and S4 | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1764 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Aug 05 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1765 | TT_TASK | Rebar fixing for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1766 | TT_TASK | Erect external formwork for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1767 | TT_TASK | Concreting for wall and roof (450m3) | Thu Aug 15 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1768 | TT_TASK | Curing for wall and roof | Fri Aug 16 08:00:00 IDT 2013 | Sun Aug 25 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1769 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1770 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1771 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 |  | COMPLETED
1772 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Feb 04 08:00:00 IST 2014 | Sat Feb 08 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1774 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Aug 07 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1775 | TT_TASK | Rebar fixing for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1776 | TT_TASK | Erect external formwork for wall and roof | Thu Aug 15 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1777 | TT_TASK | Concreting for wall and roof (450m3) | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1778 | TT_TASK | Curing for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1779 | TT_TASK | Preparation of construction joint for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 |  | COMPLETED
1780 | TT_TASK | Removal external and internal formwork for wall | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Wed Aug 21 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 |  | COMPLETED
1781 | TT_TASK | Removal internal falsework and formwork for roof | Mon Sep 16 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1782 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Nov 19 08:00:00 IST 2014 | Mon Nov 24 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1784 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1785 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1786 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1787 | TT_TASK | Concreting for roof (450m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1788 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1789 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1790 | TT_TASK | Removal internal falsework and formwork for roof | Fri Oct 18 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1791 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 13 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1794 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1795 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1796 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1797 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1798 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 28 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1799 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1800 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1801 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1802 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1803 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1804 | TT_TASK | Removal strut S5 and S4 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1806 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1807 | TT_TASK | Rebar fixing for wall and roof | Sat Jul 20 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1808 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1809 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1810 | TT_TASK | Curing for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1811 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1812 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 29 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1813 | TT_TASK | Removal internal falsework and formwork for roof | Tue Aug 06 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1814 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 18:00:00 IST 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1816 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1817 | TT_TASK | Rebar fixing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1818 | TT_TASK | Erect external formwork for wall and roof | Fri Jul 19 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1819 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1820 | TT_TASK | Curing for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Thu Mar 28 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1821 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Mar 29 08:00:00 IDT 2013 | Fri Mar 29 18:00:00 IDT 2013 |  | COMPLETED
1822 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Sat Mar 30 08:00:00 IDT 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1823 | TT_TASK | Removal internal falsework and formwork for roof | Fri Aug 02 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Mon Apr 01 18:00:00 IDT 2013 |  | COMPLETED
1824 | TT_TASK | Side walkway and cable bracket | Thu Nov 13 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1826 | TT_TASK | Erect internal formwork & Falsework for roof | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1827 | TT_TASK | Rebar fixing for roof | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 |  | COMPLETED
1828 | TT_TASK | Erect shutter formwork for roof | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 09 18:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1829 | TT_TASK | Concreting for roof (450m3) | Tue Sep 10 08:00:00 IDT 2013 | Tue Sep 10 18:00:00 IDT 2013 | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 |  | COMPLETED
1830 | TT_TASK | Curing for roof | Wed Sep 11 08:00:00 IDT 2013 | Fri Sep 20 18:00:00 IDT 2013 | Tue Jul 23 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 |  | COMPLETED
1831 | TT_TASK | Preparation of construction joint for roof | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 11 18:00:00 IDT 2013 | Sat Aug 03 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1832 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 26 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 |  | COMPLETED
1833 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 06 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Aug 13 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1835 | TT_TASK | Water proofing and soil backfilling to 0.5m below top of Tunnel Bay 3 to Bay 1 | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1836 | TT_TASK | Mass infill between D-wall and tunnel wall | Fri Oct 11 08:00:00 IDT 2013 | Wed Oct 16 18:00:00 IDT 2013 | Fri Sep 20 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1837 | TT_TASK | Removal S3 and S2 | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
1838 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 4 | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Sat May 18 18:00:00 IDT 2013 |  | COMPLETED
1839 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 5 and remove S3 & S2 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1840 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 6 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1843 | TT_TASK | Pre-drilling and guidewall | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1844 | TT_TASK | D-wall design review | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1845 | TT_TASK | D-wall construction (4741m3) | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 |  | COMPLETED
1846 | TT_TASK | Shear pin and pumping test | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 15 18:00:00 IST 2012 | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1848 | TT_TASK | ELS works to formation level from SN16 to SN19 (soil: 8,700m3 @350m3/day, Install S1 to S3 strut 5 days/layer) | Wed Sep 25 08:00:00 IDT 2013 | Wed Nov 13 18:00:00 IST 2013 | Wed May 08 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1849 | TT_TASK | Design temporary bridge and approval | Mon Sep 01 08:00:00 IDT 2014 | Wed Nov 12 18:00:00 IST 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1850 | TT_TASK | Application of tree transplant | Sat Jun 01 08:00:00 IDT 2013 | Wed Oct 23 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1851 | TT_TASK | Tree transplant | Tue Oct 14 08:00:00 IDT 2014 | Mon Nov 10 18:00:00 IST 2014 | Tue Sep 02 08:00:00 IDT 2014 | Tue Sep 30 18:00:00 IDT 2014 |  | COMPLETED
1852 | TT_TASK | Erection temporary bridge deck | Fri Oct 03 08:00:00 IDT 2014 | Fri Dec 05 18:00:00 IST 2014 | Fri Oct 03 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1853 | TT_TASK | ELS works to formation level from SN10 to SN15 (soil: 9,455m3 @330m3/day, install S1 to S3 strut 5 days/layer) | Mon Nov 24 08:00:00 IST 2014 | Sat Jan 17 18:00:00 IST 2015 | Mon Nov 24 08:00:00 IST 2014 | Tue Jun 23 18:00:00 IDT 2015 |  | COMPLETED
1856 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
1857 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1858 | TT_TASK | Erect external formwork for wall and roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1859 | TT_TASK | Concreting for wall and roof (215m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
1860 | TT_TASK | Curing for wall and roof | Sun Dec 08 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
1861 | TT_TASK | Preparation of construction joint for wall and roof | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1862 | TT_TASK | Removal external and internal formwork for wall | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1863 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1864 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 03 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 | Mon Mar 24 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
1866 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 14 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1867 | TT_TASK | Rebar fixing for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1868 | TT_TASK | Erect external formwork for wall and roof | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1869 | TT_TASK | Concreting for wall and roof (215m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1870 | TT_TASK | Curing for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Sun Dec 29 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1871 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
1872 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 17 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
1873 | TT_TASK | Removal internal falsework and formwork for roof | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1874 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 |  | COMPLETED
1876 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 28 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Nov 28 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1877 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1878 | TT_TASK | Erect external formwork for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1879 | TT_TASK | Concreting for wall and roof (215m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1880 | TT_TASK | Curing for wall and roof | Wed Jan 01 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
1881 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
1882 | TT_TASK | Removal external and internal formwork for wall | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 |  | COMPLETED
1883 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
1884 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 |  | COMPLETED
1886 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1887 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 14 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1888 | TT_TASK | Erect external formwork for wall and roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1889 | TT_TASK | Concreting for wall and roof (215m3) | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1890 | TT_TASK | Curing for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1892 | TT_TASK | Removal external and internal formwork for wall | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1893 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1894 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 |  | COMPLETED
1896 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 08:00:00 IST 2013 |  | COMPLETED
1897 | TT_TASK | Rebar fixing for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1898 | TT_TASK | Erect external formwork for wall and roof | Fri Jan 03 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1899 | TT_TASK | Concreting for wall and roof (215m3) | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1900 | TT_TASK | Curing for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 16 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1901 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Tue Jan 07 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1902 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1903 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1904 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 |  | COMPLETED
1906 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1907 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1908 | TT_TASK | Erect external formwork for wall and roof | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1909 | TT_TASK | Concreting for wall and roof (215m3) | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1910 | TT_TASK | Curing for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1911 | TT_TASK | Preparation of construction joint for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1912 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1913 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1914 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 |  | COMPLETED
1916 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1917 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 |  | COMPLETED
1918 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Tue Jun 04 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 |  | COMPLETED
1919 | TT_TASK | Concreting for wall and roof (333m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1920 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1921 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Wed Jun 12 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1922 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 |  | COMPLETED
1923 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
1924 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 05 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Tue Mar 04 18:00:00 IST 2014 |  | COMPLETED
1926 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1927 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1928 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1929 | TT_TASK | Concreting for wall and roof (412m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1930 | TT_TASK | Curing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Sun Jun 23 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Sat Mar 23 18:00:00 IST 2013 |  | COMPLETED
1931 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Mar 25 08:00:00 IST 2013 | Mon Mar 25 18:00:00 IST 2013 |  | COMPLETED
1932 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Mar 26 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1933 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jun 24 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1934 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 27 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Mon Mar 03 18:00:00 IST 2014 |  | COMPLETED
1936 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1937 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1938 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Apr 02 18:00:00 IDT 2013 |  | COMPLETED
1939 | TT_TASK | Concreting for wall and roof (320m3) | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Apr 05 08:00:00 IDT 2013 | Fri Apr 05 18:00:00 IDT 2013 |  | COMPLETED
1940 | TT_TASK | Curing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 06 08:00:00 IDT 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1941 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1942 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1943 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1944 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jan 21 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Sat Mar 01 18:00:00 IST 2014 |  | COMPLETED
1946 | TT_TASK | Excavation and saw cut D-wall | Thu Apr 02 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Sat Jul 25 18:00:00 IDT 2015 |  | COMPLETED
1947 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Aug 08 16:24:00 IDT 2015 | Mon Aug 10 16:24:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Mon Jul 13 18:00:00 IDT 2015 |  | COMPLETED
1948 | TT_TASK | Erect external formwork for base slab | Mon Aug 10 16:24:00 IDT 2015 | Wed Aug 12 16:24:00 IDT 2015 | Tue Jul 14 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
1949 | TT_TASK | Rebar fixing for base slab | Wed Aug 12 16:24:00 IDT 2015 | Fri Aug 14 16:24:00 IDT 2015 | Wed Jul 15 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1950 | TT_TASK | Erect internal kicker formwork for base slab | Fri Aug 14 16:24:00 IDT 2015 | Mon Aug 17 16:24:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Wed Aug 12 18:00:00 IDT 2015 |  | COMPLETED
1951 | TT_TASK | Concreting for base slab (90m3) | Wed Sep 02 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 | Thu Aug 13 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 |  | COMPLETED
1952 | TT_TASK | Curing for base slab | Thu Sep 03 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Fri Aug 14 08:00:00 IDT 2015 | Thu Aug 20 18:00:00 IDT 2015 |  | COMPLETED
1953 | TT_TASK | Preparation of construction joint for base slab | Thu Sep 03 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Fri Aug 21 08:00:00 IDT 2015 | Fri Aug 21 18:00:00 IDT 2015 |  | COMPLETED
1954 | TT_TASK | Removal of formwork for base slab | Fri Sep 04 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Sat Aug 22 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 |  | COMPLETED
1955 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Sep 05 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 | Mon Aug 24 08:00:00 IDT 2015 | Mon Aug 24 18:00:00 IDT 2015 |  | COMPLETED
1956 | TT_TASK | Curing | Thu Sep 10 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Tue Aug 25 08:00:00 IDT 2015 | Tue Aug 25 18:00:00 IDT 2015 |  | COMPLETED
1957 | TT_TASK | Removal strut S3 | Sat Sep 19 08:00:00 IDT 2015 | Wed Sep 23 18:00:00 IDT 2015 | Wed Sep 16 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
1958 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Sep 24 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
1959 | TT_TASK | Rebar fixing for wall and roof | Wed Sep 30 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 | Fri Sep 25 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 |  | COMPLETED
1960 | TT_TASK | Erect external formwork for wall and roof | Thu Oct 15 08:00:00 IDT 2015 | Fri Oct 16 18:00:00 IDT 2015 | Mon Oct 05 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
1961 | TT_TASK | Concreting for wall and roof (260m3) | Sat Oct 17 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 | Wed Oct 07 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1962 | TT_TASK | Curing for wall and roof | Sun Oct 18 08:00:00 IDT 2015 | Tue Oct 27 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 |  | COMPLETED
1963 | TT_TASK | Preparation of construction joint for wall and roof | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
1964 | TT_TASK | Removal external and internal formwork for wall | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
1965 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 28 08:00:00 IST 2015 | Thu Oct 29 18:00:00 IST 2015 | Thu Oct 22 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1966 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Oct 30 08:00:00 IST 2015 | Wed Nov 04 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1968 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 02 18:00:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 |  | COMPLETED
1969 | TT_TASK | Erect external formwork for base slab | Fri Jul 03 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Tue Jul 21 08:00:00 IDT 2015 | Wed Jul 22 18:00:00 IDT 2015 |  | COMPLETED
1970 | TT_TASK | Rebar fixing for base slab | Mon Jul 06 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 23 08:00:00 IDT 2015 | Fri Jul 24 18:00:00 IDT 2015 |  | COMPLETED
1971 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jul 08 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Sat Jul 25 08:00:00 IDT 2015 | Mon Jul 27 18:00:00 IDT 2015 |  | COMPLETED
1972 | TT_TASK | Concreting for base slab (123m3) | Fri Jul 10 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jul 28 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 |  | COMPLETED
1973 | TT_TASK | Curing for base slab | Sat Jul 11 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1974 | TT_TASK | Preparation of construction joint for base slab | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 |  | COMPLETED
1975 | TT_TASK | Removal of formwork for base slab | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 |  | COMPLETED
1976 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1977 | TT_TASK | Curing | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 |  | COMPLETED
1978 | TT_TASK | Removal strut S3 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1979 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 |  | COMPLETED
1980 | TT_TASK | Rebar fixing for wall and roof | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 |  | COMPLETED
1981 | TT_TASK | Erect external formwork for wall and roof | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 |  | COMPLETED
1982 | TT_TASK | Concreting for wall and roof (260m3) | Fri Oct 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 | Sat Oct 24 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
1983 | TT_TASK | Curing for wall and roof | Sat Oct 03 08:00:00 IDT 2015 | Mon Oct 12 18:00:00 IDT 2015 | Mon Oct 26 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1984 | TT_TASK | Preparation of construction joint for wall and roof | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
1985 | TT_TASK | Removal external and internal formwork for wall | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1986 | TT_TASK | Removal internal falsework and formwork for roof | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1987 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1989 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
1990 | TT_TASK | Erect external formwork for base slab | Mon Jun 15 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1991 | TT_TASK | Rebar fixing for base slab | Wed Jun 17 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
1992 | TT_TASK | Erect internal kicker formwork for base slab | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
1993 | TT_TASK | Concreting for base slab (127m3) | Tue Jun 23 08:00:00 IDT 2015 | Tue Jun 23 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
1994 | TT_TASK | Curing for base slab | Wed Jun 24 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
1995 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 24 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1996 | TT_TASK | Removal of formwork for base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
1997 | TT_TASK | Infill concrete in between D-wall and base slab | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1998 | TT_TASK | Curing | Thu May 28 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1999 | TT_TASK | Removal strut S3 | Fri May 29 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2000 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 03 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2001 | TT_TASK | Rebar fixing for wall and roof | Mon Jun 08 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2002 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2003 | TT_TASK | Concreting for wall and roof (260m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2004 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2005 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2006 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2007 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2008 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 11 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2010 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
2011 | TT_TASK | Erect external formwork for base slab | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
2012 | TT_TASK | Rebar fixing for base slab | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
2013 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
2014 | TT_TASK | Concreting for base slab (127m3) | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
2015 | TT_TASK | Curing for base slab | Thu Jun 11 08:00:00 IDT 2015 | Wed Jun 17 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2016 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 11 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
2017 | TT_TASK | Removal of formwork for base slab | Sat May 23 08:00:00 IDT 2015 | Sat May 23 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
2018 | TT_TASK | Infill concrete in between D-wall and base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
2019 | TT_TASK | Curing | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2020 | TT_TASK | Removal strut S3 | Thu May 28 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2021 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2022 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2023 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2024 | TT_TASK | Concreting for wall and roof (150m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2025 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2026 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2027 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2028 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2029 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jul 06 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
2031 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2032 | TT_TASK | Erect external formwork for base slab | Thu May 21 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2033 | TT_TASK | Rebar fixing for base slab | Sat May 23 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2034 | TT_TASK | Erect internal kicker formwork for base slab | Wed May 27 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2035 | TT_TASK | Concreting for base slab (70m3) | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2036 | TT_TASK | Curing for base slab | Sat May 30 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2037 | TT_TASK | Preparation of construction joint for base slab | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2038 | TT_TASK | Removal of formwork for base slab | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2039 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2040 | TT_TASK | Curing | Sat Jun 06 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2041 | TT_TASK | Removal strut S3 | Mon Jun 08 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat May 23 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2043 | TT_TASK | Rebar fixing for wall and roof | Fri May 29 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2044 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2045 | TT_TASK | Concreting for wall and roof (175m3) | Thu Jun 04 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2046 | TT_TASK | Curing for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sun Jun 14 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2047 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2048 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 03 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 04 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2050 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 29 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
2052 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2053 | TT_TASK | Erect external formwork for base slab | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2054 | TT_TASK | Rebar fixing for base slab | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2055 | TT_TASK | Erect internal kicker formwork for base slab | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2056 | TT_TASK | Concreting for base slab (70m3) | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2057 | TT_TASK | Curing for base slab | Wed Apr 22 08:00:00 IDT 2015 | Tue Apr 28 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2058 | TT_TASK | Preparation of construction joint for base slab | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2059 | TT_TASK | Removal of formwork for base slab | Thu Apr 23 08:00:00 IDT 2015 | Thu Apr 23 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2060 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Apr 24 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2061 | TT_TASK | Curing | Wed Apr 29 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2062 | TT_TASK | Removal strut S3 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2063 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed May 06 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2064 | TT_TASK | Rebar fixing for wall and roof | Thu May 14 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2065 | TT_TASK | Erect external formwork for wall and roof | Mon May 18 08:00:00 IDT 2015 | Tue May 19 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2066 | TT_TASK | Concreting for wall and roof (175m3) | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2067 | TT_TASK | Curing for wall and roof | Thu May 21 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2068 | TT_TASK | Preparation of construction joint for wall and roof | Thu May 21 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2069 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2070 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2071 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jun 23 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
2073 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Fri Nov 15 18:00:00 IST 2013 |  | COMPLETED
2074 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Nov 16 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2075 | TT_TASK | Rebar fixing for base slab | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
2076 | TT_TASK | Erect internal kicker formwork for base slab | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
2077 | TT_TASK | Concreting for base slab (70m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
2078 | TT_TASK | Curing for base slab | Fri Dec 20 08:00:00 IST 2013 | Thu Dec 26 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
2079 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 |  | COMPLETED
2080 | TT_TASK | Removal of formwork for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
2081 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
2082 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2083 | TT_TASK | Removal strut S3 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2084 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Apr 16 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2085 | TT_TASK | Rebar fixing for wall and roof | Thu Apr 24 08:00:00 IDT 2014 | Sat Apr 26 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 |  | COMPLETED
2086 | TT_TASK | Erect external formwork for wall and roof | Mon Apr 28 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Thu Apr 10 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2087 | TT_TASK | Concreting for wall and roof (170m3) | Wed Apr 30 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Sat Apr 12 08:00:00 IDT 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
2088 | TT_TASK | Curing for wall and roof | Thu May 01 08:00:00 IDT 2014 | Sat May 10 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Tue Apr 22 18:00:00 IDT 2014 |  | COMPLETED
2089 | TT_TASK | Preparation of construction joint for wall and roof | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 |  | COMPLETED
2090 | TT_TASK | Removal external and internal formwork for wall | Sat May 03 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Tue Apr 15 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
2091 | TT_TASK | Removal internal falsework and formwork for roof | Mon May 12 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 |  | COMPLETED
2092 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jun 05 08:00:00 IDT 2014 | Tue Jun 10 18:00:00 IDT 2014 | Thu May 29 08:00:00 IDT 2014 | Thu Dec 04 18:00:00 IST 2014 |  | COMPLETED
2094 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2095 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2096 | TT_TASK | Rebar fixing for base slab | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2097 | TT_TASK | Erect internal kicker formwork for base slab | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2098 | TT_TASK | Concreting for base slab (70m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2099 | TT_TASK | Curing for base slab | Sun Dec 08 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2100 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2101 | TT_TASK | Removal of formwork for base slab | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
2102 | TT_TASK | Infill concrete in between D-wall and base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
2103 | TT_TASK | Curing | Sun Dec 15 08:00:00 IST 2013 | Sun Dec 15 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2104 | TT_TASK | Removal strut S3 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2105 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Feb 12 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2106 | TT_TASK | Rebar fixing for wall and roof | Mon Feb 17 08:00:00 IST 2014 | Wed Feb 19 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
2107 | TT_TASK | Erect external formwork for wall and roof | Fri Feb 28 13:48:00 IST 2014 | Mon Mar 03 13:48:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2108 | TT_TASK | Concreting for wall and roof (200m3) | Mon Mar 03 13:48:00 IST 2014 | Tue Mar 04 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2109 | TT_TASK | Curing for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Fri Mar 14 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2110 | TT_TASK | Preparation of construction joint for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Wed Mar 05 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2111 | TT_TASK | Removal external and internal formwork for wall | Wed Mar 05 13:48:00 IST 2014 | Thu Mar 06 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
2112 | TT_TASK | Removal internal falsework and formwork for roof | Fri Mar 14 13:48:00 IST 2014 | Mon Mar 17 13:48:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2113 | TT_TASK | Side walkway and cable bracket (204m3) | Thu May 29 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Wed Dec 03 18:00:00 IST 2014 |  | COMPLETED
2115 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2116 | TT_TASK | Erect external formwork for base slab | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2117 | TT_TASK | Rebar fixing for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2118 | TT_TASK | Erect internal kicker formwork for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2119 | TT_TASK | Concreting for base slab (70m3) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2120 | TT_TASK | Curing for base slab | Tue Dec 03 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2121 | TT_TASK | Preparation of construction joint for base slab | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
2122 | TT_TASK | Removal of formwork for base slab | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2123 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2124 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2125 | TT_TASK | Removal strut S3 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
2126 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jan 25 08:00:00 IST 2014 | Wed Jan 29 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
2127 | TT_TASK | Rebar fixing for wall and roof | Thu Jan 30 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Fri Dec 20 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
2128 | TT_TASK | Erect external formwork for wall and roof | Thu Feb 20 08:00:00 IST 2014 | Fri Feb 21 18:00:00 IST 2014 | Thu Jan 09 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2129 | TT_TASK | Concreting for wall and roof (200m3) | Sat Feb 22 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2130 | TT_TASK | Curing for wall and roof | Sun Feb 23 08:00:00 IST 2014 | Tue Mar 04 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2131 | TT_TASK | Preparation of construction joint for wall and roof | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Tue Jan 14 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2132 | TT_TASK | Removal external and internal formwork for wall | Tue Feb 25 08:00:00 IST 2014 | Tue Feb 25 18:00:00 IST 2014 | Wed Jan 15 08:00:00 IST 2014 | Wed Jan 15 18:00:00 IST 2014 |  | COMPLETED
2133 | TT_TASK | Removal internal falsework and formwork for roof | Wed Mar 05 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2134 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
2137 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Sep 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
2138 | TT_TASK | Erect external formwork for base slab | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Sep 21 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
2139 | TT_TASK | Rebar fixing for base slab | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
2140 | TT_TASK | Erect internal kicker formwork for base slab | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
2141 | TT_TASK | Staircase construction (+12.0mPD to +14.706mPD) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2142 | TT_TASK | Concreting for base slab (30m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
2143 | TT_TASK | Curing for base slab | Fri Dec 13 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
2144 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
2145 | TT_TASK | Removal of formwork for base slab | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 18:00:00 IDT 2013 |  | COMPLETED
2146 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2147 | TT_TASK | Mass concrete at level +12.0mPD | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 |  | COMPLETED
2148 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2149 | TT_TASK | Removal strut S3 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2150 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 17 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Mon Dec 01 18:00:00 IST 2014 |  | COMPLETED
2152 | TT_TASK | Erect working platform to +21.0mPD | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2153 | TT_TASK | Rebar fixing for wall and roof | Sat Jan 11 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2154 | TT_TASK | Staircase construction (+14.706mPD to +16.956mPD) (20m3) | Fri May 02 08:00:00 IDT 2014 | Wed May 07 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2155 | TT_TASK | Staircase construction (+16.956mPD to +19.206mPD) (20m3) | Thu Jun 05 08:00:00 IDT 2014 | Mon Jun 09 18:00:00 IDT 2014 | Thu Jun 12 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2156 | TT_TASK | Staircase construction (+19.206mPD to +21.456mPD) (20m3) | Tue Jun 10 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Fri Jun 20 18:00:00 IDT 2014 |  | COMPLETED
2157 | TT_TASK | Erect external formwork for wall and roof | Sat Mar 15 08:00:00 IST 2014 | Mon Mar 17 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2158 | TT_TASK | Concreting for wall and roof (31m3) | Tue Feb 04 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2159 | TT_TASK | Curing for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 |  | COMPLETED
2160 | TT_TASK | Preparation of construction joint for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2161 | TT_TASK | Removal external and internal formwork for wall | Thu Feb 06 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2162 | TT_TASK | Removal internal falsework and formwork for roof | Sat Feb 15 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Thu Jan 23 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2164 | TT_TASK | Removal strut S2 @ SN 19 | Wed Apr 02 08:00:00 IDT 2014 | Mon Apr 07 18:00:00 IDT 2014 | Mon Mar 03 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 |  | COMPLETED
2165 | TT_TASK | Erect working platform to +24.0mPD | Tue Apr 08 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 | Fri Mar 07 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 |  | COMPLETED
2166 | TT_TASK | Erect internal formwork below strut S1 | Sat Apr 12 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 | Wed Mar 12 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 |  | COMPLETED
2167 | TT_TASK | Staircase construction (+21.456mPD to +23.706mPD) (20m3) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 |  | COMPLETED
2168 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 | Fri Mar 14 08:00:00 IST 2014 | Tue Apr 01 18:00:00 IDT 2014 |  | COMPLETED
2169 | TT_TASK | Erect external wall & internal wall formwork | Tue May 13 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Wed Apr 02 08:00:00 IDT 2014 | Thu Apr 03 18:00:00 IDT 2014 |  | COMPLETED
2170 | TT_TASK | Concreting (External Wall & Internal Wall) (264m3) | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Fri Apr 04 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2171 | TT_TASK | Curing (External Wall & Internal Wall) | Fri May 16 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2172 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Mon May 19 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Thu Apr 10 18:00:00 IDT 2014 |  | COMPLETED
2173 | TT_TASK | Waterproofing | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 |  | COMPLETED
2174 | TT_TASK | Backfilling | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2176 | TT_TASK | Removal strut S1 @ SN 19 | Thu Jun 19 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2177 | TT_TASK | Erect working platform to +30.406mPD | Tue Jun 24 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2178 | TT_TASK | Erect internal formwork | Sat Jun 28 08:00:00 IDT 2014 | Sat Jun 28 18:00:00 IDT 2014 | Wed Jun 04 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2179 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Mon Jun 30 08:00:00 IDT 2014 | Wed Jul 02 18:00:00 IDT 2014 | Thu Jun 05 08:00:00 IDT 2014 | Fri Jun 06 18:00:00 IDT 2014 |  | COMPLETED
2180 | TT_TASK | Erect external formwork (External Wall & Internal Wall) | Thu Jul 03 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2181 | TT_TASK | Concreting (External Wall & Internal Wall) (128m3) | Fri Jul 04 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2182 | TT_TASK | Curing (External Wall & Internal Wall) | Sat Jul 05 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 18:00:00 IDT 2014 |  | COMPLETED
2183 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Tue Jul 08 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2184 | TT_TASK | Waterproofing | Wed Jul 09 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Thu Jun 19 18:00:00 IDT 2014 |  | COMPLETED
2185 | TT_TASK | Backfilling | Sat Jul 12 08:00:00 IDT 2014 | Wed Jul 16 18:00:00 IDT 2014 | Fri Jun 20 08:00:00 IDT 2014 | Tue Jun 24 18:00:00 IDT 2014 |  | COMPLETED
2186 | TT_TASK | Erect falsework and soffit formwork +30.206mPD | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 | Wed Jun 25 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2187 | TT_TASK | Staircase construction (+21.456mPD to +25.956mPD) (20m3) | Sat Jul 19 08:00:00 IDT 2014 | Wed Jul 23 18:00:00 IDT 2014 | Fri Jun 27 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2188 | TT_TASK | Staircase construction (+25.956mPD to +27.606mPD) (20m3) | Sat Jul 05 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 05 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 |  | COMPLETED
2189 | TT_TASK | Rebar fixing (Beam, Floor Slab and Staircase) | Thu Jul 10 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Thu Jul 10 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2190 | TT_TASK | Concreting (Beam, Floor Slab and Staircase) (31m3) | Fri Jul 11 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2191 | TT_TASK | Curing (Beam, Floor Slab and Staircase) | Wed Sep 03 08:00:00 IDT 2014 | Tue Sep 09 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2193 | TT_TASK | Erect working platform to +33.576mPD | Wed Sep 03 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
2194 | TT_TASK | Erect external formwork (External Wall) | Mon Sep 08 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 | Fri Sep 26 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2195 | TT_TASK | Rebar fixing (External Wall) | Thu Sep 11 08:00:00 IDT 2014 | Fri Sep 12 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2196 | TT_TASK | Erect internal formwork (External Wall) | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 |  | COMPLETED
2197 | TT_TASK | Concreting (External Wall) (49m3) | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 |  | COMPLETED
2198 | TT_TASK | Curing (External Wall) | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 |  | COMPLETED
2199 | TT_TASK | Removal formwork (External Wall) | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
2200 | TT_TASK | Erect falsework and soffit formwork +32.656 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2201 | TT_TASK | Rebar fixing (Beam & Floor Slab) | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 |  | COMPLETED
2202 | TT_TASK | Concreting (Beam & Floor Slab) (31m3) | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 |  | COMPLETED
2203 | TT_TASK | Curing (Beam & Floor Slab) | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2205 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
2206 | TT_TASK | Rebar fixing (Roof Parapet Wall) | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 |  | COMPLETED
2207 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2208 | TT_TASK | Concreting (Roof Parapet Wall) (30m3) | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
2209 | TT_TASK | Curing (Roof Parapet Wall) | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 |  | COMPLETED
2210 | TT_TASK | Removal formwork (Roof Parapet Wall) | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2211 | TT_TASK | Removal of falsework and soffit formwork | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
2213 | TT_TASK | Wet trade work | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 |  | COMPLETED
2214 | TT_TASK | Metal works (Louver, Door, Cat-ladder, Architectural Fins, Handrail, Roof Sliding Hatch and Balustrade, etc) | Thu Nov 27 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Thu Nov 27 08:00:00 IST 2014 | Thu Mar 05 18:00:00 IST 2015 |  | COMPLETED
2215 | TT_TASK | Coat works | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2218 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Nov 29 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Feb 04 18:00:00 IST 2014 |  | COMPLETED
2219 | TT_TASK | Backfilling between D-wall and 0.5m below S1 14,240m3 soil | Thu Feb 06 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 | Wed Feb 05 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 |  | COMPLETED
2220 | TT_TASK | Removal of S1 | Wed Mar 12 08:00:00 IST 2014 | Tue Mar 25 18:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 |  | COMPLETED
2221 | TT_TASK | Backfilling to original ground level 21,390m3 (approx. +25.0mPD) | Sat Mar 01 08:00:00 IST 2014 | Wed Mar 19 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Sat May 03 18:00:00 IDT 2014 |  | COMPLETED
2223 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 |  | COMPLETED
2224 | TT_TASK | Backfilling between D-wall and 0.5m below S1 (2075m3) | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 |  | COMPLETED
2225 | TT_TASK | Removal of S1 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 |  | COMPLETED
2226 | TT_TASK | Backfilling to original ground level 3,900m3 (approx. +25.0mPD) (1353m3) | Sat Mar 01 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
2227 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
2228 | TT_TASK | Backfilling backfilling to +20mPD from SN8 to SN9 (Soil: 7,050m3 @ 500m3/day) | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 |  | COMPLETED
2229 | TT_TASK | Removal of S1 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
2230 | TT_TASK | Construction of mud pit | Sat Jul 06 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
2231 | TT_TASK | Backfilling from +20mPD to ground level from SN8 to SN9 (Soil: 5,000m3 @ 500m3/day) | Tue Aug 06 08:00:00 IDT 2013 | Sat Aug 17 18:00:00 IDT 2013 | Tue Jul 02 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 |  | COMPLETED
2233 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Aug 07 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2234 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) | Fri Aug 14 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2235 | TT_TASK | Placing mass concrete infill between tunnel and D-wall | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 02 18:00:00 IST 2015 | Thu Dec 24 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2236 | TT_TASK | Removal of S2 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 10 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 04 18:00:00 IST 2016 |  | COMPLETED
2237 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2238 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
2239 | TT_TASK | Removal strut S1 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2240 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
2241 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488 m3 of soil) | Mon Jan 25 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Fri Apr 01 18:00:00 IDT 2016 |  | COMPLETED
2243 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) (SN18-19) | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 |  | COMPLETED
2244 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) (SN18-19) | Sat Apr 26 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Sat Apr 26 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
2245 | TT_TASK | Placing mass concrete infill between tunnel and D-wall (SN18-19) | Tue May 20 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri May 16 18:00:00 IDT 2014 |  | COMPLETED
2246 | TT_TASK | Removal of S2 (SN16-18) | Wed Jun 04 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 |  | COMPLETED
2247 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) (SN16-18) | Mon Jun 09 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Tue May 27 18:00:00 IDT 2014 |  | COMPLETED
2248 | TT_TASK | Removal strut S1 (SN16-18) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Wed May 28 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
2249 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488m3 of soil) | Fri Jun 27 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
2251 | TT_TASK | Dismantling temporary bridge deck | Mon Jun 15 08:00:00 IDT 2015 | Tue Jul 21 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2252 | TT_TASK | Reinstatement of Works Area 4.10 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jan 11 18:00:00 IST 2017 | Mon May 02 08:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 |  | COMPLETED
2253 | TT_TASK | Complete all tree planting and reinstate Works Area 4.12C | Tue Nov 01 08:00:00 IST 2016 | Thu Jul 13 18:00:00 IDT 2017 | Sat Oct 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2254 | TT_TASK | Reinstate Works Areas 4.9, 4.9A and 4.12A prior to handover | Mon May 22 08:00:00 IDT 2017 | Sat Sep 02 18:00:00 IDT 2017 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2258 | TT_TASK | Application of power supply, environmental permits and construction substation | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2259 | TT_TASK | Procurement and Confirmation of the order of 2nd tunnel boring machine | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2260 | TT_TASK | TBM design and submission for approval | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2261 | TT_TASK | TBM materials order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
2262 | TT_TASK | TBM equipments order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 |  | COMPLETED
2263 | TT_TASK | TBM Fabrication | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
2264 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 |  | COMPLETED
2265 | TT_TASK | TBM test Run | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2266 | TT_TASK | TBM disassembly and packing for shipping to HK | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 |  | COMPLETED
2267 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
2268 | TT_TASK | Setup TBM facilities | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
2269 | TT_TASK | Fabrication 50% of South Tunnel South Bound Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
2270 | TT_TASK | Fabrication 100% of South Tunnel South Bound Precast Lining | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
2271 | TT_TASK | Fabrication 50% of South Tunnel North Bound Precast Lining | Wed Oct 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 | Wed Oct 03 08:00:00 IST 2012 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
2272 | TT_TASK | Fabrication 100% of South Tunnel North Bound Precast Lining | Mon Aug 26 08:00:00 IDT 2013 | Wed Jan 22 18:00:00 IST 2014 | Wed Feb 27 08:00:00 IST 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
2274 | TT_TASK | Ground treatment at lauching shaft Southbound | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
2275 | TT_TASK | TBM assemble, thrust frame, testing and commissioning | Sat Jun 01 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2276 | TT_TASK | Lowing back-up plant for final drive | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
2277 | TT_TASK | Assemble and set up back-up plant for final drive | Sat Jun 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2278 | TT_TASK | Erection of noise enclosure | Sat Jul 20 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 |  | COMPLETED
2279 | TT_TASK | TBM drive & lining installation CH124+912 to CH125+012 (Initial Drive) | Sat Jul 20 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Mon Mar 11 00:00:00 IST 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
2280 | TT_TASK | TBM drive & lining installation CH125+012 to CH125+338 | Tue Oct 15 08:00:00 IDT 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon May 27 08:00:00 IDT 2013 | Tue May 20 00:00:00 IDT 2014 |  | COMPLETED
2281 | TT_TASK | Dis-assemble TBM | Fri May 23 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 |  | COMPLETED
2282 | TT_TASK | Invert slab and side walkway | Fri Aug 01 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Tue Sep 02 18:00:00 IDT 2014 |  | COMPLETED
2283 | TT_TASK | Installation of cable bracket | Mon Nov 03 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 | Mon Aug 18 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2285 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Sep 01 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 | Sat Aug 09 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2286 | TT_TASK | Ground treatment at lauching shaft Northbound | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 19 18:00:00 IST 2013 | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
2287 | TT_TASK | TBM assemble, testing and commissioning | Wed Jul 02 08:00:00 IDT 2014 | Wed Sep 03 18:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2288 | TT_TASK | Setup back-up plant for final drive | Tue Jun 03 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2289 | TT_TASK | Reinstate of noise enclosure | Fri Oct 10 08:00:00 IDT 2014 | Wed Nov 05 18:00:00 IST 2014 | Tue Oct 28 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
2290 | TT_TASK | TBM drive & lining installation CH124+927 to CH125+027 (Initial Drive) | Fri Oct 10 08:00:00 IDT 2014 | Thu Nov 13 18:00:00 IST 2014 | Thu Oct 30 00:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
2291 | TT_TASK | TBM drive & lining installation CH125+027 to CH125+353 (Final Drive) | Fri Jan 02 08:00:00 IST 2015 | Thu Feb 12 18:00:00 IST 2015 | Mon Dec 08 08:00:00 IST 2014 | Fri Aug 07 00:00:00 IDT 2015 |  | COMPLETED
2292 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Tue Aug 04 08:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
2293 | TT_TASK | Dis-assemble TBM | Tue Aug 04 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
2294 | TT_TASK | Invert slab and side walkway | Wed Sep 09 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
2295 | TT_TASK | Installation of cable bracket | Thu Sep 24 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Aug 31 18:00:00 IDT 2015 |  | COMPLETED
2298 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Partial length) at down track | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 |  | COMPLETED
2299 | TT_TASK | Probe/Grout | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 | Mon Aug 11 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2300 | TT_TASK | Coring of Segment | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 |  | COMPLETED
2301 | TT_TASK | Removal of segment | Tue Sep 02 08:00:00 IDT 2014 | Thu Sep 04 18:00:00 IDT 2014 | Thu Aug 21 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2302 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Sep 05 08:00:00 IDT 2014 | Tue Oct 07 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2303 | TT_TASK | Invert Concrete | Thu Oct 23 08:00:00 IDT 2014 | Sat Nov 01 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2304 | TT_TASK | Wall and Roof concrete | Mon Nov 03 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Mon Oct 13 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
2305 | TT_TASK | Dismantle Temporary frame | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2306 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
2307 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Remaining length ) at down track | Sat May 09 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Thu Apr 16 18:00:00 IDT 2015 |  | COMPLETED
2308 | TT_TASK | Probe/Grout | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
2309 | TT_TASK | Coring of Segment | Fri Oct 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 | Fri Oct 16 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
2310 | TT_TASK | Removal of segment | Wed Oct 07 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
2311 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Oct 10 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Oct 26 08:00:00 IST 2015 | Fri Dec 11 18:00:00 IST 2015 |  | COMPLETED
2312 | TT_TASK | Invert Concrete | Thu Dec 03 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Sat Dec 12 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2313 | TT_TASK | Wall and Roof concrete | Mon Dec 14 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 15 18:00:00 IST 2016 |  | COMPLETED
2314 | TT_TASK | Dismantle Temporary frame | Wed Jan 13 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 |  | COMPLETED
2315 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2318 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 |  | COMPLETED
2319 | TT_TASK | Pre-drill and guide wall | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 |  | COMPLETED
2320 | TT_TASK | D-wall design review | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 |  | COMPLETED
2321 | TT_TASK | D-Wall Construction (1075m3) | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 |  | COMPLETED
2322 | TT_TASK | Shear pin, toe grout and pumping test | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 |  | COMPLETED
2324 | TT_TASK | SI for TBM ground treatment | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2325 | TT_TASK | Design review of TBM ground treatment | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2326 | TT_TASK | Ground treatment for TBM southbound | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
2327 | TT_TASK | Ground treatment for TBM northbound | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2329 | TT_TASK | Capping beam construction | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2330 | TT_TASK | L-Shape wall construction | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
2331 | TT_TASK | Excavate up to +28.5mPD (1488m3) | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 |  | COMPLETED
2332 | TT_TASK | Install Strut S1 +29.0mPD | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 |  | COMPLETED
2333 | TT_TASK | Excavate up to +23.5mPD (2480m3) | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 |  | COMPLETED
2334 | TT_TASK | Install Strut S2 +24.0mPD | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 |  | COMPLETED
2335 | TT_TASK | Excavate up to +19.5mPD (1984m3) | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
2336 | TT_TASK | Install Strut S3 +20.0mPD | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 |  | COMPLETED
2337 | TT_TASK | Excavate up to +15.5mPD (1984m3) | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
2338 | TT_TASK | Install Strut S4 +16.0mPD | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 |  | COMPLETED
2339 | TT_TASK | Excavate up to formation (4117m3) | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
2340 | TT_TASK | Install rock dowel and tie back | Sat Jun 02 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Sat Jun 02 08:00:00 IDT 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2341 | TT_TASK | Temporary handover the shaft to contract 822 | Mon Jun 03 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2343 | TT_TASK | Rock breaking works | Mon Aug 26 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
2344 | TT_TASK | Temporary base Slab for TBM Drive | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
2347 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2348 | TT_TASK | Erect external formwork (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Wed Aug 13 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Tue Aug 19 18:00:00 IDT 2014 |  | COMPLETED
2349 | TT_TASK | Rebar fixing (Base Slab) | Thu Aug 14 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Wed Aug 20 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2350 | TT_TASK | Erect internal kicker formwork (Base Slab) | Tue Aug 19 08:00:00 IDT 2014 | Thu Aug 21 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 |  | COMPLETED
2351 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 22 08:00:00 IDT 2014 | Fri Aug 22 18:00:00 IDT 2014 | Thu Aug 28 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2352 | TT_TASK | Concreting (Base Slab) (245m3) | Sat Aug 23 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014 | Fri Aug 29 18:00:00 IDT 2014 |  | COMPLETED
2353 | TT_TASK | Curing (Base Slab) | Mon Aug 25 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2354 | TT_TASK | Removal of formwork (Base Slab) | Mon Sep 08 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Mon Sep 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2355 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Sep 10 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Tue Sep 02 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 |  | COMPLETED
2356 | TT_TASK | Rebar fixing (Wall and roof) | Thu Sep 18 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Thu Sep 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2357 | TT_TASK | Erect external formwork (Wall) | Thu Sep 25 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2358 | TT_TASK | Clearing and inspection (Wall and roof) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2359 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
2360 | TT_TASK | Curing (Wall and roof) | Sat Oct 11 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
2361 | TT_TASK | Removal formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Thu Oct 16 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Sat Nov 01 18:00:00 IST 2014 |  | COMPLETED
2362 | TT_TASK | Removal formwork (Roof) | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2363 | TT_TASK | Side walkway and cable bracket (72m3) | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
2365 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Nov 07 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Sat Nov 07 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
2366 | TT_TASK | Erect external formwork (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Wed Nov 18 18:00:00 IST 2015 |  | COMPLETED
2367 | TT_TASK | Rebar fixing (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Tue Nov 17 18:00:00 IST 2015 | Thu Nov 19 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 |  | COMPLETED
2368 | TT_TASK | Erect internal kicker formwork (Base Slab) | Wed Nov 18 08:00:00 IST 2015 | Fri Nov 20 18:00:00 IST 2015 | Tue Nov 24 08:00:00 IST 2015 | Thu Nov 26 18:00:00 IST 2015 |  | COMPLETED
2369 | TT_TASK | Clearing and inspection (Base Slab) | Sat Nov 21 08:00:00 IST 2015 | Sat Nov 21 18:00:00 IST 2015 | Fri Nov 27 08:00:00 IST 2015 | Fri Nov 27 18:00:00 IST 2015 |  | COMPLETED
2370 | TT_TASK | Concreting (Base Slab) (245m3) | Mon Nov 23 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Nov 28 08:00:00 IST 2015 | Sat Nov 28 18:00:00 IST 2015 |  | COMPLETED
2371 | TT_TASK | Curing (Base Slab) | Tue Nov 24 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Mon Nov 30 08:00:00 IST 2015 | Thu Dec 03 18:00:00 IST 2015 |  | COMPLETED
2372 | TT_TASK | Removal of formwork (Base Slab) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Fri Dec 04 08:00:00 IST 2015 | Sat Dec 05 18:00:00 IST 2015 |  | COMPLETED
2373 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 09 18:00:00 IST 2015 | Mon Dec 07 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
2374 | TT_TASK | Rebar fixing (Wall and roof) | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2375 | TT_TASK | Erect external formwork (Wall) | Mon Jan 11 08:00:00 IST 2016 | Wed Jan 13 18:00:00 IST 2016 | Thu Jan 07 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2376 | TT_TASK | Clearing and inspection (Wall and roof) | Thu Jan 14 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2377 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Jan 15 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2378 | TT_TASK | Curing (Wall and roof) | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 |  | COMPLETED
2379 | TT_TASK | Removal formwork (Wall) | Tue Jan 19 08:00:00 IST 2016 | Thu Jan 21 18:00:00 IST 2016 | Thu Jan 28 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2380 | TT_TASK | Removal formwork and falsework (Roof) | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Sat Jan 30 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2381 | TT_TASK | Side walkway and cable bracket (72m3) | Wed Jan 06 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Thu Nov 12 08:00:00 IST 2015 | Tue Mar 01 18:00:00 IST 2016 |  | COMPLETED
2382 | TT_TASK | Provision access opening to DC | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2383 | TT_TASK | Erect falsework and soffit formwork (Opening) | Thu Mar 10 08:00:00 IST 2016 | Mon Mar 21 18:00:00 IST 2016 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2384 | TT_TASK | Rebar fixing (Roof) | Tue Mar 22 08:00:00 IST 2016 | Tue Mar 22 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2385 | TT_TASK | Clearing and inspection (Roof) | Wed Mar 23 08:00:00 IST 2016 | Wed Mar 23 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2386 | TT_TASK | Concreting (Roof) (225m3) | Thu Mar 24 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2387 | TT_TASK | Curing (Roof) | Tue Mar 29 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Jan 13 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
2388 | TT_TASK | Removal internal falsework and soffit formwork (Roof) | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
2390 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Thu Mar 17 08:00:00 IST 2016 | Fri Mar 18 18:00:00 IST 2016 | Tue Mar 01 08:00:00 IST 2016 | Wed Mar 02 18:00:00 IST 2016 |  | COMPLETED
2391 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Sat Mar 19 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Thu Mar 03 08:00:00 IST 2016 | Tue Mar 08 18:00:00 IST 2016 |  | COMPLETED
2392 | TT_TASK | Backfilling to +18.25mPD (1229 m3 of soil) | Sat Jul 02 08:00:00 IDT 2016 | Mon Jul 11 18:00:00 IDT 2016 | Mon Jul 25 08:00:00 IDT 2016 | Tue Aug 02 18:00:00 IDT 2016 |  | COMPLETED
2393 | TT_TASK | Laying 500mm mass concrete lateral support | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 |  | COMPLETED
2394 | TT_TASK | Backfilling to 0.5m below S3 (+19.5mPD) (372m3 of soil) | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 |  | COMPLETED
2395 | TT_TASK | Removal strut S3 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 |  | COMPLETED
2396 | TT_TASK | Backfilling to 0.5m below S2 (+23.5mPD) (1984m3 of soil) | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 |  | COMPLETED
2397 | TT_TASK | Removal strut S2 | Wed Aug 24 08:00:00 IDT 2016 | Fri Aug 26 18:00:00 IDT 2016 | Wed Aug 24 08:00:00 IDT 2016 | Thu Sep 01 18:00:00 IDT 2016 |  | COMPLETED
2398 | TT_TASK | Backfilling to 0.5m below S1 (+28.5mPD) (2480m3 of soil) | Mon Sep 05 08:00:00 IDT 2016 | Tue Sep 20 18:00:00 IDT 2016 | Fri Sep 02 08:00:00 IDT 2016 | Fri Sep 09 18:00:00 IDT 2016 |  | COMPLETED
2399 | TT_TASK | Removal strut S1 | Wed Sep 21 08:00:00 IDT 2016 | Thu Sep 22 18:00:00 IDT 2016 | Sat Sep 10 08:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 |  | COMPLETED
2400 | TT_TASK | Backfilling to original ground level (approx. +31.5mPD) (1488m3 of soil) | Fri Sep 23 08:00:00 IDT 2016 | Mon Oct 03 18:00:00 IDT 2016 | Thu Sep 15 08:00:00 IDT 2016 | Mon Sep 19 18:00:00 IDT 2016 |  | COMPLETED
2402 | TT_TASK | Reinstatement of TUT area (Including Hydroseeding) | Mon Oct 03 08:00:00 IDT 2016 | Mon Jun 19 18:00:00 IDT 2017 | Fri Oct 07 08:00:00 IDT 2016 |  | 216.0 | IN_PROGRESS
25 | TT_TASK | Access opening for the up track cut and cover tunnel at Tse Uk Tsuen Shaft | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 10 18:00:00 IST 2016 |  | COMPLETED
27 | TT_TASK | Close out the temporary access opening at Tse Uk Tsuen Shaft | Thu Mar 10 08:00:00 IST 2016 | Tue Apr 05 18:00:00 IDT 2016 | Thu Feb 11 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
307 | TT_TASK | Position crane for TBM retrieval (down track) | Wed Jul 02 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014 | Sat Aug 02 18:00:00 IDT 2014 |  | COMPLETED
308 | TT_TASK | TBM Break-in and Retrieval (down track) | Mon Aug 04 08:00:00 IDT 2014 | Sat Aug 30 18:00:00 IDT 2014 | Mon Aug 04 08:00:00 IDT 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
309 | TT_TASK | Position crane for TBM retrieval (up track) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 |  | COMPLETED
310 | TT_TASK | TBM Break-in and Retrieval (up track) | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
376 | TT_TASK | Supply Engineer with Survey Equipment [PS41.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
377 | TT_TASK | Provide Engineer with suitably qualified full time Survey Assistant - 4 nos. [PS41.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
378 | TT_TASK | Provide Engineer with site transportation as detailed in PS42.1 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 |  | COMPLETED
379 | TT_TASK | Submit details of qualified drivers to be assigned to the Engineer, for review [PS42.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 |  | COMPLETED
380 | TT_TASK | Install, service and maintain 10 container offices for use by the Engineer's Site Staff | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
381 | TT_TASK | Provide services and equipment for the Engineer | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
383 | TT_TASK | Master Programme - Prepare and submit for approval [GS4.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
384 | TT_TASK | Master Programme - Comments , Resubmission and Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
385 | TT_TASK | Time Chainage Programme - Prepare and submit for approval [GS4.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
386 | TT_TASK | Time Chainage Programme - Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
387 | TT_TASK | Implement and Maintain Programme Management System for 1st Audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
388 | TT_TASK | Implement and Maintain Programme Management System for 2nd Audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
389 | TT_TASK | Implement and Maintain Programme Management System for 3rd Audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
391 | TT_TASK | Environmental Management Plan - Prepare and submit for approval [GS5.1.10] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
392 | TT_TASK | Environmental Management Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
393 | TT_TASK | Quality Plan - Prepare and submit for approval [GS9.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
394 | TT_TASK | Quality Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
395 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 1st audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 |  | COMPLETED
396 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 2nd audit | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
397 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 3rd audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
398 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 4th audit | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
399 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 5th audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
400 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 6th audit | Tue Jul 02 08:00:00 IDT 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
401 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 7th audit | Thu Nov 28 08:00:00 IST 2013 | Thu Jun 05 18:00:00 IDT 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Jan 24 18:00:00 IST 2014 |  | COMPLETED
402 | TT_TASK | Health and Safety Plan - Prepare and submit [G3.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
403 | TT_TASK | System Assurance Plan - Prepare and submit for approval [PS Appendix P3.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
404 | TT_TASK | System Assurance Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
405 | TT_TASK | Design for Safety & Constructability Plan - Prepare and submit for approval [PS37.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
406 | TT_TASK | Design for Safety & Constructability Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
408 | TT_TASK | Methods of Construction - Prepare and submit for approval [GS12.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
409 | TT_TASK | Methods of Construction - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
410 | TT_TASK | Contractor's Submission Schedule - Prepare and submit for approval [GS12.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
411 | TT_TASK | Contractor's Submission Schedule - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
412 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) [PS13.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
413 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) - Approval period | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 |  | COMPLETED
414 | TT_TASK | Spoil Disposal Plan [PS17.7.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
415 | TT_TASK | Waste Management Plan [PS22.10.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
416 | TT_TASK | Independent Checking Engineer - Appoint and submit for approval [PS7.1.8] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
417 | TT_TASK | Independent Checking Engineer - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
418 | TT_TASK | Sub-contract Management Plan - Prepare and submit [PS34.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 |  | COMPLETED
419 | TT_TASK | Schedule of Utilities Services Arrangement [GS7.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
420 | TT_TASK | Site Safety Supervision Plan for Site Formation - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
421 | TT_TASK | Site Safety Supervision Plan for Site Formation - Approval period | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
422 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Prepare and Submit | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
423 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
424 | TT_TASK | Site Safety Supervision Plan for ELS - Prepare and Submit | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
425 | TT_TASK | Site Safety Supervision Plan for ELS - Approval Period | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
426 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Prepare and Submit | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
427 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Approval Period | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
428 | TT_TASK | Noise Management Plan [P22.3.9] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
429 | TT_TASK | Air Quality Management Plan [P22.4.3] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
430 | TT_TASK | Detailed Proposal for Water Pollution Control Measures and Proposed Monitoring [PS22.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
431 | TT_TASK | Groundwater Monitoring and Response Plan [PS22.5.2] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
432 | TT_TASK | Vibration Monitoring Plan [PS22.8.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 |  | COMPLETED
433 | TT_TASK | Proposed Outline TTM Scheme - Prepare & submit to the: Engineer for Review / SLG for Approval [PS19.3] | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 |  | COMPLETED
434 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Proposed TTM Scheme [PS19.4] | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 |  | COMPLETED
435 | TT_TASK | Resubmission of Proposed Outline TTM Scheme (if required) | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
436 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Resubmitted Proposed Outline TTM Scheme [PS19.4] | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 |  | COMPLETED
437 | TT_TASK | Notification Period of the Approved TTM Scheme prior to implementation [PS19.4] | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 |  | COMPLETED
440 | TT_TASK | Initial Site Survey (WA3.11) | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 |  | COMPLETED
441 | TT_TASK | Initial Site Survey Report (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 |  | COMPLETED
442 | TT_TASK | Initial Site Survey & Condition Survey (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
443 | TT_TASK | Initial Site Survey Report (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
444 | TT_TASK | Initial Site Survey & Condition Survey (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
445 | TT_TASK | Initial Site Survey Report (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
446 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 4.9 & 4.12A [PS4.2] | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
447 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 5.1 & 5.3 [PS4.2.3] | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 |  | COMPLETED
448 | TT_TASK | Proposal for Site Clearance Works [PS4.4.1] | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 |  | COMPLETED
449 | TT_TASK | Site Clearance / Site Formation Works (including demolition of EBS) | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
450 | TT_TASK | Backfill existing stream courses in Works Area 4.9, 4.10 and 4.11 [PS18.5.1] | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
451 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and submit to EPD for Approval (WA3.3 - Area M, I, L) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
452 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA3.3 - Area M, I, L) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
453 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
454 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
455 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.3 - Area M, I, L) | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
456 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA3.3 - Area M, I, L) | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
457 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA3.3 - Area M, I, L) | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
458 | TT_TASK | Remediation Report - Approval (WA3.3 - Area M, I, L) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
459 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and Submit to EPD for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
460 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
461 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
462 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.1, 3.2, 3.3, 3.3A) | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
463 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.1, 3.2, 3.3, 3.3A) | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 |  | COMPLETED
464 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 |  | COMPLETED
465 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
466 | TT_TASK | Remediation Report - Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
467 | TT_TASK | Conduct remediation for Area Q in accordance with method proposed in the approved Remediation Action Plan [PS22.9.2] | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 |  | COMPLETED
468 | TT_TASK | Remediation Report - Prepare and submit for Approval [PS22.9.2] (Area Q) | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 |  | COMPLETED
469 | TT_TASK | Remediation Report - Approval (Area Q) | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
470 | TT_TASK | Removal of contaminated soil at North Tunnels (Area N,O,P,Q,R,S) | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
471 | TT_TASK | Condition Survey EBS for presence of Asbestos and gather samples | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
472 | TT_TASK | Testing of gathered samples | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 |  | COMPLETED
473 | TT_TASK | Prepare and submit Asbestos Investigation Report (AIR) & Asbestos Abatement Plan (AAP) | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
474 | TT_TASK | Approval period of AIR & AAP | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
475 | TT_TASK | Notification period to Engineer and EPD prior to Asbestos abatement works | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
476 | TT_TASK | Asbestos abatement works | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
477 | TT_TASK | Demolition of EBS | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
478 | TT_TASK | Confirmation of tree survey | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 |  | COMPLETED
480 | TT_TASK | Installation of ground settlement markers | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 |  | COMPLETED
481 | TT_TASK | Settlement monitoring and submit report | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
482 | TT_TASK | Settlement monitoring and submit report | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 |  | COMPLETED
483 | TT_TASK | Settlement monitoring and submit report | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
484 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
485 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Wed Feb 26 18:00:00 IST 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Feb 21 18:00:00 IST 2014 |  | COMPLETED
486 | TT_TASK | Settlement monitoring and submit report | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 |  | COMPLETED
488 | TT_TASK | Permit Applications (incl. License to Search and Excavate Antiquities and Excavation Permit) | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 |  | COMPLETED
489 | TT_TASK | Check for underground utilities | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 |  | COMPLETED
490 | TT_TASK | Field walking and hand augering | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 |  | COMPLETED
491 | TT_TASK | Excavation of trial pits | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 |  | COMPLETED
492 | TT_TASK | Rescue excavation rescue works (if required) | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 |  | COMPLETED
494 | TT_TASK | Erection of Hoarding with Gate (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 |  | COMPLETED
495 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 3.1, 3.2, 3.3 and 3.3A [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
496 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 4.9, 4.10, 4.11, 4.12A~C, and 4.15 [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
497 | TT_TASK | Project Signboard Erection [PS4.6.8] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
498 | TT_TASK | Marine Survey at Barging Point [PS4.3] (before construction of barging facilities) | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 00:00:00 IST 2010 |  | COMPLETED
499 | TT_TASK | Construct barging facilities | Sat Oct 02 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Oct 02 00:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
500 | TT_TASK | Operation Plan for the Barging Facility - Prepare and Submit for Approval [PS17.1.9] | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
501 | TT_TASK | Operation Plan for the Barging Facility - Review and Approval Period | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 |  | COMPLETED
503 | TT_TASK | General and Special Attendance for Designated Contractors | Mon Dec 02 08:00:00 IST 2013 | Mon Aug 31 18:00:00 IDT 2015 | Tue Jul 02 08:00:00 IDT 2013 | Wed Mar 25 18:00:00 IST 2015 |  | COMPLETED
505 | TT_TASK | Prepare and Submit Detailed Interface Specification | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 |  | COMPLETED
506 | TT_TASK | Approval of Detailed Interface Plan | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
507 | TT_TASK | Prepare and Submit Detailed Interface Specification | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 |  | COMPLETED
508 | TT_TASK | Approval of Detailed Interface Plan | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
510 | TT_TASK | Prepare and Submit Draft Operation and Maintenance Manual [PS33.1] | Mon Aug 24 08:00:00 IDT 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jul 28 08:00:00 IDT 2014 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
511 | TT_TASK | Review and approval period of Draft Operation and Maintenance Manual | Wed Aug 10 08:00:00 IDT 2016 | Tue Sep 13 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
512 | TT_TASK | Prepare and Submit Final Operation and Maintenance Manual [PS33.1] | Wed Sep 14 08:00:00 IDT 2016 | Thu Feb 16 18:00:00 IST 2017 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
513 | TT_TASK | Provide Engineer with As-Built Drawing for the Whole of the Works [PS33.2] | Mon Nov 21 08:00:00 IST 2016 | Wed Dec 14 18:00:00 IST 2016 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
514 | TT_TASK | Provide Engineer with Asset Registration Information [PS33.3] | Fri May 19 08:00:00 IDT 2017 | Mon Jun 12 18:00:00 IDT 2017 |  |  |  | NOT_STARTED
517 | TT_TASK | Preliminary Design Programme - Prepare and Submit for Approval [PS7.1.8 - App. Z2.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
518 | TT_TASK | Preliminary Design Programme - Review and Approval Period [PS7.1.8 - App. Z2.2] | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 |  | COMPLETED
519 | TT_TASK | Preliminary Design Programme - Resubmission and Approval (if required) [PS7.1.8 - App. Z2.2] | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 |  | COMPLETED
520 | TT_TASK | Schedule of Designs - Prepare and Submit for Approval [PS7.1.8 - App. Z2.5] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
521 | TT_TASK | Detailed Proposal for Carrying Out the Cross Passage Works [PS11.5.2] | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
524 | TT_TASK | Design TBM and submit full details to the Engineer [PS7.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
525 | TT_TASK | TBM Design - Approval period | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 |  | COMPLETED
526 | TT_TASK | TBM Design - Resubmission and approval period | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 |  | COMPLETED
528 | TT_TASK | AIP Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
529 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 |  | COMPLETED
530 | TT_TASK | DDS Design - Prepare and Submit | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 |  | COMPLETED
531 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 |  | COMPLETED
532 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 |  | COMPLETED
533 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 |  | COMPLETED
534 | TT_TASK | Issue Completed Working Drawings | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
536 | TT_TASK | AIP Design - Prepare and Submit | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 |  | COMPLETED
537 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 |  | COMPLETED
538 | TT_TASK | AIP Design - Response to comments and Resubmit | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
539 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
540 | TT_TASK | DDS Design - Prepare and Submit | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
541 | TT_TASK | DDS Design - Review and Approval Period (by MTRC & related Government Authorities) | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 |  | COMPLETED
542 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 |  | COMPLETED
543 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 |  | COMPLETED
544 | TT_TASK | Issue Completed Working Drawings | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 |  | COMPLETED
546 | TT_TASK | DDS Design - Prepare and Submit | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 |  | COMPLETED
547 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 |  | COMPLETED
548 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 |  | COMPLETED
549 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 |  | COMPLETED
550 | TT_TASK | Issue Completed Working Drawings | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
552 | TT_TASK | AIP Design - Prepare and Submit | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 |  | COMPLETED
553 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
554 | TT_TASK | AIP Design - Response to comments and Resubmit | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 |  | COMPLETED
555 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
556 | TT_TASK | DDS Design - Prepare and Submit | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 |  | COMPLETED
557 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 |  | COMPLETED
558 | TT_TASK | DDS Design - Response to comments and Resubmit | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 |  | COMPLETED
559 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 |  | COMPLETED
560 | TT_TASK | Issue Completed Working Drawings | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 |  | COMPLETED
562 | TT_TASK | Prepare and Submit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 |  | COMPLETED
563 | TT_TASK | Review and Approval Period | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
564 | TT_TASK | Response to comments and Resubmit | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 |  | COMPLETED
565 | TT_TASK | Review and Approval Period (for resubmission) | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 |  | COMPLETED
568 | TT_TASK | DDS Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
569 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 |  | COMPLETED
570 | TT_TASK | DDS Design - Response to comments and Resubmit | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 |  | COMPLETED
571 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 |  | COMPLETED
572 | TT_TASK | Issue Completed Working Drawings | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
574 | TT_TASK | DDS Design - Prepare and Submit | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 |  | COMPLETED
575 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 |  | COMPLETED
576 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 |  | COMPLETED
577 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 |  | COMPLETED
578 | TT_TASK | Issue Completed Working Drawings | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 |  | COMPLETED
580 | TT_TASK | DDS Design - Prepare and Submit | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 |  | COMPLETED
581 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 |  | COMPLETED
582 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 |  | COMPLETED
583 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 |  | COMPLETED
584 | TT_TASK | Issue Completed Working Drawings | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 |  | COMPLETED
586 | TT_TASK | DDS Design - Prepare and Submit | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 |  | COMPLETED
587 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 |  | COMPLETED
588 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 |  | COMPLETED
589 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 |  | COMPLETED
590 | TT_TASK | Issue Completed Working Drawings | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 |  | COMPLETED
592 | TT_TASK | DDS Design - Prepare and Submit | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 |  | COMPLETED
593 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 |  | COMPLETED
594 | TT_TASK | DDS Design - Response to comments and Resubmit | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 |  | COMPLETED
595 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 |  | COMPLETED
596 | TT_TASK | Issue Completed Working Drawings | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
599 | TT_TASK | Formworks / Falsework - Prepare & Submit | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
600 | TT_TASK | Formworks / Falsework - Review & Approval Period (by MTRC) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
601 | TT_TASK | Formworks / Falsework - Response to comments and Resubmit | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 |  | COMPLETED
602 | TT_TASK | Formworks / Falsework - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
605 | TT_TASK | Layout of Site Hoarding - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
606 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (by MTRC) | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
607 | TT_TASK | Layout of Site Hoarding - Response to comments and Resubmit | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
608 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 |  | COMPLETED
610 | TT_TASK | Layout of Engineer's Accommodation - Prepare and Submit | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
611 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (by MTRC) | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 |  | COMPLETED
612 | TT_TASK | Layout of Engineer's Accommodation - Response to comments and Resubmit | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
613 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (for resubmit) (by MTRC & related Government Authorities | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
615 | TT_TASK | TTMS Assessment Report - Prepare and Submit | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 |  | COMPLETED
616 | TT_TASK | TTMS Assessment Report - Review and Approval Period (by MTRC) | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
617 | TT_TASK | TTMS Assessment Report - Response to comments and Resubmit | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 |  | COMPLETED
618 | TT_TASK | TTMS Assessment Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
619 | TT_TASK | Issue Completed Working Drawings | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 |  | COMPLETED
621 | TT_TASK | DIA Report - Prepare and Submit | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 |  | COMPLETED
622 | TT_TASK | DIA Report - Review and Approval Period (by MTRC) | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 |  | COMPLETED
623 | TT_TASK | DIA Report - Response to comments and Resubmit | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 |  | COMPLETED
624 | TT_TASK | DIA Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
625 | TT_TASK | Issue Completed Working Drawings | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 |  | COMPLETED
627 | TT_TASK | AIP Design - Prepare & Submit | Wed Sep 23 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 |  | COMPLETED
628 | TT_TASK | AIP Design - Review & Approval Period (by MTR) | Wed Oct 14 08:00:00 IDT 2015 | Wed Nov 11 18:00:00 IST 2015 | Mon Jun 08 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
629 | TT_TASK | AIP Design - Response to comments and Resubmit | Thu Nov 12 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Mon Jun 15 01:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
630 | TT_TASK | AIP Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jun 22 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
631 | TT_TASK | DDS Design - Prepare & Submit | Wed Jan 13 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Tue Sep 01 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 |  | COMPLETED
632 | TT_TASK | DDS Design - Review & Approval Period (by MTRC) | Fri Feb 26 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 12 18:00:00 IDT 2015 |  | COMPLETED
633 | TT_TASK | DDS Design - Response to comments & Resubmit | Tue Mar 29 08:00:00 IDT 2016 | Fri Apr 01 18:00:00 IDT 2016 | Mon Sep 14 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
634 | TT_TASK | DDS Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Apr 02 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 | Mon Sep 21 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
635 | TT_TASK | Issue Completed Working Drawings | Wed Jan 27 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
637 | TT_TASK | Layout of Barging Point - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
638 | TT_TASK | Layout of Barging Point - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
639 | TT_TASK | Layout of Barging Point - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
640 | TT_TASK | Layout of Barging Point - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
641 | TT_TASK | Loading Ramps - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
642 | TT_TASK | Loading Ramps - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
643 | TT_TASK | Loading Ramps - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
644 | TT_TASK | Loading Ramps - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
645 | TT_TASK | Weighbridge - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
646 | TT_TASK | Weighbridge - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
647 | TT_TASK | Weighbridge - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
648 | TT_TASK | Weighbridge - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
652 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
653 | TT_TASK | Pre-drill and guide wall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
654 | TT_TASK | D-wall construction (1084m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
655 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
656 | TT_TASK | Wang Toi Shan Shan Tsuen Road diversion works | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 |  | COMPLETED
658 | TT_TASK | Excavate up to +10.5mPD (369m3) | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 |  | COMPLETED
659 | TT_TASK | Install Strut S0 +11.0mPD | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 |  | COMPLETED
660 | TT_TASK | Excavate up to +8.0mPD (1525m3) | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 |  | COMPLETED
661 | TT_TASK | Install Strut S1 +8.5mPD | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 |  | COMPLETED
662 | TT_TASK | Excavate up to +4.5mPD (2135m3) | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 |  | COMPLETED
663 | TT_TASK | Install Strut S2 +5.0mPD | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 |  | COMPLETED
664 | TT_TASK | Excavate up to +0.5mPD (2440m3) | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 |  | COMPLETED
665 | TT_TASK | Install Strut S3 +1.0mPD | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 |  | COMPLETED
666 | TT_TASK | Excavate up to -6.5mPD (4340m3) | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 |  | COMPLETED
667 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
668 | TT_TASK | Construction of temporary slab and entrance seal (622m3) | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
672 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 08 18:00:00 IST 2014 | Fri Dec 05 08:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
673 | TT_TASK | Erect external formwork (Base Slab) | Tue Dec 09 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 08 08:00:00 IST 2014 | Tue Dec 09 18:00:00 IST 2014 |  | COMPLETED
674 | TT_TASK | Rebar fixing (Base Slab) | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 18:00:00 IST 2014 | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
675 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Dec 15 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Mon Dec 15 18:00:00 IST 2014 |  | COMPLETED
676 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Dec 17 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Tue Dec 16 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 |  | COMPLETED
677 | TT_TASK | Curing (Base Slab) | Thu Dec 18 08:00:00 IST 2014 | Sat Dec 27 18:00:00 IST 2014 | Wed Dec 17 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
678 | TT_TASK | Removal of formwork (Base Slab) | Fri Dec 19 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 24 18:00:00 IST 2014 |  | COMPLETED
679 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
680 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 | Mon Jun 22 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 |  | COMPLETED
681 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Jun 13 08:00:00 IDT 2015 | Mon Jun 15 18:00:00 IDT 2015 | Thu Jun 25 01:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
682 | TT_TASK | Concreting (Wall & Roof) (444m3) | Tue Jun 16 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
683 | TT_TASK | Curing (Wall & Roof) | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
684 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 |  | COMPLETED
685 | TT_TASK | Removal external formwork (Wall) | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
686 | TT_TASK | Side walkway and cable bracket (360m3) | Sat Jul 18 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Sat Jul 18 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
687 | TT_TASK | Access opening to DC (DC access period) | Tue Oct 06 08:00:00 IDT 2015 | Fri Mar 04 18:00:00 IST 2016 | Tue Oct 06 08:00:00 IDT 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
688 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Sat Dec 12 08:00:00 IST 2015 | Mon Jan 18 18:00:00 IST 2016 | Tue Nov 03 00:00:00 IST 2015 | Mon Nov 30 18:00:00 IST 2015 |  | COMPLETED
690 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 | Tue Apr 12 08:00:00 IDT 2016 | Wed Apr 13 18:00:00 IDT 2016 |  | COMPLETED
691 | TT_TASK | Erect external formwork (Base Slab) | Mon May 23 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Thu Apr 14 08:00:00 IDT 2016 | Fri Apr 15 18:00:00 IDT 2016 |  | COMPLETED
692 | TT_TASK | Rebar fixing (Base Slab) | Wed May 25 08:00:00 IDT 2016 | Fri May 27 18:00:00 IDT 2016 | Sat Apr 16 08:00:00 IDT 2016 | Tue Apr 19 18:00:00 IDT 2016 |  | COMPLETED
693 | TT_TASK | Erect internal kicker formwork (Base Slab) | Sat May 28 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 | Wed Apr 20 08:00:00 IDT 2016 | Thu Apr 21 18:00:00 IDT 2016 |  | COMPLETED
694 | TT_TASK | Concreting (Base Slab) (225m3) | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 | Fri Apr 22 08:00:00 IDT 2016 | Fri Apr 22 18:00:00 IDT 2016 |  | COMPLETED
695 | TT_TASK | Curing (Base Slab) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 08 18:00:00 IDT 2016 | Sat Apr 23 08:00:00 IDT 2016 | Fri Apr 29 18:00:00 IDT 2016 |  | COMPLETED
696 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Sat Apr 30 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
697 | TT_TASK | Removal of formwork (Base Slab) | Tue May 24 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Mon May 09 08:00:00 IDT 2016 | Tue May 10 18:00:00 IDT 2016 |  | COMPLETED
698 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed May 25 08:00:00 IDT 2016 | Sat May 28 18:00:00 IDT 2016 | Wed May 11 08:00:00 IDT 2016 | Mon May 16 18:00:00 IDT 2016 |  | COMPLETED
699 | TT_TASK | Rebar fixing (Wall & Roof) | Mon May 30 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 17 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 |  | COMPLETED
700 | TT_TASK | Erect external formwork (Wall & Roof) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 03 18:00:00 IDT 2016 | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 |  | COMPLETED
701 | TT_TASK | Concreting (Wall & Roof) (444m3) | Sat Jun 04 08:00:00 IDT 2016 | Sat Jun 04 18:00:00 IDT 2016 | Mon May 23 08:00:00 IDT 2016 | Mon May 23 18:00:00 IDT 2016 |  | COMPLETED
702 | TT_TASK | Curing (Wall & Roof) | Mon Jun 06 08:00:00 IDT 2016 | Tue Jun 14 18:00:00 IDT 2016 | Tue May 24 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 |  | COMPLETED
703 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 15 08:00:00 IDT 2016 | Wed Jun 15 18:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 |  | COMPLETED
704 | TT_TASK | Removal external formwork (Wall) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
705 | TT_TASK | Side walkway and cable bracket (102m3) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 |  | COMPLETED
706 | TT_TASK | Access opening to DC (DC access period) | Sat Jun 18 08:00:00 IDT 2016 | Thu Jul 14 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
707 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Fri Jul 15 08:00:00 IDT 2016 | Wed Aug 17 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
709 | TT_TASK | Backfilling between tunnels (2000m3) | Thu Sep 01 08:00:00 IDT 2016 | Sat Sep 17 18:00:00 IDT 2016 | Tue Sep 13 08:00:00 IDT 2016 | Fri Sep 30 18:00:00 IDT 2016 |  | COMPLETED
710 | TT_TASK | Remove Strut S2 | Mon Oct 03 08:00:00 IDT 2016 | Wed Oct 05 18:00:00 IDT 2016 | Mon Oct 03 08:00:00 IDT 2016 | Tue Oct 11 18:00:00 IDT 2016 |  | COMPLETED
711 | TT_TASK | Backfilling up top S1 Soffit | Thu Oct 06 08:00:00 IDT 2016 | Fri Oct 21 18:00:00 IDT 2016 | Fri Oct 28 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
712 | TT_TASK | Remove Strut S1 | Sat Oct 22 08:00:00 IDT 2016 | Mon Oct 24 18:00:00 IDT 2016 | Tue Oct 11 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
713 | TT_TASK | Backfilling up top S0 Soffit | Mon Nov 07 08:00:00 IST 2016 | Sat Nov 12 18:00:00 IST 2016 | Tue Nov 01 08:00:00 IST 2016 | Sat Nov 05 18:00:00 IST 2016 |  | COMPLETED
714 | TT_TASK | Remove Strut S0 | Mon Nov 14 08:00:00 IST 2016 | Tue Nov 15 18:00:00 IST 2016 | Mon Nov 07 08:00:00 IST 2016 | Tue Nov 08 18:00:00 IST 2016 |  | COMPLETED
715 | TT_TASK | Backfilling up to ground level | Wed Nov 16 08:00:00 IST 2016 | Fri Nov 18 18:00:00 IST 2016 | Wed Nov 09 08:00:00 IST 2016 | Fri Nov 11 18:00:00 IST 2016 |  | COMPLETED
719 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
720 | TT_TASK | Pre-drilling and guidewall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
721 | TT_TASK | D-wall construction (1451m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
722 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 |  | COMPLETED
724 | TT_TASK | Excavate from ground level to formation level -5.5mPD (4559m3) | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 |  | COMPLETED
725 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 |  | COMPLETED
726 | TT_TASK | Placing of blinding layer (South Bound) | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 |  | COMPLETED
727 | TT_TASK | Placing of blinding layer (North Bound) | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
729 | TT_TASK | Construction of Bay 2 to Bay 7a (3565m3) | Mon Jun 04 08:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 | Mon Jun 04 18:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 |  | COMPLETED
730 | TT_TASK | Side walkway and cable bracket (Southbound) | Fri Oct 02 08:00:00 IDT 2015 | Fri Nov 06 18:00:00 IST 2015 | Fri Oct 02 08:00:00 IDT 2015 | Sat Oct 31 18:00:00 IST 2015 |  | COMPLETED
731 | TT_TASK | Side walkway and cable bracket (Northbound) | Tue May 03 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 |  | COMPLETED
733 | TT_TASK | Backfilling (1344m3) | Wed Nov 07 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 | Wed Nov 07 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
736 | TT_TASK | Scheme Design, Mobilization, Site set up & Material delivery and Instrumentations | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
737 | TT_TASK | Downstream pipe pile wall construction (45 nos.) and grout curtain (45 nos.) | Mon Nov 12 08:00:00 IST 2012 | Fri Jan 25 18:00:00 IST 2013 | Mon Nov 12 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
738 | TT_TASK | Curtain Grout for cut slope (120 nos.) | Fri Jul 26 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
739 | TT_TASK | Drilling for ground improvement only (if require) | Mon Dec 10 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
740 | TT_TASK | If settlement reach the AAA alarm & action level TAM grouting will apply during excavation | Thu Apr 11 08:00:00 IDT 2013 | Thu May 16 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
741 | TT_TASK | Erection of temporary working platform for Up stream and Installation of Instrumentation System | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
742 | TT_TASK | Upstream pipe pile wall construction adjacent to WTSSTR, (17nos.) | Thu Dec 27 08:00:00 IST 2012 | Mon Jan 28 18:00:00 IST 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
743 | TT_TASK | Upstream pipe pile wall construction at Kam Tin River, 15m depth, 42nos. 1drill rig) | Tue Jan 29 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
744 | TT_TASK | Excavation and soil nail installation | Tue Apr 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
745 | TT_TASK | Excavation for rock and blinding layer | Sat Aug 24 08:00:00 IDT 2013 | Sat Sep 28 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
750 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
751 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
752 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
753 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
754 | TT_TASK | Concreting (164m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
755 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
756 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
757 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
758 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
759 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
760 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
761 | TT_TASK | Concreting (242m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
762 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
763 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
764 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
765 | TT_TASK | Removal internal falsework and formwork for roof | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
766 | TT_TASK | Side walkway and cable bracket (19m3) | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
770 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
771 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
772 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
773 | TT_TASK | Erect internal kicker formwork | Thu Nov 28 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 09 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
774 | TT_TASK | Concreting (121m3) | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
775 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
776 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
777 | TT_TASK | Removal of formwork | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
778 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
779 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
780 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
781 | TT_TASK | Concreting (121m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
782 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
783 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
784 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
785 | TT_TASK | Removal internal falsework and formwork for roof | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
786 | TT_TASK | Side walkway and cable bracket (38m3) | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
788 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
789 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
790 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
791 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
792 | TT_TASK | Concreting (240m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
793 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
794 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
795 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
796 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
797 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
798 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
799 | TT_TASK | Concreting (240m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
800 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
801 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
802 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
803 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
804 | TT_TASK | Side walkway and cable bracket | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
806 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
807 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
808 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
809 | TT_TASK | Concreting (222m3) | Wed Nov 06 08:00:00 IST 2013 | Wed Nov 06 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
810 | TT_TASK | Curing | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
811 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
812 | TT_TASK | Removal of formwork | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
815 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
816 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
817 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
818 | TT_TASK | Erect internal kicker formwork | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
819 | TT_TASK | Concreting (111m3) | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
820 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
821 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
822 | TT_TASK | Removal of formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
823 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
824 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
825 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
826 | TT_TASK | Concreting (220m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
827 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
828 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
829 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
830 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
831 | TT_TASK | Side walkway and cable bracket (38m3) | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 |  | COMPLETED
833 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
834 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
835 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
836 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
837 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
838 | TT_TASK | Curing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
839 | TT_TASK | Preparation of construction joint for base slab | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
840 | TT_TASK | Removal of formwork | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
841 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
842 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
843 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
844 | TT_TASK | Concreting (327m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
845 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
846 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
847 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
848 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
849 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
851 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 20 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
852 | TT_TASK | Rebar fixing | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
853 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 08:00:00 IDT 2013 |  | COMPLETED
854 | TT_TASK | Concreting (225m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
855 | TT_TASK | Curing | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
856 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
857 | TT_TASK | Removal of formwork | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
860 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 27 08:00:00 IST 2013 | Wed Nov 27 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
861 | TT_TASK | Erect external formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
862 | TT_TASK | Rebar fixing | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
863 | TT_TASK | Erect internal kicker formwork | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
864 | TT_TASK | Concreting (222m3) | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
865 | TT_TASK | Curing | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Mon Oct 28 18:00:00 IST 2013 |  | COMPLETED
866 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
867 | TT_TASK | Removal of formwork | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
868 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
869 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
870 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
871 | TT_TASK | Concreting (222m3) | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 |  | COMPLETED
872 | TT_TASK | Curing | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 07 18:00:00 IST 2014 |  | COMPLETED
873 | TT_TASK | Preparation of construction joint for wall and roof | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
874 | TT_TASK | Removal external and internal formwork for wall | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
875 | TT_TASK | Removal internal falsework and formwork for roof | Mon Feb 10 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
876 | TT_TASK | Side walkway and cable bracket (38m3) | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 |  | COMPLETED
878 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
879 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
880 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
881 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
882 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
883 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
884 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
885 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
886 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
887 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
888 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
889 | TT_TASK | Concreting (222m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
890 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
892 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
893 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
894 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
896 | TT_TASK | Placing of waterproof member T-lock & testing | Mon Nov 18 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
897 | TT_TASK | Rebar fixing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Wed Oct 23 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
898 | TT_TASK | Erect external formwork | Fri Nov 22 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
899 | TT_TASK | Concreting (222m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
900 | TT_TASK | Curing | Tue Nov 26 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
901 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
902 | TT_TASK | Removal of formwork | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
905 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
906 | TT_TASK | Erect external formwork | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
907 | TT_TASK | Rebar fixing | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
908 | TT_TASK | Erect internal kicker formwork | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
909 | TT_TASK | Concreting (330m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
910 | TT_TASK | Curing | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
911 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
912 | TT_TASK | Removal of formwork | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
913 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
914 | TT_TASK | Rebar fixing | Wed Nov 20 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
915 | TT_TASK | Erect external formwork | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
916 | TT_TASK | Concreting (330m3) | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
917 | TT_TASK | Curing | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
918 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
919 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
920 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
921 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
923 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
924 | TT_TASK | Erect external formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
925 | TT_TASK | Rebar fixing | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
926 | TT_TASK | Erect internal kicker formwork | Wed Dec 04 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
927 | TT_TASK | Concreting (240m3) | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
928 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
929 | TT_TASK | Preparation of construction joint for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
930 | TT_TASK | Removal of formwork | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
931 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
932 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
933 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
934 | TT_TASK | Concreting (240m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
935 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
936 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
937 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
938 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
939 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
941 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
942 | TT_TASK | Rebar fixing | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
943 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
944 | TT_TASK | Concreting (240m3) | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
945 | TT_TASK | Curing | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
946 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
947 | TT_TASK | Removal of formwork | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
950 | TT_TASK | Placing of waterproof member T-lock & testing | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
951 | TT_TASK | Erect external formwork | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
952 | TT_TASK | Rebar fixing | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
953 | TT_TASK | Erect internal kicker formwork | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
954 | TT_TASK | Concreting (200m3) | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
955 | TT_TASK | Curing | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
956 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
957 | TT_TASK | Removal of formwork | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
958 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 29 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
959 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
960 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
961 | TT_TASK | Concreting (200m3) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
962 | TT_TASK | Curing | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
963 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
964 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 13 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
965 | TT_TASK | Removal internal falsework and formwork for roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
966 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 |  | COMPLETED
968 | TT_TASK | Placing of waterproof member T-lock & testing | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
969 | TT_TASK | Erect external formwork | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
970 | TT_TASK | Rebar fixing | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
971 | TT_TASK | Erect internal kicker formwork | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
972 | TT_TASK | Concreting (220m3) | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
973 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
974 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
975 | TT_TASK | Removal of formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
976 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
977 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
978 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
979 | TT_TASK | Concreting (220m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
980 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
981 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
982 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
983 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
984 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
986 | TT_TASK | Placing of waterproof member T-lock & testing | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
987 | TT_TASK | Rebar fixing | Mon Nov 25 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
988 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
989 | TT_TASK | Concreting (222m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
990 | TT_TASK | Curing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
991 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
992 | TT_TASK | Removal of formwork | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
994 | TT_TASK | Removal of Temporary Nullah | Sat Mar 01 08:00:00 IST 2014 | Sat Jun 21 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
995 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (5218m3) | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 |  | COMPLETED
996 | TT_TASK | Reinstate the permenant Retaining wall of Nullah | Sat Mar 01 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Tue Mar 04 08:00:00 IST 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
997 | TT_TASK | Reinstate Nullah Base of original route | Tue Feb 25 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Tue Feb 25 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
998 | TT_TASK | Reinstate Nullah to original route | Sat Mar 29 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Sat Mar 29 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
999 | TT_TASK | Construction & connect East Box Culvert from Box 6B to KTR | Mon Apr 14 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Mon Feb 10 08:00:00 IST 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
1000 | TT_TASK | Reinstatement of Wang Toi Shan Shan Tsuen Road | Tue Dec 01 08:00:00 IST 2015 | Wed Jul 13 18:00:00 IDT 2016 | Tue Dec 01 08:00:00 IST 2015 | Mon Jul 18 18:00:00 IDT 2016 |  | COMPLETED
1003 | TT_TASK | Pre-drilling at Works Area 4.4 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
1004 | TT_TASK | Site Setup and guide wall | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1005 | TT_TASK | D-wall construction (3104m3) | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 |  | COMPLETED
1006 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
1008 | TT_TASK | Excavate up to +8.0mPD (775m3) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1009 | TT_TASK | Install Strut S1 +8.5mPD | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 |  | COMPLETED
1010 | TT_TASK | Excavate up to +4.5mPD (2713m3) | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 |  | COMPLETED
1011 | TT_TASK | Install Strut S2 +5.0mPD | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
1012 | TT_TASK | Excavate up to +0.5mPD (3100m3) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 |  | COMPLETED
1013 | TT_TASK | Install Strut S3 +1.0mPD | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1014 | TT_TASK | Excavate up to -3.0mPD (2713m3) | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1015 | TT_TASK | Install Strut S4 -2.5mPD | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 |  | COMPLETED
1016 | TT_TASK | Excavate up to -5.5mPD (4952m3) | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1017 | TT_TASK | Placing of blinding layer | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1021 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1022 | TT_TASK | Erect external formwork for base slab | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1023 | TT_TASK | Rebar fixing for base slab | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1024 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 26 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1025 | TT_TASK | Concreting for base slab (350m3) | Thu Jun 27 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1026 | TT_TASK | Curing for base slab | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1027 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1028 | TT_TASK | Removal of formwork for base slab | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1029 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1030 | TT_TASK | Removal strut S4 and S3 | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1032 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1033 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1034 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1035 | TT_TASK | Concreting for wall and roof (489m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1036 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1037 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1038 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1039 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1040 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1043 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1044 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1045 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1046 | TT_TASK | Curing for wall and roof | Sat Jun 22 08:00:00 IDT 2013 | Mon Jul 01 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1047 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1048 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1050 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Tue Dec 17 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1053 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1054 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1055 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1056 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1057 | TT_TASK | Concreting for base slab (350m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1058 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1059 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1060 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1061 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1062 | TT_TASK | Removal strut S4 and S3 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1064 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1065 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1066 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1067 | TT_TASK | Concreting for wall and roof (489m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1068 | TT_TASK | Curing for wall and roof | Wed Jun 12 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1069 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1070 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 14 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1071 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1072 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Feb 13 08:00:00 IST 2014 | Tue Feb 18 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1074 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1075 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1076 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1077 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1078 | TT_TASK | Curing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1079 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1080 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1081 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1082 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 16 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1084 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (2343m3) | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1085 | TT_TASK | Placing 0.5m thk concrete lateral support (+3.96mPD) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1086 | TT_TASK | Removal strut S2 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 23 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1088 | TT_TASK | Construction of Temporary Culvert (open channel) | Tue Jun 25 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1089 | TT_TASK | Temporary box culvert (At Box 6B Area) Saw Cut D-wall | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 |  | COMPLETED
1090 | TT_TASK | Erect 3m high block wall | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 |  | COMPLETED
1091 | TT_TASK | Connection to East Box Culvert (823B portion) | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 |  | COMPLETED
1092 | TT_TASK | Blinding | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
1093 | TT_TASK | Temporary box culvert (Outside Box 6B Area) Sheet piling | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 |  | COMPLETED
1094 | TT_TASK | ELS Works | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
1095 | TT_TASK | Blinding | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
1096 | TT_TASK | Removal of Temporary Culvert and Reinstatement | Fri May 16 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
1098 | TT_TASK | Reinstatement of TOA's | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 |  |  | IN_PROGRESS
1099 | TT_TASK | Hydroseeding works | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 | Wed Nov 30 18:00:00 IST 2016 |  | COMPLETED
1100 | TT_TASK | Tree Planting works | Thu Sep 01 08:00:00 IDT 2016 | Sat Dec 03 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
1101 | TT_TASK | Woodland Shrub Mix | Thu Sep 01 08:00:00 IDT 2016 | Fri Nov 18 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  | 200.0 | IN_PROGRESS
1104 | TT_TASK | Kam Tin River Diversion (Stage 1-3) | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1106 | TT_TASK | Concrete fill up to +8.0mPD near side A mass concrete wall | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 |  | COMPLETED
1107 | TT_TASK | Construction of mass concrete wall to +8.0mPD at side A (4 bay CH A80~A120) | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1108 | TT_TASK | Construction of base slab lining and low flow channel (4 bay A9~A10, B8~B9; LFC CH 80~110) | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1109 | TT_TASK | Construction of mass concrete wall to +8.0mPD of side B (3 bay CH B60~B90) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1110 | TT_TASK | Construction of T-shaped retaining wall (1 Bay CH B50~B60) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1111 | TT_TASK | Soil backfill at side A from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1112 | TT_TASK | Concrete backfill at side B from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1113 | TT_TASK | Removal strut at +8.5mPD near side A | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1114 | TT_TASK | Concrete fill up to +11.0mPD near side A mass concrete wall | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1115 | TT_TASK | Placing concrete block at side A from +8.0mPD to +11.0mpd at side A (4 bay CH A80~A120) | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1116 | TT_TASK | Soil backfill at side A from +8.0mPD to +11.0mPD | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1117 | TT_TASK | Removal strut at +8.5mPD near side B | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1118 | TT_TASK | Placing concrete block at side B from +8.0mPD to +11.0mPD (4 bay CH B60~B90) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1119 | TT_TASK | Concrete backfill at side B from +8.0mPD to +11.0mPD | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1121 | TT_TASK | Placing temporary concrete block to Up stream at CH30 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 |  | COMPLETED
1122 | TT_TASK | Placing temporary concrete block to Up stream at CH160 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1123 | TT_TASK | Excavation from GL to FL +5.0mPD Up stream (Low flow channel CH 30~60) | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1124 | TT_TASK | Excavation from GL to FL +5.0mPD Down stream (Low flow channel CH 130~160) | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1125 | TT_TASK | Construction of T-shaped retaining wall at Up stream of side B (2 Bay CH B30~B50) | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1126 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (3 bay CH B90~B120) | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1127 | TT_TASK | Construction of Up stream base slab lining and low flow channel (6 Bay A1~A4, B3~B4; Low flow channel CH 30~50) | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1128 | TT_TASK | Construction of Down stream base slab lining and low flow channel (5 Bay A14~A16, B14~B15; LFC CH 140~170) | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1129 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Up stream and saw cut D-wall | Fri Jun 14 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1130 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Down stream and saw cut D-wall | Wed Jun 19 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1131 | TT_TASK | Construction of remaining Up stream base slab lining and low flow channel (7 bay A5~A8, B5~B7; LFC CH 50~80) | Thu Jun 27 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1132 | TT_TASK | Construction of remaining Down stream base slab lining and low flow channel (7 bay A11~A13, B10~B13; LFC CH 110~140) | Wed Jul 03 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1134 | TT_TASK | Relocation of temporary concrete block at Up stream for construction of mass concrete wall at side B | Sat Jul 20 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1135 | TT_TASK | Relocation of temporary concrete block at Down stream for construction of mass concrete wall at side B | Tue Jul 23 08:00:00 IDT 2013 | Wed Jul 24 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1136 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Up stream of side B (3 bay CH B0~B30) | Tue Jul 23 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1137 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (4 bay CH B0~B30) | Thu Jul 25 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1141 | TT_TASK | Application of power supply, environmental permits and construction substation | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1142 | TT_TASK | Procurement and Confirmation of the order of 1st tunnel boring machine | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 |  | COMPLETED
1143 | TT_TASK | Prepare on-demand bond or bank guarantee for the procurement of TBM and submit to Engineer for approval | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 |  | COMPLETED
1144 | TT_TASK | TBM design and submission for approval | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
1145 | TT_TASK | TBM materials order and delivery to factory | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 |  | COMPLETED
1146 | TT_TASK | TBM equipments order and delivery to factory | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 |  | COMPLETED
1147 | TT_TASK | TBM Fabrication | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
1148 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 |  | COMPLETED
1149 | TT_TASK | TBM test Run | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 |  | COMPLETED
1150 | TT_TASK | TBM disassembly and packing for shipping to HK | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 |  | COMPLETED
1151 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
1152 | TT_TASK | Ground treatment for TBM lanching shaft | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 |  | COMPLETED
1153 | TT_TASK | Ground treatment for Cross Passage Tunnel | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1154 | TT_TASK | Box7A Setup TBM facilities, install noise enclosure and CNP application | Fri Jun 01 08:00:00 IDT 2012 | Sat Jan 26 18:00:00 IST 2013 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1155 | TT_TASK | Notice to Contract 824 the anticipated dates of break out TBM Shaft | Sat Jun 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1156 | TT_TASK | Fabrication of tunnel segment mould | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
1157 | TT_TASK | Fabrication 50% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1158 | TT_TASK | Fabrication 100% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
1159 | TT_TASK | Fabrication 30% of North Tunnel North Bound (Uptrack) Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1160 | TT_TASK | Fabrication 60% of North Tunnel North Bound (Uptrack) Precast Lining | Thu Oct 18 08:00:00 IST 2012 | Thu Feb 21 18:00:00 IST 2013 | Thu Oct 18 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1161 | TT_TASK | Fabrication 100% of North Tunnel North Bound (Uptrack) Precast Lining | Mon Aug 19 08:00:00 IDT 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Dec 03 08:00:00 IST 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1163 | TT_TASK | Assemble, T&C of TBM | Fri Jun 01 08:00:00 IDT 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Oct 16 00:00:00 IST 2012 |  | COMPLETED
1164 | TT_TASK | TBM drive & lining installation CH123+369 to CH123+283 Initial Drive (86m) | Sat Nov 03 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 | Wed Oct 17 00:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1165 | TT_TASK | Change Plant (Back-up cars) | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1166 | TT_TASK | TBM drive & lining installation CH123+283 to CH123+183 | Thu Jun 27 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1167 | TT_TASK | TBM drive & lining installation CH123+183 to CH123+083 | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1168 | TT_TASK | TBM drive & lining installation CH123+083 to CH122+983 | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1169 | TT_TASK | TBM drive & lining installation CH122+983 to CH122+883 | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1170 | TT_TASK | TBM drive & lining installation CH122+883 to CH122+783 | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Jun 13 08:00:00 IDT 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
1171 | TT_TASK | TBM drive & lining installation CH122+783 to CH122+683 | Sat Nov 02 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1172 | TT_TASK | TBM drive & lining installation CH122+683 to CH122+583 | Tue Dec 03 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Wed Feb 26 18:00:00 IST 2014 |  | COMPLETED
1173 | TT_TASK | TBM drive & lining installation CH122+583 to CH122+491 | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Feb 27 08:00:00 IST 2014 | Sat Aug 16 00:00:00 IDT 2014 |  | COMPLETED
1174 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1175 | TT_TASK | Dis-assemble TBM | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
1176 | TT_TASK | Invert slab, side walkway | Sat Oct 04 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 | Mon Sep 15 08:00:00 IDT 2014 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1177 | TT_TASK | Installation of cable bracket | Tue Dec 30 08:00:00 IST 2014 | Tue Jan 13 18:00:00 IST 2015 | Fri Sep 12 08:00:00 IDT 2014 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
1178 | TT_TASK | Provision of assess open for DC and modify of strut S1 and S2 at north bound | Tue Nov 04 11:12:00 IST 2014 | Thu Dec 04 11:12:00 IST 2014 | Wed Oct 01 08:00:00 IDT 2014 | Sat Oct 18 18:00:00 IDT 2014 |  | COMPLETED
1180 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Oct 06 13:00:00 IDT 2014 | Mon Oct 20 12:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
1181 | TT_TASK | Assemble, T&C of TBM | Mon Nov 03 08:00:00 IST 2014 | Fri Jan 02 18:00:00 IST 2015 | Sat Oct 04 08:00:00 IDT 2014 | Fri Nov 28 18:00:00 IST 2014 |  | COMPLETED
1182 | TT_TASK | Setup back-up plant for final drive | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
1183 | TT_TASK | Reinstate of noise enclosure | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Sat Nov 29 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1184 | TT_TASK | TBM drive & lining installation CH123+384 to CH123+284 (Initial Drive) | Sat Dec 06 08:00:00 IST 2014 | Thu Jan 22 18:00:00 IST 2015 | Tue Dec 02 00:00:00 IST 2014 | Tue Jan 20 18:00:00 IST 2015 |  | COMPLETED
1185 | TT_TASK | TBM drive & lining installation CH123+184 to CH123+084 | Wed Jan 21 08:00:00 IST 2015 | Wed Jan 28 18:00:00 IST 2015 | Wed Jan 21 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 |  | COMPLETED
1186 | TT_TASK | TBM drive & lining installation CH123+084 to CH122+984 | Wed Feb 04 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 | Thu Feb 12 08:00:00 IST 2015 | Thu Feb 26 18:00:00 IST 2015 |  | COMPLETED
1187 | TT_TASK | TBM drive & lining installation CH122+984 to CH122+884 | Thu Feb 12 08:00:00 IST 2015 | Tue Feb 24 18:00:00 IST 2015 | Fri Feb 27 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1188 | TT_TASK | TBM drive & lining installation CH122+884 to CH122+784 | Tue Mar 10 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Wed May 27 18:00:00 IDT 2015 |  | COMPLETED
1189 | TT_TASK | TBM drive & lining installation CH122+784 to CH122+684 | Wed May 06 08:00:00 IDT 2015 | Thu May 14 18:00:00 IDT 2015 | Thu May 28 08:00:00 IDT 2015 | Sat Jul 11 18:00:00 IDT 2015 |  | COMPLETED
1190 | TT_TASK | TBM drive & lining installation CH122+684 to CH122+584 | Fri Jul 03 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
1191 | TT_TASK | TBM drive & lining installation CH122+584 to CH122+506 | Tue Nov 03 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 |  | COMPLETED
1192 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 |  | COMPLETED
1193 | TT_TASK | Dis-assemble TBM | Wed Dec 16 08:00:00 IST 2015 | Fri Jan 22 18:00:00 IST 2016 | Sun Dec 13 08:00:00 IST 2015 | Sun Mar 13 18:00:00 IST 2016 |  | COMPLETED
1194 | TT_TASK | Invert slab, side walkway | Fri Apr 01 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 | Mon Mar 14 08:00:00 IST 2016 | Tue May 24 18:00:00 IDT 2016 |  | COMPLETED
1195 | TT_TASK | Installation of cable bracket | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Mar 15 18:00:00 IST 2016 |  | COMPLETED
1196 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Mon Feb 01 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 22 18:00:00 IST 2016 |  | COMPLETED
1199 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 1 (From Downtrack to Centre of CP) | Thu Apr 10 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Sat Jun 28 18:00:00 IDT 2014 |  | COMPLETED
1200 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Sun Nov 09 18:00:00 IST 2014 |  | COMPLETED
1201 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1202 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 18:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1203 | TT_TASK | Excavation 0-4mts with Shotcrete | Mon Feb 02 08:00:00 IST 2015 | Tue Feb 17 18:00:00 IST 2015 | Mon Feb 23 08:00:00 IST 2015 | Mon Mar 30 18:00:00 IDT 2015 |  | COMPLETED
1204 | TT_TASK | Invert Concrete | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1205 | TT_TASK | Wall and Roof concrete | Thu Apr 16 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 |  | COMPLETED
1206 | TT_TASK | Dismantle Temporary frame | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 |  | COMPLETED
1207 | TT_TASK | Install Door to Cross Passage (By contract 827) | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 |  | COMPLETED
1208 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 2 (From Centre of CP to Uptrack) | Sat Oct 17 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Sep 07 08:00:00 IDT 2015 | Tue Dec 01 18:00:00 IST 2015 |  | COMPLETED
1209 | TT_TASK | Probe/Grout | Thu Jun 25 08:00:00 IDT 2015 | Mon Jul 06 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Fri Apr 10 18:00:00 IDT 2015 |  | COMPLETED
1210 | TT_TASK | Coring of Segment | Tue Jul 07 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Sat Apr 11 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1211 | TT_TASK | Removal of segment | Sat Jul 11 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
1212 | TT_TASK | Excavation 0-4mts with Shotcrete | Wed Jul 15 08:00:00 IDT 2015 | Sat Jul 25 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1213 | TT_TASK | Invert Concrete | Sat Jul 18 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 | Thu May 07 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1214 | TT_TASK | Wall and Roof concrete | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1215 | TT_TASK | Dismantle Temporary frame | Tue Jan 19 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 04 18:00:00 IST 2016 |  | COMPLETED
1216 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Feb 22 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Fri Feb 05 08:00:00 IST 2016 | Sat Feb 06 18:00:00 IST 2016 |  | COMPLETED
1218 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 1 (From Downtrack to Centre of CP) | Tue Mar 11 08:00:00 IST 2014 | Wed Mar 26 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1219 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Wed Nov 12 18:00:00 IST 2014 |  | COMPLETED
1220 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Thu Nov 13 08:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1221 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Tue Nov 18 08:00:00 IST 2014 | Thu Nov 20 18:00:00 IST 2014 |  | COMPLETED
1222 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Sat Nov 22 08:00:00 IST 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1223 | TT_TASK | Invert Concrete | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
1224 | TT_TASK | Wall and Roof concrete | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1225 | TT_TASK | Dismantle Temporary frame | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1226 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1227 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 2 (From Centre of CP to Uptrack) | Thu May 21 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Mar 09 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1228 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Mon May 04 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1229 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
1230 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1231 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 22 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
1232 | TT_TASK | Invert Concrete | Sat Aug 08 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Wed Jul 08 18:00:00 IDT 2015 |  | COMPLETED
1233 | TT_TASK | Wall and Roof concrete | Tue Aug 25 08:00:00 IDT 2015 | Mon Sep 07 18:00:00 IDT 2015 | Thu Jul 09 08:00:00 IDT 2015 | Sat Aug 15 18:00:00 IDT 2015 |  | COMPLETED
1234 | TT_TASK | Dismantle Temporary frame | Tue Sep 22 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 | Mon Aug 17 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 |  | COMPLETED
1235 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1237 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 1 (From Downtrack to Centre of CP) | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Sat May 24 18:00:00 IDT 2014 |  | COMPLETED
1238 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
1239 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1240 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 |  | COMPLETED
1241 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Mon Nov 17 08:00:00 IST 2014 | Sat Nov 29 18:00:00 IST 2014 |  | COMPLETED
1242 | TT_TASK | Invert Concrete | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 |  | COMPLETED
1243 | TT_TASK | Wall and Roof concrete | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 |  | COMPLETED
1244 | TT_TASK | Dismantle Temporary frame | Tue Dec 30 08:00:00 IST 2014 | Wed Jan 07 18:00:00 IST 2015 | Tue Dec 30 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1245 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1246 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 2 (From Centre of CP to Uptrack) | Fri May 08 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 |  | COMPLETED
1247 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
1248 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
1249 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Thu May 07 18:00:00 IDT 2015 |  | COMPLETED
1250 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
1251 | TT_TASK | Invert Concrete | Wed Aug 05 08:00:00 IDT 2015 | Fri Aug 14 18:00:00 IDT 2015 | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
1252 | TT_TASK | Wall and Roof concrete | Tue Sep 15 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Wed Aug 26 18:00:00 IDT 2015 |  | COMPLETED
1253 | TT_TASK | Dismantle Temporary frame | Sat Oct 17 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Oct 08 18:00:00 IDT 2015 |  | COMPLETED
1254 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1258 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 |  | COMPLETED
1259 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1260 | TT_TASK | D-wall construction (1192m3) | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 |  | COMPLETED
1261 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1262 | TT_TASK | Construct capping beam, cobble, etc. (including bay 6 and 5) | Sat Oct 27 08:00:00 IST 2012 | Sat Feb 16 18:00:00 IST 2013 | Sat Oct 27 08:00:00 IST 2012 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1264 | TT_TASK | Excavate up to +22.0mPD (1860m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1265 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 |  | COMPLETED
1266 | TT_TASK | Excavate up to +16.5mPD (3410m3) | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 |  | COMPLETED
1267 | TT_TASK | Install Strut S2 +17.0mPD | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 |  | COMPLETED
1268 | TT_TASK | Excavate up to +11.0mPD (3410m3) | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 |  | COMPLETED
1269 | TT_TASK | Install Strut S3 +11.5mPD | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 |  | COMPLETED
1270 | TT_TASK | Excavate up to +7.0mPD (2480m3) | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 |  | COMPLETED
1271 | TT_TASK | Install Strut S4 +7.5mPD | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1272 | TT_TASK | Excavate up to +3.5mPD (2170m3) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 |  | COMPLETED
1273 | TT_TASK | Install Strut S5 +4.0mPD | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1274 | TT_TASK | Excavate up to formation (2294m3) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1275 | TT_TASK | Construct temp. 500mm thick plain concrete base slab | Thu Oct 18 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 |  | COMPLETED
1276 | TT_TASK | Removal of South Bound strut to +9.50mPD | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1277 | TT_TASK | Removal of North Bound strut to +9.50mPD | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 |  | COMPLETED
1278 | TT_TASK | Construct temp. 500mm thick TBM concrete base slab | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1279 | TT_TASK | Construction entrance seal for TBM at South Bound | Mon Nov 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1280 | TT_TASK | Construction entrance seal for TBM at North Bound | Sat Jul 20 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1281 | TT_TASK | Saw cut South Bound diaphragm wall | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1282 | TT_TASK | Saw cut North Bound diaphragm wall | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1286 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 05 18:00:00 IDT 2014 | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 |  | COMPLETED
1287 | TT_TASK | Erect external formwork (Base Slab) | Sat Sep 06 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 21 18:00:00 IDT 2014 |  | COMPLETED
1288 | TT_TASK | Rebar fixing (Base Slab) | Wed Sep 10 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Tue Jul 22 08:00:00 IDT 2014 | Sat Jul 26 18:00:00 IDT 2014 |  | COMPLETED
1289 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Sep 15 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Sun Jul 27 08:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1290 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Thu Aug 14 18:00:00 IDT 2014 |  | COMPLETED
1291 | TT_TASK | Concreting (Base Slab) (225m3) | Sat Aug 09 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Fri Aug 15 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
1292 | TT_TASK | Curing (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
1293 | TT_TASK | Removal of formwork (Base Slab) | Tue Aug 12 08:00:00 IDT 2014 | Tue Aug 12 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1294 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed Aug 13 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Mon Sep 15 18:00:00 IDT 2014 |  | COMPLETED
1295 | TT_TASK | Rebar fixing (Wall & Roof) | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 |  | COMPLETED
1296 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 |  | COMPLETED
1297 | TT_TASK | Clearing and inspection (Wall & Roof) | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
1298 | TT_TASK | Concreting (Wall & Roof) (450m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
1299 | TT_TASK | Curing (Wall & Roof) | Sat Oct 11 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
1300 | TT_TASK | Removal external formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1301 | TT_TASK | Removal internal falsework (Wall & Roof) | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 |  | COMPLETED
1302 | TT_TASK | Side walkway and cable bracket (102m3) | Sat Oct 18 08:00:00 IDT 2014 | Wed Oct 29 18:00:00 IST 2014 | Mon Sep 01 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1304 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Wed Nov 11 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Oct 19 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1305 | TT_TASK | Erect external formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 |  | COMPLETED
1306 | TT_TASK | Rebar fixing (Base Slab) | Mon Nov 16 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Tue Oct 27 08:00:00 IST 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1307 | TT_TASK | Erect internal kicker formwork (Base Slab) | Fri Nov 20 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Oct 31 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 |  | COMPLETED
1308 | TT_TASK | Clearing and inspection (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
1309 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1310 | TT_TASK | Curing (Base Slab) | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 |  | COMPLETED
1311 | TT_TASK | Removal of formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 |  | COMPLETED
1312 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
1313 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Dec 09 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
1314 | TT_TASK | Erect external formwork (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Thu Jan 07 18:00:00 IST 2016 |  | COMPLETED
1315 | TT_TASK | Clearing and inspection (Wall & Roof) | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Fri Jan 08 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
1316 | TT_TASK | Concreting (Wall & Roof) (450m3) | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
1317 | TT_TASK | Curing (Wall & Roof) | Tue Jan 12 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
1318 | TT_TASK | Removal external formwork (Wall ) | Thu Jan 14 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
1319 | TT_TASK | Removal internal falsework, formwork and reproping (Wall & Roof) | Thu Jan 28 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 |  | COMPLETED
1320 | TT_TASK | Side walkway and cable bracket (102m3) | Wed Dec 23 08:00:00 IST 2015 | Wed Jan 06 18:00:00 IST 2016 | Wed Nov 11 08:00:00 IST 2015 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
1322 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 |  | COMPLETED
1323 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 |  | COMPLETED
1324 | TT_TASK | Backfilling to 0.5m below S3 (+11.0mPD) (3486m3) | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 |  | COMPLETED
1325 | TT_TASK | Removal strut S3 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
1326 | TT_TASK | Backfilling to 0.5m below S2 (+16.5mPD) (3410m3) | Wed Mar 16 08:00:00 IST 2016 | Fri Apr 08 18:00:00 IDT 2016 | Wed Mar 16 08:00:00 IST 2016 | Tue Apr 12 18:00:00 IDT 2016 |  | COMPLETED
1327 | TT_TASK | Removal strut S2 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 |  | COMPLETED
1328 | TT_TASK | Backfilling to 0.5m below S1 (+22.0mPD) (3410m3) | Fri Apr 15 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 | Fri Apr 15 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
1329 | TT_TASK | Removal strut S1 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 |  | COMPLETED
1330 | TT_TASK | Backfilling to original ground level (approx. +25.0mPD) (1860m3) | Thu May 05 08:00:00 IDT 2016 | Tue May 17 18:00:00 IDT 2016 | Thu May 05 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
1333 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1334 | TT_TASK | D-wall construction (2844m3) | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1335 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1337 | TT_TASK | Excavate up to +22.0mPD (3720m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1338 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 |  | COMPLETED
1339 | TT_TASK | Excavate up to +16.5mPD (4880m3) | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 |  | COMPLETED
1340 | TT_TASK | Install Strut S2 +17.0mPD | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 |  | COMPLETED
1341 | TT_TASK | Excavate up to +11.0mPD (6820m3) | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
1342 | TT_TASK | Install Strut S3 +11.5mPD | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 |  | COMPLETED
1343 | TT_TASK | Excavate up to +7.0mPD (4960m3) | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 |  | COMPLETED
1344 | TT_TASK | Install Strut S4 +7.5mPD | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1345 | TT_TASK | Excavate up to +3.5mPD (4340m3) | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1346 | TT_TASK | Install Strut S5 +4.0mPD | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 |  | COMPLETED
1347 | TT_TASK | Excavate up to formation (4960m3) | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 |  | COMPLETED
1348 | TT_TASK | Construct temp. 500mm thick plain concrete base slab at Bay 5 & 6 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1349 | TT_TASK | Excavation to formation and place blinding Bay 4a | Thu Oct 18 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1350 | TT_TASK | Excavation to formation and place blinding Bay 4b | Fri Jun 21 08:00:00 IDT 2013 | Fri Jul 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1351 | TT_TASK | Excavation to formation and place blinding Bay3 | Sat Jul 13 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1352 | TT_TASK | Excavation to formation and place blinding Bay2 to Bay1 | Wed Jul 24 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1356 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 |  | COMPLETED
1357 | TT_TASK | Erect external formwork for base slab | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 |  | COMPLETED
1358 | TT_TASK | Rebar fixing for base slab | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1359 | TT_TASK | Erect internal kicker formwork for base slab | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1360 | TT_TASK | Concreting for base slab (363m3) | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1361 | TT_TASK | Curing for base slab | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1362 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1363 | TT_TASK | Removal of formwork for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1364 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1365 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 27 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1366 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1367 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1368 | TT_TASK | Curing for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1369 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1370 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 10 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1371 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 19 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jan 24 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1372 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 08 08:00:00 IST 2015 | Tue Jan 13 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1374 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 |  | COMPLETED
1375 | TT_TASK | Erect external formwork for base slab | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1376 | TT_TASK | Rebar fixing for base slab | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1377 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 |  | COMPLETED
1378 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1379 | TT_TASK | Curing for base slab | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1380 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1381 | TT_TASK | Removal of formwork for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1382 | TT_TASK | Rebar fixing for central slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1383 | TT_TASK | Erect external formwork for central slab | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1384 | TT_TASK | Concreting for central slab (450m3) | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1385 | TT_TASK | Curing for central slab | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1386 | TT_TASK | Preparation of construction joint for central slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1387 | TT_TASK | Removal of formwork for central slab | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1388 | TT_TASK | Removal strut S5 and S4 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1389 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1390 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1391 | TT_TASK | Erect external formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1392 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1393 | TT_TASK | Curing for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1394 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1395 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 08 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1396 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1397 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Nov 19 08:00:00 IST 2015 | Tue Nov 24 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 |  | COMPLETED
1400 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1401 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1402 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1403 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1404 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1405 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1406 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1407 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1408 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1409 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1410 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 10 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1411 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1412 | TT_TASK | Curing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1413 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1414 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1415 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1416 | TT_TASK | Side walkway and cable bracket | Fri Jan 02 08:00:00 IST 2015 | Wed Jan 07 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1418 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1419 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1420 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1421 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1422 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1423 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1424 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1425 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1426 | TT_TASK | Rebar fixing for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1427 | TT_TASK | Erect external formwork for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1428 | TT_TASK | Concreting for central slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1429 | TT_TASK | Curing for central slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1430 | TT_TASK | Preparation of construction joint for central slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1431 | TT_TASK | Removal of formwork for central slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 21 18:00:00 IST 2012 |  | COMPLETED
1432 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1433 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1434 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1435 | TT_TASK | Erect external formwork for wall | Mon Jul 15 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1436 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1437 | TT_TASK | Curing for wall and roof | Sun Jul 21 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1438 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1439 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 22 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1440 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 31 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1441 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Sep 16 08:00:00 IDT 2015 | Mon Sep 21 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1443 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1444 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1445 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1446 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1447 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1448 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1449 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1450 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1451 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1452 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1453 | TT_TASK | Erect external formwork for wall | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1454 | TT_TASK | Concreting for wall and roof (444m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1455 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1456 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1457 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Sat Feb 09 18:00:00 IST 2013 |  | COMPLETED
1458 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Nov 09 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Tue Oct 06 08:00:00 IDT 2015 | Sat Oct 10 18:00:00 IDT 2015 |  | COMPLETED
1461 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1462 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1463 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1464 | TT_TASK | Erect internal kicker formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1465 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1466 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1467 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1468 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1469 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1470 | TT_TASK | Curing | Wed Jun 12 08:00:00 IDT 2013 | Wed Jun 12 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1471 | TT_TASK | Removal strut S5 and S4 | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1473 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1474 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1475 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1476 | TT_TASK | Concreting for wall and roof (450m3) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1477 | TT_TASK | Curing for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1478 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1479 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1480 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 29 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1481 | TT_TASK | Side walkway and cable bracket | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1483 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1484 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1485 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1486 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1487 | TT_TASK | Curing for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1488 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1489 | TT_TASK | Removal external wall formwork for wall | Wed Jun 26 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1490 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1491 | TT_TASK | Side walkway and cable bracket | Fri Sep 04 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
1494 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1495 | TT_TASK | Erect external formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1496 | TT_TASK | Rebar fixing for base slab | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1497 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1498 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 |  | COMPLETED
1499 | TT_TASK | Curing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1500 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1501 | TT_TASK | Removal of formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1502 | TT_TASK | Shear beam | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1503 | TT_TASK | Curing | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1504 | TT_TASK | Removal strut S5 and S4 | Wed Jun 19 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1506 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 24 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1507 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1508 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1509 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1510 | TT_TASK | Curing for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1511 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1512 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1513 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1514 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
1516 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1517 | TT_TASK | Rebar fixing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1518 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1519 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1520 | TT_TASK | Curing for wall and roof | Sun Jun 23 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1521 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1522 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 25 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1523 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 03 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1524 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Aug 29 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1527 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1528 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Sat Dec 22 18:00:00 IST 2012 |  | COMPLETED
1529 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1530 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1531 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1532 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1533 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1534 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Fri Jan 11 18:00:00 IST 2013 |  | COMPLETED
1535 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Jan 12 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1536 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1537 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1539 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1540 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1541 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1542 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1543 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1544 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1545 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1546 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1547 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 |  | COMPLETED
1549 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1550 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Mon Feb 25 18:00:00 IST 2013 |  | COMPLETED
1551 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1552 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1553 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1554 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1555 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1556 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1557 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Aug 24 08:00:00 IDT 2015 | Fri Aug 28 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1560 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1561 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1562 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1563 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1564 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1565 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1566 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1567 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1568 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1569 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1570 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1572 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1573 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1574 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1575 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1576 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1577 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1578 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1579 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1580 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
1582 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1583 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1584 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1585 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1586 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1587 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1588 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1589 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1590 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Aug 18 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1593 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1594 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1595 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1596 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1597 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1598 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1599 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1600 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1601 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1602 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1603 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1605 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 31 18:00:00 IDT 2013 |  | COMPLETED
1606 | TT_TASK | Rebar fixing for wall and roof | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 |  | COMPLETED
1607 | TT_TASK | Erect external formwork for wall and roof | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 | Fri Sep 06 08:00:00 IDT 2013 | Thu Sep 12 18:00:00 IDT 2013 |  | COMPLETED
1608 | TT_TASK | Concreting for wall and roof (450m3) | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 |  | COMPLETED
1609 | TT_TASK | Curing for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1610 | TT_TASK | Preparation of construction joint for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1611 | TT_TASK | Removal external and internal formwork for wall | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Wed Sep 25 18:00:00 IDT 2013 |  | COMPLETED
1612 | TT_TASK | Removal internal falsework and formwork for roof | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1613 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 08 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1615 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 20 18:00:00 IST 2013 |  | COMPLETED
1616 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1617 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1618 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1619 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1620 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1621 | TT_TASK | Removal external wall formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1622 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1623 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Aug 12 08:00:00 IDT 2015 | Mon Aug 17 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1626 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1627 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1628 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Feb 14 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1629 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1630 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Mon Feb 18 18:00:00 IST 2013 |  | COMPLETED
1631 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1632 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1633 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1634 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1635 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1636 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1638 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jul 12 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1639 | TT_TASK | Rebar fixing for wall and roof | Wed Jul 17 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1640 | TT_TASK | Erect external formwork for wall and roof | Wed Aug 14 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1641 | TT_TASK | Concreting for wall and roof (450m3) | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1642 | TT_TASK | Curing for wall and roof | Sun Aug 11 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1643 | TT_TASK | Preparation of construction joint for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1644 | TT_TASK | Removal external and internal formwork for wall | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1645 | TT_TASK | Removal internal falsework and formwork for roof | Wed Aug 21 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1646 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 03 08:00:00 IST 2014 | Fri Mar 07 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1648 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1649 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1650 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Apr 09 08:00:00 IDT 2013 | Thu Apr 11 18:00:00 IDT 2013 |  | COMPLETED
1651 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1652 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1653 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1654 | TT_TASK | Removal external wall formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1655 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
1656 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Aug 06 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Mon Jul 27 08:00:00 IDT 2015 | Fri Jul 31 18:00:00 IDT 2015 |  | COMPLETED
1658 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Sep 12 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1659 | TT_TASK | Rebar fixing for roof | Tue Sep 17 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1660 | TT_TASK | Erect external formwork for roof | Thu Sep 19 08:00:00 IDT 2013 | Thu Sep 19 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1661 | TT_TASK | Concreting for roof (444m3) | Sat Sep 21 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1662 | TT_TASK | Curing for roof | Sun Sep 22 08:00:00 IDT 2013 | Tue Oct 01 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1663 | TT_TASK | Preparation of construction joint for roof | Mon Sep 23 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1664 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1665 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1668 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1669 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1670 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1671 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1672 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1673 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1674 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1675 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1676 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1677 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1678 | TT_TASK | Removal strut S5 and S4 | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1680 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Thu Apr 25 18:00:00 IDT 2013 |  | COMPLETED
1681 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri May 03 08:00:00 IDT 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
1682 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Thu May 16 08:00:00 IDT 2013 | Thu May 23 18:00:00 IDT 2013 |  | COMPLETED
1683 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1684 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1685 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1686 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Wed May 29 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1687 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1688 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 19 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1690 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Fri Apr 19 18:00:00 IDT 2013 |  | COMPLETED
1691 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1692 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Apr 25 08:00:00 IDT 2013 | Sat Apr 27 18:00:00 IDT 2013 |  | COMPLETED
1693 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1694 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1695 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1696 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1697 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1698 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 02 08:00:00 IDT 2015 | Sat Apr 11 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Feb 27 18:00:00 IST 2015 |  | COMPLETED
1700 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1701 | TT_TASK | Rebar fixing for roof | Tue Aug 06 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1702 | TT_TASK | Erect external formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1703 | TT_TASK | Concreting for roof (444m3) | Fri Aug 09 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 |  | COMPLETED
1704 | TT_TASK | Curing for roof | Thu Aug 01 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1705 | TT_TASK | Preparation of construction joint for roof | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 |  | COMPLETED
1706 | TT_TASK | Removal internal falsework and formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1707 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 09 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1710 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Wed Feb 20 18:00:00 IST 2013 |  | COMPLETED
1711 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1712 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1713 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1714 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1715 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1716 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1717 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1718 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1719 | TT_TASK | Curing | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1720 | TT_TASK | Removal strut S5 and S4 | Mon Jun 24 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1722 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1723 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1724 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Wed Jul 10 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1725 | TT_TASK | Concreting for wall and roof (450m3) | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1726 | TT_TASK | Curing for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1727 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1728 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 |  | COMPLETED
1729 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 |  | COMPLETED
1730 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1732 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1733 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1734 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1735 | TT_TASK | Concreting for wall and roof (450m3) | Tue Sep 03 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1736 | TT_TASK | Curing for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1737 | TT_TASK | Preparation of construction joint for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 |  | COMPLETED
1738 | TT_TASK | Removal external and internal formwork for wall | Thu Sep 05 08:00:00 IDT 2013 | Fri Sep 06 18:00:00 IDT 2013 | Thu Aug 22 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1739 | TT_TASK | Removal internal falsework and formwork for roof | Sat Sep 14 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 |  | COMPLETED
1740 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 05 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1742 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1743 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1744 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1745 | TT_TASK | Concreting for roof (363m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1746 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Sun Oct 20 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1747 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1748 | TT_TASK | Removal internal falsework and formwork for roof | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1749 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Dec 24 13:00:00 IST 2013 | Thu Jan 02 12:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1752 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1753 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1754 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1755 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Apr 12 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1756 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1757 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1758 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1759 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1760 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1761 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1762 | TT_TASK | Removal strut S5 and S4 | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1764 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Aug 05 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1765 | TT_TASK | Rebar fixing for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1766 | TT_TASK | Erect external formwork for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1767 | TT_TASK | Concreting for wall and roof (450m3) | Thu Aug 15 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1768 | TT_TASK | Curing for wall and roof | Fri Aug 16 08:00:00 IDT 2013 | Sun Aug 25 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1769 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1770 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1771 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 |  | COMPLETED
1772 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Feb 04 08:00:00 IST 2014 | Sat Feb 08 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1774 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Aug 07 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1775 | TT_TASK | Rebar fixing for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1776 | TT_TASK | Erect external formwork for wall and roof | Thu Aug 15 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1777 | TT_TASK | Concreting for wall and roof (450m3) | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1778 | TT_TASK | Curing for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1779 | TT_TASK | Preparation of construction joint for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 |  | COMPLETED
1780 | TT_TASK | Removal external and internal formwork for wall | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Wed Aug 21 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 |  | COMPLETED
1781 | TT_TASK | Removal internal falsework and formwork for roof | Mon Sep 16 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1782 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Nov 19 08:00:00 IST 2014 | Mon Nov 24 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1784 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1785 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1786 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1787 | TT_TASK | Concreting for roof (450m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1788 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1789 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1790 | TT_TASK | Removal internal falsework and formwork for roof | Fri Oct 18 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1791 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 13 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1794 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1795 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1796 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1797 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1798 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 28 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1799 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1800 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1801 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1802 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1803 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1804 | TT_TASK | Removal strut S5 and S4 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1806 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1807 | TT_TASK | Rebar fixing for wall and roof | Sat Jul 20 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1808 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1809 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1810 | TT_TASK | Curing for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1811 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1812 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 29 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1813 | TT_TASK | Removal internal falsework and formwork for roof | Tue Aug 06 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1814 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 18:00:00 IST 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1816 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1817 | TT_TASK | Rebar fixing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1818 | TT_TASK | Erect external formwork for wall and roof | Fri Jul 19 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1819 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1820 | TT_TASK | Curing for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Thu Mar 28 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1821 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Mar 29 08:00:00 IDT 2013 | Fri Mar 29 18:00:00 IDT 2013 |  | COMPLETED
1822 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Sat Mar 30 08:00:00 IDT 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1823 | TT_TASK | Removal internal falsework and formwork for roof | Fri Aug 02 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Mon Apr 01 18:00:00 IDT 2013 |  | COMPLETED
1824 | TT_TASK | Side walkway and cable bracket | Thu Nov 13 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1826 | TT_TASK | Erect internal formwork & Falsework for roof | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1827 | TT_TASK | Rebar fixing for roof | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 |  | COMPLETED
1828 | TT_TASK | Erect shutter formwork for roof | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 09 18:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1829 | TT_TASK | Concreting for roof (450m3) | Tue Sep 10 08:00:00 IDT 2013 | Tue Sep 10 18:00:00 IDT 2013 | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 |  | COMPLETED
1830 | TT_TASK | Curing for roof | Wed Sep 11 08:00:00 IDT 2013 | Fri Sep 20 18:00:00 IDT 2013 | Tue Jul 23 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 |  | COMPLETED
1831 | TT_TASK | Preparation of construction joint for roof | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 11 18:00:00 IDT 2013 | Sat Aug 03 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1832 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 26 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 |  | COMPLETED
1833 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 06 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Aug 13 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1835 | TT_TASK | Water proofing and soil backfilling to 0.5m below top of Tunnel Bay 3 to Bay 1 | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1836 | TT_TASK | Mass infill between D-wall and tunnel wall | Fri Oct 11 08:00:00 IDT 2013 | Wed Oct 16 18:00:00 IDT 2013 | Fri Sep 20 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1837 | TT_TASK | Removal S3 and S2 | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
1838 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 4 | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Sat May 18 18:00:00 IDT 2013 |  | COMPLETED
1839 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 5 and remove S3 & S2 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1840 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 6 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1843 | TT_TASK | Pre-drilling and guidewall | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1844 | TT_TASK | D-wall design review | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1845 | TT_TASK | D-wall construction (4741m3) | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 |  | COMPLETED
1846 | TT_TASK | Shear pin and pumping test | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 15 18:00:00 IST 2012 | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1848 | TT_TASK | ELS works to formation level from SN16 to SN19 (soil: 8,700m3 @350m3/day, Install S1 to S3 strut 5 days/layer) | Wed Sep 25 08:00:00 IDT 2013 | Wed Nov 13 18:00:00 IST 2013 | Wed May 08 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1849 | TT_TASK | Design temporary bridge and approval | Mon Sep 01 08:00:00 IDT 2014 | Wed Nov 12 18:00:00 IST 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1850 | TT_TASK | Application of tree transplant | Sat Jun 01 08:00:00 IDT 2013 | Wed Oct 23 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1851 | TT_TASK | Tree transplant | Tue Oct 14 08:00:00 IDT 2014 | Mon Nov 10 18:00:00 IST 2014 | Tue Sep 02 08:00:00 IDT 2014 | Tue Sep 30 18:00:00 IDT 2014 |  | COMPLETED
1852 | TT_TASK | Erection temporary bridge deck | Fri Oct 03 08:00:00 IDT 2014 | Fri Dec 05 18:00:00 IST 2014 | Fri Oct 03 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1853 | TT_TASK | ELS works to formation level from SN10 to SN15 (soil: 9,455m3 @330m3/day, install S1 to S3 strut 5 days/layer) | Mon Nov 24 08:00:00 IST 2014 | Sat Jan 17 18:00:00 IST 2015 | Mon Nov 24 08:00:00 IST 2014 | Tue Jun 23 18:00:00 IDT 2015 |  | COMPLETED
1856 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
1857 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1858 | TT_TASK | Erect external formwork for wall and roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1859 | TT_TASK | Concreting for wall and roof (215m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
1860 | TT_TASK | Curing for wall and roof | Sun Dec 08 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
1861 | TT_TASK | Preparation of construction joint for wall and roof | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1862 | TT_TASK | Removal external and internal formwork for wall | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1863 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1864 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 03 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 | Mon Mar 24 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
1866 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 14 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1867 | TT_TASK | Rebar fixing for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1868 | TT_TASK | Erect external formwork for wall and roof | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1869 | TT_TASK | Concreting for wall and roof (215m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1870 | TT_TASK | Curing for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Sun Dec 29 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1871 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
1872 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 17 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
1873 | TT_TASK | Removal internal falsework and formwork for roof | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1874 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 |  | COMPLETED
1876 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 28 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Nov 28 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1877 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1878 | TT_TASK | Erect external formwork for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1879 | TT_TASK | Concreting for wall and roof (215m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1880 | TT_TASK | Curing for wall and roof | Wed Jan 01 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
1881 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
1882 | TT_TASK | Removal external and internal formwork for wall | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 |  | COMPLETED
1883 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
1884 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 |  | COMPLETED
1886 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1887 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 14 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1888 | TT_TASK | Erect external formwork for wall and roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1889 | TT_TASK | Concreting for wall and roof (215m3) | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1890 | TT_TASK | Curing for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1892 | TT_TASK | Removal external and internal formwork for wall | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1893 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1894 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 |  | COMPLETED
1896 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 08:00:00 IST 2013 |  | COMPLETED
1897 | TT_TASK | Rebar fixing for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1898 | TT_TASK | Erect external formwork for wall and roof | Fri Jan 03 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1899 | TT_TASK | Concreting for wall and roof (215m3) | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1900 | TT_TASK | Curing for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 16 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1901 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Tue Jan 07 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1902 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1903 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1904 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 |  | COMPLETED
1906 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1907 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1908 | TT_TASK | Erect external formwork for wall and roof | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1909 | TT_TASK | Concreting for wall and roof (215m3) | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1910 | TT_TASK | Curing for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1911 | TT_TASK | Preparation of construction joint for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1912 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1913 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1914 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 |  | COMPLETED
1916 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1917 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 |  | COMPLETED
1918 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Tue Jun 04 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 |  | COMPLETED
1919 | TT_TASK | Concreting for wall and roof (333m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1920 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1921 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Wed Jun 12 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1922 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 |  | COMPLETED
1923 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
1924 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 05 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Tue Mar 04 18:00:00 IST 2014 |  | COMPLETED
1926 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1927 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1928 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1929 | TT_TASK | Concreting for wall and roof (412m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1930 | TT_TASK | Curing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Sun Jun 23 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Sat Mar 23 18:00:00 IST 2013 |  | COMPLETED
1931 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Mar 25 08:00:00 IST 2013 | Mon Mar 25 18:00:00 IST 2013 |  | COMPLETED
1932 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Mar 26 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1933 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jun 24 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1934 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 27 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Mon Mar 03 18:00:00 IST 2014 |  | COMPLETED
1936 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1937 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1938 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Apr 02 18:00:00 IDT 2013 |  | COMPLETED
1939 | TT_TASK | Concreting for wall and roof (320m3) | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Apr 05 08:00:00 IDT 2013 | Fri Apr 05 18:00:00 IDT 2013 |  | COMPLETED
1940 | TT_TASK | Curing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 06 08:00:00 IDT 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1941 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1942 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1943 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1944 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jan 21 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Sat Mar 01 18:00:00 IST 2014 |  | COMPLETED
1946 | TT_TASK | Excavation and saw cut D-wall | Thu Apr 02 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Sat Jul 25 18:00:00 IDT 2015 |  | COMPLETED
1947 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Aug 08 16:24:00 IDT 2015 | Mon Aug 10 16:24:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Mon Jul 13 18:00:00 IDT 2015 |  | COMPLETED
1948 | TT_TASK | Erect external formwork for base slab | Mon Aug 10 16:24:00 IDT 2015 | Wed Aug 12 16:24:00 IDT 2015 | Tue Jul 14 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
1949 | TT_TASK | Rebar fixing for base slab | Wed Aug 12 16:24:00 IDT 2015 | Fri Aug 14 16:24:00 IDT 2015 | Wed Jul 15 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1950 | TT_TASK | Erect internal kicker formwork for base slab | Fri Aug 14 16:24:00 IDT 2015 | Mon Aug 17 16:24:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Wed Aug 12 18:00:00 IDT 2015 |  | COMPLETED
1951 | TT_TASK | Concreting for base slab (90m3) | Wed Sep 02 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 | Thu Aug 13 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 |  | COMPLETED
1952 | TT_TASK | Curing for base slab | Thu Sep 03 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Fri Aug 14 08:00:00 IDT 2015 | Thu Aug 20 18:00:00 IDT 2015 |  | COMPLETED
1953 | TT_TASK | Preparation of construction joint for base slab | Thu Sep 03 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Fri Aug 21 08:00:00 IDT 2015 | Fri Aug 21 18:00:00 IDT 2015 |  | COMPLETED
1954 | TT_TASK | Removal of formwork for base slab | Fri Sep 04 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Sat Aug 22 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 |  | COMPLETED
1955 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Sep 05 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 | Mon Aug 24 08:00:00 IDT 2015 | Mon Aug 24 18:00:00 IDT 2015 |  | COMPLETED
1956 | TT_TASK | Curing | Thu Sep 10 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Tue Aug 25 08:00:00 IDT 2015 | Tue Aug 25 18:00:00 IDT 2015 |  | COMPLETED
1957 | TT_TASK | Removal strut S3 | Sat Sep 19 08:00:00 IDT 2015 | Wed Sep 23 18:00:00 IDT 2015 | Wed Sep 16 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
1958 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Sep 24 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
1959 | TT_TASK | Rebar fixing for wall and roof | Wed Sep 30 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 | Fri Sep 25 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 |  | COMPLETED
1960 | TT_TASK | Erect external formwork for wall and roof | Thu Oct 15 08:00:00 IDT 2015 | Fri Oct 16 18:00:00 IDT 2015 | Mon Oct 05 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
1961 | TT_TASK | Concreting for wall and roof (260m3) | Sat Oct 17 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 | Wed Oct 07 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1962 | TT_TASK | Curing for wall and roof | Sun Oct 18 08:00:00 IDT 2015 | Tue Oct 27 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 |  | COMPLETED
1963 | TT_TASK | Preparation of construction joint for wall and roof | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
1964 | TT_TASK | Removal external and internal formwork for wall | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
1965 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 28 08:00:00 IST 2015 | Thu Oct 29 18:00:00 IST 2015 | Thu Oct 22 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1966 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Oct 30 08:00:00 IST 2015 | Wed Nov 04 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1968 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 02 18:00:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 |  | COMPLETED
1969 | TT_TASK | Erect external formwork for base slab | Fri Jul 03 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Tue Jul 21 08:00:00 IDT 2015 | Wed Jul 22 18:00:00 IDT 2015 |  | COMPLETED
1970 | TT_TASK | Rebar fixing for base slab | Mon Jul 06 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 23 08:00:00 IDT 2015 | Fri Jul 24 18:00:00 IDT 2015 |  | COMPLETED
1971 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jul 08 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Sat Jul 25 08:00:00 IDT 2015 | Mon Jul 27 18:00:00 IDT 2015 |  | COMPLETED
1972 | TT_TASK | Concreting for base slab (123m3) | Fri Jul 10 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jul 28 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 |  | COMPLETED
1973 | TT_TASK | Curing for base slab | Sat Jul 11 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1974 | TT_TASK | Preparation of construction joint for base slab | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 |  | COMPLETED
1975 | TT_TASK | Removal of formwork for base slab | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 |  | COMPLETED
1976 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1977 | TT_TASK | Curing | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 |  | COMPLETED
1978 | TT_TASK | Removal strut S3 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1979 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 |  | COMPLETED
1980 | TT_TASK | Rebar fixing for wall and roof | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 |  | COMPLETED
1981 | TT_TASK | Erect external formwork for wall and roof | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 |  | COMPLETED
1982 | TT_TASK | Concreting for wall and roof (260m3) | Fri Oct 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 | Sat Oct 24 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
1983 | TT_TASK | Curing for wall and roof | Sat Oct 03 08:00:00 IDT 2015 | Mon Oct 12 18:00:00 IDT 2015 | Mon Oct 26 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1984 | TT_TASK | Preparation of construction joint for wall and roof | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
1985 | TT_TASK | Removal external and internal formwork for wall | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1986 | TT_TASK | Removal internal falsework and formwork for roof | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1987 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1989 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
1990 | TT_TASK | Erect external formwork for base slab | Mon Jun 15 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1991 | TT_TASK | Rebar fixing for base slab | Wed Jun 17 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
1992 | TT_TASK | Erect internal kicker formwork for base slab | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
1993 | TT_TASK | Concreting for base slab (127m3) | Tue Jun 23 08:00:00 IDT 2015 | Tue Jun 23 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
1994 | TT_TASK | Curing for base slab | Wed Jun 24 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
1995 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 24 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1996 | TT_TASK | Removal of formwork for base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
1997 | TT_TASK | Infill concrete in between D-wall and base slab | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1998 | TT_TASK | Curing | Thu May 28 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1999 | TT_TASK | Removal strut S3 | Fri May 29 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2000 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 03 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2001 | TT_TASK | Rebar fixing for wall and roof | Mon Jun 08 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2002 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2003 | TT_TASK | Concreting for wall and roof (260m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2004 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2005 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2006 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2007 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2008 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 11 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2010 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
2011 | TT_TASK | Erect external formwork for base slab | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
2012 | TT_TASK | Rebar fixing for base slab | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
2013 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
2014 | TT_TASK | Concreting for base slab (127m3) | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
2015 | TT_TASK | Curing for base slab | Thu Jun 11 08:00:00 IDT 2015 | Wed Jun 17 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2016 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 11 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
2017 | TT_TASK | Removal of formwork for base slab | Sat May 23 08:00:00 IDT 2015 | Sat May 23 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
2018 | TT_TASK | Infill concrete in between D-wall and base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
2019 | TT_TASK | Curing | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2020 | TT_TASK | Removal strut S3 | Thu May 28 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2021 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2022 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2023 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2024 | TT_TASK | Concreting for wall and roof (150m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2025 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2026 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2027 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2028 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2029 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jul 06 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
2031 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2032 | TT_TASK | Erect external formwork for base slab | Thu May 21 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2033 | TT_TASK | Rebar fixing for base slab | Sat May 23 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2034 | TT_TASK | Erect internal kicker formwork for base slab | Wed May 27 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2035 | TT_TASK | Concreting for base slab (70m3) | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2036 | TT_TASK | Curing for base slab | Sat May 30 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2037 | TT_TASK | Preparation of construction joint for base slab | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2038 | TT_TASK | Removal of formwork for base slab | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2039 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2040 | TT_TASK | Curing | Sat Jun 06 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2041 | TT_TASK | Removal strut S3 | Mon Jun 08 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat May 23 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2043 | TT_TASK | Rebar fixing for wall and roof | Fri May 29 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2044 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2045 | TT_TASK | Concreting for wall and roof (175m3) | Thu Jun 04 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2046 | TT_TASK | Curing for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sun Jun 14 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2047 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2048 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 03 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 04 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2050 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 29 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
2052 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2053 | TT_TASK | Erect external formwork for base slab | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2054 | TT_TASK | Rebar fixing for base slab | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2055 | TT_TASK | Erect internal kicker formwork for base slab | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2056 | TT_TASK | Concreting for base slab (70m3) | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2057 | TT_TASK | Curing for base slab | Wed Apr 22 08:00:00 IDT 2015 | Tue Apr 28 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2058 | TT_TASK | Preparation of construction joint for base slab | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2059 | TT_TASK | Removal of formwork for base slab | Thu Apr 23 08:00:00 IDT 2015 | Thu Apr 23 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2060 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Apr 24 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2061 | TT_TASK | Curing | Wed Apr 29 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2062 | TT_TASK | Removal strut S3 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2063 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed May 06 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2064 | TT_TASK | Rebar fixing for wall and roof | Thu May 14 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2065 | TT_TASK | Erect external formwork for wall and roof | Mon May 18 08:00:00 IDT 2015 | Tue May 19 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2066 | TT_TASK | Concreting for wall and roof (175m3) | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2067 | TT_TASK | Curing for wall and roof | Thu May 21 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2068 | TT_TASK | Preparation of construction joint for wall and roof | Thu May 21 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2069 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2070 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2071 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jun 23 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
2073 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Fri Nov 15 18:00:00 IST 2013 |  | COMPLETED
2074 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Nov 16 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2075 | TT_TASK | Rebar fixing for base slab | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
2076 | TT_TASK | Erect internal kicker formwork for base slab | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
2077 | TT_TASK | Concreting for base slab (70m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
2078 | TT_TASK | Curing for base slab | Fri Dec 20 08:00:00 IST 2013 | Thu Dec 26 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
2079 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 |  | COMPLETED
2080 | TT_TASK | Removal of formwork for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
2081 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
2082 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2083 | TT_TASK | Removal strut S3 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2084 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Apr 16 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2085 | TT_TASK | Rebar fixing for wall and roof | Thu Apr 24 08:00:00 IDT 2014 | Sat Apr 26 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 |  | COMPLETED
2086 | TT_TASK | Erect external formwork for wall and roof | Mon Apr 28 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Thu Apr 10 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2087 | TT_TASK | Concreting for wall and roof (170m3) | Wed Apr 30 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Sat Apr 12 08:00:00 IDT 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
2088 | TT_TASK | Curing for wall and roof | Thu May 01 08:00:00 IDT 2014 | Sat May 10 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Tue Apr 22 18:00:00 IDT 2014 |  | COMPLETED
2089 | TT_TASK | Preparation of construction joint for wall and roof | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 |  | COMPLETED
2090 | TT_TASK | Removal external and internal formwork for wall | Sat May 03 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Tue Apr 15 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
2091 | TT_TASK | Removal internal falsework and formwork for roof | Mon May 12 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 |  | COMPLETED
2092 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jun 05 08:00:00 IDT 2014 | Tue Jun 10 18:00:00 IDT 2014 | Thu May 29 08:00:00 IDT 2014 | Thu Dec 04 18:00:00 IST 2014 |  | COMPLETED
2094 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2095 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2096 | TT_TASK | Rebar fixing for base slab | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2097 | TT_TASK | Erect internal kicker formwork for base slab | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2098 | TT_TASK | Concreting for base slab (70m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2099 | TT_TASK | Curing for base slab | Sun Dec 08 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2100 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2101 | TT_TASK | Removal of formwork for base slab | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
2102 | TT_TASK | Infill concrete in between D-wall and base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
2103 | TT_TASK | Curing | Sun Dec 15 08:00:00 IST 2013 | Sun Dec 15 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2104 | TT_TASK | Removal strut S3 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2105 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Feb 12 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2106 | TT_TASK | Rebar fixing for wall and roof | Mon Feb 17 08:00:00 IST 2014 | Wed Feb 19 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
2107 | TT_TASK | Erect external formwork for wall and roof | Fri Feb 28 13:48:00 IST 2014 | Mon Mar 03 13:48:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2108 | TT_TASK | Concreting for wall and roof (200m3) | Mon Mar 03 13:48:00 IST 2014 | Tue Mar 04 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2109 | TT_TASK | Curing for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Fri Mar 14 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2110 | TT_TASK | Preparation of construction joint for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Wed Mar 05 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2111 | TT_TASK | Removal external and internal formwork for wall | Wed Mar 05 13:48:00 IST 2014 | Thu Mar 06 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
2112 | TT_TASK | Removal internal falsework and formwork for roof | Fri Mar 14 13:48:00 IST 2014 | Mon Mar 17 13:48:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2113 | TT_TASK | Side walkway and cable bracket (204m3) | Thu May 29 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Wed Dec 03 18:00:00 IST 2014 |  | COMPLETED
2115 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2116 | TT_TASK | Erect external formwork for base slab | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2117 | TT_TASK | Rebar fixing for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2118 | TT_TASK | Erect internal kicker formwork for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2119 | TT_TASK | Concreting for base slab (70m3) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2120 | TT_TASK | Curing for base slab | Tue Dec 03 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2121 | TT_TASK | Preparation of construction joint for base slab | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
2122 | TT_TASK | Removal of formwork for base slab | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2123 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2124 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2125 | TT_TASK | Removal strut S3 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
2126 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jan 25 08:00:00 IST 2014 | Wed Jan 29 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
2127 | TT_TASK | Rebar fixing for wall and roof | Thu Jan 30 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Fri Dec 20 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
2128 | TT_TASK | Erect external formwork for wall and roof | Thu Feb 20 08:00:00 IST 2014 | Fri Feb 21 18:00:00 IST 2014 | Thu Jan 09 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2129 | TT_TASK | Concreting for wall and roof (200m3) | Sat Feb 22 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2130 | TT_TASK | Curing for wall and roof | Sun Feb 23 08:00:00 IST 2014 | Tue Mar 04 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2131 | TT_TASK | Preparation of construction joint for wall and roof | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Tue Jan 14 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2132 | TT_TASK | Removal external and internal formwork for wall | Tue Feb 25 08:00:00 IST 2014 | Tue Feb 25 18:00:00 IST 2014 | Wed Jan 15 08:00:00 IST 2014 | Wed Jan 15 18:00:00 IST 2014 |  | COMPLETED
2133 | TT_TASK | Removal internal falsework and formwork for roof | Wed Mar 05 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2134 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
2137 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Sep 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
2138 | TT_TASK | Erect external formwork for base slab | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Sep 21 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
2139 | TT_TASK | Rebar fixing for base slab | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
2140 | TT_TASK | Erect internal kicker formwork for base slab | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
2141 | TT_TASK | Staircase construction (+12.0mPD to +14.706mPD) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2142 | TT_TASK | Concreting for base slab (30m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
2143 | TT_TASK | Curing for base slab | Fri Dec 13 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
2144 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
2145 | TT_TASK | Removal of formwork for base slab | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 18:00:00 IDT 2013 |  | COMPLETED
2146 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2147 | TT_TASK | Mass concrete at level +12.0mPD | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 |  | COMPLETED
2148 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2149 | TT_TASK | Removal strut S3 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2150 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 17 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Mon Dec 01 18:00:00 IST 2014 |  | COMPLETED
2152 | TT_TASK | Erect working platform to +21.0mPD | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2153 | TT_TASK | Rebar fixing for wall and roof | Sat Jan 11 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2154 | TT_TASK | Staircase construction (+14.706mPD to +16.956mPD) (20m3) | Fri May 02 08:00:00 IDT 2014 | Wed May 07 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2155 | TT_TASK | Staircase construction (+16.956mPD to +19.206mPD) (20m3) | Thu Jun 05 08:00:00 IDT 2014 | Mon Jun 09 18:00:00 IDT 2014 | Thu Jun 12 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2156 | TT_TASK | Staircase construction (+19.206mPD to +21.456mPD) (20m3) | Tue Jun 10 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Fri Jun 20 18:00:00 IDT 2014 |  | COMPLETED
2157 | TT_TASK | Erect external formwork for wall and roof | Sat Mar 15 08:00:00 IST 2014 | Mon Mar 17 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2158 | TT_TASK | Concreting for wall and roof (31m3) | Tue Feb 04 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2159 | TT_TASK | Curing for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 |  | COMPLETED
2160 | TT_TASK | Preparation of construction joint for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2161 | TT_TASK | Removal external and internal formwork for wall | Thu Feb 06 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2162 | TT_TASK | Removal internal falsework and formwork for roof | Sat Feb 15 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Thu Jan 23 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2164 | TT_TASK | Removal strut S2 @ SN 19 | Wed Apr 02 08:00:00 IDT 2014 | Mon Apr 07 18:00:00 IDT 2014 | Mon Mar 03 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 |  | COMPLETED
2165 | TT_TASK | Erect working platform to +24.0mPD | Tue Apr 08 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 | Fri Mar 07 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 |  | COMPLETED
2166 | TT_TASK | Erect internal formwork below strut S1 | Sat Apr 12 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 | Wed Mar 12 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 |  | COMPLETED
2167 | TT_TASK | Staircase construction (+21.456mPD to +23.706mPD) (20m3) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 |  | COMPLETED
2168 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 | Fri Mar 14 08:00:00 IST 2014 | Tue Apr 01 18:00:00 IDT 2014 |  | COMPLETED
2169 | TT_TASK | Erect external wall & internal wall formwork | Tue May 13 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Wed Apr 02 08:00:00 IDT 2014 | Thu Apr 03 18:00:00 IDT 2014 |  | COMPLETED
2170 | TT_TASK | Concreting (External Wall & Internal Wall) (264m3) | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Fri Apr 04 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2171 | TT_TASK | Curing (External Wall & Internal Wall) | Fri May 16 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2172 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Mon May 19 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Thu Apr 10 18:00:00 IDT 2014 |  | COMPLETED
2173 | TT_TASK | Waterproofing | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 |  | COMPLETED
2174 | TT_TASK | Backfilling | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2176 | TT_TASK | Removal strut S1 @ SN 19 | Thu Jun 19 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2177 | TT_TASK | Erect working platform to +30.406mPD | Tue Jun 24 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2178 | TT_TASK | Erect internal formwork | Sat Jun 28 08:00:00 IDT 2014 | Sat Jun 28 18:00:00 IDT 2014 | Wed Jun 04 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2179 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Mon Jun 30 08:00:00 IDT 2014 | Wed Jul 02 18:00:00 IDT 2014 | Thu Jun 05 08:00:00 IDT 2014 | Fri Jun 06 18:00:00 IDT 2014 |  | COMPLETED
2180 | TT_TASK | Erect external formwork (External Wall & Internal Wall) | Thu Jul 03 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2181 | TT_TASK | Concreting (External Wall & Internal Wall) (128m3) | Fri Jul 04 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2182 | TT_TASK | Curing (External Wall & Internal Wall) | Sat Jul 05 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 18:00:00 IDT 2014 |  | COMPLETED
2183 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Tue Jul 08 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2184 | TT_TASK | Waterproofing | Wed Jul 09 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Thu Jun 19 18:00:00 IDT 2014 |  | COMPLETED
2185 | TT_TASK | Backfilling | Sat Jul 12 08:00:00 IDT 2014 | Wed Jul 16 18:00:00 IDT 2014 | Fri Jun 20 08:00:00 IDT 2014 | Tue Jun 24 18:00:00 IDT 2014 |  | COMPLETED
2186 | TT_TASK | Erect falsework and soffit formwork +30.206mPD | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 | Wed Jun 25 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2187 | TT_TASK | Staircase construction (+21.456mPD to +25.956mPD) (20m3) | Sat Jul 19 08:00:00 IDT 2014 | Wed Jul 23 18:00:00 IDT 2014 | Fri Jun 27 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2188 | TT_TASK | Staircase construction (+25.956mPD to +27.606mPD) (20m3) | Sat Jul 05 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 05 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 |  | COMPLETED
2189 | TT_TASK | Rebar fixing (Beam, Floor Slab and Staircase) | Thu Jul 10 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Thu Jul 10 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2190 | TT_TASK | Concreting (Beam, Floor Slab and Staircase) (31m3) | Fri Jul 11 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2191 | TT_TASK | Curing (Beam, Floor Slab and Staircase) | Wed Sep 03 08:00:00 IDT 2014 | Tue Sep 09 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2193 | TT_TASK | Erect working platform to +33.576mPD | Wed Sep 03 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
2194 | TT_TASK | Erect external formwork (External Wall) | Mon Sep 08 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 | Fri Sep 26 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2195 | TT_TASK | Rebar fixing (External Wall) | Thu Sep 11 08:00:00 IDT 2014 | Fri Sep 12 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2196 | TT_TASK | Erect internal formwork (External Wall) | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 |  | COMPLETED
2197 | TT_TASK | Concreting (External Wall) (49m3) | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 |  | COMPLETED
2198 | TT_TASK | Curing (External Wall) | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 |  | COMPLETED
2199 | TT_TASK | Removal formwork (External Wall) | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
2200 | TT_TASK | Erect falsework and soffit formwork +32.656 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2201 | TT_TASK | Rebar fixing (Beam & Floor Slab) | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 |  | COMPLETED
2202 | TT_TASK | Concreting (Beam & Floor Slab) (31m3) | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 |  | COMPLETED
2203 | TT_TASK | Curing (Beam & Floor Slab) | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2205 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
2206 | TT_TASK | Rebar fixing (Roof Parapet Wall) | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 |  | COMPLETED
2207 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2208 | TT_TASK | Concreting (Roof Parapet Wall) (30m3) | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
2209 | TT_TASK | Curing (Roof Parapet Wall) | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 |  | COMPLETED
2210 | TT_TASK | Removal formwork (Roof Parapet Wall) | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2211 | TT_TASK | Removal of falsework and soffit formwork | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
2213 | TT_TASK | Wet trade work | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 |  | COMPLETED
2214 | TT_TASK | Metal works (Louver, Door, Cat-ladder, Architectural Fins, Handrail, Roof Sliding Hatch and Balustrade, etc) | Thu Nov 27 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Thu Nov 27 08:00:00 IST 2014 | Thu Mar 05 18:00:00 IST 2015 |  | COMPLETED
2215 | TT_TASK | Coat works | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2218 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Nov 29 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Feb 04 18:00:00 IST 2014 |  | COMPLETED
2219 | TT_TASK | Backfilling between D-wall and 0.5m below S1 14,240m3 soil | Thu Feb 06 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 | Wed Feb 05 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 |  | COMPLETED
2220 | TT_TASK | Removal of S1 | Wed Mar 12 08:00:00 IST 2014 | Tue Mar 25 18:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 |  | COMPLETED
2221 | TT_TASK | Backfilling to original ground level 21,390m3 (approx. +25.0mPD) | Sat Mar 01 08:00:00 IST 2014 | Wed Mar 19 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Sat May 03 18:00:00 IDT 2014 |  | COMPLETED
2223 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 |  | COMPLETED
2224 | TT_TASK | Backfilling between D-wall and 0.5m below S1 (2075m3) | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 |  | COMPLETED
2225 | TT_TASK | Removal of S1 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 |  | COMPLETED
2226 | TT_TASK | Backfilling to original ground level 3,900m3 (approx. +25.0mPD) (1353m3) | Sat Mar 01 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
2227 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
2228 | TT_TASK | Backfilling backfilling to +20mPD from SN8 to SN9 (Soil: 7,050m3 @ 500m3/day) | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 |  | COMPLETED
2229 | TT_TASK | Removal of S1 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
2230 | TT_TASK | Construction of mud pit | Sat Jul 06 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
2231 | TT_TASK | Backfilling from +20mPD to ground level from SN8 to SN9 (Soil: 5,000m3 @ 500m3/day) | Tue Aug 06 08:00:00 IDT 2013 | Sat Aug 17 18:00:00 IDT 2013 | Tue Jul 02 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 |  | COMPLETED
2233 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Aug 07 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2234 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) | Fri Aug 14 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2235 | TT_TASK | Placing mass concrete infill between tunnel and D-wall | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 02 18:00:00 IST 2015 | Thu Dec 24 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2236 | TT_TASK | Removal of S2 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 10 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 04 18:00:00 IST 2016 |  | COMPLETED
2237 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2238 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
2239 | TT_TASK | Removal strut S1 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2240 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
2241 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488 m3 of soil) | Mon Jan 25 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Fri Apr 01 18:00:00 IDT 2016 |  | COMPLETED
2243 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) (SN18-19) | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 |  | COMPLETED
2244 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) (SN18-19) | Sat Apr 26 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Sat Apr 26 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
2245 | TT_TASK | Placing mass concrete infill between tunnel and D-wall (SN18-19) | Tue May 20 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri May 16 18:00:00 IDT 2014 |  | COMPLETED
2246 | TT_TASK | Removal of S2 (SN16-18) | Wed Jun 04 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 |  | COMPLETED
2247 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) (SN16-18) | Mon Jun 09 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Tue May 27 18:00:00 IDT 2014 |  | COMPLETED
2248 | TT_TASK | Removal strut S1 (SN16-18) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Wed May 28 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
2249 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488m3 of soil) | Fri Jun 27 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
2251 | TT_TASK | Dismantling temporary bridge deck | Mon Jun 15 08:00:00 IDT 2015 | Tue Jul 21 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2252 | TT_TASK | Reinstatement of Works Area 4.10 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jan 11 18:00:00 IST 2017 | Mon May 02 08:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 |  | COMPLETED
2253 | TT_TASK | Complete all tree planting and reinstate Works Area 4.12C | Tue Nov 01 08:00:00 IST 2016 | Thu Jul 13 18:00:00 IDT 2017 | Sat Oct 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2254 | TT_TASK | Reinstate Works Areas 4.9, 4.9A and 4.12A prior to handover | Mon May 22 08:00:00 IDT 2017 | Sat Sep 02 18:00:00 IDT 2017 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2258 | TT_TASK | Application of power supply, environmental permits and construction substation | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2259 | TT_TASK | Procurement and Confirmation of the order of 2nd tunnel boring machine | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2260 | TT_TASK | TBM design and submission for approval | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2261 | TT_TASK | TBM materials order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
2262 | TT_TASK | TBM equipments order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 |  | COMPLETED
2263 | TT_TASK | TBM Fabrication | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
2264 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 |  | COMPLETED
2265 | TT_TASK | TBM test Run | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2266 | TT_TASK | TBM disassembly and packing for shipping to HK | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 |  | COMPLETED
2267 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
2268 | TT_TASK | Setup TBM facilities | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
2269 | TT_TASK | Fabrication 50% of South Tunnel South Bound Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
2270 | TT_TASK | Fabrication 100% of South Tunnel South Bound Precast Lining | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
2271 | TT_TASK | Fabrication 50% of South Tunnel North Bound Precast Lining | Wed Oct 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 | Wed Oct 03 08:00:00 IST 2012 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
2272 | TT_TASK | Fabrication 100% of South Tunnel North Bound Precast Lining | Mon Aug 26 08:00:00 IDT 2013 | Wed Jan 22 18:00:00 IST 2014 | Wed Feb 27 08:00:00 IST 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
2274 | TT_TASK | Ground treatment at lauching shaft Southbound | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
2275 | TT_TASK | TBM assemble, thrust frame, testing and commissioning | Sat Jun 01 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2276 | TT_TASK | Lowing back-up plant for final drive | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
2277 | TT_TASK | Assemble and set up back-up plant for final drive | Sat Jun 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2278 | TT_TASK | Erection of noise enclosure | Sat Jul 20 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 |  | COMPLETED
2279 | TT_TASK | TBM drive & lining installation CH124+912 to CH125+012 (Initial Drive) | Sat Jul 20 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Mon Mar 11 00:00:00 IST 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
2280 | TT_TASK | TBM drive & lining installation CH125+012 to CH125+338 | Tue Oct 15 08:00:00 IDT 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon May 27 08:00:00 IDT 2013 | Tue May 20 00:00:00 IDT 2014 |  | COMPLETED
2281 | TT_TASK | Dis-assemble TBM | Fri May 23 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 |  | COMPLETED
2282 | TT_TASK | Invert slab and side walkway | Fri Aug 01 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Tue Sep 02 18:00:00 IDT 2014 |  | COMPLETED
2283 | TT_TASK | Installation of cable bracket | Mon Nov 03 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 | Mon Aug 18 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2285 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Sep 01 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 | Sat Aug 09 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2286 | TT_TASK | Ground treatment at lauching shaft Northbound | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 19 18:00:00 IST 2013 | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
2287 | TT_TASK | TBM assemble, testing and commissioning | Wed Jul 02 08:00:00 IDT 2014 | Wed Sep 03 18:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2288 | TT_TASK | Setup back-up plant for final drive | Tue Jun 03 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2289 | TT_TASK | Reinstate of noise enclosure | Fri Oct 10 08:00:00 IDT 2014 | Wed Nov 05 18:00:00 IST 2014 | Tue Oct 28 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
2290 | TT_TASK | TBM drive & lining installation CH124+927 to CH125+027 (Initial Drive) | Fri Oct 10 08:00:00 IDT 2014 | Thu Nov 13 18:00:00 IST 2014 | Thu Oct 30 00:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
2291 | TT_TASK | TBM drive & lining installation CH125+027 to CH125+353 (Final Drive) | Fri Jan 02 08:00:00 IST 2015 | Thu Feb 12 18:00:00 IST 2015 | Mon Dec 08 08:00:00 IST 2014 | Fri Aug 07 00:00:00 IDT 2015 |  | COMPLETED
2292 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Tue Aug 04 08:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
2293 | TT_TASK | Dis-assemble TBM | Tue Aug 04 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
2294 | TT_TASK | Invert slab and side walkway | Wed Sep 09 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
2295 | TT_TASK | Installation of cable bracket | Thu Sep 24 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Aug 31 18:00:00 IDT 2015 |  | COMPLETED
2298 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Partial length) at down track | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 |  | COMPLETED
2299 | TT_TASK | Probe/Grout | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 | Mon Aug 11 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2300 | TT_TASK | Coring of Segment | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 |  | COMPLETED
2301 | TT_TASK | Removal of segment | Tue Sep 02 08:00:00 IDT 2014 | Thu Sep 04 18:00:00 IDT 2014 | Thu Aug 21 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2302 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Sep 05 08:00:00 IDT 2014 | Tue Oct 07 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2303 | TT_TASK | Invert Concrete | Thu Oct 23 08:00:00 IDT 2014 | Sat Nov 01 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2304 | TT_TASK | Wall and Roof concrete | Mon Nov 03 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Mon Oct 13 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
2305 | TT_TASK | Dismantle Temporary frame | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2306 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
2307 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Remaining length ) at down track | Sat May 09 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Thu Apr 16 18:00:00 IDT 2015 |  | COMPLETED
2308 | TT_TASK | Probe/Grout | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
2309 | TT_TASK | Coring of Segment | Fri Oct 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 | Fri Oct 16 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
2310 | TT_TASK | Removal of segment | Wed Oct 07 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
2311 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Oct 10 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Oct 26 08:00:00 IST 2015 | Fri Dec 11 18:00:00 IST 2015 |  | COMPLETED
2312 | TT_TASK | Invert Concrete | Thu Dec 03 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Sat Dec 12 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2313 | TT_TASK | Wall and Roof concrete | Mon Dec 14 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 15 18:00:00 IST 2016 |  | COMPLETED
2314 | TT_TASK | Dismantle Temporary frame | Wed Jan 13 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 |  | COMPLETED
2315 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2318 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 |  | COMPLETED
2319 | TT_TASK | Pre-drill and guide wall | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 |  | COMPLETED
2320 | TT_TASK | D-wall design review | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 |  | COMPLETED
2321 | TT_TASK | D-Wall Construction (1075m3) | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 |  | COMPLETED
2322 | TT_TASK | Shear pin, toe grout and pumping test | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 |  | COMPLETED
2324 | TT_TASK | SI for TBM ground treatment | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2325 | TT_TASK | Design review of TBM ground treatment | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2326 | TT_TASK | Ground treatment for TBM southbound | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
2327 | TT_TASK | Ground treatment for TBM northbound | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2329 | TT_TASK | Capping beam construction | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2330 | TT_TASK | L-Shape wall construction | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
2331 | TT_TASK | Excavate up to +28.5mPD (1488m3) | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 |  | COMPLETED
2332 | TT_TASK | Install Strut S1 +29.0mPD | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 |  | COMPLETED
2333 | TT_TASK | Excavate up to +23.5mPD (2480m3) | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 |  | COMPLETED
2334 | TT_TASK | Install Strut S2 +24.0mPD | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 |  | COMPLETED
2335 | TT_TASK | Excavate up to +19.5mPD (1984m3) | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
2336 | TT_TASK | Install Strut S3 +20.0mPD | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 |  | COMPLETED
2337 | TT_TASK | Excavate up to +15.5mPD (1984m3) | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
2338 | TT_TASK | Install Strut S4 +16.0mPD | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 |  | COMPLETED
2339 | TT_TASK | Excavate up to formation (4117m3) | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
2340 | TT_TASK | Install rock dowel and tie back | Sat Jun 02 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Sat Jun 02 08:00:00 IDT 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2341 | TT_TASK | Temporary handover the shaft to contract 822 | Mon Jun 03 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2343 | TT_TASK | Rock breaking works | Mon Aug 26 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
2344 | TT_TASK | Temporary base Slab for TBM Drive | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
2347 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2348 | TT_TASK | Erect external formwork (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Wed Aug 13 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Tue Aug 19 18:00:00 IDT 2014 |  | COMPLETED
2349 | TT_TASK | Rebar fixing (Base Slab) | Thu Aug 14 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Wed Aug 20 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2350 | TT_TASK | Erect internal kicker formwork (Base Slab) | Tue Aug 19 08:00:00 IDT 2014 | Thu Aug 21 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 |  | COMPLETED
2351 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 22 08:00:00 IDT 2014 | Fri Aug 22 18:00:00 IDT 2014 | Thu Aug 28 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2352 | TT_TASK | Concreting (Base Slab) (245m3) | Sat Aug 23 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014 | Fri Aug 29 18:00:00 IDT 2014 |  | COMPLETED
2353 | TT_TASK | Curing (Base Slab) | Mon Aug 25 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2354 | TT_TASK | Removal of formwork (Base Slab) | Mon Sep 08 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Mon Sep 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2355 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Sep 10 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Tue Sep 02 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 |  | COMPLETED
2356 | TT_TASK | Rebar fixing (Wall and roof) | Thu Sep 18 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Thu Sep 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2357 | TT_TASK | Erect external formwork (Wall) | Thu Sep 25 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2358 | TT_TASK | Clearing and inspection (Wall and roof) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2359 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
2360 | TT_TASK | Curing (Wall and roof) | Sat Oct 11 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
2361 | TT_TASK | Removal formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Thu Oct 16 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Sat Nov 01 18:00:00 IST 2014 |  | COMPLETED
2362 | TT_TASK | Removal formwork (Roof) | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2363 | TT_TASK | Side walkway and cable bracket (72m3) | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
2365 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Nov 07 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Sat Nov 07 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
2366 | TT_TASK | Erect external formwork (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Wed Nov 18 18:00:00 IST 2015 |  | COMPLETED
2367 | TT_TASK | Rebar fixing (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Tue Nov 17 18:00:00 IST 2015 | Thu Nov 19 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 |  | COMPLETED
2368 | TT_TASK | Erect internal kicker formwork (Base Slab) | Wed Nov 18 08:00:00 IST 2015 | Fri Nov 20 18:00:00 IST 2015 | Tue Nov 24 08:00:00 IST 2015 | Thu Nov 26 18:00:00 IST 2015 |  | COMPLETED
2369 | TT_TASK | Clearing and inspection (Base Slab) | Sat Nov 21 08:00:00 IST 2015 | Sat Nov 21 18:00:00 IST 2015 | Fri Nov 27 08:00:00 IST 2015 | Fri Nov 27 18:00:00 IST 2015 |  | COMPLETED
2370 | TT_TASK | Concreting (Base Slab) (245m3) | Mon Nov 23 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Nov 28 08:00:00 IST 2015 | Sat Nov 28 18:00:00 IST 2015 |  | COMPLETED
2371 | TT_TASK | Curing (Base Slab) | Tue Nov 24 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Mon Nov 30 08:00:00 IST 2015 | Thu Dec 03 18:00:00 IST 2015 |  | COMPLETED
2372 | TT_TASK | Removal of formwork (Base Slab) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Fri Dec 04 08:00:00 IST 2015 | Sat Dec 05 18:00:00 IST 2015 |  | COMPLETED
2373 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 09 18:00:00 IST 2015 | Mon Dec 07 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
2374 | TT_TASK | Rebar fixing (Wall and roof) | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2375 | TT_TASK | Erect external formwork (Wall) | Mon Jan 11 08:00:00 IST 2016 | Wed Jan 13 18:00:00 IST 2016 | Thu Jan 07 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2376 | TT_TASK | Clearing and inspection (Wall and roof) | Thu Jan 14 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2377 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Jan 15 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2378 | TT_TASK | Curing (Wall and roof) | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 |  | COMPLETED
2379 | TT_TASK | Removal formwork (Wall) | Tue Jan 19 08:00:00 IST 2016 | Thu Jan 21 18:00:00 IST 2016 | Thu Jan 28 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2380 | TT_TASK | Removal formwork and falsework (Roof) | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Sat Jan 30 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2381 | TT_TASK | Side walkway and cable bracket (72m3) | Wed Jan 06 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Thu Nov 12 08:00:00 IST 2015 | Tue Mar 01 18:00:00 IST 2016 |  | COMPLETED
2382 | TT_TASK | Provision access opening to DC | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2383 | TT_TASK | Erect falsework and soffit formwork (Opening) | Thu Mar 10 08:00:00 IST 2016 | Mon Mar 21 18:00:00 IST 2016 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2384 | TT_TASK | Rebar fixing (Roof) | Tue Mar 22 08:00:00 IST 2016 | Tue Mar 22 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2385 | TT_TASK | Clearing and inspection (Roof) | Wed Mar 23 08:00:00 IST 2016 | Wed Mar 23 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2386 | TT_TASK | Concreting (Roof) (225m3) | Thu Mar 24 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2387 | TT_TASK | Curing (Roof) | Tue Mar 29 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Jan 13 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
2388 | TT_TASK | Removal internal falsework and soffit formwork (Roof) | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
2390 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Thu Mar 17 08:00:00 IST 2016 | Fri Mar 18 18:00:00 IST 2016 | Tue Mar 01 08:00:00 IST 2016 | Wed Mar 02 18:00:00 IST 2016 |  | COMPLETED
2391 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Sat Mar 19 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Thu Mar 03 08:00:00 IST 2016 | Tue Mar 08 18:00:00 IST 2016 |  | COMPLETED
2392 | TT_TASK | Backfilling to +18.25mPD (1229 m3 of soil) | Sat Jul 02 08:00:00 IDT 2016 | Mon Jul 11 18:00:00 IDT 2016 | Mon Jul 25 08:00:00 IDT 2016 | Tue Aug 02 18:00:00 IDT 2016 |  | COMPLETED
2393 | TT_TASK | Laying 500mm mass concrete lateral support | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 |  | COMPLETED
2394 | TT_TASK | Backfilling to 0.5m below S3 (+19.5mPD) (372m3 of soil) | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 |  | COMPLETED
2395 | TT_TASK | Removal strut S3 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 |  | COMPLETED
2396 | TT_TASK | Backfilling to 0.5m below S2 (+23.5mPD) (1984m3 of soil) | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 |  | COMPLETED
2397 | TT_TASK | Removal strut S2 | Wed Aug 24 08:00:00 IDT 2016 | Fri Aug 26 18:00:00 IDT 2016 | Wed Aug 24 08:00:00 IDT 2016 | Thu Sep 01 18:00:00 IDT 2016 |  | COMPLETED
2398 | TT_TASK | Backfilling to 0.5m below S1 (+28.5mPD) (2480m3 of soil) | Mon Sep 05 08:00:00 IDT 2016 | Tue Sep 20 18:00:00 IDT 2016 | Fri Sep 02 08:00:00 IDT 2016 | Fri Sep 09 18:00:00 IDT 2016 |  | COMPLETED
2399 | TT_TASK | Removal strut S1 | Wed Sep 21 08:00:00 IDT 2016 | Thu Sep 22 18:00:00 IDT 2016 | Sat Sep 10 08:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 |  | COMPLETED
2400 | TT_TASK | Backfilling to original ground level (approx. +31.5mPD) (1488m3 of soil) | Fri Sep 23 08:00:00 IDT 2016 | Mon Oct 03 18:00:00 IDT 2016 | Thu Sep 15 08:00:00 IDT 2016 | Mon Sep 19 18:00:00 IDT 2016 |  | COMPLETED
2402 | TT_TASK | Reinstatement of TUT area (Including Hydroseeding) | Mon Oct 03 08:00:00 IDT 2016 | Mon Jun 19 18:00:00 IDT 2017 | Fri Oct 07 08:00:00 IDT 2016 |  | 216.0 | IN_PROGRESS
25 | TT_TASK | Access opening for the up track cut and cover tunnel at Tse Uk Tsuen Shaft | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 10 18:00:00 IST 2016 |  | COMPLETED
27 | TT_TASK | Close out the temporary access opening at Tse Uk Tsuen Shaft | Thu Mar 10 08:00:00 IST 2016 | Tue Apr 05 18:00:00 IDT 2016 | Thu Feb 11 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
307 | TT_TASK | Position crane for TBM retrieval (down track) | Wed Jul 02 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014 | Sat Aug 02 18:00:00 IDT 2014 |  | COMPLETED
308 | TT_TASK | TBM Break-in and Retrieval (down track) | Mon Aug 04 08:00:00 IDT 2014 | Sat Aug 30 18:00:00 IDT 2014 | Mon Aug 04 08:00:00 IDT 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
309 | TT_TASK | Position crane for TBM retrieval (up track) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 |  | COMPLETED
310 | TT_TASK | TBM Break-in and Retrieval (up track) | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
376 | TT_TASK | Supply Engineer with Survey Equipment [PS41.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
377 | TT_TASK | Provide Engineer with suitably qualified full time Survey Assistant - 4 nos. [PS41.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
378 | TT_TASK | Provide Engineer with site transportation as detailed in PS42.1 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 |  | COMPLETED
379 | TT_TASK | Submit details of qualified drivers to be assigned to the Engineer, for review [PS42.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 |  | COMPLETED
380 | TT_TASK | Install, service and maintain 10 container offices for use by the Engineer's Site Staff | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
381 | TT_TASK | Provide services and equipment for the Engineer | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
383 | TT_TASK | Master Programme - Prepare and submit for approval [GS4.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
384 | TT_TASK | Master Programme - Comments , Resubmission and Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
385 | TT_TASK | Time Chainage Programme - Prepare and submit for approval [GS4.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
386 | TT_TASK | Time Chainage Programme - Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
387 | TT_TASK | Implement and Maintain Programme Management System for 1st Audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
388 | TT_TASK | Implement and Maintain Programme Management System for 2nd Audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
389 | TT_TASK | Implement and Maintain Programme Management System for 3rd Audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
391 | TT_TASK | Environmental Management Plan - Prepare and submit for approval [GS5.1.10] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
392 | TT_TASK | Environmental Management Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
393 | TT_TASK | Quality Plan - Prepare and submit for approval [GS9.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
394 | TT_TASK | Quality Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
395 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 1st audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 |  | COMPLETED
396 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 2nd audit | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
397 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 3rd audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
398 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 4th audit | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
399 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 5th audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
400 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 6th audit | Tue Jul 02 08:00:00 IDT 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
401 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 7th audit | Thu Nov 28 08:00:00 IST 2013 | Thu Jun 05 18:00:00 IDT 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Jan 24 18:00:00 IST 2014 |  | COMPLETED
402 | TT_TASK | Health and Safety Plan - Prepare and submit [G3.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
403 | TT_TASK | System Assurance Plan - Prepare and submit for approval [PS Appendix P3.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
404 | TT_TASK | System Assurance Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
405 | TT_TASK | Design for Safety & Constructability Plan - Prepare and submit for approval [PS37.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
406 | TT_TASK | Design for Safety & Constructability Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
408 | TT_TASK | Methods of Construction - Prepare and submit for approval [GS12.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
409 | TT_TASK | Methods of Construction - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
410 | TT_TASK | Contractor's Submission Schedule - Prepare and submit for approval [GS12.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
411 | TT_TASK | Contractor's Submission Schedule - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
412 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) [PS13.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
413 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) - Approval period | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 |  | COMPLETED
414 | TT_TASK | Spoil Disposal Plan [PS17.7.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
415 | TT_TASK | Waste Management Plan [PS22.10.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
416 | TT_TASK | Independent Checking Engineer - Appoint and submit for approval [PS7.1.8] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
417 | TT_TASK | Independent Checking Engineer - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
418 | TT_TASK | Sub-contract Management Plan - Prepare and submit [PS34.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 |  | COMPLETED
419 | TT_TASK | Schedule of Utilities Services Arrangement [GS7.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
420 | TT_TASK | Site Safety Supervision Plan for Site Formation - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
421 | TT_TASK | Site Safety Supervision Plan for Site Formation - Approval period | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
422 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Prepare and Submit | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
423 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
424 | TT_TASK | Site Safety Supervision Plan for ELS - Prepare and Submit | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
425 | TT_TASK | Site Safety Supervision Plan for ELS - Approval Period | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
426 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Prepare and Submit | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
427 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Approval Period | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
428 | TT_TASK | Noise Management Plan [P22.3.9] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
429 | TT_TASK | Air Quality Management Plan [P22.4.3] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
430 | TT_TASK | Detailed Proposal for Water Pollution Control Measures and Proposed Monitoring [PS22.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
431 | TT_TASK | Groundwater Monitoring and Response Plan [PS22.5.2] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
432 | TT_TASK | Vibration Monitoring Plan [PS22.8.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 |  | COMPLETED
433 | TT_TASK | Proposed Outline TTM Scheme - Prepare & submit to the: Engineer for Review / SLG for Approval [PS19.3] | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 |  | COMPLETED
434 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Proposed TTM Scheme [PS19.4] | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 |  | COMPLETED
435 | TT_TASK | Resubmission of Proposed Outline TTM Scheme (if required) | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
436 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Resubmitted Proposed Outline TTM Scheme [PS19.4] | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 |  | COMPLETED
437 | TT_TASK | Notification Period of the Approved TTM Scheme prior to implementation [PS19.4] | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 |  | COMPLETED
440 | TT_TASK | Initial Site Survey (WA3.11) | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 |  | COMPLETED
441 | TT_TASK | Initial Site Survey Report (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 |  | COMPLETED
442 | TT_TASK | Initial Site Survey & Condition Survey (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
443 | TT_TASK | Initial Site Survey Report (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
444 | TT_TASK | Initial Site Survey & Condition Survey (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
445 | TT_TASK | Initial Site Survey Report (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
446 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 4.9 & 4.12A [PS4.2] | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
447 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 5.1 & 5.3 [PS4.2.3] | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 |  | COMPLETED
448 | TT_TASK | Proposal for Site Clearance Works [PS4.4.1] | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 |  | COMPLETED
449 | TT_TASK | Site Clearance / Site Formation Works (including demolition of EBS) | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
450 | TT_TASK | Backfill existing stream courses in Works Area 4.9, 4.10 and 4.11 [PS18.5.1] | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
451 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and submit to EPD for Approval (WA3.3 - Area M, I, L) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
452 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA3.3 - Area M, I, L) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
453 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
454 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
455 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.3 - Area M, I, L) | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
456 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA3.3 - Area M, I, L) | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
457 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA3.3 - Area M, I, L) | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
458 | TT_TASK | Remediation Report - Approval (WA3.3 - Area M, I, L) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
459 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and Submit to EPD for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
460 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
461 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
462 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.1, 3.2, 3.3, 3.3A) | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
463 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.1, 3.2, 3.3, 3.3A) | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 |  | COMPLETED
464 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 |  | COMPLETED
465 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
466 | TT_TASK | Remediation Report - Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
467 | TT_TASK | Conduct remediation for Area Q in accordance with method proposed in the approved Remediation Action Plan [PS22.9.2] | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 |  | COMPLETED
468 | TT_TASK | Remediation Report - Prepare and submit for Approval [PS22.9.2] (Area Q) | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 |  | COMPLETED
469 | TT_TASK | Remediation Report - Approval (Area Q) | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
470 | TT_TASK | Removal of contaminated soil at North Tunnels (Area N,O,P,Q,R,S) | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
471 | TT_TASK | Condition Survey EBS for presence of Asbestos and gather samples | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
472 | TT_TASK | Testing of gathered samples | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 |  | COMPLETED
473 | TT_TASK | Prepare and submit Asbestos Investigation Report (AIR) & Asbestos Abatement Plan (AAP) | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
474 | TT_TASK | Approval period of AIR & AAP | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
475 | TT_TASK | Notification period to Engineer and EPD prior to Asbestos abatement works | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
476 | TT_TASK | Asbestos abatement works | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
477 | TT_TASK | Demolition of EBS | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
478 | TT_TASK | Confirmation of tree survey | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 |  | COMPLETED
480 | TT_TASK | Installation of ground settlement markers | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 |  | COMPLETED
481 | TT_TASK | Settlement monitoring and submit report | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
482 | TT_TASK | Settlement monitoring and submit report | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 |  | COMPLETED
483 | TT_TASK | Settlement monitoring and submit report | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
484 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
485 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Wed Feb 26 18:00:00 IST 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Feb 21 18:00:00 IST 2014 |  | COMPLETED
486 | TT_TASK | Settlement monitoring and submit report | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 |  | COMPLETED
488 | TT_TASK | Permit Applications (incl. License to Search and Excavate Antiquities and Excavation Permit) | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 |  | COMPLETED
489 | TT_TASK | Check for underground utilities | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 |  | COMPLETED
490 | TT_TASK | Field walking and hand augering | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 |  | COMPLETED
491 | TT_TASK | Excavation of trial pits | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 |  | COMPLETED
492 | TT_TASK | Rescue excavation rescue works (if required) | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 |  | COMPLETED
494 | TT_TASK | Erection of Hoarding with Gate (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 |  | COMPLETED
495 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 3.1, 3.2, 3.3 and 3.3A [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
496 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 4.9, 4.10, 4.11, 4.12A~C, and 4.15 [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
497 | TT_TASK | Project Signboard Erection [PS4.6.8] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
498 | TT_TASK | Marine Survey at Barging Point [PS4.3] (before construction of barging facilities) | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 00:00:00 IST 2010 |  | COMPLETED
499 | TT_TASK | Construct barging facilities | Sat Oct 02 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Oct 02 00:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
500 | TT_TASK | Operation Plan for the Barging Facility - Prepare and Submit for Approval [PS17.1.9] | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
501 | TT_TASK | Operation Plan for the Barging Facility - Review and Approval Period | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 |  | COMPLETED
503 | TT_TASK | General and Special Attendance for Designated Contractors | Mon Dec 02 08:00:00 IST 2013 | Mon Aug 31 18:00:00 IDT 2015 | Tue Jul 02 08:00:00 IDT 2013 | Wed Mar 25 18:00:00 IST 2015 |  | COMPLETED
505 | TT_TASK | Prepare and Submit Detailed Interface Specification | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 |  | COMPLETED
506 | TT_TASK | Approval of Detailed Interface Plan | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
507 | TT_TASK | Prepare and Submit Detailed Interface Specification | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 |  | COMPLETED
508 | TT_TASK | Approval of Detailed Interface Plan | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
510 | TT_TASK | Prepare and Submit Draft Operation and Maintenance Manual [PS33.1] | Mon Aug 24 08:00:00 IDT 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jul 28 08:00:00 IDT 2014 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
511 | TT_TASK | Review and approval period of Draft Operation and Maintenance Manual | Wed Aug 10 08:00:00 IDT 2016 | Tue Sep 13 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
512 | TT_TASK | Prepare and Submit Final Operation and Maintenance Manual [PS33.1] | Wed Sep 14 08:00:00 IDT 2016 | Thu Feb 16 18:00:00 IST 2017 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
513 | TT_TASK | Provide Engineer with As-Built Drawing for the Whole of the Works [PS33.2] | Mon Nov 21 08:00:00 IST 2016 | Wed Dec 14 18:00:00 IST 2016 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
514 | TT_TASK | Provide Engineer with Asset Registration Information [PS33.3] | Fri May 19 08:00:00 IDT 2017 | Mon Jun 12 18:00:00 IDT 2017 |  |  |  | NOT_STARTED
517 | TT_TASK | Preliminary Design Programme - Prepare and Submit for Approval [PS7.1.8 - App. Z2.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
518 | TT_TASK | Preliminary Design Programme - Review and Approval Period [PS7.1.8 - App. Z2.2] | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 |  | COMPLETED
519 | TT_TASK | Preliminary Design Programme - Resubmission and Approval (if required) [PS7.1.8 - App. Z2.2] | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 |  | COMPLETED
520 | TT_TASK | Schedule of Designs - Prepare and Submit for Approval [PS7.1.8 - App. Z2.5] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
521 | TT_TASK | Detailed Proposal for Carrying Out the Cross Passage Works [PS11.5.2] | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
524 | TT_TASK | Design TBM and submit full details to the Engineer [PS7.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
525 | TT_TASK | TBM Design - Approval period | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 |  | COMPLETED
526 | TT_TASK | TBM Design - Resubmission and approval period | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 |  | COMPLETED
528 | TT_TASK | AIP Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
529 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 |  | COMPLETED
530 | TT_TASK | DDS Design - Prepare and Submit | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 |  | COMPLETED
531 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 |  | COMPLETED
532 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 |  | COMPLETED
533 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 |  | COMPLETED
534 | TT_TASK | Issue Completed Working Drawings | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
536 | TT_TASK | AIP Design - Prepare and Submit | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 |  | COMPLETED
537 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 |  | COMPLETED
538 | TT_TASK | AIP Design - Response to comments and Resubmit | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
539 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
540 | TT_TASK | DDS Design - Prepare and Submit | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
541 | TT_TASK | DDS Design - Review and Approval Period (by MTRC & related Government Authorities) | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 |  | COMPLETED
542 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 |  | COMPLETED
543 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 |  | COMPLETED
544 | TT_TASK | Issue Completed Working Drawings | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 |  | COMPLETED
546 | TT_TASK | DDS Design - Prepare and Submit | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 |  | COMPLETED
547 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 |  | COMPLETED
548 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 |  | COMPLETED
549 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 |  | COMPLETED
550 | TT_TASK | Issue Completed Working Drawings | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
552 | TT_TASK | AIP Design - Prepare and Submit | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 |  | COMPLETED
553 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
554 | TT_TASK | AIP Design - Response to comments and Resubmit | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 |  | COMPLETED
555 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
556 | TT_TASK | DDS Design - Prepare and Submit | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 |  | COMPLETED
557 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 |  | COMPLETED
558 | TT_TASK | DDS Design - Response to comments and Resubmit | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 |  | COMPLETED
559 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 |  | COMPLETED
560 | TT_TASK | Issue Completed Working Drawings | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 |  | COMPLETED
562 | TT_TASK | Prepare and Submit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 |  | COMPLETED
563 | TT_TASK | Review and Approval Period | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
564 | TT_TASK | Response to comments and Resubmit | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 |  | COMPLETED
565 | TT_TASK | Review and Approval Period (for resubmission) | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 |  | COMPLETED
568 | TT_TASK | DDS Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
569 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 |  | COMPLETED
570 | TT_TASK | DDS Design - Response to comments and Resubmit | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 |  | COMPLETED
571 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 |  | COMPLETED
572 | TT_TASK | Issue Completed Working Drawings | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
574 | TT_TASK | DDS Design - Prepare and Submit | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 |  | COMPLETED
575 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 |  | COMPLETED
576 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 |  | COMPLETED
577 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 |  | COMPLETED
578 | TT_TASK | Issue Completed Working Drawings | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 |  | COMPLETED
580 | TT_TASK | DDS Design - Prepare and Submit | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 |  | COMPLETED
581 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 |  | COMPLETED
582 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 |  | COMPLETED
583 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 |  | COMPLETED
584 | TT_TASK | Issue Completed Working Drawings | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 |  | COMPLETED
586 | TT_TASK | DDS Design - Prepare and Submit | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 |  | COMPLETED
587 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 |  | COMPLETED
588 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 |  | COMPLETED
589 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 |  | COMPLETED
590 | TT_TASK | Issue Completed Working Drawings | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 |  | COMPLETED
592 | TT_TASK | DDS Design - Prepare and Submit | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 |  | COMPLETED
593 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 |  | COMPLETED
594 | TT_TASK | DDS Design - Response to comments and Resubmit | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 |  | COMPLETED
595 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 |  | COMPLETED
596 | TT_TASK | Issue Completed Working Drawings | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
599 | TT_TASK | Formworks / Falsework - Prepare & Submit | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
600 | TT_TASK | Formworks / Falsework - Review & Approval Period (by MTRC) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
601 | TT_TASK | Formworks / Falsework - Response to comments and Resubmit | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 |  | COMPLETED
602 | TT_TASK | Formworks / Falsework - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
605 | TT_TASK | Layout of Site Hoarding - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
606 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (by MTRC) | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
607 | TT_TASK | Layout of Site Hoarding - Response to comments and Resubmit | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
608 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 |  | COMPLETED
610 | TT_TASK | Layout of Engineer's Accommodation - Prepare and Submit | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
611 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (by MTRC) | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 |  | COMPLETED
612 | TT_TASK | Layout of Engineer's Accommodation - Response to comments and Resubmit | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
613 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (for resubmit) (by MTRC & related Government Authorities | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
615 | TT_TASK | TTMS Assessment Report - Prepare and Submit | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 |  | COMPLETED
616 | TT_TASK | TTMS Assessment Report - Review and Approval Period (by MTRC) | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
617 | TT_TASK | TTMS Assessment Report - Response to comments and Resubmit | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 |  | COMPLETED
618 | TT_TASK | TTMS Assessment Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
619 | TT_TASK | Issue Completed Working Drawings | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 |  | COMPLETED
621 | TT_TASK | DIA Report - Prepare and Submit | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 |  | COMPLETED
622 | TT_TASK | DIA Report - Review and Approval Period (by MTRC) | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 |  | COMPLETED
623 | TT_TASK | DIA Report - Response to comments and Resubmit | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 |  | COMPLETED
624 | TT_TASK | DIA Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
625 | TT_TASK | Issue Completed Working Drawings | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 |  | COMPLETED
627 | TT_TASK | AIP Design - Prepare & Submit | Wed Sep 23 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 |  | COMPLETED
628 | TT_TASK | AIP Design - Review & Approval Period (by MTR) | Wed Oct 14 08:00:00 IDT 2015 | Wed Nov 11 18:00:00 IST 2015 | Mon Jun 08 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
629 | TT_TASK | AIP Design - Response to comments and Resubmit | Thu Nov 12 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Mon Jun 15 01:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
630 | TT_TASK | AIP Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jun 22 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
631 | TT_TASK | DDS Design - Prepare & Submit | Wed Jan 13 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Tue Sep 01 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 |  | COMPLETED
632 | TT_TASK | DDS Design - Review & Approval Period (by MTRC) | Fri Feb 26 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 12 18:00:00 IDT 2015 |  | COMPLETED
633 | TT_TASK | DDS Design - Response to comments & Resubmit | Tue Mar 29 08:00:00 IDT 2016 | Fri Apr 01 18:00:00 IDT 2016 | Mon Sep 14 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
634 | TT_TASK | DDS Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Apr 02 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 | Mon Sep 21 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
635 | TT_TASK | Issue Completed Working Drawings | Wed Jan 27 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
637 | TT_TASK | Layout of Barging Point - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
638 | TT_TASK | Layout of Barging Point - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
639 | TT_TASK | Layout of Barging Point - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
640 | TT_TASK | Layout of Barging Point - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
641 | TT_TASK | Loading Ramps - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
642 | TT_TASK | Loading Ramps - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
643 | TT_TASK | Loading Ramps - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
644 | TT_TASK | Loading Ramps - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
645 | TT_TASK | Weighbridge - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
646 | TT_TASK | Weighbridge - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
647 | TT_TASK | Weighbridge - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
648 | TT_TASK | Weighbridge - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
652 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
653 | TT_TASK | Pre-drill and guide wall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
654 | TT_TASK | D-wall construction (1084m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
655 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
656 | TT_TASK | Wang Toi Shan Shan Tsuen Road diversion works | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 |  | COMPLETED
658 | TT_TASK | Excavate up to +10.5mPD (369m3) | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 |  | COMPLETED
659 | TT_TASK | Install Strut S0 +11.0mPD | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 |  | COMPLETED
660 | TT_TASK | Excavate up to +8.0mPD (1525m3) | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 |  | COMPLETED
661 | TT_TASK | Install Strut S1 +8.5mPD | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 |  | COMPLETED
662 | TT_TASK | Excavate up to +4.5mPD (2135m3) | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 |  | COMPLETED
663 | TT_TASK | Install Strut S2 +5.0mPD | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 |  | COMPLETED
664 | TT_TASK | Excavate up to +0.5mPD (2440m3) | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 |  | COMPLETED
665 | TT_TASK | Install Strut S3 +1.0mPD | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 |  | COMPLETED
666 | TT_TASK | Excavate up to -6.5mPD (4340m3) | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 |  | COMPLETED
667 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
668 | TT_TASK | Construction of temporary slab and entrance seal (622m3) | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
672 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 08 18:00:00 IST 2014 | Fri Dec 05 08:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
673 | TT_TASK | Erect external formwork (Base Slab) | Tue Dec 09 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 08 08:00:00 IST 2014 | Tue Dec 09 18:00:00 IST 2014 |  | COMPLETED
674 | TT_TASK | Rebar fixing (Base Slab) | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 18:00:00 IST 2014 | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
675 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Dec 15 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Mon Dec 15 18:00:00 IST 2014 |  | COMPLETED
676 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Dec 17 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Tue Dec 16 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 |  | COMPLETED
677 | TT_TASK | Curing (Base Slab) | Thu Dec 18 08:00:00 IST 2014 | Sat Dec 27 18:00:00 IST 2014 | Wed Dec 17 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
678 | TT_TASK | Removal of formwork (Base Slab) | Fri Dec 19 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 24 18:00:00 IST 2014 |  | COMPLETED
679 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
680 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 | Mon Jun 22 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 |  | COMPLETED
681 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Jun 13 08:00:00 IDT 2015 | Mon Jun 15 18:00:00 IDT 2015 | Thu Jun 25 01:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
682 | TT_TASK | Concreting (Wall & Roof) (444m3) | Tue Jun 16 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
683 | TT_TASK | Curing (Wall & Roof) | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
684 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 |  | COMPLETED
685 | TT_TASK | Removal external formwork (Wall) | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
686 | TT_TASK | Side walkway and cable bracket (360m3) | Sat Jul 18 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Sat Jul 18 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
687 | TT_TASK | Access opening to DC (DC access period) | Tue Oct 06 08:00:00 IDT 2015 | Fri Mar 04 18:00:00 IST 2016 | Tue Oct 06 08:00:00 IDT 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
688 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Sat Dec 12 08:00:00 IST 2015 | Mon Jan 18 18:00:00 IST 2016 | Tue Nov 03 00:00:00 IST 2015 | Mon Nov 30 18:00:00 IST 2015 |  | COMPLETED
690 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 | Tue Apr 12 08:00:00 IDT 2016 | Wed Apr 13 18:00:00 IDT 2016 |  | COMPLETED
691 | TT_TASK | Erect external formwork (Base Slab) | Mon May 23 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Thu Apr 14 08:00:00 IDT 2016 | Fri Apr 15 18:00:00 IDT 2016 |  | COMPLETED
692 | TT_TASK | Rebar fixing (Base Slab) | Wed May 25 08:00:00 IDT 2016 | Fri May 27 18:00:00 IDT 2016 | Sat Apr 16 08:00:00 IDT 2016 | Tue Apr 19 18:00:00 IDT 2016 |  | COMPLETED
693 | TT_TASK | Erect internal kicker formwork (Base Slab) | Sat May 28 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 | Wed Apr 20 08:00:00 IDT 2016 | Thu Apr 21 18:00:00 IDT 2016 |  | COMPLETED
694 | TT_TASK | Concreting (Base Slab) (225m3) | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 | Fri Apr 22 08:00:00 IDT 2016 | Fri Apr 22 18:00:00 IDT 2016 |  | COMPLETED
695 | TT_TASK | Curing (Base Slab) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 08 18:00:00 IDT 2016 | Sat Apr 23 08:00:00 IDT 2016 | Fri Apr 29 18:00:00 IDT 2016 |  | COMPLETED
696 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Sat Apr 30 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
697 | TT_TASK | Removal of formwork (Base Slab) | Tue May 24 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Mon May 09 08:00:00 IDT 2016 | Tue May 10 18:00:00 IDT 2016 |  | COMPLETED
698 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed May 25 08:00:00 IDT 2016 | Sat May 28 18:00:00 IDT 2016 | Wed May 11 08:00:00 IDT 2016 | Mon May 16 18:00:00 IDT 2016 |  | COMPLETED
699 | TT_TASK | Rebar fixing (Wall & Roof) | Mon May 30 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 17 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 |  | COMPLETED
700 | TT_TASK | Erect external formwork (Wall & Roof) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 03 18:00:00 IDT 2016 | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 |  | COMPLETED
701 | TT_TASK | Concreting (Wall & Roof) (444m3) | Sat Jun 04 08:00:00 IDT 2016 | Sat Jun 04 18:00:00 IDT 2016 | Mon May 23 08:00:00 IDT 2016 | Mon May 23 18:00:00 IDT 2016 |  | COMPLETED
702 | TT_TASK | Curing (Wall & Roof) | Mon Jun 06 08:00:00 IDT 2016 | Tue Jun 14 18:00:00 IDT 2016 | Tue May 24 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 |  | COMPLETED
703 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 15 08:00:00 IDT 2016 | Wed Jun 15 18:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 |  | COMPLETED
704 | TT_TASK | Removal external formwork (Wall) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
705 | TT_TASK | Side walkway and cable bracket (102m3) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 |  | COMPLETED
706 | TT_TASK | Access opening to DC (DC access period) | Sat Jun 18 08:00:00 IDT 2016 | Thu Jul 14 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
707 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Fri Jul 15 08:00:00 IDT 2016 | Wed Aug 17 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
709 | TT_TASK | Backfilling between tunnels (2000m3) | Thu Sep 01 08:00:00 IDT 2016 | Sat Sep 17 18:00:00 IDT 2016 | Tue Sep 13 08:00:00 IDT 2016 | Fri Sep 30 18:00:00 IDT 2016 |  | COMPLETED
710 | TT_TASK | Remove Strut S2 | Mon Oct 03 08:00:00 IDT 2016 | Wed Oct 05 18:00:00 IDT 2016 | Mon Oct 03 08:00:00 IDT 2016 | Tue Oct 11 18:00:00 IDT 2016 |  | COMPLETED
711 | TT_TASK | Backfilling up top S1 Soffit | Thu Oct 06 08:00:00 IDT 2016 | Fri Oct 21 18:00:00 IDT 2016 | Fri Oct 28 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
712 | TT_TASK | Remove Strut S1 | Sat Oct 22 08:00:00 IDT 2016 | Mon Oct 24 18:00:00 IDT 2016 | Tue Oct 11 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
713 | TT_TASK | Backfilling up top S0 Soffit | Mon Nov 07 08:00:00 IST 2016 | Sat Nov 12 18:00:00 IST 2016 | Tue Nov 01 08:00:00 IST 2016 | Sat Nov 05 18:00:00 IST 2016 |  | COMPLETED
714 | TT_TASK | Remove Strut S0 | Mon Nov 14 08:00:00 IST 2016 | Tue Nov 15 18:00:00 IST 2016 | Mon Nov 07 08:00:00 IST 2016 | Tue Nov 08 18:00:00 IST 2016 |  | COMPLETED
715 | TT_TASK | Backfilling up to ground level | Wed Nov 16 08:00:00 IST 2016 | Fri Nov 18 18:00:00 IST 2016 | Wed Nov 09 08:00:00 IST 2016 | Fri Nov 11 18:00:00 IST 2016 |  | COMPLETED
719 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
720 | TT_TASK | Pre-drilling and guidewall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
721 | TT_TASK | D-wall construction (1451m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
722 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 |  | COMPLETED
724 | TT_TASK | Excavate from ground level to formation level -5.5mPD (4559m3) | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 |  | COMPLETED
725 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 |  | COMPLETED
726 | TT_TASK | Placing of blinding layer (South Bound) | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 |  | COMPLETED
727 | TT_TASK | Placing of blinding layer (North Bound) | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
729 | TT_TASK | Construction of Bay 2 to Bay 7a (3565m3) | Mon Jun 04 08:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 | Mon Jun 04 18:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 |  | COMPLETED
730 | TT_TASK | Side walkway and cable bracket (Southbound) | Fri Oct 02 08:00:00 IDT 2015 | Fri Nov 06 18:00:00 IST 2015 | Fri Oct 02 08:00:00 IDT 2015 | Sat Oct 31 18:00:00 IST 2015 |  | COMPLETED
731 | TT_TASK | Side walkway and cable bracket (Northbound) | Tue May 03 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 |  | COMPLETED
733 | TT_TASK | Backfilling (1344m3) | Wed Nov 07 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 | Wed Nov 07 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
736 | TT_TASK | Scheme Design, Mobilization, Site set up & Material delivery and Instrumentations | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
737 | TT_TASK | Downstream pipe pile wall construction (45 nos.) and grout curtain (45 nos.) | Mon Nov 12 08:00:00 IST 2012 | Fri Jan 25 18:00:00 IST 2013 | Mon Nov 12 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
738 | TT_TASK | Curtain Grout for cut slope (120 nos.) | Fri Jul 26 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
739 | TT_TASK | Drilling for ground improvement only (if require) | Mon Dec 10 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
740 | TT_TASK | If settlement reach the AAA alarm & action level TAM grouting will apply during excavation | Thu Apr 11 08:00:00 IDT 2013 | Thu May 16 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
741 | TT_TASK | Erection of temporary working platform for Up stream and Installation of Instrumentation System | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
742 | TT_TASK | Upstream pipe pile wall construction adjacent to WTSSTR, (17nos.) | Thu Dec 27 08:00:00 IST 2012 | Mon Jan 28 18:00:00 IST 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
743 | TT_TASK | Upstream pipe pile wall construction at Kam Tin River, 15m depth, 42nos. 1drill rig) | Tue Jan 29 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
744 | TT_TASK | Excavation and soil nail installation | Tue Apr 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
745 | TT_TASK | Excavation for rock and blinding layer | Sat Aug 24 08:00:00 IDT 2013 | Sat Sep 28 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
750 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
751 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
752 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
753 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
754 | TT_TASK | Concreting (164m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
755 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
756 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
757 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
758 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
759 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
760 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
761 | TT_TASK | Concreting (242m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
762 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
763 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
764 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
765 | TT_TASK | Removal internal falsework and formwork for roof | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
766 | TT_TASK | Side walkway and cable bracket (19m3) | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
770 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
771 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
772 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
773 | TT_TASK | Erect internal kicker formwork | Thu Nov 28 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 09 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
774 | TT_TASK | Concreting (121m3) | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
775 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
776 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
777 | TT_TASK | Removal of formwork | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
778 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
779 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
780 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
781 | TT_TASK | Concreting (121m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
782 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
783 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
784 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
785 | TT_TASK | Removal internal falsework and formwork for roof | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
786 | TT_TASK | Side walkway and cable bracket (38m3) | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
788 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
789 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
790 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
791 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
792 | TT_TASK | Concreting (240m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
793 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
794 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
795 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
796 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
797 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
798 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
799 | TT_TASK | Concreting (240m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
800 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
801 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
802 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
803 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
804 | TT_TASK | Side walkway and cable bracket | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
806 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
807 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
808 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
809 | TT_TASK | Concreting (222m3) | Wed Nov 06 08:00:00 IST 2013 | Wed Nov 06 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
810 | TT_TASK | Curing | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
811 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
812 | TT_TASK | Removal of formwork | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
815 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
816 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
817 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
818 | TT_TASK | Erect internal kicker formwork | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
819 | TT_TASK | Concreting (111m3) | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
820 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
821 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
822 | TT_TASK | Removal of formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
823 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
824 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
825 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
826 | TT_TASK | Concreting (220m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
827 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
828 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
829 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
830 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
831 | TT_TASK | Side walkway and cable bracket (38m3) | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 |  | COMPLETED
833 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
834 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
835 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
836 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
837 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
838 | TT_TASK | Curing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
839 | TT_TASK | Preparation of construction joint for base slab | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
840 | TT_TASK | Removal of formwork | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
841 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
842 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
843 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
844 | TT_TASK | Concreting (327m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
845 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
846 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
847 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
848 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
849 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
851 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 20 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
852 | TT_TASK | Rebar fixing | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
853 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 08:00:00 IDT 2013 |  | COMPLETED
854 | TT_TASK | Concreting (225m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
855 | TT_TASK | Curing | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
856 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
857 | TT_TASK | Removal of formwork | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
860 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 27 08:00:00 IST 2013 | Wed Nov 27 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
861 | TT_TASK | Erect external formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
862 | TT_TASK | Rebar fixing | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
863 | TT_TASK | Erect internal kicker formwork | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
864 | TT_TASK | Concreting (222m3) | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
865 | TT_TASK | Curing | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Mon Oct 28 18:00:00 IST 2013 |  | COMPLETED
866 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
867 | TT_TASK | Removal of formwork | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
868 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
869 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
870 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
871 | TT_TASK | Concreting (222m3) | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 |  | COMPLETED
872 | TT_TASK | Curing | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 07 18:00:00 IST 2014 |  | COMPLETED
873 | TT_TASK | Preparation of construction joint for wall and roof | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
874 | TT_TASK | Removal external and internal formwork for wall | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
875 | TT_TASK | Removal internal falsework and formwork for roof | Mon Feb 10 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
876 | TT_TASK | Side walkway and cable bracket (38m3) | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 |  | COMPLETED
878 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
879 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
880 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
881 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
882 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
883 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
884 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
885 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
886 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
887 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
888 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
889 | TT_TASK | Concreting (222m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
890 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
892 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
893 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
894 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
896 | TT_TASK | Placing of waterproof member T-lock & testing | Mon Nov 18 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
897 | TT_TASK | Rebar fixing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Wed Oct 23 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
898 | TT_TASK | Erect external formwork | Fri Nov 22 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
899 | TT_TASK | Concreting (222m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
900 | TT_TASK | Curing | Tue Nov 26 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
901 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
902 | TT_TASK | Removal of formwork | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
905 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
906 | TT_TASK | Erect external formwork | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
907 | TT_TASK | Rebar fixing | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
908 | TT_TASK | Erect internal kicker formwork | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
909 | TT_TASK | Concreting (330m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
910 | TT_TASK | Curing | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
911 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
912 | TT_TASK | Removal of formwork | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
913 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
914 | TT_TASK | Rebar fixing | Wed Nov 20 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
915 | TT_TASK | Erect external formwork | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
916 | TT_TASK | Concreting (330m3) | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
917 | TT_TASK | Curing | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
918 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
919 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
920 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
921 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
923 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
924 | TT_TASK | Erect external formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
925 | TT_TASK | Rebar fixing | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
926 | TT_TASK | Erect internal kicker formwork | Wed Dec 04 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
927 | TT_TASK | Concreting (240m3) | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
928 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
929 | TT_TASK | Preparation of construction joint for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
930 | TT_TASK | Removal of formwork | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
931 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
932 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
933 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
934 | TT_TASK | Concreting (240m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
935 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
936 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
937 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
938 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
939 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
941 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
942 | TT_TASK | Rebar fixing | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
943 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
944 | TT_TASK | Concreting (240m3) | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
945 | TT_TASK | Curing | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
946 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
947 | TT_TASK | Removal of formwork | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
950 | TT_TASK | Placing of waterproof member T-lock & testing | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
951 | TT_TASK | Erect external formwork | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
952 | TT_TASK | Rebar fixing | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
953 | TT_TASK | Erect internal kicker formwork | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
954 | TT_TASK | Concreting (200m3) | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
955 | TT_TASK | Curing | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
956 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
957 | TT_TASK | Removal of formwork | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
958 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 29 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
959 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
960 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
961 | TT_TASK | Concreting (200m3) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
962 | TT_TASK | Curing | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
963 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
964 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 13 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
965 | TT_TASK | Removal internal falsework and formwork for roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
966 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 |  | COMPLETED
968 | TT_TASK | Placing of waterproof member T-lock & testing | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
969 | TT_TASK | Erect external formwork | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
970 | TT_TASK | Rebar fixing | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
971 | TT_TASK | Erect internal kicker formwork | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
972 | TT_TASK | Concreting (220m3) | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
973 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
974 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
975 | TT_TASK | Removal of formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
976 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
977 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
978 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
979 | TT_TASK | Concreting (220m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
980 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
981 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
982 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
983 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
984 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
986 | TT_TASK | Placing of waterproof member T-lock & testing | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
987 | TT_TASK | Rebar fixing | Mon Nov 25 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
988 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
989 | TT_TASK | Concreting (222m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
990 | TT_TASK | Curing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
991 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
992 | TT_TASK | Removal of formwork | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
994 | TT_TASK | Removal of Temporary Nullah | Sat Mar 01 08:00:00 IST 2014 | Sat Jun 21 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
995 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (5218m3) | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 |  | COMPLETED
996 | TT_TASK | Reinstate the permenant Retaining wall of Nullah | Sat Mar 01 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Tue Mar 04 08:00:00 IST 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
997 | TT_TASK | Reinstate Nullah Base of original route | Tue Feb 25 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Tue Feb 25 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
998 | TT_TASK | Reinstate Nullah to original route | Sat Mar 29 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Sat Mar 29 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
999 | TT_TASK | Construction & connect East Box Culvert from Box 6B to KTR | Mon Apr 14 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Mon Feb 10 08:00:00 IST 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
1000 | TT_TASK | Reinstatement of Wang Toi Shan Shan Tsuen Road | Tue Dec 01 08:00:00 IST 2015 | Wed Jul 13 18:00:00 IDT 2016 | Tue Dec 01 08:00:00 IST 2015 | Mon Jul 18 18:00:00 IDT 2016 |  | COMPLETED
1003 | TT_TASK | Pre-drilling at Works Area 4.4 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
1004 | TT_TASK | Site Setup and guide wall | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1005 | TT_TASK | D-wall construction (3104m3) | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 |  | COMPLETED
1006 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
1008 | TT_TASK | Excavate up to +8.0mPD (775m3) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1009 | TT_TASK | Install Strut S1 +8.5mPD | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 |  | COMPLETED
1010 | TT_TASK | Excavate up to +4.5mPD (2713m3) | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 |  | COMPLETED
1011 | TT_TASK | Install Strut S2 +5.0mPD | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
1012 | TT_TASK | Excavate up to +0.5mPD (3100m3) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 |  | COMPLETED
1013 | TT_TASK | Install Strut S3 +1.0mPD | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1014 | TT_TASK | Excavate up to -3.0mPD (2713m3) | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1015 | TT_TASK | Install Strut S4 -2.5mPD | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 |  | COMPLETED
1016 | TT_TASK | Excavate up to -5.5mPD (4952m3) | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1017 | TT_TASK | Placing of blinding layer | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1021 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1022 | TT_TASK | Erect external formwork for base slab | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1023 | TT_TASK | Rebar fixing for base slab | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1024 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 26 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1025 | TT_TASK | Concreting for base slab (350m3) | Thu Jun 27 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1026 | TT_TASK | Curing for base slab | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1027 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1028 | TT_TASK | Removal of formwork for base slab | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1029 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1030 | TT_TASK | Removal strut S4 and S3 | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1032 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1033 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1034 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1035 | TT_TASK | Concreting for wall and roof (489m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1036 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1037 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1038 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1039 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1040 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1043 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1044 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1045 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1046 | TT_TASK | Curing for wall and roof | Sat Jun 22 08:00:00 IDT 2013 | Mon Jul 01 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1047 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1048 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1050 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Tue Dec 17 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1053 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1054 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1055 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1056 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1057 | TT_TASK | Concreting for base slab (350m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1058 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1059 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1060 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1061 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1062 | TT_TASK | Removal strut S4 and S3 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1064 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1065 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1066 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1067 | TT_TASK | Concreting for wall and roof (489m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1068 | TT_TASK | Curing for wall and roof | Wed Jun 12 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1069 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1070 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 14 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1071 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1072 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Feb 13 08:00:00 IST 2014 | Tue Feb 18 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1074 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1075 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1076 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1077 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1078 | TT_TASK | Curing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1079 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1080 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1081 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1082 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 16 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1084 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (2343m3) | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1085 | TT_TASK | Placing 0.5m thk concrete lateral support (+3.96mPD) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1086 | TT_TASK | Removal strut S2 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 23 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1088 | TT_TASK | Construction of Temporary Culvert (open channel) | Tue Jun 25 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1089 | TT_TASK | Temporary box culvert (At Box 6B Area) Saw Cut D-wall | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 |  | COMPLETED
1090 | TT_TASK | Erect 3m high block wall | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 |  | COMPLETED
1091 | TT_TASK | Connection to East Box Culvert (823B portion) | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 |  | COMPLETED
1092 | TT_TASK | Blinding | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
1093 | TT_TASK | Temporary box culvert (Outside Box 6B Area) Sheet piling | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 |  | COMPLETED
1094 | TT_TASK | ELS Works | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
1095 | TT_TASK | Blinding | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
1096 | TT_TASK | Removal of Temporary Culvert and Reinstatement | Fri May 16 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
1098 | TT_TASK | Reinstatement of TOA's | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 |  |  | IN_PROGRESS
1099 | TT_TASK | Hydroseeding works | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 | Wed Nov 30 18:00:00 IST 2016 |  | COMPLETED
1100 | TT_TASK | Tree Planting works | Thu Sep 01 08:00:00 IDT 2016 | Sat Dec 03 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
1101 | TT_TASK | Woodland Shrub Mix | Thu Sep 01 08:00:00 IDT 2016 | Fri Nov 18 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  | 200.0 | IN_PROGRESS
1104 | TT_TASK | Kam Tin River Diversion (Stage 1-3) | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1106 | TT_TASK | Concrete fill up to +8.0mPD near side A mass concrete wall | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 |  | COMPLETED
1107 | TT_TASK | Construction of mass concrete wall to +8.0mPD at side A (4 bay CH A80~A120) | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1108 | TT_TASK | Construction of base slab lining and low flow channel (4 bay A9~A10, B8~B9; LFC CH 80~110) | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1109 | TT_TASK | Construction of mass concrete wall to +8.0mPD of side B (3 bay CH B60~B90) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1110 | TT_TASK | Construction of T-shaped retaining wall (1 Bay CH B50~B60) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1111 | TT_TASK | Soil backfill at side A from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1112 | TT_TASK | Concrete backfill at side B from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1113 | TT_TASK | Removal strut at +8.5mPD near side A | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1114 | TT_TASK | Concrete fill up to +11.0mPD near side A mass concrete wall | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1115 | TT_TASK | Placing concrete block at side A from +8.0mPD to +11.0mpd at side A (4 bay CH A80~A120) | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1116 | TT_TASK | Soil backfill at side A from +8.0mPD to +11.0mPD | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1117 | TT_TASK | Removal strut at +8.5mPD near side B | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1118 | TT_TASK | Placing concrete block at side B from +8.0mPD to +11.0mPD (4 bay CH B60~B90) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1119 | TT_TASK | Concrete backfill at side B from +8.0mPD to +11.0mPD | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1121 | TT_TASK | Placing temporary concrete block to Up stream at CH30 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 |  | COMPLETED
1122 | TT_TASK | Placing temporary concrete block to Up stream at CH160 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1123 | TT_TASK | Excavation from GL to FL +5.0mPD Up stream (Low flow channel CH 30~60) | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1124 | TT_TASK | Excavation from GL to FL +5.0mPD Down stream (Low flow channel CH 130~160) | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1125 | TT_TASK | Construction of T-shaped retaining wall at Up stream of side B (2 Bay CH B30~B50) | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1126 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (3 bay CH B90~B120) | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1127 | TT_TASK | Construction of Up stream base slab lining and low flow channel (6 Bay A1~A4, B3~B4; Low flow channel CH 30~50) | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1128 | TT_TASK | Construction of Down stream base slab lining and low flow channel (5 Bay A14~A16, B14~B15; LFC CH 140~170) | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1129 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Up stream and saw cut D-wall | Fri Jun 14 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1130 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Down stream and saw cut D-wall | Wed Jun 19 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1131 | TT_TASK | Construction of remaining Up stream base slab lining and low flow channel (7 bay A5~A8, B5~B7; LFC CH 50~80) | Thu Jun 27 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1132 | TT_TASK | Construction of remaining Down stream base slab lining and low flow channel (7 bay A11~A13, B10~B13; LFC CH 110~140) | Wed Jul 03 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1134 | TT_TASK | Relocation of temporary concrete block at Up stream for construction of mass concrete wall at side B | Sat Jul 20 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1135 | TT_TASK | Relocation of temporary concrete block at Down stream for construction of mass concrete wall at side B | Tue Jul 23 08:00:00 IDT 2013 | Wed Jul 24 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1136 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Up stream of side B (3 bay CH B0~B30) | Tue Jul 23 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1137 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (4 bay CH B0~B30) | Thu Jul 25 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1141 | TT_TASK | Application of power supply, environmental permits and construction substation | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1142 | TT_TASK | Procurement and Confirmation of the order of 1st tunnel boring machine | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 |  | COMPLETED
1143 | TT_TASK | Prepare on-demand bond or bank guarantee for the procurement of TBM and submit to Engineer for approval | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 |  | COMPLETED
1144 | TT_TASK | TBM design and submission for approval | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
1145 | TT_TASK | TBM materials order and delivery to factory | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 |  | COMPLETED
1146 | TT_TASK | TBM equipments order and delivery to factory | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 |  | COMPLETED
1147 | TT_TASK | TBM Fabrication | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
1148 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 |  | COMPLETED
1149 | TT_TASK | TBM test Run | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 |  | COMPLETED
1150 | TT_TASK | TBM disassembly and packing for shipping to HK | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 |  | COMPLETED
1151 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
1152 | TT_TASK | Ground treatment for TBM lanching shaft | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 |  | COMPLETED
1153 | TT_TASK | Ground treatment for Cross Passage Tunnel | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1154 | TT_TASK | Box7A Setup TBM facilities, install noise enclosure and CNP application | Fri Jun 01 08:00:00 IDT 2012 | Sat Jan 26 18:00:00 IST 2013 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1155 | TT_TASK | Notice to Contract 824 the anticipated dates of break out TBM Shaft | Sat Jun 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1156 | TT_TASK | Fabrication of tunnel segment mould | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
1157 | TT_TASK | Fabrication 50% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1158 | TT_TASK | Fabrication 100% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
1159 | TT_TASK | Fabrication 30% of North Tunnel North Bound (Uptrack) Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1160 | TT_TASK | Fabrication 60% of North Tunnel North Bound (Uptrack) Precast Lining | Thu Oct 18 08:00:00 IST 2012 | Thu Feb 21 18:00:00 IST 2013 | Thu Oct 18 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1161 | TT_TASK | Fabrication 100% of North Tunnel North Bound (Uptrack) Precast Lining | Mon Aug 19 08:00:00 IDT 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Dec 03 08:00:00 IST 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1163 | TT_TASK | Assemble, T&C of TBM | Fri Jun 01 08:00:00 IDT 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Oct 16 00:00:00 IST 2012 |  | COMPLETED
1164 | TT_TASK | TBM drive & lining installation CH123+369 to CH123+283 Initial Drive (86m) | Sat Nov 03 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 | Wed Oct 17 00:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1165 | TT_TASK | Change Plant (Back-up cars) | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1166 | TT_TASK | TBM drive & lining installation CH123+283 to CH123+183 | Thu Jun 27 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1167 | TT_TASK | TBM drive & lining installation CH123+183 to CH123+083 | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1168 | TT_TASK | TBM drive & lining installation CH123+083 to CH122+983 | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1169 | TT_TASK | TBM drive & lining installation CH122+983 to CH122+883 | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1170 | TT_TASK | TBM drive & lining installation CH122+883 to CH122+783 | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Jun 13 08:00:00 IDT 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
1171 | TT_TASK | TBM drive & lining installation CH122+783 to CH122+683 | Sat Nov 02 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1172 | TT_TASK | TBM drive & lining installation CH122+683 to CH122+583 | Tue Dec 03 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Wed Feb 26 18:00:00 IST 2014 |  | COMPLETED
1173 | TT_TASK | TBM drive & lining installation CH122+583 to CH122+491 | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Feb 27 08:00:00 IST 2014 | Sat Aug 16 00:00:00 IDT 2014 |  | COMPLETED
1174 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1175 | TT_TASK | Dis-assemble TBM | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
1176 | TT_TASK | Invert slab, side walkway | Sat Oct 04 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 | Mon Sep 15 08:00:00 IDT 2014 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1177 | TT_TASK | Installation of cable bracket | Tue Dec 30 08:00:00 IST 2014 | Tue Jan 13 18:00:00 IST 2015 | Fri Sep 12 08:00:00 IDT 2014 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
1178 | TT_TASK | Provision of assess open for DC and modify of strut S1 and S2 at north bound | Tue Nov 04 11:12:00 IST 2014 | Thu Dec 04 11:12:00 IST 2014 | Wed Oct 01 08:00:00 IDT 2014 | Sat Oct 18 18:00:00 IDT 2014 |  | COMPLETED
1180 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Oct 06 13:00:00 IDT 2014 | Mon Oct 20 12:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
1181 | TT_TASK | Assemble, T&C of TBM | Mon Nov 03 08:00:00 IST 2014 | Fri Jan 02 18:00:00 IST 2015 | Sat Oct 04 08:00:00 IDT 2014 | Fri Nov 28 18:00:00 IST 2014 |  | COMPLETED
1182 | TT_TASK | Setup back-up plant for final drive | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
1183 | TT_TASK | Reinstate of noise enclosure | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Sat Nov 29 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1184 | TT_TASK | TBM drive & lining installation CH123+384 to CH123+284 (Initial Drive) | Sat Dec 06 08:00:00 IST 2014 | Thu Jan 22 18:00:00 IST 2015 | Tue Dec 02 00:00:00 IST 2014 | Tue Jan 20 18:00:00 IST 2015 |  | COMPLETED
1185 | TT_TASK | TBM drive & lining installation CH123+184 to CH123+084 | Wed Jan 21 08:00:00 IST 2015 | Wed Jan 28 18:00:00 IST 2015 | Wed Jan 21 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 |  | COMPLETED
1186 | TT_TASK | TBM drive & lining installation CH123+084 to CH122+984 | Wed Feb 04 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 | Thu Feb 12 08:00:00 IST 2015 | Thu Feb 26 18:00:00 IST 2015 |  | COMPLETED
1187 | TT_TASK | TBM drive & lining installation CH122+984 to CH122+884 | Thu Feb 12 08:00:00 IST 2015 | Tue Feb 24 18:00:00 IST 2015 | Fri Feb 27 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1188 | TT_TASK | TBM drive & lining installation CH122+884 to CH122+784 | Tue Mar 10 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Wed May 27 18:00:00 IDT 2015 |  | COMPLETED
1189 | TT_TASK | TBM drive & lining installation CH122+784 to CH122+684 | Wed May 06 08:00:00 IDT 2015 | Thu May 14 18:00:00 IDT 2015 | Thu May 28 08:00:00 IDT 2015 | Sat Jul 11 18:00:00 IDT 2015 |  | COMPLETED
1190 | TT_TASK | TBM drive & lining installation CH122+684 to CH122+584 | Fri Jul 03 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
1191 | TT_TASK | TBM drive & lining installation CH122+584 to CH122+506 | Tue Nov 03 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 |  | COMPLETED
1192 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 |  | COMPLETED
1193 | TT_TASK | Dis-assemble TBM | Wed Dec 16 08:00:00 IST 2015 | Fri Jan 22 18:00:00 IST 2016 | Sun Dec 13 08:00:00 IST 2015 | Sun Mar 13 18:00:00 IST 2016 |  | COMPLETED
1194 | TT_TASK | Invert slab, side walkway | Fri Apr 01 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 | Mon Mar 14 08:00:00 IST 2016 | Tue May 24 18:00:00 IDT 2016 |  | COMPLETED
1195 | TT_TASK | Installation of cable bracket | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Mar 15 18:00:00 IST 2016 |  | COMPLETED
1196 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Mon Feb 01 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 22 18:00:00 IST 2016 |  | COMPLETED
1199 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 1 (From Downtrack to Centre of CP) | Thu Apr 10 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Sat Jun 28 18:00:00 IDT 2014 |  | COMPLETED
1200 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Sun Nov 09 18:00:00 IST 2014 |  | COMPLETED
1201 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1202 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 18:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1203 | TT_TASK | Excavation 0-4mts with Shotcrete | Mon Feb 02 08:00:00 IST 2015 | Tue Feb 17 18:00:00 IST 2015 | Mon Feb 23 08:00:00 IST 2015 | Mon Mar 30 18:00:00 IDT 2015 |  | COMPLETED
1204 | TT_TASK | Invert Concrete | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1205 | TT_TASK | Wall and Roof concrete | Thu Apr 16 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 |  | COMPLETED
1206 | TT_TASK | Dismantle Temporary frame | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 |  | COMPLETED
1207 | TT_TASK | Install Door to Cross Passage (By contract 827) | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 |  | COMPLETED
1208 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 2 (From Centre of CP to Uptrack) | Sat Oct 17 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Sep 07 08:00:00 IDT 2015 | Tue Dec 01 18:00:00 IST 2015 |  | COMPLETED
1209 | TT_TASK | Probe/Grout | Thu Jun 25 08:00:00 IDT 2015 | Mon Jul 06 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Fri Apr 10 18:00:00 IDT 2015 |  | COMPLETED
1210 | TT_TASK | Coring of Segment | Tue Jul 07 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Sat Apr 11 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1211 | TT_TASK | Removal of segment | Sat Jul 11 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
1212 | TT_TASK | Excavation 0-4mts with Shotcrete | Wed Jul 15 08:00:00 IDT 2015 | Sat Jul 25 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1213 | TT_TASK | Invert Concrete | Sat Jul 18 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 | Thu May 07 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1214 | TT_TASK | Wall and Roof concrete | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1215 | TT_TASK | Dismantle Temporary frame | Tue Jan 19 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 04 18:00:00 IST 2016 |  | COMPLETED
1216 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Feb 22 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Fri Feb 05 08:00:00 IST 2016 | Sat Feb 06 18:00:00 IST 2016 |  | COMPLETED
1218 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 1 (From Downtrack to Centre of CP) | Tue Mar 11 08:00:00 IST 2014 | Wed Mar 26 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1219 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Wed Nov 12 18:00:00 IST 2014 |  | COMPLETED
1220 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Thu Nov 13 08:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1221 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Tue Nov 18 08:00:00 IST 2014 | Thu Nov 20 18:00:00 IST 2014 |  | COMPLETED
1222 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Sat Nov 22 08:00:00 IST 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1223 | TT_TASK | Invert Concrete | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
1224 | TT_TASK | Wall and Roof concrete | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1225 | TT_TASK | Dismantle Temporary frame | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1226 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1227 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 2 (From Centre of CP to Uptrack) | Thu May 21 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Mar 09 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1228 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Mon May 04 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1229 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
1230 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1231 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 22 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
1232 | TT_TASK | Invert Concrete | Sat Aug 08 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Wed Jul 08 18:00:00 IDT 2015 |  | COMPLETED
1233 | TT_TASK | Wall and Roof concrete | Tue Aug 25 08:00:00 IDT 2015 | Mon Sep 07 18:00:00 IDT 2015 | Thu Jul 09 08:00:00 IDT 2015 | Sat Aug 15 18:00:00 IDT 2015 |  | COMPLETED
1234 | TT_TASK | Dismantle Temporary frame | Tue Sep 22 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 | Mon Aug 17 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 |  | COMPLETED
1235 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1237 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 1 (From Downtrack to Centre of CP) | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Sat May 24 18:00:00 IDT 2014 |  | COMPLETED
1238 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
1239 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1240 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 |  | COMPLETED
1241 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Mon Nov 17 08:00:00 IST 2014 | Sat Nov 29 18:00:00 IST 2014 |  | COMPLETED
1242 | TT_TASK | Invert Concrete | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 |  | COMPLETED
1243 | TT_TASK | Wall and Roof concrete | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 |  | COMPLETED
1244 | TT_TASK | Dismantle Temporary frame | Tue Dec 30 08:00:00 IST 2014 | Wed Jan 07 18:00:00 IST 2015 | Tue Dec 30 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1245 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1246 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 2 (From Centre of CP to Uptrack) | Fri May 08 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 |  | COMPLETED
1247 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
1248 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
1249 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Thu May 07 18:00:00 IDT 2015 |  | COMPLETED
1250 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
1251 | TT_TASK | Invert Concrete | Wed Aug 05 08:00:00 IDT 2015 | Fri Aug 14 18:00:00 IDT 2015 | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
1252 | TT_TASK | Wall and Roof concrete | Tue Sep 15 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Wed Aug 26 18:00:00 IDT 2015 |  | COMPLETED
1253 | TT_TASK | Dismantle Temporary frame | Sat Oct 17 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Oct 08 18:00:00 IDT 2015 |  | COMPLETED
1254 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1258 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 |  | COMPLETED
1259 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1260 | TT_TASK | D-wall construction (1192m3) | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 |  | COMPLETED
1261 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1262 | TT_TASK | Construct capping beam, cobble, etc. (including bay 6 and 5) | Sat Oct 27 08:00:00 IST 2012 | Sat Feb 16 18:00:00 IST 2013 | Sat Oct 27 08:00:00 IST 2012 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1264 | TT_TASK | Excavate up to +22.0mPD (1860m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1265 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 |  | COMPLETED
1266 | TT_TASK | Excavate up to +16.5mPD (3410m3) | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 |  | COMPLETED
1267 | TT_TASK | Install Strut S2 +17.0mPD | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 |  | COMPLETED
1268 | TT_TASK | Excavate up to +11.0mPD (3410m3) | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 |  | COMPLETED
1269 | TT_TASK | Install Strut S3 +11.5mPD | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 |  | COMPLETED
1270 | TT_TASK | Excavate up to +7.0mPD (2480m3) | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 |  | COMPLETED
1271 | TT_TASK | Install Strut S4 +7.5mPD | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1272 | TT_TASK | Excavate up to +3.5mPD (2170m3) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 |  | COMPLETED
1273 | TT_TASK | Install Strut S5 +4.0mPD | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1274 | TT_TASK | Excavate up to formation (2294m3) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1275 | TT_TASK | Construct temp. 500mm thick plain concrete base slab | Thu Oct 18 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 |  | COMPLETED
1276 | TT_TASK | Removal of South Bound strut to +9.50mPD | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1277 | TT_TASK | Removal of North Bound strut to +9.50mPD | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 |  | COMPLETED
1278 | TT_TASK | Construct temp. 500mm thick TBM concrete base slab | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1279 | TT_TASK | Construction entrance seal for TBM at South Bound | Mon Nov 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1280 | TT_TASK | Construction entrance seal for TBM at North Bound | Sat Jul 20 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1281 | TT_TASK | Saw cut South Bound diaphragm wall | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1282 | TT_TASK | Saw cut North Bound diaphragm wall | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1286 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 05 18:00:00 IDT 2014 | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 |  | COMPLETED
1287 | TT_TASK | Erect external formwork (Base Slab) | Sat Sep 06 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 21 18:00:00 IDT 2014 |  | COMPLETED
1288 | TT_TASK | Rebar fixing (Base Slab) | Wed Sep 10 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Tue Jul 22 08:00:00 IDT 2014 | Sat Jul 26 18:00:00 IDT 2014 |  | COMPLETED
1289 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Sep 15 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Sun Jul 27 08:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1290 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Thu Aug 14 18:00:00 IDT 2014 |  | COMPLETED
1291 | TT_TASK | Concreting (Base Slab) (225m3) | Sat Aug 09 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Fri Aug 15 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
1292 | TT_TASK | Curing (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
1293 | TT_TASK | Removal of formwork (Base Slab) | Tue Aug 12 08:00:00 IDT 2014 | Tue Aug 12 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1294 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed Aug 13 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Mon Sep 15 18:00:00 IDT 2014 |  | COMPLETED
1295 | TT_TASK | Rebar fixing (Wall & Roof) | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 |  | COMPLETED
1296 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 |  | COMPLETED
1297 | TT_TASK | Clearing and inspection (Wall & Roof) | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
1298 | TT_TASK | Concreting (Wall & Roof) (450m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
1299 | TT_TASK | Curing (Wall & Roof) | Sat Oct 11 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
1300 | TT_TASK | Removal external formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1301 | TT_TASK | Removal internal falsework (Wall & Roof) | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 |  | COMPLETED
1302 | TT_TASK | Side walkway and cable bracket (102m3) | Sat Oct 18 08:00:00 IDT 2014 | Wed Oct 29 18:00:00 IST 2014 | Mon Sep 01 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1304 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Wed Nov 11 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Oct 19 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1305 | TT_TASK | Erect external formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 |  | COMPLETED
1306 | TT_TASK | Rebar fixing (Base Slab) | Mon Nov 16 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Tue Oct 27 08:00:00 IST 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1307 | TT_TASK | Erect internal kicker formwork (Base Slab) | Fri Nov 20 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Oct 31 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 |  | COMPLETED
1308 | TT_TASK | Clearing and inspection (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
1309 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1310 | TT_TASK | Curing (Base Slab) | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 |  | COMPLETED
1311 | TT_TASK | Removal of formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 |  | COMPLETED
1312 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
1313 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Dec 09 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
1314 | TT_TASK | Erect external formwork (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Thu Jan 07 18:00:00 IST 2016 |  | COMPLETED
1315 | TT_TASK | Clearing and inspection (Wall & Roof) | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Fri Jan 08 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
1316 | TT_TASK | Concreting (Wall & Roof) (450m3) | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
1317 | TT_TASK | Curing (Wall & Roof) | Tue Jan 12 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
1318 | TT_TASK | Removal external formwork (Wall ) | Thu Jan 14 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
1319 | TT_TASK | Removal internal falsework, formwork and reproping (Wall & Roof) | Thu Jan 28 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 |  | COMPLETED
1320 | TT_TASK | Side walkway and cable bracket (102m3) | Wed Dec 23 08:00:00 IST 2015 | Wed Jan 06 18:00:00 IST 2016 | Wed Nov 11 08:00:00 IST 2015 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
1322 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 |  | COMPLETED
1323 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 |  | COMPLETED
1324 | TT_TASK | Backfilling to 0.5m below S3 (+11.0mPD) (3486m3) | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 |  | COMPLETED
1325 | TT_TASK | Removal strut S3 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
1326 | TT_TASK | Backfilling to 0.5m below S2 (+16.5mPD) (3410m3) | Wed Mar 16 08:00:00 IST 2016 | Fri Apr 08 18:00:00 IDT 2016 | Wed Mar 16 08:00:00 IST 2016 | Tue Apr 12 18:00:00 IDT 2016 |  | COMPLETED
1327 | TT_TASK | Removal strut S2 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 |  | COMPLETED
1328 | TT_TASK | Backfilling to 0.5m below S1 (+22.0mPD) (3410m3) | Fri Apr 15 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 | Fri Apr 15 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
1329 | TT_TASK | Removal strut S1 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 |  | COMPLETED
1330 | TT_TASK | Backfilling to original ground level (approx. +25.0mPD) (1860m3) | Thu May 05 08:00:00 IDT 2016 | Tue May 17 18:00:00 IDT 2016 | Thu May 05 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
1333 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1334 | TT_TASK | D-wall construction (2844m3) | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1335 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1337 | TT_TASK | Excavate up to +22.0mPD (3720m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1338 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 |  | COMPLETED
1339 | TT_TASK | Excavate up to +16.5mPD (4880m3) | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 |  | COMPLETED
1340 | TT_TASK | Install Strut S2 +17.0mPD | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 |  | COMPLETED
1341 | TT_TASK | Excavate up to +11.0mPD (6820m3) | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
1342 | TT_TASK | Install Strut S3 +11.5mPD | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 |  | COMPLETED
1343 | TT_TASK | Excavate up to +7.0mPD (4960m3) | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 |  | COMPLETED
1344 | TT_TASK | Install Strut S4 +7.5mPD | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1345 | TT_TASK | Excavate up to +3.5mPD (4340m3) | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1346 | TT_TASK | Install Strut S5 +4.0mPD | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 |  | COMPLETED
1347 | TT_TASK | Excavate up to formation (4960m3) | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 |  | COMPLETED
1348 | TT_TASK | Construct temp. 500mm thick plain concrete base slab at Bay 5 & 6 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1349 | TT_TASK | Excavation to formation and place blinding Bay 4a | Thu Oct 18 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1350 | TT_TASK | Excavation to formation and place blinding Bay 4b | Fri Jun 21 08:00:00 IDT 2013 | Fri Jul 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1351 | TT_TASK | Excavation to formation and place blinding Bay3 | Sat Jul 13 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1352 | TT_TASK | Excavation to formation and place blinding Bay2 to Bay1 | Wed Jul 24 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1356 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 |  | COMPLETED
1357 | TT_TASK | Erect external formwork for base slab | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 |  | COMPLETED
1358 | TT_TASK | Rebar fixing for base slab | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1359 | TT_TASK | Erect internal kicker formwork for base slab | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1360 | TT_TASK | Concreting for base slab (363m3) | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1361 | TT_TASK | Curing for base slab | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1362 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1363 | TT_TASK | Removal of formwork for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1364 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1365 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 27 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1366 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1367 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1368 | TT_TASK | Curing for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1369 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1370 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 10 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1371 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 19 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jan 24 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1372 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 08 08:00:00 IST 2015 | Tue Jan 13 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1374 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 |  | COMPLETED
1375 | TT_TASK | Erect external formwork for base slab | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1376 | TT_TASK | Rebar fixing for base slab | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1377 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 |  | COMPLETED
1378 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1379 | TT_TASK | Curing for base slab | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1380 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1381 | TT_TASK | Removal of formwork for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1382 | TT_TASK | Rebar fixing for central slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1383 | TT_TASK | Erect external formwork for central slab | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1384 | TT_TASK | Concreting for central slab (450m3) | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1385 | TT_TASK | Curing for central slab | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1386 | TT_TASK | Preparation of construction joint for central slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1387 | TT_TASK | Removal of formwork for central slab | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1388 | TT_TASK | Removal strut S5 and S4 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1389 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1390 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1391 | TT_TASK | Erect external formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1392 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1393 | TT_TASK | Curing for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1394 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1395 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 08 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1396 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1397 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Nov 19 08:00:00 IST 2015 | Tue Nov 24 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 |  | COMPLETED
1400 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1401 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1402 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1403 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1404 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1405 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1406 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1407 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1408 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1409 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1410 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 10 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1411 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1412 | TT_TASK | Curing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1413 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1414 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1415 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1416 | TT_TASK | Side walkway and cable bracket | Fri Jan 02 08:00:00 IST 2015 | Wed Jan 07 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1418 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1419 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1420 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1421 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1422 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1423 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1424 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1425 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1426 | TT_TASK | Rebar fixing for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1427 | TT_TASK | Erect external formwork for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1428 | TT_TASK | Concreting for central slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1429 | TT_TASK | Curing for central slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1430 | TT_TASK | Preparation of construction joint for central slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1431 | TT_TASK | Removal of formwork for central slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 21 18:00:00 IST 2012 |  | COMPLETED
1432 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1433 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1434 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1435 | TT_TASK | Erect external formwork for wall | Mon Jul 15 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1436 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1437 | TT_TASK | Curing for wall and roof | Sun Jul 21 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1438 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1439 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 22 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1440 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 31 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1441 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Sep 16 08:00:00 IDT 2015 | Mon Sep 21 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1443 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1444 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1445 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1446 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1447 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1448 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1449 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1450 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1451 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1452 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1453 | TT_TASK | Erect external formwork for wall | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1454 | TT_TASK | Concreting for wall and roof (444m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1455 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1456 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1457 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Sat Feb 09 18:00:00 IST 2013 |  | COMPLETED
1458 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Nov 09 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Tue Oct 06 08:00:00 IDT 2015 | Sat Oct 10 18:00:00 IDT 2015 |  | COMPLETED
1461 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1462 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1463 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1464 | TT_TASK | Erect internal kicker formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1465 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1466 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1467 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1468 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1469 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1470 | TT_TASK | Curing | Wed Jun 12 08:00:00 IDT 2013 | Wed Jun 12 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1471 | TT_TASK | Removal strut S5 and S4 | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1473 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1474 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1475 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1476 | TT_TASK | Concreting for wall and roof (450m3) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1477 | TT_TASK | Curing for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1478 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1479 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1480 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 29 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1481 | TT_TASK | Side walkway and cable bracket | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1483 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1484 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1485 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1486 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1487 | TT_TASK | Curing for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1488 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1489 | TT_TASK | Removal external wall formwork for wall | Wed Jun 26 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1490 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1491 | TT_TASK | Side walkway and cable bracket | Fri Sep 04 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
1494 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1495 | TT_TASK | Erect external formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1496 | TT_TASK | Rebar fixing for base slab | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1497 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1498 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 |  | COMPLETED
1499 | TT_TASK | Curing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1500 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1501 | TT_TASK | Removal of formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1502 | TT_TASK | Shear beam | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1503 | TT_TASK | Curing | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1504 | TT_TASK | Removal strut S5 and S4 | Wed Jun 19 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1506 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 24 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1507 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1508 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1509 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1510 | TT_TASK | Curing for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1511 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1512 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1513 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1514 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
1516 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1517 | TT_TASK | Rebar fixing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1518 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1519 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1520 | TT_TASK | Curing for wall and roof | Sun Jun 23 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1521 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1522 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 25 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1523 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 03 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1524 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Aug 29 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1527 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1528 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Sat Dec 22 18:00:00 IST 2012 |  | COMPLETED
1529 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1530 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1531 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1532 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1533 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1534 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Fri Jan 11 18:00:00 IST 2013 |  | COMPLETED
1535 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Jan 12 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1536 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1537 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1539 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1540 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1541 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1542 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1543 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1544 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1545 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1546 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1547 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 |  | COMPLETED
1549 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1550 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Mon Feb 25 18:00:00 IST 2013 |  | COMPLETED
1551 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1552 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1553 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1554 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1555 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1556 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1557 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Aug 24 08:00:00 IDT 2015 | Fri Aug 28 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1560 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1561 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1562 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1563 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1564 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1565 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1566 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1567 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1568 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1569 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1570 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1572 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1573 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1574 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1575 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1576 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1577 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1578 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1579 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1580 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
1582 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1583 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1584 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1585 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1586 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1587 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1588 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1589 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1590 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Aug 18 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1593 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1594 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1595 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1596 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1597 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1598 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1599 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1600 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1601 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1602 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1603 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1605 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 31 18:00:00 IDT 2013 |  | COMPLETED
1606 | TT_TASK | Rebar fixing for wall and roof | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 |  | COMPLETED
1607 | TT_TASK | Erect external formwork for wall and roof | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 | Fri Sep 06 08:00:00 IDT 2013 | Thu Sep 12 18:00:00 IDT 2013 |  | COMPLETED
1608 | TT_TASK | Concreting for wall and roof (450m3) | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 |  | COMPLETED
1609 | TT_TASK | Curing for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1610 | TT_TASK | Preparation of construction joint for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1611 | TT_TASK | Removal external and internal formwork for wall | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Wed Sep 25 18:00:00 IDT 2013 |  | COMPLETED
1612 | TT_TASK | Removal internal falsework and formwork for roof | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1613 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 08 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1615 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 20 18:00:00 IST 2013 |  | COMPLETED
1616 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1617 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1618 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1619 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1620 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1621 | TT_TASK | Removal external wall formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1622 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1623 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Aug 12 08:00:00 IDT 2015 | Mon Aug 17 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1626 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1627 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1628 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Feb 14 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1629 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1630 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Mon Feb 18 18:00:00 IST 2013 |  | COMPLETED
1631 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1632 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1633 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1634 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1635 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1636 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1638 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jul 12 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1639 | TT_TASK | Rebar fixing for wall and roof | Wed Jul 17 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1640 | TT_TASK | Erect external formwork for wall and roof | Wed Aug 14 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1641 | TT_TASK | Concreting for wall and roof (450m3) | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1642 | TT_TASK | Curing for wall and roof | Sun Aug 11 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1643 | TT_TASK | Preparation of construction joint for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1644 | TT_TASK | Removal external and internal formwork for wall | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1645 | TT_TASK | Removal internal falsework and formwork for roof | Wed Aug 21 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1646 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 03 08:00:00 IST 2014 | Fri Mar 07 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1648 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1649 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1650 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Apr 09 08:00:00 IDT 2013 | Thu Apr 11 18:00:00 IDT 2013 |  | COMPLETED
1651 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1652 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1653 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1654 | TT_TASK | Removal external wall formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1655 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
1656 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Aug 06 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Mon Jul 27 08:00:00 IDT 2015 | Fri Jul 31 18:00:00 IDT 2015 |  | COMPLETED
1658 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Sep 12 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1659 | TT_TASK | Rebar fixing for roof | Tue Sep 17 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1660 | TT_TASK | Erect external formwork for roof | Thu Sep 19 08:00:00 IDT 2013 | Thu Sep 19 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1661 | TT_TASK | Concreting for roof (444m3) | Sat Sep 21 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1662 | TT_TASK | Curing for roof | Sun Sep 22 08:00:00 IDT 2013 | Tue Oct 01 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1663 | TT_TASK | Preparation of construction joint for roof | Mon Sep 23 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1664 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1665 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1668 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1669 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1670 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1671 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1672 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1673 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1674 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1675 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1676 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1677 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1678 | TT_TASK | Removal strut S5 and S4 | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1680 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Thu Apr 25 18:00:00 IDT 2013 |  | COMPLETED
1681 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri May 03 08:00:00 IDT 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
1682 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Thu May 16 08:00:00 IDT 2013 | Thu May 23 18:00:00 IDT 2013 |  | COMPLETED
1683 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1684 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1685 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1686 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Wed May 29 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1687 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1688 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 19 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1690 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Fri Apr 19 18:00:00 IDT 2013 |  | COMPLETED
1691 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1692 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Apr 25 08:00:00 IDT 2013 | Sat Apr 27 18:00:00 IDT 2013 |  | COMPLETED
1693 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1694 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1695 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1696 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1697 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1698 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 02 08:00:00 IDT 2015 | Sat Apr 11 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Feb 27 18:00:00 IST 2015 |  | COMPLETED
1700 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1701 | TT_TASK | Rebar fixing for roof | Tue Aug 06 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1702 | TT_TASK | Erect external formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1703 | TT_TASK | Concreting for roof (444m3) | Fri Aug 09 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 |  | COMPLETED
1704 | TT_TASK | Curing for roof | Thu Aug 01 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1705 | TT_TASK | Preparation of construction joint for roof | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 |  | COMPLETED
1706 | TT_TASK | Removal internal falsework and formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1707 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 09 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1710 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Wed Feb 20 18:00:00 IST 2013 |  | COMPLETED
1711 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1712 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1713 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1714 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1715 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1716 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1717 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1718 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1719 | TT_TASK | Curing | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1720 | TT_TASK | Removal strut S5 and S4 | Mon Jun 24 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1722 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1723 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1724 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Wed Jul 10 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1725 | TT_TASK | Concreting for wall and roof (450m3) | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1726 | TT_TASK | Curing for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1727 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1728 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 |  | COMPLETED
1729 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 |  | COMPLETED
1730 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1732 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1733 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1734 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1735 | TT_TASK | Concreting for wall and roof (450m3) | Tue Sep 03 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1736 | TT_TASK | Curing for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1737 | TT_TASK | Preparation of construction joint for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 |  | COMPLETED
1738 | TT_TASK | Removal external and internal formwork for wall | Thu Sep 05 08:00:00 IDT 2013 | Fri Sep 06 18:00:00 IDT 2013 | Thu Aug 22 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1739 | TT_TASK | Removal internal falsework and formwork for roof | Sat Sep 14 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 |  | COMPLETED
1740 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 05 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1742 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1743 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1744 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1745 | TT_TASK | Concreting for roof (363m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1746 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Sun Oct 20 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1747 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1748 | TT_TASK | Removal internal falsework and formwork for roof | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1749 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Dec 24 13:00:00 IST 2013 | Thu Jan 02 12:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1752 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1753 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1754 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1755 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Apr 12 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1756 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1757 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1758 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1759 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1760 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1761 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1762 | TT_TASK | Removal strut S5 and S4 | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1764 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Aug 05 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1765 | TT_TASK | Rebar fixing for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1766 | TT_TASK | Erect external formwork for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1767 | TT_TASK | Concreting for wall and roof (450m3) | Thu Aug 15 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1768 | TT_TASK | Curing for wall and roof | Fri Aug 16 08:00:00 IDT 2013 | Sun Aug 25 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1769 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1770 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1771 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 |  | COMPLETED
1772 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Feb 04 08:00:00 IST 2014 | Sat Feb 08 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1774 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Aug 07 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1775 | TT_TASK | Rebar fixing for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1776 | TT_TASK | Erect external formwork for wall and roof | Thu Aug 15 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1777 | TT_TASK | Concreting for wall and roof (450m3) | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1778 | TT_TASK | Curing for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1779 | TT_TASK | Preparation of construction joint for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 |  | COMPLETED
1780 | TT_TASK | Removal external and internal formwork for wall | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Wed Aug 21 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 |  | COMPLETED
1781 | TT_TASK | Removal internal falsework and formwork for roof | Mon Sep 16 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1782 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Nov 19 08:00:00 IST 2014 | Mon Nov 24 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1784 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1785 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1786 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1787 | TT_TASK | Concreting for roof (450m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1788 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1789 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1790 | TT_TASK | Removal internal falsework and formwork for roof | Fri Oct 18 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1791 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 13 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1794 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1795 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1796 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1797 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1798 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 28 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1799 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1800 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1801 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1802 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1803 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1804 | TT_TASK | Removal strut S5 and S4 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1806 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1807 | TT_TASK | Rebar fixing for wall and roof | Sat Jul 20 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1808 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1809 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1810 | TT_TASK | Curing for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1811 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1812 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 29 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1813 | TT_TASK | Removal internal falsework and formwork for roof | Tue Aug 06 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1814 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 18:00:00 IST 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1816 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1817 | TT_TASK | Rebar fixing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1818 | TT_TASK | Erect external formwork for wall and roof | Fri Jul 19 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1819 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1820 | TT_TASK | Curing for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Thu Mar 28 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1821 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Mar 29 08:00:00 IDT 2013 | Fri Mar 29 18:00:00 IDT 2013 |  | COMPLETED
1822 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Sat Mar 30 08:00:00 IDT 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1823 | TT_TASK | Removal internal falsework and formwork for roof | Fri Aug 02 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Mon Apr 01 18:00:00 IDT 2013 |  | COMPLETED
1824 | TT_TASK | Side walkway and cable bracket | Thu Nov 13 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1826 | TT_TASK | Erect internal formwork & Falsework for roof | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1827 | TT_TASK | Rebar fixing for roof | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 |  | COMPLETED
1828 | TT_TASK | Erect shutter formwork for roof | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 09 18:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1829 | TT_TASK | Concreting for roof (450m3) | Tue Sep 10 08:00:00 IDT 2013 | Tue Sep 10 18:00:00 IDT 2013 | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 |  | COMPLETED
1830 | TT_TASK | Curing for roof | Wed Sep 11 08:00:00 IDT 2013 | Fri Sep 20 18:00:00 IDT 2013 | Tue Jul 23 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 |  | COMPLETED
1831 | TT_TASK | Preparation of construction joint for roof | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 11 18:00:00 IDT 2013 | Sat Aug 03 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1832 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 26 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 |  | COMPLETED
1833 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 06 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Aug 13 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1835 | TT_TASK | Water proofing and soil backfilling to 0.5m below top of Tunnel Bay 3 to Bay 1 | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1836 | TT_TASK | Mass infill between D-wall and tunnel wall | Fri Oct 11 08:00:00 IDT 2013 | Wed Oct 16 18:00:00 IDT 2013 | Fri Sep 20 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1837 | TT_TASK | Removal S3 and S2 | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
1838 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 4 | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Sat May 18 18:00:00 IDT 2013 |  | COMPLETED
1839 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 5 and remove S3 & S2 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1840 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 6 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1843 | TT_TASK | Pre-drilling and guidewall | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1844 | TT_TASK | D-wall design review | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1845 | TT_TASK | D-wall construction (4741m3) | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 |  | COMPLETED
1846 | TT_TASK | Shear pin and pumping test | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 15 18:00:00 IST 2012 | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1848 | TT_TASK | ELS works to formation level from SN16 to SN19 (soil: 8,700m3 @350m3/day, Install S1 to S3 strut 5 days/layer) | Wed Sep 25 08:00:00 IDT 2013 | Wed Nov 13 18:00:00 IST 2013 | Wed May 08 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1849 | TT_TASK | Design temporary bridge and approval | Mon Sep 01 08:00:00 IDT 2014 | Wed Nov 12 18:00:00 IST 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1850 | TT_TASK | Application of tree transplant | Sat Jun 01 08:00:00 IDT 2013 | Wed Oct 23 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1851 | TT_TASK | Tree transplant | Tue Oct 14 08:00:00 IDT 2014 | Mon Nov 10 18:00:00 IST 2014 | Tue Sep 02 08:00:00 IDT 2014 | Tue Sep 30 18:00:00 IDT 2014 |  | COMPLETED
1852 | TT_TASK | Erection temporary bridge deck | Fri Oct 03 08:00:00 IDT 2014 | Fri Dec 05 18:00:00 IST 2014 | Fri Oct 03 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1853 | TT_TASK | ELS works to formation level from SN10 to SN15 (soil: 9,455m3 @330m3/day, install S1 to S3 strut 5 days/layer) | Mon Nov 24 08:00:00 IST 2014 | Sat Jan 17 18:00:00 IST 2015 | Mon Nov 24 08:00:00 IST 2014 | Tue Jun 23 18:00:00 IDT 2015 |  | COMPLETED
1856 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
1857 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1858 | TT_TASK | Erect external formwork for wall and roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1859 | TT_TASK | Concreting for wall and roof (215m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
1860 | TT_TASK | Curing for wall and roof | Sun Dec 08 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
1861 | TT_TASK | Preparation of construction joint for wall and roof | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1862 | TT_TASK | Removal external and internal formwork for wall | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1863 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1864 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 03 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 | Mon Mar 24 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
1866 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 14 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1867 | TT_TASK | Rebar fixing for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1868 | TT_TASK | Erect external formwork for wall and roof | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1869 | TT_TASK | Concreting for wall and roof (215m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1870 | TT_TASK | Curing for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Sun Dec 29 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1871 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
1872 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 17 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
1873 | TT_TASK | Removal internal falsework and formwork for roof | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1874 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 |  | COMPLETED
1876 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 28 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Nov 28 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1877 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1878 | TT_TASK | Erect external formwork for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1879 | TT_TASK | Concreting for wall and roof (215m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1880 | TT_TASK | Curing for wall and roof | Wed Jan 01 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
1881 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
1882 | TT_TASK | Removal external and internal formwork for wall | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 |  | COMPLETED
1883 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
1884 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 |  | COMPLETED
1886 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1887 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 14 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1888 | TT_TASK | Erect external formwork for wall and roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1889 | TT_TASK | Concreting for wall and roof (215m3) | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1890 | TT_TASK | Curing for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1892 | TT_TASK | Removal external and internal formwork for wall | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1893 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1894 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 |  | COMPLETED
1896 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 08:00:00 IST 2013 |  | COMPLETED
1897 | TT_TASK | Rebar fixing for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1898 | TT_TASK | Erect external formwork for wall and roof | Fri Jan 03 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1899 | TT_TASK | Concreting for wall and roof (215m3) | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1900 | TT_TASK | Curing for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 16 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1901 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Tue Jan 07 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1902 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1903 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1904 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 |  | COMPLETED
1906 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1907 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1908 | TT_TASK | Erect external formwork for wall and roof | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1909 | TT_TASK | Concreting for wall and roof (215m3) | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1910 | TT_TASK | Curing for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1911 | TT_TASK | Preparation of construction joint for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1912 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1913 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1914 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 |  | COMPLETED
1916 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1917 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 |  | COMPLETED
1918 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Tue Jun 04 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 |  | COMPLETED
1919 | TT_TASK | Concreting for wall and roof (333m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1920 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1921 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Wed Jun 12 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1922 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 |  | COMPLETED
1923 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
1924 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 05 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Tue Mar 04 18:00:00 IST 2014 |  | COMPLETED
1926 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1927 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1928 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1929 | TT_TASK | Concreting for wall and roof (412m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1930 | TT_TASK | Curing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Sun Jun 23 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Sat Mar 23 18:00:00 IST 2013 |  | COMPLETED
1931 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Mar 25 08:00:00 IST 2013 | Mon Mar 25 18:00:00 IST 2013 |  | COMPLETED
1932 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Mar 26 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1933 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jun 24 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1934 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 27 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Mon Mar 03 18:00:00 IST 2014 |  | COMPLETED
1936 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1937 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1938 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Apr 02 18:00:00 IDT 2013 |  | COMPLETED
1939 | TT_TASK | Concreting for wall and roof (320m3) | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Apr 05 08:00:00 IDT 2013 | Fri Apr 05 18:00:00 IDT 2013 |  | COMPLETED
1940 | TT_TASK | Curing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 06 08:00:00 IDT 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1941 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1942 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1943 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1944 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jan 21 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Sat Mar 01 18:00:00 IST 2014 |  | COMPLETED
1946 | TT_TASK | Excavation and saw cut D-wall | Thu Apr 02 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Sat Jul 25 18:00:00 IDT 2015 |  | COMPLETED
1947 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Aug 08 16:24:00 IDT 2015 | Mon Aug 10 16:24:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Mon Jul 13 18:00:00 IDT 2015 |  | COMPLETED
1948 | TT_TASK | Erect external formwork for base slab | Mon Aug 10 16:24:00 IDT 2015 | Wed Aug 12 16:24:00 IDT 2015 | Tue Jul 14 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
1949 | TT_TASK | Rebar fixing for base slab | Wed Aug 12 16:24:00 IDT 2015 | Fri Aug 14 16:24:00 IDT 2015 | Wed Jul 15 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1950 | TT_TASK | Erect internal kicker formwork for base slab | Fri Aug 14 16:24:00 IDT 2015 | Mon Aug 17 16:24:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Wed Aug 12 18:00:00 IDT 2015 |  | COMPLETED
1951 | TT_TASK | Concreting for base slab (90m3) | Wed Sep 02 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 | Thu Aug 13 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 |  | COMPLETED
1952 | TT_TASK | Curing for base slab | Thu Sep 03 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Fri Aug 14 08:00:00 IDT 2015 | Thu Aug 20 18:00:00 IDT 2015 |  | COMPLETED
1953 | TT_TASK | Preparation of construction joint for base slab | Thu Sep 03 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Fri Aug 21 08:00:00 IDT 2015 | Fri Aug 21 18:00:00 IDT 2015 |  | COMPLETED
1954 | TT_TASK | Removal of formwork for base slab | Fri Sep 04 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Sat Aug 22 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 |  | COMPLETED
1955 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Sep 05 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 | Mon Aug 24 08:00:00 IDT 2015 | Mon Aug 24 18:00:00 IDT 2015 |  | COMPLETED
1956 | TT_TASK | Curing | Thu Sep 10 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Tue Aug 25 08:00:00 IDT 2015 | Tue Aug 25 18:00:00 IDT 2015 |  | COMPLETED
1957 | TT_TASK | Removal strut S3 | Sat Sep 19 08:00:00 IDT 2015 | Wed Sep 23 18:00:00 IDT 2015 | Wed Sep 16 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
1958 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Sep 24 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
1959 | TT_TASK | Rebar fixing for wall and roof | Wed Sep 30 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 | Fri Sep 25 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 |  | COMPLETED
1960 | TT_TASK | Erect external formwork for wall and roof | Thu Oct 15 08:00:00 IDT 2015 | Fri Oct 16 18:00:00 IDT 2015 | Mon Oct 05 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
1961 | TT_TASK | Concreting for wall and roof (260m3) | Sat Oct 17 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 | Wed Oct 07 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1962 | TT_TASK | Curing for wall and roof | Sun Oct 18 08:00:00 IDT 2015 | Tue Oct 27 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 |  | COMPLETED
1963 | TT_TASK | Preparation of construction joint for wall and roof | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
1964 | TT_TASK | Removal external and internal formwork for wall | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
1965 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 28 08:00:00 IST 2015 | Thu Oct 29 18:00:00 IST 2015 | Thu Oct 22 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1966 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Oct 30 08:00:00 IST 2015 | Wed Nov 04 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1968 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 02 18:00:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 |  | COMPLETED
1969 | TT_TASK | Erect external formwork for base slab | Fri Jul 03 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Tue Jul 21 08:00:00 IDT 2015 | Wed Jul 22 18:00:00 IDT 2015 |  | COMPLETED
1970 | TT_TASK | Rebar fixing for base slab | Mon Jul 06 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 23 08:00:00 IDT 2015 | Fri Jul 24 18:00:00 IDT 2015 |  | COMPLETED
1971 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jul 08 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Sat Jul 25 08:00:00 IDT 2015 | Mon Jul 27 18:00:00 IDT 2015 |  | COMPLETED
1972 | TT_TASK | Concreting for base slab (123m3) | Fri Jul 10 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jul 28 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 |  | COMPLETED
1973 | TT_TASK | Curing for base slab | Sat Jul 11 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1974 | TT_TASK | Preparation of construction joint for base slab | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 |  | COMPLETED
1975 | TT_TASK | Removal of formwork for base slab | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 |  | COMPLETED
1976 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1977 | TT_TASK | Curing | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 |  | COMPLETED
1978 | TT_TASK | Removal strut S3 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1979 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 |  | COMPLETED
1980 | TT_TASK | Rebar fixing for wall and roof | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 |  | COMPLETED
1981 | TT_TASK | Erect external formwork for wall and roof | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 |  | COMPLETED
1982 | TT_TASK | Concreting for wall and roof (260m3) | Fri Oct 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 | Sat Oct 24 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
1983 | TT_TASK | Curing for wall and roof | Sat Oct 03 08:00:00 IDT 2015 | Mon Oct 12 18:00:00 IDT 2015 | Mon Oct 26 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1984 | TT_TASK | Preparation of construction joint for wall and roof | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
1985 | TT_TASK | Removal external and internal formwork for wall | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1986 | TT_TASK | Removal internal falsework and formwork for roof | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1987 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1989 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
1990 | TT_TASK | Erect external formwork for base slab | Mon Jun 15 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1991 | TT_TASK | Rebar fixing for base slab | Wed Jun 17 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
1992 | TT_TASK | Erect internal kicker formwork for base slab | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
1993 | TT_TASK | Concreting for base slab (127m3) | Tue Jun 23 08:00:00 IDT 2015 | Tue Jun 23 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
1994 | TT_TASK | Curing for base slab | Wed Jun 24 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
1995 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 24 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1996 | TT_TASK | Removal of formwork for base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
1997 | TT_TASK | Infill concrete in between D-wall and base slab | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1998 | TT_TASK | Curing | Thu May 28 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1999 | TT_TASK | Removal strut S3 | Fri May 29 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2000 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 03 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2001 | TT_TASK | Rebar fixing for wall and roof | Mon Jun 08 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2002 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2003 | TT_TASK | Concreting for wall and roof (260m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2004 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2005 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2006 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2007 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2008 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 11 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2010 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
2011 | TT_TASK | Erect external formwork for base slab | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
2012 | TT_TASK | Rebar fixing for base slab | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
2013 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
2014 | TT_TASK | Concreting for base slab (127m3) | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
2015 | TT_TASK | Curing for base slab | Thu Jun 11 08:00:00 IDT 2015 | Wed Jun 17 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2016 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 11 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
2017 | TT_TASK | Removal of formwork for base slab | Sat May 23 08:00:00 IDT 2015 | Sat May 23 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
2018 | TT_TASK | Infill concrete in between D-wall and base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
2019 | TT_TASK | Curing | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2020 | TT_TASK | Removal strut S3 | Thu May 28 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2021 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2022 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2023 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2024 | TT_TASK | Concreting for wall and roof (150m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2025 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2026 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2027 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2028 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2029 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jul 06 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
2031 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2032 | TT_TASK | Erect external formwork for base slab | Thu May 21 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2033 | TT_TASK | Rebar fixing for base slab | Sat May 23 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2034 | TT_TASK | Erect internal kicker formwork for base slab | Wed May 27 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2035 | TT_TASK | Concreting for base slab (70m3) | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2036 | TT_TASK | Curing for base slab | Sat May 30 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2037 | TT_TASK | Preparation of construction joint for base slab | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2038 | TT_TASK | Removal of formwork for base slab | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2039 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2040 | TT_TASK | Curing | Sat Jun 06 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2041 | TT_TASK | Removal strut S3 | Mon Jun 08 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat May 23 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2043 | TT_TASK | Rebar fixing for wall and roof | Fri May 29 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2044 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2045 | TT_TASK | Concreting for wall and roof (175m3) | Thu Jun 04 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2046 | TT_TASK | Curing for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sun Jun 14 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2047 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2048 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 03 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 04 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2050 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 29 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
2052 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2053 | TT_TASK | Erect external formwork for base slab | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2054 | TT_TASK | Rebar fixing for base slab | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2055 | TT_TASK | Erect internal kicker formwork for base slab | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2056 | TT_TASK | Concreting for base slab (70m3) | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2057 | TT_TASK | Curing for base slab | Wed Apr 22 08:00:00 IDT 2015 | Tue Apr 28 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2058 | TT_TASK | Preparation of construction joint for base slab | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2059 | TT_TASK | Removal of formwork for base slab | Thu Apr 23 08:00:00 IDT 2015 | Thu Apr 23 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2060 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Apr 24 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2061 | TT_TASK | Curing | Wed Apr 29 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2062 | TT_TASK | Removal strut S3 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2063 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed May 06 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2064 | TT_TASK | Rebar fixing for wall and roof | Thu May 14 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2065 | TT_TASK | Erect external formwork for wall and roof | Mon May 18 08:00:00 IDT 2015 | Tue May 19 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2066 | TT_TASK | Concreting for wall and roof (175m3) | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2067 | TT_TASK | Curing for wall and roof | Thu May 21 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2068 | TT_TASK | Preparation of construction joint for wall and roof | Thu May 21 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2069 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2070 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2071 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jun 23 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
2073 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Fri Nov 15 18:00:00 IST 2013 |  | COMPLETED
2074 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Nov 16 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2075 | TT_TASK | Rebar fixing for base slab | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
2076 | TT_TASK | Erect internal kicker formwork for base slab | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
2077 | TT_TASK | Concreting for base slab (70m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
2078 | TT_TASK | Curing for base slab | Fri Dec 20 08:00:00 IST 2013 | Thu Dec 26 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
2079 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 |  | COMPLETED
2080 | TT_TASK | Removal of formwork for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
2081 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
2082 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2083 | TT_TASK | Removal strut S3 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2084 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Apr 16 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2085 | TT_TASK | Rebar fixing for wall and roof | Thu Apr 24 08:00:00 IDT 2014 | Sat Apr 26 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 |  | COMPLETED
2086 | TT_TASK | Erect external formwork for wall and roof | Mon Apr 28 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Thu Apr 10 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2087 | TT_TASK | Concreting for wall and roof (170m3) | Wed Apr 30 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Sat Apr 12 08:00:00 IDT 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
2088 | TT_TASK | Curing for wall and roof | Thu May 01 08:00:00 IDT 2014 | Sat May 10 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Tue Apr 22 18:00:00 IDT 2014 |  | COMPLETED
2089 | TT_TASK | Preparation of construction joint for wall and roof | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 |  | COMPLETED
2090 | TT_TASK | Removal external and internal formwork for wall | Sat May 03 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Tue Apr 15 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
2091 | TT_TASK | Removal internal falsework and formwork for roof | Mon May 12 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 |  | COMPLETED
2092 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jun 05 08:00:00 IDT 2014 | Tue Jun 10 18:00:00 IDT 2014 | Thu May 29 08:00:00 IDT 2014 | Thu Dec 04 18:00:00 IST 2014 |  | COMPLETED
2094 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2095 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2096 | TT_TASK | Rebar fixing for base slab | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2097 | TT_TASK | Erect internal kicker formwork for base slab | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2098 | TT_TASK | Concreting for base slab (70m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2099 | TT_TASK | Curing for base slab | Sun Dec 08 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2100 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2101 | TT_TASK | Removal of formwork for base slab | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
2102 | TT_TASK | Infill concrete in between D-wall and base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
2103 | TT_TASK | Curing | Sun Dec 15 08:00:00 IST 2013 | Sun Dec 15 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2104 | TT_TASK | Removal strut S3 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2105 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Feb 12 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2106 | TT_TASK | Rebar fixing for wall and roof | Mon Feb 17 08:00:00 IST 2014 | Wed Feb 19 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
2107 | TT_TASK | Erect external formwork for wall and roof | Fri Feb 28 13:48:00 IST 2014 | Mon Mar 03 13:48:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2108 | TT_TASK | Concreting for wall and roof (200m3) | Mon Mar 03 13:48:00 IST 2014 | Tue Mar 04 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2109 | TT_TASK | Curing for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Fri Mar 14 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2110 | TT_TASK | Preparation of construction joint for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Wed Mar 05 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2111 | TT_TASK | Removal external and internal formwork for wall | Wed Mar 05 13:48:00 IST 2014 | Thu Mar 06 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
2112 | TT_TASK | Removal internal falsework and formwork for roof | Fri Mar 14 13:48:00 IST 2014 | Mon Mar 17 13:48:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2113 | TT_TASK | Side walkway and cable bracket (204m3) | Thu May 29 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Wed Dec 03 18:00:00 IST 2014 |  | COMPLETED
2115 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2116 | TT_TASK | Erect external formwork for base slab | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2117 | TT_TASK | Rebar fixing for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2118 | TT_TASK | Erect internal kicker formwork for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2119 | TT_TASK | Concreting for base slab (70m3) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2120 | TT_TASK | Curing for base slab | Tue Dec 03 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2121 | TT_TASK | Preparation of construction joint for base slab | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
2122 | TT_TASK | Removal of formwork for base slab | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2123 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2124 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2125 | TT_TASK | Removal strut S3 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
2126 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jan 25 08:00:00 IST 2014 | Wed Jan 29 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
2127 | TT_TASK | Rebar fixing for wall and roof | Thu Jan 30 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Fri Dec 20 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
2128 | TT_TASK | Erect external formwork for wall and roof | Thu Feb 20 08:00:00 IST 2014 | Fri Feb 21 18:00:00 IST 2014 | Thu Jan 09 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2129 | TT_TASK | Concreting for wall and roof (200m3) | Sat Feb 22 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2130 | TT_TASK | Curing for wall and roof | Sun Feb 23 08:00:00 IST 2014 | Tue Mar 04 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2131 | TT_TASK | Preparation of construction joint for wall and roof | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Tue Jan 14 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2132 | TT_TASK | Removal external and internal formwork for wall | Tue Feb 25 08:00:00 IST 2014 | Tue Feb 25 18:00:00 IST 2014 | Wed Jan 15 08:00:00 IST 2014 | Wed Jan 15 18:00:00 IST 2014 |  | COMPLETED
2133 | TT_TASK | Removal internal falsework and formwork for roof | Wed Mar 05 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2134 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
2137 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Sep 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
2138 | TT_TASK | Erect external formwork for base slab | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Sep 21 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
2139 | TT_TASK | Rebar fixing for base slab | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
2140 | TT_TASK | Erect internal kicker formwork for base slab | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
2141 | TT_TASK | Staircase construction (+12.0mPD to +14.706mPD) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2142 | TT_TASK | Concreting for base slab (30m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
2143 | TT_TASK | Curing for base slab | Fri Dec 13 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
2144 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
2145 | TT_TASK | Removal of formwork for base slab | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 18:00:00 IDT 2013 |  | COMPLETED
2146 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2147 | TT_TASK | Mass concrete at level +12.0mPD | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 |  | COMPLETED
2148 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2149 | TT_TASK | Removal strut S3 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2150 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 17 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Mon Dec 01 18:00:00 IST 2014 |  | COMPLETED
2152 | TT_TASK | Erect working platform to +21.0mPD | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2153 | TT_TASK | Rebar fixing for wall and roof | Sat Jan 11 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2154 | TT_TASK | Staircase construction (+14.706mPD to +16.956mPD) (20m3) | Fri May 02 08:00:00 IDT 2014 | Wed May 07 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2155 | TT_TASK | Staircase construction (+16.956mPD to +19.206mPD) (20m3) | Thu Jun 05 08:00:00 IDT 2014 | Mon Jun 09 18:00:00 IDT 2014 | Thu Jun 12 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2156 | TT_TASK | Staircase construction (+19.206mPD to +21.456mPD) (20m3) | Tue Jun 10 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Fri Jun 20 18:00:00 IDT 2014 |  | COMPLETED
2157 | TT_TASK | Erect external formwork for wall and roof | Sat Mar 15 08:00:00 IST 2014 | Mon Mar 17 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2158 | TT_TASK | Concreting for wall and roof (31m3) | Tue Feb 04 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2159 | TT_TASK | Curing for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 |  | COMPLETED
2160 | TT_TASK | Preparation of construction joint for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2161 | TT_TASK | Removal external and internal formwork for wall | Thu Feb 06 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2162 | TT_TASK | Removal internal falsework and formwork for roof | Sat Feb 15 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Thu Jan 23 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2164 | TT_TASK | Removal strut S2 @ SN 19 | Wed Apr 02 08:00:00 IDT 2014 | Mon Apr 07 18:00:00 IDT 2014 | Mon Mar 03 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 |  | COMPLETED
2165 | TT_TASK | Erect working platform to +24.0mPD | Tue Apr 08 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 | Fri Mar 07 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 |  | COMPLETED
2166 | TT_TASK | Erect internal formwork below strut S1 | Sat Apr 12 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 | Wed Mar 12 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 |  | COMPLETED
2167 | TT_TASK | Staircase construction (+21.456mPD to +23.706mPD) (20m3) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 |  | COMPLETED
2168 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 | Fri Mar 14 08:00:00 IST 2014 | Tue Apr 01 18:00:00 IDT 2014 |  | COMPLETED
2169 | TT_TASK | Erect external wall & internal wall formwork | Tue May 13 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Wed Apr 02 08:00:00 IDT 2014 | Thu Apr 03 18:00:00 IDT 2014 |  | COMPLETED
2170 | TT_TASK | Concreting (External Wall & Internal Wall) (264m3) | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Fri Apr 04 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2171 | TT_TASK | Curing (External Wall & Internal Wall) | Fri May 16 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2172 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Mon May 19 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Thu Apr 10 18:00:00 IDT 2014 |  | COMPLETED
2173 | TT_TASK | Waterproofing | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 |  | COMPLETED
2174 | TT_TASK | Backfilling | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2176 | TT_TASK | Removal strut S1 @ SN 19 | Thu Jun 19 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2177 | TT_TASK | Erect working platform to +30.406mPD | Tue Jun 24 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2178 | TT_TASK | Erect internal formwork | Sat Jun 28 08:00:00 IDT 2014 | Sat Jun 28 18:00:00 IDT 2014 | Wed Jun 04 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2179 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Mon Jun 30 08:00:00 IDT 2014 | Wed Jul 02 18:00:00 IDT 2014 | Thu Jun 05 08:00:00 IDT 2014 | Fri Jun 06 18:00:00 IDT 2014 |  | COMPLETED
2180 | TT_TASK | Erect external formwork (External Wall & Internal Wall) | Thu Jul 03 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2181 | TT_TASK | Concreting (External Wall & Internal Wall) (128m3) | Fri Jul 04 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2182 | TT_TASK | Curing (External Wall & Internal Wall) | Sat Jul 05 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 18:00:00 IDT 2014 |  | COMPLETED
2183 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Tue Jul 08 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2184 | TT_TASK | Waterproofing | Wed Jul 09 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Thu Jun 19 18:00:00 IDT 2014 |  | COMPLETED
2185 | TT_TASK | Backfilling | Sat Jul 12 08:00:00 IDT 2014 | Wed Jul 16 18:00:00 IDT 2014 | Fri Jun 20 08:00:00 IDT 2014 | Tue Jun 24 18:00:00 IDT 2014 |  | COMPLETED
2186 | TT_TASK | Erect falsework and soffit formwork +30.206mPD | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 | Wed Jun 25 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2187 | TT_TASK | Staircase construction (+21.456mPD to +25.956mPD) (20m3) | Sat Jul 19 08:00:00 IDT 2014 | Wed Jul 23 18:00:00 IDT 2014 | Fri Jun 27 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2188 | TT_TASK | Staircase construction (+25.956mPD to +27.606mPD) (20m3) | Sat Jul 05 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 05 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 |  | COMPLETED
2189 | TT_TASK | Rebar fixing (Beam, Floor Slab and Staircase) | Thu Jul 10 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Thu Jul 10 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2190 | TT_TASK | Concreting (Beam, Floor Slab and Staircase) (31m3) | Fri Jul 11 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2191 | TT_TASK | Curing (Beam, Floor Slab and Staircase) | Wed Sep 03 08:00:00 IDT 2014 | Tue Sep 09 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2193 | TT_TASK | Erect working platform to +33.576mPD | Wed Sep 03 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
2194 | TT_TASK | Erect external formwork (External Wall) | Mon Sep 08 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 | Fri Sep 26 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2195 | TT_TASK | Rebar fixing (External Wall) | Thu Sep 11 08:00:00 IDT 2014 | Fri Sep 12 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2196 | TT_TASK | Erect internal formwork (External Wall) | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 |  | COMPLETED
2197 | TT_TASK | Concreting (External Wall) (49m3) | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 |  | COMPLETED
2198 | TT_TASK | Curing (External Wall) | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 |  | COMPLETED
2199 | TT_TASK | Removal formwork (External Wall) | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
2200 | TT_TASK | Erect falsework and soffit formwork +32.656 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2201 | TT_TASK | Rebar fixing (Beam & Floor Slab) | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 |  | COMPLETED
2202 | TT_TASK | Concreting (Beam & Floor Slab) (31m3) | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 |  | COMPLETED
2203 | TT_TASK | Curing (Beam & Floor Slab) | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2205 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
2206 | TT_TASK | Rebar fixing (Roof Parapet Wall) | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 |  | COMPLETED
2207 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2208 | TT_TASK | Concreting (Roof Parapet Wall) (30m3) | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
2209 | TT_TASK | Curing (Roof Parapet Wall) | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 |  | COMPLETED
2210 | TT_TASK | Removal formwork (Roof Parapet Wall) | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2211 | TT_TASK | Removal of falsework and soffit formwork | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
2213 | TT_TASK | Wet trade work | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 |  | COMPLETED
2214 | TT_TASK | Metal works (Louver, Door, Cat-ladder, Architectural Fins, Handrail, Roof Sliding Hatch and Balustrade, etc) | Thu Nov 27 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Thu Nov 27 08:00:00 IST 2014 | Thu Mar 05 18:00:00 IST 2015 |  | COMPLETED
2215 | TT_TASK | Coat works | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2218 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Nov 29 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Feb 04 18:00:00 IST 2014 |  | COMPLETED
2219 | TT_TASK | Backfilling between D-wall and 0.5m below S1 14,240m3 soil | Thu Feb 06 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 | Wed Feb 05 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 |  | COMPLETED
2220 | TT_TASK | Removal of S1 | Wed Mar 12 08:00:00 IST 2014 | Tue Mar 25 18:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 |  | COMPLETED
2221 | TT_TASK | Backfilling to original ground level 21,390m3 (approx. +25.0mPD) | Sat Mar 01 08:00:00 IST 2014 | Wed Mar 19 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Sat May 03 18:00:00 IDT 2014 |  | COMPLETED
2223 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 |  | COMPLETED
2224 | TT_TASK | Backfilling between D-wall and 0.5m below S1 (2075m3) | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 |  | COMPLETED
2225 | TT_TASK | Removal of S1 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 |  | COMPLETED
2226 | TT_TASK | Backfilling to original ground level 3,900m3 (approx. +25.0mPD) (1353m3) | Sat Mar 01 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
2227 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
2228 | TT_TASK | Backfilling backfilling to +20mPD from SN8 to SN9 (Soil: 7,050m3 @ 500m3/day) | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 |  | COMPLETED
2229 | TT_TASK | Removal of S1 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
2230 | TT_TASK | Construction of mud pit | Sat Jul 06 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
2231 | TT_TASK | Backfilling from +20mPD to ground level from SN8 to SN9 (Soil: 5,000m3 @ 500m3/day) | Tue Aug 06 08:00:00 IDT 2013 | Sat Aug 17 18:00:00 IDT 2013 | Tue Jul 02 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 |  | COMPLETED
2233 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Aug 07 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2234 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) | Fri Aug 14 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2235 | TT_TASK | Placing mass concrete infill between tunnel and D-wall | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 02 18:00:00 IST 2015 | Thu Dec 24 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2236 | TT_TASK | Removal of S2 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 10 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 04 18:00:00 IST 2016 |  | COMPLETED
2237 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2238 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
2239 | TT_TASK | Removal strut S1 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2240 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
2241 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488 m3 of soil) | Mon Jan 25 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Fri Apr 01 18:00:00 IDT 2016 |  | COMPLETED
2243 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) (SN18-19) | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 |  | COMPLETED
2244 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) (SN18-19) | Sat Apr 26 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Sat Apr 26 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
2245 | TT_TASK | Placing mass concrete infill between tunnel and D-wall (SN18-19) | Tue May 20 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri May 16 18:00:00 IDT 2014 |  | COMPLETED
2246 | TT_TASK | Removal of S2 (SN16-18) | Wed Jun 04 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 |  | COMPLETED
2247 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) (SN16-18) | Mon Jun 09 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Tue May 27 18:00:00 IDT 2014 |  | COMPLETED
2248 | TT_TASK | Removal strut S1 (SN16-18) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Wed May 28 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
2249 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488m3 of soil) | Fri Jun 27 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
2251 | TT_TASK | Dismantling temporary bridge deck | Mon Jun 15 08:00:00 IDT 2015 | Tue Jul 21 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2252 | TT_TASK | Reinstatement of Works Area 4.10 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jan 11 18:00:00 IST 2017 | Mon May 02 08:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 |  | COMPLETED
2253 | TT_TASK | Complete all tree planting and reinstate Works Area 4.12C | Tue Nov 01 08:00:00 IST 2016 | Thu Jul 13 18:00:00 IDT 2017 | Sat Oct 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2254 | TT_TASK | Reinstate Works Areas 4.9, 4.9A and 4.12A prior to handover | Mon May 22 08:00:00 IDT 2017 | Sat Sep 02 18:00:00 IDT 2017 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2258 | TT_TASK | Application of power supply, environmental permits and construction substation | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2259 | TT_TASK | Procurement and Confirmation of the order of 2nd tunnel boring machine | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2260 | TT_TASK | TBM design and submission for approval | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2261 | TT_TASK | TBM materials order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
2262 | TT_TASK | TBM equipments order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 |  | COMPLETED
2263 | TT_TASK | TBM Fabrication | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
2264 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 |  | COMPLETED
2265 | TT_TASK | TBM test Run | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2266 | TT_TASK | TBM disassembly and packing for shipping to HK | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 |  | COMPLETED
2267 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
2268 | TT_TASK | Setup TBM facilities | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
2269 | TT_TASK | Fabrication 50% of South Tunnel South Bound Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
2270 | TT_TASK | Fabrication 100% of South Tunnel South Bound Precast Lining | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
2271 | TT_TASK | Fabrication 50% of South Tunnel North Bound Precast Lining | Wed Oct 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 | Wed Oct 03 08:00:00 IST 2012 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
2272 | TT_TASK | Fabrication 100% of South Tunnel North Bound Precast Lining | Mon Aug 26 08:00:00 IDT 2013 | Wed Jan 22 18:00:00 IST 2014 | Wed Feb 27 08:00:00 IST 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
2274 | TT_TASK | Ground treatment at lauching shaft Southbound | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
2275 | TT_TASK | TBM assemble, thrust frame, testing and commissioning | Sat Jun 01 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2276 | TT_TASK | Lowing back-up plant for final drive | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
2277 | TT_TASK | Assemble and set up back-up plant for final drive | Sat Jun 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2278 | TT_TASK | Erection of noise enclosure | Sat Jul 20 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 |  | COMPLETED
2279 | TT_TASK | TBM drive & lining installation CH124+912 to CH125+012 (Initial Drive) | Sat Jul 20 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Mon Mar 11 00:00:00 IST 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
2280 | TT_TASK | TBM drive & lining installation CH125+012 to CH125+338 | Tue Oct 15 08:00:00 IDT 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon May 27 08:00:00 IDT 2013 | Tue May 20 00:00:00 IDT 2014 |  | COMPLETED
2281 | TT_TASK | Dis-assemble TBM | Fri May 23 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 |  | COMPLETED
2282 | TT_TASK | Invert slab and side walkway | Fri Aug 01 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Tue Sep 02 18:00:00 IDT 2014 |  | COMPLETED
2283 | TT_TASK | Installation of cable bracket | Mon Nov 03 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 | Mon Aug 18 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2285 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Sep 01 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 | Sat Aug 09 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2286 | TT_TASK | Ground treatment at lauching shaft Northbound | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 19 18:00:00 IST 2013 | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
2287 | TT_TASK | TBM assemble, testing and commissioning | Wed Jul 02 08:00:00 IDT 2014 | Wed Sep 03 18:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2288 | TT_TASK | Setup back-up plant for final drive | Tue Jun 03 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2289 | TT_TASK | Reinstate of noise enclosure | Fri Oct 10 08:00:00 IDT 2014 | Wed Nov 05 18:00:00 IST 2014 | Tue Oct 28 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
2290 | TT_TASK | TBM drive & lining installation CH124+927 to CH125+027 (Initial Drive) | Fri Oct 10 08:00:00 IDT 2014 | Thu Nov 13 18:00:00 IST 2014 | Thu Oct 30 00:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
2291 | TT_TASK | TBM drive & lining installation CH125+027 to CH125+353 (Final Drive) | Fri Jan 02 08:00:00 IST 2015 | Thu Feb 12 18:00:00 IST 2015 | Mon Dec 08 08:00:00 IST 2014 | Fri Aug 07 00:00:00 IDT 2015 |  | COMPLETED
2292 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Tue Aug 04 08:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
2293 | TT_TASK | Dis-assemble TBM | Tue Aug 04 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
2294 | TT_TASK | Invert slab and side walkway | Wed Sep 09 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
2295 | TT_TASK | Installation of cable bracket | Thu Sep 24 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Aug 31 18:00:00 IDT 2015 |  | COMPLETED
2298 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Partial length) at down track | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 |  | COMPLETED
2299 | TT_TASK | Probe/Grout | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 | Mon Aug 11 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2300 | TT_TASK | Coring of Segment | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 |  | COMPLETED
2301 | TT_TASK | Removal of segment | Tue Sep 02 08:00:00 IDT 2014 | Thu Sep 04 18:00:00 IDT 2014 | Thu Aug 21 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2302 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Sep 05 08:00:00 IDT 2014 | Tue Oct 07 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2303 | TT_TASK | Invert Concrete | Thu Oct 23 08:00:00 IDT 2014 | Sat Nov 01 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2304 | TT_TASK | Wall and Roof concrete | Mon Nov 03 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Mon Oct 13 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
2305 | TT_TASK | Dismantle Temporary frame | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2306 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
2307 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Remaining length ) at down track | Sat May 09 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Thu Apr 16 18:00:00 IDT 2015 |  | COMPLETED
2308 | TT_TASK | Probe/Grout | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
2309 | TT_TASK | Coring of Segment | Fri Oct 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 | Fri Oct 16 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
2310 | TT_TASK | Removal of segment | Wed Oct 07 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
2311 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Oct 10 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Oct 26 08:00:00 IST 2015 | Fri Dec 11 18:00:00 IST 2015 |  | COMPLETED
2312 | TT_TASK | Invert Concrete | Thu Dec 03 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Sat Dec 12 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2313 | TT_TASK | Wall and Roof concrete | Mon Dec 14 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 15 18:00:00 IST 2016 |  | COMPLETED
2314 | TT_TASK | Dismantle Temporary frame | Wed Jan 13 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 |  | COMPLETED
2315 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2318 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 |  | COMPLETED
2319 | TT_TASK | Pre-drill and guide wall | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 |  | COMPLETED
2320 | TT_TASK | D-wall design review | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 |  | COMPLETED
2321 | TT_TASK | D-Wall Construction (1075m3) | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 |  | COMPLETED
2322 | TT_TASK | Shear pin, toe grout and pumping test | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 |  | COMPLETED
2324 | TT_TASK | SI for TBM ground treatment | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2325 | TT_TASK | Design review of TBM ground treatment | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2326 | TT_TASK | Ground treatment for TBM southbound | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
2327 | TT_TASK | Ground treatment for TBM northbound | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2329 | TT_TASK | Capping beam construction | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2330 | TT_TASK | L-Shape wall construction | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
2331 | TT_TASK | Excavate up to +28.5mPD (1488m3) | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 |  | COMPLETED
2332 | TT_TASK | Install Strut S1 +29.0mPD | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 |  | COMPLETED
2333 | TT_TASK | Excavate up to +23.5mPD (2480m3) | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 |  | COMPLETED
2334 | TT_TASK | Install Strut S2 +24.0mPD | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 |  | COMPLETED
2335 | TT_TASK | Excavate up to +19.5mPD (1984m3) | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
2336 | TT_TASK | Install Strut S3 +20.0mPD | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 |  | COMPLETED
2337 | TT_TASK | Excavate up to +15.5mPD (1984m3) | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
2338 | TT_TASK | Install Strut S4 +16.0mPD | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 |  | COMPLETED
2339 | TT_TASK | Excavate up to formation (4117m3) | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
2340 | TT_TASK | Install rock dowel and tie back | Sat Jun 02 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Sat Jun 02 08:00:00 IDT 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2341 | TT_TASK | Temporary handover the shaft to contract 822 | Mon Jun 03 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2343 | TT_TASK | Rock breaking works | Mon Aug 26 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
2344 | TT_TASK | Temporary base Slab for TBM Drive | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
2347 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2348 | TT_TASK | Erect external formwork (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Wed Aug 13 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Tue Aug 19 18:00:00 IDT 2014 |  | COMPLETED
2349 | TT_TASK | Rebar fixing (Base Slab) | Thu Aug 14 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Wed Aug 20 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2350 | TT_TASK | Erect internal kicker formwork (Base Slab) | Tue Aug 19 08:00:00 IDT 2014 | Thu Aug 21 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 |  | COMPLETED
2351 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 22 08:00:00 IDT 2014 | Fri Aug 22 18:00:00 IDT 2014 | Thu Aug 28 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2352 | TT_TASK | Concreting (Base Slab) (245m3) | Sat Aug 23 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014 | Fri Aug 29 18:00:00 IDT 2014 |  | COMPLETED
2353 | TT_TASK | Curing (Base Slab) | Mon Aug 25 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2354 | TT_TASK | Removal of formwork (Base Slab) | Mon Sep 08 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Mon Sep 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2355 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Sep 10 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Tue Sep 02 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 |  | COMPLETED
2356 | TT_TASK | Rebar fixing (Wall and roof) | Thu Sep 18 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Thu Sep 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2357 | TT_TASK | Erect external formwork (Wall) | Thu Sep 25 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2358 | TT_TASK | Clearing and inspection (Wall and roof) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2359 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
2360 | TT_TASK | Curing (Wall and roof) | Sat Oct 11 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
2361 | TT_TASK | Removal formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Thu Oct 16 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Sat Nov 01 18:00:00 IST 2014 |  | COMPLETED
2362 | TT_TASK | Removal formwork (Roof) | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2363 | TT_TASK | Side walkway and cable bracket (72m3) | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
2365 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Nov 07 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Sat Nov 07 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
2366 | TT_TASK | Erect external formwork (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Wed Nov 18 18:00:00 IST 2015 |  | COMPLETED
2367 | TT_TASK | Rebar fixing (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Tue Nov 17 18:00:00 IST 2015 | Thu Nov 19 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 |  | COMPLETED
2368 | TT_TASK | Erect internal kicker formwork (Base Slab) | Wed Nov 18 08:00:00 IST 2015 | Fri Nov 20 18:00:00 IST 2015 | Tue Nov 24 08:00:00 IST 2015 | Thu Nov 26 18:00:00 IST 2015 |  | COMPLETED
2369 | TT_TASK | Clearing and inspection (Base Slab) | Sat Nov 21 08:00:00 IST 2015 | Sat Nov 21 18:00:00 IST 2015 | Fri Nov 27 08:00:00 IST 2015 | Fri Nov 27 18:00:00 IST 2015 |  | COMPLETED
2370 | TT_TASK | Concreting (Base Slab) (245m3) | Mon Nov 23 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Nov 28 08:00:00 IST 2015 | Sat Nov 28 18:00:00 IST 2015 |  | COMPLETED
2371 | TT_TASK | Curing (Base Slab) | Tue Nov 24 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Mon Nov 30 08:00:00 IST 2015 | Thu Dec 03 18:00:00 IST 2015 |  | COMPLETED
2372 | TT_TASK | Removal of formwork (Base Slab) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Fri Dec 04 08:00:00 IST 2015 | Sat Dec 05 18:00:00 IST 2015 |  | COMPLETED
2373 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 09 18:00:00 IST 2015 | Mon Dec 07 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
2374 | TT_TASK | Rebar fixing (Wall and roof) | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2375 | TT_TASK | Erect external formwork (Wall) | Mon Jan 11 08:00:00 IST 2016 | Wed Jan 13 18:00:00 IST 2016 | Thu Jan 07 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2376 | TT_TASK | Clearing and inspection (Wall and roof) | Thu Jan 14 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2377 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Jan 15 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2378 | TT_TASK | Curing (Wall and roof) | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 |  | COMPLETED
2379 | TT_TASK | Removal formwork (Wall) | Tue Jan 19 08:00:00 IST 2016 | Thu Jan 21 18:00:00 IST 2016 | Thu Jan 28 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2380 | TT_TASK | Removal formwork and falsework (Roof) | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Sat Jan 30 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2381 | TT_TASK | Side walkway and cable bracket (72m3) | Wed Jan 06 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Thu Nov 12 08:00:00 IST 2015 | Tue Mar 01 18:00:00 IST 2016 |  | COMPLETED
2382 | TT_TASK | Provision access opening to DC | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2383 | TT_TASK | Erect falsework and soffit formwork (Opening) | Thu Mar 10 08:00:00 IST 2016 | Mon Mar 21 18:00:00 IST 2016 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2384 | TT_TASK | Rebar fixing (Roof) | Tue Mar 22 08:00:00 IST 2016 | Tue Mar 22 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2385 | TT_TASK | Clearing and inspection (Roof) | Wed Mar 23 08:00:00 IST 2016 | Wed Mar 23 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2386 | TT_TASK | Concreting (Roof) (225m3) | Thu Mar 24 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2387 | TT_TASK | Curing (Roof) | Tue Mar 29 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Jan 13 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
2388 | TT_TASK | Removal internal falsework and soffit formwork (Roof) | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
2390 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Thu Mar 17 08:00:00 IST 2016 | Fri Mar 18 18:00:00 IST 2016 | Tue Mar 01 08:00:00 IST 2016 | Wed Mar 02 18:00:00 IST 2016 |  | COMPLETED
2391 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Sat Mar 19 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Thu Mar 03 08:00:00 IST 2016 | Tue Mar 08 18:00:00 IST 2016 |  | COMPLETED
2392 | TT_TASK | Backfilling to +18.25mPD (1229 m3 of soil) | Sat Jul 02 08:00:00 IDT 2016 | Mon Jul 11 18:00:00 IDT 2016 | Mon Jul 25 08:00:00 IDT 2016 | Tue Aug 02 18:00:00 IDT 2016 |  | COMPLETED
2393 | TT_TASK | Laying 500mm mass concrete lateral support | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 |  | COMPLETED
2394 | TT_TASK | Backfilling to 0.5m below S3 (+19.5mPD) (372m3 of soil) | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 |  | COMPLETED
2395 | TT_TASK | Removal strut S3 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 |  | COMPLETED
2396 | TT_TASK | Backfilling to 0.5m below S2 (+23.5mPD) (1984m3 of soil) | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 |  | COMPLETED
2397 | TT_TASK | Removal strut S2 | Wed Aug 24 08:00:00 IDT 2016 | Fri Aug 26 18:00:00 IDT 2016 | Wed Aug 24 08:00:00 IDT 2016 | Thu Sep 01 18:00:00 IDT 2016 |  | COMPLETED
2398 | TT_TASK | Backfilling to 0.5m below S1 (+28.5mPD) (2480m3 of soil) | Mon Sep 05 08:00:00 IDT 2016 | Tue Sep 20 18:00:00 IDT 2016 | Fri Sep 02 08:00:00 IDT 2016 | Fri Sep 09 18:00:00 IDT 2016 |  | COMPLETED
2399 | TT_TASK | Removal strut S1 | Wed Sep 21 08:00:00 IDT 2016 | Thu Sep 22 18:00:00 IDT 2016 | Sat Sep 10 08:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 |  | COMPLETED
2400 | TT_TASK | Backfilling to original ground level (approx. +31.5mPD) (1488m3 of soil) | Fri Sep 23 08:00:00 IDT 2016 | Mon Oct 03 18:00:00 IDT 2016 | Thu Sep 15 08:00:00 IDT 2016 | Mon Sep 19 18:00:00 IDT 2016 |  | COMPLETED
2402 | TT_TASK | Reinstatement of TUT area (Including Hydroseeding) | Mon Oct 03 08:00:00 IDT 2016 | Mon Jun 19 18:00:00 IDT 2017 | Fri Oct 07 08:00:00 IDT 2016 |  | 216.0 | IN_PROGRESS
25 | TT_TASK | Access opening for the up track cut and cover tunnel at Tse Uk Tsuen Shaft | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 10 18:00:00 IST 2016 |  | COMPLETED
27 | TT_TASK | Close out the temporary access opening at Tse Uk Tsuen Shaft | Thu Mar 10 08:00:00 IST 2016 | Tue Apr 05 18:00:00 IDT 2016 | Thu Feb 11 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
307 | TT_TASK | Position crane for TBM retrieval (down track) | Wed Jul 02 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014 | Sat Aug 02 18:00:00 IDT 2014 |  | COMPLETED
308 | TT_TASK | TBM Break-in and Retrieval (down track) | Mon Aug 04 08:00:00 IDT 2014 | Sat Aug 30 18:00:00 IDT 2014 | Mon Aug 04 08:00:00 IDT 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
309 | TT_TASK | Position crane for TBM retrieval (up track) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 |  | COMPLETED
310 | TT_TASK | TBM Break-in and Retrieval (up track) | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
376 | TT_TASK | Supply Engineer with Survey Equipment [PS41.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
377 | TT_TASK | Provide Engineer with suitably qualified full time Survey Assistant - 4 nos. [PS41.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
378 | TT_TASK | Provide Engineer with site transportation as detailed in PS42.1 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 |  | COMPLETED
379 | TT_TASK | Submit details of qualified drivers to be assigned to the Engineer, for review [PS42.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 |  | COMPLETED
380 | TT_TASK | Install, service and maintain 10 container offices for use by the Engineer's Site Staff | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
381 | TT_TASK | Provide services and equipment for the Engineer | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
383 | TT_TASK | Master Programme - Prepare and submit for approval [GS4.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
384 | TT_TASK | Master Programme - Comments , Resubmission and Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
385 | TT_TASK | Time Chainage Programme - Prepare and submit for approval [GS4.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
386 | TT_TASK | Time Chainage Programme - Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
387 | TT_TASK | Implement and Maintain Programme Management System for 1st Audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
388 | TT_TASK | Implement and Maintain Programme Management System for 2nd Audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
389 | TT_TASK | Implement and Maintain Programme Management System for 3rd Audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
391 | TT_TASK | Environmental Management Plan - Prepare and submit for approval [GS5.1.10] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
392 | TT_TASK | Environmental Management Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
393 | TT_TASK | Quality Plan - Prepare and submit for approval [GS9.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
394 | TT_TASK | Quality Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
395 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 1st audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 |  | COMPLETED
396 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 2nd audit | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
397 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 3rd audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
398 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 4th audit | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
399 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 5th audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
400 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 6th audit | Tue Jul 02 08:00:00 IDT 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
401 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 7th audit | Thu Nov 28 08:00:00 IST 2013 | Thu Jun 05 18:00:00 IDT 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Jan 24 18:00:00 IST 2014 |  | COMPLETED
402 | TT_TASK | Health and Safety Plan - Prepare and submit [G3.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
403 | TT_TASK | System Assurance Plan - Prepare and submit for approval [PS Appendix P3.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
404 | TT_TASK | System Assurance Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
405 | TT_TASK | Design for Safety & Constructability Plan - Prepare and submit for approval [PS37.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
406 | TT_TASK | Design for Safety & Constructability Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
408 | TT_TASK | Methods of Construction - Prepare and submit for approval [GS12.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
409 | TT_TASK | Methods of Construction - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
410 | TT_TASK | Contractor's Submission Schedule - Prepare and submit for approval [GS12.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
411 | TT_TASK | Contractor's Submission Schedule - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
412 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) [PS13.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
413 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) - Approval period | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 |  | COMPLETED
414 | TT_TASK | Spoil Disposal Plan [PS17.7.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
415 | TT_TASK | Waste Management Plan [PS22.10.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
416 | TT_TASK | Independent Checking Engineer - Appoint and submit for approval [PS7.1.8] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
417 | TT_TASK | Independent Checking Engineer - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
418 | TT_TASK | Sub-contract Management Plan - Prepare and submit [PS34.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 |  | COMPLETED
419 | TT_TASK | Schedule of Utilities Services Arrangement [GS7.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
420 | TT_TASK | Site Safety Supervision Plan for Site Formation - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
421 | TT_TASK | Site Safety Supervision Plan for Site Formation - Approval period | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
422 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Prepare and Submit | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
423 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
424 | TT_TASK | Site Safety Supervision Plan for ELS - Prepare and Submit | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
425 | TT_TASK | Site Safety Supervision Plan for ELS - Approval Period | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
426 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Prepare and Submit | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
427 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Approval Period | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
428 | TT_TASK | Noise Management Plan [P22.3.9] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
429 | TT_TASK | Air Quality Management Plan [P22.4.3] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
430 | TT_TASK | Detailed Proposal for Water Pollution Control Measures and Proposed Monitoring [PS22.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
431 | TT_TASK | Groundwater Monitoring and Response Plan [PS22.5.2] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
432 | TT_TASK | Vibration Monitoring Plan [PS22.8.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 |  | COMPLETED
433 | TT_TASK | Proposed Outline TTM Scheme - Prepare & submit to the: Engineer for Review / SLG for Approval [PS19.3] | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 |  | COMPLETED
434 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Proposed TTM Scheme [PS19.4] | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 |  | COMPLETED
435 | TT_TASK | Resubmission of Proposed Outline TTM Scheme (if required) | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
436 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Resubmitted Proposed Outline TTM Scheme [PS19.4] | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 |  | COMPLETED
437 | TT_TASK | Notification Period of the Approved TTM Scheme prior to implementation [PS19.4] | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 |  | COMPLETED
440 | TT_TASK | Initial Site Survey (WA3.11) | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 |  | COMPLETED
441 | TT_TASK | Initial Site Survey Report (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 |  | COMPLETED
442 | TT_TASK | Initial Site Survey & Condition Survey (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
443 | TT_TASK | Initial Site Survey Report (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
444 | TT_TASK | Initial Site Survey & Condition Survey (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
445 | TT_TASK | Initial Site Survey Report (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
446 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 4.9 & 4.12A [PS4.2] | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
447 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 5.1 & 5.3 [PS4.2.3] | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 |  | COMPLETED
448 | TT_TASK | Proposal for Site Clearance Works [PS4.4.1] | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 |  | COMPLETED
449 | TT_TASK | Site Clearance / Site Formation Works (including demolition of EBS) | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
450 | TT_TASK | Backfill existing stream courses in Works Area 4.9, 4.10 and 4.11 [PS18.5.1] | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
451 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and submit to EPD for Approval (WA3.3 - Area M, I, L) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
452 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA3.3 - Area M, I, L) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
453 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
454 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
455 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.3 - Area M, I, L) | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
456 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA3.3 - Area M, I, L) | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
457 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA3.3 - Area M, I, L) | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
458 | TT_TASK | Remediation Report - Approval (WA3.3 - Area M, I, L) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
459 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and Submit to EPD for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
460 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
461 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
462 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.1, 3.2, 3.3, 3.3A) | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
463 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.1, 3.2, 3.3, 3.3A) | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 |  | COMPLETED
464 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 |  | COMPLETED
465 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
466 | TT_TASK | Remediation Report - Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
467 | TT_TASK | Conduct remediation for Area Q in accordance with method proposed in the approved Remediation Action Plan [PS22.9.2] | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 |  | COMPLETED
468 | TT_TASK | Remediation Report - Prepare and submit for Approval [PS22.9.2] (Area Q) | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 |  | COMPLETED
469 | TT_TASK | Remediation Report - Approval (Area Q) | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
470 | TT_TASK | Removal of contaminated soil at North Tunnels (Area N,O,P,Q,R,S) | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
471 | TT_TASK | Condition Survey EBS for presence of Asbestos and gather samples | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
472 | TT_TASK | Testing of gathered samples | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 |  | COMPLETED
473 | TT_TASK | Prepare and submit Asbestos Investigation Report (AIR) & Asbestos Abatement Plan (AAP) | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
474 | TT_TASK | Approval period of AIR & AAP | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
475 | TT_TASK | Notification period to Engineer and EPD prior to Asbestos abatement works | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
476 | TT_TASK | Asbestos abatement works | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
477 | TT_TASK | Demolition of EBS | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
478 | TT_TASK | Confirmation of tree survey | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 |  | COMPLETED
480 | TT_TASK | Installation of ground settlement markers | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 |  | COMPLETED
481 | TT_TASK | Settlement monitoring and submit report | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
482 | TT_TASK | Settlement monitoring and submit report | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 |  | COMPLETED
483 | TT_TASK | Settlement monitoring and submit report | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
484 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
485 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Wed Feb 26 18:00:00 IST 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Feb 21 18:00:00 IST 2014 |  | COMPLETED
486 | TT_TASK | Settlement monitoring and submit report | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 |  | COMPLETED
488 | TT_TASK | Permit Applications (incl. License to Search and Excavate Antiquities and Excavation Permit) | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 |  | COMPLETED
489 | TT_TASK | Check for underground utilities | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 |  | COMPLETED
490 | TT_TASK | Field walking and hand augering | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 |  | COMPLETED
491 | TT_TASK | Excavation of trial pits | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 |  | COMPLETED
492 | TT_TASK | Rescue excavation rescue works (if required) | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 |  | COMPLETED
494 | TT_TASK | Erection of Hoarding with Gate (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 |  | COMPLETED
495 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 3.1, 3.2, 3.3 and 3.3A [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
496 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 4.9, 4.10, 4.11, 4.12A~C, and 4.15 [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
497 | TT_TASK | Project Signboard Erection [PS4.6.8] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
498 | TT_TASK | Marine Survey at Barging Point [PS4.3] (before construction of barging facilities) | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 00:00:00 IST 2010 |  | COMPLETED
499 | TT_TASK | Construct barging facilities | Sat Oct 02 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Oct 02 00:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
500 | TT_TASK | Operation Plan for the Barging Facility - Prepare and Submit for Approval [PS17.1.9] | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
501 | TT_TASK | Operation Plan for the Barging Facility - Review and Approval Period | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 |  | COMPLETED
503 | TT_TASK | General and Special Attendance for Designated Contractors | Mon Dec 02 08:00:00 IST 2013 | Mon Aug 31 18:00:00 IDT 2015 | Tue Jul 02 08:00:00 IDT 2013 | Wed Mar 25 18:00:00 IST 2015 |  | COMPLETED
505 | TT_TASK | Prepare and Submit Detailed Interface Specification | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 |  | COMPLETED
506 | TT_TASK | Approval of Detailed Interface Plan | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
507 | TT_TASK | Prepare and Submit Detailed Interface Specification | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 |  | COMPLETED
508 | TT_TASK | Approval of Detailed Interface Plan | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
510 | TT_TASK | Prepare and Submit Draft Operation and Maintenance Manual [PS33.1] | Mon Aug 24 08:00:00 IDT 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jul 28 08:00:00 IDT 2014 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
511 | TT_TASK | Review and approval period of Draft Operation and Maintenance Manual | Wed Aug 10 08:00:00 IDT 2016 | Tue Sep 13 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
512 | TT_TASK | Prepare and Submit Final Operation and Maintenance Manual [PS33.1] | Wed Sep 14 08:00:00 IDT 2016 | Thu Feb 16 18:00:00 IST 2017 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
513 | TT_TASK | Provide Engineer with As-Built Drawing for the Whole of the Works [PS33.2] | Mon Nov 21 08:00:00 IST 2016 | Wed Dec 14 18:00:00 IST 2016 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
514 | TT_TASK | Provide Engineer with Asset Registration Information [PS33.3] | Fri May 19 08:00:00 IDT 2017 | Mon Jun 12 18:00:00 IDT 2017 |  |  |  | NOT_STARTED
517 | TT_TASK | Preliminary Design Programme - Prepare and Submit for Approval [PS7.1.8 - App. Z2.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
518 | TT_TASK | Preliminary Design Programme - Review and Approval Period [PS7.1.8 - App. Z2.2] | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 |  | COMPLETED
519 | TT_TASK | Preliminary Design Programme - Resubmission and Approval (if required) [PS7.1.8 - App. Z2.2] | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 |  | COMPLETED
520 | TT_TASK | Schedule of Designs - Prepare and Submit for Approval [PS7.1.8 - App. Z2.5] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
521 | TT_TASK | Detailed Proposal for Carrying Out the Cross Passage Works [PS11.5.2] | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
524 | TT_TASK | Design TBM and submit full details to the Engineer [PS7.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
525 | TT_TASK | TBM Design - Approval period | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 |  | COMPLETED
526 | TT_TASK | TBM Design - Resubmission and approval period | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 |  | COMPLETED
528 | TT_TASK | AIP Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
529 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 |  | COMPLETED
530 | TT_TASK | DDS Design - Prepare and Submit | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 |  | COMPLETED
531 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 |  | COMPLETED
532 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 |  | COMPLETED
533 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 |  | COMPLETED
534 | TT_TASK | Issue Completed Working Drawings | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
536 | TT_TASK | AIP Design - Prepare and Submit | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 |  | COMPLETED
537 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 |  | COMPLETED
538 | TT_TASK | AIP Design - Response to comments and Resubmit | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
539 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
540 | TT_TASK | DDS Design - Prepare and Submit | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
541 | TT_TASK | DDS Design - Review and Approval Period (by MTRC & related Government Authorities) | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 |  | COMPLETED
542 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 |  | COMPLETED
543 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 |  | COMPLETED
544 | TT_TASK | Issue Completed Working Drawings | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 |  | COMPLETED
546 | TT_TASK | DDS Design - Prepare and Submit | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 |  | COMPLETED
547 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 |  | COMPLETED
548 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 |  | COMPLETED
549 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 |  | COMPLETED
550 | TT_TASK | Issue Completed Working Drawings | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
552 | TT_TASK | AIP Design - Prepare and Submit | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 |  | COMPLETED
553 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
554 | TT_TASK | AIP Design - Response to comments and Resubmit | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 |  | COMPLETED
555 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
556 | TT_TASK | DDS Design - Prepare and Submit | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 |  | COMPLETED
557 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 |  | COMPLETED
558 | TT_TASK | DDS Design - Response to comments and Resubmit | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 |  | COMPLETED
559 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 |  | COMPLETED
560 | TT_TASK | Issue Completed Working Drawings | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 |  | COMPLETED
562 | TT_TASK | Prepare and Submit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 |  | COMPLETED
563 | TT_TASK | Review and Approval Period | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
564 | TT_TASK | Response to comments and Resubmit | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 |  | COMPLETED
565 | TT_TASK | Review and Approval Period (for resubmission) | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 |  | COMPLETED
568 | TT_TASK | DDS Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
569 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 |  | COMPLETED
570 | TT_TASK | DDS Design - Response to comments and Resubmit | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 |  | COMPLETED
571 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 |  | COMPLETED
572 | TT_TASK | Issue Completed Working Drawings | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
574 | TT_TASK | DDS Design - Prepare and Submit | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 |  | COMPLETED
575 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 |  | COMPLETED
576 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 |  | COMPLETED
577 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 |  | COMPLETED
578 | TT_TASK | Issue Completed Working Drawings | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 |  | COMPLETED
580 | TT_TASK | DDS Design - Prepare and Submit | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 |  | COMPLETED
581 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 |  | COMPLETED
582 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 |  | COMPLETED
583 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 |  | COMPLETED
584 | TT_TASK | Issue Completed Working Drawings | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 |  | COMPLETED
586 | TT_TASK | DDS Design - Prepare and Submit | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 |  | COMPLETED
587 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 |  | COMPLETED
588 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 |  | COMPLETED
589 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 |  | COMPLETED
590 | TT_TASK | Issue Completed Working Drawings | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 |  | COMPLETED
592 | TT_TASK | DDS Design - Prepare and Submit | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 |  | COMPLETED
593 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 |  | COMPLETED
594 | TT_TASK | DDS Design - Response to comments and Resubmit | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 |  | COMPLETED
595 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 |  | COMPLETED
596 | TT_TASK | Issue Completed Working Drawings | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
599 | TT_TASK | Formworks / Falsework - Prepare & Submit | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
600 | TT_TASK | Formworks / Falsework - Review & Approval Period (by MTRC) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
601 | TT_TASK | Formworks / Falsework - Response to comments and Resubmit | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 |  | COMPLETED
602 | TT_TASK | Formworks / Falsework - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
605 | TT_TASK | Layout of Site Hoarding - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
606 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (by MTRC) | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
607 | TT_TASK | Layout of Site Hoarding - Response to comments and Resubmit | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
608 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 |  | COMPLETED
610 | TT_TASK | Layout of Engineer's Accommodation - Prepare and Submit | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
611 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (by MTRC) | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 |  | COMPLETED
612 | TT_TASK | Layout of Engineer's Accommodation - Response to comments and Resubmit | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
613 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (for resubmit) (by MTRC & related Government Authorities | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
615 | TT_TASK | TTMS Assessment Report - Prepare and Submit | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 |  | COMPLETED
616 | TT_TASK | TTMS Assessment Report - Review and Approval Period (by MTRC) | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
617 | TT_TASK | TTMS Assessment Report - Response to comments and Resubmit | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 |  | COMPLETED
618 | TT_TASK | TTMS Assessment Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
619 | TT_TASK | Issue Completed Working Drawings | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 |  | COMPLETED
621 | TT_TASK | DIA Report - Prepare and Submit | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 |  | COMPLETED
622 | TT_TASK | DIA Report - Review and Approval Period (by MTRC) | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 |  | COMPLETED
623 | TT_TASK | DIA Report - Response to comments and Resubmit | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 |  | COMPLETED
624 | TT_TASK | DIA Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
625 | TT_TASK | Issue Completed Working Drawings | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 |  | COMPLETED
627 | TT_TASK | AIP Design - Prepare & Submit | Wed Sep 23 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 |  | COMPLETED
628 | TT_TASK | AIP Design - Review & Approval Period (by MTR) | Wed Oct 14 08:00:00 IDT 2015 | Wed Nov 11 18:00:00 IST 2015 | Mon Jun 08 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
629 | TT_TASK | AIP Design - Response to comments and Resubmit | Thu Nov 12 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Mon Jun 15 01:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
630 | TT_TASK | AIP Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jun 22 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
631 | TT_TASK | DDS Design - Prepare & Submit | Wed Jan 13 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Tue Sep 01 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 |  | COMPLETED
632 | TT_TASK | DDS Design - Review & Approval Period (by MTRC) | Fri Feb 26 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 12 18:00:00 IDT 2015 |  | COMPLETED
633 | TT_TASK | DDS Design - Response to comments & Resubmit | Tue Mar 29 08:00:00 IDT 2016 | Fri Apr 01 18:00:00 IDT 2016 | Mon Sep 14 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
634 | TT_TASK | DDS Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Apr 02 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 | Mon Sep 21 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
635 | TT_TASK | Issue Completed Working Drawings | Wed Jan 27 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
637 | TT_TASK | Layout of Barging Point - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
638 | TT_TASK | Layout of Barging Point - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
639 | TT_TASK | Layout of Barging Point - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
640 | TT_TASK | Layout of Barging Point - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
641 | TT_TASK | Loading Ramps - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
642 | TT_TASK | Loading Ramps - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
643 | TT_TASK | Loading Ramps - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
644 | TT_TASK | Loading Ramps - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
645 | TT_TASK | Weighbridge - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
646 | TT_TASK | Weighbridge - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
647 | TT_TASK | Weighbridge - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
648 | TT_TASK | Weighbridge - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
652 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
653 | TT_TASK | Pre-drill and guide wall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
654 | TT_TASK | D-wall construction (1084m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
655 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
656 | TT_TASK | Wang Toi Shan Shan Tsuen Road diversion works | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 |  | COMPLETED
658 | TT_TASK | Excavate up to +10.5mPD (369m3) | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 |  | COMPLETED
659 | TT_TASK | Install Strut S0 +11.0mPD | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 |  | COMPLETED
660 | TT_TASK | Excavate up to +8.0mPD (1525m3) | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 |  | COMPLETED
661 | TT_TASK | Install Strut S1 +8.5mPD | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 |  | COMPLETED
662 | TT_TASK | Excavate up to +4.5mPD (2135m3) | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 |  | COMPLETED
663 | TT_TASK | Install Strut S2 +5.0mPD | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 |  | COMPLETED
664 | TT_TASK | Excavate up to +0.5mPD (2440m3) | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 |  | COMPLETED
665 | TT_TASK | Install Strut S3 +1.0mPD | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 |  | COMPLETED
666 | TT_TASK | Excavate up to -6.5mPD (4340m3) | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 |  | COMPLETED
667 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
668 | TT_TASK | Construction of temporary slab and entrance seal (622m3) | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
672 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 08 18:00:00 IST 2014 | Fri Dec 05 08:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
673 | TT_TASK | Erect external formwork (Base Slab) | Tue Dec 09 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 08 08:00:00 IST 2014 | Tue Dec 09 18:00:00 IST 2014 |  | COMPLETED
674 | TT_TASK | Rebar fixing (Base Slab) | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 18:00:00 IST 2014 | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
675 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Dec 15 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Mon Dec 15 18:00:00 IST 2014 |  | COMPLETED
676 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Dec 17 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Tue Dec 16 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 |  | COMPLETED
677 | TT_TASK | Curing (Base Slab) | Thu Dec 18 08:00:00 IST 2014 | Sat Dec 27 18:00:00 IST 2014 | Wed Dec 17 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
678 | TT_TASK | Removal of formwork (Base Slab) | Fri Dec 19 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 24 18:00:00 IST 2014 |  | COMPLETED
679 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
680 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 | Mon Jun 22 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 |  | COMPLETED
681 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Jun 13 08:00:00 IDT 2015 | Mon Jun 15 18:00:00 IDT 2015 | Thu Jun 25 01:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
682 | TT_TASK | Concreting (Wall & Roof) (444m3) | Tue Jun 16 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
683 | TT_TASK | Curing (Wall & Roof) | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
684 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 |  | COMPLETED
685 | TT_TASK | Removal external formwork (Wall) | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
686 | TT_TASK | Side walkway and cable bracket (360m3) | Sat Jul 18 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Sat Jul 18 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
687 | TT_TASK | Access opening to DC (DC access period) | Tue Oct 06 08:00:00 IDT 2015 | Fri Mar 04 18:00:00 IST 2016 | Tue Oct 06 08:00:00 IDT 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
688 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Sat Dec 12 08:00:00 IST 2015 | Mon Jan 18 18:00:00 IST 2016 | Tue Nov 03 00:00:00 IST 2015 | Mon Nov 30 18:00:00 IST 2015 |  | COMPLETED
690 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 | Tue Apr 12 08:00:00 IDT 2016 | Wed Apr 13 18:00:00 IDT 2016 |  | COMPLETED
691 | TT_TASK | Erect external formwork (Base Slab) | Mon May 23 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Thu Apr 14 08:00:00 IDT 2016 | Fri Apr 15 18:00:00 IDT 2016 |  | COMPLETED
692 | TT_TASK | Rebar fixing (Base Slab) | Wed May 25 08:00:00 IDT 2016 | Fri May 27 18:00:00 IDT 2016 | Sat Apr 16 08:00:00 IDT 2016 | Tue Apr 19 18:00:00 IDT 2016 |  | COMPLETED
693 | TT_TASK | Erect internal kicker formwork (Base Slab) | Sat May 28 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 | Wed Apr 20 08:00:00 IDT 2016 | Thu Apr 21 18:00:00 IDT 2016 |  | COMPLETED
694 | TT_TASK | Concreting (Base Slab) (225m3) | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 | Fri Apr 22 08:00:00 IDT 2016 | Fri Apr 22 18:00:00 IDT 2016 |  | COMPLETED
695 | TT_TASK | Curing (Base Slab) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 08 18:00:00 IDT 2016 | Sat Apr 23 08:00:00 IDT 2016 | Fri Apr 29 18:00:00 IDT 2016 |  | COMPLETED
696 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Sat Apr 30 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
697 | TT_TASK | Removal of formwork (Base Slab) | Tue May 24 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Mon May 09 08:00:00 IDT 2016 | Tue May 10 18:00:00 IDT 2016 |  | COMPLETED
698 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed May 25 08:00:00 IDT 2016 | Sat May 28 18:00:00 IDT 2016 | Wed May 11 08:00:00 IDT 2016 | Mon May 16 18:00:00 IDT 2016 |  | COMPLETED
699 | TT_TASK | Rebar fixing (Wall & Roof) | Mon May 30 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 17 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 |  | COMPLETED
700 | TT_TASK | Erect external formwork (Wall & Roof) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 03 18:00:00 IDT 2016 | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 |  | COMPLETED
701 | TT_TASK | Concreting (Wall & Roof) (444m3) | Sat Jun 04 08:00:00 IDT 2016 | Sat Jun 04 18:00:00 IDT 2016 | Mon May 23 08:00:00 IDT 2016 | Mon May 23 18:00:00 IDT 2016 |  | COMPLETED
702 | TT_TASK | Curing (Wall & Roof) | Mon Jun 06 08:00:00 IDT 2016 | Tue Jun 14 18:00:00 IDT 2016 | Tue May 24 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 |  | COMPLETED
703 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 15 08:00:00 IDT 2016 | Wed Jun 15 18:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 |  | COMPLETED
704 | TT_TASK | Removal external formwork (Wall) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
705 | TT_TASK | Side walkway and cable bracket (102m3) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 |  | COMPLETED
706 | TT_TASK | Access opening to DC (DC access period) | Sat Jun 18 08:00:00 IDT 2016 | Thu Jul 14 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
707 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Fri Jul 15 08:00:00 IDT 2016 | Wed Aug 17 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
709 | TT_TASK | Backfilling between tunnels (2000m3) | Thu Sep 01 08:00:00 IDT 2016 | Sat Sep 17 18:00:00 IDT 2016 | Tue Sep 13 08:00:00 IDT 2016 | Fri Sep 30 18:00:00 IDT 2016 |  | COMPLETED
710 | TT_TASK | Remove Strut S2 | Mon Oct 03 08:00:00 IDT 2016 | Wed Oct 05 18:00:00 IDT 2016 | Mon Oct 03 08:00:00 IDT 2016 | Tue Oct 11 18:00:00 IDT 2016 |  | COMPLETED
711 | TT_TASK | Backfilling up top S1 Soffit | Thu Oct 06 08:00:00 IDT 2016 | Fri Oct 21 18:00:00 IDT 2016 | Fri Oct 28 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
712 | TT_TASK | Remove Strut S1 | Sat Oct 22 08:00:00 IDT 2016 | Mon Oct 24 18:00:00 IDT 2016 | Tue Oct 11 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
713 | TT_TASK | Backfilling up top S0 Soffit | Mon Nov 07 08:00:00 IST 2016 | Sat Nov 12 18:00:00 IST 2016 | Tue Nov 01 08:00:00 IST 2016 | Sat Nov 05 18:00:00 IST 2016 |  | COMPLETED
714 | TT_TASK | Remove Strut S0 | Mon Nov 14 08:00:00 IST 2016 | Tue Nov 15 18:00:00 IST 2016 | Mon Nov 07 08:00:00 IST 2016 | Tue Nov 08 18:00:00 IST 2016 |  | COMPLETED
715 | TT_TASK | Backfilling up to ground level | Wed Nov 16 08:00:00 IST 2016 | Fri Nov 18 18:00:00 IST 2016 | Wed Nov 09 08:00:00 IST 2016 | Fri Nov 11 18:00:00 IST 2016 |  | COMPLETED
719 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
720 | TT_TASK | Pre-drilling and guidewall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
721 | TT_TASK | D-wall construction (1451m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
722 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 |  | COMPLETED
724 | TT_TASK | Excavate from ground level to formation level -5.5mPD (4559m3) | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 |  | COMPLETED
725 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 |  | COMPLETED
726 | TT_TASK | Placing of blinding layer (South Bound) | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 |  | COMPLETED
727 | TT_TASK | Placing of blinding layer (North Bound) | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
729 | TT_TASK | Construction of Bay 2 to Bay 7a (3565m3) | Mon Jun 04 08:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 | Mon Jun 04 18:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 |  | COMPLETED
730 | TT_TASK | Side walkway and cable bracket (Southbound) | Fri Oct 02 08:00:00 IDT 2015 | Fri Nov 06 18:00:00 IST 2015 | Fri Oct 02 08:00:00 IDT 2015 | Sat Oct 31 18:00:00 IST 2015 |  | COMPLETED
731 | TT_TASK | Side walkway and cable bracket (Northbound) | Tue May 03 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 |  | COMPLETED
733 | TT_TASK | Backfilling (1344m3) | Wed Nov 07 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 | Wed Nov 07 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
736 | TT_TASK | Scheme Design, Mobilization, Site set up & Material delivery and Instrumentations | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
737 | TT_TASK | Downstream pipe pile wall construction (45 nos.) and grout curtain (45 nos.) | Mon Nov 12 08:00:00 IST 2012 | Fri Jan 25 18:00:00 IST 2013 | Mon Nov 12 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
738 | TT_TASK | Curtain Grout for cut slope (120 nos.) | Fri Jul 26 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
739 | TT_TASK | Drilling for ground improvement only (if require) | Mon Dec 10 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
740 | TT_TASK | If settlement reach the AAA alarm & action level TAM grouting will apply during excavation | Thu Apr 11 08:00:00 IDT 2013 | Thu May 16 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
741 | TT_TASK | Erection of temporary working platform for Up stream and Installation of Instrumentation System | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
742 | TT_TASK | Upstream pipe pile wall construction adjacent to WTSSTR, (17nos.) | Thu Dec 27 08:00:00 IST 2012 | Mon Jan 28 18:00:00 IST 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
743 | TT_TASK | Upstream pipe pile wall construction at Kam Tin River, 15m depth, 42nos. 1drill rig) | Tue Jan 29 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
744 | TT_TASK | Excavation and soil nail installation | Tue Apr 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
745 | TT_TASK | Excavation for rock and blinding layer | Sat Aug 24 08:00:00 IDT 2013 | Sat Sep 28 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
750 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
751 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
752 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
753 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
754 | TT_TASK | Concreting (164m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
755 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
756 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
757 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
758 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
759 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
760 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
761 | TT_TASK | Concreting (242m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
762 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
763 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
764 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
765 | TT_TASK | Removal internal falsework and formwork for roof | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
766 | TT_TASK | Side walkway and cable bracket (19m3) | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
770 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
771 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
772 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
773 | TT_TASK | Erect internal kicker formwork | Thu Nov 28 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 09 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
774 | TT_TASK | Concreting (121m3) | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
775 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
776 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
777 | TT_TASK | Removal of formwork | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
778 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
779 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
780 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
781 | TT_TASK | Concreting (121m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
782 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
783 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
784 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
785 | TT_TASK | Removal internal falsework and formwork for roof | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
786 | TT_TASK | Side walkway and cable bracket (38m3) | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
788 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
789 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
790 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
791 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
792 | TT_TASK | Concreting (240m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
793 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
794 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
795 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
796 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
797 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
798 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
799 | TT_TASK | Concreting (240m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
800 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
801 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
802 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
803 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
804 | TT_TASK | Side walkway and cable bracket | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
806 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
807 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
808 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
809 | TT_TASK | Concreting (222m3) | Wed Nov 06 08:00:00 IST 2013 | Wed Nov 06 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
810 | TT_TASK | Curing | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
811 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
812 | TT_TASK | Removal of formwork | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
815 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
816 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
817 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
818 | TT_TASK | Erect internal kicker formwork | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
819 | TT_TASK | Concreting (111m3) | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
820 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
821 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
822 | TT_TASK | Removal of formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
823 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
824 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
825 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
826 | TT_TASK | Concreting (220m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
827 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
828 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
829 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
830 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
831 | TT_TASK | Side walkway and cable bracket (38m3) | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 |  | COMPLETED
833 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
834 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
835 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
836 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
837 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
838 | TT_TASK | Curing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
839 | TT_TASK | Preparation of construction joint for base slab | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
840 | TT_TASK | Removal of formwork | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
841 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
842 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
843 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
844 | TT_TASK | Concreting (327m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
845 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
846 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
847 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
848 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
849 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
851 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 20 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
852 | TT_TASK | Rebar fixing | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
853 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 08:00:00 IDT 2013 |  | COMPLETED
854 | TT_TASK | Concreting (225m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
855 | TT_TASK | Curing | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
856 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
857 | TT_TASK | Removal of formwork | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
860 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 27 08:00:00 IST 2013 | Wed Nov 27 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
861 | TT_TASK | Erect external formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
862 | TT_TASK | Rebar fixing | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
863 | TT_TASK | Erect internal kicker formwork | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
864 | TT_TASK | Concreting (222m3) | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
865 | TT_TASK | Curing | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Mon Oct 28 18:00:00 IST 2013 |  | COMPLETED
866 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
867 | TT_TASK | Removal of formwork | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
868 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
869 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
870 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
871 | TT_TASK | Concreting (222m3) | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 |  | COMPLETED
872 | TT_TASK | Curing | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 07 18:00:00 IST 2014 |  | COMPLETED
873 | TT_TASK | Preparation of construction joint for wall and roof | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
874 | TT_TASK | Removal external and internal formwork for wall | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
875 | TT_TASK | Removal internal falsework and formwork for roof | Mon Feb 10 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
876 | TT_TASK | Side walkway and cable bracket (38m3) | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 |  | COMPLETED
878 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
879 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
880 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
881 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
882 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
883 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
884 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
885 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
886 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
887 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
888 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
889 | TT_TASK | Concreting (222m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
890 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
892 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
893 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
894 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
896 | TT_TASK | Placing of waterproof member T-lock & testing | Mon Nov 18 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
897 | TT_TASK | Rebar fixing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Wed Oct 23 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
898 | TT_TASK | Erect external formwork | Fri Nov 22 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
899 | TT_TASK | Concreting (222m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
900 | TT_TASK | Curing | Tue Nov 26 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
901 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
902 | TT_TASK | Removal of formwork | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
905 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
906 | TT_TASK | Erect external formwork | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
907 | TT_TASK | Rebar fixing | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
908 | TT_TASK | Erect internal kicker formwork | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
909 | TT_TASK | Concreting (330m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
910 | TT_TASK | Curing | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
911 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
912 | TT_TASK | Removal of formwork | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
913 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
914 | TT_TASK | Rebar fixing | Wed Nov 20 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
915 | TT_TASK | Erect external formwork | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
916 | TT_TASK | Concreting (330m3) | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
917 | TT_TASK | Curing | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
918 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
919 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
920 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
921 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
923 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
924 | TT_TASK | Erect external formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
925 | TT_TASK | Rebar fixing | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
926 | TT_TASK | Erect internal kicker formwork | Wed Dec 04 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
927 | TT_TASK | Concreting (240m3) | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
928 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
929 | TT_TASK | Preparation of construction joint for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
930 | TT_TASK | Removal of formwork | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
931 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
932 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
933 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
934 | TT_TASK | Concreting (240m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
935 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
936 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
937 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
938 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
939 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
941 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
942 | TT_TASK | Rebar fixing | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
943 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
944 | TT_TASK | Concreting (240m3) | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
945 | TT_TASK | Curing | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
946 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
947 | TT_TASK | Removal of formwork | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
950 | TT_TASK | Placing of waterproof member T-lock & testing | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
951 | TT_TASK | Erect external formwork | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
952 | TT_TASK | Rebar fixing | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
953 | TT_TASK | Erect internal kicker formwork | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
954 | TT_TASK | Concreting (200m3) | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
955 | TT_TASK | Curing | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
956 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
957 | TT_TASK | Removal of formwork | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
958 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 29 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
959 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
960 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
961 | TT_TASK | Concreting (200m3) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
962 | TT_TASK | Curing | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
963 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
964 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 13 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
965 | TT_TASK | Removal internal falsework and formwork for roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
966 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 |  | COMPLETED
968 | TT_TASK | Placing of waterproof member T-lock & testing | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
969 | TT_TASK | Erect external formwork | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
970 | TT_TASK | Rebar fixing | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
971 | TT_TASK | Erect internal kicker formwork | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
972 | TT_TASK | Concreting (220m3) | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
973 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
974 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
975 | TT_TASK | Removal of formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
976 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
977 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
978 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
979 | TT_TASK | Concreting (220m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
980 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
981 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
982 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
983 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
984 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
986 | TT_TASK | Placing of waterproof member T-lock & testing | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
987 | TT_TASK | Rebar fixing | Mon Nov 25 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
988 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
989 | TT_TASK | Concreting (222m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
990 | TT_TASK | Curing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
991 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
992 | TT_TASK | Removal of formwork | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
994 | TT_TASK | Removal of Temporary Nullah | Sat Mar 01 08:00:00 IST 2014 | Sat Jun 21 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
995 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (5218m3) | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 |  | COMPLETED
996 | TT_TASK | Reinstate the permenant Retaining wall of Nullah | Sat Mar 01 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Tue Mar 04 08:00:00 IST 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
997 | TT_TASK | Reinstate Nullah Base of original route | Tue Feb 25 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Tue Feb 25 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
998 | TT_TASK | Reinstate Nullah to original route | Sat Mar 29 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Sat Mar 29 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
999 | TT_TASK | Construction & connect East Box Culvert from Box 6B to KTR | Mon Apr 14 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Mon Feb 10 08:00:00 IST 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
1000 | TT_TASK | Reinstatement of Wang Toi Shan Shan Tsuen Road | Tue Dec 01 08:00:00 IST 2015 | Wed Jul 13 18:00:00 IDT 2016 | Tue Dec 01 08:00:00 IST 2015 | Mon Jul 18 18:00:00 IDT 2016 |  | COMPLETED
1003 | TT_TASK | Pre-drilling at Works Area 4.4 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
1004 | TT_TASK | Site Setup and guide wall | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1005 | TT_TASK | D-wall construction (3104m3) | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 |  | COMPLETED
1006 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
1008 | TT_TASK | Excavate up to +8.0mPD (775m3) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1009 | TT_TASK | Install Strut S1 +8.5mPD | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 |  | COMPLETED
1010 | TT_TASK | Excavate up to +4.5mPD (2713m3) | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 |  | COMPLETED
1011 | TT_TASK | Install Strut S2 +5.0mPD | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
1012 | TT_TASK | Excavate up to +0.5mPD (3100m3) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 |  | COMPLETED
1013 | TT_TASK | Install Strut S3 +1.0mPD | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1014 | TT_TASK | Excavate up to -3.0mPD (2713m3) | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1015 | TT_TASK | Install Strut S4 -2.5mPD | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 |  | COMPLETED
1016 | TT_TASK | Excavate up to -5.5mPD (4952m3) | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1017 | TT_TASK | Placing of blinding layer | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1021 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1022 | TT_TASK | Erect external formwork for base slab | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1023 | TT_TASK | Rebar fixing for base slab | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1024 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 26 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1025 | TT_TASK | Concreting for base slab (350m3) | Thu Jun 27 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1026 | TT_TASK | Curing for base slab | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1027 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1028 | TT_TASK | Removal of formwork for base slab | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1029 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1030 | TT_TASK | Removal strut S4 and S3 | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1032 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1033 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1034 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1035 | TT_TASK | Concreting for wall and roof (489m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1036 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1037 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1038 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1039 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1040 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1043 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1044 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1045 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1046 | TT_TASK | Curing for wall and roof | Sat Jun 22 08:00:00 IDT 2013 | Mon Jul 01 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1047 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1048 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1050 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Tue Dec 17 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1053 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1054 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1055 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1056 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1057 | TT_TASK | Concreting for base slab (350m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1058 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1059 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1060 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1061 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1062 | TT_TASK | Removal strut S4 and S3 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1064 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1065 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1066 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1067 | TT_TASK | Concreting for wall and roof (489m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1068 | TT_TASK | Curing for wall and roof | Wed Jun 12 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1069 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1070 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 14 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1071 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1072 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Feb 13 08:00:00 IST 2014 | Tue Feb 18 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1074 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1075 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1076 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1077 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1078 | TT_TASK | Curing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1079 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1080 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1081 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1082 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 16 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1084 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (2343m3) | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1085 | TT_TASK | Placing 0.5m thk concrete lateral support (+3.96mPD) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1086 | TT_TASK | Removal strut S2 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 23 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1088 | TT_TASK | Construction of Temporary Culvert (open channel) | Tue Jun 25 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1089 | TT_TASK | Temporary box culvert (At Box 6B Area) Saw Cut D-wall | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 |  | COMPLETED
1090 | TT_TASK | Erect 3m high block wall | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 |  | COMPLETED
1091 | TT_TASK | Connection to East Box Culvert (823B portion) | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 |  | COMPLETED
1092 | TT_TASK | Blinding | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
1093 | TT_TASK | Temporary box culvert (Outside Box 6B Area) Sheet piling | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 |  | COMPLETED
1094 | TT_TASK | ELS Works | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
1095 | TT_TASK | Blinding | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
1096 | TT_TASK | Removal of Temporary Culvert and Reinstatement | Fri May 16 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
1098 | TT_TASK | Reinstatement of TOA's | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 |  |  | IN_PROGRESS
1099 | TT_TASK | Hydroseeding works | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 | Wed Nov 30 18:00:00 IST 2016 |  | COMPLETED
1100 | TT_TASK | Tree Planting works | Thu Sep 01 08:00:00 IDT 2016 | Sat Dec 03 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
1101 | TT_TASK | Woodland Shrub Mix | Thu Sep 01 08:00:00 IDT 2016 | Fri Nov 18 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  | 200.0 | IN_PROGRESS
1104 | TT_TASK | Kam Tin River Diversion (Stage 1-3) | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1106 | TT_TASK | Concrete fill up to +8.0mPD near side A mass concrete wall | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 |  | COMPLETED
1107 | TT_TASK | Construction of mass concrete wall to +8.0mPD at side A (4 bay CH A80~A120) | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1108 | TT_TASK | Construction of base slab lining and low flow channel (4 bay A9~A10, B8~B9; LFC CH 80~110) | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1109 | TT_TASK | Construction of mass concrete wall to +8.0mPD of side B (3 bay CH B60~B90) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1110 | TT_TASK | Construction of T-shaped retaining wall (1 Bay CH B50~B60) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1111 | TT_TASK | Soil backfill at side A from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1112 | TT_TASK | Concrete backfill at side B from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1113 | TT_TASK | Removal strut at +8.5mPD near side A | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1114 | TT_TASK | Concrete fill up to +11.0mPD near side A mass concrete wall | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1115 | TT_TASK | Placing concrete block at side A from +8.0mPD to +11.0mpd at side A (4 bay CH A80~A120) | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1116 | TT_TASK | Soil backfill at side A from +8.0mPD to +11.0mPD | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1117 | TT_TASK | Removal strut at +8.5mPD near side B | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1118 | TT_TASK | Placing concrete block at side B from +8.0mPD to +11.0mPD (4 bay CH B60~B90) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1119 | TT_TASK | Concrete backfill at side B from +8.0mPD to +11.0mPD | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1121 | TT_TASK | Placing temporary concrete block to Up stream at CH30 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 |  | COMPLETED
1122 | TT_TASK | Placing temporary concrete block to Up stream at CH160 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1123 | TT_TASK | Excavation from GL to FL +5.0mPD Up stream (Low flow channel CH 30~60) | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1124 | TT_TASK | Excavation from GL to FL +5.0mPD Down stream (Low flow channel CH 130~160) | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1125 | TT_TASK | Construction of T-shaped retaining wall at Up stream of side B (2 Bay CH B30~B50) | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1126 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (3 bay CH B90~B120) | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1127 | TT_TASK | Construction of Up stream base slab lining and low flow channel (6 Bay A1~A4, B3~B4; Low flow channel CH 30~50) | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1128 | TT_TASK | Construction of Down stream base slab lining and low flow channel (5 Bay A14~A16, B14~B15; LFC CH 140~170) | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1129 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Up stream and saw cut D-wall | Fri Jun 14 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1130 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Down stream and saw cut D-wall | Wed Jun 19 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1131 | TT_TASK | Construction of remaining Up stream base slab lining and low flow channel (7 bay A5~A8, B5~B7; LFC CH 50~80) | Thu Jun 27 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1132 | TT_TASK | Construction of remaining Down stream base slab lining and low flow channel (7 bay A11~A13, B10~B13; LFC CH 110~140) | Wed Jul 03 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1134 | TT_TASK | Relocation of temporary concrete block at Up stream for construction of mass concrete wall at side B | Sat Jul 20 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1135 | TT_TASK | Relocation of temporary concrete block at Down stream for construction of mass concrete wall at side B | Tue Jul 23 08:00:00 IDT 2013 | Wed Jul 24 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1136 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Up stream of side B (3 bay CH B0~B30) | Tue Jul 23 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1137 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (4 bay CH B0~B30) | Thu Jul 25 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1141 | TT_TASK | Application of power supply, environmental permits and construction substation | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1142 | TT_TASK | Procurement and Confirmation of the order of 1st tunnel boring machine | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 |  | COMPLETED
1143 | TT_TASK | Prepare on-demand bond or bank guarantee for the procurement of TBM and submit to Engineer for approval | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 |  | COMPLETED
1144 | TT_TASK | TBM design and submission for approval | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
1145 | TT_TASK | TBM materials order and delivery to factory | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 |  | COMPLETED
1146 | TT_TASK | TBM equipments order and delivery to factory | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 |  | COMPLETED
1147 | TT_TASK | TBM Fabrication | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
1148 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 |  | COMPLETED
1149 | TT_TASK | TBM test Run | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 |  | COMPLETED
1150 | TT_TASK | TBM disassembly and packing for shipping to HK | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 |  | COMPLETED
1151 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
1152 | TT_TASK | Ground treatment for TBM lanching shaft | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 |  | COMPLETED
1153 | TT_TASK | Ground treatment for Cross Passage Tunnel | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1154 | TT_TASK | Box7A Setup TBM facilities, install noise enclosure and CNP application | Fri Jun 01 08:00:00 IDT 2012 | Sat Jan 26 18:00:00 IST 2013 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1155 | TT_TASK | Notice to Contract 824 the anticipated dates of break out TBM Shaft | Sat Jun 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1156 | TT_TASK | Fabrication of tunnel segment mould | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
1157 | TT_TASK | Fabrication 50% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1158 | TT_TASK | Fabrication 100% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
1159 | TT_TASK | Fabrication 30% of North Tunnel North Bound (Uptrack) Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1160 | TT_TASK | Fabrication 60% of North Tunnel North Bound (Uptrack) Precast Lining | Thu Oct 18 08:00:00 IST 2012 | Thu Feb 21 18:00:00 IST 2013 | Thu Oct 18 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1161 | TT_TASK | Fabrication 100% of North Tunnel North Bound (Uptrack) Precast Lining | Mon Aug 19 08:00:00 IDT 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Dec 03 08:00:00 IST 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1163 | TT_TASK | Assemble, T&C of TBM | Fri Jun 01 08:00:00 IDT 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Oct 16 00:00:00 IST 2012 |  | COMPLETED
1164 | TT_TASK | TBM drive & lining installation CH123+369 to CH123+283 Initial Drive (86m) | Sat Nov 03 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 | Wed Oct 17 00:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1165 | TT_TASK | Change Plant (Back-up cars) | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1166 | TT_TASK | TBM drive & lining installation CH123+283 to CH123+183 | Thu Jun 27 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1167 | TT_TASK | TBM drive & lining installation CH123+183 to CH123+083 | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1168 | TT_TASK | TBM drive & lining installation CH123+083 to CH122+983 | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1169 | TT_TASK | TBM drive & lining installation CH122+983 to CH122+883 | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1170 | TT_TASK | TBM drive & lining installation CH122+883 to CH122+783 | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Jun 13 08:00:00 IDT 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
1171 | TT_TASK | TBM drive & lining installation CH122+783 to CH122+683 | Sat Nov 02 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1172 | TT_TASK | TBM drive & lining installation CH122+683 to CH122+583 | Tue Dec 03 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Wed Feb 26 18:00:00 IST 2014 |  | COMPLETED
1173 | TT_TASK | TBM drive & lining installation CH122+583 to CH122+491 | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Feb 27 08:00:00 IST 2014 | Sat Aug 16 00:00:00 IDT 2014 |  | COMPLETED
1174 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1175 | TT_TASK | Dis-assemble TBM | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
1176 | TT_TASK | Invert slab, side walkway | Sat Oct 04 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 | Mon Sep 15 08:00:00 IDT 2014 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1177 | TT_TASK | Installation of cable bracket | Tue Dec 30 08:00:00 IST 2014 | Tue Jan 13 18:00:00 IST 2015 | Fri Sep 12 08:00:00 IDT 2014 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
1178 | TT_TASK | Provision of assess open for DC and modify of strut S1 and S2 at north bound | Tue Nov 04 11:12:00 IST 2014 | Thu Dec 04 11:12:00 IST 2014 | Wed Oct 01 08:00:00 IDT 2014 | Sat Oct 18 18:00:00 IDT 2014 |  | COMPLETED
1180 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Oct 06 13:00:00 IDT 2014 | Mon Oct 20 12:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
1181 | TT_TASK | Assemble, T&C of TBM | Mon Nov 03 08:00:00 IST 2014 | Fri Jan 02 18:00:00 IST 2015 | Sat Oct 04 08:00:00 IDT 2014 | Fri Nov 28 18:00:00 IST 2014 |  | COMPLETED
1182 | TT_TASK | Setup back-up plant for final drive | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
1183 | TT_TASK | Reinstate of noise enclosure | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Sat Nov 29 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1184 | TT_TASK | TBM drive & lining installation CH123+384 to CH123+284 (Initial Drive) | Sat Dec 06 08:00:00 IST 2014 | Thu Jan 22 18:00:00 IST 2015 | Tue Dec 02 00:00:00 IST 2014 | Tue Jan 20 18:00:00 IST 2015 |  | COMPLETED
1185 | TT_TASK | TBM drive & lining installation CH123+184 to CH123+084 | Wed Jan 21 08:00:00 IST 2015 | Wed Jan 28 18:00:00 IST 2015 | Wed Jan 21 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 |  | COMPLETED
1186 | TT_TASK | TBM drive & lining installation CH123+084 to CH122+984 | Wed Feb 04 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 | Thu Feb 12 08:00:00 IST 2015 | Thu Feb 26 18:00:00 IST 2015 |  | COMPLETED
1187 | TT_TASK | TBM drive & lining installation CH122+984 to CH122+884 | Thu Feb 12 08:00:00 IST 2015 | Tue Feb 24 18:00:00 IST 2015 | Fri Feb 27 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1188 | TT_TASK | TBM drive & lining installation CH122+884 to CH122+784 | Tue Mar 10 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Wed May 27 18:00:00 IDT 2015 |  | COMPLETED
1189 | TT_TASK | TBM drive & lining installation CH122+784 to CH122+684 | Wed May 06 08:00:00 IDT 2015 | Thu May 14 18:00:00 IDT 2015 | Thu May 28 08:00:00 IDT 2015 | Sat Jul 11 18:00:00 IDT 2015 |  | COMPLETED
1190 | TT_TASK | TBM drive & lining installation CH122+684 to CH122+584 | Fri Jul 03 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
1191 | TT_TASK | TBM drive & lining installation CH122+584 to CH122+506 | Tue Nov 03 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 |  | COMPLETED
1192 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 |  | COMPLETED
1193 | TT_TASK | Dis-assemble TBM | Wed Dec 16 08:00:00 IST 2015 | Fri Jan 22 18:00:00 IST 2016 | Sun Dec 13 08:00:00 IST 2015 | Sun Mar 13 18:00:00 IST 2016 |  | COMPLETED
1194 | TT_TASK | Invert slab, side walkway | Fri Apr 01 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 | Mon Mar 14 08:00:00 IST 2016 | Tue May 24 18:00:00 IDT 2016 |  | COMPLETED
1195 | TT_TASK | Installation of cable bracket | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Mar 15 18:00:00 IST 2016 |  | COMPLETED
1196 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Mon Feb 01 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 22 18:00:00 IST 2016 |  | COMPLETED
1199 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 1 (From Downtrack to Centre of CP) | Thu Apr 10 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Sat Jun 28 18:00:00 IDT 2014 |  | COMPLETED
1200 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Sun Nov 09 18:00:00 IST 2014 |  | COMPLETED
1201 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1202 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 18:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1203 | TT_TASK | Excavation 0-4mts with Shotcrete | Mon Feb 02 08:00:00 IST 2015 | Tue Feb 17 18:00:00 IST 2015 | Mon Feb 23 08:00:00 IST 2015 | Mon Mar 30 18:00:00 IDT 2015 |  | COMPLETED
1204 | TT_TASK | Invert Concrete | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1205 | TT_TASK | Wall and Roof concrete | Thu Apr 16 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 |  | COMPLETED
1206 | TT_TASK | Dismantle Temporary frame | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 |  | COMPLETED
1207 | TT_TASK | Install Door to Cross Passage (By contract 827) | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 |  | COMPLETED
1208 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 2 (From Centre of CP to Uptrack) | Sat Oct 17 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Sep 07 08:00:00 IDT 2015 | Tue Dec 01 18:00:00 IST 2015 |  | COMPLETED
1209 | TT_TASK | Probe/Grout | Thu Jun 25 08:00:00 IDT 2015 | Mon Jul 06 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Fri Apr 10 18:00:00 IDT 2015 |  | COMPLETED
1210 | TT_TASK | Coring of Segment | Tue Jul 07 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Sat Apr 11 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1211 | TT_TASK | Removal of segment | Sat Jul 11 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
1212 | TT_TASK | Excavation 0-4mts with Shotcrete | Wed Jul 15 08:00:00 IDT 2015 | Sat Jul 25 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1213 | TT_TASK | Invert Concrete | Sat Jul 18 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 | Thu May 07 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1214 | TT_TASK | Wall and Roof concrete | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1215 | TT_TASK | Dismantle Temporary frame | Tue Jan 19 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 04 18:00:00 IST 2016 |  | COMPLETED
1216 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Feb 22 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Fri Feb 05 08:00:00 IST 2016 | Sat Feb 06 18:00:00 IST 2016 |  | COMPLETED
1218 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 1 (From Downtrack to Centre of CP) | Tue Mar 11 08:00:00 IST 2014 | Wed Mar 26 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1219 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Wed Nov 12 18:00:00 IST 2014 |  | COMPLETED
1220 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Thu Nov 13 08:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1221 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Tue Nov 18 08:00:00 IST 2014 | Thu Nov 20 18:00:00 IST 2014 |  | COMPLETED
1222 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Sat Nov 22 08:00:00 IST 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1223 | TT_TASK | Invert Concrete | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
1224 | TT_TASK | Wall and Roof concrete | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1225 | TT_TASK | Dismantle Temporary frame | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1226 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1227 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 2 (From Centre of CP to Uptrack) | Thu May 21 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Mar 09 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1228 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Mon May 04 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1229 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
1230 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1231 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 22 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
1232 | TT_TASK | Invert Concrete | Sat Aug 08 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Wed Jul 08 18:00:00 IDT 2015 |  | COMPLETED
1233 | TT_TASK | Wall and Roof concrete | Tue Aug 25 08:00:00 IDT 2015 | Mon Sep 07 18:00:00 IDT 2015 | Thu Jul 09 08:00:00 IDT 2015 | Sat Aug 15 18:00:00 IDT 2015 |  | COMPLETED
1234 | TT_TASK | Dismantle Temporary frame | Tue Sep 22 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 | Mon Aug 17 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 |  | COMPLETED
1235 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1237 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 1 (From Downtrack to Centre of CP) | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Sat May 24 18:00:00 IDT 2014 |  | COMPLETED
1238 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
1239 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1240 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 |  | COMPLETED
1241 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Mon Nov 17 08:00:00 IST 2014 | Sat Nov 29 18:00:00 IST 2014 |  | COMPLETED
1242 | TT_TASK | Invert Concrete | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 |  | COMPLETED
1243 | TT_TASK | Wall and Roof concrete | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 |  | COMPLETED
1244 | TT_TASK | Dismantle Temporary frame | Tue Dec 30 08:00:00 IST 2014 | Wed Jan 07 18:00:00 IST 2015 | Tue Dec 30 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1245 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1246 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 2 (From Centre of CP to Uptrack) | Fri May 08 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 |  | COMPLETED
1247 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
1248 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
1249 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Thu May 07 18:00:00 IDT 2015 |  | COMPLETED
1250 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
1251 | TT_TASK | Invert Concrete | Wed Aug 05 08:00:00 IDT 2015 | Fri Aug 14 18:00:00 IDT 2015 | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
1252 | TT_TASK | Wall and Roof concrete | Tue Sep 15 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Wed Aug 26 18:00:00 IDT 2015 |  | COMPLETED
1253 | TT_TASK | Dismantle Temporary frame | Sat Oct 17 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Oct 08 18:00:00 IDT 2015 |  | COMPLETED
1254 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1258 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 |  | COMPLETED
1259 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1260 | TT_TASK | D-wall construction (1192m3) | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 |  | COMPLETED
1261 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1262 | TT_TASK | Construct capping beam, cobble, etc. (including bay 6 and 5) | Sat Oct 27 08:00:00 IST 2012 | Sat Feb 16 18:00:00 IST 2013 | Sat Oct 27 08:00:00 IST 2012 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1264 | TT_TASK | Excavate up to +22.0mPD (1860m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1265 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 |  | COMPLETED
1266 | TT_TASK | Excavate up to +16.5mPD (3410m3) | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 |  | COMPLETED
1267 | TT_TASK | Install Strut S2 +17.0mPD | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 |  | COMPLETED
1268 | TT_TASK | Excavate up to +11.0mPD (3410m3) | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 |  | COMPLETED
1269 | TT_TASK | Install Strut S3 +11.5mPD | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 |  | COMPLETED
1270 | TT_TASK | Excavate up to +7.0mPD (2480m3) | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 |  | COMPLETED
1271 | TT_TASK | Install Strut S4 +7.5mPD | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1272 | TT_TASK | Excavate up to +3.5mPD (2170m3) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 |  | COMPLETED
1273 | TT_TASK | Install Strut S5 +4.0mPD | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1274 | TT_TASK | Excavate up to formation (2294m3) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1275 | TT_TASK | Construct temp. 500mm thick plain concrete base slab | Thu Oct 18 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 |  | COMPLETED
1276 | TT_TASK | Removal of South Bound strut to +9.50mPD | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1277 | TT_TASK | Removal of North Bound strut to +9.50mPD | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 |  | COMPLETED
1278 | TT_TASK | Construct temp. 500mm thick TBM concrete base slab | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1279 | TT_TASK | Construction entrance seal for TBM at South Bound | Mon Nov 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1280 | TT_TASK | Construction entrance seal for TBM at North Bound | Sat Jul 20 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1281 | TT_TASK | Saw cut South Bound diaphragm wall | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1282 | TT_TASK | Saw cut North Bound diaphragm wall | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1286 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 05 18:00:00 IDT 2014 | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 |  | COMPLETED
1287 | TT_TASK | Erect external formwork (Base Slab) | Sat Sep 06 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 21 18:00:00 IDT 2014 |  | COMPLETED
1288 | TT_TASK | Rebar fixing (Base Slab) | Wed Sep 10 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Tue Jul 22 08:00:00 IDT 2014 | Sat Jul 26 18:00:00 IDT 2014 |  | COMPLETED
1289 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Sep 15 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Sun Jul 27 08:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1290 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Thu Aug 14 18:00:00 IDT 2014 |  | COMPLETED
1291 | TT_TASK | Concreting (Base Slab) (225m3) | Sat Aug 09 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Fri Aug 15 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
1292 | TT_TASK | Curing (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
1293 | TT_TASK | Removal of formwork (Base Slab) | Tue Aug 12 08:00:00 IDT 2014 | Tue Aug 12 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1294 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed Aug 13 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Mon Sep 15 18:00:00 IDT 2014 |  | COMPLETED
1295 | TT_TASK | Rebar fixing (Wall & Roof) | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 |  | COMPLETED
1296 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 |  | COMPLETED
1297 | TT_TASK | Clearing and inspection (Wall & Roof) | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
1298 | TT_TASK | Concreting (Wall & Roof) (450m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
1299 | TT_TASK | Curing (Wall & Roof) | Sat Oct 11 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
1300 | TT_TASK | Removal external formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1301 | TT_TASK | Removal internal falsework (Wall & Roof) | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 |  | COMPLETED
1302 | TT_TASK | Side walkway and cable bracket (102m3) | Sat Oct 18 08:00:00 IDT 2014 | Wed Oct 29 18:00:00 IST 2014 | Mon Sep 01 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1304 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Wed Nov 11 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Oct 19 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1305 | TT_TASK | Erect external formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 |  | COMPLETED
1306 | TT_TASK | Rebar fixing (Base Slab) | Mon Nov 16 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Tue Oct 27 08:00:00 IST 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1307 | TT_TASK | Erect internal kicker formwork (Base Slab) | Fri Nov 20 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Oct 31 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 |  | COMPLETED
1308 | TT_TASK | Clearing and inspection (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
1309 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1310 | TT_TASK | Curing (Base Slab) | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 |  | COMPLETED
1311 | TT_TASK | Removal of formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 |  | COMPLETED
1312 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
1313 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Dec 09 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
1314 | TT_TASK | Erect external formwork (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Thu Jan 07 18:00:00 IST 2016 |  | COMPLETED
1315 | TT_TASK | Clearing and inspection (Wall & Roof) | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Fri Jan 08 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
1316 | TT_TASK | Concreting (Wall & Roof) (450m3) | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
1317 | TT_TASK | Curing (Wall & Roof) | Tue Jan 12 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
1318 | TT_TASK | Removal external formwork (Wall ) | Thu Jan 14 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
1319 | TT_TASK | Removal internal falsework, formwork and reproping (Wall & Roof) | Thu Jan 28 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 |  | COMPLETED
1320 | TT_TASK | Side walkway and cable bracket (102m3) | Wed Dec 23 08:00:00 IST 2015 | Wed Jan 06 18:00:00 IST 2016 | Wed Nov 11 08:00:00 IST 2015 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
1322 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 |  | COMPLETED
1323 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 |  | COMPLETED
1324 | TT_TASK | Backfilling to 0.5m below S3 (+11.0mPD) (3486m3) | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 |  | COMPLETED
1325 | TT_TASK | Removal strut S3 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
1326 | TT_TASK | Backfilling to 0.5m below S2 (+16.5mPD) (3410m3) | Wed Mar 16 08:00:00 IST 2016 | Fri Apr 08 18:00:00 IDT 2016 | Wed Mar 16 08:00:00 IST 2016 | Tue Apr 12 18:00:00 IDT 2016 |  | COMPLETED
1327 | TT_TASK | Removal strut S2 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 |  | COMPLETED
1328 | TT_TASK | Backfilling to 0.5m below S1 (+22.0mPD) (3410m3) | Fri Apr 15 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 | Fri Apr 15 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
1329 | TT_TASK | Removal strut S1 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 |  | COMPLETED
1330 | TT_TASK | Backfilling to original ground level (approx. +25.0mPD) (1860m3) | Thu May 05 08:00:00 IDT 2016 | Tue May 17 18:00:00 IDT 2016 | Thu May 05 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
1333 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1334 | TT_TASK | D-wall construction (2844m3) | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1335 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1337 | TT_TASK | Excavate up to +22.0mPD (3720m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1338 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 |  | COMPLETED
1339 | TT_TASK | Excavate up to +16.5mPD (4880m3) | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 |  | COMPLETED
1340 | TT_TASK | Install Strut S2 +17.0mPD | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 |  | COMPLETED
1341 | TT_TASK | Excavate up to +11.0mPD (6820m3) | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
1342 | TT_TASK | Install Strut S3 +11.5mPD | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 |  | COMPLETED
1343 | TT_TASK | Excavate up to +7.0mPD (4960m3) | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 |  | COMPLETED
1344 | TT_TASK | Install Strut S4 +7.5mPD | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1345 | TT_TASK | Excavate up to +3.5mPD (4340m3) | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1346 | TT_TASK | Install Strut S5 +4.0mPD | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 |  | COMPLETED
1347 | TT_TASK | Excavate up to formation (4960m3) | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 |  | COMPLETED
1348 | TT_TASK | Construct temp. 500mm thick plain concrete base slab at Bay 5 & 6 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1349 | TT_TASK | Excavation to formation and place blinding Bay 4a | Thu Oct 18 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1350 | TT_TASK | Excavation to formation and place blinding Bay 4b | Fri Jun 21 08:00:00 IDT 2013 | Fri Jul 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1351 | TT_TASK | Excavation to formation and place blinding Bay3 | Sat Jul 13 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1352 | TT_TASK | Excavation to formation and place blinding Bay2 to Bay1 | Wed Jul 24 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1356 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 |  | COMPLETED
1357 | TT_TASK | Erect external formwork for base slab | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 |  | COMPLETED
1358 | TT_TASK | Rebar fixing for base slab | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1359 | TT_TASK | Erect internal kicker formwork for base slab | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1360 | TT_TASK | Concreting for base slab (363m3) | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1361 | TT_TASK | Curing for base slab | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1362 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1363 | TT_TASK | Removal of formwork for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1364 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1365 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 27 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1366 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1367 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1368 | TT_TASK | Curing for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1369 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1370 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 10 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1371 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 19 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jan 24 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1372 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 08 08:00:00 IST 2015 | Tue Jan 13 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1374 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 |  | COMPLETED
1375 | TT_TASK | Erect external formwork for base slab | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1376 | TT_TASK | Rebar fixing for base slab | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1377 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 |  | COMPLETED
1378 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1379 | TT_TASK | Curing for base slab | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1380 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1381 | TT_TASK | Removal of formwork for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1382 | TT_TASK | Rebar fixing for central slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1383 | TT_TASK | Erect external formwork for central slab | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1384 | TT_TASK | Concreting for central slab (450m3) | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1385 | TT_TASK | Curing for central slab | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1386 | TT_TASK | Preparation of construction joint for central slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1387 | TT_TASK | Removal of formwork for central slab | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1388 | TT_TASK | Removal strut S5 and S4 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1389 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1390 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1391 | TT_TASK | Erect external formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1392 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1393 | TT_TASK | Curing for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1394 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1395 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 08 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1396 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1397 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Nov 19 08:00:00 IST 2015 | Tue Nov 24 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 |  | COMPLETED
1400 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1401 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1402 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1403 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1404 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1405 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1406 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1407 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1408 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1409 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1410 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 10 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1411 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1412 | TT_TASK | Curing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1413 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1414 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1415 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1416 | TT_TASK | Side walkway and cable bracket | Fri Jan 02 08:00:00 IST 2015 | Wed Jan 07 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1418 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1419 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1420 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1421 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1422 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1423 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1424 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1425 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1426 | TT_TASK | Rebar fixing for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1427 | TT_TASK | Erect external formwork for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1428 | TT_TASK | Concreting for central slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1429 | TT_TASK | Curing for central slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1430 | TT_TASK | Preparation of construction joint for central slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1431 | TT_TASK | Removal of formwork for central slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 21 18:00:00 IST 2012 |  | COMPLETED
1432 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1433 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1434 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1435 | TT_TASK | Erect external formwork for wall | Mon Jul 15 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1436 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1437 | TT_TASK | Curing for wall and roof | Sun Jul 21 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1438 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1439 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 22 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1440 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 31 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1441 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Sep 16 08:00:00 IDT 2015 | Mon Sep 21 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1443 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1444 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1445 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1446 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1447 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1448 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1449 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1450 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1451 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1452 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1453 | TT_TASK | Erect external formwork for wall | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1454 | TT_TASK | Concreting for wall and roof (444m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1455 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1456 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1457 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Sat Feb 09 18:00:00 IST 2013 |  | COMPLETED
1458 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Nov 09 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Tue Oct 06 08:00:00 IDT 2015 | Sat Oct 10 18:00:00 IDT 2015 |  | COMPLETED
1461 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1462 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1463 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1464 | TT_TASK | Erect internal kicker formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1465 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1466 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1467 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1468 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1469 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1470 | TT_TASK | Curing | Wed Jun 12 08:00:00 IDT 2013 | Wed Jun 12 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1471 | TT_TASK | Removal strut S5 and S4 | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1473 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1474 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1475 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1476 | TT_TASK | Concreting for wall and roof (450m3) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1477 | TT_TASK | Curing for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1478 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1479 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1480 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 29 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1481 | TT_TASK | Side walkway and cable bracket | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1483 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1484 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1485 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1486 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1487 | TT_TASK | Curing for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1488 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1489 | TT_TASK | Removal external wall formwork for wall | Wed Jun 26 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1490 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1491 | TT_TASK | Side walkway and cable bracket | Fri Sep 04 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
1494 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1495 | TT_TASK | Erect external formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1496 | TT_TASK | Rebar fixing for base slab | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1497 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1498 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 |  | COMPLETED
1499 | TT_TASK | Curing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1500 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1501 | TT_TASK | Removal of formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1502 | TT_TASK | Shear beam | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1503 | TT_TASK | Curing | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1504 | TT_TASK | Removal strut S5 and S4 | Wed Jun 19 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1506 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 24 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1507 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1508 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1509 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1510 | TT_TASK | Curing for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1511 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1512 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1513 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1514 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
1516 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1517 | TT_TASK | Rebar fixing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1518 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1519 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1520 | TT_TASK | Curing for wall and roof | Sun Jun 23 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1521 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1522 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 25 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1523 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 03 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1524 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Aug 29 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1527 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1528 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Sat Dec 22 18:00:00 IST 2012 |  | COMPLETED
1529 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1530 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1531 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1532 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1533 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1534 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Fri Jan 11 18:00:00 IST 2013 |  | COMPLETED
1535 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Jan 12 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1536 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1537 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1539 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1540 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1541 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1542 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1543 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1544 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1545 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1546 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1547 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 |  | COMPLETED
1549 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1550 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Mon Feb 25 18:00:00 IST 2013 |  | COMPLETED
1551 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1552 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1553 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1554 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1555 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1556 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1557 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Aug 24 08:00:00 IDT 2015 | Fri Aug 28 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1560 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1561 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1562 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1563 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1564 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1565 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1566 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1567 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1568 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1569 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1570 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1572 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1573 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1574 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1575 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1576 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1577 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1578 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1579 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1580 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
1582 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1583 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1584 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1585 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1586 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1587 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1588 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1589 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1590 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Aug 18 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1593 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1594 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1595 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1596 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1597 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1598 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1599 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1600 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1601 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1602 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1603 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1605 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 31 18:00:00 IDT 2013 |  | COMPLETED
1606 | TT_TASK | Rebar fixing for wall and roof | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 |  | COMPLETED
1607 | TT_TASK | Erect external formwork for wall and roof | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 | Fri Sep 06 08:00:00 IDT 2013 | Thu Sep 12 18:00:00 IDT 2013 |  | COMPLETED
1608 | TT_TASK | Concreting for wall and roof (450m3) | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 |  | COMPLETED
1609 | TT_TASK | Curing for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1610 | TT_TASK | Preparation of construction joint for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1611 | TT_TASK | Removal external and internal formwork for wall | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Wed Sep 25 18:00:00 IDT 2013 |  | COMPLETED
1612 | TT_TASK | Removal internal falsework and formwork for roof | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1613 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 08 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1615 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 20 18:00:00 IST 2013 |  | COMPLETED
1616 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1617 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1618 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1619 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1620 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1621 | TT_TASK | Removal external wall formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1622 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1623 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Aug 12 08:00:00 IDT 2015 | Mon Aug 17 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1626 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1627 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1628 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Feb 14 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1629 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1630 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Mon Feb 18 18:00:00 IST 2013 |  | COMPLETED
1631 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1632 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1633 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1634 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1635 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1636 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1638 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jul 12 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1639 | TT_TASK | Rebar fixing for wall and roof | Wed Jul 17 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1640 | TT_TASK | Erect external formwork for wall and roof | Wed Aug 14 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1641 | TT_TASK | Concreting for wall and roof (450m3) | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1642 | TT_TASK | Curing for wall and roof | Sun Aug 11 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1643 | TT_TASK | Preparation of construction joint for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1644 | TT_TASK | Removal external and internal formwork for wall | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1645 | TT_TASK | Removal internal falsework and formwork for roof | Wed Aug 21 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1646 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 03 08:00:00 IST 2014 | Fri Mar 07 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1648 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1649 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1650 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Apr 09 08:00:00 IDT 2013 | Thu Apr 11 18:00:00 IDT 2013 |  | COMPLETED
1651 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1652 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1653 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1654 | TT_TASK | Removal external wall formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1655 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
1656 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Aug 06 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Mon Jul 27 08:00:00 IDT 2015 | Fri Jul 31 18:00:00 IDT 2015 |  | COMPLETED
1658 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Sep 12 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1659 | TT_TASK | Rebar fixing for roof | Tue Sep 17 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1660 | TT_TASK | Erect external formwork for roof | Thu Sep 19 08:00:00 IDT 2013 | Thu Sep 19 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1661 | TT_TASK | Concreting for roof (444m3) | Sat Sep 21 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1662 | TT_TASK | Curing for roof | Sun Sep 22 08:00:00 IDT 2013 | Tue Oct 01 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1663 | TT_TASK | Preparation of construction joint for roof | Mon Sep 23 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1664 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1665 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1668 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1669 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1670 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1671 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1672 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1673 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1674 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1675 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1676 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1677 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1678 | TT_TASK | Removal strut S5 and S4 | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1680 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Thu Apr 25 18:00:00 IDT 2013 |  | COMPLETED
1681 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri May 03 08:00:00 IDT 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
1682 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Thu May 16 08:00:00 IDT 2013 | Thu May 23 18:00:00 IDT 2013 |  | COMPLETED
1683 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1684 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1685 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1686 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Wed May 29 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1687 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1688 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 19 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1690 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Fri Apr 19 18:00:00 IDT 2013 |  | COMPLETED
1691 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1692 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Apr 25 08:00:00 IDT 2013 | Sat Apr 27 18:00:00 IDT 2013 |  | COMPLETED
1693 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1694 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1695 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1696 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1697 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1698 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 02 08:00:00 IDT 2015 | Sat Apr 11 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Feb 27 18:00:00 IST 2015 |  | COMPLETED
1700 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1701 | TT_TASK | Rebar fixing for roof | Tue Aug 06 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1702 | TT_TASK | Erect external formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1703 | TT_TASK | Concreting for roof (444m3) | Fri Aug 09 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 |  | COMPLETED
1704 | TT_TASK | Curing for roof | Thu Aug 01 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1705 | TT_TASK | Preparation of construction joint for roof | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 |  | COMPLETED
1706 | TT_TASK | Removal internal falsework and formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1707 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 09 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1710 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Wed Feb 20 18:00:00 IST 2013 |  | COMPLETED
1711 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1712 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1713 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1714 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1715 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1716 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1717 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1718 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1719 | TT_TASK | Curing | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1720 | TT_TASK | Removal strut S5 and S4 | Mon Jun 24 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1722 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1723 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1724 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Wed Jul 10 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1725 | TT_TASK | Concreting for wall and roof (450m3) | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1726 | TT_TASK | Curing for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1727 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1728 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 |  | COMPLETED
1729 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 |  | COMPLETED
1730 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1732 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1733 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1734 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1735 | TT_TASK | Concreting for wall and roof (450m3) | Tue Sep 03 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1736 | TT_TASK | Curing for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1737 | TT_TASK | Preparation of construction joint for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 |  | COMPLETED
1738 | TT_TASK | Removal external and internal formwork for wall | Thu Sep 05 08:00:00 IDT 2013 | Fri Sep 06 18:00:00 IDT 2013 | Thu Aug 22 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1739 | TT_TASK | Removal internal falsework and formwork for roof | Sat Sep 14 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 |  | COMPLETED
1740 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 05 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1742 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1743 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1744 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1745 | TT_TASK | Concreting for roof (363m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1746 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Sun Oct 20 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1747 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1748 | TT_TASK | Removal internal falsework and formwork for roof | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1749 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Dec 24 13:00:00 IST 2013 | Thu Jan 02 12:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1752 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1753 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1754 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1755 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Apr 12 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1756 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1757 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1758 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1759 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1760 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1761 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1762 | TT_TASK | Removal strut S5 and S4 | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1764 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Aug 05 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1765 | TT_TASK | Rebar fixing for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1766 | TT_TASK | Erect external formwork for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1767 | TT_TASK | Concreting for wall and roof (450m3) | Thu Aug 15 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1768 | TT_TASK | Curing for wall and roof | Fri Aug 16 08:00:00 IDT 2013 | Sun Aug 25 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1769 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1770 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1771 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 |  | COMPLETED
1772 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Feb 04 08:00:00 IST 2014 | Sat Feb 08 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1774 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Aug 07 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1775 | TT_TASK | Rebar fixing for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1776 | TT_TASK | Erect external formwork for wall and roof | Thu Aug 15 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1777 | TT_TASK | Concreting for wall and roof (450m3) | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1778 | TT_TASK | Curing for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1779 | TT_TASK | Preparation of construction joint for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 |  | COMPLETED
1780 | TT_TASK | Removal external and internal formwork for wall | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Wed Aug 21 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 |  | COMPLETED
1781 | TT_TASK | Removal internal falsework and formwork for roof | Mon Sep 16 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1782 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Nov 19 08:00:00 IST 2014 | Mon Nov 24 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1784 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1785 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1786 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1787 | TT_TASK | Concreting for roof (450m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1788 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1789 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1790 | TT_TASK | Removal internal falsework and formwork for roof | Fri Oct 18 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1791 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 13 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1794 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1795 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1796 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1797 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1798 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 28 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1799 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1800 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1801 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1802 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1803 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1804 | TT_TASK | Removal strut S5 and S4 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1806 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1807 | TT_TASK | Rebar fixing for wall and roof | Sat Jul 20 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1808 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1809 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1810 | TT_TASK | Curing for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1811 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1812 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 29 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1813 | TT_TASK | Removal internal falsework and formwork for roof | Tue Aug 06 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1814 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 18:00:00 IST 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1816 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1817 | TT_TASK | Rebar fixing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1818 | TT_TASK | Erect external formwork for wall and roof | Fri Jul 19 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1819 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1820 | TT_TASK | Curing for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Thu Mar 28 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1821 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Mar 29 08:00:00 IDT 2013 | Fri Mar 29 18:00:00 IDT 2013 |  | COMPLETED
1822 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Sat Mar 30 08:00:00 IDT 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1823 | TT_TASK | Removal internal falsework and formwork for roof | Fri Aug 02 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Mon Apr 01 18:00:00 IDT 2013 |  | COMPLETED
1824 | TT_TASK | Side walkway and cable bracket | Thu Nov 13 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1826 | TT_TASK | Erect internal formwork & Falsework for roof | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1827 | TT_TASK | Rebar fixing for roof | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 |  | COMPLETED
1828 | TT_TASK | Erect shutter formwork for roof | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 09 18:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1829 | TT_TASK | Concreting for roof (450m3) | Tue Sep 10 08:00:00 IDT 2013 | Tue Sep 10 18:00:00 IDT 2013 | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 |  | COMPLETED
1830 | TT_TASK | Curing for roof | Wed Sep 11 08:00:00 IDT 2013 | Fri Sep 20 18:00:00 IDT 2013 | Tue Jul 23 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 |  | COMPLETED
1831 | TT_TASK | Preparation of construction joint for roof | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 11 18:00:00 IDT 2013 | Sat Aug 03 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1832 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 26 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 |  | COMPLETED
1833 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 06 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Aug 13 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1835 | TT_TASK | Water proofing and soil backfilling to 0.5m below top of Tunnel Bay 3 to Bay 1 | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1836 | TT_TASK | Mass infill between D-wall and tunnel wall | Fri Oct 11 08:00:00 IDT 2013 | Wed Oct 16 18:00:00 IDT 2013 | Fri Sep 20 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1837 | TT_TASK | Removal S3 and S2 | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
1838 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 4 | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Sat May 18 18:00:00 IDT 2013 |  | COMPLETED
1839 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 5 and remove S3 & S2 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1840 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 6 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1843 | TT_TASK | Pre-drilling and guidewall | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1844 | TT_TASK | D-wall design review | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1845 | TT_TASK | D-wall construction (4741m3) | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 |  | COMPLETED
1846 | TT_TASK | Shear pin and pumping test | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 15 18:00:00 IST 2012 | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1848 | TT_TASK | ELS works to formation level from SN16 to SN19 (soil: 8,700m3 @350m3/day, Install S1 to S3 strut 5 days/layer) | Wed Sep 25 08:00:00 IDT 2013 | Wed Nov 13 18:00:00 IST 2013 | Wed May 08 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1849 | TT_TASK | Design temporary bridge and approval | Mon Sep 01 08:00:00 IDT 2014 | Wed Nov 12 18:00:00 IST 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1850 | TT_TASK | Application of tree transplant | Sat Jun 01 08:00:00 IDT 2013 | Wed Oct 23 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1851 | TT_TASK | Tree transplant | Tue Oct 14 08:00:00 IDT 2014 | Mon Nov 10 18:00:00 IST 2014 | Tue Sep 02 08:00:00 IDT 2014 | Tue Sep 30 18:00:00 IDT 2014 |  | COMPLETED
1852 | TT_TASK | Erection temporary bridge deck | Fri Oct 03 08:00:00 IDT 2014 | Fri Dec 05 18:00:00 IST 2014 | Fri Oct 03 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1853 | TT_TASK | ELS works to formation level from SN10 to SN15 (soil: 9,455m3 @330m3/day, install S1 to S3 strut 5 days/layer) | Mon Nov 24 08:00:00 IST 2014 | Sat Jan 17 18:00:00 IST 2015 | Mon Nov 24 08:00:00 IST 2014 | Tue Jun 23 18:00:00 IDT 2015 |  | COMPLETED
1856 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
1857 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1858 | TT_TASK | Erect external formwork for wall and roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1859 | TT_TASK | Concreting for wall and roof (215m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
1860 | TT_TASK | Curing for wall and roof | Sun Dec 08 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
1861 | TT_TASK | Preparation of construction joint for wall and roof | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1862 | TT_TASK | Removal external and internal formwork for wall | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1863 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1864 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 03 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 | Mon Mar 24 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
1866 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 14 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1867 | TT_TASK | Rebar fixing for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1868 | TT_TASK | Erect external formwork for wall and roof | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1869 | TT_TASK | Concreting for wall and roof (215m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1870 | TT_TASK | Curing for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Sun Dec 29 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1871 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
1872 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 17 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
1873 | TT_TASK | Removal internal falsework and formwork for roof | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1874 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 |  | COMPLETED
1876 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 28 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Nov 28 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1877 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1878 | TT_TASK | Erect external formwork for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1879 | TT_TASK | Concreting for wall and roof (215m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1880 | TT_TASK | Curing for wall and roof | Wed Jan 01 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
1881 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
1882 | TT_TASK | Removal external and internal formwork for wall | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 |  | COMPLETED
1883 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
1884 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 |  | COMPLETED
1886 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1887 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 14 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1888 | TT_TASK | Erect external formwork for wall and roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1889 | TT_TASK | Concreting for wall and roof (215m3) | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1890 | TT_TASK | Curing for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1892 | TT_TASK | Removal external and internal formwork for wall | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1893 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1894 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 |  | COMPLETED
1896 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 08:00:00 IST 2013 |  | COMPLETED
1897 | TT_TASK | Rebar fixing for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1898 | TT_TASK | Erect external formwork for wall and roof | Fri Jan 03 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1899 | TT_TASK | Concreting for wall and roof (215m3) | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1900 | TT_TASK | Curing for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 16 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1901 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Tue Jan 07 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1902 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1903 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1904 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 |  | COMPLETED
1906 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1907 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1908 | TT_TASK | Erect external formwork for wall and roof | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1909 | TT_TASK | Concreting for wall and roof (215m3) | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1910 | TT_TASK | Curing for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1911 | TT_TASK | Preparation of construction joint for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1912 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1913 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1914 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 |  | COMPLETED
1916 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1917 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 |  | COMPLETED
1918 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Tue Jun 04 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 |  | COMPLETED
1919 | TT_TASK | Concreting for wall and roof (333m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1920 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1921 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Wed Jun 12 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1922 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 |  | COMPLETED
1923 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
1924 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 05 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Tue Mar 04 18:00:00 IST 2014 |  | COMPLETED
1926 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1927 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1928 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1929 | TT_TASK | Concreting for wall and roof (412m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1930 | TT_TASK | Curing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Sun Jun 23 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Sat Mar 23 18:00:00 IST 2013 |  | COMPLETED
1931 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Mar 25 08:00:00 IST 2013 | Mon Mar 25 18:00:00 IST 2013 |  | COMPLETED
1932 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Mar 26 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1933 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jun 24 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1934 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 27 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Mon Mar 03 18:00:00 IST 2014 |  | COMPLETED
1936 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1937 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1938 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Apr 02 18:00:00 IDT 2013 |  | COMPLETED
1939 | TT_TASK | Concreting for wall and roof (320m3) | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Apr 05 08:00:00 IDT 2013 | Fri Apr 05 18:00:00 IDT 2013 |  | COMPLETED
1940 | TT_TASK | Curing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 06 08:00:00 IDT 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1941 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1942 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1943 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1944 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jan 21 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Sat Mar 01 18:00:00 IST 2014 |  | COMPLETED
1946 | TT_TASK | Excavation and saw cut D-wall | Thu Apr 02 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Sat Jul 25 18:00:00 IDT 2015 |  | COMPLETED
1947 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Aug 08 16:24:00 IDT 2015 | Mon Aug 10 16:24:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Mon Jul 13 18:00:00 IDT 2015 |  | COMPLETED
1948 | TT_TASK | Erect external formwork for base slab | Mon Aug 10 16:24:00 IDT 2015 | Wed Aug 12 16:24:00 IDT 2015 | Tue Jul 14 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
1949 | TT_TASK | Rebar fixing for base slab | Wed Aug 12 16:24:00 IDT 2015 | Fri Aug 14 16:24:00 IDT 2015 | Wed Jul 15 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1950 | TT_TASK | Erect internal kicker formwork for base slab | Fri Aug 14 16:24:00 IDT 2015 | Mon Aug 17 16:24:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Wed Aug 12 18:00:00 IDT 2015 |  | COMPLETED
1951 | TT_TASK | Concreting for base slab (90m3) | Wed Sep 02 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 | Thu Aug 13 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 |  | COMPLETED
1952 | TT_TASK | Curing for base slab | Thu Sep 03 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Fri Aug 14 08:00:00 IDT 2015 | Thu Aug 20 18:00:00 IDT 2015 |  | COMPLETED
1953 | TT_TASK | Preparation of construction joint for base slab | Thu Sep 03 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Fri Aug 21 08:00:00 IDT 2015 | Fri Aug 21 18:00:00 IDT 2015 |  | COMPLETED
1954 | TT_TASK | Removal of formwork for base slab | Fri Sep 04 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Sat Aug 22 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 |  | COMPLETED
1955 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Sep 05 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 | Mon Aug 24 08:00:00 IDT 2015 | Mon Aug 24 18:00:00 IDT 2015 |  | COMPLETED
1956 | TT_TASK | Curing | Thu Sep 10 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Tue Aug 25 08:00:00 IDT 2015 | Tue Aug 25 18:00:00 IDT 2015 |  | COMPLETED
1957 | TT_TASK | Removal strut S3 | Sat Sep 19 08:00:00 IDT 2015 | Wed Sep 23 18:00:00 IDT 2015 | Wed Sep 16 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
1958 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Sep 24 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
1959 | TT_TASK | Rebar fixing for wall and roof | Wed Sep 30 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 | Fri Sep 25 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 |  | COMPLETED
1960 | TT_TASK | Erect external formwork for wall and roof | Thu Oct 15 08:00:00 IDT 2015 | Fri Oct 16 18:00:00 IDT 2015 | Mon Oct 05 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
1961 | TT_TASK | Concreting for wall and roof (260m3) | Sat Oct 17 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 | Wed Oct 07 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1962 | TT_TASK | Curing for wall and roof | Sun Oct 18 08:00:00 IDT 2015 | Tue Oct 27 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 |  | COMPLETED
1963 | TT_TASK | Preparation of construction joint for wall and roof | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
1964 | TT_TASK | Removal external and internal formwork for wall | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
1965 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 28 08:00:00 IST 2015 | Thu Oct 29 18:00:00 IST 2015 | Thu Oct 22 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1966 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Oct 30 08:00:00 IST 2015 | Wed Nov 04 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1968 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 02 18:00:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 |  | COMPLETED
1969 | TT_TASK | Erect external formwork for base slab | Fri Jul 03 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Tue Jul 21 08:00:00 IDT 2015 | Wed Jul 22 18:00:00 IDT 2015 |  | COMPLETED
1970 | TT_TASK | Rebar fixing for base slab | Mon Jul 06 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 23 08:00:00 IDT 2015 | Fri Jul 24 18:00:00 IDT 2015 |  | COMPLETED
1971 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jul 08 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Sat Jul 25 08:00:00 IDT 2015 | Mon Jul 27 18:00:00 IDT 2015 |  | COMPLETED
1972 | TT_TASK | Concreting for base slab (123m3) | Fri Jul 10 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jul 28 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 |  | COMPLETED
1973 | TT_TASK | Curing for base slab | Sat Jul 11 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1974 | TT_TASK | Preparation of construction joint for base slab | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 |  | COMPLETED
1975 | TT_TASK | Removal of formwork for base slab | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 |  | COMPLETED
1976 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1977 | TT_TASK | Curing | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 |  | COMPLETED
1978 | TT_TASK | Removal strut S3 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1979 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 |  | COMPLETED
1980 | TT_TASK | Rebar fixing for wall and roof | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 |  | COMPLETED
1981 | TT_TASK | Erect external formwork for wall and roof | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 |  | COMPLETED
1982 | TT_TASK | Concreting for wall and roof (260m3) | Fri Oct 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 | Sat Oct 24 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
1983 | TT_TASK | Curing for wall and roof | Sat Oct 03 08:00:00 IDT 2015 | Mon Oct 12 18:00:00 IDT 2015 | Mon Oct 26 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1984 | TT_TASK | Preparation of construction joint for wall and roof | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
1985 | TT_TASK | Removal external and internal formwork for wall | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1986 | TT_TASK | Removal internal falsework and formwork for roof | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1987 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1989 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
1990 | TT_TASK | Erect external formwork for base slab | Mon Jun 15 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1991 | TT_TASK | Rebar fixing for base slab | Wed Jun 17 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
1992 | TT_TASK | Erect internal kicker formwork for base slab | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
1993 | TT_TASK | Concreting for base slab (127m3) | Tue Jun 23 08:00:00 IDT 2015 | Tue Jun 23 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
1994 | TT_TASK | Curing for base slab | Wed Jun 24 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
1995 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 24 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1996 | TT_TASK | Removal of formwork for base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
1997 | TT_TASK | Infill concrete in between D-wall and base slab | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1998 | TT_TASK | Curing | Thu May 28 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1999 | TT_TASK | Removal strut S3 | Fri May 29 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2000 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 03 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2001 | TT_TASK | Rebar fixing for wall and roof | Mon Jun 08 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2002 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2003 | TT_TASK | Concreting for wall and roof (260m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2004 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2005 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2006 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2007 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2008 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 11 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2010 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
2011 | TT_TASK | Erect external formwork for base slab | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
2012 | TT_TASK | Rebar fixing for base slab | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
2013 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
2014 | TT_TASK | Concreting for base slab (127m3) | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
2015 | TT_TASK | Curing for base slab | Thu Jun 11 08:00:00 IDT 2015 | Wed Jun 17 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2016 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 11 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
2017 | TT_TASK | Removal of formwork for base slab | Sat May 23 08:00:00 IDT 2015 | Sat May 23 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
2018 | TT_TASK | Infill concrete in between D-wall and base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
2019 | TT_TASK | Curing | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2020 | TT_TASK | Removal strut S3 | Thu May 28 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2021 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2022 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2023 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2024 | TT_TASK | Concreting for wall and roof (150m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2025 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2026 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2027 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2028 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2029 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jul 06 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
2031 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2032 | TT_TASK | Erect external formwork for base slab | Thu May 21 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2033 | TT_TASK | Rebar fixing for base slab | Sat May 23 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2034 | TT_TASK | Erect internal kicker formwork for base slab | Wed May 27 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2035 | TT_TASK | Concreting for base slab (70m3) | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2036 | TT_TASK | Curing for base slab | Sat May 30 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2037 | TT_TASK | Preparation of construction joint for base slab | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2038 | TT_TASK | Removal of formwork for base slab | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2039 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2040 | TT_TASK | Curing | Sat Jun 06 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2041 | TT_TASK | Removal strut S3 | Mon Jun 08 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat May 23 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2043 | TT_TASK | Rebar fixing for wall and roof | Fri May 29 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2044 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2045 | TT_TASK | Concreting for wall and roof (175m3) | Thu Jun 04 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2046 | TT_TASK | Curing for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sun Jun 14 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2047 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2048 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 03 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 04 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2050 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 29 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
2052 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2053 | TT_TASK | Erect external formwork for base slab | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2054 | TT_TASK | Rebar fixing for base slab | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2055 | TT_TASK | Erect internal kicker formwork for base slab | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2056 | TT_TASK | Concreting for base slab (70m3) | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2057 | TT_TASK | Curing for base slab | Wed Apr 22 08:00:00 IDT 2015 | Tue Apr 28 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2058 | TT_TASK | Preparation of construction joint for base slab | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2059 | TT_TASK | Removal of formwork for base slab | Thu Apr 23 08:00:00 IDT 2015 | Thu Apr 23 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2060 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Apr 24 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2061 | TT_TASK | Curing | Wed Apr 29 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2062 | TT_TASK | Removal strut S3 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2063 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed May 06 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2064 | TT_TASK | Rebar fixing for wall and roof | Thu May 14 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2065 | TT_TASK | Erect external formwork for wall and roof | Mon May 18 08:00:00 IDT 2015 | Tue May 19 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2066 | TT_TASK | Concreting for wall and roof (175m3) | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2067 | TT_TASK | Curing for wall and roof | Thu May 21 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2068 | TT_TASK | Preparation of construction joint for wall and roof | Thu May 21 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2069 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2070 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2071 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jun 23 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
2073 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Fri Nov 15 18:00:00 IST 2013 |  | COMPLETED
2074 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Nov 16 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2075 | TT_TASK | Rebar fixing for base slab | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
2076 | TT_TASK | Erect internal kicker formwork for base slab | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
2077 | TT_TASK | Concreting for base slab (70m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
2078 | TT_TASK | Curing for base slab | Fri Dec 20 08:00:00 IST 2013 | Thu Dec 26 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
2079 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 |  | COMPLETED
2080 | TT_TASK | Removal of formwork for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
2081 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
2082 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2083 | TT_TASK | Removal strut S3 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2084 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Apr 16 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2085 | TT_TASK | Rebar fixing for wall and roof | Thu Apr 24 08:00:00 IDT 2014 | Sat Apr 26 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 |  | COMPLETED
2086 | TT_TASK | Erect external formwork for wall and roof | Mon Apr 28 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Thu Apr 10 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2087 | TT_TASK | Concreting for wall and roof (170m3) | Wed Apr 30 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Sat Apr 12 08:00:00 IDT 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
2088 | TT_TASK | Curing for wall and roof | Thu May 01 08:00:00 IDT 2014 | Sat May 10 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Tue Apr 22 18:00:00 IDT 2014 |  | COMPLETED
2089 | TT_TASK | Preparation of construction joint for wall and roof | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 |  | COMPLETED
2090 | TT_TASK | Removal external and internal formwork for wall | Sat May 03 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Tue Apr 15 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
2091 | TT_TASK | Removal internal falsework and formwork for roof | Mon May 12 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 |  | COMPLETED
2092 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jun 05 08:00:00 IDT 2014 | Tue Jun 10 18:00:00 IDT 2014 | Thu May 29 08:00:00 IDT 2014 | Thu Dec 04 18:00:00 IST 2014 |  | COMPLETED
2094 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2095 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2096 | TT_TASK | Rebar fixing for base slab | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2097 | TT_TASK | Erect internal kicker formwork for base slab | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2098 | TT_TASK | Concreting for base slab (70m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2099 | TT_TASK | Curing for base slab | Sun Dec 08 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2100 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2101 | TT_TASK | Removal of formwork for base slab | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
2102 | TT_TASK | Infill concrete in between D-wall and base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
2103 | TT_TASK | Curing | Sun Dec 15 08:00:00 IST 2013 | Sun Dec 15 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2104 | TT_TASK | Removal strut S3 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2105 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Feb 12 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2106 | TT_TASK | Rebar fixing for wall and roof | Mon Feb 17 08:00:00 IST 2014 | Wed Feb 19 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
2107 | TT_TASK | Erect external formwork for wall and roof | Fri Feb 28 13:48:00 IST 2014 | Mon Mar 03 13:48:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2108 | TT_TASK | Concreting for wall and roof (200m3) | Mon Mar 03 13:48:00 IST 2014 | Tue Mar 04 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2109 | TT_TASK | Curing for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Fri Mar 14 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2110 | TT_TASK | Preparation of construction joint for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Wed Mar 05 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2111 | TT_TASK | Removal external and internal formwork for wall | Wed Mar 05 13:48:00 IST 2014 | Thu Mar 06 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
2112 | TT_TASK | Removal internal falsework and formwork for roof | Fri Mar 14 13:48:00 IST 2014 | Mon Mar 17 13:48:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2113 | TT_TASK | Side walkway and cable bracket (204m3) | Thu May 29 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Wed Dec 03 18:00:00 IST 2014 |  | COMPLETED
2115 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2116 | TT_TASK | Erect external formwork for base slab | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2117 | TT_TASK | Rebar fixing for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2118 | TT_TASK | Erect internal kicker formwork for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2119 | TT_TASK | Concreting for base slab (70m3) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2120 | TT_TASK | Curing for base slab | Tue Dec 03 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2121 | TT_TASK | Preparation of construction joint for base slab | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
2122 | TT_TASK | Removal of formwork for base slab | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2123 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2124 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2125 | TT_TASK | Removal strut S3 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
2126 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jan 25 08:00:00 IST 2014 | Wed Jan 29 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
2127 | TT_TASK | Rebar fixing for wall and roof | Thu Jan 30 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Fri Dec 20 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
2128 | TT_TASK | Erect external formwork for wall and roof | Thu Feb 20 08:00:00 IST 2014 | Fri Feb 21 18:00:00 IST 2014 | Thu Jan 09 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2129 | TT_TASK | Concreting for wall and roof (200m3) | Sat Feb 22 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2130 | TT_TASK | Curing for wall and roof | Sun Feb 23 08:00:00 IST 2014 | Tue Mar 04 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2131 | TT_TASK | Preparation of construction joint for wall and roof | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Tue Jan 14 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2132 | TT_TASK | Removal external and internal formwork for wall | Tue Feb 25 08:00:00 IST 2014 | Tue Feb 25 18:00:00 IST 2014 | Wed Jan 15 08:00:00 IST 2014 | Wed Jan 15 18:00:00 IST 2014 |  | COMPLETED
2133 | TT_TASK | Removal internal falsework and formwork for roof | Wed Mar 05 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2134 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
2137 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Sep 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
2138 | TT_TASK | Erect external formwork for base slab | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Sep 21 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
2139 | TT_TASK | Rebar fixing for base slab | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
2140 | TT_TASK | Erect internal kicker formwork for base slab | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
2141 | TT_TASK | Staircase construction (+12.0mPD to +14.706mPD) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2142 | TT_TASK | Concreting for base slab (30m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
2143 | TT_TASK | Curing for base slab | Fri Dec 13 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
2144 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
2145 | TT_TASK | Removal of formwork for base slab | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 18:00:00 IDT 2013 |  | COMPLETED
2146 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2147 | TT_TASK | Mass concrete at level +12.0mPD | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 |  | COMPLETED
2148 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2149 | TT_TASK | Removal strut S3 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2150 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 17 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Mon Dec 01 18:00:00 IST 2014 |  | COMPLETED
2152 | TT_TASK | Erect working platform to +21.0mPD | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2153 | TT_TASK | Rebar fixing for wall and roof | Sat Jan 11 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2154 | TT_TASK | Staircase construction (+14.706mPD to +16.956mPD) (20m3) | Fri May 02 08:00:00 IDT 2014 | Wed May 07 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2155 | TT_TASK | Staircase construction (+16.956mPD to +19.206mPD) (20m3) | Thu Jun 05 08:00:00 IDT 2014 | Mon Jun 09 18:00:00 IDT 2014 | Thu Jun 12 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2156 | TT_TASK | Staircase construction (+19.206mPD to +21.456mPD) (20m3) | Tue Jun 10 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Fri Jun 20 18:00:00 IDT 2014 |  | COMPLETED
2157 | TT_TASK | Erect external formwork for wall and roof | Sat Mar 15 08:00:00 IST 2014 | Mon Mar 17 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2158 | TT_TASK | Concreting for wall and roof (31m3) | Tue Feb 04 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2159 | TT_TASK | Curing for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 |  | COMPLETED
2160 | TT_TASK | Preparation of construction joint for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2161 | TT_TASK | Removal external and internal formwork for wall | Thu Feb 06 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2162 | TT_TASK | Removal internal falsework and formwork for roof | Sat Feb 15 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Thu Jan 23 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2164 | TT_TASK | Removal strut S2 @ SN 19 | Wed Apr 02 08:00:00 IDT 2014 | Mon Apr 07 18:00:00 IDT 2014 | Mon Mar 03 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 |  | COMPLETED
2165 | TT_TASK | Erect working platform to +24.0mPD | Tue Apr 08 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 | Fri Mar 07 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 |  | COMPLETED
2166 | TT_TASK | Erect internal formwork below strut S1 | Sat Apr 12 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 | Wed Mar 12 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 |  | COMPLETED
2167 | TT_TASK | Staircase construction (+21.456mPD to +23.706mPD) (20m3) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 |  | COMPLETED
2168 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 | Fri Mar 14 08:00:00 IST 2014 | Tue Apr 01 18:00:00 IDT 2014 |  | COMPLETED
2169 | TT_TASK | Erect external wall & internal wall formwork | Tue May 13 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Wed Apr 02 08:00:00 IDT 2014 | Thu Apr 03 18:00:00 IDT 2014 |  | COMPLETED
2170 | TT_TASK | Concreting (External Wall & Internal Wall) (264m3) | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Fri Apr 04 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2171 | TT_TASK | Curing (External Wall & Internal Wall) | Fri May 16 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2172 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Mon May 19 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Thu Apr 10 18:00:00 IDT 2014 |  | COMPLETED
2173 | TT_TASK | Waterproofing | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 |  | COMPLETED
2174 | TT_TASK | Backfilling | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2176 | TT_TASK | Removal strut S1 @ SN 19 | Thu Jun 19 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2177 | TT_TASK | Erect working platform to +30.406mPD | Tue Jun 24 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2178 | TT_TASK | Erect internal formwork | Sat Jun 28 08:00:00 IDT 2014 | Sat Jun 28 18:00:00 IDT 2014 | Wed Jun 04 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2179 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Mon Jun 30 08:00:00 IDT 2014 | Wed Jul 02 18:00:00 IDT 2014 | Thu Jun 05 08:00:00 IDT 2014 | Fri Jun 06 18:00:00 IDT 2014 |  | COMPLETED
2180 | TT_TASK | Erect external formwork (External Wall & Internal Wall) | Thu Jul 03 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2181 | TT_TASK | Concreting (External Wall & Internal Wall) (128m3) | Fri Jul 04 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2182 | TT_TASK | Curing (External Wall & Internal Wall) | Sat Jul 05 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 18:00:00 IDT 2014 |  | COMPLETED
2183 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Tue Jul 08 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2184 | TT_TASK | Waterproofing | Wed Jul 09 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Thu Jun 19 18:00:00 IDT 2014 |  | COMPLETED
2185 | TT_TASK | Backfilling | Sat Jul 12 08:00:00 IDT 2014 | Wed Jul 16 18:00:00 IDT 2014 | Fri Jun 20 08:00:00 IDT 2014 | Tue Jun 24 18:00:00 IDT 2014 |  | COMPLETED
2186 | TT_TASK | Erect falsework and soffit formwork +30.206mPD | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 | Wed Jun 25 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2187 | TT_TASK | Staircase construction (+21.456mPD to +25.956mPD) (20m3) | Sat Jul 19 08:00:00 IDT 2014 | Wed Jul 23 18:00:00 IDT 2014 | Fri Jun 27 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2188 | TT_TASK | Staircase construction (+25.956mPD to +27.606mPD) (20m3) | Sat Jul 05 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 05 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 |  | COMPLETED
2189 | TT_TASK | Rebar fixing (Beam, Floor Slab and Staircase) | Thu Jul 10 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Thu Jul 10 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2190 | TT_TASK | Concreting (Beam, Floor Slab and Staircase) (31m3) | Fri Jul 11 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2191 | TT_TASK | Curing (Beam, Floor Slab and Staircase) | Wed Sep 03 08:00:00 IDT 2014 | Tue Sep 09 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2193 | TT_TASK | Erect working platform to +33.576mPD | Wed Sep 03 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
2194 | TT_TASK | Erect external formwork (External Wall) | Mon Sep 08 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 | Fri Sep 26 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2195 | TT_TASK | Rebar fixing (External Wall) | Thu Sep 11 08:00:00 IDT 2014 | Fri Sep 12 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2196 | TT_TASK | Erect internal formwork (External Wall) | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 |  | COMPLETED
2197 | TT_TASK | Concreting (External Wall) (49m3) | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 |  | COMPLETED
2198 | TT_TASK | Curing (External Wall) | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 |  | COMPLETED
2199 | TT_TASK | Removal formwork (External Wall) | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
2200 | TT_TASK | Erect falsework and soffit formwork +32.656 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2201 | TT_TASK | Rebar fixing (Beam & Floor Slab) | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 |  | COMPLETED
2202 | TT_TASK | Concreting (Beam & Floor Slab) (31m3) | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 |  | COMPLETED
2203 | TT_TASK | Curing (Beam & Floor Slab) | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2205 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
2206 | TT_TASK | Rebar fixing (Roof Parapet Wall) | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 |  | COMPLETED
2207 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2208 | TT_TASK | Concreting (Roof Parapet Wall) (30m3) | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
2209 | TT_TASK | Curing (Roof Parapet Wall) | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 |  | COMPLETED
2210 | TT_TASK | Removal formwork (Roof Parapet Wall) | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2211 | TT_TASK | Removal of falsework and soffit formwork | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
2213 | TT_TASK | Wet trade work | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 |  | COMPLETED
2214 | TT_TASK | Metal works (Louver, Door, Cat-ladder, Architectural Fins, Handrail, Roof Sliding Hatch and Balustrade, etc) | Thu Nov 27 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Thu Nov 27 08:00:00 IST 2014 | Thu Mar 05 18:00:00 IST 2015 |  | COMPLETED
2215 | TT_TASK | Coat works | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2218 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Nov 29 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Feb 04 18:00:00 IST 2014 |  | COMPLETED
2219 | TT_TASK | Backfilling between D-wall and 0.5m below S1 14,240m3 soil | Thu Feb 06 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 | Wed Feb 05 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 |  | COMPLETED
2220 | TT_TASK | Removal of S1 | Wed Mar 12 08:00:00 IST 2014 | Tue Mar 25 18:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 |  | COMPLETED
2221 | TT_TASK | Backfilling to original ground level 21,390m3 (approx. +25.0mPD) | Sat Mar 01 08:00:00 IST 2014 | Wed Mar 19 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Sat May 03 18:00:00 IDT 2014 |  | COMPLETED
2223 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 |  | COMPLETED
2224 | TT_TASK | Backfilling between D-wall and 0.5m below S1 (2075m3) | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 |  | COMPLETED
2225 | TT_TASK | Removal of S1 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 |  | COMPLETED
2226 | TT_TASK | Backfilling to original ground level 3,900m3 (approx. +25.0mPD) (1353m3) | Sat Mar 01 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
2227 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
2228 | TT_TASK | Backfilling backfilling to +20mPD from SN8 to SN9 (Soil: 7,050m3 @ 500m3/day) | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 |  | COMPLETED
2229 | TT_TASK | Removal of S1 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
2230 | TT_TASK | Construction of mud pit | Sat Jul 06 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
2231 | TT_TASK | Backfilling from +20mPD to ground level from SN8 to SN9 (Soil: 5,000m3 @ 500m3/day) | Tue Aug 06 08:00:00 IDT 2013 | Sat Aug 17 18:00:00 IDT 2013 | Tue Jul 02 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 |  | COMPLETED
2233 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Aug 07 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2234 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) | Fri Aug 14 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2235 | TT_TASK | Placing mass concrete infill between tunnel and D-wall | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 02 18:00:00 IST 2015 | Thu Dec 24 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2236 | TT_TASK | Removal of S2 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 10 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 04 18:00:00 IST 2016 |  | COMPLETED
2237 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2238 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
2239 | TT_TASK | Removal strut S1 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2240 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
2241 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488 m3 of soil) | Mon Jan 25 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Fri Apr 01 18:00:00 IDT 2016 |  | COMPLETED
2243 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) (SN18-19) | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 |  | COMPLETED
2244 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) (SN18-19) | Sat Apr 26 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Sat Apr 26 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
2245 | TT_TASK | Placing mass concrete infill between tunnel and D-wall (SN18-19) | Tue May 20 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri May 16 18:00:00 IDT 2014 |  | COMPLETED
2246 | TT_TASK | Removal of S2 (SN16-18) | Wed Jun 04 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 |  | COMPLETED
2247 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) (SN16-18) | Mon Jun 09 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Tue May 27 18:00:00 IDT 2014 |  | COMPLETED
2248 | TT_TASK | Removal strut S1 (SN16-18) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Wed May 28 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
2249 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488m3 of soil) | Fri Jun 27 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
2251 | TT_TASK | Dismantling temporary bridge deck | Mon Jun 15 08:00:00 IDT 2015 | Tue Jul 21 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2252 | TT_TASK | Reinstatement of Works Area 4.10 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jan 11 18:00:00 IST 2017 | Mon May 02 08:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 |  | COMPLETED
2253 | TT_TASK | Complete all tree planting and reinstate Works Area 4.12C | Tue Nov 01 08:00:00 IST 2016 | Thu Jul 13 18:00:00 IDT 2017 | Sat Oct 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2254 | TT_TASK | Reinstate Works Areas 4.9, 4.9A and 4.12A prior to handover | Mon May 22 08:00:00 IDT 2017 | Sat Sep 02 18:00:00 IDT 2017 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2258 | TT_TASK | Application of power supply, environmental permits and construction substation | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2259 | TT_TASK | Procurement and Confirmation of the order of 2nd tunnel boring machine | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2260 | TT_TASK | TBM design and submission for approval | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2261 | TT_TASK | TBM materials order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
2262 | TT_TASK | TBM equipments order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 |  | COMPLETED
2263 | TT_TASK | TBM Fabrication | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
2264 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 |  | COMPLETED
2265 | TT_TASK | TBM test Run | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2266 | TT_TASK | TBM disassembly and packing for shipping to HK | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 |  | COMPLETED
2267 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
2268 | TT_TASK | Setup TBM facilities | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
2269 | TT_TASK | Fabrication 50% of South Tunnel South Bound Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
2270 | TT_TASK | Fabrication 100% of South Tunnel South Bound Precast Lining | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
2271 | TT_TASK | Fabrication 50% of South Tunnel North Bound Precast Lining | Wed Oct 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 | Wed Oct 03 08:00:00 IST 2012 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
2272 | TT_TASK | Fabrication 100% of South Tunnel North Bound Precast Lining | Mon Aug 26 08:00:00 IDT 2013 | Wed Jan 22 18:00:00 IST 2014 | Wed Feb 27 08:00:00 IST 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
2274 | TT_TASK | Ground treatment at lauching shaft Southbound | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
2275 | TT_TASK | TBM assemble, thrust frame, testing and commissioning | Sat Jun 01 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2276 | TT_TASK | Lowing back-up plant for final drive | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
2277 | TT_TASK | Assemble and set up back-up plant for final drive | Sat Jun 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2278 | TT_TASK | Erection of noise enclosure | Sat Jul 20 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 |  | COMPLETED
2279 | TT_TASK | TBM drive & lining installation CH124+912 to CH125+012 (Initial Drive) | Sat Jul 20 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Mon Mar 11 00:00:00 IST 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
2280 | TT_TASK | TBM drive & lining installation CH125+012 to CH125+338 | Tue Oct 15 08:00:00 IDT 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon May 27 08:00:00 IDT 2013 | Tue May 20 00:00:00 IDT 2014 |  | COMPLETED
2281 | TT_TASK | Dis-assemble TBM | Fri May 23 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 |  | COMPLETED
2282 | TT_TASK | Invert slab and side walkway | Fri Aug 01 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Tue Sep 02 18:00:00 IDT 2014 |  | COMPLETED
2283 | TT_TASK | Installation of cable bracket | Mon Nov 03 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 | Mon Aug 18 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2285 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Sep 01 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 | Sat Aug 09 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2286 | TT_TASK | Ground treatment at lauching shaft Northbound | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 19 18:00:00 IST 2013 | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
2287 | TT_TASK | TBM assemble, testing and commissioning | Wed Jul 02 08:00:00 IDT 2014 | Wed Sep 03 18:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2288 | TT_TASK | Setup back-up plant for final drive | Tue Jun 03 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2289 | TT_TASK | Reinstate of noise enclosure | Fri Oct 10 08:00:00 IDT 2014 | Wed Nov 05 18:00:00 IST 2014 | Tue Oct 28 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
2290 | TT_TASK | TBM drive & lining installation CH124+927 to CH125+027 (Initial Drive) | Fri Oct 10 08:00:00 IDT 2014 | Thu Nov 13 18:00:00 IST 2014 | Thu Oct 30 00:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
2291 | TT_TASK | TBM drive & lining installation CH125+027 to CH125+353 (Final Drive) | Fri Jan 02 08:00:00 IST 2015 | Thu Feb 12 18:00:00 IST 2015 | Mon Dec 08 08:00:00 IST 2014 | Fri Aug 07 00:00:00 IDT 2015 |  | COMPLETED
2292 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Tue Aug 04 08:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
2293 | TT_TASK | Dis-assemble TBM | Tue Aug 04 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
2294 | TT_TASK | Invert slab and side walkway | Wed Sep 09 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
2295 | TT_TASK | Installation of cable bracket | Thu Sep 24 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Aug 31 18:00:00 IDT 2015 |  | COMPLETED
2298 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Partial length) at down track | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 |  | COMPLETED
2299 | TT_TASK | Probe/Grout | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 | Mon Aug 11 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2300 | TT_TASK | Coring of Segment | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 |  | COMPLETED
2301 | TT_TASK | Removal of segment | Tue Sep 02 08:00:00 IDT 2014 | Thu Sep 04 18:00:00 IDT 2014 | Thu Aug 21 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2302 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Sep 05 08:00:00 IDT 2014 | Tue Oct 07 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2303 | TT_TASK | Invert Concrete | Thu Oct 23 08:00:00 IDT 2014 | Sat Nov 01 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2304 | TT_TASK | Wall and Roof concrete | Mon Nov 03 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Mon Oct 13 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
2305 | TT_TASK | Dismantle Temporary frame | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2306 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
2307 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Remaining length ) at down track | Sat May 09 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Thu Apr 16 18:00:00 IDT 2015 |  | COMPLETED
2308 | TT_TASK | Probe/Grout | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
2309 | TT_TASK | Coring of Segment | Fri Oct 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 | Fri Oct 16 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
2310 | TT_TASK | Removal of segment | Wed Oct 07 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
2311 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Oct 10 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Oct 26 08:00:00 IST 2015 | Fri Dec 11 18:00:00 IST 2015 |  | COMPLETED
2312 | TT_TASK | Invert Concrete | Thu Dec 03 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Sat Dec 12 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2313 | TT_TASK | Wall and Roof concrete | Mon Dec 14 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 15 18:00:00 IST 2016 |  | COMPLETED
2314 | TT_TASK | Dismantle Temporary frame | Wed Jan 13 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 |  | COMPLETED
2315 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2318 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 |  | COMPLETED
2319 | TT_TASK | Pre-drill and guide wall | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 |  | COMPLETED
2320 | TT_TASK | D-wall design review | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 |  | COMPLETED
2321 | TT_TASK | D-Wall Construction (1075m3) | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 |  | COMPLETED
2322 | TT_TASK | Shear pin, toe grout and pumping test | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 |  | COMPLETED
2324 | TT_TASK | SI for TBM ground treatment | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2325 | TT_TASK | Design review of TBM ground treatment | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2326 | TT_TASK | Ground treatment for TBM southbound | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
2327 | TT_TASK | Ground treatment for TBM northbound | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2329 | TT_TASK | Capping beam construction | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2330 | TT_TASK | L-Shape wall construction | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
2331 | TT_TASK | Excavate up to +28.5mPD (1488m3) | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 |  | COMPLETED
2332 | TT_TASK | Install Strut S1 +29.0mPD | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 |  | COMPLETED
2333 | TT_TASK | Excavate up to +23.5mPD (2480m3) | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 |  | COMPLETED
2334 | TT_TASK | Install Strut S2 +24.0mPD | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 |  | COMPLETED
2335 | TT_TASK | Excavate up to +19.5mPD (1984m3) | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
2336 | TT_TASK | Install Strut S3 +20.0mPD | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 |  | COMPLETED
2337 | TT_TASK | Excavate up to +15.5mPD (1984m3) | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
2338 | TT_TASK | Install Strut S4 +16.0mPD | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 |  | COMPLETED
2339 | TT_TASK | Excavate up to formation (4117m3) | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
2340 | TT_TASK | Install rock dowel and tie back | Sat Jun 02 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Sat Jun 02 08:00:00 IDT 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2341 | TT_TASK | Temporary handover the shaft to contract 822 | Mon Jun 03 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2343 | TT_TASK | Rock breaking works | Mon Aug 26 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
2344 | TT_TASK | Temporary base Slab for TBM Drive | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
2347 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2348 | TT_TASK | Erect external formwork (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Wed Aug 13 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Tue Aug 19 18:00:00 IDT 2014 |  | COMPLETED
2349 | TT_TASK | Rebar fixing (Base Slab) | Thu Aug 14 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Wed Aug 20 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2350 | TT_TASK | Erect internal kicker formwork (Base Slab) | Tue Aug 19 08:00:00 IDT 2014 | Thu Aug 21 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 |  | COMPLETED
2351 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 22 08:00:00 IDT 2014 | Fri Aug 22 18:00:00 IDT 2014 | Thu Aug 28 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2352 | TT_TASK | Concreting (Base Slab) (245m3) | Sat Aug 23 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014 | Fri Aug 29 18:00:00 IDT 2014 |  | COMPLETED
2353 | TT_TASK | Curing (Base Slab) | Mon Aug 25 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2354 | TT_TASK | Removal of formwork (Base Slab) | Mon Sep 08 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Mon Sep 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2355 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Sep 10 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Tue Sep 02 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 |  | COMPLETED
2356 | TT_TASK | Rebar fixing (Wall and roof) | Thu Sep 18 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Thu Sep 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2357 | TT_TASK | Erect external formwork (Wall) | Thu Sep 25 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2358 | TT_TASK | Clearing and inspection (Wall and roof) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2359 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
2360 | TT_TASK | Curing (Wall and roof) | Sat Oct 11 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
2361 | TT_TASK | Removal formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Thu Oct 16 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Sat Nov 01 18:00:00 IST 2014 |  | COMPLETED
2362 | TT_TASK | Removal formwork (Roof) | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2363 | TT_TASK | Side walkway and cable bracket (72m3) | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
2365 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Nov 07 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Sat Nov 07 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
2366 | TT_TASK | Erect external formwork (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Wed Nov 18 18:00:00 IST 2015 |  | COMPLETED
2367 | TT_TASK | Rebar fixing (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Tue Nov 17 18:00:00 IST 2015 | Thu Nov 19 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 |  | COMPLETED
2368 | TT_TASK | Erect internal kicker formwork (Base Slab) | Wed Nov 18 08:00:00 IST 2015 | Fri Nov 20 18:00:00 IST 2015 | Tue Nov 24 08:00:00 IST 2015 | Thu Nov 26 18:00:00 IST 2015 |  | COMPLETED
2369 | TT_TASK | Clearing and inspection (Base Slab) | Sat Nov 21 08:00:00 IST 2015 | Sat Nov 21 18:00:00 IST 2015 | Fri Nov 27 08:00:00 IST 2015 | Fri Nov 27 18:00:00 IST 2015 |  | COMPLETED
2370 | TT_TASK | Concreting (Base Slab) (245m3) | Mon Nov 23 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Nov 28 08:00:00 IST 2015 | Sat Nov 28 18:00:00 IST 2015 |  | COMPLETED
2371 | TT_TASK | Curing (Base Slab) | Tue Nov 24 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Mon Nov 30 08:00:00 IST 2015 | Thu Dec 03 18:00:00 IST 2015 |  | COMPLETED
2372 | TT_TASK | Removal of formwork (Base Slab) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Fri Dec 04 08:00:00 IST 2015 | Sat Dec 05 18:00:00 IST 2015 |  | COMPLETED
2373 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 09 18:00:00 IST 2015 | Mon Dec 07 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
2374 | TT_TASK | Rebar fixing (Wall and roof) | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2375 | TT_TASK | Erect external formwork (Wall) | Mon Jan 11 08:00:00 IST 2016 | Wed Jan 13 18:00:00 IST 2016 | Thu Jan 07 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2376 | TT_TASK | Clearing and inspection (Wall and roof) | Thu Jan 14 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2377 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Jan 15 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2378 | TT_TASK | Curing (Wall and roof) | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 |  | COMPLETED
2379 | TT_TASK | Removal formwork (Wall) | Tue Jan 19 08:00:00 IST 2016 | Thu Jan 21 18:00:00 IST 2016 | Thu Jan 28 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2380 | TT_TASK | Removal formwork and falsework (Roof) | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Sat Jan 30 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2381 | TT_TASK | Side walkway and cable bracket (72m3) | Wed Jan 06 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Thu Nov 12 08:00:00 IST 2015 | Tue Mar 01 18:00:00 IST 2016 |  | COMPLETED
2382 | TT_TASK | Provision access opening to DC | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2383 | TT_TASK | Erect falsework and soffit formwork (Opening) | Thu Mar 10 08:00:00 IST 2016 | Mon Mar 21 18:00:00 IST 2016 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2384 | TT_TASK | Rebar fixing (Roof) | Tue Mar 22 08:00:00 IST 2016 | Tue Mar 22 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2385 | TT_TASK | Clearing and inspection (Roof) | Wed Mar 23 08:00:00 IST 2016 | Wed Mar 23 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2386 | TT_TASK | Concreting (Roof) (225m3) | Thu Mar 24 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2387 | TT_TASK | Curing (Roof) | Tue Mar 29 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Jan 13 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
2388 | TT_TASK | Removal internal falsework and soffit formwork (Roof) | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
2390 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Thu Mar 17 08:00:00 IST 2016 | Fri Mar 18 18:00:00 IST 2016 | Tue Mar 01 08:00:00 IST 2016 | Wed Mar 02 18:00:00 IST 2016 |  | COMPLETED
2391 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Sat Mar 19 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Thu Mar 03 08:00:00 IST 2016 | Tue Mar 08 18:00:00 IST 2016 |  | COMPLETED
2392 | TT_TASK | Backfilling to +18.25mPD (1229 m3 of soil) | Sat Jul 02 08:00:00 IDT 2016 | Mon Jul 11 18:00:00 IDT 2016 | Mon Jul 25 08:00:00 IDT 2016 | Tue Aug 02 18:00:00 IDT 2016 |  | COMPLETED
2393 | TT_TASK | Laying 500mm mass concrete lateral support | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 |  | COMPLETED
2394 | TT_TASK | Backfilling to 0.5m below S3 (+19.5mPD) (372m3 of soil) | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 |  | COMPLETED
2395 | TT_TASK | Removal strut S3 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 |  | COMPLETED
2396 | TT_TASK | Backfilling to 0.5m below S2 (+23.5mPD) (1984m3 of soil) | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 |  | COMPLETED
2397 | TT_TASK | Removal strut S2 | Wed Aug 24 08:00:00 IDT 2016 | Fri Aug 26 18:00:00 IDT 2016 | Wed Aug 24 08:00:00 IDT 2016 | Thu Sep 01 18:00:00 IDT 2016 |  | COMPLETED
2398 | TT_TASK | Backfilling to 0.5m below S1 (+28.5mPD) (2480m3 of soil) | Mon Sep 05 08:00:00 IDT 2016 | Tue Sep 20 18:00:00 IDT 2016 | Fri Sep 02 08:00:00 IDT 2016 | Fri Sep 09 18:00:00 IDT 2016 |  | COMPLETED
2399 | TT_TASK | Removal strut S1 | Wed Sep 21 08:00:00 IDT 2016 | Thu Sep 22 18:00:00 IDT 2016 | Sat Sep 10 08:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 |  | COMPLETED
2400 | TT_TASK | Backfilling to original ground level (approx. +31.5mPD) (1488m3 of soil) | Fri Sep 23 08:00:00 IDT 2016 | Mon Oct 03 18:00:00 IDT 2016 | Thu Sep 15 08:00:00 IDT 2016 | Mon Sep 19 18:00:00 IDT 2016 |  | COMPLETED
2402 | TT_TASK | Reinstatement of TUT area (Including Hydroseeding) | Mon Oct 03 08:00:00 IDT 2016 | Mon Jun 19 18:00:00 IDT 2017 | Fri Oct 07 08:00:00 IDT 2016 |  | 216.0 | IN_PROGRESS
25 | TT_TASK | Access opening for the up track cut and cover tunnel at Tse Uk Tsuen Shaft | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 10 18:00:00 IST 2016 |  | COMPLETED
27 | TT_TASK | Close out the temporary access opening at Tse Uk Tsuen Shaft | Thu Mar 10 08:00:00 IST 2016 | Tue Apr 05 18:00:00 IDT 2016 | Thu Feb 11 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
307 | TT_TASK | Position crane for TBM retrieval (down track) | Wed Jul 02 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014 | Sat Aug 02 18:00:00 IDT 2014 |  | COMPLETED
308 | TT_TASK | TBM Break-in and Retrieval (down track) | Mon Aug 04 08:00:00 IDT 2014 | Sat Aug 30 18:00:00 IDT 2014 | Mon Aug 04 08:00:00 IDT 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
309 | TT_TASK | Position crane for TBM retrieval (up track) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 |  | COMPLETED
310 | TT_TASK | TBM Break-in and Retrieval (up track) | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
376 | TT_TASK | Supply Engineer with Survey Equipment [PS41.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
377 | TT_TASK | Provide Engineer with suitably qualified full time Survey Assistant - 4 nos. [PS41.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
378 | TT_TASK | Provide Engineer with site transportation as detailed in PS42.1 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 |  | COMPLETED
379 | TT_TASK | Submit details of qualified drivers to be assigned to the Engineer, for review [PS42.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 |  | COMPLETED
380 | TT_TASK | Install, service and maintain 10 container offices for use by the Engineer's Site Staff | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
381 | TT_TASK | Provide services and equipment for the Engineer | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
383 | TT_TASK | Master Programme - Prepare and submit for approval [GS4.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
384 | TT_TASK | Master Programme - Comments , Resubmission and Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
385 | TT_TASK | Time Chainage Programme - Prepare and submit for approval [GS4.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
386 | TT_TASK | Time Chainage Programme - Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
387 | TT_TASK | Implement and Maintain Programme Management System for 1st Audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
388 | TT_TASK | Implement and Maintain Programme Management System for 2nd Audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
389 | TT_TASK | Implement and Maintain Programme Management System for 3rd Audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
391 | TT_TASK | Environmental Management Plan - Prepare and submit for approval [GS5.1.10] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
392 | TT_TASK | Environmental Management Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
393 | TT_TASK | Quality Plan - Prepare and submit for approval [GS9.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
394 | TT_TASK | Quality Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
395 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 1st audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 |  | COMPLETED
396 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 2nd audit | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
397 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 3rd audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
398 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 4th audit | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
399 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 5th audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
400 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 6th audit | Tue Jul 02 08:00:00 IDT 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
401 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 7th audit | Thu Nov 28 08:00:00 IST 2013 | Thu Jun 05 18:00:00 IDT 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Jan 24 18:00:00 IST 2014 |  | COMPLETED
402 | TT_TASK | Health and Safety Plan - Prepare and submit [G3.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
403 | TT_TASK | System Assurance Plan - Prepare and submit for approval [PS Appendix P3.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
404 | TT_TASK | System Assurance Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
405 | TT_TASK | Design for Safety & Constructability Plan - Prepare and submit for approval [PS37.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
406 | TT_TASK | Design for Safety & Constructability Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
408 | TT_TASK | Methods of Construction - Prepare and submit for approval [GS12.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
409 | TT_TASK | Methods of Construction - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
410 | TT_TASK | Contractor's Submission Schedule - Prepare and submit for approval [GS12.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
411 | TT_TASK | Contractor's Submission Schedule - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
412 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) [PS13.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
413 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) - Approval period | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 |  | COMPLETED
414 | TT_TASK | Spoil Disposal Plan [PS17.7.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
415 | TT_TASK | Waste Management Plan [PS22.10.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
416 | TT_TASK | Independent Checking Engineer - Appoint and submit for approval [PS7.1.8] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
417 | TT_TASK | Independent Checking Engineer - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
418 | TT_TASK | Sub-contract Management Plan - Prepare and submit [PS34.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 |  | COMPLETED
419 | TT_TASK | Schedule of Utilities Services Arrangement [GS7.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
420 | TT_TASK | Site Safety Supervision Plan for Site Formation - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
421 | TT_TASK | Site Safety Supervision Plan for Site Formation - Approval period | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
422 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Prepare and Submit | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
423 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
424 | TT_TASK | Site Safety Supervision Plan for ELS - Prepare and Submit | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
425 | TT_TASK | Site Safety Supervision Plan for ELS - Approval Period | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
426 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Prepare and Submit | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
427 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Approval Period | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
428 | TT_TASK | Noise Management Plan [P22.3.9] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
429 | TT_TASK | Air Quality Management Plan [P22.4.3] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
430 | TT_TASK | Detailed Proposal for Water Pollution Control Measures and Proposed Monitoring [PS22.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
431 | TT_TASK | Groundwater Monitoring and Response Plan [PS22.5.2] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
432 | TT_TASK | Vibration Monitoring Plan [PS22.8.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 |  | COMPLETED
433 | TT_TASK | Proposed Outline TTM Scheme - Prepare & submit to the: Engineer for Review / SLG for Approval [PS19.3] | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 |  | COMPLETED
434 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Proposed TTM Scheme [PS19.4] | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 |  | COMPLETED
435 | TT_TASK | Resubmission of Proposed Outline TTM Scheme (if required) | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
436 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Resubmitted Proposed Outline TTM Scheme [PS19.4] | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 |  | COMPLETED
437 | TT_TASK | Notification Period of the Approved TTM Scheme prior to implementation [PS19.4] | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 |  | COMPLETED
440 | TT_TASK | Initial Site Survey (WA3.11) | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 |  | COMPLETED
441 | TT_TASK | Initial Site Survey Report (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 |  | COMPLETED
442 | TT_TASK | Initial Site Survey & Condition Survey (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
443 | TT_TASK | Initial Site Survey Report (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
444 | TT_TASK | Initial Site Survey & Condition Survey (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
445 | TT_TASK | Initial Site Survey Report (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
446 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 4.9 & 4.12A [PS4.2] | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
447 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 5.1 & 5.3 [PS4.2.3] | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 |  | COMPLETED
448 | TT_TASK | Proposal for Site Clearance Works [PS4.4.1] | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 |  | COMPLETED
449 | TT_TASK | Site Clearance / Site Formation Works (including demolition of EBS) | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
450 | TT_TASK | Backfill existing stream courses in Works Area 4.9, 4.10 and 4.11 [PS18.5.1] | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
451 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and submit to EPD for Approval (WA3.3 - Area M, I, L) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
452 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA3.3 - Area M, I, L) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
453 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
454 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
455 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.3 - Area M, I, L) | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
456 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA3.3 - Area M, I, L) | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
457 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA3.3 - Area M, I, L) | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
458 | TT_TASK | Remediation Report - Approval (WA3.3 - Area M, I, L) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
459 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and Submit to EPD for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
460 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
461 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
462 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.1, 3.2, 3.3, 3.3A) | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
463 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.1, 3.2, 3.3, 3.3A) | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 |  | COMPLETED
464 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 |  | COMPLETED
465 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
466 | TT_TASK | Remediation Report - Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
467 | TT_TASK | Conduct remediation for Area Q in accordance with method proposed in the approved Remediation Action Plan [PS22.9.2] | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 |  | COMPLETED
468 | TT_TASK | Remediation Report - Prepare and submit for Approval [PS22.9.2] (Area Q) | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 |  | COMPLETED
469 | TT_TASK | Remediation Report - Approval (Area Q) | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
470 | TT_TASK | Removal of contaminated soil at North Tunnels (Area N,O,P,Q,R,S) | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
471 | TT_TASK | Condition Survey EBS for presence of Asbestos and gather samples | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
472 | TT_TASK | Testing of gathered samples | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 |  | COMPLETED
473 | TT_TASK | Prepare and submit Asbestos Investigation Report (AIR) & Asbestos Abatement Plan (AAP) | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
474 | TT_TASK | Approval period of AIR & AAP | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
475 | TT_TASK | Notification period to Engineer and EPD prior to Asbestos abatement works | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
476 | TT_TASK | Asbestos abatement works | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
477 | TT_TASK | Demolition of EBS | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
478 | TT_TASK | Confirmation of tree survey | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 |  | COMPLETED
480 | TT_TASK | Installation of ground settlement markers | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 |  | COMPLETED
481 | TT_TASK | Settlement monitoring and submit report | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
482 | TT_TASK | Settlement monitoring and submit report | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 |  | COMPLETED
483 | TT_TASK | Settlement monitoring and submit report | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
484 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
485 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Wed Feb 26 18:00:00 IST 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Feb 21 18:00:00 IST 2014 |  | COMPLETED
486 | TT_TASK | Settlement monitoring and submit report | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 |  | COMPLETED
488 | TT_TASK | Permit Applications (incl. License to Search and Excavate Antiquities and Excavation Permit) | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 |  | COMPLETED
489 | TT_TASK | Check for underground utilities | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 |  | COMPLETED
490 | TT_TASK | Field walking and hand augering | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 |  | COMPLETED
491 | TT_TASK | Excavation of trial pits | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 |  | COMPLETED
492 | TT_TASK | Rescue excavation rescue works (if required) | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 |  | COMPLETED
494 | TT_TASK | Erection of Hoarding with Gate (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 |  | COMPLETED
495 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 3.1, 3.2, 3.3 and 3.3A [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
496 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 4.9, 4.10, 4.11, 4.12A~C, and 4.15 [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
497 | TT_TASK | Project Signboard Erection [PS4.6.8] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
498 | TT_TASK | Marine Survey at Barging Point [PS4.3] (before construction of barging facilities) | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 00:00:00 IST 2010 |  | COMPLETED
499 | TT_TASK | Construct barging facilities | Sat Oct 02 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Oct 02 00:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
500 | TT_TASK | Operation Plan for the Barging Facility - Prepare and Submit for Approval [PS17.1.9] | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
501 | TT_TASK | Operation Plan for the Barging Facility - Review and Approval Period | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 |  | COMPLETED
503 | TT_TASK | General and Special Attendance for Designated Contractors | Mon Dec 02 08:00:00 IST 2013 | Mon Aug 31 18:00:00 IDT 2015 | Tue Jul 02 08:00:00 IDT 2013 | Wed Mar 25 18:00:00 IST 2015 |  | COMPLETED
505 | TT_TASK | Prepare and Submit Detailed Interface Specification | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 |  | COMPLETED
506 | TT_TASK | Approval of Detailed Interface Plan | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
507 | TT_TASK | Prepare and Submit Detailed Interface Specification | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 |  | COMPLETED
508 | TT_TASK | Approval of Detailed Interface Plan | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
510 | TT_TASK | Prepare and Submit Draft Operation and Maintenance Manual [PS33.1] | Mon Aug 24 08:00:00 IDT 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jul 28 08:00:00 IDT 2014 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
511 | TT_TASK | Review and approval period of Draft Operation and Maintenance Manual | Wed Aug 10 08:00:00 IDT 2016 | Tue Sep 13 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
512 | TT_TASK | Prepare and Submit Final Operation and Maintenance Manual [PS33.1] | Wed Sep 14 08:00:00 IDT 2016 | Thu Feb 16 18:00:00 IST 2017 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
513 | TT_TASK | Provide Engineer with As-Built Drawing for the Whole of the Works [PS33.2] | Mon Nov 21 08:00:00 IST 2016 | Wed Dec 14 18:00:00 IST 2016 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
514 | TT_TASK | Provide Engineer with Asset Registration Information [PS33.3] | Fri May 19 08:00:00 IDT 2017 | Mon Jun 12 18:00:00 IDT 2017 |  |  |  | NOT_STARTED
517 | TT_TASK | Preliminary Design Programme - Prepare and Submit for Approval [PS7.1.8 - App. Z2.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
518 | TT_TASK | Preliminary Design Programme - Review and Approval Period [PS7.1.8 - App. Z2.2] | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 |  | COMPLETED
519 | TT_TASK | Preliminary Design Programme - Resubmission and Approval (if required) [PS7.1.8 - App. Z2.2] | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 |  | COMPLETED
520 | TT_TASK | Schedule of Designs - Prepare and Submit for Approval [PS7.1.8 - App. Z2.5] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
521 | TT_TASK | Detailed Proposal for Carrying Out the Cross Passage Works [PS11.5.2] | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
524 | TT_TASK | Design TBM and submit full details to the Engineer [PS7.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
525 | TT_TASK | TBM Design - Approval period | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 |  | COMPLETED
526 | TT_TASK | TBM Design - Resubmission and approval period | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 |  | COMPLETED
528 | TT_TASK | AIP Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
529 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 |  | COMPLETED
530 | TT_TASK | DDS Design - Prepare and Submit | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 |  | COMPLETED
531 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 |  | COMPLETED
532 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 |  | COMPLETED
533 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 |  | COMPLETED
534 | TT_TASK | Issue Completed Working Drawings | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
536 | TT_TASK | AIP Design - Prepare and Submit | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 |  | COMPLETED
537 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 |  | COMPLETED
538 | TT_TASK | AIP Design - Response to comments and Resubmit | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
539 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
540 | TT_TASK | DDS Design - Prepare and Submit | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
541 | TT_TASK | DDS Design - Review and Approval Period (by MTRC & related Government Authorities) | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 |  | COMPLETED
542 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 |  | COMPLETED
543 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 |  | COMPLETED
544 | TT_TASK | Issue Completed Working Drawings | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 |  | COMPLETED
546 | TT_TASK | DDS Design - Prepare and Submit | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 |  | COMPLETED
547 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 |  | COMPLETED
548 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 |  | COMPLETED
549 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 |  | COMPLETED
550 | TT_TASK | Issue Completed Working Drawings | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
552 | TT_TASK | AIP Design - Prepare and Submit | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 |  | COMPLETED
553 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
554 | TT_TASK | AIP Design - Response to comments and Resubmit | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 |  | COMPLETED
555 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
556 | TT_TASK | DDS Design - Prepare and Submit | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 |  | COMPLETED
557 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 |  | COMPLETED
558 | TT_TASK | DDS Design - Response to comments and Resubmit | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 |  | COMPLETED
559 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 |  | COMPLETED
560 | TT_TASK | Issue Completed Working Drawings | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 |  | COMPLETED
562 | TT_TASK | Prepare and Submit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 |  | COMPLETED
563 | TT_TASK | Review and Approval Period | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
564 | TT_TASK | Response to comments and Resubmit | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 |  | COMPLETED
565 | TT_TASK | Review and Approval Period (for resubmission) | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 |  | COMPLETED
568 | TT_TASK | DDS Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
569 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 |  | COMPLETED
570 | TT_TASK | DDS Design - Response to comments and Resubmit | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 |  | COMPLETED
571 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 |  | COMPLETED
572 | TT_TASK | Issue Completed Working Drawings | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
574 | TT_TASK | DDS Design - Prepare and Submit | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 |  | COMPLETED
575 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 |  | COMPLETED
576 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 |  | COMPLETED
577 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 |  | COMPLETED
578 | TT_TASK | Issue Completed Working Drawings | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 |  | COMPLETED
580 | TT_TASK | DDS Design - Prepare and Submit | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 |  | COMPLETED
581 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 |  | COMPLETED
582 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 |  | COMPLETED
583 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 |  | COMPLETED
584 | TT_TASK | Issue Completed Working Drawings | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 |  | COMPLETED
586 | TT_TASK | DDS Design - Prepare and Submit | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 |  | COMPLETED
587 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 |  | COMPLETED
588 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 |  | COMPLETED
589 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 |  | COMPLETED
590 | TT_TASK | Issue Completed Working Drawings | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 |  | COMPLETED
592 | TT_TASK | DDS Design - Prepare and Submit | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 |  | COMPLETED
593 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 |  | COMPLETED
594 | TT_TASK | DDS Design - Response to comments and Resubmit | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 |  | COMPLETED
595 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 |  | COMPLETED
596 | TT_TASK | Issue Completed Working Drawings | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
599 | TT_TASK | Formworks / Falsework - Prepare & Submit | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
600 | TT_TASK | Formworks / Falsework - Review & Approval Period (by MTRC) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
601 | TT_TASK | Formworks / Falsework - Response to comments and Resubmit | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 |  | COMPLETED
602 | TT_TASK | Formworks / Falsework - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
605 | TT_TASK | Layout of Site Hoarding - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
606 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (by MTRC) | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
607 | TT_TASK | Layout of Site Hoarding - Response to comments and Resubmit | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
608 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 |  | COMPLETED
610 | TT_TASK | Layout of Engineer's Accommodation - Prepare and Submit | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
611 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (by MTRC) | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 |  | COMPLETED
612 | TT_TASK | Layout of Engineer's Accommodation - Response to comments and Resubmit | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
613 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (for resubmit) (by MTRC & related Government Authorities | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
615 | TT_TASK | TTMS Assessment Report - Prepare and Submit | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 |  | COMPLETED
616 | TT_TASK | TTMS Assessment Report - Review and Approval Period (by MTRC) | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
617 | TT_TASK | TTMS Assessment Report - Response to comments and Resubmit | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 |  | COMPLETED
618 | TT_TASK | TTMS Assessment Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
619 | TT_TASK | Issue Completed Working Drawings | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 |  | COMPLETED
621 | TT_TASK | DIA Report - Prepare and Submit | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 |  | COMPLETED
622 | TT_TASK | DIA Report - Review and Approval Period (by MTRC) | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 |  | COMPLETED
623 | TT_TASK | DIA Report - Response to comments and Resubmit | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 |  | COMPLETED
624 | TT_TASK | DIA Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
625 | TT_TASK | Issue Completed Working Drawings | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 |  | COMPLETED
627 | TT_TASK | AIP Design - Prepare & Submit | Wed Sep 23 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 |  | COMPLETED
628 | TT_TASK | AIP Design - Review & Approval Period (by MTR) | Wed Oct 14 08:00:00 IDT 2015 | Wed Nov 11 18:00:00 IST 2015 | Mon Jun 08 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
629 | TT_TASK | AIP Design - Response to comments and Resubmit | Thu Nov 12 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Mon Jun 15 01:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
630 | TT_TASK | AIP Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jun 22 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
631 | TT_TASK | DDS Design - Prepare & Submit | Wed Jan 13 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Tue Sep 01 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 |  | COMPLETED
632 | TT_TASK | DDS Design - Review & Approval Period (by MTRC) | Fri Feb 26 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 12 18:00:00 IDT 2015 |  | COMPLETED
633 | TT_TASK | DDS Design - Response to comments & Resubmit | Tue Mar 29 08:00:00 IDT 2016 | Fri Apr 01 18:00:00 IDT 2016 | Mon Sep 14 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
634 | TT_TASK | DDS Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Apr 02 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 | Mon Sep 21 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
635 | TT_TASK | Issue Completed Working Drawings | Wed Jan 27 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
637 | TT_TASK | Layout of Barging Point - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
638 | TT_TASK | Layout of Barging Point - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
639 | TT_TASK | Layout of Barging Point - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
640 | TT_TASK | Layout of Barging Point - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
641 | TT_TASK | Loading Ramps - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
642 | TT_TASK | Loading Ramps - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
643 | TT_TASK | Loading Ramps - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
644 | TT_TASK | Loading Ramps - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
645 | TT_TASK | Weighbridge - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
646 | TT_TASK | Weighbridge - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
647 | TT_TASK | Weighbridge - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
648 | TT_TASK | Weighbridge - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
652 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
653 | TT_TASK | Pre-drill and guide wall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
654 | TT_TASK | D-wall construction (1084m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
655 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
656 | TT_TASK | Wang Toi Shan Shan Tsuen Road diversion works | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 |  | COMPLETED
658 | TT_TASK | Excavate up to +10.5mPD (369m3) | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 |  | COMPLETED
659 | TT_TASK | Install Strut S0 +11.0mPD | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 |  | COMPLETED
660 | TT_TASK | Excavate up to +8.0mPD (1525m3) | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 |  | COMPLETED
661 | TT_TASK | Install Strut S1 +8.5mPD | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 |  | COMPLETED
662 | TT_TASK | Excavate up to +4.5mPD (2135m3) | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 |  | COMPLETED
663 | TT_TASK | Install Strut S2 +5.0mPD | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 |  | COMPLETED
664 | TT_TASK | Excavate up to +0.5mPD (2440m3) | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 |  | COMPLETED
665 | TT_TASK | Install Strut S3 +1.0mPD | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 |  | COMPLETED
666 | TT_TASK | Excavate up to -6.5mPD (4340m3) | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 |  | COMPLETED
667 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
668 | TT_TASK | Construction of temporary slab and entrance seal (622m3) | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
672 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 08 18:00:00 IST 2014 | Fri Dec 05 08:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
673 | TT_TASK | Erect external formwork (Base Slab) | Tue Dec 09 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 08 08:00:00 IST 2014 | Tue Dec 09 18:00:00 IST 2014 |  | COMPLETED
674 | TT_TASK | Rebar fixing (Base Slab) | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 18:00:00 IST 2014 | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
675 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Dec 15 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Mon Dec 15 18:00:00 IST 2014 |  | COMPLETED
676 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Dec 17 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Tue Dec 16 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 |  | COMPLETED
677 | TT_TASK | Curing (Base Slab) | Thu Dec 18 08:00:00 IST 2014 | Sat Dec 27 18:00:00 IST 2014 | Wed Dec 17 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
678 | TT_TASK | Removal of formwork (Base Slab) | Fri Dec 19 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 24 18:00:00 IST 2014 |  | COMPLETED
679 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
680 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 | Mon Jun 22 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 |  | COMPLETED
681 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Jun 13 08:00:00 IDT 2015 | Mon Jun 15 18:00:00 IDT 2015 | Thu Jun 25 01:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
682 | TT_TASK | Concreting (Wall & Roof) (444m3) | Tue Jun 16 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
683 | TT_TASK | Curing (Wall & Roof) | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
684 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 |  | COMPLETED
685 | TT_TASK | Removal external formwork (Wall) | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
686 | TT_TASK | Side walkway and cable bracket (360m3) | Sat Jul 18 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Sat Jul 18 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
687 | TT_TASK | Access opening to DC (DC access period) | Tue Oct 06 08:00:00 IDT 2015 | Fri Mar 04 18:00:00 IST 2016 | Tue Oct 06 08:00:00 IDT 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
688 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Sat Dec 12 08:00:00 IST 2015 | Mon Jan 18 18:00:00 IST 2016 | Tue Nov 03 00:00:00 IST 2015 | Mon Nov 30 18:00:00 IST 2015 |  | COMPLETED
690 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 | Tue Apr 12 08:00:00 IDT 2016 | Wed Apr 13 18:00:00 IDT 2016 |  | COMPLETED
691 | TT_TASK | Erect external formwork (Base Slab) | Mon May 23 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Thu Apr 14 08:00:00 IDT 2016 | Fri Apr 15 18:00:00 IDT 2016 |  | COMPLETED
692 | TT_TASK | Rebar fixing (Base Slab) | Wed May 25 08:00:00 IDT 2016 | Fri May 27 18:00:00 IDT 2016 | Sat Apr 16 08:00:00 IDT 2016 | Tue Apr 19 18:00:00 IDT 2016 |  | COMPLETED
693 | TT_TASK | Erect internal kicker formwork (Base Slab) | Sat May 28 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 | Wed Apr 20 08:00:00 IDT 2016 | Thu Apr 21 18:00:00 IDT 2016 |  | COMPLETED
694 | TT_TASK | Concreting (Base Slab) (225m3) | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 | Fri Apr 22 08:00:00 IDT 2016 | Fri Apr 22 18:00:00 IDT 2016 |  | COMPLETED
695 | TT_TASK | Curing (Base Slab) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 08 18:00:00 IDT 2016 | Sat Apr 23 08:00:00 IDT 2016 | Fri Apr 29 18:00:00 IDT 2016 |  | COMPLETED
696 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Sat Apr 30 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
697 | TT_TASK | Removal of formwork (Base Slab) | Tue May 24 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Mon May 09 08:00:00 IDT 2016 | Tue May 10 18:00:00 IDT 2016 |  | COMPLETED
698 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed May 25 08:00:00 IDT 2016 | Sat May 28 18:00:00 IDT 2016 | Wed May 11 08:00:00 IDT 2016 | Mon May 16 18:00:00 IDT 2016 |  | COMPLETED
699 | TT_TASK | Rebar fixing (Wall & Roof) | Mon May 30 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 17 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 |  | COMPLETED
700 | TT_TASK | Erect external formwork (Wall & Roof) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 03 18:00:00 IDT 2016 | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 |  | COMPLETED
701 | TT_TASK | Concreting (Wall & Roof) (444m3) | Sat Jun 04 08:00:00 IDT 2016 | Sat Jun 04 18:00:00 IDT 2016 | Mon May 23 08:00:00 IDT 2016 | Mon May 23 18:00:00 IDT 2016 |  | COMPLETED
702 | TT_TASK | Curing (Wall & Roof) | Mon Jun 06 08:00:00 IDT 2016 | Tue Jun 14 18:00:00 IDT 2016 | Tue May 24 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 |  | COMPLETED
703 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 15 08:00:00 IDT 2016 | Wed Jun 15 18:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 |  | COMPLETED
704 | TT_TASK | Removal external formwork (Wall) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
705 | TT_TASK | Side walkway and cable bracket (102m3) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 |  | COMPLETED
706 | TT_TASK | Access opening to DC (DC access period) | Sat Jun 18 08:00:00 IDT 2016 | Thu Jul 14 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
707 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Fri Jul 15 08:00:00 IDT 2016 | Wed Aug 17 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
709 | TT_TASK | Backfilling between tunnels (2000m3) | Thu Sep 01 08:00:00 IDT 2016 | Sat Sep 17 18:00:00 IDT 2016 | Tue Sep 13 08:00:00 IDT 2016 | Fri Sep 30 18:00:00 IDT 2016 |  | COMPLETED
710 | TT_TASK | Remove Strut S2 | Mon Oct 03 08:00:00 IDT 2016 | Wed Oct 05 18:00:00 IDT 2016 | Mon Oct 03 08:00:00 IDT 2016 | Tue Oct 11 18:00:00 IDT 2016 |  | COMPLETED
711 | TT_TASK | Backfilling up top S1 Soffit | Thu Oct 06 08:00:00 IDT 2016 | Fri Oct 21 18:00:00 IDT 2016 | Fri Oct 28 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
712 | TT_TASK | Remove Strut S1 | Sat Oct 22 08:00:00 IDT 2016 | Mon Oct 24 18:00:00 IDT 2016 | Tue Oct 11 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
713 | TT_TASK | Backfilling up top S0 Soffit | Mon Nov 07 08:00:00 IST 2016 | Sat Nov 12 18:00:00 IST 2016 | Tue Nov 01 08:00:00 IST 2016 | Sat Nov 05 18:00:00 IST 2016 |  | COMPLETED
714 | TT_TASK | Remove Strut S0 | Mon Nov 14 08:00:00 IST 2016 | Tue Nov 15 18:00:00 IST 2016 | Mon Nov 07 08:00:00 IST 2016 | Tue Nov 08 18:00:00 IST 2016 |  | COMPLETED
715 | TT_TASK | Backfilling up to ground level | Wed Nov 16 08:00:00 IST 2016 | Fri Nov 18 18:00:00 IST 2016 | Wed Nov 09 08:00:00 IST 2016 | Fri Nov 11 18:00:00 IST 2016 |  | COMPLETED
719 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
720 | TT_TASK | Pre-drilling and guidewall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
721 | TT_TASK | D-wall construction (1451m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
722 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 |  | COMPLETED
724 | TT_TASK | Excavate from ground level to formation level -5.5mPD (4559m3) | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 |  | COMPLETED
725 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 |  | COMPLETED
726 | TT_TASK | Placing of blinding layer (South Bound) | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 |  | COMPLETED
727 | TT_TASK | Placing of blinding layer (North Bound) | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
729 | TT_TASK | Construction of Bay 2 to Bay 7a (3565m3) | Mon Jun 04 08:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 | Mon Jun 04 18:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 |  | COMPLETED
730 | TT_TASK | Side walkway and cable bracket (Southbound) | Fri Oct 02 08:00:00 IDT 2015 | Fri Nov 06 18:00:00 IST 2015 | Fri Oct 02 08:00:00 IDT 2015 | Sat Oct 31 18:00:00 IST 2015 |  | COMPLETED
731 | TT_TASK | Side walkway and cable bracket (Northbound) | Tue May 03 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 |  | COMPLETED
733 | TT_TASK | Backfilling (1344m3) | Wed Nov 07 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 | Wed Nov 07 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
736 | TT_TASK | Scheme Design, Mobilization, Site set up & Material delivery and Instrumentations | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
737 | TT_TASK | Downstream pipe pile wall construction (45 nos.) and grout curtain (45 nos.) | Mon Nov 12 08:00:00 IST 2012 | Fri Jan 25 18:00:00 IST 2013 | Mon Nov 12 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
738 | TT_TASK | Curtain Grout for cut slope (120 nos.) | Fri Jul 26 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
739 | TT_TASK | Drilling for ground improvement only (if require) | Mon Dec 10 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
740 | TT_TASK | If settlement reach the AAA alarm & action level TAM grouting will apply during excavation | Thu Apr 11 08:00:00 IDT 2013 | Thu May 16 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
741 | TT_TASK | Erection of temporary working platform for Up stream and Installation of Instrumentation System | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
742 | TT_TASK | Upstream pipe pile wall construction adjacent to WTSSTR, (17nos.) | Thu Dec 27 08:00:00 IST 2012 | Mon Jan 28 18:00:00 IST 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
743 | TT_TASK | Upstream pipe pile wall construction at Kam Tin River, 15m depth, 42nos. 1drill rig) | Tue Jan 29 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
744 | TT_TASK | Excavation and soil nail installation | Tue Apr 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
745 | TT_TASK | Excavation for rock and blinding layer | Sat Aug 24 08:00:00 IDT 2013 | Sat Sep 28 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
750 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
751 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
752 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
753 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
754 | TT_TASK | Concreting (164m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
755 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
756 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
757 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
758 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
759 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
760 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
761 | TT_TASK | Concreting (242m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
762 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
763 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
764 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
765 | TT_TASK | Removal internal falsework and formwork for roof | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
766 | TT_TASK | Side walkway and cable bracket (19m3) | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
770 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
771 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
772 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
773 | TT_TASK | Erect internal kicker formwork | Thu Nov 28 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 09 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
774 | TT_TASK | Concreting (121m3) | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
775 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
776 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
777 | TT_TASK | Removal of formwork | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
778 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
779 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
780 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
781 | TT_TASK | Concreting (121m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
782 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
783 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
784 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
785 | TT_TASK | Removal internal falsework and formwork for roof | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
786 | TT_TASK | Side walkway and cable bracket (38m3) | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
788 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
789 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
790 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
791 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
792 | TT_TASK | Concreting (240m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
793 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
794 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
795 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
796 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
797 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
798 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
799 | TT_TASK | Concreting (240m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
800 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
801 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
802 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
803 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
804 | TT_TASK | Side walkway and cable bracket | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
806 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
807 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
808 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
809 | TT_TASK | Concreting (222m3) | Wed Nov 06 08:00:00 IST 2013 | Wed Nov 06 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
810 | TT_TASK | Curing | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
811 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
812 | TT_TASK | Removal of formwork | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
815 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
816 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
817 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
818 | TT_TASK | Erect internal kicker formwork | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
819 | TT_TASK | Concreting (111m3) | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
820 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
821 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
822 | TT_TASK | Removal of formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
823 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
824 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
825 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
826 | TT_TASK | Concreting (220m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
827 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
828 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
829 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
830 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
831 | TT_TASK | Side walkway and cable bracket (38m3) | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 |  | COMPLETED
833 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
834 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
835 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
836 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
837 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
838 | TT_TASK | Curing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
839 | TT_TASK | Preparation of construction joint for base slab | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
840 | TT_TASK | Removal of formwork | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
841 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
842 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
843 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
844 | TT_TASK | Concreting (327m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
845 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
846 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
847 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
848 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
849 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
851 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 20 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
852 | TT_TASK | Rebar fixing | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
853 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 08:00:00 IDT 2013 |  | COMPLETED
854 | TT_TASK | Concreting (225m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
855 | TT_TASK | Curing | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
856 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
857 | TT_TASK | Removal of formwork | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
860 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 27 08:00:00 IST 2013 | Wed Nov 27 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
861 | TT_TASK | Erect external formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
862 | TT_TASK | Rebar fixing | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
863 | TT_TASK | Erect internal kicker formwork | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
864 | TT_TASK | Concreting (222m3) | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
865 | TT_TASK | Curing | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Mon Oct 28 18:00:00 IST 2013 |  | COMPLETED
866 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
867 | TT_TASK | Removal of formwork | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
868 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
869 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
870 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
871 | TT_TASK | Concreting (222m3) | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 |  | COMPLETED
872 | TT_TASK | Curing | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 07 18:00:00 IST 2014 |  | COMPLETED
873 | TT_TASK | Preparation of construction joint for wall and roof | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
874 | TT_TASK | Removal external and internal formwork for wall | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
875 | TT_TASK | Removal internal falsework and formwork for roof | Mon Feb 10 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
876 | TT_TASK | Side walkway and cable bracket (38m3) | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 |  | COMPLETED
878 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
879 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
880 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
881 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
882 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
883 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
884 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
885 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
886 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
887 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
888 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
889 | TT_TASK | Concreting (222m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
890 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
892 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
893 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
894 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
896 | TT_TASK | Placing of waterproof member T-lock & testing | Mon Nov 18 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
897 | TT_TASK | Rebar fixing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Wed Oct 23 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
898 | TT_TASK | Erect external formwork | Fri Nov 22 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
899 | TT_TASK | Concreting (222m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
900 | TT_TASK | Curing | Tue Nov 26 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
901 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
902 | TT_TASK | Removal of formwork | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
905 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
906 | TT_TASK | Erect external formwork | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
907 | TT_TASK | Rebar fixing | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
908 | TT_TASK | Erect internal kicker formwork | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
909 | TT_TASK | Concreting (330m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
910 | TT_TASK | Curing | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
911 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
912 | TT_TASK | Removal of formwork | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
913 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
914 | TT_TASK | Rebar fixing | Wed Nov 20 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
915 | TT_TASK | Erect external formwork | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
916 | TT_TASK | Concreting (330m3) | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
917 | TT_TASK | Curing | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
918 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
919 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
920 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
921 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
923 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
924 | TT_TASK | Erect external formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
925 | TT_TASK | Rebar fixing | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
926 | TT_TASK | Erect internal kicker formwork | Wed Dec 04 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
927 | TT_TASK | Concreting (240m3) | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
928 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
929 | TT_TASK | Preparation of construction joint for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
930 | TT_TASK | Removal of formwork | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
931 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
932 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
933 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
934 | TT_TASK | Concreting (240m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
935 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
936 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
937 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
938 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
939 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
941 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
942 | TT_TASK | Rebar fixing | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
943 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
944 | TT_TASK | Concreting (240m3) | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
945 | TT_TASK | Curing | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
946 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
947 | TT_TASK | Removal of formwork | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
950 | TT_TASK | Placing of waterproof member T-lock & testing | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
951 | TT_TASK | Erect external formwork | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
952 | TT_TASK | Rebar fixing | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
953 | TT_TASK | Erect internal kicker formwork | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
954 | TT_TASK | Concreting (200m3) | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
955 | TT_TASK | Curing | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
956 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
957 | TT_TASK | Removal of formwork | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
958 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 29 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
959 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
960 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
961 | TT_TASK | Concreting (200m3) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
962 | TT_TASK | Curing | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
963 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
964 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 13 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
965 | TT_TASK | Removal internal falsework and formwork for roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
966 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 |  | COMPLETED
968 | TT_TASK | Placing of waterproof member T-lock & testing | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
969 | TT_TASK | Erect external formwork | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
970 | TT_TASK | Rebar fixing | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
971 | TT_TASK | Erect internal kicker formwork | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
972 | TT_TASK | Concreting (220m3) | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
973 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
974 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
975 | TT_TASK | Removal of formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
976 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
977 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
978 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
979 | TT_TASK | Concreting (220m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
980 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
981 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
982 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
983 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
984 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
986 | TT_TASK | Placing of waterproof member T-lock & testing | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
987 | TT_TASK | Rebar fixing | Mon Nov 25 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
988 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
989 | TT_TASK | Concreting (222m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
990 | TT_TASK | Curing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
991 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
992 | TT_TASK | Removal of formwork | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
994 | TT_TASK | Removal of Temporary Nullah | Sat Mar 01 08:00:00 IST 2014 | Sat Jun 21 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
995 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (5218m3) | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 |  | COMPLETED
996 | TT_TASK | Reinstate the permenant Retaining wall of Nullah | Sat Mar 01 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Tue Mar 04 08:00:00 IST 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
997 | TT_TASK | Reinstate Nullah Base of original route | Tue Feb 25 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Tue Feb 25 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
998 | TT_TASK | Reinstate Nullah to original route | Sat Mar 29 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Sat Mar 29 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
999 | TT_TASK | Construction & connect East Box Culvert from Box 6B to KTR | Mon Apr 14 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Mon Feb 10 08:00:00 IST 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
1000 | TT_TASK | Reinstatement of Wang Toi Shan Shan Tsuen Road | Tue Dec 01 08:00:00 IST 2015 | Wed Jul 13 18:00:00 IDT 2016 | Tue Dec 01 08:00:00 IST 2015 | Mon Jul 18 18:00:00 IDT 2016 |  | COMPLETED
1003 | TT_TASK | Pre-drilling at Works Area 4.4 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
1004 | TT_TASK | Site Setup and guide wall | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1005 | TT_TASK | D-wall construction (3104m3) | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 |  | COMPLETED
1006 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
1008 | TT_TASK | Excavate up to +8.0mPD (775m3) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1009 | TT_TASK | Install Strut S1 +8.5mPD | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 |  | COMPLETED
1010 | TT_TASK | Excavate up to +4.5mPD (2713m3) | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 |  | COMPLETED
1011 | TT_TASK | Install Strut S2 +5.0mPD | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
1012 | TT_TASK | Excavate up to +0.5mPD (3100m3) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 |  | COMPLETED
1013 | TT_TASK | Install Strut S3 +1.0mPD | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1014 | TT_TASK | Excavate up to -3.0mPD (2713m3) | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1015 | TT_TASK | Install Strut S4 -2.5mPD | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 |  | COMPLETED
1016 | TT_TASK | Excavate up to -5.5mPD (4952m3) | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1017 | TT_TASK | Placing of blinding layer | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1021 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1022 | TT_TASK | Erect external formwork for base slab | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1023 | TT_TASK | Rebar fixing for base slab | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1024 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 26 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1025 | TT_TASK | Concreting for base slab (350m3) | Thu Jun 27 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1026 | TT_TASK | Curing for base slab | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1027 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1028 | TT_TASK | Removal of formwork for base slab | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1029 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1030 | TT_TASK | Removal strut S4 and S3 | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1032 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1033 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1034 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1035 | TT_TASK | Concreting for wall and roof (489m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1036 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1037 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1038 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1039 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1040 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1043 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1044 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1045 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1046 | TT_TASK | Curing for wall and roof | Sat Jun 22 08:00:00 IDT 2013 | Mon Jul 01 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1047 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1048 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1050 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Tue Dec 17 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1053 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1054 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1055 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1056 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1057 | TT_TASK | Concreting for base slab (350m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1058 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1059 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1060 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1061 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1062 | TT_TASK | Removal strut S4 and S3 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1064 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1065 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1066 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1067 | TT_TASK | Concreting for wall and roof (489m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1068 | TT_TASK | Curing for wall and roof | Wed Jun 12 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1069 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1070 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 14 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1071 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1072 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Feb 13 08:00:00 IST 2014 | Tue Feb 18 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1074 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1075 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1076 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1077 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1078 | TT_TASK | Curing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1079 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1080 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1081 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1082 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 16 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1084 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (2343m3) | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1085 | TT_TASK | Placing 0.5m thk concrete lateral support (+3.96mPD) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1086 | TT_TASK | Removal strut S2 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 23 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1088 | TT_TASK | Construction of Temporary Culvert (open channel) | Tue Jun 25 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1089 | TT_TASK | Temporary box culvert (At Box 6B Area) Saw Cut D-wall | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 |  | COMPLETED
1090 | TT_TASK | Erect 3m high block wall | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 |  | COMPLETED
1091 | TT_TASK | Connection to East Box Culvert (823B portion) | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 |  | COMPLETED
1092 | TT_TASK | Blinding | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
1093 | TT_TASK | Temporary box culvert (Outside Box 6B Area) Sheet piling | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 |  | COMPLETED
1094 | TT_TASK | ELS Works | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
1095 | TT_TASK | Blinding | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
1096 | TT_TASK | Removal of Temporary Culvert and Reinstatement | Fri May 16 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
1098 | TT_TASK | Reinstatement of TOA's | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 |  |  | IN_PROGRESS
1099 | TT_TASK | Hydroseeding works | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 | Wed Nov 30 18:00:00 IST 2016 |  | COMPLETED
1100 | TT_TASK | Tree Planting works | Thu Sep 01 08:00:00 IDT 2016 | Sat Dec 03 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
1101 | TT_TASK | Woodland Shrub Mix | Thu Sep 01 08:00:00 IDT 2016 | Fri Nov 18 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  | 200.0 | IN_PROGRESS
1104 | TT_TASK | Kam Tin River Diversion (Stage 1-3) | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1106 | TT_TASK | Concrete fill up to +8.0mPD near side A mass concrete wall | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 |  | COMPLETED
1107 | TT_TASK | Construction of mass concrete wall to +8.0mPD at side A (4 bay CH A80~A120) | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1108 | TT_TASK | Construction of base slab lining and low flow channel (4 bay A9~A10, B8~B9; LFC CH 80~110) | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1109 | TT_TASK | Construction of mass concrete wall to +8.0mPD of side B (3 bay CH B60~B90) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1110 | TT_TASK | Construction of T-shaped retaining wall (1 Bay CH B50~B60) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1111 | TT_TASK | Soil backfill at side A from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1112 | TT_TASK | Concrete backfill at side B from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1113 | TT_TASK | Removal strut at +8.5mPD near side A | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1114 | TT_TASK | Concrete fill up to +11.0mPD near side A mass concrete wall | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1115 | TT_TASK | Placing concrete block at side A from +8.0mPD to +11.0mpd at side A (4 bay CH A80~A120) | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1116 | TT_TASK | Soil backfill at side A from +8.0mPD to +11.0mPD | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1117 | TT_TASK | Removal strut at +8.5mPD near side B | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1118 | TT_TASK | Placing concrete block at side B from +8.0mPD to +11.0mPD (4 bay CH B60~B90) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1119 | TT_TASK | Concrete backfill at side B from +8.0mPD to +11.0mPD | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1121 | TT_TASK | Placing temporary concrete block to Up stream at CH30 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 |  | COMPLETED
1122 | TT_TASK | Placing temporary concrete block to Up stream at CH160 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1123 | TT_TASK | Excavation from GL to FL +5.0mPD Up stream (Low flow channel CH 30~60) | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1124 | TT_TASK | Excavation from GL to FL +5.0mPD Down stream (Low flow channel CH 130~160) | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1125 | TT_TASK | Construction of T-shaped retaining wall at Up stream of side B (2 Bay CH B30~B50) | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1126 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (3 bay CH B90~B120) | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1127 | TT_TASK | Construction of Up stream base slab lining and low flow channel (6 Bay A1~A4, B3~B4; Low flow channel CH 30~50) | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1128 | TT_TASK | Construction of Down stream base slab lining and low flow channel (5 Bay A14~A16, B14~B15; LFC CH 140~170) | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1129 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Up stream and saw cut D-wall | Fri Jun 14 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1130 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Down stream and saw cut D-wall | Wed Jun 19 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1131 | TT_TASK | Construction of remaining Up stream base slab lining and low flow channel (7 bay A5~A8, B5~B7; LFC CH 50~80) | Thu Jun 27 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1132 | TT_TASK | Construction of remaining Down stream base slab lining and low flow channel (7 bay A11~A13, B10~B13; LFC CH 110~140) | Wed Jul 03 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1134 | TT_TASK | Relocation of temporary concrete block at Up stream for construction of mass concrete wall at side B | Sat Jul 20 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1135 | TT_TASK | Relocation of temporary concrete block at Down stream for construction of mass concrete wall at side B | Tue Jul 23 08:00:00 IDT 2013 | Wed Jul 24 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1136 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Up stream of side B (3 bay CH B0~B30) | Tue Jul 23 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1137 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (4 bay CH B0~B30) | Thu Jul 25 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1141 | TT_TASK | Application of power supply, environmental permits and construction substation | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1142 | TT_TASK | Procurement and Confirmation of the order of 1st tunnel boring machine | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 |  | COMPLETED
1143 | TT_TASK | Prepare on-demand bond or bank guarantee for the procurement of TBM and submit to Engineer for approval | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 |  | COMPLETED
1144 | TT_TASK | TBM design and submission for approval | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
1145 | TT_TASK | TBM materials order and delivery to factory | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 |  | COMPLETED
1146 | TT_TASK | TBM equipments order and delivery to factory | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 |  | COMPLETED
1147 | TT_TASK | TBM Fabrication | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
1148 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 |  | COMPLETED
1149 | TT_TASK | TBM test Run | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 |  | COMPLETED
1150 | TT_TASK | TBM disassembly and packing for shipping to HK | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 |  | COMPLETED
1151 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
1152 | TT_TASK | Ground treatment for TBM lanching shaft | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 |  | COMPLETED
1153 | TT_TASK | Ground treatment for Cross Passage Tunnel | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1154 | TT_TASK | Box7A Setup TBM facilities, install noise enclosure and CNP application | Fri Jun 01 08:00:00 IDT 2012 | Sat Jan 26 18:00:00 IST 2013 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1155 | TT_TASK | Notice to Contract 824 the anticipated dates of break out TBM Shaft | Sat Jun 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1156 | TT_TASK | Fabrication of tunnel segment mould | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
1157 | TT_TASK | Fabrication 50% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1158 | TT_TASK | Fabrication 100% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
1159 | TT_TASK | Fabrication 30% of North Tunnel North Bound (Uptrack) Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1160 | TT_TASK | Fabrication 60% of North Tunnel North Bound (Uptrack) Precast Lining | Thu Oct 18 08:00:00 IST 2012 | Thu Feb 21 18:00:00 IST 2013 | Thu Oct 18 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1161 | TT_TASK | Fabrication 100% of North Tunnel North Bound (Uptrack) Precast Lining | Mon Aug 19 08:00:00 IDT 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Dec 03 08:00:00 IST 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1163 | TT_TASK | Assemble, T&C of TBM | Fri Jun 01 08:00:00 IDT 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Oct 16 00:00:00 IST 2012 |  | COMPLETED
1164 | TT_TASK | TBM drive & lining installation CH123+369 to CH123+283 Initial Drive (86m) | Sat Nov 03 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 | Wed Oct 17 00:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1165 | TT_TASK | Change Plant (Back-up cars) | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1166 | TT_TASK | TBM drive & lining installation CH123+283 to CH123+183 | Thu Jun 27 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1167 | TT_TASK | TBM drive & lining installation CH123+183 to CH123+083 | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1168 | TT_TASK | TBM drive & lining installation CH123+083 to CH122+983 | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1169 | TT_TASK | TBM drive & lining installation CH122+983 to CH122+883 | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1170 | TT_TASK | TBM drive & lining installation CH122+883 to CH122+783 | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Jun 13 08:00:00 IDT 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
1171 | TT_TASK | TBM drive & lining installation CH122+783 to CH122+683 | Sat Nov 02 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1172 | TT_TASK | TBM drive & lining installation CH122+683 to CH122+583 | Tue Dec 03 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Wed Feb 26 18:00:00 IST 2014 |  | COMPLETED
1173 | TT_TASK | TBM drive & lining installation CH122+583 to CH122+491 | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Feb 27 08:00:00 IST 2014 | Sat Aug 16 00:00:00 IDT 2014 |  | COMPLETED
1174 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1175 | TT_TASK | Dis-assemble TBM | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
1176 | TT_TASK | Invert slab, side walkway | Sat Oct 04 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 | Mon Sep 15 08:00:00 IDT 2014 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1177 | TT_TASK | Installation of cable bracket | Tue Dec 30 08:00:00 IST 2014 | Tue Jan 13 18:00:00 IST 2015 | Fri Sep 12 08:00:00 IDT 2014 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
1178 | TT_TASK | Provision of assess open for DC and modify of strut S1 and S2 at north bound | Tue Nov 04 11:12:00 IST 2014 | Thu Dec 04 11:12:00 IST 2014 | Wed Oct 01 08:00:00 IDT 2014 | Sat Oct 18 18:00:00 IDT 2014 |  | COMPLETED
1180 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Oct 06 13:00:00 IDT 2014 | Mon Oct 20 12:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
1181 | TT_TASK | Assemble, T&C of TBM | Mon Nov 03 08:00:00 IST 2014 | Fri Jan 02 18:00:00 IST 2015 | Sat Oct 04 08:00:00 IDT 2014 | Fri Nov 28 18:00:00 IST 2014 |  | COMPLETED
1182 | TT_TASK | Setup back-up plant for final drive | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
1183 | TT_TASK | Reinstate of noise enclosure | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Sat Nov 29 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1184 | TT_TASK | TBM drive & lining installation CH123+384 to CH123+284 (Initial Drive) | Sat Dec 06 08:00:00 IST 2014 | Thu Jan 22 18:00:00 IST 2015 | Tue Dec 02 00:00:00 IST 2014 | Tue Jan 20 18:00:00 IST 2015 |  | COMPLETED
1185 | TT_TASK | TBM drive & lining installation CH123+184 to CH123+084 | Wed Jan 21 08:00:00 IST 2015 | Wed Jan 28 18:00:00 IST 2015 | Wed Jan 21 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 |  | COMPLETED
1186 | TT_TASK | TBM drive & lining installation CH123+084 to CH122+984 | Wed Feb 04 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 | Thu Feb 12 08:00:00 IST 2015 | Thu Feb 26 18:00:00 IST 2015 |  | COMPLETED
1187 | TT_TASK | TBM drive & lining installation CH122+984 to CH122+884 | Thu Feb 12 08:00:00 IST 2015 | Tue Feb 24 18:00:00 IST 2015 | Fri Feb 27 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1188 | TT_TASK | TBM drive & lining installation CH122+884 to CH122+784 | Tue Mar 10 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Wed May 27 18:00:00 IDT 2015 |  | COMPLETED
1189 | TT_TASK | TBM drive & lining installation CH122+784 to CH122+684 | Wed May 06 08:00:00 IDT 2015 | Thu May 14 18:00:00 IDT 2015 | Thu May 28 08:00:00 IDT 2015 | Sat Jul 11 18:00:00 IDT 2015 |  | COMPLETED
1190 | TT_TASK | TBM drive & lining installation CH122+684 to CH122+584 | Fri Jul 03 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
1191 | TT_TASK | TBM drive & lining installation CH122+584 to CH122+506 | Tue Nov 03 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 |  | COMPLETED
1192 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 |  | COMPLETED
1193 | TT_TASK | Dis-assemble TBM | Wed Dec 16 08:00:00 IST 2015 | Fri Jan 22 18:00:00 IST 2016 | Sun Dec 13 08:00:00 IST 2015 | Sun Mar 13 18:00:00 IST 2016 |  | COMPLETED
1194 | TT_TASK | Invert slab, side walkway | Fri Apr 01 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 | Mon Mar 14 08:00:00 IST 2016 | Tue May 24 18:00:00 IDT 2016 |  | COMPLETED
1195 | TT_TASK | Installation of cable bracket | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Mar 15 18:00:00 IST 2016 |  | COMPLETED
1196 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Mon Feb 01 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 22 18:00:00 IST 2016 |  | COMPLETED
1199 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 1 (From Downtrack to Centre of CP) | Thu Apr 10 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Sat Jun 28 18:00:00 IDT 2014 |  | COMPLETED
1200 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Sun Nov 09 18:00:00 IST 2014 |  | COMPLETED
1201 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1202 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 18:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1203 | TT_TASK | Excavation 0-4mts with Shotcrete | Mon Feb 02 08:00:00 IST 2015 | Tue Feb 17 18:00:00 IST 2015 | Mon Feb 23 08:00:00 IST 2015 | Mon Mar 30 18:00:00 IDT 2015 |  | COMPLETED
1204 | TT_TASK | Invert Concrete | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1205 | TT_TASK | Wall and Roof concrete | Thu Apr 16 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 |  | COMPLETED
1206 | TT_TASK | Dismantle Temporary frame | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 |  | COMPLETED
1207 | TT_TASK | Install Door to Cross Passage (By contract 827) | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 |  | COMPLETED
1208 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 2 (From Centre of CP to Uptrack) | Sat Oct 17 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Sep 07 08:00:00 IDT 2015 | Tue Dec 01 18:00:00 IST 2015 |  | COMPLETED
1209 | TT_TASK | Probe/Grout | Thu Jun 25 08:00:00 IDT 2015 | Mon Jul 06 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Fri Apr 10 18:00:00 IDT 2015 |  | COMPLETED
1210 | TT_TASK | Coring of Segment | Tue Jul 07 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Sat Apr 11 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1211 | TT_TASK | Removal of segment | Sat Jul 11 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
1212 | TT_TASK | Excavation 0-4mts with Shotcrete | Wed Jul 15 08:00:00 IDT 2015 | Sat Jul 25 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1213 | TT_TASK | Invert Concrete | Sat Jul 18 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 | Thu May 07 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1214 | TT_TASK | Wall and Roof concrete | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1215 | TT_TASK | Dismantle Temporary frame | Tue Jan 19 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 04 18:00:00 IST 2016 |  | COMPLETED
1216 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Feb 22 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Fri Feb 05 08:00:00 IST 2016 | Sat Feb 06 18:00:00 IST 2016 |  | COMPLETED
1218 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 1 (From Downtrack to Centre of CP) | Tue Mar 11 08:00:00 IST 2014 | Wed Mar 26 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1219 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Wed Nov 12 18:00:00 IST 2014 |  | COMPLETED
1220 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Thu Nov 13 08:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1221 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Tue Nov 18 08:00:00 IST 2014 | Thu Nov 20 18:00:00 IST 2014 |  | COMPLETED
1222 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Sat Nov 22 08:00:00 IST 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1223 | TT_TASK | Invert Concrete | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
1224 | TT_TASK | Wall and Roof concrete | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1225 | TT_TASK | Dismantle Temporary frame | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1226 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1227 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 2 (From Centre of CP to Uptrack) | Thu May 21 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Mar 09 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1228 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Mon May 04 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1229 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
1230 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1231 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 22 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
1232 | TT_TASK | Invert Concrete | Sat Aug 08 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Wed Jul 08 18:00:00 IDT 2015 |  | COMPLETED
1233 | TT_TASK | Wall and Roof concrete | Tue Aug 25 08:00:00 IDT 2015 | Mon Sep 07 18:00:00 IDT 2015 | Thu Jul 09 08:00:00 IDT 2015 | Sat Aug 15 18:00:00 IDT 2015 |  | COMPLETED
1234 | TT_TASK | Dismantle Temporary frame | Tue Sep 22 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 | Mon Aug 17 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 |  | COMPLETED
1235 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1237 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 1 (From Downtrack to Centre of CP) | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Sat May 24 18:00:00 IDT 2014 |  | COMPLETED
1238 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
1239 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1240 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 |  | COMPLETED
1241 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Mon Nov 17 08:00:00 IST 2014 | Sat Nov 29 18:00:00 IST 2014 |  | COMPLETED
1242 | TT_TASK | Invert Concrete | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 |  | COMPLETED
1243 | TT_TASK | Wall and Roof concrete | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 |  | COMPLETED
1244 | TT_TASK | Dismantle Temporary frame | Tue Dec 30 08:00:00 IST 2014 | Wed Jan 07 18:00:00 IST 2015 | Tue Dec 30 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1245 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1246 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 2 (From Centre of CP to Uptrack) | Fri May 08 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 |  | COMPLETED
1247 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
1248 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
1249 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Thu May 07 18:00:00 IDT 2015 |  | COMPLETED
1250 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
1251 | TT_TASK | Invert Concrete | Wed Aug 05 08:00:00 IDT 2015 | Fri Aug 14 18:00:00 IDT 2015 | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
1252 | TT_TASK | Wall and Roof concrete | Tue Sep 15 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Wed Aug 26 18:00:00 IDT 2015 |  | COMPLETED
1253 | TT_TASK | Dismantle Temporary frame | Sat Oct 17 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Oct 08 18:00:00 IDT 2015 |  | COMPLETED
1254 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1258 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 |  | COMPLETED
1259 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1260 | TT_TASK | D-wall construction (1192m3) | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 |  | COMPLETED
1261 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1262 | TT_TASK | Construct capping beam, cobble, etc. (including bay 6 and 5) | Sat Oct 27 08:00:00 IST 2012 | Sat Feb 16 18:00:00 IST 2013 | Sat Oct 27 08:00:00 IST 2012 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1264 | TT_TASK | Excavate up to +22.0mPD (1860m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1265 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 |  | COMPLETED
1266 | TT_TASK | Excavate up to +16.5mPD (3410m3) | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 |  | COMPLETED
1267 | TT_TASK | Install Strut S2 +17.0mPD | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 |  | COMPLETED
1268 | TT_TASK | Excavate up to +11.0mPD (3410m3) | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 |  | COMPLETED
1269 | TT_TASK | Install Strut S3 +11.5mPD | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 |  | COMPLETED
1270 | TT_TASK | Excavate up to +7.0mPD (2480m3) | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 |  | COMPLETED
1271 | TT_TASK | Install Strut S4 +7.5mPD | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1272 | TT_TASK | Excavate up to +3.5mPD (2170m3) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 |  | COMPLETED
1273 | TT_TASK | Install Strut S5 +4.0mPD | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1274 | TT_TASK | Excavate up to formation (2294m3) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1275 | TT_TASK | Construct temp. 500mm thick plain concrete base slab | Thu Oct 18 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 |  | COMPLETED
1276 | TT_TASK | Removal of South Bound strut to +9.50mPD | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1277 | TT_TASK | Removal of North Bound strut to +9.50mPD | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 |  | COMPLETED
1278 | TT_TASK | Construct temp. 500mm thick TBM concrete base slab | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1279 | TT_TASK | Construction entrance seal for TBM at South Bound | Mon Nov 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1280 | TT_TASK | Construction entrance seal for TBM at North Bound | Sat Jul 20 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1281 | TT_TASK | Saw cut South Bound diaphragm wall | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1282 | TT_TASK | Saw cut North Bound diaphragm wall | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1286 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 05 18:00:00 IDT 2014 | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 |  | COMPLETED
1287 | TT_TASK | Erect external formwork (Base Slab) | Sat Sep 06 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 21 18:00:00 IDT 2014 |  | COMPLETED
1288 | TT_TASK | Rebar fixing (Base Slab) | Wed Sep 10 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Tue Jul 22 08:00:00 IDT 2014 | Sat Jul 26 18:00:00 IDT 2014 |  | COMPLETED
1289 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Sep 15 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Sun Jul 27 08:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1290 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Thu Aug 14 18:00:00 IDT 2014 |  | COMPLETED
1291 | TT_TASK | Concreting (Base Slab) (225m3) | Sat Aug 09 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Fri Aug 15 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
1292 | TT_TASK | Curing (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
1293 | TT_TASK | Removal of formwork (Base Slab) | Tue Aug 12 08:00:00 IDT 2014 | Tue Aug 12 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1294 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed Aug 13 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Mon Sep 15 18:00:00 IDT 2014 |  | COMPLETED
1295 | TT_TASK | Rebar fixing (Wall & Roof) | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 |  | COMPLETED
1296 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 |  | COMPLETED
1297 | TT_TASK | Clearing and inspection (Wall & Roof) | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
1298 | TT_TASK | Concreting (Wall & Roof) (450m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
1299 | TT_TASK | Curing (Wall & Roof) | Sat Oct 11 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
1300 | TT_TASK | Removal external formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1301 | TT_TASK | Removal internal falsework (Wall & Roof) | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 |  | COMPLETED
1302 | TT_TASK | Side walkway and cable bracket (102m3) | Sat Oct 18 08:00:00 IDT 2014 | Wed Oct 29 18:00:00 IST 2014 | Mon Sep 01 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1304 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Wed Nov 11 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Oct 19 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1305 | TT_TASK | Erect external formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 |  | COMPLETED
1306 | TT_TASK | Rebar fixing (Base Slab) | Mon Nov 16 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Tue Oct 27 08:00:00 IST 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1307 | TT_TASK | Erect internal kicker formwork (Base Slab) | Fri Nov 20 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Oct 31 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 |  | COMPLETED
1308 | TT_TASK | Clearing and inspection (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
1309 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1310 | TT_TASK | Curing (Base Slab) | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 |  | COMPLETED
1311 | TT_TASK | Removal of formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 |  | COMPLETED
1312 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
1313 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Dec 09 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
1314 | TT_TASK | Erect external formwork (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Thu Jan 07 18:00:00 IST 2016 |  | COMPLETED
1315 | TT_TASK | Clearing and inspection (Wall & Roof) | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Fri Jan 08 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
1316 | TT_TASK | Concreting (Wall & Roof) (450m3) | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
1317 | TT_TASK | Curing (Wall & Roof) | Tue Jan 12 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
1318 | TT_TASK | Removal external formwork (Wall ) | Thu Jan 14 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
1319 | TT_TASK | Removal internal falsework, formwork and reproping (Wall & Roof) | Thu Jan 28 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 |  | COMPLETED
1320 | TT_TASK | Side walkway and cable bracket (102m3) | Wed Dec 23 08:00:00 IST 2015 | Wed Jan 06 18:00:00 IST 2016 | Wed Nov 11 08:00:00 IST 2015 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
1322 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 |  | COMPLETED
1323 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 |  | COMPLETED
1324 | TT_TASK | Backfilling to 0.5m below S3 (+11.0mPD) (3486m3) | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 |  | COMPLETED
1325 | TT_TASK | Removal strut S3 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
1326 | TT_TASK | Backfilling to 0.5m below S2 (+16.5mPD) (3410m3) | Wed Mar 16 08:00:00 IST 2016 | Fri Apr 08 18:00:00 IDT 2016 | Wed Mar 16 08:00:00 IST 2016 | Tue Apr 12 18:00:00 IDT 2016 |  | COMPLETED
1327 | TT_TASK | Removal strut S2 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 |  | COMPLETED
1328 | TT_TASK | Backfilling to 0.5m below S1 (+22.0mPD) (3410m3) | Fri Apr 15 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 | Fri Apr 15 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
1329 | TT_TASK | Removal strut S1 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 |  | COMPLETED
1330 | TT_TASK | Backfilling to original ground level (approx. +25.0mPD) (1860m3) | Thu May 05 08:00:00 IDT 2016 | Tue May 17 18:00:00 IDT 2016 | Thu May 05 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
1333 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1334 | TT_TASK | D-wall construction (2844m3) | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1335 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1337 | TT_TASK | Excavate up to +22.0mPD (3720m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1338 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 |  | COMPLETED
1339 | TT_TASK | Excavate up to +16.5mPD (4880m3) | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 |  | COMPLETED
1340 | TT_TASK | Install Strut S2 +17.0mPD | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 |  | COMPLETED
1341 | TT_TASK | Excavate up to +11.0mPD (6820m3) | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
1342 | TT_TASK | Install Strut S3 +11.5mPD | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 |  | COMPLETED
1343 | TT_TASK | Excavate up to +7.0mPD (4960m3) | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 |  | COMPLETED
1344 | TT_TASK | Install Strut S4 +7.5mPD | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1345 | TT_TASK | Excavate up to +3.5mPD (4340m3) | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1346 | TT_TASK | Install Strut S5 +4.0mPD | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 |  | COMPLETED
1347 | TT_TASK | Excavate up to formation (4960m3) | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 |  | COMPLETED
1348 | TT_TASK | Construct temp. 500mm thick plain concrete base slab at Bay 5 & 6 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1349 | TT_TASK | Excavation to formation and place blinding Bay 4a | Thu Oct 18 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1350 | TT_TASK | Excavation to formation and place blinding Bay 4b | Fri Jun 21 08:00:00 IDT 2013 | Fri Jul 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1351 | TT_TASK | Excavation to formation and place blinding Bay3 | Sat Jul 13 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1352 | TT_TASK | Excavation to formation and place blinding Bay2 to Bay1 | Wed Jul 24 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1356 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 |  | COMPLETED
1357 | TT_TASK | Erect external formwork for base slab | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 |  | COMPLETED
1358 | TT_TASK | Rebar fixing for base slab | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1359 | TT_TASK | Erect internal kicker formwork for base slab | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1360 | TT_TASK | Concreting for base slab (363m3) | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1361 | TT_TASK | Curing for base slab | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1362 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1363 | TT_TASK | Removal of formwork for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1364 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1365 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 27 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1366 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1367 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1368 | TT_TASK | Curing for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1369 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1370 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 10 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1371 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 19 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jan 24 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1372 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 08 08:00:00 IST 2015 | Tue Jan 13 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1374 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 |  | COMPLETED
1375 | TT_TASK | Erect external formwork for base slab | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1376 | TT_TASK | Rebar fixing for base slab | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1377 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 |  | COMPLETED
1378 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1379 | TT_TASK | Curing for base slab | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1380 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1381 | TT_TASK | Removal of formwork for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1382 | TT_TASK | Rebar fixing for central slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1383 | TT_TASK | Erect external formwork for central slab | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1384 | TT_TASK | Concreting for central slab (450m3) | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1385 | TT_TASK | Curing for central slab | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1386 | TT_TASK | Preparation of construction joint for central slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1387 | TT_TASK | Removal of formwork for central slab | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1388 | TT_TASK | Removal strut S5 and S4 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1389 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1390 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1391 | TT_TASK | Erect external formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1392 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1393 | TT_TASK | Curing for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1394 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1395 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 08 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1396 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1397 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Nov 19 08:00:00 IST 2015 | Tue Nov 24 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 |  | COMPLETED
1400 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1401 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1402 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1403 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1404 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1405 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1406 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1407 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1408 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1409 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1410 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 10 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1411 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1412 | TT_TASK | Curing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1413 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1414 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1415 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1416 | TT_TASK | Side walkway and cable bracket | Fri Jan 02 08:00:00 IST 2015 | Wed Jan 07 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1418 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1419 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1420 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1421 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1422 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1423 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1424 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1425 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1426 | TT_TASK | Rebar fixing for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1427 | TT_TASK | Erect external formwork for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1428 | TT_TASK | Concreting for central slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1429 | TT_TASK | Curing for central slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1430 | TT_TASK | Preparation of construction joint for central slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1431 | TT_TASK | Removal of formwork for central slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 21 18:00:00 IST 2012 |  | COMPLETED
1432 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1433 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1434 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1435 | TT_TASK | Erect external formwork for wall | Mon Jul 15 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1436 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1437 | TT_TASK | Curing for wall and roof | Sun Jul 21 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1438 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1439 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 22 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1440 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 31 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1441 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Sep 16 08:00:00 IDT 2015 | Mon Sep 21 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1443 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1444 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1445 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1446 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1447 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1448 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1449 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1450 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1451 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1452 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1453 | TT_TASK | Erect external formwork for wall | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1454 | TT_TASK | Concreting for wall and roof (444m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1455 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1456 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1457 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Sat Feb 09 18:00:00 IST 2013 |  | COMPLETED
1458 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Nov 09 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Tue Oct 06 08:00:00 IDT 2015 | Sat Oct 10 18:00:00 IDT 2015 |  | COMPLETED
1461 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1462 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1463 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1464 | TT_TASK | Erect internal kicker formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1465 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1466 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1467 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1468 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1469 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1470 | TT_TASK | Curing | Wed Jun 12 08:00:00 IDT 2013 | Wed Jun 12 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1471 | TT_TASK | Removal strut S5 and S4 | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1473 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1474 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1475 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1476 | TT_TASK | Concreting for wall and roof (450m3) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1477 | TT_TASK | Curing for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1478 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1479 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1480 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 29 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1481 | TT_TASK | Side walkway and cable bracket | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1483 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1484 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1485 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1486 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1487 | TT_TASK | Curing for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1488 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1489 | TT_TASK | Removal external wall formwork for wall | Wed Jun 26 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1490 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1491 | TT_TASK | Side walkway and cable bracket | Fri Sep 04 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
1494 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1495 | TT_TASK | Erect external formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1496 | TT_TASK | Rebar fixing for base slab | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1497 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1498 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 |  | COMPLETED
1499 | TT_TASK | Curing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1500 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1501 | TT_TASK | Removal of formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1502 | TT_TASK | Shear beam | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1503 | TT_TASK | Curing | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1504 | TT_TASK | Removal strut S5 and S4 | Wed Jun 19 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1506 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 24 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1507 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1508 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1509 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1510 | TT_TASK | Curing for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1511 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1512 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1513 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1514 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
1516 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1517 | TT_TASK | Rebar fixing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1518 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1519 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1520 | TT_TASK | Curing for wall and roof | Sun Jun 23 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1521 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1522 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 25 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1523 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 03 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1524 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Aug 29 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1527 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1528 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Sat Dec 22 18:00:00 IST 2012 |  | COMPLETED
1529 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1530 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1531 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1532 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1533 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1534 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Fri Jan 11 18:00:00 IST 2013 |  | COMPLETED
1535 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Jan 12 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1536 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1537 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1539 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1540 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1541 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1542 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1543 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1544 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1545 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1546 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1547 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 |  | COMPLETED
1549 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1550 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Mon Feb 25 18:00:00 IST 2013 |  | COMPLETED
1551 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1552 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1553 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1554 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1555 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1556 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1557 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Aug 24 08:00:00 IDT 2015 | Fri Aug 28 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1560 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1561 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1562 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1563 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1564 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1565 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1566 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1567 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1568 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1569 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1570 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1572 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1573 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1574 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1575 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1576 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1577 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1578 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1579 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1580 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
1582 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1583 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1584 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1585 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1586 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1587 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1588 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1589 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1590 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Aug 18 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1593 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1594 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1595 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1596 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1597 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1598 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1599 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1600 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1601 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1602 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1603 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1605 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 31 18:00:00 IDT 2013 |  | COMPLETED
1606 | TT_TASK | Rebar fixing for wall and roof | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 |  | COMPLETED
1607 | TT_TASK | Erect external formwork for wall and roof | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 | Fri Sep 06 08:00:00 IDT 2013 | Thu Sep 12 18:00:00 IDT 2013 |  | COMPLETED
1608 | TT_TASK | Concreting for wall and roof (450m3) | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 |  | COMPLETED
1609 | TT_TASK | Curing for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1610 | TT_TASK | Preparation of construction joint for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1611 | TT_TASK | Removal external and internal formwork for wall | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Wed Sep 25 18:00:00 IDT 2013 |  | COMPLETED
1612 | TT_TASK | Removal internal falsework and formwork for roof | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1613 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 08 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1615 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 20 18:00:00 IST 2013 |  | COMPLETED
1616 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1617 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1618 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1619 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1620 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1621 | TT_TASK | Removal external wall formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1622 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1623 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Aug 12 08:00:00 IDT 2015 | Mon Aug 17 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1626 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1627 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1628 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Feb 14 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1629 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1630 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Mon Feb 18 18:00:00 IST 2013 |  | COMPLETED
1631 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1632 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1633 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1634 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1635 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1636 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1638 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jul 12 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1639 | TT_TASK | Rebar fixing for wall and roof | Wed Jul 17 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1640 | TT_TASK | Erect external formwork for wall and roof | Wed Aug 14 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1641 | TT_TASK | Concreting for wall and roof (450m3) | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1642 | TT_TASK | Curing for wall and roof | Sun Aug 11 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1643 | TT_TASK | Preparation of construction joint for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1644 | TT_TASK | Removal external and internal formwork for wall | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1645 | TT_TASK | Removal internal falsework and formwork for roof | Wed Aug 21 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1646 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 03 08:00:00 IST 2014 | Fri Mar 07 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1648 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1649 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1650 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Apr 09 08:00:00 IDT 2013 | Thu Apr 11 18:00:00 IDT 2013 |  | COMPLETED
1651 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1652 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1653 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1654 | TT_TASK | Removal external wall formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1655 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
1656 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Aug 06 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Mon Jul 27 08:00:00 IDT 2015 | Fri Jul 31 18:00:00 IDT 2015 |  | COMPLETED
1658 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Sep 12 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1659 | TT_TASK | Rebar fixing for roof | Tue Sep 17 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1660 | TT_TASK | Erect external formwork for roof | Thu Sep 19 08:00:00 IDT 2013 | Thu Sep 19 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1661 | TT_TASK | Concreting for roof (444m3) | Sat Sep 21 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1662 | TT_TASK | Curing for roof | Sun Sep 22 08:00:00 IDT 2013 | Tue Oct 01 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1663 | TT_TASK | Preparation of construction joint for roof | Mon Sep 23 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1664 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1665 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1668 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1669 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1670 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1671 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1672 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1673 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1674 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1675 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1676 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1677 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1678 | TT_TASK | Removal strut S5 and S4 | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1680 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Thu Apr 25 18:00:00 IDT 2013 |  | COMPLETED
1681 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri May 03 08:00:00 IDT 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
1682 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Thu May 16 08:00:00 IDT 2013 | Thu May 23 18:00:00 IDT 2013 |  | COMPLETED
1683 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1684 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1685 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1686 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Wed May 29 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1687 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1688 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 19 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1690 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Fri Apr 19 18:00:00 IDT 2013 |  | COMPLETED
1691 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1692 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Apr 25 08:00:00 IDT 2013 | Sat Apr 27 18:00:00 IDT 2013 |  | COMPLETED
1693 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1694 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1695 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1696 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1697 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1698 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 02 08:00:00 IDT 2015 | Sat Apr 11 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Feb 27 18:00:00 IST 2015 |  | COMPLETED
1700 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1701 | TT_TASK | Rebar fixing for roof | Tue Aug 06 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1702 | TT_TASK | Erect external formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1703 | TT_TASK | Concreting for roof (444m3) | Fri Aug 09 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 |  | COMPLETED
1704 | TT_TASK | Curing for roof | Thu Aug 01 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1705 | TT_TASK | Preparation of construction joint for roof | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 |  | COMPLETED
1706 | TT_TASK | Removal internal falsework and formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1707 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 09 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1710 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Wed Feb 20 18:00:00 IST 2013 |  | COMPLETED
1711 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1712 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1713 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1714 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1715 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1716 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1717 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1718 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1719 | TT_TASK | Curing | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1720 | TT_TASK | Removal strut S5 and S4 | Mon Jun 24 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1722 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1723 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1724 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Wed Jul 10 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1725 | TT_TASK | Concreting for wall and roof (450m3) | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1726 | TT_TASK | Curing for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1727 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1728 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 |  | COMPLETED
1729 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 |  | COMPLETED
1730 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1732 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1733 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1734 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1735 | TT_TASK | Concreting for wall and roof (450m3) | Tue Sep 03 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1736 | TT_TASK | Curing for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1737 | TT_TASK | Preparation of construction joint for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 |  | COMPLETED
1738 | TT_TASK | Removal external and internal formwork for wall | Thu Sep 05 08:00:00 IDT 2013 | Fri Sep 06 18:00:00 IDT 2013 | Thu Aug 22 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1739 | TT_TASK | Removal internal falsework and formwork for roof | Sat Sep 14 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 |  | COMPLETED
1740 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 05 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1742 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1743 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1744 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1745 | TT_TASK | Concreting for roof (363m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1746 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Sun Oct 20 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1747 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1748 | TT_TASK | Removal internal falsework and formwork for roof | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1749 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Dec 24 13:00:00 IST 2013 | Thu Jan 02 12:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1752 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1753 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1754 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1755 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Apr 12 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1756 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1757 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1758 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1759 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1760 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1761 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1762 | TT_TASK | Removal strut S5 and S4 | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1764 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Aug 05 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1765 | TT_TASK | Rebar fixing for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1766 | TT_TASK | Erect external formwork for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1767 | TT_TASK | Concreting for wall and roof (450m3) | Thu Aug 15 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1768 | TT_TASK | Curing for wall and roof | Fri Aug 16 08:00:00 IDT 2013 | Sun Aug 25 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1769 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1770 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1771 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 |  | COMPLETED
1772 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Feb 04 08:00:00 IST 2014 | Sat Feb 08 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1774 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Aug 07 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1775 | TT_TASK | Rebar fixing for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1776 | TT_TASK | Erect external formwork for wall and roof | Thu Aug 15 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1777 | TT_TASK | Concreting for wall and roof (450m3) | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1778 | TT_TASK | Curing for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1779 | TT_TASK | Preparation of construction joint for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 |  | COMPLETED
1780 | TT_TASK | Removal external and internal formwork for wall | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Wed Aug 21 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 |  | COMPLETED
1781 | TT_TASK | Removal internal falsework and formwork for roof | Mon Sep 16 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1782 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Nov 19 08:00:00 IST 2014 | Mon Nov 24 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1784 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1785 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1786 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1787 | TT_TASK | Concreting for roof (450m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1788 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1789 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1790 | TT_TASK | Removal internal falsework and formwork for roof | Fri Oct 18 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1791 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 13 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1794 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1795 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1796 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1797 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1798 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 28 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1799 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1800 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1801 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1802 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1803 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1804 | TT_TASK | Removal strut S5 and S4 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1806 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1807 | TT_TASK | Rebar fixing for wall and roof | Sat Jul 20 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1808 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1809 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1810 | TT_TASK | Curing for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1811 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1812 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 29 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1813 | TT_TASK | Removal internal falsework and formwork for roof | Tue Aug 06 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1814 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 18:00:00 IST 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1816 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1817 | TT_TASK | Rebar fixing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1818 | TT_TASK | Erect external formwork for wall and roof | Fri Jul 19 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1819 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1820 | TT_TASK | Curing for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Thu Mar 28 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1821 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Mar 29 08:00:00 IDT 2013 | Fri Mar 29 18:00:00 IDT 2013 |  | COMPLETED
1822 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Sat Mar 30 08:00:00 IDT 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1823 | TT_TASK | Removal internal falsework and formwork for roof | Fri Aug 02 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Mon Apr 01 18:00:00 IDT 2013 |  | COMPLETED
1824 | TT_TASK | Side walkway and cable bracket | Thu Nov 13 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1826 | TT_TASK | Erect internal formwork & Falsework for roof | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1827 | TT_TASK | Rebar fixing for roof | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 |  | COMPLETED
1828 | TT_TASK | Erect shutter formwork for roof | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 09 18:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1829 | TT_TASK | Concreting for roof (450m3) | Tue Sep 10 08:00:00 IDT 2013 | Tue Sep 10 18:00:00 IDT 2013 | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 |  | COMPLETED
1830 | TT_TASK | Curing for roof | Wed Sep 11 08:00:00 IDT 2013 | Fri Sep 20 18:00:00 IDT 2013 | Tue Jul 23 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 |  | COMPLETED
1831 | TT_TASK | Preparation of construction joint for roof | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 11 18:00:00 IDT 2013 | Sat Aug 03 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1832 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 26 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 |  | COMPLETED
1833 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 06 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Aug 13 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1835 | TT_TASK | Water proofing and soil backfilling to 0.5m below top of Tunnel Bay 3 to Bay 1 | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1836 | TT_TASK | Mass infill between D-wall and tunnel wall | Fri Oct 11 08:00:00 IDT 2013 | Wed Oct 16 18:00:00 IDT 2013 | Fri Sep 20 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1837 | TT_TASK | Removal S3 and S2 | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
1838 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 4 | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Sat May 18 18:00:00 IDT 2013 |  | COMPLETED
1839 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 5 and remove S3 & S2 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1840 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 6 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1843 | TT_TASK | Pre-drilling and guidewall | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1844 | TT_TASK | D-wall design review | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1845 | TT_TASK | D-wall construction (4741m3) | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 |  | COMPLETED
1846 | TT_TASK | Shear pin and pumping test | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 15 18:00:00 IST 2012 | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1848 | TT_TASK | ELS works to formation level from SN16 to SN19 (soil: 8,700m3 @350m3/day, Install S1 to S3 strut 5 days/layer) | Wed Sep 25 08:00:00 IDT 2013 | Wed Nov 13 18:00:00 IST 2013 | Wed May 08 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1849 | TT_TASK | Design temporary bridge and approval | Mon Sep 01 08:00:00 IDT 2014 | Wed Nov 12 18:00:00 IST 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1850 | TT_TASK | Application of tree transplant | Sat Jun 01 08:00:00 IDT 2013 | Wed Oct 23 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1851 | TT_TASK | Tree transplant | Tue Oct 14 08:00:00 IDT 2014 | Mon Nov 10 18:00:00 IST 2014 | Tue Sep 02 08:00:00 IDT 2014 | Tue Sep 30 18:00:00 IDT 2014 |  | COMPLETED
1852 | TT_TASK | Erection temporary bridge deck | Fri Oct 03 08:00:00 IDT 2014 | Fri Dec 05 18:00:00 IST 2014 | Fri Oct 03 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1853 | TT_TASK | ELS works to formation level from SN10 to SN15 (soil: 9,455m3 @330m3/day, install S1 to S3 strut 5 days/layer) | Mon Nov 24 08:00:00 IST 2014 | Sat Jan 17 18:00:00 IST 2015 | Mon Nov 24 08:00:00 IST 2014 | Tue Jun 23 18:00:00 IDT 2015 |  | COMPLETED
1856 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
1857 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1858 | TT_TASK | Erect external formwork for wall and roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1859 | TT_TASK | Concreting for wall and roof (215m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
1860 | TT_TASK | Curing for wall and roof | Sun Dec 08 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
1861 | TT_TASK | Preparation of construction joint for wall and roof | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1862 | TT_TASK | Removal external and internal formwork for wall | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1863 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1864 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 03 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 | Mon Mar 24 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
1866 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 14 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1867 | TT_TASK | Rebar fixing for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1868 | TT_TASK | Erect external formwork for wall and roof | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1869 | TT_TASK | Concreting for wall and roof (215m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1870 | TT_TASK | Curing for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Sun Dec 29 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1871 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
1872 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 17 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
1873 | TT_TASK | Removal internal falsework and formwork for roof | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1874 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 |  | COMPLETED
1876 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 28 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Nov 28 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1877 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1878 | TT_TASK | Erect external formwork for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1879 | TT_TASK | Concreting for wall and roof (215m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1880 | TT_TASK | Curing for wall and roof | Wed Jan 01 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
1881 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
1882 | TT_TASK | Removal external and internal formwork for wall | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 |  | COMPLETED
1883 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
1884 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 |  | COMPLETED
1886 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1887 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 14 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1888 | TT_TASK | Erect external formwork for wall and roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1889 | TT_TASK | Concreting for wall and roof (215m3) | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1890 | TT_TASK | Curing for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1892 | TT_TASK | Removal external and internal formwork for wall | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1893 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1894 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 |  | COMPLETED
1896 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 08:00:00 IST 2013 |  | COMPLETED
1897 | TT_TASK | Rebar fixing for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1898 | TT_TASK | Erect external formwork for wall and roof | Fri Jan 03 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1899 | TT_TASK | Concreting for wall and roof (215m3) | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1900 | TT_TASK | Curing for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 16 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1901 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Tue Jan 07 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1902 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1903 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1904 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 |  | COMPLETED
1906 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1907 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1908 | TT_TASK | Erect external formwork for wall and roof | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1909 | TT_TASK | Concreting for wall and roof (215m3) | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1910 | TT_TASK | Curing for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1911 | TT_TASK | Preparation of construction joint for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1912 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1913 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1914 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 |  | COMPLETED
1916 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1917 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 |  | COMPLETED
1918 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Tue Jun 04 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 |  | COMPLETED
1919 | TT_TASK | Concreting for wall and roof (333m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1920 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1921 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Wed Jun 12 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1922 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 |  | COMPLETED
1923 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
1924 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 05 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Tue Mar 04 18:00:00 IST 2014 |  | COMPLETED
1926 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1927 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1928 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1929 | TT_TASK | Concreting for wall and roof (412m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1930 | TT_TASK | Curing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Sun Jun 23 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Sat Mar 23 18:00:00 IST 2013 |  | COMPLETED
1931 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Mar 25 08:00:00 IST 2013 | Mon Mar 25 18:00:00 IST 2013 |  | COMPLETED
1932 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Mar 26 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1933 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jun 24 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1934 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 27 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Mon Mar 03 18:00:00 IST 2014 |  | COMPLETED
1936 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1937 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1938 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Apr 02 18:00:00 IDT 2013 |  | COMPLETED
1939 | TT_TASK | Concreting for wall and roof (320m3) | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Apr 05 08:00:00 IDT 2013 | Fri Apr 05 18:00:00 IDT 2013 |  | COMPLETED
1940 | TT_TASK | Curing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 06 08:00:00 IDT 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1941 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1942 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1943 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1944 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jan 21 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Sat Mar 01 18:00:00 IST 2014 |  | COMPLETED
1946 | TT_TASK | Excavation and saw cut D-wall | Thu Apr 02 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Sat Jul 25 18:00:00 IDT 2015 |  | COMPLETED
1947 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Aug 08 16:24:00 IDT 2015 | Mon Aug 10 16:24:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Mon Jul 13 18:00:00 IDT 2015 |  | COMPLETED
1948 | TT_TASK | Erect external formwork for base slab | Mon Aug 10 16:24:00 IDT 2015 | Wed Aug 12 16:24:00 IDT 2015 | Tue Jul 14 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
1949 | TT_TASK | Rebar fixing for base slab | Wed Aug 12 16:24:00 IDT 2015 | Fri Aug 14 16:24:00 IDT 2015 | Wed Jul 15 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1950 | TT_TASK | Erect internal kicker formwork for base slab | Fri Aug 14 16:24:00 IDT 2015 | Mon Aug 17 16:24:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Wed Aug 12 18:00:00 IDT 2015 |  | COMPLETED
1951 | TT_TASK | Concreting for base slab (90m3) | Wed Sep 02 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 | Thu Aug 13 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 |  | COMPLETED
1952 | TT_TASK | Curing for base slab | Thu Sep 03 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Fri Aug 14 08:00:00 IDT 2015 | Thu Aug 20 18:00:00 IDT 2015 |  | COMPLETED
1953 | TT_TASK | Preparation of construction joint for base slab | Thu Sep 03 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Fri Aug 21 08:00:00 IDT 2015 | Fri Aug 21 18:00:00 IDT 2015 |  | COMPLETED
1954 | TT_TASK | Removal of formwork for base slab | Fri Sep 04 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Sat Aug 22 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 |  | COMPLETED
1955 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Sep 05 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 | Mon Aug 24 08:00:00 IDT 2015 | Mon Aug 24 18:00:00 IDT 2015 |  | COMPLETED
1956 | TT_TASK | Curing | Thu Sep 10 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Tue Aug 25 08:00:00 IDT 2015 | Tue Aug 25 18:00:00 IDT 2015 |  | COMPLETED
1957 | TT_TASK | Removal strut S3 | Sat Sep 19 08:00:00 IDT 2015 | Wed Sep 23 18:00:00 IDT 2015 | Wed Sep 16 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
1958 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Sep 24 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
1959 | TT_TASK | Rebar fixing for wall and roof | Wed Sep 30 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 | Fri Sep 25 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 |  | COMPLETED
1960 | TT_TASK | Erect external formwork for wall and roof | Thu Oct 15 08:00:00 IDT 2015 | Fri Oct 16 18:00:00 IDT 2015 | Mon Oct 05 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
1961 | TT_TASK | Concreting for wall and roof (260m3) | Sat Oct 17 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 | Wed Oct 07 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1962 | TT_TASK | Curing for wall and roof | Sun Oct 18 08:00:00 IDT 2015 | Tue Oct 27 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 |  | COMPLETED
1963 | TT_TASK | Preparation of construction joint for wall and roof | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
1964 | TT_TASK | Removal external and internal formwork for wall | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
1965 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 28 08:00:00 IST 2015 | Thu Oct 29 18:00:00 IST 2015 | Thu Oct 22 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1966 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Oct 30 08:00:00 IST 2015 | Wed Nov 04 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1968 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 02 18:00:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 |  | COMPLETED
1969 | TT_TASK | Erect external formwork for base slab | Fri Jul 03 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Tue Jul 21 08:00:00 IDT 2015 | Wed Jul 22 18:00:00 IDT 2015 |  | COMPLETED
1970 | TT_TASK | Rebar fixing for base slab | Mon Jul 06 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 23 08:00:00 IDT 2015 | Fri Jul 24 18:00:00 IDT 2015 |  | COMPLETED
1971 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jul 08 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Sat Jul 25 08:00:00 IDT 2015 | Mon Jul 27 18:00:00 IDT 2015 |  | COMPLETED
1972 | TT_TASK | Concreting for base slab (123m3) | Fri Jul 10 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jul 28 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 |  | COMPLETED
1973 | TT_TASK | Curing for base slab | Sat Jul 11 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1974 | TT_TASK | Preparation of construction joint for base slab | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 |  | COMPLETED
1975 | TT_TASK | Removal of formwork for base slab | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 |  | COMPLETED
1976 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1977 | TT_TASK | Curing | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 |  | COMPLETED
1978 | TT_TASK | Removal strut S3 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1979 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 |  | COMPLETED
1980 | TT_TASK | Rebar fixing for wall and roof | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 |  | COMPLETED
1981 | TT_TASK | Erect external formwork for wall and roof | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 |  | COMPLETED
1982 | TT_TASK | Concreting for wall and roof (260m3) | Fri Oct 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 | Sat Oct 24 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
1983 | TT_TASK | Curing for wall and roof | Sat Oct 03 08:00:00 IDT 2015 | Mon Oct 12 18:00:00 IDT 2015 | Mon Oct 26 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1984 | TT_TASK | Preparation of construction joint for wall and roof | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
1985 | TT_TASK | Removal external and internal formwork for wall | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1986 | TT_TASK | Removal internal falsework and formwork for roof | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1987 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1989 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
1990 | TT_TASK | Erect external formwork for base slab | Mon Jun 15 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1991 | TT_TASK | Rebar fixing for base slab | Wed Jun 17 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
1992 | TT_TASK | Erect internal kicker formwork for base slab | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
1993 | TT_TASK | Concreting for base slab (127m3) | Tue Jun 23 08:00:00 IDT 2015 | Tue Jun 23 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
1994 | TT_TASK | Curing for base slab | Wed Jun 24 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
1995 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 24 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1996 | TT_TASK | Removal of formwork for base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
1997 | TT_TASK | Infill concrete in between D-wall and base slab | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1998 | TT_TASK | Curing | Thu May 28 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1999 | TT_TASK | Removal strut S3 | Fri May 29 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2000 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 03 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2001 | TT_TASK | Rebar fixing for wall and roof | Mon Jun 08 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2002 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2003 | TT_TASK | Concreting for wall and roof (260m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2004 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2005 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2006 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2007 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2008 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 11 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2010 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
2011 | TT_TASK | Erect external formwork for base slab | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
2012 | TT_TASK | Rebar fixing for base slab | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
2013 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
2014 | TT_TASK | Concreting for base slab (127m3) | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
2015 | TT_TASK | Curing for base slab | Thu Jun 11 08:00:00 IDT 2015 | Wed Jun 17 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2016 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 11 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
2017 | TT_TASK | Removal of formwork for base slab | Sat May 23 08:00:00 IDT 2015 | Sat May 23 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
2018 | TT_TASK | Infill concrete in between D-wall and base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
2019 | TT_TASK | Curing | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2020 | TT_TASK | Removal strut S3 | Thu May 28 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2021 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2022 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2023 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2024 | TT_TASK | Concreting for wall and roof (150m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2025 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2026 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2027 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2028 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2029 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jul 06 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
2031 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2032 | TT_TASK | Erect external formwork for base slab | Thu May 21 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2033 | TT_TASK | Rebar fixing for base slab | Sat May 23 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2034 | TT_TASK | Erect internal kicker formwork for base slab | Wed May 27 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2035 | TT_TASK | Concreting for base slab (70m3) | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2036 | TT_TASK | Curing for base slab | Sat May 30 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2037 | TT_TASK | Preparation of construction joint for base slab | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2038 | TT_TASK | Removal of formwork for base slab | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2039 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2040 | TT_TASK | Curing | Sat Jun 06 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2041 | TT_TASK | Removal strut S3 | Mon Jun 08 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat May 23 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2043 | TT_TASK | Rebar fixing for wall and roof | Fri May 29 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2044 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2045 | TT_TASK | Concreting for wall and roof (175m3) | Thu Jun 04 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2046 | TT_TASK | Curing for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sun Jun 14 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2047 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2048 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 03 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 04 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2050 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 29 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
2052 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2053 | TT_TASK | Erect external formwork for base slab | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2054 | TT_TASK | Rebar fixing for base slab | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2055 | TT_TASK | Erect internal kicker formwork for base slab | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2056 | TT_TASK | Concreting for base slab (70m3) | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2057 | TT_TASK | Curing for base slab | Wed Apr 22 08:00:00 IDT 2015 | Tue Apr 28 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2058 | TT_TASK | Preparation of construction joint for base slab | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2059 | TT_TASK | Removal of formwork for base slab | Thu Apr 23 08:00:00 IDT 2015 | Thu Apr 23 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2060 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Apr 24 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2061 | TT_TASK | Curing | Wed Apr 29 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2062 | TT_TASK | Removal strut S3 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2063 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed May 06 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2064 | TT_TASK | Rebar fixing for wall and roof | Thu May 14 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2065 | TT_TASK | Erect external formwork for wall and roof | Mon May 18 08:00:00 IDT 2015 | Tue May 19 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2066 | TT_TASK | Concreting for wall and roof (175m3) | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2067 | TT_TASK | Curing for wall and roof | Thu May 21 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2068 | TT_TASK | Preparation of construction joint for wall and roof | Thu May 21 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2069 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2070 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2071 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jun 23 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
2073 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Fri Nov 15 18:00:00 IST 2013 |  | COMPLETED
2074 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Nov 16 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2075 | TT_TASK | Rebar fixing for base slab | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
2076 | TT_TASK | Erect internal kicker formwork for base slab | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
2077 | TT_TASK | Concreting for base slab (70m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
2078 | TT_TASK | Curing for base slab | Fri Dec 20 08:00:00 IST 2013 | Thu Dec 26 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
2079 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 |  | COMPLETED
2080 | TT_TASK | Removal of formwork for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
2081 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
2082 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2083 | TT_TASK | Removal strut S3 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2084 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Apr 16 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2085 | TT_TASK | Rebar fixing for wall and roof | Thu Apr 24 08:00:00 IDT 2014 | Sat Apr 26 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 |  | COMPLETED
2086 | TT_TASK | Erect external formwork for wall and roof | Mon Apr 28 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Thu Apr 10 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2087 | TT_TASK | Concreting for wall and roof (170m3) | Wed Apr 30 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Sat Apr 12 08:00:00 IDT 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
2088 | TT_TASK | Curing for wall and roof | Thu May 01 08:00:00 IDT 2014 | Sat May 10 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Tue Apr 22 18:00:00 IDT 2014 |  | COMPLETED
2089 | TT_TASK | Preparation of construction joint for wall and roof | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 |  | COMPLETED
2090 | TT_TASK | Removal external and internal formwork for wall | Sat May 03 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Tue Apr 15 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
2091 | TT_TASK | Removal internal falsework and formwork for roof | Mon May 12 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 |  | COMPLETED
2092 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jun 05 08:00:00 IDT 2014 | Tue Jun 10 18:00:00 IDT 2014 | Thu May 29 08:00:00 IDT 2014 | Thu Dec 04 18:00:00 IST 2014 |  | COMPLETED
2094 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2095 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2096 | TT_TASK | Rebar fixing for base slab | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2097 | TT_TASK | Erect internal kicker formwork for base slab | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2098 | TT_TASK | Concreting for base slab (70m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2099 | TT_TASK | Curing for base slab | Sun Dec 08 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2100 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2101 | TT_TASK | Removal of formwork for base slab | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
2102 | TT_TASK | Infill concrete in between D-wall and base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
2103 | TT_TASK | Curing | Sun Dec 15 08:00:00 IST 2013 | Sun Dec 15 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2104 | TT_TASK | Removal strut S3 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2105 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Feb 12 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2106 | TT_TASK | Rebar fixing for wall and roof | Mon Feb 17 08:00:00 IST 2014 | Wed Feb 19 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
2107 | TT_TASK | Erect external formwork for wall and roof | Fri Feb 28 13:48:00 IST 2014 | Mon Mar 03 13:48:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2108 | TT_TASK | Concreting for wall and roof (200m3) | Mon Mar 03 13:48:00 IST 2014 | Tue Mar 04 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2109 | TT_TASK | Curing for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Fri Mar 14 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2110 | TT_TASK | Preparation of construction joint for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Wed Mar 05 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2111 | TT_TASK | Removal external and internal formwork for wall | Wed Mar 05 13:48:00 IST 2014 | Thu Mar 06 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
2112 | TT_TASK | Removal internal falsework and formwork for roof | Fri Mar 14 13:48:00 IST 2014 | Mon Mar 17 13:48:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2113 | TT_TASK | Side walkway and cable bracket (204m3) | Thu May 29 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Wed Dec 03 18:00:00 IST 2014 |  | COMPLETED
2115 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2116 | TT_TASK | Erect external formwork for base slab | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2117 | TT_TASK | Rebar fixing for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2118 | TT_TASK | Erect internal kicker formwork for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2119 | TT_TASK | Concreting for base slab (70m3) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2120 | TT_TASK | Curing for base slab | Tue Dec 03 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2121 | TT_TASK | Preparation of construction joint for base slab | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
2122 | TT_TASK | Removal of formwork for base slab | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2123 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2124 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2125 | TT_TASK | Removal strut S3 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
2126 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jan 25 08:00:00 IST 2014 | Wed Jan 29 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
2127 | TT_TASK | Rebar fixing for wall and roof | Thu Jan 30 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Fri Dec 20 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
2128 | TT_TASK | Erect external formwork for wall and roof | Thu Feb 20 08:00:00 IST 2014 | Fri Feb 21 18:00:00 IST 2014 | Thu Jan 09 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2129 | TT_TASK | Concreting for wall and roof (200m3) | Sat Feb 22 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2130 | TT_TASK | Curing for wall and roof | Sun Feb 23 08:00:00 IST 2014 | Tue Mar 04 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2131 | TT_TASK | Preparation of construction joint for wall and roof | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Tue Jan 14 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2132 | TT_TASK | Removal external and internal formwork for wall | Tue Feb 25 08:00:00 IST 2014 | Tue Feb 25 18:00:00 IST 2014 | Wed Jan 15 08:00:00 IST 2014 | Wed Jan 15 18:00:00 IST 2014 |  | COMPLETED
2133 | TT_TASK | Removal internal falsework and formwork for roof | Wed Mar 05 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2134 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
2137 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Sep 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
2138 | TT_TASK | Erect external formwork for base slab | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Sep 21 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
2139 | TT_TASK | Rebar fixing for base slab | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
2140 | TT_TASK | Erect internal kicker formwork for base slab | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
2141 | TT_TASK | Staircase construction (+12.0mPD to +14.706mPD) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2142 | TT_TASK | Concreting for base slab (30m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
2143 | TT_TASK | Curing for base slab | Fri Dec 13 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
2144 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
2145 | TT_TASK | Removal of formwork for base slab | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 18:00:00 IDT 2013 |  | COMPLETED
2146 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2147 | TT_TASK | Mass concrete at level +12.0mPD | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 |  | COMPLETED
2148 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2149 | TT_TASK | Removal strut S3 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2150 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 17 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Mon Dec 01 18:00:00 IST 2014 |  | COMPLETED
2152 | TT_TASK | Erect working platform to +21.0mPD | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2153 | TT_TASK | Rebar fixing for wall and roof | Sat Jan 11 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2154 | TT_TASK | Staircase construction (+14.706mPD to +16.956mPD) (20m3) | Fri May 02 08:00:00 IDT 2014 | Wed May 07 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2155 | TT_TASK | Staircase construction (+16.956mPD to +19.206mPD) (20m3) | Thu Jun 05 08:00:00 IDT 2014 | Mon Jun 09 18:00:00 IDT 2014 | Thu Jun 12 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2156 | TT_TASK | Staircase construction (+19.206mPD to +21.456mPD) (20m3) | Tue Jun 10 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Fri Jun 20 18:00:00 IDT 2014 |  | COMPLETED
2157 | TT_TASK | Erect external formwork for wall and roof | Sat Mar 15 08:00:00 IST 2014 | Mon Mar 17 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2158 | TT_TASK | Concreting for wall and roof (31m3) | Tue Feb 04 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2159 | TT_TASK | Curing for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 |  | COMPLETED
2160 | TT_TASK | Preparation of construction joint for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2161 | TT_TASK | Removal external and internal formwork for wall | Thu Feb 06 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2162 | TT_TASK | Removal internal falsework and formwork for roof | Sat Feb 15 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Thu Jan 23 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2164 | TT_TASK | Removal strut S2 @ SN 19 | Wed Apr 02 08:00:00 IDT 2014 | Mon Apr 07 18:00:00 IDT 2014 | Mon Mar 03 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 |  | COMPLETED
2165 | TT_TASK | Erect working platform to +24.0mPD | Tue Apr 08 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 | Fri Mar 07 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 |  | COMPLETED
2166 | TT_TASK | Erect internal formwork below strut S1 | Sat Apr 12 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 | Wed Mar 12 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 |  | COMPLETED
2167 | TT_TASK | Staircase construction (+21.456mPD to +23.706mPD) (20m3) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 |  | COMPLETED
2168 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 | Fri Mar 14 08:00:00 IST 2014 | Tue Apr 01 18:00:00 IDT 2014 |  | COMPLETED
2169 | TT_TASK | Erect external wall & internal wall formwork | Tue May 13 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Wed Apr 02 08:00:00 IDT 2014 | Thu Apr 03 18:00:00 IDT 2014 |  | COMPLETED
2170 | TT_TASK | Concreting (External Wall & Internal Wall) (264m3) | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Fri Apr 04 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2171 | TT_TASK | Curing (External Wall & Internal Wall) | Fri May 16 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2172 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Mon May 19 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Thu Apr 10 18:00:00 IDT 2014 |  | COMPLETED
2173 | TT_TASK | Waterproofing | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 |  | COMPLETED
2174 | TT_TASK | Backfilling | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2176 | TT_TASK | Removal strut S1 @ SN 19 | Thu Jun 19 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2177 | TT_TASK | Erect working platform to +30.406mPD | Tue Jun 24 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2178 | TT_TASK | Erect internal formwork | Sat Jun 28 08:00:00 IDT 2014 | Sat Jun 28 18:00:00 IDT 2014 | Wed Jun 04 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2179 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Mon Jun 30 08:00:00 IDT 2014 | Wed Jul 02 18:00:00 IDT 2014 | Thu Jun 05 08:00:00 IDT 2014 | Fri Jun 06 18:00:00 IDT 2014 |  | COMPLETED
2180 | TT_TASK | Erect external formwork (External Wall & Internal Wall) | Thu Jul 03 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2181 | TT_TASK | Concreting (External Wall & Internal Wall) (128m3) | Fri Jul 04 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2182 | TT_TASK | Curing (External Wall & Internal Wall) | Sat Jul 05 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 18:00:00 IDT 2014 |  | COMPLETED
2183 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Tue Jul 08 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2184 | TT_TASK | Waterproofing | Wed Jul 09 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Thu Jun 19 18:00:00 IDT 2014 |  | COMPLETED
2185 | TT_TASK | Backfilling | Sat Jul 12 08:00:00 IDT 2014 | Wed Jul 16 18:00:00 IDT 2014 | Fri Jun 20 08:00:00 IDT 2014 | Tue Jun 24 18:00:00 IDT 2014 |  | COMPLETED
2186 | TT_TASK | Erect falsework and soffit formwork +30.206mPD | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 | Wed Jun 25 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2187 | TT_TASK | Staircase construction (+21.456mPD to +25.956mPD) (20m3) | Sat Jul 19 08:00:00 IDT 2014 | Wed Jul 23 18:00:00 IDT 2014 | Fri Jun 27 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2188 | TT_TASK | Staircase construction (+25.956mPD to +27.606mPD) (20m3) | Sat Jul 05 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 05 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 |  | COMPLETED
2189 | TT_TASK | Rebar fixing (Beam, Floor Slab and Staircase) | Thu Jul 10 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Thu Jul 10 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2190 | TT_TASK | Concreting (Beam, Floor Slab and Staircase) (31m3) | Fri Jul 11 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2191 | TT_TASK | Curing (Beam, Floor Slab and Staircase) | Wed Sep 03 08:00:00 IDT 2014 | Tue Sep 09 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2193 | TT_TASK | Erect working platform to +33.576mPD | Wed Sep 03 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
2194 | TT_TASK | Erect external formwork (External Wall) | Mon Sep 08 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 | Fri Sep 26 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2195 | TT_TASK | Rebar fixing (External Wall) | Thu Sep 11 08:00:00 IDT 2014 | Fri Sep 12 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2196 | TT_TASK | Erect internal formwork (External Wall) | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 |  | COMPLETED
2197 | TT_TASK | Concreting (External Wall) (49m3) | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 |  | COMPLETED
2198 | TT_TASK | Curing (External Wall) | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 |  | COMPLETED
2199 | TT_TASK | Removal formwork (External Wall) | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
2200 | TT_TASK | Erect falsework and soffit formwork +32.656 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2201 | TT_TASK | Rebar fixing (Beam & Floor Slab) | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 |  | COMPLETED
2202 | TT_TASK | Concreting (Beam & Floor Slab) (31m3) | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 |  | COMPLETED
2203 | TT_TASK | Curing (Beam & Floor Slab) | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2205 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
2206 | TT_TASK | Rebar fixing (Roof Parapet Wall) | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 |  | COMPLETED
2207 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2208 | TT_TASK | Concreting (Roof Parapet Wall) (30m3) | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
2209 | TT_TASK | Curing (Roof Parapet Wall) | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 |  | COMPLETED
2210 | TT_TASK | Removal formwork (Roof Parapet Wall) | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2211 | TT_TASK | Removal of falsework and soffit formwork | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
2213 | TT_TASK | Wet trade work | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 |  | COMPLETED
2214 | TT_TASK | Metal works (Louver, Door, Cat-ladder, Architectural Fins, Handrail, Roof Sliding Hatch and Balustrade, etc) | Thu Nov 27 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Thu Nov 27 08:00:00 IST 2014 | Thu Mar 05 18:00:00 IST 2015 |  | COMPLETED
2215 | TT_TASK | Coat works | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2218 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Nov 29 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Feb 04 18:00:00 IST 2014 |  | COMPLETED
2219 | TT_TASK | Backfilling between D-wall and 0.5m below S1 14,240m3 soil | Thu Feb 06 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 | Wed Feb 05 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 |  | COMPLETED
2220 | TT_TASK | Removal of S1 | Wed Mar 12 08:00:00 IST 2014 | Tue Mar 25 18:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 |  | COMPLETED
2221 | TT_TASK | Backfilling to original ground level 21,390m3 (approx. +25.0mPD) | Sat Mar 01 08:00:00 IST 2014 | Wed Mar 19 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Sat May 03 18:00:00 IDT 2014 |  | COMPLETED
2223 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 |  | COMPLETED
2224 | TT_TASK | Backfilling between D-wall and 0.5m below S1 (2075m3) | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 |  | COMPLETED
2225 | TT_TASK | Removal of S1 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 |  | COMPLETED
2226 | TT_TASK | Backfilling to original ground level 3,900m3 (approx. +25.0mPD) (1353m3) | Sat Mar 01 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
2227 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
2228 | TT_TASK | Backfilling backfilling to +20mPD from SN8 to SN9 (Soil: 7,050m3 @ 500m3/day) | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 |  | COMPLETED
2229 | TT_TASK | Removal of S1 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
2230 | TT_TASK | Construction of mud pit | Sat Jul 06 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
2231 | TT_TASK | Backfilling from +20mPD to ground level from SN8 to SN9 (Soil: 5,000m3 @ 500m3/day) | Tue Aug 06 08:00:00 IDT 2013 | Sat Aug 17 18:00:00 IDT 2013 | Tue Jul 02 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 |  | COMPLETED
2233 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Aug 07 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2234 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) | Fri Aug 14 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2235 | TT_TASK | Placing mass concrete infill between tunnel and D-wall | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 02 18:00:00 IST 2015 | Thu Dec 24 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2236 | TT_TASK | Removal of S2 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 10 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 04 18:00:00 IST 2016 |  | COMPLETED
2237 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2238 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
2239 | TT_TASK | Removal strut S1 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2240 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
2241 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488 m3 of soil) | Mon Jan 25 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Fri Apr 01 18:00:00 IDT 2016 |  | COMPLETED
2243 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) (SN18-19) | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 |  | COMPLETED
2244 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) (SN18-19) | Sat Apr 26 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Sat Apr 26 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
2245 | TT_TASK | Placing mass concrete infill between tunnel and D-wall (SN18-19) | Tue May 20 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri May 16 18:00:00 IDT 2014 |  | COMPLETED
2246 | TT_TASK | Removal of S2 (SN16-18) | Wed Jun 04 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 |  | COMPLETED
2247 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) (SN16-18) | Mon Jun 09 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Tue May 27 18:00:00 IDT 2014 |  | COMPLETED
2248 | TT_TASK | Removal strut S1 (SN16-18) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Wed May 28 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
2249 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488m3 of soil) | Fri Jun 27 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
2251 | TT_TASK | Dismantling temporary bridge deck | Mon Jun 15 08:00:00 IDT 2015 | Tue Jul 21 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2252 | TT_TASK | Reinstatement of Works Area 4.10 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jan 11 18:00:00 IST 2017 | Mon May 02 08:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 |  | COMPLETED
2253 | TT_TASK | Complete all tree planting and reinstate Works Area 4.12C | Tue Nov 01 08:00:00 IST 2016 | Thu Jul 13 18:00:00 IDT 2017 | Sat Oct 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2254 | TT_TASK | Reinstate Works Areas 4.9, 4.9A and 4.12A prior to handover | Mon May 22 08:00:00 IDT 2017 | Sat Sep 02 18:00:00 IDT 2017 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2258 | TT_TASK | Application of power supply, environmental permits and construction substation | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2259 | TT_TASK | Procurement and Confirmation of the order of 2nd tunnel boring machine | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2260 | TT_TASK | TBM design and submission for approval | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2261 | TT_TASK | TBM materials order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
2262 | TT_TASK | TBM equipments order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 |  | COMPLETED
2263 | TT_TASK | TBM Fabrication | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
2264 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 |  | COMPLETED
2265 | TT_TASK | TBM test Run | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2266 | TT_TASK | TBM disassembly and packing for shipping to HK | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 |  | COMPLETED
2267 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
2268 | TT_TASK | Setup TBM facilities | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
2269 | TT_TASK | Fabrication 50% of South Tunnel South Bound Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
2270 | TT_TASK | Fabrication 100% of South Tunnel South Bound Precast Lining | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
2271 | TT_TASK | Fabrication 50% of South Tunnel North Bound Precast Lining | Wed Oct 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 | Wed Oct 03 08:00:00 IST 2012 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
2272 | TT_TASK | Fabrication 100% of South Tunnel North Bound Precast Lining | Mon Aug 26 08:00:00 IDT 2013 | Wed Jan 22 18:00:00 IST 2014 | Wed Feb 27 08:00:00 IST 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
2274 | TT_TASK | Ground treatment at lauching shaft Southbound | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
2275 | TT_TASK | TBM assemble, thrust frame, testing and commissioning | Sat Jun 01 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2276 | TT_TASK | Lowing back-up plant for final drive | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
2277 | TT_TASK | Assemble and set up back-up plant for final drive | Sat Jun 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2278 | TT_TASK | Erection of noise enclosure | Sat Jul 20 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 |  | COMPLETED
2279 | TT_TASK | TBM drive & lining installation CH124+912 to CH125+012 (Initial Drive) | Sat Jul 20 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Mon Mar 11 00:00:00 IST 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
2280 | TT_TASK | TBM drive & lining installation CH125+012 to CH125+338 | Tue Oct 15 08:00:00 IDT 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon May 27 08:00:00 IDT 2013 | Tue May 20 00:00:00 IDT 2014 |  | COMPLETED
2281 | TT_TASK | Dis-assemble TBM | Fri May 23 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 |  | COMPLETED
2282 | TT_TASK | Invert slab and side walkway | Fri Aug 01 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Tue Sep 02 18:00:00 IDT 2014 |  | COMPLETED
2283 | TT_TASK | Installation of cable bracket | Mon Nov 03 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 | Mon Aug 18 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2285 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Sep 01 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 | Sat Aug 09 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2286 | TT_TASK | Ground treatment at lauching shaft Northbound | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 19 18:00:00 IST 2013 | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
2287 | TT_TASK | TBM assemble, testing and commissioning | Wed Jul 02 08:00:00 IDT 2014 | Wed Sep 03 18:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2288 | TT_TASK | Setup back-up plant for final drive | Tue Jun 03 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2289 | TT_TASK | Reinstate of noise enclosure | Fri Oct 10 08:00:00 IDT 2014 | Wed Nov 05 18:00:00 IST 2014 | Tue Oct 28 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
2290 | TT_TASK | TBM drive & lining installation CH124+927 to CH125+027 (Initial Drive) | Fri Oct 10 08:00:00 IDT 2014 | Thu Nov 13 18:00:00 IST 2014 | Thu Oct 30 00:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
2291 | TT_TASK | TBM drive & lining installation CH125+027 to CH125+353 (Final Drive) | Fri Jan 02 08:00:00 IST 2015 | Thu Feb 12 18:00:00 IST 2015 | Mon Dec 08 08:00:00 IST 2014 | Fri Aug 07 00:00:00 IDT 2015 |  | COMPLETED
2292 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Tue Aug 04 08:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
2293 | TT_TASK | Dis-assemble TBM | Tue Aug 04 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
2294 | TT_TASK | Invert slab and side walkway | Wed Sep 09 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
2295 | TT_TASK | Installation of cable bracket | Thu Sep 24 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Aug 31 18:00:00 IDT 2015 |  | COMPLETED
2298 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Partial length) at down track | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 |  | COMPLETED
2299 | TT_TASK | Probe/Grout | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 | Mon Aug 11 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2300 | TT_TASK | Coring of Segment | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 |  | COMPLETED
2301 | TT_TASK | Removal of segment | Tue Sep 02 08:00:00 IDT 2014 | Thu Sep 04 18:00:00 IDT 2014 | Thu Aug 21 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2302 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Sep 05 08:00:00 IDT 2014 | Tue Oct 07 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2303 | TT_TASK | Invert Concrete | Thu Oct 23 08:00:00 IDT 2014 | Sat Nov 01 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2304 | TT_TASK | Wall and Roof concrete | Mon Nov 03 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Mon Oct 13 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
2305 | TT_TASK | Dismantle Temporary frame | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2306 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
2307 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Remaining length ) at down track | Sat May 09 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Thu Apr 16 18:00:00 IDT 2015 |  | COMPLETED
2308 | TT_TASK | Probe/Grout | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
2309 | TT_TASK | Coring of Segment | Fri Oct 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 | Fri Oct 16 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
2310 | TT_TASK | Removal of segment | Wed Oct 07 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
2311 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Oct 10 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Oct 26 08:00:00 IST 2015 | Fri Dec 11 18:00:00 IST 2015 |  | COMPLETED
2312 | TT_TASK | Invert Concrete | Thu Dec 03 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Sat Dec 12 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2313 | TT_TASK | Wall and Roof concrete | Mon Dec 14 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 15 18:00:00 IST 2016 |  | COMPLETED
2314 | TT_TASK | Dismantle Temporary frame | Wed Jan 13 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 |  | COMPLETED
2315 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2318 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 |  | COMPLETED
2319 | TT_TASK | Pre-drill and guide wall | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 |  | COMPLETED
2320 | TT_TASK | D-wall design review | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 |  | COMPLETED
2321 | TT_TASK | D-Wall Construction (1075m3) | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 |  | COMPLETED
2322 | TT_TASK | Shear pin, toe grout and pumping test | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 |  | COMPLETED
2324 | TT_TASK | SI for TBM ground treatment | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2325 | TT_TASK | Design review of TBM ground treatment | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2326 | TT_TASK | Ground treatment for TBM southbound | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
2327 | TT_TASK | Ground treatment for TBM northbound | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2329 | TT_TASK | Capping beam construction | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2330 | TT_TASK | L-Shape wall construction | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
2331 | TT_TASK | Excavate up to +28.5mPD (1488m3) | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 |  | COMPLETED
2332 | TT_TASK | Install Strut S1 +29.0mPD | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 |  | COMPLETED
2333 | TT_TASK | Excavate up to +23.5mPD (2480m3) | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 |  | COMPLETED
2334 | TT_TASK | Install Strut S2 +24.0mPD | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 |  | COMPLETED
2335 | TT_TASK | Excavate up to +19.5mPD (1984m3) | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
2336 | TT_TASK | Install Strut S3 +20.0mPD | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 |  | COMPLETED
2337 | TT_TASK | Excavate up to +15.5mPD (1984m3) | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
2338 | TT_TASK | Install Strut S4 +16.0mPD | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 |  | COMPLETED
2339 | TT_TASK | Excavate up to formation (4117m3) | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
2340 | TT_TASK | Install rock dowel and tie back | Sat Jun 02 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Sat Jun 02 08:00:00 IDT 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2341 | TT_TASK | Temporary handover the shaft to contract 822 | Mon Jun 03 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2343 | TT_TASK | Rock breaking works | Mon Aug 26 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
2344 | TT_TASK | Temporary base Slab for TBM Drive | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
2347 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2348 | TT_TASK | Erect external formwork (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Wed Aug 13 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Tue Aug 19 18:00:00 IDT 2014 |  | COMPLETED
2349 | TT_TASK | Rebar fixing (Base Slab) | Thu Aug 14 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Wed Aug 20 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2350 | TT_TASK | Erect internal kicker formwork (Base Slab) | Tue Aug 19 08:00:00 IDT 2014 | Thu Aug 21 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 |  | COMPLETED
2351 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 22 08:00:00 IDT 2014 | Fri Aug 22 18:00:00 IDT 2014 | Thu Aug 28 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2352 | TT_TASK | Concreting (Base Slab) (245m3) | Sat Aug 23 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014 | Fri Aug 29 18:00:00 IDT 2014 |  | COMPLETED
2353 | TT_TASK | Curing (Base Slab) | Mon Aug 25 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2354 | TT_TASK | Removal of formwork (Base Slab) | Mon Sep 08 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Mon Sep 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2355 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Sep 10 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Tue Sep 02 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 |  | COMPLETED
2356 | TT_TASK | Rebar fixing (Wall and roof) | Thu Sep 18 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Thu Sep 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2357 | TT_TASK | Erect external formwork (Wall) | Thu Sep 25 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2358 | TT_TASK | Clearing and inspection (Wall and roof) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2359 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
2360 | TT_TASK | Curing (Wall and roof) | Sat Oct 11 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
2361 | TT_TASK | Removal formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Thu Oct 16 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Sat Nov 01 18:00:00 IST 2014 |  | COMPLETED
2362 | TT_TASK | Removal formwork (Roof) | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2363 | TT_TASK | Side walkway and cable bracket (72m3) | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
2365 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Nov 07 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Sat Nov 07 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
2366 | TT_TASK | Erect external formwork (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Wed Nov 18 18:00:00 IST 2015 |  | COMPLETED
2367 | TT_TASK | Rebar fixing (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Tue Nov 17 18:00:00 IST 2015 | Thu Nov 19 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 |  | COMPLETED
2368 | TT_TASK | Erect internal kicker formwork (Base Slab) | Wed Nov 18 08:00:00 IST 2015 | Fri Nov 20 18:00:00 IST 2015 | Tue Nov 24 08:00:00 IST 2015 | Thu Nov 26 18:00:00 IST 2015 |  | COMPLETED
2369 | TT_TASK | Clearing and inspection (Base Slab) | Sat Nov 21 08:00:00 IST 2015 | Sat Nov 21 18:00:00 IST 2015 | Fri Nov 27 08:00:00 IST 2015 | Fri Nov 27 18:00:00 IST 2015 |  | COMPLETED
2370 | TT_TASK | Concreting (Base Slab) (245m3) | Mon Nov 23 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Nov 28 08:00:00 IST 2015 | Sat Nov 28 18:00:00 IST 2015 |  | COMPLETED
2371 | TT_TASK | Curing (Base Slab) | Tue Nov 24 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Mon Nov 30 08:00:00 IST 2015 | Thu Dec 03 18:00:00 IST 2015 |  | COMPLETED
2372 | TT_TASK | Removal of formwork (Base Slab) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Fri Dec 04 08:00:00 IST 2015 | Sat Dec 05 18:00:00 IST 2015 |  | COMPLETED
2373 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 09 18:00:00 IST 2015 | Mon Dec 07 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
2374 | TT_TASK | Rebar fixing (Wall and roof) | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2375 | TT_TASK | Erect external formwork (Wall) | Mon Jan 11 08:00:00 IST 2016 | Wed Jan 13 18:00:00 IST 2016 | Thu Jan 07 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2376 | TT_TASK | Clearing and inspection (Wall and roof) | Thu Jan 14 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2377 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Jan 15 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2378 | TT_TASK | Curing (Wall and roof) | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 |  | COMPLETED
2379 | TT_TASK | Removal formwork (Wall) | Tue Jan 19 08:00:00 IST 2016 | Thu Jan 21 18:00:00 IST 2016 | Thu Jan 28 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2380 | TT_TASK | Removal formwork and falsework (Roof) | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Sat Jan 30 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2381 | TT_TASK | Side walkway and cable bracket (72m3) | Wed Jan 06 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Thu Nov 12 08:00:00 IST 2015 | Tue Mar 01 18:00:00 IST 2016 |  | COMPLETED
2382 | TT_TASK | Provision access opening to DC | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2383 | TT_TASK | Erect falsework and soffit formwork (Opening) | Thu Mar 10 08:00:00 IST 2016 | Mon Mar 21 18:00:00 IST 2016 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2384 | TT_TASK | Rebar fixing (Roof) | Tue Mar 22 08:00:00 IST 2016 | Tue Mar 22 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2385 | TT_TASK | Clearing and inspection (Roof) | Wed Mar 23 08:00:00 IST 2016 | Wed Mar 23 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2386 | TT_TASK | Concreting (Roof) (225m3) | Thu Mar 24 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2387 | TT_TASK | Curing (Roof) | Tue Mar 29 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Jan 13 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
2388 | TT_TASK | Removal internal falsework and soffit formwork (Roof) | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
2390 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Thu Mar 17 08:00:00 IST 2016 | Fri Mar 18 18:00:00 IST 2016 | Tue Mar 01 08:00:00 IST 2016 | Wed Mar 02 18:00:00 IST 2016 |  | COMPLETED
2391 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Sat Mar 19 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Thu Mar 03 08:00:00 IST 2016 | Tue Mar 08 18:00:00 IST 2016 |  | COMPLETED
2392 | TT_TASK | Backfilling to +18.25mPD (1229 m3 of soil) | Sat Jul 02 08:00:00 IDT 2016 | Mon Jul 11 18:00:00 IDT 2016 | Mon Jul 25 08:00:00 IDT 2016 | Tue Aug 02 18:00:00 IDT 2016 |  | COMPLETED
2393 | TT_TASK | Laying 500mm mass concrete lateral support | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 |  | COMPLETED
2394 | TT_TASK | Backfilling to 0.5m below S3 (+19.5mPD) (372m3 of soil) | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 |  | COMPLETED
2395 | TT_TASK | Removal strut S3 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 |  | COMPLETED
2396 | TT_TASK | Backfilling to 0.5m below S2 (+23.5mPD) (1984m3 of soil) | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 |  | COMPLETED
2397 | TT_TASK | Removal strut S2 | Wed Aug 24 08:00:00 IDT 2016 | Fri Aug 26 18:00:00 IDT 2016 | Wed Aug 24 08:00:00 IDT 2016 | Thu Sep 01 18:00:00 IDT 2016 |  | COMPLETED
2398 | TT_TASK | Backfilling to 0.5m below S1 (+28.5mPD) (2480m3 of soil) | Mon Sep 05 08:00:00 IDT 2016 | Tue Sep 20 18:00:00 IDT 2016 | Fri Sep 02 08:00:00 IDT 2016 | Fri Sep 09 18:00:00 IDT 2016 |  | COMPLETED
2399 | TT_TASK | Removal strut S1 | Wed Sep 21 08:00:00 IDT 2016 | Thu Sep 22 18:00:00 IDT 2016 | Sat Sep 10 08:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 |  | COMPLETED
2400 | TT_TASK | Backfilling to original ground level (approx. +31.5mPD) (1488m3 of soil) | Fri Sep 23 08:00:00 IDT 2016 | Mon Oct 03 18:00:00 IDT 2016 | Thu Sep 15 08:00:00 IDT 2016 | Mon Sep 19 18:00:00 IDT 2016 |  | COMPLETED
2402 | TT_TASK | Reinstatement of TUT area (Including Hydroseeding) | Mon Oct 03 08:00:00 IDT 2016 | Mon Jun 19 18:00:00 IDT 2017 | Fri Oct 07 08:00:00 IDT 2016 |  | 216.0 | IN_PROGRESS
25 | TT_TASK | Access opening for the up track cut and cover tunnel at Tse Uk Tsuen Shaft | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 10 18:00:00 IST 2016 |  | COMPLETED
27 | TT_TASK | Close out the temporary access opening at Tse Uk Tsuen Shaft | Thu Mar 10 08:00:00 IST 2016 | Tue Apr 05 18:00:00 IDT 2016 | Thu Feb 11 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
307 | TT_TASK | Position crane for TBM retrieval (down track) | Wed Jul 02 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014 | Sat Aug 02 18:00:00 IDT 2014 |  | COMPLETED
308 | TT_TASK | TBM Break-in and Retrieval (down track) | Mon Aug 04 08:00:00 IDT 2014 | Sat Aug 30 18:00:00 IDT 2014 | Mon Aug 04 08:00:00 IDT 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
309 | TT_TASK | Position crane for TBM retrieval (up track) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 |  | COMPLETED
310 | TT_TASK | TBM Break-in and Retrieval (up track) | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
376 | TT_TASK | Supply Engineer with Survey Equipment [PS41.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
377 | TT_TASK | Provide Engineer with suitably qualified full time Survey Assistant - 4 nos. [PS41.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
378 | TT_TASK | Provide Engineer with site transportation as detailed in PS42.1 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 |  | COMPLETED
379 | TT_TASK | Submit details of qualified drivers to be assigned to the Engineer, for review [PS42.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 |  | COMPLETED
380 | TT_TASK | Install, service and maintain 10 container offices for use by the Engineer's Site Staff | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
381 | TT_TASK | Provide services and equipment for the Engineer | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
383 | TT_TASK | Master Programme - Prepare and submit for approval [GS4.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
384 | TT_TASK | Master Programme - Comments , Resubmission and Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
385 | TT_TASK | Time Chainage Programme - Prepare and submit for approval [GS4.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
386 | TT_TASK | Time Chainage Programme - Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
387 | TT_TASK | Implement and Maintain Programme Management System for 1st Audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
388 | TT_TASK | Implement and Maintain Programme Management System for 2nd Audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
389 | TT_TASK | Implement and Maintain Programme Management System for 3rd Audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
391 | TT_TASK | Environmental Management Plan - Prepare and submit for approval [GS5.1.10] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
392 | TT_TASK | Environmental Management Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
393 | TT_TASK | Quality Plan - Prepare and submit for approval [GS9.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
394 | TT_TASK | Quality Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
395 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 1st audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 |  | COMPLETED
396 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 2nd audit | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
397 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 3rd audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
398 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 4th audit | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
399 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 5th audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
400 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 6th audit | Tue Jul 02 08:00:00 IDT 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
401 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 7th audit | Thu Nov 28 08:00:00 IST 2013 | Thu Jun 05 18:00:00 IDT 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Jan 24 18:00:00 IST 2014 |  | COMPLETED
402 | TT_TASK | Health and Safety Plan - Prepare and submit [G3.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
403 | TT_TASK | System Assurance Plan - Prepare and submit for approval [PS Appendix P3.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
404 | TT_TASK | System Assurance Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
405 | TT_TASK | Design for Safety & Constructability Plan - Prepare and submit for approval [PS37.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
406 | TT_TASK | Design for Safety & Constructability Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
408 | TT_TASK | Methods of Construction - Prepare and submit for approval [GS12.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
409 | TT_TASK | Methods of Construction - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
410 | TT_TASK | Contractor's Submission Schedule - Prepare and submit for approval [GS12.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
411 | TT_TASK | Contractor's Submission Schedule - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
412 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) [PS13.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
413 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) - Approval period | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 |  | COMPLETED
414 | TT_TASK | Spoil Disposal Plan [PS17.7.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
415 | TT_TASK | Waste Management Plan [PS22.10.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
416 | TT_TASK | Independent Checking Engineer - Appoint and submit for approval [PS7.1.8] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
417 | TT_TASK | Independent Checking Engineer - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
418 | TT_TASK | Sub-contract Management Plan - Prepare and submit [PS34.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 |  | COMPLETED
419 | TT_TASK | Schedule of Utilities Services Arrangement [GS7.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
420 | TT_TASK | Site Safety Supervision Plan for Site Formation - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
421 | TT_TASK | Site Safety Supervision Plan for Site Formation - Approval period | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
422 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Prepare and Submit | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
423 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
424 | TT_TASK | Site Safety Supervision Plan for ELS - Prepare and Submit | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
425 | TT_TASK | Site Safety Supervision Plan for ELS - Approval Period | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
426 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Prepare and Submit | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
427 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Approval Period | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
428 | TT_TASK | Noise Management Plan [P22.3.9] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
429 | TT_TASK | Air Quality Management Plan [P22.4.3] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
430 | TT_TASK | Detailed Proposal for Water Pollution Control Measures and Proposed Monitoring [PS22.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
431 | TT_TASK | Groundwater Monitoring and Response Plan [PS22.5.2] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
432 | TT_TASK | Vibration Monitoring Plan [PS22.8.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 |  | COMPLETED
433 | TT_TASK | Proposed Outline TTM Scheme - Prepare & submit to the: Engineer for Review / SLG for Approval [PS19.3] | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 |  | COMPLETED
434 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Proposed TTM Scheme [PS19.4] | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 |  | COMPLETED
435 | TT_TASK | Resubmission of Proposed Outline TTM Scheme (if required) | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
436 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Resubmitted Proposed Outline TTM Scheme [PS19.4] | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 |  | COMPLETED
437 | TT_TASK | Notification Period of the Approved TTM Scheme prior to implementation [PS19.4] | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 |  | COMPLETED
440 | TT_TASK | Initial Site Survey (WA3.11) | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 |  | COMPLETED
441 | TT_TASK | Initial Site Survey Report (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 |  | COMPLETED
442 | TT_TASK | Initial Site Survey & Condition Survey (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
443 | TT_TASK | Initial Site Survey Report (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
444 | TT_TASK | Initial Site Survey & Condition Survey (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
445 | TT_TASK | Initial Site Survey Report (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
446 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 4.9 & 4.12A [PS4.2] | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
447 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 5.1 & 5.3 [PS4.2.3] | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 |  | COMPLETED
448 | TT_TASK | Proposal for Site Clearance Works [PS4.4.1] | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 |  | COMPLETED
449 | TT_TASK | Site Clearance / Site Formation Works (including demolition of EBS) | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
450 | TT_TASK | Backfill existing stream courses in Works Area 4.9, 4.10 and 4.11 [PS18.5.1] | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
451 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and submit to EPD for Approval (WA3.3 - Area M, I, L) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
452 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA3.3 - Area M, I, L) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
453 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
454 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
455 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.3 - Area M, I, L) | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
456 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA3.3 - Area M, I, L) | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
457 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA3.3 - Area M, I, L) | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
458 | TT_TASK | Remediation Report - Approval (WA3.3 - Area M, I, L) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
459 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and Submit to EPD for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
460 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
461 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
462 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.1, 3.2, 3.3, 3.3A) | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
463 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.1, 3.2, 3.3, 3.3A) | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 |  | COMPLETED
464 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 |  | COMPLETED
465 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
466 | TT_TASK | Remediation Report - Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
467 | TT_TASK | Conduct remediation for Area Q in accordance with method proposed in the approved Remediation Action Plan [PS22.9.2] | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 |  | COMPLETED
468 | TT_TASK | Remediation Report - Prepare and submit for Approval [PS22.9.2] (Area Q) | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 |  | COMPLETED
469 | TT_TASK | Remediation Report - Approval (Area Q) | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
470 | TT_TASK | Removal of contaminated soil at North Tunnels (Area N,O,P,Q,R,S) | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
471 | TT_TASK | Condition Survey EBS for presence of Asbestos and gather samples | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
472 | TT_TASK | Testing of gathered samples | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 |  | COMPLETED
473 | TT_TASK | Prepare and submit Asbestos Investigation Report (AIR) & Asbestos Abatement Plan (AAP) | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
474 | TT_TASK | Approval period of AIR & AAP | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
475 | TT_TASK | Notification period to Engineer and EPD prior to Asbestos abatement works | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
476 | TT_TASK | Asbestos abatement works | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
477 | TT_TASK | Demolition of EBS | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
478 | TT_TASK | Confirmation of tree survey | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 |  | COMPLETED
480 | TT_TASK | Installation of ground settlement markers | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 |  | COMPLETED
481 | TT_TASK | Settlement monitoring and submit report | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
482 | TT_TASK | Settlement monitoring and submit report | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 |  | COMPLETED
483 | TT_TASK | Settlement monitoring and submit report | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
484 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
485 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Wed Feb 26 18:00:00 IST 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Feb 21 18:00:00 IST 2014 |  | COMPLETED
486 | TT_TASK | Settlement monitoring and submit report | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 |  | COMPLETED
488 | TT_TASK | Permit Applications (incl. License to Search and Excavate Antiquities and Excavation Permit) | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 |  | COMPLETED
489 | TT_TASK | Check for underground utilities | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 |  | COMPLETED
490 | TT_TASK | Field walking and hand augering | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 |  | COMPLETED
491 | TT_TASK | Excavation of trial pits | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 |  | COMPLETED
492 | TT_TASK | Rescue excavation rescue works (if required) | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 |  | COMPLETED
494 | TT_TASK | Erection of Hoarding with Gate (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 |  | COMPLETED
495 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 3.1, 3.2, 3.3 and 3.3A [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
496 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 4.9, 4.10, 4.11, 4.12A~C, and 4.15 [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
497 | TT_TASK | Project Signboard Erection [PS4.6.8] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
498 | TT_TASK | Marine Survey at Barging Point [PS4.3] (before construction of barging facilities) | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 00:00:00 IST 2010 |  | COMPLETED
499 | TT_TASK | Construct barging facilities | Sat Oct 02 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Oct 02 00:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
500 | TT_TASK | Operation Plan for the Barging Facility - Prepare and Submit for Approval [PS17.1.9] | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
501 | TT_TASK | Operation Plan for the Barging Facility - Review and Approval Period | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 |  | COMPLETED
503 | TT_TASK | General and Special Attendance for Designated Contractors | Mon Dec 02 08:00:00 IST 2013 | Mon Aug 31 18:00:00 IDT 2015 | Tue Jul 02 08:00:00 IDT 2013 | Wed Mar 25 18:00:00 IST 2015 |  | COMPLETED
505 | TT_TASK | Prepare and Submit Detailed Interface Specification | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 |  | COMPLETED
506 | TT_TASK | Approval of Detailed Interface Plan | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
507 | TT_TASK | Prepare and Submit Detailed Interface Specification | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 |  | COMPLETED
508 | TT_TASK | Approval of Detailed Interface Plan | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
510 | TT_TASK | Prepare and Submit Draft Operation and Maintenance Manual [PS33.1] | Mon Aug 24 08:00:00 IDT 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jul 28 08:00:00 IDT 2014 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
511 | TT_TASK | Review and approval period of Draft Operation and Maintenance Manual | Wed Aug 10 08:00:00 IDT 2016 | Tue Sep 13 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
512 | TT_TASK | Prepare and Submit Final Operation and Maintenance Manual [PS33.1] | Wed Sep 14 08:00:00 IDT 2016 | Thu Feb 16 18:00:00 IST 2017 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
513 | TT_TASK | Provide Engineer with As-Built Drawing for the Whole of the Works [PS33.2] | Mon Nov 21 08:00:00 IST 2016 | Wed Dec 14 18:00:00 IST 2016 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
514 | TT_TASK | Provide Engineer with Asset Registration Information [PS33.3] | Fri May 19 08:00:00 IDT 2017 | Mon Jun 12 18:00:00 IDT 2017 |  |  |  | NOT_STARTED
517 | TT_TASK | Preliminary Design Programme - Prepare and Submit for Approval [PS7.1.8 - App. Z2.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
518 | TT_TASK | Preliminary Design Programme - Review and Approval Period [PS7.1.8 - App. Z2.2] | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 |  | COMPLETED
519 | TT_TASK | Preliminary Design Programme - Resubmission and Approval (if required) [PS7.1.8 - App. Z2.2] | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 |  | COMPLETED
520 | TT_TASK | Schedule of Designs - Prepare and Submit for Approval [PS7.1.8 - App. Z2.5] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
521 | TT_TASK | Detailed Proposal for Carrying Out the Cross Passage Works [PS11.5.2] | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
524 | TT_TASK | Design TBM and submit full details to the Engineer [PS7.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
525 | TT_TASK | TBM Design - Approval period | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 |  | COMPLETED
526 | TT_TASK | TBM Design - Resubmission and approval period | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 |  | COMPLETED
528 | TT_TASK | AIP Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
529 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 |  | COMPLETED
530 | TT_TASK | DDS Design - Prepare and Submit | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 |  | COMPLETED
531 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 |  | COMPLETED
532 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 |  | COMPLETED
533 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 |  | COMPLETED
534 | TT_TASK | Issue Completed Working Drawings | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
536 | TT_TASK | AIP Design - Prepare and Submit | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 |  | COMPLETED
537 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 |  | COMPLETED
538 | TT_TASK | AIP Design - Response to comments and Resubmit | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
539 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
540 | TT_TASK | DDS Design - Prepare and Submit | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
541 | TT_TASK | DDS Design - Review and Approval Period (by MTRC & related Government Authorities) | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 |  | COMPLETED
542 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 |  | COMPLETED
543 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 |  | COMPLETED
544 | TT_TASK | Issue Completed Working Drawings | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 |  | COMPLETED
546 | TT_TASK | DDS Design - Prepare and Submit | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 |  | COMPLETED
547 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 |  | COMPLETED
548 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 |  | COMPLETED
549 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 |  | COMPLETED
550 | TT_TASK | Issue Completed Working Drawings | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
552 | TT_TASK | AIP Design - Prepare and Submit | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 |  | COMPLETED
553 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
554 | TT_TASK | AIP Design - Response to comments and Resubmit | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 |  | COMPLETED
555 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
556 | TT_TASK | DDS Design - Prepare and Submit | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 |  | COMPLETED
557 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 |  | COMPLETED
558 | TT_TASK | DDS Design - Response to comments and Resubmit | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 |  | COMPLETED
559 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 |  | COMPLETED
560 | TT_TASK | Issue Completed Working Drawings | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 |  | COMPLETED
562 | TT_TASK | Prepare and Submit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 |  | COMPLETED
563 | TT_TASK | Review and Approval Period | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
564 | TT_TASK | Response to comments and Resubmit | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 |  | COMPLETED
565 | TT_TASK | Review and Approval Period (for resubmission) | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 |  | COMPLETED
568 | TT_TASK | DDS Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
569 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 |  | COMPLETED
570 | TT_TASK | DDS Design - Response to comments and Resubmit | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 |  | COMPLETED
571 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 |  | COMPLETED
572 | TT_TASK | Issue Completed Working Drawings | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
574 | TT_TASK | DDS Design - Prepare and Submit | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 |  | COMPLETED
575 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 |  | COMPLETED
576 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 |  | COMPLETED
577 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 |  | COMPLETED
578 | TT_TASK | Issue Completed Working Drawings | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 |  | COMPLETED
580 | TT_TASK | DDS Design - Prepare and Submit | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 |  | COMPLETED
581 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 |  | COMPLETED
582 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 |  | COMPLETED
583 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 |  | COMPLETED
584 | TT_TASK | Issue Completed Working Drawings | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 |  | COMPLETED
586 | TT_TASK | DDS Design - Prepare and Submit | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 |  | COMPLETED
587 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 |  | COMPLETED
588 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 |  | COMPLETED
589 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 |  | COMPLETED
590 | TT_TASK | Issue Completed Working Drawings | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 |  | COMPLETED
592 | TT_TASK | DDS Design - Prepare and Submit | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 |  | COMPLETED
593 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 |  | COMPLETED
594 | TT_TASK | DDS Design - Response to comments and Resubmit | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 |  | COMPLETED
595 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 |  | COMPLETED
596 | TT_TASK | Issue Completed Working Drawings | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
599 | TT_TASK | Formworks / Falsework - Prepare & Submit | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
600 | TT_TASK | Formworks / Falsework - Review & Approval Period (by MTRC) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
601 | TT_TASK | Formworks / Falsework - Response to comments and Resubmit | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 |  | COMPLETED
602 | TT_TASK | Formworks / Falsework - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
605 | TT_TASK | Layout of Site Hoarding - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
606 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (by MTRC) | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
607 | TT_TASK | Layout of Site Hoarding - Response to comments and Resubmit | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
608 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 |  | COMPLETED
610 | TT_TASK | Layout of Engineer's Accommodation - Prepare and Submit | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
611 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (by MTRC) | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 |  | COMPLETED
612 | TT_TASK | Layout of Engineer's Accommodation - Response to comments and Resubmit | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
613 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (for resubmit) (by MTRC & related Government Authorities | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
615 | TT_TASK | TTMS Assessment Report - Prepare and Submit | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 |  | COMPLETED
616 | TT_TASK | TTMS Assessment Report - Review and Approval Period (by MTRC) | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
617 | TT_TASK | TTMS Assessment Report - Response to comments and Resubmit | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 |  | COMPLETED
618 | TT_TASK | TTMS Assessment Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
619 | TT_TASK | Issue Completed Working Drawings | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 |  | COMPLETED
621 | TT_TASK | DIA Report - Prepare and Submit | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 |  | COMPLETED
622 | TT_TASK | DIA Report - Review and Approval Period (by MTRC) | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 |  | COMPLETED
623 | TT_TASK | DIA Report - Response to comments and Resubmit | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 |  | COMPLETED
624 | TT_TASK | DIA Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
625 | TT_TASK | Issue Completed Working Drawings | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 |  | COMPLETED
627 | TT_TASK | AIP Design - Prepare & Submit | Wed Sep 23 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 |  | COMPLETED
628 | TT_TASK | AIP Design - Review & Approval Period (by MTR) | Wed Oct 14 08:00:00 IDT 2015 | Wed Nov 11 18:00:00 IST 2015 | Mon Jun 08 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
629 | TT_TASK | AIP Design - Response to comments and Resubmit | Thu Nov 12 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Mon Jun 15 01:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
630 | TT_TASK | AIP Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jun 22 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
631 | TT_TASK | DDS Design - Prepare & Submit | Wed Jan 13 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Tue Sep 01 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 |  | COMPLETED
632 | TT_TASK | DDS Design - Review & Approval Period (by MTRC) | Fri Feb 26 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 12 18:00:00 IDT 2015 |  | COMPLETED
633 | TT_TASK | DDS Design - Response to comments & Resubmit | Tue Mar 29 08:00:00 IDT 2016 | Fri Apr 01 18:00:00 IDT 2016 | Mon Sep 14 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
634 | TT_TASK | DDS Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Apr 02 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 | Mon Sep 21 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
635 | TT_TASK | Issue Completed Working Drawings | Wed Jan 27 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
637 | TT_TASK | Layout of Barging Point - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
638 | TT_TASK | Layout of Barging Point - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
639 | TT_TASK | Layout of Barging Point - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
640 | TT_TASK | Layout of Barging Point - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
641 | TT_TASK | Loading Ramps - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
642 | TT_TASK | Loading Ramps - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
643 | TT_TASK | Loading Ramps - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
644 | TT_TASK | Loading Ramps - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
645 | TT_TASK | Weighbridge - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
646 | TT_TASK | Weighbridge - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
647 | TT_TASK | Weighbridge - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
648 | TT_TASK | Weighbridge - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
652 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
653 | TT_TASK | Pre-drill and guide wall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
654 | TT_TASK | D-wall construction (1084m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
655 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
656 | TT_TASK | Wang Toi Shan Shan Tsuen Road diversion works | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 |  | COMPLETED
658 | TT_TASK | Excavate up to +10.5mPD (369m3) | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 |  | COMPLETED
659 | TT_TASK | Install Strut S0 +11.0mPD | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 |  | COMPLETED
660 | TT_TASK | Excavate up to +8.0mPD (1525m3) | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 |  | COMPLETED
661 | TT_TASK | Install Strut S1 +8.5mPD | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 |  | COMPLETED
662 | TT_TASK | Excavate up to +4.5mPD (2135m3) | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 |  | COMPLETED
663 | TT_TASK | Install Strut S2 +5.0mPD | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 |  | COMPLETED
664 | TT_TASK | Excavate up to +0.5mPD (2440m3) | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 |  | COMPLETED
665 | TT_TASK | Install Strut S3 +1.0mPD | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 |  | COMPLETED
666 | TT_TASK | Excavate up to -6.5mPD (4340m3) | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 |  | COMPLETED
667 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
668 | TT_TASK | Construction of temporary slab and entrance seal (622m3) | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
672 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 08 18:00:00 IST 2014 | Fri Dec 05 08:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
673 | TT_TASK | Erect external formwork (Base Slab) | Tue Dec 09 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 08 08:00:00 IST 2014 | Tue Dec 09 18:00:00 IST 2014 |  | COMPLETED
674 | TT_TASK | Rebar fixing (Base Slab) | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 18:00:00 IST 2014 | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
675 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Dec 15 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Mon Dec 15 18:00:00 IST 2014 |  | COMPLETED
676 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Dec 17 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Tue Dec 16 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 |  | COMPLETED
677 | TT_TASK | Curing (Base Slab) | Thu Dec 18 08:00:00 IST 2014 | Sat Dec 27 18:00:00 IST 2014 | Wed Dec 17 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
678 | TT_TASK | Removal of formwork (Base Slab) | Fri Dec 19 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 24 18:00:00 IST 2014 |  | COMPLETED
679 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
680 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 | Mon Jun 22 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 |  | COMPLETED
681 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Jun 13 08:00:00 IDT 2015 | Mon Jun 15 18:00:00 IDT 2015 | Thu Jun 25 01:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
682 | TT_TASK | Concreting (Wall & Roof) (444m3) | Tue Jun 16 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
683 | TT_TASK | Curing (Wall & Roof) | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
684 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 |  | COMPLETED
685 | TT_TASK | Removal external formwork (Wall) | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
686 | TT_TASK | Side walkway and cable bracket (360m3) | Sat Jul 18 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Sat Jul 18 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
687 | TT_TASK | Access opening to DC (DC access period) | Tue Oct 06 08:00:00 IDT 2015 | Fri Mar 04 18:00:00 IST 2016 | Tue Oct 06 08:00:00 IDT 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
688 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Sat Dec 12 08:00:00 IST 2015 | Mon Jan 18 18:00:00 IST 2016 | Tue Nov 03 00:00:00 IST 2015 | Mon Nov 30 18:00:00 IST 2015 |  | COMPLETED
690 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 | Tue Apr 12 08:00:00 IDT 2016 | Wed Apr 13 18:00:00 IDT 2016 |  | COMPLETED
691 | TT_TASK | Erect external formwork (Base Slab) | Mon May 23 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Thu Apr 14 08:00:00 IDT 2016 | Fri Apr 15 18:00:00 IDT 2016 |  | COMPLETED
692 | TT_TASK | Rebar fixing (Base Slab) | Wed May 25 08:00:00 IDT 2016 | Fri May 27 18:00:00 IDT 2016 | Sat Apr 16 08:00:00 IDT 2016 | Tue Apr 19 18:00:00 IDT 2016 |  | COMPLETED
693 | TT_TASK | Erect internal kicker formwork (Base Slab) | Sat May 28 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 | Wed Apr 20 08:00:00 IDT 2016 | Thu Apr 21 18:00:00 IDT 2016 |  | COMPLETED
694 | TT_TASK | Concreting (Base Slab) (225m3) | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 | Fri Apr 22 08:00:00 IDT 2016 | Fri Apr 22 18:00:00 IDT 2016 |  | COMPLETED
695 | TT_TASK | Curing (Base Slab) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 08 18:00:00 IDT 2016 | Sat Apr 23 08:00:00 IDT 2016 | Fri Apr 29 18:00:00 IDT 2016 |  | COMPLETED
696 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Sat Apr 30 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
697 | TT_TASK | Removal of formwork (Base Slab) | Tue May 24 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Mon May 09 08:00:00 IDT 2016 | Tue May 10 18:00:00 IDT 2016 |  | COMPLETED
698 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed May 25 08:00:00 IDT 2016 | Sat May 28 18:00:00 IDT 2016 | Wed May 11 08:00:00 IDT 2016 | Mon May 16 18:00:00 IDT 2016 |  | COMPLETED
699 | TT_TASK | Rebar fixing (Wall & Roof) | Mon May 30 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 17 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 |  | COMPLETED
700 | TT_TASK | Erect external formwork (Wall & Roof) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 03 18:00:00 IDT 2016 | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 |  | COMPLETED
701 | TT_TASK | Concreting (Wall & Roof) (444m3) | Sat Jun 04 08:00:00 IDT 2016 | Sat Jun 04 18:00:00 IDT 2016 | Mon May 23 08:00:00 IDT 2016 | Mon May 23 18:00:00 IDT 2016 |  | COMPLETED
702 | TT_TASK | Curing (Wall & Roof) | Mon Jun 06 08:00:00 IDT 2016 | Tue Jun 14 18:00:00 IDT 2016 | Tue May 24 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 |  | COMPLETED
703 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 15 08:00:00 IDT 2016 | Wed Jun 15 18:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 |  | COMPLETED
704 | TT_TASK | Removal external formwork (Wall) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
705 | TT_TASK | Side walkway and cable bracket (102m3) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 |  | COMPLETED
706 | TT_TASK | Access opening to DC (DC access period) | Sat Jun 18 08:00:00 IDT 2016 | Thu Jul 14 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
707 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Fri Jul 15 08:00:00 IDT 2016 | Wed Aug 17 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
709 | TT_TASK | Backfilling between tunnels (2000m3) | Thu Sep 01 08:00:00 IDT 2016 | Sat Sep 17 18:00:00 IDT 2016 | Tue Sep 13 08:00:00 IDT 2016 | Fri Sep 30 18:00:00 IDT 2016 |  | COMPLETED
710 | TT_TASK | Remove Strut S2 | Mon Oct 03 08:00:00 IDT 2016 | Wed Oct 05 18:00:00 IDT 2016 | Mon Oct 03 08:00:00 IDT 2016 | Tue Oct 11 18:00:00 IDT 2016 |  | COMPLETED
711 | TT_TASK | Backfilling up top S1 Soffit | Thu Oct 06 08:00:00 IDT 2016 | Fri Oct 21 18:00:00 IDT 2016 | Fri Oct 28 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
712 | TT_TASK | Remove Strut S1 | Sat Oct 22 08:00:00 IDT 2016 | Mon Oct 24 18:00:00 IDT 2016 | Tue Oct 11 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
713 | TT_TASK | Backfilling up top S0 Soffit | Mon Nov 07 08:00:00 IST 2016 | Sat Nov 12 18:00:00 IST 2016 | Tue Nov 01 08:00:00 IST 2016 | Sat Nov 05 18:00:00 IST 2016 |  | COMPLETED
714 | TT_TASK | Remove Strut S0 | Mon Nov 14 08:00:00 IST 2016 | Tue Nov 15 18:00:00 IST 2016 | Mon Nov 07 08:00:00 IST 2016 | Tue Nov 08 18:00:00 IST 2016 |  | COMPLETED
715 | TT_TASK | Backfilling up to ground level | Wed Nov 16 08:00:00 IST 2016 | Fri Nov 18 18:00:00 IST 2016 | Wed Nov 09 08:00:00 IST 2016 | Fri Nov 11 18:00:00 IST 2016 |  | COMPLETED
719 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
720 | TT_TASK | Pre-drilling and guidewall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
721 | TT_TASK | D-wall construction (1451m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
722 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 |  | COMPLETED
724 | TT_TASK | Excavate from ground level to formation level -5.5mPD (4559m3) | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 |  | COMPLETED
725 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 |  | COMPLETED
726 | TT_TASK | Placing of blinding layer (South Bound) | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 |  | COMPLETED
727 | TT_TASK | Placing of blinding layer (North Bound) | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
729 | TT_TASK | Construction of Bay 2 to Bay 7a (3565m3) | Mon Jun 04 08:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 | Mon Jun 04 18:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 |  | COMPLETED
730 | TT_TASK | Side walkway and cable bracket (Southbound) | Fri Oct 02 08:00:00 IDT 2015 | Fri Nov 06 18:00:00 IST 2015 | Fri Oct 02 08:00:00 IDT 2015 | Sat Oct 31 18:00:00 IST 2015 |  | COMPLETED
731 | TT_TASK | Side walkway and cable bracket (Northbound) | Tue May 03 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 |  | COMPLETED
733 | TT_TASK | Backfilling (1344m3) | Wed Nov 07 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 | Wed Nov 07 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
736 | TT_TASK | Scheme Design, Mobilization, Site set up & Material delivery and Instrumentations | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
737 | TT_TASK | Downstream pipe pile wall construction (45 nos.) and grout curtain (45 nos.) | Mon Nov 12 08:00:00 IST 2012 | Fri Jan 25 18:00:00 IST 2013 | Mon Nov 12 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
738 | TT_TASK | Curtain Grout for cut slope (120 nos.) | Fri Jul 26 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
739 | TT_TASK | Drilling for ground improvement only (if require) | Mon Dec 10 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
740 | TT_TASK | If settlement reach the AAA alarm & action level TAM grouting will apply during excavation | Thu Apr 11 08:00:00 IDT 2013 | Thu May 16 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
741 | TT_TASK | Erection of temporary working platform for Up stream and Installation of Instrumentation System | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
742 | TT_TASK | Upstream pipe pile wall construction adjacent to WTSSTR, (17nos.) | Thu Dec 27 08:00:00 IST 2012 | Mon Jan 28 18:00:00 IST 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
743 | TT_TASK | Upstream pipe pile wall construction at Kam Tin River, 15m depth, 42nos. 1drill rig) | Tue Jan 29 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
744 | TT_TASK | Excavation and soil nail installation | Tue Apr 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
745 | TT_TASK | Excavation for rock and blinding layer | Sat Aug 24 08:00:00 IDT 2013 | Sat Sep 28 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
750 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
751 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
752 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
753 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
754 | TT_TASK | Concreting (164m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
755 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
756 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
757 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
758 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
759 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
760 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
761 | TT_TASK | Concreting (242m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
762 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
763 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
764 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
765 | TT_TASK | Removal internal falsework and formwork for roof | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
766 | TT_TASK | Side walkway and cable bracket (19m3) | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
770 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
771 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
772 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
773 | TT_TASK | Erect internal kicker formwork | Thu Nov 28 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 09 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
774 | TT_TASK | Concreting (121m3) | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
775 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
776 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
777 | TT_TASK | Removal of formwork | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
778 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
779 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
780 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
781 | TT_TASK | Concreting (121m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
782 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
783 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
784 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
785 | TT_TASK | Removal internal falsework and formwork for roof | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
786 | TT_TASK | Side walkway and cable bracket (38m3) | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
788 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
789 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
790 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
791 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
792 | TT_TASK | Concreting (240m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
793 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
794 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
795 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
796 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
797 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
798 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
799 | TT_TASK | Concreting (240m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
800 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
801 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
802 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
803 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
804 | TT_TASK | Side walkway and cable bracket | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
806 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
807 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
808 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
809 | TT_TASK | Concreting (222m3) | Wed Nov 06 08:00:00 IST 2013 | Wed Nov 06 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
810 | TT_TASK | Curing | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
811 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
812 | TT_TASK | Removal of formwork | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
815 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
816 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
817 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
818 | TT_TASK | Erect internal kicker formwork | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
819 | TT_TASK | Concreting (111m3) | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
820 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
821 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
822 | TT_TASK | Removal of formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
823 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
824 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
825 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
826 | TT_TASK | Concreting (220m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
827 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
828 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
829 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
830 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
831 | TT_TASK | Side walkway and cable bracket (38m3) | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 |  | COMPLETED
833 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
834 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
835 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
836 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
837 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
838 | TT_TASK | Curing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
839 | TT_TASK | Preparation of construction joint for base slab | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
840 | TT_TASK | Removal of formwork | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
841 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
842 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
843 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
844 | TT_TASK | Concreting (327m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
845 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
846 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
847 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
848 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
849 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
851 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 20 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
852 | TT_TASK | Rebar fixing | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
853 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 08:00:00 IDT 2013 |  | COMPLETED
854 | TT_TASK | Concreting (225m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
855 | TT_TASK | Curing | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
856 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
857 | TT_TASK | Removal of formwork | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
860 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 27 08:00:00 IST 2013 | Wed Nov 27 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
861 | TT_TASK | Erect external formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
862 | TT_TASK | Rebar fixing | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
863 | TT_TASK | Erect internal kicker formwork | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
864 | TT_TASK | Concreting (222m3) | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
865 | TT_TASK | Curing | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Mon Oct 28 18:00:00 IST 2013 |  | COMPLETED
866 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
867 | TT_TASK | Removal of formwork | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
868 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
869 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
870 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
871 | TT_TASK | Concreting (222m3) | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 |  | COMPLETED
872 | TT_TASK | Curing | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 07 18:00:00 IST 2014 |  | COMPLETED
873 | TT_TASK | Preparation of construction joint for wall and roof | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
874 | TT_TASK | Removal external and internal formwork for wall | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
875 | TT_TASK | Removal internal falsework and formwork for roof | Mon Feb 10 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
876 | TT_TASK | Side walkway and cable bracket (38m3) | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 |  | COMPLETED
878 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
879 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
880 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
881 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
882 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
883 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
884 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
885 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
886 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
887 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
888 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
889 | TT_TASK | Concreting (222m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
890 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
892 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
893 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
894 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
896 | TT_TASK | Placing of waterproof member T-lock & testing | Mon Nov 18 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
897 | TT_TASK | Rebar fixing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Wed Oct 23 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
898 | TT_TASK | Erect external formwork | Fri Nov 22 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
899 | TT_TASK | Concreting (222m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
900 | TT_TASK | Curing | Tue Nov 26 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
901 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
902 | TT_TASK | Removal of formwork | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
905 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
906 | TT_TASK | Erect external formwork | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
907 | TT_TASK | Rebar fixing | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
908 | TT_TASK | Erect internal kicker formwork | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
909 | TT_TASK | Concreting (330m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
910 | TT_TASK | Curing | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
911 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
912 | TT_TASK | Removal of formwork | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
913 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
914 | TT_TASK | Rebar fixing | Wed Nov 20 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
915 | TT_TASK | Erect external formwork | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
916 | TT_TASK | Concreting (330m3) | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
917 | TT_TASK | Curing | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
918 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
919 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
920 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
921 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
923 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
924 | TT_TASK | Erect external formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
925 | TT_TASK | Rebar fixing | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
926 | TT_TASK | Erect internal kicker formwork | Wed Dec 04 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
927 | TT_TASK | Concreting (240m3) | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
928 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
929 | TT_TASK | Preparation of construction joint for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
930 | TT_TASK | Removal of formwork | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
931 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
932 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
933 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
934 | TT_TASK | Concreting (240m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
935 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
936 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
937 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
938 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
939 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
941 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
942 | TT_TASK | Rebar fixing | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
943 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
944 | TT_TASK | Concreting (240m3) | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
945 | TT_TASK | Curing | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
946 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
947 | TT_TASK | Removal of formwork | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
950 | TT_TASK | Placing of waterproof member T-lock & testing | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
951 | TT_TASK | Erect external formwork | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
952 | TT_TASK | Rebar fixing | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
953 | TT_TASK | Erect internal kicker formwork | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
954 | TT_TASK | Concreting (200m3) | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
955 | TT_TASK | Curing | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
956 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
957 | TT_TASK | Removal of formwork | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
958 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 29 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
959 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
960 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
961 | TT_TASK | Concreting (200m3) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
962 | TT_TASK | Curing | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
963 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
964 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 13 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
965 | TT_TASK | Removal internal falsework and formwork for roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
966 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 |  | COMPLETED
968 | TT_TASK | Placing of waterproof member T-lock & testing | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
969 | TT_TASK | Erect external formwork | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
970 | TT_TASK | Rebar fixing | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
971 | TT_TASK | Erect internal kicker formwork | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
972 | TT_TASK | Concreting (220m3) | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
973 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
974 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
975 | TT_TASK | Removal of formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
976 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
977 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
978 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
979 | TT_TASK | Concreting (220m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
980 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
981 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
982 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
983 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
984 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
986 | TT_TASK | Placing of waterproof member T-lock & testing | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
987 | TT_TASK | Rebar fixing | Mon Nov 25 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
988 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
989 | TT_TASK | Concreting (222m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
990 | TT_TASK | Curing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
991 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
992 | TT_TASK | Removal of formwork | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
994 | TT_TASK | Removal of Temporary Nullah | Sat Mar 01 08:00:00 IST 2014 | Sat Jun 21 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
995 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (5218m3) | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 |  | COMPLETED
996 | TT_TASK | Reinstate the permenant Retaining wall of Nullah | Sat Mar 01 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Tue Mar 04 08:00:00 IST 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
997 | TT_TASK | Reinstate Nullah Base of original route | Tue Feb 25 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Tue Feb 25 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
998 | TT_TASK | Reinstate Nullah to original route | Sat Mar 29 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Sat Mar 29 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
999 | TT_TASK | Construction & connect East Box Culvert from Box 6B to KTR | Mon Apr 14 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Mon Feb 10 08:00:00 IST 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
1000 | TT_TASK | Reinstatement of Wang Toi Shan Shan Tsuen Road | Tue Dec 01 08:00:00 IST 2015 | Wed Jul 13 18:00:00 IDT 2016 | Tue Dec 01 08:00:00 IST 2015 | Mon Jul 18 18:00:00 IDT 2016 |  | COMPLETED
1003 | TT_TASK | Pre-drilling at Works Area 4.4 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
1004 | TT_TASK | Site Setup and guide wall | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1005 | TT_TASK | D-wall construction (3104m3) | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 |  | COMPLETED
1006 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
1008 | TT_TASK | Excavate up to +8.0mPD (775m3) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1009 | TT_TASK | Install Strut S1 +8.5mPD | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 |  | COMPLETED
1010 | TT_TASK | Excavate up to +4.5mPD (2713m3) | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 |  | COMPLETED
1011 | TT_TASK | Install Strut S2 +5.0mPD | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
1012 | TT_TASK | Excavate up to +0.5mPD (3100m3) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 |  | COMPLETED
1013 | TT_TASK | Install Strut S3 +1.0mPD | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1014 | TT_TASK | Excavate up to -3.0mPD (2713m3) | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1015 | TT_TASK | Install Strut S4 -2.5mPD | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 |  | COMPLETED
1016 | TT_TASK | Excavate up to -5.5mPD (4952m3) | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1017 | TT_TASK | Placing of blinding layer | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1021 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1022 | TT_TASK | Erect external formwork for base slab | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1023 | TT_TASK | Rebar fixing for base slab | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1024 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 26 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1025 | TT_TASK | Concreting for base slab (350m3) | Thu Jun 27 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1026 | TT_TASK | Curing for base slab | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1027 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1028 | TT_TASK | Removal of formwork for base slab | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1029 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1030 | TT_TASK | Removal strut S4 and S3 | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1032 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1033 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1034 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1035 | TT_TASK | Concreting for wall and roof (489m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1036 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1037 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1038 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1039 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1040 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1043 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1044 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1045 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1046 | TT_TASK | Curing for wall and roof | Sat Jun 22 08:00:00 IDT 2013 | Mon Jul 01 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1047 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1048 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1050 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Tue Dec 17 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1053 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1054 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1055 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1056 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1057 | TT_TASK | Concreting for base slab (350m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1058 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1059 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1060 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1061 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1062 | TT_TASK | Removal strut S4 and S3 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1064 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1065 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1066 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1067 | TT_TASK | Concreting for wall and roof (489m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1068 | TT_TASK | Curing for wall and roof | Wed Jun 12 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1069 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1070 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 14 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1071 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1072 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Feb 13 08:00:00 IST 2014 | Tue Feb 18 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1074 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1075 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1076 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1077 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1078 | TT_TASK | Curing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1079 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1080 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1081 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1082 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 16 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1084 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (2343m3) | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1085 | TT_TASK | Placing 0.5m thk concrete lateral support (+3.96mPD) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1086 | TT_TASK | Removal strut S2 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 23 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1088 | TT_TASK | Construction of Temporary Culvert (open channel) | Tue Jun 25 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1089 | TT_TASK | Temporary box culvert (At Box 6B Area) Saw Cut D-wall | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 |  | COMPLETED
1090 | TT_TASK | Erect 3m high block wall | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 |  | COMPLETED
1091 | TT_TASK | Connection to East Box Culvert (823B portion) | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 |  | COMPLETED
1092 | TT_TASK | Blinding | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
1093 | TT_TASK | Temporary box culvert (Outside Box 6B Area) Sheet piling | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 |  | COMPLETED
1094 | TT_TASK | ELS Works | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
1095 | TT_TASK | Blinding | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
1096 | TT_TASK | Removal of Temporary Culvert and Reinstatement | Fri May 16 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
1098 | TT_TASK | Reinstatement of TOA's | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 |  |  | IN_PROGRESS
1099 | TT_TASK | Hydroseeding works | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 | Wed Nov 30 18:00:00 IST 2016 |  | COMPLETED
1100 | TT_TASK | Tree Planting works | Thu Sep 01 08:00:00 IDT 2016 | Sat Dec 03 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
1101 | TT_TASK | Woodland Shrub Mix | Thu Sep 01 08:00:00 IDT 2016 | Fri Nov 18 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  | 200.0 | IN_PROGRESS
1104 | TT_TASK | Kam Tin River Diversion (Stage 1-3) | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1106 | TT_TASK | Concrete fill up to +8.0mPD near side A mass concrete wall | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 |  | COMPLETED
1107 | TT_TASK | Construction of mass concrete wall to +8.0mPD at side A (4 bay CH A80~A120) | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1108 | TT_TASK | Construction of base slab lining and low flow channel (4 bay A9~A10, B8~B9; LFC CH 80~110) | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1109 | TT_TASK | Construction of mass concrete wall to +8.0mPD of side B (3 bay CH B60~B90) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1110 | TT_TASK | Construction of T-shaped retaining wall (1 Bay CH B50~B60) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1111 | TT_TASK | Soil backfill at side A from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1112 | TT_TASK | Concrete backfill at side B from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1113 | TT_TASK | Removal strut at +8.5mPD near side A | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1114 | TT_TASK | Concrete fill up to +11.0mPD near side A mass concrete wall | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1115 | TT_TASK | Placing concrete block at side A from +8.0mPD to +11.0mpd at side A (4 bay CH A80~A120) | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1116 | TT_TASK | Soil backfill at side A from +8.0mPD to +11.0mPD | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1117 | TT_TASK | Removal strut at +8.5mPD near side B | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1118 | TT_TASK | Placing concrete block at side B from +8.0mPD to +11.0mPD (4 bay CH B60~B90) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1119 | TT_TASK | Concrete backfill at side B from +8.0mPD to +11.0mPD | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1121 | TT_TASK | Placing temporary concrete block to Up stream at CH30 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 |  | COMPLETED
1122 | TT_TASK | Placing temporary concrete block to Up stream at CH160 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1123 | TT_TASK | Excavation from GL to FL +5.0mPD Up stream (Low flow channel CH 30~60) | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1124 | TT_TASK | Excavation from GL to FL +5.0mPD Down stream (Low flow channel CH 130~160) | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1125 | TT_TASK | Construction of T-shaped retaining wall at Up stream of side B (2 Bay CH B30~B50) | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1126 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (3 bay CH B90~B120) | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1127 | TT_TASK | Construction of Up stream base slab lining and low flow channel (6 Bay A1~A4, B3~B4; Low flow channel CH 30~50) | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1128 | TT_TASK | Construction of Down stream base slab lining and low flow channel (5 Bay A14~A16, B14~B15; LFC CH 140~170) | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1129 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Up stream and saw cut D-wall | Fri Jun 14 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1130 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Down stream and saw cut D-wall | Wed Jun 19 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1131 | TT_TASK | Construction of remaining Up stream base slab lining and low flow channel (7 bay A5~A8, B5~B7; LFC CH 50~80) | Thu Jun 27 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1132 | TT_TASK | Construction of remaining Down stream base slab lining and low flow channel (7 bay A11~A13, B10~B13; LFC CH 110~140) | Wed Jul 03 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1134 | TT_TASK | Relocation of temporary concrete block at Up stream for construction of mass concrete wall at side B | Sat Jul 20 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1135 | TT_TASK | Relocation of temporary concrete block at Down stream for construction of mass concrete wall at side B | Tue Jul 23 08:00:00 IDT 2013 | Wed Jul 24 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1136 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Up stream of side B (3 bay CH B0~B30) | Tue Jul 23 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1137 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (4 bay CH B0~B30) | Thu Jul 25 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1141 | TT_TASK | Application of power supply, environmental permits and construction substation | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1142 | TT_TASK | Procurement and Confirmation of the order of 1st tunnel boring machine | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 |  | COMPLETED
1143 | TT_TASK | Prepare on-demand bond or bank guarantee for the procurement of TBM and submit to Engineer for approval | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 |  | COMPLETED
1144 | TT_TASK | TBM design and submission for approval | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
1145 | TT_TASK | TBM materials order and delivery to factory | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 |  | COMPLETED
1146 | TT_TASK | TBM equipments order and delivery to factory | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 |  | COMPLETED
1147 | TT_TASK | TBM Fabrication | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
1148 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 |  | COMPLETED
1149 | TT_TASK | TBM test Run | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 |  | COMPLETED
1150 | TT_TASK | TBM disassembly and packing for shipping to HK | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 |  | COMPLETED
1151 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
1152 | TT_TASK | Ground treatment for TBM lanching shaft | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 |  | COMPLETED
1153 | TT_TASK | Ground treatment for Cross Passage Tunnel | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1154 | TT_TASK | Box7A Setup TBM facilities, install noise enclosure and CNP application | Fri Jun 01 08:00:00 IDT 2012 | Sat Jan 26 18:00:00 IST 2013 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1155 | TT_TASK | Notice to Contract 824 the anticipated dates of break out TBM Shaft | Sat Jun 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1156 | TT_TASK | Fabrication of tunnel segment mould | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
1157 | TT_TASK | Fabrication 50% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1158 | TT_TASK | Fabrication 100% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
1159 | TT_TASK | Fabrication 30% of North Tunnel North Bound (Uptrack) Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1160 | TT_TASK | Fabrication 60% of North Tunnel North Bound (Uptrack) Precast Lining | Thu Oct 18 08:00:00 IST 2012 | Thu Feb 21 18:00:00 IST 2013 | Thu Oct 18 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1161 | TT_TASK | Fabrication 100% of North Tunnel North Bound (Uptrack) Precast Lining | Mon Aug 19 08:00:00 IDT 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Dec 03 08:00:00 IST 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1163 | TT_TASK | Assemble, T&C of TBM | Fri Jun 01 08:00:00 IDT 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Oct 16 00:00:00 IST 2012 |  | COMPLETED
1164 | TT_TASK | TBM drive & lining installation CH123+369 to CH123+283 Initial Drive (86m) | Sat Nov 03 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 | Wed Oct 17 00:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1165 | TT_TASK | Change Plant (Back-up cars) | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1166 | TT_TASK | TBM drive & lining installation CH123+283 to CH123+183 | Thu Jun 27 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1167 | TT_TASK | TBM drive & lining installation CH123+183 to CH123+083 | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1168 | TT_TASK | TBM drive & lining installation CH123+083 to CH122+983 | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1169 | TT_TASK | TBM drive & lining installation CH122+983 to CH122+883 | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1170 | TT_TASK | TBM drive & lining installation CH122+883 to CH122+783 | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Jun 13 08:00:00 IDT 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
1171 | TT_TASK | TBM drive & lining installation CH122+783 to CH122+683 | Sat Nov 02 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1172 | TT_TASK | TBM drive & lining installation CH122+683 to CH122+583 | Tue Dec 03 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Wed Feb 26 18:00:00 IST 2014 |  | COMPLETED
1173 | TT_TASK | TBM drive & lining installation CH122+583 to CH122+491 | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Feb 27 08:00:00 IST 2014 | Sat Aug 16 00:00:00 IDT 2014 |  | COMPLETED
1174 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1175 | TT_TASK | Dis-assemble TBM | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
1176 | TT_TASK | Invert slab, side walkway | Sat Oct 04 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 | Mon Sep 15 08:00:00 IDT 2014 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1177 | TT_TASK | Installation of cable bracket | Tue Dec 30 08:00:00 IST 2014 | Tue Jan 13 18:00:00 IST 2015 | Fri Sep 12 08:00:00 IDT 2014 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
1178 | TT_TASK | Provision of assess open for DC and modify of strut S1 and S2 at north bound | Tue Nov 04 11:12:00 IST 2014 | Thu Dec 04 11:12:00 IST 2014 | Wed Oct 01 08:00:00 IDT 2014 | Sat Oct 18 18:00:00 IDT 2014 |  | COMPLETED
1180 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Oct 06 13:00:00 IDT 2014 | Mon Oct 20 12:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
1181 | TT_TASK | Assemble, T&C of TBM | Mon Nov 03 08:00:00 IST 2014 | Fri Jan 02 18:00:00 IST 2015 | Sat Oct 04 08:00:00 IDT 2014 | Fri Nov 28 18:00:00 IST 2014 |  | COMPLETED
1182 | TT_TASK | Setup back-up plant for final drive | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
1183 | TT_TASK | Reinstate of noise enclosure | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Sat Nov 29 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1184 | TT_TASK | TBM drive & lining installation CH123+384 to CH123+284 (Initial Drive) | Sat Dec 06 08:00:00 IST 2014 | Thu Jan 22 18:00:00 IST 2015 | Tue Dec 02 00:00:00 IST 2014 | Tue Jan 20 18:00:00 IST 2015 |  | COMPLETED
1185 | TT_TASK | TBM drive & lining installation CH123+184 to CH123+084 | Wed Jan 21 08:00:00 IST 2015 | Wed Jan 28 18:00:00 IST 2015 | Wed Jan 21 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 |  | COMPLETED
1186 | TT_TASK | TBM drive & lining installation CH123+084 to CH122+984 | Wed Feb 04 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 | Thu Feb 12 08:00:00 IST 2015 | Thu Feb 26 18:00:00 IST 2015 |  | COMPLETED
1187 | TT_TASK | TBM drive & lining installation CH122+984 to CH122+884 | Thu Feb 12 08:00:00 IST 2015 | Tue Feb 24 18:00:00 IST 2015 | Fri Feb 27 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1188 | TT_TASK | TBM drive & lining installation CH122+884 to CH122+784 | Tue Mar 10 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Wed May 27 18:00:00 IDT 2015 |  | COMPLETED
1189 | TT_TASK | TBM drive & lining installation CH122+784 to CH122+684 | Wed May 06 08:00:00 IDT 2015 | Thu May 14 18:00:00 IDT 2015 | Thu May 28 08:00:00 IDT 2015 | Sat Jul 11 18:00:00 IDT 2015 |  | COMPLETED
1190 | TT_TASK | TBM drive & lining installation CH122+684 to CH122+584 | Fri Jul 03 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
1191 | TT_TASK | TBM drive & lining installation CH122+584 to CH122+506 | Tue Nov 03 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 |  | COMPLETED
1192 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 |  | COMPLETED
1193 | TT_TASK | Dis-assemble TBM | Wed Dec 16 08:00:00 IST 2015 | Fri Jan 22 18:00:00 IST 2016 | Sun Dec 13 08:00:00 IST 2015 | Sun Mar 13 18:00:00 IST 2016 |  | COMPLETED
1194 | TT_TASK | Invert slab, side walkway | Fri Apr 01 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 | Mon Mar 14 08:00:00 IST 2016 | Tue May 24 18:00:00 IDT 2016 |  | COMPLETED
1195 | TT_TASK | Installation of cable bracket | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Mar 15 18:00:00 IST 2016 |  | COMPLETED
1196 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Mon Feb 01 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 22 18:00:00 IST 2016 |  | COMPLETED
1199 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 1 (From Downtrack to Centre of CP) | Thu Apr 10 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Sat Jun 28 18:00:00 IDT 2014 |  | COMPLETED
1200 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Sun Nov 09 18:00:00 IST 2014 |  | COMPLETED
1201 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1202 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 18:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1203 | TT_TASK | Excavation 0-4mts with Shotcrete | Mon Feb 02 08:00:00 IST 2015 | Tue Feb 17 18:00:00 IST 2015 | Mon Feb 23 08:00:00 IST 2015 | Mon Mar 30 18:00:00 IDT 2015 |  | COMPLETED
1204 | TT_TASK | Invert Concrete | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1205 | TT_TASK | Wall and Roof concrete | Thu Apr 16 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 |  | COMPLETED
1206 | TT_TASK | Dismantle Temporary frame | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 |  | COMPLETED
1207 | TT_TASK | Install Door to Cross Passage (By contract 827) | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 |  | COMPLETED
1208 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 2 (From Centre of CP to Uptrack) | Sat Oct 17 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Sep 07 08:00:00 IDT 2015 | Tue Dec 01 18:00:00 IST 2015 |  | COMPLETED
1209 | TT_TASK | Probe/Grout | Thu Jun 25 08:00:00 IDT 2015 | Mon Jul 06 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Fri Apr 10 18:00:00 IDT 2015 |  | COMPLETED
1210 | TT_TASK | Coring of Segment | Tue Jul 07 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Sat Apr 11 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1211 | TT_TASK | Removal of segment | Sat Jul 11 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
1212 | TT_TASK | Excavation 0-4mts with Shotcrete | Wed Jul 15 08:00:00 IDT 2015 | Sat Jul 25 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1213 | TT_TASK | Invert Concrete | Sat Jul 18 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 | Thu May 07 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1214 | TT_TASK | Wall and Roof concrete | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1215 | TT_TASK | Dismantle Temporary frame | Tue Jan 19 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 04 18:00:00 IST 2016 |  | COMPLETED
1216 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Feb 22 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Fri Feb 05 08:00:00 IST 2016 | Sat Feb 06 18:00:00 IST 2016 |  | COMPLETED
1218 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 1 (From Downtrack to Centre of CP) | Tue Mar 11 08:00:00 IST 2014 | Wed Mar 26 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1219 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Wed Nov 12 18:00:00 IST 2014 |  | COMPLETED
1220 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Thu Nov 13 08:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1221 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Tue Nov 18 08:00:00 IST 2014 | Thu Nov 20 18:00:00 IST 2014 |  | COMPLETED
1222 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Sat Nov 22 08:00:00 IST 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1223 | TT_TASK | Invert Concrete | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
1224 | TT_TASK | Wall and Roof concrete | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1225 | TT_TASK | Dismantle Temporary frame | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1226 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1227 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 2 (From Centre of CP to Uptrack) | Thu May 21 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Mar 09 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1228 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Mon May 04 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1229 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
1230 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1231 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 22 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
1232 | TT_TASK | Invert Concrete | Sat Aug 08 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Wed Jul 08 18:00:00 IDT 2015 |  | COMPLETED
1233 | TT_TASK | Wall and Roof concrete | Tue Aug 25 08:00:00 IDT 2015 | Mon Sep 07 18:00:00 IDT 2015 | Thu Jul 09 08:00:00 IDT 2015 | Sat Aug 15 18:00:00 IDT 2015 |  | COMPLETED
1234 | TT_TASK | Dismantle Temporary frame | Tue Sep 22 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 | Mon Aug 17 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 |  | COMPLETED
1235 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1237 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 1 (From Downtrack to Centre of CP) | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Sat May 24 18:00:00 IDT 2014 |  | COMPLETED
1238 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
1239 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1240 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 |  | COMPLETED
1241 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Mon Nov 17 08:00:00 IST 2014 | Sat Nov 29 18:00:00 IST 2014 |  | COMPLETED
1242 | TT_TASK | Invert Concrete | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 |  | COMPLETED
1243 | TT_TASK | Wall and Roof concrete | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 |  | COMPLETED
1244 | TT_TASK | Dismantle Temporary frame | Tue Dec 30 08:00:00 IST 2014 | Wed Jan 07 18:00:00 IST 2015 | Tue Dec 30 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1245 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1246 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 2 (From Centre of CP to Uptrack) | Fri May 08 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 |  | COMPLETED
1247 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
1248 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
1249 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Thu May 07 18:00:00 IDT 2015 |  | COMPLETED
1250 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
1251 | TT_TASK | Invert Concrete | Wed Aug 05 08:00:00 IDT 2015 | Fri Aug 14 18:00:00 IDT 2015 | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
1252 | TT_TASK | Wall and Roof concrete | Tue Sep 15 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Wed Aug 26 18:00:00 IDT 2015 |  | COMPLETED
1253 | TT_TASK | Dismantle Temporary frame | Sat Oct 17 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Oct 08 18:00:00 IDT 2015 |  | COMPLETED
1254 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1258 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 |  | COMPLETED
1259 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1260 | TT_TASK | D-wall construction (1192m3) | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 |  | COMPLETED
1261 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1262 | TT_TASK | Construct capping beam, cobble, etc. (including bay 6 and 5) | Sat Oct 27 08:00:00 IST 2012 | Sat Feb 16 18:00:00 IST 2013 | Sat Oct 27 08:00:00 IST 2012 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1264 | TT_TASK | Excavate up to +22.0mPD (1860m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1265 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 |  | COMPLETED
1266 | TT_TASK | Excavate up to +16.5mPD (3410m3) | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 |  | COMPLETED
1267 | TT_TASK | Install Strut S2 +17.0mPD | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 |  | COMPLETED
1268 | TT_TASK | Excavate up to +11.0mPD (3410m3) | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 |  | COMPLETED
1269 | TT_TASK | Install Strut S3 +11.5mPD | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 |  | COMPLETED
1270 | TT_TASK | Excavate up to +7.0mPD (2480m3) | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 |  | COMPLETED
1271 | TT_TASK | Install Strut S4 +7.5mPD | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1272 | TT_TASK | Excavate up to +3.5mPD (2170m3) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 |  | COMPLETED
1273 | TT_TASK | Install Strut S5 +4.0mPD | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1274 | TT_TASK | Excavate up to formation (2294m3) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1275 | TT_TASK | Construct temp. 500mm thick plain concrete base slab | Thu Oct 18 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 |  | COMPLETED
1276 | TT_TASK | Removal of South Bound strut to +9.50mPD | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1277 | TT_TASK | Removal of North Bound strut to +9.50mPD | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 |  | COMPLETED
1278 | TT_TASK | Construct temp. 500mm thick TBM concrete base slab | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1279 | TT_TASK | Construction entrance seal for TBM at South Bound | Mon Nov 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1280 | TT_TASK | Construction entrance seal for TBM at North Bound | Sat Jul 20 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1281 | TT_TASK | Saw cut South Bound diaphragm wall | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1282 | TT_TASK | Saw cut North Bound diaphragm wall | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1286 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 05 18:00:00 IDT 2014 | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 |  | COMPLETED
1287 | TT_TASK | Erect external formwork (Base Slab) | Sat Sep 06 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 21 18:00:00 IDT 2014 |  | COMPLETED
1288 | TT_TASK | Rebar fixing (Base Slab) | Wed Sep 10 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Tue Jul 22 08:00:00 IDT 2014 | Sat Jul 26 18:00:00 IDT 2014 |  | COMPLETED
1289 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Sep 15 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Sun Jul 27 08:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1290 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Thu Aug 14 18:00:00 IDT 2014 |  | COMPLETED
1291 | TT_TASK | Concreting (Base Slab) (225m3) | Sat Aug 09 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Fri Aug 15 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
1292 | TT_TASK | Curing (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
1293 | TT_TASK | Removal of formwork (Base Slab) | Tue Aug 12 08:00:00 IDT 2014 | Tue Aug 12 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1294 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed Aug 13 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Mon Sep 15 18:00:00 IDT 2014 |  | COMPLETED
1295 | TT_TASK | Rebar fixing (Wall & Roof) | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 |  | COMPLETED
1296 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 |  | COMPLETED
1297 | TT_TASK | Clearing and inspection (Wall & Roof) | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
1298 | TT_TASK | Concreting (Wall & Roof) (450m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
1299 | TT_TASK | Curing (Wall & Roof) | Sat Oct 11 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
1300 | TT_TASK | Removal external formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1301 | TT_TASK | Removal internal falsework (Wall & Roof) | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 |  | COMPLETED
1302 | TT_TASK | Side walkway and cable bracket (102m3) | Sat Oct 18 08:00:00 IDT 2014 | Wed Oct 29 18:00:00 IST 2014 | Mon Sep 01 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1304 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Wed Nov 11 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Oct 19 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1305 | TT_TASK | Erect external formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 |  | COMPLETED
1306 | TT_TASK | Rebar fixing (Base Slab) | Mon Nov 16 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Tue Oct 27 08:00:00 IST 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1307 | TT_TASK | Erect internal kicker formwork (Base Slab) | Fri Nov 20 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Oct 31 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 |  | COMPLETED
1308 | TT_TASK | Clearing and inspection (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
1309 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1310 | TT_TASK | Curing (Base Slab) | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 |  | COMPLETED
1311 | TT_TASK | Removal of formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 |  | COMPLETED
1312 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
1313 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Dec 09 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
1314 | TT_TASK | Erect external formwork (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Thu Jan 07 18:00:00 IST 2016 |  | COMPLETED
1315 | TT_TASK | Clearing and inspection (Wall & Roof) | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Fri Jan 08 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
1316 | TT_TASK | Concreting (Wall & Roof) (450m3) | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
1317 | TT_TASK | Curing (Wall & Roof) | Tue Jan 12 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
1318 | TT_TASK | Removal external formwork (Wall ) | Thu Jan 14 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
1319 | TT_TASK | Removal internal falsework, formwork and reproping (Wall & Roof) | Thu Jan 28 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 |  | COMPLETED
1320 | TT_TASK | Side walkway and cable bracket (102m3) | Wed Dec 23 08:00:00 IST 2015 | Wed Jan 06 18:00:00 IST 2016 | Wed Nov 11 08:00:00 IST 2015 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
1322 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 |  | COMPLETED
1323 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 |  | COMPLETED
1324 | TT_TASK | Backfilling to 0.5m below S3 (+11.0mPD) (3486m3) | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 |  | COMPLETED
1325 | TT_TASK | Removal strut S3 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
1326 | TT_TASK | Backfilling to 0.5m below S2 (+16.5mPD) (3410m3) | Wed Mar 16 08:00:00 IST 2016 | Fri Apr 08 18:00:00 IDT 2016 | Wed Mar 16 08:00:00 IST 2016 | Tue Apr 12 18:00:00 IDT 2016 |  | COMPLETED
1327 | TT_TASK | Removal strut S2 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 |  | COMPLETED
1328 | TT_TASK | Backfilling to 0.5m below S1 (+22.0mPD) (3410m3) | Fri Apr 15 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 | Fri Apr 15 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
1329 | TT_TASK | Removal strut S1 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 |  | COMPLETED
1330 | TT_TASK | Backfilling to original ground level (approx. +25.0mPD) (1860m3) | Thu May 05 08:00:00 IDT 2016 | Tue May 17 18:00:00 IDT 2016 | Thu May 05 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
1333 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1334 | TT_TASK | D-wall construction (2844m3) | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1335 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1337 | TT_TASK | Excavate up to +22.0mPD (3720m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1338 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 |  | COMPLETED
1339 | TT_TASK | Excavate up to +16.5mPD (4880m3) | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 |  | COMPLETED
1340 | TT_TASK | Install Strut S2 +17.0mPD | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 |  | COMPLETED
1341 | TT_TASK | Excavate up to +11.0mPD (6820m3) | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
1342 | TT_TASK | Install Strut S3 +11.5mPD | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 |  | COMPLETED
1343 | TT_TASK | Excavate up to +7.0mPD (4960m3) | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 |  | COMPLETED
1344 | TT_TASK | Install Strut S4 +7.5mPD | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1345 | TT_TASK | Excavate up to +3.5mPD (4340m3) | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1346 | TT_TASK | Install Strut S5 +4.0mPD | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 |  | COMPLETED
1347 | TT_TASK | Excavate up to formation (4960m3) | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 |  | COMPLETED
1348 | TT_TASK | Construct temp. 500mm thick plain concrete base slab at Bay 5 & 6 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1349 | TT_TASK | Excavation to formation and place blinding Bay 4a | Thu Oct 18 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1350 | TT_TASK | Excavation to formation and place blinding Bay 4b | Fri Jun 21 08:00:00 IDT 2013 | Fri Jul 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1351 | TT_TASK | Excavation to formation and place blinding Bay3 | Sat Jul 13 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1352 | TT_TASK | Excavation to formation and place blinding Bay2 to Bay1 | Wed Jul 24 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1356 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 |  | COMPLETED
1357 | TT_TASK | Erect external formwork for base slab | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 |  | COMPLETED
1358 | TT_TASK | Rebar fixing for base slab | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1359 | TT_TASK | Erect internal kicker formwork for base slab | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1360 | TT_TASK | Concreting for base slab (363m3) | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1361 | TT_TASK | Curing for base slab | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1362 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1363 | TT_TASK | Removal of formwork for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1364 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1365 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 27 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1366 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1367 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1368 | TT_TASK | Curing for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1369 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1370 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 10 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1371 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 19 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jan 24 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1372 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 08 08:00:00 IST 2015 | Tue Jan 13 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1374 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 |  | COMPLETED
1375 | TT_TASK | Erect external formwork for base slab | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1376 | TT_TASK | Rebar fixing for base slab | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1377 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 |  | COMPLETED
1378 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1379 | TT_TASK | Curing for base slab | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1380 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1381 | TT_TASK | Removal of formwork for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1382 | TT_TASK | Rebar fixing for central slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1383 | TT_TASK | Erect external formwork for central slab | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1384 | TT_TASK | Concreting for central slab (450m3) | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1385 | TT_TASK | Curing for central slab | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1386 | TT_TASK | Preparation of construction joint for central slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1387 | TT_TASK | Removal of formwork for central slab | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1388 | TT_TASK | Removal strut S5 and S4 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1389 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1390 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1391 | TT_TASK | Erect external formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1392 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1393 | TT_TASK | Curing for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1394 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1395 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 08 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1396 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1397 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Nov 19 08:00:00 IST 2015 | Tue Nov 24 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 |  | COMPLETED
1400 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1401 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1402 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1403 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1404 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1405 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1406 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1407 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1408 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1409 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1410 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 10 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1411 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1412 | TT_TASK | Curing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1413 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1414 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1415 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1416 | TT_TASK | Side walkway and cable bracket | Fri Jan 02 08:00:00 IST 2015 | Wed Jan 07 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1418 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1419 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1420 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1421 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1422 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1423 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1424 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1425 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1426 | TT_TASK | Rebar fixing for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1427 | TT_TASK | Erect external formwork for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1428 | TT_TASK | Concreting for central slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1429 | TT_TASK | Curing for central slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1430 | TT_TASK | Preparation of construction joint for central slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1431 | TT_TASK | Removal of formwork for central slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 21 18:00:00 IST 2012 |  | COMPLETED
1432 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1433 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1434 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1435 | TT_TASK | Erect external formwork for wall | Mon Jul 15 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1436 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1437 | TT_TASK | Curing for wall and roof | Sun Jul 21 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1438 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1439 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 22 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1440 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 31 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1441 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Sep 16 08:00:00 IDT 2015 | Mon Sep 21 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1443 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1444 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1445 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1446 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1447 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1448 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1449 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1450 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1451 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1452 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1453 | TT_TASK | Erect external formwork for wall | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1454 | TT_TASK | Concreting for wall and roof (444m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1455 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1456 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1457 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Sat Feb 09 18:00:00 IST 2013 |  | COMPLETED
1458 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Nov 09 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Tue Oct 06 08:00:00 IDT 2015 | Sat Oct 10 18:00:00 IDT 2015 |  | COMPLETED
1461 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1462 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1463 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1464 | TT_TASK | Erect internal kicker formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1465 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1466 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1467 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1468 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1469 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1470 | TT_TASK | Curing | Wed Jun 12 08:00:00 IDT 2013 | Wed Jun 12 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1471 | TT_TASK | Removal strut S5 and S4 | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1473 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1474 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1475 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1476 | TT_TASK | Concreting for wall and roof (450m3) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1477 | TT_TASK | Curing for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1478 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1479 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1480 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 29 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1481 | TT_TASK | Side walkway and cable bracket | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1483 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1484 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1485 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1486 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1487 | TT_TASK | Curing for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1488 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1489 | TT_TASK | Removal external wall formwork for wall | Wed Jun 26 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1490 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1491 | TT_TASK | Side walkway and cable bracket | Fri Sep 04 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
1494 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1495 | TT_TASK | Erect external formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1496 | TT_TASK | Rebar fixing for base slab | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1497 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1498 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 |  | COMPLETED
1499 | TT_TASK | Curing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1500 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1501 | TT_TASK | Removal of formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1502 | TT_TASK | Shear beam | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1503 | TT_TASK | Curing | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1504 | TT_TASK | Removal strut S5 and S4 | Wed Jun 19 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1506 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 24 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1507 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1508 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1509 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1510 | TT_TASK | Curing for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1511 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1512 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1513 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1514 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
1516 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1517 | TT_TASK | Rebar fixing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1518 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1519 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1520 | TT_TASK | Curing for wall and roof | Sun Jun 23 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1521 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1522 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 25 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1523 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 03 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1524 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Aug 29 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1527 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1528 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Sat Dec 22 18:00:00 IST 2012 |  | COMPLETED
1529 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1530 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1531 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1532 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1533 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1534 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Fri Jan 11 18:00:00 IST 2013 |  | COMPLETED
1535 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Jan 12 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1536 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1537 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1539 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1540 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1541 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1542 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1543 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1544 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1545 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1546 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1547 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 |  | COMPLETED
1549 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1550 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Mon Feb 25 18:00:00 IST 2013 |  | COMPLETED
1551 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1552 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1553 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1554 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1555 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1556 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1557 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Aug 24 08:00:00 IDT 2015 | Fri Aug 28 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1560 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1561 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1562 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1563 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1564 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1565 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1566 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1567 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1568 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1569 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1570 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1572 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1573 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1574 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1575 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1576 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1577 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1578 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1579 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1580 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
1582 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1583 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1584 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1585 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1586 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1587 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1588 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1589 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1590 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Aug 18 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1593 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1594 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1595 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1596 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1597 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1598 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1599 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1600 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1601 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1602 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1603 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1605 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 31 18:00:00 IDT 2013 |  | COMPLETED
1606 | TT_TASK | Rebar fixing for wall and roof | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 |  | COMPLETED
1607 | TT_TASK | Erect external formwork for wall and roof | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 | Fri Sep 06 08:00:00 IDT 2013 | Thu Sep 12 18:00:00 IDT 2013 |  | COMPLETED
1608 | TT_TASK | Concreting for wall and roof (450m3) | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 |  | COMPLETED
1609 | TT_TASK | Curing for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1610 | TT_TASK | Preparation of construction joint for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1611 | TT_TASK | Removal external and internal formwork for wall | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Wed Sep 25 18:00:00 IDT 2013 |  | COMPLETED
1612 | TT_TASK | Removal internal falsework and formwork for roof | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1613 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 08 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1615 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 20 18:00:00 IST 2013 |  | COMPLETED
1616 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1617 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1618 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1619 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1620 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1621 | TT_TASK | Removal external wall formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1622 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1623 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Aug 12 08:00:00 IDT 2015 | Mon Aug 17 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1626 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1627 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1628 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Feb 14 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1629 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1630 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Mon Feb 18 18:00:00 IST 2013 |  | COMPLETED
1631 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1632 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1633 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1634 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1635 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1636 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1638 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jul 12 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1639 | TT_TASK | Rebar fixing for wall and roof | Wed Jul 17 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1640 | TT_TASK | Erect external formwork for wall and roof | Wed Aug 14 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1641 | TT_TASK | Concreting for wall and roof (450m3) | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1642 | TT_TASK | Curing for wall and roof | Sun Aug 11 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1643 | TT_TASK | Preparation of construction joint for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1644 | TT_TASK | Removal external and internal formwork for wall | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1645 | TT_TASK | Removal internal falsework and formwork for roof | Wed Aug 21 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1646 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 03 08:00:00 IST 2014 | Fri Mar 07 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1648 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1649 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1650 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Apr 09 08:00:00 IDT 2013 | Thu Apr 11 18:00:00 IDT 2013 |  | COMPLETED
1651 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1652 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1653 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1654 | TT_TASK | Removal external wall formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1655 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
1656 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Aug 06 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Mon Jul 27 08:00:00 IDT 2015 | Fri Jul 31 18:00:00 IDT 2015 |  | COMPLETED
1658 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Sep 12 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1659 | TT_TASK | Rebar fixing for roof | Tue Sep 17 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1660 | TT_TASK | Erect external formwork for roof | Thu Sep 19 08:00:00 IDT 2013 | Thu Sep 19 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1661 | TT_TASK | Concreting for roof (444m3) | Sat Sep 21 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1662 | TT_TASK | Curing for roof | Sun Sep 22 08:00:00 IDT 2013 | Tue Oct 01 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1663 | TT_TASK | Preparation of construction joint for roof | Mon Sep 23 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1664 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1665 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1668 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1669 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1670 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1671 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1672 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1673 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1674 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1675 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1676 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1677 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1678 | TT_TASK | Removal strut S5 and S4 | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1680 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Thu Apr 25 18:00:00 IDT 2013 |  | COMPLETED
1681 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri May 03 08:00:00 IDT 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
1682 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Thu May 16 08:00:00 IDT 2013 | Thu May 23 18:00:00 IDT 2013 |  | COMPLETED
1683 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1684 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1685 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1686 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Wed May 29 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1687 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1688 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 19 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1690 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Fri Apr 19 18:00:00 IDT 2013 |  | COMPLETED
1691 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1692 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Apr 25 08:00:00 IDT 2013 | Sat Apr 27 18:00:00 IDT 2013 |  | COMPLETED
1693 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1694 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1695 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1696 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1697 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1698 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 02 08:00:00 IDT 2015 | Sat Apr 11 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Feb 27 18:00:00 IST 2015 |  | COMPLETED
1700 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1701 | TT_TASK | Rebar fixing for roof | Tue Aug 06 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1702 | TT_TASK | Erect external formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1703 | TT_TASK | Concreting for roof (444m3) | Fri Aug 09 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 |  | COMPLETED
1704 | TT_TASK | Curing for roof | Thu Aug 01 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1705 | TT_TASK | Preparation of construction joint for roof | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 |  | COMPLETED
1706 | TT_TASK | Removal internal falsework and formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1707 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 09 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1710 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Wed Feb 20 18:00:00 IST 2013 |  | COMPLETED
1711 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1712 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1713 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1714 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1715 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1716 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1717 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1718 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1719 | TT_TASK | Curing | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1720 | TT_TASK | Removal strut S5 and S4 | Mon Jun 24 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1722 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1723 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1724 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Wed Jul 10 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1725 | TT_TASK | Concreting for wall and roof (450m3) | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1726 | TT_TASK | Curing for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1727 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1728 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 |  | COMPLETED
1729 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 |  | COMPLETED
1730 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1732 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1733 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1734 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1735 | TT_TASK | Concreting for wall and roof (450m3) | Tue Sep 03 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1736 | TT_TASK | Curing for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1737 | TT_TASK | Preparation of construction joint for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 |  | COMPLETED
1738 | TT_TASK | Removal external and internal formwork for wall | Thu Sep 05 08:00:00 IDT 2013 | Fri Sep 06 18:00:00 IDT 2013 | Thu Aug 22 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1739 | TT_TASK | Removal internal falsework and formwork for roof | Sat Sep 14 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 |  | COMPLETED
1740 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 05 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1742 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1743 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1744 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1745 | TT_TASK | Concreting for roof (363m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1746 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Sun Oct 20 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1747 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1748 | TT_TASK | Removal internal falsework and formwork for roof | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1749 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Dec 24 13:00:00 IST 2013 | Thu Jan 02 12:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1752 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1753 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1754 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1755 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Apr 12 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1756 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1757 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1758 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1759 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1760 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1761 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1762 | TT_TASK | Removal strut S5 and S4 | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1764 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Aug 05 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1765 | TT_TASK | Rebar fixing for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1766 | TT_TASK | Erect external formwork for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1767 | TT_TASK | Concreting for wall and roof (450m3) | Thu Aug 15 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1768 | TT_TASK | Curing for wall and roof | Fri Aug 16 08:00:00 IDT 2013 | Sun Aug 25 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1769 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1770 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1771 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 |  | COMPLETED
1772 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Feb 04 08:00:00 IST 2014 | Sat Feb 08 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1774 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Aug 07 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1775 | TT_TASK | Rebar fixing for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1776 | TT_TASK | Erect external formwork for wall and roof | Thu Aug 15 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1777 | TT_TASK | Concreting for wall and roof (450m3) | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1778 | TT_TASK | Curing for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1779 | TT_TASK | Preparation of construction joint for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 |  | COMPLETED
1780 | TT_TASK | Removal external and internal formwork for wall | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Wed Aug 21 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 |  | COMPLETED
1781 | TT_TASK | Removal internal falsework and formwork for roof | Mon Sep 16 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1782 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Nov 19 08:00:00 IST 2014 | Mon Nov 24 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1784 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1785 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1786 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1787 | TT_TASK | Concreting for roof (450m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1788 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1789 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1790 | TT_TASK | Removal internal falsework and formwork for roof | Fri Oct 18 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1791 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 13 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1794 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1795 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1796 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1797 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1798 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 28 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1799 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1800 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1801 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1802 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1803 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1804 | TT_TASK | Removal strut S5 and S4 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1806 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1807 | TT_TASK | Rebar fixing for wall and roof | Sat Jul 20 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1808 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1809 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1810 | TT_TASK | Curing for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1811 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1812 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 29 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1813 | TT_TASK | Removal internal falsework and formwork for roof | Tue Aug 06 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1814 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 18:00:00 IST 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1816 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1817 | TT_TASK | Rebar fixing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1818 | TT_TASK | Erect external formwork for wall and roof | Fri Jul 19 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1819 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1820 | TT_TASK | Curing for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Thu Mar 28 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1821 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Mar 29 08:00:00 IDT 2013 | Fri Mar 29 18:00:00 IDT 2013 |  | COMPLETED
1822 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Sat Mar 30 08:00:00 IDT 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1823 | TT_TASK | Removal internal falsework and formwork for roof | Fri Aug 02 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Mon Apr 01 18:00:00 IDT 2013 |  | COMPLETED
1824 | TT_TASK | Side walkway and cable bracket | Thu Nov 13 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1826 | TT_TASK | Erect internal formwork & Falsework for roof | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1827 | TT_TASK | Rebar fixing for roof | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 |  | COMPLETED
1828 | TT_TASK | Erect shutter formwork for roof | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 09 18:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1829 | TT_TASK | Concreting for roof (450m3) | Tue Sep 10 08:00:00 IDT 2013 | Tue Sep 10 18:00:00 IDT 2013 | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 |  | COMPLETED
1830 | TT_TASK | Curing for roof | Wed Sep 11 08:00:00 IDT 2013 | Fri Sep 20 18:00:00 IDT 2013 | Tue Jul 23 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 |  | COMPLETED
1831 | TT_TASK | Preparation of construction joint for roof | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 11 18:00:00 IDT 2013 | Sat Aug 03 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1832 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 26 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 |  | COMPLETED
1833 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 06 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Aug 13 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1835 | TT_TASK | Water proofing and soil backfilling to 0.5m below top of Tunnel Bay 3 to Bay 1 | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1836 | TT_TASK | Mass infill between D-wall and tunnel wall | Fri Oct 11 08:00:00 IDT 2013 | Wed Oct 16 18:00:00 IDT 2013 | Fri Sep 20 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1837 | TT_TASK | Removal S3 and S2 | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
1838 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 4 | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Sat May 18 18:00:00 IDT 2013 |  | COMPLETED
1839 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 5 and remove S3 & S2 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1840 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 6 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1843 | TT_TASK | Pre-drilling and guidewall | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1844 | TT_TASK | D-wall design review | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1845 | TT_TASK | D-wall construction (4741m3) | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 |  | COMPLETED
1846 | TT_TASK | Shear pin and pumping test | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 15 18:00:00 IST 2012 | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1848 | TT_TASK | ELS works to formation level from SN16 to SN19 (soil: 8,700m3 @350m3/day, Install S1 to S3 strut 5 days/layer) | Wed Sep 25 08:00:00 IDT 2013 | Wed Nov 13 18:00:00 IST 2013 | Wed May 08 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1849 | TT_TASK | Design temporary bridge and approval | Mon Sep 01 08:00:00 IDT 2014 | Wed Nov 12 18:00:00 IST 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1850 | TT_TASK | Application of tree transplant | Sat Jun 01 08:00:00 IDT 2013 | Wed Oct 23 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1851 | TT_TASK | Tree transplant | Tue Oct 14 08:00:00 IDT 2014 | Mon Nov 10 18:00:00 IST 2014 | Tue Sep 02 08:00:00 IDT 2014 | Tue Sep 30 18:00:00 IDT 2014 |  | COMPLETED
1852 | TT_TASK | Erection temporary bridge deck | Fri Oct 03 08:00:00 IDT 2014 | Fri Dec 05 18:00:00 IST 2014 | Fri Oct 03 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1853 | TT_TASK | ELS works to formation level from SN10 to SN15 (soil: 9,455m3 @330m3/day, install S1 to S3 strut 5 days/layer) | Mon Nov 24 08:00:00 IST 2014 | Sat Jan 17 18:00:00 IST 2015 | Mon Nov 24 08:00:00 IST 2014 | Tue Jun 23 18:00:00 IDT 2015 |  | COMPLETED
1856 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
1857 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1858 | TT_TASK | Erect external formwork for wall and roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1859 | TT_TASK | Concreting for wall and roof (215m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
1860 | TT_TASK | Curing for wall and roof | Sun Dec 08 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
1861 | TT_TASK | Preparation of construction joint for wall and roof | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1862 | TT_TASK | Removal external and internal formwork for wall | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1863 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1864 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 03 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 | Mon Mar 24 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
1866 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 14 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1867 | TT_TASK | Rebar fixing for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1868 | TT_TASK | Erect external formwork for wall and roof | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1869 | TT_TASK | Concreting for wall and roof (215m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1870 | TT_TASK | Curing for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Sun Dec 29 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1871 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
1872 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 17 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
1873 | TT_TASK | Removal internal falsework and formwork for roof | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1874 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 |  | COMPLETED
1876 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 28 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Nov 28 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1877 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1878 | TT_TASK | Erect external formwork for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1879 | TT_TASK | Concreting for wall and roof (215m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1880 | TT_TASK | Curing for wall and roof | Wed Jan 01 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
1881 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
1882 | TT_TASK | Removal external and internal formwork for wall | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 |  | COMPLETED
1883 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
1884 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 |  | COMPLETED
1886 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1887 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 14 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1888 | TT_TASK | Erect external formwork for wall and roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1889 | TT_TASK | Concreting for wall and roof (215m3) | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1890 | TT_TASK | Curing for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1892 | TT_TASK | Removal external and internal formwork for wall | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1893 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1894 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 |  | COMPLETED
1896 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 08:00:00 IST 2013 |  | COMPLETED
1897 | TT_TASK | Rebar fixing for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1898 | TT_TASK | Erect external formwork for wall and roof | Fri Jan 03 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1899 | TT_TASK | Concreting for wall and roof (215m3) | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1900 | TT_TASK | Curing for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 16 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1901 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Tue Jan 07 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1902 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1903 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1904 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 |  | COMPLETED
1906 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1907 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1908 | TT_TASK | Erect external formwork for wall and roof | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1909 | TT_TASK | Concreting for wall and roof (215m3) | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1910 | TT_TASK | Curing for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1911 | TT_TASK | Preparation of construction joint for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1912 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1913 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1914 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 |  | COMPLETED
1916 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1917 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 |  | COMPLETED
1918 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Tue Jun 04 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 |  | COMPLETED
1919 | TT_TASK | Concreting for wall and roof (333m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1920 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1921 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Wed Jun 12 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1922 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 |  | COMPLETED
1923 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
1924 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 05 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Tue Mar 04 18:00:00 IST 2014 |  | COMPLETED
1926 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1927 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1928 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1929 | TT_TASK | Concreting for wall and roof (412m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1930 | TT_TASK | Curing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Sun Jun 23 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Sat Mar 23 18:00:00 IST 2013 |  | COMPLETED
1931 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Mar 25 08:00:00 IST 2013 | Mon Mar 25 18:00:00 IST 2013 |  | COMPLETED
1932 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Mar 26 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1933 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jun 24 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1934 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 27 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Mon Mar 03 18:00:00 IST 2014 |  | COMPLETED
1936 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1937 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1938 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Apr 02 18:00:00 IDT 2013 |  | COMPLETED
1939 | TT_TASK | Concreting for wall and roof (320m3) | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Apr 05 08:00:00 IDT 2013 | Fri Apr 05 18:00:00 IDT 2013 |  | COMPLETED
1940 | TT_TASK | Curing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 06 08:00:00 IDT 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1941 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1942 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1943 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1944 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jan 21 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Sat Mar 01 18:00:00 IST 2014 |  | COMPLETED
1946 | TT_TASK | Excavation and saw cut D-wall | Thu Apr 02 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Sat Jul 25 18:00:00 IDT 2015 |  | COMPLETED
1947 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Aug 08 16:24:00 IDT 2015 | Mon Aug 10 16:24:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Mon Jul 13 18:00:00 IDT 2015 |  | COMPLETED
1948 | TT_TASK | Erect external formwork for base slab | Mon Aug 10 16:24:00 IDT 2015 | Wed Aug 12 16:24:00 IDT 2015 | Tue Jul 14 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
1949 | TT_TASK | Rebar fixing for base slab | Wed Aug 12 16:24:00 IDT 2015 | Fri Aug 14 16:24:00 IDT 2015 | Wed Jul 15 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1950 | TT_TASK | Erect internal kicker formwork for base slab | Fri Aug 14 16:24:00 IDT 2015 | Mon Aug 17 16:24:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Wed Aug 12 18:00:00 IDT 2015 |  | COMPLETED
1951 | TT_TASK | Concreting for base slab (90m3) | Wed Sep 02 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 | Thu Aug 13 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 |  | COMPLETED
1952 | TT_TASK | Curing for base slab | Thu Sep 03 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Fri Aug 14 08:00:00 IDT 2015 | Thu Aug 20 18:00:00 IDT 2015 |  | COMPLETED
1953 | TT_TASK | Preparation of construction joint for base slab | Thu Sep 03 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Fri Aug 21 08:00:00 IDT 2015 | Fri Aug 21 18:00:00 IDT 2015 |  | COMPLETED
1954 | TT_TASK | Removal of formwork for base slab | Fri Sep 04 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Sat Aug 22 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 |  | COMPLETED
1955 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Sep 05 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 | Mon Aug 24 08:00:00 IDT 2015 | Mon Aug 24 18:00:00 IDT 2015 |  | COMPLETED
1956 | TT_TASK | Curing | Thu Sep 10 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Tue Aug 25 08:00:00 IDT 2015 | Tue Aug 25 18:00:00 IDT 2015 |  | COMPLETED
1957 | TT_TASK | Removal strut S3 | Sat Sep 19 08:00:00 IDT 2015 | Wed Sep 23 18:00:00 IDT 2015 | Wed Sep 16 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
1958 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Sep 24 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
1959 | TT_TASK | Rebar fixing for wall and roof | Wed Sep 30 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 | Fri Sep 25 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 |  | COMPLETED
1960 | TT_TASK | Erect external formwork for wall and roof | Thu Oct 15 08:00:00 IDT 2015 | Fri Oct 16 18:00:00 IDT 2015 | Mon Oct 05 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
1961 | TT_TASK | Concreting for wall and roof (260m3) | Sat Oct 17 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 | Wed Oct 07 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1962 | TT_TASK | Curing for wall and roof | Sun Oct 18 08:00:00 IDT 2015 | Tue Oct 27 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 |  | COMPLETED
1963 | TT_TASK | Preparation of construction joint for wall and roof | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
1964 | TT_TASK | Removal external and internal formwork for wall | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
1965 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 28 08:00:00 IST 2015 | Thu Oct 29 18:00:00 IST 2015 | Thu Oct 22 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1966 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Oct 30 08:00:00 IST 2015 | Wed Nov 04 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1968 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 02 18:00:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 |  | COMPLETED
1969 | TT_TASK | Erect external formwork for base slab | Fri Jul 03 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Tue Jul 21 08:00:00 IDT 2015 | Wed Jul 22 18:00:00 IDT 2015 |  | COMPLETED
1970 | TT_TASK | Rebar fixing for base slab | Mon Jul 06 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 23 08:00:00 IDT 2015 | Fri Jul 24 18:00:00 IDT 2015 |  | COMPLETED
1971 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jul 08 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Sat Jul 25 08:00:00 IDT 2015 | Mon Jul 27 18:00:00 IDT 2015 |  | COMPLETED
1972 | TT_TASK | Concreting for base slab (123m3) | Fri Jul 10 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jul 28 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 |  | COMPLETED
1973 | TT_TASK | Curing for base slab | Sat Jul 11 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1974 | TT_TASK | Preparation of construction joint for base slab | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 |  | COMPLETED
1975 | TT_TASK | Removal of formwork for base slab | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 |  | COMPLETED
1976 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1977 | TT_TASK | Curing | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 |  | COMPLETED
1978 | TT_TASK | Removal strut S3 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1979 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 |  | COMPLETED
1980 | TT_TASK | Rebar fixing for wall and roof | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 |  | COMPLETED
1981 | TT_TASK | Erect external formwork for wall and roof | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 |  | COMPLETED
1982 | TT_TASK | Concreting for wall and roof (260m3) | Fri Oct 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 | Sat Oct 24 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
1983 | TT_TASK | Curing for wall and roof | Sat Oct 03 08:00:00 IDT 2015 | Mon Oct 12 18:00:00 IDT 2015 | Mon Oct 26 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1984 | TT_TASK | Preparation of construction joint for wall and roof | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
1985 | TT_TASK | Removal external and internal formwork for wall | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1986 | TT_TASK | Removal internal falsework and formwork for roof | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1987 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1989 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
1990 | TT_TASK | Erect external formwork for base slab | Mon Jun 15 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1991 | TT_TASK | Rebar fixing for base slab | Wed Jun 17 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
1992 | TT_TASK | Erect internal kicker formwork for base slab | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
1993 | TT_TASK | Concreting for base slab (127m3) | Tue Jun 23 08:00:00 IDT 2015 | Tue Jun 23 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
1994 | TT_TASK | Curing for base slab | Wed Jun 24 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
1995 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 24 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1996 | TT_TASK | Removal of formwork for base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
1997 | TT_TASK | Infill concrete in between D-wall and base slab | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1998 | TT_TASK | Curing | Thu May 28 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1999 | TT_TASK | Removal strut S3 | Fri May 29 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2000 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 03 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2001 | TT_TASK | Rebar fixing for wall and roof | Mon Jun 08 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2002 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2003 | TT_TASK | Concreting for wall and roof (260m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2004 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2005 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2006 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2007 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2008 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 11 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2010 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
2011 | TT_TASK | Erect external formwork for base slab | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
2012 | TT_TASK | Rebar fixing for base slab | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
2013 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
2014 | TT_TASK | Concreting for base slab (127m3) | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
2015 | TT_TASK | Curing for base slab | Thu Jun 11 08:00:00 IDT 2015 | Wed Jun 17 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2016 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 11 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
2017 | TT_TASK | Removal of formwork for base slab | Sat May 23 08:00:00 IDT 2015 | Sat May 23 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
2018 | TT_TASK | Infill concrete in between D-wall and base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
2019 | TT_TASK | Curing | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2020 | TT_TASK | Removal strut S3 | Thu May 28 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2021 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2022 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2023 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2024 | TT_TASK | Concreting for wall and roof (150m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2025 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2026 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2027 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2028 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2029 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jul 06 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
2031 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2032 | TT_TASK | Erect external formwork for base slab | Thu May 21 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2033 | TT_TASK | Rebar fixing for base slab | Sat May 23 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2034 | TT_TASK | Erect internal kicker formwork for base slab | Wed May 27 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2035 | TT_TASK | Concreting for base slab (70m3) | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2036 | TT_TASK | Curing for base slab | Sat May 30 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2037 | TT_TASK | Preparation of construction joint for base slab | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2038 | TT_TASK | Removal of formwork for base slab | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2039 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2040 | TT_TASK | Curing | Sat Jun 06 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2041 | TT_TASK | Removal strut S3 | Mon Jun 08 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat May 23 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2043 | TT_TASK | Rebar fixing for wall and roof | Fri May 29 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2044 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2045 | TT_TASK | Concreting for wall and roof (175m3) | Thu Jun 04 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2046 | TT_TASK | Curing for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sun Jun 14 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2047 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2048 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 03 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 04 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2050 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 29 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
2052 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2053 | TT_TASK | Erect external formwork for base slab | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2054 | TT_TASK | Rebar fixing for base slab | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2055 | TT_TASK | Erect internal kicker formwork for base slab | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2056 | TT_TASK | Concreting for base slab (70m3) | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2057 | TT_TASK | Curing for base slab | Wed Apr 22 08:00:00 IDT 2015 | Tue Apr 28 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2058 | TT_TASK | Preparation of construction joint for base slab | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2059 | TT_TASK | Removal of formwork for base slab | Thu Apr 23 08:00:00 IDT 2015 | Thu Apr 23 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2060 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Apr 24 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2061 | TT_TASK | Curing | Wed Apr 29 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2062 | TT_TASK | Removal strut S3 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2063 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed May 06 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2064 | TT_TASK | Rebar fixing for wall and roof | Thu May 14 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2065 | TT_TASK | Erect external formwork for wall and roof | Mon May 18 08:00:00 IDT 2015 | Tue May 19 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2066 | TT_TASK | Concreting for wall and roof (175m3) | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2067 | TT_TASK | Curing for wall and roof | Thu May 21 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2068 | TT_TASK | Preparation of construction joint for wall and roof | Thu May 21 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2069 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2070 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2071 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jun 23 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
2073 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Fri Nov 15 18:00:00 IST 2013 |  | COMPLETED
2074 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Nov 16 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2075 | TT_TASK | Rebar fixing for base slab | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
2076 | TT_TASK | Erect internal kicker formwork for base slab | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
2077 | TT_TASK | Concreting for base slab (70m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
2078 | TT_TASK | Curing for base slab | Fri Dec 20 08:00:00 IST 2013 | Thu Dec 26 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
2079 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 |  | COMPLETED
2080 | TT_TASK | Removal of formwork for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
2081 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
2082 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2083 | TT_TASK | Removal strut S3 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2084 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Apr 16 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2085 | TT_TASK | Rebar fixing for wall and roof | Thu Apr 24 08:00:00 IDT 2014 | Sat Apr 26 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 |  | COMPLETED
2086 | TT_TASK | Erect external formwork for wall and roof | Mon Apr 28 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Thu Apr 10 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2087 | TT_TASK | Concreting for wall and roof (170m3) | Wed Apr 30 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Sat Apr 12 08:00:00 IDT 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
2088 | TT_TASK | Curing for wall and roof | Thu May 01 08:00:00 IDT 2014 | Sat May 10 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Tue Apr 22 18:00:00 IDT 2014 |  | COMPLETED
2089 | TT_TASK | Preparation of construction joint for wall and roof | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 |  | COMPLETED
2090 | TT_TASK | Removal external and internal formwork for wall | Sat May 03 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Tue Apr 15 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
2091 | TT_TASK | Removal internal falsework and formwork for roof | Mon May 12 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 |  | COMPLETED
2092 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jun 05 08:00:00 IDT 2014 | Tue Jun 10 18:00:00 IDT 2014 | Thu May 29 08:00:00 IDT 2014 | Thu Dec 04 18:00:00 IST 2014 |  | COMPLETED
2094 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2095 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2096 | TT_TASK | Rebar fixing for base slab | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2097 | TT_TASK | Erect internal kicker formwork for base slab | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2098 | TT_TASK | Concreting for base slab (70m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2099 | TT_TASK | Curing for base slab | Sun Dec 08 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2100 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2101 | TT_TASK | Removal of formwork for base slab | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
2102 | TT_TASK | Infill concrete in between D-wall and base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
2103 | TT_TASK | Curing | Sun Dec 15 08:00:00 IST 2013 | Sun Dec 15 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2104 | TT_TASK | Removal strut S3 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2105 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Feb 12 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2106 | TT_TASK | Rebar fixing for wall and roof | Mon Feb 17 08:00:00 IST 2014 | Wed Feb 19 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
2107 | TT_TASK | Erect external formwork for wall and roof | Fri Feb 28 13:48:00 IST 2014 | Mon Mar 03 13:48:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2108 | TT_TASK | Concreting for wall and roof (200m3) | Mon Mar 03 13:48:00 IST 2014 | Tue Mar 04 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2109 | TT_TASK | Curing for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Fri Mar 14 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2110 | TT_TASK | Preparation of construction joint for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Wed Mar 05 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2111 | TT_TASK | Removal external and internal formwork for wall | Wed Mar 05 13:48:00 IST 2014 | Thu Mar 06 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
2112 | TT_TASK | Removal internal falsework and formwork for roof | Fri Mar 14 13:48:00 IST 2014 | Mon Mar 17 13:48:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2113 | TT_TASK | Side walkway and cable bracket (204m3) | Thu May 29 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Wed Dec 03 18:00:00 IST 2014 |  | COMPLETED
2115 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2116 | TT_TASK | Erect external formwork for base slab | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2117 | TT_TASK | Rebar fixing for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2118 | TT_TASK | Erect internal kicker formwork for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2119 | TT_TASK | Concreting for base slab (70m3) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2120 | TT_TASK | Curing for base slab | Tue Dec 03 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2121 | TT_TASK | Preparation of construction joint for base slab | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
2122 | TT_TASK | Removal of formwork for base slab | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2123 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2124 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2125 | TT_TASK | Removal strut S3 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
2126 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jan 25 08:00:00 IST 2014 | Wed Jan 29 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
2127 | TT_TASK | Rebar fixing for wall and roof | Thu Jan 30 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Fri Dec 20 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
2128 | TT_TASK | Erect external formwork for wall and roof | Thu Feb 20 08:00:00 IST 2014 | Fri Feb 21 18:00:00 IST 2014 | Thu Jan 09 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2129 | TT_TASK | Concreting for wall and roof (200m3) | Sat Feb 22 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2130 | TT_TASK | Curing for wall and roof | Sun Feb 23 08:00:00 IST 2014 | Tue Mar 04 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2131 | TT_TASK | Preparation of construction joint for wall and roof | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Tue Jan 14 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2132 | TT_TASK | Removal external and internal formwork for wall | Tue Feb 25 08:00:00 IST 2014 | Tue Feb 25 18:00:00 IST 2014 | Wed Jan 15 08:00:00 IST 2014 | Wed Jan 15 18:00:00 IST 2014 |  | COMPLETED
2133 | TT_TASK | Removal internal falsework and formwork for roof | Wed Mar 05 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2134 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
2137 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Sep 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
2138 | TT_TASK | Erect external formwork for base slab | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Sep 21 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
2139 | TT_TASK | Rebar fixing for base slab | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
2140 | TT_TASK | Erect internal kicker formwork for base slab | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
2141 | TT_TASK | Staircase construction (+12.0mPD to +14.706mPD) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2142 | TT_TASK | Concreting for base slab (30m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
2143 | TT_TASK | Curing for base slab | Fri Dec 13 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
2144 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
2145 | TT_TASK | Removal of formwork for base slab | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 18:00:00 IDT 2013 |  | COMPLETED
2146 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2147 | TT_TASK | Mass concrete at level +12.0mPD | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 |  | COMPLETED
2148 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2149 | TT_TASK | Removal strut S3 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2150 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 17 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Mon Dec 01 18:00:00 IST 2014 |  | COMPLETED
2152 | TT_TASK | Erect working platform to +21.0mPD | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2153 | TT_TASK | Rebar fixing for wall and roof | Sat Jan 11 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2154 | TT_TASK | Staircase construction (+14.706mPD to +16.956mPD) (20m3) | Fri May 02 08:00:00 IDT 2014 | Wed May 07 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2155 | TT_TASK | Staircase construction (+16.956mPD to +19.206mPD) (20m3) | Thu Jun 05 08:00:00 IDT 2014 | Mon Jun 09 18:00:00 IDT 2014 | Thu Jun 12 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2156 | TT_TASK | Staircase construction (+19.206mPD to +21.456mPD) (20m3) | Tue Jun 10 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Fri Jun 20 18:00:00 IDT 2014 |  | COMPLETED
2157 | TT_TASK | Erect external formwork for wall and roof | Sat Mar 15 08:00:00 IST 2014 | Mon Mar 17 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2158 | TT_TASK | Concreting for wall and roof (31m3) | Tue Feb 04 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2159 | TT_TASK | Curing for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 |  | COMPLETED
2160 | TT_TASK | Preparation of construction joint for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2161 | TT_TASK | Removal external and internal formwork for wall | Thu Feb 06 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2162 | TT_TASK | Removal internal falsework and formwork for roof | Sat Feb 15 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Thu Jan 23 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2164 | TT_TASK | Removal strut S2 @ SN 19 | Wed Apr 02 08:00:00 IDT 2014 | Mon Apr 07 18:00:00 IDT 2014 | Mon Mar 03 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 |  | COMPLETED
2165 | TT_TASK | Erect working platform to +24.0mPD | Tue Apr 08 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 | Fri Mar 07 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 |  | COMPLETED
2166 | TT_TASK | Erect internal formwork below strut S1 | Sat Apr 12 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 | Wed Mar 12 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 |  | COMPLETED
2167 | TT_TASK | Staircase construction (+21.456mPD to +23.706mPD) (20m3) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 |  | COMPLETED
2168 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 | Fri Mar 14 08:00:00 IST 2014 | Tue Apr 01 18:00:00 IDT 2014 |  | COMPLETED
2169 | TT_TASK | Erect external wall & internal wall formwork | Tue May 13 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Wed Apr 02 08:00:00 IDT 2014 | Thu Apr 03 18:00:00 IDT 2014 |  | COMPLETED
2170 | TT_TASK | Concreting (External Wall & Internal Wall) (264m3) | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Fri Apr 04 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2171 | TT_TASK | Curing (External Wall & Internal Wall) | Fri May 16 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2172 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Mon May 19 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Thu Apr 10 18:00:00 IDT 2014 |  | COMPLETED
2173 | TT_TASK | Waterproofing | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 |  | COMPLETED
2174 | TT_TASK | Backfilling | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2176 | TT_TASK | Removal strut S1 @ SN 19 | Thu Jun 19 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2177 | TT_TASK | Erect working platform to +30.406mPD | Tue Jun 24 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2178 | TT_TASK | Erect internal formwork | Sat Jun 28 08:00:00 IDT 2014 | Sat Jun 28 18:00:00 IDT 2014 | Wed Jun 04 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2179 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Mon Jun 30 08:00:00 IDT 2014 | Wed Jul 02 18:00:00 IDT 2014 | Thu Jun 05 08:00:00 IDT 2014 | Fri Jun 06 18:00:00 IDT 2014 |  | COMPLETED
2180 | TT_TASK | Erect external formwork (External Wall & Internal Wall) | Thu Jul 03 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2181 | TT_TASK | Concreting (External Wall & Internal Wall) (128m3) | Fri Jul 04 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2182 | TT_TASK | Curing (External Wall & Internal Wall) | Sat Jul 05 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 18:00:00 IDT 2014 |  | COMPLETED
2183 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Tue Jul 08 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2184 | TT_TASK | Waterproofing | Wed Jul 09 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Thu Jun 19 18:00:00 IDT 2014 |  | COMPLETED
2185 | TT_TASK | Backfilling | Sat Jul 12 08:00:00 IDT 2014 | Wed Jul 16 18:00:00 IDT 2014 | Fri Jun 20 08:00:00 IDT 2014 | Tue Jun 24 18:00:00 IDT 2014 |  | COMPLETED
2186 | TT_TASK | Erect falsework and soffit formwork +30.206mPD | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 | Wed Jun 25 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2187 | TT_TASK | Staircase construction (+21.456mPD to +25.956mPD) (20m3) | Sat Jul 19 08:00:00 IDT 2014 | Wed Jul 23 18:00:00 IDT 2014 | Fri Jun 27 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2188 | TT_TASK | Staircase construction (+25.956mPD to +27.606mPD) (20m3) | Sat Jul 05 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 05 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 |  | COMPLETED
2189 | TT_TASK | Rebar fixing (Beam, Floor Slab and Staircase) | Thu Jul 10 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Thu Jul 10 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2190 | TT_TASK | Concreting (Beam, Floor Slab and Staircase) (31m3) | Fri Jul 11 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2191 | TT_TASK | Curing (Beam, Floor Slab and Staircase) | Wed Sep 03 08:00:00 IDT 2014 | Tue Sep 09 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2193 | TT_TASK | Erect working platform to +33.576mPD | Wed Sep 03 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
2194 | TT_TASK | Erect external formwork (External Wall) | Mon Sep 08 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 | Fri Sep 26 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2195 | TT_TASK | Rebar fixing (External Wall) | Thu Sep 11 08:00:00 IDT 2014 | Fri Sep 12 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2196 | TT_TASK | Erect internal formwork (External Wall) | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 |  | COMPLETED
2197 | TT_TASK | Concreting (External Wall) (49m3) | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 |  | COMPLETED
2198 | TT_TASK | Curing (External Wall) | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 |  | COMPLETED
2199 | TT_TASK | Removal formwork (External Wall) | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
2200 | TT_TASK | Erect falsework and soffit formwork +32.656 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2201 | TT_TASK | Rebar fixing (Beam & Floor Slab) | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 |  | COMPLETED
2202 | TT_TASK | Concreting (Beam & Floor Slab) (31m3) | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 |  | COMPLETED
2203 | TT_TASK | Curing (Beam & Floor Slab) | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2205 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
2206 | TT_TASK | Rebar fixing (Roof Parapet Wall) | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 |  | COMPLETED
2207 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2208 | TT_TASK | Concreting (Roof Parapet Wall) (30m3) | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
2209 | TT_TASK | Curing (Roof Parapet Wall) | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 |  | COMPLETED
2210 | TT_TASK | Removal formwork (Roof Parapet Wall) | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2211 | TT_TASK | Removal of falsework and soffit formwork | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
2213 | TT_TASK | Wet trade work | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 |  | COMPLETED
2214 | TT_TASK | Metal works (Louver, Door, Cat-ladder, Architectural Fins, Handrail, Roof Sliding Hatch and Balustrade, etc) | Thu Nov 27 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Thu Nov 27 08:00:00 IST 2014 | Thu Mar 05 18:00:00 IST 2015 |  | COMPLETED
2215 | TT_TASK | Coat works | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2218 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Nov 29 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Feb 04 18:00:00 IST 2014 |  | COMPLETED
2219 | TT_TASK | Backfilling between D-wall and 0.5m below S1 14,240m3 soil | Thu Feb 06 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 | Wed Feb 05 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 |  | COMPLETED
2220 | TT_TASK | Removal of S1 | Wed Mar 12 08:00:00 IST 2014 | Tue Mar 25 18:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 |  | COMPLETED
2221 | TT_TASK | Backfilling to original ground level 21,390m3 (approx. +25.0mPD) | Sat Mar 01 08:00:00 IST 2014 | Wed Mar 19 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Sat May 03 18:00:00 IDT 2014 |  | COMPLETED
2223 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 |  | COMPLETED
2224 | TT_TASK | Backfilling between D-wall and 0.5m below S1 (2075m3) | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 |  | COMPLETED
2225 | TT_TASK | Removal of S1 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 |  | COMPLETED
2226 | TT_TASK | Backfilling to original ground level 3,900m3 (approx. +25.0mPD) (1353m3) | Sat Mar 01 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
2227 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
2228 | TT_TASK | Backfilling backfilling to +20mPD from SN8 to SN9 (Soil: 7,050m3 @ 500m3/day) | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 |  | COMPLETED
2229 | TT_TASK | Removal of S1 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
2230 | TT_TASK | Construction of mud pit | Sat Jul 06 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
2231 | TT_TASK | Backfilling from +20mPD to ground level from SN8 to SN9 (Soil: 5,000m3 @ 500m3/day) | Tue Aug 06 08:00:00 IDT 2013 | Sat Aug 17 18:00:00 IDT 2013 | Tue Jul 02 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 |  | COMPLETED
2233 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Aug 07 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2234 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) | Fri Aug 14 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2235 | TT_TASK | Placing mass concrete infill between tunnel and D-wall | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 02 18:00:00 IST 2015 | Thu Dec 24 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2236 | TT_TASK | Removal of S2 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 10 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 04 18:00:00 IST 2016 |  | COMPLETED
2237 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2238 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
2239 | TT_TASK | Removal strut S1 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2240 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
2241 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488 m3 of soil) | Mon Jan 25 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Fri Apr 01 18:00:00 IDT 2016 |  | COMPLETED
2243 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) (SN18-19) | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 |  | COMPLETED
2244 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) (SN18-19) | Sat Apr 26 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Sat Apr 26 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
2245 | TT_TASK | Placing mass concrete infill between tunnel and D-wall (SN18-19) | Tue May 20 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri May 16 18:00:00 IDT 2014 |  | COMPLETED
2246 | TT_TASK | Removal of S2 (SN16-18) | Wed Jun 04 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 |  | COMPLETED
2247 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) (SN16-18) | Mon Jun 09 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Tue May 27 18:00:00 IDT 2014 |  | COMPLETED
2248 | TT_TASK | Removal strut S1 (SN16-18) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Wed May 28 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
2249 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488m3 of soil) | Fri Jun 27 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
2251 | TT_TASK | Dismantling temporary bridge deck | Mon Jun 15 08:00:00 IDT 2015 | Tue Jul 21 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2252 | TT_TASK | Reinstatement of Works Area 4.10 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jan 11 18:00:00 IST 2017 | Mon May 02 08:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 |  | COMPLETED
2253 | TT_TASK | Complete all tree planting and reinstate Works Area 4.12C | Tue Nov 01 08:00:00 IST 2016 | Thu Jul 13 18:00:00 IDT 2017 | Sat Oct 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2254 | TT_TASK | Reinstate Works Areas 4.9, 4.9A and 4.12A prior to handover | Mon May 22 08:00:00 IDT 2017 | Sat Sep 02 18:00:00 IDT 2017 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2258 | TT_TASK | Application of power supply, environmental permits and construction substation | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2259 | TT_TASK | Procurement and Confirmation of the order of 2nd tunnel boring machine | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2260 | TT_TASK | TBM design and submission for approval | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2261 | TT_TASK | TBM materials order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
2262 | TT_TASK | TBM equipments order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 |  | COMPLETED
2263 | TT_TASK | TBM Fabrication | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
2264 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 |  | COMPLETED
2265 | TT_TASK | TBM test Run | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2266 | TT_TASK | TBM disassembly and packing for shipping to HK | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 |  | COMPLETED
2267 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
2268 | TT_TASK | Setup TBM facilities | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
2269 | TT_TASK | Fabrication 50% of South Tunnel South Bound Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
2270 | TT_TASK | Fabrication 100% of South Tunnel South Bound Precast Lining | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
2271 | TT_TASK | Fabrication 50% of South Tunnel North Bound Precast Lining | Wed Oct 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 | Wed Oct 03 08:00:00 IST 2012 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
2272 | TT_TASK | Fabrication 100% of South Tunnel North Bound Precast Lining | Mon Aug 26 08:00:00 IDT 2013 | Wed Jan 22 18:00:00 IST 2014 | Wed Feb 27 08:00:00 IST 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
2274 | TT_TASK | Ground treatment at lauching shaft Southbound | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
2275 | TT_TASK | TBM assemble, thrust frame, testing and commissioning | Sat Jun 01 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2276 | TT_TASK | Lowing back-up plant for final drive | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
2277 | TT_TASK | Assemble and set up back-up plant for final drive | Sat Jun 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2278 | TT_TASK | Erection of noise enclosure | Sat Jul 20 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 |  | COMPLETED
2279 | TT_TASK | TBM drive & lining installation CH124+912 to CH125+012 (Initial Drive) | Sat Jul 20 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Mon Mar 11 00:00:00 IST 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
2280 | TT_TASK | TBM drive & lining installation CH125+012 to CH125+338 | Tue Oct 15 08:00:00 IDT 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon May 27 08:00:00 IDT 2013 | Tue May 20 00:00:00 IDT 2014 |  | COMPLETED
2281 | TT_TASK | Dis-assemble TBM | Fri May 23 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 |  | COMPLETED
2282 | TT_TASK | Invert slab and side walkway | Fri Aug 01 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Tue Sep 02 18:00:00 IDT 2014 |  | COMPLETED
2283 | TT_TASK | Installation of cable bracket | Mon Nov 03 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 | Mon Aug 18 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2285 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Sep 01 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 | Sat Aug 09 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2286 | TT_TASK | Ground treatment at lauching shaft Northbound | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 19 18:00:00 IST 2013 | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
2287 | TT_TASK | TBM assemble, testing and commissioning | Wed Jul 02 08:00:00 IDT 2014 | Wed Sep 03 18:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2288 | TT_TASK | Setup back-up plant for final drive | Tue Jun 03 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2289 | TT_TASK | Reinstate of noise enclosure | Fri Oct 10 08:00:00 IDT 2014 | Wed Nov 05 18:00:00 IST 2014 | Tue Oct 28 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
2290 | TT_TASK | TBM drive & lining installation CH124+927 to CH125+027 (Initial Drive) | Fri Oct 10 08:00:00 IDT 2014 | Thu Nov 13 18:00:00 IST 2014 | Thu Oct 30 00:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
2291 | TT_TASK | TBM drive & lining installation CH125+027 to CH125+353 (Final Drive) | Fri Jan 02 08:00:00 IST 2015 | Thu Feb 12 18:00:00 IST 2015 | Mon Dec 08 08:00:00 IST 2014 | Fri Aug 07 00:00:00 IDT 2015 |  | COMPLETED
2292 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Tue Aug 04 08:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
2293 | TT_TASK | Dis-assemble TBM | Tue Aug 04 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
2294 | TT_TASK | Invert slab and side walkway | Wed Sep 09 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
2295 | TT_TASK | Installation of cable bracket | Thu Sep 24 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Aug 31 18:00:00 IDT 2015 |  | COMPLETED
2298 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Partial length) at down track | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 |  | COMPLETED
2299 | TT_TASK | Probe/Grout | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 | Mon Aug 11 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2300 | TT_TASK | Coring of Segment | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 |  | COMPLETED
2301 | TT_TASK | Removal of segment | Tue Sep 02 08:00:00 IDT 2014 | Thu Sep 04 18:00:00 IDT 2014 | Thu Aug 21 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2302 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Sep 05 08:00:00 IDT 2014 | Tue Oct 07 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2303 | TT_TASK | Invert Concrete | Thu Oct 23 08:00:00 IDT 2014 | Sat Nov 01 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2304 | TT_TASK | Wall and Roof concrete | Mon Nov 03 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Mon Oct 13 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
2305 | TT_TASK | Dismantle Temporary frame | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2306 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
2307 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Remaining length ) at down track | Sat May 09 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Thu Apr 16 18:00:00 IDT 2015 |  | COMPLETED
2308 | TT_TASK | Probe/Grout | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
2309 | TT_TASK | Coring of Segment | Fri Oct 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 | Fri Oct 16 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
2310 | TT_TASK | Removal of segment | Wed Oct 07 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
2311 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Oct 10 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Oct 26 08:00:00 IST 2015 | Fri Dec 11 18:00:00 IST 2015 |  | COMPLETED
2312 | TT_TASK | Invert Concrete | Thu Dec 03 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Sat Dec 12 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2313 | TT_TASK | Wall and Roof concrete | Mon Dec 14 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 15 18:00:00 IST 2016 |  | COMPLETED
2314 | TT_TASK | Dismantle Temporary frame | Wed Jan 13 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 |  | COMPLETED
2315 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2318 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 |  | COMPLETED
2319 | TT_TASK | Pre-drill and guide wall | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 |  | COMPLETED
2320 | TT_TASK | D-wall design review | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 |  | COMPLETED
2321 | TT_TASK | D-Wall Construction (1075m3) | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 |  | COMPLETED
2322 | TT_TASK | Shear pin, toe grout and pumping test | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 |  | COMPLETED
2324 | TT_TASK | SI for TBM ground treatment | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2325 | TT_TASK | Design review of TBM ground treatment | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2326 | TT_TASK | Ground treatment for TBM southbound | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
2327 | TT_TASK | Ground treatment for TBM northbound | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2329 | TT_TASK | Capping beam construction | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2330 | TT_TASK | L-Shape wall construction | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
2331 | TT_TASK | Excavate up to +28.5mPD (1488m3) | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 |  | COMPLETED
2332 | TT_TASK | Install Strut S1 +29.0mPD | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 |  | COMPLETED
2333 | TT_TASK | Excavate up to +23.5mPD (2480m3) | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 |  | COMPLETED
2334 | TT_TASK | Install Strut S2 +24.0mPD | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 |  | COMPLETED
2335 | TT_TASK | Excavate up to +19.5mPD (1984m3) | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
2336 | TT_TASK | Install Strut S3 +20.0mPD | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 |  | COMPLETED
2337 | TT_TASK | Excavate up to +15.5mPD (1984m3) | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
2338 | TT_TASK | Install Strut S4 +16.0mPD | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 |  | COMPLETED
2339 | TT_TASK | Excavate up to formation (4117m3) | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
2340 | TT_TASK | Install rock dowel and tie back | Sat Jun 02 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Sat Jun 02 08:00:00 IDT 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2341 | TT_TASK | Temporary handover the shaft to contract 822 | Mon Jun 03 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2343 | TT_TASK | Rock breaking works | Mon Aug 26 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
2344 | TT_TASK | Temporary base Slab for TBM Drive | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
2347 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2348 | TT_TASK | Erect external formwork (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Wed Aug 13 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Tue Aug 19 18:00:00 IDT 2014 |  | COMPLETED
2349 | TT_TASK | Rebar fixing (Base Slab) | Thu Aug 14 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Wed Aug 20 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2350 | TT_TASK | Erect internal kicker formwork (Base Slab) | Tue Aug 19 08:00:00 IDT 2014 | Thu Aug 21 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 |  | COMPLETED
2351 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 22 08:00:00 IDT 2014 | Fri Aug 22 18:00:00 IDT 2014 | Thu Aug 28 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2352 | TT_TASK | Concreting (Base Slab) (245m3) | Sat Aug 23 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014 | Fri Aug 29 18:00:00 IDT 2014 |  | COMPLETED
2353 | TT_TASK | Curing (Base Slab) | Mon Aug 25 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2354 | TT_TASK | Removal of formwork (Base Slab) | Mon Sep 08 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Mon Sep 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2355 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Sep 10 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Tue Sep 02 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 |  | COMPLETED
2356 | TT_TASK | Rebar fixing (Wall and roof) | Thu Sep 18 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Thu Sep 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2357 | TT_TASK | Erect external formwork (Wall) | Thu Sep 25 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2358 | TT_TASK | Clearing and inspection (Wall and roof) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2359 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
2360 | TT_TASK | Curing (Wall and roof) | Sat Oct 11 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
2361 | TT_TASK | Removal formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Thu Oct 16 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Sat Nov 01 18:00:00 IST 2014 |  | COMPLETED
2362 | TT_TASK | Removal formwork (Roof) | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2363 | TT_TASK | Side walkway and cable bracket (72m3) | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
2365 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Nov 07 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Sat Nov 07 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
2366 | TT_TASK | Erect external formwork (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Wed Nov 18 18:00:00 IST 2015 |  | COMPLETED
2367 | TT_TASK | Rebar fixing (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Tue Nov 17 18:00:00 IST 2015 | Thu Nov 19 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 |  | COMPLETED
2368 | TT_TASK | Erect internal kicker formwork (Base Slab) | Wed Nov 18 08:00:00 IST 2015 | Fri Nov 20 18:00:00 IST 2015 | Tue Nov 24 08:00:00 IST 2015 | Thu Nov 26 18:00:00 IST 2015 |  | COMPLETED
2369 | TT_TASK | Clearing and inspection (Base Slab) | Sat Nov 21 08:00:00 IST 2015 | Sat Nov 21 18:00:00 IST 2015 | Fri Nov 27 08:00:00 IST 2015 | Fri Nov 27 18:00:00 IST 2015 |  | COMPLETED
2370 | TT_TASK | Concreting (Base Slab) (245m3) | Mon Nov 23 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Nov 28 08:00:00 IST 2015 | Sat Nov 28 18:00:00 IST 2015 |  | COMPLETED
2371 | TT_TASK | Curing (Base Slab) | Tue Nov 24 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Mon Nov 30 08:00:00 IST 2015 | Thu Dec 03 18:00:00 IST 2015 |  | COMPLETED
2372 | TT_TASK | Removal of formwork (Base Slab) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Fri Dec 04 08:00:00 IST 2015 | Sat Dec 05 18:00:00 IST 2015 |  | COMPLETED
2373 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 09 18:00:00 IST 2015 | Mon Dec 07 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
2374 | TT_TASK | Rebar fixing (Wall and roof) | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2375 | TT_TASK | Erect external formwork (Wall) | Mon Jan 11 08:00:00 IST 2016 | Wed Jan 13 18:00:00 IST 2016 | Thu Jan 07 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2376 | TT_TASK | Clearing and inspection (Wall and roof) | Thu Jan 14 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2377 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Jan 15 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2378 | TT_TASK | Curing (Wall and roof) | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 |  | COMPLETED
2379 | TT_TASK | Removal formwork (Wall) | Tue Jan 19 08:00:00 IST 2016 | Thu Jan 21 18:00:00 IST 2016 | Thu Jan 28 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2380 | TT_TASK | Removal formwork and falsework (Roof) | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Sat Jan 30 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2381 | TT_TASK | Side walkway and cable bracket (72m3) | Wed Jan 06 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Thu Nov 12 08:00:00 IST 2015 | Tue Mar 01 18:00:00 IST 2016 |  | COMPLETED
2382 | TT_TASK | Provision access opening to DC | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2383 | TT_TASK | Erect falsework and soffit formwork (Opening) | Thu Mar 10 08:00:00 IST 2016 | Mon Mar 21 18:00:00 IST 2016 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2384 | TT_TASK | Rebar fixing (Roof) | Tue Mar 22 08:00:00 IST 2016 | Tue Mar 22 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2385 | TT_TASK | Clearing and inspection (Roof) | Wed Mar 23 08:00:00 IST 2016 | Wed Mar 23 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2386 | TT_TASK | Concreting (Roof) (225m3) | Thu Mar 24 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2387 | TT_TASK | Curing (Roof) | Tue Mar 29 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Jan 13 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
2388 | TT_TASK | Removal internal falsework and soffit formwork (Roof) | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
2390 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Thu Mar 17 08:00:00 IST 2016 | Fri Mar 18 18:00:00 IST 2016 | Tue Mar 01 08:00:00 IST 2016 | Wed Mar 02 18:00:00 IST 2016 |  | COMPLETED
2391 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Sat Mar 19 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Thu Mar 03 08:00:00 IST 2016 | Tue Mar 08 18:00:00 IST 2016 |  | COMPLETED
2392 | TT_TASK | Backfilling to +18.25mPD (1229 m3 of soil) | Sat Jul 02 08:00:00 IDT 2016 | Mon Jul 11 18:00:00 IDT 2016 | Mon Jul 25 08:00:00 IDT 2016 | Tue Aug 02 18:00:00 IDT 2016 |  | COMPLETED
2393 | TT_TASK | Laying 500mm mass concrete lateral support | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 |  | COMPLETED
2394 | TT_TASK | Backfilling to 0.5m below S3 (+19.5mPD) (372m3 of soil) | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 |  | COMPLETED
2395 | TT_TASK | Removal strut S3 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 |  | COMPLETED
2396 | TT_TASK | Backfilling to 0.5m below S2 (+23.5mPD) (1984m3 of soil) | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 |  | COMPLETED
2397 | TT_TASK | Removal strut S2 | Wed Aug 24 08:00:00 IDT 2016 | Fri Aug 26 18:00:00 IDT 2016 | Wed Aug 24 08:00:00 IDT 2016 | Thu Sep 01 18:00:00 IDT 2016 |  | COMPLETED
2398 | TT_TASK | Backfilling to 0.5m below S1 (+28.5mPD) (2480m3 of soil) | Mon Sep 05 08:00:00 IDT 2016 | Tue Sep 20 18:00:00 IDT 2016 | Fri Sep 02 08:00:00 IDT 2016 | Fri Sep 09 18:00:00 IDT 2016 |  | COMPLETED
2399 | TT_TASK | Removal strut S1 | Wed Sep 21 08:00:00 IDT 2016 | Thu Sep 22 18:00:00 IDT 2016 | Sat Sep 10 08:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 |  | COMPLETED
2400 | TT_TASK | Backfilling to original ground level (approx. +31.5mPD) (1488m3 of soil) | Fri Sep 23 08:00:00 IDT 2016 | Mon Oct 03 18:00:00 IDT 2016 | Thu Sep 15 08:00:00 IDT 2016 | Mon Sep 19 18:00:00 IDT 2016 |  | COMPLETED
2402 | TT_TASK | Reinstatement of TUT area (Including Hydroseeding) | Mon Oct 03 08:00:00 IDT 2016 | Mon Jun 19 18:00:00 IDT 2017 | Fri Oct 07 08:00:00 IDT 2016 |  | 216.0 | IN_PROGRESS
25 | TT_TASK | Access opening for the up track cut and cover tunnel at Tse Uk Tsuen Shaft | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 10 18:00:00 IST 2016 |  | COMPLETED
27 | TT_TASK | Close out the temporary access opening at Tse Uk Tsuen Shaft | Thu Mar 10 08:00:00 IST 2016 | Tue Apr 05 18:00:00 IDT 2016 | Thu Feb 11 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
307 | TT_TASK | Position crane for TBM retrieval (down track) | Wed Jul 02 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014 | Sat Aug 02 18:00:00 IDT 2014 |  | COMPLETED
308 | TT_TASK | TBM Break-in and Retrieval (down track) | Mon Aug 04 08:00:00 IDT 2014 | Sat Aug 30 18:00:00 IDT 2014 | Mon Aug 04 08:00:00 IDT 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
309 | TT_TASK | Position crane for TBM retrieval (up track) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 |  | COMPLETED
310 | TT_TASK | TBM Break-in and Retrieval (up track) | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
376 | TT_TASK | Supply Engineer with Survey Equipment [PS41.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
377 | TT_TASK | Provide Engineer with suitably qualified full time Survey Assistant - 4 nos. [PS41.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
378 | TT_TASK | Provide Engineer with site transportation as detailed in PS42.1 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 |  | COMPLETED
379 | TT_TASK | Submit details of qualified drivers to be assigned to the Engineer, for review [PS42.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 |  | COMPLETED
380 | TT_TASK | Install, service and maintain 10 container offices for use by the Engineer's Site Staff | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
381 | TT_TASK | Provide services and equipment for the Engineer | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
383 | TT_TASK | Master Programme - Prepare and submit for approval [GS4.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
384 | TT_TASK | Master Programme - Comments , Resubmission and Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
385 | TT_TASK | Time Chainage Programme - Prepare and submit for approval [GS4.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
386 | TT_TASK | Time Chainage Programme - Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
387 | TT_TASK | Implement and Maintain Programme Management System for 1st Audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
388 | TT_TASK | Implement and Maintain Programme Management System for 2nd Audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
389 | TT_TASK | Implement and Maintain Programme Management System for 3rd Audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
391 | TT_TASK | Environmental Management Plan - Prepare and submit for approval [GS5.1.10] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
392 | TT_TASK | Environmental Management Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
393 | TT_TASK | Quality Plan - Prepare and submit for approval [GS9.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
394 | TT_TASK | Quality Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
395 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 1st audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 |  | COMPLETED
396 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 2nd audit | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
397 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 3rd audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
398 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 4th audit | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
399 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 5th audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
400 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 6th audit | Tue Jul 02 08:00:00 IDT 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
401 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 7th audit | Thu Nov 28 08:00:00 IST 2013 | Thu Jun 05 18:00:00 IDT 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Jan 24 18:00:00 IST 2014 |  | COMPLETED
402 | TT_TASK | Health and Safety Plan - Prepare and submit [G3.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
403 | TT_TASK | System Assurance Plan - Prepare and submit for approval [PS Appendix P3.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
404 | TT_TASK | System Assurance Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
405 | TT_TASK | Design for Safety & Constructability Plan - Prepare and submit for approval [PS37.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
406 | TT_TASK | Design for Safety & Constructability Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
408 | TT_TASK | Methods of Construction - Prepare and submit for approval [GS12.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
409 | TT_TASK | Methods of Construction - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
410 | TT_TASK | Contractor's Submission Schedule - Prepare and submit for approval [GS12.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
411 | TT_TASK | Contractor's Submission Schedule - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
412 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) [PS13.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
413 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) - Approval period | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 |  | COMPLETED
414 | TT_TASK | Spoil Disposal Plan [PS17.7.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
415 | TT_TASK | Waste Management Plan [PS22.10.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
416 | TT_TASK | Independent Checking Engineer - Appoint and submit for approval [PS7.1.8] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
417 | TT_TASK | Independent Checking Engineer - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
418 | TT_TASK | Sub-contract Management Plan - Prepare and submit [PS34.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 |  | COMPLETED
419 | TT_TASK | Schedule of Utilities Services Arrangement [GS7.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
420 | TT_TASK | Site Safety Supervision Plan for Site Formation - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
421 | TT_TASK | Site Safety Supervision Plan for Site Formation - Approval period | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
422 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Prepare and Submit | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
423 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
424 | TT_TASK | Site Safety Supervision Plan for ELS - Prepare and Submit | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
425 | TT_TASK | Site Safety Supervision Plan for ELS - Approval Period | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
426 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Prepare and Submit | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
427 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Approval Period | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
428 | TT_TASK | Noise Management Plan [P22.3.9] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
429 | TT_TASK | Air Quality Management Plan [P22.4.3] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
430 | TT_TASK | Detailed Proposal for Water Pollution Control Measures and Proposed Monitoring [PS22.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
431 | TT_TASK | Groundwater Monitoring and Response Plan [PS22.5.2] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
432 | TT_TASK | Vibration Monitoring Plan [PS22.8.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 |  | COMPLETED
433 | TT_TASK | Proposed Outline TTM Scheme - Prepare & submit to the: Engineer for Review / SLG for Approval [PS19.3] | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 |  | COMPLETED
434 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Proposed TTM Scheme [PS19.4] | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 |  | COMPLETED
435 | TT_TASK | Resubmission of Proposed Outline TTM Scheme (if required) | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
436 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Resubmitted Proposed Outline TTM Scheme [PS19.4] | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 |  | COMPLETED
437 | TT_TASK | Notification Period of the Approved TTM Scheme prior to implementation [PS19.4] | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 |  | COMPLETED
440 | TT_TASK | Initial Site Survey (WA3.11) | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 |  | COMPLETED
441 | TT_TASK | Initial Site Survey Report (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 |  | COMPLETED
442 | TT_TASK | Initial Site Survey & Condition Survey (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
443 | TT_TASK | Initial Site Survey Report (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
444 | TT_TASK | Initial Site Survey & Condition Survey (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
445 | TT_TASK | Initial Site Survey Report (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
446 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 4.9 & 4.12A [PS4.2] | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
447 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 5.1 & 5.3 [PS4.2.3] | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 |  | COMPLETED
448 | TT_TASK | Proposal for Site Clearance Works [PS4.4.1] | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 |  | COMPLETED
449 | TT_TASK | Site Clearance / Site Formation Works (including demolition of EBS) | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
450 | TT_TASK | Backfill existing stream courses in Works Area 4.9, 4.10 and 4.11 [PS18.5.1] | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
451 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and submit to EPD for Approval (WA3.3 - Area M, I, L) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
452 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA3.3 - Area M, I, L) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
453 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
454 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
455 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.3 - Area M, I, L) | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
456 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA3.3 - Area M, I, L) | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
457 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA3.3 - Area M, I, L) | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
458 | TT_TASK | Remediation Report - Approval (WA3.3 - Area M, I, L) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
459 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and Submit to EPD for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
460 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
461 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
462 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.1, 3.2, 3.3, 3.3A) | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
463 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.1, 3.2, 3.3, 3.3A) | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 |  | COMPLETED
464 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 |  | COMPLETED
465 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
466 | TT_TASK | Remediation Report - Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
467 | TT_TASK | Conduct remediation for Area Q in accordance with method proposed in the approved Remediation Action Plan [PS22.9.2] | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 |  | COMPLETED
468 | TT_TASK | Remediation Report - Prepare and submit for Approval [PS22.9.2] (Area Q) | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 |  | COMPLETED
469 | TT_TASK | Remediation Report - Approval (Area Q) | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
470 | TT_TASK | Removal of contaminated soil at North Tunnels (Area N,O,P,Q,R,S) | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
471 | TT_TASK | Condition Survey EBS for presence of Asbestos and gather samples | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
472 | TT_TASK | Testing of gathered samples | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 |  | COMPLETED
473 | TT_TASK | Prepare and submit Asbestos Investigation Report (AIR) & Asbestos Abatement Plan (AAP) | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
474 | TT_TASK | Approval period of AIR & AAP | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
475 | TT_TASK | Notification period to Engineer and EPD prior to Asbestos abatement works | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
476 | TT_TASK | Asbestos abatement works | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
477 | TT_TASK | Demolition of EBS | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
478 | TT_TASK | Confirmation of tree survey | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 |  | COMPLETED
480 | TT_TASK | Installation of ground settlement markers | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 |  | COMPLETED
481 | TT_TASK | Settlement monitoring and submit report | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
482 | TT_TASK | Settlement monitoring and submit report | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 |  | COMPLETED
483 | TT_TASK | Settlement monitoring and submit report | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
484 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
485 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Wed Feb 26 18:00:00 IST 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Feb 21 18:00:00 IST 2014 |  | COMPLETED
486 | TT_TASK | Settlement monitoring and submit report | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 |  | COMPLETED
488 | TT_TASK | Permit Applications (incl. License to Search and Excavate Antiquities and Excavation Permit) | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 |  | COMPLETED
489 | TT_TASK | Check for underground utilities | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 |  | COMPLETED
490 | TT_TASK | Field walking and hand augering | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 |  | COMPLETED
491 | TT_TASK | Excavation of trial pits | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 |  | COMPLETED
492 | TT_TASK | Rescue excavation rescue works (if required) | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 |  | COMPLETED
494 | TT_TASK | Erection of Hoarding with Gate (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 |  | COMPLETED
495 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 3.1, 3.2, 3.3 and 3.3A [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
496 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 4.9, 4.10, 4.11, 4.12A~C, and 4.15 [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
497 | TT_TASK | Project Signboard Erection [PS4.6.8] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
498 | TT_TASK | Marine Survey at Barging Point [PS4.3] (before construction of barging facilities) | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 00:00:00 IST 2010 |  | COMPLETED
499 | TT_TASK | Construct barging facilities | Sat Oct 02 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Oct 02 00:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
500 | TT_TASK | Operation Plan for the Barging Facility - Prepare and Submit for Approval [PS17.1.9] | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
501 | TT_TASK | Operation Plan for the Barging Facility - Review and Approval Period | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 |  | COMPLETED
503 | TT_TASK | General and Special Attendance for Designated Contractors | Mon Dec 02 08:00:00 IST 2013 | Mon Aug 31 18:00:00 IDT 2015 | Tue Jul 02 08:00:00 IDT 2013 | Wed Mar 25 18:00:00 IST 2015 |  | COMPLETED
505 | TT_TASK | Prepare and Submit Detailed Interface Specification | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 |  | COMPLETED
506 | TT_TASK | Approval of Detailed Interface Plan | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
507 | TT_TASK | Prepare and Submit Detailed Interface Specification | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 |  | COMPLETED
508 | TT_TASK | Approval of Detailed Interface Plan | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
510 | TT_TASK | Prepare and Submit Draft Operation and Maintenance Manual [PS33.1] | Mon Aug 24 08:00:00 IDT 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jul 28 08:00:00 IDT 2014 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
511 | TT_TASK | Review and approval period of Draft Operation and Maintenance Manual | Wed Aug 10 08:00:00 IDT 2016 | Tue Sep 13 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
512 | TT_TASK | Prepare and Submit Final Operation and Maintenance Manual [PS33.1] | Wed Sep 14 08:00:00 IDT 2016 | Thu Feb 16 18:00:00 IST 2017 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
513 | TT_TASK | Provide Engineer with As-Built Drawing for the Whole of the Works [PS33.2] | Mon Nov 21 08:00:00 IST 2016 | Wed Dec 14 18:00:00 IST 2016 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
514 | TT_TASK | Provide Engineer with Asset Registration Information [PS33.3] | Fri May 19 08:00:00 IDT 2017 | Mon Jun 12 18:00:00 IDT 2017 |  |  |  | NOT_STARTED
517 | TT_TASK | Preliminary Design Programme - Prepare and Submit for Approval [PS7.1.8 - App. Z2.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
518 | TT_TASK | Preliminary Design Programme - Review and Approval Period [PS7.1.8 - App. Z2.2] | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 |  | COMPLETED
519 | TT_TASK | Preliminary Design Programme - Resubmission and Approval (if required) [PS7.1.8 - App. Z2.2] | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 |  | COMPLETED
520 | TT_TASK | Schedule of Designs - Prepare and Submit for Approval [PS7.1.8 - App. Z2.5] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
521 | TT_TASK | Detailed Proposal for Carrying Out the Cross Passage Works [PS11.5.2] | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
524 | TT_TASK | Design TBM and submit full details to the Engineer [PS7.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
525 | TT_TASK | TBM Design - Approval period | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 |  | COMPLETED
526 | TT_TASK | TBM Design - Resubmission and approval period | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 |  | COMPLETED
528 | TT_TASK | AIP Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
529 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 |  | COMPLETED
530 | TT_TASK | DDS Design - Prepare and Submit | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 |  | COMPLETED
531 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 |  | COMPLETED
532 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 |  | COMPLETED
533 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 |  | COMPLETED
534 | TT_TASK | Issue Completed Working Drawings | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
536 | TT_TASK | AIP Design - Prepare and Submit | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 |  | COMPLETED
537 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 |  | COMPLETED
538 | TT_TASK | AIP Design - Response to comments and Resubmit | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
539 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
540 | TT_TASK | DDS Design - Prepare and Submit | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
541 | TT_TASK | DDS Design - Review and Approval Period (by MTRC & related Government Authorities) | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 |  | COMPLETED
542 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 |  | COMPLETED
543 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 |  | COMPLETED
544 | TT_TASK | Issue Completed Working Drawings | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 |  | COMPLETED
546 | TT_TASK | DDS Design - Prepare and Submit | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 |  | COMPLETED
547 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 |  | COMPLETED
548 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 |  | COMPLETED
549 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 |  | COMPLETED
550 | TT_TASK | Issue Completed Working Drawings | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
552 | TT_TASK | AIP Design - Prepare and Submit | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 |  | COMPLETED
553 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
554 | TT_TASK | AIP Design - Response to comments and Resubmit | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 |  | COMPLETED
555 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
556 | TT_TASK | DDS Design - Prepare and Submit | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 |  | COMPLETED
557 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 |  | COMPLETED
558 | TT_TASK | DDS Design - Response to comments and Resubmit | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 |  | COMPLETED
559 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 |  | COMPLETED
560 | TT_TASK | Issue Completed Working Drawings | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 |  | COMPLETED
562 | TT_TASK | Prepare and Submit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 |  | COMPLETED
563 | TT_TASK | Review and Approval Period | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
564 | TT_TASK | Response to comments and Resubmit | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 |  | COMPLETED
565 | TT_TASK | Review and Approval Period (for resubmission) | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 |  | COMPLETED
568 | TT_TASK | DDS Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
569 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 |  | COMPLETED
570 | TT_TASK | DDS Design - Response to comments and Resubmit | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 |  | COMPLETED
571 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 |  | COMPLETED
572 | TT_TASK | Issue Completed Working Drawings | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
574 | TT_TASK | DDS Design - Prepare and Submit | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 |  | COMPLETED
575 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 |  | COMPLETED
576 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 |  | COMPLETED
577 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 |  | COMPLETED
578 | TT_TASK | Issue Completed Working Drawings | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 |  | COMPLETED
580 | TT_TASK | DDS Design - Prepare and Submit | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 |  | COMPLETED
581 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 |  | COMPLETED
582 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 |  | COMPLETED
583 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 |  | COMPLETED
584 | TT_TASK | Issue Completed Working Drawings | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 |  | COMPLETED
586 | TT_TASK | DDS Design - Prepare and Submit | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 |  | COMPLETED
587 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 |  | COMPLETED
588 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 |  | COMPLETED
589 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 |  | COMPLETED
590 | TT_TASK | Issue Completed Working Drawings | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 |  | COMPLETED
592 | TT_TASK | DDS Design - Prepare and Submit | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 |  | COMPLETED
593 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 |  | COMPLETED
594 | TT_TASK | DDS Design - Response to comments and Resubmit | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 |  | COMPLETED
595 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 |  | COMPLETED
596 | TT_TASK | Issue Completed Working Drawings | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
599 | TT_TASK | Formworks / Falsework - Prepare & Submit | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
600 | TT_TASK | Formworks / Falsework - Review & Approval Period (by MTRC) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
601 | TT_TASK | Formworks / Falsework - Response to comments and Resubmit | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 |  | COMPLETED
602 | TT_TASK | Formworks / Falsework - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
605 | TT_TASK | Layout of Site Hoarding - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
606 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (by MTRC) | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
607 | TT_TASK | Layout of Site Hoarding - Response to comments and Resubmit | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
608 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 |  | COMPLETED
610 | TT_TASK | Layout of Engineer's Accommodation - Prepare and Submit | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
611 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (by MTRC) | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 |  | COMPLETED
612 | TT_TASK | Layout of Engineer's Accommodation - Response to comments and Resubmit | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
613 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (for resubmit) (by MTRC & related Government Authorities | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
615 | TT_TASK | TTMS Assessment Report - Prepare and Submit | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 |  | COMPLETED
616 | TT_TASK | TTMS Assessment Report - Review and Approval Period (by MTRC) | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
617 | TT_TASK | TTMS Assessment Report - Response to comments and Resubmit | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 |  | COMPLETED
618 | TT_TASK | TTMS Assessment Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
619 | TT_TASK | Issue Completed Working Drawings | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 |  | COMPLETED
621 | TT_TASK | DIA Report - Prepare and Submit | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 |  | COMPLETED
622 | TT_TASK | DIA Report - Review and Approval Period (by MTRC) | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 |  | COMPLETED
623 | TT_TASK | DIA Report - Response to comments and Resubmit | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 |  | COMPLETED
624 | TT_TASK | DIA Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
625 | TT_TASK | Issue Completed Working Drawings | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 |  | COMPLETED
627 | TT_TASK | AIP Design - Prepare & Submit | Wed Sep 23 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 |  | COMPLETED
628 | TT_TASK | AIP Design - Review & Approval Period (by MTR) | Wed Oct 14 08:00:00 IDT 2015 | Wed Nov 11 18:00:00 IST 2015 | Mon Jun 08 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
629 | TT_TASK | AIP Design - Response to comments and Resubmit | Thu Nov 12 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Mon Jun 15 01:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
630 | TT_TASK | AIP Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jun 22 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
631 | TT_TASK | DDS Design - Prepare & Submit | Wed Jan 13 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Tue Sep 01 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 |  | COMPLETED
632 | TT_TASK | DDS Design - Review & Approval Period (by MTRC) | Fri Feb 26 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 12 18:00:00 IDT 2015 |  | COMPLETED
633 | TT_TASK | DDS Design - Response to comments & Resubmit | Tue Mar 29 08:00:00 IDT 2016 | Fri Apr 01 18:00:00 IDT 2016 | Mon Sep 14 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
634 | TT_TASK | DDS Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Apr 02 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 | Mon Sep 21 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
635 | TT_TASK | Issue Completed Working Drawings | Wed Jan 27 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
637 | TT_TASK | Layout of Barging Point - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
638 | TT_TASK | Layout of Barging Point - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
639 | TT_TASK | Layout of Barging Point - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
640 | TT_TASK | Layout of Barging Point - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
641 | TT_TASK | Loading Ramps - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
642 | TT_TASK | Loading Ramps - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
643 | TT_TASK | Loading Ramps - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
644 | TT_TASK | Loading Ramps - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
645 | TT_TASK | Weighbridge - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
646 | TT_TASK | Weighbridge - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
647 | TT_TASK | Weighbridge - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
648 | TT_TASK | Weighbridge - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
652 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
653 | TT_TASK | Pre-drill and guide wall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
654 | TT_TASK | D-wall construction (1084m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
655 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
656 | TT_TASK | Wang Toi Shan Shan Tsuen Road diversion works | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 |  | COMPLETED
658 | TT_TASK | Excavate up to +10.5mPD (369m3) | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 |  | COMPLETED
659 | TT_TASK | Install Strut S0 +11.0mPD | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 |  | COMPLETED
660 | TT_TASK | Excavate up to +8.0mPD (1525m3) | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 |  | COMPLETED
661 | TT_TASK | Install Strut S1 +8.5mPD | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 |  | COMPLETED
662 | TT_TASK | Excavate up to +4.5mPD (2135m3) | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 |  | COMPLETED
663 | TT_TASK | Install Strut S2 +5.0mPD | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 |  | COMPLETED
664 | TT_TASK | Excavate up to +0.5mPD (2440m3) | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 |  | COMPLETED
665 | TT_TASK | Install Strut S3 +1.0mPD | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 |  | COMPLETED
666 | TT_TASK | Excavate up to -6.5mPD (4340m3) | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 |  | COMPLETED
667 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
668 | TT_TASK | Construction of temporary slab and entrance seal (622m3) | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
672 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 08 18:00:00 IST 2014 | Fri Dec 05 08:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
673 | TT_TASK | Erect external formwork (Base Slab) | Tue Dec 09 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 08 08:00:00 IST 2014 | Tue Dec 09 18:00:00 IST 2014 |  | COMPLETED
674 | TT_TASK | Rebar fixing (Base Slab) | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 18:00:00 IST 2014 | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
675 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Dec 15 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Mon Dec 15 18:00:00 IST 2014 |  | COMPLETED
676 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Dec 17 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Tue Dec 16 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 |  | COMPLETED
677 | TT_TASK | Curing (Base Slab) | Thu Dec 18 08:00:00 IST 2014 | Sat Dec 27 18:00:00 IST 2014 | Wed Dec 17 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
678 | TT_TASK | Removal of formwork (Base Slab) | Fri Dec 19 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 24 18:00:00 IST 2014 |  | COMPLETED
679 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
680 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 | Mon Jun 22 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 |  | COMPLETED
681 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Jun 13 08:00:00 IDT 2015 | Mon Jun 15 18:00:00 IDT 2015 | Thu Jun 25 01:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
682 | TT_TASK | Concreting (Wall & Roof) (444m3) | Tue Jun 16 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
683 | TT_TASK | Curing (Wall & Roof) | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
684 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 |  | COMPLETED
685 | TT_TASK | Removal external formwork (Wall) | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
686 | TT_TASK | Side walkway and cable bracket (360m3) | Sat Jul 18 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Sat Jul 18 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
687 | TT_TASK | Access opening to DC (DC access period) | Tue Oct 06 08:00:00 IDT 2015 | Fri Mar 04 18:00:00 IST 2016 | Tue Oct 06 08:00:00 IDT 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
688 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Sat Dec 12 08:00:00 IST 2015 | Mon Jan 18 18:00:00 IST 2016 | Tue Nov 03 00:00:00 IST 2015 | Mon Nov 30 18:00:00 IST 2015 |  | COMPLETED
690 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 | Tue Apr 12 08:00:00 IDT 2016 | Wed Apr 13 18:00:00 IDT 2016 |  | COMPLETED
691 | TT_TASK | Erect external formwork (Base Slab) | Mon May 23 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Thu Apr 14 08:00:00 IDT 2016 | Fri Apr 15 18:00:00 IDT 2016 |  | COMPLETED
692 | TT_TASK | Rebar fixing (Base Slab) | Wed May 25 08:00:00 IDT 2016 | Fri May 27 18:00:00 IDT 2016 | Sat Apr 16 08:00:00 IDT 2016 | Tue Apr 19 18:00:00 IDT 2016 |  | COMPLETED
693 | TT_TASK | Erect internal kicker formwork (Base Slab) | Sat May 28 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 | Wed Apr 20 08:00:00 IDT 2016 | Thu Apr 21 18:00:00 IDT 2016 |  | COMPLETED
694 | TT_TASK | Concreting (Base Slab) (225m3) | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 | Fri Apr 22 08:00:00 IDT 2016 | Fri Apr 22 18:00:00 IDT 2016 |  | COMPLETED
695 | TT_TASK | Curing (Base Slab) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 08 18:00:00 IDT 2016 | Sat Apr 23 08:00:00 IDT 2016 | Fri Apr 29 18:00:00 IDT 2016 |  | COMPLETED
696 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Sat Apr 30 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
697 | TT_TASK | Removal of formwork (Base Slab) | Tue May 24 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Mon May 09 08:00:00 IDT 2016 | Tue May 10 18:00:00 IDT 2016 |  | COMPLETED
698 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed May 25 08:00:00 IDT 2016 | Sat May 28 18:00:00 IDT 2016 | Wed May 11 08:00:00 IDT 2016 | Mon May 16 18:00:00 IDT 2016 |  | COMPLETED
699 | TT_TASK | Rebar fixing (Wall & Roof) | Mon May 30 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 17 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 |  | COMPLETED
700 | TT_TASK | Erect external formwork (Wall & Roof) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 03 18:00:00 IDT 2016 | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 |  | COMPLETED
701 | TT_TASK | Concreting (Wall & Roof) (444m3) | Sat Jun 04 08:00:00 IDT 2016 | Sat Jun 04 18:00:00 IDT 2016 | Mon May 23 08:00:00 IDT 2016 | Mon May 23 18:00:00 IDT 2016 |  | COMPLETED
702 | TT_TASK | Curing (Wall & Roof) | Mon Jun 06 08:00:00 IDT 2016 | Tue Jun 14 18:00:00 IDT 2016 | Tue May 24 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 |  | COMPLETED
703 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 15 08:00:00 IDT 2016 | Wed Jun 15 18:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 |  | COMPLETED
704 | TT_TASK | Removal external formwork (Wall) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
705 | TT_TASK | Side walkway and cable bracket (102m3) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 |  | COMPLETED
706 | TT_TASK | Access opening to DC (DC access period) | Sat Jun 18 08:00:00 IDT 2016 | Thu Jul 14 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
707 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Fri Jul 15 08:00:00 IDT 2016 | Wed Aug 17 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
709 | TT_TASK | Backfilling between tunnels (2000m3) | Thu Sep 01 08:00:00 IDT 2016 | Sat Sep 17 18:00:00 IDT 2016 | Tue Sep 13 08:00:00 IDT 2016 | Fri Sep 30 18:00:00 IDT 2016 |  | COMPLETED
710 | TT_TASK | Remove Strut S2 | Mon Oct 03 08:00:00 IDT 2016 | Wed Oct 05 18:00:00 IDT 2016 | Mon Oct 03 08:00:00 IDT 2016 | Tue Oct 11 18:00:00 IDT 2016 |  | COMPLETED
711 | TT_TASK | Backfilling up top S1 Soffit | Thu Oct 06 08:00:00 IDT 2016 | Fri Oct 21 18:00:00 IDT 2016 | Fri Oct 28 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
712 | TT_TASK | Remove Strut S1 | Sat Oct 22 08:00:00 IDT 2016 | Mon Oct 24 18:00:00 IDT 2016 | Tue Oct 11 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
713 | TT_TASK | Backfilling up top S0 Soffit | Mon Nov 07 08:00:00 IST 2016 | Sat Nov 12 18:00:00 IST 2016 | Tue Nov 01 08:00:00 IST 2016 | Sat Nov 05 18:00:00 IST 2016 |  | COMPLETED
714 | TT_TASK | Remove Strut S0 | Mon Nov 14 08:00:00 IST 2016 | Tue Nov 15 18:00:00 IST 2016 | Mon Nov 07 08:00:00 IST 2016 | Tue Nov 08 18:00:00 IST 2016 |  | COMPLETED
715 | TT_TASK | Backfilling up to ground level | Wed Nov 16 08:00:00 IST 2016 | Fri Nov 18 18:00:00 IST 2016 | Wed Nov 09 08:00:00 IST 2016 | Fri Nov 11 18:00:00 IST 2016 |  | COMPLETED
719 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
720 | TT_TASK | Pre-drilling and guidewall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
721 | TT_TASK | D-wall construction (1451m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
722 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 |  | COMPLETED
724 | TT_TASK | Excavate from ground level to formation level -5.5mPD (4559m3) | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 |  | COMPLETED
725 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 |  | COMPLETED
726 | TT_TASK | Placing of blinding layer (South Bound) | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 |  | COMPLETED
727 | TT_TASK | Placing of blinding layer (North Bound) | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
729 | TT_TASK | Construction of Bay 2 to Bay 7a (3565m3) | Mon Jun 04 08:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 | Mon Jun 04 18:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 |  | COMPLETED
730 | TT_TASK | Side walkway and cable bracket (Southbound) | Fri Oct 02 08:00:00 IDT 2015 | Fri Nov 06 18:00:00 IST 2015 | Fri Oct 02 08:00:00 IDT 2015 | Sat Oct 31 18:00:00 IST 2015 |  | COMPLETED
731 | TT_TASK | Side walkway and cable bracket (Northbound) | Tue May 03 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 |  | COMPLETED
733 | TT_TASK | Backfilling (1344m3) | Wed Nov 07 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 | Wed Nov 07 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
736 | TT_TASK | Scheme Design, Mobilization, Site set up & Material delivery and Instrumentations | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
737 | TT_TASK | Downstream pipe pile wall construction (45 nos.) and grout curtain (45 nos.) | Mon Nov 12 08:00:00 IST 2012 | Fri Jan 25 18:00:00 IST 2013 | Mon Nov 12 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
738 | TT_TASK | Curtain Grout for cut slope (120 nos.) | Fri Jul 26 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
739 | TT_TASK | Drilling for ground improvement only (if require) | Mon Dec 10 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
740 | TT_TASK | If settlement reach the AAA alarm & action level TAM grouting will apply during excavation | Thu Apr 11 08:00:00 IDT 2013 | Thu May 16 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
741 | TT_TASK | Erection of temporary working platform for Up stream and Installation of Instrumentation System | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
742 | TT_TASK | Upstream pipe pile wall construction adjacent to WTSSTR, (17nos.) | Thu Dec 27 08:00:00 IST 2012 | Mon Jan 28 18:00:00 IST 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
743 | TT_TASK | Upstream pipe pile wall construction at Kam Tin River, 15m depth, 42nos. 1drill rig) | Tue Jan 29 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
744 | TT_TASK | Excavation and soil nail installation | Tue Apr 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
745 | TT_TASK | Excavation for rock and blinding layer | Sat Aug 24 08:00:00 IDT 2013 | Sat Sep 28 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
750 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
751 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
752 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
753 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
754 | TT_TASK | Concreting (164m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
755 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
756 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
757 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
758 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
759 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
760 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
761 | TT_TASK | Concreting (242m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
762 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
763 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
764 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
765 | TT_TASK | Removal internal falsework and formwork for roof | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
766 | TT_TASK | Side walkway and cable bracket (19m3) | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
770 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
771 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
772 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
773 | TT_TASK | Erect internal kicker formwork | Thu Nov 28 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 09 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
774 | TT_TASK | Concreting (121m3) | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
775 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
776 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
777 | TT_TASK | Removal of formwork | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
778 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
779 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
780 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
781 | TT_TASK | Concreting (121m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
782 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
783 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
784 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
785 | TT_TASK | Removal internal falsework and formwork for roof | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
786 | TT_TASK | Side walkway and cable bracket (38m3) | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
788 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
789 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
790 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
791 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
792 | TT_TASK | Concreting (240m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
793 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
794 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
795 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
796 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
797 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
798 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
799 | TT_TASK | Concreting (240m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
800 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
801 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
802 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
803 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
804 | TT_TASK | Side walkway and cable bracket | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
806 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
807 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
808 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
809 | TT_TASK | Concreting (222m3) | Wed Nov 06 08:00:00 IST 2013 | Wed Nov 06 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
810 | TT_TASK | Curing | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
811 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
812 | TT_TASK | Removal of formwork | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
815 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
816 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
817 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
818 | TT_TASK | Erect internal kicker formwork | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
819 | TT_TASK | Concreting (111m3) | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
820 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
821 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
822 | TT_TASK | Removal of formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
823 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
824 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
825 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
826 | TT_TASK | Concreting (220m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
827 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
828 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
829 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
830 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
831 | TT_TASK | Side walkway and cable bracket (38m3) | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 |  | COMPLETED
833 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
834 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
835 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
836 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
837 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
838 | TT_TASK | Curing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
839 | TT_TASK | Preparation of construction joint for base slab | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
840 | TT_TASK | Removal of formwork | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
841 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
842 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
843 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
844 | TT_TASK | Concreting (327m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
845 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
846 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
847 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
848 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
849 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
851 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 20 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
852 | TT_TASK | Rebar fixing | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
853 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 08:00:00 IDT 2013 |  | COMPLETED
854 | TT_TASK | Concreting (225m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
855 | TT_TASK | Curing | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
856 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
857 | TT_TASK | Removal of formwork | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
860 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 27 08:00:00 IST 2013 | Wed Nov 27 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
861 | TT_TASK | Erect external formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
862 | TT_TASK | Rebar fixing | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
863 | TT_TASK | Erect internal kicker formwork | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
864 | TT_TASK | Concreting (222m3) | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
865 | TT_TASK | Curing | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Mon Oct 28 18:00:00 IST 2013 |  | COMPLETED
866 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
867 | TT_TASK | Removal of formwork | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
868 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
869 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
870 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
871 | TT_TASK | Concreting (222m3) | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 |  | COMPLETED
872 | TT_TASK | Curing | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 07 18:00:00 IST 2014 |  | COMPLETED
873 | TT_TASK | Preparation of construction joint for wall and roof | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
874 | TT_TASK | Removal external and internal formwork for wall | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
875 | TT_TASK | Removal internal falsework and formwork for roof | Mon Feb 10 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
876 | TT_TASK | Side walkway and cable bracket (38m3) | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 |  | COMPLETED
878 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
879 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
880 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
881 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
882 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
883 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
884 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
885 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
886 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
887 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
888 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
889 | TT_TASK | Concreting (222m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
890 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
892 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
893 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
894 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
896 | TT_TASK | Placing of waterproof member T-lock & testing | Mon Nov 18 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
897 | TT_TASK | Rebar fixing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Wed Oct 23 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
898 | TT_TASK | Erect external formwork | Fri Nov 22 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
899 | TT_TASK | Concreting (222m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
900 | TT_TASK | Curing | Tue Nov 26 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
901 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
902 | TT_TASK | Removal of formwork | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
905 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
906 | TT_TASK | Erect external formwork | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
907 | TT_TASK | Rebar fixing | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
908 | TT_TASK | Erect internal kicker formwork | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
909 | TT_TASK | Concreting (330m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
910 | TT_TASK | Curing | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
911 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
912 | TT_TASK | Removal of formwork | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
913 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
914 | TT_TASK | Rebar fixing | Wed Nov 20 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
915 | TT_TASK | Erect external formwork | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
916 | TT_TASK | Concreting (330m3) | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
917 | TT_TASK | Curing | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
918 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
919 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
920 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
921 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
923 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
924 | TT_TASK | Erect external formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
925 | TT_TASK | Rebar fixing | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
926 | TT_TASK | Erect internal kicker formwork | Wed Dec 04 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
927 | TT_TASK | Concreting (240m3) | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
928 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
929 | TT_TASK | Preparation of construction joint for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
930 | TT_TASK | Removal of formwork | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
931 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
932 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
933 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
934 | TT_TASK | Concreting (240m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
935 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
936 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
937 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
938 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
939 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
941 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
942 | TT_TASK | Rebar fixing | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
943 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
944 | TT_TASK | Concreting (240m3) | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
945 | TT_TASK | Curing | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
946 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
947 | TT_TASK | Removal of formwork | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
950 | TT_TASK | Placing of waterproof member T-lock & testing | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
951 | TT_TASK | Erect external formwork | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
952 | TT_TASK | Rebar fixing | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
953 | TT_TASK | Erect internal kicker formwork | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
954 | TT_TASK | Concreting (200m3) | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
955 | TT_TASK | Curing | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
956 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
957 | TT_TASK | Removal of formwork | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
958 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 29 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
959 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
960 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
961 | TT_TASK | Concreting (200m3) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
962 | TT_TASK | Curing | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
963 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
964 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 13 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
965 | TT_TASK | Removal internal falsework and formwork for roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
966 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 |  | COMPLETED
968 | TT_TASK | Placing of waterproof member T-lock & testing | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
969 | TT_TASK | Erect external formwork | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
970 | TT_TASK | Rebar fixing | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
971 | TT_TASK | Erect internal kicker formwork | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
972 | TT_TASK | Concreting (220m3) | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
973 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
974 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
975 | TT_TASK | Removal of formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
976 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
977 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
978 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
979 | TT_TASK | Concreting (220m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
980 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
981 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
982 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
983 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
984 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
986 | TT_TASK | Placing of waterproof member T-lock & testing | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
987 | TT_TASK | Rebar fixing | Mon Nov 25 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
988 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
989 | TT_TASK | Concreting (222m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
990 | TT_TASK | Curing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
991 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
992 | TT_TASK | Removal of formwork | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
994 | TT_TASK | Removal of Temporary Nullah | Sat Mar 01 08:00:00 IST 2014 | Sat Jun 21 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
995 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (5218m3) | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 |  | COMPLETED
996 | TT_TASK | Reinstate the permenant Retaining wall of Nullah | Sat Mar 01 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Tue Mar 04 08:00:00 IST 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
997 | TT_TASK | Reinstate Nullah Base of original route | Tue Feb 25 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Tue Feb 25 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
998 | TT_TASK | Reinstate Nullah to original route | Sat Mar 29 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Sat Mar 29 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
999 | TT_TASK | Construction & connect East Box Culvert from Box 6B to KTR | Mon Apr 14 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Mon Feb 10 08:00:00 IST 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
1000 | TT_TASK | Reinstatement of Wang Toi Shan Shan Tsuen Road | Tue Dec 01 08:00:00 IST 2015 | Wed Jul 13 18:00:00 IDT 2016 | Tue Dec 01 08:00:00 IST 2015 | Mon Jul 18 18:00:00 IDT 2016 |  | COMPLETED
1003 | TT_TASK | Pre-drilling at Works Area 4.4 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
1004 | TT_TASK | Site Setup and guide wall | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1005 | TT_TASK | D-wall construction (3104m3) | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 |  | COMPLETED
1006 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
1008 | TT_TASK | Excavate up to +8.0mPD (775m3) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1009 | TT_TASK | Install Strut S1 +8.5mPD | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 |  | COMPLETED
1010 | TT_TASK | Excavate up to +4.5mPD (2713m3) | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 |  | COMPLETED
1011 | TT_TASK | Install Strut S2 +5.0mPD | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
1012 | TT_TASK | Excavate up to +0.5mPD (3100m3) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 |  | COMPLETED
1013 | TT_TASK | Install Strut S3 +1.0mPD | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1014 | TT_TASK | Excavate up to -3.0mPD (2713m3) | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1015 | TT_TASK | Install Strut S4 -2.5mPD | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 |  | COMPLETED
1016 | TT_TASK | Excavate up to -5.5mPD (4952m3) | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1017 | TT_TASK | Placing of blinding layer | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1021 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1022 | TT_TASK | Erect external formwork for base slab | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1023 | TT_TASK | Rebar fixing for base slab | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1024 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 26 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1025 | TT_TASK | Concreting for base slab (350m3) | Thu Jun 27 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1026 | TT_TASK | Curing for base slab | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1027 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1028 | TT_TASK | Removal of formwork for base slab | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1029 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1030 | TT_TASK | Removal strut S4 and S3 | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1032 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1033 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1034 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1035 | TT_TASK | Concreting for wall and roof (489m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1036 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1037 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1038 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1039 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1040 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1043 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1044 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1045 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1046 | TT_TASK | Curing for wall and roof | Sat Jun 22 08:00:00 IDT 2013 | Mon Jul 01 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1047 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1048 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1050 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Tue Dec 17 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1053 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1054 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1055 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1056 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1057 | TT_TASK | Concreting for base slab (350m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1058 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1059 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1060 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1061 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1062 | TT_TASK | Removal strut S4 and S3 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1064 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1065 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1066 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1067 | TT_TASK | Concreting for wall and roof (489m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1068 | TT_TASK | Curing for wall and roof | Wed Jun 12 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1069 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1070 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 14 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1071 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1072 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Feb 13 08:00:00 IST 2014 | Tue Feb 18 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1074 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1075 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1076 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1077 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1078 | TT_TASK | Curing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1079 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1080 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1081 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1082 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 16 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1084 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (2343m3) | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1085 | TT_TASK | Placing 0.5m thk concrete lateral support (+3.96mPD) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1086 | TT_TASK | Removal strut S2 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 23 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1088 | TT_TASK | Construction of Temporary Culvert (open channel) | Tue Jun 25 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1089 | TT_TASK | Temporary box culvert (At Box 6B Area) Saw Cut D-wall | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 |  | COMPLETED
1090 | TT_TASK | Erect 3m high block wall | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 |  | COMPLETED
1091 | TT_TASK | Connection to East Box Culvert (823B portion) | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 |  | COMPLETED
1092 | TT_TASK | Blinding | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
1093 | TT_TASK | Temporary box culvert (Outside Box 6B Area) Sheet piling | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 |  | COMPLETED
1094 | TT_TASK | ELS Works | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
1095 | TT_TASK | Blinding | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
1096 | TT_TASK | Removal of Temporary Culvert and Reinstatement | Fri May 16 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
1098 | TT_TASK | Reinstatement of TOA's | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 |  |  | IN_PROGRESS
1099 | TT_TASK | Hydroseeding works | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 | Wed Nov 30 18:00:00 IST 2016 |  | COMPLETED
1100 | TT_TASK | Tree Planting works | Thu Sep 01 08:00:00 IDT 2016 | Sat Dec 03 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
1101 | TT_TASK | Woodland Shrub Mix | Thu Sep 01 08:00:00 IDT 2016 | Fri Nov 18 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  | 200.0 | IN_PROGRESS
1104 | TT_TASK | Kam Tin River Diversion (Stage 1-3) | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1106 | TT_TASK | Concrete fill up to +8.0mPD near side A mass concrete wall | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 |  | COMPLETED
1107 | TT_TASK | Construction of mass concrete wall to +8.0mPD at side A (4 bay CH A80~A120) | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1108 | TT_TASK | Construction of base slab lining and low flow channel (4 bay A9~A10, B8~B9; LFC CH 80~110) | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1109 | TT_TASK | Construction of mass concrete wall to +8.0mPD of side B (3 bay CH B60~B90) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1110 | TT_TASK | Construction of T-shaped retaining wall (1 Bay CH B50~B60) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1111 | TT_TASK | Soil backfill at side A from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1112 | TT_TASK | Concrete backfill at side B from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1113 | TT_TASK | Removal strut at +8.5mPD near side A | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1114 | TT_TASK | Concrete fill up to +11.0mPD near side A mass concrete wall | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1115 | TT_TASK | Placing concrete block at side A from +8.0mPD to +11.0mpd at side A (4 bay CH A80~A120) | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1116 | TT_TASK | Soil backfill at side A from +8.0mPD to +11.0mPD | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1117 | TT_TASK | Removal strut at +8.5mPD near side B | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1118 | TT_TASK | Placing concrete block at side B from +8.0mPD to +11.0mPD (4 bay CH B60~B90) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1119 | TT_TASK | Concrete backfill at side B from +8.0mPD to +11.0mPD | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1121 | TT_TASK | Placing temporary concrete block to Up stream at CH30 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 |  | COMPLETED
1122 | TT_TASK | Placing temporary concrete block to Up stream at CH160 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1123 | TT_TASK | Excavation from GL to FL +5.0mPD Up stream (Low flow channel CH 30~60) | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1124 | TT_TASK | Excavation from GL to FL +5.0mPD Down stream (Low flow channel CH 130~160) | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1125 | TT_TASK | Construction of T-shaped retaining wall at Up stream of side B (2 Bay CH B30~B50) | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1126 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (3 bay CH B90~B120) | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1127 | TT_TASK | Construction of Up stream base slab lining and low flow channel (6 Bay A1~A4, B3~B4; Low flow channel CH 30~50) | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1128 | TT_TASK | Construction of Down stream base slab lining and low flow channel (5 Bay A14~A16, B14~B15; LFC CH 140~170) | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1129 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Up stream and saw cut D-wall | Fri Jun 14 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1130 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Down stream and saw cut D-wall | Wed Jun 19 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1131 | TT_TASK | Construction of remaining Up stream base slab lining and low flow channel (7 bay A5~A8, B5~B7; LFC CH 50~80) | Thu Jun 27 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1132 | TT_TASK | Construction of remaining Down stream base slab lining and low flow channel (7 bay A11~A13, B10~B13; LFC CH 110~140) | Wed Jul 03 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1134 | TT_TASK | Relocation of temporary concrete block at Up stream for construction of mass concrete wall at side B | Sat Jul 20 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1135 | TT_TASK | Relocation of temporary concrete block at Down stream for construction of mass concrete wall at side B | Tue Jul 23 08:00:00 IDT 2013 | Wed Jul 24 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1136 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Up stream of side B (3 bay CH B0~B30) | Tue Jul 23 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1137 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (4 bay CH B0~B30) | Thu Jul 25 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1141 | TT_TASK | Application of power supply, environmental permits and construction substation | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1142 | TT_TASK | Procurement and Confirmation of the order of 1st tunnel boring machine | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 |  | COMPLETED
1143 | TT_TASK | Prepare on-demand bond or bank guarantee for the procurement of TBM and submit to Engineer for approval | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 |  | COMPLETED
1144 | TT_TASK | TBM design and submission for approval | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
1145 | TT_TASK | TBM materials order and delivery to factory | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 |  | COMPLETED
1146 | TT_TASK | TBM equipments order and delivery to factory | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 |  | COMPLETED
1147 | TT_TASK | TBM Fabrication | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
1148 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 |  | COMPLETED
1149 | TT_TASK | TBM test Run | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 |  | COMPLETED
1150 | TT_TASK | TBM disassembly and packing for shipping to HK | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 |  | COMPLETED
1151 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
1152 | TT_TASK | Ground treatment for TBM lanching shaft | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 |  | COMPLETED
1153 | TT_TASK | Ground treatment for Cross Passage Tunnel | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1154 | TT_TASK | Box7A Setup TBM facilities, install noise enclosure and CNP application | Fri Jun 01 08:00:00 IDT 2012 | Sat Jan 26 18:00:00 IST 2013 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1155 | TT_TASK | Notice to Contract 824 the anticipated dates of break out TBM Shaft | Sat Jun 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1156 | TT_TASK | Fabrication of tunnel segment mould | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
1157 | TT_TASK | Fabrication 50% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1158 | TT_TASK | Fabrication 100% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
1159 | TT_TASK | Fabrication 30% of North Tunnel North Bound (Uptrack) Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1160 | TT_TASK | Fabrication 60% of North Tunnel North Bound (Uptrack) Precast Lining | Thu Oct 18 08:00:00 IST 2012 | Thu Feb 21 18:00:00 IST 2013 | Thu Oct 18 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1161 | TT_TASK | Fabrication 100% of North Tunnel North Bound (Uptrack) Precast Lining | Mon Aug 19 08:00:00 IDT 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Dec 03 08:00:00 IST 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1163 | TT_TASK | Assemble, T&C of TBM | Fri Jun 01 08:00:00 IDT 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Oct 16 00:00:00 IST 2012 |  | COMPLETED
1164 | TT_TASK | TBM drive & lining installation CH123+369 to CH123+283 Initial Drive (86m) | Sat Nov 03 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 | Wed Oct 17 00:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1165 | TT_TASK | Change Plant (Back-up cars) | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1166 | TT_TASK | TBM drive & lining installation CH123+283 to CH123+183 | Thu Jun 27 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1167 | TT_TASK | TBM drive & lining installation CH123+183 to CH123+083 | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1168 | TT_TASK | TBM drive & lining installation CH123+083 to CH122+983 | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1169 | TT_TASK | TBM drive & lining installation CH122+983 to CH122+883 | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1170 | TT_TASK | TBM drive & lining installation CH122+883 to CH122+783 | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Jun 13 08:00:00 IDT 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
1171 | TT_TASK | TBM drive & lining installation CH122+783 to CH122+683 | Sat Nov 02 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1172 | TT_TASK | TBM drive & lining installation CH122+683 to CH122+583 | Tue Dec 03 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Wed Feb 26 18:00:00 IST 2014 |  | COMPLETED
1173 | TT_TASK | TBM drive & lining installation CH122+583 to CH122+491 | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Feb 27 08:00:00 IST 2014 | Sat Aug 16 00:00:00 IDT 2014 |  | COMPLETED
1174 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1175 | TT_TASK | Dis-assemble TBM | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
1176 | TT_TASK | Invert slab, side walkway | Sat Oct 04 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 | Mon Sep 15 08:00:00 IDT 2014 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1177 | TT_TASK | Installation of cable bracket | Tue Dec 30 08:00:00 IST 2014 | Tue Jan 13 18:00:00 IST 2015 | Fri Sep 12 08:00:00 IDT 2014 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
1178 | TT_TASK | Provision of assess open for DC and modify of strut S1 and S2 at north bound | Tue Nov 04 11:12:00 IST 2014 | Thu Dec 04 11:12:00 IST 2014 | Wed Oct 01 08:00:00 IDT 2014 | Sat Oct 18 18:00:00 IDT 2014 |  | COMPLETED
1180 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Oct 06 13:00:00 IDT 2014 | Mon Oct 20 12:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
1181 | TT_TASK | Assemble, T&C of TBM | Mon Nov 03 08:00:00 IST 2014 | Fri Jan 02 18:00:00 IST 2015 | Sat Oct 04 08:00:00 IDT 2014 | Fri Nov 28 18:00:00 IST 2014 |  | COMPLETED
1182 | TT_TASK | Setup back-up plant for final drive | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
1183 | TT_TASK | Reinstate of noise enclosure | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Sat Nov 29 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1184 | TT_TASK | TBM drive & lining installation CH123+384 to CH123+284 (Initial Drive) | Sat Dec 06 08:00:00 IST 2014 | Thu Jan 22 18:00:00 IST 2015 | Tue Dec 02 00:00:00 IST 2014 | Tue Jan 20 18:00:00 IST 2015 |  | COMPLETED
1185 | TT_TASK | TBM drive & lining installation CH123+184 to CH123+084 | Wed Jan 21 08:00:00 IST 2015 | Wed Jan 28 18:00:00 IST 2015 | Wed Jan 21 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 |  | COMPLETED
1186 | TT_TASK | TBM drive & lining installation CH123+084 to CH122+984 | Wed Feb 04 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 | Thu Feb 12 08:00:00 IST 2015 | Thu Feb 26 18:00:00 IST 2015 |  | COMPLETED
1187 | TT_TASK | TBM drive & lining installation CH122+984 to CH122+884 | Thu Feb 12 08:00:00 IST 2015 | Tue Feb 24 18:00:00 IST 2015 | Fri Feb 27 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1188 | TT_TASK | TBM drive & lining installation CH122+884 to CH122+784 | Tue Mar 10 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Wed May 27 18:00:00 IDT 2015 |  | COMPLETED
1189 | TT_TASK | TBM drive & lining installation CH122+784 to CH122+684 | Wed May 06 08:00:00 IDT 2015 | Thu May 14 18:00:00 IDT 2015 | Thu May 28 08:00:00 IDT 2015 | Sat Jul 11 18:00:00 IDT 2015 |  | COMPLETED
1190 | TT_TASK | TBM drive & lining installation CH122+684 to CH122+584 | Fri Jul 03 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
1191 | TT_TASK | TBM drive & lining installation CH122+584 to CH122+506 | Tue Nov 03 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 |  | COMPLETED
1192 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 |  | COMPLETED
1193 | TT_TASK | Dis-assemble TBM | Wed Dec 16 08:00:00 IST 2015 | Fri Jan 22 18:00:00 IST 2016 | Sun Dec 13 08:00:00 IST 2015 | Sun Mar 13 18:00:00 IST 2016 |  | COMPLETED
1194 | TT_TASK | Invert slab, side walkway | Fri Apr 01 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 | Mon Mar 14 08:00:00 IST 2016 | Tue May 24 18:00:00 IDT 2016 |  | COMPLETED
1195 | TT_TASK | Installation of cable bracket | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Mar 15 18:00:00 IST 2016 |  | COMPLETED
1196 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Mon Feb 01 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 22 18:00:00 IST 2016 |  | COMPLETED
1199 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 1 (From Downtrack to Centre of CP) | Thu Apr 10 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Sat Jun 28 18:00:00 IDT 2014 |  | COMPLETED
1200 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Sun Nov 09 18:00:00 IST 2014 |  | COMPLETED
1201 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1202 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 18:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1203 | TT_TASK | Excavation 0-4mts with Shotcrete | Mon Feb 02 08:00:00 IST 2015 | Tue Feb 17 18:00:00 IST 2015 | Mon Feb 23 08:00:00 IST 2015 | Mon Mar 30 18:00:00 IDT 2015 |  | COMPLETED
1204 | TT_TASK | Invert Concrete | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1205 | TT_TASK | Wall and Roof concrete | Thu Apr 16 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 |  | COMPLETED
1206 | TT_TASK | Dismantle Temporary frame | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 |  | COMPLETED
1207 | TT_TASK | Install Door to Cross Passage (By contract 827) | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 |  | COMPLETED
1208 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 2 (From Centre of CP to Uptrack) | Sat Oct 17 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Sep 07 08:00:00 IDT 2015 | Tue Dec 01 18:00:00 IST 2015 |  | COMPLETED
1209 | TT_TASK | Probe/Grout | Thu Jun 25 08:00:00 IDT 2015 | Mon Jul 06 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Fri Apr 10 18:00:00 IDT 2015 |  | COMPLETED
1210 | TT_TASK | Coring of Segment | Tue Jul 07 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Sat Apr 11 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1211 | TT_TASK | Removal of segment | Sat Jul 11 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
1212 | TT_TASK | Excavation 0-4mts with Shotcrete | Wed Jul 15 08:00:00 IDT 2015 | Sat Jul 25 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1213 | TT_TASK | Invert Concrete | Sat Jul 18 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 | Thu May 07 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1214 | TT_TASK | Wall and Roof concrete | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1215 | TT_TASK | Dismantle Temporary frame | Tue Jan 19 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 04 18:00:00 IST 2016 |  | COMPLETED
1216 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Feb 22 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Fri Feb 05 08:00:00 IST 2016 | Sat Feb 06 18:00:00 IST 2016 |  | COMPLETED
1218 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 1 (From Downtrack to Centre of CP) | Tue Mar 11 08:00:00 IST 2014 | Wed Mar 26 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1219 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Wed Nov 12 18:00:00 IST 2014 |  | COMPLETED
1220 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Thu Nov 13 08:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1221 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Tue Nov 18 08:00:00 IST 2014 | Thu Nov 20 18:00:00 IST 2014 |  | COMPLETED
1222 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Sat Nov 22 08:00:00 IST 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1223 | TT_TASK | Invert Concrete | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
1224 | TT_TASK | Wall and Roof concrete | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1225 | TT_TASK | Dismantle Temporary frame | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1226 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1227 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 2 (From Centre of CP to Uptrack) | Thu May 21 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Mar 09 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1228 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Mon May 04 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1229 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
1230 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1231 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 22 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
1232 | TT_TASK | Invert Concrete | Sat Aug 08 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Wed Jul 08 18:00:00 IDT 2015 |  | COMPLETED
1233 | TT_TASK | Wall and Roof concrete | Tue Aug 25 08:00:00 IDT 2015 | Mon Sep 07 18:00:00 IDT 2015 | Thu Jul 09 08:00:00 IDT 2015 | Sat Aug 15 18:00:00 IDT 2015 |  | COMPLETED
1234 | TT_TASK | Dismantle Temporary frame | Tue Sep 22 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 | Mon Aug 17 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 |  | COMPLETED
1235 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1237 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 1 (From Downtrack to Centre of CP) | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Sat May 24 18:00:00 IDT 2014 |  | COMPLETED
1238 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
1239 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1240 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 |  | COMPLETED
1241 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Mon Nov 17 08:00:00 IST 2014 | Sat Nov 29 18:00:00 IST 2014 |  | COMPLETED
1242 | TT_TASK | Invert Concrete | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 |  | COMPLETED
1243 | TT_TASK | Wall and Roof concrete | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 |  | COMPLETED
1244 | TT_TASK | Dismantle Temporary frame | Tue Dec 30 08:00:00 IST 2014 | Wed Jan 07 18:00:00 IST 2015 | Tue Dec 30 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1245 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1246 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 2 (From Centre of CP to Uptrack) | Fri May 08 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 |  | COMPLETED
1247 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
1248 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
1249 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Thu May 07 18:00:00 IDT 2015 |  | COMPLETED
1250 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
1251 | TT_TASK | Invert Concrete | Wed Aug 05 08:00:00 IDT 2015 | Fri Aug 14 18:00:00 IDT 2015 | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
1252 | TT_TASK | Wall and Roof concrete | Tue Sep 15 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Wed Aug 26 18:00:00 IDT 2015 |  | COMPLETED
1253 | TT_TASK | Dismantle Temporary frame | Sat Oct 17 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Oct 08 18:00:00 IDT 2015 |  | COMPLETED
1254 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1258 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 |  | COMPLETED
1259 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1260 | TT_TASK | D-wall construction (1192m3) | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 |  | COMPLETED
1261 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1262 | TT_TASK | Construct capping beam, cobble, etc. (including bay 6 and 5) | Sat Oct 27 08:00:00 IST 2012 | Sat Feb 16 18:00:00 IST 2013 | Sat Oct 27 08:00:00 IST 2012 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1264 | TT_TASK | Excavate up to +22.0mPD (1860m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1265 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 |  | COMPLETED
1266 | TT_TASK | Excavate up to +16.5mPD (3410m3) | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 |  | COMPLETED
1267 | TT_TASK | Install Strut S2 +17.0mPD | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 |  | COMPLETED
1268 | TT_TASK | Excavate up to +11.0mPD (3410m3) | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 |  | COMPLETED
1269 | TT_TASK | Install Strut S3 +11.5mPD | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 |  | COMPLETED
1270 | TT_TASK | Excavate up to +7.0mPD (2480m3) | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 |  | COMPLETED
1271 | TT_TASK | Install Strut S4 +7.5mPD | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1272 | TT_TASK | Excavate up to +3.5mPD (2170m3) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 |  | COMPLETED
1273 | TT_TASK | Install Strut S5 +4.0mPD | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1274 | TT_TASK | Excavate up to formation (2294m3) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1275 | TT_TASK | Construct temp. 500mm thick plain concrete base slab | Thu Oct 18 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 |  | COMPLETED
1276 | TT_TASK | Removal of South Bound strut to +9.50mPD | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1277 | TT_TASK | Removal of North Bound strut to +9.50mPD | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 |  | COMPLETED
1278 | TT_TASK | Construct temp. 500mm thick TBM concrete base slab | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1279 | TT_TASK | Construction entrance seal for TBM at South Bound | Mon Nov 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1280 | TT_TASK | Construction entrance seal for TBM at North Bound | Sat Jul 20 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1281 | TT_TASK | Saw cut South Bound diaphragm wall | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1282 | TT_TASK | Saw cut North Bound diaphragm wall | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1286 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 05 18:00:00 IDT 2014 | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 |  | COMPLETED
1287 | TT_TASK | Erect external formwork (Base Slab) | Sat Sep 06 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 21 18:00:00 IDT 2014 |  | COMPLETED
1288 | TT_TASK | Rebar fixing (Base Slab) | Wed Sep 10 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Tue Jul 22 08:00:00 IDT 2014 | Sat Jul 26 18:00:00 IDT 2014 |  | COMPLETED
1289 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Sep 15 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Sun Jul 27 08:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1290 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Thu Aug 14 18:00:00 IDT 2014 |  | COMPLETED
1291 | TT_TASK | Concreting (Base Slab) (225m3) | Sat Aug 09 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Fri Aug 15 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
1292 | TT_TASK | Curing (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
1293 | TT_TASK | Removal of formwork (Base Slab) | Tue Aug 12 08:00:00 IDT 2014 | Tue Aug 12 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1294 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed Aug 13 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Mon Sep 15 18:00:00 IDT 2014 |  | COMPLETED
1295 | TT_TASK | Rebar fixing (Wall & Roof) | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 |  | COMPLETED
1296 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 |  | COMPLETED
1297 | TT_TASK | Clearing and inspection (Wall & Roof) | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
1298 | TT_TASK | Concreting (Wall & Roof) (450m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
1299 | TT_TASK | Curing (Wall & Roof) | Sat Oct 11 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
1300 | TT_TASK | Removal external formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1301 | TT_TASK | Removal internal falsework (Wall & Roof) | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 |  | COMPLETED
1302 | TT_TASK | Side walkway and cable bracket (102m3) | Sat Oct 18 08:00:00 IDT 2014 | Wed Oct 29 18:00:00 IST 2014 | Mon Sep 01 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1304 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Wed Nov 11 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Oct 19 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1305 | TT_TASK | Erect external formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 |  | COMPLETED
1306 | TT_TASK | Rebar fixing (Base Slab) | Mon Nov 16 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Tue Oct 27 08:00:00 IST 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1307 | TT_TASK | Erect internal kicker formwork (Base Slab) | Fri Nov 20 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Oct 31 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 |  | COMPLETED
1308 | TT_TASK | Clearing and inspection (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
1309 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1310 | TT_TASK | Curing (Base Slab) | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 |  | COMPLETED
1311 | TT_TASK | Removal of formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 |  | COMPLETED
1312 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
1313 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Dec 09 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
1314 | TT_TASK | Erect external formwork (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Thu Jan 07 18:00:00 IST 2016 |  | COMPLETED
1315 | TT_TASK | Clearing and inspection (Wall & Roof) | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Fri Jan 08 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
1316 | TT_TASK | Concreting (Wall & Roof) (450m3) | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
1317 | TT_TASK | Curing (Wall & Roof) | Tue Jan 12 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
1318 | TT_TASK | Removal external formwork (Wall ) | Thu Jan 14 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
1319 | TT_TASK | Removal internal falsework, formwork and reproping (Wall & Roof) | Thu Jan 28 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 |  | COMPLETED
1320 | TT_TASK | Side walkway and cable bracket (102m3) | Wed Dec 23 08:00:00 IST 2015 | Wed Jan 06 18:00:00 IST 2016 | Wed Nov 11 08:00:00 IST 2015 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
1322 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 |  | COMPLETED
1323 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 |  | COMPLETED
1324 | TT_TASK | Backfilling to 0.5m below S3 (+11.0mPD) (3486m3) | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 |  | COMPLETED
1325 | TT_TASK | Removal strut S3 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
1326 | TT_TASK | Backfilling to 0.5m below S2 (+16.5mPD) (3410m3) | Wed Mar 16 08:00:00 IST 2016 | Fri Apr 08 18:00:00 IDT 2016 | Wed Mar 16 08:00:00 IST 2016 | Tue Apr 12 18:00:00 IDT 2016 |  | COMPLETED
1327 | TT_TASK | Removal strut S2 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 |  | COMPLETED
1328 | TT_TASK | Backfilling to 0.5m below S1 (+22.0mPD) (3410m3) | Fri Apr 15 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 | Fri Apr 15 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
1329 | TT_TASK | Removal strut S1 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 |  | COMPLETED
1330 | TT_TASK | Backfilling to original ground level (approx. +25.0mPD) (1860m3) | Thu May 05 08:00:00 IDT 2016 | Tue May 17 18:00:00 IDT 2016 | Thu May 05 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
1333 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1334 | TT_TASK | D-wall construction (2844m3) | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1335 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1337 | TT_TASK | Excavate up to +22.0mPD (3720m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1338 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 |  | COMPLETED
1339 | TT_TASK | Excavate up to +16.5mPD (4880m3) | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 |  | COMPLETED
1340 | TT_TASK | Install Strut S2 +17.0mPD | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 |  | COMPLETED
1341 | TT_TASK | Excavate up to +11.0mPD (6820m3) | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
1342 | TT_TASK | Install Strut S3 +11.5mPD | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 |  | COMPLETED
1343 | TT_TASK | Excavate up to +7.0mPD (4960m3) | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 |  | COMPLETED
1344 | TT_TASK | Install Strut S4 +7.5mPD | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1345 | TT_TASK | Excavate up to +3.5mPD (4340m3) | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1346 | TT_TASK | Install Strut S5 +4.0mPD | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 |  | COMPLETED
1347 | TT_TASK | Excavate up to formation (4960m3) | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 |  | COMPLETED
1348 | TT_TASK | Construct temp. 500mm thick plain concrete base slab at Bay 5 & 6 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1349 | TT_TASK | Excavation to formation and place blinding Bay 4a | Thu Oct 18 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1350 | TT_TASK | Excavation to formation and place blinding Bay 4b | Fri Jun 21 08:00:00 IDT 2013 | Fri Jul 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1351 | TT_TASK | Excavation to formation and place blinding Bay3 | Sat Jul 13 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1352 | TT_TASK | Excavation to formation and place blinding Bay2 to Bay1 | Wed Jul 24 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1356 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 |  | COMPLETED
1357 | TT_TASK | Erect external formwork for base slab | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 |  | COMPLETED
1358 | TT_TASK | Rebar fixing for base slab | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1359 | TT_TASK | Erect internal kicker formwork for base slab | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1360 | TT_TASK | Concreting for base slab (363m3) | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1361 | TT_TASK | Curing for base slab | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1362 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1363 | TT_TASK | Removal of formwork for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1364 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1365 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 27 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1366 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1367 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1368 | TT_TASK | Curing for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1369 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1370 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 10 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1371 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 19 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jan 24 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1372 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 08 08:00:00 IST 2015 | Tue Jan 13 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1374 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 |  | COMPLETED
1375 | TT_TASK | Erect external formwork for base slab | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1376 | TT_TASK | Rebar fixing for base slab | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1377 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 |  | COMPLETED
1378 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1379 | TT_TASK | Curing for base slab | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1380 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1381 | TT_TASK | Removal of formwork for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1382 | TT_TASK | Rebar fixing for central slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1383 | TT_TASK | Erect external formwork for central slab | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1384 | TT_TASK | Concreting for central slab (450m3) | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1385 | TT_TASK | Curing for central slab | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1386 | TT_TASK | Preparation of construction joint for central slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1387 | TT_TASK | Removal of formwork for central slab | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1388 | TT_TASK | Removal strut S5 and S4 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1389 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1390 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1391 | TT_TASK | Erect external formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1392 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1393 | TT_TASK | Curing for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1394 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1395 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 08 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1396 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1397 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Nov 19 08:00:00 IST 2015 | Tue Nov 24 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 |  | COMPLETED
1400 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1401 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1402 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1403 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1404 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1405 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1406 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1407 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1408 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1409 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1410 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 10 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1411 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1412 | TT_TASK | Curing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1413 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1414 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1415 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1416 | TT_TASK | Side walkway and cable bracket | Fri Jan 02 08:00:00 IST 2015 | Wed Jan 07 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1418 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1419 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1420 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1421 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1422 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1423 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1424 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1425 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1426 | TT_TASK | Rebar fixing for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1427 | TT_TASK | Erect external formwork for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1428 | TT_TASK | Concreting for central slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1429 | TT_TASK | Curing for central slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1430 | TT_TASK | Preparation of construction joint for central slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1431 | TT_TASK | Removal of formwork for central slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 21 18:00:00 IST 2012 |  | COMPLETED
1432 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1433 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1434 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1435 | TT_TASK | Erect external formwork for wall | Mon Jul 15 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1436 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1437 | TT_TASK | Curing for wall and roof | Sun Jul 21 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1438 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1439 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 22 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1440 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 31 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1441 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Sep 16 08:00:00 IDT 2015 | Mon Sep 21 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1443 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1444 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1445 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1446 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1447 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1448 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1449 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1450 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1451 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1452 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1453 | TT_TASK | Erect external formwork for wall | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1454 | TT_TASK | Concreting for wall and roof (444m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1455 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1456 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1457 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Sat Feb 09 18:00:00 IST 2013 |  | COMPLETED
1458 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Nov 09 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Tue Oct 06 08:00:00 IDT 2015 | Sat Oct 10 18:00:00 IDT 2015 |  | COMPLETED
1461 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1462 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1463 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1464 | TT_TASK | Erect internal kicker formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1465 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1466 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1467 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1468 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1469 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1470 | TT_TASK | Curing | Wed Jun 12 08:00:00 IDT 2013 | Wed Jun 12 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1471 | TT_TASK | Removal strut S5 and S4 | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1473 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1474 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1475 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1476 | TT_TASK | Concreting for wall and roof (450m3) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1477 | TT_TASK | Curing for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1478 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1479 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1480 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 29 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1481 | TT_TASK | Side walkway and cable bracket | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1483 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1484 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1485 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1486 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1487 | TT_TASK | Curing for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1488 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1489 | TT_TASK | Removal external wall formwork for wall | Wed Jun 26 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1490 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1491 | TT_TASK | Side walkway and cable bracket | Fri Sep 04 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
1494 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1495 | TT_TASK | Erect external formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1496 | TT_TASK | Rebar fixing for base slab | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1497 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1498 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 |  | COMPLETED
1499 | TT_TASK | Curing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1500 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1501 | TT_TASK | Removal of formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1502 | TT_TASK | Shear beam | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1503 | TT_TASK | Curing | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1504 | TT_TASK | Removal strut S5 and S4 | Wed Jun 19 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1506 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 24 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1507 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1508 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1509 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1510 | TT_TASK | Curing for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1511 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1512 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1513 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1514 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
1516 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1517 | TT_TASK | Rebar fixing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1518 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1519 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1520 | TT_TASK | Curing for wall and roof | Sun Jun 23 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1521 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1522 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 25 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1523 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 03 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1524 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Aug 29 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1527 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1528 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Sat Dec 22 18:00:00 IST 2012 |  | COMPLETED
1529 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1530 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1531 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1532 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1533 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1534 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Fri Jan 11 18:00:00 IST 2013 |  | COMPLETED
1535 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Jan 12 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1536 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1537 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1539 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1540 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1541 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1542 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1543 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1544 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1545 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1546 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1547 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 |  | COMPLETED
1549 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1550 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Mon Feb 25 18:00:00 IST 2013 |  | COMPLETED
1551 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1552 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1553 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1554 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1555 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1556 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1557 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Aug 24 08:00:00 IDT 2015 | Fri Aug 28 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1560 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1561 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1562 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1563 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1564 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1565 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1566 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1567 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1568 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1569 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1570 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1572 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1573 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1574 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1575 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1576 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1577 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1578 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1579 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1580 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
1582 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1583 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1584 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1585 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1586 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1587 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1588 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1589 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1590 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Aug 18 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1593 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1594 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1595 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1596 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1597 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1598 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1599 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1600 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1601 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1602 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1603 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1605 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 31 18:00:00 IDT 2013 |  | COMPLETED
1606 | TT_TASK | Rebar fixing for wall and roof | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 |  | COMPLETED
1607 | TT_TASK | Erect external formwork for wall and roof | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 | Fri Sep 06 08:00:00 IDT 2013 | Thu Sep 12 18:00:00 IDT 2013 |  | COMPLETED
1608 | TT_TASK | Concreting for wall and roof (450m3) | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 |  | COMPLETED
1609 | TT_TASK | Curing for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1610 | TT_TASK | Preparation of construction joint for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1611 | TT_TASK | Removal external and internal formwork for wall | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Wed Sep 25 18:00:00 IDT 2013 |  | COMPLETED
1612 | TT_TASK | Removal internal falsework and formwork for roof | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1613 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 08 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1615 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 20 18:00:00 IST 2013 |  | COMPLETED
1616 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1617 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1618 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1619 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1620 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1621 | TT_TASK | Removal external wall formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1622 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1623 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Aug 12 08:00:00 IDT 2015 | Mon Aug 17 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1626 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1627 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1628 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Feb 14 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1629 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1630 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Mon Feb 18 18:00:00 IST 2013 |  | COMPLETED
1631 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1632 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1633 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1634 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1635 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1636 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1638 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jul 12 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1639 | TT_TASK | Rebar fixing for wall and roof | Wed Jul 17 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1640 | TT_TASK | Erect external formwork for wall and roof | Wed Aug 14 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1641 | TT_TASK | Concreting for wall and roof (450m3) | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1642 | TT_TASK | Curing for wall and roof | Sun Aug 11 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1643 | TT_TASK | Preparation of construction joint for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1644 | TT_TASK | Removal external and internal formwork for wall | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1645 | TT_TASK | Removal internal falsework and formwork for roof | Wed Aug 21 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1646 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 03 08:00:00 IST 2014 | Fri Mar 07 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1648 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1649 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1650 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Apr 09 08:00:00 IDT 2013 | Thu Apr 11 18:00:00 IDT 2013 |  | COMPLETED
1651 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1652 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1653 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1654 | TT_TASK | Removal external wall formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1655 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
1656 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Aug 06 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Mon Jul 27 08:00:00 IDT 2015 | Fri Jul 31 18:00:00 IDT 2015 |  | COMPLETED
1658 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Sep 12 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1659 | TT_TASK | Rebar fixing for roof | Tue Sep 17 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1660 | TT_TASK | Erect external formwork for roof | Thu Sep 19 08:00:00 IDT 2013 | Thu Sep 19 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1661 | TT_TASK | Concreting for roof (444m3) | Sat Sep 21 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1662 | TT_TASK | Curing for roof | Sun Sep 22 08:00:00 IDT 2013 | Tue Oct 01 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1663 | TT_TASK | Preparation of construction joint for roof | Mon Sep 23 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1664 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1665 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1668 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1669 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1670 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1671 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1672 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1673 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1674 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1675 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1676 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1677 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1678 | TT_TASK | Removal strut S5 and S4 | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1680 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Thu Apr 25 18:00:00 IDT 2013 |  | COMPLETED
1681 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri May 03 08:00:00 IDT 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
1682 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Thu May 16 08:00:00 IDT 2013 | Thu May 23 18:00:00 IDT 2013 |  | COMPLETED
1683 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1684 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1685 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1686 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Wed May 29 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1687 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1688 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 19 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1690 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Fri Apr 19 18:00:00 IDT 2013 |  | COMPLETED
1691 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1692 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Apr 25 08:00:00 IDT 2013 | Sat Apr 27 18:00:00 IDT 2013 |  | COMPLETED
1693 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1694 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1695 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1696 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1697 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1698 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 02 08:00:00 IDT 2015 | Sat Apr 11 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Feb 27 18:00:00 IST 2015 |  | COMPLETED
1700 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1701 | TT_TASK | Rebar fixing for roof | Tue Aug 06 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1702 | TT_TASK | Erect external formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1703 | TT_TASK | Concreting for roof (444m3) | Fri Aug 09 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 |  | COMPLETED
1704 | TT_TASK | Curing for roof | Thu Aug 01 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1705 | TT_TASK | Preparation of construction joint for roof | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 |  | COMPLETED
1706 | TT_TASK | Removal internal falsework and formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1707 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 09 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1710 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Wed Feb 20 18:00:00 IST 2013 |  | COMPLETED
1711 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1712 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1713 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1714 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1715 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1716 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1717 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1718 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1719 | TT_TASK | Curing | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1720 | TT_TASK | Removal strut S5 and S4 | Mon Jun 24 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1722 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1723 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1724 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Wed Jul 10 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1725 | TT_TASK | Concreting for wall and roof (450m3) | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1726 | TT_TASK | Curing for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1727 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1728 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 |  | COMPLETED
1729 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 |  | COMPLETED
1730 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1732 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1733 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1734 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1735 | TT_TASK | Concreting for wall and roof (450m3) | Tue Sep 03 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1736 | TT_TASK | Curing for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1737 | TT_TASK | Preparation of construction joint for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 |  | COMPLETED
1738 | TT_TASK | Removal external and internal formwork for wall | Thu Sep 05 08:00:00 IDT 2013 | Fri Sep 06 18:00:00 IDT 2013 | Thu Aug 22 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1739 | TT_TASK | Removal internal falsework and formwork for roof | Sat Sep 14 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 |  | COMPLETED
1740 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 05 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1742 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1743 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1744 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1745 | TT_TASK | Concreting for roof (363m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1746 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Sun Oct 20 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1747 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1748 | TT_TASK | Removal internal falsework and formwork for roof | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1749 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Dec 24 13:00:00 IST 2013 | Thu Jan 02 12:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1752 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1753 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1754 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1755 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Apr 12 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1756 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1757 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1758 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1759 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1760 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1761 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1762 | TT_TASK | Removal strut S5 and S4 | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1764 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Aug 05 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1765 | TT_TASK | Rebar fixing for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1766 | TT_TASK | Erect external formwork for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1767 | TT_TASK | Concreting for wall and roof (450m3) | Thu Aug 15 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1768 | TT_TASK | Curing for wall and roof | Fri Aug 16 08:00:00 IDT 2013 | Sun Aug 25 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1769 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1770 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1771 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 |  | COMPLETED
1772 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Feb 04 08:00:00 IST 2014 | Sat Feb 08 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1774 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Aug 07 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1775 | TT_TASK | Rebar fixing for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1776 | TT_TASK | Erect external formwork for wall and roof | Thu Aug 15 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1777 | TT_TASK | Concreting for wall and roof (450m3) | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1778 | TT_TASK | Curing for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1779 | TT_TASK | Preparation of construction joint for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 |  | COMPLETED
1780 | TT_TASK | Removal external and internal formwork for wall | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Wed Aug 21 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 |  | COMPLETED
1781 | TT_TASK | Removal internal falsework and formwork for roof | Mon Sep 16 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1782 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Nov 19 08:00:00 IST 2014 | Mon Nov 24 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1784 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1785 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1786 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1787 | TT_TASK | Concreting for roof (450m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1788 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1789 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1790 | TT_TASK | Removal internal falsework and formwork for roof | Fri Oct 18 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1791 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 13 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1794 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1795 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1796 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1797 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1798 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 28 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1799 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1800 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1801 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1802 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1803 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1804 | TT_TASK | Removal strut S5 and S4 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1806 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1807 | TT_TASK | Rebar fixing for wall and roof | Sat Jul 20 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1808 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1809 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1810 | TT_TASK | Curing for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1811 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1812 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 29 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1813 | TT_TASK | Removal internal falsework and formwork for roof | Tue Aug 06 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1814 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 18:00:00 IST 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1816 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1817 | TT_TASK | Rebar fixing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1818 | TT_TASK | Erect external formwork for wall and roof | Fri Jul 19 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1819 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1820 | TT_TASK | Curing for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Thu Mar 28 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1821 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Mar 29 08:00:00 IDT 2013 | Fri Mar 29 18:00:00 IDT 2013 |  | COMPLETED
1822 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Sat Mar 30 08:00:00 IDT 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1823 | TT_TASK | Removal internal falsework and formwork for roof | Fri Aug 02 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Mon Apr 01 18:00:00 IDT 2013 |  | COMPLETED
1824 | TT_TASK | Side walkway and cable bracket | Thu Nov 13 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1826 | TT_TASK | Erect internal formwork & Falsework for roof | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1827 | TT_TASK | Rebar fixing for roof | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 |  | COMPLETED
1828 | TT_TASK | Erect shutter formwork for roof | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 09 18:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1829 | TT_TASK | Concreting for roof (450m3) | Tue Sep 10 08:00:00 IDT 2013 | Tue Sep 10 18:00:00 IDT 2013 | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 |  | COMPLETED
1830 | TT_TASK | Curing for roof | Wed Sep 11 08:00:00 IDT 2013 | Fri Sep 20 18:00:00 IDT 2013 | Tue Jul 23 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 |  | COMPLETED
1831 | TT_TASK | Preparation of construction joint for roof | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 11 18:00:00 IDT 2013 | Sat Aug 03 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1832 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 26 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 |  | COMPLETED
1833 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 06 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Aug 13 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1835 | TT_TASK | Water proofing and soil backfilling to 0.5m below top of Tunnel Bay 3 to Bay 1 | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1836 | TT_TASK | Mass infill between D-wall and tunnel wall | Fri Oct 11 08:00:00 IDT 2013 | Wed Oct 16 18:00:00 IDT 2013 | Fri Sep 20 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1837 | TT_TASK | Removal S3 and S2 | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
1838 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 4 | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Sat May 18 18:00:00 IDT 2013 |  | COMPLETED
1839 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 5 and remove S3 & S2 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1840 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 6 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1843 | TT_TASK | Pre-drilling and guidewall | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1844 | TT_TASK | D-wall design review | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1845 | TT_TASK | D-wall construction (4741m3) | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 |  | COMPLETED
1846 | TT_TASK | Shear pin and pumping test | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 15 18:00:00 IST 2012 | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1848 | TT_TASK | ELS works to formation level from SN16 to SN19 (soil: 8,700m3 @350m3/day, Install S1 to S3 strut 5 days/layer) | Wed Sep 25 08:00:00 IDT 2013 | Wed Nov 13 18:00:00 IST 2013 | Wed May 08 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1849 | TT_TASK | Design temporary bridge and approval | Mon Sep 01 08:00:00 IDT 2014 | Wed Nov 12 18:00:00 IST 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1850 | TT_TASK | Application of tree transplant | Sat Jun 01 08:00:00 IDT 2013 | Wed Oct 23 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1851 | TT_TASK | Tree transplant | Tue Oct 14 08:00:00 IDT 2014 | Mon Nov 10 18:00:00 IST 2014 | Tue Sep 02 08:00:00 IDT 2014 | Tue Sep 30 18:00:00 IDT 2014 |  | COMPLETED
1852 | TT_TASK | Erection temporary bridge deck | Fri Oct 03 08:00:00 IDT 2014 | Fri Dec 05 18:00:00 IST 2014 | Fri Oct 03 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1853 | TT_TASK | ELS works to formation level from SN10 to SN15 (soil: 9,455m3 @330m3/day, install S1 to S3 strut 5 days/layer) | Mon Nov 24 08:00:00 IST 2014 | Sat Jan 17 18:00:00 IST 2015 | Mon Nov 24 08:00:00 IST 2014 | Tue Jun 23 18:00:00 IDT 2015 |  | COMPLETED
1856 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
1857 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1858 | TT_TASK | Erect external formwork for wall and roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1859 | TT_TASK | Concreting for wall and roof (215m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
1860 | TT_TASK | Curing for wall and roof | Sun Dec 08 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
1861 | TT_TASK | Preparation of construction joint for wall and roof | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1862 | TT_TASK | Removal external and internal formwork for wall | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1863 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1864 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 03 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 | Mon Mar 24 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
1866 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 14 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1867 | TT_TASK | Rebar fixing for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1868 | TT_TASK | Erect external formwork for wall and roof | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1869 | TT_TASK | Concreting for wall and roof (215m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1870 | TT_TASK | Curing for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Sun Dec 29 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1871 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
1872 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 17 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
1873 | TT_TASK | Removal internal falsework and formwork for roof | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1874 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 |  | COMPLETED
1876 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 28 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Nov 28 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1877 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1878 | TT_TASK | Erect external formwork for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1879 | TT_TASK | Concreting for wall and roof (215m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1880 | TT_TASK | Curing for wall and roof | Wed Jan 01 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
1881 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
1882 | TT_TASK | Removal external and internal formwork for wall | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 |  | COMPLETED
1883 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
1884 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 |  | COMPLETED
1886 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1887 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 14 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1888 | TT_TASK | Erect external formwork for wall and roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1889 | TT_TASK | Concreting for wall and roof (215m3) | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1890 | TT_TASK | Curing for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1892 | TT_TASK | Removal external and internal formwork for wall | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1893 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1894 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 |  | COMPLETED
1896 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 08:00:00 IST 2013 |  | COMPLETED
1897 | TT_TASK | Rebar fixing for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1898 | TT_TASK | Erect external formwork for wall and roof | Fri Jan 03 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1899 | TT_TASK | Concreting for wall and roof (215m3) | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1900 | TT_TASK | Curing for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 16 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1901 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Tue Jan 07 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1902 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1903 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1904 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 |  | COMPLETED
1906 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1907 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1908 | TT_TASK | Erect external formwork for wall and roof | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1909 | TT_TASK | Concreting for wall and roof (215m3) | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1910 | TT_TASK | Curing for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1911 | TT_TASK | Preparation of construction joint for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1912 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1913 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1914 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 |  | COMPLETED
1916 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1917 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 |  | COMPLETED
1918 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Tue Jun 04 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 |  | COMPLETED
1919 | TT_TASK | Concreting for wall and roof (333m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1920 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1921 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Wed Jun 12 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1922 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 |  | COMPLETED
1923 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
1924 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 05 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Tue Mar 04 18:00:00 IST 2014 |  | COMPLETED
1926 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1927 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1928 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1929 | TT_TASK | Concreting for wall and roof (412m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1930 | TT_TASK | Curing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Sun Jun 23 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Sat Mar 23 18:00:00 IST 2013 |  | COMPLETED
1931 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Mar 25 08:00:00 IST 2013 | Mon Mar 25 18:00:00 IST 2013 |  | COMPLETED
1932 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Mar 26 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1933 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jun 24 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1934 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 27 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Mon Mar 03 18:00:00 IST 2014 |  | COMPLETED
1936 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1937 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1938 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Apr 02 18:00:00 IDT 2013 |  | COMPLETED
1939 | TT_TASK | Concreting for wall and roof (320m3) | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Apr 05 08:00:00 IDT 2013 | Fri Apr 05 18:00:00 IDT 2013 |  | COMPLETED
1940 | TT_TASK | Curing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 06 08:00:00 IDT 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1941 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1942 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1943 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1944 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jan 21 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Sat Mar 01 18:00:00 IST 2014 |  | COMPLETED
1946 | TT_TASK | Excavation and saw cut D-wall | Thu Apr 02 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Sat Jul 25 18:00:00 IDT 2015 |  | COMPLETED
1947 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Aug 08 16:24:00 IDT 2015 | Mon Aug 10 16:24:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Mon Jul 13 18:00:00 IDT 2015 |  | COMPLETED
1948 | TT_TASK | Erect external formwork for base slab | Mon Aug 10 16:24:00 IDT 2015 | Wed Aug 12 16:24:00 IDT 2015 | Tue Jul 14 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
1949 | TT_TASK | Rebar fixing for base slab | Wed Aug 12 16:24:00 IDT 2015 | Fri Aug 14 16:24:00 IDT 2015 | Wed Jul 15 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1950 | TT_TASK | Erect internal kicker formwork for base slab | Fri Aug 14 16:24:00 IDT 2015 | Mon Aug 17 16:24:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Wed Aug 12 18:00:00 IDT 2015 |  | COMPLETED
1951 | TT_TASK | Concreting for base slab (90m3) | Wed Sep 02 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 | Thu Aug 13 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 |  | COMPLETED
1952 | TT_TASK | Curing for base slab | Thu Sep 03 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Fri Aug 14 08:00:00 IDT 2015 | Thu Aug 20 18:00:00 IDT 2015 |  | COMPLETED
1953 | TT_TASK | Preparation of construction joint for base slab | Thu Sep 03 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Fri Aug 21 08:00:00 IDT 2015 | Fri Aug 21 18:00:00 IDT 2015 |  | COMPLETED
1954 | TT_TASK | Removal of formwork for base slab | Fri Sep 04 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Sat Aug 22 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 |  | COMPLETED
1955 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Sep 05 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 | Mon Aug 24 08:00:00 IDT 2015 | Mon Aug 24 18:00:00 IDT 2015 |  | COMPLETED
1956 | TT_TASK | Curing | Thu Sep 10 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Tue Aug 25 08:00:00 IDT 2015 | Tue Aug 25 18:00:00 IDT 2015 |  | COMPLETED
1957 | TT_TASK | Removal strut S3 | Sat Sep 19 08:00:00 IDT 2015 | Wed Sep 23 18:00:00 IDT 2015 | Wed Sep 16 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
1958 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Sep 24 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
1959 | TT_TASK | Rebar fixing for wall and roof | Wed Sep 30 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 | Fri Sep 25 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 |  | COMPLETED
1960 | TT_TASK | Erect external formwork for wall and roof | Thu Oct 15 08:00:00 IDT 2015 | Fri Oct 16 18:00:00 IDT 2015 | Mon Oct 05 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
1961 | TT_TASK | Concreting for wall and roof (260m3) | Sat Oct 17 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 | Wed Oct 07 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1962 | TT_TASK | Curing for wall and roof | Sun Oct 18 08:00:00 IDT 2015 | Tue Oct 27 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 |  | COMPLETED
1963 | TT_TASK | Preparation of construction joint for wall and roof | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
1964 | TT_TASK | Removal external and internal formwork for wall | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
1965 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 28 08:00:00 IST 2015 | Thu Oct 29 18:00:00 IST 2015 | Thu Oct 22 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1966 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Oct 30 08:00:00 IST 2015 | Wed Nov 04 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1968 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 02 18:00:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 |  | COMPLETED
1969 | TT_TASK | Erect external formwork for base slab | Fri Jul 03 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Tue Jul 21 08:00:00 IDT 2015 | Wed Jul 22 18:00:00 IDT 2015 |  | COMPLETED
1970 | TT_TASK | Rebar fixing for base slab | Mon Jul 06 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 23 08:00:00 IDT 2015 | Fri Jul 24 18:00:00 IDT 2015 |  | COMPLETED
1971 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jul 08 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Sat Jul 25 08:00:00 IDT 2015 | Mon Jul 27 18:00:00 IDT 2015 |  | COMPLETED
1972 | TT_TASK | Concreting for base slab (123m3) | Fri Jul 10 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jul 28 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 |  | COMPLETED
1973 | TT_TASK | Curing for base slab | Sat Jul 11 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1974 | TT_TASK | Preparation of construction joint for base slab | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 |  | COMPLETED
1975 | TT_TASK | Removal of formwork for base slab | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 |  | COMPLETED
1976 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1977 | TT_TASK | Curing | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 |  | COMPLETED
1978 | TT_TASK | Removal strut S3 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1979 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 |  | COMPLETED
1980 | TT_TASK | Rebar fixing for wall and roof | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 |  | COMPLETED
1981 | TT_TASK | Erect external formwork for wall and roof | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 |  | COMPLETED
1982 | TT_TASK | Concreting for wall and roof (260m3) | Fri Oct 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 | Sat Oct 24 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
1983 | TT_TASK | Curing for wall and roof | Sat Oct 03 08:00:00 IDT 2015 | Mon Oct 12 18:00:00 IDT 2015 | Mon Oct 26 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1984 | TT_TASK | Preparation of construction joint for wall and roof | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
1985 | TT_TASK | Removal external and internal formwork for wall | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1986 | TT_TASK | Removal internal falsework and formwork for roof | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1987 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1989 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
1990 | TT_TASK | Erect external formwork for base slab | Mon Jun 15 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1991 | TT_TASK | Rebar fixing for base slab | Wed Jun 17 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
1992 | TT_TASK | Erect internal kicker formwork for base slab | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
1993 | TT_TASK | Concreting for base slab (127m3) | Tue Jun 23 08:00:00 IDT 2015 | Tue Jun 23 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
1994 | TT_TASK | Curing for base slab | Wed Jun 24 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
1995 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 24 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1996 | TT_TASK | Removal of formwork for base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
1997 | TT_TASK | Infill concrete in between D-wall and base slab | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1998 | TT_TASK | Curing | Thu May 28 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1999 | TT_TASK | Removal strut S3 | Fri May 29 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2000 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 03 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2001 | TT_TASK | Rebar fixing for wall and roof | Mon Jun 08 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2002 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2003 | TT_TASK | Concreting for wall and roof (260m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2004 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2005 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2006 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2007 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2008 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 11 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2010 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
2011 | TT_TASK | Erect external formwork for base slab | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
2012 | TT_TASK | Rebar fixing for base slab | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
2013 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
2014 | TT_TASK | Concreting for base slab (127m3) | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
2015 | TT_TASK | Curing for base slab | Thu Jun 11 08:00:00 IDT 2015 | Wed Jun 17 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2016 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 11 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
2017 | TT_TASK | Removal of formwork for base slab | Sat May 23 08:00:00 IDT 2015 | Sat May 23 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
2018 | TT_TASK | Infill concrete in between D-wall and base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
2019 | TT_TASK | Curing | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2020 | TT_TASK | Removal strut S3 | Thu May 28 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2021 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2022 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2023 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2024 | TT_TASK | Concreting for wall and roof (150m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2025 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2026 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2027 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2028 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2029 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jul 06 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
2031 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2032 | TT_TASK | Erect external formwork for base slab | Thu May 21 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2033 | TT_TASK | Rebar fixing for base slab | Sat May 23 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2034 | TT_TASK | Erect internal kicker formwork for base slab | Wed May 27 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2035 | TT_TASK | Concreting for base slab (70m3) | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2036 | TT_TASK | Curing for base slab | Sat May 30 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2037 | TT_TASK | Preparation of construction joint for base slab | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2038 | TT_TASK | Removal of formwork for base slab | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2039 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2040 | TT_TASK | Curing | Sat Jun 06 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2041 | TT_TASK | Removal strut S3 | Mon Jun 08 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat May 23 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2043 | TT_TASK | Rebar fixing for wall and roof | Fri May 29 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2044 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2045 | TT_TASK | Concreting for wall and roof (175m3) | Thu Jun 04 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2046 | TT_TASK | Curing for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sun Jun 14 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2047 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2048 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 03 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 04 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2050 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 29 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
2052 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2053 | TT_TASK | Erect external formwork for base slab | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2054 | TT_TASK | Rebar fixing for base slab | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2055 | TT_TASK | Erect internal kicker formwork for base slab | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2056 | TT_TASK | Concreting for base slab (70m3) | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2057 | TT_TASK | Curing for base slab | Wed Apr 22 08:00:00 IDT 2015 | Tue Apr 28 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2058 | TT_TASK | Preparation of construction joint for base slab | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2059 | TT_TASK | Removal of formwork for base slab | Thu Apr 23 08:00:00 IDT 2015 | Thu Apr 23 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2060 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Apr 24 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2061 | TT_TASK | Curing | Wed Apr 29 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2062 | TT_TASK | Removal strut S3 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2063 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed May 06 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2064 | TT_TASK | Rebar fixing for wall and roof | Thu May 14 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2065 | TT_TASK | Erect external formwork for wall and roof | Mon May 18 08:00:00 IDT 2015 | Tue May 19 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2066 | TT_TASK | Concreting for wall and roof (175m3) | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2067 | TT_TASK | Curing for wall and roof | Thu May 21 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2068 | TT_TASK | Preparation of construction joint for wall and roof | Thu May 21 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2069 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2070 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2071 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jun 23 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
2073 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Fri Nov 15 18:00:00 IST 2013 |  | COMPLETED
2074 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Nov 16 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2075 | TT_TASK | Rebar fixing for base slab | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
2076 | TT_TASK | Erect internal kicker formwork for base slab | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
2077 | TT_TASK | Concreting for base slab (70m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
2078 | TT_TASK | Curing for base slab | Fri Dec 20 08:00:00 IST 2013 | Thu Dec 26 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
2079 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 |  | COMPLETED
2080 | TT_TASK | Removal of formwork for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
2081 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
2082 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2083 | TT_TASK | Removal strut S3 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2084 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Apr 16 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2085 | TT_TASK | Rebar fixing for wall and roof | Thu Apr 24 08:00:00 IDT 2014 | Sat Apr 26 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 |  | COMPLETED
2086 | TT_TASK | Erect external formwork for wall and roof | Mon Apr 28 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Thu Apr 10 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2087 | TT_TASK | Concreting for wall and roof (170m3) | Wed Apr 30 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Sat Apr 12 08:00:00 IDT 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
2088 | TT_TASK | Curing for wall and roof | Thu May 01 08:00:00 IDT 2014 | Sat May 10 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Tue Apr 22 18:00:00 IDT 2014 |  | COMPLETED
2089 | TT_TASK | Preparation of construction joint for wall and roof | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 |  | COMPLETED
2090 | TT_TASK | Removal external and internal formwork for wall | Sat May 03 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Tue Apr 15 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
2091 | TT_TASK | Removal internal falsework and formwork for roof | Mon May 12 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 |  | COMPLETED
2092 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jun 05 08:00:00 IDT 2014 | Tue Jun 10 18:00:00 IDT 2014 | Thu May 29 08:00:00 IDT 2014 | Thu Dec 04 18:00:00 IST 2014 |  | COMPLETED
2094 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2095 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2096 | TT_TASK | Rebar fixing for base slab | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2097 | TT_TASK | Erect internal kicker formwork for base slab | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2098 | TT_TASK | Concreting for base slab (70m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2099 | TT_TASK | Curing for base slab | Sun Dec 08 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2100 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2101 | TT_TASK | Removal of formwork for base slab | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
2102 | TT_TASK | Infill concrete in between D-wall and base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
2103 | TT_TASK | Curing | Sun Dec 15 08:00:00 IST 2013 | Sun Dec 15 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2104 | TT_TASK | Removal strut S3 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2105 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Feb 12 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2106 | TT_TASK | Rebar fixing for wall and roof | Mon Feb 17 08:00:00 IST 2014 | Wed Feb 19 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
2107 | TT_TASK | Erect external formwork for wall and roof | Fri Feb 28 13:48:00 IST 2014 | Mon Mar 03 13:48:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2108 | TT_TASK | Concreting for wall and roof (200m3) | Mon Mar 03 13:48:00 IST 2014 | Tue Mar 04 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2109 | TT_TASK | Curing for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Fri Mar 14 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2110 | TT_TASK | Preparation of construction joint for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Wed Mar 05 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2111 | TT_TASK | Removal external and internal formwork for wall | Wed Mar 05 13:48:00 IST 2014 | Thu Mar 06 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
2112 | TT_TASK | Removal internal falsework and formwork for roof | Fri Mar 14 13:48:00 IST 2014 | Mon Mar 17 13:48:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2113 | TT_TASK | Side walkway and cable bracket (204m3) | Thu May 29 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Wed Dec 03 18:00:00 IST 2014 |  | COMPLETED
2115 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2116 | TT_TASK | Erect external formwork for base slab | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2117 | TT_TASK | Rebar fixing for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2118 | TT_TASK | Erect internal kicker formwork for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2119 | TT_TASK | Concreting for base slab (70m3) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2120 | TT_TASK | Curing for base slab | Tue Dec 03 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2121 | TT_TASK | Preparation of construction joint for base slab | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
2122 | TT_TASK | Removal of formwork for base slab | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2123 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2124 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2125 | TT_TASK | Removal strut S3 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
2126 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jan 25 08:00:00 IST 2014 | Wed Jan 29 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
2127 | TT_TASK | Rebar fixing for wall and roof | Thu Jan 30 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Fri Dec 20 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
2128 | TT_TASK | Erect external formwork for wall and roof | Thu Feb 20 08:00:00 IST 2014 | Fri Feb 21 18:00:00 IST 2014 | Thu Jan 09 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2129 | TT_TASK | Concreting for wall and roof (200m3) | Sat Feb 22 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2130 | TT_TASK | Curing for wall and roof | Sun Feb 23 08:00:00 IST 2014 | Tue Mar 04 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2131 | TT_TASK | Preparation of construction joint for wall and roof | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Tue Jan 14 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2132 | TT_TASK | Removal external and internal formwork for wall | Tue Feb 25 08:00:00 IST 2014 | Tue Feb 25 18:00:00 IST 2014 | Wed Jan 15 08:00:00 IST 2014 | Wed Jan 15 18:00:00 IST 2014 |  | COMPLETED
2133 | TT_TASK | Removal internal falsework and formwork for roof | Wed Mar 05 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2134 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
2137 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Sep 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
2138 | TT_TASK | Erect external formwork for base slab | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Sep 21 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
2139 | TT_TASK | Rebar fixing for base slab | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
2140 | TT_TASK | Erect internal kicker formwork for base slab | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
2141 | TT_TASK | Staircase construction (+12.0mPD to +14.706mPD) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2142 | TT_TASK | Concreting for base slab (30m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
2143 | TT_TASK | Curing for base slab | Fri Dec 13 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
2144 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
2145 | TT_TASK | Removal of formwork for base slab | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 18:00:00 IDT 2013 |  | COMPLETED
2146 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2147 | TT_TASK | Mass concrete at level +12.0mPD | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 |  | COMPLETED
2148 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2149 | TT_TASK | Removal strut S3 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2150 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 17 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Mon Dec 01 18:00:00 IST 2014 |  | COMPLETED
2152 | TT_TASK | Erect working platform to +21.0mPD | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2153 | TT_TASK | Rebar fixing for wall and roof | Sat Jan 11 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2154 | TT_TASK | Staircase construction (+14.706mPD to +16.956mPD) (20m3) | Fri May 02 08:00:00 IDT 2014 | Wed May 07 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2155 | TT_TASK | Staircase construction (+16.956mPD to +19.206mPD) (20m3) | Thu Jun 05 08:00:00 IDT 2014 | Mon Jun 09 18:00:00 IDT 2014 | Thu Jun 12 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2156 | TT_TASK | Staircase construction (+19.206mPD to +21.456mPD) (20m3) | Tue Jun 10 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Fri Jun 20 18:00:00 IDT 2014 |  | COMPLETED
2157 | TT_TASK | Erect external formwork for wall and roof | Sat Mar 15 08:00:00 IST 2014 | Mon Mar 17 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2158 | TT_TASK | Concreting for wall and roof (31m3) | Tue Feb 04 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2159 | TT_TASK | Curing for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 |  | COMPLETED
2160 | TT_TASK | Preparation of construction joint for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2161 | TT_TASK | Removal external and internal formwork for wall | Thu Feb 06 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2162 | TT_TASK | Removal internal falsework and formwork for roof | Sat Feb 15 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Thu Jan 23 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2164 | TT_TASK | Removal strut S2 @ SN 19 | Wed Apr 02 08:00:00 IDT 2014 | Mon Apr 07 18:00:00 IDT 2014 | Mon Mar 03 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 |  | COMPLETED
2165 | TT_TASK | Erect working platform to +24.0mPD | Tue Apr 08 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 | Fri Mar 07 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 |  | COMPLETED
2166 | TT_TASK | Erect internal formwork below strut S1 | Sat Apr 12 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 | Wed Mar 12 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 |  | COMPLETED
2167 | TT_TASK | Staircase construction (+21.456mPD to +23.706mPD) (20m3) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 |  | COMPLETED
2168 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 | Fri Mar 14 08:00:00 IST 2014 | Tue Apr 01 18:00:00 IDT 2014 |  | COMPLETED
2169 | TT_TASK | Erect external wall & internal wall formwork | Tue May 13 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Wed Apr 02 08:00:00 IDT 2014 | Thu Apr 03 18:00:00 IDT 2014 |  | COMPLETED
2170 | TT_TASK | Concreting (External Wall & Internal Wall) (264m3) | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Fri Apr 04 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2171 | TT_TASK | Curing (External Wall & Internal Wall) | Fri May 16 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2172 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Mon May 19 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Thu Apr 10 18:00:00 IDT 2014 |  | COMPLETED
2173 | TT_TASK | Waterproofing | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 |  | COMPLETED
2174 | TT_TASK | Backfilling | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2176 | TT_TASK | Removal strut S1 @ SN 19 | Thu Jun 19 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2177 | TT_TASK | Erect working platform to +30.406mPD | Tue Jun 24 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2178 | TT_TASK | Erect internal formwork | Sat Jun 28 08:00:00 IDT 2014 | Sat Jun 28 18:00:00 IDT 2014 | Wed Jun 04 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2179 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Mon Jun 30 08:00:00 IDT 2014 | Wed Jul 02 18:00:00 IDT 2014 | Thu Jun 05 08:00:00 IDT 2014 | Fri Jun 06 18:00:00 IDT 2014 |  | COMPLETED
2180 | TT_TASK | Erect external formwork (External Wall & Internal Wall) | Thu Jul 03 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2181 | TT_TASK | Concreting (External Wall & Internal Wall) (128m3) | Fri Jul 04 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2182 | TT_TASK | Curing (External Wall & Internal Wall) | Sat Jul 05 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 18:00:00 IDT 2014 |  | COMPLETED
2183 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Tue Jul 08 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2184 | TT_TASK | Waterproofing | Wed Jul 09 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Thu Jun 19 18:00:00 IDT 2014 |  | COMPLETED
2185 | TT_TASK | Backfilling | Sat Jul 12 08:00:00 IDT 2014 | Wed Jul 16 18:00:00 IDT 2014 | Fri Jun 20 08:00:00 IDT 2014 | Tue Jun 24 18:00:00 IDT 2014 |  | COMPLETED
2186 | TT_TASK | Erect falsework and soffit formwork +30.206mPD | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 | Wed Jun 25 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2187 | TT_TASK | Staircase construction (+21.456mPD to +25.956mPD) (20m3) | Sat Jul 19 08:00:00 IDT 2014 | Wed Jul 23 18:00:00 IDT 2014 | Fri Jun 27 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2188 | TT_TASK | Staircase construction (+25.956mPD to +27.606mPD) (20m3) | Sat Jul 05 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 05 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 |  | COMPLETED
2189 | TT_TASK | Rebar fixing (Beam, Floor Slab and Staircase) | Thu Jul 10 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Thu Jul 10 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2190 | TT_TASK | Concreting (Beam, Floor Slab and Staircase) (31m3) | Fri Jul 11 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2191 | TT_TASK | Curing (Beam, Floor Slab and Staircase) | Wed Sep 03 08:00:00 IDT 2014 | Tue Sep 09 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2193 | TT_TASK | Erect working platform to +33.576mPD | Wed Sep 03 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
2194 | TT_TASK | Erect external formwork (External Wall) | Mon Sep 08 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 | Fri Sep 26 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2195 | TT_TASK | Rebar fixing (External Wall) | Thu Sep 11 08:00:00 IDT 2014 | Fri Sep 12 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2196 | TT_TASK | Erect internal formwork (External Wall) | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 |  | COMPLETED
2197 | TT_TASK | Concreting (External Wall) (49m3) | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 |  | COMPLETED
2198 | TT_TASK | Curing (External Wall) | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 |  | COMPLETED
2199 | TT_TASK | Removal formwork (External Wall) | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
2200 | TT_TASK | Erect falsework and soffit formwork +32.656 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2201 | TT_TASK | Rebar fixing (Beam & Floor Slab) | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 |  | COMPLETED
2202 | TT_TASK | Concreting (Beam & Floor Slab) (31m3) | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 |  | COMPLETED
2203 | TT_TASK | Curing (Beam & Floor Slab) | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2205 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
2206 | TT_TASK | Rebar fixing (Roof Parapet Wall) | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 |  | COMPLETED
2207 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2208 | TT_TASK | Concreting (Roof Parapet Wall) (30m3) | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
2209 | TT_TASK | Curing (Roof Parapet Wall) | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 |  | COMPLETED
2210 | TT_TASK | Removal formwork (Roof Parapet Wall) | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2211 | TT_TASK | Removal of falsework and soffit formwork | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
2213 | TT_TASK | Wet trade work | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 |  | COMPLETED
2214 | TT_TASK | Metal works (Louver, Door, Cat-ladder, Architectural Fins, Handrail, Roof Sliding Hatch and Balustrade, etc) | Thu Nov 27 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Thu Nov 27 08:00:00 IST 2014 | Thu Mar 05 18:00:00 IST 2015 |  | COMPLETED
2215 | TT_TASK | Coat works | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2218 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Nov 29 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Feb 04 18:00:00 IST 2014 |  | COMPLETED
2219 | TT_TASK | Backfilling between D-wall and 0.5m below S1 14,240m3 soil | Thu Feb 06 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 | Wed Feb 05 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 |  | COMPLETED
2220 | TT_TASK | Removal of S1 | Wed Mar 12 08:00:00 IST 2014 | Tue Mar 25 18:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 |  | COMPLETED
2221 | TT_TASK | Backfilling to original ground level 21,390m3 (approx. +25.0mPD) | Sat Mar 01 08:00:00 IST 2014 | Wed Mar 19 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Sat May 03 18:00:00 IDT 2014 |  | COMPLETED
2223 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 |  | COMPLETED
2224 | TT_TASK | Backfilling between D-wall and 0.5m below S1 (2075m3) | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 |  | COMPLETED
2225 | TT_TASK | Removal of S1 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 |  | COMPLETED
2226 | TT_TASK | Backfilling to original ground level 3,900m3 (approx. +25.0mPD) (1353m3) | Sat Mar 01 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
2227 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
2228 | TT_TASK | Backfilling backfilling to +20mPD from SN8 to SN9 (Soil: 7,050m3 @ 500m3/day) | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 |  | COMPLETED
2229 | TT_TASK | Removal of S1 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
2230 | TT_TASK | Construction of mud pit | Sat Jul 06 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
2231 | TT_TASK | Backfilling from +20mPD to ground level from SN8 to SN9 (Soil: 5,000m3 @ 500m3/day) | Tue Aug 06 08:00:00 IDT 2013 | Sat Aug 17 18:00:00 IDT 2013 | Tue Jul 02 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 |  | COMPLETED
2233 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Aug 07 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2234 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) | Fri Aug 14 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2235 | TT_TASK | Placing mass concrete infill between tunnel and D-wall | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 02 18:00:00 IST 2015 | Thu Dec 24 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2236 | TT_TASK | Removal of S2 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 10 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 04 18:00:00 IST 2016 |  | COMPLETED
2237 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2238 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
2239 | TT_TASK | Removal strut S1 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2240 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
2241 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488 m3 of soil) | Mon Jan 25 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Fri Apr 01 18:00:00 IDT 2016 |  | COMPLETED
2243 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) (SN18-19) | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 |  | COMPLETED
2244 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) (SN18-19) | Sat Apr 26 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Sat Apr 26 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
2245 | TT_TASK | Placing mass concrete infill between tunnel and D-wall (SN18-19) | Tue May 20 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri May 16 18:00:00 IDT 2014 |  | COMPLETED
2246 | TT_TASK | Removal of S2 (SN16-18) | Wed Jun 04 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 |  | COMPLETED
2247 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) (SN16-18) | Mon Jun 09 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Tue May 27 18:00:00 IDT 2014 |  | COMPLETED
2248 | TT_TASK | Removal strut S1 (SN16-18) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Wed May 28 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
2249 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488m3 of soil) | Fri Jun 27 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
2251 | TT_TASK | Dismantling temporary bridge deck | Mon Jun 15 08:00:00 IDT 2015 | Tue Jul 21 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2252 | TT_TASK | Reinstatement of Works Area 4.10 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jan 11 18:00:00 IST 2017 | Mon May 02 08:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 |  | COMPLETED
2253 | TT_TASK | Complete all tree planting and reinstate Works Area 4.12C | Tue Nov 01 08:00:00 IST 2016 | Thu Jul 13 18:00:00 IDT 2017 | Sat Oct 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2254 | TT_TASK | Reinstate Works Areas 4.9, 4.9A and 4.12A prior to handover | Mon May 22 08:00:00 IDT 2017 | Sat Sep 02 18:00:00 IDT 2017 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2258 | TT_TASK | Application of power supply, environmental permits and construction substation | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2259 | TT_TASK | Procurement and Confirmation of the order of 2nd tunnel boring machine | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2260 | TT_TASK | TBM design and submission for approval | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2261 | TT_TASK | TBM materials order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
2262 | TT_TASK | TBM equipments order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 |  | COMPLETED
2263 | TT_TASK | TBM Fabrication | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
2264 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 |  | COMPLETED
2265 | TT_TASK | TBM test Run | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2266 | TT_TASK | TBM disassembly and packing for shipping to HK | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 |  | COMPLETED
2267 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
2268 | TT_TASK | Setup TBM facilities | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
2269 | TT_TASK | Fabrication 50% of South Tunnel South Bound Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
2270 | TT_TASK | Fabrication 100% of South Tunnel South Bound Precast Lining | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
2271 | TT_TASK | Fabrication 50% of South Tunnel North Bound Precast Lining | Wed Oct 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 | Wed Oct 03 08:00:00 IST 2012 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
2272 | TT_TASK | Fabrication 100% of South Tunnel North Bound Precast Lining | Mon Aug 26 08:00:00 IDT 2013 | Wed Jan 22 18:00:00 IST 2014 | Wed Feb 27 08:00:00 IST 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
2274 | TT_TASK | Ground treatment at lauching shaft Southbound | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
2275 | TT_TASK | TBM assemble, thrust frame, testing and commissioning | Sat Jun 01 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2276 | TT_TASK | Lowing back-up plant for final drive | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
2277 | TT_TASK | Assemble and set up back-up plant for final drive | Sat Jun 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2278 | TT_TASK | Erection of noise enclosure | Sat Jul 20 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 |  | COMPLETED
2279 | TT_TASK | TBM drive & lining installation CH124+912 to CH125+012 (Initial Drive) | Sat Jul 20 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Mon Mar 11 00:00:00 IST 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
2280 | TT_TASK | TBM drive & lining installation CH125+012 to CH125+338 | Tue Oct 15 08:00:00 IDT 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon May 27 08:00:00 IDT 2013 | Tue May 20 00:00:00 IDT 2014 |  | COMPLETED
2281 | TT_TASK | Dis-assemble TBM | Fri May 23 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 |  | COMPLETED
2282 | TT_TASK | Invert slab and side walkway | Fri Aug 01 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Tue Sep 02 18:00:00 IDT 2014 |  | COMPLETED
2283 | TT_TASK | Installation of cable bracket | Mon Nov 03 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 | Mon Aug 18 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2285 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Sep 01 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 | Sat Aug 09 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2286 | TT_TASK | Ground treatment at lauching shaft Northbound | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 19 18:00:00 IST 2013 | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
2287 | TT_TASK | TBM assemble, testing and commissioning | Wed Jul 02 08:00:00 IDT 2014 | Wed Sep 03 18:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2288 | TT_TASK | Setup back-up plant for final drive | Tue Jun 03 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2289 | TT_TASK | Reinstate of noise enclosure | Fri Oct 10 08:00:00 IDT 2014 | Wed Nov 05 18:00:00 IST 2014 | Tue Oct 28 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
2290 | TT_TASK | TBM drive & lining installation CH124+927 to CH125+027 (Initial Drive) | Fri Oct 10 08:00:00 IDT 2014 | Thu Nov 13 18:00:00 IST 2014 | Thu Oct 30 00:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
2291 | TT_TASK | TBM drive & lining installation CH125+027 to CH125+353 (Final Drive) | Fri Jan 02 08:00:00 IST 2015 | Thu Feb 12 18:00:00 IST 2015 | Mon Dec 08 08:00:00 IST 2014 | Fri Aug 07 00:00:00 IDT 2015 |  | COMPLETED
2292 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Tue Aug 04 08:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
2293 | TT_TASK | Dis-assemble TBM | Tue Aug 04 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
2294 | TT_TASK | Invert slab and side walkway | Wed Sep 09 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
2295 | TT_TASK | Installation of cable bracket | Thu Sep 24 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Aug 31 18:00:00 IDT 2015 |  | COMPLETED
2298 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Partial length) at down track | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 |  | COMPLETED
2299 | TT_TASK | Probe/Grout | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 | Mon Aug 11 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2300 | TT_TASK | Coring of Segment | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 |  | COMPLETED
2301 | TT_TASK | Removal of segment | Tue Sep 02 08:00:00 IDT 2014 | Thu Sep 04 18:00:00 IDT 2014 | Thu Aug 21 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2302 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Sep 05 08:00:00 IDT 2014 | Tue Oct 07 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2303 | TT_TASK | Invert Concrete | Thu Oct 23 08:00:00 IDT 2014 | Sat Nov 01 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2304 | TT_TASK | Wall and Roof concrete | Mon Nov 03 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Mon Oct 13 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
2305 | TT_TASK | Dismantle Temporary frame | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2306 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
2307 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Remaining length ) at down track | Sat May 09 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Thu Apr 16 18:00:00 IDT 2015 |  | COMPLETED
2308 | TT_TASK | Probe/Grout | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
2309 | TT_TASK | Coring of Segment | Fri Oct 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 | Fri Oct 16 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
2310 | TT_TASK | Removal of segment | Wed Oct 07 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
2311 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Oct 10 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Oct 26 08:00:00 IST 2015 | Fri Dec 11 18:00:00 IST 2015 |  | COMPLETED
2312 | TT_TASK | Invert Concrete | Thu Dec 03 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Sat Dec 12 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2313 | TT_TASK | Wall and Roof concrete | Mon Dec 14 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 15 18:00:00 IST 2016 |  | COMPLETED
2314 | TT_TASK | Dismantle Temporary frame | Wed Jan 13 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 |  | COMPLETED
2315 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2318 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 |  | COMPLETED
2319 | TT_TASK | Pre-drill and guide wall | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 |  | COMPLETED
2320 | TT_TASK | D-wall design review | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 |  | COMPLETED
2321 | TT_TASK | D-Wall Construction (1075m3) | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 |  | COMPLETED
2322 | TT_TASK | Shear pin, toe grout and pumping test | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 |  | COMPLETED
2324 | TT_TASK | SI for TBM ground treatment | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2325 | TT_TASK | Design review of TBM ground treatment | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2326 | TT_TASK | Ground treatment for TBM southbound | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
2327 | TT_TASK | Ground treatment for TBM northbound | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2329 | TT_TASK | Capping beam construction | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2330 | TT_TASK | L-Shape wall construction | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
2331 | TT_TASK | Excavate up to +28.5mPD (1488m3) | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 |  | COMPLETED
2332 | TT_TASK | Install Strut S1 +29.0mPD | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 |  | COMPLETED
2333 | TT_TASK | Excavate up to +23.5mPD (2480m3) | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 |  | COMPLETED
2334 | TT_TASK | Install Strut S2 +24.0mPD | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 |  | COMPLETED
2335 | TT_TASK | Excavate up to +19.5mPD (1984m3) | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
2336 | TT_TASK | Install Strut S3 +20.0mPD | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 |  | COMPLETED
2337 | TT_TASK | Excavate up to +15.5mPD (1984m3) | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
2338 | TT_TASK | Install Strut S4 +16.0mPD | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 |  | COMPLETED
2339 | TT_TASK | Excavate up to formation (4117m3) | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
2340 | TT_TASK | Install rock dowel and tie back | Sat Jun 02 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Sat Jun 02 08:00:00 IDT 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2341 | TT_TASK | Temporary handover the shaft to contract 822 | Mon Jun 03 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2343 | TT_TASK | Rock breaking works | Mon Aug 26 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
2344 | TT_TASK | Temporary base Slab for TBM Drive | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
2347 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2348 | TT_TASK | Erect external formwork (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Wed Aug 13 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Tue Aug 19 18:00:00 IDT 2014 |  | COMPLETED
2349 | TT_TASK | Rebar fixing (Base Slab) | Thu Aug 14 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Wed Aug 20 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2350 | TT_TASK | Erect internal kicker formwork (Base Slab) | Tue Aug 19 08:00:00 IDT 2014 | Thu Aug 21 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 |  | COMPLETED
2351 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 22 08:00:00 IDT 2014 | Fri Aug 22 18:00:00 IDT 2014 | Thu Aug 28 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2352 | TT_TASK | Concreting (Base Slab) (245m3) | Sat Aug 23 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014 | Fri Aug 29 18:00:00 IDT 2014 |  | COMPLETED
2353 | TT_TASK | Curing (Base Slab) | Mon Aug 25 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2354 | TT_TASK | Removal of formwork (Base Slab) | Mon Sep 08 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Mon Sep 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2355 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Sep 10 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Tue Sep 02 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 |  | COMPLETED
2356 | TT_TASK | Rebar fixing (Wall and roof) | Thu Sep 18 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Thu Sep 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2357 | TT_TASK | Erect external formwork (Wall) | Thu Sep 25 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2358 | TT_TASK | Clearing and inspection (Wall and roof) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2359 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
2360 | TT_TASK | Curing (Wall and roof) | Sat Oct 11 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
2361 | TT_TASK | Removal formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Thu Oct 16 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Sat Nov 01 18:00:00 IST 2014 |  | COMPLETED
2362 | TT_TASK | Removal formwork (Roof) | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2363 | TT_TASK | Side walkway and cable bracket (72m3) | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
2365 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Nov 07 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Sat Nov 07 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
2366 | TT_TASK | Erect external formwork (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Wed Nov 18 18:00:00 IST 2015 |  | COMPLETED
2367 | TT_TASK | Rebar fixing (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Tue Nov 17 18:00:00 IST 2015 | Thu Nov 19 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 |  | COMPLETED
2368 | TT_TASK | Erect internal kicker formwork (Base Slab) | Wed Nov 18 08:00:00 IST 2015 | Fri Nov 20 18:00:00 IST 2015 | Tue Nov 24 08:00:00 IST 2015 | Thu Nov 26 18:00:00 IST 2015 |  | COMPLETED
2369 | TT_TASK | Clearing and inspection (Base Slab) | Sat Nov 21 08:00:00 IST 2015 | Sat Nov 21 18:00:00 IST 2015 | Fri Nov 27 08:00:00 IST 2015 | Fri Nov 27 18:00:00 IST 2015 |  | COMPLETED
2370 | TT_TASK | Concreting (Base Slab) (245m3) | Mon Nov 23 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Nov 28 08:00:00 IST 2015 | Sat Nov 28 18:00:00 IST 2015 |  | COMPLETED
2371 | TT_TASK | Curing (Base Slab) | Tue Nov 24 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Mon Nov 30 08:00:00 IST 2015 | Thu Dec 03 18:00:00 IST 2015 |  | COMPLETED
2372 | TT_TASK | Removal of formwork (Base Slab) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Fri Dec 04 08:00:00 IST 2015 | Sat Dec 05 18:00:00 IST 2015 |  | COMPLETED
2373 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 09 18:00:00 IST 2015 | Mon Dec 07 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
2374 | TT_TASK | Rebar fixing (Wall and roof) | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2375 | TT_TASK | Erect external formwork (Wall) | Mon Jan 11 08:00:00 IST 2016 | Wed Jan 13 18:00:00 IST 2016 | Thu Jan 07 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2376 | TT_TASK | Clearing and inspection (Wall and roof) | Thu Jan 14 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2377 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Jan 15 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2378 | TT_TASK | Curing (Wall and roof) | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 |  | COMPLETED
2379 | TT_TASK | Removal formwork (Wall) | Tue Jan 19 08:00:00 IST 2016 | Thu Jan 21 18:00:00 IST 2016 | Thu Jan 28 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2380 | TT_TASK | Removal formwork and falsework (Roof) | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Sat Jan 30 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2381 | TT_TASK | Side walkway and cable bracket (72m3) | Wed Jan 06 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Thu Nov 12 08:00:00 IST 2015 | Tue Mar 01 18:00:00 IST 2016 |  | COMPLETED
2382 | TT_TASK | Provision access opening to DC | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2383 | TT_TASK | Erect falsework and soffit formwork (Opening) | Thu Mar 10 08:00:00 IST 2016 | Mon Mar 21 18:00:00 IST 2016 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2384 | TT_TASK | Rebar fixing (Roof) | Tue Mar 22 08:00:00 IST 2016 | Tue Mar 22 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2385 | TT_TASK | Clearing and inspection (Roof) | Wed Mar 23 08:00:00 IST 2016 | Wed Mar 23 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2386 | TT_TASK | Concreting (Roof) (225m3) | Thu Mar 24 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2387 | TT_TASK | Curing (Roof) | Tue Mar 29 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Jan 13 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
2388 | TT_TASK | Removal internal falsework and soffit formwork (Roof) | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
2390 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Thu Mar 17 08:00:00 IST 2016 | Fri Mar 18 18:00:00 IST 2016 | Tue Mar 01 08:00:00 IST 2016 | Wed Mar 02 18:00:00 IST 2016 |  | COMPLETED
2391 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Sat Mar 19 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Thu Mar 03 08:00:00 IST 2016 | Tue Mar 08 18:00:00 IST 2016 |  | COMPLETED
2392 | TT_TASK | Backfilling to +18.25mPD (1229 m3 of soil) | Sat Jul 02 08:00:00 IDT 2016 | Mon Jul 11 18:00:00 IDT 2016 | Mon Jul 25 08:00:00 IDT 2016 | Tue Aug 02 18:00:00 IDT 2016 |  | COMPLETED
2393 | TT_TASK | Laying 500mm mass concrete lateral support | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 |  | COMPLETED
2394 | TT_TASK | Backfilling to 0.5m below S3 (+19.5mPD) (372m3 of soil) | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 |  | COMPLETED
2395 | TT_TASK | Removal strut S3 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 |  | COMPLETED
2396 | TT_TASK | Backfilling to 0.5m below S2 (+23.5mPD) (1984m3 of soil) | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 |  | COMPLETED
2397 | TT_TASK | Removal strut S2 | Wed Aug 24 08:00:00 IDT 2016 | Fri Aug 26 18:00:00 IDT 2016 | Wed Aug 24 08:00:00 IDT 2016 | Thu Sep 01 18:00:00 IDT 2016 |  | COMPLETED
2398 | TT_TASK | Backfilling to 0.5m below S1 (+28.5mPD) (2480m3 of soil) | Mon Sep 05 08:00:00 IDT 2016 | Tue Sep 20 18:00:00 IDT 2016 | Fri Sep 02 08:00:00 IDT 2016 | Fri Sep 09 18:00:00 IDT 2016 |  | COMPLETED
2399 | TT_TASK | Removal strut S1 | Wed Sep 21 08:00:00 IDT 2016 | Thu Sep 22 18:00:00 IDT 2016 | Sat Sep 10 08:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 |  | COMPLETED
2400 | TT_TASK | Backfilling to original ground level (approx. +31.5mPD) (1488m3 of soil) | Fri Sep 23 08:00:00 IDT 2016 | Mon Oct 03 18:00:00 IDT 2016 | Thu Sep 15 08:00:00 IDT 2016 | Mon Sep 19 18:00:00 IDT 2016 |  | COMPLETED
2402 | TT_TASK | Reinstatement of TUT area (Including Hydroseeding) | Mon Oct 03 08:00:00 IDT 2016 | Mon Jun 19 18:00:00 IDT 2017 | Fri Oct 07 08:00:00 IDT 2016 |  | 216.0 | IN_PROGRESS
25 | TT_TASK | Access opening for the up track cut and cover tunnel at Tse Uk Tsuen Shaft | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 10 18:00:00 IST 2016 |  | COMPLETED
27 | TT_TASK | Close out the temporary access opening at Tse Uk Tsuen Shaft | Thu Mar 10 08:00:00 IST 2016 | Tue Apr 05 18:00:00 IDT 2016 | Thu Feb 11 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
307 | TT_TASK | Position crane for TBM retrieval (down track) | Wed Jul 02 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014 | Sat Aug 02 18:00:00 IDT 2014 |  | COMPLETED
308 | TT_TASK | TBM Break-in and Retrieval (down track) | Mon Aug 04 08:00:00 IDT 2014 | Sat Aug 30 18:00:00 IDT 2014 | Mon Aug 04 08:00:00 IDT 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
309 | TT_TASK | Position crane for TBM retrieval (up track) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 |  | COMPLETED
310 | TT_TASK | TBM Break-in and Retrieval (up track) | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
376 | TT_TASK | Supply Engineer with Survey Equipment [PS41.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
377 | TT_TASK | Provide Engineer with suitably qualified full time Survey Assistant - 4 nos. [PS41.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
378 | TT_TASK | Provide Engineer with site transportation as detailed in PS42.1 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 |  | COMPLETED
379 | TT_TASK | Submit details of qualified drivers to be assigned to the Engineer, for review [PS42.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 |  | COMPLETED
380 | TT_TASK | Install, service and maintain 10 container offices for use by the Engineer's Site Staff | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
381 | TT_TASK | Provide services and equipment for the Engineer | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
383 | TT_TASK | Master Programme - Prepare and submit for approval [GS4.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
384 | TT_TASK | Master Programme - Comments , Resubmission and Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
385 | TT_TASK | Time Chainage Programme - Prepare and submit for approval [GS4.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
386 | TT_TASK | Time Chainage Programme - Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
387 | TT_TASK | Implement and Maintain Programme Management System for 1st Audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
388 | TT_TASK | Implement and Maintain Programme Management System for 2nd Audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
389 | TT_TASK | Implement and Maintain Programme Management System for 3rd Audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
391 | TT_TASK | Environmental Management Plan - Prepare and submit for approval [GS5.1.10] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
392 | TT_TASK | Environmental Management Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
393 | TT_TASK | Quality Plan - Prepare and submit for approval [GS9.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
394 | TT_TASK | Quality Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
395 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 1st audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 |  | COMPLETED
396 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 2nd audit | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
397 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 3rd audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
398 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 4th audit | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
399 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 5th audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
400 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 6th audit | Tue Jul 02 08:00:00 IDT 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
401 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 7th audit | Thu Nov 28 08:00:00 IST 2013 | Thu Jun 05 18:00:00 IDT 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Jan 24 18:00:00 IST 2014 |  | COMPLETED
402 | TT_TASK | Health and Safety Plan - Prepare and submit [G3.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
403 | TT_TASK | System Assurance Plan - Prepare and submit for approval [PS Appendix P3.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
404 | TT_TASK | System Assurance Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
405 | TT_TASK | Design for Safety & Constructability Plan - Prepare and submit for approval [PS37.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
406 | TT_TASK | Design for Safety & Constructability Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
408 | TT_TASK | Methods of Construction - Prepare and submit for approval [GS12.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
409 | TT_TASK | Methods of Construction - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
410 | TT_TASK | Contractor's Submission Schedule - Prepare and submit for approval [GS12.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
411 | TT_TASK | Contractor's Submission Schedule - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
412 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) [PS13.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
413 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) - Approval period | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 |  | COMPLETED
414 | TT_TASK | Spoil Disposal Plan [PS17.7.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
415 | TT_TASK | Waste Management Plan [PS22.10.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
416 | TT_TASK | Independent Checking Engineer - Appoint and submit for approval [PS7.1.8] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
417 | TT_TASK | Independent Checking Engineer - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
418 | TT_TASK | Sub-contract Management Plan - Prepare and submit [PS34.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 |  | COMPLETED
419 | TT_TASK | Schedule of Utilities Services Arrangement [GS7.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
420 | TT_TASK | Site Safety Supervision Plan for Site Formation - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
421 | TT_TASK | Site Safety Supervision Plan for Site Formation - Approval period | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
422 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Prepare and Submit | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
423 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
424 | TT_TASK | Site Safety Supervision Plan for ELS - Prepare and Submit | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
425 | TT_TASK | Site Safety Supervision Plan for ELS - Approval Period | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
426 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Prepare and Submit | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
427 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Approval Period | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
428 | TT_TASK | Noise Management Plan [P22.3.9] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
429 | TT_TASK | Air Quality Management Plan [P22.4.3] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
430 | TT_TASK | Detailed Proposal for Water Pollution Control Measures and Proposed Monitoring [PS22.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
431 | TT_TASK | Groundwater Monitoring and Response Plan [PS22.5.2] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
432 | TT_TASK | Vibration Monitoring Plan [PS22.8.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 |  | COMPLETED
433 | TT_TASK | Proposed Outline TTM Scheme - Prepare & submit to the: Engineer for Review / SLG for Approval [PS19.3] | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 |  | COMPLETED
434 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Proposed TTM Scheme [PS19.4] | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 |  | COMPLETED
435 | TT_TASK | Resubmission of Proposed Outline TTM Scheme (if required) | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
436 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Resubmitted Proposed Outline TTM Scheme [PS19.4] | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 |  | COMPLETED
437 | TT_TASK | Notification Period of the Approved TTM Scheme prior to implementation [PS19.4] | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 |  | COMPLETED
440 | TT_TASK | Initial Site Survey (WA3.11) | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 |  | COMPLETED
441 | TT_TASK | Initial Site Survey Report (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 |  | COMPLETED
442 | TT_TASK | Initial Site Survey & Condition Survey (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
443 | TT_TASK | Initial Site Survey Report (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
444 | TT_TASK | Initial Site Survey & Condition Survey (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
445 | TT_TASK | Initial Site Survey Report (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
446 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 4.9 & 4.12A [PS4.2] | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
447 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 5.1 & 5.3 [PS4.2.3] | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 |  | COMPLETED
448 | TT_TASK | Proposal for Site Clearance Works [PS4.4.1] | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 |  | COMPLETED
449 | TT_TASK | Site Clearance / Site Formation Works (including demolition of EBS) | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
450 | TT_TASK | Backfill existing stream courses in Works Area 4.9, 4.10 and 4.11 [PS18.5.1] | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
451 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and submit to EPD for Approval (WA3.3 - Area M, I, L) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
452 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA3.3 - Area M, I, L) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
453 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
454 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
455 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.3 - Area M, I, L) | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
456 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA3.3 - Area M, I, L) | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
457 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA3.3 - Area M, I, L) | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
458 | TT_TASK | Remediation Report - Approval (WA3.3 - Area M, I, L) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
459 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and Submit to EPD for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
460 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
461 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
462 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.1, 3.2, 3.3, 3.3A) | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
463 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.1, 3.2, 3.3, 3.3A) | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 |  | COMPLETED
464 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 |  | COMPLETED
465 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
466 | TT_TASK | Remediation Report - Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
467 | TT_TASK | Conduct remediation for Area Q in accordance with method proposed in the approved Remediation Action Plan [PS22.9.2] | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 |  | COMPLETED
468 | TT_TASK | Remediation Report - Prepare and submit for Approval [PS22.9.2] (Area Q) | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 |  | COMPLETED
469 | TT_TASK | Remediation Report - Approval (Area Q) | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
470 | TT_TASK | Removal of contaminated soil at North Tunnels (Area N,O,P,Q,R,S) | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
471 | TT_TASK | Condition Survey EBS for presence of Asbestos and gather samples | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
472 | TT_TASK | Testing of gathered samples | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 |  | COMPLETED
473 | TT_TASK | Prepare and submit Asbestos Investigation Report (AIR) & Asbestos Abatement Plan (AAP) | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
474 | TT_TASK | Approval period of AIR & AAP | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
475 | TT_TASK | Notification period to Engineer and EPD prior to Asbestos abatement works | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
476 | TT_TASK | Asbestos abatement works | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
477 | TT_TASK | Demolition of EBS | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
478 | TT_TASK | Confirmation of tree survey | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 |  | COMPLETED
480 | TT_TASK | Installation of ground settlement markers | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 |  | COMPLETED
481 | TT_TASK | Settlement monitoring and submit report | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
482 | TT_TASK | Settlement monitoring and submit report | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 |  | COMPLETED
483 | TT_TASK | Settlement monitoring and submit report | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
484 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
485 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Wed Feb 26 18:00:00 IST 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Feb 21 18:00:00 IST 2014 |  | COMPLETED
486 | TT_TASK | Settlement monitoring and submit report | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 |  | COMPLETED
488 | TT_TASK | Permit Applications (incl. License to Search and Excavate Antiquities and Excavation Permit) | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 |  | COMPLETED
489 | TT_TASK | Check for underground utilities | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 |  | COMPLETED
490 | TT_TASK | Field walking and hand augering | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 |  | COMPLETED
491 | TT_TASK | Excavation of trial pits | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 |  | COMPLETED
492 | TT_TASK | Rescue excavation rescue works (if required) | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 |  | COMPLETED
494 | TT_TASK | Erection of Hoarding with Gate (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 |  | COMPLETED
495 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 3.1, 3.2, 3.3 and 3.3A [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
496 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 4.9, 4.10, 4.11, 4.12A~C, and 4.15 [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
497 | TT_TASK | Project Signboard Erection [PS4.6.8] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
498 | TT_TASK | Marine Survey at Barging Point [PS4.3] (before construction of barging facilities) | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 00:00:00 IST 2010 |  | COMPLETED
499 | TT_TASK | Construct barging facilities | Sat Oct 02 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Oct 02 00:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
500 | TT_TASK | Operation Plan for the Barging Facility - Prepare and Submit for Approval [PS17.1.9] | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
501 | TT_TASK | Operation Plan for the Barging Facility - Review and Approval Period | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 |  | COMPLETED
503 | TT_TASK | General and Special Attendance for Designated Contractors | Mon Dec 02 08:00:00 IST 2013 | Mon Aug 31 18:00:00 IDT 2015 | Tue Jul 02 08:00:00 IDT 2013 | Wed Mar 25 18:00:00 IST 2015 |  | COMPLETED
505 | TT_TASK | Prepare and Submit Detailed Interface Specification | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 |  | COMPLETED
506 | TT_TASK | Approval of Detailed Interface Plan | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
507 | TT_TASK | Prepare and Submit Detailed Interface Specification | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 |  | COMPLETED
508 | TT_TASK | Approval of Detailed Interface Plan | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
510 | TT_TASK | Prepare and Submit Draft Operation and Maintenance Manual [PS33.1] | Mon Aug 24 08:00:00 IDT 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jul 28 08:00:00 IDT 2014 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
511 | TT_TASK | Review and approval period of Draft Operation and Maintenance Manual | Wed Aug 10 08:00:00 IDT 2016 | Tue Sep 13 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
512 | TT_TASK | Prepare and Submit Final Operation and Maintenance Manual [PS33.1] | Wed Sep 14 08:00:00 IDT 2016 | Thu Feb 16 18:00:00 IST 2017 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
513 | TT_TASK | Provide Engineer with As-Built Drawing for the Whole of the Works [PS33.2] | Mon Nov 21 08:00:00 IST 2016 | Wed Dec 14 18:00:00 IST 2016 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
514 | TT_TASK | Provide Engineer with Asset Registration Information [PS33.3] | Fri May 19 08:00:00 IDT 2017 | Mon Jun 12 18:00:00 IDT 2017 |  |  |  | NOT_STARTED
517 | TT_TASK | Preliminary Design Programme - Prepare and Submit for Approval [PS7.1.8 - App. Z2.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
518 | TT_TASK | Preliminary Design Programme - Review and Approval Period [PS7.1.8 - App. Z2.2] | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 |  | COMPLETED
519 | TT_TASK | Preliminary Design Programme - Resubmission and Approval (if required) [PS7.1.8 - App. Z2.2] | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 |  | COMPLETED
520 | TT_TASK | Schedule of Designs - Prepare and Submit for Approval [PS7.1.8 - App. Z2.5] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
521 | TT_TASK | Detailed Proposal for Carrying Out the Cross Passage Works [PS11.5.2] | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
524 | TT_TASK | Design TBM and submit full details to the Engineer [PS7.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
525 | TT_TASK | TBM Design - Approval period | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 |  | COMPLETED
526 | TT_TASK | TBM Design - Resubmission and approval period | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 |  | COMPLETED
528 | TT_TASK | AIP Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
529 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 |  | COMPLETED
530 | TT_TASK | DDS Design - Prepare and Submit | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 |  | COMPLETED
531 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 |  | COMPLETED
532 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 |  | COMPLETED
533 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 |  | COMPLETED
534 | TT_TASK | Issue Completed Working Drawings | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
536 | TT_TASK | AIP Design - Prepare and Submit | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 |  | COMPLETED
537 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 |  | COMPLETED
538 | TT_TASK | AIP Design - Response to comments and Resubmit | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
539 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
540 | TT_TASK | DDS Design - Prepare and Submit | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
541 | TT_TASK | DDS Design - Review and Approval Period (by MTRC & related Government Authorities) | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 |  | COMPLETED
542 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 |  | COMPLETED
543 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 |  | COMPLETED
544 | TT_TASK | Issue Completed Working Drawings | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 |  | COMPLETED
546 | TT_TASK | DDS Design - Prepare and Submit | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 |  | COMPLETED
547 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 |  | COMPLETED
548 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 |  | COMPLETED
549 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 |  | COMPLETED
550 | TT_TASK | Issue Completed Working Drawings | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
552 | TT_TASK | AIP Design - Prepare and Submit | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 |  | COMPLETED
553 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
554 | TT_TASK | AIP Design - Response to comments and Resubmit | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 |  | COMPLETED
555 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
556 | TT_TASK | DDS Design - Prepare and Submit | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 |  | COMPLETED
557 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 |  | COMPLETED
558 | TT_TASK | DDS Design - Response to comments and Resubmit | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 |  | COMPLETED
559 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 |  | COMPLETED
560 | TT_TASK | Issue Completed Working Drawings | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 |  | COMPLETED
562 | TT_TASK | Prepare and Submit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 |  | COMPLETED
563 | TT_TASK | Review and Approval Period | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
564 | TT_TASK | Response to comments and Resubmit | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 |  | COMPLETED
565 | TT_TASK | Review and Approval Period (for resubmission) | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 |  | COMPLETED
568 | TT_TASK | DDS Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
569 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 |  | COMPLETED
570 | TT_TASK | DDS Design - Response to comments and Resubmit | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 |  | COMPLETED
571 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 |  | COMPLETED
572 | TT_TASK | Issue Completed Working Drawings | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
574 | TT_TASK | DDS Design - Prepare and Submit | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 |  | COMPLETED
575 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 |  | COMPLETED
576 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 |  | COMPLETED
577 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 |  | COMPLETED
578 | TT_TASK | Issue Completed Working Drawings | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 |  | COMPLETED
580 | TT_TASK | DDS Design - Prepare and Submit | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 |  | COMPLETED
581 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 |  | COMPLETED
582 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 |  | COMPLETED
583 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 |  | COMPLETED
584 | TT_TASK | Issue Completed Working Drawings | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 |  | COMPLETED
586 | TT_TASK | DDS Design - Prepare and Submit | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 |  | COMPLETED
587 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 |  | COMPLETED
588 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 |  | COMPLETED
589 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 |  | COMPLETED
590 | TT_TASK | Issue Completed Working Drawings | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 |  | COMPLETED
592 | TT_TASK | DDS Design - Prepare and Submit | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 |  | COMPLETED
593 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 |  | COMPLETED
594 | TT_TASK | DDS Design - Response to comments and Resubmit | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 |  | COMPLETED
595 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 |  | COMPLETED
596 | TT_TASK | Issue Completed Working Drawings | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
599 | TT_TASK | Formworks / Falsework - Prepare & Submit | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
600 | TT_TASK | Formworks / Falsework - Review & Approval Period (by MTRC) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
601 | TT_TASK | Formworks / Falsework - Response to comments and Resubmit | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 |  | COMPLETED
602 | TT_TASK | Formworks / Falsework - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
605 | TT_TASK | Layout of Site Hoarding - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
606 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (by MTRC) | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
607 | TT_TASK | Layout of Site Hoarding - Response to comments and Resubmit | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
608 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 |  | COMPLETED
610 | TT_TASK | Layout of Engineer's Accommodation - Prepare and Submit | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
611 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (by MTRC) | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 |  | COMPLETED
612 | TT_TASK | Layout of Engineer's Accommodation - Response to comments and Resubmit | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
613 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (for resubmit) (by MTRC & related Government Authorities | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
615 | TT_TASK | TTMS Assessment Report - Prepare and Submit | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 |  | COMPLETED
616 | TT_TASK | TTMS Assessment Report - Review and Approval Period (by MTRC) | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
617 | TT_TASK | TTMS Assessment Report - Response to comments and Resubmit | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 |  | COMPLETED
618 | TT_TASK | TTMS Assessment Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
619 | TT_TASK | Issue Completed Working Drawings | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 |  | COMPLETED
621 | TT_TASK | DIA Report - Prepare and Submit | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 |  | COMPLETED
622 | TT_TASK | DIA Report - Review and Approval Period (by MTRC) | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 |  | COMPLETED
623 | TT_TASK | DIA Report - Response to comments and Resubmit | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 |  | COMPLETED
624 | TT_TASK | DIA Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
625 | TT_TASK | Issue Completed Working Drawings | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 |  | COMPLETED
627 | TT_TASK | AIP Design - Prepare & Submit | Wed Sep 23 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 |  | COMPLETED
628 | TT_TASK | AIP Design - Review & Approval Period (by MTR) | Wed Oct 14 08:00:00 IDT 2015 | Wed Nov 11 18:00:00 IST 2015 | Mon Jun 08 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
629 | TT_TASK | AIP Design - Response to comments and Resubmit | Thu Nov 12 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Mon Jun 15 01:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
630 | TT_TASK | AIP Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jun 22 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
631 | TT_TASK | DDS Design - Prepare & Submit | Wed Jan 13 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Tue Sep 01 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 |  | COMPLETED
632 | TT_TASK | DDS Design - Review & Approval Period (by MTRC) | Fri Feb 26 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 12 18:00:00 IDT 2015 |  | COMPLETED
633 | TT_TASK | DDS Design - Response to comments & Resubmit | Tue Mar 29 08:00:00 IDT 2016 | Fri Apr 01 18:00:00 IDT 2016 | Mon Sep 14 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
634 | TT_TASK | DDS Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Apr 02 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 | Mon Sep 21 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
635 | TT_TASK | Issue Completed Working Drawings | Wed Jan 27 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
637 | TT_TASK | Layout of Barging Point - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
638 | TT_TASK | Layout of Barging Point - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
639 | TT_TASK | Layout of Barging Point - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
640 | TT_TASK | Layout of Barging Point - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
641 | TT_TASK | Loading Ramps - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
642 | TT_TASK | Loading Ramps - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
643 | TT_TASK | Loading Ramps - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
644 | TT_TASK | Loading Ramps - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
645 | TT_TASK | Weighbridge - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
646 | TT_TASK | Weighbridge - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
647 | TT_TASK | Weighbridge - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
648 | TT_TASK | Weighbridge - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
652 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
653 | TT_TASK | Pre-drill and guide wall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
654 | TT_TASK | D-wall construction (1084m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
655 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
656 | TT_TASK | Wang Toi Shan Shan Tsuen Road diversion works | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 |  | COMPLETED
658 | TT_TASK | Excavate up to +10.5mPD (369m3) | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 |  | COMPLETED
659 | TT_TASK | Install Strut S0 +11.0mPD | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 |  | COMPLETED
660 | TT_TASK | Excavate up to +8.0mPD (1525m3) | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 |  | COMPLETED
661 | TT_TASK | Install Strut S1 +8.5mPD | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 |  | COMPLETED
662 | TT_TASK | Excavate up to +4.5mPD (2135m3) | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 |  | COMPLETED
663 | TT_TASK | Install Strut S2 +5.0mPD | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 |  | COMPLETED
664 | TT_TASK | Excavate up to +0.5mPD (2440m3) | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 |  | COMPLETED
665 | TT_TASK | Install Strut S3 +1.0mPD | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 |  | COMPLETED
666 | TT_TASK | Excavate up to -6.5mPD (4340m3) | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 |  | COMPLETED
667 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
668 | TT_TASK | Construction of temporary slab and entrance seal (622m3) | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
672 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 08 18:00:00 IST 2014 | Fri Dec 05 08:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
673 | TT_TASK | Erect external formwork (Base Slab) | Tue Dec 09 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 08 08:00:00 IST 2014 | Tue Dec 09 18:00:00 IST 2014 |  | COMPLETED
674 | TT_TASK | Rebar fixing (Base Slab) | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 18:00:00 IST 2014 | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
675 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Dec 15 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Mon Dec 15 18:00:00 IST 2014 |  | COMPLETED
676 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Dec 17 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Tue Dec 16 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 |  | COMPLETED
677 | TT_TASK | Curing (Base Slab) | Thu Dec 18 08:00:00 IST 2014 | Sat Dec 27 18:00:00 IST 2014 | Wed Dec 17 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
678 | TT_TASK | Removal of formwork (Base Slab) | Fri Dec 19 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 24 18:00:00 IST 2014 |  | COMPLETED
679 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
680 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 | Mon Jun 22 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 |  | COMPLETED
681 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Jun 13 08:00:00 IDT 2015 | Mon Jun 15 18:00:00 IDT 2015 | Thu Jun 25 01:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
682 | TT_TASK | Concreting (Wall & Roof) (444m3) | Tue Jun 16 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
683 | TT_TASK | Curing (Wall & Roof) | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
684 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 |  | COMPLETED
685 | TT_TASK | Removal external formwork (Wall) | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
686 | TT_TASK | Side walkway and cable bracket (360m3) | Sat Jul 18 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Sat Jul 18 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
687 | TT_TASK | Access opening to DC (DC access period) | Tue Oct 06 08:00:00 IDT 2015 | Fri Mar 04 18:00:00 IST 2016 | Tue Oct 06 08:00:00 IDT 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
688 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Sat Dec 12 08:00:00 IST 2015 | Mon Jan 18 18:00:00 IST 2016 | Tue Nov 03 00:00:00 IST 2015 | Mon Nov 30 18:00:00 IST 2015 |  | COMPLETED
690 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 | Tue Apr 12 08:00:00 IDT 2016 | Wed Apr 13 18:00:00 IDT 2016 |  | COMPLETED
691 | TT_TASK | Erect external formwork (Base Slab) | Mon May 23 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Thu Apr 14 08:00:00 IDT 2016 | Fri Apr 15 18:00:00 IDT 2016 |  | COMPLETED
692 | TT_TASK | Rebar fixing (Base Slab) | Wed May 25 08:00:00 IDT 2016 | Fri May 27 18:00:00 IDT 2016 | Sat Apr 16 08:00:00 IDT 2016 | Tue Apr 19 18:00:00 IDT 2016 |  | COMPLETED
693 | TT_TASK | Erect internal kicker formwork (Base Slab) | Sat May 28 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 | Wed Apr 20 08:00:00 IDT 2016 | Thu Apr 21 18:00:00 IDT 2016 |  | COMPLETED
694 | TT_TASK | Concreting (Base Slab) (225m3) | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 | Fri Apr 22 08:00:00 IDT 2016 | Fri Apr 22 18:00:00 IDT 2016 |  | COMPLETED
695 | TT_TASK | Curing (Base Slab) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 08 18:00:00 IDT 2016 | Sat Apr 23 08:00:00 IDT 2016 | Fri Apr 29 18:00:00 IDT 2016 |  | COMPLETED
696 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Sat Apr 30 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
697 | TT_TASK | Removal of formwork (Base Slab) | Tue May 24 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Mon May 09 08:00:00 IDT 2016 | Tue May 10 18:00:00 IDT 2016 |  | COMPLETED
698 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed May 25 08:00:00 IDT 2016 | Sat May 28 18:00:00 IDT 2016 | Wed May 11 08:00:00 IDT 2016 | Mon May 16 18:00:00 IDT 2016 |  | COMPLETED
699 | TT_TASK | Rebar fixing (Wall & Roof) | Mon May 30 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 17 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 |  | COMPLETED
700 | TT_TASK | Erect external formwork (Wall & Roof) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 03 18:00:00 IDT 2016 | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 |  | COMPLETED
701 | TT_TASK | Concreting (Wall & Roof) (444m3) | Sat Jun 04 08:00:00 IDT 2016 | Sat Jun 04 18:00:00 IDT 2016 | Mon May 23 08:00:00 IDT 2016 | Mon May 23 18:00:00 IDT 2016 |  | COMPLETED
702 | TT_TASK | Curing (Wall & Roof) | Mon Jun 06 08:00:00 IDT 2016 | Tue Jun 14 18:00:00 IDT 2016 | Tue May 24 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 |  | COMPLETED
703 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 15 08:00:00 IDT 2016 | Wed Jun 15 18:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 |  | COMPLETED
704 | TT_TASK | Removal external formwork (Wall) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
705 | TT_TASK | Side walkway and cable bracket (102m3) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 |  | COMPLETED
706 | TT_TASK | Access opening to DC (DC access period) | Sat Jun 18 08:00:00 IDT 2016 | Thu Jul 14 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
707 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Fri Jul 15 08:00:00 IDT 2016 | Wed Aug 17 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
709 | TT_TASK | Backfilling between tunnels (2000m3) | Thu Sep 01 08:00:00 IDT 2016 | Sat Sep 17 18:00:00 IDT 2016 | Tue Sep 13 08:00:00 IDT 2016 | Fri Sep 30 18:00:00 IDT 2016 |  | COMPLETED
710 | TT_TASK | Remove Strut S2 | Mon Oct 03 08:00:00 IDT 2016 | Wed Oct 05 18:00:00 IDT 2016 | Mon Oct 03 08:00:00 IDT 2016 | Tue Oct 11 18:00:00 IDT 2016 |  | COMPLETED
711 | TT_TASK | Backfilling up top S1 Soffit | Thu Oct 06 08:00:00 IDT 2016 | Fri Oct 21 18:00:00 IDT 2016 | Fri Oct 28 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
712 | TT_TASK | Remove Strut S1 | Sat Oct 22 08:00:00 IDT 2016 | Mon Oct 24 18:00:00 IDT 2016 | Tue Oct 11 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
713 | TT_TASK | Backfilling up top S0 Soffit | Mon Nov 07 08:00:00 IST 2016 | Sat Nov 12 18:00:00 IST 2016 | Tue Nov 01 08:00:00 IST 2016 | Sat Nov 05 18:00:00 IST 2016 |  | COMPLETED
714 | TT_TASK | Remove Strut S0 | Mon Nov 14 08:00:00 IST 2016 | Tue Nov 15 18:00:00 IST 2016 | Mon Nov 07 08:00:00 IST 2016 | Tue Nov 08 18:00:00 IST 2016 |  | COMPLETED
715 | TT_TASK | Backfilling up to ground level | Wed Nov 16 08:00:00 IST 2016 | Fri Nov 18 18:00:00 IST 2016 | Wed Nov 09 08:00:00 IST 2016 | Fri Nov 11 18:00:00 IST 2016 |  | COMPLETED
719 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
720 | TT_TASK | Pre-drilling and guidewall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
721 | TT_TASK | D-wall construction (1451m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
722 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 |  | COMPLETED
724 | TT_TASK | Excavate from ground level to formation level -5.5mPD (4559m3) | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 |  | COMPLETED
725 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 |  | COMPLETED
726 | TT_TASK | Placing of blinding layer (South Bound) | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 |  | COMPLETED
727 | TT_TASK | Placing of blinding layer (North Bound) | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
729 | TT_TASK | Construction of Bay 2 to Bay 7a (3565m3) | Mon Jun 04 08:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 | Mon Jun 04 18:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 |  | COMPLETED
730 | TT_TASK | Side walkway and cable bracket (Southbound) | Fri Oct 02 08:00:00 IDT 2015 | Fri Nov 06 18:00:00 IST 2015 | Fri Oct 02 08:00:00 IDT 2015 | Sat Oct 31 18:00:00 IST 2015 |  | COMPLETED
731 | TT_TASK | Side walkway and cable bracket (Northbound) | Tue May 03 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 |  | COMPLETED
733 | TT_TASK | Backfilling (1344m3) | Wed Nov 07 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 | Wed Nov 07 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
736 | TT_TASK | Scheme Design, Mobilization, Site set up & Material delivery and Instrumentations | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
737 | TT_TASK | Downstream pipe pile wall construction (45 nos.) and grout curtain (45 nos.) | Mon Nov 12 08:00:00 IST 2012 | Fri Jan 25 18:00:00 IST 2013 | Mon Nov 12 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
738 | TT_TASK | Curtain Grout for cut slope (120 nos.) | Fri Jul 26 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
739 | TT_TASK | Drilling for ground improvement only (if require) | Mon Dec 10 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
740 | TT_TASK | If settlement reach the AAA alarm & action level TAM grouting will apply during excavation | Thu Apr 11 08:00:00 IDT 2013 | Thu May 16 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
741 | TT_TASK | Erection of temporary working platform for Up stream and Installation of Instrumentation System | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
742 | TT_TASK | Upstream pipe pile wall construction adjacent to WTSSTR, (17nos.) | Thu Dec 27 08:00:00 IST 2012 | Mon Jan 28 18:00:00 IST 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
743 | TT_TASK | Upstream pipe pile wall construction at Kam Tin River, 15m depth, 42nos. 1drill rig) | Tue Jan 29 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
744 | TT_TASK | Excavation and soil nail installation | Tue Apr 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
745 | TT_TASK | Excavation for rock and blinding layer | Sat Aug 24 08:00:00 IDT 2013 | Sat Sep 28 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
750 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
751 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
752 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
753 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
754 | TT_TASK | Concreting (164m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
755 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
756 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
757 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
758 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
759 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
760 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
761 | TT_TASK | Concreting (242m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
762 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
763 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
764 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
765 | TT_TASK | Removal internal falsework and formwork for roof | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
766 | TT_TASK | Side walkway and cable bracket (19m3) | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
770 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
771 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
772 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
773 | TT_TASK | Erect internal kicker formwork | Thu Nov 28 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 09 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
774 | TT_TASK | Concreting (121m3) | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
775 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
776 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
777 | TT_TASK | Removal of formwork | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
778 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
779 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
780 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
781 | TT_TASK | Concreting (121m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
782 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
783 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
784 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
785 | TT_TASK | Removal internal falsework and formwork for roof | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
786 | TT_TASK | Side walkway and cable bracket (38m3) | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
788 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
789 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
790 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
791 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
792 | TT_TASK | Concreting (240m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
793 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
794 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
795 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
796 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
797 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
798 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
799 | TT_TASK | Concreting (240m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
800 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
801 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
802 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
803 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
804 | TT_TASK | Side walkway and cable bracket | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
806 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
807 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
808 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
809 | TT_TASK | Concreting (222m3) | Wed Nov 06 08:00:00 IST 2013 | Wed Nov 06 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
810 | TT_TASK | Curing | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
811 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
812 | TT_TASK | Removal of formwork | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
815 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
816 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
817 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
818 | TT_TASK | Erect internal kicker formwork | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
819 | TT_TASK | Concreting (111m3) | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
820 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
821 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
822 | TT_TASK | Removal of formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
823 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
824 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
825 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
826 | TT_TASK | Concreting (220m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
827 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
828 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
829 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
830 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
831 | TT_TASK | Side walkway and cable bracket (38m3) | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 |  | COMPLETED
833 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
834 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
835 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
836 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
837 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
838 | TT_TASK | Curing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
839 | TT_TASK | Preparation of construction joint for base slab | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
840 | TT_TASK | Removal of formwork | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
841 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
842 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
843 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
844 | TT_TASK | Concreting (327m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
845 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
846 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
847 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
848 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
849 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
851 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 20 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
852 | TT_TASK | Rebar fixing | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
853 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 08:00:00 IDT 2013 |  | COMPLETED
854 | TT_TASK | Concreting (225m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
855 | TT_TASK | Curing | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
856 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
857 | TT_TASK | Removal of formwork | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
860 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 27 08:00:00 IST 2013 | Wed Nov 27 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
861 | TT_TASK | Erect external formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
862 | TT_TASK | Rebar fixing | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
863 | TT_TASK | Erect internal kicker formwork | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
864 | TT_TASK | Concreting (222m3) | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
865 | TT_TASK | Curing | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Mon Oct 28 18:00:00 IST 2013 |  | COMPLETED
866 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
867 | TT_TASK | Removal of formwork | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
868 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
869 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
870 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
871 | TT_TASK | Concreting (222m3) | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 |  | COMPLETED
872 | TT_TASK | Curing | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 07 18:00:00 IST 2014 |  | COMPLETED
873 | TT_TASK | Preparation of construction joint for wall and roof | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
874 | TT_TASK | Removal external and internal formwork for wall | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
875 | TT_TASK | Removal internal falsework and formwork for roof | Mon Feb 10 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
876 | TT_TASK | Side walkway and cable bracket (38m3) | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 |  | COMPLETED
878 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
879 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
880 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
881 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
882 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
883 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
884 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
885 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
886 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
887 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
888 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
889 | TT_TASK | Concreting (222m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
890 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
892 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
893 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
894 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
896 | TT_TASK | Placing of waterproof member T-lock & testing | Mon Nov 18 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
897 | TT_TASK | Rebar fixing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Wed Oct 23 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
898 | TT_TASK | Erect external formwork | Fri Nov 22 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
899 | TT_TASK | Concreting (222m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
900 | TT_TASK | Curing | Tue Nov 26 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
901 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
902 | TT_TASK | Removal of formwork | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
905 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
906 | TT_TASK | Erect external formwork | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
907 | TT_TASK | Rebar fixing | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
908 | TT_TASK | Erect internal kicker formwork | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
909 | TT_TASK | Concreting (330m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
910 | TT_TASK | Curing | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
911 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
912 | TT_TASK | Removal of formwork | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
913 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
914 | TT_TASK | Rebar fixing | Wed Nov 20 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
915 | TT_TASK | Erect external formwork | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
916 | TT_TASK | Concreting (330m3) | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
917 | TT_TASK | Curing | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
918 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
919 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
920 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
921 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
923 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
924 | TT_TASK | Erect external formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
925 | TT_TASK | Rebar fixing | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
926 | TT_TASK | Erect internal kicker formwork | Wed Dec 04 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
927 | TT_TASK | Concreting (240m3) | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
928 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
929 | TT_TASK | Preparation of construction joint for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
930 | TT_TASK | Removal of formwork | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
931 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
932 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
933 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
934 | TT_TASK | Concreting (240m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
935 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
936 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
937 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
938 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
939 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
941 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
942 | TT_TASK | Rebar fixing | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
943 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
944 | TT_TASK | Concreting (240m3) | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
945 | TT_TASK | Curing | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
946 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
947 | TT_TASK | Removal of formwork | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
950 | TT_TASK | Placing of waterproof member T-lock & testing | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
951 | TT_TASK | Erect external formwork | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
952 | TT_TASK | Rebar fixing | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
953 | TT_TASK | Erect internal kicker formwork | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
954 | TT_TASK | Concreting (200m3) | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
955 | TT_TASK | Curing | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
956 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
957 | TT_TASK | Removal of formwork | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
958 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 29 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
959 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
960 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
961 | TT_TASK | Concreting (200m3) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
962 | TT_TASK | Curing | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
963 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
964 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 13 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
965 | TT_TASK | Removal internal falsework and formwork for roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
966 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 |  | COMPLETED
968 | TT_TASK | Placing of waterproof member T-lock & testing | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
969 | TT_TASK | Erect external formwork | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
970 | TT_TASK | Rebar fixing | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
971 | TT_TASK | Erect internal kicker formwork | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
972 | TT_TASK | Concreting (220m3) | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
973 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
974 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
975 | TT_TASK | Removal of formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
976 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
977 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
978 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
979 | TT_TASK | Concreting (220m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
980 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
981 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
982 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
983 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
984 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
986 | TT_TASK | Placing of waterproof member T-lock & testing | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
987 | TT_TASK | Rebar fixing | Mon Nov 25 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
988 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
989 | TT_TASK | Concreting (222m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
990 | TT_TASK | Curing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
991 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
992 | TT_TASK | Removal of formwork | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
994 | TT_TASK | Removal of Temporary Nullah | Sat Mar 01 08:00:00 IST 2014 | Sat Jun 21 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
995 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (5218m3) | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 |  | COMPLETED
996 | TT_TASK | Reinstate the permenant Retaining wall of Nullah | Sat Mar 01 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Tue Mar 04 08:00:00 IST 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
997 | TT_TASK | Reinstate Nullah Base of original route | Tue Feb 25 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Tue Feb 25 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
998 | TT_TASK | Reinstate Nullah to original route | Sat Mar 29 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Sat Mar 29 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
999 | TT_TASK | Construction & connect East Box Culvert from Box 6B to KTR | Mon Apr 14 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Mon Feb 10 08:00:00 IST 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
1000 | TT_TASK | Reinstatement of Wang Toi Shan Shan Tsuen Road | Tue Dec 01 08:00:00 IST 2015 | Wed Jul 13 18:00:00 IDT 2016 | Tue Dec 01 08:00:00 IST 2015 | Mon Jul 18 18:00:00 IDT 2016 |  | COMPLETED
1003 | TT_TASK | Pre-drilling at Works Area 4.4 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
1004 | TT_TASK | Site Setup and guide wall | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1005 | TT_TASK | D-wall construction (3104m3) | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 |  | COMPLETED
1006 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
1008 | TT_TASK | Excavate up to +8.0mPD (775m3) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1009 | TT_TASK | Install Strut S1 +8.5mPD | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 |  | COMPLETED
1010 | TT_TASK | Excavate up to +4.5mPD (2713m3) | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 |  | COMPLETED
1011 | TT_TASK | Install Strut S2 +5.0mPD | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
1012 | TT_TASK | Excavate up to +0.5mPD (3100m3) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 |  | COMPLETED
1013 | TT_TASK | Install Strut S3 +1.0mPD | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1014 | TT_TASK | Excavate up to -3.0mPD (2713m3) | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1015 | TT_TASK | Install Strut S4 -2.5mPD | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 |  | COMPLETED
1016 | TT_TASK | Excavate up to -5.5mPD (4952m3) | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1017 | TT_TASK | Placing of blinding layer | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1021 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1022 | TT_TASK | Erect external formwork for base slab | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1023 | TT_TASK | Rebar fixing for base slab | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1024 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 26 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1025 | TT_TASK | Concreting for base slab (350m3) | Thu Jun 27 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1026 | TT_TASK | Curing for base slab | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1027 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1028 | TT_TASK | Removal of formwork for base slab | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1029 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1030 | TT_TASK | Removal strut S4 and S3 | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1032 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1033 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1034 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1035 | TT_TASK | Concreting for wall and roof (489m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1036 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1037 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1038 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1039 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1040 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1043 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1044 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1045 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1046 | TT_TASK | Curing for wall and roof | Sat Jun 22 08:00:00 IDT 2013 | Mon Jul 01 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1047 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1048 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1050 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Tue Dec 17 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1053 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1054 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1055 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1056 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1057 | TT_TASK | Concreting for base slab (350m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1058 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1059 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1060 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1061 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1062 | TT_TASK | Removal strut S4 and S3 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1064 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1065 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1066 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1067 | TT_TASK | Concreting for wall and roof (489m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1068 | TT_TASK | Curing for wall and roof | Wed Jun 12 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1069 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1070 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 14 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1071 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1072 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Feb 13 08:00:00 IST 2014 | Tue Feb 18 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1074 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1075 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1076 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1077 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1078 | TT_TASK | Curing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1079 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1080 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1081 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1082 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 16 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1084 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (2343m3) | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1085 | TT_TASK | Placing 0.5m thk concrete lateral support (+3.96mPD) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1086 | TT_TASK | Removal strut S2 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 23 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1088 | TT_TASK | Construction of Temporary Culvert (open channel) | Tue Jun 25 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1089 | TT_TASK | Temporary box culvert (At Box 6B Area) Saw Cut D-wall | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 |  | COMPLETED
1090 | TT_TASK | Erect 3m high block wall | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 |  | COMPLETED
1091 | TT_TASK | Connection to East Box Culvert (823B portion) | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 |  | COMPLETED
1092 | TT_TASK | Blinding | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
1093 | TT_TASK | Temporary box culvert (Outside Box 6B Area) Sheet piling | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 |  | COMPLETED
1094 | TT_TASK | ELS Works | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
1095 | TT_TASK | Blinding | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
1096 | TT_TASK | Removal of Temporary Culvert and Reinstatement | Fri May 16 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
1098 | TT_TASK | Reinstatement of TOA's | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 |  |  | IN_PROGRESS
1099 | TT_TASK | Hydroseeding works | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 | Wed Nov 30 18:00:00 IST 2016 |  | COMPLETED
1100 | TT_TASK | Tree Planting works | Thu Sep 01 08:00:00 IDT 2016 | Sat Dec 03 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
1101 | TT_TASK | Woodland Shrub Mix | Thu Sep 01 08:00:00 IDT 2016 | Fri Nov 18 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  | 200.0 | IN_PROGRESS
1104 | TT_TASK | Kam Tin River Diversion (Stage 1-3) | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1106 | TT_TASK | Concrete fill up to +8.0mPD near side A mass concrete wall | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 |  | COMPLETED
1107 | TT_TASK | Construction of mass concrete wall to +8.0mPD at side A (4 bay CH A80~A120) | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1108 | TT_TASK | Construction of base slab lining and low flow channel (4 bay A9~A10, B8~B9; LFC CH 80~110) | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1109 | TT_TASK | Construction of mass concrete wall to +8.0mPD of side B (3 bay CH B60~B90) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1110 | TT_TASK | Construction of T-shaped retaining wall (1 Bay CH B50~B60) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1111 | TT_TASK | Soil backfill at side A from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1112 | TT_TASK | Concrete backfill at side B from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1113 | TT_TASK | Removal strut at +8.5mPD near side A | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1114 | TT_TASK | Concrete fill up to +11.0mPD near side A mass concrete wall | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1115 | TT_TASK | Placing concrete block at side A from +8.0mPD to +11.0mpd at side A (4 bay CH A80~A120) | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1116 | TT_TASK | Soil backfill at side A from +8.0mPD to +11.0mPD | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1117 | TT_TASK | Removal strut at +8.5mPD near side B | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1118 | TT_TASK | Placing concrete block at side B from +8.0mPD to +11.0mPD (4 bay CH B60~B90) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1119 | TT_TASK | Concrete backfill at side B from +8.0mPD to +11.0mPD | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1121 | TT_TASK | Placing temporary concrete block to Up stream at CH30 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 |  | COMPLETED
1122 | TT_TASK | Placing temporary concrete block to Up stream at CH160 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1123 | TT_TASK | Excavation from GL to FL +5.0mPD Up stream (Low flow channel CH 30~60) | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1124 | TT_TASK | Excavation from GL to FL +5.0mPD Down stream (Low flow channel CH 130~160) | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1125 | TT_TASK | Construction of T-shaped retaining wall at Up stream of side B (2 Bay CH B30~B50) | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1126 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (3 bay CH B90~B120) | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1127 | TT_TASK | Construction of Up stream base slab lining and low flow channel (6 Bay A1~A4, B3~B4; Low flow channel CH 30~50) | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1128 | TT_TASK | Construction of Down stream base slab lining and low flow channel (5 Bay A14~A16, B14~B15; LFC CH 140~170) | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1129 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Up stream and saw cut D-wall | Fri Jun 14 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1130 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Down stream and saw cut D-wall | Wed Jun 19 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1131 | TT_TASK | Construction of remaining Up stream base slab lining and low flow channel (7 bay A5~A8, B5~B7; LFC CH 50~80) | Thu Jun 27 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1132 | TT_TASK | Construction of remaining Down stream base slab lining and low flow channel (7 bay A11~A13, B10~B13; LFC CH 110~140) | Wed Jul 03 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1134 | TT_TASK | Relocation of temporary concrete block at Up stream for construction of mass concrete wall at side B | Sat Jul 20 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1135 | TT_TASK | Relocation of temporary concrete block at Down stream for construction of mass concrete wall at side B | Tue Jul 23 08:00:00 IDT 2013 | Wed Jul 24 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1136 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Up stream of side B (3 bay CH B0~B30) | Tue Jul 23 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1137 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (4 bay CH B0~B30) | Thu Jul 25 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1141 | TT_TASK | Application of power supply, environmental permits and construction substation | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1142 | TT_TASK | Procurement and Confirmation of the order of 1st tunnel boring machine | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 |  | COMPLETED
1143 | TT_TASK | Prepare on-demand bond or bank guarantee for the procurement of TBM and submit to Engineer for approval | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 |  | COMPLETED
1144 | TT_TASK | TBM design and submission for approval | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
1145 | TT_TASK | TBM materials order and delivery to factory | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 |  | COMPLETED
1146 | TT_TASK | TBM equipments order and delivery to factory | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 |  | COMPLETED
1147 | TT_TASK | TBM Fabrication | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
1148 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 |  | COMPLETED
1149 | TT_TASK | TBM test Run | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 |  | COMPLETED
1150 | TT_TASK | TBM disassembly and packing for shipping to HK | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 |  | COMPLETED
1151 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
1152 | TT_TASK | Ground treatment for TBM lanching shaft | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 |  | COMPLETED
1153 | TT_TASK | Ground treatment for Cross Passage Tunnel | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1154 | TT_TASK | Box7A Setup TBM facilities, install noise enclosure and CNP application | Fri Jun 01 08:00:00 IDT 2012 | Sat Jan 26 18:00:00 IST 2013 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1155 | TT_TASK | Notice to Contract 824 the anticipated dates of break out TBM Shaft | Sat Jun 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1156 | TT_TASK | Fabrication of tunnel segment mould | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
1157 | TT_TASK | Fabrication 50% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1158 | TT_TASK | Fabrication 100% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
1159 | TT_TASK | Fabrication 30% of North Tunnel North Bound (Uptrack) Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1160 | TT_TASK | Fabrication 60% of North Tunnel North Bound (Uptrack) Precast Lining | Thu Oct 18 08:00:00 IST 2012 | Thu Feb 21 18:00:00 IST 2013 | Thu Oct 18 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1161 | TT_TASK | Fabrication 100% of North Tunnel North Bound (Uptrack) Precast Lining | Mon Aug 19 08:00:00 IDT 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Dec 03 08:00:00 IST 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1163 | TT_TASK | Assemble, T&C of TBM | Fri Jun 01 08:00:00 IDT 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Oct 16 00:00:00 IST 2012 |  | COMPLETED
1164 | TT_TASK | TBM drive & lining installation CH123+369 to CH123+283 Initial Drive (86m) | Sat Nov 03 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 | Wed Oct 17 00:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1165 | TT_TASK | Change Plant (Back-up cars) | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1166 | TT_TASK | TBM drive & lining installation CH123+283 to CH123+183 | Thu Jun 27 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1167 | TT_TASK | TBM drive & lining installation CH123+183 to CH123+083 | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1168 | TT_TASK | TBM drive & lining installation CH123+083 to CH122+983 | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1169 | TT_TASK | TBM drive & lining installation CH122+983 to CH122+883 | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1170 | TT_TASK | TBM drive & lining installation CH122+883 to CH122+783 | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Jun 13 08:00:00 IDT 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
1171 | TT_TASK | TBM drive & lining installation CH122+783 to CH122+683 | Sat Nov 02 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1172 | TT_TASK | TBM drive & lining installation CH122+683 to CH122+583 | Tue Dec 03 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Wed Feb 26 18:00:00 IST 2014 |  | COMPLETED
1173 | TT_TASK | TBM drive & lining installation CH122+583 to CH122+491 | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Feb 27 08:00:00 IST 2014 | Sat Aug 16 00:00:00 IDT 2014 |  | COMPLETED
1174 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1175 | TT_TASK | Dis-assemble TBM | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
1176 | TT_TASK | Invert slab, side walkway | Sat Oct 04 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 | Mon Sep 15 08:00:00 IDT 2014 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1177 | TT_TASK | Installation of cable bracket | Tue Dec 30 08:00:00 IST 2014 | Tue Jan 13 18:00:00 IST 2015 | Fri Sep 12 08:00:00 IDT 2014 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
1178 | TT_TASK | Provision of assess open for DC and modify of strut S1 and S2 at north bound | Tue Nov 04 11:12:00 IST 2014 | Thu Dec 04 11:12:00 IST 2014 | Wed Oct 01 08:00:00 IDT 2014 | Sat Oct 18 18:00:00 IDT 2014 |  | COMPLETED
1180 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Oct 06 13:00:00 IDT 2014 | Mon Oct 20 12:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
1181 | TT_TASK | Assemble, T&C of TBM | Mon Nov 03 08:00:00 IST 2014 | Fri Jan 02 18:00:00 IST 2015 | Sat Oct 04 08:00:00 IDT 2014 | Fri Nov 28 18:00:00 IST 2014 |  | COMPLETED
1182 | TT_TASK | Setup back-up plant for final drive | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
1183 | TT_TASK | Reinstate of noise enclosure | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Sat Nov 29 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1184 | TT_TASK | TBM drive & lining installation CH123+384 to CH123+284 (Initial Drive) | Sat Dec 06 08:00:00 IST 2014 | Thu Jan 22 18:00:00 IST 2015 | Tue Dec 02 00:00:00 IST 2014 | Tue Jan 20 18:00:00 IST 2015 |  | COMPLETED
1185 | TT_TASK | TBM drive & lining installation CH123+184 to CH123+084 | Wed Jan 21 08:00:00 IST 2015 | Wed Jan 28 18:00:00 IST 2015 | Wed Jan 21 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 |  | COMPLETED
1186 | TT_TASK | TBM drive & lining installation CH123+084 to CH122+984 | Wed Feb 04 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 | Thu Feb 12 08:00:00 IST 2015 | Thu Feb 26 18:00:00 IST 2015 |  | COMPLETED
1187 | TT_TASK | TBM drive & lining installation CH122+984 to CH122+884 | Thu Feb 12 08:00:00 IST 2015 | Tue Feb 24 18:00:00 IST 2015 | Fri Feb 27 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1188 | TT_TASK | TBM drive & lining installation CH122+884 to CH122+784 | Tue Mar 10 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Wed May 27 18:00:00 IDT 2015 |  | COMPLETED
1189 | TT_TASK | TBM drive & lining installation CH122+784 to CH122+684 | Wed May 06 08:00:00 IDT 2015 | Thu May 14 18:00:00 IDT 2015 | Thu May 28 08:00:00 IDT 2015 | Sat Jul 11 18:00:00 IDT 2015 |  | COMPLETED
1190 | TT_TASK | TBM drive & lining installation CH122+684 to CH122+584 | Fri Jul 03 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
1191 | TT_TASK | TBM drive & lining installation CH122+584 to CH122+506 | Tue Nov 03 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 |  | COMPLETED
1192 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 |  | COMPLETED
1193 | TT_TASK | Dis-assemble TBM | Wed Dec 16 08:00:00 IST 2015 | Fri Jan 22 18:00:00 IST 2016 | Sun Dec 13 08:00:00 IST 2015 | Sun Mar 13 18:00:00 IST 2016 |  | COMPLETED
1194 | TT_TASK | Invert slab, side walkway | Fri Apr 01 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 | Mon Mar 14 08:00:00 IST 2016 | Tue May 24 18:00:00 IDT 2016 |  | COMPLETED
1195 | TT_TASK | Installation of cable bracket | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Mar 15 18:00:00 IST 2016 |  | COMPLETED
1196 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Mon Feb 01 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 22 18:00:00 IST 2016 |  | COMPLETED
1199 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 1 (From Downtrack to Centre of CP) | Thu Apr 10 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Sat Jun 28 18:00:00 IDT 2014 |  | COMPLETED
1200 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Sun Nov 09 18:00:00 IST 2014 |  | COMPLETED
1201 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1202 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 18:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1203 | TT_TASK | Excavation 0-4mts with Shotcrete | Mon Feb 02 08:00:00 IST 2015 | Tue Feb 17 18:00:00 IST 2015 | Mon Feb 23 08:00:00 IST 2015 | Mon Mar 30 18:00:00 IDT 2015 |  | COMPLETED
1204 | TT_TASK | Invert Concrete | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1205 | TT_TASK | Wall and Roof concrete | Thu Apr 16 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 |  | COMPLETED
1206 | TT_TASK | Dismantle Temporary frame | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 |  | COMPLETED
1207 | TT_TASK | Install Door to Cross Passage (By contract 827) | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 |  | COMPLETED
1208 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 2 (From Centre of CP to Uptrack) | Sat Oct 17 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Sep 07 08:00:00 IDT 2015 | Tue Dec 01 18:00:00 IST 2015 |  | COMPLETED
1209 | TT_TASK | Probe/Grout | Thu Jun 25 08:00:00 IDT 2015 | Mon Jul 06 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Fri Apr 10 18:00:00 IDT 2015 |  | COMPLETED
1210 | TT_TASK | Coring of Segment | Tue Jul 07 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Sat Apr 11 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1211 | TT_TASK | Removal of segment | Sat Jul 11 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
1212 | TT_TASK | Excavation 0-4mts with Shotcrete | Wed Jul 15 08:00:00 IDT 2015 | Sat Jul 25 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1213 | TT_TASK | Invert Concrete | Sat Jul 18 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 | Thu May 07 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1214 | TT_TASK | Wall and Roof concrete | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1215 | TT_TASK | Dismantle Temporary frame | Tue Jan 19 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 04 18:00:00 IST 2016 |  | COMPLETED
1216 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Feb 22 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Fri Feb 05 08:00:00 IST 2016 | Sat Feb 06 18:00:00 IST 2016 |  | COMPLETED
1218 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 1 (From Downtrack to Centre of CP) | Tue Mar 11 08:00:00 IST 2014 | Wed Mar 26 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1219 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Wed Nov 12 18:00:00 IST 2014 |  | COMPLETED
1220 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Thu Nov 13 08:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1221 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Tue Nov 18 08:00:00 IST 2014 | Thu Nov 20 18:00:00 IST 2014 |  | COMPLETED
1222 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Sat Nov 22 08:00:00 IST 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1223 | TT_TASK | Invert Concrete | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
1224 | TT_TASK | Wall and Roof concrete | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1225 | TT_TASK | Dismantle Temporary frame | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1226 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1227 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 2 (From Centre of CP to Uptrack) | Thu May 21 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Mar 09 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1228 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Mon May 04 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1229 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
1230 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1231 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 22 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
1232 | TT_TASK | Invert Concrete | Sat Aug 08 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Wed Jul 08 18:00:00 IDT 2015 |  | COMPLETED
1233 | TT_TASK | Wall and Roof concrete | Tue Aug 25 08:00:00 IDT 2015 | Mon Sep 07 18:00:00 IDT 2015 | Thu Jul 09 08:00:00 IDT 2015 | Sat Aug 15 18:00:00 IDT 2015 |  | COMPLETED
1234 | TT_TASK | Dismantle Temporary frame | Tue Sep 22 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 | Mon Aug 17 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 |  | COMPLETED
1235 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1237 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 1 (From Downtrack to Centre of CP) | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Sat May 24 18:00:00 IDT 2014 |  | COMPLETED
1238 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
1239 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1240 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 |  | COMPLETED
1241 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Mon Nov 17 08:00:00 IST 2014 | Sat Nov 29 18:00:00 IST 2014 |  | COMPLETED
1242 | TT_TASK | Invert Concrete | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 |  | COMPLETED
1243 | TT_TASK | Wall and Roof concrete | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 |  | COMPLETED
1244 | TT_TASK | Dismantle Temporary frame | Tue Dec 30 08:00:00 IST 2014 | Wed Jan 07 18:00:00 IST 2015 | Tue Dec 30 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1245 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1246 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 2 (From Centre of CP to Uptrack) | Fri May 08 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 |  | COMPLETED
1247 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
1248 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
1249 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Thu May 07 18:00:00 IDT 2015 |  | COMPLETED
1250 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
1251 | TT_TASK | Invert Concrete | Wed Aug 05 08:00:00 IDT 2015 | Fri Aug 14 18:00:00 IDT 2015 | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
1252 | TT_TASK | Wall and Roof concrete | Tue Sep 15 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Wed Aug 26 18:00:00 IDT 2015 |  | COMPLETED
1253 | TT_TASK | Dismantle Temporary frame | Sat Oct 17 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Oct 08 18:00:00 IDT 2015 |  | COMPLETED
1254 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1258 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 |  | COMPLETED
1259 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1260 | TT_TASK | D-wall construction (1192m3) | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 |  | COMPLETED
1261 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1262 | TT_TASK | Construct capping beam, cobble, etc. (including bay 6 and 5) | Sat Oct 27 08:00:00 IST 2012 | Sat Feb 16 18:00:00 IST 2013 | Sat Oct 27 08:00:00 IST 2012 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1264 | TT_TASK | Excavate up to +22.0mPD (1860m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1265 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 |  | COMPLETED
1266 | TT_TASK | Excavate up to +16.5mPD (3410m3) | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 |  | COMPLETED
1267 | TT_TASK | Install Strut S2 +17.0mPD | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 |  | COMPLETED
1268 | TT_TASK | Excavate up to +11.0mPD (3410m3) | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 |  | COMPLETED
1269 | TT_TASK | Install Strut S3 +11.5mPD | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 |  | COMPLETED
1270 | TT_TASK | Excavate up to +7.0mPD (2480m3) | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 |  | COMPLETED
1271 | TT_TASK | Install Strut S4 +7.5mPD | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1272 | TT_TASK | Excavate up to +3.5mPD (2170m3) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 |  | COMPLETED
1273 | TT_TASK | Install Strut S5 +4.0mPD | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1274 | TT_TASK | Excavate up to formation (2294m3) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1275 | TT_TASK | Construct temp. 500mm thick plain concrete base slab | Thu Oct 18 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 |  | COMPLETED
1276 | TT_TASK | Removal of South Bound strut to +9.50mPD | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1277 | TT_TASK | Removal of North Bound strut to +9.50mPD | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 |  | COMPLETED
1278 | TT_TASK | Construct temp. 500mm thick TBM concrete base slab | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1279 | TT_TASK | Construction entrance seal for TBM at South Bound | Mon Nov 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1280 | TT_TASK | Construction entrance seal for TBM at North Bound | Sat Jul 20 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1281 | TT_TASK | Saw cut South Bound diaphragm wall | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1282 | TT_TASK | Saw cut North Bound diaphragm wall | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1286 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 05 18:00:00 IDT 2014 | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 |  | COMPLETED
1287 | TT_TASK | Erect external formwork (Base Slab) | Sat Sep 06 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 21 18:00:00 IDT 2014 |  | COMPLETED
1288 | TT_TASK | Rebar fixing (Base Slab) | Wed Sep 10 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Tue Jul 22 08:00:00 IDT 2014 | Sat Jul 26 18:00:00 IDT 2014 |  | COMPLETED
1289 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Sep 15 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Sun Jul 27 08:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1290 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Thu Aug 14 18:00:00 IDT 2014 |  | COMPLETED
1291 | TT_TASK | Concreting (Base Slab) (225m3) | Sat Aug 09 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Fri Aug 15 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
1292 | TT_TASK | Curing (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
1293 | TT_TASK | Removal of formwork (Base Slab) | Tue Aug 12 08:00:00 IDT 2014 | Tue Aug 12 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1294 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed Aug 13 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Mon Sep 15 18:00:00 IDT 2014 |  | COMPLETED
1295 | TT_TASK | Rebar fixing (Wall & Roof) | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 |  | COMPLETED
1296 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 |  | COMPLETED
1297 | TT_TASK | Clearing and inspection (Wall & Roof) | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
1298 | TT_TASK | Concreting (Wall & Roof) (450m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
1299 | TT_TASK | Curing (Wall & Roof) | Sat Oct 11 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
1300 | TT_TASK | Removal external formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1301 | TT_TASK | Removal internal falsework (Wall & Roof) | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 |  | COMPLETED
1302 | TT_TASK | Side walkway and cable bracket (102m3) | Sat Oct 18 08:00:00 IDT 2014 | Wed Oct 29 18:00:00 IST 2014 | Mon Sep 01 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1304 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Wed Nov 11 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Oct 19 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1305 | TT_TASK | Erect external formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 |  | COMPLETED
1306 | TT_TASK | Rebar fixing (Base Slab) | Mon Nov 16 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Tue Oct 27 08:00:00 IST 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1307 | TT_TASK | Erect internal kicker formwork (Base Slab) | Fri Nov 20 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Oct 31 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 |  | COMPLETED
1308 | TT_TASK | Clearing and inspection (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
1309 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1310 | TT_TASK | Curing (Base Slab) | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 |  | COMPLETED
1311 | TT_TASK | Removal of formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 |  | COMPLETED
1312 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
1313 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Dec 09 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
1314 | TT_TASK | Erect external formwork (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Thu Jan 07 18:00:00 IST 2016 |  | COMPLETED
1315 | TT_TASK | Clearing and inspection (Wall & Roof) | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Fri Jan 08 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
1316 | TT_TASK | Concreting (Wall & Roof) (450m3) | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
1317 | TT_TASK | Curing (Wall & Roof) | Tue Jan 12 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
1318 | TT_TASK | Removal external formwork (Wall ) | Thu Jan 14 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
1319 | TT_TASK | Removal internal falsework, formwork and reproping (Wall & Roof) | Thu Jan 28 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 |  | COMPLETED
1320 | TT_TASK | Side walkway and cable bracket (102m3) | Wed Dec 23 08:00:00 IST 2015 | Wed Jan 06 18:00:00 IST 2016 | Wed Nov 11 08:00:00 IST 2015 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
1322 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 |  | COMPLETED
1323 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 |  | COMPLETED
1324 | TT_TASK | Backfilling to 0.5m below S3 (+11.0mPD) (3486m3) | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 |  | COMPLETED
1325 | TT_TASK | Removal strut S3 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
1326 | TT_TASK | Backfilling to 0.5m below S2 (+16.5mPD) (3410m3) | Wed Mar 16 08:00:00 IST 2016 | Fri Apr 08 18:00:00 IDT 2016 | Wed Mar 16 08:00:00 IST 2016 | Tue Apr 12 18:00:00 IDT 2016 |  | COMPLETED
1327 | TT_TASK | Removal strut S2 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 |  | COMPLETED
1328 | TT_TASK | Backfilling to 0.5m below S1 (+22.0mPD) (3410m3) | Fri Apr 15 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 | Fri Apr 15 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
1329 | TT_TASK | Removal strut S1 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 |  | COMPLETED
1330 | TT_TASK | Backfilling to original ground level (approx. +25.0mPD) (1860m3) | Thu May 05 08:00:00 IDT 2016 | Tue May 17 18:00:00 IDT 2016 | Thu May 05 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
1333 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1334 | TT_TASK | D-wall construction (2844m3) | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1335 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1337 | TT_TASK | Excavate up to +22.0mPD (3720m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1338 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 |  | COMPLETED
1339 | TT_TASK | Excavate up to +16.5mPD (4880m3) | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 |  | COMPLETED
1340 | TT_TASK | Install Strut S2 +17.0mPD | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 |  | COMPLETED
1341 | TT_TASK | Excavate up to +11.0mPD (6820m3) | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
1342 | TT_TASK | Install Strut S3 +11.5mPD | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 |  | COMPLETED
1343 | TT_TASK | Excavate up to +7.0mPD (4960m3) | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 |  | COMPLETED
1344 | TT_TASK | Install Strut S4 +7.5mPD | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1345 | TT_TASK | Excavate up to +3.5mPD (4340m3) | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1346 | TT_TASK | Install Strut S5 +4.0mPD | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 |  | COMPLETED
1347 | TT_TASK | Excavate up to formation (4960m3) | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 |  | COMPLETED
1348 | TT_TASK | Construct temp. 500mm thick plain concrete base slab at Bay 5 & 6 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1349 | TT_TASK | Excavation to formation and place blinding Bay 4a | Thu Oct 18 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1350 | TT_TASK | Excavation to formation and place blinding Bay 4b | Fri Jun 21 08:00:00 IDT 2013 | Fri Jul 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1351 | TT_TASK | Excavation to formation and place blinding Bay3 | Sat Jul 13 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1352 | TT_TASK | Excavation to formation and place blinding Bay2 to Bay1 | Wed Jul 24 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1356 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 |  | COMPLETED
1357 | TT_TASK | Erect external formwork for base slab | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 |  | COMPLETED
1358 | TT_TASK | Rebar fixing for base slab | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1359 | TT_TASK | Erect internal kicker formwork for base slab | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1360 | TT_TASK | Concreting for base slab (363m3) | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1361 | TT_TASK | Curing for base slab | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1362 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1363 | TT_TASK | Removal of formwork for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1364 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1365 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 27 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1366 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1367 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1368 | TT_TASK | Curing for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1369 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1370 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 10 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1371 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 19 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jan 24 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1372 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 08 08:00:00 IST 2015 | Tue Jan 13 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1374 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 |  | COMPLETED
1375 | TT_TASK | Erect external formwork for base slab | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1376 | TT_TASK | Rebar fixing for base slab | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1377 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 |  | COMPLETED
1378 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1379 | TT_TASK | Curing for base slab | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1380 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1381 | TT_TASK | Removal of formwork for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1382 | TT_TASK | Rebar fixing for central slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1383 | TT_TASK | Erect external formwork for central slab | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1384 | TT_TASK | Concreting for central slab (450m3) | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1385 | TT_TASK | Curing for central slab | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1386 | TT_TASK | Preparation of construction joint for central slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1387 | TT_TASK | Removal of formwork for central slab | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1388 | TT_TASK | Removal strut S5 and S4 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1389 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1390 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1391 | TT_TASK | Erect external formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1392 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1393 | TT_TASK | Curing for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1394 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1395 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 08 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1396 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1397 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Nov 19 08:00:00 IST 2015 | Tue Nov 24 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 |  | COMPLETED
1400 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1401 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1402 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1403 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1404 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1405 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1406 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1407 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1408 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1409 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1410 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 10 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1411 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1412 | TT_TASK | Curing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1413 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1414 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1415 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1416 | TT_TASK | Side walkway and cable bracket | Fri Jan 02 08:00:00 IST 2015 | Wed Jan 07 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1418 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1419 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1420 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1421 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1422 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1423 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1424 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1425 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1426 | TT_TASK | Rebar fixing for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1427 | TT_TASK | Erect external formwork for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1428 | TT_TASK | Concreting for central slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1429 | TT_TASK | Curing for central slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1430 | TT_TASK | Preparation of construction joint for central slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1431 | TT_TASK | Removal of formwork for central slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 21 18:00:00 IST 2012 |  | COMPLETED
1432 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1433 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1434 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1435 | TT_TASK | Erect external formwork for wall | Mon Jul 15 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1436 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1437 | TT_TASK | Curing for wall and roof | Sun Jul 21 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1438 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1439 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 22 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1440 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 31 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1441 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Sep 16 08:00:00 IDT 2015 | Mon Sep 21 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1443 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1444 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1445 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1446 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1447 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1448 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1449 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1450 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1451 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1452 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1453 | TT_TASK | Erect external formwork for wall | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1454 | TT_TASK | Concreting for wall and roof (444m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1455 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1456 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1457 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Sat Feb 09 18:00:00 IST 2013 |  | COMPLETED
1458 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Nov 09 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Tue Oct 06 08:00:00 IDT 2015 | Sat Oct 10 18:00:00 IDT 2015 |  | COMPLETED
1461 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1462 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1463 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1464 | TT_TASK | Erect internal kicker formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1465 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1466 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1467 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1468 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1469 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1470 | TT_TASK | Curing | Wed Jun 12 08:00:00 IDT 2013 | Wed Jun 12 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1471 | TT_TASK | Removal strut S5 and S4 | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1473 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1474 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1475 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1476 | TT_TASK | Concreting for wall and roof (450m3) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1477 | TT_TASK | Curing for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1478 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1479 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1480 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 29 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1481 | TT_TASK | Side walkway and cable bracket | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1483 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1484 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1485 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1486 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1487 | TT_TASK | Curing for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1488 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1489 | TT_TASK | Removal external wall formwork for wall | Wed Jun 26 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1490 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1491 | TT_TASK | Side walkway and cable bracket | Fri Sep 04 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
1494 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1495 | TT_TASK | Erect external formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1496 | TT_TASK | Rebar fixing for base slab | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1497 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1498 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 |  | COMPLETED
1499 | TT_TASK | Curing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1500 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1501 | TT_TASK | Removal of formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1502 | TT_TASK | Shear beam | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1503 | TT_TASK | Curing | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1504 | TT_TASK | Removal strut S5 and S4 | Wed Jun 19 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1506 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 24 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1507 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1508 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1509 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1510 | TT_TASK | Curing for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1511 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1512 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1513 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1514 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
1516 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1517 | TT_TASK | Rebar fixing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1518 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1519 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1520 | TT_TASK | Curing for wall and roof | Sun Jun 23 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1521 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1522 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 25 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1523 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 03 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1524 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Aug 29 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1527 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1528 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Sat Dec 22 18:00:00 IST 2012 |  | COMPLETED
1529 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1530 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1531 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1532 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1533 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1534 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Fri Jan 11 18:00:00 IST 2013 |  | COMPLETED
1535 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Jan 12 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1536 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1537 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1539 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1540 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1541 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1542 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1543 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1544 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1545 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1546 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1547 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 |  | COMPLETED
1549 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1550 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Mon Feb 25 18:00:00 IST 2013 |  | COMPLETED
1551 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1552 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1553 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1554 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1555 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1556 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1557 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Aug 24 08:00:00 IDT 2015 | Fri Aug 28 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1560 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1561 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1562 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1563 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1564 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1565 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1566 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1567 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1568 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1569 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1570 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1572 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1573 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1574 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1575 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1576 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1577 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1578 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1579 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1580 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
1582 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1583 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1584 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1585 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1586 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1587 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1588 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1589 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1590 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Aug 18 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1593 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1594 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1595 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1596 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1597 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1598 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1599 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1600 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1601 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1602 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1603 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1605 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 31 18:00:00 IDT 2013 |  | COMPLETED
1606 | TT_TASK | Rebar fixing for wall and roof | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 |  | COMPLETED
1607 | TT_TASK | Erect external formwork for wall and roof | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 | Fri Sep 06 08:00:00 IDT 2013 | Thu Sep 12 18:00:00 IDT 2013 |  | COMPLETED
1608 | TT_TASK | Concreting for wall and roof (450m3) | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 |  | COMPLETED
1609 | TT_TASK | Curing for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1610 | TT_TASK | Preparation of construction joint for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1611 | TT_TASK | Removal external and internal formwork for wall | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Wed Sep 25 18:00:00 IDT 2013 |  | COMPLETED
1612 | TT_TASK | Removal internal falsework and formwork for roof | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1613 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 08 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1615 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 20 18:00:00 IST 2013 |  | COMPLETED
1616 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1617 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1618 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1619 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1620 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1621 | TT_TASK | Removal external wall formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1622 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1623 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Aug 12 08:00:00 IDT 2015 | Mon Aug 17 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1626 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1627 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1628 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Feb 14 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1629 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1630 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Mon Feb 18 18:00:00 IST 2013 |  | COMPLETED
1631 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1632 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1633 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1634 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1635 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1636 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1638 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jul 12 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1639 | TT_TASK | Rebar fixing for wall and roof | Wed Jul 17 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1640 | TT_TASK | Erect external formwork for wall and roof | Wed Aug 14 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1641 | TT_TASK | Concreting for wall and roof (450m3) | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1642 | TT_TASK | Curing for wall and roof | Sun Aug 11 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1643 | TT_TASK | Preparation of construction joint for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1644 | TT_TASK | Removal external and internal formwork for wall | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1645 | TT_TASK | Removal internal falsework and formwork for roof | Wed Aug 21 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1646 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 03 08:00:00 IST 2014 | Fri Mar 07 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1648 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1649 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1650 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Apr 09 08:00:00 IDT 2013 | Thu Apr 11 18:00:00 IDT 2013 |  | COMPLETED
1651 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1652 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1653 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1654 | TT_TASK | Removal external wall formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1655 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
1656 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Aug 06 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Mon Jul 27 08:00:00 IDT 2015 | Fri Jul 31 18:00:00 IDT 2015 |  | COMPLETED
1658 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Sep 12 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1659 | TT_TASK | Rebar fixing for roof | Tue Sep 17 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1660 | TT_TASK | Erect external formwork for roof | Thu Sep 19 08:00:00 IDT 2013 | Thu Sep 19 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1661 | TT_TASK | Concreting for roof (444m3) | Sat Sep 21 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1662 | TT_TASK | Curing for roof | Sun Sep 22 08:00:00 IDT 2013 | Tue Oct 01 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1663 | TT_TASK | Preparation of construction joint for roof | Mon Sep 23 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1664 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1665 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1668 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1669 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1670 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1671 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1672 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1673 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1674 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1675 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1676 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1677 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1678 | TT_TASK | Removal strut S5 and S4 | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1680 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Thu Apr 25 18:00:00 IDT 2013 |  | COMPLETED
1681 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri May 03 08:00:00 IDT 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
1682 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Thu May 16 08:00:00 IDT 2013 | Thu May 23 18:00:00 IDT 2013 |  | COMPLETED
1683 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1684 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1685 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1686 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Wed May 29 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1687 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1688 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 19 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1690 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Fri Apr 19 18:00:00 IDT 2013 |  | COMPLETED
1691 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1692 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Apr 25 08:00:00 IDT 2013 | Sat Apr 27 18:00:00 IDT 2013 |  | COMPLETED
1693 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1694 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1695 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1696 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1697 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1698 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 02 08:00:00 IDT 2015 | Sat Apr 11 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Feb 27 18:00:00 IST 2015 |  | COMPLETED
1700 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1701 | TT_TASK | Rebar fixing for roof | Tue Aug 06 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1702 | TT_TASK | Erect external formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1703 | TT_TASK | Concreting for roof (444m3) | Fri Aug 09 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 |  | COMPLETED
1704 | TT_TASK | Curing for roof | Thu Aug 01 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1705 | TT_TASK | Preparation of construction joint for roof | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 |  | COMPLETED
1706 | TT_TASK | Removal internal falsework and formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1707 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 09 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1710 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Wed Feb 20 18:00:00 IST 2013 |  | COMPLETED
1711 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1712 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1713 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1714 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1715 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1716 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1717 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1718 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1719 | TT_TASK | Curing | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1720 | TT_TASK | Removal strut S5 and S4 | Mon Jun 24 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1722 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1723 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1724 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Wed Jul 10 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1725 | TT_TASK | Concreting for wall and roof (450m3) | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1726 | TT_TASK | Curing for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1727 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1728 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 |  | COMPLETED
1729 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 |  | COMPLETED
1730 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1732 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1733 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1734 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1735 | TT_TASK | Concreting for wall and roof (450m3) | Tue Sep 03 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1736 | TT_TASK | Curing for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1737 | TT_TASK | Preparation of construction joint for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 |  | COMPLETED
1738 | TT_TASK | Removal external and internal formwork for wall | Thu Sep 05 08:00:00 IDT 2013 | Fri Sep 06 18:00:00 IDT 2013 | Thu Aug 22 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1739 | TT_TASK | Removal internal falsework and formwork for roof | Sat Sep 14 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 |  | COMPLETED
1740 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 05 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1742 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1743 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1744 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1745 | TT_TASK | Concreting for roof (363m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1746 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Sun Oct 20 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1747 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1748 | TT_TASK | Removal internal falsework and formwork for roof | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1749 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Dec 24 13:00:00 IST 2013 | Thu Jan 02 12:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1752 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1753 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1754 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1755 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Apr 12 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1756 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1757 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1758 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1759 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1760 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1761 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1762 | TT_TASK | Removal strut S5 and S4 | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1764 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Aug 05 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1765 | TT_TASK | Rebar fixing for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1766 | TT_TASK | Erect external formwork for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1767 | TT_TASK | Concreting for wall and roof (450m3) | Thu Aug 15 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1768 | TT_TASK | Curing for wall and roof | Fri Aug 16 08:00:00 IDT 2013 | Sun Aug 25 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1769 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1770 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1771 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 |  | COMPLETED
1772 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Feb 04 08:00:00 IST 2014 | Sat Feb 08 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1774 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Aug 07 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1775 | TT_TASK | Rebar fixing for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1776 | TT_TASK | Erect external formwork for wall and roof | Thu Aug 15 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1777 | TT_TASK | Concreting for wall and roof (450m3) | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1778 | TT_TASK | Curing for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1779 | TT_TASK | Preparation of construction joint for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 |  | COMPLETED
1780 | TT_TASK | Removal external and internal formwork for wall | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Wed Aug 21 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 |  | COMPLETED
1781 | TT_TASK | Removal internal falsework and formwork for roof | Mon Sep 16 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1782 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Nov 19 08:00:00 IST 2014 | Mon Nov 24 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1784 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1785 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1786 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1787 | TT_TASK | Concreting for roof (450m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1788 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1789 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1790 | TT_TASK | Removal internal falsework and formwork for roof | Fri Oct 18 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1791 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 13 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1794 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1795 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1796 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1797 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1798 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 28 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1799 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1800 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1801 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1802 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1803 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1804 | TT_TASK | Removal strut S5 and S4 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1806 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1807 | TT_TASK | Rebar fixing for wall and roof | Sat Jul 20 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1808 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1809 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1810 | TT_TASK | Curing for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1811 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1812 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 29 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1813 | TT_TASK | Removal internal falsework and formwork for roof | Tue Aug 06 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1814 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 18:00:00 IST 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1816 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1817 | TT_TASK | Rebar fixing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1818 | TT_TASK | Erect external formwork for wall and roof | Fri Jul 19 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1819 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1820 | TT_TASK | Curing for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Thu Mar 28 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1821 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Mar 29 08:00:00 IDT 2013 | Fri Mar 29 18:00:00 IDT 2013 |  | COMPLETED
1822 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Sat Mar 30 08:00:00 IDT 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1823 | TT_TASK | Removal internal falsework and formwork for roof | Fri Aug 02 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Mon Apr 01 18:00:00 IDT 2013 |  | COMPLETED
1824 | TT_TASK | Side walkway and cable bracket | Thu Nov 13 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1826 | TT_TASK | Erect internal formwork & Falsework for roof | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1827 | TT_TASK | Rebar fixing for roof | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 |  | COMPLETED
1828 | TT_TASK | Erect shutter formwork for roof | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 09 18:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1829 | TT_TASK | Concreting for roof (450m3) | Tue Sep 10 08:00:00 IDT 2013 | Tue Sep 10 18:00:00 IDT 2013 | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 |  | COMPLETED
1830 | TT_TASK | Curing for roof | Wed Sep 11 08:00:00 IDT 2013 | Fri Sep 20 18:00:00 IDT 2013 | Tue Jul 23 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 |  | COMPLETED
1831 | TT_TASK | Preparation of construction joint for roof | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 11 18:00:00 IDT 2013 | Sat Aug 03 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1832 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 26 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 |  | COMPLETED
1833 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 06 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Aug 13 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1835 | TT_TASK | Water proofing and soil backfilling to 0.5m below top of Tunnel Bay 3 to Bay 1 | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1836 | TT_TASK | Mass infill between D-wall and tunnel wall | Fri Oct 11 08:00:00 IDT 2013 | Wed Oct 16 18:00:00 IDT 2013 | Fri Sep 20 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1837 | TT_TASK | Removal S3 and S2 | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
1838 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 4 | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Sat May 18 18:00:00 IDT 2013 |  | COMPLETED
1839 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 5 and remove S3 & S2 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1840 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 6 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1843 | TT_TASK | Pre-drilling and guidewall | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1844 | TT_TASK | D-wall design review | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1845 | TT_TASK | D-wall construction (4741m3) | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 |  | COMPLETED
1846 | TT_TASK | Shear pin and pumping test | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 15 18:00:00 IST 2012 | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1848 | TT_TASK | ELS works to formation level from SN16 to SN19 (soil: 8,700m3 @350m3/day, Install S1 to S3 strut 5 days/layer) | Wed Sep 25 08:00:00 IDT 2013 | Wed Nov 13 18:00:00 IST 2013 | Wed May 08 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1849 | TT_TASK | Design temporary bridge and approval | Mon Sep 01 08:00:00 IDT 2014 | Wed Nov 12 18:00:00 IST 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1850 | TT_TASK | Application of tree transplant | Sat Jun 01 08:00:00 IDT 2013 | Wed Oct 23 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1851 | TT_TASK | Tree transplant | Tue Oct 14 08:00:00 IDT 2014 | Mon Nov 10 18:00:00 IST 2014 | Tue Sep 02 08:00:00 IDT 2014 | Tue Sep 30 18:00:00 IDT 2014 |  | COMPLETED
1852 | TT_TASK | Erection temporary bridge deck | Fri Oct 03 08:00:00 IDT 2014 | Fri Dec 05 18:00:00 IST 2014 | Fri Oct 03 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1853 | TT_TASK | ELS works to formation level from SN10 to SN15 (soil: 9,455m3 @330m3/day, install S1 to S3 strut 5 days/layer) | Mon Nov 24 08:00:00 IST 2014 | Sat Jan 17 18:00:00 IST 2015 | Mon Nov 24 08:00:00 IST 2014 | Tue Jun 23 18:00:00 IDT 2015 |  | COMPLETED
1856 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
1857 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1858 | TT_TASK | Erect external formwork for wall and roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1859 | TT_TASK | Concreting for wall and roof (215m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
1860 | TT_TASK | Curing for wall and roof | Sun Dec 08 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
1861 | TT_TASK | Preparation of construction joint for wall and roof | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1862 | TT_TASK | Removal external and internal formwork for wall | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1863 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1864 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 03 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 | Mon Mar 24 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
1866 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 14 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1867 | TT_TASK | Rebar fixing for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1868 | TT_TASK | Erect external formwork for wall and roof | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1869 | TT_TASK | Concreting for wall and roof (215m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1870 | TT_TASK | Curing for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Sun Dec 29 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1871 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
1872 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 17 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
1873 | TT_TASK | Removal internal falsework and formwork for roof | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1874 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 |  | COMPLETED
1876 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 28 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Nov 28 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1877 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1878 | TT_TASK | Erect external formwork for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1879 | TT_TASK | Concreting for wall and roof (215m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1880 | TT_TASK | Curing for wall and roof | Wed Jan 01 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
1881 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
1882 | TT_TASK | Removal external and internal formwork for wall | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 |  | COMPLETED
1883 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
1884 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 |  | COMPLETED
1886 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1887 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 14 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1888 | TT_TASK | Erect external formwork for wall and roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1889 | TT_TASK | Concreting for wall and roof (215m3) | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1890 | TT_TASK | Curing for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1892 | TT_TASK | Removal external and internal formwork for wall | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1893 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1894 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 |  | COMPLETED
1896 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 08:00:00 IST 2013 |  | COMPLETED
1897 | TT_TASK | Rebar fixing for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1898 | TT_TASK | Erect external formwork for wall and roof | Fri Jan 03 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1899 | TT_TASK | Concreting for wall and roof (215m3) | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1900 | TT_TASK | Curing for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 16 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1901 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Tue Jan 07 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1902 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1903 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1904 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 |  | COMPLETED
1906 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1907 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1908 | TT_TASK | Erect external formwork for wall and roof | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1909 | TT_TASK | Concreting for wall and roof (215m3) | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1910 | TT_TASK | Curing for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1911 | TT_TASK | Preparation of construction joint for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1912 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1913 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1914 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 |  | COMPLETED
1916 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1917 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 |  | COMPLETED
1918 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Tue Jun 04 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 |  | COMPLETED
1919 | TT_TASK | Concreting for wall and roof (333m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1920 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1921 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Wed Jun 12 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1922 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 |  | COMPLETED
1923 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
1924 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 05 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Tue Mar 04 18:00:00 IST 2014 |  | COMPLETED
1926 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1927 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1928 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1929 | TT_TASK | Concreting for wall and roof (412m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1930 | TT_TASK | Curing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Sun Jun 23 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Sat Mar 23 18:00:00 IST 2013 |  | COMPLETED
1931 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Mar 25 08:00:00 IST 2013 | Mon Mar 25 18:00:00 IST 2013 |  | COMPLETED
1932 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Mar 26 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1933 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jun 24 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1934 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 27 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Mon Mar 03 18:00:00 IST 2014 |  | COMPLETED
1936 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1937 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1938 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Apr 02 18:00:00 IDT 2013 |  | COMPLETED
1939 | TT_TASK | Concreting for wall and roof (320m3) | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Apr 05 08:00:00 IDT 2013 | Fri Apr 05 18:00:00 IDT 2013 |  | COMPLETED
1940 | TT_TASK | Curing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 06 08:00:00 IDT 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1941 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1942 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1943 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1944 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jan 21 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Sat Mar 01 18:00:00 IST 2014 |  | COMPLETED
1946 | TT_TASK | Excavation and saw cut D-wall | Thu Apr 02 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Sat Jul 25 18:00:00 IDT 2015 |  | COMPLETED
1947 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Aug 08 16:24:00 IDT 2015 | Mon Aug 10 16:24:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Mon Jul 13 18:00:00 IDT 2015 |  | COMPLETED
1948 | TT_TASK | Erect external formwork for base slab | Mon Aug 10 16:24:00 IDT 2015 | Wed Aug 12 16:24:00 IDT 2015 | Tue Jul 14 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
1949 | TT_TASK | Rebar fixing for base slab | Wed Aug 12 16:24:00 IDT 2015 | Fri Aug 14 16:24:00 IDT 2015 | Wed Jul 15 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1950 | TT_TASK | Erect internal kicker formwork for base slab | Fri Aug 14 16:24:00 IDT 2015 | Mon Aug 17 16:24:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Wed Aug 12 18:00:00 IDT 2015 |  | COMPLETED
1951 | TT_TASK | Concreting for base slab (90m3) | Wed Sep 02 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 | Thu Aug 13 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 |  | COMPLETED
1952 | TT_TASK | Curing for base slab | Thu Sep 03 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Fri Aug 14 08:00:00 IDT 2015 | Thu Aug 20 18:00:00 IDT 2015 |  | COMPLETED
1953 | TT_TASK | Preparation of construction joint for base slab | Thu Sep 03 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Fri Aug 21 08:00:00 IDT 2015 | Fri Aug 21 18:00:00 IDT 2015 |  | COMPLETED
1954 | TT_TASK | Removal of formwork for base slab | Fri Sep 04 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Sat Aug 22 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 |  | COMPLETED
1955 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Sep 05 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 | Mon Aug 24 08:00:00 IDT 2015 | Mon Aug 24 18:00:00 IDT 2015 |  | COMPLETED
1956 | TT_TASK | Curing | Thu Sep 10 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Tue Aug 25 08:00:00 IDT 2015 | Tue Aug 25 18:00:00 IDT 2015 |  | COMPLETED
1957 | TT_TASK | Removal strut S3 | Sat Sep 19 08:00:00 IDT 2015 | Wed Sep 23 18:00:00 IDT 2015 | Wed Sep 16 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
1958 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Sep 24 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
1959 | TT_TASK | Rebar fixing for wall and roof | Wed Sep 30 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 | Fri Sep 25 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 |  | COMPLETED
1960 | TT_TASK | Erect external formwork for wall and roof | Thu Oct 15 08:00:00 IDT 2015 | Fri Oct 16 18:00:00 IDT 2015 | Mon Oct 05 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
1961 | TT_TASK | Concreting for wall and roof (260m3) | Sat Oct 17 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 | Wed Oct 07 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1962 | TT_TASK | Curing for wall and roof | Sun Oct 18 08:00:00 IDT 2015 | Tue Oct 27 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 |  | COMPLETED
1963 | TT_TASK | Preparation of construction joint for wall and roof | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
1964 | TT_TASK | Removal external and internal formwork for wall | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
1965 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 28 08:00:00 IST 2015 | Thu Oct 29 18:00:00 IST 2015 | Thu Oct 22 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1966 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Oct 30 08:00:00 IST 2015 | Wed Nov 04 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1968 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 02 18:00:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 |  | COMPLETED
1969 | TT_TASK | Erect external formwork for base slab | Fri Jul 03 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Tue Jul 21 08:00:00 IDT 2015 | Wed Jul 22 18:00:00 IDT 2015 |  | COMPLETED
1970 | TT_TASK | Rebar fixing for base slab | Mon Jul 06 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 23 08:00:00 IDT 2015 | Fri Jul 24 18:00:00 IDT 2015 |  | COMPLETED
1971 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jul 08 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Sat Jul 25 08:00:00 IDT 2015 | Mon Jul 27 18:00:00 IDT 2015 |  | COMPLETED
1972 | TT_TASK | Concreting for base slab (123m3) | Fri Jul 10 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jul 28 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 |  | COMPLETED
1973 | TT_TASK | Curing for base slab | Sat Jul 11 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1974 | TT_TASK | Preparation of construction joint for base slab | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 |  | COMPLETED
1975 | TT_TASK | Removal of formwork for base slab | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 |  | COMPLETED
1976 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1977 | TT_TASK | Curing | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 |  | COMPLETED
1978 | TT_TASK | Removal strut S3 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1979 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 |  | COMPLETED
1980 | TT_TASK | Rebar fixing for wall and roof | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 |  | COMPLETED
1981 | TT_TASK | Erect external formwork for wall and roof | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 |  | COMPLETED
1982 | TT_TASK | Concreting for wall and roof (260m3) | Fri Oct 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 | Sat Oct 24 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
1983 | TT_TASK | Curing for wall and roof | Sat Oct 03 08:00:00 IDT 2015 | Mon Oct 12 18:00:00 IDT 2015 | Mon Oct 26 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1984 | TT_TASK | Preparation of construction joint for wall and roof | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
1985 | TT_TASK | Removal external and internal formwork for wall | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1986 | TT_TASK | Removal internal falsework and formwork for roof | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1987 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1989 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
1990 | TT_TASK | Erect external formwork for base slab | Mon Jun 15 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1991 | TT_TASK | Rebar fixing for base slab | Wed Jun 17 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
1992 | TT_TASK | Erect internal kicker formwork for base slab | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
1993 | TT_TASK | Concreting for base slab (127m3) | Tue Jun 23 08:00:00 IDT 2015 | Tue Jun 23 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
1994 | TT_TASK | Curing for base slab | Wed Jun 24 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
1995 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 24 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1996 | TT_TASK | Removal of formwork for base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
1997 | TT_TASK | Infill concrete in between D-wall and base slab | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1998 | TT_TASK | Curing | Thu May 28 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1999 | TT_TASK | Removal strut S3 | Fri May 29 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2000 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 03 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2001 | TT_TASK | Rebar fixing for wall and roof | Mon Jun 08 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2002 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2003 | TT_TASK | Concreting for wall and roof (260m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2004 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2005 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2006 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2007 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2008 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 11 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2010 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
2011 | TT_TASK | Erect external formwork for base slab | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
2012 | TT_TASK | Rebar fixing for base slab | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
2013 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
2014 | TT_TASK | Concreting for base slab (127m3) | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
2015 | TT_TASK | Curing for base slab | Thu Jun 11 08:00:00 IDT 2015 | Wed Jun 17 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2016 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 11 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
2017 | TT_TASK | Removal of formwork for base slab | Sat May 23 08:00:00 IDT 2015 | Sat May 23 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
2018 | TT_TASK | Infill concrete in between D-wall and base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
2019 | TT_TASK | Curing | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2020 | TT_TASK | Removal strut S3 | Thu May 28 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2021 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2022 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2023 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2024 | TT_TASK | Concreting for wall and roof (150m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2025 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2026 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2027 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2028 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2029 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jul 06 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
2031 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2032 | TT_TASK | Erect external formwork for base slab | Thu May 21 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2033 | TT_TASK | Rebar fixing for base slab | Sat May 23 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2034 | TT_TASK | Erect internal kicker formwork for base slab | Wed May 27 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2035 | TT_TASK | Concreting for base slab (70m3) | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2036 | TT_TASK | Curing for base slab | Sat May 30 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2037 | TT_TASK | Preparation of construction joint for base slab | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2038 | TT_TASK | Removal of formwork for base slab | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2039 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2040 | TT_TASK | Curing | Sat Jun 06 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2041 | TT_TASK | Removal strut S3 | Mon Jun 08 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat May 23 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2043 | TT_TASK | Rebar fixing for wall and roof | Fri May 29 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2044 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2045 | TT_TASK | Concreting for wall and roof (175m3) | Thu Jun 04 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2046 | TT_TASK | Curing for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sun Jun 14 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2047 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2048 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 03 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 04 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2050 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 29 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
2052 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2053 | TT_TASK | Erect external formwork for base slab | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2054 | TT_TASK | Rebar fixing for base slab | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2055 | TT_TASK | Erect internal kicker formwork for base slab | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2056 | TT_TASK | Concreting for base slab (70m3) | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2057 | TT_TASK | Curing for base slab | Wed Apr 22 08:00:00 IDT 2015 | Tue Apr 28 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2058 | TT_TASK | Preparation of construction joint for base slab | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2059 | TT_TASK | Removal of formwork for base slab | Thu Apr 23 08:00:00 IDT 2015 | Thu Apr 23 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2060 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Apr 24 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2061 | TT_TASK | Curing | Wed Apr 29 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2062 | TT_TASK | Removal strut S3 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2063 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed May 06 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2064 | TT_TASK | Rebar fixing for wall and roof | Thu May 14 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2065 | TT_TASK | Erect external formwork for wall and roof | Mon May 18 08:00:00 IDT 2015 | Tue May 19 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2066 | TT_TASK | Concreting for wall and roof (175m3) | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2067 | TT_TASK | Curing for wall and roof | Thu May 21 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2068 | TT_TASK | Preparation of construction joint for wall and roof | Thu May 21 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2069 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2070 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2071 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jun 23 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
2073 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Fri Nov 15 18:00:00 IST 2013 |  | COMPLETED
2074 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Nov 16 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2075 | TT_TASK | Rebar fixing for base slab | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
2076 | TT_TASK | Erect internal kicker formwork for base slab | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
2077 | TT_TASK | Concreting for base slab (70m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
2078 | TT_TASK | Curing for base slab | Fri Dec 20 08:00:00 IST 2013 | Thu Dec 26 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
2079 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 |  | COMPLETED
2080 | TT_TASK | Removal of formwork for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
2081 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
2082 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2083 | TT_TASK | Removal strut S3 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2084 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Apr 16 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2085 | TT_TASK | Rebar fixing for wall and roof | Thu Apr 24 08:00:00 IDT 2014 | Sat Apr 26 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 |  | COMPLETED
2086 | TT_TASK | Erect external formwork for wall and roof | Mon Apr 28 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Thu Apr 10 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2087 | TT_TASK | Concreting for wall and roof (170m3) | Wed Apr 30 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Sat Apr 12 08:00:00 IDT 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
2088 | TT_TASK | Curing for wall and roof | Thu May 01 08:00:00 IDT 2014 | Sat May 10 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Tue Apr 22 18:00:00 IDT 2014 |  | COMPLETED
2089 | TT_TASK | Preparation of construction joint for wall and roof | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 |  | COMPLETED
2090 | TT_TASK | Removal external and internal formwork for wall | Sat May 03 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Tue Apr 15 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
2091 | TT_TASK | Removal internal falsework and formwork for roof | Mon May 12 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 |  | COMPLETED
2092 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jun 05 08:00:00 IDT 2014 | Tue Jun 10 18:00:00 IDT 2014 | Thu May 29 08:00:00 IDT 2014 | Thu Dec 04 18:00:00 IST 2014 |  | COMPLETED
2094 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2095 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2096 | TT_TASK | Rebar fixing for base slab | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2097 | TT_TASK | Erect internal kicker formwork for base slab | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2098 | TT_TASK | Concreting for base slab (70m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2099 | TT_TASK | Curing for base slab | Sun Dec 08 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2100 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2101 | TT_TASK | Removal of formwork for base slab | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
2102 | TT_TASK | Infill concrete in between D-wall and base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
2103 | TT_TASK | Curing | Sun Dec 15 08:00:00 IST 2013 | Sun Dec 15 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2104 | TT_TASK | Removal strut S3 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2105 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Feb 12 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2106 | TT_TASK | Rebar fixing for wall and roof | Mon Feb 17 08:00:00 IST 2014 | Wed Feb 19 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
2107 | TT_TASK | Erect external formwork for wall and roof | Fri Feb 28 13:48:00 IST 2014 | Mon Mar 03 13:48:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2108 | TT_TASK | Concreting for wall and roof (200m3) | Mon Mar 03 13:48:00 IST 2014 | Tue Mar 04 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2109 | TT_TASK | Curing for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Fri Mar 14 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2110 | TT_TASK | Preparation of construction joint for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Wed Mar 05 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2111 | TT_TASK | Removal external and internal formwork for wall | Wed Mar 05 13:48:00 IST 2014 | Thu Mar 06 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
2112 | TT_TASK | Removal internal falsework and formwork for roof | Fri Mar 14 13:48:00 IST 2014 | Mon Mar 17 13:48:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2113 | TT_TASK | Side walkway and cable bracket (204m3) | Thu May 29 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Wed Dec 03 18:00:00 IST 2014 |  | COMPLETED
2115 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2116 | TT_TASK | Erect external formwork for base slab | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2117 | TT_TASK | Rebar fixing for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2118 | TT_TASK | Erect internal kicker formwork for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2119 | TT_TASK | Concreting for base slab (70m3) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2120 | TT_TASK | Curing for base slab | Tue Dec 03 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2121 | TT_TASK | Preparation of construction joint for base slab | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
2122 | TT_TASK | Removal of formwork for base slab | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2123 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2124 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2125 | TT_TASK | Removal strut S3 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
2126 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jan 25 08:00:00 IST 2014 | Wed Jan 29 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
2127 | TT_TASK | Rebar fixing for wall and roof | Thu Jan 30 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Fri Dec 20 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
2128 | TT_TASK | Erect external formwork for wall and roof | Thu Feb 20 08:00:00 IST 2014 | Fri Feb 21 18:00:00 IST 2014 | Thu Jan 09 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2129 | TT_TASK | Concreting for wall and roof (200m3) | Sat Feb 22 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2130 | TT_TASK | Curing for wall and roof | Sun Feb 23 08:00:00 IST 2014 | Tue Mar 04 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2131 | TT_TASK | Preparation of construction joint for wall and roof | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Tue Jan 14 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2132 | TT_TASK | Removal external and internal formwork for wall | Tue Feb 25 08:00:00 IST 2014 | Tue Feb 25 18:00:00 IST 2014 | Wed Jan 15 08:00:00 IST 2014 | Wed Jan 15 18:00:00 IST 2014 |  | COMPLETED
2133 | TT_TASK | Removal internal falsework and formwork for roof | Wed Mar 05 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2134 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
2137 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Sep 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
2138 | TT_TASK | Erect external formwork for base slab | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Sep 21 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
2139 | TT_TASK | Rebar fixing for base slab | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
2140 | TT_TASK | Erect internal kicker formwork for base slab | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
2141 | TT_TASK | Staircase construction (+12.0mPD to +14.706mPD) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2142 | TT_TASK | Concreting for base slab (30m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
2143 | TT_TASK | Curing for base slab | Fri Dec 13 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
2144 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
2145 | TT_TASK | Removal of formwork for base slab | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 18:00:00 IDT 2013 |  | COMPLETED
2146 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2147 | TT_TASK | Mass concrete at level +12.0mPD | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 |  | COMPLETED
2148 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2149 | TT_TASK | Removal strut S3 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2150 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 17 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Mon Dec 01 18:00:00 IST 2014 |  | COMPLETED
2152 | TT_TASK | Erect working platform to +21.0mPD | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2153 | TT_TASK | Rebar fixing for wall and roof | Sat Jan 11 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2154 | TT_TASK | Staircase construction (+14.706mPD to +16.956mPD) (20m3) | Fri May 02 08:00:00 IDT 2014 | Wed May 07 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2155 | TT_TASK | Staircase construction (+16.956mPD to +19.206mPD) (20m3) | Thu Jun 05 08:00:00 IDT 2014 | Mon Jun 09 18:00:00 IDT 2014 | Thu Jun 12 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2156 | TT_TASK | Staircase construction (+19.206mPD to +21.456mPD) (20m3) | Tue Jun 10 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Fri Jun 20 18:00:00 IDT 2014 |  | COMPLETED
2157 | TT_TASK | Erect external formwork for wall and roof | Sat Mar 15 08:00:00 IST 2014 | Mon Mar 17 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2158 | TT_TASK | Concreting for wall and roof (31m3) | Tue Feb 04 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2159 | TT_TASK | Curing for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 |  | COMPLETED
2160 | TT_TASK | Preparation of construction joint for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2161 | TT_TASK | Removal external and internal formwork for wall | Thu Feb 06 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2162 | TT_TASK | Removal internal falsework and formwork for roof | Sat Feb 15 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Thu Jan 23 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2164 | TT_TASK | Removal strut S2 @ SN 19 | Wed Apr 02 08:00:00 IDT 2014 | Mon Apr 07 18:00:00 IDT 2014 | Mon Mar 03 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 |  | COMPLETED
2165 | TT_TASK | Erect working platform to +24.0mPD | Tue Apr 08 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 | Fri Mar 07 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 |  | COMPLETED
2166 | TT_TASK | Erect internal formwork below strut S1 | Sat Apr 12 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 | Wed Mar 12 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 |  | COMPLETED
2167 | TT_TASK | Staircase construction (+21.456mPD to +23.706mPD) (20m3) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 |  | COMPLETED
2168 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 | Fri Mar 14 08:00:00 IST 2014 | Tue Apr 01 18:00:00 IDT 2014 |  | COMPLETED
2169 | TT_TASK | Erect external wall & internal wall formwork | Tue May 13 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Wed Apr 02 08:00:00 IDT 2014 | Thu Apr 03 18:00:00 IDT 2014 |  | COMPLETED
2170 | TT_TASK | Concreting (External Wall & Internal Wall) (264m3) | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Fri Apr 04 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2171 | TT_TASK | Curing (External Wall & Internal Wall) | Fri May 16 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2172 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Mon May 19 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Thu Apr 10 18:00:00 IDT 2014 |  | COMPLETED
2173 | TT_TASK | Waterproofing | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 |  | COMPLETED
2174 | TT_TASK | Backfilling | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2176 | TT_TASK | Removal strut S1 @ SN 19 | Thu Jun 19 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2177 | TT_TASK | Erect working platform to +30.406mPD | Tue Jun 24 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2178 | TT_TASK | Erect internal formwork | Sat Jun 28 08:00:00 IDT 2014 | Sat Jun 28 18:00:00 IDT 2014 | Wed Jun 04 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2179 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Mon Jun 30 08:00:00 IDT 2014 | Wed Jul 02 18:00:00 IDT 2014 | Thu Jun 05 08:00:00 IDT 2014 | Fri Jun 06 18:00:00 IDT 2014 |  | COMPLETED
2180 | TT_TASK | Erect external formwork (External Wall & Internal Wall) | Thu Jul 03 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2181 | TT_TASK | Concreting (External Wall & Internal Wall) (128m3) | Fri Jul 04 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2182 | TT_TASK | Curing (External Wall & Internal Wall) | Sat Jul 05 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 18:00:00 IDT 2014 |  | COMPLETED
2183 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Tue Jul 08 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2184 | TT_TASK | Waterproofing | Wed Jul 09 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Thu Jun 19 18:00:00 IDT 2014 |  | COMPLETED
2185 | TT_TASK | Backfilling | Sat Jul 12 08:00:00 IDT 2014 | Wed Jul 16 18:00:00 IDT 2014 | Fri Jun 20 08:00:00 IDT 2014 | Tue Jun 24 18:00:00 IDT 2014 |  | COMPLETED
2186 | TT_TASK | Erect falsework and soffit formwork +30.206mPD | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 | Wed Jun 25 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2187 | TT_TASK | Staircase construction (+21.456mPD to +25.956mPD) (20m3) | Sat Jul 19 08:00:00 IDT 2014 | Wed Jul 23 18:00:00 IDT 2014 | Fri Jun 27 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2188 | TT_TASK | Staircase construction (+25.956mPD to +27.606mPD) (20m3) | Sat Jul 05 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 05 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 |  | COMPLETED
2189 | TT_TASK | Rebar fixing (Beam, Floor Slab and Staircase) | Thu Jul 10 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Thu Jul 10 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2190 | TT_TASK | Concreting (Beam, Floor Slab and Staircase) (31m3) | Fri Jul 11 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2191 | TT_TASK | Curing (Beam, Floor Slab and Staircase) | Wed Sep 03 08:00:00 IDT 2014 | Tue Sep 09 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2193 | TT_TASK | Erect working platform to +33.576mPD | Wed Sep 03 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
2194 | TT_TASK | Erect external formwork (External Wall) | Mon Sep 08 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 | Fri Sep 26 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2195 | TT_TASK | Rebar fixing (External Wall) | Thu Sep 11 08:00:00 IDT 2014 | Fri Sep 12 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2196 | TT_TASK | Erect internal formwork (External Wall) | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 |  | COMPLETED
2197 | TT_TASK | Concreting (External Wall) (49m3) | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 |  | COMPLETED
2198 | TT_TASK | Curing (External Wall) | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 |  | COMPLETED
2199 | TT_TASK | Removal formwork (External Wall) | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
2200 | TT_TASK | Erect falsework and soffit formwork +32.656 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2201 | TT_TASK | Rebar fixing (Beam & Floor Slab) | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 |  | COMPLETED
2202 | TT_TASK | Concreting (Beam & Floor Slab) (31m3) | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 |  | COMPLETED
2203 | TT_TASK | Curing (Beam & Floor Slab) | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2205 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
2206 | TT_TASK | Rebar fixing (Roof Parapet Wall) | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 |  | COMPLETED
2207 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2208 | TT_TASK | Concreting (Roof Parapet Wall) (30m3) | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
2209 | TT_TASK | Curing (Roof Parapet Wall) | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 |  | COMPLETED
2210 | TT_TASK | Removal formwork (Roof Parapet Wall) | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2211 | TT_TASK | Removal of falsework and soffit formwork | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
2213 | TT_TASK | Wet trade work | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 |  | COMPLETED
2214 | TT_TASK | Metal works (Louver, Door, Cat-ladder, Architectural Fins, Handrail, Roof Sliding Hatch and Balustrade, etc) | Thu Nov 27 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Thu Nov 27 08:00:00 IST 2014 | Thu Mar 05 18:00:00 IST 2015 |  | COMPLETED
2215 | TT_TASK | Coat works | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2218 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Nov 29 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Feb 04 18:00:00 IST 2014 |  | COMPLETED
2219 | TT_TASK | Backfilling between D-wall and 0.5m below S1 14,240m3 soil | Thu Feb 06 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 | Wed Feb 05 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 |  | COMPLETED
2220 | TT_TASK | Removal of S1 | Wed Mar 12 08:00:00 IST 2014 | Tue Mar 25 18:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 |  | COMPLETED
2221 | TT_TASK | Backfilling to original ground level 21,390m3 (approx. +25.0mPD) | Sat Mar 01 08:00:00 IST 2014 | Wed Mar 19 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Sat May 03 18:00:00 IDT 2014 |  | COMPLETED
2223 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 |  | COMPLETED
2224 | TT_TASK | Backfilling between D-wall and 0.5m below S1 (2075m3) | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 |  | COMPLETED
2225 | TT_TASK | Removal of S1 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 |  | COMPLETED
2226 | TT_TASK | Backfilling to original ground level 3,900m3 (approx. +25.0mPD) (1353m3) | Sat Mar 01 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
2227 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
2228 | TT_TASK | Backfilling backfilling to +20mPD from SN8 to SN9 (Soil: 7,050m3 @ 500m3/day) | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 |  | COMPLETED
2229 | TT_TASK | Removal of S1 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
2230 | TT_TASK | Construction of mud pit | Sat Jul 06 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
2231 | TT_TASK | Backfilling from +20mPD to ground level from SN8 to SN9 (Soil: 5,000m3 @ 500m3/day) | Tue Aug 06 08:00:00 IDT 2013 | Sat Aug 17 18:00:00 IDT 2013 | Tue Jul 02 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 |  | COMPLETED
2233 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Aug 07 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2234 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) | Fri Aug 14 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2235 | TT_TASK | Placing mass concrete infill between tunnel and D-wall | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 02 18:00:00 IST 2015 | Thu Dec 24 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2236 | TT_TASK | Removal of S2 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 10 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 04 18:00:00 IST 2016 |  | COMPLETED
2237 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2238 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
2239 | TT_TASK | Removal strut S1 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2240 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
2241 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488 m3 of soil) | Mon Jan 25 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Fri Apr 01 18:00:00 IDT 2016 |  | COMPLETED
2243 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) (SN18-19) | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 |  | COMPLETED
2244 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) (SN18-19) | Sat Apr 26 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Sat Apr 26 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
2245 | TT_TASK | Placing mass concrete infill between tunnel and D-wall (SN18-19) | Tue May 20 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri May 16 18:00:00 IDT 2014 |  | COMPLETED
2246 | TT_TASK | Removal of S2 (SN16-18) | Wed Jun 04 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 |  | COMPLETED
2247 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) (SN16-18) | Mon Jun 09 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Tue May 27 18:00:00 IDT 2014 |  | COMPLETED
2248 | TT_TASK | Removal strut S1 (SN16-18) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Wed May 28 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
2249 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488m3 of soil) | Fri Jun 27 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
2251 | TT_TASK | Dismantling temporary bridge deck | Mon Jun 15 08:00:00 IDT 2015 | Tue Jul 21 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2252 | TT_TASK | Reinstatement of Works Area 4.10 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jan 11 18:00:00 IST 2017 | Mon May 02 08:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 |  | COMPLETED
2253 | TT_TASK | Complete all tree planting and reinstate Works Area 4.12C | Tue Nov 01 08:00:00 IST 2016 | Thu Jul 13 18:00:00 IDT 2017 | Sat Oct 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2254 | TT_TASK | Reinstate Works Areas 4.9, 4.9A and 4.12A prior to handover | Mon May 22 08:00:00 IDT 2017 | Sat Sep 02 18:00:00 IDT 2017 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2258 | TT_TASK | Application of power supply, environmental permits and construction substation | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2259 | TT_TASK | Procurement and Confirmation of the order of 2nd tunnel boring machine | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2260 | TT_TASK | TBM design and submission for approval | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2261 | TT_TASK | TBM materials order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
2262 | TT_TASK | TBM equipments order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 |  | COMPLETED
2263 | TT_TASK | TBM Fabrication | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
2264 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 |  | COMPLETED
2265 | TT_TASK | TBM test Run | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2266 | TT_TASK | TBM disassembly and packing for shipping to HK | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 |  | COMPLETED
2267 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
2268 | TT_TASK | Setup TBM facilities | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
2269 | TT_TASK | Fabrication 50% of South Tunnel South Bound Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
2270 | TT_TASK | Fabrication 100% of South Tunnel South Bound Precast Lining | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
2271 | TT_TASK | Fabrication 50% of South Tunnel North Bound Precast Lining | Wed Oct 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 | Wed Oct 03 08:00:00 IST 2012 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
2272 | TT_TASK | Fabrication 100% of South Tunnel North Bound Precast Lining | Mon Aug 26 08:00:00 IDT 2013 | Wed Jan 22 18:00:00 IST 2014 | Wed Feb 27 08:00:00 IST 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
2274 | TT_TASK | Ground treatment at lauching shaft Southbound | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
2275 | TT_TASK | TBM assemble, thrust frame, testing and commissioning | Sat Jun 01 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2276 | TT_TASK | Lowing back-up plant for final drive | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
2277 | TT_TASK | Assemble and set up back-up plant for final drive | Sat Jun 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2278 | TT_TASK | Erection of noise enclosure | Sat Jul 20 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 |  | COMPLETED
2279 | TT_TASK | TBM drive & lining installation CH124+912 to CH125+012 (Initial Drive) | Sat Jul 20 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Mon Mar 11 00:00:00 IST 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
2280 | TT_TASK | TBM drive & lining installation CH125+012 to CH125+338 | Tue Oct 15 08:00:00 IDT 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon May 27 08:00:00 IDT 2013 | Tue May 20 00:00:00 IDT 2014 |  | COMPLETED
2281 | TT_TASK | Dis-assemble TBM | Fri May 23 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 |  | COMPLETED
2282 | TT_TASK | Invert slab and side walkway | Fri Aug 01 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Tue Sep 02 18:00:00 IDT 2014 |  | COMPLETED
2283 | TT_TASK | Installation of cable bracket | Mon Nov 03 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 | Mon Aug 18 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2285 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Sep 01 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 | Sat Aug 09 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2286 | TT_TASK | Ground treatment at lauching shaft Northbound | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 19 18:00:00 IST 2013 | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
2287 | TT_TASK | TBM assemble, testing and commissioning | Wed Jul 02 08:00:00 IDT 2014 | Wed Sep 03 18:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2288 | TT_TASK | Setup back-up plant for final drive | Tue Jun 03 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2289 | TT_TASK | Reinstate of noise enclosure | Fri Oct 10 08:00:00 IDT 2014 | Wed Nov 05 18:00:00 IST 2014 | Tue Oct 28 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
2290 | TT_TASK | TBM drive & lining installation CH124+927 to CH125+027 (Initial Drive) | Fri Oct 10 08:00:00 IDT 2014 | Thu Nov 13 18:00:00 IST 2014 | Thu Oct 30 00:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
2291 | TT_TASK | TBM drive & lining installation CH125+027 to CH125+353 (Final Drive) | Fri Jan 02 08:00:00 IST 2015 | Thu Feb 12 18:00:00 IST 2015 | Mon Dec 08 08:00:00 IST 2014 | Fri Aug 07 00:00:00 IDT 2015 |  | COMPLETED
2292 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Tue Aug 04 08:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
2293 | TT_TASK | Dis-assemble TBM | Tue Aug 04 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
2294 | TT_TASK | Invert slab and side walkway | Wed Sep 09 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
2295 | TT_TASK | Installation of cable bracket | Thu Sep 24 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Aug 31 18:00:00 IDT 2015 |  | COMPLETED
2298 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Partial length) at down track | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 |  | COMPLETED
2299 | TT_TASK | Probe/Grout | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 | Mon Aug 11 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2300 | TT_TASK | Coring of Segment | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 |  | COMPLETED
2301 | TT_TASK | Removal of segment | Tue Sep 02 08:00:00 IDT 2014 | Thu Sep 04 18:00:00 IDT 2014 | Thu Aug 21 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2302 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Sep 05 08:00:00 IDT 2014 | Tue Oct 07 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2303 | TT_TASK | Invert Concrete | Thu Oct 23 08:00:00 IDT 2014 | Sat Nov 01 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2304 | TT_TASK | Wall and Roof concrete | Mon Nov 03 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Mon Oct 13 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
2305 | TT_TASK | Dismantle Temporary frame | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2306 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
2307 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Remaining length ) at down track | Sat May 09 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Thu Apr 16 18:00:00 IDT 2015 |  | COMPLETED
2308 | TT_TASK | Probe/Grout | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
2309 | TT_TASK | Coring of Segment | Fri Oct 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 | Fri Oct 16 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
2310 | TT_TASK | Removal of segment | Wed Oct 07 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
2311 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Oct 10 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Oct 26 08:00:00 IST 2015 | Fri Dec 11 18:00:00 IST 2015 |  | COMPLETED
2312 | TT_TASK | Invert Concrete | Thu Dec 03 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Sat Dec 12 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2313 | TT_TASK | Wall and Roof concrete | Mon Dec 14 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 15 18:00:00 IST 2016 |  | COMPLETED
2314 | TT_TASK | Dismantle Temporary frame | Wed Jan 13 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 |  | COMPLETED
2315 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2318 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 |  | COMPLETED
2319 | TT_TASK | Pre-drill and guide wall | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 |  | COMPLETED
2320 | TT_TASK | D-wall design review | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 |  | COMPLETED
2321 | TT_TASK | D-Wall Construction (1075m3) | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 |  | COMPLETED
2322 | TT_TASK | Shear pin, toe grout and pumping test | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 |  | COMPLETED
2324 | TT_TASK | SI for TBM ground treatment | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2325 | TT_TASK | Design review of TBM ground treatment | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2326 | TT_TASK | Ground treatment for TBM southbound | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
2327 | TT_TASK | Ground treatment for TBM northbound | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2329 | TT_TASK | Capping beam construction | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2330 | TT_TASK | L-Shape wall construction | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
2331 | TT_TASK | Excavate up to +28.5mPD (1488m3) | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 |  | COMPLETED
2332 | TT_TASK | Install Strut S1 +29.0mPD | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 |  | COMPLETED
2333 | TT_TASK | Excavate up to +23.5mPD (2480m3) | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 |  | COMPLETED
2334 | TT_TASK | Install Strut S2 +24.0mPD | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 |  | COMPLETED
2335 | TT_TASK | Excavate up to +19.5mPD (1984m3) | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
2336 | TT_TASK | Install Strut S3 +20.0mPD | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 |  | COMPLETED
2337 | TT_TASK | Excavate up to +15.5mPD (1984m3) | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
2338 | TT_TASK | Install Strut S4 +16.0mPD | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 |  | COMPLETED
2339 | TT_TASK | Excavate up to formation (4117m3) | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
2340 | TT_TASK | Install rock dowel and tie back | Sat Jun 02 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Sat Jun 02 08:00:00 IDT 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2341 | TT_TASK | Temporary handover the shaft to contract 822 | Mon Jun 03 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2343 | TT_TASK | Rock breaking works | Mon Aug 26 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
2344 | TT_TASK | Temporary base Slab for TBM Drive | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
2347 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2348 | TT_TASK | Erect external formwork (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Wed Aug 13 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Tue Aug 19 18:00:00 IDT 2014 |  | COMPLETED
2349 | TT_TASK | Rebar fixing (Base Slab) | Thu Aug 14 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Wed Aug 20 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2350 | TT_TASK | Erect internal kicker formwork (Base Slab) | Tue Aug 19 08:00:00 IDT 2014 | Thu Aug 21 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 |  | COMPLETED
2351 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 22 08:00:00 IDT 2014 | Fri Aug 22 18:00:00 IDT 2014 | Thu Aug 28 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2352 | TT_TASK | Concreting (Base Slab) (245m3) | Sat Aug 23 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014 | Fri Aug 29 18:00:00 IDT 2014 |  | COMPLETED
2353 | TT_TASK | Curing (Base Slab) | Mon Aug 25 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2354 | TT_TASK | Removal of formwork (Base Slab) | Mon Sep 08 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Mon Sep 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2355 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Sep 10 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Tue Sep 02 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 |  | COMPLETED
2356 | TT_TASK | Rebar fixing (Wall and roof) | Thu Sep 18 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Thu Sep 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2357 | TT_TASK | Erect external formwork (Wall) | Thu Sep 25 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2358 | TT_TASK | Clearing and inspection (Wall and roof) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2359 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
2360 | TT_TASK | Curing (Wall and roof) | Sat Oct 11 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
2361 | TT_TASK | Removal formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Thu Oct 16 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Sat Nov 01 18:00:00 IST 2014 |  | COMPLETED
2362 | TT_TASK | Removal formwork (Roof) | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2363 | TT_TASK | Side walkway and cable bracket (72m3) | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
2365 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Nov 07 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Sat Nov 07 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
2366 | TT_TASK | Erect external formwork (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Wed Nov 18 18:00:00 IST 2015 |  | COMPLETED
2367 | TT_TASK | Rebar fixing (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Tue Nov 17 18:00:00 IST 2015 | Thu Nov 19 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 |  | COMPLETED
2368 | TT_TASK | Erect internal kicker formwork (Base Slab) | Wed Nov 18 08:00:00 IST 2015 | Fri Nov 20 18:00:00 IST 2015 | Tue Nov 24 08:00:00 IST 2015 | Thu Nov 26 18:00:00 IST 2015 |  | COMPLETED
2369 | TT_TASK | Clearing and inspection (Base Slab) | Sat Nov 21 08:00:00 IST 2015 | Sat Nov 21 18:00:00 IST 2015 | Fri Nov 27 08:00:00 IST 2015 | Fri Nov 27 18:00:00 IST 2015 |  | COMPLETED
2370 | TT_TASK | Concreting (Base Slab) (245m3) | Mon Nov 23 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Nov 28 08:00:00 IST 2015 | Sat Nov 28 18:00:00 IST 2015 |  | COMPLETED
2371 | TT_TASK | Curing (Base Slab) | Tue Nov 24 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Mon Nov 30 08:00:00 IST 2015 | Thu Dec 03 18:00:00 IST 2015 |  | COMPLETED
2372 | TT_TASK | Removal of formwork (Base Slab) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Fri Dec 04 08:00:00 IST 2015 | Sat Dec 05 18:00:00 IST 2015 |  | COMPLETED
2373 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 09 18:00:00 IST 2015 | Mon Dec 07 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
2374 | TT_TASK | Rebar fixing (Wall and roof) | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2375 | TT_TASK | Erect external formwork (Wall) | Mon Jan 11 08:00:00 IST 2016 | Wed Jan 13 18:00:00 IST 2016 | Thu Jan 07 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2376 | TT_TASK | Clearing and inspection (Wall and roof) | Thu Jan 14 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2377 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Jan 15 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2378 | TT_TASK | Curing (Wall and roof) | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 |  | COMPLETED
2379 | TT_TASK | Removal formwork (Wall) | Tue Jan 19 08:00:00 IST 2016 | Thu Jan 21 18:00:00 IST 2016 | Thu Jan 28 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2380 | TT_TASK | Removal formwork and falsework (Roof) | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Sat Jan 30 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2381 | TT_TASK | Side walkway and cable bracket (72m3) | Wed Jan 06 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Thu Nov 12 08:00:00 IST 2015 | Tue Mar 01 18:00:00 IST 2016 |  | COMPLETED
2382 | TT_TASK | Provision access opening to DC | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2383 | TT_TASK | Erect falsework and soffit formwork (Opening) | Thu Mar 10 08:00:00 IST 2016 | Mon Mar 21 18:00:00 IST 2016 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2384 | TT_TASK | Rebar fixing (Roof) | Tue Mar 22 08:00:00 IST 2016 | Tue Mar 22 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2385 | TT_TASK | Clearing and inspection (Roof) | Wed Mar 23 08:00:00 IST 2016 | Wed Mar 23 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2386 | TT_TASK | Concreting (Roof) (225m3) | Thu Mar 24 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2387 | TT_TASK | Curing (Roof) | Tue Mar 29 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Jan 13 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
2388 | TT_TASK | Removal internal falsework and soffit formwork (Roof) | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
2390 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Thu Mar 17 08:00:00 IST 2016 | Fri Mar 18 18:00:00 IST 2016 | Tue Mar 01 08:00:00 IST 2016 | Wed Mar 02 18:00:00 IST 2016 |  | COMPLETED
2391 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Sat Mar 19 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Thu Mar 03 08:00:00 IST 2016 | Tue Mar 08 18:00:00 IST 2016 |  | COMPLETED
2392 | TT_TASK | Backfilling to +18.25mPD (1229 m3 of soil) | Sat Jul 02 08:00:00 IDT 2016 | Mon Jul 11 18:00:00 IDT 2016 | Mon Jul 25 08:00:00 IDT 2016 | Tue Aug 02 18:00:00 IDT 2016 |  | COMPLETED
2393 | TT_TASK | Laying 500mm mass concrete lateral support | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 |  | COMPLETED
2394 | TT_TASK | Backfilling to 0.5m below S3 (+19.5mPD) (372m3 of soil) | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 |  | COMPLETED
2395 | TT_TASK | Removal strut S3 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 |  | COMPLETED
2396 | TT_TASK | Backfilling to 0.5m below S2 (+23.5mPD) (1984m3 of soil) | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 |  | COMPLETED
2397 | TT_TASK | Removal strut S2 | Wed Aug 24 08:00:00 IDT 2016 | Fri Aug 26 18:00:00 IDT 2016 | Wed Aug 24 08:00:00 IDT 2016 | Thu Sep 01 18:00:00 IDT 2016 |  | COMPLETED
2398 | TT_TASK | Backfilling to 0.5m below S1 (+28.5mPD) (2480m3 of soil) | Mon Sep 05 08:00:00 IDT 2016 | Tue Sep 20 18:00:00 IDT 2016 | Fri Sep 02 08:00:00 IDT 2016 | Fri Sep 09 18:00:00 IDT 2016 |  | COMPLETED
2399 | TT_TASK | Removal strut S1 | Wed Sep 21 08:00:00 IDT 2016 | Thu Sep 22 18:00:00 IDT 2016 | Sat Sep 10 08:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 |  | COMPLETED
2400 | TT_TASK | Backfilling to original ground level (approx. +31.5mPD) (1488m3 of soil) | Fri Sep 23 08:00:00 IDT 2016 | Mon Oct 03 18:00:00 IDT 2016 | Thu Sep 15 08:00:00 IDT 2016 | Mon Sep 19 18:00:00 IDT 2016 |  | COMPLETED
2402 | TT_TASK | Reinstatement of TUT area (Including Hydroseeding) | Mon Oct 03 08:00:00 IDT 2016 | Mon Jun 19 18:00:00 IDT 2017 | Fri Oct 07 08:00:00 IDT 2016 |  | 216.0 | IN_PROGRESS
25 | TT_TASK | Access opening for the up track cut and cover tunnel at Tse Uk Tsuen Shaft | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 10 18:00:00 IST 2016 |  | COMPLETED
27 | TT_TASK | Close out the temporary access opening at Tse Uk Tsuen Shaft | Thu Mar 10 08:00:00 IST 2016 | Tue Apr 05 18:00:00 IDT 2016 | Thu Feb 11 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
307 | TT_TASK | Position crane for TBM retrieval (down track) | Wed Jul 02 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014 | Sat Aug 02 18:00:00 IDT 2014 |  | COMPLETED
308 | TT_TASK | TBM Break-in and Retrieval (down track) | Mon Aug 04 08:00:00 IDT 2014 | Sat Aug 30 18:00:00 IDT 2014 | Mon Aug 04 08:00:00 IDT 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
309 | TT_TASK | Position crane for TBM retrieval (up track) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 |  | COMPLETED
310 | TT_TASK | TBM Break-in and Retrieval (up track) | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
376 | TT_TASK | Supply Engineer with Survey Equipment [PS41.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
377 | TT_TASK | Provide Engineer with suitably qualified full time Survey Assistant - 4 nos. [PS41.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
378 | TT_TASK | Provide Engineer with site transportation as detailed in PS42.1 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 |  | COMPLETED
379 | TT_TASK | Submit details of qualified drivers to be assigned to the Engineer, for review [PS42.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 |  | COMPLETED
380 | TT_TASK | Install, service and maintain 10 container offices for use by the Engineer's Site Staff | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
381 | TT_TASK | Provide services and equipment for the Engineer | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
383 | TT_TASK | Master Programme - Prepare and submit for approval [GS4.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
384 | TT_TASK | Master Programme - Comments , Resubmission and Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
385 | TT_TASK | Time Chainage Programme - Prepare and submit for approval [GS4.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
386 | TT_TASK | Time Chainage Programme - Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
387 | TT_TASK | Implement and Maintain Programme Management System for 1st Audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
388 | TT_TASK | Implement and Maintain Programme Management System for 2nd Audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
389 | TT_TASK | Implement and Maintain Programme Management System for 3rd Audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
391 | TT_TASK | Environmental Management Plan - Prepare and submit for approval [GS5.1.10] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
392 | TT_TASK | Environmental Management Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
393 | TT_TASK | Quality Plan - Prepare and submit for approval [GS9.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
394 | TT_TASK | Quality Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
395 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 1st audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 |  | COMPLETED
396 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 2nd audit | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
397 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 3rd audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
398 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 4th audit | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
399 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 5th audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
400 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 6th audit | Tue Jul 02 08:00:00 IDT 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
401 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 7th audit | Thu Nov 28 08:00:00 IST 2013 | Thu Jun 05 18:00:00 IDT 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Jan 24 18:00:00 IST 2014 |  | COMPLETED
402 | TT_TASK | Health and Safety Plan - Prepare and submit [G3.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
403 | TT_TASK | System Assurance Plan - Prepare and submit for approval [PS Appendix P3.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
404 | TT_TASK | System Assurance Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
405 | TT_TASK | Design for Safety & Constructability Plan - Prepare and submit for approval [PS37.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
406 | TT_TASK | Design for Safety & Constructability Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
408 | TT_TASK | Methods of Construction - Prepare and submit for approval [GS12.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
409 | TT_TASK | Methods of Construction - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
410 | TT_TASK | Contractor's Submission Schedule - Prepare and submit for approval [GS12.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
411 | TT_TASK | Contractor's Submission Schedule - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
412 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) [PS13.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
413 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) - Approval period | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 |  | COMPLETED
414 | TT_TASK | Spoil Disposal Plan [PS17.7.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
415 | TT_TASK | Waste Management Plan [PS22.10.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
416 | TT_TASK | Independent Checking Engineer - Appoint and submit for approval [PS7.1.8] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
417 | TT_TASK | Independent Checking Engineer - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
418 | TT_TASK | Sub-contract Management Plan - Prepare and submit [PS34.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 |  | COMPLETED
419 | TT_TASK | Schedule of Utilities Services Arrangement [GS7.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
420 | TT_TASK | Site Safety Supervision Plan for Site Formation - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
421 | TT_TASK | Site Safety Supervision Plan for Site Formation - Approval period | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
422 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Prepare and Submit | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
423 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
424 | TT_TASK | Site Safety Supervision Plan for ELS - Prepare and Submit | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
425 | TT_TASK | Site Safety Supervision Plan for ELS - Approval Period | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
426 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Prepare and Submit | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
427 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Approval Period | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
428 | TT_TASK | Noise Management Plan [P22.3.9] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
429 | TT_TASK | Air Quality Management Plan [P22.4.3] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
430 | TT_TASK | Detailed Proposal for Water Pollution Control Measures and Proposed Monitoring [PS22.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
431 | TT_TASK | Groundwater Monitoring and Response Plan [PS22.5.2] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
432 | TT_TASK | Vibration Monitoring Plan [PS22.8.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 |  | COMPLETED
433 | TT_TASK | Proposed Outline TTM Scheme - Prepare & submit to the: Engineer for Review / SLG for Approval [PS19.3] | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 |  | COMPLETED
434 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Proposed TTM Scheme [PS19.4] | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 |  | COMPLETED
435 | TT_TASK | Resubmission of Proposed Outline TTM Scheme (if required) | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
436 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Resubmitted Proposed Outline TTM Scheme [PS19.4] | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 |  | COMPLETED
437 | TT_TASK | Notification Period of the Approved TTM Scheme prior to implementation [PS19.4] | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 |  | COMPLETED
440 | TT_TASK | Initial Site Survey (WA3.11) | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 |  | COMPLETED
441 | TT_TASK | Initial Site Survey Report (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 |  | COMPLETED
442 | TT_TASK | Initial Site Survey & Condition Survey (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
443 | TT_TASK | Initial Site Survey Report (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
444 | TT_TASK | Initial Site Survey & Condition Survey (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
445 | TT_TASK | Initial Site Survey Report (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
446 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 4.9 & 4.12A [PS4.2] | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
447 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 5.1 & 5.3 [PS4.2.3] | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 |  | COMPLETED
448 | TT_TASK | Proposal for Site Clearance Works [PS4.4.1] | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 |  | COMPLETED
449 | TT_TASK | Site Clearance / Site Formation Works (including demolition of EBS) | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
450 | TT_TASK | Backfill existing stream courses in Works Area 4.9, 4.10 and 4.11 [PS18.5.1] | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
451 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and submit to EPD for Approval (WA3.3 - Area M, I, L) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
452 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA3.3 - Area M, I, L) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
453 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
454 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
455 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.3 - Area M, I, L) | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
456 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA3.3 - Area M, I, L) | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
457 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA3.3 - Area M, I, L) | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
458 | TT_TASK | Remediation Report - Approval (WA3.3 - Area M, I, L) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
459 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and Submit to EPD for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
460 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
461 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
462 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.1, 3.2, 3.3, 3.3A) | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
463 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.1, 3.2, 3.3, 3.3A) | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 |  | COMPLETED
464 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 |  | COMPLETED
465 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
466 | TT_TASK | Remediation Report - Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
467 | TT_TASK | Conduct remediation for Area Q in accordance with method proposed in the approved Remediation Action Plan [PS22.9.2] | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 |  | COMPLETED
468 | TT_TASK | Remediation Report - Prepare and submit for Approval [PS22.9.2] (Area Q) | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 |  | COMPLETED
469 | TT_TASK | Remediation Report - Approval (Area Q) | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
470 | TT_TASK | Removal of contaminated soil at North Tunnels (Area N,O,P,Q,R,S) | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
471 | TT_TASK | Condition Survey EBS for presence of Asbestos and gather samples | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
472 | TT_TASK | Testing of gathered samples | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 |  | COMPLETED
473 | TT_TASK | Prepare and submit Asbestos Investigation Report (AIR) & Asbestos Abatement Plan (AAP) | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
474 | TT_TASK | Approval period of AIR & AAP | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
475 | TT_TASK | Notification period to Engineer and EPD prior to Asbestos abatement works | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
476 | TT_TASK | Asbestos abatement works | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
477 | TT_TASK | Demolition of EBS | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
478 | TT_TASK | Confirmation of tree survey | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 |  | COMPLETED
480 | TT_TASK | Installation of ground settlement markers | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 |  | COMPLETED
481 | TT_TASK | Settlement monitoring and submit report | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
482 | TT_TASK | Settlement monitoring and submit report | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 |  | COMPLETED
483 | TT_TASK | Settlement monitoring and submit report | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
484 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
485 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Wed Feb 26 18:00:00 IST 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Feb 21 18:00:00 IST 2014 |  | COMPLETED
486 | TT_TASK | Settlement monitoring and submit report | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 |  | COMPLETED
488 | TT_TASK | Permit Applications (incl. License to Search and Excavate Antiquities and Excavation Permit) | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 |  | COMPLETED
489 | TT_TASK | Check for underground utilities | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 |  | COMPLETED
490 | TT_TASK | Field walking and hand augering | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 |  | COMPLETED
491 | TT_TASK | Excavation of trial pits | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 |  | COMPLETED
492 | TT_TASK | Rescue excavation rescue works (if required) | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 |  | COMPLETED
494 | TT_TASK | Erection of Hoarding with Gate (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 |  | COMPLETED
495 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 3.1, 3.2, 3.3 and 3.3A [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
496 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 4.9, 4.10, 4.11, 4.12A~C, and 4.15 [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
497 | TT_TASK | Project Signboard Erection [PS4.6.8] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
498 | TT_TASK | Marine Survey at Barging Point [PS4.3] (before construction of barging facilities) | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 00:00:00 IST 2010 |  | COMPLETED
499 | TT_TASK | Construct barging facilities | Sat Oct 02 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Oct 02 00:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
500 | TT_TASK | Operation Plan for the Barging Facility - Prepare and Submit for Approval [PS17.1.9] | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
501 | TT_TASK | Operation Plan for the Barging Facility - Review and Approval Period | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 |  | COMPLETED
503 | TT_TASK | General and Special Attendance for Designated Contractors | Mon Dec 02 08:00:00 IST 2013 | Mon Aug 31 18:00:00 IDT 2015 | Tue Jul 02 08:00:00 IDT 2013 | Wed Mar 25 18:00:00 IST 2015 |  | COMPLETED
505 | TT_TASK | Prepare and Submit Detailed Interface Specification | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 |  | COMPLETED
506 | TT_TASK | Approval of Detailed Interface Plan | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
507 | TT_TASK | Prepare and Submit Detailed Interface Specification | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 |  | COMPLETED
508 | TT_TASK | Approval of Detailed Interface Plan | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
510 | TT_TASK | Prepare and Submit Draft Operation and Maintenance Manual [PS33.1] | Mon Aug 24 08:00:00 IDT 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jul 28 08:00:00 IDT 2014 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
511 | TT_TASK | Review and approval period of Draft Operation and Maintenance Manual | Wed Aug 10 08:00:00 IDT 2016 | Tue Sep 13 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
512 | TT_TASK | Prepare and Submit Final Operation and Maintenance Manual [PS33.1] | Wed Sep 14 08:00:00 IDT 2016 | Thu Feb 16 18:00:00 IST 2017 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
513 | TT_TASK | Provide Engineer with As-Built Drawing for the Whole of the Works [PS33.2] | Mon Nov 21 08:00:00 IST 2016 | Wed Dec 14 18:00:00 IST 2016 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
514 | TT_TASK | Provide Engineer with Asset Registration Information [PS33.3] | Fri May 19 08:00:00 IDT 2017 | Mon Jun 12 18:00:00 IDT 2017 |  |  |  | NOT_STARTED
517 | TT_TASK | Preliminary Design Programme - Prepare and Submit for Approval [PS7.1.8 - App. Z2.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
518 | TT_TASK | Preliminary Design Programme - Review and Approval Period [PS7.1.8 - App. Z2.2] | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 |  | COMPLETED
519 | TT_TASK | Preliminary Design Programme - Resubmission and Approval (if required) [PS7.1.8 - App. Z2.2] | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 |  | COMPLETED
520 | TT_TASK | Schedule of Designs - Prepare and Submit for Approval [PS7.1.8 - App. Z2.5] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
521 | TT_TASK | Detailed Proposal for Carrying Out the Cross Passage Works [PS11.5.2] | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
524 | TT_TASK | Design TBM and submit full details to the Engineer [PS7.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
525 | TT_TASK | TBM Design - Approval period | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 |  | COMPLETED
526 | TT_TASK | TBM Design - Resubmission and approval period | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 |  | COMPLETED
528 | TT_TASK | AIP Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
529 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 |  | COMPLETED
530 | TT_TASK | DDS Design - Prepare and Submit | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 |  | COMPLETED
531 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 |  | COMPLETED
532 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 |  | COMPLETED
533 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 |  | COMPLETED
534 | TT_TASK | Issue Completed Working Drawings | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
536 | TT_TASK | AIP Design - Prepare and Submit | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 |  | COMPLETED
537 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 |  | COMPLETED
538 | TT_TASK | AIP Design - Response to comments and Resubmit | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
539 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
540 | TT_TASK | DDS Design - Prepare and Submit | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
541 | TT_TASK | DDS Design - Review and Approval Period (by MTRC & related Government Authorities) | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 |  | COMPLETED
542 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 |  | COMPLETED
543 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 |  | COMPLETED
544 | TT_TASK | Issue Completed Working Drawings | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 |  | COMPLETED
546 | TT_TASK | DDS Design - Prepare and Submit | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 |  | COMPLETED
547 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 |  | COMPLETED
548 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 |  | COMPLETED
549 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 |  | COMPLETED
550 | TT_TASK | Issue Completed Working Drawings | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
552 | TT_TASK | AIP Design - Prepare and Submit | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 |  | COMPLETED
553 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
554 | TT_TASK | AIP Design - Response to comments and Resubmit | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 |  | COMPLETED
555 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
556 | TT_TASK | DDS Design - Prepare and Submit | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 |  | COMPLETED
557 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 |  | COMPLETED
558 | TT_TASK | DDS Design - Response to comments and Resubmit | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 |  | COMPLETED
559 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 |  | COMPLETED
560 | TT_TASK | Issue Completed Working Drawings | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 |  | COMPLETED
562 | TT_TASK | Prepare and Submit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 |  | COMPLETED
563 | TT_TASK | Review and Approval Period | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
564 | TT_TASK | Response to comments and Resubmit | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 |  | COMPLETED
565 | TT_TASK | Review and Approval Period (for resubmission) | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 |  | COMPLETED
568 | TT_TASK | DDS Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
569 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 |  | COMPLETED
570 | TT_TASK | DDS Design - Response to comments and Resubmit | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 |  | COMPLETED
571 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 |  | COMPLETED
572 | TT_TASK | Issue Completed Working Drawings | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
574 | TT_TASK | DDS Design - Prepare and Submit | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 |  | COMPLETED
575 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 |  | COMPLETED
576 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 |  | COMPLETED
577 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 |  | COMPLETED
578 | TT_TASK | Issue Completed Working Drawings | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 |  | COMPLETED
580 | TT_TASK | DDS Design - Prepare and Submit | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 |  | COMPLETED
581 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 |  | COMPLETED
582 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 |  | COMPLETED
583 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 |  | COMPLETED
584 | TT_TASK | Issue Completed Working Drawings | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 |  | COMPLETED
586 | TT_TASK | DDS Design - Prepare and Submit | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 |  | COMPLETED
587 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 |  | COMPLETED
588 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 |  | COMPLETED
589 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 |  | COMPLETED
590 | TT_TASK | Issue Completed Working Drawings | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 |  | COMPLETED
592 | TT_TASK | DDS Design - Prepare and Submit | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 |  | COMPLETED
593 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 |  | COMPLETED
594 | TT_TASK | DDS Design - Response to comments and Resubmit | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 |  | COMPLETED
595 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 |  | COMPLETED
596 | TT_TASK | Issue Completed Working Drawings | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
599 | TT_TASK | Formworks / Falsework - Prepare & Submit | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
600 | TT_TASK | Formworks / Falsework - Review & Approval Period (by MTRC) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
601 | TT_TASK | Formworks / Falsework - Response to comments and Resubmit | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 |  | COMPLETED
602 | TT_TASK | Formworks / Falsework - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
605 | TT_TASK | Layout of Site Hoarding - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
606 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (by MTRC) | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
607 | TT_TASK | Layout of Site Hoarding - Response to comments and Resubmit | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
608 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 |  | COMPLETED
610 | TT_TASK | Layout of Engineer's Accommodation - Prepare and Submit | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
611 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (by MTRC) | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 |  | COMPLETED
612 | TT_TASK | Layout of Engineer's Accommodation - Response to comments and Resubmit | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
613 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (for resubmit) (by MTRC & related Government Authorities | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
615 | TT_TASK | TTMS Assessment Report - Prepare and Submit | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 |  | COMPLETED
616 | TT_TASK | TTMS Assessment Report - Review and Approval Period (by MTRC) | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
617 | TT_TASK | TTMS Assessment Report - Response to comments and Resubmit | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 |  | COMPLETED
618 | TT_TASK | TTMS Assessment Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
619 | TT_TASK | Issue Completed Working Drawings | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 |  | COMPLETED
621 | TT_TASK | DIA Report - Prepare and Submit | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 |  | COMPLETED
622 | TT_TASK | DIA Report - Review and Approval Period (by MTRC) | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 |  | COMPLETED
623 | TT_TASK | DIA Report - Response to comments and Resubmit | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 |  | COMPLETED
624 | TT_TASK | DIA Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
625 | TT_TASK | Issue Completed Working Drawings | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 |  | COMPLETED
627 | TT_TASK | AIP Design - Prepare & Submit | Wed Sep 23 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 |  | COMPLETED
628 | TT_TASK | AIP Design - Review & Approval Period (by MTR) | Wed Oct 14 08:00:00 IDT 2015 | Wed Nov 11 18:00:00 IST 2015 | Mon Jun 08 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
629 | TT_TASK | AIP Design - Response to comments and Resubmit | Thu Nov 12 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Mon Jun 15 01:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
630 | TT_TASK | AIP Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jun 22 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
631 | TT_TASK | DDS Design - Prepare & Submit | Wed Jan 13 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Tue Sep 01 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 |  | COMPLETED
632 | TT_TASK | DDS Design - Review & Approval Period (by MTRC) | Fri Feb 26 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 12 18:00:00 IDT 2015 |  | COMPLETED
633 | TT_TASK | DDS Design - Response to comments & Resubmit | Tue Mar 29 08:00:00 IDT 2016 | Fri Apr 01 18:00:00 IDT 2016 | Mon Sep 14 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
634 | TT_TASK | DDS Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Apr 02 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 | Mon Sep 21 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
635 | TT_TASK | Issue Completed Working Drawings | Wed Jan 27 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
637 | TT_TASK | Layout of Barging Point - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
638 | TT_TASK | Layout of Barging Point - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
639 | TT_TASK | Layout of Barging Point - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
640 | TT_TASK | Layout of Barging Point - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
641 | TT_TASK | Loading Ramps - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
642 | TT_TASK | Loading Ramps - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
643 | TT_TASK | Loading Ramps - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
644 | TT_TASK | Loading Ramps - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
645 | TT_TASK | Weighbridge - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
646 | TT_TASK | Weighbridge - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
647 | TT_TASK | Weighbridge - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
648 | TT_TASK | Weighbridge - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
652 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
653 | TT_TASK | Pre-drill and guide wall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
654 | TT_TASK | D-wall construction (1084m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
655 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
656 | TT_TASK | Wang Toi Shan Shan Tsuen Road diversion works | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 |  | COMPLETED
658 | TT_TASK | Excavate up to +10.5mPD (369m3) | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 |  | COMPLETED
659 | TT_TASK | Install Strut S0 +11.0mPD | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 |  | COMPLETED
660 | TT_TASK | Excavate up to +8.0mPD (1525m3) | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 |  | COMPLETED
661 | TT_TASK | Install Strut S1 +8.5mPD | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 |  | COMPLETED
662 | TT_TASK | Excavate up to +4.5mPD (2135m3) | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 |  | COMPLETED
663 | TT_TASK | Install Strut S2 +5.0mPD | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 |  | COMPLETED
664 | TT_TASK | Excavate up to +0.5mPD (2440m3) | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 |  | COMPLETED
665 | TT_TASK | Install Strut S3 +1.0mPD | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 |  | COMPLETED
666 | TT_TASK | Excavate up to -6.5mPD (4340m3) | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 |  | COMPLETED
667 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
668 | TT_TASK | Construction of temporary slab and entrance seal (622m3) | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
672 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 08 18:00:00 IST 2014 | Fri Dec 05 08:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
673 | TT_TASK | Erect external formwork (Base Slab) | Tue Dec 09 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 08 08:00:00 IST 2014 | Tue Dec 09 18:00:00 IST 2014 |  | COMPLETED
674 | TT_TASK | Rebar fixing (Base Slab) | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 18:00:00 IST 2014 | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
675 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Dec 15 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Mon Dec 15 18:00:00 IST 2014 |  | COMPLETED
676 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Dec 17 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Tue Dec 16 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 |  | COMPLETED
677 | TT_TASK | Curing (Base Slab) | Thu Dec 18 08:00:00 IST 2014 | Sat Dec 27 18:00:00 IST 2014 | Wed Dec 17 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
678 | TT_TASK | Removal of formwork (Base Slab) | Fri Dec 19 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 24 18:00:00 IST 2014 |  | COMPLETED
679 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
680 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 | Mon Jun 22 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 |  | COMPLETED
681 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Jun 13 08:00:00 IDT 2015 | Mon Jun 15 18:00:00 IDT 2015 | Thu Jun 25 01:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
682 | TT_TASK | Concreting (Wall & Roof) (444m3) | Tue Jun 16 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
683 | TT_TASK | Curing (Wall & Roof) | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
684 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 |  | COMPLETED
685 | TT_TASK | Removal external formwork (Wall) | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
686 | TT_TASK | Side walkway and cable bracket (360m3) | Sat Jul 18 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Sat Jul 18 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
687 | TT_TASK | Access opening to DC (DC access period) | Tue Oct 06 08:00:00 IDT 2015 | Fri Mar 04 18:00:00 IST 2016 | Tue Oct 06 08:00:00 IDT 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
688 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Sat Dec 12 08:00:00 IST 2015 | Mon Jan 18 18:00:00 IST 2016 | Tue Nov 03 00:00:00 IST 2015 | Mon Nov 30 18:00:00 IST 2015 |  | COMPLETED
690 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 | Tue Apr 12 08:00:00 IDT 2016 | Wed Apr 13 18:00:00 IDT 2016 |  | COMPLETED
691 | TT_TASK | Erect external formwork (Base Slab) | Mon May 23 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Thu Apr 14 08:00:00 IDT 2016 | Fri Apr 15 18:00:00 IDT 2016 |  | COMPLETED
692 | TT_TASK | Rebar fixing (Base Slab) | Wed May 25 08:00:00 IDT 2016 | Fri May 27 18:00:00 IDT 2016 | Sat Apr 16 08:00:00 IDT 2016 | Tue Apr 19 18:00:00 IDT 2016 |  | COMPLETED
693 | TT_TASK | Erect internal kicker formwork (Base Slab) | Sat May 28 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 | Wed Apr 20 08:00:00 IDT 2016 | Thu Apr 21 18:00:00 IDT 2016 |  | COMPLETED
694 | TT_TASK | Concreting (Base Slab) (225m3) | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 | Fri Apr 22 08:00:00 IDT 2016 | Fri Apr 22 18:00:00 IDT 2016 |  | COMPLETED
695 | TT_TASK | Curing (Base Slab) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 08 18:00:00 IDT 2016 | Sat Apr 23 08:00:00 IDT 2016 | Fri Apr 29 18:00:00 IDT 2016 |  | COMPLETED
696 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Sat Apr 30 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
697 | TT_TASK | Removal of formwork (Base Slab) | Tue May 24 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Mon May 09 08:00:00 IDT 2016 | Tue May 10 18:00:00 IDT 2016 |  | COMPLETED
698 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed May 25 08:00:00 IDT 2016 | Sat May 28 18:00:00 IDT 2016 | Wed May 11 08:00:00 IDT 2016 | Mon May 16 18:00:00 IDT 2016 |  | COMPLETED
699 | TT_TASK | Rebar fixing (Wall & Roof) | Mon May 30 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 17 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 |  | COMPLETED
700 | TT_TASK | Erect external formwork (Wall & Roof) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 03 18:00:00 IDT 2016 | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 |  | COMPLETED
701 | TT_TASK | Concreting (Wall & Roof) (444m3) | Sat Jun 04 08:00:00 IDT 2016 | Sat Jun 04 18:00:00 IDT 2016 | Mon May 23 08:00:00 IDT 2016 | Mon May 23 18:00:00 IDT 2016 |  | COMPLETED
702 | TT_TASK | Curing (Wall & Roof) | Mon Jun 06 08:00:00 IDT 2016 | Tue Jun 14 18:00:00 IDT 2016 | Tue May 24 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 |  | COMPLETED
703 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 15 08:00:00 IDT 2016 | Wed Jun 15 18:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 |  | COMPLETED
704 | TT_TASK | Removal external formwork (Wall) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
705 | TT_TASK | Side walkway and cable bracket (102m3) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 |  | COMPLETED
706 | TT_TASK | Access opening to DC (DC access period) | Sat Jun 18 08:00:00 IDT 2016 | Thu Jul 14 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
707 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Fri Jul 15 08:00:00 IDT 2016 | Wed Aug 17 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
709 | TT_TASK | Backfilling between tunnels (2000m3) | Thu Sep 01 08:00:00 IDT 2016 | Sat Sep 17 18:00:00 IDT 2016 | Tue Sep 13 08:00:00 IDT 2016 | Fri Sep 30 18:00:00 IDT 2016 |  | COMPLETED
710 | TT_TASK | Remove Strut S2 | Mon Oct 03 08:00:00 IDT 2016 | Wed Oct 05 18:00:00 IDT 2016 | Mon Oct 03 08:00:00 IDT 2016 | Tue Oct 11 18:00:00 IDT 2016 |  | COMPLETED
711 | TT_TASK | Backfilling up top S1 Soffit | Thu Oct 06 08:00:00 IDT 2016 | Fri Oct 21 18:00:00 IDT 2016 | Fri Oct 28 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
712 | TT_TASK | Remove Strut S1 | Sat Oct 22 08:00:00 IDT 2016 | Mon Oct 24 18:00:00 IDT 2016 | Tue Oct 11 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
713 | TT_TASK | Backfilling up top S0 Soffit | Mon Nov 07 08:00:00 IST 2016 | Sat Nov 12 18:00:00 IST 2016 | Tue Nov 01 08:00:00 IST 2016 | Sat Nov 05 18:00:00 IST 2016 |  | COMPLETED
714 | TT_TASK | Remove Strut S0 | Mon Nov 14 08:00:00 IST 2016 | Tue Nov 15 18:00:00 IST 2016 | Mon Nov 07 08:00:00 IST 2016 | Tue Nov 08 18:00:00 IST 2016 |  | COMPLETED
715 | TT_TASK | Backfilling up to ground level | Wed Nov 16 08:00:00 IST 2016 | Fri Nov 18 18:00:00 IST 2016 | Wed Nov 09 08:00:00 IST 2016 | Fri Nov 11 18:00:00 IST 2016 |  | COMPLETED
719 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
720 | TT_TASK | Pre-drilling and guidewall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
721 | TT_TASK | D-wall construction (1451m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
722 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 |  | COMPLETED
724 | TT_TASK | Excavate from ground level to formation level -5.5mPD (4559m3) | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 |  | COMPLETED
725 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 |  | COMPLETED
726 | TT_TASK | Placing of blinding layer (South Bound) | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 |  | COMPLETED
727 | TT_TASK | Placing of blinding layer (North Bound) | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
729 | TT_TASK | Construction of Bay 2 to Bay 7a (3565m3) | Mon Jun 04 08:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 | Mon Jun 04 18:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 |  | COMPLETED
730 | TT_TASK | Side walkway and cable bracket (Southbound) | Fri Oct 02 08:00:00 IDT 2015 | Fri Nov 06 18:00:00 IST 2015 | Fri Oct 02 08:00:00 IDT 2015 | Sat Oct 31 18:00:00 IST 2015 |  | COMPLETED
731 | TT_TASK | Side walkway and cable bracket (Northbound) | Tue May 03 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 |  | COMPLETED
733 | TT_TASK | Backfilling (1344m3) | Wed Nov 07 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 | Wed Nov 07 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
736 | TT_TASK | Scheme Design, Mobilization, Site set up & Material delivery and Instrumentations | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
737 | TT_TASK | Downstream pipe pile wall construction (45 nos.) and grout curtain (45 nos.) | Mon Nov 12 08:00:00 IST 2012 | Fri Jan 25 18:00:00 IST 2013 | Mon Nov 12 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
738 | TT_TASK | Curtain Grout for cut slope (120 nos.) | Fri Jul 26 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
739 | TT_TASK | Drilling for ground improvement only (if require) | Mon Dec 10 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
740 | TT_TASK | If settlement reach the AAA alarm & action level TAM grouting will apply during excavation | Thu Apr 11 08:00:00 IDT 2013 | Thu May 16 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
741 | TT_TASK | Erection of temporary working platform for Up stream and Installation of Instrumentation System | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
742 | TT_TASK | Upstream pipe pile wall construction adjacent to WTSSTR, (17nos.) | Thu Dec 27 08:00:00 IST 2012 | Mon Jan 28 18:00:00 IST 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
743 | TT_TASK | Upstream pipe pile wall construction at Kam Tin River, 15m depth, 42nos. 1drill rig) | Tue Jan 29 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
744 | TT_TASK | Excavation and soil nail installation | Tue Apr 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
745 | TT_TASK | Excavation for rock and blinding layer | Sat Aug 24 08:00:00 IDT 2013 | Sat Sep 28 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
750 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
751 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
752 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
753 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
754 | TT_TASK | Concreting (164m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
755 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
756 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
757 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
758 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
759 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
760 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
761 | TT_TASK | Concreting (242m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
762 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
763 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
764 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
765 | TT_TASK | Removal internal falsework and formwork for roof | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
766 | TT_TASK | Side walkway and cable bracket (19m3) | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
770 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
771 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
772 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
773 | TT_TASK | Erect internal kicker formwork | Thu Nov 28 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 09 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
774 | TT_TASK | Concreting (121m3) | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
775 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
776 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
777 | TT_TASK | Removal of formwork | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
778 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
779 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
780 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
781 | TT_TASK | Concreting (121m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
782 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
783 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
784 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
785 | TT_TASK | Removal internal falsework and formwork for roof | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
786 | TT_TASK | Side walkway and cable bracket (38m3) | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
788 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
789 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
790 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
791 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
792 | TT_TASK | Concreting (240m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
793 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
794 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
795 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
796 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
797 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
798 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
799 | TT_TASK | Concreting (240m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
800 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
801 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
802 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
803 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
804 | TT_TASK | Side walkway and cable bracket | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
806 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
807 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
808 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
809 | TT_TASK | Concreting (222m3) | Wed Nov 06 08:00:00 IST 2013 | Wed Nov 06 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
810 | TT_TASK | Curing | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
811 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
812 | TT_TASK | Removal of formwork | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
815 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
816 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
817 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
818 | TT_TASK | Erect internal kicker formwork | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
819 | TT_TASK | Concreting (111m3) | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
820 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
821 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
822 | TT_TASK | Removal of formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
823 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
824 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
825 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
826 | TT_TASK | Concreting (220m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
827 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
828 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
829 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
830 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
831 | TT_TASK | Side walkway and cable bracket (38m3) | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 |  | COMPLETED
833 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
834 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
835 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
836 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
837 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
838 | TT_TASK | Curing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
839 | TT_TASK | Preparation of construction joint for base slab | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
840 | TT_TASK | Removal of formwork | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
841 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
842 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
843 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
844 | TT_TASK | Concreting (327m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
845 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
846 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
847 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
848 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
849 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
851 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 20 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
852 | TT_TASK | Rebar fixing | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
853 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 08:00:00 IDT 2013 |  | COMPLETED
854 | TT_TASK | Concreting (225m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
855 | TT_TASK | Curing | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
856 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
857 | TT_TASK | Removal of formwork | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
860 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 27 08:00:00 IST 2013 | Wed Nov 27 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
861 | TT_TASK | Erect external formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
862 | TT_TASK | Rebar fixing | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
863 | TT_TASK | Erect internal kicker formwork | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
864 | TT_TASK | Concreting (222m3) | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
865 | TT_TASK | Curing | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Mon Oct 28 18:00:00 IST 2013 |  | COMPLETED
866 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
867 | TT_TASK | Removal of formwork | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
868 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
869 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
870 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
871 | TT_TASK | Concreting (222m3) | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 |  | COMPLETED
872 | TT_TASK | Curing | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 07 18:00:00 IST 2014 |  | COMPLETED
873 | TT_TASK | Preparation of construction joint for wall and roof | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
874 | TT_TASK | Removal external and internal formwork for wall | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
875 | TT_TASK | Removal internal falsework and formwork for roof | Mon Feb 10 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
876 | TT_TASK | Side walkway and cable bracket (38m3) | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 |  | COMPLETED
878 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
879 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
880 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
881 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
882 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
883 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
884 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
885 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
886 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
887 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
888 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
889 | TT_TASK | Concreting (222m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
890 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
892 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
893 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
894 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
896 | TT_TASK | Placing of waterproof member T-lock & testing | Mon Nov 18 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
897 | TT_TASK | Rebar fixing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Wed Oct 23 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
898 | TT_TASK | Erect external formwork | Fri Nov 22 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
899 | TT_TASK | Concreting (222m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
900 | TT_TASK | Curing | Tue Nov 26 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
901 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
902 | TT_TASK | Removal of formwork | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
905 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
906 | TT_TASK | Erect external formwork | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
907 | TT_TASK | Rebar fixing | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
908 | TT_TASK | Erect internal kicker formwork | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
909 | TT_TASK | Concreting (330m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
910 | TT_TASK | Curing | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
911 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
912 | TT_TASK | Removal of formwork | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
913 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
914 | TT_TASK | Rebar fixing | Wed Nov 20 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
915 | TT_TASK | Erect external formwork | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
916 | TT_TASK | Concreting (330m3) | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
917 | TT_TASK | Curing | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
918 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
919 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
920 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
921 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
923 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
924 | TT_TASK | Erect external formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
925 | TT_TASK | Rebar fixing | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
926 | TT_TASK | Erect internal kicker formwork | Wed Dec 04 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
927 | TT_TASK | Concreting (240m3) | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
928 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
929 | TT_TASK | Preparation of construction joint for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
930 | TT_TASK | Removal of formwork | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
931 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
932 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
933 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
934 | TT_TASK | Concreting (240m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
935 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
936 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
937 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
938 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
939 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
941 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
942 | TT_TASK | Rebar fixing | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
943 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
944 | TT_TASK | Concreting (240m3) | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
945 | TT_TASK | Curing | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
946 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
947 | TT_TASK | Removal of formwork | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
950 | TT_TASK | Placing of waterproof member T-lock & testing | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
951 | TT_TASK | Erect external formwork | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
952 | TT_TASK | Rebar fixing | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
953 | TT_TASK | Erect internal kicker formwork | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
954 | TT_TASK | Concreting (200m3) | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
955 | TT_TASK | Curing | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
956 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
957 | TT_TASK | Removal of formwork | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
958 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 29 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
959 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
960 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
961 | TT_TASK | Concreting (200m3) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
962 | TT_TASK | Curing | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
963 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
964 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 13 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
965 | TT_TASK | Removal internal falsework and formwork for roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
966 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 |  | COMPLETED
968 | TT_TASK | Placing of waterproof member T-lock & testing | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
969 | TT_TASK | Erect external formwork | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
970 | TT_TASK | Rebar fixing | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
971 | TT_TASK | Erect internal kicker formwork | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
972 | TT_TASK | Concreting (220m3) | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
973 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
974 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
975 | TT_TASK | Removal of formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
976 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
977 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
978 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
979 | TT_TASK | Concreting (220m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
980 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
981 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
982 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
983 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
984 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
986 | TT_TASK | Placing of waterproof member T-lock & testing | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
987 | TT_TASK | Rebar fixing | Mon Nov 25 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
988 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
989 | TT_TASK | Concreting (222m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
990 | TT_TASK | Curing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
991 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
992 | TT_TASK | Removal of formwork | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
994 | TT_TASK | Removal of Temporary Nullah | Sat Mar 01 08:00:00 IST 2014 | Sat Jun 21 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
995 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (5218m3) | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 |  | COMPLETED
996 | TT_TASK | Reinstate the permenant Retaining wall of Nullah | Sat Mar 01 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Tue Mar 04 08:00:00 IST 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
997 | TT_TASK | Reinstate Nullah Base of original route | Tue Feb 25 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Tue Feb 25 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
998 | TT_TASK | Reinstate Nullah to original route | Sat Mar 29 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Sat Mar 29 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
999 | TT_TASK | Construction & connect East Box Culvert from Box 6B to KTR | Mon Apr 14 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Mon Feb 10 08:00:00 IST 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
1000 | TT_TASK | Reinstatement of Wang Toi Shan Shan Tsuen Road | Tue Dec 01 08:00:00 IST 2015 | Wed Jul 13 18:00:00 IDT 2016 | Tue Dec 01 08:00:00 IST 2015 | Mon Jul 18 18:00:00 IDT 2016 |  | COMPLETED
1003 | TT_TASK | Pre-drilling at Works Area 4.4 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
1004 | TT_TASK | Site Setup and guide wall | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1005 | TT_TASK | D-wall construction (3104m3) | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 |  | COMPLETED
1006 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
1008 | TT_TASK | Excavate up to +8.0mPD (775m3) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1009 | TT_TASK | Install Strut S1 +8.5mPD | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 |  | COMPLETED
1010 | TT_TASK | Excavate up to +4.5mPD (2713m3) | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 |  | COMPLETED
1011 | TT_TASK | Install Strut S2 +5.0mPD | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
1012 | TT_TASK | Excavate up to +0.5mPD (3100m3) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 |  | COMPLETED
1013 | TT_TASK | Install Strut S3 +1.0mPD | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1014 | TT_TASK | Excavate up to -3.0mPD (2713m3) | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1015 | TT_TASK | Install Strut S4 -2.5mPD | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 |  | COMPLETED
1016 | TT_TASK | Excavate up to -5.5mPD (4952m3) | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1017 | TT_TASK | Placing of blinding layer | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1021 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1022 | TT_TASK | Erect external formwork for base slab | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1023 | TT_TASK | Rebar fixing for base slab | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1024 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 26 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1025 | TT_TASK | Concreting for base slab (350m3) | Thu Jun 27 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1026 | TT_TASK | Curing for base slab | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1027 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1028 | TT_TASK | Removal of formwork for base slab | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1029 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1030 | TT_TASK | Removal strut S4 and S3 | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1032 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1033 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1034 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1035 | TT_TASK | Concreting for wall and roof (489m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1036 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1037 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1038 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1039 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1040 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1043 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1044 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1045 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1046 | TT_TASK | Curing for wall and roof | Sat Jun 22 08:00:00 IDT 2013 | Mon Jul 01 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1047 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1048 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1050 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Tue Dec 17 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1053 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1054 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1055 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1056 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1057 | TT_TASK | Concreting for base slab (350m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1058 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1059 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1060 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1061 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1062 | TT_TASK | Removal strut S4 and S3 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1064 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1065 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1066 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1067 | TT_TASK | Concreting for wall and roof (489m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1068 | TT_TASK | Curing for wall and roof | Wed Jun 12 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1069 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1070 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 14 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1071 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1072 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Feb 13 08:00:00 IST 2014 | Tue Feb 18 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1074 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1075 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1076 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1077 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1078 | TT_TASK | Curing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1079 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1080 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1081 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1082 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 16 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1084 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (2343m3) | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1085 | TT_TASK | Placing 0.5m thk concrete lateral support (+3.96mPD) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1086 | TT_TASK | Removal strut S2 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 23 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1088 | TT_TASK | Construction of Temporary Culvert (open channel) | Tue Jun 25 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1089 | TT_TASK | Temporary box culvert (At Box 6B Area) Saw Cut D-wall | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 |  | COMPLETED
1090 | TT_TASK | Erect 3m high block wall | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 |  | COMPLETED
1091 | TT_TASK | Connection to East Box Culvert (823B portion) | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 |  | COMPLETED
1092 | TT_TASK | Blinding | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
1093 | TT_TASK | Temporary box culvert (Outside Box 6B Area) Sheet piling | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 |  | COMPLETED
1094 | TT_TASK | ELS Works | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
1095 | TT_TASK | Blinding | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
1096 | TT_TASK | Removal of Temporary Culvert and Reinstatement | Fri May 16 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
1098 | TT_TASK | Reinstatement of TOA's | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 |  |  | IN_PROGRESS
1099 | TT_TASK | Hydroseeding works | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 | Wed Nov 30 18:00:00 IST 2016 |  | COMPLETED
1100 | TT_TASK | Tree Planting works | Thu Sep 01 08:00:00 IDT 2016 | Sat Dec 03 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
1101 | TT_TASK | Woodland Shrub Mix | Thu Sep 01 08:00:00 IDT 2016 | Fri Nov 18 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  | 200.0 | IN_PROGRESS
1104 | TT_TASK | Kam Tin River Diversion (Stage 1-3) | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1106 | TT_TASK | Concrete fill up to +8.0mPD near side A mass concrete wall | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 |  | COMPLETED
1107 | TT_TASK | Construction of mass concrete wall to +8.0mPD at side A (4 bay CH A80~A120) | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1108 | TT_TASK | Construction of base slab lining and low flow channel (4 bay A9~A10, B8~B9; LFC CH 80~110) | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1109 | TT_TASK | Construction of mass concrete wall to +8.0mPD of side B (3 bay CH B60~B90) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1110 | TT_TASK | Construction of T-shaped retaining wall (1 Bay CH B50~B60) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1111 | TT_TASK | Soil backfill at side A from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1112 | TT_TASK | Concrete backfill at side B from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1113 | TT_TASK | Removal strut at +8.5mPD near side A | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1114 | TT_TASK | Concrete fill up to +11.0mPD near side A mass concrete wall | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1115 | TT_TASK | Placing concrete block at side A from +8.0mPD to +11.0mpd at side A (4 bay CH A80~A120) | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1116 | TT_TASK | Soil backfill at side A from +8.0mPD to +11.0mPD | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1117 | TT_TASK | Removal strut at +8.5mPD near side B | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1118 | TT_TASK | Placing concrete block at side B from +8.0mPD to +11.0mPD (4 bay CH B60~B90) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1119 | TT_TASK | Concrete backfill at side B from +8.0mPD to +11.0mPD | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1121 | TT_TASK | Placing temporary concrete block to Up stream at CH30 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 |  | COMPLETED
1122 | TT_TASK | Placing temporary concrete block to Up stream at CH160 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1123 | TT_TASK | Excavation from GL to FL +5.0mPD Up stream (Low flow channel CH 30~60) | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1124 | TT_TASK | Excavation from GL to FL +5.0mPD Down stream (Low flow channel CH 130~160) | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1125 | TT_TASK | Construction of T-shaped retaining wall at Up stream of side B (2 Bay CH B30~B50) | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1126 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (3 bay CH B90~B120) | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1127 | TT_TASK | Construction of Up stream base slab lining and low flow channel (6 Bay A1~A4, B3~B4; Low flow channel CH 30~50) | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1128 | TT_TASK | Construction of Down stream base slab lining and low flow channel (5 Bay A14~A16, B14~B15; LFC CH 140~170) | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1129 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Up stream and saw cut D-wall | Fri Jun 14 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1130 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Down stream and saw cut D-wall | Wed Jun 19 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1131 | TT_TASK | Construction of remaining Up stream base slab lining and low flow channel (7 bay A5~A8, B5~B7; LFC CH 50~80) | Thu Jun 27 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1132 | TT_TASK | Construction of remaining Down stream base slab lining and low flow channel (7 bay A11~A13, B10~B13; LFC CH 110~140) | Wed Jul 03 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1134 | TT_TASK | Relocation of temporary concrete block at Up stream for construction of mass concrete wall at side B | Sat Jul 20 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1135 | TT_TASK | Relocation of temporary concrete block at Down stream for construction of mass concrete wall at side B | Tue Jul 23 08:00:00 IDT 2013 | Wed Jul 24 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1136 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Up stream of side B (3 bay CH B0~B30) | Tue Jul 23 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1137 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (4 bay CH B0~B30) | Thu Jul 25 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1141 | TT_TASK | Application of power supply, environmental permits and construction substation | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1142 | TT_TASK | Procurement and Confirmation of the order of 1st tunnel boring machine | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 |  | COMPLETED
1143 | TT_TASK | Prepare on-demand bond or bank guarantee for the procurement of TBM and submit to Engineer for approval | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 |  | COMPLETED
1144 | TT_TASK | TBM design and submission for approval | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
1145 | TT_TASK | TBM materials order and delivery to factory | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 |  | COMPLETED
1146 | TT_TASK | TBM equipments order and delivery to factory | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 |  | COMPLETED
1147 | TT_TASK | TBM Fabrication | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
1148 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 |  | COMPLETED
1149 | TT_TASK | TBM test Run | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 |  | COMPLETED
1150 | TT_TASK | TBM disassembly and packing for shipping to HK | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 |  | COMPLETED
1151 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
1152 | TT_TASK | Ground treatment for TBM lanching shaft | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 |  | COMPLETED
1153 | TT_TASK | Ground treatment for Cross Passage Tunnel | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1154 | TT_TASK | Box7A Setup TBM facilities, install noise enclosure and CNP application | Fri Jun 01 08:00:00 IDT 2012 | Sat Jan 26 18:00:00 IST 2013 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1155 | TT_TASK | Notice to Contract 824 the anticipated dates of break out TBM Shaft | Sat Jun 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1156 | TT_TASK | Fabrication of tunnel segment mould | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
1157 | TT_TASK | Fabrication 50% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1158 | TT_TASK | Fabrication 100% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
1159 | TT_TASK | Fabrication 30% of North Tunnel North Bound (Uptrack) Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1160 | TT_TASK | Fabrication 60% of North Tunnel North Bound (Uptrack) Precast Lining | Thu Oct 18 08:00:00 IST 2012 | Thu Feb 21 18:00:00 IST 2013 | Thu Oct 18 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1161 | TT_TASK | Fabrication 100% of North Tunnel North Bound (Uptrack) Precast Lining | Mon Aug 19 08:00:00 IDT 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Dec 03 08:00:00 IST 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1163 | TT_TASK | Assemble, T&C of TBM | Fri Jun 01 08:00:00 IDT 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Oct 16 00:00:00 IST 2012 |  | COMPLETED
1164 | TT_TASK | TBM drive & lining installation CH123+369 to CH123+283 Initial Drive (86m) | Sat Nov 03 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 | Wed Oct 17 00:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1165 | TT_TASK | Change Plant (Back-up cars) | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1166 | TT_TASK | TBM drive & lining installation CH123+283 to CH123+183 | Thu Jun 27 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1167 | TT_TASK | TBM drive & lining installation CH123+183 to CH123+083 | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1168 | TT_TASK | TBM drive & lining installation CH123+083 to CH122+983 | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1169 | TT_TASK | TBM drive & lining installation CH122+983 to CH122+883 | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1170 | TT_TASK | TBM drive & lining installation CH122+883 to CH122+783 | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Jun 13 08:00:00 IDT 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
1171 | TT_TASK | TBM drive & lining installation CH122+783 to CH122+683 | Sat Nov 02 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1172 | TT_TASK | TBM drive & lining installation CH122+683 to CH122+583 | Tue Dec 03 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Wed Feb 26 18:00:00 IST 2014 |  | COMPLETED
1173 | TT_TASK | TBM drive & lining installation CH122+583 to CH122+491 | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Feb 27 08:00:00 IST 2014 | Sat Aug 16 00:00:00 IDT 2014 |  | COMPLETED
1174 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1175 | TT_TASK | Dis-assemble TBM | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
1176 | TT_TASK | Invert slab, side walkway | Sat Oct 04 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 | Mon Sep 15 08:00:00 IDT 2014 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1177 | TT_TASK | Installation of cable bracket | Tue Dec 30 08:00:00 IST 2014 | Tue Jan 13 18:00:00 IST 2015 | Fri Sep 12 08:00:00 IDT 2014 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
1178 | TT_TASK | Provision of assess open for DC and modify of strut S1 and S2 at north bound | Tue Nov 04 11:12:00 IST 2014 | Thu Dec 04 11:12:00 IST 2014 | Wed Oct 01 08:00:00 IDT 2014 | Sat Oct 18 18:00:00 IDT 2014 |  | COMPLETED
1180 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Oct 06 13:00:00 IDT 2014 | Mon Oct 20 12:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
1181 | TT_TASK | Assemble, T&C of TBM | Mon Nov 03 08:00:00 IST 2014 | Fri Jan 02 18:00:00 IST 2015 | Sat Oct 04 08:00:00 IDT 2014 | Fri Nov 28 18:00:00 IST 2014 |  | COMPLETED
1182 | TT_TASK | Setup back-up plant for final drive | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
1183 | TT_TASK | Reinstate of noise enclosure | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Sat Nov 29 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1184 | TT_TASK | TBM drive & lining installation CH123+384 to CH123+284 (Initial Drive) | Sat Dec 06 08:00:00 IST 2014 | Thu Jan 22 18:00:00 IST 2015 | Tue Dec 02 00:00:00 IST 2014 | Tue Jan 20 18:00:00 IST 2015 |  | COMPLETED
1185 | TT_TASK | TBM drive & lining installation CH123+184 to CH123+084 | Wed Jan 21 08:00:00 IST 2015 | Wed Jan 28 18:00:00 IST 2015 | Wed Jan 21 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 |  | COMPLETED
1186 | TT_TASK | TBM drive & lining installation CH123+084 to CH122+984 | Wed Feb 04 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 | Thu Feb 12 08:00:00 IST 2015 | Thu Feb 26 18:00:00 IST 2015 |  | COMPLETED
1187 | TT_TASK | TBM drive & lining installation CH122+984 to CH122+884 | Thu Feb 12 08:00:00 IST 2015 | Tue Feb 24 18:00:00 IST 2015 | Fri Feb 27 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1188 | TT_TASK | TBM drive & lining installation CH122+884 to CH122+784 | Tue Mar 10 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Wed May 27 18:00:00 IDT 2015 |  | COMPLETED
1189 | TT_TASK | TBM drive & lining installation CH122+784 to CH122+684 | Wed May 06 08:00:00 IDT 2015 | Thu May 14 18:00:00 IDT 2015 | Thu May 28 08:00:00 IDT 2015 | Sat Jul 11 18:00:00 IDT 2015 |  | COMPLETED
1190 | TT_TASK | TBM drive & lining installation CH122+684 to CH122+584 | Fri Jul 03 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
1191 | TT_TASK | TBM drive & lining installation CH122+584 to CH122+506 | Tue Nov 03 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 |  | COMPLETED
1192 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 |  | COMPLETED
1193 | TT_TASK | Dis-assemble TBM | Wed Dec 16 08:00:00 IST 2015 | Fri Jan 22 18:00:00 IST 2016 | Sun Dec 13 08:00:00 IST 2015 | Sun Mar 13 18:00:00 IST 2016 |  | COMPLETED
1194 | TT_TASK | Invert slab, side walkway | Fri Apr 01 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 | Mon Mar 14 08:00:00 IST 2016 | Tue May 24 18:00:00 IDT 2016 |  | COMPLETED
1195 | TT_TASK | Installation of cable bracket | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Mar 15 18:00:00 IST 2016 |  | COMPLETED
1196 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Mon Feb 01 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 22 18:00:00 IST 2016 |  | COMPLETED
1199 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 1 (From Downtrack to Centre of CP) | Thu Apr 10 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Sat Jun 28 18:00:00 IDT 2014 |  | COMPLETED
1200 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Sun Nov 09 18:00:00 IST 2014 |  | COMPLETED
1201 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1202 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 18:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1203 | TT_TASK | Excavation 0-4mts with Shotcrete | Mon Feb 02 08:00:00 IST 2015 | Tue Feb 17 18:00:00 IST 2015 | Mon Feb 23 08:00:00 IST 2015 | Mon Mar 30 18:00:00 IDT 2015 |  | COMPLETED
1204 | TT_TASK | Invert Concrete | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1205 | TT_TASK | Wall and Roof concrete | Thu Apr 16 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 |  | COMPLETED
1206 | TT_TASK | Dismantle Temporary frame | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 |  | COMPLETED
1207 | TT_TASK | Install Door to Cross Passage (By contract 827) | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 |  | COMPLETED
1208 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 2 (From Centre of CP to Uptrack) | Sat Oct 17 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Sep 07 08:00:00 IDT 2015 | Tue Dec 01 18:00:00 IST 2015 |  | COMPLETED
1209 | TT_TASK | Probe/Grout | Thu Jun 25 08:00:00 IDT 2015 | Mon Jul 06 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Fri Apr 10 18:00:00 IDT 2015 |  | COMPLETED
1210 | TT_TASK | Coring of Segment | Tue Jul 07 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Sat Apr 11 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1211 | TT_TASK | Removal of segment | Sat Jul 11 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
1212 | TT_TASK | Excavation 0-4mts with Shotcrete | Wed Jul 15 08:00:00 IDT 2015 | Sat Jul 25 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1213 | TT_TASK | Invert Concrete | Sat Jul 18 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 | Thu May 07 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1214 | TT_TASK | Wall and Roof concrete | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1215 | TT_TASK | Dismantle Temporary frame | Tue Jan 19 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 04 18:00:00 IST 2016 |  | COMPLETED
1216 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Feb 22 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Fri Feb 05 08:00:00 IST 2016 | Sat Feb 06 18:00:00 IST 2016 |  | COMPLETED
1218 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 1 (From Downtrack to Centre of CP) | Tue Mar 11 08:00:00 IST 2014 | Wed Mar 26 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1219 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Wed Nov 12 18:00:00 IST 2014 |  | COMPLETED
1220 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Thu Nov 13 08:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1221 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Tue Nov 18 08:00:00 IST 2014 | Thu Nov 20 18:00:00 IST 2014 |  | COMPLETED
1222 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Sat Nov 22 08:00:00 IST 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1223 | TT_TASK | Invert Concrete | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
1224 | TT_TASK | Wall and Roof concrete | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1225 | TT_TASK | Dismantle Temporary frame | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1226 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1227 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 2 (From Centre of CP to Uptrack) | Thu May 21 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Mar 09 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1228 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Mon May 04 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1229 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
1230 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1231 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 22 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
1232 | TT_TASK | Invert Concrete | Sat Aug 08 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Wed Jul 08 18:00:00 IDT 2015 |  | COMPLETED
1233 | TT_TASK | Wall and Roof concrete | Tue Aug 25 08:00:00 IDT 2015 | Mon Sep 07 18:00:00 IDT 2015 | Thu Jul 09 08:00:00 IDT 2015 | Sat Aug 15 18:00:00 IDT 2015 |  | COMPLETED
1234 | TT_TASK | Dismantle Temporary frame | Tue Sep 22 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 | Mon Aug 17 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 |  | COMPLETED
1235 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1237 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 1 (From Downtrack to Centre of CP) | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Sat May 24 18:00:00 IDT 2014 |  | COMPLETED
1238 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
1239 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1240 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 |  | COMPLETED
1241 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Mon Nov 17 08:00:00 IST 2014 | Sat Nov 29 18:00:00 IST 2014 |  | COMPLETED
1242 | TT_TASK | Invert Concrete | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 |  | COMPLETED
1243 | TT_TASK | Wall and Roof concrete | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 |  | COMPLETED
1244 | TT_TASK | Dismantle Temporary frame | Tue Dec 30 08:00:00 IST 2014 | Wed Jan 07 18:00:00 IST 2015 | Tue Dec 30 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1245 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1246 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 2 (From Centre of CP to Uptrack) | Fri May 08 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 |  | COMPLETED
1247 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
1248 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
1249 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Thu May 07 18:00:00 IDT 2015 |  | COMPLETED
1250 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
1251 | TT_TASK | Invert Concrete | Wed Aug 05 08:00:00 IDT 2015 | Fri Aug 14 18:00:00 IDT 2015 | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
1252 | TT_TASK | Wall and Roof concrete | Tue Sep 15 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Wed Aug 26 18:00:00 IDT 2015 |  | COMPLETED
1253 | TT_TASK | Dismantle Temporary frame | Sat Oct 17 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Oct 08 18:00:00 IDT 2015 |  | COMPLETED
1254 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1258 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 |  | COMPLETED
1259 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1260 | TT_TASK | D-wall construction (1192m3) | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 |  | COMPLETED
1261 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1262 | TT_TASK | Construct capping beam, cobble, etc. (including bay 6 and 5) | Sat Oct 27 08:00:00 IST 2012 | Sat Feb 16 18:00:00 IST 2013 | Sat Oct 27 08:00:00 IST 2012 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1264 | TT_TASK | Excavate up to +22.0mPD (1860m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1265 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 |  | COMPLETED
1266 | TT_TASK | Excavate up to +16.5mPD (3410m3) | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 |  | COMPLETED
1267 | TT_TASK | Install Strut S2 +17.0mPD | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 |  | COMPLETED
1268 | TT_TASK | Excavate up to +11.0mPD (3410m3) | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 |  | COMPLETED
1269 | TT_TASK | Install Strut S3 +11.5mPD | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 |  | COMPLETED
1270 | TT_TASK | Excavate up to +7.0mPD (2480m3) | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 |  | COMPLETED
1271 | TT_TASK | Install Strut S4 +7.5mPD | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1272 | TT_TASK | Excavate up to +3.5mPD (2170m3) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 |  | COMPLETED
1273 | TT_TASK | Install Strut S5 +4.0mPD | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1274 | TT_TASK | Excavate up to formation (2294m3) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1275 | TT_TASK | Construct temp. 500mm thick plain concrete base slab | Thu Oct 18 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 |  | COMPLETED
1276 | TT_TASK | Removal of South Bound strut to +9.50mPD | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1277 | TT_TASK | Removal of North Bound strut to +9.50mPD | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 |  | COMPLETED
1278 | TT_TASK | Construct temp. 500mm thick TBM concrete base slab | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1279 | TT_TASK | Construction entrance seal for TBM at South Bound | Mon Nov 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1280 | TT_TASK | Construction entrance seal for TBM at North Bound | Sat Jul 20 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1281 | TT_TASK | Saw cut South Bound diaphragm wall | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1282 | TT_TASK | Saw cut North Bound diaphragm wall | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1286 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 05 18:00:00 IDT 2014 | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 |  | COMPLETED
1287 | TT_TASK | Erect external formwork (Base Slab) | Sat Sep 06 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 21 18:00:00 IDT 2014 |  | COMPLETED
1288 | TT_TASK | Rebar fixing (Base Slab) | Wed Sep 10 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Tue Jul 22 08:00:00 IDT 2014 | Sat Jul 26 18:00:00 IDT 2014 |  | COMPLETED
1289 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Sep 15 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Sun Jul 27 08:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1290 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Thu Aug 14 18:00:00 IDT 2014 |  | COMPLETED
1291 | TT_TASK | Concreting (Base Slab) (225m3) | Sat Aug 09 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Fri Aug 15 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
1292 | TT_TASK | Curing (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
1293 | TT_TASK | Removal of formwork (Base Slab) | Tue Aug 12 08:00:00 IDT 2014 | Tue Aug 12 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1294 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed Aug 13 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Mon Sep 15 18:00:00 IDT 2014 |  | COMPLETED
1295 | TT_TASK | Rebar fixing (Wall & Roof) | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 |  | COMPLETED
1296 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 |  | COMPLETED
1297 | TT_TASK | Clearing and inspection (Wall & Roof) | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
1298 | TT_TASK | Concreting (Wall & Roof) (450m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
1299 | TT_TASK | Curing (Wall & Roof) | Sat Oct 11 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
1300 | TT_TASK | Removal external formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1301 | TT_TASK | Removal internal falsework (Wall & Roof) | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 |  | COMPLETED
1302 | TT_TASK | Side walkway and cable bracket (102m3) | Sat Oct 18 08:00:00 IDT 2014 | Wed Oct 29 18:00:00 IST 2014 | Mon Sep 01 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1304 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Wed Nov 11 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Oct 19 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1305 | TT_TASK | Erect external formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 |  | COMPLETED
1306 | TT_TASK | Rebar fixing (Base Slab) | Mon Nov 16 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Tue Oct 27 08:00:00 IST 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1307 | TT_TASK | Erect internal kicker formwork (Base Slab) | Fri Nov 20 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Oct 31 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 |  | COMPLETED
1308 | TT_TASK | Clearing and inspection (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
1309 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1310 | TT_TASK | Curing (Base Slab) | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 |  | COMPLETED
1311 | TT_TASK | Removal of formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 |  | COMPLETED
1312 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
1313 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Dec 09 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
1314 | TT_TASK | Erect external formwork (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Thu Jan 07 18:00:00 IST 2016 |  | COMPLETED
1315 | TT_TASK | Clearing and inspection (Wall & Roof) | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Fri Jan 08 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
1316 | TT_TASK | Concreting (Wall & Roof) (450m3) | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
1317 | TT_TASK | Curing (Wall & Roof) | Tue Jan 12 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
1318 | TT_TASK | Removal external formwork (Wall ) | Thu Jan 14 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
1319 | TT_TASK | Removal internal falsework, formwork and reproping (Wall & Roof) | Thu Jan 28 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 |  | COMPLETED
1320 | TT_TASK | Side walkway and cable bracket (102m3) | Wed Dec 23 08:00:00 IST 2015 | Wed Jan 06 18:00:00 IST 2016 | Wed Nov 11 08:00:00 IST 2015 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
1322 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 |  | COMPLETED
1323 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 |  | COMPLETED
1324 | TT_TASK | Backfilling to 0.5m below S3 (+11.0mPD) (3486m3) | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 |  | COMPLETED
1325 | TT_TASK | Removal strut S3 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
1326 | TT_TASK | Backfilling to 0.5m below S2 (+16.5mPD) (3410m3) | Wed Mar 16 08:00:00 IST 2016 | Fri Apr 08 18:00:00 IDT 2016 | Wed Mar 16 08:00:00 IST 2016 | Tue Apr 12 18:00:00 IDT 2016 |  | COMPLETED
1327 | TT_TASK | Removal strut S2 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 |  | COMPLETED
1328 | TT_TASK | Backfilling to 0.5m below S1 (+22.0mPD) (3410m3) | Fri Apr 15 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 | Fri Apr 15 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
1329 | TT_TASK | Removal strut S1 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 |  | COMPLETED
1330 | TT_TASK | Backfilling to original ground level (approx. +25.0mPD) (1860m3) | Thu May 05 08:00:00 IDT 2016 | Tue May 17 18:00:00 IDT 2016 | Thu May 05 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
1333 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1334 | TT_TASK | D-wall construction (2844m3) | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1335 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1337 | TT_TASK | Excavate up to +22.0mPD (3720m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1338 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 |  | COMPLETED
1339 | TT_TASK | Excavate up to +16.5mPD (4880m3) | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 |  | COMPLETED
1340 | TT_TASK | Install Strut S2 +17.0mPD | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 |  | COMPLETED
1341 | TT_TASK | Excavate up to +11.0mPD (6820m3) | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
1342 | TT_TASK | Install Strut S3 +11.5mPD | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 |  | COMPLETED
1343 | TT_TASK | Excavate up to +7.0mPD (4960m3) | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 |  | COMPLETED
1344 | TT_TASK | Install Strut S4 +7.5mPD | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1345 | TT_TASK | Excavate up to +3.5mPD (4340m3) | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1346 | TT_TASK | Install Strut S5 +4.0mPD | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 |  | COMPLETED
1347 | TT_TASK | Excavate up to formation (4960m3) | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 |  | COMPLETED
1348 | TT_TASK | Construct temp. 500mm thick plain concrete base slab at Bay 5 & 6 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1349 | TT_TASK | Excavation to formation and place blinding Bay 4a | Thu Oct 18 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1350 | TT_TASK | Excavation to formation and place blinding Bay 4b | Fri Jun 21 08:00:00 IDT 2013 | Fri Jul 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1351 | TT_TASK | Excavation to formation and place blinding Bay3 | Sat Jul 13 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1352 | TT_TASK | Excavation to formation and place blinding Bay2 to Bay1 | Wed Jul 24 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1356 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 |  | COMPLETED
1357 | TT_TASK | Erect external formwork for base slab | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 |  | COMPLETED
1358 | TT_TASK | Rebar fixing for base slab | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1359 | TT_TASK | Erect internal kicker formwork for base slab | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1360 | TT_TASK | Concreting for base slab (363m3) | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1361 | TT_TASK | Curing for base slab | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1362 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1363 | TT_TASK | Removal of formwork for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1364 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1365 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 27 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1366 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1367 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1368 | TT_TASK | Curing for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1369 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1370 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 10 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1371 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 19 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jan 24 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1372 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 08 08:00:00 IST 2015 | Tue Jan 13 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1374 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 |  | COMPLETED
1375 | TT_TASK | Erect external formwork for base slab | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1376 | TT_TASK | Rebar fixing for base slab | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1377 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 |  | COMPLETED
1378 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1379 | TT_TASK | Curing for base slab | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1380 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1381 | TT_TASK | Removal of formwork for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1382 | TT_TASK | Rebar fixing for central slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1383 | TT_TASK | Erect external formwork for central slab | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1384 | TT_TASK | Concreting for central slab (450m3) | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1385 | TT_TASK | Curing for central slab | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1386 | TT_TASK | Preparation of construction joint for central slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1387 | TT_TASK | Removal of formwork for central slab | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1388 | TT_TASK | Removal strut S5 and S4 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1389 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1390 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1391 | TT_TASK | Erect external formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1392 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1393 | TT_TASK | Curing for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1394 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1395 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 08 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1396 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1397 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Nov 19 08:00:00 IST 2015 | Tue Nov 24 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 |  | COMPLETED
1400 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1401 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1402 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1403 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1404 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1405 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1406 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1407 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1408 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1409 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1410 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 10 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1411 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1412 | TT_TASK | Curing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1413 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1414 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1415 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1416 | TT_TASK | Side walkway and cable bracket | Fri Jan 02 08:00:00 IST 2015 | Wed Jan 07 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1418 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1419 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1420 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1421 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1422 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1423 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1424 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1425 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1426 | TT_TASK | Rebar fixing for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1427 | TT_TASK | Erect external formwork for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1428 | TT_TASK | Concreting for central slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1429 | TT_TASK | Curing for central slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1430 | TT_TASK | Preparation of construction joint for central slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1431 | TT_TASK | Removal of formwork for central slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 21 18:00:00 IST 2012 |  | COMPLETED
1432 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1433 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1434 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1435 | TT_TASK | Erect external formwork for wall | Mon Jul 15 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1436 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1437 | TT_TASK | Curing for wall and roof | Sun Jul 21 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1438 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1439 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 22 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1440 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 31 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1441 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Sep 16 08:00:00 IDT 2015 | Mon Sep 21 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1443 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1444 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1445 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1446 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1447 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1448 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1449 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1450 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1451 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1452 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1453 | TT_TASK | Erect external formwork for wall | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1454 | TT_TASK | Concreting for wall and roof (444m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1455 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1456 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1457 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Sat Feb 09 18:00:00 IST 2013 |  | COMPLETED
1458 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Nov 09 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Tue Oct 06 08:00:00 IDT 2015 | Sat Oct 10 18:00:00 IDT 2015 |  | COMPLETED
1461 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1462 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1463 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1464 | TT_TASK | Erect internal kicker formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1465 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1466 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1467 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1468 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1469 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1470 | TT_TASK | Curing | Wed Jun 12 08:00:00 IDT 2013 | Wed Jun 12 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1471 | TT_TASK | Removal strut S5 and S4 | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1473 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1474 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1475 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1476 | TT_TASK | Concreting for wall and roof (450m3) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1477 | TT_TASK | Curing for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1478 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1479 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1480 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 29 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1481 | TT_TASK | Side walkway and cable bracket | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1483 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1484 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1485 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1486 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1487 | TT_TASK | Curing for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1488 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1489 | TT_TASK | Removal external wall formwork for wall | Wed Jun 26 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1490 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1491 | TT_TASK | Side walkway and cable bracket | Fri Sep 04 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
1494 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1495 | TT_TASK | Erect external formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1496 | TT_TASK | Rebar fixing for base slab | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1497 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1498 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 |  | COMPLETED
1499 | TT_TASK | Curing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1500 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1501 | TT_TASK | Removal of formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1502 | TT_TASK | Shear beam | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1503 | TT_TASK | Curing | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1504 | TT_TASK | Removal strut S5 and S4 | Wed Jun 19 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1506 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 24 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1507 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1508 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1509 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1510 | TT_TASK | Curing for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1511 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1512 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1513 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1514 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
1516 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1517 | TT_TASK | Rebar fixing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1518 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1519 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1520 | TT_TASK | Curing for wall and roof | Sun Jun 23 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1521 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1522 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 25 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1523 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 03 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1524 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Aug 29 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1527 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1528 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Sat Dec 22 18:00:00 IST 2012 |  | COMPLETED
1529 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1530 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1531 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1532 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1533 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1534 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Fri Jan 11 18:00:00 IST 2013 |  | COMPLETED
1535 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Jan 12 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1536 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1537 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1539 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1540 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1541 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1542 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1543 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1544 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1545 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1546 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1547 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 |  | COMPLETED
1549 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1550 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Mon Feb 25 18:00:00 IST 2013 |  | COMPLETED
1551 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1552 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1553 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1554 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1555 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1556 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1557 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Aug 24 08:00:00 IDT 2015 | Fri Aug 28 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1560 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1561 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1562 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1563 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1564 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1565 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1566 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1567 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1568 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1569 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1570 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1572 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1573 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1574 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1575 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1576 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1577 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1578 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1579 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1580 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
1582 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1583 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1584 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1585 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1586 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1587 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1588 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1589 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1590 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Aug 18 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1593 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1594 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1595 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1596 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1597 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1598 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1599 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1600 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1601 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1602 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1603 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1605 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 31 18:00:00 IDT 2013 |  | COMPLETED
1606 | TT_TASK | Rebar fixing for wall and roof | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 |  | COMPLETED
1607 | TT_TASK | Erect external formwork for wall and roof | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 | Fri Sep 06 08:00:00 IDT 2013 | Thu Sep 12 18:00:00 IDT 2013 |  | COMPLETED
1608 | TT_TASK | Concreting for wall and roof (450m3) | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 |  | COMPLETED
1609 | TT_TASK | Curing for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1610 | TT_TASK | Preparation of construction joint for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1611 | TT_TASK | Removal external and internal formwork for wall | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Wed Sep 25 18:00:00 IDT 2013 |  | COMPLETED
1612 | TT_TASK | Removal internal falsework and formwork for roof | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1613 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 08 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1615 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 20 18:00:00 IST 2013 |  | COMPLETED
1616 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1617 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1618 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1619 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1620 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1621 | TT_TASK | Removal external wall formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1622 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1623 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Aug 12 08:00:00 IDT 2015 | Mon Aug 17 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1626 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1627 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1628 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Feb 14 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1629 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1630 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Mon Feb 18 18:00:00 IST 2013 |  | COMPLETED
1631 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1632 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1633 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1634 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1635 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1636 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1638 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jul 12 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1639 | TT_TASK | Rebar fixing for wall and roof | Wed Jul 17 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1640 | TT_TASK | Erect external formwork for wall and roof | Wed Aug 14 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1641 | TT_TASK | Concreting for wall and roof (450m3) | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1642 | TT_TASK | Curing for wall and roof | Sun Aug 11 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1643 | TT_TASK | Preparation of construction joint for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1644 | TT_TASK | Removal external and internal formwork for wall | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1645 | TT_TASK | Removal internal falsework and formwork for roof | Wed Aug 21 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1646 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 03 08:00:00 IST 2014 | Fri Mar 07 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1648 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1649 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1650 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Apr 09 08:00:00 IDT 2013 | Thu Apr 11 18:00:00 IDT 2013 |  | COMPLETED
1651 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1652 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1653 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1654 | TT_TASK | Removal external wall formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1655 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
1656 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Aug 06 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Mon Jul 27 08:00:00 IDT 2015 | Fri Jul 31 18:00:00 IDT 2015 |  | COMPLETED
1658 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Sep 12 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1659 | TT_TASK | Rebar fixing for roof | Tue Sep 17 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1660 | TT_TASK | Erect external formwork for roof | Thu Sep 19 08:00:00 IDT 2013 | Thu Sep 19 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1661 | TT_TASK | Concreting for roof (444m3) | Sat Sep 21 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1662 | TT_TASK | Curing for roof | Sun Sep 22 08:00:00 IDT 2013 | Tue Oct 01 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1663 | TT_TASK | Preparation of construction joint for roof | Mon Sep 23 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1664 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1665 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1668 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1669 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1670 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1671 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1672 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1673 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1674 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1675 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1676 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1677 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1678 | TT_TASK | Removal strut S5 and S4 | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1680 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Thu Apr 25 18:00:00 IDT 2013 |  | COMPLETED
1681 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri May 03 08:00:00 IDT 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
1682 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Thu May 16 08:00:00 IDT 2013 | Thu May 23 18:00:00 IDT 2013 |  | COMPLETED
1683 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1684 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1685 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1686 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Wed May 29 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1687 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1688 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 19 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1690 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Fri Apr 19 18:00:00 IDT 2013 |  | COMPLETED
1691 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1692 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Apr 25 08:00:00 IDT 2013 | Sat Apr 27 18:00:00 IDT 2013 |  | COMPLETED
1693 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1694 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1695 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1696 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1697 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1698 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 02 08:00:00 IDT 2015 | Sat Apr 11 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Feb 27 18:00:00 IST 2015 |  | COMPLETED
1700 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1701 | TT_TASK | Rebar fixing for roof | Tue Aug 06 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1702 | TT_TASK | Erect external formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1703 | TT_TASK | Concreting for roof (444m3) | Fri Aug 09 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 |  | COMPLETED
1704 | TT_TASK | Curing for roof | Thu Aug 01 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1705 | TT_TASK | Preparation of construction joint for roof | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 |  | COMPLETED
1706 | TT_TASK | Removal internal falsework and formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1707 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 09 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1710 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Wed Feb 20 18:00:00 IST 2013 |  | COMPLETED
1711 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1712 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1713 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1714 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1715 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1716 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1717 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1718 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1719 | TT_TASK | Curing | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1720 | TT_TASK | Removal strut S5 and S4 | Mon Jun 24 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1722 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1723 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1724 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Wed Jul 10 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1725 | TT_TASK | Concreting for wall and roof (450m3) | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1726 | TT_TASK | Curing for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1727 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1728 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 |  | COMPLETED
1729 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 |  | COMPLETED
1730 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1732 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1733 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1734 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1735 | TT_TASK | Concreting for wall and roof (450m3) | Tue Sep 03 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1736 | TT_TASK | Curing for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1737 | TT_TASK | Preparation of construction joint for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 |  | COMPLETED
1738 | TT_TASK | Removal external and internal formwork for wall | Thu Sep 05 08:00:00 IDT 2013 | Fri Sep 06 18:00:00 IDT 2013 | Thu Aug 22 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1739 | TT_TASK | Removal internal falsework and formwork for roof | Sat Sep 14 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 |  | COMPLETED
1740 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 05 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1742 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1743 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1744 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1745 | TT_TASK | Concreting for roof (363m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1746 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Sun Oct 20 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1747 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1748 | TT_TASK | Removal internal falsework and formwork for roof | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1749 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Dec 24 13:00:00 IST 2013 | Thu Jan 02 12:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1752 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1753 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1754 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1755 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Apr 12 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1756 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1757 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1758 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1759 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1760 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1761 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1762 | TT_TASK | Removal strut S5 and S4 | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1764 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Aug 05 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1765 | TT_TASK | Rebar fixing for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1766 | TT_TASK | Erect external formwork for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1767 | TT_TASK | Concreting for wall and roof (450m3) | Thu Aug 15 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1768 | TT_TASK | Curing for wall and roof | Fri Aug 16 08:00:00 IDT 2013 | Sun Aug 25 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1769 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1770 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1771 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 |  | COMPLETED
1772 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Feb 04 08:00:00 IST 2014 | Sat Feb 08 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1774 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Aug 07 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1775 | TT_TASK | Rebar fixing for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1776 | TT_TASK | Erect external formwork for wall and roof | Thu Aug 15 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1777 | TT_TASK | Concreting for wall and roof (450m3) | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1778 | TT_TASK | Curing for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1779 | TT_TASK | Preparation of construction joint for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 |  | COMPLETED
1780 | TT_TASK | Removal external and internal formwork for wall | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Wed Aug 21 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 |  | COMPLETED
1781 | TT_TASK | Removal internal falsework and formwork for roof | Mon Sep 16 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1782 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Nov 19 08:00:00 IST 2014 | Mon Nov 24 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1784 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1785 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1786 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1787 | TT_TASK | Concreting for roof (450m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1788 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1789 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1790 | TT_TASK | Removal internal falsework and formwork for roof | Fri Oct 18 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1791 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 13 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1794 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1795 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1796 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1797 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1798 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 28 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1799 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1800 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1801 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1802 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1803 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1804 | TT_TASK | Removal strut S5 and S4 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1806 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1807 | TT_TASK | Rebar fixing for wall and roof | Sat Jul 20 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1808 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1809 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1810 | TT_TASK | Curing for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1811 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1812 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 29 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1813 | TT_TASK | Removal internal falsework and formwork for roof | Tue Aug 06 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1814 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 18:00:00 IST 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1816 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1817 | TT_TASK | Rebar fixing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1818 | TT_TASK | Erect external formwork for wall and roof | Fri Jul 19 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1819 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1820 | TT_TASK | Curing for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Thu Mar 28 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1821 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Mar 29 08:00:00 IDT 2013 | Fri Mar 29 18:00:00 IDT 2013 |  | COMPLETED
1822 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Sat Mar 30 08:00:00 IDT 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1823 | TT_TASK | Removal internal falsework and formwork for roof | Fri Aug 02 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Mon Apr 01 18:00:00 IDT 2013 |  | COMPLETED
1824 | TT_TASK | Side walkway and cable bracket | Thu Nov 13 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1826 | TT_TASK | Erect internal formwork & Falsework for roof | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1827 | TT_TASK | Rebar fixing for roof | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 |  | COMPLETED
1828 | TT_TASK | Erect shutter formwork for roof | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 09 18:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1829 | TT_TASK | Concreting for roof (450m3) | Tue Sep 10 08:00:00 IDT 2013 | Tue Sep 10 18:00:00 IDT 2013 | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 |  | COMPLETED
1830 | TT_TASK | Curing for roof | Wed Sep 11 08:00:00 IDT 2013 | Fri Sep 20 18:00:00 IDT 2013 | Tue Jul 23 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 |  | COMPLETED
1831 | TT_TASK | Preparation of construction joint for roof | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 11 18:00:00 IDT 2013 | Sat Aug 03 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1832 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 26 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 |  | COMPLETED
1833 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 06 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Aug 13 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1835 | TT_TASK | Water proofing and soil backfilling to 0.5m below top of Tunnel Bay 3 to Bay 1 | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1836 | TT_TASK | Mass infill between D-wall and tunnel wall | Fri Oct 11 08:00:00 IDT 2013 | Wed Oct 16 18:00:00 IDT 2013 | Fri Sep 20 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1837 | TT_TASK | Removal S3 and S2 | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
1838 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 4 | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Sat May 18 18:00:00 IDT 2013 |  | COMPLETED
1839 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 5 and remove S3 & S2 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1840 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 6 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1843 | TT_TASK | Pre-drilling and guidewall | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1844 | TT_TASK | D-wall design review | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1845 | TT_TASK | D-wall construction (4741m3) | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 |  | COMPLETED
1846 | TT_TASK | Shear pin and pumping test | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 15 18:00:00 IST 2012 | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1848 | TT_TASK | ELS works to formation level from SN16 to SN19 (soil: 8,700m3 @350m3/day, Install S1 to S3 strut 5 days/layer) | Wed Sep 25 08:00:00 IDT 2013 | Wed Nov 13 18:00:00 IST 2013 | Wed May 08 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1849 | TT_TASK | Design temporary bridge and approval | Mon Sep 01 08:00:00 IDT 2014 | Wed Nov 12 18:00:00 IST 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1850 | TT_TASK | Application of tree transplant | Sat Jun 01 08:00:00 IDT 2013 | Wed Oct 23 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1851 | TT_TASK | Tree transplant | Tue Oct 14 08:00:00 IDT 2014 | Mon Nov 10 18:00:00 IST 2014 | Tue Sep 02 08:00:00 IDT 2014 | Tue Sep 30 18:00:00 IDT 2014 |  | COMPLETED
1852 | TT_TASK | Erection temporary bridge deck | Fri Oct 03 08:00:00 IDT 2014 | Fri Dec 05 18:00:00 IST 2014 | Fri Oct 03 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1853 | TT_TASK | ELS works to formation level from SN10 to SN15 (soil: 9,455m3 @330m3/day, install S1 to S3 strut 5 days/layer) | Mon Nov 24 08:00:00 IST 2014 | Sat Jan 17 18:00:00 IST 2015 | Mon Nov 24 08:00:00 IST 2014 | Tue Jun 23 18:00:00 IDT 2015 |  | COMPLETED
1856 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
1857 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1858 | TT_TASK | Erect external formwork for wall and roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1859 | TT_TASK | Concreting for wall and roof (215m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
1860 | TT_TASK | Curing for wall and roof | Sun Dec 08 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
1861 | TT_TASK | Preparation of construction joint for wall and roof | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1862 | TT_TASK | Removal external and internal formwork for wall | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1863 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1864 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 03 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 | Mon Mar 24 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
1866 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 14 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1867 | TT_TASK | Rebar fixing for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1868 | TT_TASK | Erect external formwork for wall and roof | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1869 | TT_TASK | Concreting for wall and roof (215m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1870 | TT_TASK | Curing for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Sun Dec 29 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1871 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
1872 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 17 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
1873 | TT_TASK | Removal internal falsework and formwork for roof | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1874 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 |  | COMPLETED
1876 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 28 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Nov 28 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1877 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1878 | TT_TASK | Erect external formwork for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1879 | TT_TASK | Concreting for wall and roof (215m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1880 | TT_TASK | Curing for wall and roof | Wed Jan 01 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
1881 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
1882 | TT_TASK | Removal external and internal formwork for wall | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 |  | COMPLETED
1883 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
1884 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 |  | COMPLETED
1886 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1887 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 14 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1888 | TT_TASK | Erect external formwork for wall and roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1889 | TT_TASK | Concreting for wall and roof (215m3) | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1890 | TT_TASK | Curing for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1892 | TT_TASK | Removal external and internal formwork for wall | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1893 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1894 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 |  | COMPLETED
1896 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 08:00:00 IST 2013 |  | COMPLETED
1897 | TT_TASK | Rebar fixing for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1898 | TT_TASK | Erect external formwork for wall and roof | Fri Jan 03 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1899 | TT_TASK | Concreting for wall and roof (215m3) | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1900 | TT_TASK | Curing for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 16 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1901 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Tue Jan 07 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1902 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1903 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1904 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 |  | COMPLETED
1906 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1907 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1908 | TT_TASK | Erect external formwork for wall and roof | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1909 | TT_TASK | Concreting for wall and roof (215m3) | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1910 | TT_TASK | Curing for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1911 | TT_TASK | Preparation of construction joint for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1912 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1913 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1914 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 |  | COMPLETED
1916 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1917 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 |  | COMPLETED
1918 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Tue Jun 04 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 |  | COMPLETED
1919 | TT_TASK | Concreting for wall and roof (333m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1920 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1921 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Wed Jun 12 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1922 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 |  | COMPLETED
1923 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
1924 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 05 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Tue Mar 04 18:00:00 IST 2014 |  | COMPLETED
1926 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1927 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1928 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1929 | TT_TASK | Concreting for wall and roof (412m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1930 | TT_TASK | Curing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Sun Jun 23 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Sat Mar 23 18:00:00 IST 2013 |  | COMPLETED
1931 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Mar 25 08:00:00 IST 2013 | Mon Mar 25 18:00:00 IST 2013 |  | COMPLETED
1932 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Mar 26 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1933 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jun 24 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1934 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 27 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Mon Mar 03 18:00:00 IST 2014 |  | COMPLETED
1936 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1937 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1938 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Apr 02 18:00:00 IDT 2013 |  | COMPLETED
1939 | TT_TASK | Concreting for wall and roof (320m3) | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Apr 05 08:00:00 IDT 2013 | Fri Apr 05 18:00:00 IDT 2013 |  | COMPLETED
1940 | TT_TASK | Curing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 06 08:00:00 IDT 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1941 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1942 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1943 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1944 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jan 21 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Sat Mar 01 18:00:00 IST 2014 |  | COMPLETED
1946 | TT_TASK | Excavation and saw cut D-wall | Thu Apr 02 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Sat Jul 25 18:00:00 IDT 2015 |  | COMPLETED
1947 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Aug 08 16:24:00 IDT 2015 | Mon Aug 10 16:24:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Mon Jul 13 18:00:00 IDT 2015 |  | COMPLETED
1948 | TT_TASK | Erect external formwork for base slab | Mon Aug 10 16:24:00 IDT 2015 | Wed Aug 12 16:24:00 IDT 2015 | Tue Jul 14 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
1949 | TT_TASK | Rebar fixing for base slab | Wed Aug 12 16:24:00 IDT 2015 | Fri Aug 14 16:24:00 IDT 2015 | Wed Jul 15 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1950 | TT_TASK | Erect internal kicker formwork for base slab | Fri Aug 14 16:24:00 IDT 2015 | Mon Aug 17 16:24:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Wed Aug 12 18:00:00 IDT 2015 |  | COMPLETED
1951 | TT_TASK | Concreting for base slab (90m3) | Wed Sep 02 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 | Thu Aug 13 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 |  | COMPLETED
1952 | TT_TASK | Curing for base slab | Thu Sep 03 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Fri Aug 14 08:00:00 IDT 2015 | Thu Aug 20 18:00:00 IDT 2015 |  | COMPLETED
1953 | TT_TASK | Preparation of construction joint for base slab | Thu Sep 03 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Fri Aug 21 08:00:00 IDT 2015 | Fri Aug 21 18:00:00 IDT 2015 |  | COMPLETED
1954 | TT_TASK | Removal of formwork for base slab | Fri Sep 04 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Sat Aug 22 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 |  | COMPLETED
1955 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Sep 05 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 | Mon Aug 24 08:00:00 IDT 2015 | Mon Aug 24 18:00:00 IDT 2015 |  | COMPLETED
1956 | TT_TASK | Curing | Thu Sep 10 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Tue Aug 25 08:00:00 IDT 2015 | Tue Aug 25 18:00:00 IDT 2015 |  | COMPLETED
1957 | TT_TASK | Removal strut S3 | Sat Sep 19 08:00:00 IDT 2015 | Wed Sep 23 18:00:00 IDT 2015 | Wed Sep 16 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
1958 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Sep 24 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
1959 | TT_TASK | Rebar fixing for wall and roof | Wed Sep 30 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 | Fri Sep 25 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 |  | COMPLETED
1960 | TT_TASK | Erect external formwork for wall and roof | Thu Oct 15 08:00:00 IDT 2015 | Fri Oct 16 18:00:00 IDT 2015 | Mon Oct 05 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
1961 | TT_TASK | Concreting for wall and roof (260m3) | Sat Oct 17 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 | Wed Oct 07 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1962 | TT_TASK | Curing for wall and roof | Sun Oct 18 08:00:00 IDT 2015 | Tue Oct 27 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 |  | COMPLETED
1963 | TT_TASK | Preparation of construction joint for wall and roof | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
1964 | TT_TASK | Removal external and internal formwork for wall | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
1965 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 28 08:00:00 IST 2015 | Thu Oct 29 18:00:00 IST 2015 | Thu Oct 22 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1966 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Oct 30 08:00:00 IST 2015 | Wed Nov 04 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1968 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 02 18:00:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 |  | COMPLETED
1969 | TT_TASK | Erect external formwork for base slab | Fri Jul 03 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Tue Jul 21 08:00:00 IDT 2015 | Wed Jul 22 18:00:00 IDT 2015 |  | COMPLETED
1970 | TT_TASK | Rebar fixing for base slab | Mon Jul 06 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 23 08:00:00 IDT 2015 | Fri Jul 24 18:00:00 IDT 2015 |  | COMPLETED
1971 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jul 08 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Sat Jul 25 08:00:00 IDT 2015 | Mon Jul 27 18:00:00 IDT 2015 |  | COMPLETED
1972 | TT_TASK | Concreting for base slab (123m3) | Fri Jul 10 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jul 28 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 |  | COMPLETED
1973 | TT_TASK | Curing for base slab | Sat Jul 11 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1974 | TT_TASK | Preparation of construction joint for base slab | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 |  | COMPLETED
1975 | TT_TASK | Removal of formwork for base slab | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 |  | COMPLETED
1976 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1977 | TT_TASK | Curing | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 |  | COMPLETED
1978 | TT_TASK | Removal strut S3 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1979 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 |  | COMPLETED
1980 | TT_TASK | Rebar fixing for wall and roof | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 |  | COMPLETED
1981 | TT_TASK | Erect external formwork for wall and roof | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 |  | COMPLETED
1982 | TT_TASK | Concreting for wall and roof (260m3) | Fri Oct 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 | Sat Oct 24 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
1983 | TT_TASK | Curing for wall and roof | Sat Oct 03 08:00:00 IDT 2015 | Mon Oct 12 18:00:00 IDT 2015 | Mon Oct 26 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1984 | TT_TASK | Preparation of construction joint for wall and roof | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
1985 | TT_TASK | Removal external and internal formwork for wall | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1986 | TT_TASK | Removal internal falsework and formwork for roof | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1987 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1989 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
1990 | TT_TASK | Erect external formwork for base slab | Mon Jun 15 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1991 | TT_TASK | Rebar fixing for base slab | Wed Jun 17 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
1992 | TT_TASK | Erect internal kicker formwork for base slab | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
1993 | TT_TASK | Concreting for base slab (127m3) | Tue Jun 23 08:00:00 IDT 2015 | Tue Jun 23 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
1994 | TT_TASK | Curing for base slab | Wed Jun 24 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
1995 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 24 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1996 | TT_TASK | Removal of formwork for base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
1997 | TT_TASK | Infill concrete in between D-wall and base slab | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1998 | TT_TASK | Curing | Thu May 28 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1999 | TT_TASK | Removal strut S3 | Fri May 29 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2000 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 03 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2001 | TT_TASK | Rebar fixing for wall and roof | Mon Jun 08 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2002 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2003 | TT_TASK | Concreting for wall and roof (260m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2004 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2005 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2006 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2007 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2008 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 11 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2010 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
2011 | TT_TASK | Erect external formwork for base slab | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
2012 | TT_TASK | Rebar fixing for base slab | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
2013 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
2014 | TT_TASK | Concreting for base slab (127m3) | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
2015 | TT_TASK | Curing for base slab | Thu Jun 11 08:00:00 IDT 2015 | Wed Jun 17 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2016 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 11 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
2017 | TT_TASK | Removal of formwork for base slab | Sat May 23 08:00:00 IDT 2015 | Sat May 23 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
2018 | TT_TASK | Infill concrete in between D-wall and base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
2019 | TT_TASK | Curing | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2020 | TT_TASK | Removal strut S3 | Thu May 28 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2021 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2022 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2023 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2024 | TT_TASK | Concreting for wall and roof (150m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2025 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2026 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2027 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2028 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2029 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jul 06 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
2031 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2032 | TT_TASK | Erect external formwork for base slab | Thu May 21 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2033 | TT_TASK | Rebar fixing for base slab | Sat May 23 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2034 | TT_TASK | Erect internal kicker formwork for base slab | Wed May 27 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2035 | TT_TASK | Concreting for base slab (70m3) | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2036 | TT_TASK | Curing for base slab | Sat May 30 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2037 | TT_TASK | Preparation of construction joint for base slab | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2038 | TT_TASK | Removal of formwork for base slab | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2039 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2040 | TT_TASK | Curing | Sat Jun 06 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2041 | TT_TASK | Removal strut S3 | Mon Jun 08 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat May 23 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2043 | TT_TASK | Rebar fixing for wall and roof | Fri May 29 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2044 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2045 | TT_TASK | Concreting for wall and roof (175m3) | Thu Jun 04 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2046 | TT_TASK | Curing for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sun Jun 14 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2047 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2048 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 03 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 04 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2050 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 29 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
2052 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2053 | TT_TASK | Erect external formwork for base slab | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2054 | TT_TASK | Rebar fixing for base slab | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2055 | TT_TASK | Erect internal kicker formwork for base slab | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2056 | TT_TASK | Concreting for base slab (70m3) | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2057 | TT_TASK | Curing for base slab | Wed Apr 22 08:00:00 IDT 2015 | Tue Apr 28 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2058 | TT_TASK | Preparation of construction joint for base slab | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2059 | TT_TASK | Removal of formwork for base slab | Thu Apr 23 08:00:00 IDT 2015 | Thu Apr 23 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2060 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Apr 24 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2061 | TT_TASK | Curing | Wed Apr 29 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2062 | TT_TASK | Removal strut S3 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2063 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed May 06 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2064 | TT_TASK | Rebar fixing for wall and roof | Thu May 14 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2065 | TT_TASK | Erect external formwork for wall and roof | Mon May 18 08:00:00 IDT 2015 | Tue May 19 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2066 | TT_TASK | Concreting for wall and roof (175m3) | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2067 | TT_TASK | Curing for wall and roof | Thu May 21 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2068 | TT_TASK | Preparation of construction joint for wall and roof | Thu May 21 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2069 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2070 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2071 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jun 23 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
2073 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Fri Nov 15 18:00:00 IST 2013 |  | COMPLETED
2074 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Nov 16 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2075 | TT_TASK | Rebar fixing for base slab | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
2076 | TT_TASK | Erect internal kicker formwork for base slab | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
2077 | TT_TASK | Concreting for base slab (70m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
2078 | TT_TASK | Curing for base slab | Fri Dec 20 08:00:00 IST 2013 | Thu Dec 26 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
2079 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 |  | COMPLETED
2080 | TT_TASK | Removal of formwork for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
2081 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
2082 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2083 | TT_TASK | Removal strut S3 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2084 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Apr 16 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2085 | TT_TASK | Rebar fixing for wall and roof | Thu Apr 24 08:00:00 IDT 2014 | Sat Apr 26 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 |  | COMPLETED
2086 | TT_TASK | Erect external formwork for wall and roof | Mon Apr 28 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Thu Apr 10 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2087 | TT_TASK | Concreting for wall and roof (170m3) | Wed Apr 30 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Sat Apr 12 08:00:00 IDT 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
2088 | TT_TASK | Curing for wall and roof | Thu May 01 08:00:00 IDT 2014 | Sat May 10 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Tue Apr 22 18:00:00 IDT 2014 |  | COMPLETED
2089 | TT_TASK | Preparation of construction joint for wall and roof | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 |  | COMPLETED
2090 | TT_TASK | Removal external and internal formwork for wall | Sat May 03 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Tue Apr 15 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
2091 | TT_TASK | Removal internal falsework and formwork for roof | Mon May 12 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 |  | COMPLETED
2092 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jun 05 08:00:00 IDT 2014 | Tue Jun 10 18:00:00 IDT 2014 | Thu May 29 08:00:00 IDT 2014 | Thu Dec 04 18:00:00 IST 2014 |  | COMPLETED
2094 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2095 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2096 | TT_TASK | Rebar fixing for base slab | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2097 | TT_TASK | Erect internal kicker formwork for base slab | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2098 | TT_TASK | Concreting for base slab (70m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2099 | TT_TASK | Curing for base slab | Sun Dec 08 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2100 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2101 | TT_TASK | Removal of formwork for base slab | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
2102 | TT_TASK | Infill concrete in between D-wall and base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
2103 | TT_TASK | Curing | Sun Dec 15 08:00:00 IST 2013 | Sun Dec 15 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2104 | TT_TASK | Removal strut S3 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2105 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Feb 12 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2106 | TT_TASK | Rebar fixing for wall and roof | Mon Feb 17 08:00:00 IST 2014 | Wed Feb 19 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
2107 | TT_TASK | Erect external formwork for wall and roof | Fri Feb 28 13:48:00 IST 2014 | Mon Mar 03 13:48:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2108 | TT_TASK | Concreting for wall and roof (200m3) | Mon Mar 03 13:48:00 IST 2014 | Tue Mar 04 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2109 | TT_TASK | Curing for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Fri Mar 14 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2110 | TT_TASK | Preparation of construction joint for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Wed Mar 05 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2111 | TT_TASK | Removal external and internal formwork for wall | Wed Mar 05 13:48:00 IST 2014 | Thu Mar 06 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
2112 | TT_TASK | Removal internal falsework and formwork for roof | Fri Mar 14 13:48:00 IST 2014 | Mon Mar 17 13:48:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2113 | TT_TASK | Side walkway and cable bracket (204m3) | Thu May 29 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Wed Dec 03 18:00:00 IST 2014 |  | COMPLETED
2115 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2116 | TT_TASK | Erect external formwork for base slab | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2117 | TT_TASK | Rebar fixing for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2118 | TT_TASK | Erect internal kicker formwork for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2119 | TT_TASK | Concreting for base slab (70m3) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2120 | TT_TASK | Curing for base slab | Tue Dec 03 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2121 | TT_TASK | Preparation of construction joint for base slab | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
2122 | TT_TASK | Removal of formwork for base slab | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2123 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2124 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2125 | TT_TASK | Removal strut S3 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
2126 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jan 25 08:00:00 IST 2014 | Wed Jan 29 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
2127 | TT_TASK | Rebar fixing for wall and roof | Thu Jan 30 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Fri Dec 20 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
2128 | TT_TASK | Erect external formwork for wall and roof | Thu Feb 20 08:00:00 IST 2014 | Fri Feb 21 18:00:00 IST 2014 | Thu Jan 09 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2129 | TT_TASK | Concreting for wall and roof (200m3) | Sat Feb 22 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2130 | TT_TASK | Curing for wall and roof | Sun Feb 23 08:00:00 IST 2014 | Tue Mar 04 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2131 | TT_TASK | Preparation of construction joint for wall and roof | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Tue Jan 14 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2132 | TT_TASK | Removal external and internal formwork for wall | Tue Feb 25 08:00:00 IST 2014 | Tue Feb 25 18:00:00 IST 2014 | Wed Jan 15 08:00:00 IST 2014 | Wed Jan 15 18:00:00 IST 2014 |  | COMPLETED
2133 | TT_TASK | Removal internal falsework and formwork for roof | Wed Mar 05 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2134 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
2137 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Sep 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
2138 | TT_TASK | Erect external formwork for base slab | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Sep 21 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
2139 | TT_TASK | Rebar fixing for base slab | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
2140 | TT_TASK | Erect internal kicker formwork for base slab | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
2141 | TT_TASK | Staircase construction (+12.0mPD to +14.706mPD) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2142 | TT_TASK | Concreting for base slab (30m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
2143 | TT_TASK | Curing for base slab | Fri Dec 13 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
2144 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
2145 | TT_TASK | Removal of formwork for base slab | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 18:00:00 IDT 2013 |  | COMPLETED
2146 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2147 | TT_TASK | Mass concrete at level +12.0mPD | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 |  | COMPLETED
2148 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2149 | TT_TASK | Removal strut S3 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2150 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 17 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Mon Dec 01 18:00:00 IST 2014 |  | COMPLETED
2152 | TT_TASK | Erect working platform to +21.0mPD | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2153 | TT_TASK | Rebar fixing for wall and roof | Sat Jan 11 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2154 | TT_TASK | Staircase construction (+14.706mPD to +16.956mPD) (20m3) | Fri May 02 08:00:00 IDT 2014 | Wed May 07 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2155 | TT_TASK | Staircase construction (+16.956mPD to +19.206mPD) (20m3) | Thu Jun 05 08:00:00 IDT 2014 | Mon Jun 09 18:00:00 IDT 2014 | Thu Jun 12 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2156 | TT_TASK | Staircase construction (+19.206mPD to +21.456mPD) (20m3) | Tue Jun 10 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Fri Jun 20 18:00:00 IDT 2014 |  | COMPLETED
2157 | TT_TASK | Erect external formwork for wall and roof | Sat Mar 15 08:00:00 IST 2014 | Mon Mar 17 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2158 | TT_TASK | Concreting for wall and roof (31m3) | Tue Feb 04 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2159 | TT_TASK | Curing for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 |  | COMPLETED
2160 | TT_TASK | Preparation of construction joint for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2161 | TT_TASK | Removal external and internal formwork for wall | Thu Feb 06 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2162 | TT_TASK | Removal internal falsework and formwork for roof | Sat Feb 15 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Thu Jan 23 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2164 | TT_TASK | Removal strut S2 @ SN 19 | Wed Apr 02 08:00:00 IDT 2014 | Mon Apr 07 18:00:00 IDT 2014 | Mon Mar 03 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 |  | COMPLETED
2165 | TT_TASK | Erect working platform to +24.0mPD | Tue Apr 08 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 | Fri Mar 07 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 |  | COMPLETED
2166 | TT_TASK | Erect internal formwork below strut S1 | Sat Apr 12 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 | Wed Mar 12 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 |  | COMPLETED
2167 | TT_TASK | Staircase construction (+21.456mPD to +23.706mPD) (20m3) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 |  | COMPLETED
2168 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 | Fri Mar 14 08:00:00 IST 2014 | Tue Apr 01 18:00:00 IDT 2014 |  | COMPLETED
2169 | TT_TASK | Erect external wall & internal wall formwork | Tue May 13 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Wed Apr 02 08:00:00 IDT 2014 | Thu Apr 03 18:00:00 IDT 2014 |  | COMPLETED
2170 | TT_TASK | Concreting (External Wall & Internal Wall) (264m3) | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Fri Apr 04 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2171 | TT_TASK | Curing (External Wall & Internal Wall) | Fri May 16 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2172 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Mon May 19 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Thu Apr 10 18:00:00 IDT 2014 |  | COMPLETED
2173 | TT_TASK | Waterproofing | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 |  | COMPLETED
2174 | TT_TASK | Backfilling | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2176 | TT_TASK | Removal strut S1 @ SN 19 | Thu Jun 19 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2177 | TT_TASK | Erect working platform to +30.406mPD | Tue Jun 24 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2178 | TT_TASK | Erect internal formwork | Sat Jun 28 08:00:00 IDT 2014 | Sat Jun 28 18:00:00 IDT 2014 | Wed Jun 04 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2179 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Mon Jun 30 08:00:00 IDT 2014 | Wed Jul 02 18:00:00 IDT 2014 | Thu Jun 05 08:00:00 IDT 2014 | Fri Jun 06 18:00:00 IDT 2014 |  | COMPLETED
2180 | TT_TASK | Erect external formwork (External Wall & Internal Wall) | Thu Jul 03 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2181 | TT_TASK | Concreting (External Wall & Internal Wall) (128m3) | Fri Jul 04 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2182 | TT_TASK | Curing (External Wall & Internal Wall) | Sat Jul 05 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 18:00:00 IDT 2014 |  | COMPLETED
2183 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Tue Jul 08 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2184 | TT_TASK | Waterproofing | Wed Jul 09 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Thu Jun 19 18:00:00 IDT 2014 |  | COMPLETED
2185 | TT_TASK | Backfilling | Sat Jul 12 08:00:00 IDT 2014 | Wed Jul 16 18:00:00 IDT 2014 | Fri Jun 20 08:00:00 IDT 2014 | Tue Jun 24 18:00:00 IDT 2014 |  | COMPLETED
2186 | TT_TASK | Erect falsework and soffit formwork +30.206mPD | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 | Wed Jun 25 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2187 | TT_TASK | Staircase construction (+21.456mPD to +25.956mPD) (20m3) | Sat Jul 19 08:00:00 IDT 2014 | Wed Jul 23 18:00:00 IDT 2014 | Fri Jun 27 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2188 | TT_TASK | Staircase construction (+25.956mPD to +27.606mPD) (20m3) | Sat Jul 05 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 05 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 |  | COMPLETED
2189 | TT_TASK | Rebar fixing (Beam, Floor Slab and Staircase) | Thu Jul 10 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Thu Jul 10 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2190 | TT_TASK | Concreting (Beam, Floor Slab and Staircase) (31m3) | Fri Jul 11 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2191 | TT_TASK | Curing (Beam, Floor Slab and Staircase) | Wed Sep 03 08:00:00 IDT 2014 | Tue Sep 09 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2193 | TT_TASK | Erect working platform to +33.576mPD | Wed Sep 03 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
2194 | TT_TASK | Erect external formwork (External Wall) | Mon Sep 08 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 | Fri Sep 26 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2195 | TT_TASK | Rebar fixing (External Wall) | Thu Sep 11 08:00:00 IDT 2014 | Fri Sep 12 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2196 | TT_TASK | Erect internal formwork (External Wall) | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 |  | COMPLETED
2197 | TT_TASK | Concreting (External Wall) (49m3) | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 |  | COMPLETED
2198 | TT_TASK | Curing (External Wall) | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 |  | COMPLETED
2199 | TT_TASK | Removal formwork (External Wall) | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
2200 | TT_TASK | Erect falsework and soffit formwork +32.656 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2201 | TT_TASK | Rebar fixing (Beam & Floor Slab) | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 |  | COMPLETED
2202 | TT_TASK | Concreting (Beam & Floor Slab) (31m3) | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 |  | COMPLETED
2203 | TT_TASK | Curing (Beam & Floor Slab) | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2205 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
2206 | TT_TASK | Rebar fixing (Roof Parapet Wall) | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 |  | COMPLETED
2207 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2208 | TT_TASK | Concreting (Roof Parapet Wall) (30m3) | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
2209 | TT_TASK | Curing (Roof Parapet Wall) | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 |  | COMPLETED
2210 | TT_TASK | Removal formwork (Roof Parapet Wall) | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2211 | TT_TASK | Removal of falsework and soffit formwork | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
2213 | TT_TASK | Wet trade work | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 |  | COMPLETED
2214 | TT_TASK | Metal works (Louver, Door, Cat-ladder, Architectural Fins, Handrail, Roof Sliding Hatch and Balustrade, etc) | Thu Nov 27 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Thu Nov 27 08:00:00 IST 2014 | Thu Mar 05 18:00:00 IST 2015 |  | COMPLETED
2215 | TT_TASK | Coat works | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2218 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Nov 29 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Feb 04 18:00:00 IST 2014 |  | COMPLETED
2219 | TT_TASK | Backfilling between D-wall and 0.5m below S1 14,240m3 soil | Thu Feb 06 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 | Wed Feb 05 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 |  | COMPLETED
2220 | TT_TASK | Removal of S1 | Wed Mar 12 08:00:00 IST 2014 | Tue Mar 25 18:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 |  | COMPLETED
2221 | TT_TASK | Backfilling to original ground level 21,390m3 (approx. +25.0mPD) | Sat Mar 01 08:00:00 IST 2014 | Wed Mar 19 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Sat May 03 18:00:00 IDT 2014 |  | COMPLETED
2223 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 |  | COMPLETED
2224 | TT_TASK | Backfilling between D-wall and 0.5m below S1 (2075m3) | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 |  | COMPLETED
2225 | TT_TASK | Removal of S1 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 |  | COMPLETED
2226 | TT_TASK | Backfilling to original ground level 3,900m3 (approx. +25.0mPD) (1353m3) | Sat Mar 01 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
2227 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
2228 | TT_TASK | Backfilling backfilling to +20mPD from SN8 to SN9 (Soil: 7,050m3 @ 500m3/day) | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 |  | COMPLETED
2229 | TT_TASK | Removal of S1 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
2230 | TT_TASK | Construction of mud pit | Sat Jul 06 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
2231 | TT_TASK | Backfilling from +20mPD to ground level from SN8 to SN9 (Soil: 5,000m3 @ 500m3/day) | Tue Aug 06 08:00:00 IDT 2013 | Sat Aug 17 18:00:00 IDT 2013 | Tue Jul 02 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 |  | COMPLETED
2233 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Aug 07 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2234 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) | Fri Aug 14 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2235 | TT_TASK | Placing mass concrete infill between tunnel and D-wall | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 02 18:00:00 IST 2015 | Thu Dec 24 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2236 | TT_TASK | Removal of S2 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 10 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 04 18:00:00 IST 2016 |  | COMPLETED
2237 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2238 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
2239 | TT_TASK | Removal strut S1 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2240 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
2241 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488 m3 of soil) | Mon Jan 25 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Fri Apr 01 18:00:00 IDT 2016 |  | COMPLETED
2243 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) (SN18-19) | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 |  | COMPLETED
2244 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) (SN18-19) | Sat Apr 26 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Sat Apr 26 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
2245 | TT_TASK | Placing mass concrete infill between tunnel and D-wall (SN18-19) | Tue May 20 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri May 16 18:00:00 IDT 2014 |  | COMPLETED
2246 | TT_TASK | Removal of S2 (SN16-18) | Wed Jun 04 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 |  | COMPLETED
2247 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) (SN16-18) | Mon Jun 09 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Tue May 27 18:00:00 IDT 2014 |  | COMPLETED
2248 | TT_TASK | Removal strut S1 (SN16-18) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Wed May 28 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
2249 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488m3 of soil) | Fri Jun 27 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
2251 | TT_TASK | Dismantling temporary bridge deck | Mon Jun 15 08:00:00 IDT 2015 | Tue Jul 21 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2252 | TT_TASK | Reinstatement of Works Area 4.10 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jan 11 18:00:00 IST 2017 | Mon May 02 08:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 |  | COMPLETED
2253 | TT_TASK | Complete all tree planting and reinstate Works Area 4.12C | Tue Nov 01 08:00:00 IST 2016 | Thu Jul 13 18:00:00 IDT 2017 | Sat Oct 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2254 | TT_TASK | Reinstate Works Areas 4.9, 4.9A and 4.12A prior to handover | Mon May 22 08:00:00 IDT 2017 | Sat Sep 02 18:00:00 IDT 2017 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2258 | TT_TASK | Application of power supply, environmental permits and construction substation | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2259 | TT_TASK | Procurement and Confirmation of the order of 2nd tunnel boring machine | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2260 | TT_TASK | TBM design and submission for approval | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2261 | TT_TASK | TBM materials order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
2262 | TT_TASK | TBM equipments order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 |  | COMPLETED
2263 | TT_TASK | TBM Fabrication | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
2264 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 |  | COMPLETED
2265 | TT_TASK | TBM test Run | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2266 | TT_TASK | TBM disassembly and packing for shipping to HK | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 |  | COMPLETED
2267 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
2268 | TT_TASK | Setup TBM facilities | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
2269 | TT_TASK | Fabrication 50% of South Tunnel South Bound Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
2270 | TT_TASK | Fabrication 100% of South Tunnel South Bound Precast Lining | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
2271 | TT_TASK | Fabrication 50% of South Tunnel North Bound Precast Lining | Wed Oct 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 | Wed Oct 03 08:00:00 IST 2012 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
2272 | TT_TASK | Fabrication 100% of South Tunnel North Bound Precast Lining | Mon Aug 26 08:00:00 IDT 2013 | Wed Jan 22 18:00:00 IST 2014 | Wed Feb 27 08:00:00 IST 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
2274 | TT_TASK | Ground treatment at lauching shaft Southbound | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
2275 | TT_TASK | TBM assemble, thrust frame, testing and commissioning | Sat Jun 01 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2276 | TT_TASK | Lowing back-up plant for final drive | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
2277 | TT_TASK | Assemble and set up back-up plant for final drive | Sat Jun 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2278 | TT_TASK | Erection of noise enclosure | Sat Jul 20 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 |  | COMPLETED
2279 | TT_TASK | TBM drive & lining installation CH124+912 to CH125+012 (Initial Drive) | Sat Jul 20 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Mon Mar 11 00:00:00 IST 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
2280 | TT_TASK | TBM drive & lining installation CH125+012 to CH125+338 | Tue Oct 15 08:00:00 IDT 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon May 27 08:00:00 IDT 2013 | Tue May 20 00:00:00 IDT 2014 |  | COMPLETED
2281 | TT_TASK | Dis-assemble TBM | Fri May 23 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 |  | COMPLETED
2282 | TT_TASK | Invert slab and side walkway | Fri Aug 01 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Tue Sep 02 18:00:00 IDT 2014 |  | COMPLETED
2283 | TT_TASK | Installation of cable bracket | Mon Nov 03 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 | Mon Aug 18 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2285 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Sep 01 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 | Sat Aug 09 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2286 | TT_TASK | Ground treatment at lauching shaft Northbound | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 19 18:00:00 IST 2013 | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
2287 | TT_TASK | TBM assemble, testing and commissioning | Wed Jul 02 08:00:00 IDT 2014 | Wed Sep 03 18:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2288 | TT_TASK | Setup back-up plant for final drive | Tue Jun 03 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2289 | TT_TASK | Reinstate of noise enclosure | Fri Oct 10 08:00:00 IDT 2014 | Wed Nov 05 18:00:00 IST 2014 | Tue Oct 28 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
2290 | TT_TASK | TBM drive & lining installation CH124+927 to CH125+027 (Initial Drive) | Fri Oct 10 08:00:00 IDT 2014 | Thu Nov 13 18:00:00 IST 2014 | Thu Oct 30 00:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
2291 | TT_TASK | TBM drive & lining installation CH125+027 to CH125+353 (Final Drive) | Fri Jan 02 08:00:00 IST 2015 | Thu Feb 12 18:00:00 IST 2015 | Mon Dec 08 08:00:00 IST 2014 | Fri Aug 07 00:00:00 IDT 2015 |  | COMPLETED
2292 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Tue Aug 04 08:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
2293 | TT_TASK | Dis-assemble TBM | Tue Aug 04 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
2294 | TT_TASK | Invert slab and side walkway | Wed Sep 09 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
2295 | TT_TASK | Installation of cable bracket | Thu Sep 24 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Aug 31 18:00:00 IDT 2015 |  | COMPLETED
2298 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Partial length) at down track | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 |  | COMPLETED
2299 | TT_TASK | Probe/Grout | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 | Mon Aug 11 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2300 | TT_TASK | Coring of Segment | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 |  | COMPLETED
2301 | TT_TASK | Removal of segment | Tue Sep 02 08:00:00 IDT 2014 | Thu Sep 04 18:00:00 IDT 2014 | Thu Aug 21 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2302 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Sep 05 08:00:00 IDT 2014 | Tue Oct 07 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2303 | TT_TASK | Invert Concrete | Thu Oct 23 08:00:00 IDT 2014 | Sat Nov 01 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2304 | TT_TASK | Wall and Roof concrete | Mon Nov 03 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Mon Oct 13 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
2305 | TT_TASK | Dismantle Temporary frame | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2306 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
2307 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Remaining length ) at down track | Sat May 09 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Thu Apr 16 18:00:00 IDT 2015 |  | COMPLETED
2308 | TT_TASK | Probe/Grout | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
2309 | TT_TASK | Coring of Segment | Fri Oct 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 | Fri Oct 16 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
2310 | TT_TASK | Removal of segment | Wed Oct 07 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
2311 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Oct 10 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Oct 26 08:00:00 IST 2015 | Fri Dec 11 18:00:00 IST 2015 |  | COMPLETED
2312 | TT_TASK | Invert Concrete | Thu Dec 03 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Sat Dec 12 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2313 | TT_TASK | Wall and Roof concrete | Mon Dec 14 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 15 18:00:00 IST 2016 |  | COMPLETED
2314 | TT_TASK | Dismantle Temporary frame | Wed Jan 13 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 |  | COMPLETED
2315 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2318 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 |  | COMPLETED
2319 | TT_TASK | Pre-drill and guide wall | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 |  | COMPLETED
2320 | TT_TASK | D-wall design review | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 |  | COMPLETED
2321 | TT_TASK | D-Wall Construction (1075m3) | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 |  | COMPLETED
2322 | TT_TASK | Shear pin, toe grout and pumping test | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 |  | COMPLETED
2324 | TT_TASK | SI for TBM ground treatment | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2325 | TT_TASK | Design review of TBM ground treatment | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2326 | TT_TASK | Ground treatment for TBM southbound | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
2327 | TT_TASK | Ground treatment for TBM northbound | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2329 | TT_TASK | Capping beam construction | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2330 | TT_TASK | L-Shape wall construction | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
2331 | TT_TASK | Excavate up to +28.5mPD (1488m3) | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 |  | COMPLETED
2332 | TT_TASK | Install Strut S1 +29.0mPD | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 |  | COMPLETED
2333 | TT_TASK | Excavate up to +23.5mPD (2480m3) | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 |  | COMPLETED
2334 | TT_TASK | Install Strut S2 +24.0mPD | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 |  | COMPLETED
2335 | TT_TASK | Excavate up to +19.5mPD (1984m3) | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
2336 | TT_TASK | Install Strut S3 +20.0mPD | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 |  | COMPLETED
2337 | TT_TASK | Excavate up to +15.5mPD (1984m3) | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
2338 | TT_TASK | Install Strut S4 +16.0mPD | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 |  | COMPLETED
2339 | TT_TASK | Excavate up to formation (4117m3) | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
2340 | TT_TASK | Install rock dowel and tie back | Sat Jun 02 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Sat Jun 02 08:00:00 IDT 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2341 | TT_TASK | Temporary handover the shaft to contract 822 | Mon Jun 03 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2343 | TT_TASK | Rock breaking works | Mon Aug 26 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
2344 | TT_TASK | Temporary base Slab for TBM Drive | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
2347 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2348 | TT_TASK | Erect external formwork (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Wed Aug 13 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Tue Aug 19 18:00:00 IDT 2014 |  | COMPLETED
2349 | TT_TASK | Rebar fixing (Base Slab) | Thu Aug 14 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Wed Aug 20 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2350 | TT_TASK | Erect internal kicker formwork (Base Slab) | Tue Aug 19 08:00:00 IDT 2014 | Thu Aug 21 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 |  | COMPLETED
2351 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 22 08:00:00 IDT 2014 | Fri Aug 22 18:00:00 IDT 2014 | Thu Aug 28 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2352 | TT_TASK | Concreting (Base Slab) (245m3) | Sat Aug 23 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014 | Fri Aug 29 18:00:00 IDT 2014 |  | COMPLETED
2353 | TT_TASK | Curing (Base Slab) | Mon Aug 25 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2354 | TT_TASK | Removal of formwork (Base Slab) | Mon Sep 08 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Mon Sep 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2355 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Sep 10 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Tue Sep 02 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 |  | COMPLETED
2356 | TT_TASK | Rebar fixing (Wall and roof) | Thu Sep 18 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Thu Sep 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2357 | TT_TASK | Erect external formwork (Wall) | Thu Sep 25 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2358 | TT_TASK | Clearing and inspection (Wall and roof) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2359 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
2360 | TT_TASK | Curing (Wall and roof) | Sat Oct 11 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
2361 | TT_TASK | Removal formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Thu Oct 16 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Sat Nov 01 18:00:00 IST 2014 |  | COMPLETED
2362 | TT_TASK | Removal formwork (Roof) | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2363 | TT_TASK | Side walkway and cable bracket (72m3) | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
2365 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Nov 07 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Sat Nov 07 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
2366 | TT_TASK | Erect external formwork (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Wed Nov 18 18:00:00 IST 2015 |  | COMPLETED
2367 | TT_TASK | Rebar fixing (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Tue Nov 17 18:00:00 IST 2015 | Thu Nov 19 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 |  | COMPLETED
2368 | TT_TASK | Erect internal kicker formwork (Base Slab) | Wed Nov 18 08:00:00 IST 2015 | Fri Nov 20 18:00:00 IST 2015 | Tue Nov 24 08:00:00 IST 2015 | Thu Nov 26 18:00:00 IST 2015 |  | COMPLETED
2369 | TT_TASK | Clearing and inspection (Base Slab) | Sat Nov 21 08:00:00 IST 2015 | Sat Nov 21 18:00:00 IST 2015 | Fri Nov 27 08:00:00 IST 2015 | Fri Nov 27 18:00:00 IST 2015 |  | COMPLETED
2370 | TT_TASK | Concreting (Base Slab) (245m3) | Mon Nov 23 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Nov 28 08:00:00 IST 2015 | Sat Nov 28 18:00:00 IST 2015 |  | COMPLETED
2371 | TT_TASK | Curing (Base Slab) | Tue Nov 24 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Mon Nov 30 08:00:00 IST 2015 | Thu Dec 03 18:00:00 IST 2015 |  | COMPLETED
2372 | TT_TASK | Removal of formwork (Base Slab) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Fri Dec 04 08:00:00 IST 2015 | Sat Dec 05 18:00:00 IST 2015 |  | COMPLETED
2373 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 09 18:00:00 IST 2015 | Mon Dec 07 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
2374 | TT_TASK | Rebar fixing (Wall and roof) | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2375 | TT_TASK | Erect external formwork (Wall) | Mon Jan 11 08:00:00 IST 2016 | Wed Jan 13 18:00:00 IST 2016 | Thu Jan 07 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2376 | TT_TASK | Clearing and inspection (Wall and roof) | Thu Jan 14 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2377 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Jan 15 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2378 | TT_TASK | Curing (Wall and roof) | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 |  | COMPLETED
2379 | TT_TASK | Removal formwork (Wall) | Tue Jan 19 08:00:00 IST 2016 | Thu Jan 21 18:00:00 IST 2016 | Thu Jan 28 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2380 | TT_TASK | Removal formwork and falsework (Roof) | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Sat Jan 30 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2381 | TT_TASK | Side walkway and cable bracket (72m3) | Wed Jan 06 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Thu Nov 12 08:00:00 IST 2015 | Tue Mar 01 18:00:00 IST 2016 |  | COMPLETED
2382 | TT_TASK | Provision access opening to DC | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2383 | TT_TASK | Erect falsework and soffit formwork (Opening) | Thu Mar 10 08:00:00 IST 2016 | Mon Mar 21 18:00:00 IST 2016 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2384 | TT_TASK | Rebar fixing (Roof) | Tue Mar 22 08:00:00 IST 2016 | Tue Mar 22 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2385 | TT_TASK | Clearing and inspection (Roof) | Wed Mar 23 08:00:00 IST 2016 | Wed Mar 23 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2386 | TT_TASK | Concreting (Roof) (225m3) | Thu Mar 24 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2387 | TT_TASK | Curing (Roof) | Tue Mar 29 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Jan 13 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
2388 | TT_TASK | Removal internal falsework and soffit formwork (Roof) | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
2390 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Thu Mar 17 08:00:00 IST 2016 | Fri Mar 18 18:00:00 IST 2016 | Tue Mar 01 08:00:00 IST 2016 | Wed Mar 02 18:00:00 IST 2016 |  | COMPLETED
2391 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Sat Mar 19 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Thu Mar 03 08:00:00 IST 2016 | Tue Mar 08 18:00:00 IST 2016 |  | COMPLETED
2392 | TT_TASK | Backfilling to +18.25mPD (1229 m3 of soil) | Sat Jul 02 08:00:00 IDT 2016 | Mon Jul 11 18:00:00 IDT 2016 | Mon Jul 25 08:00:00 IDT 2016 | Tue Aug 02 18:00:00 IDT 2016 |  | COMPLETED
2393 | TT_TASK | Laying 500mm mass concrete lateral support | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 |  | COMPLETED
2394 | TT_TASK | Backfilling to 0.5m below S3 (+19.5mPD) (372m3 of soil) | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 |  | COMPLETED
2395 | TT_TASK | Removal strut S3 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 |  | COMPLETED
2396 | TT_TASK | Backfilling to 0.5m below S2 (+23.5mPD) (1984m3 of soil) | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 |  | COMPLETED
2397 | TT_TASK | Removal strut S2 | Wed Aug 24 08:00:00 IDT 2016 | Fri Aug 26 18:00:00 IDT 2016 | Wed Aug 24 08:00:00 IDT 2016 | Thu Sep 01 18:00:00 IDT 2016 |  | COMPLETED
2398 | TT_TASK | Backfilling to 0.5m below S1 (+28.5mPD) (2480m3 of soil) | Mon Sep 05 08:00:00 IDT 2016 | Tue Sep 20 18:00:00 IDT 2016 | Fri Sep 02 08:00:00 IDT 2016 | Fri Sep 09 18:00:00 IDT 2016 |  | COMPLETED
2399 | TT_TASK | Removal strut S1 | Wed Sep 21 08:00:00 IDT 2016 | Thu Sep 22 18:00:00 IDT 2016 | Sat Sep 10 08:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 |  | COMPLETED
2400 | TT_TASK | Backfilling to original ground level (approx. +31.5mPD) (1488m3 of soil) | Fri Sep 23 08:00:00 IDT 2016 | Mon Oct 03 18:00:00 IDT 2016 | Thu Sep 15 08:00:00 IDT 2016 | Mon Sep 19 18:00:00 IDT 2016 |  | COMPLETED
2402 | TT_TASK | Reinstatement of TUT area (Including Hydroseeding) | Mon Oct 03 08:00:00 IDT 2016 | Mon Jun 19 18:00:00 IDT 2017 | Fri Oct 07 08:00:00 IDT 2016 |  | 216.0 | IN_PROGRESS
25 | TT_TASK | Access opening for the up track cut and cover tunnel at Tse Uk Tsuen Shaft | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 10 18:00:00 IST 2016 |  | COMPLETED
27 | TT_TASK | Close out the temporary access opening at Tse Uk Tsuen Shaft | Thu Mar 10 08:00:00 IST 2016 | Tue Apr 05 18:00:00 IDT 2016 | Thu Feb 11 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
307 | TT_TASK | Position crane for TBM retrieval (down track) | Wed Jul 02 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014 | Sat Aug 02 18:00:00 IDT 2014 |  | COMPLETED
308 | TT_TASK | TBM Break-in and Retrieval (down track) | Mon Aug 04 08:00:00 IDT 2014 | Sat Aug 30 18:00:00 IDT 2014 | Mon Aug 04 08:00:00 IDT 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
309 | TT_TASK | Position crane for TBM retrieval (up track) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 |  | COMPLETED
310 | TT_TASK | TBM Break-in and Retrieval (up track) | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
376 | TT_TASK | Supply Engineer with Survey Equipment [PS41.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
377 | TT_TASK | Provide Engineer with suitably qualified full time Survey Assistant - 4 nos. [PS41.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
378 | TT_TASK | Provide Engineer with site transportation as detailed in PS42.1 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 |  | COMPLETED
379 | TT_TASK | Submit details of qualified drivers to be assigned to the Engineer, for review [PS42.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 |  | COMPLETED
380 | TT_TASK | Install, service and maintain 10 container offices for use by the Engineer's Site Staff | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
381 | TT_TASK | Provide services and equipment for the Engineer | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
383 | TT_TASK | Master Programme - Prepare and submit for approval [GS4.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
384 | TT_TASK | Master Programme - Comments , Resubmission and Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
385 | TT_TASK | Time Chainage Programme - Prepare and submit for approval [GS4.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
386 | TT_TASK | Time Chainage Programme - Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
387 | TT_TASK | Implement and Maintain Programme Management System for 1st Audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
388 | TT_TASK | Implement and Maintain Programme Management System for 2nd Audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
389 | TT_TASK | Implement and Maintain Programme Management System for 3rd Audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
391 | TT_TASK | Environmental Management Plan - Prepare and submit for approval [GS5.1.10] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
392 | TT_TASK | Environmental Management Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
393 | TT_TASK | Quality Plan - Prepare and submit for approval [GS9.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
394 | TT_TASK | Quality Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
395 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 1st audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 |  | COMPLETED
396 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 2nd audit | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
397 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 3rd audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
398 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 4th audit | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
399 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 5th audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
400 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 6th audit | Tue Jul 02 08:00:00 IDT 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
401 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 7th audit | Thu Nov 28 08:00:00 IST 2013 | Thu Jun 05 18:00:00 IDT 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Jan 24 18:00:00 IST 2014 |  | COMPLETED
402 | TT_TASK | Health and Safety Plan - Prepare and submit [G3.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
403 | TT_TASK | System Assurance Plan - Prepare and submit for approval [PS Appendix P3.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
404 | TT_TASK | System Assurance Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
405 | TT_TASK | Design for Safety & Constructability Plan - Prepare and submit for approval [PS37.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
406 | TT_TASK | Design for Safety & Constructability Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
408 | TT_TASK | Methods of Construction - Prepare and submit for approval [GS12.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
409 | TT_TASK | Methods of Construction - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
410 | TT_TASK | Contractor's Submission Schedule - Prepare and submit for approval [GS12.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
411 | TT_TASK | Contractor's Submission Schedule - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
412 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) [PS13.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
413 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) - Approval period | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 |  | COMPLETED
414 | TT_TASK | Spoil Disposal Plan [PS17.7.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
415 | TT_TASK | Waste Management Plan [PS22.10.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
416 | TT_TASK | Independent Checking Engineer - Appoint and submit for approval [PS7.1.8] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
417 | TT_TASK | Independent Checking Engineer - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
418 | TT_TASK | Sub-contract Management Plan - Prepare and submit [PS34.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 |  | COMPLETED
419 | TT_TASK | Schedule of Utilities Services Arrangement [GS7.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
420 | TT_TASK | Site Safety Supervision Plan for Site Formation - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
421 | TT_TASK | Site Safety Supervision Plan for Site Formation - Approval period | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
422 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Prepare and Submit | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
423 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
424 | TT_TASK | Site Safety Supervision Plan for ELS - Prepare and Submit | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
425 | TT_TASK | Site Safety Supervision Plan for ELS - Approval Period | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
426 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Prepare and Submit | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
427 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Approval Period | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
428 | TT_TASK | Noise Management Plan [P22.3.9] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
429 | TT_TASK | Air Quality Management Plan [P22.4.3] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
430 | TT_TASK | Detailed Proposal for Water Pollution Control Measures and Proposed Monitoring [PS22.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
431 | TT_TASK | Groundwater Monitoring and Response Plan [PS22.5.2] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
432 | TT_TASK | Vibration Monitoring Plan [PS22.8.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 |  | COMPLETED
433 | TT_TASK | Proposed Outline TTM Scheme - Prepare & submit to the: Engineer for Review / SLG for Approval [PS19.3] | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 |  | COMPLETED
434 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Proposed TTM Scheme [PS19.4] | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 |  | COMPLETED
435 | TT_TASK | Resubmission of Proposed Outline TTM Scheme (if required) | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
436 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Resubmitted Proposed Outline TTM Scheme [PS19.4] | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 |  | COMPLETED
437 | TT_TASK | Notification Period of the Approved TTM Scheme prior to implementation [PS19.4] | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 |  | COMPLETED
440 | TT_TASK | Initial Site Survey (WA3.11) | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 |  | COMPLETED
441 | TT_TASK | Initial Site Survey Report (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 |  | COMPLETED
442 | TT_TASK | Initial Site Survey & Condition Survey (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
443 | TT_TASK | Initial Site Survey Report (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
444 | TT_TASK | Initial Site Survey & Condition Survey (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
445 | TT_TASK | Initial Site Survey Report (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
446 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 4.9 & 4.12A [PS4.2] | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
447 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 5.1 & 5.3 [PS4.2.3] | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 |  | COMPLETED
448 | TT_TASK | Proposal for Site Clearance Works [PS4.4.1] | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 |  | COMPLETED
449 | TT_TASK | Site Clearance / Site Formation Works (including demolition of EBS) | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
450 | TT_TASK | Backfill existing stream courses in Works Area 4.9, 4.10 and 4.11 [PS18.5.1] | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
451 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and submit to EPD for Approval (WA3.3 - Area M, I, L) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
452 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA3.3 - Area M, I, L) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
453 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
454 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
455 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.3 - Area M, I, L) | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
456 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA3.3 - Area M, I, L) | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
457 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA3.3 - Area M, I, L) | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
458 | TT_TASK | Remediation Report - Approval (WA3.3 - Area M, I, L) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
459 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and Submit to EPD for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
460 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
461 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
462 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.1, 3.2, 3.3, 3.3A) | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
463 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.1, 3.2, 3.3, 3.3A) | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 |  | COMPLETED
464 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 |  | COMPLETED
465 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
466 | TT_TASK | Remediation Report - Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
467 | TT_TASK | Conduct remediation for Area Q in accordance with method proposed in the approved Remediation Action Plan [PS22.9.2] | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 |  | COMPLETED
468 | TT_TASK | Remediation Report - Prepare and submit for Approval [PS22.9.2] (Area Q) | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 |  | COMPLETED
469 | TT_TASK | Remediation Report - Approval (Area Q) | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
470 | TT_TASK | Removal of contaminated soil at North Tunnels (Area N,O,P,Q,R,S) | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
471 | TT_TASK | Condition Survey EBS for presence of Asbestos and gather samples | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
472 | TT_TASK | Testing of gathered samples | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 |  | COMPLETED
473 | TT_TASK | Prepare and submit Asbestos Investigation Report (AIR) & Asbestos Abatement Plan (AAP) | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
474 | TT_TASK | Approval period of AIR & AAP | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
475 | TT_TASK | Notification period to Engineer and EPD prior to Asbestos abatement works | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
476 | TT_TASK | Asbestos abatement works | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
477 | TT_TASK | Demolition of EBS | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
478 | TT_TASK | Confirmation of tree survey | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 |  | COMPLETED
480 | TT_TASK | Installation of ground settlement markers | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 |  | COMPLETED
481 | TT_TASK | Settlement monitoring and submit report | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
482 | TT_TASK | Settlement monitoring and submit report | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 |  | COMPLETED
483 | TT_TASK | Settlement monitoring and submit report | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
484 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
485 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Wed Feb 26 18:00:00 IST 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Feb 21 18:00:00 IST 2014 |  | COMPLETED
486 | TT_TASK | Settlement monitoring and submit report | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 |  | COMPLETED
488 | TT_TASK | Permit Applications (incl. License to Search and Excavate Antiquities and Excavation Permit) | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 |  | COMPLETED
489 | TT_TASK | Check for underground utilities | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 |  | COMPLETED
490 | TT_TASK | Field walking and hand augering | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 |  | COMPLETED
491 | TT_TASK | Excavation of trial pits | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 |  | COMPLETED
492 | TT_TASK | Rescue excavation rescue works (if required) | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 |  | COMPLETED
494 | TT_TASK | Erection of Hoarding with Gate (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 |  | COMPLETED
495 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 3.1, 3.2, 3.3 and 3.3A [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
496 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 4.9, 4.10, 4.11, 4.12A~C, and 4.15 [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
497 | TT_TASK | Project Signboard Erection [PS4.6.8] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
498 | TT_TASK | Marine Survey at Barging Point [PS4.3] (before construction of barging facilities) | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 00:00:00 IST 2010 |  | COMPLETED
499 | TT_TASK | Construct barging facilities | Sat Oct 02 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Oct 02 00:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
500 | TT_TASK | Operation Plan for the Barging Facility - Prepare and Submit for Approval [PS17.1.9] | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
501 | TT_TASK | Operation Plan for the Barging Facility - Review and Approval Period | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 |  | COMPLETED
503 | TT_TASK | General and Special Attendance for Designated Contractors | Mon Dec 02 08:00:00 IST 2013 | Mon Aug 31 18:00:00 IDT 2015 | Tue Jul 02 08:00:00 IDT 2013 | Wed Mar 25 18:00:00 IST 2015 |  | COMPLETED
505 | TT_TASK | Prepare and Submit Detailed Interface Specification | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 |  | COMPLETED
506 | TT_TASK | Approval of Detailed Interface Plan | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
507 | TT_TASK | Prepare and Submit Detailed Interface Specification | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 |  | COMPLETED
508 | TT_TASK | Approval of Detailed Interface Plan | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
510 | TT_TASK | Prepare and Submit Draft Operation and Maintenance Manual [PS33.1] | Mon Aug 24 08:00:00 IDT 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jul 28 08:00:00 IDT 2014 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
511 | TT_TASK | Review and approval period of Draft Operation and Maintenance Manual | Wed Aug 10 08:00:00 IDT 2016 | Tue Sep 13 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
512 | TT_TASK | Prepare and Submit Final Operation and Maintenance Manual [PS33.1] | Wed Sep 14 08:00:00 IDT 2016 | Thu Feb 16 18:00:00 IST 2017 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
513 | TT_TASK | Provide Engineer with As-Built Drawing for the Whole of the Works [PS33.2] | Mon Nov 21 08:00:00 IST 2016 | Wed Dec 14 18:00:00 IST 2016 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
514 | TT_TASK | Provide Engineer with Asset Registration Information [PS33.3] | Fri May 19 08:00:00 IDT 2017 | Mon Jun 12 18:00:00 IDT 2017 |  |  |  | NOT_STARTED
517 | TT_TASK | Preliminary Design Programme - Prepare and Submit for Approval [PS7.1.8 - App. Z2.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
518 | TT_TASK | Preliminary Design Programme - Review and Approval Period [PS7.1.8 - App. Z2.2] | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 |  | COMPLETED
519 | TT_TASK | Preliminary Design Programme - Resubmission and Approval (if required) [PS7.1.8 - App. Z2.2] | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 |  | COMPLETED
520 | TT_TASK | Schedule of Designs - Prepare and Submit for Approval [PS7.1.8 - App. Z2.5] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
521 | TT_TASK | Detailed Proposal for Carrying Out the Cross Passage Works [PS11.5.2] | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
524 | TT_TASK | Design TBM and submit full details to the Engineer [PS7.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
525 | TT_TASK | TBM Design - Approval period | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 |  | COMPLETED
526 | TT_TASK | TBM Design - Resubmission and approval period | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 |  | COMPLETED
528 | TT_TASK | AIP Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
529 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 |  | COMPLETED
530 | TT_TASK | DDS Design - Prepare and Submit | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 |  | COMPLETED
531 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 |  | COMPLETED
532 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 |  | COMPLETED
533 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 |  | COMPLETED
534 | TT_TASK | Issue Completed Working Drawings | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
536 | TT_TASK | AIP Design - Prepare and Submit | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 |  | COMPLETED
537 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 |  | COMPLETED
538 | TT_TASK | AIP Design - Response to comments and Resubmit | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
539 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
540 | TT_TASK | DDS Design - Prepare and Submit | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
541 | TT_TASK | DDS Design - Review and Approval Period (by MTRC & related Government Authorities) | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 |  | COMPLETED
542 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 |  | COMPLETED
543 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 |  | COMPLETED
544 | TT_TASK | Issue Completed Working Drawings | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 |  | COMPLETED
546 | TT_TASK | DDS Design - Prepare and Submit | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 |  | COMPLETED
547 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 |  | COMPLETED
548 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 |  | COMPLETED
549 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 |  | COMPLETED
550 | TT_TASK | Issue Completed Working Drawings | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
552 | TT_TASK | AIP Design - Prepare and Submit | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 |  | COMPLETED
553 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
554 | TT_TASK | AIP Design - Response to comments and Resubmit | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 |  | COMPLETED
555 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
556 | TT_TASK | DDS Design - Prepare and Submit | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 |  | COMPLETED
557 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 |  | COMPLETED
558 | TT_TASK | DDS Design - Response to comments and Resubmit | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 |  | COMPLETED
559 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 |  | COMPLETED
560 | TT_TASK | Issue Completed Working Drawings | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 |  | COMPLETED
562 | TT_TASK | Prepare and Submit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 |  | COMPLETED
563 | TT_TASK | Review and Approval Period | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
564 | TT_TASK | Response to comments and Resubmit | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 |  | COMPLETED
565 | TT_TASK | Review and Approval Period (for resubmission) | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 |  | COMPLETED
568 | TT_TASK | DDS Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
569 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 |  | COMPLETED
570 | TT_TASK | DDS Design - Response to comments and Resubmit | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 |  | COMPLETED
571 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 |  | COMPLETED
572 | TT_TASK | Issue Completed Working Drawings | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
574 | TT_TASK | DDS Design - Prepare and Submit | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 |  | COMPLETED
575 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 |  | COMPLETED
576 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 |  | COMPLETED
577 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 |  | COMPLETED
578 | TT_TASK | Issue Completed Working Drawings | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 |  | COMPLETED
580 | TT_TASK | DDS Design - Prepare and Submit | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 |  | COMPLETED
581 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 |  | COMPLETED
582 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 |  | COMPLETED
583 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 |  | COMPLETED
584 | TT_TASK | Issue Completed Working Drawings | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 |  | COMPLETED
586 | TT_TASK | DDS Design - Prepare and Submit | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 |  | COMPLETED
587 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 |  | COMPLETED
588 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 |  | COMPLETED
589 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 |  | COMPLETED
590 | TT_TASK | Issue Completed Working Drawings | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 |  | COMPLETED
592 | TT_TASK | DDS Design - Prepare and Submit | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 |  | COMPLETED
593 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 |  | COMPLETED
594 | TT_TASK | DDS Design - Response to comments and Resubmit | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 |  | COMPLETED
595 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 |  | COMPLETED
596 | TT_TASK | Issue Completed Working Drawings | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
599 | TT_TASK | Formworks / Falsework - Prepare & Submit | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
600 | TT_TASK | Formworks / Falsework - Review & Approval Period (by MTRC) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
601 | TT_TASK | Formworks / Falsework - Response to comments and Resubmit | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 |  | COMPLETED
602 | TT_TASK | Formworks / Falsework - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
605 | TT_TASK | Layout of Site Hoarding - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
606 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (by MTRC) | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
607 | TT_TASK | Layout of Site Hoarding - Response to comments and Resubmit | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
608 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 |  | COMPLETED
610 | TT_TASK | Layout of Engineer's Accommodation - Prepare and Submit | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
611 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (by MTRC) | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 |  | COMPLETED
612 | TT_TASK | Layout of Engineer's Accommodation - Response to comments and Resubmit | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
613 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (for resubmit) (by MTRC & related Government Authorities | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
615 | TT_TASK | TTMS Assessment Report - Prepare and Submit | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 |  | COMPLETED
616 | TT_TASK | TTMS Assessment Report - Review and Approval Period (by MTRC) | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
617 | TT_TASK | TTMS Assessment Report - Response to comments and Resubmit | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 |  | COMPLETED
618 | TT_TASK | TTMS Assessment Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
619 | TT_TASK | Issue Completed Working Drawings | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 |  | COMPLETED
621 | TT_TASK | DIA Report - Prepare and Submit | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 |  | COMPLETED
622 | TT_TASK | DIA Report - Review and Approval Period (by MTRC) | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 |  | COMPLETED
623 | TT_TASK | DIA Report - Response to comments and Resubmit | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 |  | COMPLETED
624 | TT_TASK | DIA Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
625 | TT_TASK | Issue Completed Working Drawings | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 |  | COMPLETED
627 | TT_TASK | AIP Design - Prepare & Submit | Wed Sep 23 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 |  | COMPLETED
628 | TT_TASK | AIP Design - Review & Approval Period (by MTR) | Wed Oct 14 08:00:00 IDT 2015 | Wed Nov 11 18:00:00 IST 2015 | Mon Jun 08 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
629 | TT_TASK | AIP Design - Response to comments and Resubmit | Thu Nov 12 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Mon Jun 15 01:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
630 | TT_TASK | AIP Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jun 22 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
631 | TT_TASK | DDS Design - Prepare & Submit | Wed Jan 13 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Tue Sep 01 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 |  | COMPLETED
632 | TT_TASK | DDS Design - Review & Approval Period (by MTRC) | Fri Feb 26 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 12 18:00:00 IDT 2015 |  | COMPLETED
633 | TT_TASK | DDS Design - Response to comments & Resubmit | Tue Mar 29 08:00:00 IDT 2016 | Fri Apr 01 18:00:00 IDT 2016 | Mon Sep 14 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
634 | TT_TASK | DDS Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Apr 02 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 | Mon Sep 21 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
635 | TT_TASK | Issue Completed Working Drawings | Wed Jan 27 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
637 | TT_TASK | Layout of Barging Point - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
638 | TT_TASK | Layout of Barging Point - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
639 | TT_TASK | Layout of Barging Point - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
640 | TT_TASK | Layout of Barging Point - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
641 | TT_TASK | Loading Ramps - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
642 | TT_TASK | Loading Ramps - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
643 | TT_TASK | Loading Ramps - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
644 | TT_TASK | Loading Ramps - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
645 | TT_TASK | Weighbridge - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
646 | TT_TASK | Weighbridge - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
647 | TT_TASK | Weighbridge - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
648 | TT_TASK | Weighbridge - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
652 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
653 | TT_TASK | Pre-drill and guide wall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
654 | TT_TASK | D-wall construction (1084m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
655 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
656 | TT_TASK | Wang Toi Shan Shan Tsuen Road diversion works | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 |  | COMPLETED
658 | TT_TASK | Excavate up to +10.5mPD (369m3) | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 |  | COMPLETED
659 | TT_TASK | Install Strut S0 +11.0mPD | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 |  | COMPLETED
660 | TT_TASK | Excavate up to +8.0mPD (1525m3) | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 |  | COMPLETED
661 | TT_TASK | Install Strut S1 +8.5mPD | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 |  | COMPLETED
662 | TT_TASK | Excavate up to +4.5mPD (2135m3) | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 |  | COMPLETED
663 | TT_TASK | Install Strut S2 +5.0mPD | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 |  | COMPLETED
664 | TT_TASK | Excavate up to +0.5mPD (2440m3) | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 |  | COMPLETED
665 | TT_TASK | Install Strut S3 +1.0mPD | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 |  | COMPLETED
666 | TT_TASK | Excavate up to -6.5mPD (4340m3) | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 |  | COMPLETED
667 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
668 | TT_TASK | Construction of temporary slab and entrance seal (622m3) | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
672 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 08 18:00:00 IST 2014 | Fri Dec 05 08:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
673 | TT_TASK | Erect external formwork (Base Slab) | Tue Dec 09 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 08 08:00:00 IST 2014 | Tue Dec 09 18:00:00 IST 2014 |  | COMPLETED
674 | TT_TASK | Rebar fixing (Base Slab) | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 18:00:00 IST 2014 | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
675 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Dec 15 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Mon Dec 15 18:00:00 IST 2014 |  | COMPLETED
676 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Dec 17 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Tue Dec 16 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 |  | COMPLETED
677 | TT_TASK | Curing (Base Slab) | Thu Dec 18 08:00:00 IST 2014 | Sat Dec 27 18:00:00 IST 2014 | Wed Dec 17 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
678 | TT_TASK | Removal of formwork (Base Slab) | Fri Dec 19 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 24 18:00:00 IST 2014 |  | COMPLETED
679 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
680 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 | Mon Jun 22 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 |  | COMPLETED
681 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Jun 13 08:00:00 IDT 2015 | Mon Jun 15 18:00:00 IDT 2015 | Thu Jun 25 01:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
682 | TT_TASK | Concreting (Wall & Roof) (444m3) | Tue Jun 16 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
683 | TT_TASK | Curing (Wall & Roof) | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
684 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 |  | COMPLETED
685 | TT_TASK | Removal external formwork (Wall) | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
686 | TT_TASK | Side walkway and cable bracket (360m3) | Sat Jul 18 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Sat Jul 18 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
687 | TT_TASK | Access opening to DC (DC access period) | Tue Oct 06 08:00:00 IDT 2015 | Fri Mar 04 18:00:00 IST 2016 | Tue Oct 06 08:00:00 IDT 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
688 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Sat Dec 12 08:00:00 IST 2015 | Mon Jan 18 18:00:00 IST 2016 | Tue Nov 03 00:00:00 IST 2015 | Mon Nov 30 18:00:00 IST 2015 |  | COMPLETED
690 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 | Tue Apr 12 08:00:00 IDT 2016 | Wed Apr 13 18:00:00 IDT 2016 |  | COMPLETED
691 | TT_TASK | Erect external formwork (Base Slab) | Mon May 23 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Thu Apr 14 08:00:00 IDT 2016 | Fri Apr 15 18:00:00 IDT 2016 |  | COMPLETED
692 | TT_TASK | Rebar fixing (Base Slab) | Wed May 25 08:00:00 IDT 2016 | Fri May 27 18:00:00 IDT 2016 | Sat Apr 16 08:00:00 IDT 2016 | Tue Apr 19 18:00:00 IDT 2016 |  | COMPLETED
693 | TT_TASK | Erect internal kicker formwork (Base Slab) | Sat May 28 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 | Wed Apr 20 08:00:00 IDT 2016 | Thu Apr 21 18:00:00 IDT 2016 |  | COMPLETED
694 | TT_TASK | Concreting (Base Slab) (225m3) | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 | Fri Apr 22 08:00:00 IDT 2016 | Fri Apr 22 18:00:00 IDT 2016 |  | COMPLETED
695 | TT_TASK | Curing (Base Slab) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 08 18:00:00 IDT 2016 | Sat Apr 23 08:00:00 IDT 2016 | Fri Apr 29 18:00:00 IDT 2016 |  | COMPLETED
696 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Sat Apr 30 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
697 | TT_TASK | Removal of formwork (Base Slab) | Tue May 24 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Mon May 09 08:00:00 IDT 2016 | Tue May 10 18:00:00 IDT 2016 |  | COMPLETED
698 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed May 25 08:00:00 IDT 2016 | Sat May 28 18:00:00 IDT 2016 | Wed May 11 08:00:00 IDT 2016 | Mon May 16 18:00:00 IDT 2016 |  | COMPLETED
699 | TT_TASK | Rebar fixing (Wall & Roof) | Mon May 30 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 17 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 |  | COMPLETED
700 | TT_TASK | Erect external formwork (Wall & Roof) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 03 18:00:00 IDT 2016 | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 |  | COMPLETED
701 | TT_TASK | Concreting (Wall & Roof) (444m3) | Sat Jun 04 08:00:00 IDT 2016 | Sat Jun 04 18:00:00 IDT 2016 | Mon May 23 08:00:00 IDT 2016 | Mon May 23 18:00:00 IDT 2016 |  | COMPLETED
702 | TT_TASK | Curing (Wall & Roof) | Mon Jun 06 08:00:00 IDT 2016 | Tue Jun 14 18:00:00 IDT 2016 | Tue May 24 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 |  | COMPLETED
703 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 15 08:00:00 IDT 2016 | Wed Jun 15 18:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 |  | COMPLETED
704 | TT_TASK | Removal external formwork (Wall) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
705 | TT_TASK | Side walkway and cable bracket (102m3) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 |  | COMPLETED
706 | TT_TASK | Access opening to DC (DC access period) | Sat Jun 18 08:00:00 IDT 2016 | Thu Jul 14 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
707 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Fri Jul 15 08:00:00 IDT 2016 | Wed Aug 17 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
709 | TT_TASK | Backfilling between tunnels (2000m3) | Thu Sep 01 08:00:00 IDT 2016 | Sat Sep 17 18:00:00 IDT 2016 | Tue Sep 13 08:00:00 IDT 2016 | Fri Sep 30 18:00:00 IDT 2016 |  | COMPLETED
710 | TT_TASK | Remove Strut S2 | Mon Oct 03 08:00:00 IDT 2016 | Wed Oct 05 18:00:00 IDT 2016 | Mon Oct 03 08:00:00 IDT 2016 | Tue Oct 11 18:00:00 IDT 2016 |  | COMPLETED
711 | TT_TASK | Backfilling up top S1 Soffit | Thu Oct 06 08:00:00 IDT 2016 | Fri Oct 21 18:00:00 IDT 2016 | Fri Oct 28 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
712 | TT_TASK | Remove Strut S1 | Sat Oct 22 08:00:00 IDT 2016 | Mon Oct 24 18:00:00 IDT 2016 | Tue Oct 11 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
713 | TT_TASK | Backfilling up top S0 Soffit | Mon Nov 07 08:00:00 IST 2016 | Sat Nov 12 18:00:00 IST 2016 | Tue Nov 01 08:00:00 IST 2016 | Sat Nov 05 18:00:00 IST 2016 |  | COMPLETED
714 | TT_TASK | Remove Strut S0 | Mon Nov 14 08:00:00 IST 2016 | Tue Nov 15 18:00:00 IST 2016 | Mon Nov 07 08:00:00 IST 2016 | Tue Nov 08 18:00:00 IST 2016 |  | COMPLETED
715 | TT_TASK | Backfilling up to ground level | Wed Nov 16 08:00:00 IST 2016 | Fri Nov 18 18:00:00 IST 2016 | Wed Nov 09 08:00:00 IST 2016 | Fri Nov 11 18:00:00 IST 2016 |  | COMPLETED
719 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
720 | TT_TASK | Pre-drilling and guidewall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
721 | TT_TASK | D-wall construction (1451m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
722 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 |  | COMPLETED
724 | TT_TASK | Excavate from ground level to formation level -5.5mPD (4559m3) | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 |  | COMPLETED
725 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 |  | COMPLETED
726 | TT_TASK | Placing of blinding layer (South Bound) | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 |  | COMPLETED
727 | TT_TASK | Placing of blinding layer (North Bound) | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
729 | TT_TASK | Construction of Bay 2 to Bay 7a (3565m3) | Mon Jun 04 08:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 | Mon Jun 04 18:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 |  | COMPLETED
730 | TT_TASK | Side walkway and cable bracket (Southbound) | Fri Oct 02 08:00:00 IDT 2015 | Fri Nov 06 18:00:00 IST 2015 | Fri Oct 02 08:00:00 IDT 2015 | Sat Oct 31 18:00:00 IST 2015 |  | COMPLETED
731 | TT_TASK | Side walkway and cable bracket (Northbound) | Tue May 03 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 |  | COMPLETED
733 | TT_TASK | Backfilling (1344m3) | Wed Nov 07 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 | Wed Nov 07 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
736 | TT_TASK | Scheme Design, Mobilization, Site set up & Material delivery and Instrumentations | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
737 | TT_TASK | Downstream pipe pile wall construction (45 nos.) and grout curtain (45 nos.) | Mon Nov 12 08:00:00 IST 2012 | Fri Jan 25 18:00:00 IST 2013 | Mon Nov 12 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
738 | TT_TASK | Curtain Grout for cut slope (120 nos.) | Fri Jul 26 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
739 | TT_TASK | Drilling for ground improvement only (if require) | Mon Dec 10 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
740 | TT_TASK | If settlement reach the AAA alarm & action level TAM grouting will apply during excavation | Thu Apr 11 08:00:00 IDT 2013 | Thu May 16 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
741 | TT_TASK | Erection of temporary working platform for Up stream and Installation of Instrumentation System | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
742 | TT_TASK | Upstream pipe pile wall construction adjacent to WTSSTR, (17nos.) | Thu Dec 27 08:00:00 IST 2012 | Mon Jan 28 18:00:00 IST 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
743 | TT_TASK | Upstream pipe pile wall construction at Kam Tin River, 15m depth, 42nos. 1drill rig) | Tue Jan 29 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
744 | TT_TASK | Excavation and soil nail installation | Tue Apr 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
745 | TT_TASK | Excavation for rock and blinding layer | Sat Aug 24 08:00:00 IDT 2013 | Sat Sep 28 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
750 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
751 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
752 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
753 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
754 | TT_TASK | Concreting (164m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
755 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
756 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
757 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
758 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
759 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
760 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
761 | TT_TASK | Concreting (242m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
762 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
763 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
764 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
765 | TT_TASK | Removal internal falsework and formwork for roof | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
766 | TT_TASK | Side walkway and cable bracket (19m3) | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
770 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
771 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
772 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
773 | TT_TASK | Erect internal kicker formwork | Thu Nov 28 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 09 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
774 | TT_TASK | Concreting (121m3) | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
775 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
776 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
777 | TT_TASK | Removal of formwork | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
778 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
779 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
780 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
781 | TT_TASK | Concreting (121m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
782 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
783 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
784 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
785 | TT_TASK | Removal internal falsework and formwork for roof | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
786 | TT_TASK | Side walkway and cable bracket (38m3) | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
788 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
789 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
790 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
791 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
792 | TT_TASK | Concreting (240m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
793 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
794 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
795 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
796 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
797 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
798 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
799 | TT_TASK | Concreting (240m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
800 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
801 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
802 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
803 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
804 | TT_TASK | Side walkway and cable bracket | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
806 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
807 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
808 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
809 | TT_TASK | Concreting (222m3) | Wed Nov 06 08:00:00 IST 2013 | Wed Nov 06 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
810 | TT_TASK | Curing | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
811 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
812 | TT_TASK | Removal of formwork | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
815 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
816 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
817 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
818 | TT_TASK | Erect internal kicker formwork | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
819 | TT_TASK | Concreting (111m3) | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
820 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
821 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
822 | TT_TASK | Removal of formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
823 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
824 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
825 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
826 | TT_TASK | Concreting (220m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
827 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
828 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
829 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
830 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
831 | TT_TASK | Side walkway and cable bracket (38m3) | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 |  | COMPLETED
833 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
834 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
835 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
836 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
837 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
838 | TT_TASK | Curing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
839 | TT_TASK | Preparation of construction joint for base slab | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
840 | TT_TASK | Removal of formwork | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
841 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
842 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
843 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
844 | TT_TASK | Concreting (327m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
845 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
846 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
847 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
848 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
849 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
851 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 20 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
852 | TT_TASK | Rebar fixing | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
853 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 08:00:00 IDT 2013 |  | COMPLETED
854 | TT_TASK | Concreting (225m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
855 | TT_TASK | Curing | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
856 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
857 | TT_TASK | Removal of formwork | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
860 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 27 08:00:00 IST 2013 | Wed Nov 27 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
861 | TT_TASK | Erect external formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
862 | TT_TASK | Rebar fixing | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
863 | TT_TASK | Erect internal kicker formwork | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
864 | TT_TASK | Concreting (222m3) | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
865 | TT_TASK | Curing | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Mon Oct 28 18:00:00 IST 2013 |  | COMPLETED
866 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
867 | TT_TASK | Removal of formwork | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
868 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
869 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
870 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
871 | TT_TASK | Concreting (222m3) | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 |  | COMPLETED
872 | TT_TASK | Curing | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 07 18:00:00 IST 2014 |  | COMPLETED
873 | TT_TASK | Preparation of construction joint for wall and roof | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
874 | TT_TASK | Removal external and internal formwork for wall | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
875 | TT_TASK | Removal internal falsework and formwork for roof | Mon Feb 10 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
876 | TT_TASK | Side walkway and cable bracket (38m3) | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 |  | COMPLETED
878 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
879 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
880 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
881 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
882 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
883 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
884 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
885 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
886 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
887 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
888 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
889 | TT_TASK | Concreting (222m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
890 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
892 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
893 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
894 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
896 | TT_TASK | Placing of waterproof member T-lock & testing | Mon Nov 18 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
897 | TT_TASK | Rebar fixing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Wed Oct 23 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
898 | TT_TASK | Erect external formwork | Fri Nov 22 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
899 | TT_TASK | Concreting (222m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
900 | TT_TASK | Curing | Tue Nov 26 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
901 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
902 | TT_TASK | Removal of formwork | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
905 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
906 | TT_TASK | Erect external formwork | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
907 | TT_TASK | Rebar fixing | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
908 | TT_TASK | Erect internal kicker formwork | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
909 | TT_TASK | Concreting (330m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
910 | TT_TASK | Curing | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
911 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
912 | TT_TASK | Removal of formwork | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
913 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
914 | TT_TASK | Rebar fixing | Wed Nov 20 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
915 | TT_TASK | Erect external formwork | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
916 | TT_TASK | Concreting (330m3) | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
917 | TT_TASK | Curing | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
918 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
919 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
920 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
921 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
923 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
924 | TT_TASK | Erect external formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
925 | TT_TASK | Rebar fixing | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
926 | TT_TASK | Erect internal kicker formwork | Wed Dec 04 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
927 | TT_TASK | Concreting (240m3) | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
928 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
929 | TT_TASK | Preparation of construction joint for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
930 | TT_TASK | Removal of formwork | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
931 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
932 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
933 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
934 | TT_TASK | Concreting (240m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
935 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
936 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
937 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
938 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
939 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
941 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
942 | TT_TASK | Rebar fixing | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
943 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
944 | TT_TASK | Concreting (240m3) | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
945 | TT_TASK | Curing | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
946 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
947 | TT_TASK | Removal of formwork | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
950 | TT_TASK | Placing of waterproof member T-lock & testing | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
951 | TT_TASK | Erect external formwork | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
952 | TT_TASK | Rebar fixing | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
953 | TT_TASK | Erect internal kicker formwork | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
954 | TT_TASK | Concreting (200m3) | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
955 | TT_TASK | Curing | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
956 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
957 | TT_TASK | Removal of formwork | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
958 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 29 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
959 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
960 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
961 | TT_TASK | Concreting (200m3) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
962 | TT_TASK | Curing | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
963 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
964 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 13 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
965 | TT_TASK | Removal internal falsework and formwork for roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
966 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 |  | COMPLETED
968 | TT_TASK | Placing of waterproof member T-lock & testing | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
969 | TT_TASK | Erect external formwork | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
970 | TT_TASK | Rebar fixing | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
971 | TT_TASK | Erect internal kicker formwork | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
972 | TT_TASK | Concreting (220m3) | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
973 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
974 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
975 | TT_TASK | Removal of formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
976 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
977 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
978 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
979 | TT_TASK | Concreting (220m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
980 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
981 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
982 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
983 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
984 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
986 | TT_TASK | Placing of waterproof member T-lock & testing | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
987 | TT_TASK | Rebar fixing | Mon Nov 25 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
988 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
989 | TT_TASK | Concreting (222m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
990 | TT_TASK | Curing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
991 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
992 | TT_TASK | Removal of formwork | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
994 | TT_TASK | Removal of Temporary Nullah | Sat Mar 01 08:00:00 IST 2014 | Sat Jun 21 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
995 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (5218m3) | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 |  | COMPLETED
996 | TT_TASK | Reinstate the permenant Retaining wall of Nullah | Sat Mar 01 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Tue Mar 04 08:00:00 IST 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
997 | TT_TASK | Reinstate Nullah Base of original route | Tue Feb 25 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Tue Feb 25 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
998 | TT_TASK | Reinstate Nullah to original route | Sat Mar 29 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Sat Mar 29 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
999 | TT_TASK | Construction & connect East Box Culvert from Box 6B to KTR | Mon Apr 14 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Mon Feb 10 08:00:00 IST 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
1000 | TT_TASK | Reinstatement of Wang Toi Shan Shan Tsuen Road | Tue Dec 01 08:00:00 IST 2015 | Wed Jul 13 18:00:00 IDT 2016 | Tue Dec 01 08:00:00 IST 2015 | Mon Jul 18 18:00:00 IDT 2016 |  | COMPLETED
1003 | TT_TASK | Pre-drilling at Works Area 4.4 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
1004 | TT_TASK | Site Setup and guide wall | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1005 | TT_TASK | D-wall construction (3104m3) | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 |  | COMPLETED
1006 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
1008 | TT_TASK | Excavate up to +8.0mPD (775m3) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1009 | TT_TASK | Install Strut S1 +8.5mPD | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 |  | COMPLETED
1010 | TT_TASK | Excavate up to +4.5mPD (2713m3) | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 |  | COMPLETED
1011 | TT_TASK | Install Strut S2 +5.0mPD | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
1012 | TT_TASK | Excavate up to +0.5mPD (3100m3) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 |  | COMPLETED
1013 | TT_TASK | Install Strut S3 +1.0mPD | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1014 | TT_TASK | Excavate up to -3.0mPD (2713m3) | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1015 | TT_TASK | Install Strut S4 -2.5mPD | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 |  | COMPLETED
1016 | TT_TASK | Excavate up to -5.5mPD (4952m3) | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1017 | TT_TASK | Placing of blinding layer | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1021 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1022 | TT_TASK | Erect external formwork for base slab | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1023 | TT_TASK | Rebar fixing for base slab | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1024 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 26 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1025 | TT_TASK | Concreting for base slab (350m3) | Thu Jun 27 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1026 | TT_TASK | Curing for base slab | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1027 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1028 | TT_TASK | Removal of formwork for base slab | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1029 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1030 | TT_TASK | Removal strut S4 and S3 | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1032 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1033 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1034 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1035 | TT_TASK | Concreting for wall and roof (489m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1036 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1037 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1038 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1039 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1040 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1043 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1044 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1045 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1046 | TT_TASK | Curing for wall and roof | Sat Jun 22 08:00:00 IDT 2013 | Mon Jul 01 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1047 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1048 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1050 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Tue Dec 17 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1053 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1054 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1055 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1056 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1057 | TT_TASK | Concreting for base slab (350m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1058 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1059 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1060 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1061 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1062 | TT_TASK | Removal strut S4 and S3 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1064 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1065 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1066 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1067 | TT_TASK | Concreting for wall and roof (489m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1068 | TT_TASK | Curing for wall and roof | Wed Jun 12 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1069 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1070 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 14 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1071 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1072 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Feb 13 08:00:00 IST 2014 | Tue Feb 18 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1074 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1075 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1076 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1077 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1078 | TT_TASK | Curing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1079 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1080 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1081 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1082 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 16 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1084 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (2343m3) | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1085 | TT_TASK | Placing 0.5m thk concrete lateral support (+3.96mPD) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1086 | TT_TASK | Removal strut S2 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 23 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1088 | TT_TASK | Construction of Temporary Culvert (open channel) | Tue Jun 25 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1089 | TT_TASK | Temporary box culvert (At Box 6B Area) Saw Cut D-wall | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 |  | COMPLETED
1090 | TT_TASK | Erect 3m high block wall | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 |  | COMPLETED
1091 | TT_TASK | Connection to East Box Culvert (823B portion) | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 |  | COMPLETED
1092 | TT_TASK | Blinding | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
1093 | TT_TASK | Temporary box culvert (Outside Box 6B Area) Sheet piling | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 |  | COMPLETED
1094 | TT_TASK | ELS Works | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
1095 | TT_TASK | Blinding | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
1096 | TT_TASK | Removal of Temporary Culvert and Reinstatement | Fri May 16 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
1098 | TT_TASK | Reinstatement of TOA's | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 |  |  | IN_PROGRESS
1099 | TT_TASK | Hydroseeding works | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 | Wed Nov 30 18:00:00 IST 2016 |  | COMPLETED
1100 | TT_TASK | Tree Planting works | Thu Sep 01 08:00:00 IDT 2016 | Sat Dec 03 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
1101 | TT_TASK | Woodland Shrub Mix | Thu Sep 01 08:00:00 IDT 2016 | Fri Nov 18 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  | 200.0 | IN_PROGRESS
1104 | TT_TASK | Kam Tin River Diversion (Stage 1-3) | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1106 | TT_TASK | Concrete fill up to +8.0mPD near side A mass concrete wall | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 |  | COMPLETED
1107 | TT_TASK | Construction of mass concrete wall to +8.0mPD at side A (4 bay CH A80~A120) | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1108 | TT_TASK | Construction of base slab lining and low flow channel (4 bay A9~A10, B8~B9; LFC CH 80~110) | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1109 | TT_TASK | Construction of mass concrete wall to +8.0mPD of side B (3 bay CH B60~B90) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1110 | TT_TASK | Construction of T-shaped retaining wall (1 Bay CH B50~B60) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1111 | TT_TASK | Soil backfill at side A from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1112 | TT_TASK | Concrete backfill at side B from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1113 | TT_TASK | Removal strut at +8.5mPD near side A | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1114 | TT_TASK | Concrete fill up to +11.0mPD near side A mass concrete wall | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1115 | TT_TASK | Placing concrete block at side A from +8.0mPD to +11.0mpd at side A (4 bay CH A80~A120) | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1116 | TT_TASK | Soil backfill at side A from +8.0mPD to +11.0mPD | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1117 | TT_TASK | Removal strut at +8.5mPD near side B | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1118 | TT_TASK | Placing concrete block at side B from +8.0mPD to +11.0mPD (4 bay CH B60~B90) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1119 | TT_TASK | Concrete backfill at side B from +8.0mPD to +11.0mPD | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1121 | TT_TASK | Placing temporary concrete block to Up stream at CH30 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 |  | COMPLETED
1122 | TT_TASK | Placing temporary concrete block to Up stream at CH160 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1123 | TT_TASK | Excavation from GL to FL +5.0mPD Up stream (Low flow channel CH 30~60) | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1124 | TT_TASK | Excavation from GL to FL +5.0mPD Down stream (Low flow channel CH 130~160) | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1125 | TT_TASK | Construction of T-shaped retaining wall at Up stream of side B (2 Bay CH B30~B50) | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1126 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (3 bay CH B90~B120) | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1127 | TT_TASK | Construction of Up stream base slab lining and low flow channel (6 Bay A1~A4, B3~B4; Low flow channel CH 30~50) | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1128 | TT_TASK | Construction of Down stream base slab lining and low flow channel (5 Bay A14~A16, B14~B15; LFC CH 140~170) | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1129 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Up stream and saw cut D-wall | Fri Jun 14 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1130 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Down stream and saw cut D-wall | Wed Jun 19 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1131 | TT_TASK | Construction of remaining Up stream base slab lining and low flow channel (7 bay A5~A8, B5~B7; LFC CH 50~80) | Thu Jun 27 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1132 | TT_TASK | Construction of remaining Down stream base slab lining and low flow channel (7 bay A11~A13, B10~B13; LFC CH 110~140) | Wed Jul 03 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1134 | TT_TASK | Relocation of temporary concrete block at Up stream for construction of mass concrete wall at side B | Sat Jul 20 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1135 | TT_TASK | Relocation of temporary concrete block at Down stream for construction of mass concrete wall at side B | Tue Jul 23 08:00:00 IDT 2013 | Wed Jul 24 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1136 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Up stream of side B (3 bay CH B0~B30) | Tue Jul 23 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1137 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (4 bay CH B0~B30) | Thu Jul 25 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1141 | TT_TASK | Application of power supply, environmental permits and construction substation | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1142 | TT_TASK | Procurement and Confirmation of the order of 1st tunnel boring machine | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 |  | COMPLETED
1143 | TT_TASK | Prepare on-demand bond or bank guarantee for the procurement of TBM and submit to Engineer for approval | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 |  | COMPLETED
1144 | TT_TASK | TBM design and submission for approval | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
1145 | TT_TASK | TBM materials order and delivery to factory | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 |  | COMPLETED
1146 | TT_TASK | TBM equipments order and delivery to factory | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 |  | COMPLETED
1147 | TT_TASK | TBM Fabrication | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
1148 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 |  | COMPLETED
1149 | TT_TASK | TBM test Run | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 |  | COMPLETED
1150 | TT_TASK | TBM disassembly and packing for shipping to HK | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 |  | COMPLETED
1151 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
1152 | TT_TASK | Ground treatment for TBM lanching shaft | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 |  | COMPLETED
1153 | TT_TASK | Ground treatment for Cross Passage Tunnel | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1154 | TT_TASK | Box7A Setup TBM facilities, install noise enclosure and CNP application | Fri Jun 01 08:00:00 IDT 2012 | Sat Jan 26 18:00:00 IST 2013 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1155 | TT_TASK | Notice to Contract 824 the anticipated dates of break out TBM Shaft | Sat Jun 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1156 | TT_TASK | Fabrication of tunnel segment mould | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
1157 | TT_TASK | Fabrication 50% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1158 | TT_TASK | Fabrication 100% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
1159 | TT_TASK | Fabrication 30% of North Tunnel North Bound (Uptrack) Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1160 | TT_TASK | Fabrication 60% of North Tunnel North Bound (Uptrack) Precast Lining | Thu Oct 18 08:00:00 IST 2012 | Thu Feb 21 18:00:00 IST 2013 | Thu Oct 18 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1161 | TT_TASK | Fabrication 100% of North Tunnel North Bound (Uptrack) Precast Lining | Mon Aug 19 08:00:00 IDT 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Dec 03 08:00:00 IST 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1163 | TT_TASK | Assemble, T&C of TBM | Fri Jun 01 08:00:00 IDT 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Oct 16 00:00:00 IST 2012 |  | COMPLETED
1164 | TT_TASK | TBM drive & lining installation CH123+369 to CH123+283 Initial Drive (86m) | Sat Nov 03 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 | Wed Oct 17 00:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1165 | TT_TASK | Change Plant (Back-up cars) | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1166 | TT_TASK | TBM drive & lining installation CH123+283 to CH123+183 | Thu Jun 27 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1167 | TT_TASK | TBM drive & lining installation CH123+183 to CH123+083 | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1168 | TT_TASK | TBM drive & lining installation CH123+083 to CH122+983 | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1169 | TT_TASK | TBM drive & lining installation CH122+983 to CH122+883 | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1170 | TT_TASK | TBM drive & lining installation CH122+883 to CH122+783 | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Jun 13 08:00:00 IDT 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
1171 | TT_TASK | TBM drive & lining installation CH122+783 to CH122+683 | Sat Nov 02 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1172 | TT_TASK | TBM drive & lining installation CH122+683 to CH122+583 | Tue Dec 03 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Wed Feb 26 18:00:00 IST 2014 |  | COMPLETED
1173 | TT_TASK | TBM drive & lining installation CH122+583 to CH122+491 | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Feb 27 08:00:00 IST 2014 | Sat Aug 16 00:00:00 IDT 2014 |  | COMPLETED
1174 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1175 | TT_TASK | Dis-assemble TBM | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
1176 | TT_TASK | Invert slab, side walkway | Sat Oct 04 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 | Mon Sep 15 08:00:00 IDT 2014 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1177 | TT_TASK | Installation of cable bracket | Tue Dec 30 08:00:00 IST 2014 | Tue Jan 13 18:00:00 IST 2015 | Fri Sep 12 08:00:00 IDT 2014 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
1178 | TT_TASK | Provision of assess open for DC and modify of strut S1 and S2 at north bound | Tue Nov 04 11:12:00 IST 2014 | Thu Dec 04 11:12:00 IST 2014 | Wed Oct 01 08:00:00 IDT 2014 | Sat Oct 18 18:00:00 IDT 2014 |  | COMPLETED
1180 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Oct 06 13:00:00 IDT 2014 | Mon Oct 20 12:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
1181 | TT_TASK | Assemble, T&C of TBM | Mon Nov 03 08:00:00 IST 2014 | Fri Jan 02 18:00:00 IST 2015 | Sat Oct 04 08:00:00 IDT 2014 | Fri Nov 28 18:00:00 IST 2014 |  | COMPLETED
1182 | TT_TASK | Setup back-up plant for final drive | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
1183 | TT_TASK | Reinstate of noise enclosure | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Sat Nov 29 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1184 | TT_TASK | TBM drive & lining installation CH123+384 to CH123+284 (Initial Drive) | Sat Dec 06 08:00:00 IST 2014 | Thu Jan 22 18:00:00 IST 2015 | Tue Dec 02 00:00:00 IST 2014 | Tue Jan 20 18:00:00 IST 2015 |  | COMPLETED
1185 | TT_TASK | TBM drive & lining installation CH123+184 to CH123+084 | Wed Jan 21 08:00:00 IST 2015 | Wed Jan 28 18:00:00 IST 2015 | Wed Jan 21 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 |  | COMPLETED
1186 | TT_TASK | TBM drive & lining installation CH123+084 to CH122+984 | Wed Feb 04 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 | Thu Feb 12 08:00:00 IST 2015 | Thu Feb 26 18:00:00 IST 2015 |  | COMPLETED
1187 | TT_TASK | TBM drive & lining installation CH122+984 to CH122+884 | Thu Feb 12 08:00:00 IST 2015 | Tue Feb 24 18:00:00 IST 2015 | Fri Feb 27 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1188 | TT_TASK | TBM drive & lining installation CH122+884 to CH122+784 | Tue Mar 10 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Wed May 27 18:00:00 IDT 2015 |  | COMPLETED
1189 | TT_TASK | TBM drive & lining installation CH122+784 to CH122+684 | Wed May 06 08:00:00 IDT 2015 | Thu May 14 18:00:00 IDT 2015 | Thu May 28 08:00:00 IDT 2015 | Sat Jul 11 18:00:00 IDT 2015 |  | COMPLETED
1190 | TT_TASK | TBM drive & lining installation CH122+684 to CH122+584 | Fri Jul 03 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
1191 | TT_TASK | TBM drive & lining installation CH122+584 to CH122+506 | Tue Nov 03 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 |  | COMPLETED
1192 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 |  | COMPLETED
1193 | TT_TASK | Dis-assemble TBM | Wed Dec 16 08:00:00 IST 2015 | Fri Jan 22 18:00:00 IST 2016 | Sun Dec 13 08:00:00 IST 2015 | Sun Mar 13 18:00:00 IST 2016 |  | COMPLETED
1194 | TT_TASK | Invert slab, side walkway | Fri Apr 01 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 | Mon Mar 14 08:00:00 IST 2016 | Tue May 24 18:00:00 IDT 2016 |  | COMPLETED
1195 | TT_TASK | Installation of cable bracket | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Mar 15 18:00:00 IST 2016 |  | COMPLETED
1196 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Mon Feb 01 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 22 18:00:00 IST 2016 |  | COMPLETED
1199 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 1 (From Downtrack to Centre of CP) | Thu Apr 10 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Sat Jun 28 18:00:00 IDT 2014 |  | COMPLETED
1200 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Sun Nov 09 18:00:00 IST 2014 |  | COMPLETED
1201 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1202 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 18:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1203 | TT_TASK | Excavation 0-4mts with Shotcrete | Mon Feb 02 08:00:00 IST 2015 | Tue Feb 17 18:00:00 IST 2015 | Mon Feb 23 08:00:00 IST 2015 | Mon Mar 30 18:00:00 IDT 2015 |  | COMPLETED
1204 | TT_TASK | Invert Concrete | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1205 | TT_TASK | Wall and Roof concrete | Thu Apr 16 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 |  | COMPLETED
1206 | TT_TASK | Dismantle Temporary frame | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 |  | COMPLETED
1207 | TT_TASK | Install Door to Cross Passage (By contract 827) | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 |  | COMPLETED
1208 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 2 (From Centre of CP to Uptrack) | Sat Oct 17 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Sep 07 08:00:00 IDT 2015 | Tue Dec 01 18:00:00 IST 2015 |  | COMPLETED
1209 | TT_TASK | Probe/Grout | Thu Jun 25 08:00:00 IDT 2015 | Mon Jul 06 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Fri Apr 10 18:00:00 IDT 2015 |  | COMPLETED
1210 | TT_TASK | Coring of Segment | Tue Jul 07 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Sat Apr 11 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1211 | TT_TASK | Removal of segment | Sat Jul 11 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
1212 | TT_TASK | Excavation 0-4mts with Shotcrete | Wed Jul 15 08:00:00 IDT 2015 | Sat Jul 25 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1213 | TT_TASK | Invert Concrete | Sat Jul 18 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 | Thu May 07 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1214 | TT_TASK | Wall and Roof concrete | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1215 | TT_TASK | Dismantle Temporary frame | Tue Jan 19 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 04 18:00:00 IST 2016 |  | COMPLETED
1216 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Feb 22 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Fri Feb 05 08:00:00 IST 2016 | Sat Feb 06 18:00:00 IST 2016 |  | COMPLETED
1218 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 1 (From Downtrack to Centre of CP) | Tue Mar 11 08:00:00 IST 2014 | Wed Mar 26 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1219 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Wed Nov 12 18:00:00 IST 2014 |  | COMPLETED
1220 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Thu Nov 13 08:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1221 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Tue Nov 18 08:00:00 IST 2014 | Thu Nov 20 18:00:00 IST 2014 |  | COMPLETED
1222 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Sat Nov 22 08:00:00 IST 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1223 | TT_TASK | Invert Concrete | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
1224 | TT_TASK | Wall and Roof concrete | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1225 | TT_TASK | Dismantle Temporary frame | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1226 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1227 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 2 (From Centre of CP to Uptrack) | Thu May 21 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Mar 09 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1228 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Mon May 04 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1229 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
1230 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1231 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 22 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
1232 | TT_TASK | Invert Concrete | Sat Aug 08 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Wed Jul 08 18:00:00 IDT 2015 |  | COMPLETED
1233 | TT_TASK | Wall and Roof concrete | Tue Aug 25 08:00:00 IDT 2015 | Mon Sep 07 18:00:00 IDT 2015 | Thu Jul 09 08:00:00 IDT 2015 | Sat Aug 15 18:00:00 IDT 2015 |  | COMPLETED
1234 | TT_TASK | Dismantle Temporary frame | Tue Sep 22 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 | Mon Aug 17 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 |  | COMPLETED
1235 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1237 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 1 (From Downtrack to Centre of CP) | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Sat May 24 18:00:00 IDT 2014 |  | COMPLETED
1238 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
1239 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1240 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 |  | COMPLETED
1241 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Mon Nov 17 08:00:00 IST 2014 | Sat Nov 29 18:00:00 IST 2014 |  | COMPLETED
1242 | TT_TASK | Invert Concrete | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 |  | COMPLETED
1243 | TT_TASK | Wall and Roof concrete | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 |  | COMPLETED
1244 | TT_TASK | Dismantle Temporary frame | Tue Dec 30 08:00:00 IST 2014 | Wed Jan 07 18:00:00 IST 2015 | Tue Dec 30 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1245 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1246 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 2 (From Centre of CP to Uptrack) | Fri May 08 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 |  | COMPLETED
1247 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
1248 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
1249 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Thu May 07 18:00:00 IDT 2015 |  | COMPLETED
1250 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
1251 | TT_TASK | Invert Concrete | Wed Aug 05 08:00:00 IDT 2015 | Fri Aug 14 18:00:00 IDT 2015 | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
1252 | TT_TASK | Wall and Roof concrete | Tue Sep 15 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Wed Aug 26 18:00:00 IDT 2015 |  | COMPLETED
1253 | TT_TASK | Dismantle Temporary frame | Sat Oct 17 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Oct 08 18:00:00 IDT 2015 |  | COMPLETED
1254 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1258 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 |  | COMPLETED
1259 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1260 | TT_TASK | D-wall construction (1192m3) | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 |  | COMPLETED
1261 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1262 | TT_TASK | Construct capping beam, cobble, etc. (including bay 6 and 5) | Sat Oct 27 08:00:00 IST 2012 | Sat Feb 16 18:00:00 IST 2013 | Sat Oct 27 08:00:00 IST 2012 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1264 | TT_TASK | Excavate up to +22.0mPD (1860m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1265 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 |  | COMPLETED
1266 | TT_TASK | Excavate up to +16.5mPD (3410m3) | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 |  | COMPLETED
1267 | TT_TASK | Install Strut S2 +17.0mPD | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 |  | COMPLETED
1268 | TT_TASK | Excavate up to +11.0mPD (3410m3) | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 |  | COMPLETED
1269 | TT_TASK | Install Strut S3 +11.5mPD | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 |  | COMPLETED
1270 | TT_TASK | Excavate up to +7.0mPD (2480m3) | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 |  | COMPLETED
1271 | TT_TASK | Install Strut S4 +7.5mPD | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1272 | TT_TASK | Excavate up to +3.5mPD (2170m3) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 |  | COMPLETED
1273 | TT_TASK | Install Strut S5 +4.0mPD | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1274 | TT_TASK | Excavate up to formation (2294m3) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1275 | TT_TASK | Construct temp. 500mm thick plain concrete base slab | Thu Oct 18 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 |  | COMPLETED
1276 | TT_TASK | Removal of South Bound strut to +9.50mPD | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1277 | TT_TASK | Removal of North Bound strut to +9.50mPD | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 |  | COMPLETED
1278 | TT_TASK | Construct temp. 500mm thick TBM concrete base slab | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1279 | TT_TASK | Construction entrance seal for TBM at South Bound | Mon Nov 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1280 | TT_TASK | Construction entrance seal for TBM at North Bound | Sat Jul 20 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1281 | TT_TASK | Saw cut South Bound diaphragm wall | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1282 | TT_TASK | Saw cut North Bound diaphragm wall | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1286 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 05 18:00:00 IDT 2014 | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 |  | COMPLETED
1287 | TT_TASK | Erect external formwork (Base Slab) | Sat Sep 06 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 21 18:00:00 IDT 2014 |  | COMPLETED
1288 | TT_TASK | Rebar fixing (Base Slab) | Wed Sep 10 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Tue Jul 22 08:00:00 IDT 2014 | Sat Jul 26 18:00:00 IDT 2014 |  | COMPLETED
1289 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Sep 15 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Sun Jul 27 08:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1290 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Thu Aug 14 18:00:00 IDT 2014 |  | COMPLETED
1291 | TT_TASK | Concreting (Base Slab) (225m3) | Sat Aug 09 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Fri Aug 15 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
1292 | TT_TASK | Curing (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
1293 | TT_TASK | Removal of formwork (Base Slab) | Tue Aug 12 08:00:00 IDT 2014 | Tue Aug 12 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1294 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed Aug 13 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Mon Sep 15 18:00:00 IDT 2014 |  | COMPLETED
1295 | TT_TASK | Rebar fixing (Wall & Roof) | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 |  | COMPLETED
1296 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 |  | COMPLETED
1297 | TT_TASK | Clearing and inspection (Wall & Roof) | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
1298 | TT_TASK | Concreting (Wall & Roof) (450m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
1299 | TT_TASK | Curing (Wall & Roof) | Sat Oct 11 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
1300 | TT_TASK | Removal external formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1301 | TT_TASK | Removal internal falsework (Wall & Roof) | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 |  | COMPLETED
1302 | TT_TASK | Side walkway and cable bracket (102m3) | Sat Oct 18 08:00:00 IDT 2014 | Wed Oct 29 18:00:00 IST 2014 | Mon Sep 01 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1304 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Wed Nov 11 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Oct 19 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1305 | TT_TASK | Erect external formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 |  | COMPLETED
1306 | TT_TASK | Rebar fixing (Base Slab) | Mon Nov 16 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Tue Oct 27 08:00:00 IST 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1307 | TT_TASK | Erect internal kicker formwork (Base Slab) | Fri Nov 20 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Oct 31 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 |  | COMPLETED
1308 | TT_TASK | Clearing and inspection (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
1309 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1310 | TT_TASK | Curing (Base Slab) | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 |  | COMPLETED
1311 | TT_TASK | Removal of formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 |  | COMPLETED
1312 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
1313 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Dec 09 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
1314 | TT_TASK | Erect external formwork (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Thu Jan 07 18:00:00 IST 2016 |  | COMPLETED
1315 | TT_TASK | Clearing and inspection (Wall & Roof) | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Fri Jan 08 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
1316 | TT_TASK | Concreting (Wall & Roof) (450m3) | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
1317 | TT_TASK | Curing (Wall & Roof) | Tue Jan 12 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
1318 | TT_TASK | Removal external formwork (Wall ) | Thu Jan 14 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
1319 | TT_TASK | Removal internal falsework, formwork and reproping (Wall & Roof) | Thu Jan 28 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 |  | COMPLETED
1320 | TT_TASK | Side walkway and cable bracket (102m3) | Wed Dec 23 08:00:00 IST 2015 | Wed Jan 06 18:00:00 IST 2016 | Wed Nov 11 08:00:00 IST 2015 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
1322 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 |  | COMPLETED
1323 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 |  | COMPLETED
1324 | TT_TASK | Backfilling to 0.5m below S3 (+11.0mPD) (3486m3) | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 |  | COMPLETED
1325 | TT_TASK | Removal strut S3 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
1326 | TT_TASK | Backfilling to 0.5m below S2 (+16.5mPD) (3410m3) | Wed Mar 16 08:00:00 IST 2016 | Fri Apr 08 18:00:00 IDT 2016 | Wed Mar 16 08:00:00 IST 2016 | Tue Apr 12 18:00:00 IDT 2016 |  | COMPLETED
1327 | TT_TASK | Removal strut S2 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 |  | COMPLETED
1328 | TT_TASK | Backfilling to 0.5m below S1 (+22.0mPD) (3410m3) | Fri Apr 15 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 | Fri Apr 15 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
1329 | TT_TASK | Removal strut S1 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 |  | COMPLETED
1330 | TT_TASK | Backfilling to original ground level (approx. +25.0mPD) (1860m3) | Thu May 05 08:00:00 IDT 2016 | Tue May 17 18:00:00 IDT 2016 | Thu May 05 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
1333 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1334 | TT_TASK | D-wall construction (2844m3) | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1335 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1337 | TT_TASK | Excavate up to +22.0mPD (3720m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1338 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 |  | COMPLETED
1339 | TT_TASK | Excavate up to +16.5mPD (4880m3) | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 |  | COMPLETED
1340 | TT_TASK | Install Strut S2 +17.0mPD | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 |  | COMPLETED
1341 | TT_TASK | Excavate up to +11.0mPD (6820m3) | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
1342 | TT_TASK | Install Strut S3 +11.5mPD | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 |  | COMPLETED
1343 | TT_TASK | Excavate up to +7.0mPD (4960m3) | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 |  | COMPLETED
1344 | TT_TASK | Install Strut S4 +7.5mPD | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1345 | TT_TASK | Excavate up to +3.5mPD (4340m3) | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1346 | TT_TASK | Install Strut S5 +4.0mPD | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 |  | COMPLETED
1347 | TT_TASK | Excavate up to formation (4960m3) | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 |  | COMPLETED
1348 | TT_TASK | Construct temp. 500mm thick plain concrete base slab at Bay 5 & 6 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1349 | TT_TASK | Excavation to formation and place blinding Bay 4a | Thu Oct 18 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1350 | TT_TASK | Excavation to formation and place blinding Bay 4b | Fri Jun 21 08:00:00 IDT 2013 | Fri Jul 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1351 | TT_TASK | Excavation to formation and place blinding Bay3 | Sat Jul 13 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1352 | TT_TASK | Excavation to formation and place blinding Bay2 to Bay1 | Wed Jul 24 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1356 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 |  | COMPLETED
1357 | TT_TASK | Erect external formwork for base slab | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 |  | COMPLETED
1358 | TT_TASK | Rebar fixing for base slab | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1359 | TT_TASK | Erect internal kicker formwork for base slab | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1360 | TT_TASK | Concreting for base slab (363m3) | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1361 | TT_TASK | Curing for base slab | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1362 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1363 | TT_TASK | Removal of formwork for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1364 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1365 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 27 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1366 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1367 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1368 | TT_TASK | Curing for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1369 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1370 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 10 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1371 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 19 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jan 24 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1372 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 08 08:00:00 IST 2015 | Tue Jan 13 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1374 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 |  | COMPLETED
1375 | TT_TASK | Erect external formwork for base slab | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1376 | TT_TASK | Rebar fixing for base slab | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1377 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 |  | COMPLETED
1378 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1379 | TT_TASK | Curing for base slab | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1380 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1381 | TT_TASK | Removal of formwork for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1382 | TT_TASK | Rebar fixing for central slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1383 | TT_TASK | Erect external formwork for central slab | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1384 | TT_TASK | Concreting for central slab (450m3) | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1385 | TT_TASK | Curing for central slab | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1386 | TT_TASK | Preparation of construction joint for central slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1387 | TT_TASK | Removal of formwork for central slab | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1388 | TT_TASK | Removal strut S5 and S4 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1389 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1390 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1391 | TT_TASK | Erect external formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1392 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1393 | TT_TASK | Curing for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1394 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1395 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 08 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1396 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1397 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Nov 19 08:00:00 IST 2015 | Tue Nov 24 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 |  | COMPLETED
1400 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1401 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1402 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1403 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1404 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1405 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1406 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1407 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1408 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1409 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1410 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 10 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1411 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1412 | TT_TASK | Curing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1413 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1414 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1415 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1416 | TT_TASK | Side walkway and cable bracket | Fri Jan 02 08:00:00 IST 2015 | Wed Jan 07 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1418 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1419 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1420 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1421 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1422 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1423 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1424 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1425 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1426 | TT_TASK | Rebar fixing for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1427 | TT_TASK | Erect external formwork for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1428 | TT_TASK | Concreting for central slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1429 | TT_TASK | Curing for central slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1430 | TT_TASK | Preparation of construction joint for central slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1431 | TT_TASK | Removal of formwork for central slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 21 18:00:00 IST 2012 |  | COMPLETED
1432 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1433 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1434 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1435 | TT_TASK | Erect external formwork for wall | Mon Jul 15 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1436 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1437 | TT_TASK | Curing for wall and roof | Sun Jul 21 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1438 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1439 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 22 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1440 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 31 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1441 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Sep 16 08:00:00 IDT 2015 | Mon Sep 21 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1443 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1444 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1445 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1446 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1447 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1448 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1449 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1450 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1451 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1452 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1453 | TT_TASK | Erect external formwork for wall | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1454 | TT_TASK | Concreting for wall and roof (444m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1455 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1456 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1457 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Sat Feb 09 18:00:00 IST 2013 |  | COMPLETED
1458 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Nov 09 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Tue Oct 06 08:00:00 IDT 2015 | Sat Oct 10 18:00:00 IDT 2015 |  | COMPLETED
1461 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1462 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1463 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1464 | TT_TASK | Erect internal kicker formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1465 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1466 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1467 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1468 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1469 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1470 | TT_TASK | Curing | Wed Jun 12 08:00:00 IDT 2013 | Wed Jun 12 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1471 | TT_TASK | Removal strut S5 and S4 | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1473 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1474 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1475 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1476 | TT_TASK | Concreting for wall and roof (450m3) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1477 | TT_TASK | Curing for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1478 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1479 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1480 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 29 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1481 | TT_TASK | Side walkway and cable bracket | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1483 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1484 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1485 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1486 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1487 | TT_TASK | Curing for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1488 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1489 | TT_TASK | Removal external wall formwork for wall | Wed Jun 26 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1490 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1491 | TT_TASK | Side walkway and cable bracket | Fri Sep 04 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
1494 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1495 | TT_TASK | Erect external formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1496 | TT_TASK | Rebar fixing for base slab | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1497 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1498 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 |  | COMPLETED
1499 | TT_TASK | Curing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1500 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1501 | TT_TASK | Removal of formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1502 | TT_TASK | Shear beam | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1503 | TT_TASK | Curing | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1504 | TT_TASK | Removal strut S5 and S4 | Wed Jun 19 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1506 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 24 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1507 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1508 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1509 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1510 | TT_TASK | Curing for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1511 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1512 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1513 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1514 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
1516 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1517 | TT_TASK | Rebar fixing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1518 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1519 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1520 | TT_TASK | Curing for wall and roof | Sun Jun 23 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1521 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1522 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 25 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1523 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 03 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1524 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Aug 29 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1527 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1528 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Sat Dec 22 18:00:00 IST 2012 |  | COMPLETED
1529 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1530 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1531 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1532 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1533 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1534 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Fri Jan 11 18:00:00 IST 2013 |  | COMPLETED
1535 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Jan 12 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1536 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1537 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1539 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1540 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1541 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1542 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1543 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1544 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1545 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1546 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1547 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 |  | COMPLETED
1549 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1550 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Mon Feb 25 18:00:00 IST 2013 |  | COMPLETED
1551 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1552 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1553 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1554 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1555 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1556 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1557 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Aug 24 08:00:00 IDT 2015 | Fri Aug 28 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1560 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1561 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1562 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1563 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1564 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1565 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1566 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1567 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1568 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1569 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1570 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1572 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1573 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1574 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1575 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1576 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1577 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1578 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1579 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1580 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
1582 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1583 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1584 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1585 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1586 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1587 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1588 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1589 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1590 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Aug 18 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1593 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1594 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1595 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1596 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1597 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1598 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1599 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1600 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1601 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1602 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1603 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1605 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 31 18:00:00 IDT 2013 |  | COMPLETED
1606 | TT_TASK | Rebar fixing for wall and roof | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 |  | COMPLETED
1607 | TT_TASK | Erect external formwork for wall and roof | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 | Fri Sep 06 08:00:00 IDT 2013 | Thu Sep 12 18:00:00 IDT 2013 |  | COMPLETED
1608 | TT_TASK | Concreting for wall and roof (450m3) | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 |  | COMPLETED
1609 | TT_TASK | Curing for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1610 | TT_TASK | Preparation of construction joint for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1611 | TT_TASK | Removal external and internal formwork for wall | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Wed Sep 25 18:00:00 IDT 2013 |  | COMPLETED
1612 | TT_TASK | Removal internal falsework and formwork for roof | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1613 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 08 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1615 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 20 18:00:00 IST 2013 |  | COMPLETED
1616 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1617 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1618 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1619 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1620 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1621 | TT_TASK | Removal external wall formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1622 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1623 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Aug 12 08:00:00 IDT 2015 | Mon Aug 17 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1626 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1627 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1628 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Feb 14 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1629 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1630 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Mon Feb 18 18:00:00 IST 2013 |  | COMPLETED
1631 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1632 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1633 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1634 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1635 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1636 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1638 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jul 12 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1639 | TT_TASK | Rebar fixing for wall and roof | Wed Jul 17 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1640 | TT_TASK | Erect external formwork for wall and roof | Wed Aug 14 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1641 | TT_TASK | Concreting for wall and roof (450m3) | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1642 | TT_TASK | Curing for wall and roof | Sun Aug 11 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1643 | TT_TASK | Preparation of construction joint for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1644 | TT_TASK | Removal external and internal formwork for wall | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1645 | TT_TASK | Removal internal falsework and formwork for roof | Wed Aug 21 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1646 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 03 08:00:00 IST 2014 | Fri Mar 07 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1648 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1649 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1650 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Apr 09 08:00:00 IDT 2013 | Thu Apr 11 18:00:00 IDT 2013 |  | COMPLETED
1651 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1652 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1653 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1654 | TT_TASK | Removal external wall formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1655 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
1656 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Aug 06 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Mon Jul 27 08:00:00 IDT 2015 | Fri Jul 31 18:00:00 IDT 2015 |  | COMPLETED
1658 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Sep 12 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1659 | TT_TASK | Rebar fixing for roof | Tue Sep 17 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1660 | TT_TASK | Erect external formwork for roof | Thu Sep 19 08:00:00 IDT 2013 | Thu Sep 19 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1661 | TT_TASK | Concreting for roof (444m3) | Sat Sep 21 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1662 | TT_TASK | Curing for roof | Sun Sep 22 08:00:00 IDT 2013 | Tue Oct 01 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1663 | TT_TASK | Preparation of construction joint for roof | Mon Sep 23 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1664 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1665 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1668 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1669 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1670 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1671 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1672 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1673 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1674 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1675 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1676 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1677 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1678 | TT_TASK | Removal strut S5 and S4 | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1680 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Thu Apr 25 18:00:00 IDT 2013 |  | COMPLETED
1681 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri May 03 08:00:00 IDT 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
1682 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Thu May 16 08:00:00 IDT 2013 | Thu May 23 18:00:00 IDT 2013 |  | COMPLETED
1683 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1684 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1685 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1686 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Wed May 29 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1687 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1688 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 19 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1690 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Fri Apr 19 18:00:00 IDT 2013 |  | COMPLETED
1691 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1692 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Apr 25 08:00:00 IDT 2013 | Sat Apr 27 18:00:00 IDT 2013 |  | COMPLETED
1693 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1694 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1695 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1696 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1697 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1698 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 02 08:00:00 IDT 2015 | Sat Apr 11 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Feb 27 18:00:00 IST 2015 |  | COMPLETED
1700 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1701 | TT_TASK | Rebar fixing for roof | Tue Aug 06 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1702 | TT_TASK | Erect external formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1703 | TT_TASK | Concreting for roof (444m3) | Fri Aug 09 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 |  | COMPLETED
1704 | TT_TASK | Curing for roof | Thu Aug 01 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1705 | TT_TASK | Preparation of construction joint for roof | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 |  | COMPLETED
1706 | TT_TASK | Removal internal falsework and formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1707 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 09 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1710 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Wed Feb 20 18:00:00 IST 2013 |  | COMPLETED
1711 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1712 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1713 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1714 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1715 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1716 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1717 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1718 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1719 | TT_TASK | Curing | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1720 | TT_TASK | Removal strut S5 and S4 | Mon Jun 24 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1722 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1723 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1724 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Wed Jul 10 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1725 | TT_TASK | Concreting for wall and roof (450m3) | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1726 | TT_TASK | Curing for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1727 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1728 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 |  | COMPLETED
1729 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 |  | COMPLETED
1730 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1732 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1733 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1734 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1735 | TT_TASK | Concreting for wall and roof (450m3) | Tue Sep 03 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1736 | TT_TASK | Curing for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1737 | TT_TASK | Preparation of construction joint for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 |  | COMPLETED
1738 | TT_TASK | Removal external and internal formwork for wall | Thu Sep 05 08:00:00 IDT 2013 | Fri Sep 06 18:00:00 IDT 2013 | Thu Aug 22 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1739 | TT_TASK | Removal internal falsework and formwork for roof | Sat Sep 14 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 |  | COMPLETED
1740 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 05 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1742 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1743 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1744 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1745 | TT_TASK | Concreting for roof (363m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1746 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Sun Oct 20 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1747 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1748 | TT_TASK | Removal internal falsework and formwork for roof | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1749 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Dec 24 13:00:00 IST 2013 | Thu Jan 02 12:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1752 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1753 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1754 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1755 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Apr 12 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1756 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1757 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1758 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1759 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1760 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1761 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1762 | TT_TASK | Removal strut S5 and S4 | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1764 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Aug 05 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1765 | TT_TASK | Rebar fixing for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1766 | TT_TASK | Erect external formwork for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1767 | TT_TASK | Concreting for wall and roof (450m3) | Thu Aug 15 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1768 | TT_TASK | Curing for wall and roof | Fri Aug 16 08:00:00 IDT 2013 | Sun Aug 25 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1769 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1770 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1771 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 |  | COMPLETED
1772 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Feb 04 08:00:00 IST 2014 | Sat Feb 08 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1774 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Aug 07 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1775 | TT_TASK | Rebar fixing for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1776 | TT_TASK | Erect external formwork for wall and roof | Thu Aug 15 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1777 | TT_TASK | Concreting for wall and roof (450m3) | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1778 | TT_TASK | Curing for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1779 | TT_TASK | Preparation of construction joint for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 |  | COMPLETED
1780 | TT_TASK | Removal external and internal formwork for wall | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Wed Aug 21 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 |  | COMPLETED
1781 | TT_TASK | Removal internal falsework and formwork for roof | Mon Sep 16 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1782 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Nov 19 08:00:00 IST 2014 | Mon Nov 24 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1784 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1785 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1786 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1787 | TT_TASK | Concreting for roof (450m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1788 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1789 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1790 | TT_TASK | Removal internal falsework and formwork for roof | Fri Oct 18 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1791 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 13 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1794 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1795 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1796 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1797 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1798 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 28 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1799 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1800 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1801 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1802 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1803 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1804 | TT_TASK | Removal strut S5 and S4 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1806 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1807 | TT_TASK | Rebar fixing for wall and roof | Sat Jul 20 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1808 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1809 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1810 | TT_TASK | Curing for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1811 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1812 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 29 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1813 | TT_TASK | Removal internal falsework and formwork for roof | Tue Aug 06 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1814 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 18:00:00 IST 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1816 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1817 | TT_TASK | Rebar fixing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1818 | TT_TASK | Erect external formwork for wall and roof | Fri Jul 19 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1819 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1820 | TT_TASK | Curing for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Thu Mar 28 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1821 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Mar 29 08:00:00 IDT 2013 | Fri Mar 29 18:00:00 IDT 2013 |  | COMPLETED
1822 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Sat Mar 30 08:00:00 IDT 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1823 | TT_TASK | Removal internal falsework and formwork for roof | Fri Aug 02 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Mon Apr 01 18:00:00 IDT 2013 |  | COMPLETED
1824 | TT_TASK | Side walkway and cable bracket | Thu Nov 13 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1826 | TT_TASK | Erect internal formwork & Falsework for roof | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1827 | TT_TASK | Rebar fixing for roof | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 |  | COMPLETED
1828 | TT_TASK | Erect shutter formwork for roof | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 09 18:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1829 | TT_TASK | Concreting for roof (450m3) | Tue Sep 10 08:00:00 IDT 2013 | Tue Sep 10 18:00:00 IDT 2013 | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 |  | COMPLETED
1830 | TT_TASK | Curing for roof | Wed Sep 11 08:00:00 IDT 2013 | Fri Sep 20 18:00:00 IDT 2013 | Tue Jul 23 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 |  | COMPLETED
1831 | TT_TASK | Preparation of construction joint for roof | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 11 18:00:00 IDT 2013 | Sat Aug 03 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1832 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 26 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 |  | COMPLETED
1833 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 06 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Aug 13 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1835 | TT_TASK | Water proofing and soil backfilling to 0.5m below top of Tunnel Bay 3 to Bay 1 | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1836 | TT_TASK | Mass infill between D-wall and tunnel wall | Fri Oct 11 08:00:00 IDT 2013 | Wed Oct 16 18:00:00 IDT 2013 | Fri Sep 20 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1837 | TT_TASK | Removal S3 and S2 | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
1838 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 4 | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Sat May 18 18:00:00 IDT 2013 |  | COMPLETED
1839 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 5 and remove S3 & S2 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1840 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 6 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1843 | TT_TASK | Pre-drilling and guidewall | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1844 | TT_TASK | D-wall design review | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1845 | TT_TASK | D-wall construction (4741m3) | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 |  | COMPLETED
1846 | TT_TASK | Shear pin and pumping test | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 15 18:00:00 IST 2012 | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1848 | TT_TASK | ELS works to formation level from SN16 to SN19 (soil: 8,700m3 @350m3/day, Install S1 to S3 strut 5 days/layer) | Wed Sep 25 08:00:00 IDT 2013 | Wed Nov 13 18:00:00 IST 2013 | Wed May 08 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1849 | TT_TASK | Design temporary bridge and approval | Mon Sep 01 08:00:00 IDT 2014 | Wed Nov 12 18:00:00 IST 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1850 | TT_TASK | Application of tree transplant | Sat Jun 01 08:00:00 IDT 2013 | Wed Oct 23 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1851 | TT_TASK | Tree transplant | Tue Oct 14 08:00:00 IDT 2014 | Mon Nov 10 18:00:00 IST 2014 | Tue Sep 02 08:00:00 IDT 2014 | Tue Sep 30 18:00:00 IDT 2014 |  | COMPLETED
1852 | TT_TASK | Erection temporary bridge deck | Fri Oct 03 08:00:00 IDT 2014 | Fri Dec 05 18:00:00 IST 2014 | Fri Oct 03 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1853 | TT_TASK | ELS works to formation level from SN10 to SN15 (soil: 9,455m3 @330m3/day, install S1 to S3 strut 5 days/layer) | Mon Nov 24 08:00:00 IST 2014 | Sat Jan 17 18:00:00 IST 2015 | Mon Nov 24 08:00:00 IST 2014 | Tue Jun 23 18:00:00 IDT 2015 |  | COMPLETED
1856 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
1857 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1858 | TT_TASK | Erect external formwork for wall and roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1859 | TT_TASK | Concreting for wall and roof (215m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
1860 | TT_TASK | Curing for wall and roof | Sun Dec 08 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
1861 | TT_TASK | Preparation of construction joint for wall and roof | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1862 | TT_TASK | Removal external and internal formwork for wall | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1863 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1864 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 03 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 | Mon Mar 24 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
1866 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 14 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1867 | TT_TASK | Rebar fixing for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1868 | TT_TASK | Erect external formwork for wall and roof | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1869 | TT_TASK | Concreting for wall and roof (215m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1870 | TT_TASK | Curing for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Sun Dec 29 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1871 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
1872 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 17 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
1873 | TT_TASK | Removal internal falsework and formwork for roof | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1874 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 |  | COMPLETED
1876 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 28 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Nov 28 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1877 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1878 | TT_TASK | Erect external formwork for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1879 | TT_TASK | Concreting for wall and roof (215m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1880 | TT_TASK | Curing for wall and roof | Wed Jan 01 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
1881 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
1882 | TT_TASK | Removal external and internal formwork for wall | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 |  | COMPLETED
1883 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
1884 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 |  | COMPLETED
1886 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1887 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 14 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1888 | TT_TASK | Erect external formwork for wall and roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1889 | TT_TASK | Concreting for wall and roof (215m3) | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1890 | TT_TASK | Curing for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1892 | TT_TASK | Removal external and internal formwork for wall | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1893 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1894 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 |  | COMPLETED
1896 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 08:00:00 IST 2013 |  | COMPLETED
1897 | TT_TASK | Rebar fixing for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1898 | TT_TASK | Erect external formwork for wall and roof | Fri Jan 03 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1899 | TT_TASK | Concreting for wall and roof (215m3) | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1900 | TT_TASK | Curing for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 16 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1901 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Tue Jan 07 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1902 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1903 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1904 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 |  | COMPLETED
1906 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1907 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1908 | TT_TASK | Erect external formwork for wall and roof | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1909 | TT_TASK | Concreting for wall and roof (215m3) | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1910 | TT_TASK | Curing for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1911 | TT_TASK | Preparation of construction joint for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1912 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1913 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1914 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 |  | COMPLETED
1916 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1917 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 |  | COMPLETED
1918 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Tue Jun 04 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 |  | COMPLETED
1919 | TT_TASK | Concreting for wall and roof (333m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1920 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1921 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Wed Jun 12 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1922 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 |  | COMPLETED
1923 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
1924 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 05 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Tue Mar 04 18:00:00 IST 2014 |  | COMPLETED
1926 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1927 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1928 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1929 | TT_TASK | Concreting for wall and roof (412m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1930 | TT_TASK | Curing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Sun Jun 23 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Sat Mar 23 18:00:00 IST 2013 |  | COMPLETED
1931 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Mar 25 08:00:00 IST 2013 | Mon Mar 25 18:00:00 IST 2013 |  | COMPLETED
1932 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Mar 26 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1933 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jun 24 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1934 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 27 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Mon Mar 03 18:00:00 IST 2014 |  | COMPLETED
1936 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1937 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1938 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Apr 02 18:00:00 IDT 2013 |  | COMPLETED
1939 | TT_TASK | Concreting for wall and roof (320m3) | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Apr 05 08:00:00 IDT 2013 | Fri Apr 05 18:00:00 IDT 2013 |  | COMPLETED
1940 | TT_TASK | Curing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 06 08:00:00 IDT 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1941 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1942 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1943 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1944 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jan 21 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Sat Mar 01 18:00:00 IST 2014 |  | COMPLETED
1946 | TT_TASK | Excavation and saw cut D-wall | Thu Apr 02 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Sat Jul 25 18:00:00 IDT 2015 |  | COMPLETED
1947 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Aug 08 16:24:00 IDT 2015 | Mon Aug 10 16:24:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Mon Jul 13 18:00:00 IDT 2015 |  | COMPLETED
1948 | TT_TASK | Erect external formwork for base slab | Mon Aug 10 16:24:00 IDT 2015 | Wed Aug 12 16:24:00 IDT 2015 | Tue Jul 14 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
1949 | TT_TASK | Rebar fixing for base slab | Wed Aug 12 16:24:00 IDT 2015 | Fri Aug 14 16:24:00 IDT 2015 | Wed Jul 15 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1950 | TT_TASK | Erect internal kicker formwork for base slab | Fri Aug 14 16:24:00 IDT 2015 | Mon Aug 17 16:24:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Wed Aug 12 18:00:00 IDT 2015 |  | COMPLETED
1951 | TT_TASK | Concreting for base slab (90m3) | Wed Sep 02 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 | Thu Aug 13 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 |  | COMPLETED
1952 | TT_TASK | Curing for base slab | Thu Sep 03 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Fri Aug 14 08:00:00 IDT 2015 | Thu Aug 20 18:00:00 IDT 2015 |  | COMPLETED
1953 | TT_TASK | Preparation of construction joint for base slab | Thu Sep 03 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Fri Aug 21 08:00:00 IDT 2015 | Fri Aug 21 18:00:00 IDT 2015 |  | COMPLETED
1954 | TT_TASK | Removal of formwork for base slab | Fri Sep 04 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Sat Aug 22 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 |  | COMPLETED
1955 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Sep 05 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 | Mon Aug 24 08:00:00 IDT 2015 | Mon Aug 24 18:00:00 IDT 2015 |  | COMPLETED
1956 | TT_TASK | Curing | Thu Sep 10 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Tue Aug 25 08:00:00 IDT 2015 | Tue Aug 25 18:00:00 IDT 2015 |  | COMPLETED
1957 | TT_TASK | Removal strut S3 | Sat Sep 19 08:00:00 IDT 2015 | Wed Sep 23 18:00:00 IDT 2015 | Wed Sep 16 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
1958 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Sep 24 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
1959 | TT_TASK | Rebar fixing for wall and roof | Wed Sep 30 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 | Fri Sep 25 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 |  | COMPLETED
1960 | TT_TASK | Erect external formwork for wall and roof | Thu Oct 15 08:00:00 IDT 2015 | Fri Oct 16 18:00:00 IDT 2015 | Mon Oct 05 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
1961 | TT_TASK | Concreting for wall and roof (260m3) | Sat Oct 17 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 | Wed Oct 07 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1962 | TT_TASK | Curing for wall and roof | Sun Oct 18 08:00:00 IDT 2015 | Tue Oct 27 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 |  | COMPLETED
1963 | TT_TASK | Preparation of construction joint for wall and roof | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
1964 | TT_TASK | Removal external and internal formwork for wall | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
1965 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 28 08:00:00 IST 2015 | Thu Oct 29 18:00:00 IST 2015 | Thu Oct 22 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1966 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Oct 30 08:00:00 IST 2015 | Wed Nov 04 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1968 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 02 18:00:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 |  | COMPLETED
1969 | TT_TASK | Erect external formwork for base slab | Fri Jul 03 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Tue Jul 21 08:00:00 IDT 2015 | Wed Jul 22 18:00:00 IDT 2015 |  | COMPLETED
1970 | TT_TASK | Rebar fixing for base slab | Mon Jul 06 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 23 08:00:00 IDT 2015 | Fri Jul 24 18:00:00 IDT 2015 |  | COMPLETED
1971 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jul 08 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Sat Jul 25 08:00:00 IDT 2015 | Mon Jul 27 18:00:00 IDT 2015 |  | COMPLETED
1972 | TT_TASK | Concreting for base slab (123m3) | Fri Jul 10 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jul 28 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 |  | COMPLETED
1973 | TT_TASK | Curing for base slab | Sat Jul 11 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1974 | TT_TASK | Preparation of construction joint for base slab | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 |  | COMPLETED
1975 | TT_TASK | Removal of formwork for base slab | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 |  | COMPLETED
1976 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1977 | TT_TASK | Curing | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 |  | COMPLETED
1978 | TT_TASK | Removal strut S3 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1979 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 |  | COMPLETED
1980 | TT_TASK | Rebar fixing for wall and roof | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 |  | COMPLETED
1981 | TT_TASK | Erect external formwork for wall and roof | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 |  | COMPLETED
1982 | TT_TASK | Concreting for wall and roof (260m3) | Fri Oct 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 | Sat Oct 24 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
1983 | TT_TASK | Curing for wall and roof | Sat Oct 03 08:00:00 IDT 2015 | Mon Oct 12 18:00:00 IDT 2015 | Mon Oct 26 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1984 | TT_TASK | Preparation of construction joint for wall and roof | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
1985 | TT_TASK | Removal external and internal formwork for wall | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1986 | TT_TASK | Removal internal falsework and formwork for roof | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1987 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1989 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
1990 | TT_TASK | Erect external formwork for base slab | Mon Jun 15 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1991 | TT_TASK | Rebar fixing for base slab | Wed Jun 17 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
1992 | TT_TASK | Erect internal kicker formwork for base slab | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
1993 | TT_TASK | Concreting for base slab (127m3) | Tue Jun 23 08:00:00 IDT 2015 | Tue Jun 23 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
1994 | TT_TASK | Curing for base slab | Wed Jun 24 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
1995 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 24 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1996 | TT_TASK | Removal of formwork for base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
1997 | TT_TASK | Infill concrete in between D-wall and base slab | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1998 | TT_TASK | Curing | Thu May 28 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1999 | TT_TASK | Removal strut S3 | Fri May 29 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2000 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 03 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2001 | TT_TASK | Rebar fixing for wall and roof | Mon Jun 08 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2002 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2003 | TT_TASK | Concreting for wall and roof (260m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2004 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2005 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2006 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2007 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2008 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 11 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2010 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
2011 | TT_TASK | Erect external formwork for base slab | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
2012 | TT_TASK | Rebar fixing for base slab | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
2013 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
2014 | TT_TASK | Concreting for base slab (127m3) | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
2015 | TT_TASK | Curing for base slab | Thu Jun 11 08:00:00 IDT 2015 | Wed Jun 17 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2016 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 11 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
2017 | TT_TASK | Removal of formwork for base slab | Sat May 23 08:00:00 IDT 2015 | Sat May 23 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
2018 | TT_TASK | Infill concrete in between D-wall and base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
2019 | TT_TASK | Curing | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2020 | TT_TASK | Removal strut S3 | Thu May 28 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2021 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2022 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2023 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2024 | TT_TASK | Concreting for wall and roof (150m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2025 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2026 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2027 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2028 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2029 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jul 06 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
2031 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2032 | TT_TASK | Erect external formwork for base slab | Thu May 21 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2033 | TT_TASK | Rebar fixing for base slab | Sat May 23 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2034 | TT_TASK | Erect internal kicker formwork for base slab | Wed May 27 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2035 | TT_TASK | Concreting for base slab (70m3) | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2036 | TT_TASK | Curing for base slab | Sat May 30 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2037 | TT_TASK | Preparation of construction joint for base slab | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2038 | TT_TASK | Removal of formwork for base slab | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2039 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2040 | TT_TASK | Curing | Sat Jun 06 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2041 | TT_TASK | Removal strut S3 | Mon Jun 08 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat May 23 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2043 | TT_TASK | Rebar fixing for wall and roof | Fri May 29 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2044 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2045 | TT_TASK | Concreting for wall and roof (175m3) | Thu Jun 04 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2046 | TT_TASK | Curing for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sun Jun 14 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2047 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2048 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 03 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 04 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2050 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 29 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
2052 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2053 | TT_TASK | Erect external formwork for base slab | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2054 | TT_TASK | Rebar fixing for base slab | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2055 | TT_TASK | Erect internal kicker formwork for base slab | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2056 | TT_TASK | Concreting for base slab (70m3) | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2057 | TT_TASK | Curing for base slab | Wed Apr 22 08:00:00 IDT 2015 | Tue Apr 28 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2058 | TT_TASK | Preparation of construction joint for base slab | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2059 | TT_TASK | Removal of formwork for base slab | Thu Apr 23 08:00:00 IDT 2015 | Thu Apr 23 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2060 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Apr 24 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2061 | TT_TASK | Curing | Wed Apr 29 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2062 | TT_TASK | Removal strut S3 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2063 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed May 06 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2064 | TT_TASK | Rebar fixing for wall and roof | Thu May 14 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2065 | TT_TASK | Erect external formwork for wall and roof | Mon May 18 08:00:00 IDT 2015 | Tue May 19 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2066 | TT_TASK | Concreting for wall and roof (175m3) | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2067 | TT_TASK | Curing for wall and roof | Thu May 21 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2068 | TT_TASK | Preparation of construction joint for wall and roof | Thu May 21 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2069 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2070 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2071 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jun 23 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
2073 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Fri Nov 15 18:00:00 IST 2013 |  | COMPLETED
2074 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Nov 16 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2075 | TT_TASK | Rebar fixing for base slab | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
2076 | TT_TASK | Erect internal kicker formwork for base slab | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
2077 | TT_TASK | Concreting for base slab (70m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
2078 | TT_TASK | Curing for base slab | Fri Dec 20 08:00:00 IST 2013 | Thu Dec 26 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
2079 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 |  | COMPLETED
2080 | TT_TASK | Removal of formwork for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
2081 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
2082 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2083 | TT_TASK | Removal strut S3 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2084 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Apr 16 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2085 | TT_TASK | Rebar fixing for wall and roof | Thu Apr 24 08:00:00 IDT 2014 | Sat Apr 26 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 |  | COMPLETED
2086 | TT_TASK | Erect external formwork for wall and roof | Mon Apr 28 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Thu Apr 10 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2087 | TT_TASK | Concreting for wall and roof (170m3) | Wed Apr 30 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Sat Apr 12 08:00:00 IDT 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
2088 | TT_TASK | Curing for wall and roof | Thu May 01 08:00:00 IDT 2014 | Sat May 10 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Tue Apr 22 18:00:00 IDT 2014 |  | COMPLETED
2089 | TT_TASK | Preparation of construction joint for wall and roof | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 |  | COMPLETED
2090 | TT_TASK | Removal external and internal formwork for wall | Sat May 03 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Tue Apr 15 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
2091 | TT_TASK | Removal internal falsework and formwork for roof | Mon May 12 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 |  | COMPLETED
2092 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jun 05 08:00:00 IDT 2014 | Tue Jun 10 18:00:00 IDT 2014 | Thu May 29 08:00:00 IDT 2014 | Thu Dec 04 18:00:00 IST 2014 |  | COMPLETED
2094 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2095 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2096 | TT_TASK | Rebar fixing for base slab | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2097 | TT_TASK | Erect internal kicker formwork for base slab | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2098 | TT_TASK | Concreting for base slab (70m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2099 | TT_TASK | Curing for base slab | Sun Dec 08 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2100 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2101 | TT_TASK | Removal of formwork for base slab | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
2102 | TT_TASK | Infill concrete in between D-wall and base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
2103 | TT_TASK | Curing | Sun Dec 15 08:00:00 IST 2013 | Sun Dec 15 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2104 | TT_TASK | Removal strut S3 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2105 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Feb 12 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2106 | TT_TASK | Rebar fixing for wall and roof | Mon Feb 17 08:00:00 IST 2014 | Wed Feb 19 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
2107 | TT_TASK | Erect external formwork for wall and roof | Fri Feb 28 13:48:00 IST 2014 | Mon Mar 03 13:48:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2108 | TT_TASK | Concreting for wall and roof (200m3) | Mon Mar 03 13:48:00 IST 2014 | Tue Mar 04 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2109 | TT_TASK | Curing for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Fri Mar 14 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2110 | TT_TASK | Preparation of construction joint for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Wed Mar 05 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2111 | TT_TASK | Removal external and internal formwork for wall | Wed Mar 05 13:48:00 IST 2014 | Thu Mar 06 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
2112 | TT_TASK | Removal internal falsework and formwork for roof | Fri Mar 14 13:48:00 IST 2014 | Mon Mar 17 13:48:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2113 | TT_TASK | Side walkway and cable bracket (204m3) | Thu May 29 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Wed Dec 03 18:00:00 IST 2014 |  | COMPLETED
2115 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2116 | TT_TASK | Erect external formwork for base slab | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2117 | TT_TASK | Rebar fixing for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2118 | TT_TASK | Erect internal kicker formwork for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2119 | TT_TASK | Concreting for base slab (70m3) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2120 | TT_TASK | Curing for base slab | Tue Dec 03 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2121 | TT_TASK | Preparation of construction joint for base slab | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
2122 | TT_TASK | Removal of formwork for base slab | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2123 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2124 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2125 | TT_TASK | Removal strut S3 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
2126 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jan 25 08:00:00 IST 2014 | Wed Jan 29 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
2127 | TT_TASK | Rebar fixing for wall and roof | Thu Jan 30 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Fri Dec 20 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
2128 | TT_TASK | Erect external formwork for wall and roof | Thu Feb 20 08:00:00 IST 2014 | Fri Feb 21 18:00:00 IST 2014 | Thu Jan 09 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2129 | TT_TASK | Concreting for wall and roof (200m3) | Sat Feb 22 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2130 | TT_TASK | Curing for wall and roof | Sun Feb 23 08:00:00 IST 2014 | Tue Mar 04 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2131 | TT_TASK | Preparation of construction joint for wall and roof | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Tue Jan 14 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2132 | TT_TASK | Removal external and internal formwork for wall | Tue Feb 25 08:00:00 IST 2014 | Tue Feb 25 18:00:00 IST 2014 | Wed Jan 15 08:00:00 IST 2014 | Wed Jan 15 18:00:00 IST 2014 |  | COMPLETED
2133 | TT_TASK | Removal internal falsework and formwork for roof | Wed Mar 05 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2134 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
2137 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Sep 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
2138 | TT_TASK | Erect external formwork for base slab | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Sep 21 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
2139 | TT_TASK | Rebar fixing for base slab | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
2140 | TT_TASK | Erect internal kicker formwork for base slab | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
2141 | TT_TASK | Staircase construction (+12.0mPD to +14.706mPD) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2142 | TT_TASK | Concreting for base slab (30m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
2143 | TT_TASK | Curing for base slab | Fri Dec 13 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
2144 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
2145 | TT_TASK | Removal of formwork for base slab | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 18:00:00 IDT 2013 |  | COMPLETED
2146 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2147 | TT_TASK | Mass concrete at level +12.0mPD | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 |  | COMPLETED
2148 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2149 | TT_TASK | Removal strut S3 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2150 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 17 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Mon Dec 01 18:00:00 IST 2014 |  | COMPLETED
2152 | TT_TASK | Erect working platform to +21.0mPD | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2153 | TT_TASK | Rebar fixing for wall and roof | Sat Jan 11 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2154 | TT_TASK | Staircase construction (+14.706mPD to +16.956mPD) (20m3) | Fri May 02 08:00:00 IDT 2014 | Wed May 07 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2155 | TT_TASK | Staircase construction (+16.956mPD to +19.206mPD) (20m3) | Thu Jun 05 08:00:00 IDT 2014 | Mon Jun 09 18:00:00 IDT 2014 | Thu Jun 12 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2156 | TT_TASK | Staircase construction (+19.206mPD to +21.456mPD) (20m3) | Tue Jun 10 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Fri Jun 20 18:00:00 IDT 2014 |  | COMPLETED
2157 | TT_TASK | Erect external formwork for wall and roof | Sat Mar 15 08:00:00 IST 2014 | Mon Mar 17 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2158 | TT_TASK | Concreting for wall and roof (31m3) | Tue Feb 04 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2159 | TT_TASK | Curing for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 |  | COMPLETED
2160 | TT_TASK | Preparation of construction joint for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2161 | TT_TASK | Removal external and internal formwork for wall | Thu Feb 06 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2162 | TT_TASK | Removal internal falsework and formwork for roof | Sat Feb 15 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Thu Jan 23 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2164 | TT_TASK | Removal strut S2 @ SN 19 | Wed Apr 02 08:00:00 IDT 2014 | Mon Apr 07 18:00:00 IDT 2014 | Mon Mar 03 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 |  | COMPLETED
2165 | TT_TASK | Erect working platform to +24.0mPD | Tue Apr 08 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 | Fri Mar 07 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 |  | COMPLETED
2166 | TT_TASK | Erect internal formwork below strut S1 | Sat Apr 12 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 | Wed Mar 12 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 |  | COMPLETED
2167 | TT_TASK | Staircase construction (+21.456mPD to +23.706mPD) (20m3) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 |  | COMPLETED
2168 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 | Fri Mar 14 08:00:00 IST 2014 | Tue Apr 01 18:00:00 IDT 2014 |  | COMPLETED
2169 | TT_TASK | Erect external wall & internal wall formwork | Tue May 13 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Wed Apr 02 08:00:00 IDT 2014 | Thu Apr 03 18:00:00 IDT 2014 |  | COMPLETED
2170 | TT_TASK | Concreting (External Wall & Internal Wall) (264m3) | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Fri Apr 04 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2171 | TT_TASK | Curing (External Wall & Internal Wall) | Fri May 16 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2172 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Mon May 19 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Thu Apr 10 18:00:00 IDT 2014 |  | COMPLETED
2173 | TT_TASK | Waterproofing | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 |  | COMPLETED
2174 | TT_TASK | Backfilling | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2176 | TT_TASK | Removal strut S1 @ SN 19 | Thu Jun 19 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2177 | TT_TASK | Erect working platform to +30.406mPD | Tue Jun 24 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2178 | TT_TASK | Erect internal formwork | Sat Jun 28 08:00:00 IDT 2014 | Sat Jun 28 18:00:00 IDT 2014 | Wed Jun 04 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2179 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Mon Jun 30 08:00:00 IDT 2014 | Wed Jul 02 18:00:00 IDT 2014 | Thu Jun 05 08:00:00 IDT 2014 | Fri Jun 06 18:00:00 IDT 2014 |  | COMPLETED
2180 | TT_TASK | Erect external formwork (External Wall & Internal Wall) | Thu Jul 03 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2181 | TT_TASK | Concreting (External Wall & Internal Wall) (128m3) | Fri Jul 04 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2182 | TT_TASK | Curing (External Wall & Internal Wall) | Sat Jul 05 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 18:00:00 IDT 2014 |  | COMPLETED
2183 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Tue Jul 08 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2184 | TT_TASK | Waterproofing | Wed Jul 09 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Thu Jun 19 18:00:00 IDT 2014 |  | COMPLETED
2185 | TT_TASK | Backfilling | Sat Jul 12 08:00:00 IDT 2014 | Wed Jul 16 18:00:00 IDT 2014 | Fri Jun 20 08:00:00 IDT 2014 | Tue Jun 24 18:00:00 IDT 2014 |  | COMPLETED
2186 | TT_TASK | Erect falsework and soffit formwork +30.206mPD | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 | Wed Jun 25 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2187 | TT_TASK | Staircase construction (+21.456mPD to +25.956mPD) (20m3) | Sat Jul 19 08:00:00 IDT 2014 | Wed Jul 23 18:00:00 IDT 2014 | Fri Jun 27 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2188 | TT_TASK | Staircase construction (+25.956mPD to +27.606mPD) (20m3) | Sat Jul 05 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 05 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 |  | COMPLETED
2189 | TT_TASK | Rebar fixing (Beam, Floor Slab and Staircase) | Thu Jul 10 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Thu Jul 10 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2190 | TT_TASK | Concreting (Beam, Floor Slab and Staircase) (31m3) | Fri Jul 11 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2191 | TT_TASK | Curing (Beam, Floor Slab and Staircase) | Wed Sep 03 08:00:00 IDT 2014 | Tue Sep 09 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2193 | TT_TASK | Erect working platform to +33.576mPD | Wed Sep 03 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
2194 | TT_TASK | Erect external formwork (External Wall) | Mon Sep 08 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 | Fri Sep 26 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2195 | TT_TASK | Rebar fixing (External Wall) | Thu Sep 11 08:00:00 IDT 2014 | Fri Sep 12 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2196 | TT_TASK | Erect internal formwork (External Wall) | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 |  | COMPLETED
2197 | TT_TASK | Concreting (External Wall) (49m3) | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 |  | COMPLETED
2198 | TT_TASK | Curing (External Wall) | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 |  | COMPLETED
2199 | TT_TASK | Removal formwork (External Wall) | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
2200 | TT_TASK | Erect falsework and soffit formwork +32.656 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2201 | TT_TASK | Rebar fixing (Beam & Floor Slab) | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 |  | COMPLETED
2202 | TT_TASK | Concreting (Beam & Floor Slab) (31m3) | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 |  | COMPLETED
2203 | TT_TASK | Curing (Beam & Floor Slab) | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2205 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
2206 | TT_TASK | Rebar fixing (Roof Parapet Wall) | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 |  | COMPLETED
2207 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2208 | TT_TASK | Concreting (Roof Parapet Wall) (30m3) | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
2209 | TT_TASK | Curing (Roof Parapet Wall) | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 |  | COMPLETED
2210 | TT_TASK | Removal formwork (Roof Parapet Wall) | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2211 | TT_TASK | Removal of falsework and soffit formwork | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
2213 | TT_TASK | Wet trade work | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 |  | COMPLETED
2214 | TT_TASK | Metal works (Louver, Door, Cat-ladder, Architectural Fins, Handrail, Roof Sliding Hatch and Balustrade, etc) | Thu Nov 27 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Thu Nov 27 08:00:00 IST 2014 | Thu Mar 05 18:00:00 IST 2015 |  | COMPLETED
2215 | TT_TASK | Coat works | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2218 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Nov 29 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Feb 04 18:00:00 IST 2014 |  | COMPLETED
2219 | TT_TASK | Backfilling between D-wall and 0.5m below S1 14,240m3 soil | Thu Feb 06 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 | Wed Feb 05 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 |  | COMPLETED
2220 | TT_TASK | Removal of S1 | Wed Mar 12 08:00:00 IST 2014 | Tue Mar 25 18:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 |  | COMPLETED
2221 | TT_TASK | Backfilling to original ground level 21,390m3 (approx. +25.0mPD) | Sat Mar 01 08:00:00 IST 2014 | Wed Mar 19 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Sat May 03 18:00:00 IDT 2014 |  | COMPLETED
2223 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 |  | COMPLETED
2224 | TT_TASK | Backfilling between D-wall and 0.5m below S1 (2075m3) | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 |  | COMPLETED
2225 | TT_TASK | Removal of S1 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 |  | COMPLETED
2226 | TT_TASK | Backfilling to original ground level 3,900m3 (approx. +25.0mPD) (1353m3) | Sat Mar 01 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
2227 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
2228 | TT_TASK | Backfilling backfilling to +20mPD from SN8 to SN9 (Soil: 7,050m3 @ 500m3/day) | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 |  | COMPLETED
2229 | TT_TASK | Removal of S1 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
2230 | TT_TASK | Construction of mud pit | Sat Jul 06 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
2231 | TT_TASK | Backfilling from +20mPD to ground level from SN8 to SN9 (Soil: 5,000m3 @ 500m3/day) | Tue Aug 06 08:00:00 IDT 2013 | Sat Aug 17 18:00:00 IDT 2013 | Tue Jul 02 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 |  | COMPLETED
2233 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Aug 07 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2234 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) | Fri Aug 14 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2235 | TT_TASK | Placing mass concrete infill between tunnel and D-wall | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 02 18:00:00 IST 2015 | Thu Dec 24 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2236 | TT_TASK | Removal of S2 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 10 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 04 18:00:00 IST 2016 |  | COMPLETED
2237 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2238 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
2239 | TT_TASK | Removal strut S1 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2240 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
2241 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488 m3 of soil) | Mon Jan 25 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Fri Apr 01 18:00:00 IDT 2016 |  | COMPLETED
2243 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) (SN18-19) | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 |  | COMPLETED
2244 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) (SN18-19) | Sat Apr 26 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Sat Apr 26 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
2245 | TT_TASK | Placing mass concrete infill between tunnel and D-wall (SN18-19) | Tue May 20 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri May 16 18:00:00 IDT 2014 |  | COMPLETED
2246 | TT_TASK | Removal of S2 (SN16-18) | Wed Jun 04 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 |  | COMPLETED
2247 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) (SN16-18) | Mon Jun 09 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Tue May 27 18:00:00 IDT 2014 |  | COMPLETED
2248 | TT_TASK | Removal strut S1 (SN16-18) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Wed May 28 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
2249 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488m3 of soil) | Fri Jun 27 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
2251 | TT_TASK | Dismantling temporary bridge deck | Mon Jun 15 08:00:00 IDT 2015 | Tue Jul 21 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2252 | TT_TASK | Reinstatement of Works Area 4.10 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jan 11 18:00:00 IST 2017 | Mon May 02 08:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 |  | COMPLETED
2253 | TT_TASK | Complete all tree planting and reinstate Works Area 4.12C | Tue Nov 01 08:00:00 IST 2016 | Thu Jul 13 18:00:00 IDT 2017 | Sat Oct 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2254 | TT_TASK | Reinstate Works Areas 4.9, 4.9A and 4.12A prior to handover | Mon May 22 08:00:00 IDT 2017 | Sat Sep 02 18:00:00 IDT 2017 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2258 | TT_TASK | Application of power supply, environmental permits and construction substation | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2259 | TT_TASK | Procurement and Confirmation of the order of 2nd tunnel boring machine | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2260 | TT_TASK | TBM design and submission for approval | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2261 | TT_TASK | TBM materials order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
2262 | TT_TASK | TBM equipments order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 |  | COMPLETED
2263 | TT_TASK | TBM Fabrication | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
2264 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 |  | COMPLETED
2265 | TT_TASK | TBM test Run | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2266 | TT_TASK | TBM disassembly and packing for shipping to HK | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 |  | COMPLETED
2267 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
2268 | TT_TASK | Setup TBM facilities | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
2269 | TT_TASK | Fabrication 50% of South Tunnel South Bound Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
2270 | TT_TASK | Fabrication 100% of South Tunnel South Bound Precast Lining | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
2271 | TT_TASK | Fabrication 50% of South Tunnel North Bound Precast Lining | Wed Oct 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 | Wed Oct 03 08:00:00 IST 2012 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
2272 | TT_TASK | Fabrication 100% of South Tunnel North Bound Precast Lining | Mon Aug 26 08:00:00 IDT 2013 | Wed Jan 22 18:00:00 IST 2014 | Wed Feb 27 08:00:00 IST 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
2274 | TT_TASK | Ground treatment at lauching shaft Southbound | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
2275 | TT_TASK | TBM assemble, thrust frame, testing and commissioning | Sat Jun 01 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2276 | TT_TASK | Lowing back-up plant for final drive | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
2277 | TT_TASK | Assemble and set up back-up plant for final drive | Sat Jun 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2278 | TT_TASK | Erection of noise enclosure | Sat Jul 20 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 |  | COMPLETED
2279 | TT_TASK | TBM drive & lining installation CH124+912 to CH125+012 (Initial Drive) | Sat Jul 20 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Mon Mar 11 00:00:00 IST 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
2280 | TT_TASK | TBM drive & lining installation CH125+012 to CH125+338 | Tue Oct 15 08:00:00 IDT 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon May 27 08:00:00 IDT 2013 | Tue May 20 00:00:00 IDT 2014 |  | COMPLETED
2281 | TT_TASK | Dis-assemble TBM | Fri May 23 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 |  | COMPLETED
2282 | TT_TASK | Invert slab and side walkway | Fri Aug 01 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Tue Sep 02 18:00:00 IDT 2014 |  | COMPLETED
2283 | TT_TASK | Installation of cable bracket | Mon Nov 03 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 | Mon Aug 18 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2285 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Sep 01 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 | Sat Aug 09 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2286 | TT_TASK | Ground treatment at lauching shaft Northbound | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 19 18:00:00 IST 2013 | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
2287 | TT_TASK | TBM assemble, testing and commissioning | Wed Jul 02 08:00:00 IDT 2014 | Wed Sep 03 18:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2288 | TT_TASK | Setup back-up plant for final drive | Tue Jun 03 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2289 | TT_TASK | Reinstate of noise enclosure | Fri Oct 10 08:00:00 IDT 2014 | Wed Nov 05 18:00:00 IST 2014 | Tue Oct 28 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
2290 | TT_TASK | TBM drive & lining installation CH124+927 to CH125+027 (Initial Drive) | Fri Oct 10 08:00:00 IDT 2014 | Thu Nov 13 18:00:00 IST 2014 | Thu Oct 30 00:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
2291 | TT_TASK | TBM drive & lining installation CH125+027 to CH125+353 (Final Drive) | Fri Jan 02 08:00:00 IST 2015 | Thu Feb 12 18:00:00 IST 2015 | Mon Dec 08 08:00:00 IST 2014 | Fri Aug 07 00:00:00 IDT 2015 |  | COMPLETED
2292 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Tue Aug 04 08:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
2293 | TT_TASK | Dis-assemble TBM | Tue Aug 04 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
2294 | TT_TASK | Invert slab and side walkway | Wed Sep 09 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
2295 | TT_TASK | Installation of cable bracket | Thu Sep 24 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Aug 31 18:00:00 IDT 2015 |  | COMPLETED
2298 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Partial length) at down track | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 |  | COMPLETED
2299 | TT_TASK | Probe/Grout | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 | Mon Aug 11 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2300 | TT_TASK | Coring of Segment | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 |  | COMPLETED
2301 | TT_TASK | Removal of segment | Tue Sep 02 08:00:00 IDT 2014 | Thu Sep 04 18:00:00 IDT 2014 | Thu Aug 21 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2302 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Sep 05 08:00:00 IDT 2014 | Tue Oct 07 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2303 | TT_TASK | Invert Concrete | Thu Oct 23 08:00:00 IDT 2014 | Sat Nov 01 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2304 | TT_TASK | Wall and Roof concrete | Mon Nov 03 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Mon Oct 13 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
2305 | TT_TASK | Dismantle Temporary frame | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2306 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
2307 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Remaining length ) at down track | Sat May 09 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Thu Apr 16 18:00:00 IDT 2015 |  | COMPLETED
2308 | TT_TASK | Probe/Grout | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
2309 | TT_TASK | Coring of Segment | Fri Oct 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 | Fri Oct 16 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
2310 | TT_TASK | Removal of segment | Wed Oct 07 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
2311 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Oct 10 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Oct 26 08:00:00 IST 2015 | Fri Dec 11 18:00:00 IST 2015 |  | COMPLETED
2312 | TT_TASK | Invert Concrete | Thu Dec 03 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Sat Dec 12 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2313 | TT_TASK | Wall and Roof concrete | Mon Dec 14 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 15 18:00:00 IST 2016 |  | COMPLETED
2314 | TT_TASK | Dismantle Temporary frame | Wed Jan 13 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 |  | COMPLETED
2315 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Mon Jan 18 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2318 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 | Mon Mar 21 08:00:00 IST 2011 | Sat May 28 18:00:00 IDT 2011 |  | COMPLETED
2319 | TT_TASK | Pre-drill and guide wall | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 | Mon May 30 08:00:00 IDT 2011 | Wed Jul 13 18:00:00 IDT 2011 |  | COMPLETED
2320 | TT_TASK | D-wall design review | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 | Thu Jul 14 08:00:00 IDT 2011 | Wed Aug 17 18:00:00 IDT 2011 |  | COMPLETED
2321 | TT_TASK | D-Wall Construction (1075m3) | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 | Thu Aug 18 08:00:00 IDT 2011 | Fri Nov 11 18:00:00 IST 2011 |  | COMPLETED
2322 | TT_TASK | Shear pin, toe grout and pumping test | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 | Sat Nov 12 08:00:00 IST 2011 | Wed Feb 29 18:00:00 IST 2012 |  | COMPLETED
2324 | TT_TASK | SI for TBM ground treatment | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2325 | TT_TASK | Design review of TBM ground treatment | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2326 | TT_TASK | Ground treatment for TBM southbound | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
2327 | TT_TASK | Ground treatment for TBM northbound | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2329 | TT_TASK | Capping beam construction | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 | Thu Mar 01 08:00:00 IST 2012 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
2330 | TT_TASK | L-Shape wall construction | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 | Mon Apr 02 08:00:00 IDT 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
2331 | TT_TASK | Excavate up to +28.5mPD (1488m3) | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 | Mon Apr 16 08:00:00 IDT 2012 | Fri Apr 20 18:00:00 IDT 2012 |  | COMPLETED
2332 | TT_TASK | Install Strut S1 +29.0mPD | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 | Thu Apr 19 08:00:00 IDT 2012 | Mon Apr 23 18:00:00 IDT 2012 |  | COMPLETED
2333 | TT_TASK | Excavate up to +23.5mPD (2480m3) | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 | Tue Apr 24 08:00:00 IDT 2012 | Fri May 04 18:00:00 IDT 2012 |  | COMPLETED
2334 | TT_TASK | Install Strut S2 +24.0mPD | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 | Sat May 05 08:00:00 IDT 2012 | Wed May 09 18:00:00 IDT 2012 |  | COMPLETED
2335 | TT_TASK | Excavate up to +19.5mPD (1984m3) | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 | Thu May 10 08:00:00 IDT 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
2336 | TT_TASK | Install Strut S3 +20.0mPD | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 | Tue May 29 08:00:00 IDT 2012 | Fri Jun 01 18:00:00 IDT 2012 |  | COMPLETED
2337 | TT_TASK | Excavate up to +15.5mPD (1984m3) | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Sat Jun 02 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
2338 | TT_TASK | Install Strut S4 +16.0mPD | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Mon Aug 06 18:00:00 IDT 2012 |  | COMPLETED
2339 | TT_TASK | Excavate up to formation (4117m3) | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Tue Aug 07 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
2340 | TT_TASK | Install rock dowel and tie back | Sat Jun 02 08:00:00 IDT 2012 | Sat Dec 01 18:00:00 IST 2012 | Sat Jun 02 08:00:00 IDT 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2341 | TT_TASK | Temporary handover the shaft to contract 822 | Mon Jun 03 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
2343 | TT_TASK | Rock breaking works | Mon Aug 26 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
2344 | TT_TASK | Temporary base Slab for TBM Drive | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Thu May 09 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
2347 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2348 | TT_TASK | Erect external formwork (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Wed Aug 13 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Tue Aug 19 18:00:00 IDT 2014 |  | COMPLETED
2349 | TT_TASK | Rebar fixing (Base Slab) | Thu Aug 14 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Wed Aug 20 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2350 | TT_TASK | Erect internal kicker formwork (Base Slab) | Tue Aug 19 08:00:00 IDT 2014 | Thu Aug 21 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 |  | COMPLETED
2351 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 22 08:00:00 IDT 2014 | Fri Aug 22 18:00:00 IDT 2014 | Thu Aug 28 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2352 | TT_TASK | Concreting (Base Slab) (245m3) | Sat Aug 23 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 | Fri Aug 29 08:00:00 IDT 2014 | Fri Aug 29 18:00:00 IDT 2014 |  | COMPLETED
2353 | TT_TASK | Curing (Base Slab) | Mon Aug 25 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 30 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2354 | TT_TASK | Removal of formwork (Base Slab) | Mon Sep 08 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Mon Sep 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2355 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Sep 10 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Tue Sep 02 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 |  | COMPLETED
2356 | TT_TASK | Rebar fixing (Wall and roof) | Thu Sep 18 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Thu Sep 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2357 | TT_TASK | Erect external formwork (Wall) | Thu Sep 25 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2358 | TT_TASK | Clearing and inspection (Wall and roof) | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2359 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
2360 | TT_TASK | Curing (Wall and roof) | Sat Oct 11 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
2361 | TT_TASK | Removal formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Thu Oct 16 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Sat Nov 01 18:00:00 IST 2014 |  | COMPLETED
2362 | TT_TASK | Removal formwork (Roof) | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2363 | TT_TASK | Side walkway and cable bracket (72m3) | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
2365 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Nov 07 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Sat Nov 07 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
2366 | TT_TASK | Erect external formwork (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Wed Nov 18 18:00:00 IST 2015 |  | COMPLETED
2367 | TT_TASK | Rebar fixing (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Tue Nov 17 18:00:00 IST 2015 | Thu Nov 19 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 |  | COMPLETED
2368 | TT_TASK | Erect internal kicker formwork (Base Slab) | Wed Nov 18 08:00:00 IST 2015 | Fri Nov 20 18:00:00 IST 2015 | Tue Nov 24 08:00:00 IST 2015 | Thu Nov 26 18:00:00 IST 2015 |  | COMPLETED
2369 | TT_TASK | Clearing and inspection (Base Slab) | Sat Nov 21 08:00:00 IST 2015 | Sat Nov 21 18:00:00 IST 2015 | Fri Nov 27 08:00:00 IST 2015 | Fri Nov 27 18:00:00 IST 2015 |  | COMPLETED
2370 | TT_TASK | Concreting (Base Slab) (245m3) | Mon Nov 23 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Nov 28 08:00:00 IST 2015 | Sat Nov 28 18:00:00 IST 2015 |  | COMPLETED
2371 | TT_TASK | Curing (Base Slab) | Tue Nov 24 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Mon Nov 30 08:00:00 IST 2015 | Thu Dec 03 18:00:00 IST 2015 |  | COMPLETED
2372 | TT_TASK | Removal of formwork (Base Slab) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 01 18:00:00 IST 2015 | Fri Dec 04 08:00:00 IST 2015 | Sat Dec 05 18:00:00 IST 2015 |  | COMPLETED
2373 | TT_TASK | Erect internal formwork and scaffold system (Wall and roof) | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 09 18:00:00 IST 2015 | Mon Dec 07 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
2374 | TT_TASK | Rebar fixing (Wall and roof) | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2375 | TT_TASK | Erect external formwork (Wall) | Mon Jan 11 08:00:00 IST 2016 | Wed Jan 13 18:00:00 IST 2016 | Thu Jan 07 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2376 | TT_TASK | Clearing and inspection (Wall and roof) | Thu Jan 14 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2377 | TT_TASK | Concreting (Wall and roof) (166m3) | Fri Jan 15 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2378 | TT_TASK | Curing (Wall and roof) | Sat Jan 16 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 |  | COMPLETED
2379 | TT_TASK | Removal formwork (Wall) | Tue Jan 19 08:00:00 IST 2016 | Thu Jan 21 18:00:00 IST 2016 | Thu Jan 28 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2380 | TT_TASK | Removal formwork and falsework (Roof) | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 01 18:00:00 IST 2016 | Sat Jan 30 08:00:00 IST 2016 | Sat Jan 30 18:00:00 IST 2016 |  | COMPLETED
2381 | TT_TASK | Side walkway and cable bracket (72m3) | Wed Jan 06 08:00:00 IST 2016 | Sat Jan 16 18:00:00 IST 2016 | Thu Nov 12 08:00:00 IST 2015 | Tue Mar 01 18:00:00 IST 2016 |  | COMPLETED
2382 | TT_TASK | Provision access opening to DC | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2383 | TT_TASK | Erect falsework and soffit formwork (Opening) | Thu Mar 10 08:00:00 IST 2016 | Mon Mar 21 18:00:00 IST 2016 | Mon Dec 28 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2384 | TT_TASK | Rebar fixing (Roof) | Tue Mar 22 08:00:00 IST 2016 | Tue Mar 22 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
2385 | TT_TASK | Clearing and inspection (Roof) | Wed Mar 23 08:00:00 IST 2016 | Wed Mar 23 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 |  | COMPLETED
2386 | TT_TASK | Concreting (Roof) (225m3) | Thu Mar 24 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Tue Jan 12 08:00:00 IST 2016 | Tue Jan 12 18:00:00 IST 2016 |  | COMPLETED
2387 | TT_TASK | Curing (Roof) | Tue Mar 29 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Jan 13 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
2388 | TT_TASK | Removal internal falsework and soffit formwork (Roof) | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 | Mon Mar 14 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
2390 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Thu Mar 17 08:00:00 IST 2016 | Fri Mar 18 18:00:00 IST 2016 | Tue Mar 01 08:00:00 IST 2016 | Wed Mar 02 18:00:00 IST 2016 |  | COMPLETED
2391 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Sat Mar 19 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Thu Mar 03 08:00:00 IST 2016 | Tue Mar 08 18:00:00 IST 2016 |  | COMPLETED
2392 | TT_TASK | Backfilling to +18.25mPD (1229 m3 of soil) | Sat Jul 02 08:00:00 IDT 2016 | Mon Jul 11 18:00:00 IDT 2016 | Mon Jul 25 08:00:00 IDT 2016 | Tue Aug 02 18:00:00 IDT 2016 |  | COMPLETED
2393 | TT_TASK | Laying 500mm mass concrete lateral support | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 | Wed Aug 03 08:00:00 IDT 2016 | Wed Aug 03 18:00:00 IDT 2016 |  | COMPLETED
2394 | TT_TASK | Backfilling to 0.5m below S3 (+19.5mPD) (372m3 of soil) | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 | Thu Aug 04 08:00:00 IDT 2016 | Sat Aug 06 18:00:00 IDT 2016 |  | COMPLETED
2395 | TT_TASK | Removal strut S3 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 | Mon Aug 08 08:00:00 IDT 2016 | Wed Aug 10 18:00:00 IDT 2016 |  | COMPLETED
2396 | TT_TASK | Backfilling to 0.5m below S2 (+23.5mPD) (1984m3 of soil) | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 | Thu Aug 11 08:00:00 IDT 2016 | Tue Aug 23 18:00:00 IDT 2016 |  | COMPLETED
2397 | TT_TASK | Removal strut S2 | Wed Aug 24 08:00:00 IDT 2016 | Fri Aug 26 18:00:00 IDT 2016 | Wed Aug 24 08:00:00 IDT 2016 | Thu Sep 01 18:00:00 IDT 2016 |  | COMPLETED
2398 | TT_TASK | Backfilling to 0.5m below S1 (+28.5mPD) (2480m3 of soil) | Mon Sep 05 08:00:00 IDT 2016 | Tue Sep 20 18:00:00 IDT 2016 | Fri Sep 02 08:00:00 IDT 2016 | Fri Sep 09 18:00:00 IDT 2016 |  | COMPLETED
2399 | TT_TASK | Removal strut S1 | Wed Sep 21 08:00:00 IDT 2016 | Thu Sep 22 18:00:00 IDT 2016 | Sat Sep 10 08:00:00 IDT 2016 | Wed Sep 14 18:00:00 IDT 2016 |  | COMPLETED
2400 | TT_TASK | Backfilling to original ground level (approx. +31.5mPD) (1488m3 of soil) | Fri Sep 23 08:00:00 IDT 2016 | Mon Oct 03 18:00:00 IDT 2016 | Thu Sep 15 08:00:00 IDT 2016 | Mon Sep 19 18:00:00 IDT 2016 |  | COMPLETED
2402 | TT_TASK | Reinstatement of TUT area (Including Hydroseeding) | Mon Oct 03 08:00:00 IDT 2016 | Mon Jun 19 18:00:00 IDT 2017 | Fri Oct 07 08:00:00 IDT 2016 |  | 216.0 | IN_PROGRESS
25 | TT_TASK | Access opening for the up track cut and cover tunnel at Tse Uk Tsuen Shaft | Tue Feb 02 08:00:00 IST 2016 | Wed Mar 09 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 10 18:00:00 IST 2016 |  | COMPLETED
27 | TT_TASK | Close out the temporary access opening at Tse Uk Tsuen Shaft | Thu Mar 10 08:00:00 IST 2016 | Tue Apr 05 18:00:00 IDT 2016 | Thu Feb 11 08:00:00 IST 2016 | Wed Mar 16 18:00:00 IST 2016 |  | COMPLETED
307 | TT_TASK | Position crane for TBM retrieval (down track) | Wed Jul 02 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 26 08:00:00 IDT 2014 | Sat Aug 02 18:00:00 IDT 2014 |  | COMPLETED
308 | TT_TASK | TBM Break-in and Retrieval (down track) | Mon Aug 04 08:00:00 IDT 2014 | Sat Aug 30 18:00:00 IDT 2014 | Mon Aug 04 08:00:00 IDT 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
309 | TT_TASK | Position crane for TBM retrieval (up track) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 |  | COMPLETED
310 | TT_TASK | TBM Break-in and Retrieval (up track) | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 | Wed Dec 09 08:00:00 IST 2015 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
376 | TT_TASK | Supply Engineer with Survey Equipment [PS41.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
377 | TT_TASK | Provide Engineer with suitably qualified full time Survey Assistant - 4 nos. [PS41.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
378 | TT_TASK | Provide Engineer with site transportation as detailed in PS42.1 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 24 18:00:00 IDT 2010 |  | COMPLETED
379 | TT_TASK | Submit details of qualified drivers to be assigned to the Engineer, for review [PS42.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 03 18:00:00 IDT 2010 |  | COMPLETED
380 | TT_TASK | Install, service and maintain 10 container offices for use by the Engineer's Site Staff | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 | Mon Dec 20 08:00:00 IST 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
381 | TT_TASK | Provide services and equipment for the Engineer | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 | Wed Aug 04 08:00:00 IDT 2010 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
383 | TT_TASK | Master Programme - Prepare and submit for approval [GS4.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
384 | TT_TASK | Master Programme - Comments , Resubmission and Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
385 | TT_TASK | Time Chainage Programme - Prepare and submit for approval [GS4.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Aug 30 18:00:00 IDT 2010 |  | COMPLETED
386 | TT_TASK | Time Chainage Programme - Approval period | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Tue Aug 31 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
387 | TT_TASK | Implement and Maintain Programme Management System for 1st Audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
388 | TT_TASK | Implement and Maintain Programme Management System for 2nd Audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
389 | TT_TASK | Implement and Maintain Programme Management System for 3rd Audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
391 | TT_TASK | Environmental Management Plan - Prepare and submit for approval [GS5.1.10] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
392 | TT_TASK | Environmental Management Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
393 | TT_TASK | Quality Plan - Prepare and submit for approval [GS9.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
394 | TT_TASK | Quality Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
395 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 1st audit | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 | Tue Oct 05 08:00:00 IST 2010 | Fri Jan 28 18:00:00 IST 2011 |  | COMPLETED
396 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 2nd audit | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 | Sat Jan 29 08:00:00 IST 2011 | Fri Jul 29 18:00:00 IDT 2011 |  | COMPLETED
397 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 3rd audit | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Jul 30 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
398 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 4th audit | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
399 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 5th audit | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 | Sat Jul 28 08:00:00 IDT 2012 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
400 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 6th audit | Tue Jul 02 08:00:00 IDT 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
401 | TT_TASK | Implement and Maintain Specified Plans and satisfactorily confirmed by Engineer for 7th audit | Thu Nov 28 08:00:00 IST 2013 | Thu Jun 05 18:00:00 IDT 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Jan 24 18:00:00 IST 2014 |  | COMPLETED
402 | TT_TASK | Health and Safety Plan - Prepare and submit [G3.6.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
403 | TT_TASK | System Assurance Plan - Prepare and submit for approval [PS Appendix P3.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
404 | TT_TASK | System Assurance Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
405 | TT_TASK | Design for Safety & Constructability Plan - Prepare and submit for approval [PS37.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
406 | TT_TASK | Design for Safety & Constructability Plan - Approval period | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 | Fri Aug 20 08:00:00 IDT 2010 | Tue Sep 21 18:00:00 IST 2010 |  | COMPLETED
408 | TT_TASK | Methods of Construction - Prepare and submit for approval [GS12.1.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
409 | TT_TASK | Methods of Construction - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
410 | TT_TASK | Contractor's Submission Schedule - Prepare and submit for approval [GS12.11.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
411 | TT_TASK | Contractor's Submission Schedule - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 | Mon Aug 16 08:00:00 IDT 2010 | Mon Oct 04 18:00:00 IST 2010 |  | COMPLETED
412 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) [PS13.3.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
413 | TT_TASK | Survey Method Statement (Survey Control of Tunnel) - Approval period | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 | Mon Oct 18 08:00:00 IST 2010 | Sat Nov 13 18:00:00 IST 2010 |  | COMPLETED
414 | TT_TASK | Spoil Disposal Plan [PS17.7.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
415 | TT_TASK | Waste Management Plan [PS22.10.1] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 12 18:00:00 IDT 2010 |  | COMPLETED
416 | TT_TASK | Independent Checking Engineer - Appoint and submit for approval [PS7.1.8] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
417 | TT_TASK | Independent Checking Engineer - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
418 | TT_TASK | Sub-contract Management Plan - Prepare and submit [PS34.1] | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Tue Aug 10 18:00:00 IDT 2010 |  | COMPLETED
419 | TT_TASK | Schedule of Utilities Services Arrangement [GS7.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
420 | TT_TASK | Site Safety Supervision Plan for Site Formation - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
421 | TT_TASK | Site Safety Supervision Plan for Site Formation - Approval period | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
422 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Prepare and Submit | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 14 18:00:00 IDT 2010 |  | COMPLETED
423 | TT_TASK | Site Safety Supervision Plan for Site Investigation - Approval period | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
424 | TT_TASK | Site Safety Supervision Plan for ELS - Prepare and Submit | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Mon Sep 27 18:00:00 IST 2010 |  | COMPLETED
425 | TT_TASK | Site Safety Supervision Plan for ELS - Approval Period | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Tue Sep 28 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
426 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Prepare and Submit | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
427 | TT_TASK | Site Safety Supervision Plan for Tunnel Works - Approval Period | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
428 | TT_TASK | Noise Management Plan [P22.3.9] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
429 | TT_TASK | Air Quality Management Plan [P22.4.3] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
430 | TT_TASK | Detailed Proposal for Water Pollution Control Measures and Proposed Monitoring [PS22.5.1] | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Wed Sep 08 18:00:00 IDT 2010 |  | COMPLETED
431 | TT_TASK | Groundwater Monitoring and Response Plan [PS22.5.2] | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Aug 19 18:00:00 IDT 2010 |  | COMPLETED
432 | TT_TASK | Vibration Monitoring Plan [PS22.8.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 21 18:00:00 IDT 2010 |  | COMPLETED
433 | TT_TASK | Proposed Outline TTM Scheme - Prepare & submit to the: Engineer for Review / SLG for Approval [PS19.3] | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Sep 04 18:00:00 IDT 2010 |  | COMPLETED
434 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Proposed TTM Scheme [PS19.4] | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 | Mon Sep 06 08:00:00 IDT 2010 | Sat Nov 27 18:00:00 IST 2010 |  | COMPLETED
435 | TT_TASK | Resubmission of Proposed Outline TTM Scheme (if required) | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Mon Nov 29 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
436 | TT_TASK | Reviewal Period / Approval Process by Engineer/SLG of the Resubmitted Proposed Outline TTM Scheme [PS19.4] | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Mar 02 18:00:00 IST 2011 |  | COMPLETED
437 | TT_TASK | Notification Period of the Approved TTM Scheme prior to implementation [PS19.4] | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 | Thu Mar 03 08:00:00 IST 2011 | Mon Mar 14 18:00:00 IST 2011 |  | COMPLETED
440 | TT_TASK | Initial Site Survey (WA3.11) | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 | Mon Aug 16 08:00:00 IDT 2010 | Wed Aug 18 18:00:00 IDT 2010 |  | COMPLETED
441 | TT_TASK | Initial Site Survey Report (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Wed Aug 25 18:00:00 IDT 2010 |  | COMPLETED
442 | TT_TASK | Initial Site Survey & Condition Survey (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
443 | TT_TASK | Initial Site Survey Report (WA3.1, 3.2, 3.3, 3.3A, 3.3B, 4.2, 4.3, 4.4) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
444 | TT_TASK | Initial Site Survey & Condition Survey (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
445 | TT_TASK | Initial Site Survey Report (WA4.9A, 4.10, 4.10A, 4.11, 4.12B, 4.12C, 4.15, 4.15A, 4.15B) | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
446 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 4.9 & 4.12A [PS4.2] | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
447 | TT_TASK | Temporary Occupation Area: Conduct, prepare and submit TOA Record Survey for Works Areas 5.1 & 5.3 [PS4.2.3] | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 07 18:00:00 IST 2011 |  | COMPLETED
448 | TT_TASK | Proposal for Site Clearance Works [PS4.4.1] | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Fri Jan 14 18:00:00 IST 2011 |  | COMPLETED
449 | TT_TASK | Site Clearance / Site Formation Works (including demolition of EBS) | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
450 | TT_TASK | Backfill existing stream courses in Works Area 4.9, 4.10 and 4.11 [PS18.5.1] | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 | Tue Jan 11 08:00:00 IST 2011 | Sat Apr 16 18:00:00 IDT 2011 |  | COMPLETED
451 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and submit to EPD for Approval (WA3.3 - Area M, I, L) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
452 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA3.3 - Area M, I, L) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
453 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
454 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.3 - Area M, I, L) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
455 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.3 - Area M, I, L) | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 06 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
456 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA3.3 - Area M, I, L) | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 | Mon Feb 21 08:00:00 IST 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
457 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA3.3 - Area M, I, L) | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 20 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
458 | TT_TASK | Remediation Report - Approval (WA3.3 - Area M, I, L) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
459 | TT_TASK | Contamination Assessment Plan (CAP) - Prepare and Submit to EPD for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 | Tue Oct 05 08:00:00 IST 2010 | Tue Oct 19 18:00:00 IST 2010 |  | COMPLETED
460 | TT_TASK | Contamination Assessment Plan (CAP) - Approval Period (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 | Wed Oct 20 08:00:00 IST 2010 | Tue Nov 30 18:00:00 IST 2010 |  | COMPLETED
461 | TT_TASK | Conduct Contamination Assessment in accordance with the Approved CAP (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 06 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
462 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Prepare & Submit to EPD for Approval (WA3.1, 3.2, 3.3, 3.3A) | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Mon Dec 13 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
463 | TT_TASK | Contamination Assessment Report & Remediation Action Plan - Approval (WA3.1, 3.2, 3.3, 3.3A) | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 26 18:00:00 IST 2011 |  | COMPLETED
464 | TT_TASK | Conduct remediation in accordance with the approved Remediation Action Plan (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 | Mon Feb 28 08:00:00 IST 2011 | Tue Jul 26 18:00:00 IDT 2011 |  | COMPLETED
465 | TT_TASK | Remediation Report - Prepare and submit for Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 | Wed Jul 13 08:00:00 IDT 2011 | Tue Aug 09 18:00:00 IDT 2011 |  | COMPLETED
466 | TT_TASK | Remediation Report - Approval (WA 3.1, 3.2, 3.3 remaining, 3.3A) | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 | Wed Aug 10 08:00:00 IDT 2011 | Wed Sep 21 18:00:00 IDT 2011 |  | COMPLETED
467 | TT_TASK | Conduct remediation for Area Q in accordance with method proposed in the approved Remediation Action Plan [PS22.9.2] | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 | Mon Dec 06 08:00:00 IST 2010 | Fri May 06 18:00:00 IDT 2011 |  | COMPLETED
468 | TT_TASK | Remediation Report - Prepare and submit for Approval [PS22.9.2] (Area Q) | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 | Sat May 07 08:00:00 IDT 2011 | Sat Jun 04 18:00:00 IDT 2011 |  | COMPLETED
469 | TT_TASK | Remediation Report - Approval (Area Q) | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 | Tue Jun 07 08:00:00 IDT 2011 | Tue Jul 19 18:00:00 IDT 2011 |  | COMPLETED
470 | TT_TASK | Removal of contaminated soil at North Tunnels (Area N,O,P,Q,R,S) | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Thu Sep 22 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
471 | TT_TASK | Condition Survey EBS for presence of Asbestos and gather samples | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Sat Dec 18 18:00:00 IST 2010 |  | COMPLETED
472 | TT_TASK | Testing of gathered samples | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 | Mon Dec 20 08:00:00 IST 2010 | Tue Dec 28 18:00:00 IST 2010 |  | COMPLETED
473 | TT_TASK | Prepare and submit Asbestos Investigation Report (AIR) & Asbestos Abatement Plan (AAP) | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 | Wed Dec 29 08:00:00 IST 2010 | Wed Jan 12 18:00:00 IST 2011 |  | COMPLETED
474 | TT_TASK | Approval period of AIR & AAP | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 | Thu Jan 13 08:00:00 IST 2011 | Sat Feb 19 18:00:00 IST 2011 |  | COMPLETED
475 | TT_TASK | Notification period to Engineer and EPD prior to Asbestos abatement works | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Mon Feb 21 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
476 | TT_TASK | Asbestos abatement works | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
477 | TT_TASK | Demolition of EBS | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
478 | TT_TASK | Confirmation of tree survey | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Tue Jan 18 18:00:00 IST 2011 |  | COMPLETED
480 | TT_TASK | Installation of ground settlement markers | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 | Thu Jan 20 08:00:00 IST 2011 | Sat May 21 18:00:00 IDT 2011 |  | COMPLETED
481 | TT_TASK | Settlement monitoring and submit report | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 | Mon May 23 08:00:00 IDT 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
482 | TT_TASK | Settlement monitoring and submit report | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 | Sat Jan 28 08:00:00 IST 2012 | Thu Jun 21 18:00:00 IDT 2012 |  | COMPLETED
483 | TT_TASK | Settlement monitoring and submit report | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 | Fri Jun 22 08:00:00 IDT 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
484 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Feb 23 08:00:00 IST 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
485 | TT_TASK | Settlement monitoring and submit report | Thu Aug 01 08:00:00 IDT 2013 | Wed Feb 26 18:00:00 IST 2014 | Sat Jul 27 08:00:00 IDT 2013 | Fri Feb 21 18:00:00 IST 2014 |  | COMPLETED
486 | TT_TASK | Settlement monitoring and submit report | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 | Sat Feb 22 08:00:00 IST 2014 | Fri Jul 25 18:00:00 IDT 2014 |  | COMPLETED
488 | TT_TASK | Permit Applications (incl. License to Search and Excavate Antiquities and Excavation Permit) | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 | Mon Jan 03 08:00:00 IST 2011 | Mon Feb 28 18:00:00 IST 2011 |  | COMPLETED
489 | TT_TASK | Check for underground utilities | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Thu Mar 03 18:00:00 IST 2011 |  | COMPLETED
490 | TT_TASK | Field walking and hand augering | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 | Fri Mar 04 08:00:00 IST 2011 | Thu Mar 10 18:00:00 IST 2011 |  | COMPLETED
491 | TT_TASK | Excavation of trial pits | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 | Fri Mar 11 08:00:00 IST 2011 | Thu Mar 17 18:00:00 IST 2011 |  | COMPLETED
492 | TT_TASK | Rescue excavation rescue works (if required) | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 | Fri Mar 18 08:00:00 IST 2011 | Sat Jul 09 18:00:00 IDT 2011 |  | COMPLETED
494 | TT_TASK | Erection of Hoarding with Gate (WA3.11) | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 | Thu Aug 19 08:00:00 IDT 2010 | Mon Aug 23 18:00:00 IDT 2010 |  | COMPLETED
495 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 3.1, 3.2, 3.3 and 3.3A [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
496 | TT_TASK | Erection of Metal Steel Hoarding, Gate, and Chainlink Fence at Works Areas 4.9, 4.10, 4.11, 4.12A~C, and 4.15 [PS4.6.1] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 19 18:00:00 IST 2011 |  | COMPLETED
497 | TT_TASK | Project Signboard Erection [PS4.6.8] | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 | Mon Dec 20 08:00:00 IST 2010 | Wed Jan 05 18:00:00 IST 2011 |  | COMPLETED
498 | TT_TASK | Marine Survey at Barging Point [PS4.3] (before construction of barging facilities) | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Thu Sep 30 00:00:00 IST 2010 |  | COMPLETED
499 | TT_TASK | Construct barging facilities | Sat Oct 02 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Oct 02 00:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
500 | TT_TASK | Operation Plan for the Barging Facility - Prepare and Submit for Approval [PS17.1.9] | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
501 | TT_TASK | Operation Plan for the Barging Facility - Review and Approval Period | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 22 18:00:00 IST 2011 |  | COMPLETED
503 | TT_TASK | General and Special Attendance for Designated Contractors | Mon Dec 02 08:00:00 IST 2013 | Mon Aug 31 18:00:00 IDT 2015 | Tue Jul 02 08:00:00 IDT 2013 | Wed Mar 25 18:00:00 IST 2015 |  | COMPLETED
505 | TT_TASK | Prepare and Submit Detailed Interface Specification | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 | Sat Oct 08 08:00:00 IST 2011 | Fri Dec 16 18:00:00 IST 2011 |  | COMPLETED
506 | TT_TASK | Approval of Detailed Interface Plan | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 | Sat Dec 17 08:00:00 IST 2011 | Fri Jan 27 18:00:00 IST 2012 |  | COMPLETED
507 | TT_TASK | Prepare and Submit Detailed Interface Specification | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 | Tue Apr 10 08:00:00 IDT 2012 | Wed Jun 20 18:00:00 IDT 2012 |  | COMPLETED
508 | TT_TASK | Approval of Detailed Interface Plan | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 | Thu Jun 21 08:00:00 IDT 2012 | Fri Jul 27 18:00:00 IDT 2012 |  | COMPLETED
510 | TT_TASK | Prepare and Submit Draft Operation and Maintenance Manual [PS33.1] | Mon Aug 24 08:00:00 IDT 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jul 28 08:00:00 IDT 2014 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
511 | TT_TASK | Review and approval period of Draft Operation and Maintenance Manual | Wed Aug 10 08:00:00 IDT 2016 | Tue Sep 13 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
512 | TT_TASK | Prepare and Submit Final Operation and Maintenance Manual [PS33.1] | Wed Sep 14 08:00:00 IDT 2016 | Thu Feb 16 18:00:00 IST 2017 | Thu Jun 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
513 | TT_TASK | Provide Engineer with As-Built Drawing for the Whole of the Works [PS33.2] | Mon Nov 21 08:00:00 IST 2016 | Wed Dec 14 18:00:00 IST 2016 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
514 | TT_TASK | Provide Engineer with Asset Registration Information [PS33.3] | Fri May 19 08:00:00 IDT 2017 | Mon Jun 12 18:00:00 IDT 2017 |  |  |  | NOT_STARTED
517 | TT_TASK | Preliminary Design Programme - Prepare and Submit for Approval [PS7.1.8 - App. Z2.1] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
518 | TT_TASK | Preliminary Design Programme - Review and Approval Period [PS7.1.8 - App. Z2.2] | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Thu Aug 26 18:00:00 IDT 2010 |  | COMPLETED
519 | TT_TASK | Preliminary Design Programme - Resubmission and Approval (if required) [PS7.1.8 - App. Z2.2] | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 | Fri Aug 27 08:00:00 IDT 2010 | Sat Oct 02 18:00:00 IST 2010 |  | COMPLETED
520 | TT_TASK | Schedule of Designs - Prepare and Submit for Approval [PS7.1.8 - App. Z2.5] | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
521 | TT_TASK | Detailed Proposal for Carrying Out the Cross Passage Works [PS11.5.2] | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
524 | TT_TASK | Design TBM and submit full details to the Engineer [PS7.2.1] | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
525 | TT_TASK | TBM Design - Approval period | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Aug 27 18:00:00 IDT 2010 |  | COMPLETED
526 | TT_TASK | TBM Design - Resubmission and approval period | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 | Sat Aug 28 08:00:00 IDT 2010 | Wed Sep 15 18:00:00 IST 2010 |  | COMPLETED
528 | TT_TASK | AIP Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Aug 13 18:00:00 IDT 2010 |  | COMPLETED
529 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 | Sat Aug 14 08:00:00 IDT 2010 | Fri Sep 10 18:00:00 IDT 2010 |  | COMPLETED
530 | TT_TASK | DDS Design - Prepare and Submit | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 | Sat Sep 11 08:00:00 IDT 2010 | Thu Oct 28 18:00:00 IST 2010 |  | COMPLETED
531 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 | Fri Oct 29 08:00:00 IST 2010 | Thu Nov 25 18:00:00 IST 2010 |  | COMPLETED
532 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 02 18:00:00 IST 2010 |  | COMPLETED
533 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 | Fri Dec 03 08:00:00 IST 2010 | Mon Jan 03 18:00:00 IST 2011 |  | COMPLETED
534 | TT_TASK | Issue Completed Working Drawings | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Jan 07 18:00:00 IST 2011 |  | COMPLETED
536 | TT_TASK | AIP Design - Prepare and Submit | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 | Sat Jan 08 08:00:00 IST 2011 | Tue Feb 22 18:00:00 IST 2011 |  | COMPLETED
537 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 | Wed Feb 23 08:00:00 IST 2011 | Tue Mar 22 18:00:00 IST 2011 |  | COMPLETED
538 | TT_TASK | AIP Design - Response to comments and Resubmit | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 | Wed Mar 23 08:00:00 IST 2011 | Thu Mar 24 18:00:00 IST 2011 |  | COMPLETED
539 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Tue Apr 26 18:00:00 IDT 2011 |  | COMPLETED
540 | TT_TASK | DDS Design - Prepare and Submit | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 | Fri Mar 25 08:00:00 IST 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
541 | TT_TASK | DDS Design - Review and Approval Period (by MTRC & related Government Authorities) | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Fri Jun 10 18:00:00 IDT 2011 |  | COMPLETED
542 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 | Sat Jun 11 08:00:00 IDT 2011 | Wed Jun 15 18:00:00 IDT 2011 |  | COMPLETED
543 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 | Thu Jun 16 08:00:00 IDT 2011 | Thu Jul 14 18:00:00 IDT 2011 |  | COMPLETED
544 | TT_TASK | Issue Completed Working Drawings | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 | Fri Jul 15 08:00:00 IDT 2011 | Mon Jul 18 18:00:00 IDT 2011 |  | COMPLETED
546 | TT_TASK | DDS Design - Prepare and Submit | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 | Tue Jul 19 08:00:00 IDT 2011 | Mon Aug 29 18:00:00 IDT 2011 |  | COMPLETED
547 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Sep 29 18:00:00 IDT 2011 |  | COMPLETED
548 | TT_TASK | DDS Design - Response to comments and Resubmit | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 | Fri Sep 30 08:00:00 IDT 2011 | Thu Oct 06 18:00:00 IST 2011 |  | COMPLETED
549 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 | Fri Oct 07 08:00:00 IST 2011 | Sat Nov 05 18:00:00 IST 2011 |  | COMPLETED
550 | TT_TASK | Issue Completed Working Drawings | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Mon Nov 07 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
552 | TT_TASK | AIP Design - Prepare and Submit | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 | Tue Aug 30 08:00:00 IDT 2011 | Thu Oct 13 18:00:00 IST 2011 |  | COMPLETED
553 | TT_TASK | AIP Design - Review and Approval Period (by MTRC) | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 | Fri Oct 14 08:00:00 IST 2011 | Thu Nov 10 18:00:00 IST 2011 |  | COMPLETED
554 | TT_TASK | AIP Design - Response to comments and Resubmit | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 | Fri Nov 11 08:00:00 IST 2011 | Sat Nov 12 18:00:00 IST 2011 |  | COMPLETED
555 | TT_TASK | AIP Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
556 | TT_TASK | DDS Design - Prepare and Submit | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 | Mon Nov 14 08:00:00 IST 2011 | Sat Dec 24 18:00:00 IST 2011 |  | COMPLETED
557 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 | Wed Dec 28 08:00:00 IST 2011 | Sat Jan 28 18:00:00 IST 2012 |  | COMPLETED
558 | TT_TASK | DDS Design - Response to comments and Resubmit | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 | Mon Jan 30 08:00:00 IST 2012 | Thu Feb 02 18:00:00 IST 2012 |  | COMPLETED
559 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 | Fri Feb 03 08:00:00 IST 2012 | Thu Mar 01 18:00:00 IST 2012 |  | COMPLETED
560 | TT_TASK | Issue Completed Working Drawings | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 | Fri Mar 02 08:00:00 IST 2012 | Mon Mar 05 18:00:00 IST 2012 |  | COMPLETED
562 | TT_TASK | Prepare and Submit | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 | Fri Nov 26 08:00:00 IST 2010 | Thu Dec 09 18:00:00 IST 2010 |  | COMPLETED
563 | TT_TASK | Review and Approval Period | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 | Fri Dec 10 08:00:00 IST 2010 | Mon Jan 10 18:00:00 IST 2011 |  | COMPLETED
564 | TT_TASK | Response to comments and Resubmit | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 | Tue Jan 11 08:00:00 IST 2011 | Thu Jan 13 18:00:00 IST 2011 |  | COMPLETED
565 | TT_TASK | Review and Approval Period (for resubmission) | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 | Fri Jan 14 08:00:00 IST 2011 | Mon Feb 14 18:00:00 IST 2011 |  | COMPLETED
568 | TT_TASK | DDS Design - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
569 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 | Mon Aug 30 08:00:00 IDT 2010 | Wed Sep 29 18:00:00 IST 2010 |  | COMPLETED
570 | TT_TASK | DDS Design - Response to comments and Resubmit | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 | Thu Sep 30 08:00:00 IST 2010 | Tue Oct 05 18:00:00 IST 2010 |  | COMPLETED
571 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 | Wed Oct 06 08:00:00 IST 2010 | Fri Nov 05 18:00:00 IST 2010 |  | COMPLETED
572 | TT_TASK | Issue Completed Working Drawings | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 | Sat Nov 06 08:00:00 IST 2010 | Wed Nov 10 18:00:00 IST 2010 |  | COMPLETED
574 | TT_TASK | DDS Design - Prepare and Submit | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 | Thu Nov 11 08:00:00 IST 2010 | Wed Dec 22 18:00:00 IST 2010 |  | COMPLETED
575 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 | Thu Dec 23 08:00:00 IST 2010 | Tue Jan 25 18:00:00 IST 2011 |  | COMPLETED
576 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 | Wed Jan 26 08:00:00 IST 2011 | Sat Jan 29 18:00:00 IST 2011 |  | COMPLETED
577 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 | Mon Jan 31 08:00:00 IST 2011 | Fri Mar 04 18:00:00 IST 2011 |  | COMPLETED
578 | TT_TASK | Issue Completed Working Drawings | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 | Sat Mar 05 08:00:00 IST 2011 | Wed Mar 09 18:00:00 IST 2011 |  | COMPLETED
580 | TT_TASK | DDS Design - Prepare and Submit | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 | Thu Mar 10 08:00:00 IST 2011 | Thu Apr 21 18:00:00 IDT 2011 |  | COMPLETED
581 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 | Tue Apr 26 08:00:00 IDT 2011 | Fri May 27 18:00:00 IDT 2011 |  | COMPLETED
582 | TT_TASK | DDS Design - Response to comments and Resubmit | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 | Sat May 28 08:00:00 IDT 2011 | Wed Jun 01 18:00:00 IDT 2011 |  | COMPLETED
583 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 | Thu Jun 02 08:00:00 IDT 2011 | Mon Jul 04 18:00:00 IDT 2011 |  | COMPLETED
584 | TT_TASK | Issue Completed Working Drawings | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 | Tue Jul 05 08:00:00 IDT 2011 | Fri Jul 08 18:00:00 IDT 2011 |  | COMPLETED
586 | TT_TASK | DDS Design - Prepare and Submit | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 | Sat Jul 09 08:00:00 IDT 2011 | Fri Aug 19 18:00:00 IDT 2011 |  | COMPLETED
587 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 | Sat Aug 20 08:00:00 IDT 2011 | Tue Sep 20 18:00:00 IDT 2011 |  | COMPLETED
588 | TT_TASK | DDS Design - Response to comments and Resubmit | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 | Wed Sep 21 08:00:00 IDT 2011 | Sat Sep 24 18:00:00 IDT 2011 |  | COMPLETED
589 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 | Mon Sep 26 08:00:00 IDT 2011 | Thu Oct 27 18:00:00 IST 2011 |  | COMPLETED
590 | TT_TASK | Issue Completed Working Drawings | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 | Fri Oct 28 08:00:00 IST 2011 | Tue Nov 01 18:00:00 IST 2011 |  | COMPLETED
592 | TT_TASK | DDS Design - Prepare and Submit | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 | Wed Nov 02 08:00:00 IST 2011 | Tue Dec 13 18:00:00 IST 2011 |  | COMPLETED
593 | TT_TASK | DDS Design - Review and Approval Period (by MTRC) | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Mon Jan 16 18:00:00 IST 2012 |  | COMPLETED
594 | TT_TASK | DDS Design - Response to comments and Resubmit | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 | Tue Jan 17 08:00:00 IST 2012 | Fri Jan 20 18:00:00 IST 2012 |  | COMPLETED
595 | TT_TASK | DDS Design - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 | Sat Jan 21 08:00:00 IST 2012 | Thu Feb 23 18:00:00 IST 2012 |  | COMPLETED
596 | TT_TASK | Issue Completed Working Drawings | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Fri Feb 24 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
599 | TT_TASK | Formworks / Falsework - Prepare & Submit | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Wed Dec 14 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
600 | TT_TASK | Formworks / Falsework - Review & Approval Period (by MTRC) | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Tue Feb 28 18:00:00 IST 2012 |  | COMPLETED
601 | TT_TASK | Formworks / Falsework - Response to comments and Resubmit | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 | Wed Feb 29 08:00:00 IST 2012 | Tue Mar 13 18:00:00 IST 2012 |  | COMPLETED
602 | TT_TASK | Formworks / Falsework - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 | Wed Mar 14 08:00:00 IST 2012 | Sat Apr 14 18:00:00 IDT 2012 |  | COMPLETED
605 | TT_TASK | Layout of Site Hoarding - Prepare and Submit | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 | Mon Jul 19 08:00:00 IDT 2010 | Sat Jul 31 18:00:00 IDT 2010 |  | COMPLETED
606 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (by MTRC) | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 | Mon Aug 02 08:00:00 IDT 2010 | Sat Aug 28 18:00:00 IDT 2010 |  | COMPLETED
607 | TT_TASK | Layout of Site Hoarding - Response to comments and Resubmit | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 | Mon Aug 30 08:00:00 IDT 2010 | Sat Sep 11 18:00:00 IDT 2010 |  | COMPLETED
608 | TT_TASK | Layout of Site Hoarding - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 | Mon Sep 13 08:00:00 IST 2010 | Tue Oct 12 18:00:00 IST 2010 |  | COMPLETED
610 | TT_TASK | Layout of Engineer's Accommodation - Prepare and Submit | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 | Wed Oct 13 08:00:00 IST 2010 | Wed Oct 27 18:00:00 IST 2010 |  | COMPLETED
611 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (by MTRC) | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 | Thu Oct 28 08:00:00 IST 2010 | Wed Nov 24 18:00:00 IST 2010 |  | COMPLETED
612 | TT_TASK | Layout of Engineer's Accommodation - Response to comments and Resubmit | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 | Thu Nov 25 08:00:00 IST 2010 | Wed Dec 08 18:00:00 IST 2010 |  | COMPLETED
613 | TT_TASK | Layout of Engineer's Accommodation - Review and Approval Period (for resubmit) (by MTRC & related Government Authorities | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 | Thu Dec 09 08:00:00 IST 2010 | Sat Jan 08 18:00:00 IST 2011 |  | COMPLETED
615 | TT_TASK | TTMS Assessment Report - Prepare and Submit | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 | Mon Jan 10 08:00:00 IST 2011 | Wed Feb 23 18:00:00 IST 2011 |  | COMPLETED
616 | TT_TASK | TTMS Assessment Report - Review and Approval Period (by MTRC) | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Thu Feb 24 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
617 | TT_TASK | TTMS Assessment Report - Response to comments and Resubmit | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Apr 06 18:00:00 IDT 2011 |  | COMPLETED
618 | TT_TASK | TTMS Assessment Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 | Thu Apr 07 08:00:00 IDT 2011 | Thu May 12 18:00:00 IDT 2011 |  | COMPLETED
619 | TT_TASK | Issue Completed Working Drawings | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 | Fri May 13 08:00:00 IDT 2011 | Thu May 26 18:00:00 IDT 2011 |  | COMPLETED
621 | TT_TASK | DIA Report - Prepare and Submit | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 | Thu Feb 24 08:00:00 IST 2011 | Thu Apr 07 18:00:00 IDT 2011 |  | COMPLETED
622 | TT_TASK | DIA Report - Review and Approval Period (by MTRC) | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 | Fri Apr 08 08:00:00 IDT 2011 | Fri May 13 18:00:00 IDT 2011 |  | COMPLETED
623 | TT_TASK | DIA Report - Response to comments and Resubmit | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 | Sat May 14 08:00:00 IDT 2011 | Wed May 18 18:00:00 IDT 2011 |  | COMPLETED
624 | TT_TASK | DIA Report - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 | Thu May 19 08:00:00 IDT 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
625 | TT_TASK | Issue Completed Working Drawings | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 | Mon Jun 20 08:00:00 IDT 2011 | Thu Jun 23 18:00:00 IDT 2011 |  | COMPLETED
627 | TT_TASK | AIP Design - Prepare & Submit | Wed Sep 23 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 |  | COMPLETED
628 | TT_TASK | AIP Design - Review & Approval Period (by MTR) | Wed Oct 14 08:00:00 IDT 2015 | Wed Nov 11 18:00:00 IST 2015 | Mon Jun 08 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
629 | TT_TASK | AIP Design - Response to comments and Resubmit | Thu Nov 12 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Mon Jun 15 01:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
630 | TT_TASK | AIP Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Jun 22 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
631 | TT_TASK | DDS Design - Prepare & Submit | Wed Jan 13 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Tue Sep 01 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 |  | COMPLETED
632 | TT_TASK | DDS Design - Review & Approval Period (by MTRC) | Fri Feb 26 08:00:00 IST 2016 | Thu Mar 24 18:00:00 IST 2016 | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 12 18:00:00 IDT 2015 |  | COMPLETED
633 | TT_TASK | DDS Design - Response to comments & Resubmit | Tue Mar 29 08:00:00 IDT 2016 | Fri Apr 01 18:00:00 IDT 2016 | Mon Sep 14 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
634 | TT_TASK | DDS Design - Review & Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Apr 02 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 | Mon Sep 21 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
635 | TT_TASK | Issue Completed Working Drawings | Wed Jan 27 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Thu Oct 22 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
637 | TT_TASK | Layout of Barging Point - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
638 | TT_TASK | Layout of Barging Point - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
639 | TT_TASK | Layout of Barging Point - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
640 | TT_TASK | Layout of Barging Point - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
641 | TT_TASK | Loading Ramps - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
642 | TT_TASK | Loading Ramps - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
643 | TT_TASK | Loading Ramps - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
644 | TT_TASK | Loading Ramps - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
645 | TT_TASK | Weighbridge - Prepare and Submit | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 | Wed Nov 30 08:00:00 IST 2011 | Tue Dec 06 18:00:00 IST 2011 |  | COMPLETED
646 | TT_TASK | Weighbridge - Review and Approval Period (by MTRC) | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 | Wed Dec 07 08:00:00 IST 2011 | Thu Dec 29 18:00:00 IST 2011 |  | COMPLETED
647 | TT_TASK | Weighbridge - Response to comments and Resubmit | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 | Fri Dec 30 08:00:00 IST 2011 | Fri Jan 06 18:00:00 IST 2012 |  | COMPLETED
648 | TT_TASK | Weighbridge - Review and Approval Period (for resubmission) (by MTRC & related Government Authorities) | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
652 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
653 | TT_TASK | Pre-drill and guide wall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
654 | TT_TASK | D-wall construction (1084m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
655 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
656 | TT_TASK | Wang Toi Shan Shan Tsuen Road diversion works | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 | Tue Jul 26 08:00:00 IDT 2011 | Thu Dec 15 18:00:00 IST 2011 |  | COMPLETED
658 | TT_TASK | Excavate up to +10.5mPD (369m3) | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Fri Dec 02 18:00:00 IST 2011 |  | COMPLETED
659 | TT_TASK | Install Strut S0 +11.0mPD | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 | Sat Dec 03 08:00:00 IST 2011 | Wed Dec 07 18:00:00 IST 2011 |  | COMPLETED
660 | TT_TASK | Excavate up to +8.0mPD (1525m3) | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 | Tue Dec 06 08:00:00 IST 2011 | Mon Dec 12 18:00:00 IST 2011 |  | COMPLETED
661 | TT_TASK | Install Strut S1 +8.5mPD | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 | Sat Dec 10 08:00:00 IST 2011 | Wed Dec 14 18:00:00 IST 2011 |  | COMPLETED
662 | TT_TASK | Excavate up to +4.5mPD (2135m3) | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 | Tue Dec 13 08:00:00 IST 2011 | Tue Dec 20 18:00:00 IST 2011 |  | COMPLETED
663 | TT_TASK | Install Strut S2 +5.0mPD | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 | Mon Dec 19 08:00:00 IST 2011 | Thu Dec 22 18:00:00 IST 2011 |  | COMPLETED
664 | TT_TASK | Excavate up to +0.5mPD (2440m3) | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 | Wed Dec 21 08:00:00 IST 2011 | Mon Jan 09 18:00:00 IST 2012 |  | COMPLETED
665 | TT_TASK | Install Strut S3 +1.0mPD | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 | Sat Jan 07 08:00:00 IST 2012 | Wed Jan 11 18:00:00 IST 2012 |  | COMPLETED
666 | TT_TASK | Excavate up to -6.5mPD (4340m3) | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 | Tue Jan 10 08:00:00 IST 2012 | Tue May 22 18:00:00 IDT 2012 |  | COMPLETED
667 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Mon May 28 18:00:00 IDT 2012 |  | COMPLETED
668 | TT_TASK | Construction of temporary slab and entrance seal (622m3) | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Thu May 24 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
672 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 08 18:00:00 IST 2014 | Fri Dec 05 08:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
673 | TT_TASK | Erect external formwork (Base Slab) | Tue Dec 09 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 08 08:00:00 IST 2014 | Tue Dec 09 18:00:00 IST 2014 |  | COMPLETED
674 | TT_TASK | Rebar fixing (Base Slab) | Thu Dec 11 08:00:00 IST 2014 | Sat Dec 13 18:00:00 IST 2014 | Wed Dec 10 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
675 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Dec 15 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Mon Dec 15 18:00:00 IST 2014 |  | COMPLETED
676 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Dec 17 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Tue Dec 16 08:00:00 IST 2014 | Tue Dec 16 18:00:00 IST 2014 |  | COMPLETED
677 | TT_TASK | Curing (Base Slab) | Thu Dec 18 08:00:00 IST 2014 | Sat Dec 27 18:00:00 IST 2014 | Wed Dec 17 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
678 | TT_TASK | Removal of formwork (Base Slab) | Fri Dec 19 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 24 18:00:00 IST 2014 |  | COMPLETED
679 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
680 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 | Mon Jun 22 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 |  | COMPLETED
681 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Jun 13 08:00:00 IDT 2015 | Mon Jun 15 18:00:00 IDT 2015 | Thu Jun 25 01:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
682 | TT_TASK | Concreting (Wall & Roof) (444m3) | Tue Jun 16 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
683 | TT_TASK | Curing (Wall & Roof) | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Wed Jul 08 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
684 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Thu Jul 16 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 |  | COMPLETED
685 | TT_TASK | Removal external formwork (Wall) | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Fri Jul 17 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
686 | TT_TASK | Side walkway and cable bracket (360m3) | Sat Jul 18 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Sat Jul 18 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
687 | TT_TASK | Access opening to DC (DC access period) | Tue Oct 06 08:00:00 IDT 2015 | Fri Mar 04 18:00:00 IST 2016 | Tue Oct 06 08:00:00 IDT 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
688 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Sat Dec 12 08:00:00 IST 2015 | Mon Jan 18 18:00:00 IST 2016 | Tue Nov 03 00:00:00 IST 2015 | Mon Nov 30 18:00:00 IST 2015 |  | COMPLETED
690 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 | Tue Apr 12 08:00:00 IDT 2016 | Wed Apr 13 18:00:00 IDT 2016 |  | COMPLETED
691 | TT_TASK | Erect external formwork (Base Slab) | Mon May 23 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Thu Apr 14 08:00:00 IDT 2016 | Fri Apr 15 18:00:00 IDT 2016 |  | COMPLETED
692 | TT_TASK | Rebar fixing (Base Slab) | Wed May 25 08:00:00 IDT 2016 | Fri May 27 18:00:00 IDT 2016 | Sat Apr 16 08:00:00 IDT 2016 | Tue Apr 19 18:00:00 IDT 2016 |  | COMPLETED
693 | TT_TASK | Erect internal kicker formwork (Base Slab) | Sat May 28 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 | Wed Apr 20 08:00:00 IDT 2016 | Thu Apr 21 18:00:00 IDT 2016 |  | COMPLETED
694 | TT_TASK | Concreting (Base Slab) (225m3) | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 | Fri Apr 22 08:00:00 IDT 2016 | Fri Apr 22 18:00:00 IDT 2016 |  | COMPLETED
695 | TT_TASK | Curing (Base Slab) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 08 18:00:00 IDT 2016 | Sat Apr 23 08:00:00 IDT 2016 | Fri Apr 29 18:00:00 IDT 2016 |  | COMPLETED
696 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Sat Apr 30 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
697 | TT_TASK | Removal of formwork (Base Slab) | Tue May 24 08:00:00 IDT 2016 | Tue May 24 18:00:00 IDT 2016 | Mon May 09 08:00:00 IDT 2016 | Tue May 10 18:00:00 IDT 2016 |  | COMPLETED
698 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed May 25 08:00:00 IDT 2016 | Sat May 28 18:00:00 IDT 2016 | Wed May 11 08:00:00 IDT 2016 | Mon May 16 18:00:00 IDT 2016 |  | COMPLETED
699 | TT_TASK | Rebar fixing (Wall & Roof) | Mon May 30 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 17 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 |  | COMPLETED
700 | TT_TASK | Erect external formwork (Wall & Roof) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 03 18:00:00 IDT 2016 | Fri May 20 08:00:00 IDT 2016 | Sat May 21 18:00:00 IDT 2016 |  | COMPLETED
701 | TT_TASK | Concreting (Wall & Roof) (444m3) | Sat Jun 04 08:00:00 IDT 2016 | Sat Jun 04 18:00:00 IDT 2016 | Mon May 23 08:00:00 IDT 2016 | Mon May 23 18:00:00 IDT 2016 |  | COMPLETED
702 | TT_TASK | Curing (Wall & Roof) | Mon Jun 06 08:00:00 IDT 2016 | Tue Jun 14 18:00:00 IDT 2016 | Tue May 24 08:00:00 IDT 2016 | Mon May 30 18:00:00 IDT 2016 |  | COMPLETED
703 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 15 08:00:00 IDT 2016 | Wed Jun 15 18:00:00 IDT 2016 | Tue May 31 08:00:00 IDT 2016 | Tue May 31 18:00:00 IDT 2016 |  | COMPLETED
704 | TT_TASK | Removal external formwork (Wall) | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
705 | TT_TASK | Side walkway and cable bracket (102m3) | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 | Thu Jun 02 08:00:00 IDT 2016 | Fri Jun 17 18:00:00 IDT 2016 |  | COMPLETED
706 | TT_TASK | Access opening to DC (DC access period) | Sat Jun 18 08:00:00 IDT 2016 | Thu Jul 14 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
707 | TT_TASK | Remaining wall and roof slab (Closing of DC access opening) | Fri Jul 15 08:00:00 IDT 2016 | Wed Aug 17 18:00:00 IDT 2016 | Sat Jun 18 08:00:00 IDT 2016 | Sat Jun 18 18:00:00 IDT 2016 |  | COMPLETED
709 | TT_TASK | Backfilling between tunnels (2000m3) | Thu Sep 01 08:00:00 IDT 2016 | Sat Sep 17 18:00:00 IDT 2016 | Tue Sep 13 08:00:00 IDT 2016 | Fri Sep 30 18:00:00 IDT 2016 |  | COMPLETED
710 | TT_TASK | Remove Strut S2 | Mon Oct 03 08:00:00 IDT 2016 | Wed Oct 05 18:00:00 IDT 2016 | Mon Oct 03 08:00:00 IDT 2016 | Tue Oct 11 18:00:00 IDT 2016 |  | COMPLETED
711 | TT_TASK | Backfilling up top S1 Soffit | Thu Oct 06 08:00:00 IDT 2016 | Fri Oct 21 18:00:00 IDT 2016 | Fri Oct 28 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
712 | TT_TASK | Remove Strut S1 | Sat Oct 22 08:00:00 IDT 2016 | Mon Oct 24 18:00:00 IDT 2016 | Tue Oct 11 08:00:00 IDT 2016 | Tue Nov 01 18:00:00 IST 2016 |  | COMPLETED
713 | TT_TASK | Backfilling up top S0 Soffit | Mon Nov 07 08:00:00 IST 2016 | Sat Nov 12 18:00:00 IST 2016 | Tue Nov 01 08:00:00 IST 2016 | Sat Nov 05 18:00:00 IST 2016 |  | COMPLETED
714 | TT_TASK | Remove Strut S0 | Mon Nov 14 08:00:00 IST 2016 | Tue Nov 15 18:00:00 IST 2016 | Mon Nov 07 08:00:00 IST 2016 | Tue Nov 08 18:00:00 IST 2016 |  | COMPLETED
715 | TT_TASK | Backfilling up to ground level | Wed Nov 16 08:00:00 IST 2016 | Fri Nov 18 18:00:00 IST 2016 | Wed Nov 09 08:00:00 IST 2016 | Fri Nov 11 18:00:00 IST 2016 |  | COMPLETED
719 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 | Mon Dec 06 08:00:00 IST 2010 | Tue Dec 14 18:00:00 IST 2010 |  | COMPLETED
720 | TT_TASK | Pre-drilling and guidewall | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 | Wed Dec 15 08:00:00 IST 2010 | Mon Mar 07 18:00:00 IST 2011 |  | COMPLETED
721 | TT_TASK | D-wall construction (1451m3) | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 | Tue Mar 08 08:00:00 IST 2011 | Tue Jul 05 18:00:00 IDT 2011 |  | COMPLETED
722 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 | Wed Jul 06 08:00:00 IDT 2011 | Mon Nov 21 18:00:00 IST 2011 |  | COMPLETED
724 | TT_TASK | Excavate from ground level to formation level -5.5mPD (4559m3) | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 | Tue Nov 29 08:00:00 IST 2011 | Sat May 26 18:00:00 IDT 2012 |  | COMPLETED
725 | TT_TASK | Install rock dowel and tie back | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 | Mon Jan 16 08:00:00 IST 2012 | Thu Jul 12 18:00:00 IDT 2012 |  | COMPLETED
726 | TT_TASK | Placing of blinding layer (South Bound) | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Sat Jun 02 18:00:00 IDT 2012 |  | COMPLETED
727 | TT_TASK | Placing of blinding layer (North Bound) | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
729 | TT_TASK | Construction of Bay 2 to Bay 7a (3565m3) | Mon Jun 04 08:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 | Mon Jun 04 18:00:00 IDT 2012 | Tue Nov 06 18:00:00 IST 2012 |  | COMPLETED
730 | TT_TASK | Side walkway and cable bracket (Southbound) | Fri Oct 02 08:00:00 IDT 2015 | Fri Nov 06 18:00:00 IST 2015 | Fri Oct 02 08:00:00 IDT 2015 | Sat Oct 31 18:00:00 IST 2015 |  | COMPLETED
731 | TT_TASK | Side walkway and cable bracket (Northbound) | Tue May 03 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 |  | COMPLETED
733 | TT_TASK | Backfilling (1344m3) | Wed Nov 07 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 | Wed Nov 07 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
736 | TT_TASK | Scheme Design, Mobilization, Site set up & Material delivery and Instrumentations | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 | Sat Sep 01 08:00:00 IDT 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
737 | TT_TASK | Downstream pipe pile wall construction (45 nos.) and grout curtain (45 nos.) | Mon Nov 12 08:00:00 IST 2012 | Fri Jan 25 18:00:00 IST 2013 | Mon Nov 12 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
738 | TT_TASK | Curtain Grout for cut slope (120 nos.) | Fri Jul 26 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
739 | TT_TASK | Drilling for ground improvement only (if require) | Mon Dec 10 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
740 | TT_TASK | If settlement reach the AAA alarm & action level TAM grouting will apply during excavation | Thu Apr 11 08:00:00 IDT 2013 | Thu May 16 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
741 | TT_TASK | Erection of temporary working platform for Up stream and Installation of Instrumentation System | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
742 | TT_TASK | Upstream pipe pile wall construction adjacent to WTSSTR, (17nos.) | Thu Dec 27 08:00:00 IST 2012 | Mon Jan 28 18:00:00 IST 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
743 | TT_TASK | Upstream pipe pile wall construction at Kam Tin River, 15m depth, 42nos. 1drill rig) | Tue Jan 29 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 | Tue Jan 08 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
744 | TT_TASK | Excavation and soil nail installation | Tue Apr 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
745 | TT_TASK | Excavation for rock and blinding layer | Sat Aug 24 08:00:00 IDT 2013 | Sat Sep 28 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
750 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
751 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
752 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
753 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
754 | TT_TASK | Concreting (164m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
755 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
756 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
757 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
758 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
759 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
760 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
761 | TT_TASK | Concreting (242m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
762 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
763 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
764 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
765 | TT_TASK | Removal internal falsework and formwork for roof | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
766 | TT_TASK | Side walkway and cable bracket (19m3) | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
770 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
771 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
772 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
773 | TT_TASK | Erect internal kicker formwork | Thu Nov 28 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 09 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
774 | TT_TASK | Concreting (121m3) | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
775 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
776 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
777 | TT_TASK | Removal of formwork | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
778 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
779 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 |  | COMPLETED
780 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
781 | TT_TASK | Concreting (121m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
782 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
783 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
784 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
785 | TT_TASK | Removal internal falsework and formwork for roof | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
786 | TT_TASK | Side walkway and cable bracket (38m3) | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 | Tue May 27 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
788 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
789 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Sep 30 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
790 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
791 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
792 | TT_TASK | Concreting (240m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
793 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 14 18:00:00 IDT 2013 |  | COMPLETED
794 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
795 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 |  | COMPLETED
796 | TT_TASK | Erect internal formwork & Falsework | Tue Jan 28 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Wed Oct 23 08:00:00 IDT 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
797 | TT_TASK | Rebar fixing | Wed Jan 15 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
798 | TT_TASK | Erect external formwork | Sat Jan 18 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
799 | TT_TASK | Concreting (240m3) | Tue Jan 21 08:00:00 IST 2014 | Tue Jan 21 18:00:00 IST 2014 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
800 | TT_TASK | Curing | Wed Jan 22 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
801 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jan 22 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
802 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 22 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
803 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
804 | TT_TASK | Side walkway and cable bracket | Fri Mar 13 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Fri Mar 27 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
806 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
807 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
808 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
809 | TT_TASK | Concreting (222m3) | Wed Nov 06 08:00:00 IST 2013 | Wed Nov 06 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
810 | TT_TASK | Curing | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
811 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
812 | TT_TASK | Removal of formwork | Thu Nov 07 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
815 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
816 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
817 | TT_TASK | Rebar fixing | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
818 | TT_TASK | Erect internal kicker formwork | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
819 | TT_TASK | Concreting (111m3) | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
820 | TT_TASK | Curing | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
821 | TT_TASK | Preparation of construction joint for base slab | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
822 | TT_TASK | Removal of formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
823 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
824 | TT_TASK | Rebar fixing | Wed Nov 06 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
825 | TT_TASK | Erect external formwork | Sat Nov 09 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 |  | COMPLETED
826 | TT_TASK | Concreting (220m3) | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Fri Nov 22 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
827 | TT_TASK | Curing | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
828 | TT_TASK | Preparation of construction joint for wall and roof | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
829 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
830 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
831 | TT_TASK | Side walkway and cable bracket (38m3) | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 | Wed May 21 08:00:00 IDT 2014 | Mon May 26 18:00:00 IDT 2014 |  | COMPLETED
833 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
834 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
835 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
836 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
837 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
838 | TT_TASK | Curing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
839 | TT_TASK | Preparation of construction joint for base slab | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
840 | TT_TASK | Removal of formwork | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
841 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
842 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
843 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
844 | TT_TASK | Concreting (327m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
845 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
846 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
847 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
848 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
849 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
851 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 20 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
852 | TT_TASK | Rebar fixing | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
853 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 08:00:00 IDT 2013 |  | COMPLETED
854 | TT_TASK | Concreting (225m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Fri Oct 18 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
855 | TT_TASK | Curing | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
856 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
857 | TT_TASK | Removal of formwork | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
860 | TT_TASK | Placing of waterproof member T-lock & testing | Wed Nov 27 08:00:00 IST 2013 | Wed Nov 27 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
861 | TT_TASK | Erect external formwork | Thu Nov 28 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
862 | TT_TASK | Rebar fixing | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
863 | TT_TASK | Erect internal kicker formwork | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
864 | TT_TASK | Concreting (222m3) | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
865 | TT_TASK | Curing | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Mon Oct 28 18:00:00 IST 2013 |  | COMPLETED
866 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
867 | TT_TASK | Removal of formwork | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
868 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
869 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
870 | TT_TASK | Erect external formwork | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
871 | TT_TASK | Concreting (222m3) | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 |  | COMPLETED
872 | TT_TASK | Curing | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Jan 07 18:00:00 IST 2014 |  | COMPLETED
873 | TT_TASK | Preparation of construction joint for wall and roof | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
874 | TT_TASK | Removal external and internal formwork for wall | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Tue Dec 24 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
875 | TT_TASK | Removal internal falsework and formwork for roof | Mon Feb 10 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
876 | TT_TASK | Side walkway and cable bracket (38m3) | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 |  | COMPLETED
878 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 01 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 | Sat Oct 19 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
879 | TT_TASK | Erect external formwork | Sat Nov 02 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
880 | TT_TASK | Rebar fixing | Mon Nov 04 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
881 | TT_TASK | Erect internal kicker formwork | Wed Nov 06 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
882 | TT_TASK | Concreting (222m3) | Fri Nov 08 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
883 | TT_TASK | Curing | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 16 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
884 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
885 | TT_TASK | Removal of formwork | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
886 | TT_TASK | Erect internal formwork & Falsework | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Mon Nov 04 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
887 | TT_TASK | Rebar fixing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
888 | TT_TASK | Erect external formwork | Mon Dec 23 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
889 | TT_TASK | Concreting (222m3) | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
890 | TT_TASK | Curing | Sat Dec 28 08:00:00 IST 2013 | Thu Jan 09 18:00:00 IST 2014 | Sat Dec 14 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 |  | COMPLETED
891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
892 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 28 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
893 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
894 | TT_TASK | Side walkway and cable bracket (38m3) | Sat Mar 07 08:00:00 IST 2015 | Thu Mar 12 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Thu Mar 26 18:00:00 IST 2015 |  | COMPLETED
896 | TT_TASK | Placing of waterproof member T-lock & testing | Mon Nov 18 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
897 | TT_TASK | Rebar fixing | Tue Nov 19 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Wed Oct 23 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
898 | TT_TASK | Erect external formwork | Fri Nov 22 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 |  | COMPLETED
899 | TT_TASK | Concreting (222m3) | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Sat Oct 26 18:00:00 IDT 2013 |  | COMPLETED
900 | TT_TASK | Curing | Tue Nov 26 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
901 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Tue Oct 29 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
902 | TT_TASK | Removal of formwork | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Oct 28 08:00:00 IST 2013 | Tue Oct 29 18:00:00 IST 2013 |  | COMPLETED
905 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
906 | TT_TASK | Erect external formwork | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 |  | COMPLETED
907 | TT_TASK | Rebar fixing | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
908 | TT_TASK | Erect internal kicker formwork | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
909 | TT_TASK | Concreting (330m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
910 | TT_TASK | Curing | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
911 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
912 | TT_TASK | Removal of formwork | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
913 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
914 | TT_TASK | Rebar fixing | Wed Nov 20 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 | Wed Nov 20 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
915 | TT_TASK | Erect external formwork | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
916 | TT_TASK | Concreting (330m3) | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
917 | TT_TASK | Curing | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
918 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
919 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
920 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
921 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Fri May 09 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
923 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
924 | TT_TASK | Erect external formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
925 | TT_TASK | Rebar fixing | Mon Dec 02 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 |  | COMPLETED
926 | TT_TASK | Erect internal kicker formwork | Wed Dec 04 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Tue Oct 08 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
927 | TT_TASK | Concreting (240m3) | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
928 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
929 | TT_TASK | Preparation of construction joint for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
930 | TT_TASK | Removal of formwork | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
931 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
932 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
933 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
934 | TT_TASK | Concreting (240m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
935 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
936 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
937 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
938 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
939 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
941 | TT_TASK | Placing of waterproof member T-lock & testing | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
942 | TT_TASK | Rebar fixing | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Oct 04 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
943 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 |  | COMPLETED
944 | TT_TASK | Concreting (240m3) | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
945 | TT_TASK | Curing | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
946 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
947 | TT_TASK | Removal of formwork | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
950 | TT_TASK | Placing of waterproof member T-lock & testing | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
951 | TT_TASK | Erect external formwork | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
952 | TT_TASK | Rebar fixing | Fri Dec 20 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
953 | TT_TASK | Erect internal kicker formwork | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
954 | TT_TASK | Concreting (200m3) | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
955 | TT_TASK | Curing | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 20 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
956 | TT_TASK | Preparation of construction joint for base slab | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
957 | TT_TASK | Removal of formwork | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
958 | TT_TASK | Erect internal formwork & Falsework | Fri Nov 29 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
959 | TT_TASK | Rebar fixing | Wed Dec 04 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
960 | TT_TASK | Erect external formwork | Tue Dec 10 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
961 | TT_TASK | Concreting (200m3) | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
962 | TT_TASK | Curing | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
963 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
964 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 13 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
965 | TT_TASK | Removal internal falsework and formwork for roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 |  | COMPLETED
966 | TT_TASK | Side walkway and cable bracket (38m3) | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Thu May 08 18:00:00 IDT 2014 |  | COMPLETED
968 | TT_TASK | Placing of waterproof member T-lock & testing | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
969 | TT_TASK | Erect external formwork | Thu Oct 31 08:00:00 IST 2013 | Thu Oct 31 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
970 | TT_TASK | Rebar fixing | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
971 | TT_TASK | Erect internal kicker formwork | Fri Nov 01 08:00:00 IST 2013 | Sat Nov 02 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
972 | TT_TASK | Concreting (220m3) | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
973 | TT_TASK | Curing | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
974 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
975 | TT_TASK | Removal of formwork | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
976 | TT_TASK | Erect internal formwork & Falsework | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
977 | TT_TASK | Rebar fixing | Wed Dec 18 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
978 | TT_TASK | Erect external formwork | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Wed Nov 27 08:00:00 IST 2013 | Thu Nov 28 18:00:00 IST 2013 |  | COMPLETED
979 | TT_TASK | Concreting (220m3) | Tue Dec 24 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 |  | COMPLETED
980 | TT_TASK | Curing | Fri Dec 27 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 | Sat Nov 30 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
981 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 27 08:00:00 IST 2013 | Fri Dec 27 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 |  | COMPLETED
982 | TT_TASK | Removal external and internal formwork for wall | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
983 | TT_TASK | Removal internal falsework and formwork for roof | Sat Dec 28 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
984 | TT_TASK | Side walkway and cable bracket (38m3) | Mon Mar 02 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 | Mon Mar 16 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
986 | TT_TASK | Placing of waterproof member T-lock & testing | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Mon Sep 23 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
987 | TT_TASK | Rebar fixing | Mon Nov 25 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 | Wed Sep 25 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 |  | COMPLETED
988 | TT_TASK | Erect external formwork | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Sat Sep 28 08:00:00 IDT 2013 | Mon Sep 30 18:00:00 IDT 2013 |  | COMPLETED
989 | TT_TASK | Concreting (222m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Wed Oct 02 18:00:00 IDT 2013 |  | COMPLETED
990 | TT_TASK | Curing | Thu Dec 19 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
991 | TT_TASK | Preparation of construction joint for base slab | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Oct 03 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 |  | COMPLETED
992 | TT_TASK | Removal of formwork | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
994 | TT_TASK | Removal of Temporary Nullah | Sat Mar 01 08:00:00 IST 2014 | Sat Jun 21 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
995 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (5218m3) | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Thu Jan 30 18:00:00 IST 2014 |  | COMPLETED
996 | TT_TASK | Reinstate the permenant Retaining wall of Nullah | Sat Mar 01 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Tue Mar 04 08:00:00 IST 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
997 | TT_TASK | Reinstate Nullah Base of original route | Tue Feb 25 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Tue Feb 25 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
998 | TT_TASK | Reinstate Nullah to original route | Sat Mar 29 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Sat Mar 29 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
999 | TT_TASK | Construction & connect East Box Culvert from Box 6B to KTR | Mon Apr 14 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Mon Feb 10 08:00:00 IST 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
1000 | TT_TASK | Reinstatement of Wang Toi Shan Shan Tsuen Road | Tue Dec 01 08:00:00 IST 2015 | Wed Jul 13 18:00:00 IDT 2016 | Tue Dec 01 08:00:00 IST 2015 | Mon Jul 18 18:00:00 IDT 2016 |  | COMPLETED
1003 | TT_TASK | Pre-drilling at Works Area 4.4 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 | Tue Mar 01 08:00:00 IST 2011 | Wed Nov 30 18:00:00 IST 2011 |  | COMPLETED
1004 | TT_TASK | Site Setup and guide wall | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Thu Dec 01 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1005 | TT_TASK | D-wall construction (3104m3) | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 | Tue Jan 03 08:00:00 IST 2012 | Tue Jul 10 18:00:00 IDT 2012 |  | COMPLETED
1006 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 | Wed Jul 11 08:00:00 IDT 2012 | Fri Aug 31 18:00:00 IDT 2012 |  | COMPLETED
1008 | TT_TASK | Excavate up to +8.0mPD (775m3) | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Sat Sep 01 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1009 | TT_TASK | Install Strut S1 +8.5mPD | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Sat Sep 08 18:00:00 IDT 2012 |  | COMPLETED
1010 | TT_TASK | Excavate up to +4.5mPD (2713m3) | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 | Mon Sep 10 08:00:00 IDT 2012 | Tue Sep 25 18:00:00 IST 2012 |  | COMPLETED
1011 | TT_TASK | Install Strut S2 +5.0mPD | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 | Wed Sep 26 08:00:00 IST 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
1012 | TT_TASK | Excavate up to +0.5mPD (3100m3) | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Wed Oct 03 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 |  | COMPLETED
1013 | TT_TASK | Install Strut S3 +1.0mPD | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1014 | TT_TASK | Excavate up to -3.0mPD (2713m3) | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1015 | TT_TASK | Install Strut S4 -2.5mPD | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Thu Nov 15 18:00:00 IST 2012 |  | COMPLETED
1016 | TT_TASK | Excavate up to -5.5mPD (4952m3) | Fri Nov 16 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1017 | TT_TASK | Placing of blinding layer | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1021 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1022 | TT_TASK | Erect external formwork for base slab | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1023 | TT_TASK | Rebar fixing for base slab | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1024 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 26 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1025 | TT_TASK | Concreting for base slab (350m3) | Thu Jun 27 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1026 | TT_TASK | Curing for base slab | Fri Jun 28 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1027 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1028 | TT_TASK | Removal of formwork for base slab | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1029 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1030 | TT_TASK | Removal strut S4 and S3 | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1032 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1033 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1034 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1035 | TT_TASK | Concreting for wall and roof (489m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1036 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1037 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1038 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1039 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1040 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1043 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1044 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1045 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1046 | TT_TASK | Curing for wall and roof | Sat Jun 22 08:00:00 IDT 2013 | Mon Jul 01 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1047 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1048 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1050 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 10 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Tue Dec 17 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1053 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1054 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1055 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1056 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1057 | TT_TASK | Concreting for base slab (350m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1058 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1059 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1060 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1061 | TT_TASK | Infill concrete in between D-wall and base slab (204m3) | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1062 | TT_TASK | Removal strut S4 and S3 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1064 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1065 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1066 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1067 | TT_TASK | Concreting for wall and roof (489m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1068 | TT_TASK | Curing for wall and roof | Wed Jun 12 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1069 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1070 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 14 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1071 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1072 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Feb 13 08:00:00 IST 2014 | Tue Feb 18 18:00:00 IST 2014 | Tue Oct 22 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1074 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1075 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1076 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1077 | TT_TASK | Concreting for wall and roof (489m3) | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1078 | TT_TASK | Curing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1079 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1080 | TT_TASK | Removal external and internal formwork for wall | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1081 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1082 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 16 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1084 | TT_TASK | Backfilling to 0.5m below the top of C&C Tunnel (+3.46mPD) (2343m3) | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1085 | TT_TASK | Placing 0.5m thk concrete lateral support (+3.96mPD) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1086 | TT_TASK | Removal strut S2 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 23 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1088 | TT_TASK | Construction of Temporary Culvert (open channel) | Tue Jun 25 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1089 | TT_TASK | Temporary box culvert (At Box 6B Area) Saw Cut D-wall | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Tue Apr 08 18:00:00 IDT 2014 |  | COMPLETED
1090 | TT_TASK | Erect 3m high block wall | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Mon Apr 28 18:00:00 IDT 2014 |  | COMPLETED
1091 | TT_TASK | Connection to East Box Culvert (823B portion) | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Tue Apr 29 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 |  | COMPLETED
1092 | TT_TASK | Blinding | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
1093 | TT_TASK | Temporary box culvert (Outside Box 6B Area) Sheet piling | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 |  | COMPLETED
1094 | TT_TASK | ELS Works | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Thu Apr 24 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 |  | COMPLETED
1095 | TT_TASK | Blinding | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
1096 | TT_TASK | Removal of Temporary Culvert and Reinstatement | Fri May 16 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
1098 | TT_TASK | Reinstatement of TOA's | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 |  |  | IN_PROGRESS
1099 | TT_TASK | Hydroseeding works | Tue Nov 01 08:00:00 IST 2016 | Wed Mar 29 18:00:00 IDT 2017 | Tue Nov 01 08:00:00 IST 2016 | Wed Nov 30 18:00:00 IST 2016 |  | COMPLETED
1100 | TT_TASK | Tree Planting works | Thu Sep 01 08:00:00 IDT 2016 | Sat Dec 03 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
1101 | TT_TASK | Woodland Shrub Mix | Thu Sep 01 08:00:00 IDT 2016 | Fri Nov 18 18:00:00 IST 2016 | Thu Sep 01 08:00:00 IDT 2016 |  | 200.0 | IN_PROGRESS
1104 | TT_TASK | Kam Tin River Diversion (Stage 1-3) | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 | Wed Mar 16 08:00:00 IST 2011 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1106 | TT_TASK | Concrete fill up to +8.0mPD near side A mass concrete wall | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Thu Nov 08 18:00:00 IST 2012 |  | COMPLETED
1107 | TT_TASK | Construction of mass concrete wall to +8.0mPD at side A (4 bay CH A80~A120) | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1108 | TT_TASK | Construction of base slab lining and low flow channel (4 bay A9~A10, B8~B9; LFC CH 80~110) | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1109 | TT_TASK | Construction of mass concrete wall to +8.0mPD of side B (3 bay CH B60~B90) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1110 | TT_TASK | Construction of T-shaped retaining wall (1 Bay CH B50~B60) | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1111 | TT_TASK | Soil backfill at side A from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1112 | TT_TASK | Concrete backfill at side B from +5.0mPD to +8.0mPD | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1113 | TT_TASK | Removal strut at +8.5mPD near side A | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1114 | TT_TASK | Concrete fill up to +11.0mPD near side A mass concrete wall | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1115 | TT_TASK | Placing concrete block at side A from +8.0mPD to +11.0mpd at side A (4 bay CH A80~A120) | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1116 | TT_TASK | Soil backfill at side A from +8.0mPD to +11.0mPD | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1117 | TT_TASK | Removal strut at +8.5mPD near side B | Sat Jun 15 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1118 | TT_TASK | Placing concrete block at side B from +8.0mPD to +11.0mPD (4 bay CH B60~B90) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1119 | TT_TASK | Concrete backfill at side B from +8.0mPD to +11.0mPD | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1121 | TT_TASK | Placing temporary concrete block to Up stream at CH30 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 | Thu Nov 01 08:00:00 IST 2012 | Mon Nov 05 18:00:00 IST 2012 |  | COMPLETED
1122 | TT_TASK | Placing temporary concrete block to Up stream at CH160 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 09 18:00:00 IST 2012 |  | COMPLETED
1123 | TT_TASK | Excavation from GL to FL +5.0mPD Up stream (Low flow channel CH 30~60) | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Tue Nov 06 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1124 | TT_TASK | Excavation from GL to FL +5.0mPD Down stream (Low flow channel CH 130~160) | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Sat Nov 10 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1125 | TT_TASK | Construction of T-shaped retaining wall at Up stream of side B (2 Bay CH B30~B50) | Sat Nov 24 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1126 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (3 bay CH B90~B120) | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1127 | TT_TASK | Construction of Up stream base slab lining and low flow channel (6 Bay A1~A4, B3~B4; Low flow channel CH 30~50) | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1128 | TT_TASK | Construction of Down stream base slab lining and low flow channel (5 Bay A14~A16, B14~B15; LFC CH 140~170) | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1129 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Up stream and saw cut D-wall | Fri Jun 14 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1130 | TT_TASK | Remaining excavation from GL to FL +5.0mPD Down stream and saw cut D-wall | Wed Jun 19 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1131 | TT_TASK | Construction of remaining Up stream base slab lining and low flow channel (7 bay A5~A8, B5~B7; LFC CH 50~80) | Thu Jun 27 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1132 | TT_TASK | Construction of remaining Down stream base slab lining and low flow channel (7 bay A11~A13, B10~B13; LFC CH 110~140) | Wed Jul 03 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1134 | TT_TASK | Relocation of temporary concrete block at Up stream for construction of mass concrete wall at side B | Sat Jul 20 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1135 | TT_TASK | Relocation of temporary concrete block at Down stream for construction of mass concrete wall at side B | Tue Jul 23 08:00:00 IDT 2013 | Wed Jul 24 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1136 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Up stream of side B (3 bay CH B0~B30) | Tue Jul 23 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1137 | TT_TASK | Construction of mass concrete wall to +11.0mPD at Down stream of side B (4 bay CH B0~B30) | Thu Jul 25 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1141 | TT_TASK | Application of power supply, environmental permits and construction substation | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 | Mon Jul 19 08:00:00 IDT 2010 | Sat Dec 31 18:00:00 IST 2011 |  | COMPLETED
1142 | TT_TASK | Procurement and Confirmation of the order of 1st tunnel boring machine | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Sep 17 18:00:00 IST 2010 |  | COMPLETED
1143 | TT_TASK | Prepare on-demand bond or bank guarantee for the procurement of TBM and submit to Engineer for approval | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 | Mon Jul 19 08:00:00 IDT 2010 | Fri Nov 19 18:00:00 IST 2010 |  | COMPLETED
1144 | TT_TASK | TBM design and submission for approval | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 | Thu Sep 16 08:00:00 IST 2010 | Fri Oct 15 18:00:00 IST 2010 |  | COMPLETED
1145 | TT_TASK | TBM materials order and delivery to factory | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 | Mon Oct 18 08:00:00 IST 2010 | Tue Feb 15 18:00:00 IST 2011 |  | COMPLETED
1146 | TT_TASK | TBM equipments order and delivery to factory | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 | Wed Dec 01 08:00:00 IST 2010 | Thu Jun 30 18:00:00 IDT 2011 |  | COMPLETED
1147 | TT_TASK | TBM Fabrication | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 | Tue Jan 04 08:00:00 IST 2011 | Fri Mar 25 18:00:00 IST 2011 |  | COMPLETED
1148 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 | Sat Mar 26 08:00:00 IST 2011 | Wed Jul 20 18:00:00 IDT 2011 |  | COMPLETED
1149 | TT_TASK | TBM test Run | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 | Thu Jul 21 08:00:00 IDT 2011 | Wed Aug 10 18:00:00 IDT 2011 |  | COMPLETED
1150 | TT_TASK | TBM disassembly and packing for shipping to HK | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 | Thu Aug 11 08:00:00 IDT 2011 | Fri Sep 09 18:00:00 IDT 2011 |  | COMPLETED
1151 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 | Sat Sep 10 08:00:00 IDT 2011 | Sat Mar 31 18:00:00 IDT 2012 |  | COMPLETED
1152 | TT_TASK | Ground treatment for TBM lanching shaft | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 | Tue Jul 05 08:00:00 IDT 2011 | Sat Oct 22 18:00:00 IST 2011 |  | COMPLETED
1153 | TT_TASK | Ground treatment for Cross Passage Tunnel | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 | Mon Oct 24 08:00:00 IST 2011 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1154 | TT_TASK | Box7A Setup TBM facilities, install noise enclosure and CNP application | Fri Jun 01 08:00:00 IDT 2012 | Sat Jan 26 18:00:00 IST 2013 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1155 | TT_TASK | Notice to Contract 824 the anticipated dates of break out TBM Shaft | Sat Jun 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1156 | TT_TASK | Fabrication of tunnel segment mould | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 | Tue Feb 15 08:00:00 IST 2011 | Sat Jun 18 18:00:00 IDT 2011 |  | COMPLETED
1157 | TT_TASK | Fabrication 50% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 | Thu Sep 01 08:00:00 IDT 2011 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1158 | TT_TASK | Fabrication 100% of North Tunnel South Bound (Downtrack) Precast Lining | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
1159 | TT_TASK | Fabrication 30% of North Tunnel North Bound (Uptrack) Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1160 | TT_TASK | Fabrication 60% of North Tunnel North Bound (Uptrack) Precast Lining | Thu Oct 18 08:00:00 IST 2012 | Thu Feb 21 18:00:00 IST 2013 | Thu Oct 18 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1161 | TT_TASK | Fabrication 100% of North Tunnel North Bound (Uptrack) Precast Lining | Mon Aug 19 08:00:00 IDT 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Dec 03 08:00:00 IST 2012 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1163 | TT_TASK | Assemble, T&C of TBM | Fri Jun 01 08:00:00 IDT 2012 | Fri Nov 02 18:00:00 IST 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Oct 16 00:00:00 IST 2012 |  | COMPLETED
1164 | TT_TASK | TBM drive & lining installation CH123+369 to CH123+283 Initial Drive (86m) | Sat Nov 03 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 | Wed Oct 17 00:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1165 | TT_TASK | Change Plant (Back-up cars) | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1166 | TT_TASK | TBM drive & lining installation CH123+283 to CH123+183 | Thu Jun 27 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1167 | TT_TASK | TBM drive & lining installation CH123+183 to CH123+083 | Wed Jul 03 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1168 | TT_TASK | TBM drive & lining installation CH123+083 to CH122+983 | Sat Jun 01 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1169 | TT_TASK | TBM drive & lining installation CH122+983 to CH122+883 | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1170 | TT_TASK | TBM drive & lining installation CH122+883 to CH122+783 | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Jun 13 08:00:00 IDT 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
1171 | TT_TASK | TBM drive & lining installation CH122+783 to CH122+683 | Sat Nov 02 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1172 | TT_TASK | TBM drive & lining installation CH122+683 to CH122+583 | Tue Dec 03 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Wed Feb 26 18:00:00 IST 2014 |  | COMPLETED
1173 | TT_TASK | TBM drive & lining installation CH122+583 to CH122+491 | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Feb 27 08:00:00 IST 2014 | Sat Aug 16 00:00:00 IDT 2014 |  | COMPLETED
1174 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1175 | TT_TASK | Dis-assemble TBM | Tue Aug 26 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
1176 | TT_TASK | Invert slab, side walkway | Sat Oct 04 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 | Mon Sep 15 08:00:00 IDT 2014 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1177 | TT_TASK | Installation of cable bracket | Tue Dec 30 08:00:00 IST 2014 | Tue Jan 13 18:00:00 IST 2015 | Fri Sep 12 08:00:00 IDT 2014 | Fri Jul 17 18:00:00 IDT 2015 |  | COMPLETED
1178 | TT_TASK | Provision of assess open for DC and modify of strut S1 and S2 at north bound | Tue Nov 04 11:12:00 IST 2014 | Thu Dec 04 11:12:00 IST 2014 | Wed Oct 01 08:00:00 IDT 2014 | Sat Oct 18 18:00:00 IDT 2014 |  | COMPLETED
1180 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Oct 06 13:00:00 IDT 2014 | Mon Oct 20 12:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
1181 | TT_TASK | Assemble, T&C of TBM | Mon Nov 03 08:00:00 IST 2014 | Fri Jan 02 18:00:00 IST 2015 | Sat Oct 04 08:00:00 IDT 2014 | Fri Nov 28 18:00:00 IST 2014 |  | COMPLETED
1182 | TT_TASK | Setup back-up plant for final drive | Sat Nov 15 08:00:00 IST 2014 | Fri Dec 19 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
1183 | TT_TASK | Reinstate of noise enclosure | Sat Dec 06 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Sat Nov 29 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1184 | TT_TASK | TBM drive & lining installation CH123+384 to CH123+284 (Initial Drive) | Sat Dec 06 08:00:00 IST 2014 | Thu Jan 22 18:00:00 IST 2015 | Tue Dec 02 00:00:00 IST 2014 | Tue Jan 20 18:00:00 IST 2015 |  | COMPLETED
1185 | TT_TASK | TBM drive & lining installation CH123+184 to CH123+084 | Wed Jan 21 08:00:00 IST 2015 | Wed Jan 28 18:00:00 IST 2015 | Wed Jan 21 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 |  | COMPLETED
1186 | TT_TASK | TBM drive & lining installation CH123+084 to CH122+984 | Wed Feb 04 08:00:00 IST 2015 | Wed Feb 11 18:00:00 IST 2015 | Thu Feb 12 08:00:00 IST 2015 | Thu Feb 26 18:00:00 IST 2015 |  | COMPLETED
1187 | TT_TASK | TBM drive & lining installation CH122+984 to CH122+884 | Thu Feb 12 08:00:00 IST 2015 | Tue Feb 24 18:00:00 IST 2015 | Fri Feb 27 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1188 | TT_TASK | TBM drive & lining installation CH122+884 to CH122+784 | Tue Mar 10 08:00:00 IST 2015 | Wed Mar 18 18:00:00 IST 2015 | Sat Mar 21 08:00:00 IST 2015 | Wed May 27 18:00:00 IDT 2015 |  | COMPLETED
1189 | TT_TASK | TBM drive & lining installation CH122+784 to CH122+684 | Wed May 06 08:00:00 IDT 2015 | Thu May 14 18:00:00 IDT 2015 | Thu May 28 08:00:00 IDT 2015 | Sat Jul 11 18:00:00 IDT 2015 |  | COMPLETED
1190 | TT_TASK | TBM drive & lining installation CH122+684 to CH122+584 | Fri Jul 03 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Sat Nov 14 18:00:00 IST 2015 |  | COMPLETED
1191 | TT_TASK | TBM drive & lining installation CH122+584 to CH122+506 | Tue Nov 03 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 | Mon Nov 16 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 |  | COMPLETED
1192 | TT_TASK | Position crane for TBM retrieval at Tai Kong Po Shaft | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Mon Dec 07 18:00:00 IST 2015 |  | COMPLETED
1193 | TT_TASK | Dis-assemble TBM | Wed Dec 16 08:00:00 IST 2015 | Fri Jan 22 18:00:00 IST 2016 | Sun Dec 13 08:00:00 IST 2015 | Sun Mar 13 18:00:00 IST 2016 |  | COMPLETED
1194 | TT_TASK | Invert slab, side walkway | Fri Apr 01 08:00:00 IDT 2016 | Thu May 19 18:00:00 IDT 2016 | Mon Mar 14 08:00:00 IST 2016 | Tue May 24 18:00:00 IDT 2016 |  | COMPLETED
1195 | TT_TASK | Installation of cable bracket | Mon Sep 07 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Mar 15 18:00:00 IST 2016 |  | COMPLETED
1196 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Mon Feb 01 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Mon Feb 01 08:00:00 IST 2016 | Mon Feb 22 18:00:00 IST 2016 |  | COMPLETED
1199 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 1 (From Downtrack to Centre of CP) | Thu Apr 10 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Tue Feb 04 08:00:00 IST 2014 | Sat Jun 28 18:00:00 IDT 2014 |  | COMPLETED
1200 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Sun Nov 09 18:00:00 IST 2014 |  | COMPLETED
1201 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1202 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 18:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1203 | TT_TASK | Excavation 0-4mts with Shotcrete | Mon Feb 02 08:00:00 IST 2015 | Tue Feb 17 18:00:00 IST 2015 | Mon Feb 23 08:00:00 IST 2015 | Mon Mar 30 18:00:00 IDT 2015 |  | COMPLETED
1204 | TT_TASK | Invert Concrete | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1205 | TT_TASK | Wall and Roof concrete | Thu Apr 16 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 |  | COMPLETED
1206 | TT_TASK | Dismantle Temporary frame | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 |  | COMPLETED
1207 | TT_TASK | Install Door to Cross Passage (By contract 827) | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Fri Jul 10 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 |  | COMPLETED
1208 | TT_TASK | Install temporary support inside Main Tunnel for CP26 Stage 2 (From Centre of CP to Uptrack) | Sat Oct 17 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 | Mon Sep 07 08:00:00 IDT 2015 | Tue Dec 01 18:00:00 IST 2015 |  | COMPLETED
1209 | TT_TASK | Probe/Grout | Thu Jun 25 08:00:00 IDT 2015 | Mon Jul 06 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Fri Apr 10 18:00:00 IDT 2015 |  | COMPLETED
1210 | TT_TASK | Coring of Segment | Tue Jul 07 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Sat Apr 11 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1211 | TT_TASK | Removal of segment | Sat Jul 11 08:00:00 IDT 2015 | Tue Jul 14 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
1212 | TT_TASK | Excavation 0-4mts with Shotcrete | Wed Jul 15 08:00:00 IDT 2015 | Sat Jul 25 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1213 | TT_TASK | Invert Concrete | Sat Jul 18 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 | Thu May 07 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1214 | TT_TASK | Wall and Roof concrete | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1215 | TT_TASK | Dismantle Temporary frame | Tue Jan 19 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 | Tue Jan 26 08:00:00 IST 2016 | Thu Feb 04 18:00:00 IST 2016 |  | COMPLETED
1216 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Feb 22 08:00:00 IST 2016 | Thu Feb 25 18:00:00 IST 2016 | Fri Feb 05 08:00:00 IST 2016 | Sat Feb 06 18:00:00 IST 2016 |  | COMPLETED
1218 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 1 (From Downtrack to Centre of CP) | Tue Mar 11 08:00:00 IST 2014 | Wed Mar 26 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1219 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Tue Nov 04 08:00:00 IST 2014 | Wed Nov 12 18:00:00 IST 2014 |  | COMPLETED
1220 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Thu Nov 13 08:00:00 IST 2014 | Mon Nov 17 18:00:00 IST 2014 |  | COMPLETED
1221 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Tue Nov 18 08:00:00 IST 2014 | Thu Nov 20 18:00:00 IST 2014 |  | COMPLETED
1222 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Sat Nov 22 08:00:00 IST 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1223 | TT_TASK | Invert Concrete | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Wed Dec 03 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 |  | COMPLETED
1224 | TT_TASK | Wall and Roof concrete | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Sat Dec 13 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1225 | TT_TASK | Dismantle Temporary frame | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 | Fri Jan 02 08:00:00 IST 2015 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1226 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1227 | TT_TASK | Install temporary support inside Main Tunnel for CP27 Stage 2 (From Centre of CP to Uptrack) | Thu May 21 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Mar 09 08:00:00 IST 2015 | Fri Mar 20 18:00:00 IST 2015 |  | COMPLETED
1228 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Mon May 04 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1229 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
1230 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 |  | COMPLETED
1231 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 22 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
1232 | TT_TASK | Invert Concrete | Sat Aug 08 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Wed Jul 08 18:00:00 IDT 2015 |  | COMPLETED
1233 | TT_TASK | Wall and Roof concrete | Tue Aug 25 08:00:00 IDT 2015 | Mon Sep 07 18:00:00 IDT 2015 | Thu Jul 09 08:00:00 IDT 2015 | Sat Aug 15 18:00:00 IDT 2015 |  | COMPLETED
1234 | TT_TASK | Dismantle Temporary frame | Tue Sep 22 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 | Mon Aug 17 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 |  | COMPLETED
1235 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1237 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 1 (From Downtrack to Centre of CP) | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Sat May 24 18:00:00 IDT 2014 |  | COMPLETED
1238 | TT_TASK | Probe/Grout | Tue Nov 04 11:12:00 IST 2014 | Fri Nov 14 11:12:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
1239 | TT_TASK | Coring of Segment | Fri Nov 14 11:12:00 IST 2014 | Wed Nov 19 11:12:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
1240 | TT_TASK | Removal of segment | Wed Nov 19 11:12:00 IST 2014 | Sat Nov 22 11:12:00 IST 2014 | Fri Nov 14 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 |  | COMPLETED
1241 | TT_TASK | Excavation 0-4mts with Shotcrete | Sat Nov 22 11:12:00 IST 2014 | Tue Dec 09 11:12:00 IST 2014 | Mon Nov 17 08:00:00 IST 2014 | Sat Nov 29 18:00:00 IST 2014 |  | COMPLETED
1242 | TT_TASK | Invert Concrete | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 | Mon Dec 01 08:00:00 IST 2014 | Wed Dec 10 18:00:00 IST 2014 |  | COMPLETED
1243 | TT_TASK | Wall and Roof concrete | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 | Thu Dec 11 08:00:00 IST 2014 | Mon Dec 29 18:00:00 IST 2014 |  | COMPLETED
1244 | TT_TASK | Dismantle Temporary frame | Tue Dec 30 08:00:00 IST 2014 | Wed Jan 07 18:00:00 IST 2015 | Tue Dec 30 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
1245 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 | Sat Jan 10 08:00:00 IST 2015 | Wed Jan 14 18:00:00 IST 2015 |  | COMPLETED
1246 | TT_TASK | Install temporary support inside Main Tunnel for CP28 Stage 2 (From Centre of CP to Uptrack) | Fri May 08 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Mar 06 18:00:00 IST 2015 |  | COMPLETED
1247 | TT_TASK | Probe/Grout | Mon Jul 06 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Sat May 02 18:00:00 IDT 2015 |  | COMPLETED
1248 | TT_TASK | Coring of Segment | Thu Jul 16 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 | Sat May 02 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
1249 | TT_TASK | Removal of segment | Tue Jul 21 08:00:00 IDT 2015 | Thu Jul 23 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Thu May 07 18:00:00 IDT 2015 |  | COMPLETED
1250 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Jul 24 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Fri May 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 |  | COMPLETED
1251 | TT_TASK | Invert Concrete | Wed Aug 05 08:00:00 IDT 2015 | Fri Aug 14 18:00:00 IDT 2015 | Wed Jun 10 08:00:00 IDT 2015 | Fri Jun 19 18:00:00 IDT 2015 |  | COMPLETED
1252 | TT_TASK | Wall and Roof concrete | Tue Sep 15 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Wed Aug 26 18:00:00 IDT 2015 |  | COMPLETED
1253 | TT_TASK | Dismantle Temporary frame | Sat Oct 17 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Oct 08 18:00:00 IDT 2015 |  | COMPLETED
1254 | TT_TASK | Install Door to Cross Passage (By contract 827) | Sat Dec 12 08:00:00 IST 2015 | Wed Dec 16 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1258 | TT_TASK | Site Possession and Site set up and Mobilization | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 | Mon Apr 18 08:00:00 IDT 2011 | Mon Jul 11 18:00:00 IDT 2011 |  | COMPLETED
1259 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1260 | TT_TASK | D-wall construction (1192m3) | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Thu Mar 15 18:00:00 IST 2012 |  | COMPLETED
1261 | TT_TASK | Sonic test, shear pin, toe grout and pumping test | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Fri Mar 16 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1262 | TT_TASK | Construct capping beam, cobble, etc. (including bay 6 and 5) | Sat Oct 27 08:00:00 IST 2012 | Sat Feb 16 18:00:00 IST 2013 | Sat Oct 27 08:00:00 IST 2012 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1264 | TT_TASK | Excavate up to +22.0mPD (1860m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1265 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Tue Jun 05 18:00:00 IDT 2012 |  | COMPLETED
1266 | TT_TASK | Excavate up to +16.5mPD (3410m3) | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 | Wed Jun 06 08:00:00 IDT 2012 | Tue Jul 03 18:00:00 IDT 2012 |  | COMPLETED
1267 | TT_TASK | Install Strut S2 +17.0mPD | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 | Wed Jul 04 08:00:00 IDT 2012 | Sat Jul 07 18:00:00 IDT 2012 |  | COMPLETED
1268 | TT_TASK | Excavate up to +11.0mPD (3410m3) | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 | Mon Jul 09 08:00:00 IDT 2012 | Thu Aug 02 18:00:00 IDT 2012 |  | COMPLETED
1269 | TT_TASK | Install Strut S3 +11.5mPD | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 | Fri Aug 03 08:00:00 IDT 2012 | Tue Aug 07 18:00:00 IDT 2012 |  | COMPLETED
1270 | TT_TASK | Excavate up to +7.0mPD (2480m3) | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 | Wed Aug 08 08:00:00 IDT 2012 | Sat Aug 25 18:00:00 IDT 2012 |  | COMPLETED
1271 | TT_TASK | Install Strut S4 +7.5mPD | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Mon Aug 27 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
1272 | TT_TASK | Excavate up to +3.5mPD (2170m3) | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 15 18:00:00 IDT 2012 |  | COMPLETED
1273 | TT_TASK | Install Strut S5 +4.0mPD | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Mon Sep 17 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1274 | TT_TASK | Excavate up to formation (2294m3) | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1275 | TT_TASK | Construct temp. 500mm thick plain concrete base slab | Thu Oct 18 08:00:00 IST 2012 | Fri Oct 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Sat Oct 20 08:00:00 IST 2012 |  | COMPLETED
1276 | TT_TASK | Removal of South Bound strut to +9.50mPD | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 | Mon Oct 22 08:00:00 IST 2012 | Thu Oct 25 18:00:00 IST 2012 |  | COMPLETED
1277 | TT_TASK | Removal of North Bound strut to +9.50mPD | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Mon Oct 29 18:00:00 IST 2012 |  | COMPLETED
1278 | TT_TASK | Construct temp. 500mm thick TBM concrete base slab | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 | Fri Oct 26 08:00:00 IST 2012 | Sat Nov 10 18:00:00 IST 2012 |  | COMPLETED
1279 | TT_TASK | Construction entrance seal for TBM at South Bound | Mon Nov 12 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 | Fri Nov 16 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1280 | TT_TASK | Construction entrance seal for TBM at North Bound | Sat Jul 20 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1281 | TT_TASK | Saw cut South Bound diaphragm wall | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1282 | TT_TASK | Saw cut North Bound diaphragm wall | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1286 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Thu Sep 04 08:00:00 IDT 2014 | Fri Sep 05 18:00:00 IDT 2014 | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 |  | COMPLETED
1287 | TT_TASK | Erect external formwork (Base Slab) | Sat Sep 06 08:00:00 IDT 2014 | Mon Sep 08 18:00:00 IDT 2014 | Sat Jul 19 08:00:00 IDT 2014 | Mon Jul 21 18:00:00 IDT 2014 |  | COMPLETED
1288 | TT_TASK | Rebar fixing (Base Slab) | Wed Sep 10 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Tue Jul 22 08:00:00 IDT 2014 | Sat Jul 26 18:00:00 IDT 2014 |  | COMPLETED
1289 | TT_TASK | Erect internal kicker formwork (Base Slab) | Mon Sep 15 08:00:00 IDT 2014 | Wed Sep 17 18:00:00 IDT 2014 | Sun Jul 27 08:00:00 IDT 2014 | Thu Jul 31 18:00:00 IDT 2014 |  | COMPLETED
1290 | TT_TASK | Clearing and inspection (Base Slab) | Fri Aug 08 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 | Thu Aug 14 08:00:00 IDT 2014 | Thu Aug 14 18:00:00 IDT 2014 |  | COMPLETED
1291 | TT_TASK | Concreting (Base Slab) (225m3) | Sat Aug 09 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 | Fri Aug 15 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
1292 | TT_TASK | Curing (Base Slab) | Mon Aug 11 08:00:00 IDT 2014 | Mon Aug 18 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
1293 | TT_TASK | Removal of formwork (Base Slab) | Tue Aug 12 08:00:00 IDT 2014 | Tue Aug 12 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Mon Aug 25 18:00:00 IDT 2014 |  | COMPLETED
1294 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Wed Aug 13 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 | Tue Aug 26 08:00:00 IDT 2014 | Mon Sep 15 18:00:00 IDT 2014 |  | COMPLETED
1295 | TT_TASK | Rebar fixing (Wall & Roof) | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 | Tue Sep 16 08:00:00 IDT 2014 | Fri Sep 19 18:00:00 IDT 2014 |  | COMPLETED
1296 | TT_TASK | Erect external formwork (Wall & Roof) | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 | Sat Sep 20 08:00:00 IDT 2014 | Wed Sep 24 18:00:00 IDT 2014 |  | COMPLETED
1297 | TT_TASK | Clearing and inspection (Wall & Roof) | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 | Thu Sep 25 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
1298 | TT_TASK | Concreting (Wall & Roof) (450m3) | Fri Oct 10 08:00:00 IDT 2014 | Fri Oct 10 18:00:00 IDT 2014 | Sat Oct 25 08:00:00 IDT 2014 | Sat Oct 25 18:00:00 IDT 2014 |  | COMPLETED
1299 | TT_TASK | Curing (Wall & Roof) | Sat Oct 11 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Fri Nov 07 18:00:00 IST 2014 |  | COMPLETED
1300 | TT_TASK | Removal external formwork (Wall) | Tue Oct 14 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Thu Oct 30 08:00:00 IST 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1301 | TT_TASK | Removal internal falsework (Wall & Roof) | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 | Sat Nov 08 08:00:00 IST 2014 | Mon Nov 10 18:00:00 IST 2014 |  | COMPLETED
1302 | TT_TASK | Side walkway and cable bracket (102m3) | Sat Oct 18 08:00:00 IDT 2014 | Wed Oct 29 18:00:00 IST 2014 | Mon Sep 01 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
1304 | TT_TASK | Placing of waterproof member T-lock & testing (Base Slab) | Wed Nov 11 08:00:00 IST 2015 | Thu Nov 12 18:00:00 IST 2015 | Mon Oct 19 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1305 | TT_TASK | Erect external formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Sat Nov 14 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Mon Oct 26 18:00:00 IST 2015 |  | COMPLETED
1306 | TT_TASK | Rebar fixing (Base Slab) | Mon Nov 16 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Tue Oct 27 08:00:00 IST 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1307 | TT_TASK | Erect internal kicker formwork (Base Slab) | Fri Nov 20 08:00:00 IST 2015 | Mon Nov 23 18:00:00 IST 2015 | Sat Oct 31 08:00:00 IST 2015 | Mon Nov 09 18:00:00 IST 2015 |  | COMPLETED
1308 | TT_TASK | Clearing and inspection (Base Slab) | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 | Tue Nov 10 08:00:00 IST 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
1309 | TT_TASK | Concreting (Base Slab) (225m3) | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Wed Nov 11 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1310 | TT_TASK | Curing (Base Slab) | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 | Thu Nov 12 08:00:00 IST 2015 | Thu Nov 19 18:00:00 IST 2015 |  | COMPLETED
1311 | TT_TASK | Removal of formwork (Base Slab) | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Fri Nov 13 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 |  | COMPLETED
1312 | TT_TASK | Erect internal formwork & Falsework (Wall & Roof) | Tue Dec 01 08:00:00 IST 2015 | Tue Dec 08 18:00:00 IST 2015 | Tue Dec 01 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
1313 | TT_TASK | Rebar fixing (Wall & Roof) | Wed Dec 09 08:00:00 IST 2015 | Sat Dec 12 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Sat Jan 02 18:00:00 IST 2016 |  | COMPLETED
1314 | TT_TASK | Erect external formwork (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Mon Jan 04 08:00:00 IST 2016 | Thu Jan 07 18:00:00 IST 2016 |  | COMPLETED
1315 | TT_TASK | Clearing and inspection (Wall & Roof) | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 | Fri Jan 08 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
1316 | TT_TASK | Concreting (Wall & Roof) (450m3) | Mon Jan 11 08:00:00 IST 2016 | Mon Jan 11 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Sat Jan 09 18:00:00 IST 2016 |  | COMPLETED
1317 | TT_TASK | Curing (Wall & Roof) | Tue Jan 12 08:00:00 IST 2016 | Wed Jan 27 18:00:00 IST 2016 | Mon Jan 11 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
1318 | TT_TASK | Removal external formwork (Wall ) | Thu Jan 14 08:00:00 IST 2016 | Fri Jan 15 18:00:00 IST 2016 | Wed Jan 13 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
1319 | TT_TASK | Removal internal falsework, formwork and reproping (Wall & Roof) | Thu Jan 28 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Tue Jan 26 18:00:00 IST 2016 |  | COMPLETED
1320 | TT_TASK | Side walkway and cable bracket (102m3) | Wed Dec 23 08:00:00 IST 2015 | Wed Jan 06 18:00:00 IST 2016 | Wed Nov 11 08:00:00 IST 2015 | Mon Feb 01 18:00:00 IST 2016 |  | COMPLETED
1322 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 | Tue Feb 02 08:00:00 IST 2016 | Wed Feb 03 18:00:00 IST 2016 |  | COMPLETED
1323 | TT_TASK | Protection screening to waterproofing member (Wall & Roof) | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 | Thu Feb 04 08:00:00 IST 2016 | Thu Feb 18 18:00:00 IST 2016 |  | COMPLETED
1324 | TT_TASK | Backfilling to 0.5m below S3 (+11.0mPD) (3486m3) | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 | Fri Feb 19 08:00:00 IST 2016 | Thu Mar 10 18:00:00 IST 2016 |  | COMPLETED
1325 | TT_TASK | Removal strut S3 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 | Fri Mar 11 08:00:00 IST 2016 | Sat Mar 12 18:00:00 IST 2016 |  | COMPLETED
1326 | TT_TASK | Backfilling to 0.5m below S2 (+16.5mPD) (3410m3) | Wed Mar 16 08:00:00 IST 2016 | Fri Apr 08 18:00:00 IDT 2016 | Wed Mar 16 08:00:00 IST 2016 | Tue Apr 12 18:00:00 IDT 2016 |  | COMPLETED
1327 | TT_TASK | Removal strut S2 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 | Wed Apr 13 08:00:00 IDT 2016 | Thu Apr 14 18:00:00 IDT 2016 |  | COMPLETED
1328 | TT_TASK | Backfilling to 0.5m below S1 (+22.0mPD) (3410m3) | Fri Apr 15 08:00:00 IDT 2016 | Thu May 05 18:00:00 IDT 2016 | Fri Apr 15 08:00:00 IDT 2016 | Sat Apr 30 18:00:00 IDT 2016 |  | COMPLETED
1329 | TT_TASK | Removal strut S1 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 | Tue May 03 08:00:00 IDT 2016 | Wed May 04 18:00:00 IDT 2016 |  | COMPLETED
1330 | TT_TASK | Backfilling to original ground level (approx. +25.0mPD) (1860m3) | Thu May 05 08:00:00 IDT 2016 | Tue May 17 18:00:00 IDT 2016 | Thu May 05 08:00:00 IDT 2016 | Wed Jun 01 18:00:00 IDT 2016 |  | COMPLETED
1333 | TT_TASK | Pre-drilling and guidewall | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 | Tue Jul 12 08:00:00 IDT 2011 | Wed Sep 14 18:00:00 IDT 2011 |  | COMPLETED
1334 | TT_TASK | D-wall construction (2844m3) | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Sep 15 08:00:00 IDT 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1335 | TT_TASK | Sonic test, shear pin, toe grout and pumping Test | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Thu May 17 18:00:00 IDT 2012 |  | COMPLETED
1337 | TT_TASK | Excavate up to +22.0mPD (3720m3) | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 | Fri May 18 08:00:00 IDT 2012 | Thu May 31 18:00:00 IDT 2012 |  | COMPLETED
1338 | TT_TASK | Install Strut S1 +22.5mPD | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 | Fri Jun 01 08:00:00 IDT 2012 | Thu Jun 07 18:00:00 IDT 2012 |  | COMPLETED
1339 | TT_TASK | Excavate up to +16.5mPD (4880m3) | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 | Fri Jun 08 08:00:00 IDT 2012 | Wed Jun 27 18:00:00 IDT 2012 |  | COMPLETED
1340 | TT_TASK | Install Strut S2 +17.0mPD | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 | Thu Jun 28 08:00:00 IDT 2012 | Thu Jul 05 18:00:00 IDT 2012 |  | COMPLETED
1341 | TT_TASK | Excavate up to +11.0mPD (6820m3) | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 | Fri Jul 06 08:00:00 IDT 2012 | Wed Aug 01 18:00:00 IDT 2012 |  | COMPLETED
1342 | TT_TASK | Install Strut S3 +11.5mPD | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 | Thu Aug 02 08:00:00 IDT 2012 | Wed Aug 08 18:00:00 IDT 2012 |  | COMPLETED
1343 | TT_TASK | Excavate up to +7.0mPD (4960m3) | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 | Thu Aug 09 08:00:00 IDT 2012 | Tue Aug 28 18:00:00 IDT 2012 |  | COMPLETED
1344 | TT_TASK | Install Strut S4 +7.5mPD | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 | Wed Aug 29 08:00:00 IDT 2012 | Tue Sep 04 18:00:00 IDT 2012 |  | COMPLETED
1345 | TT_TASK | Excavate up to +3.5mPD (4340m3) | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 | Wed Sep 05 08:00:00 IDT 2012 | Thu Sep 20 18:00:00 IDT 2012 |  | COMPLETED
1346 | TT_TASK | Install Strut S5 +4.0mPD | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 | Fri Sep 21 08:00:00 IDT 2012 | Thu Sep 27 18:00:00 IST 2012 |  | COMPLETED
1347 | TT_TASK | Excavate up to formation (4960m3) | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 | Fri Sep 28 08:00:00 IST 2012 | Sat Oct 13 18:00:00 IST 2012 |  | COMPLETED
1348 | TT_TASK | Construct temp. 500mm thick plain concrete base slab at Bay 5 & 6 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Wed Oct 17 18:00:00 IST 2012 |  | COMPLETED
1349 | TT_TASK | Excavation to formation and place blinding Bay 4a | Thu Oct 18 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Oct 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1350 | TT_TASK | Excavation to formation and place blinding Bay 4b | Fri Jun 21 08:00:00 IDT 2013 | Fri Jul 12 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1351 | TT_TASK | Excavation to formation and place blinding Bay3 | Sat Jul 13 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1352 | TT_TASK | Excavation to formation and place blinding Bay2 to Bay1 | Wed Jul 24 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1356 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 | Mon Nov 12 08:00:00 IST 2012 | Mon Nov 12 18:00:00 IST 2012 |  | COMPLETED
1357 | TT_TASK | Erect external formwork for base slab | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Wed Nov 14 18:00:00 IST 2012 |  | COMPLETED
1358 | TT_TASK | Rebar fixing for base slab | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Thu Nov 15 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1359 | TT_TASK | Erect internal kicker formwork for base slab | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Sat Nov 17 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
1360 | TT_TASK | Concreting for base slab (363m3) | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Mon Nov 19 18:00:00 IST 2012 |  | COMPLETED
1361 | TT_TASK | Curing for base slab | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1362 | TT_TASK | Preparation of construction joint for base slab | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 | Tue Nov 20 08:00:00 IST 2012 | Tue Nov 20 18:00:00 IST 2012 |  | COMPLETED
1363 | TT_TASK | Removal of formwork for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1364 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1365 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 27 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1366 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1367 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Tue Jan 08 08:00:00 IST 2013 | Tue Jan 08 18:00:00 IST 2013 |  | COMPLETED
1368 | TT_TASK | Curing for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 09 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1369 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1370 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 10 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Wed Jan 23 18:00:00 IST 2013 |  | COMPLETED
1371 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 19 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jan 24 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1372 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 08 08:00:00 IST 2015 | Tue Jan 13 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1374 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 | Tue Nov 13 08:00:00 IST 2012 | Tue Nov 13 18:00:00 IST 2012 |  | COMPLETED
1375 | TT_TASK | Erect external formwork for base slab | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 | Wed Nov 14 08:00:00 IST 2012 | Fri Nov 16 18:00:00 IST 2012 |  | COMPLETED
1376 | TT_TASK | Rebar fixing for base slab | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Mon Nov 19 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1377 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Thu Nov 22 18:00:00 IST 2012 |  | COMPLETED
1378 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Fri Nov 23 18:00:00 IST 2012 |  | COMPLETED
1379 | TT_TASK | Curing for base slab | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Fri Nov 23 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1380 | TT_TASK | Preparation of construction joint for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1381 | TT_TASK | Removal of formwork for base slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1382 | TT_TASK | Rebar fixing for central slab | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Sat Nov 24 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1383 | TT_TASK | Erect external formwork for central slab | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1384 | TT_TASK | Concreting for central slab (450m3) | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
1385 | TT_TASK | Curing for central slab | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Mon Dec 03 18:00:00 IST 2012 |  | COMPLETED
1386 | TT_TASK | Preparation of construction joint for central slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1387 | TT_TASK | Removal of formwork for central slab | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1388 | TT_TASK | Removal strut S5 and S4 | Thu Nov 29 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1389 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1390 | TT_TASK | Rebar fixing for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1391 | TT_TASK | Erect external formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Wed Jan 02 08:00:00 IST 2013 | Fri Jan 04 18:00:00 IST 2013 |  | COMPLETED
1392 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1393 | TT_TASK | Curing for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1394 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1395 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 08 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1396 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1397 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Nov 19 08:00:00 IST 2015 | Tue Nov 24 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Tue Oct 13 18:00:00 IDT 2015 |  | COMPLETED
1400 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1401 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1402 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1403 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1404 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1405 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1406 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1407 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1408 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1409 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1410 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 10 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1411 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 15 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1412 | TT_TASK | Curing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1413 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1414 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jan 30 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1415 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1416 | TT_TASK | Side walkway and cable bracket | Fri Jan 02 08:00:00 IST 2015 | Wed Jan 07 18:00:00 IST 2015 | Mon Dec 01 08:00:00 IST 2014 | Fri Dec 05 18:00:00 IST 2014 |  | COMPLETED
1418 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1419 | TT_TASK | Erect external formwork for base slab | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1420 | TT_TASK | Rebar fixing for base slab | Mon Jun 03 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1421 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1422 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1423 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1424 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1425 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1426 | TT_TASK | Rebar fixing for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1427 | TT_TASK | Erect external formwork for central slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1428 | TT_TASK | Concreting for central slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1429 | TT_TASK | Curing for central slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Wed Dec 19 18:00:00 IST 2012 |  | COMPLETED
1430 | TT_TASK | Preparation of construction joint for central slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1431 | TT_TASK | Removal of formwork for central slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Fri Dec 21 18:00:00 IST 2012 |  | COMPLETED
1432 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 31 18:00:00 IST 2012 |  | COMPLETED
1433 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 26 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1434 | TT_TASK | Rebar fixing for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Sat Jul 13 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1435 | TT_TASK | Erect external formwork for wall | Mon Jul 15 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1436 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1437 | TT_TASK | Curing for wall and roof | Sun Jul 21 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1438 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1439 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 22 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1440 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 31 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1441 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Sep 16 08:00:00 IDT 2015 | Mon Sep 21 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1443 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Tue Nov 27 08:00:00 IST 2012 | Tue Nov 27 18:00:00 IST 2012 |  | COMPLETED
1444 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Wed Nov 28 08:00:00 IST 2012 | Sat Dec 01 18:00:00 IST 2012 |  | COMPLETED
1445 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 03 08:00:00 IST 2012 | Wed Dec 05 18:00:00 IST 2012 |  | COMPLETED
1446 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 06 08:00:00 IST 2012 | Thu Dec 06 18:00:00 IST 2012 |  | COMPLETED
1447 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 07 08:00:00 IST 2012 | Fri Dec 07 18:00:00 IST 2012 |  | COMPLETED
1448 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Dec 08 08:00:00 IST 2012 | Fri Dec 14 18:00:00 IST 2012 |  | COMPLETED
1449 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1450 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1451 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1452 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1453 | TT_TASK | Erect external formwork for wall | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1454 | TT_TASK | Concreting for wall and roof (444m3) | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1455 | TT_TASK | Curing for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1456 | TT_TASK | Removal external and internal formwork for wall | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1457 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Sat Feb 09 18:00:00 IST 2013 |  | COMPLETED
1458 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Nov 09 08:00:00 IST 2015 | Fri Nov 13 18:00:00 IST 2015 | Tue Oct 06 08:00:00 IDT 2015 | Sat Oct 10 18:00:00 IDT 2015 |  | COMPLETED
1461 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1462 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Sat Dec 15 18:00:00 IST 2012 |  | COMPLETED
1463 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 15 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1464 | TT_TASK | Erect internal kicker formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 17 08:00:00 IST 2012 | Mon Dec 17 18:00:00 IST 2012 |  | COMPLETED
1465 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Tue Dec 18 08:00:00 IST 2012 | Tue Dec 18 18:00:00 IST 2012 |  | COMPLETED
1466 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Dec 19 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1467 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Fri Dec 28 18:00:00 IST 2012 |  | COMPLETED
1468 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1469 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Wed Jan 02 18:00:00 IST 2013 |  | COMPLETED
1470 | TT_TASK | Curing | Wed Jun 12 08:00:00 IDT 2013 | Wed Jun 12 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1471 | TT_TASK | Removal strut S5 and S4 | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Mon Jan 07 18:00:00 IST 2013 |  | COMPLETED
1473 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 29 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1474 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Jan 04 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1475 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1476 | TT_TASK | Concreting for wall and roof (450m3) | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Tue Jan 15 18:00:00 IST 2013 |  | COMPLETED
1477 | TT_TASK | Curing for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Wed Jan 16 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1478 | TT_TASK | Preparation of construction joint for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1479 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Wed Jan 30 18:00:00 IST 2013 |  | COMPLETED
1480 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jun 29 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 | Thu Jan 31 08:00:00 IST 2013 | Thu Jan 31 18:00:00 IST 2013 |  | COMPLETED
1481 | TT_TASK | Side walkway and cable bracket | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 | Wed Dec 24 08:00:00 IST 2014 | Wed Dec 31 18:00:00 IST 2014 |  | COMPLETED
1483 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Jan 03 18:00:00 IST 2013 |  | COMPLETED
1484 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1485 | TT_TASK | Erect external formwork for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1486 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1487 | TT_TASK | Curing for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Thu Jul 04 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1488 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1489 | TT_TASK | Removal external wall formwork for wall | Wed Jun 26 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Feb 08 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1490 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jul 05 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1491 | TT_TASK | Side walkway and cable bracket | Fri Sep 04 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
1494 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 | Wed Nov 21 08:00:00 IST 2012 | Wed Nov 21 18:00:00 IST 2012 |  | COMPLETED
1495 | TT_TASK | Erect external formwork for base slab | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 | Thu Nov 22 08:00:00 IST 2012 | Sat Nov 24 18:00:00 IST 2012 |  | COMPLETED
1496 | TT_TASK | Rebar fixing for base slab | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 | Mon Nov 26 08:00:00 IST 2012 | Wed Nov 28 18:00:00 IST 2012 |  | COMPLETED
1497 | TT_TASK | Erect internal kicker formwork for base slab | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 | Thu Nov 29 08:00:00 IST 2012 | Thu Nov 29 18:00:00 IST 2012 |  | COMPLETED
1498 | TT_TASK | Concreting for base slab (363m3) | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 | Fri Nov 30 08:00:00 IST 2012 | Fri Nov 30 18:00:00 IST 2012 |  | COMPLETED
1499 | TT_TASK | Curing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Dec 01 08:00:00 IST 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1500 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Dec 10 08:00:00 IST 2012 | Mon Dec 10 18:00:00 IST 2012 |  | COMPLETED
1501 | TT_TASK | Removal of formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Tue Dec 11 08:00:00 IST 2012 | Tue Dec 11 18:00:00 IST 2012 |  | COMPLETED
1502 | TT_TASK | Shear beam | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Wed Dec 12 08:00:00 IST 2012 | Wed Dec 12 18:00:00 IST 2012 |  | COMPLETED
1503 | TT_TASK | Curing | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Thu Dec 13 08:00:00 IST 2012 | Thu Dec 13 18:00:00 IST 2012 |  | COMPLETED
1504 | TT_TASK | Removal strut S5 and S4 | Wed Jun 19 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1506 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Mon Dec 24 08:00:00 IST 2012 | Sat Dec 29 18:00:00 IST 2012 |  | COMPLETED
1507 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Dec 31 08:00:00 IST 2012 | Sat Jan 05 18:00:00 IST 2013 |  | COMPLETED
1508 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 13 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 07 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1509 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1510 | TT_TASK | Curing for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1511 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Thu Jan 24 18:00:00 IST 2013 |  | COMPLETED
1512 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 19 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1513 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 28 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1514 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 | Thu Dec 18 08:00:00 IST 2014 | Tue Dec 23 18:00:00 IST 2014 |  | COMPLETED
1516 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Jan 05 08:00:00 IST 2013 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1517 | TT_TASK | Rebar fixing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 17 18:00:00 IST 2013 |  | COMPLETED
1518 | TT_TASK | Erect external formwork for wall and roof | Thu Jun 20 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1519 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1520 | TT_TASK | Curing for wall and roof | Sun Jun 23 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1521 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jun 24 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1522 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 25 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1523 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 03 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1524 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Aug 29 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1527 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Thu Dec 20 08:00:00 IST 2012 | Thu Dec 20 18:00:00 IST 2012 |  | COMPLETED
1528 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Fri Dec 21 08:00:00 IST 2012 | Sat Dec 22 18:00:00 IST 2012 |  | COMPLETED
1529 | TT_TASK | Rebar fixing for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Sat Dec 22 08:00:00 IST 2012 | Mon Dec 24 18:00:00 IST 2012 |  | COMPLETED
1530 | TT_TASK | Erect internal kicker formwork for base slab | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1531 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 06 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Dec 27 08:00:00 IST 2012 | Thu Dec 27 18:00:00 IST 2012 |  | COMPLETED
1532 | TT_TASK | Curing for base slab | Fri Jun 07 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Dec 28 08:00:00 IST 2012 | Wed Jan 09 18:00:00 IST 2013 |  | COMPLETED
1533 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Jan 10 08:00:00 IST 2013 | Thu Jan 10 18:00:00 IST 2013 |  | COMPLETED
1534 | TT_TASK | Removal of formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Jan 11 08:00:00 IST 2013 | Fri Jan 11 18:00:00 IST 2013 |  | COMPLETED
1535 | TT_TASK | Shear beam | Mon Jun 10 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Jan 12 08:00:00 IST 2013 | Sat Jan 12 18:00:00 IST 2013 |  | COMPLETED
1536 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1537 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1539 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1540 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1541 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1542 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1543 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1544 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon Mar 18 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1545 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Sat Mar 16 18:00:00 IST 2013 |  | COMPLETED
1546 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1547 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 | Fri Dec 12 08:00:00 IST 2014 | Wed Dec 17 18:00:00 IST 2014 |  | COMPLETED
1549 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1550 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Mon Feb 25 18:00:00 IST 2013 |  | COMPLETED
1551 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1552 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1553 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1554 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1555 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1556 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1557 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Aug 24 08:00:00 IDT 2015 | Fri Aug 28 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
1560 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Jan 14 08:00:00 IST 2013 | Mon Jan 14 18:00:00 IST 2013 |  | COMPLETED
1561 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Jan 15 08:00:00 IST 2013 | Wed Jan 16 18:00:00 IST 2013 |  | COMPLETED
1562 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Thu Jan 17 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1563 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jun 05 08:00:00 IDT 2013 | Thu Jun 06 18:00:00 IDT 2013 | Fri Jan 18 08:00:00 IST 2013 | Fri Jan 18 18:00:00 IST 2013 |  | COMPLETED
1564 | TT_TASK | Concreting for base slab (363m3) | Fri Jun 07 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 19 08:00:00 IST 2013 | Sat Jan 19 18:00:00 IST 2013 |  | COMPLETED
1565 | TT_TASK | Curing for base slab | Sat Jun 08 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1566 | TT_TASK | Preparation of construction joint for base slab | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Jan 29 08:00:00 IST 2013 | Tue Jan 29 18:00:00 IST 2013 |  | COMPLETED
1567 | TT_TASK | Removal of formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1568 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Jan 21 08:00:00 IST 2013 | Mon Jan 21 18:00:00 IST 2013 |  | COMPLETED
1569 | TT_TASK | Curing | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Jan 22 08:00:00 IST 2013 | Tue Jan 22 18:00:00 IST 2013 |  | COMPLETED
1570 | TT_TASK | Removal strut S5 and S4 | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Jan 23 08:00:00 IST 2013 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
1572 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1573 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1574 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1575 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1576 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1577 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1578 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1579 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1580 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 | Sat Dec 06 08:00:00 IST 2014 | Thu Dec 11 18:00:00 IST 2014 |  | COMPLETED
1582 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1583 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1584 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1585 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1586 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1587 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1588 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1589 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1590 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Aug 18 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1593 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Fri Jan 25 08:00:00 IST 2013 | Fri Jan 25 18:00:00 IST 2013 |  | COMPLETED
1594 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Mon Jan 28 18:00:00 IST 2013 |  | COMPLETED
1595 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1596 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Feb 01 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
1597 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Sat Feb 02 18:00:00 IST 2013 |  | COMPLETED
1598 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Fri Feb 08 18:00:00 IST 2013 |  | COMPLETED
1599 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1600 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1601 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Tue Feb 05 18:00:00 IST 2013 |  | COMPLETED
1602 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 06 08:00:00 IST 2013 | Wed Feb 06 18:00:00 IST 2013 |  | COMPLETED
1603 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu Feb 07 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1605 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 31 18:00:00 IDT 2013 |  | COMPLETED
1606 | TT_TASK | Rebar fixing for wall and roof | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 04 18:00:00 IDT 2013 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 |  | COMPLETED
1607 | TT_TASK | Erect external formwork for wall and roof | Sat Oct 05 08:00:00 IDT 2013 | Mon Oct 07 18:00:00 IDT 2013 | Fri Sep 06 08:00:00 IDT 2013 | Thu Sep 12 18:00:00 IDT 2013 |  | COMPLETED
1608 | TT_TASK | Concreting for wall and roof (450m3) | Tue Oct 08 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Fri Sep 13 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 |  | COMPLETED
1609 | TT_TASK | Curing for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Sat Sep 14 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1610 | TT_TASK | Preparation of construction joint for wall and roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1611 | TT_TASK | Removal external and internal formwork for wall | Thu Oct 10 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Wed Sep 25 18:00:00 IDT 2013 |  | COMPLETED
1612 | TT_TASK | Removal internal falsework and formwork for roof | Sat Oct 19 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Thu Sep 26 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1613 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 08 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1615 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 20 18:00:00 IST 2013 |  | COMPLETED
1616 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1617 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1618 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1619 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1620 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1621 | TT_TASK | Removal external wall formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1622 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Tue Apr 30 08:00:00 IDT 2013 | Tue Apr 30 18:00:00 IDT 2013 |  | COMPLETED
1623 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Aug 12 08:00:00 IDT 2015 | Mon Aug 17 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
1626 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Mon Feb 04 08:00:00 IST 2013 | Mon Feb 04 18:00:00 IST 2013 |  | COMPLETED
1627 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Tue Feb 05 08:00:00 IST 2013 | Thu Feb 07 18:00:00 IST 2013 |  | COMPLETED
1628 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Thu Feb 14 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1629 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1630 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Mon Feb 18 18:00:00 IST 2013 |  | COMPLETED
1631 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1632 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1633 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Feb 19 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1634 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1635 | TT_TASK | Curing | Wed Jun 19 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1636 | TT_TASK | Removal strut S5 and S4 | Thu Jun 20 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1638 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Jul 12 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1639 | TT_TASK | Rebar fixing for wall and roof | Wed Jul 17 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1640 | TT_TASK | Erect external formwork for wall and roof | Wed Aug 14 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1641 | TT_TASK | Concreting for wall and roof (450m3) | Fri Aug 16 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1642 | TT_TASK | Curing for wall and roof | Sun Aug 11 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1643 | TT_TASK | Preparation of construction joint for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1644 | TT_TASK | Removal external and internal formwork for wall | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1645 | TT_TASK | Removal internal falsework and formwork for roof | Wed Aug 21 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1646 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 03 08:00:00 IST 2014 | Fri Mar 07 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1648 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Mar 21 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1649 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Apr 02 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1650 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Tue Apr 09 08:00:00 IDT 2013 | Thu Apr 11 18:00:00 IDT 2013 |  | COMPLETED
1651 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 13 08:00:00 IDT 2013 | Sat Apr 13 18:00:00 IDT 2013 |  | COMPLETED
1652 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1653 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1654 | TT_TASK | Removal external wall formwork for wall | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1655 | TT_TASK | Removal internal falsework and formwork for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 22 08:00:00 IDT 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
1656 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Aug 06 08:00:00 IDT 2015 | Tue Aug 11 18:00:00 IDT 2015 | Mon Jul 27 08:00:00 IDT 2015 | Fri Jul 31 18:00:00 IDT 2015 |  | COMPLETED
1658 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Sep 12 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 |  | COMPLETED
1659 | TT_TASK | Rebar fixing for roof | Tue Sep 17 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 | Thu Jun 27 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 |  | COMPLETED
1660 | TT_TASK | Erect external formwork for roof | Thu Sep 19 08:00:00 IDT 2013 | Thu Sep 19 18:00:00 IDT 2013 | Sat Jul 06 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 |  | COMPLETED
1661 | TT_TASK | Concreting for roof (444m3) | Sat Sep 21 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 | Thu Jul 11 08:00:00 IDT 2013 | Thu Jul 11 18:00:00 IDT 2013 |  | COMPLETED
1662 | TT_TASK | Curing for roof | Sun Sep 22 08:00:00 IDT 2013 | Tue Oct 01 18:00:00 IDT 2013 | Fri Jul 12 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1663 | TT_TASK | Preparation of construction joint for roof | Mon Sep 23 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 |  | COMPLETED
1664 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 02 08:00:00 IDT 2013 | Thu Oct 03 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1665 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 |  | COMPLETED
1668 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Sat Feb 16 08:00:00 IST 2013 | Sat Feb 16 18:00:00 IST 2013 |  | COMPLETED
1669 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1670 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1671 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Tue Feb 26 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1672 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Fri Mar 01 18:00:00 IST 2013 |  | COMPLETED
1673 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1674 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Sat Mar 02 08:00:00 IST 2013 | Sat Mar 02 18:00:00 IST 2013 |  | COMPLETED
1675 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1676 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Tue Mar 05 18:00:00 IST 2013 |  | COMPLETED
1677 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1678 | TT_TASK | Removal strut S5 and S4 | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1680 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 25 08:00:00 IDT 2013 | Fri Jun 28 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Thu Apr 25 18:00:00 IDT 2013 |  | COMPLETED
1681 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 29 08:00:00 IDT 2013 | Wed Jul 03 18:00:00 IDT 2013 | Fri May 03 08:00:00 IDT 2013 | Wed May 08 18:00:00 IDT 2013 |  | COMPLETED
1682 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Thu May 16 08:00:00 IDT 2013 | Thu May 23 18:00:00 IDT 2013 |  | COMPLETED
1683 | TT_TASK | Concreting for wall and roof (450m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1684 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1685 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1686 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Wed Jul 10 18:00:00 IDT 2013 | Wed May 29 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1687 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1688 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 19 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Sat Oct 05 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1690 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Apr 15 08:00:00 IDT 2013 | Fri Apr 19 18:00:00 IDT 2013 |  | COMPLETED
1691 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Sat Apr 20 08:00:00 IDT 2013 | Wed Apr 24 18:00:00 IDT 2013 |  | COMPLETED
1692 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 18 08:00:00 IDT 2013 | Wed Jun 19 18:00:00 IDT 2013 | Thu Apr 25 08:00:00 IDT 2013 | Sat Apr 27 18:00:00 IDT 2013 |  | COMPLETED
1693 | TT_TASK | Concreting for wall and roof (450m3) | Thu Jun 20 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri May 24 08:00:00 IDT 2013 | Fri May 24 18:00:00 IDT 2013 |  | COMPLETED
1694 | TT_TASK | Curing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Sun Jun 30 18:00:00 IDT 2013 | Sat May 25 08:00:00 IDT 2013 | Sat May 25 18:00:00 IDT 2013 |  | COMPLETED
1695 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Mon May 27 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1696 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1697 | TT_TASK | Removal internal falsework and formwork for roof | Tue Jul 02 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1698 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 02 08:00:00 IDT 2015 | Sat Apr 11 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Fri Feb 27 18:00:00 IST 2015 |  | COMPLETED
1700 | TT_TASK | Erect internal formwork & Falsework for roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
1701 | TT_TASK | Rebar fixing for roof | Tue Aug 06 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Tue May 28 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1702 | TT_TASK | Erect external formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Thu May 30 18:00:00 IDT 2013 |  | COMPLETED
1703 | TT_TASK | Concreting for roof (444m3) | Fri Aug 09 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Fri May 31 18:00:00 IDT 2013 |  | COMPLETED
1704 | TT_TASK | Curing for roof | Thu Aug 01 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1705 | TT_TASK | Preparation of construction joint for roof | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 |  | COMPLETED
1706 | TT_TASK | Removal internal falsework and formwork for roof | Thu Aug 08 08:00:00 IDT 2013 | Fri Aug 09 18:00:00 IDT 2013 | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1707 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jan 09 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1710 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Feb 20 08:00:00 IST 2013 | Wed Feb 20 18:00:00 IST 2013 |  | COMPLETED
1711 | TT_TASK | Erect external formwork for base slab | Mon Jun 03 08:00:00 IDT 2013 | Tue Jun 04 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Fri Feb 22 18:00:00 IST 2013 |  | COMPLETED
1712 | TT_TASK | Rebar fixing for base slab | Wed Jun 05 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Mon Mar 04 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1713 | TT_TASK | Erect internal kicker formwork for base slab | Sat Jun 08 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1714 | TT_TASK | Concreting for base slab (363m3) | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1715 | TT_TASK | Curing for base slab | Wed Jun 12 08:00:00 IDT 2013 | Tue Jun 18 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1716 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1717 | TT_TASK | Removal of formwork for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1718 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1719 | TT_TASK | Curing | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 01 18:00:00 IDT 2013 | Wed Mar 13 08:00:00 IST 2013 | Wed Mar 13 18:00:00 IST 2013 |  | COMPLETED
1720 | TT_TASK | Removal strut S5 and S4 | Mon Jun 24 08:00:00 IDT 2013 | Thu Jun 27 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1722 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1723 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1724 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Wed Jul 10 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1725 | TT_TASK | Concreting for wall and roof (450m3) | Mon Aug 12 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1726 | TT_TASK | Curing for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1727 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1728 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 |  | COMPLETED
1729 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 |  | COMPLETED
1730 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Feb 10 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1732 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Aug 01 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1733 | TT_TASK | Rebar fixing for wall and roof | Tue Aug 06 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1734 | TT_TASK | Erect external formwork for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1735 | TT_TASK | Concreting for wall and roof (450m3) | Tue Sep 03 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1736 | TT_TASK | Curing for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Fri Sep 13 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1737 | TT_TASK | Preparation of construction joint for wall and roof | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Wed Aug 21 18:00:00 IDT 2013 |  | COMPLETED
1738 | TT_TASK | Removal external and internal formwork for wall | Thu Sep 05 08:00:00 IDT 2013 | Fri Sep 06 18:00:00 IDT 2013 | Thu Aug 22 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1739 | TT_TASK | Removal internal falsework and formwork for roof | Sat Sep 14 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Sat Aug 24 08:00:00 IDT 2013 | Sat Aug 24 18:00:00 IDT 2013 |  | COMPLETED
1740 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 05 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1742 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1743 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1744 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1745 | TT_TASK | Concreting for roof (363m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1746 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Sun Oct 20 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1747 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1748 | TT_TASK | Removal internal falsework and formwork for roof | Mon Oct 21 08:00:00 IDT 2013 | Tue Oct 22 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1749 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Dec 24 13:00:00 IST 2013 | Thu Jan 02 12:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1752 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1753 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1754 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1755 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Fri Apr 12 08:00:00 IDT 2013 | Mon Apr 15 18:00:00 IDT 2013 |  | COMPLETED
1756 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Tue Apr 16 08:00:00 IDT 2013 | Tue Apr 16 18:00:00 IDT 2013 |  | COMPLETED
1757 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Wed Apr 17 08:00:00 IDT 2013 | Wed Apr 17 18:00:00 IDT 2013 |  | COMPLETED
1758 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1759 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Thu Apr 18 08:00:00 IDT 2013 | Thu Apr 18 18:00:00 IDT 2013 |  | COMPLETED
1760 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1761 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Thu May 02 18:00:00 IDT 2013 |  | COMPLETED
1762 | TT_TASK | Removal strut S5 and S4 | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Sat Jun 22 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 |  | COMPLETED
1764 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Aug 05 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Jul 02 18:00:00 IDT 2013 |  | COMPLETED
1765 | TT_TASK | Rebar fixing for wall and roof | Fri Aug 09 08:00:00 IDT 2013 | Mon Aug 12 18:00:00 IDT 2013 | Wed Jul 03 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1766 | TT_TASK | Erect external formwork for wall and roof | Tue Aug 13 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 |  | COMPLETED
1767 | TT_TASK | Concreting for wall and roof (450m3) | Thu Aug 15 08:00:00 IDT 2013 | Thu Aug 15 18:00:00 IDT 2013 | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 |  | COMPLETED
1768 | TT_TASK | Curing for wall and roof | Fri Aug 16 08:00:00 IDT 2013 | Sun Aug 25 18:00:00 IDT 2013 | Mon Jul 29 08:00:00 IDT 2013 | Wed Jul 31 18:00:00 IDT 2013 |  | COMPLETED
1769 | TT_TASK | Preparation of construction joint for wall and roof | Mon Sep 02 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 | Thu Aug 01 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1770 | TT_TASK | Removal external and internal formwork for wall | Tue Sep 03 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Fri Aug 02 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1771 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Mon Aug 05 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 |  | COMPLETED
1772 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Feb 04 08:00:00 IST 2014 | Sat Feb 08 18:00:00 IST 2014 | Fri Aug 23 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1774 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Aug 07 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 |  | COMPLETED
1775 | TT_TASK | Rebar fixing for wall and roof | Mon Aug 12 08:00:00 IDT 2013 | Wed Aug 14 18:00:00 IDT 2013 | Tue Jul 16 08:00:00 IDT 2013 | Mon Jul 29 18:00:00 IDT 2013 |  | COMPLETED
1776 | TT_TASK | Erect external formwork for wall and roof | Thu Aug 15 08:00:00 IDT 2013 | Fri Aug 16 18:00:00 IDT 2013 | Tue Jul 30 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 |  | COMPLETED
1777 | TT_TASK | Concreting for wall and roof (450m3) | Wed Sep 04 08:00:00 IDT 2013 | Wed Sep 04 18:00:00 IDT 2013 | Wed Aug 07 08:00:00 IDT 2013 | Wed Aug 07 18:00:00 IDT 2013 |  | COMPLETED
1778 | TT_TASK | Curing for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 | Thu Aug 08 08:00:00 IDT 2013 | Mon Aug 19 18:00:00 IDT 2013 |  | COMPLETED
1779 | TT_TASK | Preparation of construction joint for wall and roof | Thu Sep 05 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Tue Aug 20 08:00:00 IDT 2013 | Tue Aug 20 18:00:00 IDT 2013 |  | COMPLETED
1780 | TT_TASK | Removal external and internal formwork for wall | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Wed Aug 21 08:00:00 IDT 2013 | Thu Aug 22 18:00:00 IDT 2013 |  | COMPLETED
1781 | TT_TASK | Removal internal falsework and formwork for roof | Mon Sep 16 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Fri Aug 23 08:00:00 IDT 2013 | Fri Aug 23 18:00:00 IDT 2013 |  | COMPLETED
1782 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Nov 19 08:00:00 IST 2014 | Mon Nov 24 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1784 | TT_TASK | Erect internal formwork & Falsework for roof | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 | Fri Aug 30 08:00:00 IDT 2013 | Tue Sep 03 18:00:00 IDT 2013 |  | COMPLETED
1785 | TT_TASK | Rebar fixing for roof | Mon Oct 07 08:00:00 IDT 2013 | Tue Oct 08 18:00:00 IDT 2013 | Tue Sep 10 08:00:00 IDT 2013 | Sat Sep 14 18:00:00 IDT 2013 |  | COMPLETED
1786 | TT_TASK | Erect external formwork for roof | Wed Oct 09 08:00:00 IDT 2013 | Wed Oct 09 18:00:00 IDT 2013 | Mon Sep 16 08:00:00 IDT 2013 | Tue Sep 17 18:00:00 IDT 2013 |  | COMPLETED
1787 | TT_TASK | Concreting for roof (450m3) | Thu Oct 10 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 | Wed Sep 18 08:00:00 IDT 2013 | Wed Sep 18 18:00:00 IDT 2013 |  | COMPLETED
1788 | TT_TASK | Curing for roof | Fri Oct 11 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 | Thu Sep 19 08:00:00 IDT 2013 | Mon Sep 23 18:00:00 IDT 2013 |  | COMPLETED
1789 | TT_TASK | Preparation of construction joint for roof | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
1790 | TT_TASK | Removal internal falsework and formwork for roof | Fri Oct 18 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 | Wed Sep 25 08:00:00 IDT 2013 | Thu Sep 26 18:00:00 IDT 2013 |  | COMPLETED
1791 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 13 08:00:00 IST 2014 | Fri Jan 17 18:00:00 IST 2014 | Tue Aug 13 08:00:00 IDT 2013 | Thu Aug 29 18:00:00 IDT 2013 |  | COMPLETED
1794 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 01 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 | Thu Feb 21 08:00:00 IST 2013 | Thu Feb 21 18:00:00 IST 2013 |  | COMPLETED
1795 | TT_TASK | Erect external formwork for base slab | Tue Jun 04 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Sat Feb 23 18:00:00 IST 2013 |  | COMPLETED
1796 | TT_TASK | Rebar fixing for base slab | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Feb 25 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1797 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Wed Feb 27 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
1798 | TT_TASK | Concreting for base slab (363m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Thu Feb 28 08:00:00 IST 2013 | Thu Feb 28 18:00:00 IST 2013 |  | COMPLETED
1799 | TT_TASK | Curing for base slab | Fri Jun 14 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Mon Mar 04 18:00:00 IST 2013 |  | COMPLETED
1800 | TT_TASK | Preparation of construction joint for base slab | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Tue Mar 05 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1801 | TT_TASK | Removal of formwork for base slab | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Wed Mar 06 08:00:00 IST 2013 | Thu Mar 07 18:00:00 IST 2013 |  | COMPLETED
1802 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Jun 17 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Fri Mar 08 18:00:00 IST 2013 |  | COMPLETED
1803 | TT_TASK | Curing | Fri Jun 21 08:00:00 IDT 2013 | Fri Jun 21 18:00:00 IDT 2013 | Sat Mar 09 08:00:00 IST 2013 | Sat Mar 09 18:00:00 IST 2013 |  | COMPLETED
1804 | TT_TASK | Removal strut S5 and S4 | Sat Jun 22 08:00:00 IDT 2013 | Wed Jun 26 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Mon Mar 11 18:00:00 IST 2013 |  | COMPLETED
1806 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jul 09 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 | Fri Mar 01 08:00:00 IST 2013 | Wed Mar 06 18:00:00 IST 2013 |  | COMPLETED
1807 | TT_TASK | Rebar fixing for wall and roof | Sat Jul 20 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Thu Mar 07 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1808 | TT_TASK | Erect external formwork for wall and roof | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Tue Mar 12 08:00:00 IST 2013 | Thu Mar 14 18:00:00 IST 2013 |  | COMPLETED
1809 | TT_TASK | Concreting for wall and roof (450m3) | Fri Jul 26 08:00:00 IDT 2013 | Fri Jul 26 18:00:00 IDT 2013 | Fri Mar 15 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1810 | TT_TASK | Curing for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Mon Aug 05 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1811 | TT_TASK | Preparation of construction joint for wall and roof | Sat Jul 27 08:00:00 IDT 2013 | Sat Jul 27 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Tue Mar 19 18:00:00 IST 2013 |  | COMPLETED
1812 | TT_TASK | Removal external and internal formwork for wall | Mon Jul 29 08:00:00 IDT 2013 | Tue Jul 30 18:00:00 IDT 2013 | Wed Mar 20 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1813 | TT_TASK | Removal internal falsework and formwork for roof | Tue Aug 06 08:00:00 IDT 2013 | Tue Aug 06 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1814 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jan 25 08:00:00 IST 2014 | Thu Jan 30 18:00:00 IST 2014 | Fri Aug 30 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1816 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Jul 11 08:00:00 IDT 2013 | Mon Jul 15 18:00:00 IDT 2013 | Fri Mar 08 08:00:00 IST 2013 | Tue Mar 12 18:00:00 IST 2013 |  | COMPLETED
1817 | TT_TASK | Rebar fixing for wall and roof | Tue Jul 16 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Thu Mar 14 08:00:00 IST 2013 | Mon Mar 18 18:00:00 IST 2013 |  | COMPLETED
1818 | TT_TASK | Erect external formwork for wall and roof | Fri Jul 19 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 | Tue Mar 19 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1819 | TT_TASK | Concreting for wall and roof (450m3) | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Wed Mar 27 18:00:00 IST 2013 |  | COMPLETED
1820 | TT_TASK | Curing for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Thu Aug 01 18:00:00 IDT 2013 | Thu Mar 28 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1821 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jul 23 08:00:00 IDT 2013 | Tue Jul 23 18:00:00 IDT 2013 | Fri Mar 29 08:00:00 IDT 2013 | Fri Mar 29 18:00:00 IDT 2013 |  | COMPLETED
1822 | TT_TASK | Removal external and internal formwork for wall | Wed Jul 24 08:00:00 IDT 2013 | Thu Jul 25 18:00:00 IDT 2013 | Sat Mar 30 08:00:00 IDT 2013 | Sat Mar 30 18:00:00 IDT 2013 |  | COMPLETED
1823 | TT_TASK | Removal internal falsework and formwork for roof | Fri Aug 02 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Mon Apr 01 18:00:00 IDT 2013 |  | COMPLETED
1824 | TT_TASK | Side walkway and cable bracket | Thu Nov 13 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Fri May 02 08:00:00 IDT 2014 | Fri May 09 18:00:00 IDT 2014 |  | COMPLETED
1826 | TT_TASK | Erect internal formwork & Falsework for roof | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 |  | COMPLETED
1827 | TT_TASK | Rebar fixing for roof | Fri Sep 06 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Thu Jul 18 08:00:00 IDT 2013 | Fri Jul 19 18:00:00 IDT 2013 |  | COMPLETED
1828 | TT_TASK | Erect shutter formwork for roof | Mon Sep 09 08:00:00 IDT 2013 | Mon Sep 09 18:00:00 IDT 2013 | Sat Jul 20 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
1829 | TT_TASK | Concreting for roof (450m3) | Tue Sep 10 08:00:00 IDT 2013 | Tue Sep 10 18:00:00 IDT 2013 | Mon Jul 22 08:00:00 IDT 2013 | Mon Jul 22 18:00:00 IDT 2013 |  | COMPLETED
1830 | TT_TASK | Curing for roof | Wed Sep 11 08:00:00 IDT 2013 | Fri Sep 20 18:00:00 IDT 2013 | Tue Jul 23 08:00:00 IDT 2013 | Fri Aug 02 18:00:00 IDT 2013 |  | COMPLETED
1831 | TT_TASK | Preparation of construction joint for roof | Wed Sep 11 08:00:00 IDT 2013 | Wed Sep 11 18:00:00 IDT 2013 | Sat Aug 03 08:00:00 IDT 2013 | Sat Aug 03 18:00:00 IDT 2013 |  | COMPLETED
1832 | TT_TASK | Removal internal falsework and formwork for roof | Thu Sep 26 08:00:00 IDT 2013 | Fri Sep 27 18:00:00 IDT 2013 | Mon Aug 19 08:00:00 IDT 2013 | Mon Sep 02 18:00:00 IDT 2013 |  | COMPLETED
1833 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Dec 06 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Tue Aug 13 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
1835 | TT_TASK | Water proofing and soil backfilling to 0.5m below top of Tunnel Bay 3 to Bay 1 | Wed Oct 02 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 | Tue Sep 24 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1836 | TT_TASK | Mass infill between D-wall and tunnel wall | Fri Oct 11 08:00:00 IDT 2013 | Wed Oct 16 18:00:00 IDT 2013 | Fri Sep 20 08:00:00 IDT 2013 | Thu Oct 17 18:00:00 IDT 2013 |  | COMPLETED
1837 | TT_TASK | Removal S3 and S2 | Wed Nov 13 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
1838 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 4 | Sat Jun 08 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 02 08:00:00 IDT 2013 | Sat May 18 18:00:00 IDT 2013 |  | COMPLETED
1839 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 5 and remove S3 & S2 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Mon Jan 28 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1840 | TT_TASK | Water proofing and concrete backfilling to top of Tunnel Bay 6 | Sat Jun 01 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 15 18:00:00 IST 2013 |  | COMPLETED
1843 | TT_TASK | Pre-drilling and guidewall | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Thu Nov 24 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
1844 | TT_TASK | D-wall design review | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 | Wed Feb 01 08:00:00 IST 2012 | Wed Feb 15 18:00:00 IST 2012 |  | COMPLETED
1845 | TT_TASK | D-wall construction (4741m3) | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 | Thu Feb 16 08:00:00 IST 2012 | Fri Jun 15 18:00:00 IDT 2012 |  | COMPLETED
1846 | TT_TASK | Shear pin and pumping test | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 15 18:00:00 IST 2012 | Sat Jun 16 08:00:00 IDT 2012 | Sat Dec 08 18:00:00 IST 2012 |  | COMPLETED
1848 | TT_TASK | ELS works to formation level from SN16 to SN19 (soil: 8,700m3 @350m3/day, Install S1 to S3 strut 5 days/layer) | Wed Sep 25 08:00:00 IDT 2013 | Wed Nov 13 18:00:00 IST 2013 | Wed May 08 08:00:00 IDT 2013 | Fri Oct 18 18:00:00 IDT 2013 |  | COMPLETED
1849 | TT_TASK | Design temporary bridge and approval | Mon Sep 01 08:00:00 IDT 2014 | Wed Nov 12 18:00:00 IST 2014 | Fri Aug 01 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1850 | TT_TASK | Application of tree transplant | Sat Jun 01 08:00:00 IDT 2013 | Wed Oct 23 18:00:00 IDT 2013 | Thu Jan 03 08:00:00 IST 2013 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
1851 | TT_TASK | Tree transplant | Tue Oct 14 08:00:00 IDT 2014 | Mon Nov 10 18:00:00 IST 2014 | Tue Sep 02 08:00:00 IDT 2014 | Tue Sep 30 18:00:00 IDT 2014 |  | COMPLETED
1852 | TT_TASK | Erection temporary bridge deck | Fri Oct 03 08:00:00 IDT 2014 | Fri Dec 05 18:00:00 IST 2014 | Fri Oct 03 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
1853 | TT_TASK | ELS works to formation level from SN10 to SN15 (soil: 9,455m3 @330m3/day, install S1 to S3 strut 5 days/layer) | Mon Nov 24 08:00:00 IST 2014 | Sat Jan 17 18:00:00 IST 2015 | Mon Nov 24 08:00:00 IST 2014 | Tue Jun 23 18:00:00 IDT 2015 |  | COMPLETED
1856 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Sat Oct 26 08:00:00 IDT 2013 | Mon Nov 04 18:00:00 IST 2013 |  | COMPLETED
1857 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Tue Nov 05 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1858 | TT_TASK | Erect external formwork for wall and roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1859 | TT_TASK | Concreting for wall and roof (215m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 |  | COMPLETED
1860 | TT_TASK | Curing for wall and roof | Sun Dec 08 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 24 18:00:00 IST 2013 |  | COMPLETED
1861 | TT_TASK | Preparation of construction joint for wall and roof | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1862 | TT_TASK | Removal external and internal formwork for wall | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1863 | TT_TASK | Removal internal falsework and formwork for roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Fri Dec 27 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1864 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Apr 03 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 | Mon Mar 24 08:00:00 IST 2014 | Fri Mar 28 18:00:00 IDT 2014 |  | COMPLETED
1866 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 14 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
1867 | TT_TASK | Rebar fixing for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1868 | TT_TASK | Erect external formwork for wall and roof | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Mon Dec 09 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 |  | COMPLETED
1869 | TT_TASK | Concreting for wall and roof (215m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
1870 | TT_TASK | Curing for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Sun Dec 29 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Sat Dec 28 18:00:00 IST 2013 |  | COMPLETED
1871 | TT_TASK | Preparation of construction joint for wall and roof | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Mon Dec 16 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 |  | COMPLETED
1872 | TT_TASK | Removal external and internal formwork for wall | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Tue Dec 17 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 |  | COMPLETED
1873 | TT_TASK | Removal internal falsework and formwork for roof | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Mon Dec 30 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1874 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 |  | COMPLETED
1876 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Nov 28 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Nov 28 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
1877 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 28 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 | Thu Dec 12 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 |  | COMPLETED
1878 | TT_TASK | Erect external formwork for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 |  | COMPLETED
1879 | TT_TASK | Concreting for wall and roof (215m3) | Sat Jan 04 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Tue Dec 31 08:00:00 IST 2013 | Tue Dec 31 18:00:00 IST 2013 |  | COMPLETED
1880 | TT_TASK | Curing for wall and roof | Wed Jan 01 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
1881 | TT_TASK | Preparation of construction joint for wall and roof | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
1882 | TT_TASK | Removal external and internal formwork for wall | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 03 18:00:00 IST 2014 |  | COMPLETED
1883 | TT_TASK | Removal internal falsework and formwork for roof | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
1884 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 | Sat Mar 22 08:00:00 IST 2014 | Thu Mar 27 18:00:00 IST 2014 |  | COMPLETED
1886 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Dec 13 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1887 | TT_TASK | Rebar fixing for wall and roof | Sat Dec 14 08:00:00 IST 2013 | Tue Dec 17 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1888 | TT_TASK | Erect external formwork for wall and roof | Wed Dec 18 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1889 | TT_TASK | Concreting for wall and roof (215m3) | Fri Dec 20 08:00:00 IST 2013 | Fri Dec 20 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1890 | TT_TASK | Curing for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Mon Dec 30 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1891 | TT_TASK | Preparation of construction joint for wall and roof | Sat Dec 21 08:00:00 IST 2013 | Sat Dec 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1892 | TT_TASK | Removal external and internal formwork for wall | Mon Dec 23 08:00:00 IST 2013 | Mon Dec 23 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1893 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1894 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 | Mon Mar 17 08:00:00 IST 2014 | Fri Mar 21 18:00:00 IST 2014 |  | COMPLETED
1896 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Fri Jan 03 18:00:00 IST 2014 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 08:00:00 IST 2013 |  | COMPLETED
1897 | TT_TASK | Rebar fixing for wall and roof | Mon Dec 30 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1898 | TT_TASK | Erect external formwork for wall and roof | Fri Jan 03 08:00:00 IST 2014 | Sat Jan 04 18:00:00 IST 2014 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1899 | TT_TASK | Concreting for wall and roof (215m3) | Mon Jan 06 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1900 | TT_TASK | Curing for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 16 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1901 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jan 07 08:00:00 IST 2014 | Tue Jan 07 18:00:00 IST 2014 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1902 | TT_TASK | Removal external and internal formwork for wall | Wed Jan 08 08:00:00 IST 2014 | Wed Jan 08 18:00:00 IST 2014 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1903 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1904 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 | Tue Mar 11 08:00:00 IST 2014 | Sat Mar 15 18:00:00 IST 2014 |  | COMPLETED
1906 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Fri Nov 01 08:00:00 IST 2013 | Tue Nov 05 18:00:00 IST 2013 | Thu Oct 24 08:00:00 IDT 2013 | Sat Nov 16 18:00:00 IST 2013 |  | COMPLETED
1907 | TT_TASK | Rebar fixing for wall and roof | Tue Nov 05 08:00:00 IST 2013 | Thu Nov 07 18:00:00 IST 2013 | Mon Nov 18 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
1908 | TT_TASK | Erect external formwork for wall and roof | Fri Nov 08 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
1909 | TT_TASK | Concreting for wall and roof (215m3) | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
1910 | TT_TASK | Curing for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Thu Nov 21 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
1911 | TT_TASK | Preparation of construction joint for wall and roof | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Nov 25 18:00:00 IST 2013 |  | COMPLETED
1912 | TT_TASK | Removal external and internal formwork for wall | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 | Tue Nov 26 08:00:00 IST 2013 | Tue Nov 26 18:00:00 IST 2013 |  | COMPLETED
1913 | TT_TASK | Removal internal falsework and formwork for roof | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 |  | COMPLETED
1914 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 | Wed Mar 05 08:00:00 IST 2014 | Mon Mar 10 18:00:00 IST 2014 |  | COMPLETED
1916 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Mon Jun 17 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Thu May 23 08:00:00 IDT 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
1917 | TT_TASK | Rebar fixing for wall and roof | Fri Jun 21 08:00:00 IDT 2013 | Mon Jun 24 18:00:00 IDT 2013 | Thu May 30 08:00:00 IDT 2013 | Mon Jun 03 18:00:00 IDT 2013 |  | COMPLETED
1918 | TT_TASK | Erect external formwork for wall and roof | Thu Jul 04 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Tue Jun 04 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 |  | COMPLETED
1919 | TT_TASK | Concreting for wall and roof (333m3) | Sat Jul 06 08:00:00 IDT 2013 | Sat Jul 06 18:00:00 IDT 2013 | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 |  | COMPLETED
1920 | TT_TASK | Curing for wall and roof | Sun Jul 07 08:00:00 IDT 2013 | Tue Jul 16 18:00:00 IDT 2013 | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 |  | COMPLETED
1921 | TT_TASK | Preparation of construction joint for wall and roof | Mon Jul 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Wed Jun 12 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 |  | COMPLETED
1922 | TT_TASK | Removal external and internal formwork for wall | Tue Jul 09 08:00:00 IDT 2013 | Tue Jul 09 18:00:00 IDT 2013 | Sat Jun 15 08:00:00 IDT 2013 | Mon Jun 17 18:00:00 IDT 2013 |  | COMPLETED
1923 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jul 17 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Wed Jun 19 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
1924 | TT_TASK | Side walkway and cable bracket (204m3) | Wed Feb 05 08:00:00 IST 2014 | Mon Feb 10 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Tue Mar 04 18:00:00 IST 2014 |  | COMPLETED
1926 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 15 08:00:00 IST 2013 | Tue Feb 19 18:00:00 IST 2013 |  | COMPLETED
1927 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Mar 11 08:00:00 IST 2013 | Fri Mar 15 18:00:00 IST 2013 |  | COMPLETED
1928 | TT_TASK | Erect external formwork for wall and roof | Mon Jun 10 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Sat Mar 16 08:00:00 IST 2013 | Thu Mar 21 18:00:00 IST 2013 |  | COMPLETED
1929 | TT_TASK | Concreting for wall and roof (412m3) | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Fri Mar 22 08:00:00 IST 2013 | Fri Mar 22 18:00:00 IST 2013 |  | COMPLETED
1930 | TT_TASK | Curing for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Sun Jun 23 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Sat Mar 23 18:00:00 IST 2013 |  | COMPLETED
1931 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 14 08:00:00 IDT 2013 | Fri Jun 14 18:00:00 IDT 2013 | Mon Mar 25 08:00:00 IST 2013 | Mon Mar 25 18:00:00 IST 2013 |  | COMPLETED
1932 | TT_TASK | Removal external and internal formwork for wall | Sat Jun 15 08:00:00 IDT 2013 | Sat Jun 15 18:00:00 IDT 2013 | Tue Mar 26 08:00:00 IST 2013 | Tue Mar 26 18:00:00 IST 2013 |  | COMPLETED
1933 | TT_TASK | Removal internal falsework and formwork for roof | Mon Jun 24 08:00:00 IDT 2013 | Tue Jun 25 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1934 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jan 27 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Mon Mar 03 18:00:00 IST 2014 |  | COMPLETED
1936 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jun 01 08:00:00 IDT 2013 | Wed Jun 05 18:00:00 IDT 2013 | Fri Feb 22 08:00:00 IST 2013 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
1937 | TT_TASK | Rebar fixing for wall and roof | Thu Jun 06 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Mar 23 08:00:00 IST 2013 | Thu Mar 28 18:00:00 IST 2013 |  | COMPLETED
1938 | TT_TASK | Erect external formwork for wall and roof | Sat Jun 08 08:00:00 IDT 2013 | Sat Jun 08 18:00:00 IDT 2013 | Mon Apr 01 08:00:00 IDT 2013 | Tue Apr 02 18:00:00 IDT 2013 |  | COMPLETED
1939 | TT_TASK | Concreting for wall and roof (320m3) | Mon Jun 10 08:00:00 IDT 2013 | Mon Jun 10 18:00:00 IDT 2013 | Fri Apr 05 08:00:00 IDT 2013 | Fri Apr 05 18:00:00 IDT 2013 |  | COMPLETED
1940 | TT_TASK | Curing for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Thu Jun 20 18:00:00 IDT 2013 | Sat Apr 06 08:00:00 IDT 2013 | Sat Apr 06 18:00:00 IDT 2013 |  | COMPLETED
1941 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 11 08:00:00 IDT 2013 | Tue Jun 11 18:00:00 IDT 2013 | Mon Apr 08 08:00:00 IDT 2013 | Mon Apr 08 18:00:00 IDT 2013 |  | COMPLETED
1942 | TT_TASK | Removal external and internal formwork for wall | Thu Jun 13 08:00:00 IDT 2013 | Thu Jun 13 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1943 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 21 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 | Wed Apr 10 08:00:00 IDT 2013 | Wed Apr 10 18:00:00 IDT 2013 |  | COMPLETED
1944 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jan 21 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 | Mon Jul 29 08:00:00 IDT 2013 | Sat Mar 01 18:00:00 IST 2014 |  | COMPLETED
1946 | TT_TASK | Excavation and saw cut D-wall | Thu Apr 02 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon Feb 23 08:00:00 IST 2015 | Sat Jul 25 18:00:00 IDT 2015 |  | COMPLETED
1947 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Aug 08 16:24:00 IDT 2015 | Mon Aug 10 16:24:00 IDT 2015 | Mon Jul 13 08:00:00 IDT 2015 | Mon Jul 13 18:00:00 IDT 2015 |  | COMPLETED
1948 | TT_TASK | Erect external formwork for base slab | Mon Aug 10 16:24:00 IDT 2015 | Wed Aug 12 16:24:00 IDT 2015 | Tue Jul 14 08:00:00 IDT 2015 | Wed Jul 15 18:00:00 IDT 2015 |  | COMPLETED
1949 | TT_TASK | Rebar fixing for base slab | Wed Aug 12 16:24:00 IDT 2015 | Fri Aug 14 16:24:00 IDT 2015 | Wed Jul 15 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1950 | TT_TASK | Erect internal kicker formwork for base slab | Fri Aug 14 16:24:00 IDT 2015 | Mon Aug 17 16:24:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Wed Aug 12 18:00:00 IDT 2015 |  | COMPLETED
1951 | TT_TASK | Concreting for base slab (90m3) | Wed Sep 02 08:00:00 IDT 2015 | Wed Sep 02 18:00:00 IDT 2015 | Thu Aug 13 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 |  | COMPLETED
1952 | TT_TASK | Curing for base slab | Thu Sep 03 08:00:00 IDT 2015 | Wed Sep 09 18:00:00 IDT 2015 | Fri Aug 14 08:00:00 IDT 2015 | Thu Aug 20 18:00:00 IDT 2015 |  | COMPLETED
1953 | TT_TASK | Preparation of construction joint for base slab | Thu Sep 03 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Fri Aug 21 08:00:00 IDT 2015 | Fri Aug 21 18:00:00 IDT 2015 |  | COMPLETED
1954 | TT_TASK | Removal of formwork for base slab | Fri Sep 04 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Sat Aug 22 08:00:00 IDT 2015 | Sat Aug 22 18:00:00 IDT 2015 |  | COMPLETED
1955 | TT_TASK | Infill concrete in between D-wall and base slab | Sat Sep 05 08:00:00 IDT 2015 | Sat Sep 05 18:00:00 IDT 2015 | Mon Aug 24 08:00:00 IDT 2015 | Mon Aug 24 18:00:00 IDT 2015 |  | COMPLETED
1956 | TT_TASK | Curing | Thu Sep 10 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Tue Aug 25 08:00:00 IDT 2015 | Tue Aug 25 18:00:00 IDT 2015 |  | COMPLETED
1957 | TT_TASK | Removal strut S3 | Sat Sep 19 08:00:00 IDT 2015 | Wed Sep 23 18:00:00 IDT 2015 | Wed Sep 16 08:00:00 IDT 2015 | Sat Sep 19 18:00:00 IDT 2015 |  | COMPLETED
1958 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Thu Sep 24 08:00:00 IDT 2015 | Tue Sep 29 18:00:00 IDT 2015 | Mon Sep 21 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
1959 | TT_TASK | Rebar fixing for wall and roof | Wed Sep 30 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 | Fri Sep 25 08:00:00 IDT 2015 | Wed Sep 30 18:00:00 IDT 2015 |  | COMPLETED
1960 | TT_TASK | Erect external formwork for wall and roof | Thu Oct 15 08:00:00 IDT 2015 | Fri Oct 16 18:00:00 IDT 2015 | Mon Oct 05 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
1961 | TT_TASK | Concreting for wall and roof (260m3) | Sat Oct 17 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 | Wed Oct 07 08:00:00 IDT 2015 | Wed Oct 07 18:00:00 IDT 2015 |  | COMPLETED
1962 | TT_TASK | Curing for wall and roof | Sun Oct 18 08:00:00 IDT 2015 | Tue Oct 27 18:00:00 IST 2015 | Thu Oct 08 08:00:00 IDT 2015 | Sat Oct 17 18:00:00 IDT 2015 |  | COMPLETED
1963 | TT_TASK | Preparation of construction joint for wall and roof | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 | Mon Oct 19 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
1964 | TT_TASK | Removal external and internal formwork for wall | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 | Tue Oct 20 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED
1965 | TT_TASK | Removal internal falsework and formwork for roof | Wed Oct 28 08:00:00 IST 2015 | Thu Oct 29 18:00:00 IST 2015 | Thu Oct 22 08:00:00 IDT 2015 | Fri Oct 23 18:00:00 IDT 2015 |  | COMPLETED
1966 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Oct 30 08:00:00 IST 2015 | Wed Nov 04 18:00:00 IST 2015 | Sat Oct 24 08:00:00 IDT 2015 | Fri Oct 30 18:00:00 IST 2015 |  | COMPLETED
1968 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Thu Jul 02 08:00:00 IDT 2015 | Thu Jul 02 18:00:00 IDT 2015 | Mon Jul 20 08:00:00 IDT 2015 | Mon Jul 20 18:00:00 IDT 2015 |  | COMPLETED
1969 | TT_TASK | Erect external formwork for base slab | Fri Jul 03 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Tue Jul 21 08:00:00 IDT 2015 | Wed Jul 22 18:00:00 IDT 2015 |  | COMPLETED
1970 | TT_TASK | Rebar fixing for base slab | Mon Jul 06 08:00:00 IDT 2015 | Tue Jul 07 18:00:00 IDT 2015 | Thu Jul 23 08:00:00 IDT 2015 | Fri Jul 24 18:00:00 IDT 2015 |  | COMPLETED
1971 | TT_TASK | Erect internal kicker formwork for base slab | Wed Jul 08 08:00:00 IDT 2015 | Thu Jul 09 18:00:00 IDT 2015 | Sat Jul 25 08:00:00 IDT 2015 | Mon Jul 27 18:00:00 IDT 2015 |  | COMPLETED
1972 | TT_TASK | Concreting for base slab (123m3) | Fri Jul 10 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jul 28 08:00:00 IDT 2015 | Tue Jul 28 18:00:00 IDT 2015 |  | COMPLETED
1973 | TT_TASK | Curing for base slab | Sat Jul 11 08:00:00 IDT 2015 | Fri Jul 17 18:00:00 IDT 2015 | Wed Jul 29 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1974 | TT_TASK | Preparation of construction joint for base slab | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 | Sat Aug 01 08:00:00 IDT 2015 | Sat Aug 01 18:00:00 IDT 2015 |  | COMPLETED
1975 | TT_TASK | Removal of formwork for base slab | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 | Mon Aug 03 08:00:00 IDT 2015 | Mon Aug 03 18:00:00 IDT 2015 |  | COMPLETED
1976 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 | Tue Aug 04 08:00:00 IDT 2015 | Tue Aug 04 18:00:00 IDT 2015 |  | COMPLETED
1977 | TT_TASK | Curing | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 | Wed Aug 05 08:00:00 IDT 2015 | Wed Aug 05 18:00:00 IDT 2015 |  | COMPLETED
1978 | TT_TASK | Removal strut S3 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 | Thu Aug 06 08:00:00 IDT 2015 | Mon Aug 10 18:00:00 IDT 2015 |  | COMPLETED
1979 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 | Tue Sep 01 08:00:00 IDT 2015 | Fri Sep 04 18:00:00 IDT 2015 |  | COMPLETED
1980 | TT_TASK | Rebar fixing for wall and roof | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 | Sat Sep 05 08:00:00 IDT 2015 | Tue Sep 08 18:00:00 IDT 2015 |  | COMPLETED
1981 | TT_TASK | Erect external formwork for wall and roof | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Thu Sep 10 18:00:00 IDT 2015 |  | COMPLETED
1982 | TT_TASK | Concreting for wall and roof (260m3) | Fri Oct 02 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 | Sat Oct 24 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 |  | COMPLETED
1983 | TT_TASK | Curing for wall and roof | Sat Oct 03 08:00:00 IDT 2015 | Mon Oct 12 18:00:00 IDT 2015 | Mon Oct 26 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1984 | TT_TASK | Preparation of construction joint for wall and roof | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 | Mon Nov 02 08:00:00 IST 2015 | Mon Nov 02 18:00:00 IST 2015 |  | COMPLETED
1985 | TT_TASK | Removal external and internal formwork for wall | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 | Tue Nov 03 08:00:00 IST 2015 | Tue Nov 03 18:00:00 IST 2015 |  | COMPLETED
1986 | TT_TASK | Removal internal falsework and formwork for roof | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 | Wed Nov 04 08:00:00 IST 2015 | Thu Nov 05 18:00:00 IST 2015 |  | COMPLETED
1987 | TT_TASK | Side walkway and cable bracket (204m3) | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 | Fri Nov 06 08:00:00 IST 2015 | Wed Nov 11 18:00:00 IST 2015 |  | COMPLETED
1989 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
1990 | TT_TASK | Erect external formwork for base slab | Mon Jun 15 08:00:00 IDT 2015 | Tue Jun 16 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
1991 | TT_TASK | Rebar fixing for base slab | Wed Jun 17 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
1992 | TT_TASK | Erect internal kicker formwork for base slab | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
1993 | TT_TASK | Concreting for base slab (127m3) | Tue Jun 23 08:00:00 IDT 2015 | Tue Jun 23 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
1994 | TT_TASK | Curing for base slab | Wed Jun 24 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
1995 | TT_TASK | Preparation of construction joint for base slab | Wed Jun 24 08:00:00 IDT 2015 | Wed Jun 24 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
1996 | TT_TASK | Removal of formwork for base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
1997 | TT_TASK | Infill concrete in between D-wall and base slab | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
1998 | TT_TASK | Curing | Thu May 28 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
1999 | TT_TASK | Removal strut S3 | Fri May 29 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2000 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Jun 03 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2001 | TT_TASK | Rebar fixing for wall and roof | Mon Jun 08 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2002 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2003 | TT_TASK | Concreting for wall and roof (260m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2004 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2005 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2006 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2007 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2008 | TT_TASK | Side walkway and cable bracket (204m3) | Sat Jul 11 08:00:00 IDT 2015 | Thu Jul 16 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2010 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 |  | COMPLETED
2011 | TT_TASK | Erect external formwork for base slab | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 |  | COMPLETED
2012 | TT_TASK | Rebar fixing for base slab | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 |  | COMPLETED
2013 | TT_TASK | Erect internal kicker formwork for base slab | Mon Jun 08 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 |  | COMPLETED
2014 | TT_TASK | Concreting for base slab (127m3) | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 |  | COMPLETED
2015 | TT_TASK | Curing for base slab | Thu Jun 11 08:00:00 IDT 2015 | Wed Jun 17 18:00:00 IDT 2015 | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2016 | TT_TASK | Preparation of construction joint for base slab | Thu Jun 11 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Thu Apr 30 18:00:00 IDT 2015 |  | COMPLETED
2017 | TT_TASK | Removal of formwork for base slab | Sat May 23 08:00:00 IDT 2015 | Sat May 23 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Mon May 11 18:00:00 IDT 2015 |  | COMPLETED
2018 | TT_TASK | Infill concrete in between D-wall and base slab | Tue May 26 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Tue May 12 08:00:00 IDT 2015 | Tue May 12 18:00:00 IDT 2015 |  | COMPLETED
2019 | TT_TASK | Curing | Wed May 27 08:00:00 IDT 2015 | Wed May 27 18:00:00 IDT 2015 | Wed May 13 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2020 | TT_TASK | Removal strut S3 | Thu May 28 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Mon May 18 18:00:00 IDT 2015 |  | COMPLETED
2021 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue May 19 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 |  | COMPLETED
2022 | TT_TASK | Rebar fixing for wall and roof | Sat Jun 06 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Sat May 23 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 |  | COMPLETED
2023 | TT_TASK | Erect external formwork for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Thu Jun 11 08:00:00 IDT 2015 | Fri Jun 12 18:00:00 IDT 2015 |  | COMPLETED
2024 | TT_TASK | Concreting for wall and roof (150m3) | Mon Jun 08 08:00:00 IDT 2015 | Mon Jun 08 18:00:00 IDT 2015 | Sat Jun 13 08:00:00 IDT 2015 | Sat Jun 13 18:00:00 IDT 2015 |  | COMPLETED
2025 | TT_TASK | Curing for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Thu Jun 18 18:00:00 IDT 2015 | Mon Jun 15 08:00:00 IDT 2015 | Thu Jun 25 18:00:00 IDT 2015 |  | COMPLETED
2026 | TT_TASK | Preparation of construction joint for wall and roof | Tue Jun 09 08:00:00 IDT 2015 | Tue Jun 09 18:00:00 IDT 2015 | Fri Jun 26 08:00:00 IDT 2015 | Fri Jun 26 18:00:00 IDT 2015 |  | COMPLETED
2027 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 10 08:00:00 IDT 2015 | Wed Jun 10 18:00:00 IDT 2015 | Sat Jun 27 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 |  | COMPLETED
2028 | TT_TASK | Removal internal falsework and formwork for roof | Fri Jun 19 08:00:00 IDT 2015 | Mon Jun 22 18:00:00 IDT 2015 | Mon Jun 29 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2029 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jul 06 08:00:00 IDT 2015 | Fri Jul 10 18:00:00 IDT 2015 | Tue Jun 30 08:00:00 IDT 2015 | Mon Oct 05 18:00:00 IDT 2015 |  | COMPLETED
2031 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2032 | TT_TASK | Erect external formwork for base slab | Thu May 21 08:00:00 IDT 2015 | Fri May 22 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2033 | TT_TASK | Rebar fixing for base slab | Sat May 23 08:00:00 IDT 2015 | Tue May 26 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2034 | TT_TASK | Erect internal kicker formwork for base slab | Wed May 27 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2035 | TT_TASK | Concreting for base slab (70m3) | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2036 | TT_TASK | Curing for base slab | Sat May 30 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2037 | TT_TASK | Preparation of construction joint for base slab | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2038 | TT_TASK | Removal of formwork for base slab | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2039 | TT_TASK | Infill concrete in between D-wall and base slab | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2040 | TT_TASK | Curing | Sat Jun 06 08:00:00 IDT 2015 | Sat Jun 06 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2041 | TT_TASK | Removal strut S3 | Mon Jun 08 08:00:00 IDT 2015 | Thu Jun 11 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2042 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat May 23 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2043 | TT_TASK | Rebar fixing for wall and roof | Fri May 29 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2044 | TT_TASK | Erect external formwork for wall and roof | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2045 | TT_TASK | Concreting for wall and roof (175m3) | Thu Jun 04 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2046 | TT_TASK | Curing for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Sun Jun 14 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2047 | TT_TASK | Preparation of construction joint for wall and roof | Fri Jun 05 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2048 | TT_TASK | Removal external and internal formwork for wall | Wed Jun 03 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2049 | TT_TASK | Removal internal falsework and formwork for roof | Thu Jun 04 08:00:00 IDT 2015 | Fri Jun 05 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2050 | TT_TASK | Side walkway and cable bracket (204m3) | Mon Jun 29 08:00:00 IDT 2015 | Sat Jul 04 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Sat Oct 03 18:00:00 IDT 2015 |  | COMPLETED
2052 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Mon Apr 13 08:00:00 IDT 2015 | Mon Apr 13 18:00:00 IDT 2015 | Mon Mar 16 08:00:00 IST 2015 | Mon Mar 16 18:00:00 IST 2015 |  | COMPLETED
2053 | TT_TASK | Erect external formwork for base slab | Tue Apr 14 08:00:00 IDT 2015 | Wed Apr 15 18:00:00 IDT 2015 | Tue Mar 17 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2054 | TT_TASK | Rebar fixing for base slab | Thu Apr 16 08:00:00 IDT 2015 | Fri Apr 17 18:00:00 IDT 2015 | Fri Mar 20 08:00:00 IST 2015 | Sat Mar 28 18:00:00 IDT 2015 |  | COMPLETED
2055 | TT_TASK | Erect internal kicker formwork for base slab | Sat Apr 18 08:00:00 IDT 2015 | Mon Apr 20 18:00:00 IDT 2015 | Mon Mar 30 08:00:00 IDT 2015 | Wed Apr 01 18:00:00 IDT 2015 |  | COMPLETED
2056 | TT_TASK | Concreting for base slab (70m3) | Tue Apr 21 08:00:00 IDT 2015 | Tue Apr 21 18:00:00 IDT 2015 | Thu Apr 02 08:00:00 IDT 2015 | Thu Apr 02 18:00:00 IDT 2015 |  | COMPLETED
2057 | TT_TASK | Curing for base slab | Wed Apr 22 08:00:00 IDT 2015 | Tue Apr 28 18:00:00 IDT 2015 | Wed Apr 08 08:00:00 IDT 2015 | Sat Apr 18 18:00:00 IDT 2015 |  | COMPLETED
2058 | TT_TASK | Preparation of construction joint for base slab | Wed Apr 22 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Wed Apr 22 18:00:00 IDT 2015 |  | COMPLETED
2059 | TT_TASK | Removal of formwork for base slab | Thu Apr 23 08:00:00 IDT 2015 | Thu Apr 23 18:00:00 IDT 2015 | Thu Apr 23 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 |  | COMPLETED
2060 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Apr 24 08:00:00 IDT 2015 | Fri Apr 24 18:00:00 IDT 2015 | Sat Apr 25 08:00:00 IDT 2015 | Mon Apr 27 18:00:00 IDT 2015 |  | COMPLETED
2061 | TT_TASK | Curing | Wed Apr 29 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 | Tue Apr 28 08:00:00 IDT 2015 | Wed Apr 29 18:00:00 IDT 2015 |  | COMPLETED
2062 | TT_TASK | Removal strut S3 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 | Thu Apr 30 08:00:00 IDT 2015 | Tue May 05 18:00:00 IDT 2015 |  | COMPLETED
2063 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed May 06 08:00:00 IDT 2015 | Wed May 06 18:00:00 IDT 2015 | Wed May 06 08:00:00 IDT 2015 | Sat May 09 18:00:00 IDT 2015 |  | COMPLETED
2064 | TT_TASK | Rebar fixing for wall and roof | Thu May 14 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 | Mon May 11 08:00:00 IDT 2015 | Wed May 13 18:00:00 IDT 2015 |  | COMPLETED
2065 | TT_TASK | Erect external formwork for wall and roof | Mon May 18 08:00:00 IDT 2015 | Tue May 19 18:00:00 IDT 2015 | Thu May 14 08:00:00 IDT 2015 | Fri May 15 18:00:00 IDT 2015 |  | COMPLETED
2066 | TT_TASK | Concreting for wall and roof (175m3) | Wed May 20 08:00:00 IDT 2015 | Wed May 20 18:00:00 IDT 2015 | Sat May 16 08:00:00 IDT 2015 | Sat May 16 18:00:00 IDT 2015 |  | COMPLETED
2067 | TT_TASK | Curing for wall and roof | Thu May 21 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 | Mon May 18 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 |  | COMPLETED
2068 | TT_TASK | Preparation of construction joint for wall and roof | Thu May 21 08:00:00 IDT 2015 | Thu May 21 18:00:00 IDT 2015 | Sat May 30 08:00:00 IDT 2015 | Sat May 30 18:00:00 IDT 2015 |  | COMPLETED
2069 | TT_TASK | Removal external and internal formwork for wall | Tue Jun 02 08:00:00 IDT 2015 | Tue Jun 02 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Mon Jun 01 18:00:00 IDT 2015 |  | COMPLETED
2070 | TT_TASK | Removal internal falsework and formwork for roof | Wed Jun 03 08:00:00 IDT 2015 | Thu Jun 04 18:00:00 IDT 2015 | Tue Jun 02 08:00:00 IDT 2015 | Wed Jun 03 18:00:00 IDT 2015 |  | COMPLETED
2071 | TT_TASK | Side walkway and cable bracket (204m3) | Tue Jun 23 08:00:00 IDT 2015 | Sat Jun 27 18:00:00 IDT 2015 | Thu Jun 04 08:00:00 IDT 2015 | Fri Oct 02 18:00:00 IDT 2015 |  | COMPLETED
2073 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Fri Nov 15 08:00:00 IST 2013 | Fri Nov 15 18:00:00 IST 2013 |  | COMPLETED
2074 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Nov 16 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2075 | TT_TASK | Rebar fixing for base slab | Sat Dec 14 08:00:00 IST 2013 | Mon Dec 16 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Wed Nov 20 18:00:00 IST 2013 |  | COMPLETED
2076 | TT_TASK | Erect internal kicker formwork for base slab | Tue Dec 17 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Thu Nov 21 08:00:00 IST 2013 | Fri Nov 22 18:00:00 IST 2013 |  | COMPLETED
2077 | TT_TASK | Concreting for base slab (70m3) | Thu Dec 19 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Nov 23 08:00:00 IST 2013 | Sat Nov 23 18:00:00 IST 2013 |  | COMPLETED
2078 | TT_TASK | Curing for base slab | Fri Dec 20 08:00:00 IST 2013 | Thu Dec 26 18:00:00 IST 2013 | Mon Nov 25 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 |  | COMPLETED
2079 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 |  | COMPLETED
2080 | TT_TASK | Removal of formwork for base slab | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 |  | COMPLETED
2081 | TT_TASK | Infill concrete in between D-wall and base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Thu Dec 05 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 |  | COMPLETED
2082 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2083 | TT_TASK | Removal strut S3 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2084 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Apr 16 08:00:00 IDT 2014 | Wed Apr 23 18:00:00 IDT 2014 | Tue Apr 01 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2085 | TT_TASK | Rebar fixing for wall and roof | Thu Apr 24 08:00:00 IDT 2014 | Sat Apr 26 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Wed Apr 09 18:00:00 IDT 2014 |  | COMPLETED
2086 | TT_TASK | Erect external formwork for wall and roof | Mon Apr 28 08:00:00 IDT 2014 | Tue Apr 29 18:00:00 IDT 2014 | Thu Apr 10 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2087 | TT_TASK | Concreting for wall and roof (170m3) | Wed Apr 30 08:00:00 IDT 2014 | Wed Apr 30 18:00:00 IDT 2014 | Sat Apr 12 08:00:00 IDT 2014 | Sat Apr 12 18:00:00 IDT 2014 |  | COMPLETED
2088 | TT_TASK | Curing for wall and roof | Thu May 01 08:00:00 IDT 2014 | Sat May 10 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Tue Apr 22 18:00:00 IDT 2014 |  | COMPLETED
2089 | TT_TASK | Preparation of construction joint for wall and roof | Fri May 02 08:00:00 IDT 2014 | Fri May 02 18:00:00 IDT 2014 | Mon Apr 14 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 |  | COMPLETED
2090 | TT_TASK | Removal external and internal formwork for wall | Sat May 03 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Tue Apr 15 08:00:00 IDT 2014 | Tue Apr 15 18:00:00 IDT 2014 |  | COMPLETED
2091 | TT_TASK | Removal internal falsework and formwork for roof | Mon May 12 08:00:00 IDT 2014 | Tue May 13 18:00:00 IDT 2014 | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 |  | COMPLETED
2092 | TT_TASK | Side walkway and cable bracket (204m3) | Thu Jun 05 08:00:00 IDT 2014 | Tue Jun 10 18:00:00 IDT 2014 | Thu May 29 08:00:00 IDT 2014 | Thu Dec 04 18:00:00 IST 2014 |  | COMPLETED
2094 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2095 | TT_TASK | Erect external formwork for base slab | Thu Dec 12 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2096 | TT_TASK | Rebar fixing for base slab | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2097 | TT_TASK | Erect internal kicker formwork for base slab | Thu Dec 05 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2098 | TT_TASK | Concreting for base slab (70m3) | Sat Dec 07 08:00:00 IST 2013 | Sat Dec 07 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2099 | TT_TASK | Curing for base slab | Sun Dec 08 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2100 | TT_TASK | Preparation of construction joint for base slab | Mon Dec 09 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2101 | TT_TASK | Removal of formwork for base slab | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Nov 13 08:00:00 IST 2013 | Wed Nov 13 18:00:00 IST 2013 |  | COMPLETED
2102 | TT_TASK | Infill concrete in between D-wall and base slab | Wed Dec 11 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Thu Nov 14 08:00:00 IST 2013 | Thu Nov 14 18:00:00 IST 2013 |  | COMPLETED
2103 | TT_TASK | Curing | Sun Dec 15 08:00:00 IST 2013 | Sun Dec 15 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2104 | TT_TASK | Removal strut S3 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2105 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Wed Feb 12 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2106 | TT_TASK | Rebar fixing for wall and roof | Mon Feb 17 08:00:00 IST 2014 | Wed Feb 19 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Jan 02 18:00:00 IST 2014 |  | COMPLETED
2107 | TT_TASK | Erect external formwork for wall and roof | Fri Feb 28 13:48:00 IST 2014 | Mon Mar 03 13:48:00 IST 2014 | Fri Jan 03 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2108 | TT_TASK | Concreting for wall and roof (200m3) | Mon Mar 03 13:48:00 IST 2014 | Tue Mar 04 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2109 | TT_TASK | Curing for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Fri Mar 14 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2110 | TT_TASK | Preparation of construction joint for wall and roof | Tue Mar 04 13:48:00 IST 2014 | Wed Mar 05 13:48:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2111 | TT_TASK | Removal external and internal formwork for wall | Wed Mar 05 13:48:00 IST 2014 | Thu Mar 06 13:48:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Mon Jan 13 18:00:00 IST 2014 |  | COMPLETED
2112 | TT_TASK | Removal internal falsework and formwork for roof | Fri Mar 14 13:48:00 IST 2014 | Mon Mar 17 13:48:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2113 | TT_TASK | Side walkway and cable bracket (204m3) | Thu May 29 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Wed Dec 03 18:00:00 IST 2014 |  | COMPLETED
2115 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Fri Nov 29 08:00:00 IST 2013 | Fri Nov 29 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2116 | TT_TASK | Erect external formwork for base slab | Sat Nov 30 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Thu Oct 17 08:00:00 IDT 2013 | Mon Oct 21 18:00:00 IDT 2013 |  | COMPLETED
2117 | TT_TASK | Rebar fixing for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Tue Oct 22 08:00:00 IDT 2013 | Fri Oct 25 18:00:00 IDT 2013 |  | COMPLETED
2118 | TT_TASK | Erect internal kicker formwork for base slab | Fri Nov 29 08:00:00 IST 2013 | Sat Nov 30 18:00:00 IST 2013 | Thu Nov 07 08:00:00 IST 2013 | Fri Nov 08 18:00:00 IST 2013 |  | COMPLETED
2119 | TT_TASK | Concreting for base slab (70m3) | Mon Dec 02 08:00:00 IST 2013 | Mon Dec 02 18:00:00 IST 2013 | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 |  | COMPLETED
2120 | TT_TASK | Curing for base slab | Tue Dec 03 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 18 18:00:00 IST 2013 |  | COMPLETED
2121 | TT_TASK | Preparation of construction joint for base slab | Tue Dec 03 08:00:00 IST 2013 | Tue Dec 03 18:00:00 IST 2013 | Mon Nov 11 08:00:00 IST 2013 | Mon Nov 11 18:00:00 IST 2013 |  | COMPLETED
2122 | TT_TASK | Removal of formwork for base slab | Wed Dec 04 08:00:00 IST 2013 | Wed Dec 04 18:00:00 IST 2013 | Tue Nov 12 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 |  | COMPLETED
2123 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2124 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Nov 19 08:00:00 IST 2013 | Tue Nov 19 18:00:00 IST 2013 |  | COMPLETED
2125 | TT_TASK | Removal strut S3 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Wed Dec 11 18:00:00 IST 2013 |  | COMPLETED
2126 | TT_TASK | Erect internal formwork & Falsework for wall and roof | Sat Jan 25 08:00:00 IST 2014 | Wed Jan 29 18:00:00 IST 2014 | Mon Dec 16 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 |  | COMPLETED
2127 | TT_TASK | Rebar fixing for wall and roof | Thu Jan 30 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Fri Dec 20 08:00:00 IST 2013 | Wed Jan 08 18:00:00 IST 2014 |  | COMPLETED
2128 | TT_TASK | Erect external formwork for wall and roof | Thu Feb 20 08:00:00 IST 2014 | Fri Feb 21 18:00:00 IST 2014 | Thu Jan 09 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2129 | TT_TASK | Concreting for wall and roof (200m3) | Sat Feb 22 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2130 | TT_TASK | Curing for wall and roof | Sun Feb 23 08:00:00 IST 2014 | Tue Mar 04 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2131 | TT_TASK | Preparation of construction joint for wall and roof | Mon Feb 24 08:00:00 IST 2014 | Mon Feb 24 18:00:00 IST 2014 | Tue Jan 14 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2132 | TT_TASK | Removal external and internal formwork for wall | Tue Feb 25 08:00:00 IST 2014 | Tue Feb 25 18:00:00 IST 2014 | Wed Jan 15 08:00:00 IST 2014 | Wed Jan 15 18:00:00 IST 2014 |  | COMPLETED
2133 | TT_TASK | Removal internal falsework and formwork for roof | Wed Mar 05 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Fri Jan 24 08:00:00 IST 2014 | Sat Jan 25 18:00:00 IST 2014 |  | COMPLETED
2134 | TT_TASK | Side walkway and cable bracket (204m3) | Fri May 23 08:00:00 IDT 2014 | Wed May 28 18:00:00 IDT 2014 | Fri May 23 08:00:00 IDT 2014 | Tue Dec 02 18:00:00 IST 2014 |  | COMPLETED
2137 | TT_TASK | Placing of waterproof member T-lock & testing for base slab | Sat Nov 09 08:00:00 IST 2013 | Sat Nov 09 18:00:00 IST 2013 | Thu Sep 19 08:00:00 IDT 2013 | Sat Sep 21 18:00:00 IDT 2013 |  | COMPLETED
2138 | TT_TASK | Erect external formwork for base slab | Mon Nov 11 08:00:00 IST 2013 | Tue Nov 12 18:00:00 IST 2013 | Sat Sep 21 08:00:00 IDT 2013 | Tue Sep 24 18:00:00 IDT 2013 |  | COMPLETED
2139 | TT_TASK | Rebar fixing for base slab | Mon Dec 09 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Wed Oct 02 08:00:00 IDT 2013 | Sat Oct 05 18:00:00 IDT 2013 |  | COMPLETED
2140 | TT_TASK | Erect internal kicker formwork for base slab | Wed Dec 11 08:00:00 IST 2013 | Thu Dec 12 18:00:00 IST 2013 | Mon Oct 07 08:00:00 IDT 2013 | Thu Oct 10 18:00:00 IDT 2013 |  | COMPLETED
2141 | TT_TASK | Staircase construction (+12.0mPD to +14.706mPD) | Tue Feb 04 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2142 | TT_TASK | Concreting for base slab (30m3) | Wed Dec 18 08:00:00 IST 2013 | Wed Dec 18 18:00:00 IST 2013 | Fri Oct 11 08:00:00 IDT 2013 | Fri Oct 11 18:00:00 IDT 2013 |  | COMPLETED
2143 | TT_TASK | Curing for base slab | Fri Dec 13 08:00:00 IST 2013 | Thu Dec 19 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 19 18:00:00 IDT 2013 |  | COMPLETED
2144 | TT_TASK | Preparation of construction joint for base slab | Fri Dec 13 08:00:00 IST 2013 | Fri Dec 13 18:00:00 IST 2013 | Sat Oct 12 08:00:00 IDT 2013 | Sat Oct 12 18:00:00 IDT 2013 |  | COMPLETED
2145 | TT_TASK | Removal of formwork for base slab | Sat Dec 14 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Tue Oct 15 08:00:00 IDT 2013 | Tue Oct 15 18:00:00 IDT 2013 |  | COMPLETED
2146 | TT_TASK | Infill concrete in between D-wall and base slab | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 | Fri Dec 06 08:00:00 IST 2013 | Fri Dec 06 18:00:00 IST 2013 |  | COMPLETED
2147 | TT_TASK | Mass concrete at level +12.0mPD | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 | Sat Dec 07 08:00:00 IST 2013 | Mon Dec 09 18:00:00 IST 2013 |  | COMPLETED
2148 | TT_TASK | Curing | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 | Tue Dec 10 08:00:00 IST 2013 | Tue Dec 10 18:00:00 IST 2013 |  | COMPLETED
2149 | TT_TASK | Removal strut S3 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 | Wed Dec 11 08:00:00 IST 2013 | Sat Dec 14 18:00:00 IST 2013 |  | COMPLETED
2150 | TT_TASK | Side walkway and cable bracket (204m3) | Sat May 17 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Mon Dec 01 18:00:00 IST 2014 |  | COMPLETED
2152 | TT_TASK | Erect working platform to +21.0mPD | Tue Jan 07 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 | Thu Jan 02 08:00:00 IST 2014 | Mon Jan 06 18:00:00 IST 2014 |  | COMPLETED
2153 | TT_TASK | Rebar fixing for wall and roof | Sat Jan 11 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 | Tue Jan 07 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2154 | TT_TASK | Staircase construction (+14.706mPD to +16.956mPD) (20m3) | Fri May 02 08:00:00 IDT 2014 | Wed May 07 18:00:00 IDT 2014 | Fri May 02 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2155 | TT_TASK | Staircase construction (+16.956mPD to +19.206mPD) (20m3) | Thu Jun 05 08:00:00 IDT 2014 | Mon Jun 09 18:00:00 IDT 2014 | Thu Jun 12 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2156 | TT_TASK | Staircase construction (+19.206mPD to +21.456mPD) (20m3) | Tue Jun 10 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Fri Jun 20 18:00:00 IDT 2014 |  | COMPLETED
2157 | TT_TASK | Erect external formwork for wall and roof | Sat Mar 15 08:00:00 IST 2014 | Mon Mar 17 18:00:00 IST 2014 | Wed Jan 08 08:00:00 IST 2014 | Thu Jan 09 18:00:00 IST 2014 |  | COMPLETED
2158 | TT_TASK | Concreting for wall and roof (31m3) | Tue Feb 04 08:00:00 IST 2014 | Tue Feb 04 18:00:00 IST 2014 | Fri Jan 10 08:00:00 IST 2014 | Fri Jan 10 18:00:00 IST 2014 |  | COMPLETED
2159 | TT_TASK | Curing for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Fri Feb 14 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Wed Jan 22 18:00:00 IST 2014 |  | COMPLETED
2160 | TT_TASK | Preparation of construction joint for wall and roof | Wed Feb 05 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Sat Jan 11 08:00:00 IST 2014 | Sat Jan 11 18:00:00 IST 2014 |  | COMPLETED
2161 | TT_TASK | Removal external and internal formwork for wall | Thu Feb 06 08:00:00 IST 2014 | Fri Feb 07 18:00:00 IST 2014 | Mon Jan 13 08:00:00 IST 2014 | Tue Jan 14 18:00:00 IST 2014 |  | COMPLETED
2162 | TT_TASK | Removal internal falsework and formwork for roof | Sat Feb 15 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Thu Jan 23 08:00:00 IST 2014 | Thu Jan 23 18:00:00 IST 2014 |  | COMPLETED
2164 | TT_TASK | Removal strut S2 @ SN 19 | Wed Apr 02 08:00:00 IDT 2014 | Mon Apr 07 18:00:00 IDT 2014 | Mon Mar 03 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 |  | COMPLETED
2165 | TT_TASK | Erect working platform to +24.0mPD | Tue Apr 08 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 | Fri Mar 07 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 |  | COMPLETED
2166 | TT_TASK | Erect internal formwork below strut S1 | Sat Apr 12 08:00:00 IDT 2014 | Mon Apr 14 18:00:00 IDT 2014 | Wed Mar 12 08:00:00 IST 2014 | Thu Mar 13 18:00:00 IST 2014 |  | COMPLETED
2167 | TT_TASK | Staircase construction (+21.456mPD to +23.706mPD) (20m3) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 |  | COMPLETED
2168 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Wed Apr 23 08:00:00 IDT 2014 | Thu Apr 24 18:00:00 IDT 2014 | Fri Mar 14 08:00:00 IST 2014 | Tue Apr 01 18:00:00 IDT 2014 |  | COMPLETED
2169 | TT_TASK | Erect external wall & internal wall formwork | Tue May 13 08:00:00 IDT 2014 | Wed May 14 18:00:00 IDT 2014 | Wed Apr 02 08:00:00 IDT 2014 | Thu Apr 03 18:00:00 IDT 2014 |  | COMPLETED
2170 | TT_TASK | Concreting (External Wall & Internal Wall) (264m3) | Thu May 15 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 | Fri Apr 04 08:00:00 IDT 2014 | Fri Apr 04 18:00:00 IDT 2014 |  | COMPLETED
2171 | TT_TASK | Curing (External Wall & Internal Wall) | Fri May 16 08:00:00 IDT 2014 | Thu May 22 18:00:00 IDT 2014 | Mon Apr 07 08:00:00 IDT 2014 | Fri Apr 11 18:00:00 IDT 2014 |  | COMPLETED
2172 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Mon May 19 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Wed Apr 09 08:00:00 IDT 2014 | Thu Apr 10 18:00:00 IDT 2014 |  | COMPLETED
2173 | TT_TASK | Waterproofing | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 | Thu Jun 19 08:00:00 IDT 2014 | Sat Jun 21 18:00:00 IDT 2014 |  | COMPLETED
2174 | TT_TASK | Backfilling | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2176 | TT_TASK | Removal strut S1 @ SN 19 | Thu Jun 19 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2177 | TT_TASK | Erect working platform to +30.406mPD | Tue Jun 24 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2178 | TT_TASK | Erect internal formwork | Sat Jun 28 08:00:00 IDT 2014 | Sat Jun 28 18:00:00 IDT 2014 | Wed Jun 04 08:00:00 IDT 2014 | Wed Jun 04 18:00:00 IDT 2014 |  | COMPLETED
2179 | TT_TASK | Rebar fixing (External Wall & Internal Wall) | Mon Jun 30 08:00:00 IDT 2014 | Wed Jul 02 18:00:00 IDT 2014 | Thu Jun 05 08:00:00 IDT 2014 | Fri Jun 06 18:00:00 IDT 2014 |  | COMPLETED
2180 | TT_TASK | Erect external formwork (External Wall & Internal Wall) | Thu Jul 03 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2181 | TT_TASK | Concreting (External Wall & Internal Wall) (128m3) | Fri Jul 04 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 | Sat Jun 07 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 |  | COMPLETED
2182 | TT_TASK | Curing (External Wall & Internal Wall) | Sat Jul 05 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Mon Jun 09 08:00:00 IDT 2014 | Sat Jun 14 18:00:00 IDT 2014 |  | COMPLETED
2183 | TT_TASK | Removal formwork (External Wall & Internal Wall) | Tue Jul 08 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Mon Jun 16 08:00:00 IDT 2014 | Mon Jun 16 18:00:00 IDT 2014 |  | COMPLETED
2184 | TT_TASK | Waterproofing | Wed Jul 09 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Tue Jun 17 08:00:00 IDT 2014 | Thu Jun 19 18:00:00 IDT 2014 |  | COMPLETED
2185 | TT_TASK | Backfilling | Sat Jul 12 08:00:00 IDT 2014 | Wed Jul 16 18:00:00 IDT 2014 | Fri Jun 20 08:00:00 IDT 2014 | Tue Jun 24 18:00:00 IDT 2014 |  | COMPLETED
2186 | TT_TASK | Erect falsework and soffit formwork +30.206mPD | Thu Jul 17 08:00:00 IDT 2014 | Fri Jul 18 18:00:00 IDT 2014 | Wed Jun 25 08:00:00 IDT 2014 | Thu Jun 26 18:00:00 IDT 2014 |  | COMPLETED
2187 | TT_TASK | Staircase construction (+21.456mPD to +25.956mPD) (20m3) | Sat Jul 19 08:00:00 IDT 2014 | Wed Jul 23 18:00:00 IDT 2014 | Fri Jun 27 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2188 | TT_TASK | Staircase construction (+25.956mPD to +27.606mPD) (20m3) | Sat Jul 05 08:00:00 IDT 2014 | Wed Jul 09 18:00:00 IDT 2014 | Sat Jul 05 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 |  | COMPLETED
2189 | TT_TASK | Rebar fixing (Beam, Floor Slab and Staircase) | Thu Jul 10 08:00:00 IDT 2014 | Thu Jul 10 18:00:00 IDT 2014 | Thu Jul 10 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 |  | COMPLETED
2190 | TT_TASK | Concreting (Beam, Floor Slab and Staircase) (31m3) | Fri Jul 11 08:00:00 IDT 2014 | Fri Jul 11 18:00:00 IDT 2014 | Fri Jul 11 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 |  | COMPLETED
2191 | TT_TASK | Curing (Beam, Floor Slab and Staircase) | Wed Sep 03 08:00:00 IDT 2014 | Tue Sep 09 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Mon Sep 29 18:00:00 IDT 2014 |  | COMPLETED
2193 | TT_TASK | Erect working platform to +33.576mPD | Wed Sep 03 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 | Mon Sep 22 08:00:00 IDT 2014 | Thu Sep 25 18:00:00 IDT 2014 |  | COMPLETED
2194 | TT_TASK | Erect external formwork (External Wall) | Mon Sep 08 08:00:00 IDT 2014 | Wed Sep 10 18:00:00 IDT 2014 | Fri Sep 26 08:00:00 IDT 2014 | Sat Sep 27 18:00:00 IDT 2014 |  | COMPLETED
2195 | TT_TASK | Rebar fixing (External Wall) | Thu Sep 11 08:00:00 IDT 2014 | Fri Sep 12 18:00:00 IDT 2014 | Mon Sep 29 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2196 | TT_TASK | Erect internal formwork (External Wall) | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 04 18:00:00 IDT 2014 |  | COMPLETED
2197 | TT_TASK | Concreting (External Wall) (49m3) | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 | Mon Oct 06 08:00:00 IDT 2014 | Mon Oct 06 18:00:00 IDT 2014 |  | COMPLETED
2198 | TT_TASK | Curing (External Wall) | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 | Tue Oct 07 08:00:00 IDT 2014 | Mon Oct 13 18:00:00 IDT 2014 |  | COMPLETED
2199 | TT_TASK | Removal formwork (External Wall) | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 | Thu Oct 09 08:00:00 IDT 2014 | Thu Oct 09 18:00:00 IDT 2014 |  | COMPLETED
2200 | TT_TASK | Erect falsework and soffit formwork +32.656 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 | Fri Oct 10 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2201 | TT_TASK | Rebar fixing (Beam & Floor Slab) | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 | Mon Oct 13 08:00:00 IDT 2014 | Tue Oct 14 18:00:00 IDT 2014 |  | COMPLETED
2202 | TT_TASK | Concreting (Beam & Floor Slab) (31m3) | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 | Wed Oct 15 08:00:00 IDT 2014 | Wed Oct 15 18:00:00 IDT 2014 |  | COMPLETED
2203 | TT_TASK | Curing (Beam & Floor Slab) | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2205 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 | Thu Oct 16 08:00:00 IDT 2014 | Fri Oct 17 18:00:00 IDT 2014 |  | COMPLETED
2206 | TT_TASK | Rebar fixing (Roof Parapet Wall) | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 | Sat Oct 18 08:00:00 IDT 2014 | Mon Oct 20 18:00:00 IDT 2014 |  | COMPLETED
2207 | TT_TASK | Erect external formwork (Roof Parapet Wall) | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 | Tue Oct 21 08:00:00 IDT 2014 | Wed Oct 22 18:00:00 IDT 2014 |  | COMPLETED
2208 | TT_TASK | Concreting (Roof Parapet Wall) (30m3) | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 | Thu Oct 23 08:00:00 IDT 2014 | Thu Oct 23 18:00:00 IDT 2014 |  | COMPLETED
2209 | TT_TASK | Curing (Roof Parapet Wall) | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 | Fri Oct 24 08:00:00 IDT 2014 | Thu Oct 30 18:00:00 IST 2014 |  | COMPLETED
2210 | TT_TASK | Removal formwork (Roof Parapet Wall) | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 | Mon Oct 27 08:00:00 IST 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2211 | TT_TASK | Removal of falsework and soffit formwork | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 | Fri Oct 31 08:00:00 IST 2014 | Tue Nov 04 18:00:00 IST 2014 |  | COMPLETED
2213 | TT_TASK | Wet trade work | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 | Wed Nov 05 08:00:00 IST 2014 | Wed Nov 26 18:00:00 IST 2014 |  | COMPLETED
2214 | TT_TASK | Metal works (Louver, Door, Cat-ladder, Architectural Fins, Handrail, Roof Sliding Hatch and Balustrade, etc) | Thu Nov 27 08:00:00 IST 2014 | Fri Dec 12 18:00:00 IST 2014 | Thu Nov 27 08:00:00 IST 2014 | Thu Mar 05 18:00:00 IST 2015 |  | COMPLETED
2215 | TT_TASK | Coat works | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 | Fri Mar 06 08:00:00 IST 2015 | Thu Mar 19 18:00:00 IST 2015 |  | COMPLETED
2218 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Nov 29 08:00:00 IST 2013 | Thu Dec 05 18:00:00 IST 2013 | Wed Jun 26 08:00:00 IDT 2013 | Tue Feb 04 18:00:00 IST 2014 |  | COMPLETED
2219 | TT_TASK | Backfilling between D-wall and 0.5m below S1 14,240m3 soil | Thu Feb 06 08:00:00 IST 2014 | Tue Mar 11 18:00:00 IST 2014 | Wed Feb 05 08:00:00 IST 2014 | Sat Feb 22 18:00:00 IST 2014 |  | COMPLETED
2220 | TT_TASK | Removal of S1 | Wed Mar 12 08:00:00 IST 2014 | Tue Mar 25 18:00:00 IST 2014 | Mon Feb 24 08:00:00 IST 2014 | Fri Feb 28 18:00:00 IST 2014 |  | COMPLETED
2221 | TT_TASK | Backfilling to original ground level 21,390m3 (approx. +25.0mPD) | Sat Mar 01 08:00:00 IST 2014 | Wed Mar 19 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Sat May 03 18:00:00 IDT 2014 |  | COMPLETED
2223 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 | Tue Feb 04 08:00:00 IST 2014 | Wed Feb 05 18:00:00 IST 2014 |  | COMPLETED
2224 | TT_TASK | Backfilling between D-wall and 0.5m below S1 (2075m3) | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 | Thu Feb 06 08:00:00 IST 2014 | Thu Feb 13 18:00:00 IST 2014 |  | COMPLETED
2225 | TT_TASK | Removal of S1 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 | Fri Feb 14 08:00:00 IST 2014 | Sat Feb 15 18:00:00 IST 2014 |  | COMPLETED
2226 | TT_TASK | Backfilling to original ground level 3,900m3 (approx. +25.0mPD) (1353m3) | Sat Mar 01 08:00:00 IST 2014 | Thu Mar 06 18:00:00 IST 2014 | Sat Mar 01 08:00:00 IST 2014 | Fri May 02 18:00:00 IDT 2014 |  | COMPLETED
2227 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jul 02 08:00:00 IDT 2013 | Fri Jul 05 18:00:00 IDT 2013 | Wed Mar 27 08:00:00 IST 2013 | Tue Apr 23 18:00:00 IDT 2013 |  | COMPLETED
2228 | TT_TASK | Backfilling backfilling to +20mPD from SN8 to SN9 (Soil: 7,050m3 @ 500m3/day) | Tue Jul 02 08:00:00 IDT 2013 | Wed Jul 17 18:00:00 IDT 2013 | Sat Jun 01 08:00:00 IDT 2013 | Sat Jun 29 18:00:00 IDT 2013 |  | COMPLETED
2229 | TT_TASK | Removal of S1 | Mon Sep 02 08:00:00 IDT 2013 | Thu Sep 05 18:00:00 IDT 2013 | Sat Jul 13 08:00:00 IDT 2013 | Sat Jul 20 18:00:00 IDT 2013 |  | COMPLETED
2230 | TT_TASK | Construction of mud pit | Sat Jul 06 08:00:00 IDT 2013 | Thu Jul 18 18:00:00 IDT 2013 | Fri May 31 08:00:00 IDT 2013 | Sat Jun 22 18:00:00 IDT 2013 |  | COMPLETED
2231 | TT_TASK | Backfilling from +20mPD to ground level from SN8 to SN9 (Soil: 5,000m3 @ 500m3/day) | Tue Aug 06 08:00:00 IDT 2013 | Sat Aug 17 18:00:00 IDT 2013 | Tue Jul 02 08:00:00 IDT 2013 | Sat Aug 10 18:00:00 IDT 2013 |  | COMPLETED
2233 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Fri Aug 07 08:00:00 IDT 2015 | Thu Aug 13 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 |  | COMPLETED
2234 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) | Fri Aug 14 08:00:00 IDT 2015 | Tue Aug 18 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2235 | TT_TASK | Placing mass concrete infill between tunnel and D-wall | Wed Dec 02 08:00:00 IST 2015 | Wed Dec 02 18:00:00 IST 2015 | Thu Dec 24 08:00:00 IST 2015 | Thu Dec 24 18:00:00 IST 2015 |  | COMPLETED
2236 | TT_TASK | Removal of S2 | Mon Dec 07 08:00:00 IST 2015 | Thu Dec 10 18:00:00 IST 2015 | Mon Dec 28 08:00:00 IST 2015 | Mon Jan 04 18:00:00 IST 2016 |  | COMPLETED
2237 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 | Tue Jan 05 08:00:00 IST 2016 | Fri Jan 08 18:00:00 IST 2016 |  | COMPLETED
2238 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 | Sat Jan 09 08:00:00 IST 2016 | Thu Jan 14 18:00:00 IST 2016 |  | COMPLETED
2239 | TT_TASK | Removal strut S1 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 | Fri Jan 15 08:00:00 IST 2016 | Tue Jan 19 18:00:00 IST 2016 |  | COMPLETED
2240 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 | Wed Jan 20 08:00:00 IST 2016 | Sat Jan 23 18:00:00 IST 2016 |  | COMPLETED
2241 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488 m3 of soil) | Mon Jan 25 08:00:00 IST 2016 | Fri Jan 29 18:00:00 IST 2016 | Mon Jan 25 08:00:00 IST 2016 | Fri Apr 01 18:00:00 IDT 2016 |  | COMPLETED
2243 | TT_TASK | Spray waterproofing member & testing (Wall & Roof) (SN18-19) | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 | Wed Apr 16 08:00:00 IDT 2014 | Fri Apr 25 18:00:00 IDT 2014 |  | COMPLETED
2244 | TT_TASK | Backfilling between D-wall and 0.5m below S2 (180m3) (SN18-19) | Sat Apr 26 08:00:00 IDT 2014 | Sat May 03 18:00:00 IDT 2014 | Sat Apr 26 08:00:00 IDT 2014 | Thu May 15 18:00:00 IDT 2014 |  | COMPLETED
2245 | TT_TASK | Placing mass concrete infill between tunnel and D-wall (SN18-19) | Tue May 20 08:00:00 IDT 2014 | Tue May 20 18:00:00 IDT 2014 | Fri May 16 08:00:00 IDT 2014 | Fri May 16 18:00:00 IDT 2014 |  | COMPLETED
2246 | TT_TASK | Removal of S2 (SN16-18) | Wed Jun 04 08:00:00 IDT 2014 | Sat Jun 07 18:00:00 IDT 2014 | Sat May 17 08:00:00 IDT 2014 | Wed May 21 18:00:00 IDT 2014 |  | COMPLETED
2247 | TT_TASK | Backfilling to 0.5m below S1 (+24.0mPD) (2480m3 of soil) (SN16-18) | Mon Jun 09 08:00:00 IDT 2014 | Fri Jun 13 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Tue May 27 18:00:00 IDT 2014 |  | COMPLETED
2248 | TT_TASK | Removal strut S1 (SN16-18) | Sat Jun 14 08:00:00 IDT 2014 | Wed Jun 18 18:00:00 IDT 2014 | Wed May 28 08:00:00 IDT 2014 | Sat May 31 18:00:00 IDT 2014 |  | COMPLETED
2249 | TT_TASK | Backfilling to original ground level (approx. +27.0mPD) (1488m3 of soil) | Fri Jun 27 08:00:00 IDT 2014 | Thu Jul 03 18:00:00 IDT 2014 | Mon Jun 23 08:00:00 IDT 2014 | Fri Jun 27 18:00:00 IDT 2014 |  | COMPLETED
2251 | TT_TASK | Dismantling temporary bridge deck | Mon Jun 15 08:00:00 IDT 2015 | Tue Jul 21 18:00:00 IDT 2015 | Mon Jun 01 08:00:00 IDT 2015 | Tue Jun 30 18:00:00 IDT 2015 |  | COMPLETED
2252 | TT_TASK | Reinstatement of Works Area 4.10 | Wed Jun 01 08:00:00 IDT 2016 | Wed Jan 11 18:00:00 IST 2017 | Mon May 02 08:00:00 IDT 2016 | Thu Jun 30 18:00:00 IDT 2016 |  | COMPLETED
2253 | TT_TASK | Complete all tree planting and reinstate Works Area 4.12C | Tue Nov 01 08:00:00 IST 2016 | Thu Jul 13 18:00:00 IDT 2017 | Sat Oct 01 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2254 | TT_TASK | Reinstate Works Areas 4.9, 4.9A and 4.12A prior to handover | Mon May 22 08:00:00 IDT 2017 | Sat Sep 02 18:00:00 IDT 2017 | Sat Jul 02 08:00:00 IDT 2016 |  |  | IN_PROGRESS
2258 | TT_TASK | Application of power supply, environmental permits and construction substation | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 | Tue Nov 15 08:00:00 IST 2011 | Wed Oct 31 18:00:00 IST 2012 |  | COMPLETED
2259 | TT_TASK | Procurement and Confirmation of the order of 2nd tunnel boring machine | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2260 | TT_TASK | TBM design and submission for approval | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 | Tue Nov 15 08:00:00 IST 2011 | Sat Dec 10 18:00:00 IST 2011 |  | COMPLETED
2261 | TT_TASK | TBM materials order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Tue Jan 31 18:00:00 IST 2012 |  | COMPLETED
2262 | TT_TASK | TBM equipments order and delivery to factory | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 | Mon Dec 12 08:00:00 IST 2011 | Sat Mar 24 18:00:00 IST 2012 |  | COMPLETED
2263 | TT_TASK | TBM Fabrication | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 | Wed Feb 01 08:00:00 IST 2012 | Sat May 19 18:00:00 IDT 2012 |  | COMPLETED
2264 | TT_TASK | Final assembly for tunnel boring machine at the factory | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 | Sat Apr 21 08:00:00 IDT 2012 | Sat Jun 09 18:00:00 IDT 2012 |  | COMPLETED
2265 | TT_TASK | TBM test Run | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 | Mon Jun 11 08:00:00 IDT 2012 | Sat Jun 30 18:00:00 IDT 2012 |  | COMPLETED
2266 | TT_TASK | TBM disassembly and packing for shipping to HK | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 | Tue Jul 03 08:00:00 IDT 2012 | Fri Jul 20 18:00:00 IDT 2012 |  | COMPLETED
2267 | TT_TASK | TBM Shipping to HK and delivery to site | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 | Sat Jul 21 08:00:00 IDT 2012 | Tue Jul 31 18:00:00 IDT 2012 |  | COMPLETED
2268 | TT_TASK | Setup TBM facilities | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 | Wed Aug 01 08:00:00 IDT 2012 | Mon Nov 26 18:00:00 IST 2012 |  | COMPLETED
2269 | TT_TASK | Fabrication 50% of South Tunnel South Bound Precast Lining | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 | Wed Aug 01 08:00:00 IDT 2012 | Thu Aug 30 18:00:00 IDT 2012 |  | COMPLETED
2270 | TT_TASK | Fabrication 100% of South Tunnel South Bound Precast Lining | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 | Fri Aug 31 08:00:00 IDT 2012 | Sat Sep 29 18:00:00 IST 2012 |  | COMPLETED
2271 | TT_TASK | Fabrication 50% of South Tunnel North Bound Precast Lining | Wed Oct 03 08:00:00 IST 2012 | Thu Feb 28 18:00:00 IST 2013 | Wed Oct 03 08:00:00 IST 2012 | Tue Feb 26 18:00:00 IST 2013 |  | COMPLETED
2272 | TT_TASK | Fabrication 100% of South Tunnel North Bound Precast Lining | Mon Aug 26 08:00:00 IDT 2013 | Wed Jan 22 18:00:00 IST 2014 | Wed Feb 27 08:00:00 IST 2013 | Wed May 29 18:00:00 IDT 2013 |  | COMPLETED
2274 | TT_TASK | Ground treatment at lauching shaft Southbound | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 | Mon Oct 15 08:00:00 IST 2012 | Sat Nov 17 18:00:00 IST 2012 |  | COMPLETED
2275 | TT_TASK | TBM assemble, thrust frame, testing and commissioning | Sat Jun 01 08:00:00 IDT 2013 | Thu Aug 08 18:00:00 IDT 2013 | Fri Dec 14 08:00:00 IST 2012 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2276 | TT_TASK | Lowing back-up plant for final drive | Sat Jun 01 08:00:00 IDT 2013 | Fri Jun 07 18:00:00 IDT 2013 | Sat Jan 26 08:00:00 IST 2013 | Fri Feb 01 18:00:00 IST 2013 |  | COMPLETED
2277 | TT_TASK | Assemble and set up back-up plant for final drive | Sat Jun 08 08:00:00 IDT 2013 | Mon Jul 08 18:00:00 IDT 2013 | Sat Feb 02 08:00:00 IST 2013 | Wed Feb 27 18:00:00 IST 2013 |  | COMPLETED
2278 | TT_TASK | Erection of noise enclosure | Sat Jul 20 08:00:00 IDT 2013 | Mon Sep 16 18:00:00 IDT 2013 | Mon Feb 18 08:00:00 IST 2013 | Fri Nov 01 18:00:00 IST 2013 |  | COMPLETED
2279 | TT_TASK | TBM drive & lining installation CH124+912 to CH125+012 (Initial Drive) | Sat Jul 20 08:00:00 IDT 2013 | Sat Sep 07 18:00:00 IDT 2013 | Mon Mar 11 00:00:00 IST 2013 | Mon May 27 18:00:00 IDT 2013 |  | COMPLETED
2280 | TT_TASK | TBM drive & lining installation CH125+012 to CH125+338 | Tue Oct 15 08:00:00 IDT 2013 | Mon Nov 18 18:00:00 IST 2013 | Mon May 27 08:00:00 IDT 2013 | Tue May 20 00:00:00 IDT 2014 |  | COMPLETED
2281 | TT_TASK | Dis-assemble TBM | Fri May 23 08:00:00 IDT 2014 | Mon Jun 23 18:00:00 IDT 2014 | Thu May 22 08:00:00 IDT 2014 | Fri Aug 08 18:00:00 IDT 2014 |  | COMPLETED
2282 | TT_TASK | Invert slab and side walkway | Fri Aug 01 08:00:00 IDT 2014 | Sat Sep 13 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Tue Sep 02 18:00:00 IDT 2014 |  | COMPLETED
2283 | TT_TASK | Installation of cable bracket | Mon Nov 03 08:00:00 IST 2014 | Sat Nov 15 18:00:00 IST 2014 | Mon Aug 18 08:00:00 IDT 2014 | Sat Sep 06 18:00:00 IDT 2014 |  | COMPLETED
2285 | TT_TASK | Removal of Roof of Noise Enclosure | Mon Sep 01 08:00:00 IDT 2014 | Sat Sep 20 18:00:00 IDT 2014 | Sat Aug 09 08:00:00 IDT 2014 | Thu Aug 28 18:00:00 IDT 2014 |  | COMPLETED
2286 | TT_TASK | Ground treatment at lauching shaft Northbound | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 19 18:00:00 IST 2013 | Tue Nov 27 08:00:00 IST 2012 | Sat Jan 26 18:00:00 IST 2013 |  | COMPLETED
2287 | TT_TASK | TBM assemble, testing and commissioning | Wed Jul 02 08:00:00 IDT 2014 | Wed Sep 03 18:00:00 IDT 2014 | Mon Jul 14 08:00:00 IDT 2014 | Mon Oct 27 18:00:00 IST 2014 |  | COMPLETED
2288 | TT_TASK | Setup back-up plant for final drive | Tue Jun 03 08:00:00 IDT 2014 | Tue Jul 08 18:00:00 IDT 2014 | Tue Jun 03 08:00:00 IDT 2014 | Fri Jul 04 18:00:00 IDT 2014 |  | COMPLETED
2289 | TT_TASK | Reinstate of noise enclosure | Fri Oct 10 08:00:00 IDT 2014 | Wed Nov 05 18:00:00 IST 2014 | Tue Oct 28 08:00:00 IST 2014 | Fri Jan 09 18:00:00 IST 2015 |  | COMPLETED
2290 | TT_TASK | TBM drive & lining installation CH124+927 to CH125+027 (Initial Drive) | Fri Oct 10 08:00:00 IDT 2014 | Thu Nov 13 18:00:00 IST 2014 | Thu Oct 30 00:00:00 IST 2014 | Sat Dec 06 18:00:00 IST 2014 |  | COMPLETED
2291 | TT_TASK | TBM drive & lining installation CH125+027 to CH125+353 (Final Drive) | Fri Jan 02 08:00:00 IST 2015 | Thu Feb 12 18:00:00 IST 2015 | Mon Dec 08 08:00:00 IST 2014 | Fri Aug 07 00:00:00 IDT 2015 |  | COMPLETED
2292 | TT_TASK | Demobilization of TBM facilities and noise enclosure | Tue Aug 04 08:00:00 IDT 2015 | Sat Aug 29 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Mon Oct 19 18:00:00 IDT 2015 |  | COMPLETED
2293 | TT_TASK | Dis-assemble TBM | Tue Aug 04 08:00:00 IDT 2015 | Thu Sep 03 18:00:00 IDT 2015 | Mon Aug 10 08:00:00 IDT 2015 | Thu Sep 24 18:00:00 IDT 2015 |  | COMPLETED
2294 | TT_TASK | Invert slab and side walkway | Wed Sep 09 08:00:00 IDT 2015 | Sat Oct 24 18:00:00 IDT 2015 | Wed Sep 09 08:00:00 IDT 2015 | Tue Nov 10 18:00:00 IST 2015 |  | COMPLETED
2295 | TT_TASK | Installation of cable bracket | Thu Sep 24 08:00:00 IDT 2015 | Fri Oct 09 18:00:00 IDT 2015 | Thu Jul 02 08:00:00 IDT 2015 | Mon Aug 31 18:00:00 IDT 2015 |  | COMPLETED
2298 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Partial length) at down track | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 16 18:00:00 IDT 2014 | Fri Aug 01 08:00:00 IDT 2014 | Sat Aug 09 18:00:00 IDT 2014 |  | COMPLETED
2299 | TT_TASK | Probe/Grout | Mon Aug 18 08:00:00 IDT 2014 | Wed Aug 27 18:00:00 IDT 2014 | Mon Aug 11 08:00:00 IDT 2014 | Fri Aug 15 18:00:00 IDT 2014 |  | COMPLETED
2300 | TT_TASK | Coring of Segment | Thu Aug 28 08:00:00 IDT 2014 | Mon Sep 01 18:00:00 IDT 2014 | Sat Aug 16 08:00:00 IDT 2014 | Wed Aug 20 18:00:00 IDT 2014 |  | COMPLETED
2301 | TT_TASK | Removal of segment | Tue Sep 02 08:00:00 IDT 2014 | Thu Sep 04 18:00:00 IDT 2014 | Thu Aug 21 08:00:00 IDT 2014 | Sat Aug 23 18:00:00 IDT 2014 |  | COMPLETED
2302 | TT_TASK | Excavation 0-4mts with Shotcrete | Fri Sep 05 08:00:00 IDT 2014 | Tue Oct 07 18:00:00 IDT 2014 | Mon Aug 25 08:00:00 IDT 2014 | Fri Oct 03 18:00:00 IDT 2014 |  | COMPLETED
2303 | TT_TASK | Invert Concrete | Thu Oct 23 08:00:00 IDT 2014 | Sat Nov 01 18:00:00 IST 2014 | Sat Oct 04 08:00:00 IDT 2014 | Sat Oct 11 18:00:00 IDT 2014 |  | COMPLETED
2304 | TT_TASK | Wall and Roof concrete | Mon Nov 03 08:00:00 IST 2014 | Tue Nov 18 18:00:00 IST 2014 | Mon Oct 13 08:00:00 IDT 2014 | Fri Oct 31 18:00:00 IST 2014 |  | COMPLETED
2305 | TT_TASK | Dismantle Temporary frame | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 | Sat Nov 01 08:00:00 IST 2014 | Sat Nov 08 18:00:00 IST 2014 |  | COMPLETED
2306 | TT_TASK | Install Door to Cross Passage (By contract 827) | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 | Mon Nov 10 08:00:00 IST 2014 | Thu Nov 13 18:00:00 IST 2014 |  | COMPLETED
2307 | TT_TASK | Install and Erect Temporary support inside Main Tunnel for Cross Passage Tunnel CP32 (Remaining length ) at down track | Sat May 09 08:00:00 IDT 2015 | Thu May 28 18:00:00 IDT 2015 | Wed Apr 01 08:00:00 IDT 2015 | Thu Apr 16 18:00:00 IDT 2015 |  | COMPLETED
2308 | TT_TASK | Probe/Grout | Fri May 29 08:00:00 IDT 2015 | Fri May 29 18:00:00 IDT 2015 | Mon Apr 20 08:00:00 IDT 2015 | Mon Jun 29 18:00:00 IDT 2015 |  | COMPLETED
2309 | TT_TASK | Coring of Segment | Fri Oct 02 08:00:00 IDT 2015 | Tue Oct 06 18:00:00 IDT 2015 | Fri Oct 16 08:00:00 IDT 2015 | Tue Oct 20 18:00:00 IDT 2015 |  | COMPLETED