## Sheet1
ID | d0 | Label | TaskType | PlannedStart | PlannedEnd | ActualStart | ActualEnd | Float | Status | source_file | Constraint | ConstraintDate
A3920 | black | ENVIRONMENTAL PERMIT ISSUED | TT_Mile | 28/06/2021 | 28/06/2021 | 14/06/2016 | 14/06/2016 | 0 | TK_Complete | CCGTD1_IPS
A3930 | black | PNTP TO OEM (START ENGINEERING) | TT_Mile | 28/06/2021 | 28/06/2021 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete | CCGTD1_IPS
A3940 | black | PNTP TO ADVANCED WORKS CONTRACTOR FOR TRIAL PILES | TT_Mile | 28/06/2021 | 28/06/2021 | 07/11/2016 | 07/11/2016 | 0 | TK_Complete | CCGTD1_IPS
A3950 | black | HONG KONG GOVERNMENT APPROVAL / NTP | TT_Mile | 28/06/2021 | 28/06/2021 | 13/12/2016 | 13/12/2016 | 0 | TK_Complete | CCGTD1_IPS
A3960 | black | ADVANCED WORKS CONTRACT AWARD | TT_Mile | 28/06/2021 | 28/06/2021 | 15/12/2016 | 15/12/2016 | 0 | TK_Complete | CCGTD1_IPS
A3970 | black | OEM CONTRACT AWARD / BOP CONTRACT AWARD | TT_Mile | 28/06/2021 | 28/06/2021 | 19/12/2016 | 19/12/2016 | 0 | TK_Complete | CCGTD1_IPS
A3980 | black | MAIN CIVIL WORKS CONTRACT AWARD | TT_Mile | 28/06/2021 | 28/06/2021 | 29/05/2017 | 29/05/2017 | 0 | TK_Complete | CCGTD1_IPS
A3990 | black | SITE ESTABLISHMENT CONTRACT AWARD | TT_Mile | 28/06/2021 | 28/06/2021 | 05/06/2017 | 05/06/2017 | 0 | TK_Complete | CCGTD1_IPS
A4000 | black | E&amp;M INSTALLATION CONTRACT AWARD | TT_Mile | 28/06/2021 | 28/06/2021 | 22/09/2017 | 22/09/2017 | 0 | TK_Complete | CCGTD1_IPS
A4130 | black | START OF MAIN CIVIL WORKS ON SITE | TT_Mile | 01/06/2021 | 01/06/2021 | 19/06/2017 | 19/06/2017 | 0 | TK_Complete | CCGTD1_IPS
A4140 | black | START OF E&amp;M WORKS ON SITE | TT_Mile | 01/06/2021 | 01/06/2021 | 19/02/2018 | 19/02/2018 | 0 | TK_Complete | CCGTD1_IPS
A4150 | black | START OF COLD COMMISSIONING | TT_Mile | 01/06/2021 | 01/06/2021 | 29/07/2019 | 29/07/2019 | 0 | TK_Complete | CCGTD1_IPS
A4160 | black | Back Energisation | TT_Mile | 01/06/2021 | 01/06/2021 | 01/12/2019 | 01/12/2019 | 0 | TK_Complete | CCGTD1_IPS
A4170 | black | START CHEMICAL CLEANING | TT_Mile | 01/06/2021 | 01/06/2021 | 14/12/2019 | 14/12/2019 | 0 | TK_Complete | CCGTD1_IPS
A4180 | black | FIRST FIRE | TT_Mile | 01/06/2021 | 01/06/2021 | 24/01/2020 | 24/01/2020 | 0 | TK_Complete | CCGTD1_IPS
A4190 | black | START HOT COMMISSIONING (PART 1 - GAS) | TT_Mile | 01/06/2021 | 01/06/2021 | 24/01/2020 | 24/01/2020 | 0 | TK_Complete | CCGTD1_IPS
A4200 | black | STEAM BLOW | TT_Mile | 01/06/2021 | 01/06/2021 | 28/01/2020 | 28/01/2020 | 0 | TK_Complete | CCGTD1_IPS
A4210 | black | UNIT UNDER OPERATIONAL CONTROL | TT_Mile | 01/06/2021 | 01/06/2021 | 28/09/2020 | 28/09/2020 | 0 | TK_Complete | CCGTD1_IPS
A4220 | black | PART 1 COMMISSIONING CLEARANCE CERTIFICATE (CCC) ISSUED: UNIT UNDER OPERATION) | TT_Mile | 01/06/2021 | 01/06/2021 | 28/09/2020 | 28/09/2020 | 0 | TK_Complete | CCGTD1_IPS
A4230 | black | D1 OP PERMIT | TT_Mile | 01/06/2021 | 01/06/2021 | 29/09/2020 | 29/09/2020 | 0 | TK_Complete | CCGTD1_IPS
A4240 | black | START OF TB2 OUTAGE RECTIFICATION WORKS (SIEMENS) | TT_Mile | 01/06/2021 | 01/06/2021 | 22/02/2021 | 22/02/2021 | 0 | TK_Complete | CCGTD1_IPS
A4250 | black | START HOT COMMISSIONING (PART 2 - OIL) | TT_Mile | 01/06/2021 | 01/06/2021 | 23/03/2021 | 23/03/2021 | 0 | TK_Complete | CCGTD1_IPS
A4260 | blue | COMPLETION OF ALL COMMISSIONING WORKS &amp; HANDOVER to OPERATIONS | TT_FinMile | 01/06/2021 | 01/06/2021 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete | CCGTD1_IPS
S1030 | blue | Turbine Hall Over Head Crane Ready | TT_FinMile | 01/06/2021 | 01/06/2021 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete | CCGTD1_IPS
S1070 | black | Start first Hydro Test | TT_Mile | 01/06/2021 | 01/06/2021 | 13/05/2019 | 13/05/2019 | 0 | TK_Complete | CCGTD1_IPS
S1080 | black | Start Chemical Clean | TT_Mile | 01/06/2021 | 01/06/2021 | 14/12/2019 | 14/12/2019 | 0 | TK_Complete | CCGTD1_IPS
S1095 | black | 400KV Commencement | TT_Mile | 01/06/2021 | 01/06/2021 | 17/07/2017 | 17/07/2017 | 0 | TK_Complete | CCGTD1_IPS
S1110 | blue | Back Energisation | TT_FinMile | 01/06/2021 | 01/06/2021 | 01/12/2019 | 01/12/2019 | 0 | TK_Complete | CCGTD1_IPS
S1130 | black | First Fire | TT_Mile | 02/06/2021 | 02/06/2021 | 24/01/2020 | 24/01/2020 | 0 | TK_Complete | CCGTD1_IPS
A3400 | blue | CP 1 Conceptual Study | TT_FinMile | 09/09/2020 | 09/09/2020 | 14/11/2014 | 14/11/2014 | 0 | TK_Complete | CCGTD1_IPS
A3410 | blue | Advance Notice Guide | TT_FinMile | 09/09/2020 | 09/09/2020 | 01/04/2015 | 01/04/2015 | 0 | TK_Complete | CCGTD1_IPS
A3420 | blue | CP2 Project Basis | TT_FinMile | 09/09/2020 | 09/09/2020 | 21/07/2016 | 21/07/2016 | 0 | TK_Complete | CCGTD1_IPS
A3430 | blue | CP3 Project Strategy | TT_FinMile | 09/09/2020 | 09/09/2020 | 21/07/2016 | 21/07/2016 | 0 | TK_Complete | CCGTD1_IPS
A3440 | blue | Final Investment Decision Guide | TT_FinMile | 09/09/2020 | 09/09/2020 | 27/07/2016 | 27/07/2016 | 0 | TK_Complete | CCGTD1_IPS
A3450 | blue | CP4 Design | TT_FinMile | 09/09/2020 | 09/09/2020 | 26/09/2016 | 26/09/2016 | 0 | TK_Complete | CCGTD1_IPS
A3460 | blue | Construction | TT_FinMile | 09/09/2020 | 09/09/2020 | 26/09/2016 | 26/09/2016 | 0 | TK_Complete | CCGTD1_IPS
A3470 | blue | CP Commissioning &amp; Start Up | TT_FinMile | 09/09/2020 | 09/09/2020 | 21/01/2020 | 21/01/2020 | 0 | TK_Complete | CCGTD1_IPS
A3480 | blue | Project Acceptance Gate | TT_FinMile | 09/09/2020 | 09/09/2020 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete | CCGTD1_IPS
A4010 | black | Access to Site | TT_Mile | 28/06/2021 | 28/06/2021 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete | CCGTD1_IPS
A4020 | black | Pile Characteristics and Pile Load capacity supplien to OEM | TT_Mile | 28/06/2021 | 28/06/2021 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete | CCGTD1_IPS
A4030 | black | Raw Water Available | TT_Mile | 28/06/2021 | 28/06/2021 | 26/07/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
A4040 | black | Demineralized water available (For Construction) | TT_Mile | 28/06/2021 | 28/06/2021 | 19/05/2019 | 19/05/2019 | 0 | TK_Complete | CCGTD1_IPS
A4050 | black | HV Grid Available | TT_Mile | 29/06/2021 | 29/06/2021 | 08/01/2020 | 08/01/2020 | 0 | TK_Complete | CCGTD1_IPS
A4060 | blue | MV Available (Back Energizing) | TT_FinMile | 01/06/2021 | 01/06/2021 | 01/12/2019 | 01/12/2019 | 0 | TK_Complete | CCGTD1_IPS
A4070 | black | Fuel Gas Required | TT_Mile | 29/06/2021 | 29/06/2021 | 08/01/2020 | 08/01/2020 | 0 | TK_Complete | CCGTD1_IPS
A4080 | black | Fuel Oil Required | TT_Mile | 28/06/2021 | 28/06/2021 | 17/06/2020 | 17/06/2020 | 0 | TK_Complete | CCGTD1_IPS
SS.3170 | red | Prepare Drainage Diversion Submission | TT_Task | 31/03/2016 | 27/04/2016 | 31/03/2016 | 23/04/2016 | 0 | TK_Complete | CCGTD1_IPS
SS.3140 | red | Drainage Diversion 1st Submission | TT_Task | 01/06/2016 | 17/08/2016 | 26/05/2016 | 20/07/2016 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 01/06/2016
SS.3200 | red | Drainage Diversion GBP | TT_Task | 15/09/2016 | 05/12/2016 | 15/09/2016 | 11/11/2016 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 15/09/2016
SS.3210 | red | Drainage Diversion - Consent | TT_Task | 01/12/2016 | 09/01/2017 | 01/12/2016 | 28/12/2016 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 01/12/2016
SS.3320 | red | Drainage Diversion Resubmission (Structural) | TT_Task | 15/09/2016 | 17/11/2016 | 15/09/2016 | 09/11/2016 | 0 | TK_Complete | CCGTD1_IPS
SS.3340 | red | Drainage Diversion Resubmission (Drainage Plans) | TT_Task | 15/09/2016 | 17/11/2016 | 15/09/2016 | 09/11/2016 | 0 | TK_Complete | CCGTD1_IPS
SS.3400 | red | Drainage Diversion 1st Amendment (Structural) | TT_Task | 19/05/2017 | 19/06/2017 | 19/05/2017 | 14/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SS.3420 | red | Drainage Diversion ELS 1st Submission | TT_Task | 18/01/2017 | 23/03/2017 | 18/01/2017 | 16/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SS.3430 | red | Drainage Diversion ELS 1st Amendment | TT_Task | 21/04/2017 | 23/05/2017 | 21/04/2017 | 19/05/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_LATER_THAN | 21/04/2017
SS.3180 | red | Prepare warehouse demolition and A&amp;A works | TT_Task | 29/07/2015 | 03/11/2015 | 29/07/2015 | 02/11/2015 | 0 | TK_Complete | CCGTD1_IPS
SS.3190 | red | Prepare warehouse demolition and A&amp;A works amendment | TT_Task | 04/07/2016 | 05/09/2016 | 02/07/2016 | 24/08/2016 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 01/07/2016
SS.3000 | red | Warehouse demolition and A&amp;A works (GBP &amp; Structural) - 1st Submission | TT_Task | 03/11/2015 | 05/01/2016 | 03/11/2015 | 28/12/2015 | 0 | TK_Complete | CCGTD1_IPS
SS.3060 | red | Warehouse demolition and A&amp;A works (GBP) - Amendment Submission | TT_Task | 01/09/2016 | 12/10/2016 | 25/08/2016 | 04/10/2016 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 01/09/2016
SS.3061 | red | Warehouse demolition and A&amp;A works (Structural)- Amendment Submission | TT_Task | 01/09/2016 | 12/10/2016 | 05/04/2017 | 28/04/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 01/09/2016
SS.3070 | red | Warehouse demolition and A&amp;A works - Consent | TT_Task | 26/09/2016 | 03/11/2016 | 20/10/2016 | 21/11/2016 | 0 | TK_Complete | CCGTD1_IPS
SS.3220 | red | Prepare Power Island Piling Submission | TT_Task | 01/12/2015 | 19/02/2016 | 01/12/2015 | 28/01/2016 | 0 | TK_Complete | CCGTD1_IPS
SS.3010 | red | Power Island Piling - 1st Submission | TT_Task | 01/02/2016 | 18/04/2016 | 29/01/2016 | 24/03/2016 | 0 | TK_Complete | CCGTD1_IPS
SS.3050 | red | Power Island Piling - Amendment | TT_Task | 09/08/2016 | 21/09/2016 | 09/08/2016 | 09/09/2016 | 0 | TK_Complete | CCGTD1_IPS
SS.3080 | red | Power Island Piling - Consent | TT_Task | 12/09/2016 | 11/11/2016 | 09/09/2016 | 25/10/2016 | 0 | TK_Complete | CCGTD1_IPS
SS.3110 | red | BA14 submission &amp; pile test | TT_Task | 25/05/2017 | 03/07/2017 | 25/05/2017 | 21/06/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 25/05/2017
SS.3120 | red | Piling 1st Submission | TT_Task | 29/01/2016 | 28/03/2016 | 29/01/2016 | 24/03/2016 | 0 | TK_Complete | CCGTD1_IPS
SS.3130 | red | Piling 1st Amendment | TT_Task | 09/08/2016 | 15/09/2016 | 09/08/2016 | 09/09/2016 | 0 | TK_Complete | CCGTD1_IPS
SS.3230 | red | Piling 2nd Amendment | TT_Task | 07/11/2016 | 07/12/2016 | 07/11/2016 | 02/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SS.3250 | red | Piling 3rd Amendment | TT_Task | 21/02/2017 | 24/03/2017 | 21/02/2017 | 21/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SS.3270 | red | Piling 4th Amendment | TT_Task | 21/03/2017 | 14/04/2017 | 21/03/2017 | 12/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SS.3300 | red | Piling 5th Amendment | TT_Task | 02/05/2017 | 22/05/2017 | 02/05/2017 | 19/05/2017 | 0 | TK_Complete | CCGTD1_IPS
CS.1060 | red | Warehouse Demolition works | TT_Task | 01/06/2021 | 05/07/2021 | 16/12/2016 | 17/01/2017 | 0 | TK_Complete | CCGTD1_IPS
CS.1070 | red | Warehouse A&amp;A Works, ready for main contract fitout (150 Days - 14/5/2017) | TT_Task | 01/06/2021 | 09/09/2021 | 18/01/2017 | 21/04/2017 | 0 | TK_Complete | CCGTD1_IPS
A4090 | red | Turbine Hall (Driven Piles) | TT_Task | 01/06/2021 | 14/10/2021 | 20/12/2016 | 04/05/2017 | 0 | TK_Complete | CCGTD1_IPS
A4095 | red | Site Drainage A&amp;A works &amp; Site Demob | TT_Task | 01/06/2021 | 07/06/2021 | 20/12/2016 | 30/09/2017 | 0 | TK_Complete | CCGTD1_IPS
A4100 | red | Turbine Hall (Pre-Bore Socket H-Piles) | TT_Task | 01/06/2021 | 12/07/2021 | 20/12/2016 | 06/05/2017 | 0 | TK_Complete | CCGTD1_IPS
A4110 | red | HRSG (Driven H-Piles) | TT_Task | 01/06/2021 | 09/07/2021 | 20/12/2016 | 04/05/2017 | 0 | TK_Complete | CCGTD1_IPS
A4120 | red | Post Drilling / BD Selection / Load Tests / BD Consent for Pile Cap | TT_Task | 01/06/2021 | 23/07/2021 | 09/05/2017 | 30/06/2017 | 0 | TK_Complete | CCGTD1_IPS
CS.1075 | red | Construct Trials &amp; Test for BD inspection and acknowledgement | TT_Task | 01/06/2021 | 18/06/2021 | 08/11/2016 | 23/11/2016 | 0 | TK_Complete | CCGTD1_IPS
A3490 | red | Bulk excavation | TT_Task | 01/06/2021 | 05/07/2021 | 14/06/2017 | 19/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI----2-005 | black | PRE-NOTICE TO PROCEED (PNTP) | TT_Mile | 03/11/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 03/11/2016
SI----2-007 | black | NOTICE TO PROCEED (NTP) | TT_Mile | 14/01/2017 | 14/01/2017 | 19/12/2016 | 19/12/2016 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 19/12/2016
SI----2C00 | black | START ENGINEERING | TT_Mile | 26/11/2016 | 26/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete | CCGTD1_IPS
SI----2D00 | black | START PRODUCTS (GT, ST, GENERATOR, CONDENSER) | TT_Mile | 03/11/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-3412-32 | black | GENERAL LAYOUT ACCEPTED FROM CLIENT (AS BASIS OF CONTRACT SIGNING) | TT_Mile | 03/11/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-U--5-015 | black | PILE CHARACTERISTICS AND PILE LOAD CAPACITY RELEASED BY CLP | TT_Mile | 03/11/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1---2-00 | black | COMMENCEMENT OF AGREEMENT FOR ADVANCED ENGINEERING CONTRACT DATED 26-APR-2016 | TT_Mile | 11/08/2019 | 11/08/2019 | 16/04/2016 | 16/04/2016 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 19/05/2016
SI1---2-05 | blue | (1a) COMPLETION AND SUBMISSION OF DATA FOR BD SUBMISSION | TT_FinMile | 11/08/2019 | 11/08/2019 | 18/06/2016 | 18/06/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1---2-10 | blue | (1b) COMPLETION AND SUBMISSION OF ALL OTHER DATA IN ATTACHMENT 1B | TT_FinMile | 11/08/2019 | 11/08/2019 | 18/06/2016 | 18/06/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1---2-15 | blue | (2) COMPLETION AND SUBMISSION OF ALL ENGINEERING FOR HRSG FOR BD SUBMISSION | TT_FinMile | 31/01/2017 | 31/01/2017 | 28/01/2017 | 28/01/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1---2-20 | blue | (5a) COMPLETION OF INSURANCE CERTIFICATE / NOMINATION OF TFA ETC. | TT_FinMile | 31/05/2017 | 31/05/2017 | 03/05/2017 | 03/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1---2-25 | blue | (5b) COMPLETION OF MOBILIZATION OF TFA FOR CIVIL WORKS | TT_FinMile | 25/11/2017 | 25/11/2017 | 30/10/2017 | 30/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1---2-30 | blue | (6a) COMPLETION OF NOMINATION OF TFA / COMMISSIONING PROCEDURE AND ETC. | TT_FinMile | 11/08/2018 | 11/08/2018 | 11/08/2018 | 11/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1---2-35 | blue | (6b) COMPLETION AND SIGN OFF OF ALL CHECK SHEET TO ALLOW 1ST FIRE | TT_FinMile | 16/03/2019 | 16/03/2019 | 23/01/2020 | 23/01/2020 | 0 | TK_Complete | CCGTD1_IPS
SI1---3-00 | blue | (3a) DELIVERY (ON-SITE) OF CAST-IN-PLACE EMBEDS FOR TURBINE TABLE AND TURBINE HALL | TT_FinMile | 25/08/2017 | 25/08/2017 | 20/07/2017 | 20/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1---3-05 | blue | (3b) DELIVERY (ON-SITE) OF CAST-IN-PLACE EMBEDS FOR HRSG AND STACK | TT_FinMile | 25/09/2017 | 25/09/2017 | 28/08/2017 | 28/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1---3-10 | blue | (3c) DELIVERY (ON-SITE) OF CAST-IN-PLACE EMBEDS FOR REMAINING PLANT | TT_FinMile | 26/02/2018 | 26/02/2018 | 26/01/2018 | 26/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1---3-15 | blue | (4a) DELIVERY (ON-SITE) OF UMC CRANE / PRELIMINARY O&amp;M MANUAL AND HRSG STEEL / CASING | TT_FinMile | 26/02/2018 | 26/02/2018 | 01/01/2018 | 01/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1---3-20 | blue | (4b1) DELIVERY (ON-SITE) OF STEAM TURBINE AND GENERATOR | TT_FinMile | 01/04/2018 | 01/04/2018 | 01/04/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1---3-25 | blue | (4c) DELIVERY (ON-SITE) OF GAS TURBINE AND CONDENSER | TT_FinMile | 01/04/2018 | 01/04/2018 | 01/04/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1---3-30 | blue | (4d) DELIVERY (ON-SITE) OF HRSG PIPING AND BALANCE OF HRSG EQUIPMENT | TT_FinMile | 30/07/2018 | 30/07/2018 | 18/08/2018 | 18/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1---3-35 | blue | (4e) DELIVERY (ON-SITE) OF BALANCE OF ALL SIEMENS SUPPLIED EQUIPMENT | TT_FinMile | 01/12/2018 | 01/12/2018 | 01/12/2018 | 01/12/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1---3-37 | blue | (4b2) DELIVERY (ON-SITE) OF HRSG MODULES / DRUMS | TT_FinMile | 21/04/2018 | 21/04/2018 | 08/04/2018 | 08/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1---3-39 | blue | (BOP2) FUEL GAS SUPPLY PIPEWORK SYSTEM | TT_FinMile | 08/06/2018 | 08/06/2018 | 08/06/2018 | 08/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1---3-43 | blue | (BOP3) 6.6kV CONNECTION &amp; HYDROGEN / CO2 / SUPPLY PIPEWORK &amp; FUEL OIL FORWARDING SYSTEM | TT_FinMile | 05/08/2018 | 05/08/2018 | 05/08/2018 | 05/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1---3-47 | blue | (BOP1) FIRE FIGHTING CONNECTION PIPEWORK SYSTEM | TT_FinMile | 26/03/2018 | 26/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1---3-49 | blue | (BOP4) DELIVERY OF ALL BALANCE EQUIPMENT FOR CONNECTION WORKS | TT_FinMile | 09/09/2018 | 09/09/2018 | 25/10/2018 | 25/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1---3-51 | blue | (BOP5) COMPLETION AND SIGN OFF OF ALL CHECK SHEET TO ALLOW 1ST FIRE | TT_FinMile | 16/03/2019 | 16/03/2019 | 23/01/2020 | 23/01/2020 | 0 | TK_Complete | CCGTD1_IPS
SI-HA-2-85&amp; | black | PARTIAL ORDER PLACED HRSG | TT_Mile | 03/11/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-HA-2-87&amp; | black | ORDER PLACED HRSG | TT_Mile | 14/01/2017 | 14/01/2017 | 19/12/2016 | 19/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-1102-15 | blue | PRELIMINARY OPERATING AND MAINTENANCE DOCUMENTATION (O&amp;M) | TT_FinMile | 07/12/2018 | 07/12/2018 | 07/12/2018 | 07/12/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-3512-40 | blue | STEAM BLOWING INSTRUCTION | TT_FinMile | 09/02/2019 | 09/02/2019 | 31/10/2019 | 31/10/2019 | 0 | TK_Complete | CCGTD1_IPS
SI-3512E40 | blue | COMMISSIONING MANUAL (TC) ON SITE/ CLIENT | TT_FinMile | 28/10/2018 | 28/10/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-MAV2-01 | blue | CLEANING INSTRUCTION TURBOSET LUBE AND LIFTING OIL SYSTEM | TT_FinMile | 06/09/2018 | 06/09/2018 | 06/09/2018 | 06/09/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 06/09/2018
SI-M--2C20 | blue | LAYOUT DOCUMENTS [external interfaces final] | TT_FinMile | 01/04/2017 | 01/04/2017 | 31/03/2017 | 31/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-MB-2-20 | blue | LAYOUT DOCUMENTS AIR INTAKE, EXHAUST GAS SYSTEM [external interfaces final] | TT_FinMile | 31/03/2017 | 31/03/2017 | 31/03/2017 | 31/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-M--2D20 | blue | SYSTEM DOCUMENTS [external interfaces final] | TT_FinMile | 31/03/2017 | 31/03/2017 | 31/03/2017 | 31/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-3412-50 | red | SEISMIC REPORT | TT_Task | 09/07/2016 | 04/08/2016 | 09/07/2016 | 05/08/2016 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 11/08/2016
SI-3022-39 | red | GENERAL DESIGN CRITERIA (SIEMENS SCOPE ONLY) | TT_Task | 03/11/2016 | 14/12/2016 | 03/11/2016 | 14/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-SG-2-26 | blue | DESIGN REVIEW - EXPLOSION PROTECTION (ATEX / IEC60079) | TT_FinMile | 31/03/2017 | 31/03/2017 | 20/03/2017 | 20/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-SG-2-35 | red | PREPARATION FINAL FIRE- / EXPLOSION PROT. CONCEPT AND ESCAPE ROUTE/FIRE PROTECTION DWGs | TT_Task | 14/02/2017 | 13/03/2017 | 01/02/2017 | 08/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-SG-2-50 | blue | FINAL ESCAPE ROUTE AND FIRE PROTECTION DWGS AVAILABLE | TT_FinMile | 18/03/2017 | 18/03/2017 | 08/03/2017 | 08/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-3412-40 | red | NOISE PROTECTION CONCEPT | TT_Task | 01/10/2016 | 05/04/2017 | 11/06/2016 | 26/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-U--2B10 | black | RFQ STEEL WORKS (excl.EMBEDDED PARTS) | TT_Mile | 14/02/2017 | 14/02/2017 | 18/01/2017 | 18/01/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-U--2B85 | black | ORDER PLACED STEEL WORKS (excl.EMBEDDED PARTS) | TT_Mile | 18/05/2017 | 18/05/2017 | 24/04/2017 | 24/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-U--2B87 | red | QUOTATION STAGE STEEL WORKS (excl.EMBEDDED PARTS) | TT_Task | 14/02/2017 | 12/04/2017 | 18/01/2017 | 23/04/2017 | 0 | TK_Complete | CCGTD1_IPS
CP-3412-35 | red | REVIEW BY CLIENT FOR CONCEPT DESIGN DOCUMENTS | TT_Task | 01/03/2017 | 21/03/2017 | 28/02/2017 | 20/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-3412-07 | blue | PRELIMINARY EXTERNAL WORKS DESIGN AVAILABLE | TT_FinMile | 28/10/2016 | 28/10/2016 | 16/09/2016 | 16/09/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-3412A00 | red | CONCEPT DESIGN (part I) PLOT PLAN | TT_Task | 01/10/2016 | 27/10/2016 | 20/08/2016 | 16/09/2016 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 22/09/2016
SI-3412D30 | blue | FINAL HYDRAULIC DESIGN AVAILABLE | TT_FinMile | 30/04/2017 | 30/04/2017 | 28/04/2017 | 28/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-3022-05 | blue | GENERAL DESIGN CRITERIA FOR STRUCTURAL ENGINEERING FINALISED FOR HRSG ORDER (Phase 1) | TT_FinMile | 01/10/2016 | 01/10/2016 | 05/08/2016 | 05/08/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-3412-09 | blue | FINAL AND COMPLETE ROOM NUMBERS ASSIGNED TO EQUIPMENT | TT_FinMile | 25/07/2017 | 25/07/2017 | 25/06/2017 | 25/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-3412-11 | blue | LIST OF ALL ROOM NUMBERS AVAILABLE | TT_FinMile | 23/03/2017 | 23/03/2017 | 08/03/2017 | 08/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-3412-20 | blue | (C) BASIC DESIGN PLANT LAYOUT DWGS AVAILABLE FOR UMC BUILDING | TT_FinMile | 21/02/2017 | 21/02/2017 | 16/01/2017 | 16/01/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-3412A15 | red | BASIC DESIGN PLANT LAYOUT | TT_Task | 19/01/2017 | 11/03/2017 | 15/12/2016 | 08/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI---P2J75 | red | PREPARATION RFQ PREFAB. MODULES | TT_Task | 26/11/2016 | 04/03/2017 | 03/11/2016 | 28/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI---P2J80 | red | QUOTATION STAGE PREFAB. MODULES | TT_Task | 16/03/2017 | 18/05/2017 | 01/03/2017 | 30/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI---P2J85 | black | ORDER PLACED PREFAB. MODULES | TT_Mile | 01/06/2017 | 01/06/2017 | 30/04/2017 | 30/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-GM-3B25 | red | DETAIL DESIGN, MANUFACTURING, SHOP TEST SUMP PUMP GM/UGU | TT_Task | 26/11/2017 | 25/04/2018 | 26/10/2017 | 05/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-GM-3B80 | blue | (RFS) READY FOR SHIPMENT SUMP PUMP GM/UGU | TT_FinMile | 15/06/2018 | 15/06/2018 | 12/10/2018 | 12/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-GM-4B25 | red | TRANSPORT SUMP PUMP GM/UGU | TT_Task | 16/06/2018 | 14/08/2018 | 21/11/2018 | 25/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-GM-4B27 | blue | (OTD-OS) ON SITE SUMP PUMP GM/UGU | TT_FinMile | 14/08/2018 | 14/08/2018 | 25/11/2018 | 25/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-SGA3A25 | red | DETAIL DESIGN, MANUFACTURING, SHOP TEST FIRE FIGHTING RING MAIN SGA | TT_Task | 30/08/2017 | 27/12/2017 | 18/08/2017 | 15/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-SGA3A80 | blue | (RFS) READY FOR SHIPMENT FIRE FIGHTING RING MAIN SGA | TT_FinMile | 29/05/2018 | 29/05/2018 | 20/11/2018 | 20/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-SGA4A40 | blue | (OTD-OS) ON SITE FIRE FIGHTING RING MAIN SGA | TT_FinMile | 24/07/2018 | 24/07/2018 | 29/11/2018 | 29/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-SGA4A42 | red | TRANSPORT FIRE FIGHTING RING MAIN SGA | TT_Task | 30/05/2018 | 24/07/2018 | 21/11/2018 | 29/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-3062-17 | blue | FINAL EL.SPECS. (BLACK BOXES, MOTORS) | TT_FinMile | 13/01/2017 | 13/01/2017 | 14/12/2016 | 14/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-B--2A50 | blue | (ELV2) PRELIMINARY EL. LOAD DATA FOR LV | TT_FinMile | 28/02/2017 | 28/02/2017 | 17/02/2017 | 17/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-B--2A55 | blue | (ELV3) FINAL EL. LOAD DATA FOR LV | TT_FinMile | 25/06/2017 | 25/06/2017 | 12/06/2017 | 12/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-BF-2-55 | blue | LV- SWITCHGEAR DATA FINAL | TT_FinMile | 27/10/2017 | 27/10/2017 | 27/09/2017 | 27/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SP-B--2-56 | black | CONSUMER LIST (VEL) COMPLETED (FINAL) | TT_Mile | 01/04/2017 | 01/04/2017 | 23/03/2017 | 23/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SP-B--2-58 | black | E-CONSUMER LIST WITH MOUNTING LOCATION GT TO GT I&amp;C (VEL) | TT_Mile | 25/07/2017 | 25/07/2017 | 11/07/2017 | 11/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-B--2-13 | red | PREPARATION OF LENGTH MATRIX | TT_Task | 11/04/2017 | 24/04/2017 | 28/03/2017 | 10/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-B--2-14 | blue | 1ST. ROOM TO ROOM MATRIX | TT_FinMile | 10/04/2017 | 10/04/2017 | 27/03/2017 | 27/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-B--2-15 | red | DESIGN POWER / CONTROL CABLES | TT_Task | 11/05/2017 | 27/10/2017 | 11/04/2017 | 27/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-B--2-19 | blue | 1ST. LENGTH MATRIX AVAILABLE | TT_FinMile | 10/05/2017 | 10/05/2017 | 10/04/2017 | 10/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-B--2-30 | red | DETAIL DESIGN CABLE ROUTING | TT_Task | 26/06/2017 | 03/01/2018 | 13/06/2017 | 21/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-B--2-54 | blue | BINDING ELECTRICAL AND I&amp;C CABLE LIST DATA AVAILABLE | TT_FinMile | 16/12/2017 | 16/12/2017 | 27/11/2017 | 27/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-B--4-54 | blue | CABLE PULLING DATA TRANSFER TO SITE | TT_FinMile | 30/04/2018 | 30/04/2018 | 29/06/2018 | 29/06/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 30/04/2018
SI-BZK3-25 | red | MANUFACTURING, SHOP TEST MV/LV CABLES BZK (1ST SET 30%) | TT_Task | 26/08/2017 | 09/02/2018 | 25/08/2017 | 06/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZK3-80 | blue | (RFS) READY FOR SHIPMENT MV/LV CABLES BZK (1ST SET 30%) | TT_FinMile | 28/03/2018 | 28/03/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZK3-90 | red | MANUFACTURING, SHOP TEST MV/LV CABLES BZK (2ND SET 80%) | TT_Task | 29/03/2018 | 27/05/2018 | 15/05/2018 | 10/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZK3-92 | blue | (RFS) READY FOR SHIPMENT MV/LV CABLES BZK (2ND SET 80%) | TT_FinMile | 27/05/2018 | 27/05/2018 | 10/07/2018 | 10/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZK4-64 | red | TRANSPORT MV/LV CABLES BZK (1ST SET 30%) | TT_Task | 29/03/2018 | 27/04/2018 | 14/04/2018 | 24/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZK4-66 | red | TRANSPORT MV/LV CABLES BZK (2ND SET 80%) | TT_Task | 28/05/2018 | 15/07/2018 | 21/07/2018 | 26/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZP3-25 | red | MANUFACTURING, SHOP TEST FIRST CABLE SUPPORT SYSTEM BZP (FOR PRE-FAB MODULES) | TT_Task | 26/06/2017 | 18/08/2017 | 02/06/2017 | 01/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-BZP3-80 | blue | (RFS) READY FOR SHIPMENT CABLE SUPPORT SYSTEM BZP (FOR PRE-FAB MODULES) | TT_FinMile | 02/10/2017 | 02/10/2017 | 01/09/2017 | 01/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-BZP3-82 | red | MANUFACTURING, SHOP TEST CABLE SUPPORT SYSTEM BZP (MAIN) | TT_Task | 16/10/2017 | 10/12/2017 | 15/09/2017 | 08/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZP3-84 | blue | (RFS) READY FOR SHIPMENT FIRST CABLE SUPPORT SYSTEM BZP (MAIN) | TT_FinMile | 08/04/2018 | 08/04/2018 | 08/04/2018 | 08/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZP3B25 | red | MANUFACTURING, SHOP TEST CABLE SUPPORT SYSTEM BZP (BOP) | TT_Task | 26/11/2017 | 20/01/2018 | 17/11/2017 | 31/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZP3B80 | blue | (RFS) READY FOR SHIPMENT CABLE SUPPORT SYSTEM BZP (BOP) | TT_FinMile | 23/04/2018 | 23/04/2018 | 31/05/2018 | 31/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZP4-29 | red | TRANSPORT FIRST CABLE SUPPORT SYSTEM BZP (MAIN) | TT_Task | 09/04/2018 | 07/06/2018 | 09/04/2018 | 21/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZP4-31 | red | TRANSPORT FIRST CABLE SUPPORT SYSTEM BZP (FOR PRE-FAB MODULES) | TT_Task | 26/10/2017 | 12/12/2017 | 29/09/2017 | 29/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-BZP4B27 | red | TRANSPORT SECOND CABLE SUPPORT SYSTEM BZP (BOP) | TT_Task | 24/04/2018 | 22/06/2018 | 01/06/2018 | 20/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CYA3-25 | red | MANUFACTURING, SHOP TEST TELECOMMUNICATION CYA | TT_Task | 26/10/2017 | 09/02/2018 | 29/09/2017 | 25/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CYA3-80 | blue | (RFS) READY FOR SHIPMENT TELECOMMUNICATION CYA | TT_FinMile | 14/05/2018 | 14/05/2018 | 28/06/2018 | 28/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CYA4-27 | red | TRANSPORT TELECOMMUNICATION CYA | TT_Task | 15/05/2018 | 06/07/2018 | 29/06/2018 | 13/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CYP3-25 | red | MANUFACTURING, SHOP TEST SECURITY CYP | TT_Task | 26/10/2017 | 09/02/2018 | 29/09/2017 | 25/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CYP3-80 | blue | (RFS) READY FOR SHIPMENT SECURITY CYP | TT_FinMile | 14/05/2018 | 14/05/2018 | 28/06/2018 | 28/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CYP4-27 | red | TRANSPORT SECURITY CYP | TT_Task | 15/05/2018 | 06/07/2018 | 29/06/2018 | 13/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1C--4-27 | red | ST I&amp;C TRANSPORT TO SITE FIELD INSTRUMENTATION | TT_Task | 26/03/2018 | 24/05/2018 | 16/03/2018 | 13/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-HA-2-10 | red | ENGINEERING P&amp;IDs, SYSTEM DESCRIPTION HRSG-SYSTEMS | TT_Task | 14/01/2017 | 20/01/2017 | 10/12/2016 | 16/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-HA-2-11 | blue | P&amp;IDs, DATA SHEETS, LIFE TIME DESIGN CRITERIA FOR INQUIRY AND ORDERING HRSG AVAILABLE | TT_FinMile | 30/09/2016 | 30/09/2016 | 08/07/2016 | 08/07/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-HA-2-59 | red | DESIGN REVIEW INCL. SIL-STUDY HRSG-SYSTEMS | TT_Task | 21/01/2017 | 24/02/2017 | 17/12/2016 | 31/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-HA-2-65 | blue | (DF) PROCESS FINAL HRSG-SYSTEMS | TT_FinMile | 31/03/2017 | 31/03/2017 | 31/03/2017 | 31/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-HA-2-68&amp; | blue | DATA INPUT HRSG COMPLETED FOR I&amp;C DESIGN | TT_FinMile | 26/01/2018 | 26/01/2018 | 08/02/2017 | 08/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-HA-2-75 | red | PREPARING DOCUMENTS INQUIRY/ CONTRACT ODER FOR HRSG | TT_Task | 01/10/2016 | 10/11/2016 | 11/06/2016 | 22/07/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-HA-2-86 | red | SYSTEM MEETINGS WITH HRSG SUPPLIERS | TT_Task | 03/11/2016 | 15/12/2016 | 03/11/2016 | 15/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-L--2-05 | red | PREPARATION P&amp;IDs L- SYSTEMS (FIRST ISSUE) | TT_Task | 10/12/2016 | 21/01/2017 | 17/11/2016 | 28/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-L--2-10 | red | ENGINEERING P&amp;IDs, SYSTEM DESCRIPTION L- SYSTEMS | TT_Task | 03/02/2017 | 23/03/2017 | 29/12/2016 | 15/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-L--2-25 | red | DESIGN REVIEW INTERFACE ST / L- SYSTEMS | TT_Task | 14/01/2017 | 03/02/2017 | 13/01/2017 | 15/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-L--2-30 | red | REVISION P&amp;IDs AFTER 3D DRV L- SYSTEMS | TT_Task | 08/09/2017 | 05/10/2017 | 07/08/2017 | 09/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-L--2-35 | red | DESIGN DATA SHEETS L- COMPONENTS | TT_Task | 26/11/2016 | 11/03/2017 | 03/11/2016 | 16/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-L--2-45 | blue | DESIGN DATA SHEETS FOR ALL L- COMPONENTS AVAILABLE | TT_FinMile | 28/02/2017 | 28/02/2017 | 16/02/2017 | 16/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-L--2-50 | blue | (DF) MECHANICAL ENGINEERING, PLANT LAYOUT L- SYSTEMS | TT_FinMile | 10/10/2017 | 10/10/2017 | 09/09/2017 | 09/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-L--2-65 | blue | (DF) PROCESS FINAL L- SYSTEMS | TT_FinMile | 08/04/2017 | 08/04/2017 | 10/03/2017 | 10/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-L--2-70 | blue | (DF) I&amp;C DATA L- SYSTEMS | TT_FinMile | 08/10/2017 | 08/10/2017 | 07/09/2017 | 07/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-L--2-75 | red | DESIGN REVIEW INCL. SIL-STUDY L- SYSTEMS | TT_Task | 01/03/2017 | 04/04/2017 | 17/02/2017 | 10/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-L--2I45 | blue | DESIGN DATA SHEETS SAFETY, CONTROL VALVES L- SYSTEMS | TT_FinMile | 10/05/2017 | 10/05/2017 | 09/04/2017 | 09/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-P--2-05 | red | PREPARATION P&amp;IDs P-SYSTEMS (FIRST ISSUE) | TT_Task | 10/12/2016 | 21/01/2017 | 17/11/2016 | 29/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-P--2-10 | red | ENGINEERING P&amp;IDs, SYSTEM DESCRIPTION P-SYSTEMS | TT_Task | 14/01/2017 | 03/03/2017 | 30/12/2016 | 16/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-P--2-28 | red | SUMMARY DATA MANAGEMENT P-SYSTEMS | TT_Task | 01/04/2017 | 12/08/2017 | 11/03/2017 | 29/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-P--2-30 | red | REVISION P&amp;IDs AFTER 3D DRV P-SYSTEM | TT_Task | 26/09/2017 | 23/10/2017 | 05/09/2017 | 29/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-P--2-35 | red | DESIGN DATA SHEETS P-COMPONENTS | TT_Task | 26/11/2016 | 25/02/2017 | 03/11/2016 | 15/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-P--2-45 | blue | DESIGN DATA SHEETS FOR ALL P-COMPONENTS AVAILABLE | TT_FinMile | 28/02/2017 | 28/02/2017 | 15/02/2017 | 15/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-P--2-50 | blue | (DF) MECHANICAL ENGINEERING, PLANT LAYOUT P-SYSTEMS | TT_FinMile | 01/11/2017 | 01/11/2017 | 29/09/2017 | 29/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-P--2-65 | blue | (DF) PROCESS FINAL P-SYSTEMS | TT_FinMile | 08/04/2017 | 08/04/2017 | 10/03/2017 | 10/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-P--2-70 | blue | (DF) I&amp;C DATA P-SYSTEMS | TT_FinMile | 25/09/2017 | 25/09/2017 | 25/08/2017 | 25/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-P--2-75 | red | DESIGN REVIEW INCL. SIL-STUDY P-SYSTEMS | TT_Task | 01/03/2017 | 04/04/2017 | 17/02/2017 | 10/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-P--2I45 | blue | DESIGN DATA SHEETS SAFETY, CONTROL VALVES P-SYSTEMS | TT_FinMile | 28/02/2017 | 28/02/2017 | 15/02/2017 | 15/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-PAC2B45 | blue | DESIGN DATA SHEETS FOR CW PUMP PAC | TT_FinMile | 13/01/2017 | 13/01/2017 | 15/12/2016 | 15/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-G--2-05 | red | PREPARATION P&amp;IDs GA-/GHC/GM-/MBU20 - SYSTEMS (FIRST ISSUE) AND WATER BALANCE | TT_Task | 10/12/2016 | 21/01/2017 | 17/11/2016 | 26/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI-G--2-10 | red | ENGINEERING P&amp;IDs, SYSTEM DESCRIPTION G-/S-/MBU20 - SYSTEMS | TT_Task | 03/02/2017 | 20/04/2017 | 27/12/2016 | 13/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-G--2-30 | red | REVISION P&amp;IDs AFTER 3D DRV G-/S-/MBU20 | TT_Task | 27/10/2017 | 09/11/2017 | 27/09/2017 | 12/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-G--2-35 | red | DESIGN DATA SHEETS G-/MBU20 - COMPONENTS | TT_Task | 03/11/2016 | 09/02/2017 | 03/11/2016 | 09/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-G--2-50 | blue | (DF) MECHANICAL ENGINEERING, PLANT LAYOUT G-/S-/MBU20-SYSTEMS | TT_FinMile | 09/11/2017 | 09/11/2017 | 12/10/2017 | 12/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-G--2-65 | blue | (DF) PROCESS FINAL G-/S-/MBU20 -SYSTEM | TT_FinMile | 30/04/2017 | 30/04/2017 | 24/04/2017 | 24/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-G--2-70 | blue | (DF) I&amp;C DATA G/-S-/MBU20-SYSTEMS | TT_FinMile | 08/10/2017 | 08/10/2017 | 07/09/2017 | 07/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-G--2-75 | red | DESIGN REVIEW INCL. SIL-STUDY G-/S-/MBU20-SYSTEMS | TT_Task | 16/03/2017 | 26/04/2017 | 14/03/2017 | 24/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-G--2A05 | red | PREPARATION P&amp;IDs GHD/GKB/SCB - SYSTEMS (FIRST ISSUE) | TT_Task | 10/12/2016 | 18/02/2017 | 17/11/2016 | 09/01/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-G--2A45 | blue | DESIGN DATA SHEETS FOR ALL G-/MBU20 - COMPONENTS AVAILABLE | TT_FinMile | 14/02/2017 | 14/02/2017 | 09/02/2017 | 09/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-G--2B45 | blue | DESIGN DATA SHEETS SAFETY, CONTROL VALVES G-, MBU2-SYSTEMS | TT_FinMile | 14/02/2017 | 14/02/2017 | 09/02/2017 | 09/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-C--2-15 | red | BASIC DESIGN, SPECIFICATION BOP I&amp;C | TT_Task | 03/11/2016 | 18/01/2017 | 03/11/2016 | 18/01/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-C--2-50 | blue | (ICSY2) PRELIMINARY FUNCTION DESCRIPTIONS, LOGICS AND HMI GRAPHICS | TT_FinMile | 28/08/2017 | 28/08/2017 | 27/07/2017 | 27/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-C--2A40 | red | HW ENGINEERING BOP I&amp;C | TT_Task | 15/02/2017 | 26/09/2017 | 02/02/2017 | 13/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-C--2A70 | blue | (DF) BOP I&amp;C HW FOR FIELD EQUIPMENT AND CABINETS | TT_FinMile | 25/09/2017 | 25/09/2017 | 13/09/2017 | 13/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-C--2B00 | black | SETUP T3000 DB | TT_Mile | 01/05/2017 | 01/05/2017 | 07/04/2017 | 07/04/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 07/04/2017
SI-C--2B35 | red | SW ENGINEERING BOP I&amp;C, T3000 DB MERGING | TT_Task | 01/05/2017 | 19/11/2017 | 07/04/2017 | 24/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-C--2B40 | blue | (DF) T3000 DB | TT_FinMile | 25/02/2018 | 25/02/2018 | 24/01/2018 | 24/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-C--2B41 | red | SW ENGINEERING BOP I&amp;C, T3000 DB MERGING, PROXIE GENERATION | TT_Task | 26/01/2018 | 08/03/2018 | 25/01/2018 | 24/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-C--2B70 | blue | HANDOVER T3000 DB FOR TEST | TT_FinMile | 26/03/2018 | 26/03/2018 | 24/03/2018 | 24/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-C--2C50 | blue | (ICBB2) PRELIMINARY MEASUREMENT LIST, SIGNAL LIST AND BB INTERFACE SHEETS | TT_FinMile | 15/03/2017 | 15/03/2017 | 01/03/2017 | 01/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-C--2C55 | blue | (ICBB3) FINAL MEASUREMENT LIST, SIGNAL LIST AND BB INTERFACE SHEETS | TT_FinMile | 25/08/2017 | 25/08/2017 | 29/07/2017 | 29/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-CJJ2-38 | blue | ST INPUT FOR I&amp;C UNIT COORDINATION | TT_FinMile | 25/08/2017 | 25/08/2017 | 02/08/2017 | 02/08/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 02/08/2017
SI-CJP2-38 | blue | GT INPUT FOR I&amp;C UNIT COORDINATION | TT_FinMile | 25/08/2017 | 25/08/2017 | 17/08/2017 | 17/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-C--2-55 | blue | (ICSY3) FINAL LOGICS AND HMI GRAPHICS | TT_FinMile | 22/10/2017 | 22/10/2017 | 22/09/2017 | 22/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1CJ-2-50 | blue | (DF) BOP I&amp;C HARDWARE FOR PLANT SHOP TEST AND I&amp;C FOR UQA ELEC. ROOM | TT_FinMile | 26/09/2017 | 26/09/2017 | 08/09/2017 | 08/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1CJ-3-20 | red | DETAIL DESIGN HW ENGINEERING BOP I&amp;C CABINETS FOR PLANT SHOP TEST AND I&amp;C FOR UQA ELEC. ROOM | TT_Task | 21/06/2017 | 26/09/2017 | 21/05/2017 | 26/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1CJ-3-25 | red | MANUFACTURING BOP I&amp;C CABINETS FOR PLANT SHOP TEST AND I&amp;C FOR UQA ELEC. ROOM | TT_Task | 27/09/2017 | 26/12/2017 | 14/09/2017 | 25/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1CJ-3-80 | blue | (RFS) READY FOR SHIPMENT BOP I&amp;C CABINETS FOR PLANT SHOP TEST AND I&amp;C FOR UQA ELEC. ROOM | TT_FinMile | 18/02/2018 | 18/02/2018 | 08/01/2018 | 08/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1CJ-4-25 | red | TRANSPORT TO WORKSHOP BOP I&amp;C CABINETS FOR PLANT SHOP TEST AND I&amp;C FOR UQA ELEC. ROOM | TT_Task | 19/02/2018 | 04/03/2018 | 09/01/2018 | 22/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-C--3-80 | blue | (RFS) READY FOR SHIPMENT BOP I&amp;C FIELD CABINETS | TT_FinMile | 19/06/2018 | 19/06/2018 | 06/07/2018 | 06/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-C--3B25 | red | DETAIL DESIGN, MANUFACTURING, SHOP TEST FOR BOP I&amp;C FIELD DEVICES AND ERECTION MATERIAL | TT_Task | 26/08/2017 | 02/03/2018 | 29/07/2017 | 06/07/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 29/07/2017
SI-C--3B80 | blue | (RFS) READY FOR SHIPMENT BOP I&amp;C FIELD DEVICES AND ERECTION MATERIAL | TT_FinMile | 19/06/2018 | 19/06/2018 | 25/07/2018 | 25/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-C--4B25 | red | TRANSPORT TO SITE BOP I&amp;C FIELD DEVICES AND ERECTION MATERIAL | TT_Task | 20/06/2018 | 18/08/2018 | 25/07/2018 | 25/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-C--4B42 | blue | (OTD-OS) ON SITE BOP I&amp;C FIELD DEVICES AND ERECTION MATERIAL | TT_FinMile | 18/08/2018 | 18/08/2018 | 25/08/2018 | 25/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CP-3-25 | red | DETAIL DESIGN, MANUFACTURING, SHOP TEST FOR BOP I&amp;C FIELD CABINETS | TT_Task | 01/06/2017 | 14/02/2018 | 20/05/2017 | 24/07/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 20/05/2017
SI-CP-4-25 | red | TRANSPORT TO SITE BOP I&amp;C FIELD CABINETS | TT_Task | 20/06/2018 | 18/08/2018 | 25/07/2018 | 25/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CP-4-42 | blue | (OTD-OS) ON SITE BOP I&amp;C FIELD CABINETS | TT_FinMile | 18/08/2018 | 18/08/2018 | 25/08/2018 | 25/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-C--3C25 | red | DETAIL DESIGN, MANUFACTURING, SHOP TEST FOR BOP I&amp;C CABLES | TT_Task | 26/09/2017 | 12/02/2018 | 16/09/2017 | 30/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-C--3C80 | blue | (RFS) READY FOR SHIPMENT BOP I&amp;C CABLES | TT_FinMile | 19/06/2018 | 19/06/2018 | 30/06/2018 | 30/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-C--4C25 | red | TRANSPORT TO SITE FOR BOP I&amp;C CABLES | TT_Task | 20/06/2018 | 18/08/2018 | 01/07/2018 | 06/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-C--4C40 | blue | (OTD-OS) ON SITE BOP I&amp;C CABLES | TT_FinMile | 18/08/2018 | 18/08/2018 | 06/08/2018 | 06/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CR-3-25 | red | DETAIL DESIGN, MANUFACTURING/ SHOP TEST FOR CCR HMI EQUIPMENT | TT_Task | 01/06/2017 | 17/01/2018 | 18/05/2017 | 22/08/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 18/05/2017
SI-CR-3-26 | blue | CENTRAL CONTROL ROOM I&amp;C EQUIPMENT CONCEPT PLAN READY | TT_FinMile | 12/12/2021 | 12/12/2021 | 17/05/2017 | 17/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-CR-3-80 | blue | (RFS) READY FOR SHIPMENT CCR HMI EQUIPMENT | TT_FinMile | 19/06/2018 | 19/06/2018 | 23/08/2018 | 23/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CR-4-25 | red | TRANSPORT TO SITE CCR HMI EQUIPMENT | TT_Task | 20/06/2018 | 18/08/2018 | 07/10/2018 | 12/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CR-4-42 | blue | (OTD-OS) ON SITE CCR HMI EQUIPMENT | TT_FinMile | 18/08/2018 | 18/08/2018 | 12/11/2018 | 12/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CFE3-25 | red | DETAIL DESIGN, MANUFACTURING/ SHOP TEST FOR EMISSION MONITORING SYSTEM | TT_Task | 01/05/2017 | 18/02/2018 | 15/04/2017 | 24/05/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 15/04/2017
SI-CFE3-80 | blue | (RFS) READY FOR SHIPMENT EMISSION MONITORING SYSTEM - CONTAINER | TT_FinMile | 30/06/2018 | 30/06/2018 | 31/10/2019 | 31/10/2019 | 0 | TK_Complete | CCGTD1_IPS
SI-CFE4-25 | red | TRANSPORT TO SITE EMISSION MONITORING SYSTEM | TT_Task | 01/07/2018 | 29/08/2018 | 31/10/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SI-CFE4-42 | blue | (OTD-OS) ON SITE EMISSION MONITORING SYSTEM | TT_FinMile | 29/08/2018 | 29/08/2018 | 14/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2A60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS AND LOADS AVAILABLE TS FOUNDATION UMC | TT_FinMile | 30/04/2017 | 30/04/2017 | 18/04/2017 | 18/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2A65 | blue | (MS4) CONCRETE STRUCTURE FINAL INPUT EMBEDDED PARTS TS FOUNDATION UMC | TT_FinMile | 30/04/2017 | 30/04/2017 | 18/04/2017 | 18/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2A70 | red | DETAIL DESIGN / CHECKER CONCRETE STRUCTURE TS FOUNDATION UMC | TT_Task | 14/02/2017 | 15/05/2017 | 02/02/2017 | 13/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3B27 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT EMBEDDED PARTS FOR TURBOSET FDN UMC | TT_Task | 01/05/2017 | 01/08/2017 | 01/04/2017 | 11/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC4A50 | black | EMBEDDED PARTS FOR TURBOSET FOUNDATION UMC ON-SITE | TT_Mile | 21/08/2017 | 21/08/2017 | 20/07/2017 | 20/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2Y45 | red | PREPARATION BASIC BUILDING DWGS COND. PIT UMC | TT_Task | 14/02/2017 | 20/03/2017 | 05/02/2017 | 22/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2Y60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE COND.PIT UMC 3a | TT_FinMile | 28/02/2017 | 28/02/2017 | 18/02/2017 | 18/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2-45 | red | PREPARATION BASIC BUILDING DWGS UMC | TT_Task | 29/03/2017 | 02/05/2017 | 14/03/2017 | 29/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2-60 | blue | (MS3) CONCRETE STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 10/04/2017 | 10/04/2017 | 21/03/2017 | 21/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2B60 | blue | (MS3) CRANE WALKWAY FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 07/04/2017 | 07/04/2017 | 29/03/2017 | 29/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2B70 | red | DETAIL DESIGN / CHECKER CRANE WALKWAY UMC | TT_Task | 01/04/2017 | 23/06/2017 | 16/03/2017 | 24/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2B75 | black | (F) DETAIL DESIGN CRANE WALKWAY WITH CONTRACTOR UMC | TT_Mile | 26/11/2017 | 26/11/2017 | 09/11/2017 | 09/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2G60 | blue | (MS3) STEEL PLATFORM LUBE OIL, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 25/06/2017 | 25/06/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2G70 | red | DETAIL DESIGN / CHECKER STEEL PLATFORM LUBE OIL UMC | TT_Task | 26/06/2017 | 11/08/2017 | 02/06/2017 | 24/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2G75 | black | (F) DETAIL DESIGN STEEL PLATFORM LUBE OIL DWGS WITH CONTRACTOR UMC | TT_Mile | 26/11/2017 | 26/11/2017 | 09/11/2017 | 09/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3B25 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE CRANE WALKWAY UMC | TT_Task | 31/10/2017 | 18/01/2018 | 10/11/2017 | 23/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3G25 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM LUBE OIL UMC | TT_Task | 31/10/2017 | 18/01/2018 | 10/11/2017 | 23/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I113 | blue | (MS3) STEEL PLATFORM CRANE RAILS FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 01/07/2017 | 01/07/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I115 | red | DETAIL DESIGN / CHECKER STEEL PLATFORM CRANE RAILS UMC | TT_Task | 02/07/2017 | 02/09/2017 | 02/06/2017 | 07/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I117 | black | (F) DETAIL DESIGN STEEL PLATFORM CRANE RAILS DWGS WITH CONTRACTOR UMC | TT_Mile | 31/10/2017 | 31/10/2017 | 25/11/2017 | 25/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3I39 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT STEEL PLATFORM CRANE RAILS UMC | TT_Task | 31/10/2017 | 18/01/2018 | 25/11/2017 | 14/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2F60 | blue | (MS3) STEEL PLATFORM ENTRANCE, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 31/05/2017 | 31/05/2017 | 25/05/2017 | 25/05/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 25/05/2017
SI1UMC2F70 | red | DETAIL DESIGN / CHECKER STEEL PLATFORM ENTRANCE UMC | TT_Task | 01/06/2017 | 26/07/2017 | 26/05/2017 | 25/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2F75 | black | (F) DETAIL DESIGN STEEL PLATFORM ENTRANCE DWGS WITH CONTRACTOR UMC | TT_Mile | 26/11/2017 | 26/11/2017 | 24/11/2017 | 24/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3F25 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM ENTRANCE UMC | TT_Task | 21/11/2017 | 08/02/2018 | 24/11/2017 | 27/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2E60 | blue | (MS3) STEEL PLATFORM COND. PIT, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 30/04/2017 | 30/04/2017 | 18/04/2017 | 18/04/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 08/04/2017
SI1UMC2E70 | red | DETAIL DESIGN / CHECKER STEEL PLATFORM COND. PIT UMC | TT_Task | 01/05/2017 | 02/07/2017 | 09/04/2017 | 30/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2E75 | black | (F) DETAIL DESIGN STEEL PLATFORM COND. PIT DWGS WITH CONTRACTOR UMC | TT_Mile | 31/10/2017 | 31/10/2017 | 25/11/2017 | 25/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3E25 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM COND. PIT UMC | TT_Task | 26/11/2017 | 18/01/2018 | 25/11/2017 | 23/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2L60 | blue | (MS3) STEEL PLATFORM ST, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 25/06/2017 | 25/06/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2L70 | red | DETAIL DESIGN / CHECKER STEEL PLATFORM ST UMC | TT_Task | 26/06/2017 | 17/08/2017 | 02/06/2017 | 26/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2L75 | black | (F) DETAIL DESIGN STEEL PLATFORM ST DWGS WITH CONTRACTOR UMC | TT_Mile | 26/11/2017 | 26/11/2017 | 25/11/2017 | 25/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3L25 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM GENERATOR UMC | TT_Task | 26/11/2017 | 09/03/2018 | 25/11/2017 | 30/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2J60 | blue | (MS3) STEEL PLATFORM GT, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 31/05/2017 | 31/05/2017 | 19/05/2017 | 19/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2J70 | red | DETAIL DESIGN / CHECKER STEEL PLATFORM GT UMC | TT_Task | 01/06/2017 | 02/08/2017 | 01/05/2017 | 24/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2J75 | black | (F) DETAIL DESIGN STEEL PLATFORM GT DWGS WITH CONTRACTOR UMC | TT_Mile | 31/10/2017 | 31/10/2017 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3J25 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM GT UMC | TT_Task | 26/11/2017 | 13/02/2018 | 01/11/2017 | 23/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I83 | blue | (MS3) STEEL PLATFORM CONDENSER MANHOLE ACCESS FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 25/06/2017 | 25/06/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I85 | red | DETAIL DESIGN / CHECKER STEEL PLATFORM CONDENSER MANHOLE ACCESS UMC | TT_Task | 26/06/2017 | 16/09/2017 | 02/06/2017 | 14/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I87 | black | (F) DETAIL DESIGN STEEL PLATFORM CONDENSER MANHOLE ACCESS DWGS WITH CONTRACTOR UMC | TT_Mile | 26/01/2018 | 26/01/2018 | 24/01/2018 | 24/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3I29 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM CONDENSER MANHOLE ACCESS UMC | TT_Task | 26/01/2018 | 05/04/2018 | 24/01/2018 | 27/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I101 | blue | (MS3) STEEL PLATFORM OVER TG FDN FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 02/07/2017 | 02/07/2017 | 08/06/2017 | 08/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I103 | red | DETAIL DESIGN / CHECKER STEEL PLATFORM OVER TG FDN UMC | TT_Task | 03/07/2017 | 16/09/2017 | 09/06/2017 | 15/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I105 | black | (F) DETAIL DESIGN STEEL PLATFORM OVER TG FDN DWGS WITH CONTRACTOR UMC | TT_Mile | 26/01/2018 | 26/01/2018 | 20/01/2018 | 20/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3I35 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM OVER TG FDN UMC | TT_Task | 26/01/2018 | 06/06/2018 | 20/01/2018 | 15/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I107 | blue | (MS3) STEEL MISC. PLATFORM FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 02/07/2017 | 02/07/2017 | 08/06/2017 | 08/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I109 | red | DETAIL DESIGN / CHECKER STEEL MISC. PLATFORM UMC | TT_Task | 03/07/2017 | 16/09/2017 | 09/06/2017 | 04/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I111 | black | (F) DETAIL DESIGN STEEL MISC. PLATFORM DWGS WITH CONTRACTOR UMC | TT_Mile | 02/03/2018 | 02/03/2018 | 20/01/2018 | 20/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3I37 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL MISC. PLATFORM UMC | TT_Task | 02/03/2018 | 10/07/2018 | 20/01/2018 | 15/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I60 | blue | (MS3) STEEL PLATFORM BEARING ACCESS FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 25/06/2017 | 25/06/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I70 | red | DETAIL DESIGN / CHECKER STEEL PLATFORM BEARING ACCESS UMC | TT_Task | 26/06/2017 | 16/09/2017 | 02/06/2017 | 15/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I75 | black | (F) DETAIL DESIGN STEEL PLATFORM BEARING ACCESS DWGS WITH CONTRACTOR UMC | TT_Mile | 26/01/2018 | 26/01/2018 | 20/01/2018 | 20/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3I25 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM BEARING ACCESS UMC | TT_Task | 26/01/2018 | 05/06/2018 | 20/01/2018 | 15/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I89 | blue | (MS3) STEEL PLATFORM PIPE ACCESS NEAR CEP FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 31/03/2017 | 31/03/2017 | 15/03/2017 | 15/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I91 | red | DETAIL DESIGN / CHECKER STEEL PLATFORM PIPE ACCESS NEAR CEP UMC | TT_Task | 01/04/2017 | 02/06/2017 | 16/03/2017 | 12/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I93 | black | (F) DETAIL DESIGN STEEL PLATFORM PIPE ACCESS NEAR CEP DWGS WITH CONTRACTOR UMC | TT_Mile | 26/11/2017 | 26/11/2017 | 21/11/2017 | 21/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3I31 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM PIPE ACCESS NEAR CEP UMC | TT_Task | 26/11/2017 | 09/03/2018 | 21/11/2017 | 30/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I95 | blue | (MS3) STEEL PLATFORM LP BY-PASS FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 25/06/2017 | 25/06/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I97 | red | DETAIL DESIGN / CHECKER STEEL PLATFORM LP BY-PASS UMC | TT_Task | 26/06/2017 | 17/08/2017 | 02/06/2017 | 26/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I99 | black | (F) DETAIL DESIGN STEEL PLATFORM LP BY-PASS DWGS WITH CONTRACTOR UMC | TT_Mile | 21/11/2017 | 21/11/2017 | 21/11/2017 | 21/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3I33 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM LP BY-PASS UMC | TT_Task | 26/11/2017 | 03/02/2018 | 21/11/2017 | 30/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I77 | blue | (MS3) STEEL PLATFORM BUS DUCT SUPPORT FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 25/06/2017 | 25/06/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I79 | red | DETAIL DESIGN / CHECKER STEEL PLATFORM BUS DUCT SUPPORT UMC | TT_Task | 26/06/2017 | 16/09/2017 | 02/06/2017 | 14/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2I81 | black | (F) DETAIL DESIGN STEEL PLATFORM BUS DUCT SUPPORT DWGS WITH CONTRACTOR UMC | TT_Mile | 26/01/2018 | 26/01/2018 | 20/01/2018 | 20/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3I27 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM BUS DUCT SUPPORT UMC | TT_Task | 26/01/2018 | 06/06/2018 | 20/01/2018 | 15/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2P60 | blue | (MS3) STEEL ATTACHED TO MAIN FRAME, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 25/08/2017 | 25/08/2017 | 03/08/2017 | 03/08/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 03/08/2017
SI1UMC2P70 | red | DETAIL DESIGN / CHECKER STEEL ATTACHED TO MAIN FRAME | TT_Task | 26/08/2017 | 20/10/2017 | 04/08/2017 | 14/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2P75 | black | (F) DETAIL DESIGN STEEL ATTACHED TO MAIN FRAME DWGS WITH CONTRACTOR UMC | TT_Mile | 26/01/2018 | 26/01/2018 | 20/01/2018 | 20/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3P25 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL ATTACHED TO MAIN FRAME | TT_Task | 26/01/2018 | 06/06/2018 | 20/01/2018 | 27/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2O77 | blue | (MS3) UMCM1Y MODULE PIPE RACK, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 14/02/2017 | 14/02/2017 | 13/02/2017 | 13/02/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 13/02/2017
SI1UMC2X10 | red | DETAIL DESIGN UMCM1Y MODULE PIPE RACK | TT_Task | 01/03/2017 | 12/09/2017 | 14/02/2017 | 28/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3X10 | red | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL UMCM1Y MODULE PIPE RACK | TT_Task | 29/09/2017 | 13/12/2017 | 29/08/2017 | 12/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3X25 | red | MANUFACTURING UMCM1Y MODULE PIPE RACK | TT_Task | 26/10/2017 | 02/02/2018 | 02/10/2017 | 26/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC4X25 | red | TRANSPORT UMCM1Y MODULE PIPE RACK | TT_Task | 15/04/2018 | 27/04/2018 | 23/05/2018 | 29/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC4X42 | blue | (OTD-OS) ON SITE UMCM1Y MODULE PIPE RACK | TT_FinMile | 27/04/2018 | 27/04/2018 | 29/05/2018 | 29/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC2O60 | blue | (MS3) UMCL1Y MODULE PIPE RACK, FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 14/02/2017 | 14/02/2017 | 06/02/2017 | 06/02/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 06/02/2017
SI1UMC2Y10 | red | DETAIL DESIGN UMCL1Y MODULE PIPE RACK | TT_Task | 14/02/2017 | 17/07/2017 | 07/02/2017 | 10/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3Y10 | red | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL UMCL1Y MODULE PIPE RACK | TT_Task | 09/08/2017 | 19/11/2017 | 11/07/2017 | 21/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC3Y25 | red | MANUFACTURING UMCL1Y MODULE PIPE RACK | TT_Task | 21/11/2017 | 08/02/2018 | 22/10/2017 | 01/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC4Y25 | red | TRANSPORT UMCL1Y MODULE PIPE RACK | TT_Task | 15/04/2018 | 27/04/2018 | 17/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMC4Y42 | blue | (OTD-OS) ON SITE UMCL1Y MODULE PIPE RACK | TT_FinMile | 27/04/2018 | 27/04/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BZP2K30 | red | DETAIL DESIGN CABLE SUPPORT SYSTEM STEEL PLATFOR UMC | TT_Task | 25/07/2017 | 18/09/2017 | 30/06/2017 | 24/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1MAL2-10 | red | DETAIL DESIGN MAL00Y MODULE | TT_Task | 16/03/2017 | 23/08/2017 | 02/03/2017 | 27/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1MAL2O79 | blue | (MS3) MAL00Y MODULE FINAL DIMENSIONS AND LOADS AVAILABLE UMC | TT_FinMile | 31/03/2017 | 31/03/2017 | 15/03/2017 | 15/03/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 01/03/2017
SI1MAL3-10 | red | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL MAL00Y MODULE | TT_Task | 11/09/2017 | 06/12/2017 | 28/07/2017 | 04/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1MAL3-25 | red | MANUFACTURING MAL00Y MODULE | TT_Task | 06/12/2017 | 09/02/2018 | 05/11/2017 | 15/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MAL4-42 | red | TRANSPORT MAL00Y MODULE | TT_Task | 15/04/2018 | 27/04/2018 | 17/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MAL4-44 | blue | (OTD-OS) ON SITE MAL00Y MODULE | TT_FinMile | 27/04/2018 | 27/04/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1SMM2-60 | blue | (DF) FINAL INPUT FOR MS3 CRANE SMM01/02 FOR UMC | TT_FinMile | 31/03/2017 | 31/03/2017 | 15/03/2017 | 15/03/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 15/03/2017
SI1SMM2-75 | red | CONTRACT REVIEW, PREPARATION RFQ CRANE SMM01/02 FOR UMC | TT_Task | 14/01/2017 | 12/02/2017 | 12/12/2016 | 30/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1SMM2-80 | red | QUOTATION STAGE CRANE SMM01/02 FOR UMC | TT_Task | 13/02/2017 | 19/03/2017 | 31/12/2016 | 27/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1SMM2-85 | black | ORDER PLACED CRANE SMM01/02 FOR UMC | TT_Mile | 01/03/2017 | 01/03/2017 | 28/02/2017 | 28/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1SMM3-25 | red | FABRICATION DESIGN, MANUFACTURING, SHOP TEST CRANE SMM01, 02 FOR UMC | TT_Task | 16/03/2017 | 21/12/2017 | 01/03/2017 | 30/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1SMM3-80 | blue | (RFS) READY FOR SHIPMENT CRANE SMM01/02 FOR UMC | TT_FinMile | 20/12/2017 | 20/12/2017 | 30/11/2017 | 30/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1SMM4-27 | red | TRANSPORT CRANE SMM01/02 FOR UMC | TT_Task | 16/12/2017 | 14/01/2018 | 13/12/2017 | 01/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1SMM4-40 | blue | (OTD-OS) ON SITE CRANE SMM01/02 FOR UMC | TT_FinMile | 08/02/2018 | 08/02/2018 | 01/01/2018 | 01/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1SMM3A25 | red | FABRICATION DESIGN, MANUFACTURING, SHOP TEST CRANE SMM03 FOR UMC | TT_Task | 01/06/2017 | 29/11/2017 | 30/05/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1SMM3A80 | blue | (RFS) READY FOR SHIPMENT CRANES SMM03 FOR UMC | TT_FinMile | 26/01/2018 | 26/01/2018 | 14/12/2017 | 14/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1SMM4A27 | red | TRANSPORT CRANES SMM03 FOR UMC | TT_Task | 26/01/2018 | 24/02/2018 | 15/12/2017 | 15/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1SMM4A40 | blue | (OTD-OS) ON SITE CRANES SMM03 FOR UMC | TT_FinMile | 25/02/2018 | 25/02/2018 | 15/01/2018 | 15/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MA-3-25 | red | DETAIL DESIGN / MANUFACTURING / ASSEMBLY HP/IP-LP ST &amp; ST-AUXILIARIES MA | TT_Task | 26/11/2016 | 24/01/2018 | 20/11/2016 | 21/11/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 20/11/2016
SI1MAD4-27 | red | TRANSPORT ST BEARINGS MAD | TT_Task | 16/12/2017 | 21/01/2018 | 03/12/2017 | 08/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MAD3-80 | black | DELIVERY ST BEARINGS MAD EX WORKS | TT_Mile | 26/10/2017 | 26/10/2017 | 06/10/2017 | 06/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MAD4-15 | red | TRANSPORT ST BEARINGS MAD TO NORTH SEA PORT | TT_Task | 26/10/2017 | 01/11/2017 | 06/10/2017 | 12/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1MA-4-63 | red | TRANSPORT STEAM TURBINE MA- (HP/IP) (incl. FCA) | TT_Task | 26/01/2018 | 31/03/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MA-3-82 | black | DELIVERY STEAM TURBINE MA- (HP/IP) EX WORKS | TT_Mile | 26/01/2018 | 26/01/2018 | 12/12/2017 | 12/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MA-4-15 | red | TRANSPORT STEAM TURBINE MA- (HP/IP) TO NORTH SEA PORT | TT_Task | 26/01/2018 | 01/02/2018 | 12/01/2018 | 15/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MA-4-65 | red | TRANSPORT ST MA- (LP OUTER CASING) | TT_Task | 26/03/2018 | 12/04/2018 | 07/03/2018 | 04/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MA-4-67 | red | TRANSPORT ST MA- (LP-ROTOR, INNER CASING) | TT_Task | 26/01/2018 | 05/04/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MA-3-84 | black | DELIVERY ST MA- (LP OUTER CASING) EX WORKS | TT_Mile | 26/11/2017 | 26/11/2017 | 27/10/2017 | 27/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MA-3-86 | black | DELIVERY ST MA- (LP ROTOR, INNERCASING) EX WORKS | TT_Mile | 26/01/2018 | 26/01/2018 | 14/12/2017 | 14/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MA-4-22 | red | TRANSPORT ST MA- (LP OUTER CASING) TO BANTEN PORT | TT_Task | 26/01/2018 | 01/02/2018 | 30/11/2017 | 06/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MA-4-26 | red | TRANSPORT ST MA- (LP-ROTOR, INNER CASING) TO NORTH SEA PORT | TT_Task | 26/01/2018 | 01/02/2018 | 28/12/2017 | 03/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MA-4-57 | red | TRANSPORT ST VALVES (for MAL00Y MODULE) TO MODULE ASSEMBLY SHOP | TT_Task | 26/09/2017 | 13/11/2017 | 15/09/2017 | 24/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MA-3-88 | black | DELIVERY ST VALVES (for MAL00Y MODULE) EX WORKS | TT_Mile | 26/09/2017 | 26/09/2017 | 15/09/2017 | 15/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1MAG4-25 | red | TRANSPORT CONDENSER MAG | TT_Task | 07/03/2018 | 24/03/2018 | 07/03/2018 | 04/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MAG4-42 | blue | (OTD-OS) ON SITE CONDENSER MAG | TT_FinMile | 31/03/2018 | 31/03/2018 | 04/04/2018 | 04/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MAG3-25 | red | DESIGN / MANUFACTURING ST CONDENSER MAG | TT_Task | 01/03/2017 | 23/02/2018 | 22/02/2017 | 03/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MAG3-80 | black | DELIVERY ST CONDENSER MAG EX WORKS | TT_Mile | 26/01/2018 | 26/01/2018 | 03/01/2018 | 03/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MAG4-15 | red | TRANSPORT ST CONDENSER MAG TO PORT OF EXPORT | TT_Task | 26/03/2018 | 01/04/2018 | 26/02/2018 | 28/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MA-4-61 | red | TRANSPORT REMOVAL SYSTEM MAJ (China factory to Site) | TT_Task | 04/03/2018 | 18/03/2018 | 04/03/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MAJ4-46 | blue | (OTD-OS) ON SITE REMOVAL SYSTEM MAJ | TT_FinMile | 26/03/2018 | 26/03/2018 | 23/03/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MAJ3-80 | black | DELIVERY AIR REMOVAL SYSTEM MAJ EX WORKS | TT_Mile | 26/03/2018 | 26/03/2018 | 02/03/2018 | 02/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MAV4-25 | red | TRANSPORT LUBE OIL MODUL MAV | TT_Task | 26/01/2018 | 15/03/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MAV4-42 | blue | (OTD-OS) ON SITE LUBE OIL MODUL MAV | TT_FinMile | 31/03/2018 | 31/03/2018 | 01/04/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MAV3-80 | black | DELIVERY ST LUBE OIL MODULE MAV EX WORKS | TT_Mile | 19/02/2018 | 19/02/2018 | 04/01/2018 | 04/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MAV4-15 | red | TRANSPORT ST LUBE OIL MODULE MAV TO NORTH SEA PORT | TT_Task | 26/01/2018 | 01/02/2018 | 08/01/2018 | 14/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MAW4-25 | red | TRANSPORT TO SITE ST GLAND STEAM CONDENSER MAW | TT_Task | 18/01/2018 | 28/03/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MAW4-42 | blue | (OTD-OS) ON SITE ST GLAND STEAM CONDENSER MAW | TT_FinMile | 31/03/2018 | 31/03/2018 | 01/04/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MAW3-80 | black | DELIVERY ST GLAND STEAM CONDENSER MAW EX WORKS | TT_Mile | 05/01/2018 | 05/01/2018 | 04/12/2017 | 04/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MAW4-15 | red | TRANSPORT ST GLAND STEAM CONDENSER MAW TO NORTH SEA PORT | TT_Task | 26/01/2018 | 01/02/2018 | 08/01/2018 | 14/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MAX4-25 | red | TRANSPORT TO SITE HYDRAULIC SYSTEM MAX | TT_Task | 26/01/2018 | 26/03/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MAX4-42 | blue | (OTD-OS) ON SITE HYDRAULIC SYSTEM MAX | TT_FinMile | 31/03/2018 | 31/03/2018 | 01/04/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MAX3-80 | black | DELIVERY ST HYDRAULIC SYSTEM MAX EX WORKS | TT_Mile | 17/12/2017 | 17/12/2017 | 16/11/2017 | 16/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MAX4-15 | red | TRANSPORT ST HYDRAULIC SYSTEM MAX TO NORTH SEA PORT | TT_Task | 26/01/2018 | 01/02/2018 | 08/01/2018 | 14/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MPB4-27 | red | TRANSPORT ST NOISE PROTECTION SYSTEM MPB20 | TT_Task | 15/02/2018 | 18/04/2018 | 15/02/2018 | 21/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MPB3-80 | black | DELIVERY ST ENCLOSURE MPB20 EX WORKS | TT_Mile | 26/01/2018 | 26/01/2018 | 19/01/2018 | 19/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MPB4-15 | red | TRANSPORT ST ENCLOSURE MPB20 TO NORTH SEA PORT | TT_Task | 26/01/2018 | 01/02/2018 | 19/01/2018 | 25/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MKA4-27 | red | TRANSPORT GENERATOR MK | TT_Task | 26/01/2018 | 05/04/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MKA2-85 | black | ORDER PLACED ST GENERATOR MKA INCL. COOLER MKA70 | TT_Mile | 26/11/2016 | 26/11/2016 | 24/11/2016 | 24/11/2016 | 0 | TK_Complete | CCGTD1_IPS
SP1MKA3-25 | red | MANUFACTURING ST GENERATOR MKA INCL. COOLER MKA70 | TT_Task | 24/11/2016 | 13/01/2018 | 24/11/2016 | 14/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MKA3-80 | black | DELIVERY ST GENERATOR MKA INCL. COOLER MKA70 EX WORKS | TT_Mile | 26/01/2018 | 26/01/2018 | 02/01/2018 | 02/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MKA4-15 | red | TRANSPORT ST GENERATOR MKA INCL. COOLER MKA70 TO PORT OF EXPORT | TT_Task | 26/01/2018 | 01/02/2018 | 02/01/2018 | 10/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MKA4E27 | red | TRANSPORT GENERATOR SKIDS MKA | TT_Task | 26/03/2018 | 08/05/2018 | 18/03/2018 | 13/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MB-4E31 | red | TRANSPORT GT INTERCONNECTING PIPING MB- | TT_Task | 26/02/2018 | 06/05/2018 | 15/02/2018 | 21/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MB-3A80 | black | DELIVERY GT INTERCONNECTING PIPING MB- EX WORKS | TT_Mile | 26/02/2018 | 26/02/2018 | 14/02/2018 | 14/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MBA4-27 | red | TRANSPORT GAS TURBINE MB | TT_Task | 02/02/2018 | 12/04/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MB-2G75 | red | PREPARATION OF RFQ GT INSULATION MB- | TT_Task | 01/05/2017 | 14/05/2017 | 16/04/2017 | 29/04/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 16/04/2017
SP1MB-2G80 | red | QUOTATION STAGE GT INSULATION MB- | TT_Task | 15/05/2017 | 28/05/2017 | 30/04/2017 | 13/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MB-2G85 | black | ORDER PLACED GT INSULATION MB- | TT_Mile | 01/06/2017 | 01/06/2017 | 14/05/2017 | 14/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MB-3-25 | red | DESIGN / PROCUREMENT / MANUFACTURING GAS TURBINE | TT_Task | 14/01/2017 | 12/03/2018 | 18/12/2016 | 14/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MB-3-80 | black | DELIVERY GAS TURBINE MB- EX WORKS | TT_Mile | 26/01/2018 | 26/01/2018 | 02/01/2018 | 02/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MB-3G25 | red | DESIGN / MANUFACTURING GT INSULATION MB- | TT_Task | 01/06/2017 | 01/01/2018 | 14/05/2017 | 14/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MB-3G80 | black | DELIVERY GT INSULATION MB- EX WORKS | TT_Mile | 26/01/2018 | 26/01/2018 | 15/12/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MB-4-15 | red | TRANSPORT GAS TURBINE MB- TO NORTH SEA PORT | TT_Task | 26/01/2018 | 01/02/2018 | 02/01/2018 | 10/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MB-4E29 | red | TRANSPORT GT AUXILIARIES MB- | TT_Task | 26/03/2018 | 08/05/2018 | 18/03/2018 | 13/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MBL4-25 | red | TRANSPORT AIR INTAKE SYSTEM MBL | TT_Task | 09/02/2018 | 19/04/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MBL4-42 | blue | (OTD-OS) ON SITE AIR INTAKE SYSTEM MBL | TT_FinMile | 31/03/2018 | 31/03/2018 | 01/04/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MBL3-25 | red | DETAIL DESIGN / MANUFACTURING AIR INTAKE SYSTEM MBL | TT_Task | 16/03/2017 | 07/12/2017 | 02/03/2017 | 23/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MBL3-80 | black | DELIVERY AIR INTAKE SYSTEM MBL EX WORKS | TT_Mile | 16/12/2017 | 16/12/2017 | 15/12/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MBL4-15 | red | TRANSPORT AIR INTAKE SYSTEM MBL TO PORT OF EXPORT | TT_Task | 26/01/2018 | 08/02/2018 | 02/01/2018 | 10/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MPB4E27 | red | TRANSPORT GT ENCLOSURE INCL.VENT.MPB/SAM | TT_Task | 26/02/2018 | 06/05/2018 | 14/01/2018 | 22/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1SGJ4-27 | red | TRANSPORT ECONOPAC FIRE PROT.SYSTEM CYE/SGJ | TT_Task | 26/03/2018 | 08/05/2018 | 18/03/2018 | 13/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1SGJ3-25 | red | DETAIL DESIGN / MANUFACTURING FIRE FIGHTING / GAS DETECTION SGJ / CYQ / CYE | TT_Task | 01/04/2017 | 22/12/2017 | 16/03/2017 | 25/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1SGJ3-80 | black | DELIVERY FIRE FIGHTING / GAS DETECTION SGJ / CYQ / CYE EX WORKS | TT_Mile | 16/12/2017 | 16/12/2017 | 04/12/2017 | 04/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LBG3C25 | red | FABRICATION DESIGN, PROCUREMENT, PRE-FABRICATION EL.SUPERHEATER LBG | TT_Task | 01/05/2017 | 07/10/2017 | 29/04/2017 | 08/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LBG3C80 | blue | (RFS) READY FOR SHIPMENT EL.SUPERHEATER LBG | TT_FinMile | 26/02/2018 | 26/02/2018 | 26/01/2018 | 26/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LBG4C25 | red | TRANSPORT ELECTRICAL SUPERHEATER LBG | TT_Task | 08/03/2018 | 12/04/2018 | 08/02/2018 | 15/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LBG4C42 | blue | (OTD-OS) ON SITE ELECTRICAL SUPERHEATER LBG | TT_FinMile | 13/04/2018 | 13/04/2018 | 15/03/2018 | 15/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LCB2B14 | black | CONFIRMED PUMP CURVES CONDENSATE EXTRACTION PUMP LCB | TT_Mile | 20/03/2017 | 20/03/2017 | 16/03/2017 | 16/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LCB2B60 | blue | (DF) FINAL INPUT FOR MS3 CONDENSATE EXTRACTION PUMP LCB | TT_FinMile | 30/04/2017 | 30/04/2017 | 11/04/2017 | 11/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LCB2B65 | blue | (DF) FINAL INPUT FOR M2 CONDENSATE EXTRACTION PUMP LCB | TT_FinMile | 30/04/2017 | 30/04/2017 | 11/04/2017 | 11/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LCB2B75 | red | CONTRACT REVIEW, PREPARATION RFQ CONDENSATE EXTRACTION PUMP LCB | TT_Task | 26/11/2016 | 14/01/2017 | 10/11/2016 | 29/12/2016 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 10/11/2016
SI1LCB2B80 | red | QUOTATION STAGE CONDENSATE EXTRACTION PUMP LCB | TT_Task | 03/02/2017 | 14/04/2017 | 30/12/2016 | 14/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LCB2B85 | black | ORDER PLACED CONDENSATE EXTRACTION PUMP LCB | TT_Mile | 26/03/2017 | 26/03/2017 | 15/03/2017 | 15/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LCB3B25 | red | DETAIL DESIGN, MANUFACTURING, SHOP TEST CONDENSATE EXTRACTION PUMP LCB | TT_Task | 26/08/2017 | 14/06/2018 | 08/08/2017 | 24/04/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 08/08/2017
SI1LCB3B80 | blue | (RFS) READY FOR SHIPMENT CONDENSATE EXTRACTION PUMP LCB | TT_FinMile | 27/04/2018 | 27/04/2018 | 25/05/2018 | 25/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LCB4B25 | red | TRANSPORT CONDENSATE EXTRACTION PUMP LCB | TT_Task | 28/04/2018 | 08/06/2018 | 25/05/2018 | 01/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LCB4B42 | blue | (OTD-OS) ON SITE CONDENSATE EXTRACTION PUMP LCB | TT_FinMile | 08/06/2018 | 08/06/2018 | 01/06/2018 | 01/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PAH2-60 | blue | (DF) FINAL INPUT FOR MS3 CONCRETE CONDENSER TUBE CLEANING SYSTEM PAH | TT_FinMile | 05/05/2017 | 05/05/2017 | 21/04/2017 | 21/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PAH2-65 | blue | (DF) FINAL INPUT FOR M2 CONDENSER TUBE CLEANING SYSTEM PAH | TT_FinMile | 05/05/2017 | 05/05/2017 | 21/04/2017 | 21/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PAH2-75 | red | PREPARATION RFQ CONDENSER TUBE CLEANING SYSTEM PAH | TT_Task | 10/12/2016 | 30/12/2016 | 09/12/2016 | 29/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1PAH2-80 | red | QUOTATION STAGE CONDENSER TUBE CLEANING SYSTEM PAH | TT_Task | 14/01/2017 | 14/03/2017 | 30/12/2016 | 21/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PAH2-85 | black | ORDER PLACED CONDENSER TUBE CLEANING SYSTEM PAH | TT_Mile | 08/05/2017 | 08/05/2017 | 22/04/2017 | 22/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PAH2A60 | blue | (DF) FINAL INPUT FOR MS3 STEEL CONDENSER TUBE CLEANING SYSTEM PAH | TT_FinMile | 31/05/2017 | 31/05/2017 | 05/05/2017 | 05/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PAH3-25 | red | DETAIL DESIGN, MANUFACTURING CONDENSER TUBE CLEANING SYSTEM PAH | TT_Task | 01/05/2017 | 14/01/2018 | 23/04/2017 | 18/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PAH3-80 | blue | (RFS) READY FOR SHIPMENT CONDENSER TUBE CLEANING SYSTEM PAH | TT_FinMile | 26/01/2018 | 26/01/2018 | 16/12/2017 | 16/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PAH4-27 | red | TRANSPORT CONDENSER TUBE CLEANING SYSTEM PAH | TT_Task | 26/01/2018 | 15/03/2018 | 16/12/2017 | 17/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PCB2B60 | blue | (DF) FINAL INPUT FOR MS3 IN UMC SERVICE COOLING WATER PUMP PCB | TT_FinMile | 31/03/2017 | 31/03/2017 | 30/03/2017 | 30/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PCB2B65 | blue | (DF) FINAL INPUT FOR M2 SERVICE COOLING WATER PUMP PCB | TT_FinMile | 31/03/2017 | 31/03/2017 | 30/03/2017 | 30/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PCB2B75 | red | CONTRACT REVIEW, PREPARATION RFQ SERVICE COOLING WATER PUMP PCB | TT_Task | 17/12/2016 | 08/01/2017 | 24/11/2016 | 16/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1PCB2B80 | red | QUOTATION STAGE SERVICE COOLING WATER PUMP PCB | TT_Task | 02/02/2017 | 08/03/2017 | 29/12/2016 | 02/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PCB2B85 | black | ORDER PLACED SERVICE COOLING WATER PUMP PCB | TT_Mile | 19/03/2017 | 19/03/2017 | 03/03/2017 | 03/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PCB3B25 | red | DETAIL DESIGN, MANUFACTURING, SHOP TEST SERVICE COOLING WATER PUMP PCB | TT_Task | 19/03/2017 | 04/11/2017 | 04/03/2017 | 06/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PCB3B80 | blue | (RFS) READY FOR SHIPMENT SERVICE COOLING WATER PUMP PCB | TT_FinMile | 26/01/2018 | 26/01/2018 | 15/12/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PCB4B27 | red | TRANSPORT SERVICE COOLING WATER PUMP PCB | TT_Task | 26/01/2018 | 15/03/2018 | 31/01/2018 | 14/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PDB2-60 | blue | (DF) FINAL INPUT FOR MS3 CONCRETE DEBRIS FILTER PDB | TT_FinMile | 31/05/2017 | 31/05/2017 | 12/05/2017 | 12/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PDB2-65 | blue | (DF) FINAL INPUT FOR M2 DEBRIS FILTER PDB | TT_FinMile | 31/05/2017 | 31/05/2017 | 12/05/2017 | 12/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PDB2-75 | red | PREPARATION RFQ DEBRIS FILTER PDB | TT_Task | 10/12/2016 | 30/12/2016 | 09/12/2016 | 29/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1PDB2-80 | red | QUOTATION STAGE DEBRIS FILTER PDB | TT_Task | 03/02/2017 | 09/03/2017 | 30/12/2016 | 21/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PDB2-85 | black | ORDER PLACED DEBRIS FILTER PDB | TT_Mile | 15/05/2017 | 15/05/2017 | 22/04/2017 | 22/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PDB2A60 | blue | (DF) FINAL INPUT FOR MS3 STEEL DEBRIS FILTER PDB | TT_FinMile | 31/05/2017 | 31/05/2017 | 19/05/2017 | 19/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PDB3-25 | red | DETAIL DESIGN, MANUFACTURING DEBRIS FILTER PDB | TT_Task | 15/05/2017 | 04/02/2018 | 23/04/2017 | 04/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PDB3-80 | blue | (RFS) READY FOR SHIPMENT DEBRIS FILTER PDB | TT_FinMile | 14/02/2018 | 14/02/2018 | 04/01/2018 | 04/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PDB4-27 | red | TRANSPORT DEBRIS FILTER PDB | TT_Task | 15/02/2018 | 28/03/2018 | 08/02/2018 | 20/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB2B60 | blue | (DF) FINAL INPUT FOR MS3 CCW PUMP PGB | TT_FinMile | 31/03/2017 | 31/03/2017 | 27/03/2017 | 27/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB2B65 | blue | (DF) FINAL INPUT FOR M2 CCW PUMP PGB | TT_FinMile | 31/03/2017 | 31/03/2017 | 27/03/2017 | 27/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB2B75 | red | CONTRACT REVIEW, PREPARATION RFQ CCW PUMP PGB | TT_Task | 26/11/2016 | 30/12/2016 | 24/11/2016 | 28/12/2016 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 24/11/2016
SI1PGB2B80 | red | QUOTATION STAGE CCW PUMP PGB | TT_Task | 02/02/2017 | 05/04/2017 | 29/12/2016 | 02/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB2B85 | black | ORDER PLACED CCW PUMP PGB | TT_Mile | 17/03/2017 | 17/03/2017 | 03/03/2017 | 03/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB3B25 | red | DETAIL DESIGN, MANUFACTURING, SHOP TEST CCW PUMP PGB | TT_Task | 17/03/2017 | 12/12/2017 | 04/03/2017 | 06/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB3B80 | blue | (RFS) READY FOR SHIPMENT CCW PUMP PGB | TT_FinMile | 26/01/2018 | 26/01/2018 | 15/12/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB4B27 | red | TRANSPORT CCW PUMP PGB | TT_Task | 26/01/2018 | 15/03/2018 | 31/01/2018 | 13/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB2C60 | blue | (DF) FINAL INPUT FOR MS3 HEAT EXCHANGER PGB | TT_FinMile | 03/06/2017 | 03/06/2017 | 31/05/2017 | 31/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB2C65 | blue | (DF) FINAL INPUT FOR M2 HEAT EXCHANGER PGB | TT_FinMile | 25/06/2017 | 25/06/2017 | 13/06/2017 | 13/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB2C75 | red | PREPARATION RFQ HEAT EXCHANGER PGB | TT_Task | 01/02/2017 | 28/02/2017 | 19/01/2017 | 15/03/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 19/01/2017
SI1PGB2C80 | red | QUOTATION STAGE HEAT EXCHANGER PGB | TT_Task | 01/04/2017 | 26/04/2017 | 16/03/2017 | 16/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB2C85 | black | ORDER PLACED HEAT EXCHANGER PGB | TT_Mile | 02/06/2017 | 02/06/2017 | 17/05/2017 | 17/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB3C25 | red | FABRICATION DESIGN, PROCUREMENT, PRE-FABRICATION HEAT EXCHANGER PGB | TT_Task | 02/06/2017 | 18/12/2017 | 18/05/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB3C80 | blue | (RFS) READY FOR SHIPMENT HEAT EXCHANGER PGB | TT_FinMile | 15/12/2017 | 15/12/2017 | 15/12/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB4C27 | red | TRANSPORT HEAT EXCHANGER PGB | TT_Task | 26/01/2018 | 15/03/2018 | 31/01/2018 | 13/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB2D60 | blue | (DF) FINAL INPUT FOR MS3 EXPANSION TANK PGB | TT_FinMile | 25/08/2017 | 25/08/2017 | 29/07/2017 | 29/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB2D65 | blue | (DF) FINAL INPUT FOR M2 EXPANSION TANK PGB | TT_FinMile | 25/08/2017 | 25/08/2017 | 08/08/2017 | 08/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB2D75 | red | PREPARATION RFQ EXPANSION TANK PGB | TT_Task | 01/02/2017 | 28/02/2017 | 23/01/2017 | 15/03/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 23/01/2017
SI1PGB2D80 | red | QUOTATION STAGE EXPANSION TANK PGB | TT_Task | 01/04/2017 | 26/04/2017 | 16/03/2017 | 11/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB2D85 | black | ORDER PLACED EXPANSION TANK PGB | TT_Mile | 26/07/2017 | 26/07/2017 | 12/07/2017 | 12/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB3D25 | red | FABRICATION DESIGN, PROCUREMENT, PRE-FABRICATION EXPANSION TANK PGB | TT_Task | 26/07/2017 | 23/01/2018 | 12/07/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 01/06/2017
SI1PGB3D80 | blue | (RFS) READY FOR SHIPMENT EXPANSION TANK PGB | TT_FinMile | 26/01/2018 | 26/01/2018 | 04/12/2017 | 04/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PGB4D27 | red | TRANSPORT EXPANSION TANK PGB | TT_Task | 26/01/2018 | 15/03/2018 | 08/02/2018 | 20/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PXB2-10 | red | DETAIL DESIGN PXB00Y MODULE | TT_Task | 13/06/2017 | 21/11/2017 | 13/05/2017 | 09/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PXB2N60 | blue | (MS3) PXB00Y MODULE FINAL DIMENSIONS AND LOADS AVAILABLE | TT_FinMile | 14/07/2017 | 14/07/2017 | 19/06/2017 | 19/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PXB3-10 | red | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL PXB00Y MODULE | TT_Task | 09/11/2017 | 12/02/2018 | 10/10/2017 | 13/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PXB3-20 | blue | DELIVERY OF COMPONENTS PXB00Y MODULE | TT_FinMile | 18/03/2018 | 18/03/2018 | 15/02/2018 | 15/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PXB3-25 | red | MANUFACTURING PXB00Y MODULE | TT_Task | 26/01/2018 | 08/04/2018 | 14/01/2018 | 31/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PXB4-25 | red | TRANSPORT PXB00Y MODULE | TT_Task | 15/05/2018 | 30/05/2018 | 18/06/2018 | 25/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PXB4-42 | blue | (OTD-OS) ON SITE PXB00Y MODULE | TT_FinMile | 30/05/2018 | 30/05/2018 | 25/06/2018 | 25/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1CJT4-27 | red | TRANSPORT TO SITE SFC/SEE CUBICLE CJT | TT_Task | 26/03/2018 | 08/05/2018 | 18/03/2018 | 13/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1SCA3-80 | blue | (RFS) READY FOR SHIPMENT COMPRESSOR MAIN BODY SCA | TT_FinMile | 13/07/2018 | 13/07/2018 | 28/09/2018 | 28/09/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1SCA3-82 | blue | (RFS) READY FOR SHIPMENT RECEIVER TANKS SCA | TT_FinMile | 31/08/2018 | 31/08/2018 | 28/09/2018 | 28/09/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1SCA4-25 | red | TRANSPORT COMPRESSOR MAIN BODY SCA | TT_Task | 14/07/2018 | 11/09/2018 | 24/11/2018 | 02/01/2019 | 0 | TK_Complete | CCGTD1_IPS
SI1SCA4-42 | red | TRANSPORT RECEIVER TANKS SCA | TT_Task | 01/09/2018 | 30/10/2018 | 24/11/2018 | 02/01/2019 | 0 | TK_Complete | CCGTD1_IPS
SI1SCA4-44 | blue | (OTD-OS) ON SITE RECEIVER TANKS SCA | TT_FinMile | 30/10/2018 | 30/10/2018 | 02/01/2019 | 02/01/2019 | 0 | TK_Complete | CCGTD1_IPS
SI1SCA4-46 | blue | (OTD-OS) ON SITE COMPRESSOR MAIN BODY SCA | TT_FinMile | 11/09/2018 | 11/09/2018 | 02/01/2019 | 02/01/2019 | 0 | TK_Complete | CCGTD1_IPS
SI1UBA2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE 10UBA BUILDING or 10UBD | TT_FinMile | 12/12/2021 | 12/12/2021 | 16/02/2017 | 16/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UBA2-77 | red | PREPARATION BASIC BUILDING DWGS UBA BUILDING | TT_Task | 14/02/2017 | 20/03/2017 | 03/02/2017 | 22/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UBA2B60 | blue | (MS3) STEEL STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE 10UBA BUILDING or 10UBD | TT_FinMile | 25/08/2017 | 25/08/2017 | 11/08/2017 | 11/08/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 11/08/2017
SI1BZP2C30 | red | DETAIL DESIGN CABLE SUPPORT SYSTEM UBA/UBD | TT_Task | 01/03/2017 | 23/05/2017 | 21/02/2017 | 30/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1BBA3-25 | red | MANUFACTURING, SHOP TEST MV-SWITCHGEAR BBA | TT_Task | 02/09/2017 | 23/02/2018 | 01/08/2017 | 30/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BBA3-80 | blue | (RFS) READY FOR SHIPMENT MV-SWITCHGEAR BBA | TT_FinMile | 01/04/2018 | 01/04/2018 | 12/04/2018 | 12/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BBA4-12 | red | TRANSPORT TO SITE MV-SWITCHGEAR BBA | TT_Task | 02/04/2018 | 30/04/2018 | 17/06/2018 | 23/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BFA3-25 | red | MANUFACTURING, SHOP TEST LV-/DC-SWITCHGEAR BFA | TT_Task | 30/10/2017 | 25/02/2018 | 30/09/2017 | 25/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BFA3-80 | blue | (RFS) READY FOR SHIPMENT LV-/DC-SWITCHGEAR BFA | TT_FinMile | 16/05/2018 | 16/05/2018 | 27/06/2018 | 27/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BFA4-12 | red | TRANSPORT TO SITE LV-/DC-SWITCHGEAR BFA | TT_Task | 17/05/2018 | 15/07/2018 | 14/08/2018 | 20/09/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UBA3G58 | black | CABINET AT WORKSHOP FOR SHOP TEST CABINET 10UBA BUILDING | TT_Mile | 26/02/2018 | 26/02/2018 | 23/01/2018 | 23/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UBA3G60 | red | PREPARATION, SHOP TEST, DISMANTLING CABINET 10UBA BUILDING | TT_Task | 26/03/2018 | 03/06/2018 | 03/03/2018 | 30/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UBA3G80 | blue | (RFS) READY FOR SHIPMENT CABINET 10UBA BUILDING | TT_FinMile | 05/06/2018 | 05/06/2018 | 25/07/2018 | 25/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UBA4G27 | red | TRANSPORT TO SITE CABINET 10UBA BUILDING | TT_Task | 06/06/2018 | 04/08/2018 | 25/07/2018 | 25/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1CHA3-25 | red | MANUFACTURING, SHOP TEST PROT./SYNCHR./METERING CHA | TT_Task | 26/08/2017 | 05/03/2018 | 15/08/2017 | 13/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1CHA3-80 | blue | (RFS) READY FOR SHIPMENT PROT./SYNCHR./METERING CHA | TT_FinMile | 26/04/2018 | 26/04/2018 | 25/04/2018 | 25/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1CHA4-12 | red | TRANSPORT TO SITE PROT., SYNCHR., METERING CHA | TT_Task | 27/04/2018 | 07/06/2018 | 27/05/2018 | 30/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MBJ4-25 | red | TRANSPORT TO SITE SFC TRANSFORMER MBJ | TT_Task | 01/03/2018 | 09/05/2018 | 18/01/2018 | 01/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MBJ4-27 | red | PREPARATION FOR DISPATCH TO SITE SEE/SFC TRANSFORMER MBJ | TT_Task | 26/01/2018 | 11/03/2018 | 15/12/2017 | 15/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MKC4-27 | red | TRANSPORT TO SITE SEE TRANSFORMER MKC | TT_Task | 26/03/2018 | 26/04/2018 | 23/03/2018 | 01/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MKC2-80 | red | ORDERING / NEGOTIATIONS SEE/SFC TRANSFORMER MKC / MBJ | TT_Task | 14/02/2017 | 01/03/2017 | 01/02/2017 | 01/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MKC2-85 | black | ORDER PLACED SEE/SFC TRANSFORMER MKC / MBJ | TT_Mile | 17/03/2017 | 17/03/2017 | 02/03/2017 | 02/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MKC3-25 | red | MANUFACTURING SEE/SFC TRANSFORMER MKC / MBJ | TT_Task | 17/03/2017 | 22/12/2017 | 02/03/2017 | 12/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MKC3-65 | red | FINAL CHECK &amp; DISPATCH SEE/SFC TRANSFORMER MKC / MBJ | TT_Task | 16/12/2017 | 22/12/2017 | 13/12/2017 | 19/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MKC3-80 | black | DELIVERY SEE/SFC TRANSFORMER GT MKC / MBJ EX WORKS | TT_Mile | 30/01/2018 | 30/01/2018 | 20/12/2017 | 20/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UBD2-45 | red | PREPARATION BASIC BUILDING DWGS UBD01/02/03/04 | TT_Task | 01/06/2017 | 05/07/2017 | 10/05/2017 | 09/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UBD2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UBD01/02/03/04 | TT_FinMile | 31/05/2017 | 31/05/2017 | 23/05/2017 | 23/05/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 23/05/2017
SI1UBD2-70 | red | DETAIL DESIGN / CHECKER CONCRETE STRUCTURE UBD01/02/03/04 | TT_Task | 09/07/2017 | 10/09/2017 | 10/06/2017 | 30/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UBD3-70 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM UBD | TT_Task | 26/01/2018 | 07/05/2018 | 29/12/2017 | 27/06/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 29/12/2017
SI1UBF2-45 | red | PREPARATION BASIC BUILDING DWGS UBF/UBE | TT_Task | 01/06/2017 | 05/07/2017 | 04/05/2017 | 24/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UBF2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UBF/UBE | TT_FinMile | 15/06/2017 | 15/06/2017 | 17/05/2017 | 17/05/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 17/05/2017
SI1UBF2B60 | blue | (MS3) STEEL STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE UBF/UBE | TT_FinMile | 25/07/2017 | 25/07/2017 | 18/07/2017 | 18/07/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 18/07/2017
SI1UBF2B70 | red | DETAIL DESIGN / CHECKER STEEL STRUCTURE UBF/UBE | TT_Task | 25/07/2017 | 18/09/2017 | 19/07/2017 | 09/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UBF3B70 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM UBF | TT_Task | 26/01/2018 | 07/05/2018 | 29/12/2017 | 27/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UBL2-45 | red | PREPARATION BASIC BUILDING DWGS UBL | TT_Task | 26/06/2017 | 30/07/2017 | 01/05/2017 | 24/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UBL2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UBL | TT_FinMile | 25/06/2017 | 25/06/2017 | 15/05/2017 | 15/05/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 14/06/2017
SI1UBL3-60 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL PLATFORM UBL | TT_Task | 26/01/2018 | 27/05/2018 | 29/12/2017 | 27/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BAA3-25 | red | MANUFACTURING, SHOP TEST IPB BAA | TT_Task | 01/09/2017 | 01/03/2018 | 31/07/2017 | 27/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BAA3-80 | blue | (RFS) READY FOR SHIPMENT IPB BAA | TT_FinMile | 27/03/2018 | 27/03/2018 | 27/02/2018 | 27/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BAA4-27 | red | TRANSPORT IPB BAA | TT_Task | 26/08/2020 | 05/10/2020 | 07/05/2018 | 20/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BAT3-25 | red | MANUFACTURING, SHOP TEST MAIN TRANSFORMER BAT | TT_Task | 01/02/2017 | 27/12/2017 | 24/01/2017 | 02/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BAT3-80 | blue | (RFS) READY FOR SHIPMENT MAIN TRANSFORMER BAT | TT_FinMile | 26/08/2020 | 26/08/2020 | 30/04/2018 | 30/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BAT4-27 | red | TRANSPORT MAIN TRANSFORMER BAT | TT_Task | 02/05/2018 | 16/05/2018 | 03/05/2018 | 05/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BBT3-25 | red | MANUFACTURING, SHOP TEST AUXILIARY TRANSFORMER BBT | TT_Task | 01/02/2017 | 27/12/2017 | 24/01/2017 | 27/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1BBT3-80 | blue | (RFS) READY FOR SHIPMENT AUXILIARY TRANSFORMER BBT | TT_FinMile | 13/02/2018 | 13/02/2018 | 03/01/2018 | 03/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BBT4-27 | red | TRANSPORT AUXILIARY TRANSFORMER BBT | TT_Task | 26/02/2018 | 28/02/2018 | 31/01/2018 | 03/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BZP2I30 | red | DETAIL DESIGN CABLE SUPPORT SYSTEM UBE/UBF | TT_Task | 01/07/2017 | 11/08/2017 | 08/06/2017 | 28/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1ULD2-45 | red | PREPARATION BASIC BUILDING DWGS ULD | TT_Task | 12/04/2017 | 16/05/2017 | 27/03/2017 | 25/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1ULD2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE ULD | TT_FinMile | 15/05/2017 | 15/05/2017 | 18/04/2017 | 18/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1ULD2E75 | black | (F) DETAIL DESIGN STEEL PLATFORM ULD DWGS WITH CONTRACTOR | TT_Mile | 26/11/2017 | 26/11/2017 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LD-3-25 | red | DESIGN, MANUFACTURING, SHOP TEST CONDENSATE POLISHING PLANT LD | TT_Task | 16/03/2017 | 12/01/2018 | 01/03/2017 | 20/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LD-3-80 | blue | (RFS) READY FOR SHIPMENT CONDENSATE POLISHING PLANT LD | TT_FinMile | 06/06/2018 | 06/06/2018 | 21/09/2018 | 21/09/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LD-4-25 | red | TRANSPORT CONDENSATE POLISHING PLANT LD | TT_Task | 07/06/2018 | 25/07/2018 | 02/10/2018 | 06/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LD-4-42 | blue | (OTD-OS) ON SITE CONDENSATE POLISHING PLANT LD | TT_FinMile | 25/07/2018 | 25/07/2018 | 06/11/2018 | 06/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LDK3B25 | red | DETAIL DESIGN, MANUFACTURING, SHOP TEST CONDENSATE POLISHING PUMP LDK | TT_Task | 15/06/2017 | 10/04/2018 | 20/05/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LDK3B80 | blue | (RFS) READY FOR SHIPMENT CONDENSATE POLISHING PUMP LDK | TT_FinMile | 26/01/2018 | 26/01/2018 | 02/01/2018 | 02/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LDK4B25 | red | TRANSPORT CONDENSATE POLISHING PUMP LDK | TT_Task | 26/02/2018 | 17/04/2018 | 25/02/2018 | 06/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LDK4B42 | blue | (OTD-OS) ON SITE CONDENSATE POLISHING PUMP LDK | TT_FinMile | 31/05/2018 | 31/05/2018 | 06/04/2018 | 06/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UEZ2-45 | red | PREPARATION BASIC BUILDING DWGS UEZ01/02 | TT_Task | 26/06/2017 | 30/07/2017 | 17/06/2017 | 07/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UEZ2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UEZ01/02 | TT_FinMile | 25/07/2017 | 25/07/2017 | 10/07/2017 | 10/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UEZ2-70 | red | DETAIL DESIGN / CHECKER CONCRETE STRUCTURE UEZ01/02 | TT_Task | 05/09/2017 | 06/11/2017 | 08/08/2017 | 04/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1BAC2-75 | black | RFQ GENERATOR CIRCUIT BREAKER BAC | TT_Mile | 08/05/2017 | 08/05/2017 | 08/04/2017 | 08/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1BAC2-80 | red | QUOTATION STAGE GENERATOR CIRCUIT BREAKER BAC | TT_Task | 08/05/2017 | 04/06/2017 | 08/04/2017 | 05/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1BAC2-85 | black | ORDER PLACED GENERATOR CIRCUIT BREAKER BAC | TT_Mile | 01/06/2017 | 01/06/2017 | 06/05/2017 | 06/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1BAC3-25 | red | MANUFACTURING, SHOP TEST GENERATOR CIRCUIT BREAKER BAC | TT_Task | 01/06/2017 | 13/03/2018 | 06/05/2017 | 20/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1BAC3-80 | blue | (RFS) READY FOR SHIPMENT GENERATOR .CIRCUIT BREAKER BAC | TT_FinMile | 28/03/2018 | 28/03/2018 | 20/12/2017 | 20/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1BAC4-27 | red | TRANSPORT GENERATOR CIRCUIT BREAKER BAC | TT_Task | 05/02/2018 | 06/03/2018 | 05/02/2018 | 16/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0UBN2-45 | red | PREPARATION BASIC BUILDING DWGS UBN | TT_Task | 01/06/2017 | 05/07/2017 | 10/05/2017 | 25/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0UBN2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UBN | TT_FinMile | 31/05/2017 | 31/05/2017 | 23/05/2017 | 23/05/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 23/05/2017
SI0XKA2-15 | red | BASIC DESIGN, SPECIFICATION EMERGENCY DIESEL GENERATOR SET XKA | TT_Task | 01/06/2017 | 28/06/2017 | 16/05/2017 | 12/06/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 16/05/2017
SI0XKA2-75 | black | RFQ EMERGENCY DIESEL GENERATOR SET XKA | TT_Mile | 26/06/2017 | 26/06/2017 | 13/06/2017 | 13/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0XKA2-80 | red | QUOTATION STAGE EMERGENCY DIESEL GENERATOR SET XKA | TT_Task | 08/07/2017 | 04/08/2017 | 13/06/2017 | 31/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0XKA2-85 | black | ORDER PLACED EMERGENCY DIESEL GENERATOR SET XKA | TT_Mile | 02/09/2017 | 02/09/2017 | 01/08/2017 | 01/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0XKA3-25 | red | MANUFACTURING, SHOP TEST EMERGENCY DIESEL GENERATOR SET XKA | TT_Task | 02/09/2017 | 18/05/2018 | 01/08/2017 | 31/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0XKA3-80 | blue | (RFS) READY FOR SHIPMENT EMERGENCY DIESEL GENERATOR SET XKA | TT_FinMile | 23/05/2018 | 23/05/2018 | 25/09/2018 | 25/09/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0XKA4-27 | red | TRANSPORT EMERGENCY DIESEL GENERATOR .SET XKA | TT_Task | 24/05/2018 | 22/07/2018 | 15/10/2018 | 17/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0BZP2H30 | red | DETAIL DESIGN CABLE SUPPORT SYSTEM UBN | TT_Task | 25/07/2017 | 04/09/2017 | 01/07/2017 | 24/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1BFT3-25 | red | MANUFACTURING, SHOP TEST LV-TRANSFORMERS BFT | TT_Task | 25/07/2017 | 22/01/2018 | 20/07/2017 | 21/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BFT3-80 | blue | (RFS) READY FOR SHIPMENT LV-TRANSFORMERS BFT | TT_FinMile | 24/03/2018 | 24/03/2018 | 21/02/2018 | 21/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BFT4-27 | red | TRANSPORT LV-TRANSFORMERS BFT | TT_Task | 25/03/2018 | 23/05/2018 | 08/04/2018 | 15/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0UBH2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UBH01 | TT_FinMile | 31/05/2017 | 31/05/2017 | 17/05/2017 | 17/05/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 17/05/2017
SI1UMX2-45 | red | PREPARATION BASIC BUILDING DWGS UMX | TT_Task | 01/05/2017 | 04/06/2017 | 08/04/2017 | 12/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMX2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UMX | TT_FinMile | 30/04/2017 | 30/04/2017 | 21/04/2017 | 21/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1MBR4-25 | red | TRANSPORT DIFFUSER MBR | TT_Task | 26/03/2018 | 27/03/2018 | 28/02/2018 | 02/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MBR4-44 | blue | (OTD-OS) ON SITE EXHAUST GAS SYSTEM TURBINE EXHAUST MANIFOLD MBR | TT_FinMile | 26/03/2018 | 26/03/2018 | 10/03/2018 | 10/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MBR4-46 | blue | (OTD-OS) ON SITE EXHAUST GAS SYSTEM DIFFUSER MBR | TT_FinMile | 26/03/2018 | 26/03/2018 | 02/03/2018 | 02/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1MBR4A42 | red | TRANSPORT TURBINE EXHAUST MANIFOLD MBR | TT_Task | 26/03/2018 | 01/04/2018 | 02/03/2018 | 10/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SP1MBR3-25 | red | DETAIL DESIGN / MANUFACTURING DIFFUSER MBR | TT_Task | 16/03/2017 | 06/12/2017 | 10/03/2017 | 30/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MBR3-80 | black | DELIVERY DIFFUSER MBR EX WORKS | TT_Mile | 26/01/2018 | 26/01/2018 | 15/12/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MBR3A25 | red | DETAIL DESIGN / MANUFACTURING TURBINE EXHAUST MANIFOLD MBR | TT_Task | 09/04/2017 | 30/12/2017 | 24/03/2017 | 14/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MBR3A80 | black | DELIVERY TURBINE EXHAUST MANIFOLD MBR EX WORKS | TT_Mile | 26/01/2018 | 26/01/2018 | 15/12/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MBR4-15 | red | TRANSPORT DIFFUSER MBR TO PORT OF EXPORT | TT_Task | 26/01/2018 | 08/02/2018 | 15/12/2017 | 28/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SP1MBR4A15 | red | TRANSPORT TURBINE EXHAUST MANIFOLD MBR TO PORT OF EXPORT | TT_Task | 26/01/2018 | 08/02/2018 | 15/12/2017 | 28/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1USX2-60 | black | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE USX | TT_Mile | 26/11/2017 | 26/11/2017 | 23/11/2017 | 23/11/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 23/11/2017
SI1UEN2-45 | red | PREPARATION BASIC BUILDING DWGS 10UEN | TT_Task | 26/06/2017 | 30/07/2017 | 17/06/2017 | 30/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UEN2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE 10UEN | TT_FinMile | 25/07/2017 | 25/07/2017 | 25/06/2017 | 25/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1BZP2F30 | red | DETAIL DESIGN CABLE SUPPORT SYSTEM 10UEN | TT_Task | 25/07/2017 | 04/09/2017 | 22/07/2017 | 01/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-2-04 | black | P&amp;IDs INPUT AGREED WITH BOP-PIPING GAS SYSTEM EK/EKC | TT_Mile | 01/02/2017 | 01/02/2017 | 21/01/2017 | 21/01/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-2-60 | blue | (DF) FINAL INPUT FOR MS3 FUEL GAS SUPPLY SYSTEM EK/EKC | TT_FinMile | 25/06/2017 | 25/06/2017 | 09/06/2017 | 09/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-2-65 | blue | (DF) FINAL INPUT FOR M2 GAS SYSTEM EK/EKC | TT_FinMile | 31/05/2017 | 31/05/2017 | 28/04/2017 | 28/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-2-80 | red | QUOTATION STAGE FUEL GAS SUPPLY SYSTEM EK/EKC | TT_Task | 01/02/2017 | 28/03/2017 | 21/01/2017 | 27/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-2-85 | black | ORDER PLACED FUEL GAS SUPPLY SYSTEM EK/EKC | TT_Mile | 14/05/2017 | 14/05/2017 | 28/04/2017 | 28/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-3-25 | red | DETAIL DESIGN, MANUFACTURING FUEL GAS SUPPLY SYSTEM EK/EKC | TT_Task | 01/05/2017 | 25/10/2017 | 28/04/2017 | 24/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-3-55 | red | PRE ERECTION GAS SYSTEM/ PREHEATER EK/EKC | TT_Task | 16/02/2018 | 02/07/2018 | 06/01/2018 | 29/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-3-80 | blue | (RFS) READY FOR SHIPMENT GAS SYSTEM EK/EKC | TT_FinMile | 05/05/2018 | 05/05/2018 | 29/03/2018 | 29/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-4-25 | red | TRANSPORT FUEL GAS SUPPLY SYSTEM EK/EKC | TT_Task | 06/05/2018 | 04/07/2018 | 22/04/2018 | 29/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-4-46 | blue | (OTD-OS) ON SITE FUEL GAS SUPPLY SYSTEM EK/EKC | TT_FinMile | 04/07/2018 | 04/07/2018 | 29/05/2018 | 29/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UHA2-45 | red | PREPARATION BASIC BUILDING DWGS UHA | TT_Task | 15/02/2017 | 21/03/2017 | 02/02/2017 | 03/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UHA2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UHA | TT_FinMile | 02/03/2017 | 02/03/2017 | 15/02/2017 | 15/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2-00 | black | PRELIMINARY ERECTION CONCEPT HRSG | TT_Mile | 01/04/2017 | 01/04/2017 | 18/03/2017 | 18/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2-01 | black | FINAL ERECTION CONCEPT HRSG | TT_Mile | 01/06/2017 | 01/06/2017 | 13/05/2017 | 13/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2-10 | red | TECHNICAL CLARIFICATION WITH HRSG SUPPLIER | TT_Task | 05/11/2016 | 24/11/2016 | 10/09/2016 | 30/09/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2-72 | red | PROJECT SPECIFIC ADAPTION OF HRSG SPECIFICATION | TT_Task | 02/07/2016 | 28/07/2016 | 09/07/2016 | 05/08/2016 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 11/08/2016
SI1HA-2-73 | blue | COATING INSTRUCTION | TT_FinMile | 28/10/2016 | 28/10/2016 | 02/09/2016 | 02/09/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2-77 | red | OFFER PREPARATION BY HRSG SUPPLIER | TT_Task | 01/10/2016 | 03/11/2016 | 06/08/2016 | 09/09/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2-78 | black | HRSG OFFER AVAILABLE | TT_Mile | 05/11/2016 | 05/11/2016 | 10/09/2016 | 10/09/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2-85 | black | PARTIAL ORDER PLACED HRSG | TT_Mile | 03/11/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2-87 | black | ORDER PLACED HRSG | TT_Mile | 14/01/2017 | 14/01/2017 | 19/12/2016 | 19/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2A05 | black | GENERAL ARRANGMENT DWGS PRELIMINARY UHA | TT_Mile | 03/11/2016 | 03/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2A15 | blue | (MH3) FINAL DIMENSIONS AND LOADS AVAILABLE FOR HRSG | TT_FinMile | 14/02/2017 | 14/02/2017 | 31/01/2017 | 31/01/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2A60 | blue | (DF) FINAL INPUT FOR MS3 HRSG | TT_FinMile | 28/02/2017 | 28/02/2017 | 15/02/2017 | 15/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-3A05 | red | BASIC DESIGN MAIN STEEL STRUCTURE HRSG | TT_Task | 03/11/2016 | 07/02/2017 | 03/11/2016 | 15/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-3A25 | red | DETAIL DESIGN, MANUFACTURING MAIN STEEL STRUCTURE HRSG (Main Frame/Casing) | TT_Task | 01/03/2017 | 30/12/2017 | 16/02/2017 | 30/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-3A80 | black | (RFS) READY FOR SHIPMENT MAIN STEEL STRUCTURE HRSG (Main Frame/Casing) | TT_Mile | 03/03/2018 | 03/03/2018 | 31/01/2018 | 31/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-3A85 | black | EMBEDDED PARTS READY FOR SHIPMENT (Incl. STACK) | TT_Mile | 26/08/2017 | 26/08/2017 | 16/08/2017 | 16/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-3A90 | blue | (OTD-OS) HRSG EMBEDDED PARTS ON SITE (Incl. STACK) | TT_FinMile | 26/09/2017 | 26/09/2017 | 28/08/2017 | 28/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-4A42 | red | TRANSPORT MAIN STEEL STRUCTURE HRSG (Main Frame/Casing)) | TT_Task | 26/03/2018 | 30/03/2018 | 01/03/2018 | 08/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-4A44 | blue | (OTD-OS) ON SITE MAIN STEEL STRUCTURE HRSG (Main Frame/Casing) | TT_FinMile | 30/03/2018 | 30/03/2018 | 08/03/2018 | 08/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-3C25 | red | BASIC AND DETAIL DESIGN, MANUFACTURING STEEL STRUCTURE HRSG - SECONDARY STEEL | TT_Task | 26/06/2017 | 25/12/2017 | 15/06/2017 | 04/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-3C80 | black | (RFS) READY FOR SHIPMENT STEEL STRUCTURE HRSG - SECONDARY STEEL | TT_Mile | 06/06/2018 | 06/06/2018 | 13/04/2018 | 13/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-4C40 | blue | (OTD-OS) ON SITE STEEL STRUCTURE HRSG - SECONDARY STEEL | TT_FinMile | 13/06/2018 | 13/06/2018 | 31/05/2018 | 31/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-4C42 | red | TRANSPORT STEEL STRUCTURE HRSG - SECONDARY STEEL | TT_Task | 06/06/2018 | 13/06/2018 | 12/05/2018 | 31/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-2D60 | blue | FINAL INPUT FOR (MS3) STACK | TT_FinMile | 02/03/2017 | 02/03/2017 | 15/02/2017 | 15/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-3D05 | red | BASIC AND DETAIL DESIGN / ORDERING STEEL STRUCTURE HRSG - STACK | TT_Task | 24/11/2016 | 15/02/2017 | 24/11/2016 | 28/07/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 24/11/2016
SI1HB-3D25 | red | MANUFACTURING STEEL STRUCTURE HRSG - STACK | TT_Task | 16/12/2017 | 13/06/2018 | 30/11/2017 | 17/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-3D80 | black | (RFS) READY FOR SHIPMENT STEEL STRUCTURE HRSG - STACK | TT_Mile | 06/08/2018 | 06/08/2018 | 18/08/2018 | 18/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-4D40 | blue | (OTD-OS) ON SITE EXHAUST STACK HRSG | TT_FinMile | 24/08/2018 | 24/08/2018 | 30/08/2018 | 30/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-4D42 | red | TRANSPORT STEEL STRUCTURE HRSG - STACK | TT_Task | 06/08/2018 | 24/08/2018 | 21/08/2018 | 30/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-3E80 | black | (RFS) READY FOR SHIPMENT INLET &amp; OUTLET DUCT | TT_Mile | 26/03/2018 | 26/03/2018 | 30/01/2018 | 30/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-4E40 | blue | (OTD-OS) ON SITE INLET &amp; OUTLET DUCT | TT_FinMile | 30/03/2018 | 30/03/2018 | 08/03/2018 | 08/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HB-4E42 | red | TRANSPORT INLET &amp; OUTLET DUCT | TT_Task | 26/03/2018 | 30/03/2018 | 01/03/2018 | 08/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-3C80 | black | (RFS) READY FOR SHIPMENT MODULES | TT_Mile | 26/01/2018 | 26/01/2018 | 13/01/2018 | 13/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-4C42 | blue | (OTD-OS) ON SITE MODULES | TT_FinMile | 06/05/2018 | 06/05/2018 | 08/04/2018 | 08/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-4C44 | red | TRANSPORT MODULES | TT_Task | 26/03/2018 | 06/04/2018 | 14/03/2018 | 08/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-3D25 | red | DESIGN, MANUFACTURING, DELIVERY HRSG DRUMS | TT_Task | 03/11/2016 | 23/01/2018 | 03/11/2016 | 09/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-3D80 | black | (RFS) READY FOR SHIPMENT HRSG DRUMS | TT_Mile | 17/05/2018 | 17/05/2018 | 17/04/2018 | 17/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-4D42 | red | TRANSPORT HRSG DRUMS | TT_Task | 17/05/2018 | 27/05/2018 | 17/04/2018 | 26/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-4D44 | blue | (OTD-OS) ON SITE HRSG DRUMS | TT_FinMile | 27/05/2018 | 27/05/2018 | 26/04/2018 | 26/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2A11 | red | PROJECT SPECIFIC PRELIMINARY PIPE ROUTING AND SUPPORT CONCEPT HRSG | TT_Task | 03/11/2016 | 31/01/2017 | 03/11/2016 | 31/01/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2A40 | black | AGREED PIPING DESIGN BASIC REPORT (PDBR) | TT_Mile | 14/02/2017 | 14/02/2017 | 01/02/2017 | 01/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2A54 | red | STRESS ANALYSIS BY MTEC FOR HRSG-SYSTEMS LAB/LBA10/LBB/C | TT_Task | 14/02/2017 | 18/04/2017 | 01/02/2017 | 28/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2A55 | blue | PIPE STRESS ANALYSIS AND REPORT FOR HRSG SYSTEMS LAB/LBA10/LBB/LBC AVAILABLE | TT_FinMile | 30/04/2017 | 30/04/2017 | 28/04/2017 | 28/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2A56 | red | REVIEW PIPE STRESS CALCULATION FOR HRSG SYSTEMS LAB/LBA10/LBB/LBC | TT_Task | 01/05/2017 | 21/05/2017 | 29/04/2017 | 03/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2A65 | blue | (DF) FINAL INPUT FOR M2 HRSG | TT_FinMile | 05/08/2017 | 05/08/2017 | 07/07/2017 | 07/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2E15 | blue | PRELIMINARY PIPING DESIGN BASIC REPORT HRSG | TT_FinMile | 31/01/2017 | 31/01/2017 | 15/01/2017 | 15/01/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2E20 | blue | (DF) BASIC DESIGN PIPE ROUTING FOR HRSG SYSTEMS LAB/LBA10/LBB/LBC | TT_FinMile | 05/08/2017 | 05/08/2017 | 07/07/2017 | 07/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HAD3E25 | red | BASIC DESIGN, DETAIL DESIGN, ORDERING, DELIVERY, MANUFACTURING PIPING MATERIAL HRSG | TT_Task | 14/02/2017 | 01/05/2018 | 01/02/2017 | 25/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HAD3E80 | black | (RFS) READY FOR SHIPMENT PIPING MATERIAL HRSG | TT_Mile | 06/07/2018 | 06/07/2018 | 26/06/2018 | 26/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HAD4E42 | red | TRANSPORT PIPING MATERIAL HRSG | TT_Task | 06/07/2018 | 25/07/2018 | 23/07/2018 | 18/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HAD4E44 | blue | (OTD-OS) ON SITE PIPING MATERIAL HRSG | TT_FinMile | 25/07/2018 | 25/07/2018 | 18/08/2018 | 18/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1CJF2-80 | red | BASIC DESIGN,QUOTATION STAGE, ODERING ELECTRICAL AND I&amp;C-EQUIPMENT FOR HRSG | TT_Task | 10/06/2017 | 09/10/2017 | 07/05/2017 | 02/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1CJF3-25 | red | DETAIL DESIGN, MANUFACTURING ELECTRICAL AND I&amp;C-EQUIPMENT FOR HRSG | TT_Task | 02/11/2017 | 29/04/2018 | 03/10/2017 | 15/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1CJF3-80 | black | (RFS) READY FOR SHIPMENT ELECTRICAL AND I&amp;C-EQUIPMENT FOR HRSG | TT_Mile | 06/07/2018 | 06/07/2018 | 16/06/2018 | 16/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1CJF4-40 | blue | (OTD-OS) ON SITE ELECTRICAL AND I&amp;C-EQUIPMENT FOR HRSG | TT_FinMile | 08/08/2018 | 08/08/2018 | 31/07/2018 | 31/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1CJF4-42 | red | TRANSPORT ELECTRICAL AND I&amp;C-EQUIPMENT FOR HRSG | TT_Task | 06/07/2018 | 08/08/2018 | 25/06/2018 | 31/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2-31 | blue | DATA INPUT HRSG COMPLETED FOR I&amp;C DESIGN | TT_FinMile | 25/06/2017 | 25/06/2017 | 09/06/2017 | 09/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HA-2-70 | blue | (DF) I&amp;C DATA FOR HRSG | TT_FinMile | 02/10/2017 | 02/10/2017 | 05/09/2017 | 05/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UHW2-45 | red | PREPARATION BASIC BUILDING DWGS UHW | TT_Task | 10/03/2017 | 13/04/2017 | 23/02/2017 | 29/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UHW2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UHW | TT_FinMile | 28/04/2017 | 28/04/2017 | 21/03/2017 | 21/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UHW2B60 | black | (MS3) STEEL STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE UHW | TT_Mile | 25/07/2017 | 25/07/2017 | 24/07/2017 | 24/07/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 24/07/2017
SI1UHW2B70 | red | DETAIL DESIGN / CHECKER STEEL STRUCTURE UHW | TT_Task | 25/07/2017 | 18/09/2017 | 24/07/2017 | 09/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UHW2B75 | black | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR UHW | TT_Mile | 26/01/2018 | 26/01/2018 | 29/12/2017 | 29/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UHW3B27 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL STRUCTURE UHW | TT_Task | 26/01/2018 | 27/05/2018 | 29/12/2017 | 27/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LBH2D80 | red | BASIC DESIGN, QUOTATION STAGE, ORDERING CLEAN DRAIN FLASH TANK LBH | TT_Task | 26/11/2016 | 17/03/2017 | 17/11/2016 | 28/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LBH3D25 | red | DETAIL DESIGN, MANUFTURING CLEAN DRAIN FLASH TANK LBH | TT_Task | 29/05/2017 | 10/04/2018 | 29/04/2017 | 12/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LBH3D80 | blue | (RFS) READY FOR SHIPMENT CLEAN DRAIN FLASH TANK LBH | TT_FinMile | 26/05/2018 | 26/05/2018 | 13/06/2018 | 13/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LBH4D40 | blue | (OTD-OS) ON SITE CLEAN DRAIN FLASH TANK LBH | TT_FinMile | 22/07/2018 | 22/07/2018 | 25/07/2018 | 25/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LBH4D42 | red | TRANSPORT CLEAN DRAIN FLASH TANK LBH | TT_Task | 27/05/2018 | 22/07/2018 | 14/06/2018 | 25/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LCL3B25 | red | DETAIL DESIGN, MANUFACTURING, SHOP TEST STEAM GENERATOR DRAIN PUMP LCL | TT_Task | 26/06/2017 | 09/02/2018 | 02/06/2017 | 11/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LCL3B80 | blue | (RFS) READY FOR SHIPMENT STEAM GENERATOR DRAIN PUMP LCL | TT_FinMile | 25/02/2018 | 25/02/2018 | 15/01/2018 | 15/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LCL4B25 | red | TRANSPORT STEAM GENERATOR DRAIN PUMP LCL | TT_Task | 26/02/2018 | 02/04/2018 | 08/02/2018 | 15/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LCL4B42 | blue | (OTD-OS) ON SITE STEAM GENERATOR DRAIN PUMP LCL | TT_FinMile | 13/04/2018 | 13/04/2018 | 15/03/2018 | 15/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1ULA2-45 | red | PREPARATION BASIC BUILDING DWGS ULA | TT_Task | 15/05/2017 | 18/06/2017 | 10/04/2017 | 30/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1ULA2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE ULA | TT_FinMile | 29/05/2017 | 29/05/2017 | 23/04/2017 | 23/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1ULA2B60 | blue | (MS3) STEEL STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE ULA | TT_FinMile | 25/06/2017 | 25/06/2017 | 02/06/2017 | 02/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1ULA2B70 | red | DETAIL DESIGN / CHECKER STEEL STRUCTURE ULA | TT_Task | 26/06/2017 | 27/08/2017 | 02/06/2017 | 27/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1ULA2B75 | black | (F) DETAIL DESIGN STEEL STRUCTURE WITH CONTRACTOR ULA | TT_Mile | 26/01/2018 | 26/01/2018 | 29/12/2017 | 29/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1ULA3B27 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL STRUCTURE ULA | TT_Task | 26/01/2018 | 12/06/2018 | 29/12/2017 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BZP2E30 | red | DETAIL DESIGN CABLE SUPPORT SYSTEM ULA | TT_Task | 17/07/2017 | 10/09/2017 | 23/06/2017 | 24/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LCA2B14 | black | CONFIRMED PUMP CURVES COND.RECIRC.PUMP LCA51 | TT_Mile | 01/06/2017 | 01/06/2017 | 19/05/2017 | 19/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LCA2B60 | blue | (DF) FINAL INPUT FOR MS3 COND. RECIRC.PUMP LCA51 | TT_FinMile | 25/06/2017 | 25/06/2017 | 08/06/2017 | 08/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LCA2B65 | blue | (DF) FINAL INPUT FOR M2 COND.RECIRC.PUMP LCA51 | TT_FinMile | 25/06/2017 | 25/06/2017 | 08/06/2017 | 08/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LCA2B75 | red | CONTRACT REVIEW, PREPARATION RFQ CONDENSATE RECIRC.PUMP LCA51 | TT_Task | 14/01/2017 | 28/02/2017 | 15/12/2016 | 23/01/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 15/12/2016
SI1LCA2B80 | red | QUOTATION STAGE CONDENSATE RECIRC.PUMP LCA51 | TT_Task | 01/02/2017 | 17/03/2017 | 24/01/2017 | 18/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LCA2B85 | black | ORDER PLACED CONDENSATE RECIRCULATING PUMP LCA51 (MPA) | TT_Mile | 15/06/2017 | 15/06/2017 | 19/05/2017 | 19/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LCA3B25 | red | MANUFACTURING, SHOP TEST CONDENSATE RECIRCULATION PUMP LCA51 | TT_Task | 01/06/2017 | 08/01/2018 | 19/05/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LCA3B80 | blue | (RFS) READY FOR SHIPMENT COND.RECIRC. PUMP LCA51 | TT_FinMile | 26/01/2018 | 26/01/2018 | 02/01/2018 | 02/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LCA4B27 | red | TRANSPORT CONDENSATE RECIRCULATING PUMP LCA51 | TT_Task | 26/01/2018 | 15/03/2018 | 02/01/2018 | 10/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LCA2-10 | red | DETAIL DESIGN LCA50Y MODULE | TT_Task | 01/06/2017 | 09/11/2017 | 20/05/2017 | 28/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LCA3-10 | red | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL LCA50Y MODULE | TT_Task | 29/11/2017 | 04/03/2018 | 29/10/2017 | 01/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LCA3-20 | blue | DELIVERY OF COMPONENTS LCA50Y MODULE | TT_FinMile | 22/03/2018 | 22/03/2018 | 19/02/2018 | 19/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LCA3-25 | red | MANUFACTURING LCA50Y MODULE | TT_Task | 05/03/2018 | 16/05/2018 | 02/02/2018 | 31/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LCA4-25 | red | TRANSPORT LCA50Y MODULE | TT_Task | 20/09/2018 | 05/10/2018 | 18/06/2018 | 25/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LCA4-42 | blue | (OTD-OS) ON SITE LCA50Y MODULE | TT_FinMile | 05/10/2018 | 05/10/2018 | 25/06/2018 | 25/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC2B14 | black | CONFIRMED PUMP CURVES FEEDWATER PUMP LAC | TT_Mile | 26/11/2016 | 26/11/2016 | 03/11/2016 | 03/11/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC2B60 | blue | (DF) FINAL INPUT FOR MS3 FEEDWATER PUMP LAC | TT_FinMile | 31/03/2017 | 31/03/2017 | 15/03/2017 | 15/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC2B65 | blue | (DF) FINAL INPUT FOR M2 FEEDWATER PUMP LAC | TT_FinMile | 31/03/2017 | 31/03/2017 | 15/03/2017 | 15/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC2B75 | red | CONTRACT REVIEW, PREPARATION RFQ FEEDWATER PUMP LAC | TT_Task | 26/11/2016 | 08/01/2017 | 03/11/2016 | 16/12/2016 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC2B80 | red | QUOTATION STAGE FEEDWATER PUMP LAC (MPA) | TT_Task | 21/01/2017 | 17/02/2017 | 17/12/2016 | 13/01/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC2B85 | black | ORDER PLACED FEEDWATER PUMP LAC | TT_Mile | 17/02/2017 | 17/02/2017 | 14/02/2017 | 14/02/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC3B25 | red | DETAIL DESIGN, MANUFACTURING, SHOP TEST FEEDWATER PUMP LAC | TT_Task | 01/03/2017 | 04/12/2017 | 14/02/2017 | 19/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC3B80 | blue | (RFS) READY FOR SHIPMENT FEEDWATER PUMP LAC | TT_FinMile | 25/11/2017 | 25/11/2017 | 24/11/2017 | 24/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC4B25 | red | TRANSPORT FEEDWATER PUMP LAC | TT_Task | 26/11/2017 | 13/01/2018 | 12/12/2017 | 05/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC2-10 | red | DETAIL DESIGN LAC10Y MODULE | TT_Task | 16/03/2017 | 28/08/2017 | 14/03/2017 | 26/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC3-10 | red | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL LAC10Y MODULE | TT_Task | 27/09/2017 | 20/12/2017 | 27/08/2017 | 19/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC3-20 | blue | DELIVERY OF COMPONENTS LAC10Y MODULE | TT_FinMile | 05/03/2018 | 05/03/2018 | 02/02/2018 | 02/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC3-25 | red | MANUFACTURING LAC10Y MODULE | TT_Task | 17/12/2017 | 12/05/2018 | 16/11/2017 | 31/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC4-25 | red | TRANSPORT LAC10Y MODULE | TT_Task | 20/09/2018 | 05/10/2018 | 18/06/2018 | 25/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1LAC4-42 | blue | (OTD-OS) ON SITE LAC10Y MODULE | TT_FinMile | 05/10/2018 | 05/10/2018 | 25/06/2018 | 25/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1QC-3-25 | red | DESIGN, MANUFACTURING, SHOP TEST DOSING CONTAINER QC | TT_Task | 04/06/2017 | 11/10/2017 | 11/05/2017 | 17/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1QC-3-80 | blue | (RFS) READY FOR SHIPMENT DOSING CONTAINER QC | TT_FinMile | 24/08/2018 | 24/08/2018 | 18/05/2018 | 18/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1QC-4-25 | red | TRANSPORT DOSING CONTAINER QC | TT_Task | 25/08/2018 | 12/10/2018 | 25/05/2018 | 07/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1QC-4-42 | blue | (OTD-OS) ON SITE DOSING CONTAINER QC | TT_FinMile | 12/10/2018 | 12/10/2018 | 07/07/2018 | 07/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1QU-3-25 | red | DESIGN, MANUFACTURING, SHOP TEST SAMPLING CONTAINER QU | TT_Task | 05/06/2017 | 21/11/2017 | 11/05/2017 | 06/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1QU-3-80 | blue | (RFS) READY FOR SHIPMENT SAMPLING CONTAINER QU | TT_FinMile | 04/10/2018 | 04/10/2018 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1QU-4-25 | red | TRANSPORT SAMPLING CONTAINER QU | TT_Task | 05/10/2018 | 22/11/2018 | 02/09/2018 | 06/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1QU-4-42 | blue | (OTD-OS) ON SITE SAMPLING CONTAINER QU | TT_FinMile | 22/11/2018 | 22/11/2018 | 06/10/2018 | 06/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMY2-45 | red | PREPARATION BASIC BUILDING DWGS UMY | TT_Task | 26/06/2017 | 30/07/2017 | 02/06/2017 | 21/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMY2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UMY | TT_FinMile | 25/06/2017 | 25/06/2017 | 15/06/2017 | 15/06/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 15/06/2017
SI1UMY3-60 | red | FABRICATION DESIGN, FABRICATION, TRANSPORT, ON SITE STEEL STRUCTURE UMY | TT_Task | 26/01/2018 | 27/05/2018 | 29/12/2017 | 15/09/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMY2B60 | blue | (MS3) STEEL STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE UMY00Y | TT_FinMile | 31/05/2017 | 31/05/2017 | 12/05/2017 | 12/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMY2B70 | red | DETAIL DESIGN / CHECKER STEEL STRUCTURE UMY00Y | TT_Task | 02/06/2017 | 25/11/2017 | 13/05/2017 | 25/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UMY3-29 | red | MANUFACTURING UMY00Y MODULE | TT_Task | 01/08/2018 | 06/10/2018 | 26/04/2018 | 06/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMY3B25 | red | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL UMY00Y MODULE | TT_Task | 05/02/2018 | 02/05/2018 | 26/12/2017 | 23/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMY4-44 | blue | (OTD-OS) ON SITE UMY00Y MODULE | TT_FinMile | 05/11/2018 | 05/11/2018 | 05/11/2018 | 05/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UMY4B30 | red | TRANSPORT STEEL STRUCTURE UMY00Y | TT_Task | 22/10/2018 | 05/11/2018 | 17/10/2018 | 05/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BZP2D30 | red | DETAIL DESIGN CABLE SUPPORT SYSTEM UMY | TT_Task | 23/10/2017 | 17/12/2017 | 22/09/2017 | 16/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UHX2-45 | red | PREPARATION BASIC BUILDING DWGS UHX | TT_Task | 26/08/2017 | 29/09/2017 | 25/08/2017 | 24/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UHX2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UHX | TT_FinMile | 25/09/2017 | 25/09/2017 | 30/08/2017 | 30/08/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 30/08/2017
SI1UTX2-45 | red | PREPARATION BASIC BUILDING DWGS UTX | TT_Task | 02/11/2017 | 06/12/2017 | 25/09/2017 | 18/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UTX2-60 | black | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UTX | TT_Mile | 16/11/2017 | 16/11/2017 | 30/09/2017 | 30/09/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 16/11/2017
SI1UVM2-45 | red | PREPARATION BASIC BUILDING DWGS SCR UNIT | TT_Task | 01/05/2017 | 04/06/2017 | 29/04/2017 | 30/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UVM2-50 | red | PREPARATION FOUNDATION GROUNDING DWGS SCR UNIT | TT_Task | 01/05/2017 | 14/05/2017 | 29/04/2017 | 12/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UVM2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE SCR UNIT | TT_FinMile | 16/06/2017 | 16/06/2017 | 12/05/2017 | 12/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1HSJ3-25 | red | DESIGN, MANUFACTURING, SHOP TEST SCR UNIT | TT_Task | 15/05/2017 | 08/03/2018 | 15/04/2017 | 15/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HSJ3-80 | blue | (RFS) READY FOR SHIPMENT SCR UNIT | TT_FinMile | 04/09/2018 | 04/09/2018 | 16/06/2018 | 16/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HSJ3-85 | blue | (RFS) READY FOR SHIPMENT SCR CATALYST | TT_FinMile | 04/11/2018 | 04/11/2018 | 30/08/2018 | 30/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HSJ4-40 | blue | (OTD-OS) ON SITE SCR UNIT | TT_FinMile | 03/11/2018 | 03/11/2018 | 26/10/2018 | 26/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HSJ4-44 | red | TRANSPORT SCR UNIT | TT_Task | 05/09/2018 | 03/11/2018 | 18/07/2018 | 26/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1HSJ4-46 | red | TRANSPORT SCR CATALYST | TT_Task | 05/11/2018 | 03/01/2019 | 27/01/2019 | 21/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SI1HSJ4-48 | blue | (OTD-OS) ON SITE SCR CATALYST | TT_FinMile | 03/01/2019 | 03/01/2019 | 21/02/2019 | 21/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SI1--P3-25 | red | DETAIL DESIGN, SUPPLY, PREFAB., SHOP TEST STANDARD PIPING SUPPORT PARTS ALL SIZES | TT_Task | 26/08/2017 | 05/02/2018 | 04/08/2017 | 14/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1--P3A35 | red | PREFABRICATION, SHOP TEST ALLOYED AND OTHER PIPING MATERIAL (DN&gt;=80) ALL SIZES | TT_Task | 29/11/2017 | 23/01/2018 | 20/11/2017 | 02/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1--P3A50 | black | ON SITE FINAL ISOs &gt;= 80 / SUPPORT PARTS ALL SIZES | TT_Mile | 26/03/2018 | 26/03/2018 | 03/03/2018 | 03/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1--P4A25 | red | TRANSPORT (1ST) PIPING (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | TT_Task | 26/03/2018 | 08/04/2018 | 20/03/2018 | 10/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1--P4A42 | red | TRANSPORT (2ND) PIPING (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | TT_Task | 12/03/2019 | 25/03/2019 | 20/04/2018 | 02/05/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 09/04/2018
SI1--P4A44 | black | ON SITE (2ND) PIPES (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | TT_Mile | 02/05/2018 | 02/05/2018 | 02/05/2018 | 02/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1--P4A46 | red | TRANSPORT (3RD) PIPING (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | TT_Task | 14/05/2018 | 27/05/2018 | 04/07/2018 | 13/07/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 14/05/2018
SI1--P4A48 | black | ON SITE (3RD) PIPES (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | TT_Mile | 28/05/2018 | 28/05/2018 | 13/07/2018 | 13/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1--P4A50 | red | TRANSPORT (4TH) PIPING (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | TT_Task | 03/06/2018 | 16/06/2018 | 16/07/2018 | 20/07/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 03/06/2018
SI1--P4A52 | black | ON SITE (4TH) PIPES (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | TT_Mile | 17/06/2018 | 17/06/2018 | 20/07/2018 | 20/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1--P4A54 | black | ON SITE (1ST) PIPES (DN &gt;=80) AND STANDARD SUPPORT PARTS ALL SIZES | TT_Mile | 12/03/2019 | 12/03/2019 | 10/04/2018 | 10/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1--P3H25 | red | DETAIL DESIGN, SUPPLY, SHOP TEST PIPING (DN &lt;80) AND SECONDARY STEEL ALL SIZES | TT_Task | 26/08/2017 | 28/01/2018 | 26/07/2017 | 29/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1--P3H50 | black | ON SITE FINAL ISOs &lt; 80 | TT_Mile | 26/02/2018 | 26/02/2018 | 18/02/2018 | 18/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1--P4H25 | red | TRANSPORT (1ST) PIPING (DN &lt;80) | TT_Task | 02/05/2018 | 08/05/2018 | 30/03/2018 | 10/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1--P4H42 | red | TRANSPORT (2ND) PIPING (DN &lt;80) | TT_Task | 14/05/2018 | 27/05/2018 | 22/04/2018 | 02/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1--P4H44 | black | ON SITE PIPES (2ND) (DN &lt;80) | TT_Mile | 28/05/2018 | 28/05/2018 | 02/05/2018 | 02/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1--P4H46 | black | ON SITE PIPES (1ST) (DN &lt;80) | TT_Mile | 09/05/2018 | 09/05/2018 | 10/04/2018 | 10/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0--P4E10 | red | TRANSPORT TO PREFABRICATION SHOP (ALLOYED MATERIAL) | TT_Task | 31/10/2017 | 27/11/2017 | 01/10/2017 | 28/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0--P4A10 | red | TRANSPORT TO PREFABRICATION SHOP (NON-ALLOYED MATERIALS) | TT_Task | 09/10/2017 | 12/11/2017 | 08/09/2017 | 12/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0--P4A15 | red | TRANSPORT TO PREFABRICATION SHOP (GRP MATERIALS) | TT_Task | 17/11/2017 | 04/01/2018 | 18/10/2017 | 25/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI---P4I25 | red | TRANSPORT VALVES | TT_Task | 05/03/2018 | 18/03/2018 | 02/02/2018 | 23/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI---P4I42 | blue | (OTD-OS) ON SITE VALVES | TT_FinMile | 11/03/2018 | 11/03/2018 | 23/02/2018 | 23/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-ZTB4A27 | red | TRANSPORT PIPING FOR STEAM BLOWING SYSTEM ZTB | TT_Task | 02/05/2018 | 19/06/2018 | 16/11/2018 | 23/11/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 28/04/2018
SI1UPY2-10 | red | DETAIL DESIGN UPY00Y MODULE | TT_Task | 26/06/2017 | 03/12/2017 | 05/06/2017 | 17/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UPY2B77 | blue | (MS3) STEEL STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE UPY00Y | TT_FinMile | 25/06/2017 | 25/06/2017 | 07/06/2017 | 07/06/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 07/06/2017
SI1UPY3-10 | red | DELIVERY OF SKID FRAME STEEL, PIPING MATERIAL UPY00Y MODULE | TT_Task | 19/12/2017 | 24/03/2018 | 18/11/2017 | 21/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UPY3-20 | blue | DELIVERY OF COMPONENTS UPY00Y MODULE | TT_FinMile | 26/02/2018 | 26/02/2018 | 26/01/2018 | 26/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UPY3-25 | red | MANUFACTURING UPY00Y MODULE | TT_Task | 25/03/2018 | 01/07/2018 | 22/02/2018 | 15/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UPY4-25 | red | TRANSPORT UPY00Y MODULE | TT_Task | 23/07/2018 | 06/08/2018 | 23/11/2018 | 30/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1UPY4-42 | blue | (OTD-OS) ON SITE UPY00Y MODULE | TT_FinMile | 06/08/2018 | 06/08/2018 | 30/11/2018 | 30/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1BZP2G30 | red | DETAIL DESIGN CABLE SUPPORT SYSTEM UQA ELECTRICAL ROOM | TT_Task | 26/06/2017 | 06/08/2017 | 02/06/2017 | 24/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UQA2E77 | red | PREPARATION BASIC BUILDING DWGS 10UQA | TT_Task | 03/05/2017 | 06/06/2017 | 01/04/2017 | 28/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1UQA2E79 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE 10UQA | TT_FinMile | 16/05/2017 | 16/05/2017 | 15/04/2017 | 15/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PBB2B100 | black | ORDER PLACED DEBRIS FILTER PBB | TT_Mile | 15/05/2017 | 15/05/2017 | 22/04/2017 | 22/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PBB2B105 | blue | (DF) FINAL INPUT FOR M2 DEBRIS FILTER PBB | TT_FinMile | 31/05/2017 | 31/05/2017 | 06/05/2017 | 06/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PBB2B110 | blue | (DF) FINAL INPUT FOR MS3 DEBRIS FILTER PBB | TT_FinMile | 06/05/2017 | 06/05/2017 | 29/04/2017 | 29/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PBB2B90 | red | CONTRACT REVIEW, PREPARATION RFQ DEBRIS FILTER PBB | TT_Task | 14/01/2017 | 10/02/2017 | 19/12/2016 | 15/01/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PBB2B95 | red | QUOTATION STAGE DEBRIS FILTER PBB | TT_Task | 05/03/2017 | 18/03/2017 | 26/01/2017 | 21/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PBB3B85 | red | DETAIL DESIGN, MANUFACTURING, SHOP TEST DEBRIS FILTER PBB | TT_Task | 15/05/2017 | 05/02/2018 | 23/04/2017 | 18/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PBB3B90 | blue | (RFS) READY FOR SHIPMENT DEBRIS FILTER PBB | TT_FinMile | 26/01/2018 | 26/01/2018 | 18/12/2017 | 18/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1PBB4B47 | red | TRANSPORT DEBRIS FILTER PBB | TT_Task | 26/01/2018 | 15/03/2018 | 19/12/2017 | 17/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PAC3B25 | red | DETAIL DESIGN, MANUFACTURING, SHOP TEST CIRC. CW PUMP PAC | TT_Task | 06/05/2017 | 23/06/2018 | 16/04/2017 | 22/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PAC3B80 | blue | (RFS) READY FOR SHIPMENT CIRC. CW PUMP PAC | TT_FinMile | 30/06/2018 | 30/06/2018 | 30/05/2018 | 30/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PAC4B25 | red | TRANSPORT CIRC. CW PUMP PAC | TT_Task | 01/07/2018 | 18/08/2018 | 09/06/2018 | 07/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PAC4B42 | blue | (OTD-OS) ON SITE CIRC. CW PUMP PAC | TT_FinMile | 18/08/2018 | 18/08/2018 | 07/07/2018 | 07/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PAC4E42 | blue | (OTD-OS) ON SITE EMBEDDED PARTS PUMP PAC | TT_FinMile | 18/08/2018 | 18/08/2018 | 07/07/2018 | 07/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1SMQ3A85 | red | FABRICATION DESIGN, MANUFACTURING, SHOP TEST CRANE SMQ FOR UQA | TT_Task | 25/07/2017 | 22/01/2018 | 19/07/2017 | 28/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1SMQ3A90 | blue | (RFS) READY FOR SHIPMENT CRANE SMQ FOR UQA | TT_FinMile | 28/03/2018 | 28/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1SMQ4A47 | red | TRANSPORT CRANE SMQ FOR UQA | TT_Task | 17/04/2018 | 10/05/2018 | 22/03/2018 | 23/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1SMQ4A50 | blue | (OTD-OS) ON SITE CRANE SMQ FOR UQA | TT_FinMile | 25/05/2018 | 25/05/2018 | 23/04/2018 | 23/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PAA3-25 | red | DETAIL DESIGN, MANUFACTURING CW BAR SCREEN FOR PAB SYSTEM | TT_Task | 26/11/2017 | 23/04/2018 | 26/10/2017 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PAA3-80 | blue | (RFS) READY FOR SHIPMENT CW BAR SCREEN FOR PAB SYSTEM | TT_FinMile | 26/03/2018 | 26/03/2018 | 23/03/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PAA4-52 | red | TRANSPORT CW BAR SCREEN FOR PAB SYSTEM | TT_Task | 02/05/2018 | 15/05/2018 | 23/05/2018 | 28/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1PAA4-54 | blue | (OTD-OS) ON SITE CW BAR SCREEN FOR PAB SYSTEM | TT_FinMile | 15/05/2018 | 15/05/2018 | 28/05/2018 | 28/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0GN-3B82 | red | DETAIL DESIGN, MANUFACTURING, SHOP TEST PROCESS DRAINS TREATMENT GN- | TT_Task | 08/08/2017 | 29/03/2018 | 12/07/2017 | 18/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0GN-3B84 | blue | (RFS) READY FOR SHIPMENT PROCESS DRAINS TREATMENT GN- | TT_FinMile | 25/05/2018 | 25/05/2018 | 30/05/2018 | 30/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0GN-4B42 | red | TRANSPORT PROCESS DRAINS TREATMENT GN- | TT_Task | 26/05/2018 | 24/07/2018 | 10/06/2018 | 16/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0GN-4B46 | blue | (OTD-OS) ON SITE PROCESS DRAINS TREATMENT GN- | TT_FinMile | 24/07/2018 | 24/07/2018 | 16/07/2018 | 16/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1USV2-79 | black | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE USV | TT_Mile | 03/07/2017 | 03/07/2017 | 02/06/2017 | 02/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI1STG-3-82 | red | DESIGN, MANUFACTURING, SHOP TEST LABORATORY CONTAINER STG | TT_Task | 26/10/2017 | 08/04/2018 | 25/09/2017 | 07/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1STG-3-84 | blue | (RFS) READY FOR SHIPMENT LABORATORY CONTAINER STG | TT_FinMile | 01/07/2018 | 01/07/2018 | 25/08/2018 | 25/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1STG-4-42 | red | TRANSPORT LABORATORY CONTAINER STG | TT_Task | 02/07/2018 | 19/08/2018 | 26/08/2018 | 08/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SI1STG-4-46 | blue | (OTD-OS) ON SITE LABORATORY CONTAINER STG | TT_FinMile | 19/08/2018 | 19/08/2018 | 08/10/2018 | 08/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0UEN2-45 | red | PREPARATION BASIC BUILDING DWGS 00UEN | TT_Task | 26/06/2017 | 30/07/2017 | 17/06/2017 | 30/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0UEN2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE 00UEN | TT_FinMile | 25/07/2017 | 25/07/2017 | 25/06/2017 | 25/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0UGY2-45 | red | PREPARATION BASIC BUILDING DWGS UGY | TT_Task | 26/08/2017 | 29/09/2017 | 25/08/2017 | 24/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0UGY2-60 | blue | (MS3) CONCRETE STRUCTURE FINAL DIMENSIONS LOADS AVAILABLE UGY | TT_FinMile | 25/09/2017 | 25/09/2017 | 27/08/2017 | 27/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0UGY2B60 | blue | (MS3) STEEL STRUCTURE, FINAL DIMENSIONS AND LOADS AVAILABLE UGY | TT_FinMile | 25/06/2017 | 25/06/2017 | 01/06/2017 | 01/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0UGY2B70 | red | DETAIL DESIGN / CHECKER STEEL STRUCTURE UGY | TT_Task | 08/08/2017 | 02/10/2017 | 10/07/2017 | 15/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0BZP2B30 | red | DETAIL DESIGN CABLE SUPPORT SYSTEM UCA | TT_Task | 01/03/2017 | 11/04/2017 | 21/02/2017 | 03/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0ACA3-25 | red | MANUFACTURING, SHOP TEST HV-SWITCHGEAR GIL | TT_Task | 14/04/2017 | 30/03/2018 | 30/03/2017 | 09/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0ACA3-85 | blue | (RFS) READY FOR SHIPMENT HV-SWITCHGEAR GIL | TT_FinMile | 06/05/2018 | 06/05/2018 | 30/03/2018 | 30/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0ACA3-87 | red | PACKING HV-SWITCHGEAR GIL | TT_Task | 07/04/2018 | 06/05/2018 | 10/03/2018 | 30/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0ACA4-57 | red | TRANSPORT HV-SWITCHGEAR GIL | TT_Task | 07/05/2018 | 04/06/2018 | 01/06/2018 | 10/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0ACA4-59 | blue | (OTD-OS) ON SITE HV-SWITCHGEAR GIL | TT_FinMile | 05/06/2018 | 05/06/2018 | 10/07/2018 | 10/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CYE2-20 | red | (BOP) TECHNICAL CLARIFICATION FIRE ALARM SYSTEM CYE | TT_Task | 14/01/2017 | 10/02/2017 | 10/12/2016 | 06/01/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-CYE2-25 | red | (BOP) BASIC DESIGN, SPECIFICATION FIRE ALARM SYSTEM CYE | TT_Task | 14/01/2017 | 10/02/2017 | 07/01/2017 | 22/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-CYE2-30 | blue | (BOP) RFQ FIRE ALARM SYSTEM CYE | TT_FinMile | 30/04/2017 | 30/04/2017 | 31/03/2017 | 31/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-CYE2-35 | red | (BOP) QUOTATION STAGE FIRE ALARM SYSTEM CYE | TT_Task | 17/05/2017 | 25/06/2017 | 01/04/2017 | 19/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-CYE2-40 | black | (BOP) ORDER PLACED FIRE ALARM SYSTEM CYE | TT_Mile | 26/08/2017 | 26/08/2017 | 18/08/2017 | 18/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-CYE3-90 | red | (BOP) MANUFACTURING, SHOP TEST FIRE ALARM SYSTEM CYE | TT_Task | 26/08/2017 | 07/01/2018 | 18/08/2017 | 17/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CYE3-92 | blue | (BOP) (RFS) READY FOR SHIPMENT FIRE ALARM SYSTEM CYE | TT_FinMile | 01/03/2018 | 01/03/2018 | 23/02/2018 | 23/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-CYE4-60 | red | (BOP) TRANSPORT FIRE ALARM SYSTEM CYE | TT_Task | 02/03/2018 | 06/03/2018 | 24/02/2018 | 28/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-SG-2-10 | black | (BOP) ORDER PLACED FIRE FIGHTING SYSTEM SG | TT_Mile | 26/08/2017 | 26/08/2017 | 18/08/2017 | 18/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-SG-2-95 | red | (BOP) TECHNICAL CLARIFICATION FIRE FIGHTING SYSTEM SG | TT_Task | 01/03/2017 | 28/03/2017 | 25/02/2017 | 24/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-SG-2-96 | red | (BOP) BASIC DESIGN, SPECIFICATION FIRE FIGHTING SYSTEM SG | TT_Task | 01/04/2017 | 14/04/2017 | 25/03/2017 | 07/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-SG-2-97 | blue | (BOP) RFQ FIRE FIGHTING SYSTEM SG | TT_FinMile | 21/05/2017 | 21/05/2017 | 31/03/2017 | 31/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-SG-2-99 | red | (BOP) QUOTATION STAGE FIRE FIGHTING SYSTEM SG | TT_Task | 22/05/2017 | 30/06/2017 | 01/04/2017 | 19/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-SG-3-86 | red | (BOP) MANUFACTURING, SHOP TEST FIRE FIGHTING SYSTEM SG | TT_Task | 26/08/2017 | 07/01/2018 | 18/08/2017 | 15/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-SG-3-88 | blue | (BOP) (RFS) READY FOR SHIPMENT FIRE FIGHTING SYSTEM SG | TT_FinMile | 05/07/2018 | 05/07/2018 | 16/08/2018 | 16/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-SG-4-58 | red | (BOP) TRANSPORT FIRE FIGHTING SYSTEM SG | TT_Task | 06/07/2018 | 30/08/2018 | 17/08/2018 | 21/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-2-87 | red | (BOP) BASIC DESIGN, PREPARATION RFQ FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | TT_Task | 01/04/2017 | 26/05/2017 | 18/03/2017 | 12/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-2-89 | red | (BOP) QUOTATION STAGE FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | TT_Task | 13/06/2017 | 03/07/2017 | 13/05/2017 | 02/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-2-91 | black | (BOP) ORDER PLACED FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | TT_Mile | 28/06/2017 | 28/06/2017 | 03/06/2017 | 03/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-2-97 | red | (BOP) TECHNICAL CLARIFICATION FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | TT_Task | 01/02/2017 | 28/03/2017 | 21/01/2017 | 17/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-3-82 | red | (BOP) DETAIL DESIGN, MANUFACTURING FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | TT_Task | 26/06/2017 | 21/04/2018 | 03/06/2017 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-3-86 | blue | (BOP) (RFS) READY FOR SHIPMENT GAS SYSTEM EK (Add. ISOLATING VALVES ONLY) | TT_FinMile | 05/05/2018 | 05/05/2018 | 29/03/2018 | 29/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-4-42 | red | (BOP) TRANSPORT FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | TT_Task | 06/05/2018 | 04/07/2018 | 22/04/2018 | 29/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-EK-4-48 | blue | (OTD-OS) (BOP) ON SITE FUEL GAS SUPPLY SYSTEM EK (Add. ISOLATING VALVES ONLY) | TT_FinMile | 04/07/2018 | 04/07/2018 | 29/05/2018 | 29/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZK2-135 | red | (BOP) BASIC DESIGN, SPECIFICATION MV CABLES BZK | TT_Task | 20/05/2017 | 16/06/2017 | 20/04/2017 | 17/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-BZK2-87 | red | (BOP) TECHNICAL CLARIFICATION MV CABLES BZK | TT_Task | 01/04/2017 | 28/04/2017 | 23/03/2017 | 19/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-BZK2-89 | blue | (BOP) RFQ MV CABLES BZK | TT_FinMile | 17/06/2017 | 17/06/2017 | 17/05/2017 | 17/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-BZK2-91 | red | (BOP) QUOTATION STAGE MV CABLES BZK | TT_Task | 18/06/2017 | 29/07/2017 | 18/05/2017 | 24/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-BZK2-93 | black | (BOP) ORDER PLACED MV CABLES BZK | TT_Mile | 26/08/2017 | 26/08/2017 | 25/08/2017 | 25/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-BZK3-82 | red | (BOP) MANUFACTURING, SHOP TEST MV CABLES BZK | TT_Task | 26/08/2017 | 12/05/2018 | 25/08/2017 | 10/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZK3-84 | blue | (BOP) (RFS) READY FOR SHIPMENT MV CABLES BZK | TT_FinMile | 01/07/2018 | 01/07/2018 | 31/07/2018 | 31/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZK3-86 | red | (BOP) FINAL CHECK BEFORE SHIPMENT MV CABLES BZK | TT_Task | 18/06/2018 | 01/07/2018 | 27/06/2018 | 10/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-BZK4-62 | red | (BOP) TRANSPORT MV CABLES BZK | TT_Task | 02/07/2018 | 30/08/2018 | 03/08/2018 | 20/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-MBH2-10 | red | (BOP) TECHNICAL CLARIFICATION HYDROGEN SUPPLY SYSTEM | TT_Task | 01/05/2017 | 11/06/2017 | 22/04/2017 | 02/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-MBH2-15 | red | (BOP) BASIC DESIGN, SPECIFICATION HYDROGEN SUPPLY SYSTEM (incl. FSD COMPLIANCE CHECK) | TT_Task | 28/06/2017 | 07/09/2017 | 03/06/2017 | 13/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-MBH2-20 | blue | (BOP) RFQ HYDROGEN SUPPLY SYSTEM | TT_FinMile | 14/09/2017 | 14/09/2017 | 13/08/2017 | 13/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-MBH2-25 | red | (BOP) QUOTATION STAGE HYDROGEN SUPPLY SYSTEM | TT_Task | 15/09/2017 | 26/10/2017 | 14/08/2017 | 24/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-MBH2-30 | black | (BOP) ORDER PLACED HYDROGEN SUPPLY SYSTEM | TT_Mile | 26/09/2017 | 26/09/2017 | 25/09/2017 | 25/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-MBH3-90 | red | (BOP) MANUFACTURING, SHOP TEST HYDROGEN SUPPLY SYSTEM | TT_Task | 26/09/2017 | 02/06/2018 | 25/09/2017 | 11/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-MBH3-92 | blue | (BOP) (RFS) READY FOR SHIPMENT HYDROGEN SUPPLY SYSTEM | TT_FinMile | 08/07/2018 | 08/07/2018 | 11/05/2018 | 11/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-MBH4-60 | red | (BOP) TRANSPORT HYDROGEN SUPPLY SYSTEM | TT_Task | 09/07/2018 | 06/09/2018 | 12/05/2018 | 13/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-MKG2-32 | red | (BOP) TECHNICAL CLARIFICATION CO2 SUPPLY SYSTEM | TT_Task | 01/05/2017 | 11/06/2017 | 22/04/2017 | 02/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-MKG2-35 | red | (BOP) BASIC DESIGN, SPECIFICATION CO2 SUPPLY SYSTEM (incl. FSD COMPLIANCE CHECK) | TT_Task | 28/06/2017 | 07/09/2017 | 03/06/2017 | 13/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-MKG2-40 | blue | (BOP) RFQ CO2 SUPPLY SYSTEM | TT_FinMile | 14/09/2017 | 14/09/2017 | 13/08/2017 | 13/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-MKG2-45 | red | (BOP) QUOTATION STAGE CO2 SUPPLY SYSTEM | TT_Task | 15/09/2017 | 26/10/2017 | 14/08/2017 | 24/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-MKG2-50 | black | (BOP) ORDER PLACED CO2 SUPPLY SYSTEM | TT_Mile | 26/09/2017 | 26/09/2017 | 25/09/2017 | 25/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-MKG3-94 | red | (BOP) MANUFACTURING, SHOP TEST CO2 SUPPLY SYSTEM | TT_Task | 26/09/2017 | 02/06/2018 | 25/09/2017 | 11/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-MKG3-96 | blue | (BOP) (RFS) READY FOR SHIPMENT CO2 SUPPLY SYSTEM | TT_FinMile | 08/07/2018 | 08/07/2018 | 11/05/2018 | 11/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-MKG4-62 | red | (BOP) TRANSPORT CO2 SUPPLY SYSTEM | TT_Task | 09/07/2018 | 06/09/2018 | 12/05/2018 | 13/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0EG-2-87 | red | (BOP) TECHNICAL CLARIFICATION FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | TT_Task | 14/02/2017 | 20/03/2017 | 04/02/2017 | 10/03/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0EG-2-89 | red | (BOP) QUOTATION STAGE FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | TT_Task | 20/06/2017 | 14/08/2017 | 26/05/2017 | 20/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0EG-2-93 | black | (BOP) ORDER PLACED FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | TT_Mile | 13/09/2017 | 13/09/2017 | 21/08/2017 | 21/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0EG-2-99 | red | (BOP) BASIC DESIGN, PREPARATION RFQ FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | TT_Task | 26/03/2017 | 13/05/2017 | 11/03/2017 | 25/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0EG-3-82 | red | (BOP) DETAIL DESIGN, MANUFACTURING, SHOP TEST FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | TT_Task | 13/09/2017 | 27/06/2018 | 21/08/2017 | 28/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0EG-3-84 | blue | (BOP) (RFS) READY FOR SHIPMENT FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | TT_FinMile | 02/07/2018 | 02/07/2018 | 26/05/2018 | 26/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0EG-4-42 | red | (BOP) TRANSPORT FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | TT_Task | 03/07/2018 | 31/08/2018 | 27/05/2018 | 30/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0EG-4-46 | blue | (OTD-OS) (BOP) ON SITE FUEL FUEL OIL FORWARDING SYSTEM EG (incl. PUMPS) | TT_FinMile | 31/08/2018 | 31/08/2018 | 30/06/2018 | 30/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0PUN2-20 | red | (BOP) BASIC DESIGN, PREPARATION RFQ SEAWATER BOOSTER PUMP | TT_Task | 03/05/2017 | 04/07/2017 | 03/04/2017 | 04/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0PUN2-25 | red | (BOP) QUOTATION STAGE SEAWATER BOOSTER PUMP | TT_Task | 30/06/2017 | 24/08/2017 | 05/06/2017 | 31/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0PUN2-40 | black | (BOP) ORDER PLACED SEAWATER BOOSTER PUMP | TT_Mile | 26/03/2018 | 26/03/2018 | 26/02/2018 | 26/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0PUN2-47 | red | (BOP) TECHNICAL CLARIFICATION SEAWATER BOOSTER PUMP | TT_Task | 01/03/2017 | 04/04/2017 | 27/02/2017 | 02/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI0PUN3-35 | red | (BOP) DETAIL DESIGN, MANUFACTURING, SHOP TESTSEAWATER BOOSTER PUMP | TT_Task | 26/03/2018 | 09/08/2018 | 26/02/2018 | 15/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0PUN3-50 | blue | (BOP) (RFS) READY FOR SHIPMENT SEAWATER BOOSTER PUMP | TT_FinMile | 18/08/2018 | 18/08/2018 | 22/11/2018 | 22/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0PUN4-55 | red | (BOP) TRANSPORT SEAWATER BOOSTER PUMP | TT_Task | 19/08/2018 | 06/10/2018 | 23/11/2018 | 27/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI0PUN4-62 | blue | (OTD-OS) (BOP) ON SITE SEAWATER BOOSTER PUMP | TT_FinMile | 06/10/2018 | 06/10/2018 | 27/11/2018 | 27/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-SCB2-20 | red | (BOP) BASIC DESIGN, SPECIFICATION COMPRESSED AIR INTERCONNECTION SYSTEM | TT_Task | 19/07/2017 | 29/08/2017 | 24/06/2017 | 04/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-SCB2-25 | red | (BOP) TECHNICAL CLARIFICATION COMPRESSED AIR INTERCONNECTION SYSTEM | TT_Task | 01/06/2017 | 12/07/2017 | 13/05/2017 | 23/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-SCB2-30 | blue | (BOP) RFQ COMPRESSED AIR INTERCONNECTION SYSTEM | TT_FinMile | 05/09/2017 | 05/09/2017 | 04/08/2017 | 04/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-SCB2-35 | red | (BOP) QUOTATION STAGE COMPRESSED AIR INTERCONNECTION SYSTEM | TT_Task | 06/09/2017 | 17/10/2017 | 05/08/2017 | 24/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-SCB2-40 | black | (BOP) ORDER PLACED COMPRESSED AIR INTERCONNECTION SYSTEM | TT_Mile | 26/09/2017 | 26/09/2017 | 25/09/2017 | 25/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-SCB3-45 | red | (BOP) MANUFACTURING, SHOP TEST COMPRESSED AIR INTERCONNECTION SYSTEM | TT_Task | 26/09/2017 | 07/07/2018 | 25/09/2017 | 31/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-SCB3-50 | blue | (BOP) (RFS) READY FOR SHIPMENT COMPRESSED AIR INTERCONNECTION SYSTEM | TT_FinMile | 03/08/2018 | 03/08/2018 | 31/07/2018 | 31/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-SCB4-66 | red | (BOP) TRANSPORT COMPRESSED AIR INTERCONNECTION SYSTEM | TT_Task | 04/08/2018 | 02/10/2018 | 01/08/2018 | 15/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-GHD2-20 | red | (BOP) BASIC DESIGN, SPECIFICATION WATER PIPEWORK SYSTEM | TT_Task | 08/05/2017 | 02/07/2017 | 08/04/2017 | 27/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-GHD2-25 | blue | (BOP) RFQ WATER PIPEWORK SYSTEM | TT_FinMile | 26/07/2017 | 26/07/2017 | 27/06/2017 | 27/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-GHD2-30 | red | (BOP) QUOTATION STAGE WATER PIPEWORK SYSTEM | TT_Task | 27/07/2017 | 06/09/2017 | 28/06/2017 | 24/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-GHD2-35 | black | (BOP) ORDER PLACED WATER PIPEWORK SYSTEM | TT_Mile | 26/09/2017 | 26/09/2017 | 25/09/2017 | 25/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-GHD2-37 | red | (BOP) TECHNICAL CLARIFICATION WATER PIPEWORK SYSTEM | TT_Task | 01/03/2017 | 11/04/2017 | 25/02/2017 | 07/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-GHD3-40 | red | (BOP) MANUFACTURING, SHOP TEST WATER PIPEWORK SYSTEM | TT_Task | 26/09/2017 | 03/07/2018 | 25/09/2017 | 11/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-GHD3-50 | blue | (BOP) (RFS) READY FOR SHIPMENT WATER PIPEWORK SYSTEM | TT_FinMile | 14/07/2018 | 14/07/2018 | 11/05/2018 | 11/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-GHD4-64 | red | (BOP) TRANSPORT WATER PIPEWORK SYSTEM | TT_Task | 15/07/2018 | 12/09/2018 | 12/05/2018 | 13/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-PAS2-39 | red | (BOP) TECHNICAL CLARIFICATION NOX WATER INJECTION PUMP | TT_Task | 01/03/2017 | 11/04/2017 | 25/02/2017 | 07/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-PAS2-41 | red | (BOP) BASIC DESIGN, SPECIFICATION NOX WATER INJECTION PUMP | TT_Task | 08/05/2017 | 02/07/2017 | 08/04/2017 | 02/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-PAS2-43 | blue | (BOP) RFQ NOX WATER INJECTION PUMP | TT_FinMile | 27/06/2017 | 27/06/2017 | 02/06/2017 | 02/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-PAS2-45 | red | (BOP) QUOTATION STAGE NOX WATER INJECTION PUMP | TT_Task | 28/06/2017 | 08/08/2017 | 03/06/2017 | 31/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-PAS2-47 | black | (BOP) ORDER PLACED NOX WATER INJECTION PUMP | TT_Mile | 26/01/2018 | 26/01/2018 | 27/12/2017 | 27/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SI-PAS3-52 | red | (BOP) MANUFACTURING, SHOP TEST NOX WATER INJECTION PUMP | TT_Task | 26/01/2018 | 11/08/2018 | 27/12/2017 | 15/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-PAS3-54 | blue | (BOP) (RFS) READY FOR SHIPMENT NOX WATER INJECTION PUMP | TT_FinMile | 18/08/2018 | 18/08/2018 | 15/10/2018 | 15/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-PAS4-64 | red | (BOP) TRANSPORT NOX WATER INJECTION PUMP | TT_Task | 19/08/2018 | 06/10/2018 | 19/10/2018 | 25/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SI-PAS4-68 | blue | (OTD-OS) (BOP) ON SITE NOX WATER INJECTION PUMP | TT_FinMile | 06/10/2018 | 06/10/2018 | 25/10/2018 | 25/10/2018 | 0 | TK_Complete | CCGTD1_IPS
COMM | black | Commencement of Works (Day 1) | TT_Mile | 29/05/2017 | 29/05/2017 | 29/05/2017 | 29/05/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 29/05/2017
COMP | blue | Completion of Works (Day 947) (SA1) | TT_FinMile | 01/01/2020 | 01/01/2020 | 31/12/2019 | 31/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 31/12/2019
_LOI | black | Letter of Intent (LOI) | TT_Mile | 23/05/2017 | 23/05/2017 | 23/05/2017 | 23/05/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 23/05/2017
CW1.3 | blue | Complete Removal of Temp. Bulk head at Seawall Outfall | TT_FinMile | 01/01/2020 | 01/01/2020 | 23/12/2019 | 23/12/2019 | 0 | TK_Complete | CCGTD1_IPS
KD_A02XX | blue | A2 - Complete Site Clearance and Establishment Works | TT_FinMile | 11/09/2017 | 11/09/2017 | 08/09/2017 | 08/09/2017 | 0 | TK_Complete | CCGTD1_IPS
KD_A99XX | blue | Completion of Section A of the Works (Day 90) | TT_FinMile | 16/10/2017 | 16/10/2017 | 08/09/2017 | 08/09/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 26/08/2017
CW1.1 | blue | Pump Station Structural Completion (= M&amp;E Access) | TT_FinMile | 02/06/2019 | 02/06/2019 | 12/05/2019 | 12/05/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 14/04/2019
KD_B01XX | blue | B1 - Complete Foundation Structures and Pile Caps for Stack, Diffuser and HRSG Main Plant with Lift and Staircase Towers | TT_FinMile | 15/03/2018 | 15/03/2018 | 31/01/2018 | 31/01/2018 | 0 | TK_Complete | CCGTD1_IPS
KD_B04XX | blue | B4 - Install Southern Section of UG large diameter Intake &amp; Discharge CWP and finish ground surface for machinery access | TT_FinMile | 09/04/2019 | 09/04/2019 | 12/02/2019 | 12/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 14/02/2019
KD_B05XX | blue | B5 - Construct Condensate Pit | TT_FinMile | 26/11/2018 | 26/11/2018 | 22/11/2018 | 22/11/2018 | 0 | TK_Complete | CCGTD1_IPS
KD_B06XX | blue | B6 - Construct Turboset foundation and supporting pile cap | TT_FinMile | 23/04/2018 | 23/04/2018 | 20/04/2018 | 20/04/2018 | 0 | TK_Complete | CCGTD1_IPS
KD_B07XX | blue | B7 - Construct pile caps, tie beams and G/F slab for Turbine Hall Building | TT_FinMile | 26/11/2018 | 26/11/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
KD_B08XX | blue | B8 - Construct supporting structure for O/H Cranes of Turbine Hall incl. associated roof structures &amp; partial side walls | TT_FinMile | 26/06/2018 | 26/06/2018 | 27/05/2018 | 27/05/2018 | 0 | TK_Complete | CCGTD1_IPS
KD_B09XX | blue | B9 - Complete Underground Earthing and Lightning Protection Installation inside the Turbine Hall | TT_FinMile | 26/11/2018 | 26/11/2018 | 09/09/2018 | 09/09/2018 | 0 | TK_Complete | CCGTD1_IPS
KD_B10XX | blue | B10 - Complete Underground Drainage Works inside the Turbine Hall | TT_FinMile | 26/01/2019 | 26/01/2019 | 22/11/2018 | 22/11/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 30/11/2018
KD_B99XX | blue | Completion of Section B of the Works (Day 255) | TT_FinMile | 09/04/2019 | 09/04/2019 | 12/02/2019 | 12/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 07/02/2018
CW1.2 | blue | Cooling Water System Ready to Provide Water | TT_FinMile | 01/01/2020 | 01/01/2020 | 24/12/2019 | 24/12/2019 | 0 | TK_Complete | CCGTD1_IPS
KD_C01XX | blue | C1 - Construct Crane Walkway, Condensate Pit and Condenser Platforms within Turbine Hall Building | TT_FinMile | 31/03/2019 | 31/03/2019 | 19/03/2019 | 19/03/2019 | 0 | TK_Complete | CCGTD1_IPS
KD_C03XX | blue | C3 - Construct Polishing Pit , ALL foundations, G/F slab for Condensate Polishing Plant area of Turbine Hall | TT_FinMile | 26/11/2018 | 26/11/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
KD_C04XX | blue | C4 - Install and T&amp;C two 250t O/H cranes within Turbine Hall and H/O to M&amp;E Contractor | TT_FinMile | 26/11/2018 | 26/11/2018 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete | CCGTD1_IPS
KD_C05XX | blue | C5 - Construct trench between Condenser and Condensate Polishing Pit | TT_FinMile | 26/11/2018 | 26/11/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
KD_C06XX | blue | C6 - Construct foundations &amp; plinths for support steel structure for A/G sections of CWP to the south of Turbine Hall | TT_FinMile | 09/04/2019 | 09/04/2019 | 07/03/2019 | 07/03/2019 | 0 | TK_Complete | CCGTD1_IPS
KD_C07XX | blue | C7 - Complete ALL civil works incl. foundations, pile cap, fire walls &amp; hard standings for Generator Transformer Area | TT_FinMile | 09/04/2019 | 09/04/2019 | 18/02/2019 | 18/02/2019 | 0 | TK_Complete | CCGTD1_IPS
KD_C08XX | blue | C8 - Install Middle Section of U/G large diameter Intake &amp; Discharge CWP and finish surface ground for machinery access | TT_FinMile | 03/09/2018 | 03/09/2018 | 03/09/2018 | 03/09/2018 | 0 | TK_Complete | CCGTD1_IPS
1.2 | blue | Utilites Trench | TT_FinMile | 31/03/2019 | 31/03/2019 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 14/02/2019
1.3 | blue | Gas Pipeline Trench | TT_FinMile | 31/03/2019 | 31/03/2019 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 14/02/2019
1.4 | blue | Gas Blending Skid Area Foundation | TT_FinMile | 31/03/2019 | 31/03/2019 | 29/01/2019 | 29/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 14/02/2019
1.5 | blue | Utilities Trench | TT_FinMile | 31/03/2019 | 31/03/2019 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 14/02/2019
3.1 | blue | Underground Cable Corridor incl. LV Transformer Fdn | TT_FinMile | 31/03/2019 | 31/03/2019 | 12/02/2019 | 12/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 14/02/2019
3.2 | blue | Neutralization Pit | TT_FinMile | 26/01/2019 | 26/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 14/02/2019
3.3a | blue | Generator Transformer Foundation | TT_FinMile | 04/02/2019 | 04/02/2019 | 25/01/2019 | 25/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 14/02/2019
3.3b | blue | Generator Transformer Blast Wall | TT_FinMile | 09/04/2019 | 09/04/2019 | 12/02/2019 | 12/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 14/02/2019
3.4 | blue | Excitation Transfomer Foundation | TT_FinMile | 31/03/2019 | 31/03/2019 | 30/01/2019 | 30/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 14/02/2019
3.5 | blue | Unit Transformer Foundation | TT_FinMile | 31/03/2019 | 31/03/2019 | 04/02/2019 | 04/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 14/02/2019
KD_D04XX | blue | D4 - Construct Duct Bank between Switchgear Building and Generator Transformer Area | TT_FinMile | 31/03/2019 | 31/03/2019 | 12/02/2019 | 12/02/2019 | 0 | TK_Complete | CCGTD1_IPS
KD_D05XX | blue | D5 - Construct Boiler Blow Down Pit | TT_FinMile | 26/11/2018 | 26/11/2018 | 17/08/2018 | 17/08/2018 | 0 | TK_Complete | CCGTD1_IPS
KD_D06XX | blue | D6 - Complete foundations and plinths for ALL equipment, pipe bridge and sleeper way to the west of HRSG Area | TT_FinMile | 26/01/2019 | 26/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS
KD_D08XX | blue | D8 - Complete foundations and plinths for LV Auxiliary Power Transformers | TT_FinMile | 31/03/2019 | 31/03/2019 | 04/02/2019 | 04/02/2019 | 0 | TK_Complete | CCGTD1_IPS
KD_D11XX | blue | D11 - Complete foundations and plinths for Close Cooling Water Structure | TT_FinMile | 09/04/2019 | 09/04/2019 | 04/03/2019 | 04/03/2019 | 0 | TK_Complete | CCGTD1_IPS
KD_E02XX | blue | E2 - Complete ALL outdoor pipe trenches including 10UEZ01, 10UEZ02 and 10UGZ | TT_FinMile | 31/03/2019 | 31/03/2019 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS
KD_E04XX | blue | E4 - Complete foundation &amp; plinths for Fuel Gas Pruge Air, Gas Receiving Station, Fuel Gas Blending System | TT_FinMile | 31/03/2019 | 31/03/2019 | 29/01/2019 | 29/01/2019 | 0 | TK_Complete | CCGTD1_IPS
KD_E08XX | blue | E8 - Deferred Works Item 01 (p.r.t. Act ID DEF_WK01) | TT_FinMile | 26/11/2018 | 26/11/2018 | 05/08/2018 | 05/08/2018 | 0 | TK_Complete | CCGTD1_IPS
TH1.3 | blue | Turbine Hall all round inner skin (GL.1-5) | TT_FinMile | 31/03/2019 | 31/03/2019 | 31/01/2019 | 31/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/01/2019
TH2.2 | blue | North Elevation (GL1-5) | TT_FinMile | 31/03/2019 | 31/03/2019 | 29/01/2019 | 29/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/01/2019
KD_F02XX | blue | F2 - Complete Oil Contaminated Drainage System incl' external drainage, oil interceptor and pipe trenches | TT_FinMile | 09/04/2019 | 09/04/2019 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS
KD_F08bXX | blue | F8b - Deferred Works Item 03 (p.r.t. Act ID DEF_WK03) | TT_FinMile | 26/01/2019 | 26/01/2019 | 14/11/2018 | 14/11/2018 | 0 | TK_Complete | CCGTD1_IPS
KD_F08eXX | blue | F8e - Deferred Works Item 07 (p.r.t. Act ID DEF_WK07) | TT_FinMile | 26/01/2019 | 26/01/2019 | 15/12/2018 | 15/12/2018 | 0 | TK_Complete | CCGTD1_IPS
TH2.3 | blue | Kalzip (Dog House &amp; Curved Areas) | TT_FinMile | 01/08/2019 | 01/08/2019 | 14/06/2019 | 14/06/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 28/02/2019
TH2.4 | blue | West Elevation (GL5) | TT_FinMile | 31/03/2019 | 31/03/2019 | 28/02/2019 | 28/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 28/02/2019
TH2.5 | blue | East side elevation GL1 | TT_FinMile | 01/05/2019 | 01/05/2019 | 30/04/2019 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 28/02/2019
TH2.6 | blue | South Elevation (GL1-5) | TT_FinMile | 31/03/2019 | 31/03/2019 | 28/02/2019 | 28/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 28/02/2019
TH3.1 | blue | North Elevation (GL5-10) | TT_FinMile | 01/05/2019 | 01/05/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 28/02/2019
TH3.2 | blue | West Elevation (GL10) | TT_FinMile | 01/08/2019 | 01/08/2019 | 30/03/2019 | 30/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 28/02/2019
TH3.6 | blue | Kalzip Roof (GL7-10) | TT_FinMile | 01/01/2020 | 01/01/2020 | 21/10/2019 | 21/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 28/02/2019
KD_G07bXX | blue | G7b - Deferred Works Item 09 (p.r.t. Act ID DEF_WK09) | TT_FinMile | 26/01/2019 | 26/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS
TH3.3 | blue | West Elevation (GL7) | TT_FinMile | 01/01/2020 | 01/01/2020 | 25/10/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/03/2019
TH3.3A | blue | West Elevation water tight (GL7) | TT_FinMile | 31/03/2019 | 31/03/2019 | 31/03/2019 | 31/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/03/2019
TH3.4 | blue | South Elevation (GL5-10) | TT_FinMile | 01/05/2019 | 01/05/2019 | 29/03/2019 | 29/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/03/2019
TH3.4A | blue | South Elevation water tight (GL5-10) | TT_FinMile | 31/03/2019 | 31/03/2019 | 14/03/2019 | 14/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/03/2019
SW1.1 | blue | Completion of all site works | TT_FinMile | 22/02/2020 | 22/02/2020 | 08/09/2020 | 08/09/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/12/2019
1.1 | blue | Urea Plant Area | TT_FinMile | 26/01/2019 | 26/01/2019 | 11/01/2019 | 11/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/12/2018
2.1 | blue | Remaining Feedwater Pump Foundation | TT_FinMile | 26/01/2019 | 26/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/12/2018
2.2 | blue | Condensate Recirculating Pump Foundation | TT_FinMile | 26/01/2019 | 26/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/12/2018
2.3 | blue | Remaining HRSG West Foundation | TT_FinMile | 26/01/2019 | 26/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/12/2018
2.4 | blue | Diesel Generator Foundation (Shaft F Area) | TT_FinMile | 01/08/2019 | 01/08/2019 | 02/07/2019 | 02/07/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 14/02/2019
2.5 | blue | Gas Preheating Skid Area Foundation | TT_FinMile | 05/08/2019 | 05/08/2019 | 04/05/2019 | 04/05/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/03/2019
3.6 | blue | Main CW collection piece (UPY00Y) and Cooling Water Pump Foundations (PxB00Y) | TT_FinMile | 09/04/2019 | 09/04/2019 | 07/03/2019 | 07/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 01/03/2019
3.7 | blue | Rain Collection Pump Station Structural Completion (Top Slab) | TT_FinMile | 26/01/2019 | 26/01/2019 | 07/01/2019 | 07/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 05/02/2019
4.1 | blue | HRSG South Remaining Foundations and Drainage | TT_FinMile | 01/05/2019 | 01/05/2019 | 12/04/2019 | 12/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 28/02/2019
4.2 | blue | HRSG East Remaining Foundation (incl. Fdn for Urea Decomposition Chamber) | TT_FinMile | 01/08/2019 | 01/08/2019 | 29/06/2019 | 29/06/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 30/03/2019
P1_Rooms | blue | Priority 1 Rooms | TT_FinMile | 26/01/2019 | 26/01/2019 | 01/01/2019 | 01/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 01/01/2019
P2_Rooms | blue | Priority 2 Rooms | TT_FinMile | 31/03/2019 | 31/03/2019 | 05/02/2019 | 05/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 05/02/2019
P3_Rooms | blue | Priority 3 Rooms | TT_FinMile | 31/03/2019 | 31/03/2019 | 30/03/2019 | 30/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 14/02/2019
TH1.1 | blue | GL5-7 [Mechanical Annex] - Access for E&amp;M | TT_FinMile | 25/02/2019 | 25/02/2019 | 18/12/2018 | 18/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 18/12/2018
TH1.2 | blue | GL7-10 [SwitchGear Block] - Concrete roof (under air intake) GL E-L poured | TT_FinMile | 26/01/2019 | 26/01/2019 | 29/12/2018 | 29/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 29/12/2018
TH2.1 | blue | Kalzip Roof | TT_FinMile | 26/01/2019 | 26/01/2019 | 29/12/2018 | 29/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 01/01/2019
TH3.1A | blue | North Elevation water tight (GL5-10) | TT_FinMile | 26/01/2019 | 26/01/2019 | 19/01/2019 | 19/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 05/02/2019
TH3.2A | blue | West Elevation water tight (GL10) - Elect Rooms | TT_FinMile | 31/03/2019 | 31/03/2019 | 04/02/2019 | 04/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 05/02/2019
TH3.5 | blue | Kalzip Roof (GL5-7) | TT_FinMile | 26/01/2019 | 26/01/2019 | 15/01/2019 | 15/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 15/01/2019
TH4.1 | blue | Turbine Hall Lift operational with EMSD lift certificate | TT_FinMile | 30/01/2020 | 30/01/2020 | 12/03/2020 | 12/03/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/08/2019
MS-01-1XX | blue | MS-01-1 / Execute Contract | TT_FinMile | 29/05/2017 | 29/05/2017 | 29/05/2017 | 29/05/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 29/05/2017
MS_01XX | blue | MS-01 / Achievement of Milestone Requirements | TT_FinMile | 31/05/2017 | 31/05/2017 | 31/05/2017 | 31/05/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 31/05/2017
MS-02-1XX | blue | MS-02-1 / Excute Articles of Agreement | TT_FinMile | 07/12/2017 | 07/12/2017 | 06/12/2017 | 06/12/2017 | 0 | TK_Complete | CCGTD1_IPS
MS-02-2XX | blue | MS-02-2 / Submit to CLP Temp. Works for Shaft A, Pump Station, Diversion Culvert (Wall Only) | TT_FinMile | 02/11/2017 | 02/11/2017 | 16/11/2017 | 16/11/2017 | 0 | TK_Complete | CCGTD1_IPS
MS-02-3XX | blue | MS-02-3 / Submit to CLP Temp. Works for Shaft D (Wall, Excav &amp; ELS) | TT_FinMile | 15/06/2017 | 15/06/2017 | 15/06/2017 | 15/06/2017 | 0 | TK_Complete | CCGTD1_IPS
MS-02-4XX | blue | MS-02-4 / Submit to CLP Temp. Works for Shaft F (Skin Wall) &amp; Double Pipe Trench (Southern Sheet Pile) | TT_FinMile | 21/06/2017 | 21/06/2017 | 21/06/2017 | 21/06/2017 | 0 | TK_Complete | CCGTD1_IPS
MS-02-5XX | blue | MS-02-5 / Submit to CLP Temp. Works for Shaft F &amp; Doble Pipe Trench (Open Cut Alternative) | TT_FinMile | 21/06/2017 | 21/06/2017 | 21/06/2017 | 21/06/2017 | 0 | TK_Complete | CCGTD1_IPS
MS-02-6XX | blue | MS-02-6 / Submit to CLP Temp. Works for Power Island (Open Cut Amendment) | TT_FinMile | 21/06/2017 | 21/06/2017 | 21/06/2017 | 21/06/2017 | 0 | TK_Complete | CCGTD1_IPS
MS_02XX | blue | MS-02 / Achievement of Milestone Requirements | TT_FinMile | 28/08/2017 | 28/08/2017 | 08/08/2017 | 08/08/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 31/07/2017
MS-03-1XX | blue | MS-03-1 / Submit to CLP Temp. Works for Shaft A, Pump Station, Diversion Culvert (Excav. &amp; ELS) | TT_FinMile | 29/11/2017 | 29/11/2017 | 05/12/2017 | 05/12/2017 | 0 | TK_Complete | CCGTD1_IPS
MS-03-2XX | blue | MS-03-2 / Submit to CLP Temp. Works for Shaft E &amp; Discharge Culvert (Wall, Excav. &amp; ELS) | TT_FinMile | 15/08/2017 | 15/08/2017 | 20/07/2017 | 20/07/2017 | 0 | TK_Complete | CCGTD1_IPS
MS-03-3XX | blue | MS-03-3 / Submit to CLP Temp. Bulkhead Design for Outfall Apron Modification | TT_FinMile | 06/01/2018 | 06/01/2018 | 16/11/2017 | 16/11/2017 | 0 | TK_Complete | CCGTD1_IPS
MS_03XX | blue | MS-03 / Achievement of Milestone Requirements | TT_FinMile | 23/04/2018 | 23/04/2018 | 16/11/2017 | 16/11/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 31/07/2017
MS-04-1XX | blue | MS-04-1 / Complete Section A Works | TT_FinMile | 23/10/2017 | 23/10/2017 | 08/09/2017 | 08/09/2017 | 0 | TK_Complete | CCGTD1_IPS
MS-04-2XX | blue | MS-04-2 / Award Subcontract - Excavation &amp; ELS | TT_FinMile | 15/12/2017 | 15/12/2017 | 22/12/2017 | 22/12/2017 | 0 | TK_Complete | CCGTD1_IPS
MS-04-3XX | blue | MS-04-3 / Award Subcontract - Grouting and Sheet / Pipe Piling | TT_FinMile | 28/08/2017 | 28/08/2017 | 26/08/2017 | 26/08/2017 | 0 | TK_Complete | CCGTD1_IPS
MS-04-4XX | blue | MS-04-4 / Award Subcontract - Steel Structures &amp; Heaving Lifting | TT_FinMile | 24/10/2017 | 24/10/2017 | 24/10/2017 | 24/10/2017 | 0 | TK_Complete | CCGTD1_IPS
MS-04-5XX | blue | MS-04-5 / Award Subcontract - Standing Seam Roof, Aluminium Cladding &amp; Curtain Wall | TT_FinMile | 23/04/2018 | 23/04/2018 | 20/12/2017 | 20/12/2017 | 0 | TK_Complete | CCGTD1_IPS
MS-04-6XX | blue | MS-04-6 / Award Subcontract - CWP Installation | TT_FinMile | 26/05/2018 | 26/05/2018 | 04/04/2018 | 04/04/2018 | 0 | TK_Complete | CCGTD1_IPS
MS-04-7XX | blue | MS-04-7 / Issue Purchase Order - CW Pipes | TT_FinMile | 23/04/2018 | 23/04/2018 | 25/01/2018 | 25/01/2018 | 0 | TK_Complete | CCGTD1_IPS
MS-04-8XX | blue | MS-04-8 / Award Subcontract - Building Services | TT_FinMile | 23/04/2018 | 23/04/2018 | 20/02/2018 | 20/02/2018 | 0 | TK_Complete | CCGTD1_IPS
MS_04XX | blue | MS-04 / Achievement of Milestone Requirements | TT_FinMile | 26/05/2018 | 26/05/2018 | 04/04/2018 | 04/04/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 31/08/2017
MS-05-1XX | blue | MS-05-1 / Submit to CLP Temp. Works for SCW &amp; Intake Culvert Modification (Wall only) | TT_FinMile | 11/09/2017 | 11/09/2017 | 19/09/2017 | 19/09/2017 | 0 | TK_Complete | CCGTD1_IPS
MS-05-2XX | blue | MS-05-2 / Submit to CLP Temp. Works for SCW &amp; Intake Culvert Modification (Excav. &amp; ELS) | TT_FinMile | 11/09/2017 | 11/09/2017 | 19/09/2017 | 19/09/2017 | 0 | TK_Complete | CCGTD1_IPS
MS-05-3XX | blue | MS-05-3 / Issue Purchase Order - CW Pipes | TT_FinMile | 23/04/2018 | 23/04/2018 | 25/01/2018 | 25/01/2018 | 0 | TK_Complete | CCGTD1_IPS
MS_05XX | blue | MS-05 / Achievement of Milestone Requirements | TT_FinMile | 23/04/2018 | 23/04/2018 | 25/01/2018 | 25/01/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 31/08/2017
MS-06-1XX | blue | MS-06-1 / Delivery of All CWP for Southern Section | TT_FinMile | 26/05/2018 | 26/05/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS
MS-06-2XX | blue | MS-06-2 / First Delivery of Turbine Hall Structural Steelwork | TT_FinMile | 09/12/2017 | 09/12/2017 | 08/12/2017 | 08/12/2017 | 0 | TK_Complete | CCGTD1_IPS
MS_06XX | blue | MS-06 / Achievement of Milestone Requirements | TT_FinMile | 26/05/2018 | 26/05/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 30/11/2017
MS-06aXX | blue | MS-06a-1/ First Delivery of Turbine Hall Roof / Wall Cladding | TT_FinMile | 23/04/2018 | 23/04/2018 | 21/03/2018 | 21/03/2018 | 0 | TK_Complete | CCGTD1_IPS
MS_06aXX | blue | MS-06a / Achievement of Milestone Requirements | TT_FinMile | 23/04/2018 | 23/04/2018 | 21/03/2018 | 21/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 31/12/2017
MS-06bXX | blue | MS-06b-1 / First Delivery of Turbine Hall Curtain Wall / Glazing | TT_FinMile | 26/01/2019 | 26/01/2019 | 10/01/2019 | 10/01/2019 | 0 | TK_Complete | CCGTD1_IPS
MS_06bXX | blue | MS-06b / Achievement of Milestone Requirements | TT_FinMile | 26/01/2019 | 26/01/2019 | 10/01/2019 | 10/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 31/01/2018
MS-06c-1XX | blue | MS-06c-1 / Pumping Station (Complete Pumping Test and Report Submission to BD) | TT_FinMile | 26/01/2019 | 26/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS
MS-06c-2XX | blue | MS-06c-2 / Shaft F Excavation to -11mPD | TT_FinMile | 26/01/2019 | 26/01/2019 | 20/01/2019 | 20/01/2019 | 0 | TK_Complete | CCGTD1_IPS
MS_06cXX | blue | MS-06c / Achievement of Milestone Requirements | TT_FinMile | 26/01/2019 | 26/01/2019 | 20/01/2019 | 20/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 31/01/2018
MS-07-1XX | blue | MS-07-1 / Complete Turboset Foundation and Supporting Pile Cap | TT_FinMile | 23/04/2018 | 23/04/2018 | 20/04/2018 | 20/04/2018 | 0 | TK_Complete | CCGTD1_IPS
MS-07-2XX | blue | MS-07-2 / Complete All Foundation for Stack, Diffuser and HRSG | TT_FinMile | 26/05/2018 | 26/05/2018 | 31/01/2018 | 31/01/2018 | 0 | TK_Complete | CCGTD1_IPS
MS_07XX | blue | MS-07 / Achievement of Milestone Requirements | TT_FinMile | 23/04/2018 | 23/04/2018 | 20/04/2018 | 20/04/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 28/02/2018
MS-08XX | blue | MS08-1 / Complete Supporting Structures for Overhead Cranes of Turbine Hall Building incl. Associated Roof Structures | TT_FinMile | 26/07/2018 | 26/07/2018 | 12/07/2018 | 12/07/2018 | 0 | TK_Complete | CCGTD1_IPS
MS_08XX | blue | MS-08 / Achievement of Milestone Requirements | TT_FinMile | 26/07/2018 | 26/07/2018 | 12/07/2018 | 12/07/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 28/02/2018
MS-09-1XX | blue | MS-09-1 / Complete Southern Section of CW Trench | TT_FinMile | 04/02/2019 | 04/02/2019 | 02/01/2019 | 02/01/2019 | 0 | TK_Complete | CCGTD1_IPS
MS-09-2XX | blue | MS-09-2 / Complete Condensate Pit | TT_FinMile | 26/11/2018 | 26/11/2018 | 09/09/2018 | 09/09/2018 | 0 | TK_Complete | CCGTD1_IPS
MS-09-3XX | blue | MS-09-3 / Pile Caps, Tie Beams and Ground Floor Slab for Turbine Hall Bldg | TT_FinMile | 29/11/2018 | 29/11/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
MS_09XX | blue | MS-09 / Achievement of Milestone Requirements | TT_FinMile | 04/02/2019 | 04/02/2019 | 02/01/2019 | 02/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 28/02/2018
MS-10-1XX | blue | MS-10-1 / Complete Crane Walkway and Platforms within Turbine Hall | TT_FinMile | 31/03/2019 | 31/03/2019 | 19/03/2019 | 19/03/2019 | 0 | TK_Complete | CCGTD1_IPS
MS-10-3XX | blue | MS-10-3 / Complete Condensate Polishing Pit | TT_FinMile | 26/11/2018 | 26/11/2018 | 09/09/2018 | 09/09/2018 | 0 | TK_Complete | CCGTD1_IPS
MS-10-4XX | blue | MS-10-4 / Install 2 nos of 250t Overhead Crane | TT_FinMile | 26/11/2018 | 26/11/2018 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete | CCGTD1_IPS
MS-10-5XX | blue | MS-10-5 / Complete All Civil Works for Generator Transformer Area | TT_FinMile | 09/04/2019 | 09/04/2019 | 18/02/2019 | 18/02/2019 | 0 | TK_Complete | CCGTD1_IPS
MS-12-1XX | blue | MS-12-1 / TBM Delivery to Site | TT_FinMile | 26/11/2018 | 26/11/2018 | 26/08/2018 | 26/08/2018 | 0 | TK_Complete | CCGTD1_IPS
CWS-2BA5 | red | BA5 - Approval to GBP Amendment CW System - Diversion Culvert, Pump Station, Discharge Culvert, Shaft F, etc {4a1} | TT_Task | 06/07/2017 | 04/08/2017 | 27/06/2017 | 25/07/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 05/07/2017
CWS-2BA8XX | blue | BA8 - Consent to GBP Amendment Cooling Water System Part 1 - Diversion Culvert, Pump Station | TT_FinMile | 01/01/2020 | 01/01/2020 | 22/10/2019 | 22/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CWS_2BA5XX | blue | BA5 - Approval to GBP Amendment Cooling Water System Part 2 - Shaft F, Seal Pit, Discharge Culvert | TT_FinMile | 05/07/2017 | 05/07/2017 | 05/07/2017 | 05/07/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 05/07/2017
CWS_2BA8XX | blue | BA8 - Consent to GBP Amendment Cooling Water System Part 2 - Shaft F, Seal Pit, Discharge Culvert | TT_FinMile | 01/01/2020 | 01/01/2020 | 10/05/2019 | 10/05/2019 | 0 | TK_Complete | CCGTD1_IPS
CWSd1BA5 | red | BA5 - (1st) BD Approval to Cooling Water System Permanent Drainage Plan {4d} | TT_Task | 09/08/2017 | 08/10/2017 | 26/06/2017 | 22/08/2017 | 0 | TK_Complete | CCGTD1_IPS
CWSd1BA8 | red | BA8 - (1st) BD Consent to Cooling Water System Permanent Drainage Plan {4d} - actual dates TBC | TT_Task | 26/08/2017 | 24/09/2017 | 23/08/2017 | 21/09/2017 | 0 | TK_Complete | CCGTD1_IPS
CWSd2BA5 | red | BA5 - Approval to (Minor) Amendment for Cooling Water System Permanent Drainage Plan {4di} | TT_Task | 01/03/2018 | 30/04/2018 | 29/03/2018 | 18/04/2018 | 0 | TK_Complete | CCGTD1_IPS
CWSd2BA8 | blue | BA8 - Consent to (Minor) Amendment for Cooling Water System Permanent Drainage Plan {4di} [WITHDRAWN] | TT_FinMile | 01/06/2019 | 01/06/2019 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete | CCGTD1_IPS
CWSd3BA5 | red | BA5 - Approval to 2nd (Minor) Amendment for Cooling Water System Permanent Drainage Plan {4dii} | TT_Task | 01/06/2019 | 01/06/2019 | 02/05/2019 | 27/05/2019 | 0 | TK_Complete | CCGTD1_IPS
CWSd3BA8 | red | BA8 - Consent to 2nd (Minor) Amendment for Cooling Water System Permanent Drainage Plan {4dii} | TT_Task | 02/08/2019 | 29/08/2019 | 13/06/2019 | 22/07/2019 | 0 | TK_Complete | CCGTD1_IPS
DBCp1BA5 | red | BA5 - (1st) BD Approval for Permanent Works for Discharge Box Culvert {4c1} | TT_Task | 23/08/2017 | 22/10/2017 | 14/07/2017 | 12/09/2017 | 0 | TK_Complete | CCGTD1_IPS
DBCp1BA8 | red | BA8 - (1st) BD Consent to Permanent Works for Discharge Box Culvert {4c1} - actual dates TBC | TT_Task | 13/09/2017 | 12/10/2017 | 13/09/2017 | 12/10/2017 | 0 | TK_Complete | CCGTD1_IPS
DBCp2BA5 | red | BA5 - Approval to (Minor) Amendment for Permanent Works for Discharge Box Culvert {4c1i}[WITHDRAWN] | TT_Task | 08/12/2017 | 02/01/2018 | 08/12/2017 | 02/01/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 08/12/2017
DBCp2BA5a | red | BA5 - Approval to (Minor) Amendment for Permanent Works for Discharge Box Culvert {4c1i(r1)}[RESUBMISSION#1] | TT_Task | 06/03/2018 | 05/04/2018 | 02/01/2018 | 25/01/2018 | 0 | TK_Complete | CCGTD1_IPS
DBCp2BA8 | red | BA8 - Consent to (Major) Amendment for Permanent Works for Discharge Box Culvert {4c1i(r1)} - actual date TBC | TT_Task | 06/04/2018 | 05/05/2018 | 26/01/2018 | 24/02/2018 | 0 | TK_Complete | CCGTD1_IPS
PPSp1BA5 | red | BA5 - (1st) BD Approval to Permanent Works for Pump Station, Diversion Culvert {4c1} | TT_Task | 07/08/2017 | 06/10/2017 | 14/07/2017 | 12/09/2017 | 0 | TK_Complete | CCGTD1_IPS
PPSp1BA8 | red | BA8 - (1st) BD Consent to Permanent Works for Pump Station, Diversion Culvert {4c1} - actual dates TBC | TT_Task | 13/09/2017 | 12/10/2017 | 13/09/2017 | 12/10/2017 | 0 | TK_Complete | CCGTD1_IPS
PPSp2BA5 | red | BA5 - Approval to (Minor) Amendment for Permanent Works for Pump Station, Diversion Culvert {4c1i}[WITHDRAWN] | TT_Task | 08/12/2017 | 07/01/2018 | 08/12/2017 | 02/01/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 08/12/2017
PPSp2BA5a | red | BA5 - Approval to (Minor) Amendment for Permanent Works for Pump Sttn, Diver.Culvert {4c1i(r1)}[RESUMIT#1] | TT_Task | 26/02/2018 | 28/03/2018 | 02/01/2018 | 25/01/2018 | 0 | TK_Complete | CCGTD1_IPS
PPSp2BA8 | red | BA8 - Consent to (Major) Amendment for Permanent Works for Pump Station, Diversion Culvert {4c1i(r1)} | TT_Task | 26/02/2018 | 27/03/2018 | 26/01/2018 | 24/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SEAp1BA5 | red | BA5 - (1st) BD Aprpoval to Permanent works for Seal Pit (4c2} | TT_Task | 23/08/2017 | 22/10/2017 | 18/08/2017 | 16/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SEAp1BA8 | red | BA8 - (1st) BD Consent to Permanent works for Seal Pit {4c2} - actual dates TBC | TT_Task | 18/10/2017 | 16/11/2017 | 17/10/2017 | 15/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SEAp2BA5 | red | BA5 - Approval to (Major) Amendment for Permanent works for Seal Pit {4c2i} | TT_Task | 26/02/2018 | 28/03/2018 | 19/01/2018 | 13/02/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 05/01/2018
SEAp2BA8 | red | BA8 - Consent to (Major) Amendment for Permanent works for Seal Pit {4c2i} - actual dates TBC | TT_Task | 29/03/2018 | 27/04/2018 | 14/02/2018 | 15/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SFFp1BA5 | red | BA5 - (1st) BD Approval to Permanent works for Shaft F {4c2} | TT_Task | 23/08/2017 | 22/10/2017 | 18/08/2017 | 16/10/2017 | 0 | TK_Complete | CCGTD1_IPS
SFFp1BA8 | red | BA8 - (1st) BD Consent to Permanent works for Shaft F {4c2} - actual dates TBC | TT_Task | 18/10/2017 | 16/11/2017 | 17/10/2017 | 15/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SFFp2BA5 | red | BA5 - Approval to (Major) Amendment for Permanent works for Shaft F {4c2i} | TT_Task | 26/02/2018 | 28/03/2018 | 19/01/2018 | 13/02/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 05/01/2018
SFFp2BA8 | red | BA8 - Consent to (Major) Amendment for Permanent works for Shaft F {4c2i} | TT_Task | 29/03/2018 | 27/04/2018 | 14/02/2018 | 15/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SFAt1BA5 | red | BA5 - (1st) BD Approval to Temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only) {4b4} | TT_Task | 11/06/2017 | 09/08/2017 | 11/04/2017 | 15/06/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 10/06/2017
SFAt1BA8 | red | BA8 - (1st) BD Consent toTemporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only) {4b4} | TT_Task | 07/08/2017 | 03/09/2017 | 16/06/2017 | 13/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SFAt1BA8a | red | BA5 &amp; BA8 - BD Amendment (Type II) - Shaft A Location Shift {4b4-1} | TT_Task | 07/08/2017 | 03/09/2017 | 10/07/2017 | 07/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SFDt1BA5 | red | BA5 - (1st) BD Approval to Temporary works for Shaft D (with LCAL's proposal incorporated) [DISAPPROVED] {4b3(r1)} | TT_Task | 16/08/2017 | 15/10/2017 | 21/06/2017 | 16/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SFEt1BA5 | blue | BA5 - (1st) BD Approval toTemporary works for Shaft E and Discharge Culvert {4b2(r)} | TT_FinMile | 22/04/2017 | 22/04/2017 | 02/05/2017 | 02/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SFFt1BA5 | blue | BA5 - (1st) BD Approval to Temporary works for Shaft F and Double Pipe Trench {4b1(r)} | TT_FinMile | 22/04/2017 | 22/04/2017 | 04/05/2017 | 04/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SFFt1BA8 | red | BA8 - (1st) BD Consent to Temporary works for Shaft F and Double Pipe Trench (for Shaft F Wall only) {4b1(r)} | TT_Task | 03/07/2017 | 03/07/2017 | 05/05/2017 | 21/06/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 27/06/2017
SFFtABA5 | blue | BA5 - (1st) BD Approval to Temp works for Shaft F &amp; Double Pipe Trench (Alternative for Zone A Sheet Pile) {4b1-alt A} | TT_FinMile | 24/05/2017 | 24/05/2017 | 23/05/2017 | 23/05/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 24/05/2017
SFFtABA8 | red | BA8 - (1st) BD Consent to Temp works for Shaft F &amp; Double Pipe Trench (Alternative for Zone A Sheet Pile) {4b1-alt A} | TT_Task | 03/07/2017 | 03/07/2017 | 24/05/2017 | 21/06/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 27/06/2017
SFJt1BA5 | red | BA5 - Amendment to Temp works for Shaft F &amp; Double Pipe Trench - Pipe Jacking [DISAPPROVED] {4b1-1} | TT_Task | 03/07/2017 | 31/08/2017 | 19/05/2017 | 10/07/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 27/06/2017
SFJt1BA5a | red | BA5 - Resubmission of Amendment (Type II) for Shaft F &amp; DPT master construction sequence {4b1-1(r)} | TT_Task | 22/06/2017 | 21/08/2017 | 24/07/2017 | 22/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SFJt2BA5 | red | BA5 - Resubmission for Shaft F(Ring Beam) &amp; Double Pipe Trench Amendment - Pipe Jacking {4b1-2} | TT_Task | 07/09/2017 | 06/11/2017 | 18/09/2017 | 22/11/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 07/09/2017
SFJt2BA8 | red | BA8 - Consent for Shaft F(Ring Beam) &amp; Double Pipe Trench Amendment - Pipe Jacking {4b1-2} | TT_Task | 05/12/2017 | 04/01/2018 | 28/11/2017 | 28/12/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 05/12/2017
SCW_1BA5 | blue | BA5 - (1st) BD Approval to GBP for SCW Pump Sump A&amp;A {5a} | TT_FinMile | 29/04/2017 | 29/04/2017 | 04/05/2017 | 04/05/2017 | 0 | TK_Complete | CCGTD1_IPS
SCW_2BA5 | red | BA5 - Approval to (Major) Amendment for GBP for SCW Pump Sump A&amp;A {5a1} AF-TBC | TT_Task | 23/04/2018 | 23/05/2018 | 06/03/2018 | 05/04/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 28/02/2018
SCWd1BA5 | red | BA5 - (1st) BD Approval to Drainage Plan for SCW and Culvert Modification {5d} | TT_Task | 09/08/2017 | 08/10/2017 | 26/06/2017 | 22/08/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 08/08/2017
SCWd1BA8 | red | BA8 - (1st) BD Consent to Draiange Plan for SCW and Culvert Modification {5d} - actual dates TBC | TT_Task | 28/08/2017 | 24/09/2017 | 08/03/2018 | 06/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SCWd2BA5XX | red | BA5 - Approval to (Major) Amendment for Drainage Plan for SCW and Culvert Modification {5di} actual dates TBC | TT_Task | 10/12/2017 | 08/02/2018 | 30/03/2018 |  | 2920 | TK_Active | CCGTD1_IPS | START_NO_EARLIER_THAN | 10/12/2017
SCWp1BA5 | red | BA5 - (1st) BD Approval to Permanent works for SCW and Culvert Modification {5c} [DISAPPROVED] | TT_Task | 10/11/2017 | 09/01/2018 | 01/12/2017 | 22/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SCWp1BA8 | red | BA8 - (1st) BD Consent to Permanent works for SCW and Culvert Modification {5c} [CANCELLED] | TT_Task | 30/04/2018 | 29/05/2018 | 22/01/2018 | 22/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SCWp2BA5 | red | BA5 - Approval to (Major) Amendment for Permanent works for SCW and Culvert Modification {5c(r)} [RESUBMISSION] | TT_Task | 23/04/2018 | 22/06/2018 | 05/03/2018 | 11/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SCWp2BA8 | red | BA8 - Consent to (Major) Amendment for Permanent works for SCW and Culvert Modification {5c(r)} [RESUBMISSION] | TT_Task | 31/03/2019 | 29/04/2019 | 23/11/2018 | 19/12/2018 | 0 | TK_Complete | CCGTD1_IPS
SCWt1BA5 | red | BA5 - (1st) BD Approval to Temporary works for SCW and Culvert Modification (Wall only) [DISAPPROVED] {5b1} | TT_Task | 31/05/2017 | 18/07/2017 | 24/05/2017 | 11/07/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 30/05/2017
SCWtaBA5 | red | BA5 - (1st) BD Approval to Temp works for SCW &amp; Culvert Modification (Resubmit incl wall, excav.&amp; anchor)(Wet){5b1(r)} | TT_Task | 29/08/2017 | 28/10/2017 | 20/09/2017 | 24/11/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 29/08/2017
SCWtaBA8 | red | BA8 - (1st) BD Consent to Temp works for SCW &amp; Culvert Modification (Resubmit incl wall, excav.&amp; anchor)(Wet){5b1(r)} | TT_Task | 26/02/2018 | 27/03/2018 | 29/01/2018 | 26/02/2018 | 0 | TK_Complete | CCGTD1_IPS
ICM_1BA5 | red | BA5 - (1st) BD Approval to GBP for Outfall Modification (incl' works outside lot boundary) [p.r.t.Act.ID.CWS-2BA5] {6a} | TT_Task | 07/08/2017 | 04/09/2017 | 27/06/2017 | 25/07/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 31/07/2017
ICMp1BA5 | red | BA5 - (1st) BD Approval to Permenent Works for Outfall Modification (incl' works outside lot boundary) {6c} [WITHDRAWN] | TT_Task | 08/12/2017 | 06/02/2018 | 02/01/2018 | 25/01/2018 | 0 | TK_Complete | CCGTD1_IPS
ICMp1BA8 | red | BA8 - (1st) BD Consent to Permanent Works for Outfall Modification (incl' works outside lot boundary) {6c} | TT_Task | 26/02/2018 | 27/03/2018 | 26/01/2018 | 24/02/2018 | 0 | TK_Complete | CCGTD1_IPS
ICMp2BA5 | red | BA5 - Approval to (Major) Amendment for Permenent Works for Outfall Modif (incl' works outside lot boundary){6ci} AD-TBC | TT_Task | 28/04/2018 | 27/06/2018 | 08/03/2018 | 07/05/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 08/03/2018
ICMp2BA8 | red | BA8 - Consent to (Major) Amendment for Permanent Works for Outfall Modif (incl' works outside lot boundary) {6ci} AD-TBC | TT_Task | 10/06/2018 | 09/07/2018 | 08/05/2018 | 06/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ICMt1BA5 | red | BA5 - (1st) BD Approval to Temp.Works for Outfall Modif (incl' works outside lot boundary) {6b incl in 4b2-2}[APPROVED] | TT_Task | 26/02/2018 | 27/04/2018 | 14/02/2018 | 24/04/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 17/01/2018
ICMt1BA8 | red | BA8 - (1st) BD Consent to Temp.Works for Outfall Modif (incl' works outside lot boundary) {6b incl in 4b2-2} | TT_Task | 11/06/2018 | 08/07/2018 | 04/05/2018 | 06/07/2018 | 0 | TK_Complete | CCGTD1_IPS
POW-1BA5 | blue | BA5 - (1st) BD Approval to GBP Amendment for Turbine Hall and HRSG incl' outdoor equipment structures {7a1} | TT_FinMile | 15/08/2017 | 15/08/2017 | 04/05/2017 | 04/05/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 15/08/2017
POWd1BA5 | red | BA5 - (1st) BD Approval to Drainage Plans for Power Island Areas {8a} | TT_Task | 10/07/2017 | 30/08/2017 | 10/05/2017 | 30/06/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 09/07/2017
POWd1BA8 | red | BA8 - (1st) BD Consent to Drainage Plans for Power Island Areas {8a} | TT_Task | 07/08/2017 | 05/09/2017 | 01/08/2017 | 31/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SBHS2BA5 | blue | BA5 - Approval to 1st Amendment (Major) for substructures of HRSG and Stack {7b1} | TT_FinMile | 31/03/2017 | 31/03/2017 | 19/04/2017 | 19/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SBHS2BA8 | blue | BA8 - Consent to 1st Amendment for (Major) substructures of HRSG and Stack {7b1} | TT_FinMile | 02/07/2017 | 02/07/2017 | 27/06/2017 | 27/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SBHS3BA5 | red | BA5 - Approval to 2nd Amendment (Type II) for substructures of HRSG and Stack {7b2} | TT_Task | 07/08/2017 | 06/09/2017 | 30/06/2017 | 26/07/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 23/07/2017
SBHS3BA8 | red | BA8 - Consent to 2nd Amendment (Type II) for substructures of HRSG and Stack {7b2} | TT_Task | 06/09/2017 | 05/10/2017 | 30/06/2017 | 26/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SBOE1BA5 | blue | BA5 - BD Approval to Structural Plan (Package 1) for Outdoor Equipment foundations and plinths [WITHDRAWN] {7f} | TT_FinMile | 26/05/2017 | 26/05/2017 | 19/05/2017 | 19/05/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 26/05/2017
SBOE2BA5 | red | BA5 - Approval to Resubmission of Structural Plan (Package 1) for Outdoor Equipment foundations and plinths {7f(r)} | TT_Task | 07/08/2017 | 06/10/2017 | 31/07/2017 | 27/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SBOE2BA8 | red | BA8 - (1st) BD Consent to Structural Plan (Package 1) for Outdoor Equipment foundations and plinths {7f(r)} | TT_Task | 30/09/2017 | 29/10/2017 | 08/02/2018 | 07/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SBOE3BA5 | red | BA5 - BD Approval to Structural Plan (Package 2) for Outdoor Equipment foundations and plinths {7g} | TT_Task | 30/10/2017 | 29/12/2017 | 30/10/2017 | 29/12/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 30/10/2017
SBOE3BA8 | red | BA8 - BD Consent to Structural Plan (Package 2) for Outdoor Equipment foundations and plinths {7g} | TT_Task | 03/04/2018 | 02/05/2018 | 08/02/2018 | 07/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SBTH2BA5 | blue | BA5 - Approval to 1st Amendment (Major) for pile caps and tie beams within Turbine Hall {7b1} | TT_FinMile | 31/03/2017 | 31/03/2017 | 19/04/2017 | 19/04/2017 | 0 | TK_Complete | CCGTD1_IPS
SBTH2BA8 | blue | BA8 - Consent to 1st Amendment (Major) for pile caps and tie beams within Turbine Hall {7b1} | TT_FinMile | 02/07/2017 | 02/07/2017 | 27/06/2017 | 27/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SBTH3BA5 | red | BA5 - Approval to 2nd Amendment (Type II) for pile caps and tie beams within Turbine Hall {7b2} | TT_Task | 07/08/2017 | 06/09/2017 | 30/06/2017 | 26/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SBTH3BA8 | red | BA8 - Consent to 2nd Amendment (Type II) for pile caps and tie beams within Turbine Hall {7b2} | TT_Task | 07/08/2017 | 05/09/2017 | 30/06/2017 | 26/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SPHS1BA5XX | blue | BA5 - (1st) BD Approval to Structural Plan for superstructures of HRSG, Stack, Stair Towers, Rack &amp; Platforms | TT_FinMile | 02/07/2017 | 02/07/2017 | 30/06/2017 | 30/06/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 30/06/2017
SPSB2BA5 | red | BA5 - Approval to (2nd) Amendment for superstructures for Turbine Hall {7d2} | TT_Task | 15/06/2017 | 14/07/2017 | 19/06/2017 | 18/07/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 14/06/2017
SPTH2BA5 | red | BA5 - Approval to (1st) Amendment for superstructures for Turbine Hall {7d1} | TT_Task | 26/05/2017 | 24/06/2017 | 25/04/2017 | 24/05/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 25/05/2017
SPTH3BA5XX | blue | BA5 - Approval to (Minor) Amendment for superstructures for Turbine Hall {7d1} | TT_FinMile | 02/07/2017 | 02/07/2017 | 01/07/2017 | 01/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SPTH3BA8 | red | BA8 - Consent to Amendment for superstructures for Turbine Hall {7d2} | TT_Task | 07/08/2017 | 05/09/2017 | 19/07/2017 | 01/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SPTHaBA5XX | blue | BA5 - (1st) BD Approval to Structural Plan for maintenance platforms and pipe racks within Turbine Hall | TT_FinMile | 14/07/2017 | 14/07/2017 | 14/07/2017 | 14/07/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 14/07/2017
THCL1BA5 | red | BA5 - (1st) BD Approval to Cladding Plan for Turbine Hall (incl' Switchgear Block) [DISAPPROVED] {7e} | TT_Task | 07/08/2017 | 05/10/2017 | 09/05/2017 | 04/07/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 08/07/2017
THCL2BA5 | red | BA5 - Approval to Resubmission of Cladding Plan for Turbine Hall (incl' Switchgear Block) [WITHDRWN] {7e(r1)} | TT_Task | 11/08/2017 | 10/10/2017 | 15/08/2017 | 12/10/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 11/08/2017
THCL2BA5a | red | BA5 - Approval to Resubmission of Cladding Plan for Turbine Hall (incl' Switchgear Block) {7e(r2)} | TT_Task | 11/08/2017 | 10/10/2017 | 12/10/2017 | 05/12/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 11/08/2017
THCL2BA5b | red | BA5 - Approval to 1st Amendment of Cladding Plan for Turbine Hall (incl' Switchgear Block) {7e(r2)(i)} | TT_Task | 11/08/2017 | 10/10/2017 | 15/02/2018 | 15/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 11/08/2017
THCL2BA8 | red | BA8 - (1st) BD Consent to Cladding Plan for Turbine Hall (incl' Switchgear Block) {7e(r2)} AD-TBC | TT_Task | 16/03/2018 | 14/04/2018 | 16/03/2018 | 14/04/2018 | 0 | TK_Complete | CCGTD1_IPS
POWe1BA5 | blue | BA5 - (1st) BD Approval to ELS Plans for substructures {7c2} | TT_FinMile | 21/05/2017 | 21/05/2017 | 19/05/2017 | 19/05/2017 | 0 | TK_Complete | CCGTD1_IPS
POWe1BA8 | blue | BA8 - (1st) BD Consent to ELS Plans for substructures {7c2} | TT_FinMile | 25/06/2017 | 25/06/2017 | 14/07/2017 | 14/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SFA-BA58 | red | BA5 - Amendment (Minor) for Temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only){4b4-2}[WITHDRAWN] | TT_Task | 03/11/2017 | 01/01/2018 | 16/11/2017 | 11/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SFA-BA58a | red | BA5 - Amendment (Minor) for Temp.works for Shaft A, Pump Station, Diversion Culvert (Wall Only){4b4-2(r1)} [WITHDRAWN] | TT_Task | 27/11/2017 | 25/12/2017 | 21/12/2017 | 02/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SFA-BA58a1 | red | BA5 - Amendment (Minor) for Temp.works for Shaft A, Pump Sttn, Div. Culvert (Wall Only){4b4-2(r2)} | TT_Task | 27/11/2017 | 25/12/2017 | 02/01/2018 | 30/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SFA-BA58b | red | BA8 - Consent for Temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only){4b4-2(r1)} [N.A.] | TT_Task | 26/02/2018 | 25/03/2018 | 30/01/2018 | 30/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SFA_BA58 | red | BA5 - Amendment (Major) for Temporary works for Shaft A, Pump Station, Diversion Culvert (Excav &amp; ELS) {4b5}[WITHDRAWN] | TT_Task | 30/11/2017 | 28/02/2018 | 05/12/2017 | 11/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SFA_BA58a | red | BA5 - Amendment (Major) for Temp.works for Shaft A, Pump Station, Diversion Culvert (Excav &amp; ELS) {4b4-3} [WITHDRAWN] | TT_Task | 12/03/2018 | 11/05/2018 | 14/02/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 08/01/2018
SFA_BA58a1 | red | BA5 - Amendment (Minor) for Temp.works for Shaft A, Pump Station, Diversion Culvert (Excav &amp; ELS) {4b4-3(r1)} [APPROVED] | TT_Task | 12/03/2018 | 10/04/2018 | 23/03/2018 | 24/04/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 08/01/2018
SFA_BA58b | red | BA5 - Consent for Temporary works for Shaft A, Pump Station, Diversion Culvert (Excav &amp; ELS) {4b4-4} | TT_Task | 26/05/2018 | 22/06/2018 | 28/06/2018 | 25/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SFD_BA05 | red | BA5 - Resubmission of Temp works for Shaft D (Wall Only) {4b3(r2)} | TT_Task | 06/10/2017 | 04/12/2017 | 09/10/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 06/10/2017
SFD_BA05a | red | BA5 - Resubmission of Temp works for Shaft D (Excav &amp; ELS) {4b3(r2)-1} | TT_Task | 23/04/2018 | 21/06/2018 | 13/03/2018 | 15/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SFDt1BA8 | red | BA8 - (1st) Consent for Shaft D (Pipe Pile Wall &amp; Grout Curtain) {4b3(r2)} | TT_Task | 26/02/2018 | 27/03/2018 | 19/01/2018 | 12/02/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 03/01/2018
SFDt1BA8a | red | BA8 - Consent for Shaft D (Excav &amp; ELS) {4b3a(r2)-1}[WITHDRAWN] | TT_Task | 14/06/2018 | 11/07/2018 | 21/05/2018 | 18/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SFE-BA58 | red | BA5 &amp; BA8 - Amendment (Major) for Temp.works for Shaft E &amp; Discharge Culvert (alt sheet pile)[WITHDRAWN]{4b2-1} | TT_Task | 04/11/2017 | 03/12/2017 | 21/07/2017 | 08/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SFE_BA58 | red | BA5 &amp; BA8 - Amendment (Type II) for Temp.works for Shaft E &amp; Discharge Culvert (Wall only){4b2-1(r)} | TT_Task | 06/10/2017 | 04/12/2017 | 06/10/2017 | 03/11/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 06/10/2017
SFE_BA58a | red | BA5 - Amendment (pipe jacking) for Temp.works for Shaft E &amp; Discharge Culvert (Excav. &amp; ELS){4b2-2) [WITHDRAWN] | TT_Task | 26/02/2018 | 27/04/2018 | 14/02/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 17/01/2018
SFE_BA58a1 | red | BA5 - Amendment (pipe jacking) for Temp.works for Shaft E &amp; Discharge Culvert (Excav. &amp; ELS){4b2-2(r1)} {APPROVED] | TT_Task | 26/02/2018 | 27/03/2018 | 23/03/2018 | 24/04/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 17/01/2018
SFE_BA58b | red | BA8 - Consent (pipe jacking) for Temp.works for Shaft E &amp; Discharge Culvert (Excav. &amp; ELS){4b2-2(r1)} | TT_Task | 11/06/2018 | 08/07/2018 | 04/05/2018 | 06/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF-BA58 | red | BA5 &amp; BA8 - Amendment to Zone A Sheet Pile Alternative [WITHDRA WN] {4b1i} | TT_Task | 22/06/2017 | 21/07/2017 | 23/06/2017 | 07/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SFF-BA58a | red | BA5 - Resub.of (Type II) Amendment for Zone A Sheet Pile Alternative {4b1-alt A-1} [APPROVED AS TYPE I] | TT_Task | 27/11/2017 | 26/12/2017 | 24/07/2017 | 22/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SFF-BA58b | red | BA8 - Consnet for Zone A Sheet Pile Alternative {4b1-alt A-1} | TT_Task | 22/06/2017 | 19/07/2017 | 29/08/2017 | 25/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SFF-BA58b1 | red | BA5 &amp; BA8 - Shaft F (Type II) Amendment - Delink Effluent Pit {4b1-4} [APPROVED] | TT_Task | 23/04/2018 | 22/05/2018 | 08/03/2018 | 10/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF-BA58b2 | red | BA5 &amp; BA8 - Shaft F (Type II) Amendment - Increase AAA Level and Pumping Test {4b1-5} [WITHDRAWAL] | TT_Task | 27/05/2018 | 23/06/2018 | 26/04/2018 | 18/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF-BA58b3 | red | BA5 &amp; BA8 - Shaft F (Type II) Amendment - Increase AAA Level and Pumping Test {4b1-5(r1)} | TT_Task | 27/05/2018 | 25/06/2018 | 18/05/2018 | 22/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF-BA58c | red | BA5 - Submission of Zone C / Resequencing (originally an Alternative but resubmitted &amp; approved as a Major Rev) {4b1-?} | TT_Task | 26/01/2019 | 26/03/2019 | 24/12/2018 | 06/03/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 14/12/2018
SFF-BA58d | red | BA8 - Consent for Zone C / Resequencing {4b1-?} | TT_Task | 27/04/2019 | 24/05/2019 | 25/02/2019 | 22/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF_BA58 | red | BA5 - Submission of Zone B Open Cut Alternative {4b1-alt B} [APPROVED] | TT_Task | 22/06/2017 | 19/09/2017 | 22/06/2017 | 18/08/2017 | 0 | TK_Complete | CCGTD1_IPS
SFF_BA58a | red | BA8 - Consent for Zone B Open Cut Alternative {4b1-alt B} | TT_Task | 26/06/2018 | 23/07/2018 | 04/05/2018 | 26/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SCW-BA58 | red | BA5 - Alternative for Temp works for SCW &amp; Culvert Modifi (Wall Only)(Dry){5b1-alt} [DISAPPROVED] | TT_Task | 28/11/2017 | 26/01/2018 | 21/12/2017 | 06/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SCW_BA58 | red | BA5 - Alternative for Temp works for SCW &amp; Culvert Modif (Excav)(Dry){5b1-alt} [DISAPPROVED] | TT_Task | 28/11/2017 | 26/01/2018 | 21/12/2017 | 06/02/2018 | 0 | TK_Complete | CCGTD1_IPS
POW_BA58 | red | BA5 &amp; BA8 - Amendment for Excav &amp; ELS Plan for Power Island Area (Open Cut)(Phase 1 &amp; 2){7c2i} | TT_Task | 22/06/2017 | 19/09/2017 | 22/06/2017 | 25/09/2017 | 0 | TK_Complete | CCGTD1_IPS
POW_BA58_1 | red | BA8 - Consent for Excav &amp; ELS Plan for Power Island Area (Open Cut)(Phase 3){7c2i} | TT_Task | 22/06/2017 | 19/09/2017 | 26/09/2017 | 20/10/2017 | 0 | TK_Complete | CCGTD1_IPS
POW_BA58_2 | red | BA5 &amp; BA8 -Type II Amendment Power Island Open Cut (Phase 1,2,3) {7c2ii} | TT_Task | 22/06/2017 | 19/09/2017 | 26/10/2017 | 23/11/2017 | 0 | TK_Complete | CCGTD1_IPS
POW_BA58_3 | red | BA5 &amp; BA8 -Type II Amendment (for grout curtain) Power Island Open Cut (Phase 1,2,3){7c2iii} | TT_Task | 22/06/2017 | 19/09/2017 | 15/12/2017 | 09/01/2018 | 0 | TK_Complete | CCGTD1_IPS
POW_BA58_4 | red | BA8 -Consent for Power Island Open Cut (Phase 4){7c2iii}[WITHDRAWN] | TT_Task | 23/04/2018 | 20/05/2018 | 04/05/2018 | 30/05/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB05 | red | Supervision Plans - Preparation and Submission to RO | TT_Task | 29/05/2017 | 11/06/2017 | 29/05/2017 | 11/06/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB06 | red | Supervision Plans - RO Review and Comment | TT_Task | 12/06/2017 | 18/06/2017 | 12/06/2017 | 18/06/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB10 | red | Structural Steel Shop Drawing &amp; Calculation - Preparation and Submission to RO (1st round) | TT_Task | 01/09/2017 | 28/09/2017 | 01/09/2017 | 02/11/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB11 | red | Structural Steel Shop Drawing &amp; Calculation - RO Review and Comment (1st round) | TT_Task | 13/11/2017 | 26/11/2017 | 03/11/2017 | 23/11/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB15 | red | Roof Cladding Shop Drawing &amp; Calculation - RO Review and Comment | TT_Task | 26/02/2018 | 11/03/2018 | 27/01/2018 | 05/02/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB16 | red | Roof Cladding Shop Drawing &amp; Calculation - RO Comment and Approval | TT_Task | 26/03/2018 | 08/04/2018 | 10/02/2018 | 13/02/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB20 | red | Irrigation Shop Drawing - RO Review and Comment | TT_Task | 08/03/2019 | 04/04/2019 | 24/03/2018 | 10/10/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB21 | red | Irrigation Shop Drawing - RO Comment and Approval | TT_Task | 19/04/2019 | 02/05/2019 | 20/07/2018 | 12/02/2019 | 0 | TK_Complete | CCGTD1_IPS
GENSUB25 | red | Lift Shop Drawing - RO Review and Comment (AD TBC) | TT_Task | 14/06/2018 | 27/06/2018 | 14/06/2018 | 27/06/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB26 | red | Lift Shop Drawing - RO Comment and Approval (AD TBC) | TT_Task | 04/08/2018 | 10/08/2018 | 05/07/2018 | 11/07/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB30 | red | CWP Manufacturing Drawing - Preparation and Submission to RO | TT_Task | 26/02/2018 | 16/03/2018 | 31/12/2017 | 18/01/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB31 | red | CWP Manufacturing Drawing - RO Review and Comment | TT_Task | 17/03/2018 | 23/03/2018 | 19/01/2018 | 25/01/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB35 | red | Precast Concrete Intake Chamber - Submission of Quality Plan and Inspection Plan (Approval status TBC) | TT_Task | 26/11/2018 | 09/12/2018 | 03/08/2018 | 19/11/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB36 | red | Precast Concrete Intake Chamber Fabrication Drawing - Preparation and Submission to RO | TT_Task | 26/12/2018 | 24/01/2019 | 04/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB37 | red | Precast Concrete Intake Chamber Fabrication Drawing - RO Review and Comment | TT_Task | 27/01/2019 | 25/02/2019 | 01/01/2019 | 31/01/2019 | 0 | TK_Complete | CCGTD1_IPS
GENSUB40 | red | TTM for Pumping Station - Preparation and Submission to RO | TT_Task | 08/08/2017 | 21/08/2017 | 08/08/2017 | 07/09/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB40a | red | TTM for Pumping Station - RO Review and Comment [APPROVED] | TT_Task | 27/11/2017 | 10/12/2017 | 08/09/2017 | 29/11/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB40b | red | TTM for Pumping Station - Issue of LWC for barricading the areas | TT_Task | 27/11/2017 | 27/11/2017 | 30/11/2017 | 05/12/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB40c | red | TTM for Pumping Station - Barrication as per approved site layout and TTM | TT_Task | 27/11/2017 | 27/11/2017 | 05/12/2017 | 05/12/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB41 | red | TTM for Pumping Station - Declaration of unplanted area | TT_Task | 11/09/2017 | 24/09/2017 | 06/12/2017 | 16/12/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB50 | red | TTM for Shaft D - Preparation and Submission to RO | TT_Task | 16/12/2017 | 29/12/2017 | 08/08/2017 | 07/09/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB50a | red | TTM for Shaft D - RO Review and Comment [APPROVED] | TT_Task | 27/11/2017 | 10/12/2017 | 08/09/2017 | 27/12/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB50b | red | TTM for Shaft D - Issue of LWC to barricade the proposed temp. EVA location | TT_Task | 01/03/2018 | 01/03/2018 | 28/12/2017 | 28/12/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB50b1 | red | TTM for Shaft D - LWC 14 day expiry period | TT_Task | 01/03/2018 | 14/03/2018 | 29/12/2017 | 11/01/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB50c | red | TTM for Shaft D - Barrication as per approved temporary EVA location | TT_Task | 02/03/2018 | 07/03/2018 | 29/12/2017 | 03/01/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB50d | red | TTM for Shaft D - Issue of XP for EVA diversion | TT_Task | 08/03/2018 | 08/03/2018 | 04/01/2018 | 26/01/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB50d1 | red | TTM for Shaft D - Extend expired LWC | TT_Task | 08/03/2018 | 08/03/2018 | 27/01/2018 | 29/01/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB50e | red | TTM for Shaft D - Construct temporary EVA | TT_Task | 23/04/2018 | 26/04/2018 | 26/02/2018 | 01/03/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB50f | red | TTM for Shaft D - Issue of LWC to barricade the proposed site area | TT_Task | 27/04/2018 | 30/04/2018 | 02/03/2018 | 06/03/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB51 | red | TTM for Shaft D - Declaration of unplanted area | TT_Task | 01/05/2018 | 07/05/2018 | 07/03/2018 | 18/03/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB60 | red | TTM for Sea Bank Road - Preparation and Submission to RO | TT_Task | 31/08/2017 | 13/09/2017 | 08/08/2017 | 07/09/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB60a | red | TTM for Sea Bank Road - RO Review and Comment [APPROVED] | TT_Task | 27/11/2017 | 10/12/2017 | 08/09/2017 | 27/12/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB60b | red | TTM for Sea Bank Road - Issue of LWC to barricade the proposed hammer head locations | TT_Task | 01/03/2018 | 01/03/2018 | 28/12/2017 | 28/12/2017 | 0 | TK_Complete | CCGTD1_IPS
GENSUB60b1 | red | TTM for Sea Bank Road - LWC 14 day expiry period | TT_Task | 01/03/2018 | 14/03/2018 | 29/12/2017 | 11/01/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB60c | red | TTM for Sea Bank Road - Barrication as per approved hammer head locations | TT_Task | 02/03/2018 | 07/03/2018 | 29/12/2017 | 03/01/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB60d | red | TTM for Sea Bank Road - Issue of XP for hammer heads construction | TT_Task | 08/03/2018 | 08/03/2018 | 04/01/2018 | 26/01/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB60d1 | red | TTM for Sea Bank Road - Extend expired LWC | TT_Task | 08/03/2018 | 08/03/2018 | 27/01/2018 | 29/01/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB60e | red | TTM for Sea Bank Road - Hammer heads construction | TT_Task | 01/03/2018 | 09/03/2018 | 29/01/2018 | 24/02/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB60f | red | TTM for Sea Bank Road - Issue of LWC to barricade the proposed site area | TT_Task | 23/04/2018 | 26/04/2018 | 02/03/2018 | 06/03/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB61 | red | TTM for Sea Bank Road - Declaration of unplanted area | TT_Task | 27/04/2018 | 03/05/2018 | 07/03/2018 | 18/03/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB80 | red | Wall Cladding Shop Drawing &amp; Calculation - RO Review and Comment | TT_Task | 23/04/2018 | 20/05/2018 | 24/02/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB82 | red | Wall Cladding Shop Drawing &amp; Calculation - RO Comment and Approval (= ready for BD submission) | TT_Task | 23/04/2018 | 06/05/2018 | 14/04/2018 | 24/05/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB84 | red | Wall Cladding - BD Approval | TT_Task | 26/05/2018 | 24/07/2018 | 25/05/2018 | 23/07/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB86 | red | Wall Cladding - BD Consent | TT_Task | 26/08/2018 | 22/09/2018 | 24/08/2018 | 20/09/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 24/08/2018
GENSUB88 | red | Glazing - BD Approval | TT_Task | 26/06/2018 | 24/08/2018 | 20/06/2018 | 21/08/2018 | 0 | TK_Complete | CCGTD1_IPS
GENSUB90 | red | Glazing - BD Consent | TT_Task | 26/11/2018 | 23/12/2018 | 18/10/2018 | 06/11/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 15/09/2018
GENSUB92 | red | Louvre - BD Approval | TT_Task | 26/11/2018 | 24/01/2019 | 19/11/2018 | 15/01/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 15/09/2018
GENSUB94 | red | Louvre - BD Consent | TT_Task | 26/01/2019 | 22/02/2019 | 06/12/2018 | 18/01/2019 | 0 | TK_Complete | CCGTD1_IPS
GENSUB96 | red | Lift Shaft Glazing - BD Approval | TT_Task | 26/11/2018 | 24/01/2019 | 09/11/2018 | 07/01/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 01/10/2018
GENSUB98 | red | Lift Shaft Glazing - BD Consent | TT_Task | 26/01/2019 | 22/02/2019 | 06/12/2018 | 11/01/2019 | 0 | TK_Complete | CCGTD1_IPS
GENSUB9A | red | Aluminum - BD Approval | TT_Task | 26/11/2018 | 24/01/2019 | 08/11/2018 | 07/01/2019 | 0 | TK_Complete | CCGTD1_IPS
GENSUB9B | red | Aluminum - BD Consent | TT_Task | 26/01/2019 | 22/02/2019 | 06/12/2018 | 11/01/2019 | 0 | TK_Complete | CCGTD1_IPS
SFAtSA10 | red | Submission and approval of temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only) {4b4-2} | TT_Task | 04/07/2017 | 17/07/2017 | 04/07/2017 | 20/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SFAtSA20 | red | Submission and approval of temporary works for Shaft A, Pump Station, Diversion Culvert (Excav. &amp; ELS) - for MS-03 {4b5} | TT_Task | 07/08/2017 | 15/08/2017 | 07/08/2017 | 05/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SFAtSA21 | red | Submission and approval of temporary works for Shaft A, Pump Station, Diversion Culvert (Excav. &amp; ELS) {4b5} | TT_Task | 05/09/2017 | 18/09/2017 | 05/09/2017 | 12/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SFDtSA10 | red | Submission and approval of temporary works for Shaft D (Wall, Excav. &amp; ELS) {4b3(r1)} | TT_Task | 02/06/2017 | 15/06/2017 | 08/06/2017 | 20/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SFEtSA09 | red | Submission and approval of temporary works for Shaft E and Discharge Culvert (Wall, Excav. &amp; ELS) - for MS-03 {4b2i-1} | TT_Task | 07/08/2017 | 15/08/2017 | 03/07/2017 | 20/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SFEtSA10 | red | Submission and approval of temporary works for Shaft E and Discharge Culvert (Wall, Excav. &amp; ELS) {4b2-1} | TT_Task | 05/10/2017 | 03/11/2017 | 03/07/2017 | 20/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SFFtSA10 | red | Submission and approval of temporary works for Shaft F (Skin Wall) &amp; Double Pipe (Southern Sheet Pile) {4b1i} | TT_Task | 10/06/2017 | 21/06/2017 | 09/06/2017 | 22/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SFFtSA10a | red | Resubmission and approval of temporary works for Shaft F (Skin Wall) only {4b1-1(r)} | TT_Task | 10/06/2017 | 21/06/2017 | 18/07/2017 | 23/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SFFtSA10b | red | Resubmission and approval of Zone A (Southern Sheet Pile) {4b1-alt A-1} | TT_Task | 10/06/2017 | 21/06/2017 | 19/07/2017 | 23/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SFFtSA20 | red | Submission and approval of temporary works for Shaft F and Double Pipe Trench (Open Cut) {4b1-alt B} | TT_Task | 10/06/2017 | 21/06/2017 | 09/06/2017 | 22/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SCWtSA09 | red | Submission and approval of temporary works for SCW and Intake Culvert Modification (Wall Only) - for MS-05 {5b1(r)} | TT_Task | 17/08/2017 | 30/08/2017 | 17/08/2017 | 19/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SCWtSA10 | red | Submission and approval of temporary works for SCW and Intake Culvert Modification (Wall Only) {5b1-alt} | TT_Task | 17/08/2017 | 30/08/2017 | 17/08/2017 | 19/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SCWtSA19 | red | Submission and approval of temporary works for SCW and Intake Culvert Modification (Excav &amp; ELS) - for MS-05 {5b1(r)} | TT_Task | 17/08/2017 | 30/08/2017 | 17/08/2017 | 19/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SCWtSA20 | red | Submission and approval of temporary works for SCW and Intake Culvert Modification (Excav &amp; ELS) {5b1-alt} | TT_Task | 17/08/2017 | 30/08/2017 | 17/08/2017 | 19/12/2017 | 0 | TK_Complete | CCGTD1_IPS
OAMtSA10 | red | Submission and approval of temporary works for Outfall Apron Modification | TT_Task | 07/01/2018 | 03/02/2018 | 16/11/2017 | 10/01/2018 | 0 | TK_Complete | CCGTD1_IPS
POWtSA10 | red | Submission and approval of temporary works for Power Island Area (Open Cut) {7c2i} | TT_Task | 10/06/2017 | 21/06/2017 | 10/06/2017 | 21/06/2017 | 0 | TK_Complete | CCGTD1_IPS
TWORK010XX | blue | Temporary Works designed by Contractor - Batch 1 ready for submission | TT_FinMile | 11/06/2017 | 11/06/2017 | 11/06/2017 | 11/06/2017 | 0 | TK_Complete | CCGTD1_IPS
TWORK020XX | blue | Temporary Works designed by Contractor - Batch 2 ready for submission | TT_FinMile | 27/06/2017 | 27/06/2017 | 27/06/2017 | 27/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SFAtDN10 | red | Review and design temporary works for Shaft A, Pump Station, Diversion Culvert (Wall Only) {4b4-2} | TT_Task | 04/06/2017 | 03/07/2017 | 04/06/2017 | 03/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SFAtDN19 | red | Review and design temporary works for Shaft A, Pump Station, Diversion Culvert (Excavation &amp; ELS) - for MS-03 {4b5} | TT_Task | 28/06/2017 | 11/07/2017 | 28/06/2017 | 25/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SFAtDN20 | red | Review and design temporary works for Shaft A, Pump Station, Diversion Culvert (Excavation &amp; ELS) {4b5} | TT_Task | 07/07/2017 | 04/09/2017 | 07/07/2017 | 04/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SFDtDN10 | red | Review and design temporary works for Shaft D (Wall, Excav. &amp; ELS) {4b3(r1)} | TT_Task | 23/05/2017 | 01/06/2017 | 23/05/2017 | 01/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SFEtDN09 | red | Review and design temporary works for Shaft E and Discharge Culvert (Wall, Excav. &amp; ELS) - for MS-03 {4b2-1} | TT_Task | 28/06/2017 | 11/07/2017 | 12/06/2017 | 02/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SFEtDN10 | red | Review and design temporary works for Shaft E and Discharge Culvert (Wall, Excav. &amp; ELS) {4b2-1} | TT_Task | 05/09/2017 | 04/10/2017 | 12/06/2017 | 02/07/2017 | 0 | TK_Complete | CCGTD1_IPS
SFFtDN20 | red | Review and design temp works for Shaft F &amp; Double Pipe Trench - Shaft F (Skin Wall) &amp; Southern Section Sheet Pile {4b1i} | TT_Task | 27/05/2017 | 09/06/2017 | 27/05/2017 | 09/06/2017 | 0 | TK_Complete | CCGTD1_IPS
SFFtDN30 | red | Review and design temp works for Shaft F &amp; Double Pipe Trench - Open Cut {4b1-alt B} | TT_Task | 27/05/2017 | 09/06/2017 | 27/05/2017 | 09/06/2017 | 0 | TK_Complete | CCGTD1_IPS
ICMtDN09 | red | Review and design temporary works for SCW and Intake Culvert Modification (Wall Only) - for MS-05 {5b1(r)} | TT_Task | 07/08/2017 | 20/08/2017 | 28/07/2017 | 10/08/2017 | 0 | TK_Complete | CCGTD1_IPS
ICMtDN10 | red | Review and design temporary works for SCW and Intake Culvert Modification (Wall Only) {5b1-alt} | TT_Task | 11/08/2017 | 09/09/2017 | 28/07/2017 | 16/08/2017 | 0 | TK_Complete | CCGTD1_IPS
ICMtDN19 | red | Review and design temporary works for SCW and Intake Culvert Modification (Excavation &amp; ELS) - for MS-05 {5b1(r)} | TT_Task | 07/08/2017 | 20/08/2017 | 28/07/2017 | 10/08/2017 | 0 | TK_Complete | CCGTD1_IPS
ICMtDN20 | red | Review and design temporary works for SCW and Intake Culvert Modification (Excavation &amp; ELS) {5b1-alt} | TT_Task | 10/09/2017 | 09/10/2017 | 28/07/2017 | 16/08/2017 | 0 | TK_Complete | CCGTD1_IPS
OAMtDN10 | red | Review and design a temporary bulkhead for Outfall Apron Modification | TT_Task | 29/05/2017 | 27/06/2017 | 12/07/2017 | 06/01/2018 | 0 | TK_Complete | CCGTD1_IPS
POWtDN10 | red | Review and design temporary works for Power Island Area (Open Cut) {7c2i} | TT_Task | 27/05/2017 | 09/06/2017 | 27/05/2017 | 09/06/2017 | 0 | TK_Complete | CCGTD1_IPS
MCGZDN10 | red | Roof Cladding - Review engineer's drawings and prepare design | TT_Task | 16/10/2017 | 12/11/2017 | 16/10/2017 | 26/01/2018 | 0 | TK_Complete | CCGTD1_IPS
MCGZDN20 | red | Roof Cladding - ICE Check and Issue Cert | TT_Task | 26/07/2018 | 08/08/2018 | 10/07/2018 | 23/07/2018 | 0 | TK_Complete | CCGTD1_IPS
MCGZDN30 | red | Roof Cladding - Performance mock-up test (by approved laboratory) | TT_Task | 09/08/2018 | 05/09/2018 | 24/07/2018 | 20/08/2018 | 0 | TK_Complete | CCGTD1_IPS
MCGZDN40 | red | Roof Cladding - Address engineer's comment and prepare resubmission | TT_Task | 12/03/2018 | 25/03/2018 | 06/02/2018 | 09/02/2018 | 0 | TK_Complete | CCGTD1_IPS
MCGZDN50 | red | Roof Cladding - Review engineer's drawings and prepare design | TT_Task | 23/04/2018 | 20/05/2018 | 27/01/2018 | 23/02/2018 | 0 | TK_Complete | CCGTD1_IPS
MCGZDN60 | red | Roof Cladding - Address engineer's comment and prepare resubmission | TT_Task | 23/04/2018 | 20/05/2018 | 24/03/2018 | 13/04/2018 | 0 | TK_Complete | CCGTD1_IPS
IRRIDN10 | red | Irrigation System - Review engineer's drawings and prepare design | TT_Task | 08/02/2019 | 07/03/2019 | 21/02/2018 | 21/09/2018 | 0 | TK_Complete | CCGTD1_IPS
IRRIDN20 | red | Irrigation System - Address engineer's comment and prepare resubmission | TT_Task | 05/04/2019 | 18/04/2019 | 14/06/2018 | 18/01/2019 | 0 | TK_Complete | CCGTD1_IPS
LIFTDN10 | red | Lifts - Review engineer's drawings and prepare design (AD TBC) | TT_Task | 21/12/2017 | 17/01/2018 | 21/12/2017 | 13/06/2018 | 0 | TK_Complete | CCGTD1_IPS
LIFTDN20 | red | Lifts - Address engineer's comment and prepare resubmission (AD TBC) | TT_Task | 28/07/2018 | 03/08/2018 | 28/06/2018 | 04/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV005010 | red | Event 005 - New Requirements on Lift No.1 | TT_Task | 27/11/2017 | 26/12/2017 | 16/11/2017 | 20/12/2017 | 0 | TK_Complete | CCGTD1_IPS
EV005020 | blue | Event 005 - Award Lift Subcontract | TT_FinMile | 15/12/2017 | 15/12/2017 | 20/12/2017 | 20/12/2017 | 0 | TK_Complete | CCGTD1_IPS
PROSC010 | red | Procurement of Subcontract - Excavation &amp; ELS (and other civil works) | TT_Task | 03/07/2017 | 31/08/2017 | 29/05/2017 | 22/12/2017 | 0 | TK_Complete | CCGTD1_IPS
PROSC020 | red | Procurement of Subcontract - Grouting &amp; Sheet /Pipe Piling | TT_Task | 03/07/2017 | 31/08/2017 | 29/05/2017 | 26/08/2017 | 0 | TK_Complete | CCGTD1_IPS
PROSC030 | red | Procurement of Subcontract - Steel Structure &amp; Heavy Lifting | TT_Task | 03/07/2017 | 15/09/2017 | 29/05/2017 | 24/10/2017 | 0 | TK_Complete | CCGTD1_IPS
PROSC040 | red | Procurement of Subcontract - Standing Seam Roof, Aluminium Cladding &amp; Curtain Wall | TT_Task | 03/07/2017 | 15/09/2017 | 29/05/2017 | 20/12/2017 | 0 | TK_Complete | CCGTD1_IPS
PROSC050 | red | Procurement of Subcontract - CWP Installation (Jacking / TBM) | TT_Task | 03/07/2017 | 15/09/2017 | 29/05/2017 | 19/04/2018 | 0 | TK_Complete | CCGTD1_IPS
PROSC051 | red | Procurement of Subcontract - CWP Installation (Laying in trench) | TT_Task | 27/11/2017 | 09/02/2018 | 29/05/2017 | 04/04/2018 | 0 | TK_Complete | CCGTD1_IPS
PROSC060 | red | Procurement of Subcontract - Building Service Installation (i.e., Elect, ACMV, FS, P&amp;D) | TT_Task | 04/09/2017 | 27/10/2017 | 04/09/2017 | 20/02/2018 | 0 | TK_Complete | CCGTD1_IPS
PROSC070 | red | Procurement of Subcontract - Lift Installation (once awarded to Otis) | TT_Task | 07/08/2017 | 25/09/2017 | 07/08/2017 | 17/10/2017 | 0 | TK_Complete | CCGTD1_IPS
PROSC080 | red | Procurement of Subcontract - Supply of Precast Concrete Structure (i.e. Diversion Culvert) | TT_Task | 26/02/2018 | 14/04/2018 | 05/02/2018 | 01/06/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 27/12/2017
PROPE010 | red | Sourcing, Reconditioning and Delivery of TBM (AD TBC) | TT_Task | 16/06/2018 | 05/10/2018 | 07/05/2018 | 26/08/2018 | 0 | TK_Complete | CCGTD1_IPS
PROPE015 | black | TBM On Site (early date) (AD TBC) | TT_Mile | 26/11/2018 | 26/11/2018 | 26/08/2018 | 26/08/2018 | 0 | TK_Complete | CCGTD1_IPS
PROPE020 | red | Fabrication and Delivery of Lifts (AS / EF TBC) | TT_Task | 11/08/2018 | 25/01/2019 | 12/07/2018 | 22/09/2019 | 0 | TK_Complete | CCGTD1_IPS
PROMA009 | red | Manufacturing and Delivery of CWP materials (1st Batch) (Zone B prioritized) | TT_Task | 26/02/2018 | 20/05/2018 | 22/12/2017 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 31/12/2017
PROMA010 | black | CWP Installation start on site (1st Batch) (Zone A) | TT_Mile | 26/11/2018 | 26/11/2018 | 03/11/2018 | 03/11/2018 | 0 | TK_Complete | CCGTD1_IPS
PROMA011 | red | Manufacturing and Delivery of CWP materials (2nd Batch) | TT_Task | 26/05/2018 | 09/07/2018 | 28/04/2018 | 27/05/2018 | 0 | TK_Complete | CCGTD1_IPS
PROMA012 | red | Manufacturing and Delivery of CWP materials (3rd Batch) | TT_Task | 28/06/2018 | 25/09/2018 | 28/05/2018 | 16/12/2018 | 0 | TK_Complete | CCGTD1_IPS
PROMA013 | red | Manufacturing and Delivery of CWP materials (4th Batch) | TT_Task | 26/01/2019 | 25/04/2019 | 17/12/2018 | 25/05/2019 | 0 | TK_Complete | CCGTD1_IPS
PROMA014 | black | CWP Pipe Jacking start on site (using 3rd Batch Pipe Mtl) | TT_Mile | 01/09/2019 | 01/09/2019 | 09/07/2019 | 09/07/2019 | 0 | TK_Complete | CCGTD1_IPS
PROMA020 | red | Manufacturing and Delivery of Structural Steels (Early Delivery) | TT_Task | 06/11/2017 | 10/12/2017 | 24/11/2017 | 08/12/2017 | 0 | TK_Complete | CCGTD1_IPS
PROMA025 | red | Manufacturing and Delivery of Structural Steels (1st Batch) | TT_Task | 06/03/2018 | 06/03/2018 | 24/11/2017 | 27/03/2018 | 0 | TK_Complete | CCGTD1_IPS
PROMA030 | red | Manufacturing and Delivery Roof /Wall Cladding (1st Batch) | TT_Task | 26/02/2018 | 15/04/2018 | 18/01/2018 | 21/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 18/01/2018
PROMA040 | red | Manufacturing and Delivery of Curtain Wall /Glazing (1st Batch) | TT_Task | 26/11/2018 | 23/02/2019 | 09/11/2018 | 10/01/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 15/09/2018
PROMA050 | red | Fabrication and Delivery of Precast Concrete Intake Chamber | TT_Task | 01/05/2019 | 23/07/2019 | 26/03/2019 | 01/10/2019 | 0 | TK_Complete | CCGTD1_IPS
PROMA060 | red | Procurement and Delivery of Conductor Materials for Earth Mat | TT_Task | 03/07/2017 | 11/08/2017 | 03/07/2017 | 08/09/2017 | 0 | TK_Complete | CCGTD1_IPS
PROMA080 | red | Fabrication and Delivery of Temporary Bulkhead | TT_Task | 14/03/2018 | 17/04/2018 | 19/01/2018 | 12/02/2018 | 0 | TK_Complete | CCGTD1_IPS
CLPSUP05 | blue | OFCI Item No.1 - Cast-in Embedded Items for Turbine Hall and Turbine Table (AD TBC) | TT_FinMile | 30/07/2017 | 30/07/2017 | 18/07/2017 | 18/07/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 30/07/2017
CLPSUP10 | blue | OFCI Item No.2 - Cast-in Embedded Items for HRSG and Stack (AD TBC) | TT_FinMile | 25/09/2017 | 25/09/2017 | 29/08/2017 | 29/08/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 29/08/2017
CLPSUP15 | blue | OFCI Item No.3 - Cast-in Embedded Items for Remaining Plant (AD TBC) | TT_FinMile | 26/02/2018 | 26/02/2018 | 01/02/2018 | 01/02/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 01/02/2018
CLPSUP20 | blue | OFCI Item No.4 - Overhead Cranes (AD TBC) | TT_FinMile | 26/02/2018 | 26/02/2018 | 04/01/2018 | 04/01/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 04/01/2018
CLPSUP45 | blue | OFCI Item No.9 - Crane Walkway (actual dates TBC) | TT_FinMile | 17/12/2017 | 17/12/2017 | 17/12/2017 | 17/12/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 17/12/2017
CLPSUP50 | red | OFCI Item No.,10 - Platforms (actual dates TBC) | TT_Task | 03/11/2017 | 06/04/2018 | 03/11/2017 | 30/04/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 03/11/2017
ESTAB010 | red | Site Establishment - Erect Hoarding | TT_Task | 25/09/2017 | 16/10/2017 | 25/09/2017 | 16/10/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 17/07/2017
ESTAB020 | red | Site Establishment - Site Clearance (incl. Fencing, Wheel Washing Facilities and Hard Standings for Area 2c, 4a, 4b &amp; 5) | TT_Task | 17/07/2017 | 18/08/2017 | 17/07/2017 | 08/09/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 17/07/2017
ESTAB030 | red | Site Establishment - Conduct Survey to Existing Structures and Structural Survey to Cooling Water Outfall Structure | TT_Task | 03/07/2017 | 04/08/2017 | 01/06/2017 | 23/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ESTAB040 | red | Site Establishment - Site Mobilisation Works | TT_Task | 04/07/2017 | 05/08/2017 | 19/06/2017 | 16/10/2017 | 0 | TK_Complete | CCGTD1_IPS
GEOT0010 | red | Site Establishment - Install Instrumentation to Monitor Building Settlment, Ground/Utility Settlement and Vibrations | TT_Task | 28/06/2017 | 25/09/2017 | 26/06/2017 | 11/02/2018 | 0 | TK_Complete | CCGTD1_IPS
EV001010 | red | Event 001 - SCW Penstock Repair 10~16 Sep 2017 | TT_Task | 10/09/2017 | 16/09/2017 | 10/09/2017 | 16/09/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 10/09/2017
EV007010 | red | Event 007 - Approval of Site Arrangement and TTA | TT_Task | 23/10/2017 | 23/10/2017 | 07/09/2017 | 29/11/2017 | 0 | TK_Complete | CCGTD1_IPS
EV007010a | red | Event 007 - Issue of LWC for barricading the areas | TT_Task | 27/11/2017 | 27/11/2017 | 30/11/2017 | 05/12/2017 | 0 | TK_Complete | CCGTD1_IPS
EV007010b | red | Event 007 - Barrication as per approved site layout and TTM | TT_Task | 27/11/2017 | 27/11/2017 | 05/12/2017 | 05/12/2017 | 0 | TK_Complete | CCGTD1_IPS
EV008010 | red | Event 008 - Declaration of unplanted area / Isolation of SCWP(?) | TT_Task | 13/12/2017 | 05/01/2018 | 06/12/2017 | 16/12/2017 | 0 | TK_Complete | CCGTD1_IPS
EV008010a | red | Event 008 - Excavation Permit | TT_Task | 27/11/2017 | 27/11/2017 | 15/12/2017 | 29/12/2017 | 0 | TK_Complete | CCGTD1_IPS
EV009002 | red | Event 009 - 2 nos Pre-drill abortive | TT_Task | 03/03/2018 | 31/03/2018 | 30/12/2017 | 26/01/2018 | 0 | TK_Complete | CCGTD1_IPS
EV009010 | red | Event 009 - Additional Pre-drill (2 out of 4 nos.) | TT_Task | 23/04/2018 | 28/05/2018 | 20/04/2018 | 04/05/2018 | 0 | TK_Complete | CCGTD1_IPS
EV009015 | red | Event 009 - 3rd pre-drill encountered unchartered UU and rigs demob to help out inclinometer and SPT at Shaft F | TT_Task | 26/05/2018 | 11/06/2018 | 05/05/2018 | 28/05/2018 | 0 | TK_Complete | CCGTD1_IPS
EV009020 | red | Event 009 - Additional Pre-drill (remaining 2 nos.) | TT_Task | 29/06/2018 | 16/07/2018 | 29/05/2018 | 23/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV017510 | red | Event 017(I) - Advanced Precautionary Grouting | TT_Task | 26/01/2019 | 08/03/2019 | 27/12/2018 | 09/02/2019 | 0 | TK_Complete | CCGTD1_IPS
EV026010 | red | Event 026 - Tie beam amendment (i.e. steel tie beam, phased consent for excav below +3.5, delete TAM &amp; CS4)[WITHDRAWN] | TT_Task | 26/08/2018 | 30/08/2018 | 24/08/2018 | 28/08/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 24/08/2018
EV026020 | red | Event 026 - Resubmission of tie beam amendment | TT_Task | 13/12/2018 | 11/01/2019 | 13/09/2018 | 14/11/2018 | 0 | TK_Complete | CCGTD1_IPS
EV026030 | red | Event 026 - BA8 consent for APG | TT_Task | 26/12/2018 | 22/01/2019 | 14/11/2018 | 14/12/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 30/11/2018
EV043010 | red | Event 043 - RP11 encounter underground obstruction | TT_Task | 26/11/2018 | 09/12/2018 | 29/09/2018 | 12/10/2018 | 0 | TK_Complete | CCGTD1_IPS
EV043020 | red | Event 043 - RP14, 15, 16 encounter underground obstruction | TT_Task | 26/11/2018 | 23/12/2018 | 01/11/2018 | 29/11/2018 | 0 | TK_Complete | CCGTD1_IPS
EV043030 | red | Event 043 - Socketed H-pile amendment (Type II) [APPROVAL DEEMED] | TT_Task | 26/01/2019 | 24/02/2019 | 27/12/2018 | 25/01/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 27/12/2018
ICM00010 | red | Intake Culvert Modif - Utilities Diversion | TT_Task | 26/05/2018 | 29/06/2018 | 25/04/2018 | 21/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ICM00020 | red | Intake Culvert Modif - Remove parts of existing gantry crane | TT_Task | 01/06/2018 | 16/06/2018 | 06/04/2018 | 21/04/2018 | 0 | TK_Complete | CCGTD1_IPS
ICM00022 | red | Intake Culvert Modif - Remove tie beams of existing gantry foundations | TT_Task | 01/04/2019 | 09/04/2019 | 18/03/2019 | 23/03/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM00025 | red | Intake Culvert Modif - Install socket H-pile (All except RP14-16) | TT_Task | 27/08/2018 | 13/10/2018 | 09/08/2018 | 10/11/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 09/08/2018
ICM00030 | red | Intake Culvert Modif - Install socket H-pile (RP14, RP15, RP16) | TT_Task | 08/02/2019 | 22/02/2019 | 12/01/2019 | 31/01/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM00032 | red | Intake Culvert Modif - CS3 Pipe Pile Wall | TT_Task | 26/01/2019 | 31/01/2019 | 08/01/2019 | 12/01/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 08/01/2019
ICM00033 | red | Intake Culvert Modif - Grout Curtain (behind CS3) | TT_Task | 01/04/2019 | 12/04/2019 | 09/02/2019 | 18/02/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 15/02/2019
ICM00035 | red | Intake Culvert Modif - BA8 consent for excavation below +3.5 and above +2.425 mPD (Zone 1 for Tie Back )(AD TBC) | TT_Task | 03/04/2019 | 30/04/2019 | 31/01/2019 | 29/03/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 31/01/2019
ICM00036 | red | Intake Culvert Modif - Zone 1 excavation to +2.425 mPD | TT_Task | 03/04/2019 | 09/04/2019 | 28/02/2019 | 29/03/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM00040 | red | Intake Culvert Modif - Construct Tie-back system | TT_Task | 10/04/2019 | 21/05/2019 | 25/03/2019 | 15/04/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM00050 | red | Intake Culvert Modif - Remove parts of existing crest wall and fence | TT_Task | 10/09/2018 | 29/09/2018 | 10/09/2018 | 09/10/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 28/08/2018
ICM00060 | red | Intake Culvert Modif - Install silt curtain | TT_Task | 27/08/2018 | 28/08/2018 | 21/08/2018 | 23/08/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 21/08/2018
ICM00070 | red | Intake Culvert Modif - Remove rock armour | TT_Task | 26/11/2018 | 01/12/2018 | 10/10/2018 | 14/10/2018 | 0 | TK_Complete | CCGTD1_IPS
ICM00080 | red | Intake Culvert Modif - Rock fill to form a working platform at +3.5mPD | TT_Task | 03/12/2018 | 05/12/2018 | 15/10/2018 | 14/11/2018 | 0 | TK_Complete | CCGTD1_IPS
ICM10010 | red | Intake Culvert Modif - 406 Dia. Pipe Pile Walls (CS2) | TT_Task | 26/11/2018 | 21/01/2019 | 24/11/2018 | 14/01/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10020 | red | Intake Culvert Modif - Grout Curtain (behind CS2) | TT_Task | 26/01/2019 | 08/03/2019 | 16/01/2019 | 23/02/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10029 | red | Intake Culvert Modif - BA8 consent for excavation below +3.5 and above +2.425 mPD (Zone 2 for Intake Chamber)(AD TBC) | TT_Task | 31/03/2019 | 27/04/2019 | 28/02/2019 | 29/03/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10030 | red | Intake Culvert Modif - Zone 2 Excavate to +2.425mPD | TT_Task | 01/05/2019 | 07/05/2019 | 10/04/2019 | 18/04/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10040 | red | Intake Culvert Modif - Install twin batten waling frame | TT_Task | 01/05/2019 | 07/05/2019 | 22/04/2019 | 26/04/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10045 | red | Intake Culvert Modif - BA8 consent for excavation below +2.425 mPD (AD TBC) | TT_Task | 31/03/2019 | 27/04/2019 | 28/02/2019 | 29/03/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10050 | red | Intake Culvert Modif - Excavate to top of existing intake culvert | TT_Task | 01/05/2019 | 07/05/2019 | 27/04/2019 | 29/05/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10060 | red | Intake Culvert Modif - Install staging platform | TT_Task | 06/06/2019 | 11/07/2019 | 29/05/2019 | 21/06/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10070 | red | Intake Culvert Modif - Saw cut and remove the existing box culvert at the location of proposed diversion chamber | TT_Task | 01/08/2019 | 24/08/2019 | 18/07/2019 | 24/09/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10080 | red | Intake Culvert Modif - Excavate either side of culvert to -5.4mPD | TT_Task | 10/08/2019 | 11/08/2019 | 22/06/2019 | 17/07/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10090 | red | Intake Culvert Modif - Prepare bedding and leveling | TT_Task | 01/11/2019 | 06/11/2019 | 25/09/2019 | 15/10/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10100 | red | Intake Culvert Modif - Install precast segments for the base slab | TT_Task | 01/11/2019 | 01/11/2019 | 16/10/2019 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10110 | red | Intake Culvert Modif - Tremie concrete to segment joints of base slab | TT_Task | 01/11/2019 | 01/11/2019 | 21/10/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10120 | red | Intake Culvert Modif - Install precast segments for the columns and side walls | TT_Task | 03/11/2019 | 04/11/2019 | 18/10/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10130 | red | Intake Culvert Modif - Tremie concrete to segment joints of columns and side walls | TT_Task | 02/11/2019 | 03/11/2019 | 21/10/2019 | 15/11/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10140 | red | Intake Culvert Modif - Install precast segments for top slab and beams | TT_Task | 07/11/2019 | 07/11/2019 | 20/10/2019 | 20/10/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10150 | red | Intake Culvert Modif - Tremie concrete to segment joints of top slab | TT_Task | 04/11/2019 | 04/11/2019 | 22/10/2019 | 28/10/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10170 | red | Intake Culvert Modif - Backfill between the proposed chamber and pipe pile walls | TT_Task | 23/11/2019 | 04/12/2019 | 21/10/2019 | 15/11/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10180 | red | Intake Culvert Modif - Reinstate the seawall and rock armour to 0.5m below the shoring | TT_Task | 09/01/2020 | 11/01/2020 | 11/12/2019 | 13/12/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10190 | red | Intake Culvert Modif - Remove twin batten waling frame | TT_Task | 09/01/2020 | 13/01/2020 | 16/11/2019 | 20/11/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10200 | red | Intake Culvert Modif - Backfill and reinstate the crest wall and fence | TT_Task | 16/01/2020 | 22/01/2020 | 16/01/2020 | 22/01/2020 | 0 | TK_Complete | CCGTD1_IPS
ICM10210 | red | Intake Culvert Modif - Install temporary penstock at the connection with Diversion Culvert | TT_Task | 24/11/2019 | 26/11/2019 | 16/10/2019 | 20/10/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10220 | red | Intake Culvert Modif - Observe and repair leaks | TT_Task | 06/01/2020 | 09/01/2020 | 06/11/2019 | 09/11/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10230 | red | Intake Culvert Modif - Make good interior surface | TT_Task | 24/01/2020 | 30/01/2020 | 21/10/2019 | 15/11/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10240 | red | Intake Culvert Modif - Remove temporary penstock | TT_Task | 15/02/2020 | 16/02/2020 | 19/12/2019 | 20/12/2019 | 0 | TK_Complete | CCGTD1_IPS
ICM10250 | red | Intake Culvert Modif - Reinstate existing utilities and gantry crane | TT_Task | 09/01/2020 | 22/01/2020 | 16/12/2019 | 28/02/2020 | 0 | TK_Complete | CCGTD1_IPS
EV007011 | red | Event 007 - Approval of Site Arrangement and TTA | TT_Task | 23/10/2017 | 23/10/2017 | 07/09/2017 | 29/11/2017 | 0 | TK_Complete | CCGTD1_IPS
EV007011a | red | Event 007 - Issue of LWC for barricading the areas | TT_Task | 27/11/2017 | 27/11/2017 | 30/11/2017 | 05/12/2017 | 0 | TK_Complete | CCGTD1_IPS
EV007011b | red | Event 007 - Barrication as per approved site layout and TTM | TT_Task | 27/11/2017 | 27/11/2017 | 05/12/2017 | 05/12/2017 | 0 | TK_Complete | CCGTD1_IPS
EV008011 | red | Event 008 - Declaration of unplanted area | TT_Task | 13/12/2017 | 30/12/2017 | 06/12/2017 | 16/12/2017 | 0 | TK_Complete | CCGTD1_IPS
EV008011a | red | Event 008 - Excavation Permit | TT_Task | 27/11/2017 | 27/11/2017 | 15/12/2017 | 29/12/2017 | 0 | TK_Complete | CCGTD1_IPS
EV017110 | red | Event 017 - Diversion Culvert APG | TT_Task | 06/12/2018 | 03/01/2019 | 11/10/2018 | 27/11/2018 | 0 | TK_Complete | CCGTD1_IPS
EV019120 | red | Event 019 - Diversion Culvert C1 plate load test | TT_Task | 01/11/2019 | 05/11/2019 | 04/10/2019 | 08/10/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC00010 | red | Diversion Culvert - Utilities Diversion Stage 1 | TT_Task | 27/08/2018 | 31/08/2018 | 14/08/2018 | 18/08/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 14/08/2018
IBC00020 | red | Diversion Culvert - Utilities Diversion Stage 2 | TT_Task | 26/01/2019 | 18/02/2019 | 30/12/2018 | 21/01/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 15/12/2018
IBC00030 | red | Diversion Culvert - Utilities Diversion Stage 3 | TT_Task | 26/01/2019 | 18/02/2019 | 22/01/2019 | 12/02/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10010 | red | Diversion Culvert - Pipe pile along the inner cofferdam wall alignment | TT_Task | 26/12/2018 | 06/02/2019 | 12/12/2018 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10030 | red | Diversion Culvert - Grout curtain along the inner cofferdam wall alignment | TT_Task | 08/04/2019 | 11/05/2019 | 28/03/2019 | 24/05/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10050 | red | Diversion Culvert - Install silt curtain | TT_Task | 27/08/2018 | 28/08/2018 | 21/08/2018 | 23/08/2018 | 0 | TK_Complete | CCGTD1_IPS
IBC10060 | red | Diversion Culvert - Remove parts of crest wall and fence | TT_Task | 26/11/2018 | 08/12/2018 | 03/09/2018 | 08/09/2018 | 0 | TK_Complete | CCGTD1_IPS
IBC10070 | red | Diversion Culvert - Remove rock armour from the existing seawall | TT_Task | 03/12/2018 | 08/12/2018 | 10/09/2018 | 22/09/2018 | 0 | TK_Complete | CCGTD1_IPS
IBC10080 | red | Diversion Culvert - Rock fill to +4mPD to form temporary piling platform | TT_Task | 10/12/2018 | 12/12/2018 | 24/09/2018 | 06/10/2018 | 0 | TK_Complete | CCGTD1_IPS
IBC10090 | red | Diversion Culvert - Pipe pile along the outer cofferdam wall alignment | TT_Task | 26/12/2018 | 01/02/2019 | 01/12/2018 | 11/04/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10100 | red | Diversion Culvert - Grout curtain along the outer cofferdam wall alignment | TT_Task | 01/04/2019 | 04/05/2019 | 04/03/2019 | 24/05/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10110 | red | Diversion Culvert - Pumping Test and Report Submission (C1) | TT_Task | 01/08/2019 | 21/08/2019 | 01/06/2019 | 13/06/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10115 | red | Diversion Culvert - Pumping Test and Report Submission (C2) | TT_Task | 01/08/2019 | 21/08/2019 | 08/06/2019 | 11/07/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10120 | red | Diversion Culvert - BD Consent for Commencement of Excavation &amp; ELS (C1) | TT_Task | 15/08/2019 | 11/09/2019 | 06/06/2019 | 16/07/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10125 | red | Diversion Culvert - BD Consent for Commencement of Excavation &amp; ELS (C2) [APPROVAL DEEMED] | TT_Task | 01/08/2019 | 28/08/2019 | 12/07/2019 | 04/09/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10140 | red | Diversion Culvert - Excavate to 0.5m below 1st layer of struts | TT_Task | 01/08/2019 | 05/08/2019 | 17/06/2019 | 24/06/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10150 | red | Diversion Culvert - Install 1st layer of struts and temporary support to existing utilities | TT_Task | 01/08/2019 | 05/08/2019 | 25/06/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10160 | red | Diversion Culvert - Excavate to 0.5m below 2nd layer of struts | TT_Task | 01/08/2019 | 04/08/2019 | 27/07/2019 | 25/08/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10170 | red | Diversion Culvert - Install 2nd layer of struts | TT_Task | 09/09/2019 | 20/09/2019 | 15/08/2019 | 29/08/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10180 | red | Diversion Culvert - Excavate to 0.5m below 3rd layer of struts | TT_Task | 01/09/2019 | 08/09/2019 | 27/08/2019 | 04/09/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10190 | red | Diversion Culvert - Install 3rd layer of struts | TT_Task | 02/11/2019 | 09/11/2019 | 02/09/2019 | 13/09/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10200 | red | Diversion Culvert - Excavate to 0.5m below 4th layer struts | TT_Task | 01/11/2019 | 09/11/2019 | 14/09/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10210 | red | Diversion Culvert - Install 4th layer of struts | TT_Task | 01/11/2019 | 08/11/2019 | 26/09/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10220 | red | Diversion Culvert - Excavate to final excavation level -5.5 mPD | TT_Task | 01/11/2019 | 08/11/2019 | 01/10/2019 | 22/10/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10230 | red | Diversion Culvert (C1) - Cast base slab and walls to 0.5m below 4th layer of struts | TT_Task | 01/11/2019 | 06/11/2019 | 23/10/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10240 | red | Diversion Culvert - Backfill void between culvert and pipe pile wall to 0.5m below 4th layer of struts | TT_Task | 04/01/2020 | 04/01/2020 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10250 | red | Diversion Culvert - Remove 4th layer of struts | TT_Task | 05/01/2020 | 07/01/2020 | 05/11/2019 | 06/11/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10270 | red | Diversion Culvert (C1) - Cast remaining walls and top slab | TT_Task | 08/01/2020 | 18/01/2020 | 07/11/2019 | 28/11/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10280 | red | Diversion Culvert - Trim the interfacing sheet pile wall adjoining Pumping Station to -5.5 mPD | TT_Task | 17/01/2020 | 18/01/2020 | 07/11/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10290 | red | Diversion Culvert (C1) - Connect Diversion Culvert to Pumping Station | TT_Task | 18/01/2020 | 18/01/2020 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10300 | red | Diversion Culvert - Backfill and reinstate quay wall concrete block to 0.5m below 3rd layer of struts | TT_Task | 02/01/2020 | 06/01/2020 | 03/12/2019 | 24/12/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10310 | red | Diversion Culvert - Remove 3rd layer of struts | TT_Task | 07/01/2020 | 08/01/2020 | 07/12/2019 | 24/12/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10320 | red | Diversion Culvert - Backfill and reinstate quay wall concrete block to 0.5m below 2nd layer of struts | TT_Task | 09/01/2020 | 13/01/2020 | 08/12/2019 | 28/12/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10330 | red | Diversion Culvert - Remove 2nd layer of struts | TT_Task | 14/01/2020 | 15/01/2020 | 11/12/2019 | 28/12/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10340 | red | Diversion Culvert - Backfill and reinstate quay wall concrete block to 0.5m below 1st layer of struts (incl' utilities) | TT_Task | 02/01/2020 | 06/01/2020 | 30/12/2019 | 15/02/2020 | 0 | TK_Complete | CCGTD1_IPS
IBC10350 | red | Diversion Culvert - Remove 1st layer of struts | TT_Task | 17/02/2020 | 18/02/2020 | 17/02/2020 | 18/02/2020 | 0 | TK_Complete | CCGTD1_IPS
IBC10355 | red | Diversion Culvert (C2) - Construction of Diversion Culvert including excavation &amp; ELS | TT_Task | 10/01/2020 | 15/02/2020 | 02/11/2019 | 15/12/2019 | 0 | TK_Complete | CCGTD1_IPS
IBC10360 | red | Diversion Culvert - Backfill and reinstate to ground level including crest wall and fence | TT_Task | 19/02/2020 | 25/02/2020 | 19/02/2020 | 25/02/2020 | 0 | TK_Complete | CCGTD1_IPS
EV016035 | red | Event 016 - Bund Wall Settlement / Preventive grouting (50 nos.) | TT_Task | 26/02/2018 | 22/03/2018 | 02/04/2018 | 03/05/2018 | 0 | TK_Complete | CCGTD1_IPS
EV017035 | red | Event 017P - Advanced Preventive Grouting as per AAA amendment (Part 1 - 66 out of 86) | TT_Task | 26/06/2018 | 24/08/2018 | 02/06/2018 | 25/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV017045 | red | Event 017P - Advanced Preventive Grouting as per AAA amendment (Part 2 - 20 out of 86) | TT_Task | 26/11/2018 | 05/12/2018 | 30/08/2018 | 07/09/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 30/08/2018
EV025100 | red | Event 025P - Preventive grouting stopped as it's being legalized via AAA amendment | TT_Task | 26/06/2018 | 29/06/2018 | 23/06/2018 | 26/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV027010 | red | Event 027 - Finalizing strategy and preparing for resubmission of re-sequencing amendment | TT_Task | 26/08/2018 | 15/09/2018 | 24/08/2018 | 27/09/2018 | 0 | TK_Complete | CCGTD1_IPS
EV027020 | red | Event 027 - BA5 Re-sequencing alternative(by ARUP) prioritizing Pump Station | TT_Task | 15/12/2018 | 12/02/2019 | 28/09/2018 | 13/12/2018 | 0 | TK_Complete | CCGTD1_IPS
EV044010 | red | Event 044 - Plate Load Test PL2 at stratum of Pump Station | TT_Task | 31/03/2019 | 06/04/2019 | 13/03/2019 | 18/03/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10015 | red | CWPS - Pipe Piles | TT_Task | 26/07/2018 | 04/10/2018 | 19/07/2018 | 12/10/2018 | 0 | TK_Complete | CCGTD1_IPS
PPS10020 | red | CWPS - Grout Curtain | TT_Task | 09/01/2019 | 19/02/2019 | 18/10/2018 | 28/11/2018 | 0 | TK_Complete | CCGTD1_IPS
PPS10040 | red | CWPS - Pumping Test and Report Submission | TT_Task | 26/12/2018 | 15/01/2019 | 06/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS
PPS10045 | red | CWPS - BD Consent for Commencement of Excavation &amp; ELS | TT_Task | 26/01/2019 | 22/02/2019 | 31/12/2018 | 01/02/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10050 | red | CWPS - Excavate to 0.5m below 1st layer of struts | TT_Task | 28/01/2019 | 16/02/2019 | 28/12/2018 | 17/01/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10060 | red | CWPS - Install 1st layer of struts | TT_Task | 26/01/2019 | 02/02/2019 | 17/01/2019 | 31/01/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10070 | red | CWPS - Excavate to 0.5m below 2nd layer of struts | TT_Task | 01/04/2019 | 05/04/2019 | 31/01/2019 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10080 | red | CWPS - Install 2nd layer of struts | TT_Task | 01/04/2019 | 08/04/2019 | 15/02/2019 | 21/02/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10090 | red | CWPS - Excavate to 0.5m below 3rd layer of struts | TT_Task | 01/04/2019 | 04/04/2019 | 22/02/2019 | 25/02/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10100 | red | CWPS - Install 3rd layer of struts | TT_Task | 01/04/2019 | 06/04/2019 | 26/02/2019 | 02/03/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10110 | red | CWPS - Excavate to 0.5m below 4th layer struts | TT_Task | 08/04/2019 | 11/04/2019 | 03/03/2019 | 12/03/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10120 | red | CWPS - Install 4th layer of struts | TT_Task | 01/04/2019 | 06/04/2019 | 11/03/2019 | 18/03/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10250 | red | CWPS - Excavate to final excavation level -6.5 mPD | TT_Task | 01/04/2019 | 02/04/2019 | 11/03/2019 | 23/03/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10260 | red | CWPS - Cast base slab | TT_Task | 01/04/2019 | 06/04/2019 | 24/03/2019 | 27/03/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10270 | red | CWPS - Remove 4th layer of struts | TT_Task | 01/04/2019 | 06/04/2019 | 28/03/2019 | 30/03/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10280 | red | CWPS - Construct pumping station RC structures to 0.5m below 3rd layer of strut | TT_Task | 01/05/2019 | 05/05/2019 | 30/03/2019 | 05/04/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10290 | red | CWPS - Backfill the void between RC wall and pipe pile wall to 0.5m below 3rd layer of strut | TT_Task | 01/05/2019 | 02/05/2019 | 05/04/2019 | 06/04/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10300 | red | CWPS - Remove 3rd layer of struts | TT_Task | 03/05/2019 | 04/05/2019 | 06/04/2019 | 10/04/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10310 | red | CWPS - Construct pumping station RC structures to 0.5m below 2nd layer of strut | TT_Task | 05/05/2019 | 10/05/2019 | 09/04/2019 | 18/04/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10320 | red | CWPS - Backfill the void between RC wall and pipe pile wall to 0.5m below 2nd layer of strut | TT_Task | 01/05/2019 | 02/05/2019 | 19/04/2019 | 19/04/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10330 | red | CWPS - Remove 2nd layer of struts | TT_Task | 02/05/2019 | 03/05/2019 | 13/04/2019 | 23/04/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10340 | red | CWPS - Construct pumping station RC structures to 0.5m below 1st layer of strut | TT_Task | 01/05/2019 | 03/05/2019 | 14/04/2019 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10350 | red | CWPS - Install CW pipes between Valve Chamber and Shaft A | TT_Task | 01/01/2020 | 04/01/2020 | 10/12/2019 | 17/12/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10360 | red | CWPS - Backfill the void between RC wall and pipe pile wall to 0.5m below 1st layer of strut | TT_Task | 01/08/2019 | 02/08/2019 | 01/05/2019 | 01/05/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10370 | red | CWPS - Remove 1st layer of struts | TT_Task | 03/05/2019 | 04/05/2019 | 25/04/2019 | 06/05/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10380 | red | CWPS - Cast top slab of Pumping Station | TT_Task | 03/05/2019 | 11/05/2019 | 25/04/2019 | 18/05/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10390 | red | CWPS - Trim pipe piles | TT_Task | 03/06/2019 | 04/06/2019 | 07/05/2019 | 20/05/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10400 | red | CWPS - Backfill to ground level | TT_Task | 08/06/2019 | 08/06/2019 | 21/05/2019 | 21/05/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10410 | red | CWPS - Construct misc RC structures (i.e. footings, trenches, staircase and switchroom) | TT_Task | 10/06/2019 | 29/06/2019 | 14/05/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10420 | red | CWPS - ABWF works | TT_Task | 01/08/2019 | 13/09/2019 | 21/06/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
PPS10430 | red | CWPS - Building Service installation | TT_Task | 10/08/2019 | 23/09/2019 | 13/06/2019 | 19/12/2019 | 0 | TK_Complete | CCGTD1_IPS
EV003010 | red | Event 003 - 6.6kVA Cable Strike at Shaft A | TT_Task | 24/10/2017 | 06/11/2017 | 24/10/2017 | 24/11/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 24/10/2017
EV004010 | red | Event 004 - Trial trench prior to pre-drill | TT_Task | 07/11/2017 | 09/11/2017 | 25/11/2017 | 30/11/2017 | 0 | TK_Complete | CCGTD1_IPS
EV004020 | red | Event 004 - Pre-drill to verifiy rock head level of Shaft A | TT_Task | 02/12/2017 | 21/12/2017 | 01/12/2017 | 20/12/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 01/12/2017
EV004030 | red | Event 004 - Trial trench prior to piling | TT_Task | 27/11/2017 | 17/12/2017 | 21/12/2017 | 10/01/2018 | 0 | TK_Complete | CCGTD1_IPS
EV004040 | red | Event 004a - Protection to existing cables and removal of existing light post | TT_Task | 26/02/2018 | 10/03/2018 | 08/01/2018 | 20/01/2018 | 0 | TK_Complete | CCGTD1_IPS
EV011070 | blue | Event 011A - Trial jet grout consent condition imposed on shaft excavation | TT_FinMile | 23/04/2018 | 23/04/2018 | 26/02/2018 | 26/02/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 26/02/2018
EV011080 | red | Event 011A - Install trial jet grout ( x3 nos.) | TT_Task | 27/08/2018 | 30/08/2018 | 27/07/2018 | 31/07/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 27/07/2018
EV011090 | red | Event 011A - Core sample after 21 days from grout installed | TT_Task | 26/11/2018 | 03/12/2018 | 03/09/2018 | 12/10/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 03/09/2018
EV011100 | red | Event 011A - Test to early achievement of 28 day strength | TT_Task | 04/12/2018 | 06/12/2018 | 02/10/2018 | 11/10/2018 | 0 | TK_Complete | CCGTD1_IPS
EV011110 | red | Event 011A - Formal test report issued for submission in 7 calendar days | TT_Task | 26/11/2018 | 02/12/2018 | 13/11/2018 | 30/11/2018 | 0 | TK_Complete | CCGTD1_IPS
EV011120 | red | Event 011A - Shaft A - BA8 for full scale grout block and excav below -4.6 mPD | TT_Task | 21/02/2019 | 20/03/2019 | 30/11/2018 | 24/12/2018 | 0 | TK_Complete | CCGTD1_IPS
EV013010 | black | Event 013 - Moblization for piling works start | TT_Mile | 26/02/2018 | 26/02/2018 | 16/01/2018 | 16/01/2018 | 0 | TK_Complete | CCGTD1_IPS
EV013020 | red | Event 013 - Crane damaged and repaired | TT_Task | 27/02/2018 | 07/03/2018 | 19/01/2018 | 27/01/2018 | 0 | TK_Complete | CCGTD1_IPS
EV013030 | blue | Event 013 - Mobilization for piling works complete | TT_FinMile | 26/02/2018 | 26/02/2018 | 03/02/2018 | 03/02/2018 | 0 | TK_Complete | CCGTD1_IPS
EV013040 | red | Event 014 - Clarifying extent of monitoring and instrumentation prerequisite to start of Shaft A piling works | TT_Task | 26/02/2018 | 05/03/2018 | 04/02/2018 | 11/02/2018 | 0 | TK_Complete | CCGTD1_IPS
EV016010 | black | Event 016 - Settlement oberved at adjacent bund wall and piling suspended | TT_Mile | 26/02/2018 | 26/02/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
EV016020 | red | Event 016 - Piling rigs demobilized and site clear for preventive grouting | TT_Task | 26/02/2018 | 04/03/2018 | 19/03/2018 | 25/03/2018 | 0 | TK_Complete | CCGTD1_IPS
EV016030 | red | Event 016 - Preventive grouting (18 nos. out of 20 critical completed) | TT_Task | 26/02/2018 | 06/03/2018 | 26/03/2018 | 03/04/2018 | 0 | TK_Complete | CCGTD1_IPS
EV016040 | black | Event 016 - Further settlement oberved and grouting suspended | TT_Mile | 26/02/2018 | 26/02/2018 | 04/04/2018 | 04/04/2018 | 0 | TK_Complete | CCGTD1_IPS
EV016045 | red | Event 016 - Awaiting engineering solution and management direction | TT_Task | 17/04/2018 | 25/04/2018 | 04/04/2018 | 16/04/2018 | 0 | TK_Complete | CCGTD1_IPS
EV016050 | red | Event 016 - Remedial grouting to bund wall (5 nos.) | TT_Task | 17/04/2018 | 25/04/2018 | 17/04/2018 | 19/04/2018 | 0 | TK_Complete | CCGTD1_IPS
EV016060 | red | Event 016 - Preventive grouting (the last remaining 2 nos.) | TT_Task | 30/05/2018 | 31/05/2018 | 21/04/2018 | 23/04/2018 | 0 | TK_Complete | CCGTD1_IPS
EV016070 | red | Event 016 - Remobilize piling rig | TT_Task | 31/03/2019 | 02/04/2019 | 26/01/2019 | 28/01/2019 | 0 | TK_Complete | CCGTD1_IPS
EV016080 | black | Event 016 - Resume Shaft A piling works | TT_Mile | 29/08/2018 | 29/08/2018 | 30/07/2018 | 30/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV017080 | red | Event 017A - Advanced Preventive Grouting (42 nos.) | TT_Task | 26/06/2018 | 27/07/2018 | 29/05/2018 | 29/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV021010 | red | Event 021A - AAA amendment for Shaft A /Pump Station/ Diversion Culvert | TT_Task | 01/06/2018 | 30/06/2018 | 23/05/2018 | 03/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV021015 | red | Event 021A - Additional monitoring points hand-marked on approval drawings by BD | TT_Task | 26/06/2018 | 08/07/2018 | 23/06/2018 | 03/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV023010 | red | Event 023 - Re-seqeuncing Submission (Alternative) for Shaft A /Pump Station/ Diversion Culvert (BA5)[WITHDRAWN] | TT_Task | 26/07/2018 | 23/09/2018 | 29/06/2018 | 23/08/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 29/06/2018
EV025000 | red | Event 025A - Preventive grouting stopped as it's being legalized via AAA amendment | TT_Task | 26/06/2018 | 29/06/2018 | 23/06/2018 | 26/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV028002 | red | Event 028 - Redo PPA#39 - 5th amendment (Type II) | TT_Task | 26/11/2018 | 25/12/2018 | 13/07/2018 | 13/08/2018 | 0 | TK_Complete | CCGTD1_IPS
EV028004 | red | Event 028 - Redo PPA #39 - install 508 dia. pile [FAILED] | TT_Task | 26/11/2018 | 26/11/2018 | 13/10/2018 | 13/10/2018 | 0 | TK_Complete | CCGTD1_IPS
EV028006 | red | Event 028 - Redo PPA#39 - remedial proposal added to 6th amendment | TT_Task | 27/11/2018 | 08/12/2018 | 15/10/2018 | 26/10/2018 | 0 | TK_Complete | CCGTD1_IPS
EV028008 | blue | Event 028 - Redo PPA#39 - 6th amendment due by 03Nov18; approval deemed | TT_FinMile | 26/11/2018 | 26/11/2018 | 03/11/2018 | 03/11/2018 | 0 | TK_Complete | CCGTD1_IPS
EV028010 | red | Event 028 - Redo PPA#39 - install replacement pile #42, 43 | TT_Task | 29/11/2018 | 05/12/2018 | 14/11/2018 | 17/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SFA10010 | red | Shaft A - Grout Blocks (at receiving area) (total drilling 830m) | TT_Task | 26/01/2019 | 27/03/2019 | 11/01/2019 | 02/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10011 | blue | Shaft A /Grout Block - Complete grout at pre-determined core locations | TT_FinMile | 01/04/2019 | 01/04/2019 | 21/01/2019 | 21/01/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10012 | red | Shaft A /Grout Block - Full core samples | TT_Task | 01/04/2019 | 15/04/2019 | 22/01/2019 | 18/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10013 | red | Shaf A /Grout Block - Grout test to 28 day strength | TT_Task | 31/03/2019 | 02/04/2019 | 08/02/2019 | 02/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10014 | red | Shaft A/ Grout Block - Jet grout assessment report | TT_Task | 31/03/2019 | 06/04/2019 | 03/03/2019 | 08/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10015 | red | Shaft A - BA8 consent for pile wall opening | TT_Task | 01/06/2019 | 28/06/2019 | 11/05/2019 | 05/06/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10020 | red | Shaft A - 610 Dia. Pipe Pile Wall @ 750 c/c (41nos, total driving 1558m) | TT_Task | 15/03/2018 | 26/04/2018 | 12/02/2018 | 04/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SFA10030 | red | Shaft A - Grout Curtain (behind pipe pile wall) (total drilling 1271m) | TT_Task | 29/11/2018 | 20/12/2018 | 03/11/2018 | 18/12/2018 | 0 | TK_Complete | CCGTD1_IPS
SFA10035 | red | Shaft A - Dewatering / observation wells (x 6 nos.) | TT_Task | 10/01/2019 | 12/01/2019 | 19/12/2018 | 20/12/2018 | 0 | TK_Complete | CCGTD1_IPS
SFA10040 | red | Shaft A - Pumping Test and Report Submission | TT_Task | 29/12/2018 | 18/01/2019 | 22/12/2018 | 23/01/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10045 | red | Shaft A - BD Consent for Excavation &amp; ELS | TT_Task | 26/01/2019 | 22/02/2019 | 23/01/2019 | 18/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10050 | red | Shaft A - Excavate to below 1st layer of ring beam / install lagging plate | TT_Task | 01/04/2019 | 06/04/2019 | 06/02/2019 | 10/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10060 | red | Shaft A - Intstall 1st layer of ring beam | TT_Task | 08/04/2019 | 10/04/2019 | 11/02/2019 | 19/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10070 | red | Shaft A - Excavate to below 2nd layer of ring beam | TT_Task | 01/04/2019 | 06/04/2019 | 19/02/2019 | 25/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10080 | red | Shaft A - Intstall lagging plates and 2nd layer of ring beam | TT_Task | 01/04/2019 | 06/04/2019 | 26/02/2019 | 03/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10090 | red | Shaft A - Excavate to below 3rd layer of ring beam | TT_Task | 01/04/2019 | 05/04/2019 | 04/03/2019 | 12/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10100 | red | Shaft A - Intstall lagging plates and 3rd layer of ring beam | TT_Task | 02/04/2019 | 06/04/2019 | 13/03/2019 | 17/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10110 | red | Shaft A - Excavate to below 4th layer of ring beam | TT_Task | 01/04/2019 | 05/04/2019 | 18/03/2019 | 26/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10120 | red | Shaft A - Intstall lagging plates and 4th layer of ring beam | TT_Task | 02/04/2019 | 06/04/2019 | 26/03/2019 | 05/04/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10130 | red | Shaft A - Excavate to below 5th layer of ring beam | TT_Task | 01/05/2019 | 06/05/2019 | 11/04/2019 | 21/04/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 11/04/2019
SFA10140 | red | Shaft A - Intstall lagging plates and 5th layer of ring beam | TT_Task | 02/05/2019 | 07/05/2019 | 21/04/2019 | 23/04/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10150 | red | Shaft A - Excavate to below 6th layer of ring beam | TT_Task | 08/05/2019 | 13/05/2019 | 24/04/2019 | 29/04/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10160 | red | Shaft A - Intstall lagging plates and 6th layer of ring beam | TT_Task | 09/05/2019 | 14/05/2019 | 29/04/2019 | 02/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10170 | red | Shaft A - Excavate to below 7th layer of ring beam | TT_Task | 04/06/2019 | 08/06/2019 | 03/05/2019 | 09/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10180 | red | Shaft A - Intstall lagging plates and 7th layer of ring beam | TT_Task | 05/06/2019 | 10/06/2019 | 09/05/2019 | 10/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10190 | red | Shaft A - Excavate to below 8th layer of ring beam | TT_Task | 11/06/2019 | 14/06/2019 | 11/05/2019 | 15/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10200 | red | Shaft A - Intstall lagging plates and 8thnd layer of ring beam | TT_Task | 12/06/2019 | 15/06/2019 | 15/05/2019 | 19/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10205 | red | Shaft A - Excavate to below 9th layer of ring beam | TT_Task | 17/06/2019 | 22/06/2019 | 20/05/2019 | 25/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10210 | red | Shaft A - Intstall lagging plates and 9th layer of ring beam | TT_Task | 18/06/2019 | 24/06/2019 | 25/05/2019 | 28/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10212XX | red | Shaft A - 9th layer of skin wall achieve required strength | TT_Task | 01/09/2019 | 01/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10215 | red | Shaft A - Excavate to below 10th layer of ring beam | TT_Task | 01/06/2019 | 05/06/2019 | 28/05/2019 | 30/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10215XX | red | Shaft A - Excavate 10th layer further down 2m | TT_Task | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10217XX | red | Shaft A - Construct 10th layer of 250mm skin wall | TT_Task | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10220 | red | Shaft A - Intstall lagging plates and 10th layer of ring beam | TT_Task | 01/06/2019 | 05/06/2019 | 01/06/2019 | 09/06/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10220XX | red | Shaft A - Excavate 11th layer further down 2m | TT_Task | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10222XX | red | Shaft A - Construct 11th layer of 250mm skin wall | TT_Task | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10223XX | red | Shaft A - 11th layer of skin wall achieve required strength | TT_Task | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10225XX | red | Shaft A - Excavate 12th layer further down 2m | TT_Task | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10227XX | red | Shaft A - Construct 12th layer of 250mm skin wall | TT_Task | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10230XX | red | Shaft A - Excavate 13th layer further down 2m | TT_Task | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10232XX | red | Shaft A - Construct 13th layer of 250mm skin wall | TT_Task | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10233XX | red | Shaft A - 13th layer of skin wall achieve required strength | TT_Task | 02/09/2019 | 02/09/2019 | 29/05/2019 | 29/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10250 | red | Shaft A - Excavate to final excavation level -22 mPD / Install lagging plate | TT_Task | 06/06/2019 | 06/06/2019 | 31/05/2019 | 31/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10260 | red | Shaft A - Cast bottom skin wall, base slab and receiving platform | TT_Task | 01/08/2019 | 14/08/2019 | 03/06/2019 | 11/07/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10280 | red | Shaft A - Break through pipe pile wall and at the TBM receiving areas | TT_Task | 06/09/2019 | 10/09/2019 | 05/08/2019 | 09/08/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10282 | red | Shaft A - Get the shaft ready for receiving TBM | TT_Task | 01/08/2019 | 05/08/2019 | 12/07/2019 | 04/08/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA10284 | red | Shaft A - Cement mortar and with flooding with water | TT_Task | 11/09/2019 | 12/09/2019 | 10/08/2019 | 11/08/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA20010 | red | Shaft A - Receive TBM and demob off site | TT_Task | 01/11/2019 | 09/11/2019 | 22/08/2019 | 24/09/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 02/09/2019
SFA20020 | red | Shaft A - Install 1st vertical CW pipe section | TT_Task | 01/11/2019 | 06/11/2019 | 10/10/2019 | 13/10/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA20030 | red | Shaft A - Backfill to -18 mPD approx. 1m below the next pipe joint | TT_Task | 01/11/2019 | 05/11/2019 | 14/10/2019 | 14/10/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA20050 | red | Shaft A - Install remaining vertiicle CW pipe sections / fittings / headers | TT_Task | 01/11/2019 | 18/11/2019 | 24/10/2019 | 09/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA20060 | red | Shaft A - Backfill from -18 to +0.4 mPD | TT_Task | 01/11/2019 | 18/11/2019 | 28/10/2019 | 12/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA20210 | red | Shaft A - Construct rocket slab &amp; open pipe pile wall | TT_Task | 01/01/2020 | 07/01/2020 | 13/11/2019 | 09/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFA20220 | red | Shaft A - Backfill to ground level | TT_Task | 01/01/2020 | 02/01/2020 | 18/12/2019 | 19/12/2019 | 0 | TK_Complete | CCGTD1_IPS
EV002010 | red | Event 002 - Shaft F Pre-drilling (5 nos.) | TT_Task | 06/10/2017 | 14/10/2017 | 06/10/2017 | 17/10/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 04/10/2017
EV002020 | red | Event 002a - Shaft F Pre-drilling (4 nos. additional) | TT_Task | 19/10/2017 | 01/11/2017 | 19/10/2017 | 01/11/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 19/10/2017
EV003020 | red | Event 003a - 6.6kVA cable strike at Shaft A | TT_Task | 23/10/2017 | 23/10/2017 | 24/10/2017 | 17/11/2017 | 0 | TK_Complete | CCGTD1_IPS
EV003021 | blue | Event 003a - Permit to excavation granted | TT_FinMile | 23/10/2017 | 23/10/2017 | 17/11/2017 | 17/11/2017 | 0 | TK_Complete | CCGTD1_IPS
EV003022 | red | Event 003a - Additional trial trenhes prior to pipe piling | TT_Task | 23/10/2017 | 23/10/2017 | 18/11/2017 | 23/11/2017 | 0 | TK_Complete | CCGTD1_IPS
EV011010 | blue | Event 011F - Trial jet grout consent condition imposed on shaft excavation | TT_FinMile | 23/04/2018 | 23/04/2018 | 26/02/2018 | 26/02/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 26/02/2018
EV011020 | red | Event 011F - Install trial get grout ( x3 nos.) | TT_Task | 23/04/2018 | 25/04/2018 | 07/03/2018 | 09/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 07/03/2018
EV011030 | red | Event 011F - Core sample after 21 days from grout installed | TT_Task | 07/05/2018 | 19/05/2018 | 29/03/2018 | 24/05/2018 | 0 | TK_Complete | CCGTD1_IPS
EV011040 | red | Event 011F - Test to early achievement of 28 day strength | TT_Task | 26/07/2018 | 28/07/2018 | 12/07/2018 | 14/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV011050 | red | Event 011F - Formal test report issued for submission in 7 calendar days | TT_Task | 02/08/2018 | 08/08/2018 | 15/07/2018 | 28/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV011052 | red | Event 011F - BD interview on trial jet grout assessment report | TT_Task | 01/12/2018 | 01/12/2018 | 04/09/2018 | 04/09/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 04/09/2018
EV011060 | red | Event 011F - Shaft F - BA8 for full scale grout block and excav below -9.6 mPD | TT_Task | 11/12/2018 | 07/01/2019 | 05/10/2018 | 22/11/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012010 | blue | Event 012F - Settlement Assessment - BD monitoring team visit to site | TT_FinMile | 23/04/2018 | 23/04/2018 | 01/03/2018 | 01/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 01/03/2018
EV012020 | red | Event 012F - Settlement Assessment - Report preparation and submission to BD | TT_Task | 23/04/2018 | 03/05/2018 | 02/03/2018 | 13/03/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012030 | red | Event 012F - Settlement Assessment - Report review by BD | TT_Task | 04/05/2018 | 17/05/2018 | 14/03/2018 | 22/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012035 | blue | Event 012F - Settlement Assessment - BD accept the report and resume to handle BA8 consent application | TT_FinMile | 15/07/2018 | 15/07/2018 | 22/06/2018 | 22/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012040 | red | Event 012F - Request and Issue of ROI for screen wall and other precautionary measures | TT_Task | 23/04/2018 | 27/04/2018 | 14/03/2018 | 28/03/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012050 | red | Event 012F - Settlement Assessment - Install screen wall as precautionary measure (i.e. JCG x17 nos.) | TT_Task | 28/04/2018 | 19/05/2018 | 29/03/2018 | 13/04/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012060 | red | Event 012F - Settlement Assessment - Install TAM grout in between screen wall and Shaft F pile wall | TT_Task | 28/04/2018 | 08/05/2018 | 19/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012065 | red | Event 012F - Settlement Assessment - ADMS to existing CWP (x32) | TT_Task | 28/04/2018 | 29/05/2018 | 02/05/2018 | 15/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012070 | red | Event 012F - Settlement Assessment - SPT (x3) | TT_Task | 28/04/2018 | 26/05/2018 | 05/05/2018 | 01/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012075 | red | Event 012F - Settlement Assessment - Trial Pile (x3) | TT_Task | 28/04/2018 | 14/05/2018 | 17/05/2018 | 31/05/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012080 | red | Event 012F - Settlement Assessment - Exposing CWP pipe crown (x7) | TT_Task | 28/04/2018 | 08/05/2018 | 21/05/2018 | 28/05/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012085 | red | Event 012F - Settlement Assessment - Full core sample (x1) of jet grout screen wall | TT_Task | 26/06/2018 | 04/07/2018 | 26/05/2018 | 08/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV022006 | red | Event 022 - Additional monitoring points hand-marked by BD during AAA amendement | TT_Task | 26/06/2018 | 15/07/2018 | 23/06/2018 | 04/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV022008 | red | Event 022 - Re-do Stage 1 pump test as per AAA amendment | TT_Task | 28/06/2018 | 09/07/2018 | 28/06/2018 | 22/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV022010 | red | Event 022 - Stage 2 pump test as per AAA amendment | TT_Task | 26/07/2018 | 09/08/2018 | 23/07/2018 | 15/08/2018 | 0 | TK_Complete | CCGTD1_IPS
EV022012 | red | Event 022 - Re-do Stage 2 pump test at -9.6 mPD | TT_Task | 26/12/2018 | 15/01/2019 | 15/12/2018 | 08/01/2019 | 0 | TK_Complete | CCGTD1_IPS
EV024010 | red | Event 024 - Re-do full core of trial jet grout x1 no. as per AAA amendment | TT_Task | 26/07/2018 | 01/08/2018 | 09/07/2018 | 11/07/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 12/07/2018
EV024020 | red | Event 024 - Re-do full core / backfill grout to core hole | TT_Task | 26/07/2018 | 26/07/2018 | 12/07/2018 | 12/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV024030 | red | Event 024 - Re-do full core / curing grout cube for 28 days | TT_Task | 26/07/2018 | 22/08/2018 | 13/07/2018 | 09/08/2018 | 0 | TK_Complete | CCGTD1_IPS
EV024040 | red | Event 024 - Redo full core / cube test and lab report | TT_Task | 26/11/2018 | 30/11/2018 | 03/08/2018 | 11/08/2018 | 0 | TK_Complete | CCGTD1_IPS
EV029010 | red | Event 029 - MC grouting note amendment (Type II) | TT_Task | 26/07/2018 | 24/08/2018 | 13/07/2018 | 13/08/2018 | 0 | TK_Complete | CCGTD1_IPS
EV029020 | red | Event 029 - Resubmit BA14 for grout curtain | TT_Task | 26/08/2018 | 26/08/2018 | 13/08/2018 | 13/08/2018 | 0 | TK_Complete | CCGTD1_IPS
EV030010 | red | Event 030 - Additional Tests / Agree and finalize test method and location | TT_Task | 26/07/2018 | 23/09/2018 | 23/06/2018 | 23/08/2018 | 0 | TK_Complete | CCGTD1_IPS
EV030020 | red | Event 030 - Additional Tests / Carry out the additional tests | TT_Task | 26/08/2018 | 14/09/2018 | 24/08/2018 | 14/09/2018 | 0 | TK_Complete | CCGTD1_IPS
EV030030 | red | Event 030 - Additional tests / (Type II) Amendment | TT_Task | 26/08/2018 | 24/09/2018 | 23/08/2018 | 19/09/2018 | 0 | TK_Complete | CCGTD1_IPS
EV030040 | red | Event 030 - Additional tests / Prepare and submit assessment report to BD 1 week prior to excavation below +3.2 | TT_Task | 26/11/2018 | 02/12/2018 | 19/09/2018 | 25/09/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10010 | red | Shaft F - Grout Blocks (at launching areas) (total drilling 1822m) | TT_Task | 27/12/2018 | 23/01/2019 | 26/11/2018 | 27/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10011 | blue | Shaft F /Grout Block - Complete grout at pre-determined core locations (AD TBC) | TT_FinMile | 31/03/2019 | 31/03/2019 | 25/02/2019 | 25/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10012 | red | Shaft F /Grout Block - Core sample after 21 days from grout installed (AD TBC) | TT_Task | 18/04/2019 | 15/05/2019 | 26/02/2019 | 18/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10013 | red | Shaf F /Grout Block - Test to early achievement of 28 day strength (AD TBC) | TT_Task | 16/05/2019 | 18/05/2019 | 19/03/2019 | 21/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10014 | red | Shaft F/ Grout Block - Formal test report issued for submission in 7 calendar days (AD TBC) | TT_Task | 19/05/2019 | 25/05/2019 | 22/03/2019 | 28/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10015 | red | Shaft F - BA8 consent for pile wall opening | TT_Task | 01/05/2019 | 28/05/2019 | 18/04/2019 | 31/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10020 | red | Shaft F - 610 Dia. Pipe Pile Wall @ 750 c/c (57 nos., total driving 2223m) | TT_Task | 01/11/2017 | 14/12/2017 | 24/11/2017 | 02/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10025 | red | Shaft F - BD Consent for Commencement of Excavation &amp; ELS (above +3.2 mPD) | TT_Task | 15/06/2018 | 12/07/2018 | 03/05/2018 | 06/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10030 | red | Shaft F - Grout Curtain (behind pipe pile wall) (total drilling 1950m) | TT_Task | 01/03/2018 | 09/04/2018 | 23/02/2018 | 26/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10035 | red | Shaft F - Install pump well and observation well | TT_Task | 23/04/2018 | 03/05/2018 | 17/03/2018 | 26/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 14/03/2018
SFF10040 | red | Shaft F - Pumping Test (Stage 1) [not accepted by BD] | TT_Task | 06/05/2018 | 14/05/2018 | 29/03/2018 | 30/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10041 | red | Shaft F - Prepare and submit Stage 1 pumping test report | TT_Task | 26/07/2018 | 30/07/2018 | 23/07/2018 | 07/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10043 | red | Shaft F - BD Consent for Commencement of Excavation &amp; ELS (from +3.2 to -9.6 mPD)[WITHDRAWN] | TT_Task | 26/08/2018 | 08/09/2018 | 30/07/2018 | 12/08/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 30/07/2018
SFF10045 | red | Shaft F - BD Consent for Commencement of Excavation &amp; ELS (from +3.2 to -9.6 mPD)[RESUBMIT] | TT_Task | 09/09/2018 | 06/10/2018 | 13/08/2018 | 07/09/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 13/08/2018
SFF10050 | red | Shaft F - Excavate to below 1st layer of ring beam / Install lagging plates | TT_Task | 27/08/2018 | 06/09/2018 | 16/08/2018 | 07/09/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10055 | red | Shaft F - BD Consent for Commencement of Excavation &amp; ELS below -17 mPD | TT_Task | 26/01/2019 | 22/02/2019 | 08/01/2019 | 13/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10060 | red | Shaft F - Intstall 1st layer of ring beam | TT_Task | 27/11/2018 | 05/12/2018 | 08/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10070 | red | Shaft F - Excavate to below 2nd layer of ring beam | TT_Task | 26/11/2018 | 29/11/2018 | 02/10/2018 | 06/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10080 | red | Shaft F - Intstall lagging plates and 2nd layer of ring beam | TT_Task | 27/11/2018 | 30/11/2018 | 04/10/2018 | 11/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10090 | red | Shaft F - Excavate to below 3rd layer of ring beam | TT_Task | 01/12/2018 | 05/12/2018 | 11/10/2018 | 17/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10100 | red | Shaft F - Intstall lagging plates and 3rd layer of ring beam | TT_Task | 03/12/2018 | 06/12/2018 | 12/10/2018 | 28/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10110 | red | Shaft F - Excavate to below 4th layer of ring beam | TT_Task | 07/12/2018 | 11/12/2018 | 29/10/2018 | 03/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10120 | red | Shaft F - Intstall lagging plates and 4th layer of ring beam | TT_Task | 08/12/2018 | 12/12/2018 | 31/10/2018 | 08/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10130 | red | Shaft F - Excavate to below 5th layer of ring beam | TT_Task | 26/11/2018 | 30/11/2018 | 09/11/2018 | 14/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10140 | red | Shaft F - Intstall lagging plates and 5th layer of ring beam (AF TBC) | TT_Task | 26/11/2018 | 29/11/2018 | 10/11/2018 | 20/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10150 | red | Shaft F - Excavate to below 6th layer of ring beam (AS TBC) | TT_Task | 26/11/2018 | 29/11/2018 | 21/11/2018 | 27/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10160 | red | Shaft F - Intstall lagging plates and 6th layer of ring beam | TT_Task | 26/11/2018 | 28/11/2018 | 23/11/2018 | 03/12/2018 | 0 | TK_Complete | CCGTD1_IPS
SFF10170 | red | Shaft F - Excavate to below 7th layer of ring beam | TT_Task | 31/01/2019 | 06/02/2019 | 01/01/2019 | 07/01/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10180 | red | Shaft F - Intstall lagging plates and 7th layer of ring beam | TT_Task | 26/01/2019 | 05/02/2019 | 03/01/2019 | 15/01/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10190 | red | Shaft F - Excavate to below 8th layer of ring beam | TT_Task | 26/01/2019 | 01/02/2019 | 15/01/2019 | 20/01/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10200 | red | Shaft F - Intstall lagging plates and 8th layer of ring beam | TT_Task | 26/01/2019 | 05/02/2019 | 16/01/2019 | 25/01/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10205 | red | Shaft F - Excavate to below 9th layer of ring beam | TT_Task | 01/04/2019 | 06/04/2019 | 26/01/2019 | 01/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10210 | red | Shaft F - Intstall lagging plates and 9th layer of ring beam | TT_Task | 01/04/2019 | 10/04/2019 | 27/01/2019 | 08/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10215 | red | Shaft F - Excavate to below 10th layer of ring beam | TT_Task | 11/04/2019 | 16/04/2019 | 08/02/2019 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10217 | red | Shaft F - Intstall lagging plates and 10th layer of ring beam | TT_Task | 01/04/2019 | 05/04/2019 | 09/02/2019 | 21/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10220 | red | Shaft F - Excavate to below 11th layer of ring beam | TT_Task | 06/04/2019 | 11/04/2019 | 22/02/2019 | 28/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10222 | red | Shaft F - Intstall lagging plates and 11th layer of ring beam | TT_Task | 08/04/2019 | 12/04/2019 | 23/02/2019 | 08/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10225 | red | Shaft F - Excavate to below 12th layer of ring beam | TT_Task | 01/04/2019 | 16/04/2019 | 09/03/2019 | 07/04/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10227 | red | Shaft F - Intstall lagging plates and 12th layer of ring beam | TT_Task | 04/04/2019 | 05/04/2019 | 16/03/2019 | 09/04/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10230 | red | Shaft F - Excavate to below 13th layer of ring beam | TT_Task | 09/05/2019 | 17/05/2019 | 10/04/2019 | 06/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10232 | red | Shaft F - Intstall lagging plates and 13th layer of ring beam | TT_Task | 01/06/2019 | 10/06/2019 | 01/05/2019 | 09/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10250 | red | Shaft F - BD inspection on stratum | TT_Task | 11/06/2019 | 11/06/2019 | 10/05/2019 | 10/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10260 | red | Shaft F - Cast base slab and bottom skin wall | TT_Task | 01/06/2019 | 14/06/2019 | 11/05/2019 | 07/06/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10280 | red | Shaft F - Break through pipe pile wall for TBM driving to Shaft A | TT_Task | 05/08/2019 | 15/08/2019 | 08/06/2019 | 25/06/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10290 | red | Shaft F - Break through pipe pile wall for TBM driving from Shaft E | TT_Task | 07/11/2019 | 17/11/2019 | 09/09/2019 | 24/09/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF10300 | red | Shaft F - Install bulkhead and flooding the shaft (E drive) | TT_Task | 18/11/2019 | 19/11/2019 | 09/10/2019 | 13/10/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF20010 | red | Shaft F - Set up and launch micro TBM to Shaft A | TT_Task | 01/08/2019 | 25/08/2019 | 15/06/2019 | 08/07/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF20020 | red | Shaft F - Micro tunneling and pipe jacking to Shaft A | TT_Task | 01/08/2019 | 18/08/2019 | 09/07/2019 | 21/08/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF20022 | red | Shaft F - Grouting and Welding CWP between Shaft A and Shaft F | TT_Task | 10/11/2019 | 29/11/2019 | 05/09/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF20023XX | red | Shaft F - Testing to CWP between Shaft A and Shaft F | TT_Task | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF20030 | red | Shaft F - Micro tunneling and pipe jacking from Shaft E (Part 2 of 2) | TT_Task | 01/11/2019 | 11/11/2019 | 19/09/2019 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF20032 | red | Grouting and Welding CWP between Shaft E and Shaft F (Part 2 of 2) | TT_Task | 01/01/2020 | 06/01/2020 | 09/11/2019 | 15/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF20033XX | red | Testing to CWP between Shaft E and Shaft F (Part 2 of 2) | TT_Task | 01/01/2020 | 07/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF20035 | red | Shaft F - Demob launching rails (F drive) and install retrieval rails (E drive) | TT_Task | 01/01/2020 | 06/01/2020 | 08/09/2019 | 08/09/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 02/09/2019
SFF20040 | red | Shaft F - Receive TBM and demob off site | TT_Task | 01/01/2020 | 06/01/2020 | 18/10/2019 | 29/10/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF30010XX | red | Shaft F - Construct permanent shaft wall (Pour 1 of 8 / standard lift 3m) | TT_Task | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF30040XX | red | Shaft F - Construct permanent shaft wall (Pour 2 of 8) | TT_Task | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF30070XX | red | Shaft F - Construct permanent shaft wall (Pour 3 of 8) | TT_Task | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF30100XX | red | Shaft F - Construct permanent shaft wall (Pour 4 of 8) | TT_Task | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF30130XX | red | Shaft F - Construct permanent shaft wall (Pour 5 of 8) | TT_Task | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF30160XX | red | Shaft F - Construct permanent shaft wall (Pour 6 of 8) | TT_Task | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF30190XX | red | Shaft F - Construct permanent shaft wall (Pour 7 of 8) | TT_Task | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF30250XX | red | Shaft F - Construct the top slab of permanent shaft (with temporary opening for material delivery) | TT_Task | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF30260XX | red | Shaft F - Construct Maintenance Access Shaft and Emergency Access Shaft | TT_Task | 01/01/2020 | 01/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF30262 | red | Shaft F - Install vertical sections and precast stair wells including mass fill | TT_Task | 01/01/2020 | 08/02/2020 | 30/10/2019 | 06/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF30264 | red | Shaft F - Install CW pipe bends / horizontal section of supply pipeline above the top landing unit of staircase | TT_Task | 07/01/2020 | 09/01/2020 | 07/12/2019 | 23/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF30265XX | red | Shaft F - Install CW pipe bends / horizontal section of discharge pipeline above the top slab | TT_Task | 01/01/2020 | 07/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF30266XX | red | Shaft F - Seal up pipe penetrations through the top slab | TT_Task | 10/01/2020 | 10/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFF30290 | red | Shaft F - Backfill to 2m existing ground level | TT_Task | 26/03/2020 | 01/04/2020 | 26/03/2020 | 01/04/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 20/01/2020
SFF30310 | red | Shaft F - Trim pipe pile wall to 2m below ground level | TT_Task | 02/04/2020 | 03/04/2020 | 02/04/2020 | 03/04/2020 | 0 | TK_Complete | CCGTD1_IPS
SFF30320 | red | Shaft F - Backfill and reinstate to ground level | TT_Task | 04/04/2020 | 10/04/2020 | 04/04/2020 | 10/04/2020 | 0 | TK_Complete | CCGTD1_IPS
SFF30330 | red | Shaft F - ABWF (i.e. finishes, metal works, etc) | TT_Task | 26/03/2020 | 21/04/2020 | 26/03/2020 | 21/04/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 13/01/2020
SFF30340 | red | Shaft F - Building Services installation | TT_Task | 26/03/2020 | 21/04/2020 | 26/03/2020 | 21/04/2020 | 0 | TK_Complete | CCGTD1_IPS
DPT10010 | red | DPT /Zone A (Southern Section) - Pre-boring for sheet pile wall | TT_Task | 17/10/2017 | 15/11/2017 | 13/10/2017 | 14/01/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT10020 | red | DPT /Zone A (Southern Section) - Sheet Piling | TT_Task | 02/11/2017 | 27/11/2017 | 02/11/2017 | 31/01/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 02/11/2017
DPT10040 | red | DPT /Zone A (Southern Section) - Pumping Test and Report Submission | TT_Task | 10/04/2018 | 21/04/2018 | 09/02/2018 | 24/02/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT10045 | red | DPT /Zone A (Southern Section) - BD Consent for Commencement of Excavation &amp; ELS | TT_Task | 18/06/2018 | 15/07/2018 | 18/05/2018 | 22/06/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT10050 | red | DPT /Zone A (Southern Section) - Excavate to 0.5m below 1st layer of struts | TT_Task | 26/07/2018 | 03/08/2018 | 26/06/2018 | 06/07/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT10060 | red | DPT /Zone A (Southern Section) - Install 1st layer of struts | TT_Task | 02/08/2018 | 16/08/2018 | 05/07/2018 | 13/08/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT10070 | red | DPT /Zone A (Southern Section) - Excavate to 0.5m below 2nd layer of struts | TT_Task | 07/09/2018 | 24/09/2018 | 09/08/2018 | 25/08/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 08/08/2018
DPT10080 | red | DPT /Zone A (Southern Section) - Install 2nd layer of struts | TT_Task | 27/08/2018 | 20/09/2018 | 25/08/2018 | 05/10/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT10090 | red | DPT /Zone A (Southern Section) - Excavate to final excavation level -1.4 mPD | TT_Task | 26/11/2018 | 04/12/2018 | 24/09/2018 | 16/10/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT10100 | red | DPT /Zone A (Southern Section) - Cast base slab | TT_Task | 26/11/2018 | 04/12/2018 | 15/10/2018 | 08/11/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT10110 | red | DPT /Zone A (Southern Section) - Remove 2nd layer of struts | TT_Task | 01/12/2018 | 10/12/2018 | 25/10/2018 | 16/11/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT10120 | red | DPT /Zone A (Southern Section) - Install Cooling Water Pipe (39 nos.) | TT_Task | 26/11/2018 | 22/12/2018 | 03/11/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT10125XX | red | DPT /Zone A (Southern Section) - Testing to Cooling Water Pipe (TBC) | TT_Task | 01/01/2020 | 10/01/2020 | 01/01/2019 | 01/01/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT10130 | red | DPT /Zone A (Southern Section) - Backfill to 0.5m below 1st layer of struts | TT_Task | 23/02/2019 | 28/02/2019 | 17/12/2018 | 22/12/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT10135 | red | DPT /Zone A (Southern Section) - Concrete surround | TT_Task | 02/02/2019 | 22/02/2019 | 01/12/2018 | 15/12/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT10140 | red | DPT /Zone A (Southern Section) - Remove 1st layer of struts | TT_Task | 18/02/2019 | 02/03/2019 | 28/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT10150 | red | DPT /Zone A (Southern Section) - Trim down sheet pile 2m | TT_Task | 01/03/2019 | 07/03/2019 | 30/12/2018 | 02/01/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT10160 | red | DPT /Zone A (Southern Section) - Backfill and form slope to the formation of Generator Transformer | TT_Task | 11/03/2019 | 11/03/2019 | 28/12/2018 | 02/01/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT20010 | red | DPT /Zone B (Middle Section) - Grouting to the eastern side of double pipe trench | TT_Task | 25/09/2017 | 02/11/2017 | 23/09/2017 | 07/02/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT20030 | red | DPT /Zone B (Middle Section) - Grouting to the western side of double pipe trench | TT_Task | 03/10/2017 | 06/11/2017 | 02/10/2017 | 07/02/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT20092 | red | DPT/ Zone B Central - Open cut excavation | TT_Task | 26/01/2019 | 14/02/2019 | 29/11/2018 | 18/12/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT20094 | red | DPT/ Zone B South (i.e. Zone A Interface) - Open cut excavation | TT_Task | 26/01/2019 | 08/02/2019 | 31/12/2018 | 12/01/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT20096 | red | DPT/ Zone B North (i.e. KSS Interface) - Open cut excavation | TT_Task | 26/01/2019 | 06/02/2019 | 24/01/2019 | 08/02/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT20098 | red | DPT/ Zone B North (i.e. KSS Crane Access) - Open cut excavation | TT_Task | 01/04/2019 | 11/04/2019 | 09/03/2019 | 11/03/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT20102 | red | DPT/ Zone B Central - Base slab | TT_Task | 26/01/2019 | 31/01/2019 | 18/12/2018 | 22/12/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT20104 | red | DPT/ Zone B South (i.e. Zone A Interface) - Base slab | TT_Task | 26/01/2019 | 30/01/2019 | 13/01/2019 | 17/01/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT20106 | red | DPT/ Zone B North (i.e. KSS Interface) - Base slab | TT_Task | 01/04/2019 | 04/04/2019 | 09/02/2019 | 12/02/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 08/02/2019
DPT20108 | red | DPT/ Zone B North (i.e. KSS Crane Access) - Base slab | TT_Task | 01/04/2019 | 04/04/2019 | 13/03/2019 | 15/03/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT20122 | red | DPT/ Zone B Central - CW pipe installation | TT_Task | 26/01/2019 | 05/02/2019 | 24/12/2018 | 03/01/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT20124 | red | DPT/ Zone B South (i.e. Zone A Interface) - CW pipe installation | TT_Task | 26/01/2019 | 01/02/2019 | 17/01/2019 | 23/01/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT20126 | red | DPT/ Zone B North (i.e. KSS Interface) - CW pipe installation | TT_Task | 31/03/2019 | 01/04/2019 | 13/02/2019 | 15/02/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT20128 | red | DPT/ Zone B North (i.e. KSS Crane Access) - CW pipe installation | TT_Task | 31/03/2019 | 05/04/2019 | 16/03/2019 | 21/03/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT20130XX | red | DPT /Zone B (Middle Section) - Testing to Cooling Water Pipe (TBC) | TT_Task | 01/01/2020 | 11/01/2020 | 03/04/2019 | 03/04/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT20162 | red | DPT/ Zone B Central - Concrete surround &amp; backfill | TT_Task | 26/01/2019 | 08/02/2019 | 07/01/2019 | 19/01/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT20164 | red | DPT/ Zone B South (i.e. Zone A Interface) - Concrete surround &amp; backfill | TT_Task | 26/01/2019 | 08/02/2019 | 17/01/2019 | 30/01/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT20166 | red | DPT/ Zone B North (i.e. KSS Interface) - Concrete surround &amp; backfill | TT_Task | 02/04/2019 | 17/04/2019 | 16/02/2019 | 25/02/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT20168 | red | DPT/ Zone B North (i.e. KSS Crane Access) - Concrete surround &amp; backfill | TT_Task | 06/04/2019 | 27/04/2019 | 15/03/2019 | 02/04/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT30010 | red | DPT /Zone C (Northern Section) - Pipe Piles adjoining Shaft F (13 nos) | TT_Task | 23/04/2018 | 05/05/2018 | 03/03/2018 | 13/03/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT30015 | red | DPT /Zone C (Northern Section) - Remaining Eastern Pipe Pile (60 nos) | TT_Task | 07/05/2018 | 25/06/2018 | 14/03/2018 | 02/05/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT30020 | red | DPT /Zone C (Northern Section) - Remaining Western Pipe Pile (50 nos) | TT_Task | 13/06/2018 | 24/07/2018 | 07/04/2018 | 28/04/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT30030 | red | DPT /Zone C (Northern Section) - Grout Curtain East | TT_Task | 26/05/2018 | 30/06/2018 | 27/04/2018 | 07/06/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT30035 | red | DPT /Zone C (Northern Section) - Grout Curtain West | TT_Task | 16/06/2018 | 19/07/2018 | 27/04/2018 | 07/06/2018 | 0 | TK_Complete | CCGTD1_IPS
DPT30040 | red | DPT /Zone C (Northern Section) - Pumping Test and Report Submission | TT_Task | 02/05/2019 | 22/05/2019 | 26/04/2019 | 03/07/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT30045 | red | DPT /Zone C (Northern Section) - BD Consent for Commencement of Excavation &amp; ELS | TT_Task | 21/08/2019 | 17/09/2019 | 25/06/2019 | 22/07/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT30082 | red | DPT /Zone C (Northern Section) - Excavation to 0.5m below 1st layer struts | TT_Task | 01/08/2019 | 14/08/2019 | 12/07/2019 | 22/07/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT30084 | red | DPT /Zone C (Northern Section) - Install 1st layer of struts | TT_Task | 15/08/2019 | 28/08/2019 | 22/07/2019 | 27/07/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT30086 | red | DPT /Zone C (Northern Section) - Excavation to 0.5m below 2nd layer struts | TT_Task | 01/08/2019 | 14/08/2019 | 31/07/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT30088 | red | DPT /Zone C (Northern Section) - Install 2nd layer of struts | TT_Task | 15/09/2019 | 21/09/2019 | 22/08/2019 | 03/09/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT30090 | red | DPT /Zone C (Northern Section) - Excavation to formation level | TT_Task | 04/11/2019 | 10/11/2019 | 04/09/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT30100 | red | DPT /Zone C (Northern Section) - Plate load test x2 sets | TT_Task | 01/11/2019 | 06/11/2019 | 13/09/2019 | 16/09/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT30120 | red | DPT /Zone C (Northern Section) - Install Cooling Water Pipe | TT_Task | 17/09/2019 | 05/10/2019 | 24/08/2019 | 15/10/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT30125XX | red | DPT /Zone C (Northern Section) - Testing to Cooling Water Pipe | TT_Task | 01/01/2020 | 01/01/2020 | 16/10/2019 | 16/10/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT30130 | red | DPT /Zone C (Northern Section) - Break Shaft F pipe pile wall at the supply pipeline interface | TT_Task | 01/01/2020 | 03/01/2020 | 14/12/2019 | 16/12/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT30140 | red | DPT /Zone C (Northern Section) - Connect CW supply pipeline to Shaft F | TT_Task | 13/01/2020 | 15/01/2020 | 07/12/2019 | 23/12/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT30150 | red | DPT /Seal Pit - Stitch connection of Seal Pit between Shaft F and Zone C | TT_Task | 24/02/2020 | 06/03/2020 | 08/12/2019 | 22/12/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT30200 | red | DPT /Zone C (Northern Section) - Trim top 2m pipe piles | TT_Task | 13/01/2020 | 18/01/2020 | 13/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 13/01/2020
DPT30210 | red | DPT /Zone C (Northern Section) - Backfill and reinstate to ground level | TT_Task | 20/01/2020 | 05/02/2020 | 20/01/2020 | 05/02/2020 | 0 | TK_Complete | CCGTD1_IPS
DPT40010 | red | DPT /Seal Pit - Construct parts of structure within Zone C | TT_Task | 01/01/2020 | 23/02/2020 | 19/09/2019 | 19/12/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT40020 | red | DPT /Seal Pit - Connect CW pipes to the discharge line at Zone C | TT_Task | 01/01/2020 | 06/01/2020 | 26/11/2019 | 26/11/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT40030 | red | DPT /Seal Pit - Construct balance of structure in Shaft F / Zone C | TT_Task | 01/01/2020 | 21/01/2020 | 07/12/2019 | 07/12/2019 | 0 | TK_Complete | CCGTD1_IPS
DPT40040 | red | DPT /Seal Pit - ABWF | TT_Task | 13/01/2020 | 30/01/2020 | 13/01/2020 | 30/01/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 13/01/2020
DPT40050 | red | DPT /Seal Pit - Building Services Installation | TT_Task | 13/01/2020 | 30/01/2020 | 13/01/2020 | 30/01/2020 | 0 | TK_Complete | CCGTD1_IPS
EV006010 | red | Event 006 - Unchartered UU found at Zone A (slow down pre-boring progress) | TT_Task | 23/10/2017 | 23/10/2017 | 09/11/2017 | 29/12/2017 | 0 | TK_Complete | CCGTD1_IPS
EV012100 | blue | Event 012ZA - Settlement Assessment - BD monitoring team visit to site | TT_FinMile | 23/04/2018 | 23/04/2018 | 01/03/2018 | 01/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 01/03/2018
EV012110 | red | Event 012ZA - Settlement Assessment - Report preparation and submission to BD | TT_Task | 23/04/2018 | 28/04/2018 | 05/03/2018 | 17/05/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012120 | red | Event 012ZA - Settlement Assessment - Report review and comment by BD | TT_Task | 29/04/2018 | 12/05/2018 | 16/03/2018 | 22/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012130 | blue | Event 012ZA - Settlement Assessment - BD accept the report and resume to handle BA8 consent application | TT_FinMile | 17/07/2018 | 17/07/2018 | 22/06/2018 | 22/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012140 | red | Event 012ZA - Request and Issue of ROI for Post Grouting to Transformer Rd and other precautionary measures | TT_Task | 29/04/2018 | 03/05/2018 | 08/03/2018 | 18/03/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012150 | red | Event 012ZA - Settlement Assessment - Post remedial grouting to Transformer Rd (36 nos. +4 SPT) | TT_Task | 05/05/2018 | 25/05/2018 | 19/03/2018 | 04/04/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012160 | red | Event 012ZA - Settlement Assessment - Instruction of additional remedial grouting (24 nos. - ROI #72) | TT_Task | 05/05/2018 | 10/05/2018 | 05/04/2018 | 11/04/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012170 | red | Event 012ZA - Settlement Assessment - Post remedial grouting to Transformer Rd (24 nos.) | TT_Task | 05/05/2018 | 16/05/2018 | 12/04/2018 | 23/04/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012180 | red | Event 012ZA - Settlement Assessment - Awaiting confirmation on locations of 2 nos,. additional SPT | TT_Task | 27/05/2018 | 01/06/2018 | 24/04/2018 | 25/04/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012190 | red | Event 012ZA - Settlement Assessment - 2 nos. additional SPT | TT_Task | 02/06/2018 | 08/06/2018 | 26/04/2018 | 05/05/2018 | 0 | TK_Complete | CCGTD1_IPS
EV012200 | red | Event 012ZA - Settlement Assessment - Preparation and submission of supplementary information | TT_Task | 26/05/2018 | 08/06/2018 | 06/05/2018 | 17/05/2018 | 0 | TK_Complete | CCGTD1_IPS
EV020020 | black | Event 020 - Crane Access to Gas Filer across Zone B for M&amp;E (KSS) - Access Date | TT_Mile | 26/11/2018 | 26/11/2018 | 03/09/2018 | 03/09/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 05/09/2018
EV020030 | blue | Event 020 - KSS handover back the area | TT_FinMile | 31/03/2019 | 31/03/2019 | 08/03/2019 | 08/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 17/02/2019
EV021810 | red | Event 021(ZA) - AAA amendment for Zone A {4b1-alt A-2} [WITHDRAWN] | TT_Task | 26/05/2018 | 24/06/2018 | 16/03/2018 | 04/04/2018 | 0 | TK_Complete | CCGTD1_IPS
EV021820 | red | Event 021(ZA) - AAA amendment for Zone A {4b1-alt A-2(r1)} [WITHDRAWN] | TT_Task | 26/05/2018 | 24/06/2018 | 24/04/2018 | 18/05/2018 | 0 | TK_Complete | CCGTD1_IPS
EV021830 | red | Event 021(ZA) - AAA amendment for Zone A {4b1-alt A-2(r2)} | TT_Task | 26/05/2018 | 24/06/2018 | 18/05/2018 | 22/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV039010 | red | Event 039(ZA) - Transformer Generator resequencing amendment (Part 1) | TT_Task | 26/07/2018 | 24/08/2018 | 29/06/2018 | 27/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV039020 | red | Event 039(ZA) - Transformer Generator resequencing amendment (Part 2) | TT_Task | 26/08/2018 | 24/09/2018 | 24/08/2018 | 20/09/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 24/08/2018
EV042010 | red | Event 042 - Zone B FEL amendment (Type II) | TT_Task | 26/01/2019 | 24/02/2019 | 30/11/2018 | 28/12/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 23/11/2018
EV042020 | red | Event 042 - BA8 consent for Zone B FEL amendment | TT_Task | 26/01/2019 | 24/02/2019 | 30/11/2018 | 28/12/2018 | 0 | TK_Complete | CCGTD1_IPS
EV045000 | red | Event 045 - Shaft F / Zone C Re-sequencing - Additional pipe piles | TT_Task | 26/01/2019 | 26/01/2019 | 11/01/2019 | 23/01/2019 | 0 | TK_Complete | CCGTD1_IPS
EV045010 | red | Event 045 - Shaft F / Zone C Re-sequencing - Additional TAM grout | TT_Task | 01/04/2019 | 13/04/2019 | 23/03/2019 | 01/04/2019 | 0 | TK_Complete | CCGTD1_IPS
EV011130 | blue | Event 011D - Trial jet grout consent condition imposed on shaft excavation | TT_FinMile | 23/04/2018 | 23/04/2018 | 26/02/2018 | 26/02/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 26/02/2018
EV011140 | red | Event 011D - Install trial jet grout | TT_Task | 26/07/2018 | 28/07/2018 | 25/07/2018 | 28/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV017010 | red | Event 017D - Shaft D Advanced Precautionary Grouting (32 out of 53) | TT_Task | 06/06/2018 | 05/07/2018 | 05/05/2018 | 09/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV017012 | red | Event 017D - Shaft D Advanced Precautionary Grouting (1 out of 53) | TT_Task | 26/07/2018 | 26/07/2018 | 21/06/2018 | 22/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV017014 | red | Event 017D - Shaft D Advanced Precautionary Grouting (9 out of 53) | TT_Task | 26/07/2018 | 26/07/2018 | 26/06/2018 | 03/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV017016 | red | Event 017D - Shaft D Advanced Precautionary Grouting (11 out of 53) | TT_Task | 26/08/2018 | 30/08/2018 | 29/07/2018 | 02/08/2018 | 0 | TK_Complete | CCGTD1_IPS
EV021310 | red | Event 021D - Shaft D AAA amendment (Type II) / submission &amp; approval | TT_Task | 26/06/2018 | 25/07/2018 | 30/05/2018 | 03/07/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 28/05/2018
EV021320 | red | Event 021D - Shaft D AAA amendment / consent for APG &amp; trial jet grout | TT_Task | 26/07/2018 | 22/08/2018 | 18/06/2018 | 25/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV031010 | red | Event 031D - Works suspended after FS main stirke in Diversion Culvet works area | TT_Task | 26/07/2018 | 26/07/2018 | 04/07/2018 | 09/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV032010 | red | Event 032D - Works suspension instructed to await BD consent | TT_Task | 26/07/2018 | 26/07/2018 | 12/07/2018 | 23/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV032020 | blue | Event 032D - Site Memo 383 suggesting works can be resumed as 28d consent statutory time overdue since 15/7/18 | TT_FinMile | 26/07/2018 | 26/07/2018 | 23/07/2018 | 23/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV033010 | blue | Event 033 - ROI #144 / date of issuance | TT_FinMile | 26/08/2018 | 26/08/2018 | 24/08/2018 | 24/08/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 24/08/2018
SFD00010 | red | Shaft D - Utilities Diversion | TT_Task | 23/04/2018 | 14/06/2018 | 07/03/2018 | 20/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SFD10302 | red | Grouting and Welding to CWP between Shaft E and Shaft F (Part 1 of 2) | TT_Task | 01/01/2020 | 09/01/2020 | 31/10/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
EV011190 | blue | Event 011E - Trial jet grout consent condition imposed on shaft excavation | TT_FinMile | 23/04/2018 | 23/04/2018 | 26/02/2018 | 26/02/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 26/02/2018
EV011200 | red | Event 011E - Install trial get grout ( x3 nos.) | TT_Task | 27/08/2018 | 30/08/2018 | 04/08/2018 | 07/08/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 04/08/2018
EV011210 | red | Event 011E - Permeability Test + Core sample after 21 days from grout installed | TT_Task | 06/12/2018 | 19/12/2018 | 07/09/2018 | 20/09/2018 | 0 | TK_Complete | CCGTD1_IPS
EV011220 | red | Event 011E - Test to early achievement of 28 day strength | TT_Task | 06/12/2018 | 08/12/2018 | 13/09/2018 | 21/09/2018 | 0 | TK_Complete | CCGTD1_IPS
EV011225 | red | Event 011E - Curing and cube test to backfill grout | TT_Task | 06/12/2018 | 02/01/2019 | 21/09/2018 | 18/10/2018 | 0 | TK_Complete | CCGTD1_IPS
EV011230 | red | Event 011E - Formal test report issued for submission in 7 calendar days | TT_Task | 06/12/2018 | 12/12/2018 | 03/11/2018 | 04/12/2018 | 0 | TK_Complete | CCGTD1_IPS
EV011240 | red | Event 011E - Shaft E - BA8 for full scale grout block and excav below -1.6 mPD | TT_Task | 05/01/2019 | 01/02/2019 | 30/11/2018 | 24/12/2018 | 0 | TK_Complete | CCGTD1_IPS
EV017020 | red | Event 017E - Shaft E - Preventive Grouting | TT_Task | 06/06/2018 | 05/07/2018 | 10/05/2018 | 25/05/2018 | 0 | TK_Complete | CCGTD1_IPS
EV021610 | red | Event 021E - AAA amendment (and cofferdam enlargement) for Shaft E | TT_Task | 26/07/2018 | 24/08/2018 | 29/06/2018 | 27/07/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 29/06/2018
EV021620 | red | Event 021E - Consent for pipe piles (incl' APG) and grout curtain further to AAA amendment | TT_Task | 26/08/2018 | 05/09/2018 | 27/07/2018 | 06/08/2018 | 0 | TK_Complete | CCGTD1_IPS
EV034010 | blue | Event 034 - ROI #113 Crest Wall Removal / date of issuance | TT_FinMile | 16/07/2018 | 16/07/2018 | 16/07/2018 | 16/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV034020 | red | Event 034 - ROI #113 Crest Wall Removal / method statement, mobilize subcon, etc | TT_Task | 26/07/2018 | 24/08/2018 | 17/07/2018 | 14/08/2018 | 0 | TK_Complete | CCGTD1_IPS
EV034030 | red | Event 034 - ROI #113 Crest Wall Removal / site works | TT_Task | 15/09/2018 | 05/10/2018 | 15/08/2018 | 10/09/2018 | 0 | TK_Complete | CCGTD1_IPS
EV060010 | red | Event 060E - Probing test to jet grout block | TT_Task | 01/06/2019 | 02/06/2019 | 16/05/2019 | 16/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE00010 | red | Shaft E - Utilities Diversion | TT_Task | 04/05/2018 | 25/06/2018 | 19/03/2018 | 30/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SFE10025 | black | Shaft E - Implement TTM on Sea Bank Road | TT_Mile | 04/05/2018 | 04/05/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SFE10029 | red | Shaft E - Grout Block (at lunching area) | TT_Task | 10/04/2019 | 11/05/2019 | 12/02/2019 | 16/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10029a | blue | Shaft E /Grout Block - Complete grout at pre-determined core locations | TT_FinMile | 29/04/2019 | 29/04/2019 | 27/02/2019 | 27/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10029b | red | Shaft E /Grout Block - Core sample | TT_Task | 17/05/2019 | 06/06/2019 | 27/02/2019 | 15/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10029c | red | Shaf E /Grout Block - Test to early achievement of 28 day strength | TT_Task | 29/04/2019 | 01/05/2019 | 12/03/2019 | 29/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10029d | red | Shaft E/ Grout Block - Jet grout assessment report (AF TBC) | TT_Task | 04/05/2019 | 10/05/2019 | 30/03/2019 | 23/04/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10029e | red | Shaft E - BA8 consent for pile wall opening | TT_Task | 04/05/2019 | 31/05/2019 | 18/04/2019 | 12/06/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10030 | red | Shaft E - 610 Dia. Pipe Pile Wall @ 750 c/c (52 nos) | TT_Task | 03/07/2018 | 12/09/2018 | 04/06/2018 | 16/11/2018 | 0 | TK_Complete | CCGTD1_IPS
SFE10032 | red | Shaft E - BD Consent for Excavation &amp; ELS above +4.7 mPD | TT_Task | 26/12/2018 | 22/01/2019 | 18/12/2018 | 25/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10035 | red | Shaft E - Grout Curtain (behind pipe pile wall) (total drilling 1490m) | TT_Task | 26/11/2018 | 17/12/2018 | 20/11/2018 | 10/12/2018 | 0 | TK_Complete | CCGTD1_IPS
SFE10045 | red | Shaft E - Pumping Test and Report Submission | TT_Task | 26/12/2018 | 15/01/2019 | 15/12/2018 | 28/01/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10046 | red | Shaft E - BD Consent for Excavation &amp; ELS from +4.7 to -1.6 mPD | TT_Task | 02/04/2019 | 29/04/2019 | 29/01/2019 | 25/02/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10050 | red | Shaft E - Excavate to 0.5m below 1st layer of struts / Install lagging plate | TT_Task | 13/02/2019 | 19/02/2019 | 15/01/2019 | 19/01/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10060 | red | Shaft E - Install 1st layer of struts (22 t) | TT_Task | 20/02/2019 | 23/02/2019 | 20/01/2019 | 23/01/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10070 | red | Shaft E - Excavate to below 2nd layer of strut | TT_Task | 01/04/2019 | 05/04/2019 | 01/03/2019 | 05/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10080 | red | Shaft E - Intstall lagging plates and 2nd layer of strut | TT_Task | 02/04/2019 | 06/04/2019 | 02/03/2019 | 08/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10090 | red | Shaft E - Excavate to below 3rd layer of strut | TT_Task | 01/04/2019 | 05/04/2019 | 09/03/2019 | 10/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10100 | red | Shaft E - Intstall lagging plates and 3rd layer of strut | TT_Task | 02/04/2019 | 06/04/2019 | 11/03/2019 | 15/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10110 | red | Shaft E - Excavate to below 4th layer of strut | TT_Task | 01/04/2019 | 05/04/2019 | 16/03/2019 | 17/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10120 | red | Shaft E - Intstall lagging plates and 4th layer of strut | TT_Task | 02/04/2019 | 06/04/2019 | 17/03/2019 | 26/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10130 | red | Shaft E - Excavate to below 5th layer of strut | TT_Task | 01/04/2019 | 05/04/2019 | 27/03/2019 | 28/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10140 | red | Shaft E - Intstall lagging plates and 5th layer of strut | TT_Task | 01/04/2019 | 05/04/2019 | 28/03/2019 | 02/04/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10150 | red | Shaft E - Excavate to below 6th layer of strut | TT_Task | 01/05/2019 | 06/05/2019 | 03/04/2019 | 05/04/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10160 | red | Shaft E - Intstall lagging plates and 6th layer of strut | TT_Task | 02/05/2019 | 07/05/2019 | 06/04/2019 | 09/04/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10170 | red | Shaft E - Excavate to below 7th layer of strut | TT_Task | 08/05/2019 | 13/05/2019 | 11/04/2019 | 13/04/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10180 | red | Shaft E - Intstall lagging plates and 7th layer of strut | TT_Task | 01/05/2019 | 06/05/2019 | 14/04/2019 | 24/04/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10190 | red | Shaft E - Excavate to below 8th layer of strut | TT_Task | 01/05/2019 | 06/05/2019 | 25/04/2019 | 01/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10200 | red | Shaft E - Intstall lagging plates and 8th layer of strut | TT_Task | 03/06/2019 | 06/06/2019 | 02/05/2019 | 05/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10250 | red | Shaft E - Excavate to final excavation level -18 mPD /install lagging plate/ S9 at FEL | TT_Task | 01/06/2019 | 12/06/2019 | 06/05/2019 | 22/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10260 | red | Shaft E - Cast base slab /skin wall | TT_Task | 03/06/2019 | 12/06/2019 | 19/05/2019 | 11/06/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10270 | red | Shaft E - Cast-in bottom layers of struts with base slab | TT_Task | 01/06/2019 | 01/06/2019 | 22/05/2019 | 22/05/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10275 | red | Shaft E - Break through the pipe pile wall for launching TBM | TT_Task | 05/08/2019 | 15/08/2019 | 12/06/2019 | 27/06/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10277 | red | Shaft E - Set up and launch TBM to Shaft F | TT_Task | 01/08/2019 | 25/08/2019 | 12/06/2019 | 16/08/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10278 | red | Shaft E - Micro tunneling and pipe jacking to Shaft F (Part 1 of 2) | TT_Task | 18/09/2019 | 02/10/2019 | 17/08/2019 | 18/09/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE10280 | red | Shaft E - Remove jacking frame, thrust block and etc | TT_Task | 01/01/2020 | 01/01/2020 | 30/10/2019 | 12/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE30045 | red | Shaft E - Install CW pipe to 0.5m above 7th layer of strut and mass fill | TT_Task | 01/01/2020 | 02/01/2020 | 13/11/2019 | 16/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE30065 | red | Shaft E - Install CW pipe to 0.5m above 6th layer of strut and mass fill | TT_Task | 03/01/2020 | 04/01/2020 | 18/11/2019 | 20/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE30085 | red | Shaft E - Install CW pipe to 0.5m above 5th layer of strut and mass fill | TT_Task | 01/01/2020 | 02/01/2020 | 21/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE30105 | red | Shaft E - Install CW pipe to 0.5m above 4th layer of strut and mass fill | TT_Task | 03/01/2020 | 04/01/2020 | 23/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE30115 | red | Shaft E - Install CW pipe to 0.5m above 3rd layer of strut and mass fill | TT_Task | 05/01/2020 | 06/01/2020 | 24/11/2019 | 26/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE30125 | red | Shaft E - Install CW pipe to 0.5m above 2nd layer of strut and mass fill | TT_Task | 07/01/2020 | 08/01/2020 | 27/11/2019 | 28/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE30127XX | red | Testing to CWP between Shaft E and Shaft F (Part 1 of 2) | TT_Task | 01/01/2020 | 07/01/2020 | 29/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE30128 | red | Shaft E - Connect CW pipe to Discharge Culvert | TT_Task | 12/01/2020 | 13/01/2020 | 10/12/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SFE30165 | red | Shaft E - Trim pipe piles | TT_Task | 01/01/2020 | 04/01/2020 | 01/01/2020 | 04/01/2020 | 0 | TK_Complete | CCGTD1_IPS
SFE30170 | red | Shaft E - Backfill and reinstate to ground level | TT_Task | 05/01/2020 | 10/01/2020 | 05/01/2020 | 10/01/2020 | 0 | TK_Complete | CCGTD1_IPS
SFE30180 | blue | Shaft E - All stages of TTM ended; traffic resumed to normal at Shaft E location | TT_FinMile | 10/01/2020 | 10/01/2020 | 10/01/2020 | 10/01/2020 | 0 | TK_Complete | CCGTD1_IPS
DBC00010 | red | Discharge Culvert - Utilities Diversion along Sea Bank Road | TT_Task | 04/05/2018 | 25/06/2018 | 25/04/2018 | 20/06/2018 | 0 | TK_Complete | CCGTD1_IPS
DBC10010 | red | Discharge Culvert /Zone A (Eastern Section) - Pipe Pile (PPS080-240, PPS330-490 excl' 1800 culvert) | TT_Task | 05/12/2018 | 17/01/2019 | 28/08/2018 | 12/11/2018 | 0 | TK_Complete | CCGTD1_IPS
DBC10020 | red | Discharge Culvert /Zone A (Eastern Section) - Grout curtain behind pile wall - excl' 1800 drainage area | TT_Task | 26/11/2018 | 08/01/2019 | 19/09/2018 | 12/01/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10030 | red | Discharge Culvert /Zone A (Eastern Section) - all remaining works held up by the issue of 1800 culvert | TT_Task | 31/03/2019 | 28/06/2019 | 26/01/2019 | 10/07/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10040 | red | Discharge Culvert /Zone A1 (Eastern Section) - Pumping Test &amp; Assessment Report to BD | TT_Task | 01/05/2019 | 21/05/2019 | 01/04/2019 | 22/05/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10045 | red | Discharge Culvert /Zone A1 (Eastern Section) - BD Consent for Commencement of Excavation &amp; ELS | TT_Task | 09/06/2019 | 06/07/2019 | 16/05/2019 | 12/06/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10050 | red | Discharge Culvert /Zone A1 (Eastern Section) - Excavate to 0.5m below 1st layer of struts | TT_Task | 01/08/2019 | 03/08/2019 | 26/05/2019 | 28/05/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10060 | red | Discharge Culvert /Zone A1 (Eastern Section) - Install 1st layer of struts | TT_Task | 05/08/2019 | 09/08/2019 | 29/05/2019 | 01/06/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10070 | red | Discharge Culvert /Zone A1 (Eastern Section) - Excavate below 1st layer of struts to FEL | TT_Task | 01/08/2019 | 10/08/2019 | 14/06/2019 | 24/06/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10080 | red | Discharge Culvert /Zone A1 (Eastern Section) - Lagging plate below 1st layer of struts to FEL | TT_Task | 01/08/2019 | 05/08/2019 | 25/06/2019 | 04/07/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10090 | red | Discharge Culvert /Zone A1 (Eastern Section) - Blinding concrete | TT_Task | 01/08/2019 | 06/08/2019 | 05/07/2019 | 09/07/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10100 | red | Discharge Culvert /Zone A1 (Eastern Section) - Cast base slab and kicker | TT_Task | 01/08/2019 | 22/08/2019 | 10/07/2019 | 17/07/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10110 | red | Discharge Culvert /Zone A1 (Eastern Section) - Construct manholes | TT_Task | 02/01/2020 | 22/01/2020 | 26/08/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10115 | red | Discharge Culvert /Zone A1 (Eastern Section) - Install drainage pipes | TT_Task | 23/01/2020 | 05/02/2020 | 26/08/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10120 | red | Discharge Culvert /Zone A1 (Eastern Section) - Cast side walls and top slab | TT_Task | 12/08/2019 | 02/09/2019 | 17/07/2019 | 06/08/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10125 | red | Discharge Culvert /Zone A1 (Eastern Section) - Backfill to 0.5m below 1st layer of struts | TT_Task | 02/01/2020 | 04/01/2020 | 07/08/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10140 | red | Discharge Culvert /Zone A1 (Eastern Section) - Remove 1st layer of struts | TT_Task | 06/01/2020 | 06/01/2020 | 12/08/2019 | 12/08/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10150 | red | Discharge Culvert /Zone A1 (Eastern Section) - Trim pipe piles | TT_Task | 07/01/2020 | 13/01/2020 | 13/08/2019 | 20/08/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC10160 | red | Discharge Culvert /Zone A1 (Eastern Section) - Backfill and reinstate to ground level | TT_Task | 14/01/2020 | 20/01/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20010 | red | Discharge Culvert /Zone B(&amp;A3) (Western Section) - Pipe Pile (PPS001-079, PPS491-570) - excl' 1800 drainage area | TT_Task | 18/01/2019 | 06/03/2019 | 22/10/2018 | 29/11/2018 | 0 | TK_Complete | CCGTD1_IPS
DBC20020 | red | Discharge Culvert / Grout Curtain (as a temporary cut off from Zone A2) | TT_Task | 07/05/2019 | 17/05/2019 | 06/03/2019 | 19/03/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20030 | red | Discharge Culvert /Zone B(&amp;A3) (Western Section) - Grout curtain behind pipe pile wall | TT_Task | 26/01/2019 | 04/03/2019 | 21/11/2018 | 10/01/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20040 | red | Discharge Culvert /Zone A3 (Western Section) - Pumping Test &amp; Assessment Report to BD | TT_Task | 01/06/2019 | 21/06/2019 | 27/05/2019 | 12/06/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20045 | red | Discharge Culvert /Zone A3 (Western Section) - BD Consent for Commencement of Excavation &amp; ELS | TT_Task | 01/08/2019 | 28/08/2019 | 06/06/2019 | 03/07/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20050 | red | Discharge Culvert /Zone A3 (Western Section) - Excavate to 0.5m below 1st layer of struts | TT_Task | 01/08/2019 | 03/08/2019 | 18/07/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20055 | red | Discharge Culvert /Zone B (Shaft E Interface Section) - Pumping Test &amp; Assessment Report to BD | TT_Task | 01/08/2019 | 21/08/2019 | 11/06/2019 | 26/06/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 17/06/2019
DBC20060 | red | Discharge Culvert /Zone A3 (Western Section) - Install 1st layer of struts | TT_Task | 01/08/2019 | 05/08/2019 | 22/07/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20065 | red | Discharge Culvert /Zone B (Shaft E Interface Section) - BD Consent for Commencement of Excavation &amp; ELS | TT_Task | 01/01/2020 | 28/01/2020 | 15/11/2019 | 12/12/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20070 | red | Discharge Culvert /Zone A3 (Western Section) - Excavate below 1st layer of struts to FEL | TT_Task | 01/08/2019 | 10/08/2019 | 27/07/2019 | 06/08/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20080 | red | Discharge Culvert /Zone A3 (Western Section) - Lagging plate below 1st layer of struts to FEL | TT_Task | 09/09/2019 | 13/09/2019 | 08/08/2019 | 12/08/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20090 | red | Discharge Culvert /Zone A3 (Western Section) - Blinding concrete | TT_Task | 02/01/2020 | 07/01/2020 | 12/11/2019 | 12/11/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20100 | red | Discharge Culvert /Zone A3 (Western Section) - Cast base slab and kicker | TT_Task | 08/01/2020 | 16/01/2020 | 13/11/2019 | 20/11/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20110 | red | Discharge Culvert /Zone A3 (Western Section) - Construct manholes | TT_Task | 02/01/2020 | 22/01/2020 | 16/12/2019 | 24/01/2020 | 0 | TK_Complete | CCGTD1_IPS
DBC20115 | red | Discharge Culvert /Zone A3 (Western Section) - Install drainage pipes | TT_Task | 16/01/2020 | 22/01/2020 | 16/12/2019 | 24/01/2020 | 0 | TK_Complete | CCGTD1_IPS
DBC20120 | red | Discharge Culvert /Zone A3 (Western Section) - Cast side walls and top slab | TT_Task | 17/01/2020 | 01/02/2020 | 21/11/2019 | 15/12/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20125 | red | Discharge Culvert /Zone A3 (Western Section) - Backfill to 0.5m below 1st layer of struts | TT_Task | 02/01/2020 | 04/01/2020 | 16/12/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20140 | red | Discharge Culvert /Zone A3 (Western Section) - Remove 1st layer of struts | TT_Task | 06/01/2020 | 06/01/2020 | 19/12/2019 | 19/12/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20150 | red | Discharge Culvert /Zone A3 (Western Section) - Trim pipe piles | TT_Task | 07/01/2020 | 13/01/2020 | 20/12/2019 | 28/12/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC20160 | red | Discharge Culvert /Zone A3 (Western Section) - Backfill and reinstate to ground level | TT_Task | 01/02/2020 | 07/02/2020 | 01/02/2020 | 07/02/2020 | 0 | TK_Complete | CCGTD1_IPS
DBC30005 | red | Discharge Culvert /Zone B (Shaft E Interface Section) - 1st layer excavation and ELS | TT_Task | 01/01/2020 | 07/01/2020 | 18/11/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC30010 | red | Discharge Culvert /Zone B (Shaft E Interface Section) - Excavation below 1st layer of strut to FEL | TT_Task | 08/01/2020 | 11/01/2020 | 22/11/2019 | 26/11/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC30020 | red | Discharge Culvert /Shaft E Interface - Install CW pipe between Shaft E and Discharge Culvert | TT_Task | 03/01/2020 | 11/01/2020 | 06/12/2019 | 15/12/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC30030 | red | Discharge Culvert /Zone B (Shaft E Interface Section) - Remaining drainage works and backfill | TT_Task | 01/01/2020 | 30/01/2020 | 19/12/2019 | 24/01/2020 | 0 | TK_Complete | CCGTD1_IPS
DBC30100 | red | Discharge Culvert /Zone B (Shaft E Interface Section) - RC works | TT_Task | 12/01/2020 | 26/01/2020 | 27/11/2019 | 15/12/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC30110 | red | Discharge Culvert /Zone B (Shaft E Interface Section) - Strip internal space | TT_Task | 12/01/2020 | 14/01/2020 | 17/12/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS
DBC40010 | red | Discharge Culvert /Zone A2 (1800 Drainage Section) - Remaining drainage works and backfill | TT_Task | 01/01/2020 | 30/01/2020 | 26/11/2019 | 24/01/2020 | 0 | TK_Complete | CCGTD1_IPS
EV017030 | red | Event 017S - Sea Bank Road (Zone A and Zone B excl' 1800 culvert) - Advanced Precautionary Grouting | TT_Task | 02/06/2018 | 31/07/2018 | 25/05/2018 | 30/08/2018 | 0 | TK_Complete | CCGTD1_IPS
EV017040 | red | Event 017S - Sea Bank Road (Zone C) - Advanced Precautionary Grouting inside creast wall | TT_Task | 26/11/2018 | 30/11/2018 | 04/09/2018 | 08/09/2018 | 0 | TK_Complete | CCGTD1_IPS
EV017050 | red | Event 017S - Sea Bank Road (Zone C) - Advanced Precautionary Grouting outside creast wall | TT_Task | 26/11/2018 | 30/11/2018 | 16/10/2018 | 20/10/2018 | 0 | TK_Complete | CCGTD1_IPS
EV025900 | red | Event 025S - Preventive grouting stopped as it's being legalized via AAA amendment | TT_Task | 27/06/2018 | 02/08/2018 | 22/06/2018 | 29/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV037000 | red | Event 037a - Discharge Culvert / Zone A &amp; B amendment (Type II) | TT_Task | 26/01/2019 | 24/02/2019 | 02/01/2019 | 31/01/2019 | 0 | TK_Complete | CCGTD1_IPS
EV037005 | red | Event 037b - Discharge Culvert / 1800 drainage amendment (Type II) | TT_Task | 26/01/2019 | 24/02/2019 | 02/01/2019 | 31/01/2019 | 0 | TK_Complete | CCGTD1_IPS
EV037008 | red | Event 037d - Discharge Culvert / 1800 drainage &amp; TBM alignment (Type II) | TT_Task | 31/03/2019 | 29/04/2019 | 26/03/2019 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS
EV044020 | red | Event 044 - Set up and conduct plate load test PL4 at SBR Zone A3 | TT_Task | 01/11/2019 | 06/11/2019 | 06/09/2019 | 09/09/2019 | 0 | TK_Complete | CCGTD1_IPS
EV055010 | red | Event 055 - 1800 drainage pipe at SBR / Pumping test and assessment report to BD (Zone A2) | TT_Task | 01/08/2019 | 17/08/2019 | 17/07/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
EV055020 | red | Event 055 - 1800 drainage pipe at SBR / Excavation consent (Zone A2) | TT_Task | 11/08/2019 | 07/09/2019 | 31/07/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
EV055030 | red | Event 055 - 1800 drainage pipe at SBR / Excavation and construction of Discharge Culvert (Zone A2) | TT_Task | 01/11/2019 | 27/01/2020 | 07/09/2019 | 25/11/2019 | 0 | TK_Complete | CCGTD1_IPS
EV062010 | red | Event 062 - Construct temporary mucking pit at SBR Zone A3 | TT_Task | 14/09/2019 | 18/09/2019 | 13/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CNY_2018 | red | Outfall Apron Modif - Bulkhead Installation | TT_Task | 18/04/2018 | 21/04/2018 | 22/02/2018 | 25/02/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 22/02/2018
CNY_2019 | red | Outfall Apron Modif - Bulkhead Modification (fixing method) - during CNY shutdown | TT_Task | 31/03/2019 | 03/04/2019 | 08/02/2019 | 09/02/2019 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 08/02/2019
EV036010 | red | Event 036 - Dicharge Culvert / Outfall portion amendment (Type II) | TT_Task | 26/11/2018 | 25/12/2018 | 12/09/2018 | 10/10/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 12/09/2018
EV056010 | red | Event 056 - Bulkhead Modification (fixing method) - pre CNY | TT_Task | 26/01/2019 | 26/01/2019 | 24/01/2019 | 30/01/2019 | 0 | TK_Complete | CCGTD1_IPS
EV059010 | red | Event 059 - Discharge Culvert / Zone C /Plate Load Test | TT_Task | 30/05/2019 | 05/06/2019 | 02/03/2019 | 18/03/2019 | 0 | TK_Complete | CCGTD1_IPS
OAM10010 | red | Outfall Apron Modif /behind the crest wall - Remove rock armour and crest wall | TT_Task | 27/08/2018 | 03/09/2018 | 08/10/2018 | 10/10/2018 | 0 | TK_Complete | CCGTD1_IPS
OAM10020 | red | Outfall Apron Modif /behind the crest wall - Rock fill to +5.7mPD to form temporary working platform | TT_Task | 27/08/2018 | 30/08/2018 | 10/10/2018 | 12/10/2018 | 0 | TK_Complete | CCGTD1_IPS
OAM10030 | red | Outfall Apron Modif /behind the crest wall - Pipe Piles (PPS271-280) | TT_Task | 26/11/2018 | 28/11/2018 | 22/10/2018 | 24/10/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 28/08/2018
OAM10040 | red | Outfall Apron Modif /on Sea Bank Road - Pile Piles (PPS241-270, PPS281-329) | TT_Task | 29/11/2018 | 04/12/2018 | 17/09/2018 | 03/10/2018 | 0 | TK_Complete | CCGTD1_IPS
OAM10050 | red | Outfall Apron Modif /behind the crest wall - Grout Curtain | TT_Task | 26/11/2018 | 04/12/2018 | 27/10/2018 | 05/11/2018 | 0 | TK_Complete | CCGTD1_IPS
OAM10060 | red | Outfall Apron Modif /on Sea Bank Road - Grout Curtain | TT_Task | 05/12/2018 | 12/12/2018 | 04/10/2018 | 05/11/2018 | 0 | TK_Complete | CCGTD1_IPS
OAM10070 | red | Outfall Apron Modif - Grout Curtain (as temporary cut off from Zone B and behind Outfall side wall) | TT_Task | 26/11/2018 | 03/12/2018 | 25/10/2018 | 01/11/2018 | 0 | TK_Complete | CCGTD1_IPS
OAM10080 | red | Outfall Apron Modif - Pumping Test and assessment report to BD | TT_Task | 26/11/2018 | 13/12/2018 | 08/11/2018 | 21/12/2018 | 0 | TK_Complete | CCGTD1_IPS
OAM10085 | red | Outfall Apron Modif - BD Consent for Commencement of Excavation &amp; ELS | TT_Task | 27/01/2019 | 23/02/2019 | 21/12/2018 | 01/02/2019 | 0 | TK_Complete | CCGTD1_IPS
OAM10090 | red | Outfall Apron Modif - Excavate to 0.5m below the shoring layer | TT_Task | 26/01/2019 | 28/01/2019 | 04/01/2019 | 12/01/2019 | 0 | TK_Complete | CCGTD1_IPS
OAM10100 | red | Outfall Apron Modif - Install the shoring | TT_Task | 29/01/2019 | 31/01/2019 | 14/01/2019 | 22/01/2019 | 0 | TK_Complete | CCGTD1_IPS
OAM10110 | red | Outfall Apron Modif - Excavate to final excavation level +1.5 mPD (Zone C) | TT_Task | 01/04/2019 | 02/04/2019 | 14/02/2019 | 01/03/2019 | 0 | TK_Complete | CCGTD1_IPS
OAM10115 | red | Outfall Apron Modif - Construct the box culvert section in Zone C | TT_Task | 01/06/2019 | 29/06/2019 | 08/05/2019 | 12/08/2019 | 0 | TK_Complete | CCGTD1_IPS
OAM10120 | red | Outfall Apron Modif - Construct the box culvert to 0.5 m below the shoring | TT_Task | 01/11/2019 | 14/11/2019 | 24/08/2019 | 02/09/2019 | 0 | TK_Complete | CCGTD1_IPS
OAM10130 | red | Outfall Apron Modif - Form the designed opening on apron wing wall (after stop logs installed) | TT_Task | 01/11/2019 | 04/11/2019 | 06/09/2019 | 24/09/2019 | 0 | TK_Complete | CCGTD1_IPS
OAM10140 | red | Outfall Apron Modif - Backfill to 0.5m below the shoring | TT_Task | 02/01/2020 | 03/01/2020 | 31/10/2019 | 01/11/2019 | 0 | TK_Complete | CCGTD1_IPS
OAM10150 | red | Outfall Apron Modif - Remove the shoring | TT_Task | 04/01/2020 | 04/01/2020 | 02/11/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
OAM10160 | red | Outfall Apron Modif - Construct the remaining box culvert structure | TT_Task | 05/11/2019 | 11/11/2019 | 25/09/2019 | 30/10/2019 | 0 | TK_Complete | CCGTD1_IPS
OAM10170 | red | Outfall Apron Modif - Trim pipe pile | TT_Task | 13/01/2020 | 14/01/2020 | 02/11/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
OAM10180 | red | Outfall Apron Modif - Backfill and reinstate crest wall and rock armour | TT_Task | 15/01/2020 | 21/01/2020 | 05/11/2019 | 09/11/2019 | 0 | TK_Complete | CCGTD1_IPS
THTT0010 | red | Turbine Table - Further excavate from +4.1 to +3.0 | TT_Task | 04/08/2017 | 22/08/2017 | 04/08/2017 | 28/08/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 31/07/2017
THTT0020 | red | Turbine Table - Cast blinding concrete | TT_Task | 27/11/2017 | 28/11/2017 | 23/10/2017 | 24/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT1010 | red | Turbine Table TT1 - Trim pile and prepare pile head | TT_Task | 25/09/2017 | 29/09/2017 | 25/09/2017 | 29/09/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 05/09/2017
THTT1020 | red | Turbine Table TT1 - Capping plate and rebar starter | TT_Task | 30/09/2017 | 07/10/2017 | 30/09/2017 | 07/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT1030 | red | Turbine Table TT1 Bottom Half - Erect side formwork (if any) | TT_Task | 26/10/2017 | 27/10/2017 | 26/10/2017 | 27/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT1040 | red | Turbine Table TT1 Bottom Half - Fix rebar | TT_Task | 30/10/2017 | 01/11/2017 | 30/10/2017 | 01/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT1050 | red | Turbine Table TT1 Bottom Half - Close formwork (if any) | TT_Task | 02/11/2017 | 02/11/2017 | 02/11/2017 | 02/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT1060 | red | Turbine Table TT1 Bottom Half - Pour concrete (mono pour) | TT_Task | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT1090 | red | Turbine Table TT1 - Install cast-in / embed items | TT_Task | 03/11/2017 | 06/11/2017 | 03/11/2017 | 06/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT1100 | red | Turbine Table TT1 Upper Half - Fix rebar | TT_Task | 04/11/2017 | 07/11/2017 | 04/11/2017 | 07/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT1110 | red | Turbine Table TT1 Upper Half - Close formwork (if any) | TT_Task | 08/11/2017 | 08/11/2017 | 08/11/2017 | 08/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT1120 | red | Turbine Table TT1 Upper Half - Pour concrete (mono pour) | TT_Task | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT1200 | red | Turbine Table TT1 - Construct Plinth PL1, PL2 with cast-in / embed items | TT_Task | 29/12/2017 | 19/01/2018 | 20/12/2017 | 25/01/2018 | 0 | TK_Complete | CCGTD1_IPS
THTT2010 | red | Turbine Table TT2 - Trim pile and prepare pile head | TT_Task | 30/09/2017 | 07/10/2017 | 30/09/2017 | 07/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT2020 | red | Turbine Table TT2 - Capping plate and rebar starter | TT_Task | 09/10/2017 | 13/10/2017 | 09/10/2017 | 13/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT2030 | red | Turbine Table TT2 Bottom Half - Erect side formwork (if any) | TT_Task | 03/11/2017 | 04/11/2017 | 03/11/2017 | 04/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT2040 | red | Turbine Table TT2 Bottom Half - Fix rebar | TT_Task | 06/11/2017 | 08/11/2017 | 06/11/2017 | 08/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT2050 | red | Turbine Table TT2 Bottom Half - Close formwork (if any) | TT_Task | 09/11/2017 | 09/11/2017 | 09/11/2017 | 09/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT2060 | red | Turbine Table TT2 Bottom Half - Pour concrete (mono pour) | TT_Task | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT2090 | red | Turbine Table TT2 - Install cast-in / embed items | TT_Task | 10/11/2017 | 13/11/2017 | 10/11/2017 | 13/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT2100 | red | Turbine Table TT2 Upper Half - Fix rebar | TT_Task | 11/11/2017 | 14/11/2017 | 11/11/2017 | 14/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT2110 | red | Turbine Table TT2 Upper Half - Close formwork (if any) | TT_Task | 15/11/2017 | 15/11/2017 | 15/11/2017 | 15/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT2120 | red | Turbine Table TT2 Upper Half - Pour concrete (mono pour) | TT_Task | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT2200 | red | Turbine Table TT2 - Construct Plinth PL3 with cast-in / embed items | TT_Task | 28/02/2018 | 15/03/2018 | 29/12/2017 | 29/01/2018 | 0 | TK_Complete | CCGTD1_IPS
THTT3010 | red | Turbine Table TT3 - Trim pile and prepare pile head | TT_Task | 09/10/2017 | 13/10/2017 | 09/10/2017 | 13/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT3020 | red | Turbine Table TT3 - Capping plate and rebar starter | TT_Task | 14/10/2017 | 19/10/2017 | 14/10/2017 | 19/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT3030 | red | Turbine Table TT3 Bottom Half - Erect side formwork (if any) | TT_Task | 10/11/2017 | 11/11/2017 | 10/11/2017 | 11/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT3040 | red | Turbine Table TT3 Bottom Half - Fix rebar | TT_Task | 13/11/2017 | 15/11/2017 | 13/11/2017 | 15/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT3050 | red | Turbine Table TT3 Bottom Half - Close formwork (if any) | TT_Task | 16/11/2017 | 16/11/2017 | 16/11/2017 | 16/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT3060 | red | Turbine Table TT3 Bottom Half - Pour concrete (mono pour) | TT_Task | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT3090 | red | Turbine Table TT3 - Install cast-in / embed items | TT_Task | 17/11/2017 | 20/11/2017 | 17/11/2017 | 20/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT3100 | red | Turbine Table TT3 Upper Half - Fix rebar | TT_Task | 18/11/2017 | 21/11/2017 | 18/11/2017 | 21/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT3110 | red | Turbine Table TT3 Upper Half - Close formwork (if any) | TT_Task | 22/11/2017 | 22/11/2017 | 22/11/2017 | 22/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT3120 | red | Turbine Table TT3 Upper Half - Pour concrete (mono pour) | TT_Task | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT3200 | red | Turbine Table TT3 - Construct Plinth PL4, 5, 6, 7, 8, 8a with cast-in / embed items | TT_Task | 28/02/2018 | 27/03/2018 | 29/12/2017 | 20/04/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 15/01/2018
THTT4010 | red | Turbine Table TT4 - Trim pile and prepare pile head | TT_Task | 14/10/2017 | 19/10/2017 | 14/10/2017 | 19/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT4020 | red | Turbine Table TT4 - Capping plate and rebar starter | TT_Task | 20/10/2017 | 24/10/2017 | 20/10/2017 | 23/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT4030 | red | Turbine Table TT4 - Erect side formwork (if any) | TT_Task | 24/11/2017 | 25/11/2017 | 24/11/2017 | 25/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT4040 | red | Turbine Table TT4 - Fix rebar and cast-in / embed items | TT_Task | 29/11/2017 | 01/12/2017 | 29/11/2017 | 01/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT4050 | red | Turbine Table TT4 - Close formwork (if any) | TT_Task | 01/12/2017 | 01/12/2017 | 01/12/2017 | 01/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT4060 | red | Turbine Table TT4 - Pour concrete (mono pour) | TT_Task | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT4200 | red | Turbine Table TT4 - Construct Plinth CEPL1, CEPL2 with cast-in / embed items | TT_Task | 16/03/2018 | 27/03/2018 | 16/01/2018 | 27/01/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 15/01/2018
THTT5010 | red | Turbine Table TT5 - Trim pile and prepare pile head | TT_Task | 20/10/2017 | 24/10/2017 | 20/10/2017 | 24/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT5020 | red | Turbine Table TT5 - Capping plate and rebar starter | TT_Task | 26/10/2017 | 31/10/2017 | 26/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT5030 | red | Turbine Table TT5 Bottom Half - Erect side formwork (if any) | TT_Task | 17/11/2017 | 18/11/2017 | 17/11/2017 | 18/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT5040 | red | Turbine Table TT5 Bottom Half - Fix rebar | TT_Task | 20/11/2017 | 22/11/2017 | 20/11/2017 | 22/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT5050 | red | Turbine Table TT5 Bottom Half - Close formwork (if any) | TT_Task | 23/11/2017 | 23/11/2017 | 23/11/2017 | 23/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT5060 | red | Turbine Table TT5 Bottom Half - Pour concrete (mono pour) | TT_Task | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT5090 | red | Turbine Table TT5 - Install cast-in / embed items | TT_Task | 24/11/2017 | 27/11/2017 | 24/11/2017 | 29/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT5100 | red | Turbine Table TT5 Upper Half - Fix rebar | TT_Task | 25/11/2017 | 28/11/2017 | 25/11/2017 | 30/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT5110 | red | Turbine Table TT5 Upper Half - Close formwork (if any) | TT_Task | 29/11/2017 | 29/11/2017 | 29/11/2017 | 29/11/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT5120 | red | Turbine Table TT5 Upper Half - Pour concrete (mono pour) | TT_Task | 02/12/2017 | 02/12/2017 | 02/12/2017 | 02/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THTT5130 | red | Turbine Table TT5 - Construct Plinth PL9, 10, 11, 12, 13 with cast-in / embed items | TT_Task | 28/03/2018 | 17/04/2018 | 19/01/2018 | 10/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF0020 | red | Ground Slab TH1 - Blinding to the profile of pile caps and ground beams | TT_Task | 06/10/2017 | 09/10/2017 | 08/09/2017 | 04/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THGF0030 | red | Ground Slab TH1 - Trim pile and prepare pile head | TT_Task | 10/10/2017 | 14/10/2017 | 05/09/2017 | 06/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THGF0040 | red | Ground Slab TH1 - Capping plate and rebar starter | TT_Task | 25/09/2017 | 07/10/2017 | 14/09/2017 | 07/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THGF0050 | red | Ground Slab TH1 - Erect side formwork | TT_Task | 09/10/2017 | 10/10/2017 | 22/09/2017 | 13/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF0060 | red | Ground Slab TH1 - Fix rebar for pile caps and ground beams and install cast-in / embed items | TT_Task | 12/10/2017 | 16/10/2017 | 20/09/2017 | 13/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF0070 | red | Ground Slab TH1 - Pour caps and beams to the level of ground floor slab underside | TT_Task | 17/10/2017 | 17/10/2017 | 23/09/2017 | 14/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF0080 | red | Ground Slab TH1 - Prepare CJ | TT_Task | 15/03/2018 | 15/03/2018 | 08/02/2018 | 13/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF0090 | red | Ground Slab TH1 - Fix ground floor slab rebar | TT_Task | 16/03/2018 | 21/03/2018 | 08/02/2018 | 13/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF0100 | red | Ground Slab TH1 - Pour ground slab | TT_Task | 22/03/2018 | 22/03/2018 | 14/02/2018 | 14/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF0110 | red | Ground Slab TH1 - Strike formwork (if any) | TT_Task | 23/03/2018 | 23/03/2018 | 20/02/2018 | 21/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF1020 | red | Ground Slab TH2 - Blinding to the profile of pile caps and ground beams | TT_Task | 19/03/2018 | 21/03/2018 | 18/01/2018 | 20/01/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF1030 | red | Ground Slab TH2 - Trim pile and prepare pile head | TT_Task | 10/10/2017 | 14/10/2017 | 05/09/2017 | 15/01/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF1040 | red | Ground Slab TH2 - Capping plate and rebar starter | TT_Task | 14/03/2018 | 17/03/2018 | 13/01/2018 | 17/01/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF1050 | red | Ground Slab TH2 - Erect side formwork | TT_Task | 22/03/2018 | 23/03/2018 | 02/02/2018 | 03/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF1060 | red | Ground Slab TH2 - Fix rebar for pile caps and ground beams install cast-in / embed items | TT_Task | 02/03/2018 | 07/03/2018 | 02/02/2018 | 03/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF1070 | red | Ground Slab TH2 - Pour caps and beams to the level of ground floor slab underside | TT_Task | 03/05/2018 | 03/05/2018 | 05/03/2018 | 05/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF1080 | red | Ground Slab TH2 - Prepare CJ | TT_Task | 06/03/2018 | 07/03/2018 | 24/02/2018 | 03/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF1090 | red | Ground Slab TH2 - Fix ground floor slab rebar | TT_Task | 26/02/2018 | 08/03/2018 | 24/02/2018 | 03/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF1100 | red | Ground Slab TH2 - Pour ground slab | TT_Task | 03/05/2018 | 03/05/2018 | 05/03/2018 | 05/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF1110 | red | Ground Slab TH2 - Strike formwork (if any) | TT_Task | 04/05/2018 | 04/05/2018 | 06/03/2018 | 06/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF2020 | red | Ground Slab TH3 - Blinding to the profile of pile caps and ground beams | TT_Task | 16/10/2017 | 19/10/2017 | 08/09/2017 | 04/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THGF2030 | red | Ground Slab TH3 - Trim pile and prepare pile head | TT_Task | 20/10/2017 | 24/10/2017 | 05/09/2017 | 13/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THGF2040 | red | Ground Slab TH3 - Capping plate and rebar starter | TT_Task | 10/10/2017 | 14/10/2017 | 10/10/2017 | 14/10/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 13/09/2017
THGF2050 | red | Ground Slab TH3 - Erect side formwork | TT_Task | 27/12/2017 | 30/12/2017 | 05/12/2017 | 13/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF2060 | red | Ground Slab TH3 - Fix rebar for pile caps and ground beams install cast-in / embed items | TT_Task | 02/01/2018 | 08/01/2018 | 09/12/2017 | 13/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF2070 | red | Ground Slab TH3 - Pour caps and beams to the level of ground floor slab underside | TT_Task | 14/03/2018 | 14/03/2018 | 20/01/2018 | 14/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF2080 | red | Ground Slab TH3 - Prepare CJ | TT_Task | 15/03/2018 | 15/03/2018 | 08/02/2018 | 13/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF2090 | red | Ground Slab TH3 - Fix ground floor slab rebar | TT_Task | 16/03/2018 | 21/03/2018 | 08/02/2018 | 13/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF2100 | red | Ground Slab TH3 - Pour ground slab | TT_Task | 22/03/2018 | 22/03/2018 | 14/02/2018 | 14/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF2110 | red | Ground Slab TH3 - Strike formwork (if any) | TT_Task | 23/03/2018 | 23/03/2018 | 20/02/2018 | 21/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF3010 | red | Ground Slab TH4 - Backfill the interface area between Turbine Table to +4.2 mPD | TT_Task | 06/12/2018 | 08/12/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF3020 | red | Ground Slab TH4 - Blinding to the profile of pile caps and ground beams | TT_Task | 26/11/2018 | 28/11/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF3030 | red | Ground Slab TH4 - Trim pile and prepare pile head | TT_Task | 27/12/2017 | 30/12/2017 | 18/12/2017 | 21/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THGF3040 | red | Ground Slab TH4 - Capping plate and rebar starter | TT_Task | 28/12/2017 | 02/01/2018 | 19/12/2017 | 22/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THGF3050 | red | Ground Slab TH4 - Erect side formwork | TT_Task | 26/11/2018 | 27/11/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF3060 | red | Ground Slab TH4 - Fix rebar for pile caps and ground beams install cast-in / embed items | TT_Task | 26/11/2018 | 29/11/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF3070 | red | Ground Slab TH4 - Pour caps and beams to the level of ground floor slab underside | TT_Task | 05/12/2018 | 05/12/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF3080 | red | Ground Slab TH4 - Prepare CJ | TT_Task | 30/11/2018 | 30/11/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF3090 | red | Ground Slab TH4 - Fix ground floor slab rebar | TT_Task | 01/12/2018 | 04/12/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF3100 | red | Ground Slab TH4 - Pour ground slab | TT_Task | 05/12/2018 | 05/12/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF4020 | red | Ground Slab TH5 - Blinding to the profile of pile caps and ground beams | TT_Task | 09/10/2017 | 12/10/2017 | 08/09/2017 | 06/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF4030 | red | Ground Slab TH5 - Trim pile and prepare pile head | TT_Task | 13/10/2017 | 17/10/2017 | 05/09/2017 | 20/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THGF4040 | red | Ground Slab TH5 - Capping plate and rebar starter | TT_Task | 17/10/2017 | 21/10/2017 | 17/10/2017 | 21/10/2017 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 14/09/2017
THGF4050 | red | Ground Slab TH5 - Erect side formwork | TT_Task | 06/03/2018 | 09/03/2018 | 07/02/2018 | 06/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF4060 | red | Ground Slab TH5 - Fix rebar for pile caps and ground beams install cast-in / embed items | TT_Task | 02/03/2018 | 09/03/2018 | 07/02/2018 | 06/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF4070 | red | Ground Slab TH5 - Pour caps and beams to the level of ground floor slab underside | TT_Task | 08/05/2018 | 08/05/2018 | 07/03/2018 | 07/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF4080 | red | Ground Slab TH5 - Prepare CJ | TT_Task | 23/04/2018 | 04/05/2018 | 26/02/2018 | 06/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF4090 | red | Ground Slab TH5 - Fix ground floor slab rebar | TT_Task | 24/04/2018 | 04/05/2018 | 27/02/2018 | 06/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF4100 | red | Ground Slab TH5 - Pour ground slab | TT_Task | 08/05/2018 | 08/05/2018 | 07/03/2018 | 07/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF4110 | red | Ground Slab TH5 - Strike formwork (if any) | TT_Task | 10/05/2018 | 10/05/2018 | 08/03/2018 | 08/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF5010 | red | Ground Slab TH6 - Backfill the interface area between Turbine Table to +4.2 mPD | TT_Task | 06/12/2018 | 08/12/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF5020 | red | Ground Slab TH6 - Blinding to the profile of pile caps and ground beams | TT_Task | 29/11/2018 | 01/12/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF5030 | red | Ground Slab TH6 - Trim pile and prepare pile head | TT_Task | 27/12/2017 | 30/12/2017 | 11/12/2017 | 14/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THGF5040 | red | Ground Slab TH6 - Capping plate and rebar starter | TT_Task | 28/12/2017 | 02/01/2018 | 12/12/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THGF5050 | red | Ground Slab TH6 - Erect side formwork | TT_Task | 26/11/2018 | 27/11/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF5060 | red | Ground Slab TH6 - Fix rebar for pile caps and ground beams install cast-in / embed items | TT_Task | 26/11/2018 | 29/11/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF5070 | red | Ground Slab TH6 - Pour caps and beams to the level of ground floor slab underside | TT_Task | 05/12/2018 | 05/12/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF5080 | red | Ground Slab TH6 - Prepare CJ | TT_Task | 30/11/2018 | 30/11/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF5090 | red | Ground Slab TH6 - Fix ground floor slab rebar | TT_Task | 01/12/2018 | 04/12/2018 | 10/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF5100 | red | Ground Slab TH6 - Pour ground slab | TT_Task | 05/12/2018 | 05/12/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF6020 | red | Ground Slab TH7 - Blinding to the profile of pile caps and ground beams | TT_Task | 02/03/2018 | 05/03/2018 | 22/02/2018 | 24/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF6030 | red | Ground Slab TH7 - Trim pile and prepare pile head | TT_Task | 21/10/2017 | 27/10/2017 | 21/10/2017 | 10/01/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF6040 | red | Ground Slab TH7 - Capping plate and rebar starter | TT_Task | 06/03/2018 | 09/03/2018 | 08/01/2018 | 21/02/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF6050 | red | Ground Slab TH7 - Erect side formwork | TT_Task | 06/03/2018 | 07/03/2018 | 07/02/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF6060 | red | Ground Slab TH7 - Fix rebar for pile caps and ground beams install cast-in / embed items | TT_Task | 06/03/2018 | 09/03/2018 | 07/02/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF6070 | red | Ground Slab TH7 - Pour caps and beams to the level of ground floor slab underside | TT_Task | 29/05/2018 | 29/05/2018 | 29/03/2018 | 28/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF6080 | red | Ground Slab TH7 - Prepare CJ | TT_Task | 23/04/2018 | 30/04/2018 | 17/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF6090 | red | Ground Slab TH7 - Fix ground floor slab rebar | TT_Task | 23/04/2018 | 30/04/2018 | 17/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF6100 | red | Ground Slab TH7 - Pour ground slab | TT_Task | 29/05/2018 | 29/05/2018 | 28/04/2018 | 28/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF6110 | red | Ground Slab TH7 - Strike formwork (if any) | TT_Task | 31/05/2018 | 31/05/2018 | 30/04/2018 | 30/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF7020 | red | Ground Slab TH8 - Blinding to the profile of pile caps and ground beams | TT_Task | 20/03/2018 | 22/03/2018 | 19/01/2018 | 22/01/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF7030 | red | Ground Slab TH8 - Trim pile and prepare pile head | TT_Task | 14/03/2018 | 17/03/2018 | 13/01/2018 | 17/01/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF7040 | red | Ground Slab TH8 - Capping plate and rebar starter | TT_Task | 15/03/2018 | 19/03/2018 | 15/01/2018 | 18/01/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF7050 | red | Ground Slab TH8 - Erect side formwork | TT_Task | 23/04/2018 | 12/05/2018 | 26/02/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF7060 | red | Ground Slab TH8 - Fix rebar for pile caps and ground beams install cast-in / embed items | TT_Task | 23/04/2018 | 12/05/2018 | 26/02/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF7070 | red | Ground Slab TH8 - Pour caps and beams to the level of ground floor slab underside | TT_Task | 14/05/2018 | 14/05/2018 | 24/03/2018 | 24/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF7080 | red | Ground Slab TH8 - Prepare CJ | TT_Task | 07/05/2018 | 12/05/2018 | 14/03/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF7090 | red | Ground Slab TH8 - Fix ground floor slab rebar | TT_Task | 07/05/2018 | 12/05/2018 | 14/03/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF7100 | red | Ground Slab TH8 - Pour ground slab | TT_Task | 14/05/2018 | 14/05/2018 | 24/03/2018 | 24/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF7110 | red | Ground Slab TH8 - Strike formwork (if any) | TT_Task | 15/05/2018 | 15/05/2018 | 25/03/2018 | 25/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF8020 | red | Ground Slab TH9 - Blinding to the profile of pile caps and ground beams | TT_Task | 20/03/2018 | 22/03/2018 | 19/01/2018 | 22/01/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF8030 | red | Ground Slab TH9 - Trim pile and prepare pile head | TT_Task | 14/03/2018 | 17/03/2018 | 13/01/2018 | 17/01/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF8040 | red | Ground Slab TH9 - Capping plate and rebar starter | TT_Task | 15/03/2018 | 19/03/2018 | 15/01/2018 | 18/01/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF8050 | red | Ground Slab TH9 - Erect side formwork | TT_Task | 23/04/2018 | 12/05/2018 | 26/02/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF8060 | red | Ground Slab TH9 - Fix rebar for pile caps and ground beams install cast-in / embed items | TT_Task | 23/04/2018 | 12/05/2018 | 26/02/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF8070 | red | Ground Slab TH9 - Pour caps and beams to the level of ground floor slab underside | TT_Task | 14/05/2018 | 14/05/2018 | 24/03/2018 | 24/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF8080 | red | Ground Slab TH9 - Prepare CJ | TT_Task | 07/05/2018 | 12/05/2018 | 14/03/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF8090 | red | Ground Slab TH9 - Fix ground floor slab rebar | TT_Task | 07/05/2018 | 12/05/2018 | 14/03/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF8100 | red | Ground Slab TH9 - Pour ground slab | TT_Task | 14/05/2018 | 14/05/2018 | 24/03/2018 | 24/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF8110 | red | Ground Slab TH9 - Strike formwork (if any) | TT_Task | 26/11/2018 | 26/11/2018 | 25/03/2018 | 25/03/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF9010 | red | Ground Slab TH10 - Backfill the interface area between Cond.Polishing Pit | TT_Task | 06/12/2018 | 08/12/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF9020 | red | Ground Slab TH10 - Blinding to the profile of pile caps and ground beams | TT_Task | 26/11/2018 | 28/11/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF9030 | red | Ground Slab TH10 - Trim pile and prepare pile head | TT_Task | 27/12/2017 | 30/12/2017 | 04/12/2017 | 07/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THGF9040 | red | Ground Slab TH10 - Capping plate and rebar starter | TT_Task | 28/12/2017 | 02/01/2018 | 05/12/2017 | 08/12/2017 | 0 | TK_Complete | CCGTD1_IPS
THGF9050 | red | Ground Slab TH10 - Erect side formwork | TT_Task | 26/11/2018 | 27/11/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF9060 | red | Ground Slab TH10 - Fix rebar for pile caps and ground beams install cast-in / embed items | TT_Task | 26/11/2018 | 29/11/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF9070 | red | Ground Slab TH10 - Pour caps and beams to the level of ground floor slab underside | TT_Task | 05/12/2018 | 05/12/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF9080 | red | Ground Slab TH10 - Prepare CJ | TT_Task | 26/11/2018 | 26/11/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF9090 | red | Ground Slab TH10 - Fix ground floor slab rebar | TT_Task | 01/12/2018 | 04/12/2018 | 10/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF9100 | red | Ground Slab TH10 - Pour ground slab | TT_Task | 05/12/2018 | 05/12/2018 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THGF9110 | red | Ground Slab TH10 - Strike formwork (if any) | TT_Task | 27/11/2018 | 27/11/2018 | 02/10/2018 | 02/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0010 | red | Condensate Pit - Further excavate from +4.1 mPD to the pit formation level | TT_Task | 26/02/2018 | 27/02/2018 | 15/01/2018 | 27/01/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0015 | red | Condensate Pit - Sheet piling adjoining Turbine Table | TT_Task | 28/09/2017 | 24/10/2017 | 30/09/2017 | 21/10/2017 | 0 | TK_Complete | CCGTD1_IPS
THCP0020 | red | Condensate Pit - Sheet piling for the sump pit | TT_Task | 27/12/2017 | 08/01/2018 | 21/12/2017 | 14/01/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 04/12/2017
THCP0030 | red | Condensate Pit - Excavation and construct the sump pit to the underside level of pit slab | TT_Task | 26/11/2018 | 04/12/2018 | 08/10/2018 | 09/11/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0040 | red | Condensate Pit - Trim sheet pile head (pump pit) | TT_Task | 05/12/2018 | 06/12/2018 | 25/06/2018 | 05/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0042 | red | Condensate Pit - Complete the slab around the sump pit (previosuly left out) | TT_Task | 07/12/2018 | 10/12/2018 | 12/11/2018 | 22/11/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0050 | red | Condensate Pit - Trim pile and prepare pile head | TT_Task | 28/02/2018 | 01/03/2018 | 29/01/2018 | 16/06/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0060 | red | Condensate Pit - Capping plate and rebar starter | TT_Task | 01/03/2018 | 03/03/2018 | 30/01/2018 | 19/06/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0070 | red | Condensate Pit - Vertical blinding to the profile of pile caps, ground beams and shallow pits | TT_Task | 12/05/2018 | 15/05/2018 | 13/03/2018 | 14/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0075 | red | Condensate Pit - Install waterproofing | TT_Task | 15/05/2018 | 15/05/2018 | 20/03/2018 | 27/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0080 | red | Condensate Pit - Fix rebar for pile caps, ground beams and shallow pits | TT_Task | 18/05/2018 | 21/05/2018 | 21/03/2018 | 06/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0090 | red | Condensate Pit - Close formwork | TT_Task | 24/05/2018 | 24/05/2018 | 16/04/2018 | 06/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0100 | red | Condensate Pit - Pour caps, beams and shallow pits to the underside level of pit slab | TT_Task | 25/05/2018 | 25/05/2018 | 18/04/2018 | 07/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0110 | red | Condensate Pit - Prepare CJ | TT_Task | 26/05/2018 | 26/05/2018 | 19/04/2018 | 10/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0120 | red | Condensate Pit - Fix pit slab rebar | TT_Task | 28/05/2018 | 29/05/2018 | 21/03/2018 | 06/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0130 | red | Condensate Pit - Pour pit slab and kicker | TT_Task | 31/05/2018 | 31/05/2018 | 18/04/2018 | 07/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0140 | red | Condensate Pit - Erect wall formwork | TT_Task | 01/06/2018 | 02/06/2018 | 19/04/2018 | 31/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0150 | red | Condensate Pit - Fix wall and column rebar | TT_Task | 04/06/2018 | 07/06/2018 | 19/04/2018 | 31/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0160 | red | Condensate Pit - Close wall formwork | TT_Task | 07/06/2018 | 07/06/2018 | 22/04/2018 | 02/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0170 | red | Condensate Pit - Pour walls and columns to the underside of Turbine Hall ground slab | TT_Task | 31/07/2018 | 31/07/2018 | 04/05/2018 | 03/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0180 | red | Condensate Pit - Curing | TT_Task | 02/12/2018 | 04/12/2018 | 04/09/2018 | 06/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0190 | red | Condensate Pit - Apply waterproofing to the external face of pit wall | TT_Task | 26/11/2018 | 27/11/2018 | 07/09/2018 | 07/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THCP0200 | red | Condensate Pit - Backfill againt basement wall | TT_Task | 26/11/2018 | 28/11/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0010 | red | Cond.Polishing Pit - Further excavate from +4.1 mPD to the pit formation level | TT_Task | 26/02/2018 | 02/03/2018 | 15/01/2018 | 27/01/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0050 | red | Cond.Polishing Pit - Trim pile and prepare pile head | TT_Task | 03/03/2018 | 05/03/2018 | 29/01/2018 | 21/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0060 | red | Cond.Polishing Pit - Capping plate and rebar starter | TT_Task | 05/03/2018 | 07/03/2018 | 30/01/2018 | 22/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0070 | red | Cond.Polishing Pit - Vertical blinding to the profile of pile caps, ground beams and shallow pits | TT_Task | 14/05/2018 | 17/05/2018 | 12/04/2018 | 31/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0075 | red | Cond.Polishing Pit - Install waterproofing | TT_Task | 18/05/2018 | 18/05/2018 | 16/04/2018 | 26/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0080 | red | Cond.Polishing Pit - Fix rebar for pile caps, ground beams and shallow pits | TT_Task | 01/06/2018 | 04/06/2018 | 03/05/2018 | 22/06/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0090 | red | Cond.Polishing Pit - Close formwork | TT_Task | 04/06/2018 | 04/06/2018 | 23/05/2018 | 30/06/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0100 | red | Cond.Polishing Pit - Pour caps, beams and shallow pits to the underside level of pit slab | TT_Task | 05/06/2018 | 05/06/2018 | 24/05/2018 | 01/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0110 | red | Cond.Polishing Pit - Prepare CJ | TT_Task | 07/06/2018 | 07/06/2018 | 25/05/2018 | 04/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0120 | red | Cond.Polishing Pit - Fix pit slab rebar | TT_Task | 05/07/2018 | 06/07/2018 | 22/05/2018 | 22/06/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0130 | red | Cond.Polishing Pit - Pour pit slab | TT_Task | 30/06/2018 | 30/06/2018 | 24/05/2018 | 01/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0140 | red | Cond.Polishing Pit - Erect wall formwork | TT_Task | 03/07/2018 | 07/07/2018 | 12/06/2018 | 18/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0150 | red | Cond.Polishing Pit - Fix wall and column rebar | TT_Task | 26/06/2018 | 17/07/2018 | 09/06/2018 | 24/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0160 | red | Cond.Polishing Pit - Close wall formwork | TT_Task | 30/06/2018 | 19/07/2018 | 12/06/2018 | 04/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0170 | red | Cond.Polishing Pit - Pour walls and columns to the underside of Turbine Hall ground slab | TT_Task | 26/07/2018 | 10/08/2018 | 01/07/2018 | 07/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0180 | red | Cond.Polishing Pit - Curing | TT_Task | 09/09/2018 | 11/09/2018 | 08/08/2018 | 10/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0190 | red | Cond.Polishing Pit - Apply waterproofing to the external face of pit wall | TT_Task | 10/09/2018 | 11/09/2018 | 09/08/2018 | 10/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THPP0200 | red | Cond.Polishing Pit - Backfill againt basement wall | TT_Task | 26/11/2018 | 28/11/2018 | 07/09/2018 | 09/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0010 | red | Turbine Hall GL1~5 - Erect steel columns SC1(SC2) (w/ Overhead Crane support columns) at GL.1-5 /H | TT_Task | 23/04/2018 | 10/05/2018 | 29/03/2018 | 13/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0020 | red | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.1 /G2-C | TT_Task | 28/04/2018 | 07/05/2018 | 31/03/2018 | 07/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0030 | red | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /G | TT_Task | 08/05/2018 | 09/05/2018 | 09/04/2018 | 10/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0040 | red | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /F | TT_Task | 08/05/2018 | 09/05/2018 | 09/04/2018 | 10/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0050 | red | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /E | TT_Task | 26/05/2018 | 26/05/2018 | 03/05/2018 | 03/05/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 02/05/2018
THSS0060 | red | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /D | TT_Task | 28/05/2018 | 28/05/2018 | 05/05/2018 | 05/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0070 | red | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /C | TT_Task | 29/05/2018 | 29/05/2018 | 07/05/2018 | 07/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0080 | red | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.1 /B | TT_Task | 04/06/2018 | 04/06/2018 | 02/05/2018 | 02/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0090 | red | Turbine Hall GL1~5 - Erect steel columns SC1(SC2)(w/ Overhead Crane support columns) at GL.1-4 /A | TT_Task | 05/06/2018 | 08/06/2018 | 03/05/2018 | 08/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0100 | red | Turbine Hall GL1~5 - Erect steel columns SC1 (w/ Overhead Crane support columns) at GL.5 /A | TT_Task | 09/06/2018 | 13/06/2018 | 09/05/2018 | 12/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0110 | red | Turbine Hall GL.1-5 /H-G2/G1 (Bay 1a) - Connect erected columns by beams and bracing to +37.26 | TT_Task | 11/05/2018 | 14/05/2018 | 14/04/2018 | 17/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0120 | red | Turbine Hall GL.1-5 /G2/G1-G (Bay 2a) - Connect erected columns by beams and bracing to +37.26 | TT_Task | 14/05/2018 | 16/05/2018 | 17/04/2018 | 19/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0130 | red | Turbine Hall GL.1-5 /G-F (Bay 3a) - Connect erected columns by beams and bracing to +37.26 | TT_Task | 16/05/2018 | 18/05/2018 | 19/04/2018 | 21/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0140 | red | Turbine Hall GL.1-5 /F-E (Bay 4a) - Connect erected columns by beams and bracing to +37.26 | TT_Task | 28/05/2018 | 30/05/2018 | 05/05/2018 | 08/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0150 | red | Turbine Hall GL.1-5 /E-D (Bay 5a) - Connect erected columns by beams and bracing to +37.26 | TT_Task | 30/05/2018 | 02/06/2018 | 08/05/2018 | 10/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0160 | red | Turbine Hall GL.1-5 /D-C (Bay 6a) - Connect erected columns by beams and bracing to +37.26 | TT_Task | 02/06/2018 | 05/06/2018 | 10/05/2018 | 12/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0170 | red | Turbine Hall GL.1-5 /C-B (Bay 7a) - Connect erected columns by beams and bracing to +37.26 | TT_Task | 05/06/2018 | 07/06/2018 | 12/05/2018 | 15/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0180 | red | Turbine Hall GL.1-5 /B-A (Bay 8a) - Connect erected columns by beams and bracing to +37.26 | TT_Task | 14/06/2018 | 16/06/2018 | 15/05/2018 | 17/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0210 | red | Turbine Hall GL.1-5 - Install main beams to the steel columns at GL.1-5 /H, +37.26 | TT_Task | 15/05/2018 | 16/05/2018 | 18/04/2018 | 19/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0220 | red | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /G2-G1, +37.26 | TT_Task | 17/05/2018 | 18/05/2018 | 12/04/2018 | 13/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0230 | red | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /G, +37.26 | TT_Task | 19/05/2018 | 21/05/2018 | 17/04/2018 | 18/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0240 | red | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /F, +37.26 | TT_Task | 26/05/2018 | 28/05/2018 | 23/04/2018 | 24/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0250 | red | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /E, +37.26 | TT_Task | 04/06/2018 | 05/06/2018 | 11/05/2018 | 12/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0260 | red | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /D, +37.26 | TT_Task | 06/06/2018 | 07/06/2018 | 14/05/2018 | 15/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0270 | red | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /C, +37.26 | TT_Task | 08/06/2018 | 09/06/2018 | 16/05/2018 | 17/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0280 | red | Turbine Hall GL.1-5 - Install main trusses to the steel columns at GL.1-5 /B, +37.26 | TT_Task | 16/06/2018 | 19/06/2018 | 17/05/2018 | 18/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0290 | red | Turbine Hall GL.1-5 - Install main beams to the steel columns at GL.1-5 /A, +37.26 | TT_Task | 19/06/2018 | 20/06/2018 | 18/05/2018 | 19/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0310 | red | Turbine Hall GL.1-5 /H-G2/G1 (Bay 1a) - Connect installed trusses by secondary beams and bracing | TT_Task | 26/05/2018 | 29/05/2018 | 23/04/2018 | 25/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0320 | red | Turbine Hall GL.1-5 /G2/G1-G (Bay 2a) - Connect installed trusses by secondary beams and bracing | TT_Task | 26/05/2018 | 29/05/2018 | 23/04/2018 | 25/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0330 | red | Turbine Hall GL.1-5 /G-F (Bay 3a) - Connect installed trusses by secondary beams and bracing | TT_Task | 29/05/2018 | 31/05/2018 | 25/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0340 | red | Turbine Hall GL.1-5 /F-E (Bay 4a) - Connect installed trusses by secondary beams and bracing | TT_Task | 06/06/2018 | 08/06/2018 | 14/05/2018 | 16/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0350 | red | Turbine Hall GL.1-5 /E-D (Bay 5a) - Connect installed trusses by secondary beams and bracing | TT_Task | 08/06/2018 | 11/06/2018 | 16/05/2018 | 18/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0360 | red | Turbine Hall GL.1-5 /D-C (Bay 6a) - Connect installed trusses by secondary beams and bracing | TT_Task | 11/06/2018 | 13/06/2018 | 18/05/2018 | 21/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0370XX | red | Turbine Hall GL.1-5 /C-B (Bay 7a) - Connect installed trusses by secondary beams and bracing [Deferred Works] | TT_Task | 02/01/2020 | 02/01/2020 | 19/05/2018 | 19/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0380 | red | Turbine Hall GL.1-5 /B-A (Bay 8a) - Connect installed trusses by secondary beams and bracing | TT_Task | 21/06/2018 | 23/06/2018 | 21/05/2018 | 24/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0420 | red | Turbine Hall GL.2-4 /G2/G1-G (Bay 2a) - Install upper roof steel structure | TT_Task | 30/05/2018 | 31/05/2018 | 26/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0430 | red | Turbine Hall GL.2-4 /G-F (Bay 3a) - Install upper roof steel structure | TT_Task | 02/06/2018 | 04/06/2018 | 28/04/2018 | 30/04/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0440 | red | Turbine Hall GL.2-4 /F-E (Bay 4a) - Install upper roof steel structure | TT_Task | 05/06/2018 | 06/06/2018 | 02/05/2018 | 03/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0450 | red | Turbine Hall GL.2-4 /E-D (Bay 5a) - Install upper roof steel structure | TT_Task | 12/06/2018 | 13/06/2018 | 19/05/2018 | 21/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0460 | red | Turbine Hall GL.2-4 /D-C (Bay 6a) - Install upper roof steel structure | TT_Task | 14/06/2018 | 15/06/2018 | 23/05/2018 | 24/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS0470XX | red | Turbine Hall GL.2-4 /C-B (Bay 7a) - Install upper roof steel structure [Deferred Works] | TT_Task | 02/01/2020 | 02/01/2020 | 19/05/2018 | 19/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1010 | red | Turbine Hall GL5-7 - Erect steel columns SC3(SC2) at GL.6-7 /H | TT_Task | 26/06/2018 | 27/06/2018 | 11/06/2018 | 16/06/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1020 | red | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /G2-G1 | TT_Task | 28/06/2018 | 30/06/2018 | 14/06/2018 | 20/06/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1030 | red | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /F1 | TT_Task | 26/11/2018 | 26/11/2018 | 26/09/2018 | 26/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1040 | red | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /F | TT_Task | 26/11/2018 | 26/11/2018 | 27/09/2018 | 27/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1050 | red | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /E | TT_Task | 27/11/2018 | 27/11/2018 | 28/09/2018 | 28/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1060 | red | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /D | TT_Task | 28/11/2018 | 28/11/2018 | 29/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1070 | red | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /C | TT_Task | 29/11/2018 | 29/11/2018 | 02/10/2018 | 02/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1080 | red | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /B | TT_Task | 30/11/2018 | 30/11/2018 | 03/10/2018 | 03/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1090 | red | Turbine Hall GL5-7 - Erect steel columns SC3 at GL.7 /A | TT_Task | 26/11/2018 | 28/11/2018 | 04/10/2018 | 06/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1110 | red | Turbine Hall GL5-7 /H-G1 (Bay 1b) - Connect erected columns by beams and bracing to +32.26 | TT_Task | 26/06/2018 | 28/06/2018 | 21/06/2018 | 23/06/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1120 | red | Turbine Hall GL5-7 /G1 -F (Bay 2b) - Connect erected columns by beams and bracing to +32.26 | TT_Task | 26/11/2018 | 28/11/2018 | 28/09/2018 | 02/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1130 | red | Turbine Hall GL5-7 /F-E (Bay 3b) - Connect erected columns by beams and bracing to +32.26 | TT_Task | 26/11/2018 | 28/11/2018 | 03/10/2018 | 05/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1140 | red | Turbine Hall GL5-7 /E-D (Bay 4b) - Connect erected columns by beams and bracing to +32.26 | TT_Task | 29/11/2018 | 01/12/2018 | 06/10/2018 | 09/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1150 | red | Turbine Hall GL5-7 /D-C (Bay 5b) - Connect erected columns by beams and bracing to +32.26 | TT_Task | 03/12/2018 | 05/12/2018 | 10/10/2018 | 12/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1160 | red | Turbine Hall GL5-7 /C-B (Bay 6b) - Connect erected columns by beams and bracing to +32.26 | TT_Task | 06/12/2018 | 08/12/2018 | 13/10/2018 | 16/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1170 | red | Turbine Hall GL5-7 /B-A (Bay 7b) - Connect erected columns by beams and bracing to +32.26 | TT_Task | 10/12/2018 | 12/12/2018 | 17/10/2018 | 23/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1210 | red | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /H, +32.26 | TT_Task | 03/07/2018 | 03/07/2018 | 25/06/2018 | 25/06/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1220 | red | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /G1, +32.26 | TT_Task | 26/11/2018 | 26/11/2018 | 03/10/2018 | 03/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1230 | red | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /F, +32.26 | TT_Task | 29/11/2018 | 29/11/2018 | 06/10/2018 | 06/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1240 | red | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /E, +32.26 | TT_Task | 03/12/2018 | 03/12/2018 | 10/10/2018 | 10/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1250 | red | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /D, +32.26 | TT_Task | 06/12/2018 | 06/12/2018 | 13/10/2018 | 13/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1260 | red | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /C, +32.26 | TT_Task | 10/12/2018 | 10/12/2018 | 17/10/2018 | 17/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1270 | red | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /B, +32.26 | TT_Task | 13/12/2018 | 13/12/2018 | 24/10/2018 | 24/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1280 | red | Turbine Hall GL.5-7 - Install main beams to the steel columns at GL.5-7 /A, +32.26 | TT_Task | 13/12/2018 | 13/12/2018 | 25/10/2018 | 25/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1310 | red | Turbine Hall GL5-7 /H-G1 (Bay 1b) - Connect installed trusses by secondary beams and bracing (Event 046 - ROI #199) | TT_Task | 26/11/2018 | 26/11/2018 | 30/10/2018 | 03/11/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1320 | red | Turbine Hall GL5-7 /G1 -F (Bay 2b) - Connect installed trusses by secondary beams and bracing | TT_Task | 26/11/2018 | 27/11/2018 | 08/10/2018 | 09/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1330 | red | Turbine Hall GL5-7 /F-E (Bay 3b) - Connect installed trusses by secondary beams and bracing | TT_Task | 28/11/2018 | 29/11/2018 | 11/10/2018 | 12/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1340 | red | Turbine Hall GL5-7 /E-D (Bay 4b) - Connect installed trusses by secondary beams and bracing | TT_Task | 30/11/2018 | 01/12/2018 | 15/10/2018 | 16/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1350 | red | Turbine Hall GL5-7 /D-C (Bay 5b) - Connect installed trusses by secondary beams and bracing | TT_Task | 03/12/2018 | 04/12/2018 | 18/10/2018 | 19/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1360 | red | Turbine Hall GL5-7 /C-B (Bay 6b) - Connect installed trusses by 2ndary beams &amp; bracing [DEF_WK07 not required] | TT_Task | 26/11/2018 | 27/11/2018 | 25/10/2018 | 26/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS1370 | red | Turbine Hall GL5-7 /B-A (Bay 7b) - Connect installed trusses by secondary beams and bracing | TT_Task | 14/12/2018 | 15/12/2018 | 27/10/2018 | 29/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2010 | red | Turbine Hall GL.7-10 (Bay 1c) - Erect steel columns and bracing SC4 at GL.7-10 /K1-G1 | TT_Task | 28/06/2018 | 30/06/2018 | 21/06/2018 | 10/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2020 | red | Turbine Hall GL.7-10 (Bay 2c) - Erect steel columns and bracing SC4 at GL.7-10 /G1-F | TT_Task | 26/11/2018 | 28/11/2018 | 28/09/2018 | 02/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2030 | red | Turbine Hall GL.7-10 (Bay 3c) - Erect steel columns and bracing SC4 at GL.7-10 /F-C | TT_Task | 26/11/2018 | 28/11/2018 | 30/10/2018 | 01/11/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2040 | red | Turbine Hall GL.7-10 (Bay 4c) - Erect steel columns and bracing SC4 at GL.7-10 /C-A | TT_Task | 29/11/2018 | 01/12/2018 | 06/11/2018 | 08/11/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2110 | red | Turbine Hall GL.7-10 (Bay 1c) - Install steel main and secondary beams at level +10.8 | TT_Task | 03/07/2018 | 05/07/2018 | 25/06/2018 | 12/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2120 | red | Turbine Hall GL.7-10 (Bay 2c) - Install steel main and secondary beams at to level +10.8 | TT_Task | 06/12/2018 | 08/12/2018 | 03/10/2018 | 05/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2130 | red | Turbine Hall GL.7-10 (Bay 3c) - Install steel main and secondary beams at to level +10.8 | TT_Task | 26/11/2018 | 28/11/2018 | 02/11/2018 | 05/11/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2210 | red | Turbine Hall GL.7-10 (Bay 1c) - Construct floor slab at level +10.8 | TT_Task | 27/08/2018 | 29/08/2018 | 23/07/2018 | 06/09/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2220 | red | Turbine Hall GL.7-10 (Bay 2c) - Construct floor slab at to level +10.8 | TT_Task | 26/11/2018 | 28/11/2018 | 02/11/2018 | 18/11/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2230 | red | Turbine Hall GL.7-10 (Bay 3c) - Construct floor slab at level +10.8 | TT_Task | 26/01/2019 | 13/02/2019 | 28/11/2018 | 14/12/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2240 | blue | Turbine Hall GL.7-10 - Complete floor slab at level +10.8 | TT_FinMile | 13/02/2019 | 13/02/2019 | 14/12/2018 | 14/12/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2310 | red | Turbine Hall GL.7-10 (Bay 1c) - Install steel beams and bracing at level +14.85 | TT_Task | 26/07/2018 | 08/08/2018 | 29/06/2018 | 14/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2320 | red | Turbine Hall GL.7-10 (Bay 2c) - Install steel beams and bracing at level +14.85 | TT_Task | 13/12/2018 | 17/12/2018 | 06/10/2018 | 10/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2330 | red | Turbine Hall GL.7-10 (Bay 3c) - Install steel beams and bracing at level +14.85 | TT_Task | 26/11/2018 | 29/11/2018 | 09/11/2018 | 13/11/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2340 | red | Turbine Hall GL.7-10 (Bay 4c) - Install steel beams and bracing at level +14.85 | TT_Task | 30/11/2018 | 04/12/2018 | 14/11/2018 | 19/11/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2400 | red | Turbine Hall GL.7-10 (Bay 1c) - Construct roof slab at level +14.85 | TT_Task | 26/11/2018 | 18/12/2018 | 27/09/2018 | 23/10/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2410 | red | Turbine Hall GL.7-10 (Bay 2c) - Construct roof slab at level +14.85 | TT_Task | 26/01/2019 | 13/02/2019 | 24/11/2018 | 14/12/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2420 | red | Turbine Hall GL.7-10 (Bay 3c) - Construct roof slab at level +14.85 | TT_Task | 26/01/2019 | 15/02/2019 | 16/12/2018 | 29/12/2018 | 0 | TK_Complete | CCGTD1_IPS
THSS2430 | blue | Turbine Hall GL.7-10 - Complete roof slab at level +14.85 | TT_FinMile | 26/01/2019 | 26/01/2019 | 29/12/2018 | 29/12/2018 | 0 | TK_Complete | CCGTD1_IPS
DEF_WK01 | red | DW01 - Construct Roof of Turbine Hall (GL.B~C /1-5) after installation of main OH crane | TT_Task | 26/07/2018 | 31/08/2018 | 23/07/2018 | 05/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF0510 | red | Turbine Hall GL.1-5 /H-G2/G1 (Bay 1a) - Kalbau | TT_Task | 26/06/2018 | 28/06/2018 | 07/06/2018 | 26/06/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 06/06/2018
THRF0520 | red | Turbine Hall GL.1-5 /G2/G1-G (Bay 2a) - Kalbau | TT_Task | 29/06/2018 | 03/07/2018 | 20/06/2018 | 29/06/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF0530 | red | Turbine Hall GL.1-5 /G-F (Bay 3a) - Kalbau | TT_Task | 31/07/2018 | 02/08/2018 | 29/06/2018 | 03/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF0540 | red | Turbine Hall GL.1-5 /F-E (Bay 4a) - Kalbau | TT_Task | 04/08/2018 | 07/08/2018 | 03/07/2018 | 07/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF0550 | red | Turbine Hall GL.1-5 /E-D (Bay 5a) - Kalbau | TT_Task | 08/08/2018 | 10/08/2018 | 07/07/2018 | 09/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF0560 | red | Turbine Hall GL.1-5 /D-C (Bay 6a) - Kalbau | TT_Task | 11/08/2018 | 14/08/2018 | 09/07/2018 | 10/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF0570XX | red | Turbine Hall GL.1-5 /C-B (Bay 7a) - Install standing seam roof cladding [Deferred Works] | TT_Task | 02/01/2020 | 02/01/2020 | 19/05/2018 | 19/05/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF0580 | red | Turbine Hall GL.1-5 /B-A (Bay 8a) - Kalbau | TT_Task | 19/07/2018 | 21/07/2018 | 13/06/2018 | 12/07/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF0590 | blue | Turbine Hall GL.1-5 - Weathertight (i.e. Kalbau installed with temporary measures) | TT_FinMile | 05/09/2018 | 05/09/2018 | 05/08/2018 | 05/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF0610 | red | Turbine Hall GL.1-5 - Vapour barrier &amp; ST clips | TT_Task | 26/11/2018 | 28/12/2018 | 27/10/2018 | 14/11/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF0620 | red | Turbine Hall GL.1-5 - Insulation &amp; Kalzip | TT_Task | 26/11/2018 | 12/12/2018 | 23/11/2018 | 29/12/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF0630 | red | Turbine Hall GL.1-5 - Remaining works related to dog houses | TT_Task | 02/05/2019 | 22/05/2019 | 11/02/2019 | 14/06/2019 | 0 | TK_Complete | CCGTD1_IPS
DEF_WK08 | red | DW08 - Construct Roof of Turbine Hall(GL.F~G1 /5-7) after equip.installation on platfrom at +12.15 | TT_Task | 01/06/2019 | 29/06/2019 | 04/05/2019 | 09/09/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF1410 | red | Turbine Hall GL5-7 - Cleats, purlins, bridging, bracing, etc | TT_Task | 03/07/2018 | 23/08/2018 | 25/06/2018 | 09/12/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF1420 | red | Turbine Hall GL5-7 /H-G1 (Bay 1b) - Kalbau | TT_Task | 26/11/2018 | 28/11/2018 | 10/11/2018 | 12/12/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF1430 | red | Turbine Hall GL5-7 /F-E (Bay 3b) - Kalbau | TT_Task | 29/11/2018 | 01/12/2018 | 12/11/2018 | 14/11/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF1440 | red | Turbine Hall GL5-7 /E-D (Bay 4b) - Kalbau | TT_Task | 29/11/2018 | 01/12/2018 | 14/11/2018 | 16/11/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF1450 | red | Turbine Hall GL5-7 /D-C (Bay 5b) - Kalbau | TT_Task | 03/12/2018 | 05/12/2018 | 16/11/2018 | 19/11/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF1460 | red | Turbine Hall GL5-7 /C-B (Bay 6b) - Kalbau (DEF_WK07 confirmed not required) | TT_Task | 26/01/2019 | 29/01/2019 | 13/12/2018 | 15/12/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF1470 | red | Turbine Hall GL5-7 /B-A (Bay 7b) - Kalbau | TT_Task | 29/01/2019 | 31/01/2019 | 16/12/2018 | 18/12/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF1480 | blue | Turbine Hall GL5-7 - Weathertight (i.e. Kalbau installed with temporary measures) | TT_FinMile | 31/01/2019 | 31/01/2019 | 18/12/2018 | 18/12/2018 | 0 | TK_Complete | CCGTD1_IPS
THRF5085 | red | West Elevation / GL.7 / Gutter subframe | TT_Task | 01/04/2019 | 05/05/2019 | 22/03/2019 | 04/09/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF5090 | red | West Elevation / GL.7 / Gutter Installation | TT_Task | 10/07/2019 | 27/07/2019 | 15/05/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF5160 | red | Turbine Hall GL.5-7 - Vapour barrier &amp; ST clips | TT_Task | 26/01/2019 | 15/02/2019 | 23/12/2018 | 12/01/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF5170 | red | Turbine Hall GL.5-7 - Insulation &amp; Kalzip | TT_Task | 02/02/2019 | 22/02/2019 | 04/01/2019 | 15/01/2019 | 0 | TK_Complete | CCGTD1_IPS
EV058010 | blue | Air Intake &amp; Bus Duct Installation / M&amp;E access available | TT_FinMile | 26/01/2019 | 26/01/2019 | 19/01/2019 | 19/01/2019 | 0 | TK_Complete | CCGTD1_IPS
EV058020 | red | Air Intake &amp; Bus Duct Installation / Construction period | TT_Task | 26/01/2019 | 25/04/2019 | 20/01/2019 | 08/09/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF2400 | red | Turbine Hall GL.7-10 - Cleats, purlins, bridging, etc | TT_Task | 26/01/2019 | 05/03/2019 | 15/11/2018 | 19/01/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF2410 | red | Turbine Hall GL.7-10 (Bay 1c) - embeds and subframe | TT_Task | 01/09/2019 | 07/09/2019 | 05/08/2019 | 11/08/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF2420 | red | Turbine Hall GL.7-10 (Bay 2c) - Embeds and subframe | TT_Task | 07/09/2019 | 13/09/2019 | 11/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF2430 | red | Turbine Hall GL.7-10 (Bay 3c) - Embeds and subframe | TT_Task | 01/01/2020 | 31/01/2020 | 09/09/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF2440 | red | Turbine Hall GL.7-10 (Bay 4c) - Kalbau | TT_Task | 06/03/2019 | 22/03/2019 | 12/01/2019 | 19/01/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF2450 | blue | Turbine Hall GL.7-10 - Weathertight (i.e. Kalbau installed with temporary measures) | TT_FinMile | 26/01/2019 | 26/01/2019 | 19/01/2019 | 19/01/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF2452 | red | Turbine Hall GL.7-10 (Bay 4c) - Deferred Opening | TT_Task | 01/08/2019 | 16/08/2019 | 01/03/2019 | 16/03/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF2454 | red | Turbine Hall GL.7-10 (Bay 4c) - Kalzip | TT_Task | 01/08/2019 | 20/08/2019 | 06/03/2019 | 25/03/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF2470 | red | Turbine Hall GL.7-10 / F-K - Kalbau/ VB/ ST clip/ Insul./ Kalzip | TT_Task | 01/09/2019 | 17/09/2019 | 14/08/2019 | 25/09/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF2480 | red | Turbine Hall GL.7-10 / A-F - Kalbau/ VB/ ST clip/ Insul./ Kalzip | TT_Task | 01/02/2020 | 21/02/2020 | 05/10/2019 | 21/10/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF5110 | red | West Elevation / GL.10, K -E / Gutter subframe | TT_Task | 06/05/2019 | 10/05/2019 | 28/03/2019 | 09/05/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF5120 | red | West Elevation / GL. 10, E -A / Gutter subframe | TT_Task | 08/04/2019 | 12/04/2019 | 28/03/2019 | 09/05/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF5130 | red | West Elevation / GL. 10, K -E / Gutter Installation | TT_Task | 13/09/2019 | 27/09/2019 | 17/06/2019 | 27/07/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF5140 | red | West Elevation / GL. 10, E -A / Gutter Installation | TT_Task | 13/09/2019 | 27/09/2019 | 17/06/2019 | 27/07/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF5010 | red | East Elevation / GL.1, A-E / Gutter subframe | TT_Task | 02/05/2019 | 08/05/2019 | 04/04/2019 | 14/05/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 04/04/2019
THRF5020 | red | East Elevation / GL.1, E -K / Gutter subframe | TT_Task | 09/05/2019 | 15/05/2019 | 04/04/2019 | 14/05/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF5040 | red | East Elevation / GL. 1, A-E / Gutter Installation | TT_Task | 19/06/2019 | 02/07/2019 | 17/05/2019 | 22/06/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF5050 | red | East Elevation / GL. 1, E-K / Gutter Installation | TT_Task | 19/06/2019 | 02/07/2019 | 17/05/2019 | 22/06/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF5060 | red | West Elevation / GL.5, A-E / Gutter subframe | TT_Task | 01/04/2019 | 15/04/2019 | 26/03/2019 | 15/05/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF5070 | red | West Elevation / GL.5, E-K / Gutter subframe | TT_Task | 02/05/2019 | 14/05/2019 | 26/03/2019 | 15/05/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF5100 | red | West Elevation / GL.5, A-E / Gutter Installation | TT_Task | 01/06/2019 | 15/06/2019 | 11/05/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
THRF5105 | red | West Elevation / GL.5, E-K / Gutter Installation | TT_Task | 01/06/2019 | 15/06/2019 | 11/05/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
DEF_WK03 | red | DW03 - Construct Walls of Turbine Hall below +12.0(GL.K /5-7) after erection of Condensate Pipe Rack &amp; associated equip | TT_Task | 01/04/2019 | 01/06/2019 | 07/11/2018 | 14/11/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 01/04/2019
RCWL0010 | red | Perimeter RC Wall / North Elevation - GL.1 -5 | TT_Task | 30/10/2018 | 09/11/2018 | 02/07/2018 | 19/07/2018 | 0 | TK_Complete | CCGTD1_IPS
RCWL0030 | red | Perimeter RC Wall / North Elevation - GL.7 -10 | TT_Task | 21/08/2018 | 24/08/2018 | 12/04/2018 | 12/05/2018 | 0 | TK_Complete | CCGTD1_IPS
RCWL0040 | red | Perimeter RC Wall / East Elevation - GL.A -C | TT_Task | 12/07/2018 | 16/07/2018 | 21/06/2018 | 27/07/2018 | 0 | TK_Complete | CCGTD1_IPS
RCWL0050 | red | Perimeter RC Wall / East Elevation - GL.C -E | TT_Task | 07/07/2018 | 11/07/2018 | 21/06/2018 | 27/07/2018 | 0 | TK_Complete | CCGTD1_IPS
RCWL0060 | red | Perimeter RC Wall / East Elevation - GL.E -G | TT_Task | 30/06/2018 | 05/07/2018 | 02/06/2018 | 16/06/2018 | 0 | TK_Complete | CCGTD1_IPS
RCWL0070 | red | Perimeter RC Wall / East Elevation - GL.G -K | TT_Task | 26/06/2018 | 29/06/2018 | 02/06/2018 | 16/06/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 16/06/2018
RCWL0080 | red | Perimeter RC Wall / South Elevation - GL.10 -7 | TT_Task | 26/11/2018 | 30/11/2018 | 19/10/2018 | 28/10/2018 | 0 | TK_Complete | CCGTD1_IPS
RCWL0090 | red | Perimeter RC Wall / South Elevation - GL.7 -5 [Deferred Works] | TT_Task | 26/11/2018 | 26/11/2018 | 19/10/2018 | 28/10/2018 | 0 | TK_Complete | CCGTD1_IPS
RCWL0100 | red | Perimeter RC Wall / South Elevation - GL.5 -2 | TT_Task | 27/08/2018 | 31/08/2018 | 11/07/2018 | 25/07/2018 | 0 | TK_Complete | CCGTD1_IPS
RCWL0110 | red | Perimeter RC Wall / West Elevation - GL.K -G | TT_Task | 06/08/2018 | 09/08/2018 | 12/04/2018 | 12/05/2018 | 0 | TK_Complete | CCGTD1_IPS
RCWL0120 | red | Perimeter RC Wall / West Elevation - GL.G -E | TT_Task | 26/11/2018 | 29/11/2018 | 20/10/2018 | 24/11/2018 | 0 | TK_Complete | CCGTD1_IPS
RCWL0130 | red | Perimeter RC Wall / West Elevation - GL.E -C | TT_Task | 30/11/2018 | 04/12/2018 | 20/10/2018 | 04/11/2018 | 0 | TK_Complete | CCGTD1_IPS
RCWL0140 | red | Perimeter RC Wall / West Elevation - GL.C -A | TT_Task | 26/11/2018 | 29/11/2018 | 19/10/2018 | 28/10/2018 | 0 | TK_Complete | CCGTD1_IPS
DEF_WK05 | red | DW05 - Construct Int.Structural Steel Members of Turbine Hall below +23.9 (GL.A-C/11) | TT_Task | 01/08/2019 | 30/08/2019 | 18/04/2019 | 16/05/2019 | 0 | TK_Complete | CCGTD1_IPS
DEF_WK11 | red | DW11 - Capping of all cladding openings required by / following the installation of all items of plant and equip (TBC) | TT_Task | 01/06/2019 | 15/08/2019 | 13/05/2019 | 24/01/2020 | 0 | TK_Complete | CCGTD1_IPS
LIFT1020 | red | Lift No.1 - Glazing panel to lift shaft | TT_Task | 02/05/2019 | 29/05/2019 | 27/03/2019 | 15/05/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 18/02/2019
MCGZ0010 | red | North Elevation GL.1-5 / Cleats, purlins, bridging, bracing, etc | TT_Task | 26/11/2018 | 08/12/2018 | 27/09/2018 | 15/01/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ0020 | red | North Elevation GL.1-5 / Kalbau | TT_Task | 23/02/2019 | 09/03/2019 | 25/12/2018 | 19/01/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ0030 | red | North Elevation GL.1-5 / Vapour barrier &amp; ST clips | TT_Task | 01/02/2019 | 28/02/2019 | 14/01/2019 | 24/01/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ0040 | red | East Elevation at GL.1 / Mullion &amp; transom | TT_Task | 26/01/2019 | 09/03/2019 | 13/12/2018 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 07/12/2018
MCGZ0050 | red | East Elevation at GL.1 / Glazing panels | TT_Task | 11/03/2019 | 02/05/2019 | 24/01/2019 | 03/03/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 18/01/2019
MCGZ0070 | red | East Elevation at GL.1 / Subframe for aluminum features | TT_Task | 04/04/2019 | 24/04/2019 | 11/02/2019 | 31/05/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ0080 | red | South Elevation GL.1-5 / Cleats, purlins, bridging, bracing, etc | TT_Task | 26/11/2018 | 23/02/2019 | 03/10/2018 | 16/01/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ0090 | red | South Elevation GL.1-5 / Kalbau | TT_Task | 25/02/2019 | 23/03/2019 | 20/11/2018 | 31/01/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ0100 | red | South Elevation GL.1-5 / Vapour barrier &amp; ST clips | TT_Task | 31/01/2019 | 27/02/2019 | 02/01/2019 | 28/02/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ0105 | red | South Elevation GL.1-5 / Insulation &amp; Kalzip | TT_Task | 15/04/2019 | 02/05/2019 | 13/02/2019 | 28/02/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ0110 | red | West Elevation at GL.5 / Mullion &amp; transom | TT_Task | 26/01/2019 | 12/02/2019 | 07/01/2019 | 22/02/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ0120 | red | West Elevation at GL.5 / Glazing panels | TT_Task | 27/04/2019 | 02/05/2019 | 20/02/2019 | 28/02/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ0140 | red | West Elevation at GL.5 / Subframe for aluminum features | TT_Task | 02/05/2019 | 20/05/2019 | 01/04/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ0150 | red | West Elevation at GL.5 / Aluminum featured claddings | TT_Task | 16/08/2019 | 28/08/2019 | 03/07/2019 | 15/08/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1010 | red | North Elevation GL.1-5 / Insulation &amp; Kalzip | TT_Task | 02/02/2019 | 01/03/2019 | 21/01/2019 | 29/01/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1015 | red | North Elevation GL.5-10 / Cleats, purlins, bridging, bracing, etc | TT_Task | 26/01/2019 | 04/03/2019 | 23/11/2018 | 24/12/2018 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1030 | red | North Elevation GL.5-10 / Kalbau | TT_Task | 22/02/2019 | 04/03/2019 | 17/12/2018 | 19/01/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1040 | red | East Elevation at GL.1 / Aluminum featured claddings | TT_Task | 01/08/2019 | 19/08/2019 | 25/06/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1050 | red | East Elevation at GL.1 / Cleats, purlins, bridging, bracing, etc | TT_Task | 26/11/2018 | 12/01/2019 | 31/08/2018 | 20/10/2018 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1060 | red | East Elevation at GL.1 / Subframe for wall claddings | TT_Task | 26/01/2019 | 01/02/2019 | 30/11/2018 | 05/12/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 29/11/2018
MCGZ1070 | red | Eest Elevation at GL.1 / Remaining cleats, purlins, bracing, etc. | TT_Task | 02/02/2019 | 22/02/2019 | 03/12/2018 | 09/12/2018 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1080 | red | South Elevation GL.5-10 / Cleats, purlins, bridging, bracing, etc | TT_Task | 26/01/2019 | 15/03/2019 | 28/11/2018 | 13/03/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1090 | red | South Elevation GL.5-10 / Kalbau | TT_Task | 02/03/2019 | 15/03/2019 | 07/01/2019 | 14/03/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1100 | red | South Elevation GL.5-10 / Vapour barrier &amp; ST clips | TT_Task | 04/05/2019 | 25/05/2019 | 08/03/2019 | 31/03/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1105 | red | South Elevation GL.5-10 / Insulation &amp; Kalzip | TT_Task | 20/05/2019 | 01/06/2019 | 15/03/2019 | 29/03/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1110 | red | West Elevation at GL.7 / Mullion &amp; transom | TT_Task | 01/04/2019 | 04/05/2019 | 15/02/2019 | 20/03/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 10/12/2018
MCGZ1120 | red | West Elevation at GL.7 / Glazing panels | TT_Task | 29/04/2019 | 11/05/2019 | 12/03/2019 | 30/03/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1122 | blue | West Elevation at GL.7 / Access to Air Intake [EVENT063] | TT_FinMile | 01/08/2019 | 01/08/2019 | 19/07/2019 | 19/07/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1124 | red | West Elevation at GL.7 / Erect PERI bridge over scaffold [EVENT063] | TT_Task | 01/08/2019 | 15/08/2019 | 20/07/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1126 | red | West Elevation at GL.7 / Complete remaining glazing [EVENT063] | TT_Task | 05/09/2019 | 28/09/2019 | 05/08/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1140 | red | West Elevation at GL.7 / Subframe for aluminum features | TT_Task | 02/05/2019 | 13/05/2019 | 01/04/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1150 | red | West Elevation at GL.7 / Aluminum featured claddings | TT_Task | 23/08/2019 | 02/09/2019 | 15/07/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1160 | red | West Elevation at GL.7 / Cleats, purlins, bridging, bracing, etc | TT_Task | 26/01/2019 | 27/04/2019 | 29/11/2018 | 28/03/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 10/12/2018
MCGZ1170 | red | West Elevation at GL.7 / Kalbau | TT_Task | 25/04/2019 | 10/05/2019 | 21/03/2019 | 31/03/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1172 | black | West Elevation at GL.7 / Vent pipe support frame handed over to KSS [EVENT / ROI] | TT_Mile | 02/01/2020 | 02/01/2020 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 05/09/2019
MCGZ1174 | red | West Elevation at GL.7 / KSS mounting vent pipe onto support frame [EVENT] | TT_Task | 02/01/2020 | 14/01/2020 | 05/09/2019 | 27/09/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1176 | red | West Elevation at GL.7 / KSS place vent pipe and support frame in position, bolt fixing by LCAL [EVENT / ROI] | TT_Task | 15/01/2020 | 15/01/2020 | 28/09/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1180 | red | West Elevation at GL.7 / Vapour barrier &amp; ST clips | TT_Task | 02/05/2019 | 24/05/2019 | 01/04/2019 | 03/10/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ1190 | red | West Elevation at GL.7 / Insulation &amp; Kalzip | TT_Task | 18/05/2019 | 31/05/2019 | 29/04/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2010 | red | North Elevation GL.5-10 / Vapour barrier &amp; ST clips | TT_Task | 31/12/2018 | 14/01/2019 | 31/12/2018 | 28/03/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2020 | red | North Elevation GL.5-10 / Insulation &amp; Kalzip | TT_Task | 02/02/2019 | 22/02/2019 | 08/01/2019 | 01/04/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2040 | red | East Elevation at GL.1 / Kalbau | TT_Task | 26/11/2018 | 29/12/2018 | 09/11/2018 | 09/12/2018 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2050 | red | East Elevation at GL.1 / Vapour barrier &amp; ST clips | TT_Task | 01/04/2019 | 25/04/2019 | 28/03/2019 | 20/04/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2060 | red | East Elevation at GL.1 / Insulation &amp; Kalzip | TT_Task | 07/05/2019 | 28/05/2019 | 20/04/2019 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2070 | red | East Elevation at GL.1 / Louvres (incl' those at the Loft) | TT_Task | 12/04/2019 | 16/05/2019 | 16/01/2019 | 01/03/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2078 | blue | South Elevation GL.7-10 / KSS handover the area [EVENT] | TT_FinMile | 01/01/2020 | 01/01/2020 | 15/09/2019 | 15/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 15/09/2019
MCGZ2090 | red | North Elevation GL.1-10 / Aluminum features claddings | TT_Task | 02/09/2019 | 18/10/2019 | 16/08/2019 | 16/11/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2100 | red | South Elevation GL.1-10 / Aluminum features claddings | TT_Task | 02/01/2020 | 03/02/2020 | 24/09/2019 | 21/10/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2110 | red | West Elevation at GL.10 / Mullion &amp; transom | TT_Task | 01/04/2019 | 08/04/2019 | 18/03/2019 | 25/03/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2120 | red | West Elevation at GL.10 / Glazing panels | TT_Task | 09/04/2019 | 15/04/2019 | 25/03/2019 | 30/03/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2140 | red | West Elevation at GL.10 / Subframe for aluminum features | TT_Task | 02/05/2019 | 18/05/2019 | 25/03/2019 | 15/08/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2150 | red | West Elevation at GL.10 / Aluminum featured claddings | TT_Task | 16/08/2019 | 29/08/2019 | 18/07/2019 | 22/08/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2160 | red | West Elevation at GL.10 / Cleats, purlins, bridging, bracing, etc | TT_Task | 01/06/2019 | 15/06/2019 | 02/05/2019 | 18/07/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2170 | red | West Elevation at GL.10 / Aluminum wall cladding | TT_Task | 22/08/2019 | 03/09/2019 | 23/05/2019 | 31/10/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2180 | red | West Elevation at GL.10 / Louvres to 1st floor rooms | TT_Task | 02/05/2019 | 14/05/2019 | 27/04/2019 | 13/06/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 19/02/2019
MCGZ2190 | red | West Elevation at GL.10 / Louvres to ground floor rooms | TT_Task | 15/05/2019 | 24/05/2019 | 27/04/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2200 | red | North Elevation GL.1-10 / Louvres | TT_Task | 02/05/2019 | 13/07/2019 | 04/04/2019 | 25/09/2019 | 0 | TK_Complete | CCGTD1_IPS
MCGZ2210 | red | South Elevation GL.1-10 / Louvres | TT_Task | 01/04/2019 | 15/06/2019 | 11/03/2019 | 20/04/2019 | 0 | TK_Complete | CCGTD1_IPS
PLAT0060 | red | Crane Walkway, Steel Platforms and Staircases | TT_Task | 26/01/2019 | 22/02/2019 | 13/08/2018 | 19/03/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 02/01/2019
PLAT0070 | red | GMS grating at Loft Level at +37.8 | TT_Task | 01/08/2019 | 29/09/2019 | 20/06/2019 | 11/09/2019 | 0 | TK_Complete | CCGTD1_IPS
BDWK0010 | red | Lube Oil Module - Construct 1m high bund wall | TT_Task | 16/10/2018 | 26/10/2018 | 15/08/2018 | 24/08/2018 | 0 | TK_Complete | CCGTD1_IPS
BDWK0015 | red | Switchgear Block - Construct internal concrete wall G/F | TT_Task | 27/10/2018 | 16/11/2018 | 10/05/2018 | 08/01/2019 | 0 | TK_Complete | CCGTD1_IPS
BDWK0020 | red | Switchgear Block - Construct internal concrete wall 1/F | TT_Task | 26/01/2019 | 22/02/2019 | 24/10/2018 | 12/01/2019 | 0 | TK_Complete | CCGTD1_IPS
BDWK0030 | red | Turbine Building (GL001) - ABWF works | TT_Task | 26/01/2019 | 22/02/2019 | 01/09/2018 | 27/02/2020 | 0 | TK_Complete | CCGTD1_IPS
BDWK0040 | red | Condensate Polishing Plant (GL002) - ABWF works | TT_Task | 23/02/2019 | 01/03/2019 | 07/12/2018 | 27/02/2020 | 0 | TK_Complete | CCGTD1_IPS
BDWK0050 | red | Switchgear Block G/F - ABWF works | TT_Task | 26/01/2019 | 01/03/2019 | 04/10/2018 | 30/03/2019 | 0 | TK_Complete | CCGTD1_IPS
BDWK0060 | red | Switchgear Block 1/F - ABWF works | TT_Task | 26/01/2019 | 01/03/2019 | 28/11/2018 | 30/03/2019 | 0 | TK_Complete | CCGTD1_IPS
BDWK0070 | red | Raised floor to Electronic Equipment and Control Room | TT_Task | 02/05/2019 | 17/05/2019 | 08/04/2019 | 11/05/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 04/04/2019
BDWK0080XX | red | Suespended ceiling to Control Room and ELV Room [descoped; TBC] | TT_Task | 02/05/2019 | 17/05/2019 | 08/04/2019 | 11/05/2019 | 0 | TK_Complete | CCGTD1_IPS
BDWK0100 | red | Doors, louvre, roller shutters, handrails, etc | TT_Task | 01/04/2019 | 13/08/2019 | 18/03/2019 | 27/02/2020 | 0 | TK_Complete | CCGTD1_IPS
BDWK0110 | red | Finishes to perimeter concrete walls (i.e. tiling) | TT_Task | 02/01/2020 | 25/02/2020 | 06/11/2019 | 24/12/2019 | 0 | TK_Complete | CCGTD1_IPS
OHCN0005 | red | Overhead Crane - Unpack and Checking | TT_Task | 01/05/2018 | 14/05/2018 | 08/01/2018 | 19/01/2018 | 0 | TK_Complete | CCGTD1_IPS
OHCN0006 | red | Overhead Crane - Pre-assembly at Green Lawn | TT_Task | 23/04/2018 | 23/05/2018 | 02/03/2018 | 29/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 02/03/2018
OHCN0006a | black | Overhead Crane / Event - Crane rail hold down bolt on site (supplied nby Siemens) | TT_Mile | 26/05/2018 | 26/05/2018 | 26/05/2018 | 26/05/2018 | 0 | TK_Complete | CCGTD1_IPS
OHCN0006b | red | Overhead Crane / Event - Bolt inspection and handover | TT_Task | 26/06/2018 | 29/06/2018 | 26/05/2018 | 29/05/2018 | 0 | TK_Complete | CCGTD1_IPS
OHCN0006c | red | Overhead Crane / Event - Rail installation / Weld on ground | TT_Task | 26/06/2018 | 10/07/2018 | 30/05/2018 | 13/06/2018 | 0 | TK_Complete | CCGTD1_IPS
OHCN0006d | red | Overhead Crane / Event - Rail installation / Lift-up | TT_Task | 26/06/2018 | 29/06/2018 | 14/06/2018 | 17/06/2018 | 0 | TK_Complete | CCGTD1_IPS
OHCN0006e | red | Overhead Crane / Event - Rail installation / Re-delivery of bolts | TT_Task | 26/06/2018 | 04/07/2018 | 18/06/2018 | 26/06/2018 | 0 | TK_Complete | CCGTD1_IPS
OHCN0006f | red | Overhead Crane / Event - Rail installation / Clip down | TT_Task | 26/07/2018 | 05/08/2018 | 27/06/2018 | 13/07/2018 | 0 | TK_Complete | CCGTD1_IPS
OHCN0007 | red | Overhead Crane - Lift up and sit on position 1 of 2 | TT_Task | 06/08/2018 | 08/08/2018 | 14/07/2018 | 16/07/2018 | 0 | TK_Complete | CCGTD1_IPS
OHCN0008 | red | Overhead Crane - Lift up and sit on position 2 of 2 | TT_Task | 08/08/2018 | 10/08/2018 | 17/07/2018 | 19/07/2018 | 0 | TK_Complete | CCGTD1_IPS
OHCN0010 | red | Overhead Crane - E&amp;M Fit-out and T&amp;C | TT_Task | 26/07/2018 | 04/09/2018 | 20/07/2018 | 31/08/2018 | 0 | TK_Complete | CCGTD1_IPS
THEL0012 | red | Turbine Hall Area - Lightning Pit and Earth Pit | TT_Task | 02/01/2020 | 20/01/2020 | 22/07/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS
THEL0020 | red | Turbine Hall Area (GL.1-5) - Cable containment (Elect) | TT_Task | 06/06/2019 | 08/07/2019 | 18/03/2019 | 07/11/2019 | 0 | TK_Complete | CCGTD1_IPS
THEL0030 | red | Turbine Hall Area (GL.5-7) - Cable containment (Elect) | TT_Task | 22/06/2019 | 15/07/2019 | 22/04/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
THEL0040 | red | Turbine Hall Area (GL.8-10) - Cable containment (Elect) | TT_Task | 04/07/2019 | 22/07/2019 | 27/05/2019 | 31/10/2019 | 0 | TK_Complete | CCGTD1_IPS
THEL0050 | red | Turbine Hall Area (High/ Roof Level) - Cable containmen (Elect) | TT_Task | 09/10/2018 | 15/10/2018 | 28/05/2018 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS
THEL0055 | red | Turbine Hall Area (incl' Switchgear Block) - Major Electrical Equipment on site | TT_Task | 01/06/2019 | 30/06/2019 | 01/04/2019 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 01/04/2019
THEL0060 | red | Switchgear Block - Installation of LV Switchboard, Transformers, UPS, DBs, etc | TT_Task | 02/07/2019 | 27/08/2019 | 12/11/2018 | 31/05/2019 | 0 | TK_Complete | CCGTD1_IPS
THEL1020 | red | Turbine Hall Area (GL.1-5) - Light fitting, power point, earting point incl. final termination | TT_Task | 02/01/2020 | 22/02/2020 | 08/11/2019 | 07/02/2020 | 0 | TK_Complete | CCGTD1_IPS
THEL1030 | red | Turbine Hall Area (GL.5-7) - Light fitting, power point, earthing point incl. final termination | TT_Task | 02/01/2020 | 22/02/2020 | 06/12/2019 | 07/02/2020 | 0 | TK_Complete | CCGTD1_IPS
THEL1040 | red | Turbine Hall Area (GL.8-10) - Light fitting, power point, earthing point incl. final termination | TT_Task | 21/01/2020 | 12/03/2020 | 01/11/2019 | 07/02/2020 | 0 | TK_Complete | CCGTD1_IPS
THEL1050 | red | Turbine Hall Area / Roof Level - Installation of Photovoltaic Power System | TT_Task | 02/01/2020 | 04/03/2020 | 12/10/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
THAC0010 | black | Turbine Hall Area (incl' Switchgear Block) - Major ACMV Equipment on site | TT_Mile | 01/04/2019 | 01/04/2019 | 01/02/2019 | 01/02/2019 | 0 | TK_Complete | CCGTD1_IPS
THAC0015 | red | Turbine Hall Area / GL.1-5 - Ductwork and fan installation (ACMV) | TT_Task | 01/06/2019 | 26/06/2019 | 02/05/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS
THAC0020 | red | Turbine Hall Area / GL.5-7 - Ductwork and fan installation (ACMV) | TT_Task | 02/09/2019 | 07/11/2019 | 26/08/2019 | 06/12/2019 | 0 | TK_Complete | CCGTD1_IPS
THAC0050 | red | Switchgear Block - Installation of Indoor Unit (VEUs) | TT_Task | 01/04/2019 | 26/04/2019 | 04/02/2019 | 30/03/2019 | 0 | TK_Complete | CCGTD1_IPS
THAC0060 | red | Switchgear Block (Turbine Hall Roof Level GL.7-10) - Installation of Outdoor Unit (VCUs) | TT_Task | 02/09/2019 | 15/10/2019 | 19/08/2019 | 15/11/2019 | 0 | TK_Complete | CCGTD1_IPS
THAC0070 | red | Turbine Hall Area / Loft Level - Installation of Roof Extraction Fan | TT_Task | 02/09/2019 | 28/10/2019 | 15/08/2019 | 01/11/2019 | 0 | TK_Complete | CCGTD1_IPS
THAC0080 | red | Turbine Hall Area - Final ductwork and air grille / diffuser | TT_Task | 02/01/2020 | 19/02/2020 | 26/10/2019 | 06/12/2019 | 0 | TK_Complete | CCGTD1_IPS
THFS0110 | red | Turbine Hall - Installation of fire alarm panels | TT_Task | 02/01/2020 | 15/01/2020 | 01/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
THFS0120 | red | Turbine Hall - Installation of detectors incl' wiring and termination | TT_Task | 02/01/2020 | 15/01/2020 | 01/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
THFS0122 | red | Turbine Hall - Lift No.1 detector installation | TT_Task | 02/01/2020 | 15/01/2020 | 01/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
THFS0124 | red | Turbine Hall - Loft Platform detector installation | TT_Task | 02/01/2020 | 15/01/2020 | 01/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
THFS0130 | red | Turbine Hall - Installation of portable fire fighting equipment | TT_Task | 08/01/2020 | 09/01/2020 | 09/03/2020 | 10/03/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 07/01/2020
THFS0140 | red | Turbine Hall - Testing and Commisisoning to FS installation | TT_Task | 16/01/2020 | 22/01/2020 | 15/11/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
LIFT1030 | red | Lift No.1 - Lift Installation incl' T&amp;C | TT_Task | 01/11/2019 | 01/01/2020 | 23/09/2019 | 31/12/2019 | 0 | TK_Complete | CCGTD1_IPS
LIFT1040 | red | Lift No.1 - Submit Form LE5 and EMSD Inspection | TT_Task | 02/01/2020 | 21/01/2020 | 19/02/2020 | 04/03/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 02/01/2020
LIFT1050 | red | Lift No.1 - Obtain Use Permit | TT_Task | 22/01/2020 | 30/01/2020 | 05/03/2020 | 12/03/2020 | 0 | TK_Complete | CCGTD1_IPS
STCK0010 | red | Exhaust Stack - Further excavation from +4.2 mPD to the required formation level | TT_Task | 16/11/2017 | 17/11/2017 | 16/11/2017 | 17/11/2017 | 0 | TK_Complete | CCGTD1_IPS
STCK0015 | red | Exhaust Stack - Cast blinding concrete | TT_Task | 10/01/2018 | 13/01/2018 | 13/12/2017 | 14/12/2017 | 0 | TK_Complete | CCGTD1_IPS
STCK0020 | red | Exhaust Stack - Trim pile and prepare pile head | TT_Task | 29/09/2017 | 12/10/2017 | 26/09/2017 | 19/11/2017 | 0 | TK_Complete | CCGTD1_IPS
STCK0030 | red | Exhaust Stack - Capping plate and rebar starter | TT_Task | 21/11/2017 | 29/11/2017 | 21/11/2017 | 08/12/2017 | 0 | TK_Complete | CCGTD1_IPS
STCK0040 | red | Exhaust Stack - Erect side formwork | TT_Task | 06/01/2018 | 12/01/2018 | 21/12/2017 | 06/01/2018 | 0 | TK_Complete | CCGTD1_IPS
STCK0050 | red | Exhaust Stack - Fix rebar and install cast-in /embed items | TT_Task | 15/01/2018 | 27/01/2018 | 21/12/2017 | 10/01/2018 | 0 | TK_Complete | CCGTD1_IPS
STCK0060 | red | Exhaust Stack - Pour pile cap (incl' Lift Pit No.2) | TT_Task | 12/03/2018 | 12/03/2018 | 12/01/2018 | 12/01/2018 | 0 | TK_Complete | CCGTD1_IPS
STCK0070 | red | Exhaust Stack - Strike formwork | TT_Task | 13/03/2018 | 13/03/2018 | 13/01/2018 | 13/01/2018 | 0 | TK_Complete | CCGTD1_IPS
HRSG0015 | red | HRSG - Cast vertical blinding to the profile of caps and beams | TT_Task | 28/12/2017 | 02/01/2018 | 02/12/2017 | 08/12/2017 | 0 | TK_Complete | CCGTD1_IPS
HRSG0020 | red | HRSG - Trim pile and prepare pile head | TT_Task | 24/11/2017 | 12/12/2017 | 26/09/2017 | 19/11/2017 | 0 | TK_Complete | CCGTD1_IPS
HRSG0030 | red | HRSG - Capping plate and rebar starter | TT_Task | 25/11/2017 | 13/12/2017 | 29/09/2017 | 30/11/2017 | 0 | TK_Complete | CCGTD1_IPS
HRSG0050 | red | HRSG - Fix rebar and install cast-in /embed items (Part 1 of 2) | TT_Task | 03/01/2018 | 12/01/2018 | 02/12/2017 | 13/01/2018 | 0 | TK_Complete | CCGTD1_IPS
HRSG0060 | red | HRSG - Pour pile cap (Part 1 of 2) | TT_Task | 13/03/2018 | 13/03/2018 | 15/01/2018 | 15/01/2018 | 0 | TK_Complete | CCGTD1_IPS
HRSG0070 | red | HRSG - Fix rebar and install cast-in /embed items (Part 2 of 2) | TT_Task | 13/03/2018 | 14/03/2018 | 24/01/2018 | 30/01/2018 | 0 | TK_Complete | CCGTD1_IPS
HRSG0080 | red | HRSG - Pour pile cap (Part 2 of 2) | TT_Task | 15/03/2018 | 15/03/2018 | 31/01/2018 | 31/01/2018 | 0 | TK_Complete | CCGTD1_IPS
PR010010 | red | Pipe Rack 01 - Foundation and Plinths | TT_Task | 09/04/2019 | 07/05/2019 | 23/02/2019 | 07/03/2019 | 0 | TK_Complete | CCGTD1_IPS
DEF_WK06 | red | DW06 - Construct Metal Fence and Removal Shelter at Transformer Area | TT_Task | 10/01/2020 | 10/03/2020 | 15/10/2019 | 20/12/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 15/02/2019
EV039110 | red | Event 039(TX) - Power Island Phase 4 /5 resequencing amendment | TT_Task | 26/11/2018 | 25/12/2018 | 15/10/2018 | 12/11/2018 | 0 | TK_Complete | CCGTD1_IPS
EV039120 | red | Event 039(TX) - BA8 consent for Phase 5 excavation [APPROVAL DEEMED] | TT_Task | 26/01/2019 | 22/02/2019 | 11/12/2018 | 07/01/2019 | 0 | TK_Complete | CCGTD1_IPS
EV039210 | red | Event 039(TX) - MV Aux.TX / open cut to the required formation level w/ a berm 5m wide at Zone A north PPW | TT_Task | 26/01/2019 | 30/01/2019 | 30/11/2018 | 02/12/2018 | 0 | TK_Complete | CCGTD1_IPS
EV039220 | red | Event 039(TX) - MV Aux.TX / conduct plate load test PL4 | TT_Task | 31/01/2019 | 15/02/2019 | 03/12/2018 | 13/12/2018 | 0 | TK_Complete | CCGTD1_IPS
EV039230 | red | Event 039(TX) - MV Aux.TX / construct foundation CT11-FT1 (Part 1 of 2) | TT_Task | 16/02/2019 | 26/02/2019 | 14/12/2018 | 12/01/2019 | 0 | TK_Complete | CCGTD1_IPS
EV039240 | red | Event 039(TX) - MV Aux.TX / construct pit wall to +6.15 and plinth PL3 | TT_Task | 27/02/2019 | 08/03/2019 | 13/01/2019 | 24/01/2019 | 0 | TK_Complete | CCGTD1_IPS
EV039250 | red | Event 039(TX) - MV Aux.TX / construct fire wall to +11.55 and corbels at G.L.AA | TT_Task | 31/01/2019 | 20/02/2019 | 25/01/2019 | 04/02/2019 | 0 | TK_Complete | CCGTD1_IPS
EV039260 | red | Event 039(TX) - MV Aux.TX / apply hardener | TT_Task | 01/04/2019 | 02/04/2019 | 16/02/2019 | 18/02/2019 | 0 | TK_Complete | CCGTD1_IPS
EV039270 | black | Event 039(TX) - MV Aux.TX / access for M&amp;E | TT_Mile | 03/04/2019 | 03/04/2019 | 19/02/2019 | 19/02/2019 | 0 | TK_Complete | CCGTD1_IPS
EV039310 | red | Event 039(TX) - Start-up TX / backfill to the required formation | TT_Task | 31/01/2019 | 04/02/2019 | 02/01/2019 | 07/01/2019 | 0 | TK_Complete | CCGTD1_IPS
EV039320 | red | Event 039(TX) - Start-up TX / construct foundation CT12-FT1 | TT_Task | 26/01/2019 | 12/02/2019 | 12/01/2019 | 22/01/2019 | 0 | TK_Complete | CCGTD1_IPS
EV039330 | red | Event 039(TX) - Start-up TX / construct plinth PL1 &amp; PL2 | TT_Task | 13/02/2019 | 22/02/2019 | 24/01/2019 | 30/01/2019 | 0 | TK_Complete | CCGTD1_IPS
EV039340 | red | Event 039(TX) - Start-up TX / apply hardener | TT_Task | 01/04/2019 | 02/04/2019 | 12/02/2019 | 13/02/2019 | 0 | TK_Complete | CCGTD1_IPS
EV039350 | black | Event 039(TX) - Start-up TX / access for M&amp;E | TT_Mile | 03/04/2019 | 03/04/2019 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS
GNTX0010 | red | Generator TX - Further excavate from +4.2 to the required formation level | TT_Task | 04/02/2019 | 12/02/2019 | 07/01/2019 | 07/01/2019 | 0 | TK_Complete | CCGTD1_IPS
GNTX0020 | red | Generator TX - Cast vertical blinding | TT_Task | 04/02/2019 | 14/02/2019 | 05/01/2019 | 07/01/2019 | 0 | TK_Complete | CCGTD1_IPS
GNTX0030 | red | Generator TX - Construct base slabs | TT_Task | 15/02/2019 | 28/02/2019 | 08/01/2019 | 12/01/2019 | 0 | TK_Complete | CCGTD1_IPS
GNTX0040 | red | Generator TX - Construct equipment plinths | TT_Task | 04/02/2019 | 13/02/2019 | 13/01/2019 | 25/01/2019 | 0 | TK_Complete | CCGTD1_IPS
GNTX0050 | red | Generator TX - Construct concrete blast walls | TT_Task | 04/02/2019 | 20/02/2019 | 22/01/2019 | 12/02/2019 | 0 | TK_Complete | CCGTD1_IPS
M&amp;E_WK08 | red | M&amp;E Works by Others #8 - Erect Transformers and dress out (indicative only) | TT_Task | 02/05/2019 | 31/08/2019 | 11/03/2019 | 14/10/2019 | 0 | TK_Complete | CCGTD1_IPS
DBSG0010 | red | Duct Bank between Switchgear Blk &amp; Gen.TX - Construct drawpit BS01, BS03, BS04, BS05 | TT_Task | 08/03/2019 | 14/03/2019 | 12/10/2018 | 25/01/2019 | 0 | TK_Complete | CCGTD1_IPS
DBSG0020 | red | Duct Bank between Switchgear Blk &amp; Gen.TX - Install cable ducting with concrete surround | TT_Task | 15/03/2019 | 28/03/2019 | 06/11/2018 | 12/02/2019 | 0 | TK_Complete | CCGTD1_IPS
BBDP0010 | red | Boiler Blow Down Pit - Further excavate from +4.2 to the final formation level | TT_Task | 26/06/2018 | 28/06/2018 | 28/05/2018 | 02/06/2018 | 0 | TK_Complete | CCGTD1_IPS
BBDP0070 | red | Boiler Blow Down Pit - Cast vertical blinding to the profile of base slab and shallow ppit | TT_Task | 02/08/2018 | 06/08/2018 | 04/07/2018 | 14/07/2018 | 0 | TK_Complete | CCGTD1_IPS
BBDP0075 | red | Boiler Blow Down Pit - Install waterproofing | TT_Task | 26/07/2018 | 27/07/2018 | 12/07/2018 | 14/07/2018 | 0 | TK_Complete | CCGTD1_IPS
BBDP0080 | red | Boiler Blow Down Pit - Fix bottom layer rebar | TT_Task | 28/07/2018 | 07/08/2018 | 16/07/2018 | 21/07/2018 | 0 | TK_Complete | CCGTD1_IPS
BBDP0090 | red | Boiler Blow Down Pit - Close formwork (if any) | TT_Task | 03/09/2018 | 03/09/2018 | 09/08/2018 | 09/08/2018 | 0 | TK_Complete | CCGTD1_IPS
BBDP0100 | red | Boiler Blow Down Pit - Pour base slab and shallow pit | TT_Task | 04/09/2018 | 04/09/2018 | 10/08/2018 | 10/08/2018 | 0 | TK_Complete | CCGTD1_IPS
BBDP0110 | red | Boiler Blow Down Pit - Prepare CJ | TT_Task | 06/09/2018 | 06/09/2018 | 11/08/2018 | 11/08/2018 | 0 | TK_Complete | CCGTD1_IPS
BBDP0140 | red | Boiler Blow Down Pit - Erect wall and column formwork | TT_Task | 27/08/2018 | 30/08/2018 | 26/07/2018 | 28/07/2018 | 0 | TK_Complete | CCGTD1_IPS
BBDP0150 | red | Boiler Blow Down Pit - Fix upper layer rebar | TT_Task | 30/08/2018 | 01/09/2018 | 04/08/2018 | 07/08/2018 | 0 | TK_Complete | CCGTD1_IPS
BBDP0160 | red | Boiler Blow Down Pit - Close wall formwork | TT_Task | 31/08/2018 | 03/09/2018 | 06/08/2018 | 09/08/2018 | 0 | TK_Complete | CCGTD1_IPS
BBDP0170 | red | Boiler Blow Down Pit- Pour walls and columns to the underside of Feedwater Platform slab | TT_Task | 04/09/2018 | 04/09/2018 | 10/08/2018 | 10/08/2018 | 0 | TK_Complete | CCGTD1_IPS
BBDP0180 | red | Boiler Blow Down Pit - Curing | TT_Task | 05/09/2018 | 11/09/2018 | 11/08/2018 | 17/08/2018 | 0 | TK_Complete | CCGTD1_IPS
BBDP0190 | red | Boiler Blow Down Pit - Apply waterproofing to the external face of pit wall | TT_Task | 21/08/2018 | 23/08/2018 | 12/07/2018 | 14/07/2018 | 0 | TK_Complete | CCGTD1_IPS
BBDP0200 | red | Boiler Blow Down Pit - Backfill againt basement wall | TT_Task | 26/07/2018 | 27/07/2018 | 30/06/2018 | 03/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV015010 | red | Event 015 - HRSG West occupied by M&amp;E Contract for HRSG Erection | TT_Task | 23/04/2018 | 03/06/2018 | 07/03/2018 | 25/05/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 09/03/2018
EV015020 | red | Event 015 - Remob, excavation, earthing, backfill to formation levels, set-up for plate load test | TT_Task | 26/06/2018 | 10/07/2018 | 26/05/2018 | 09/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV015030 | red | Event 015 - Clarification on plate load test requirements and invitation for BD inspection | TT_Task | 26/06/2018 | 26/06/2018 | 10/06/2018 | 20/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV019010 | red | Event 019 - Plate Load Test Set Up | TT_Task | 28/02/2018 | 06/03/2018 | 09/02/2018 | 13/02/2018 | 0 | TK_Complete | CCGTD1_IPS
EV019030 | red | Event 019 - Plate Load Test ( x2 nos) | TT_Task | 01/08/2018 | 14/08/2018 | 21/06/2018 | 25/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV019040 | red | Event 019 - Photo records for foundation dimension set-out | TT_Task | 26/07/2018 | 29/07/2018 | 26/06/2018 | 29/06/2018 | 0 | TK_Complete | CCGTD1_IPS
EV035010 | red | Event 035 - CLP allocated space for relocation of rebar yard | TT_Task | 26/07/2018 | 26/07/2018 | 16/07/2018 | 25/07/2018 | 0 | TK_Complete | CCGTD1_IPS
EV040001 | black | Event 040 - Balance of Feedwater Platform area handed back by KSS | TT_Mile | 26/11/2018 | 26/11/2018 | 04/09/2018 | 04/09/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 04/09/2018
FWPT0010 | red | FW Platform - Construct base slab GL.K-S (= Pipe Bridge) | TT_Task | 26/07/2018 | 27/09/2018 | 30/06/2018 | 23/08/2018 | 0 | TK_Complete | CCGTD1_IPS
FWPT0020 | red | FW Platform - Construct base slab GL.S-V (= Feedwater Platform) | TT_Task | 31/08/2018 | 11/10/2018 | 30/07/2018 | 08/10/2018 | 0 | TK_Complete | CCGTD1_IPS
FWPT0030 | red | FW Platform - Construct plinths for FW Pump, Con.Recirculation Pump, Sampling Skid, Amonnia &amp; Phosphate Dosing Container | TT_Task | 27/08/2018 | 13/09/2018 | 24/08/2018 | 27/10/2018 | 0 | TK_Complete | CCGTD1_IPS
FWPT0040 | red | FW Platform - Construct of remaining Feedwater Platform foundation and plinth | TT_Task | 26/11/2018 | 15/12/2018 | 15/11/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS
APTX0010 | red | LV Aux. Power TX - Construct 600mm deep foundation | TT_Task | 01/04/2019 | 09/04/2019 | 29/01/2019 | 04/02/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 29/01/2019
EV047010 | red | RW Collection Pump Rm - Stratum Requirement (ROI#182) | TT_Task | 26/11/2018 | 12/12/2018 | 10/10/2018 | 26/10/2018 | 0 | TK_Complete | CCGTD1_IPS
EV048010 | red | RW Collection Pump Rm - Install re-prop below S1 as per Zone A (4th) amendment | TT_Task | 16/02/2019 | 22/02/2019 | 05/12/2018 | 15/12/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0020 | red | RW Collection Pump Rm - Vertical blinding to the profile of base slab and shallow sump pit | TT_Task | 26/11/2018 | 28/11/2018 | 31/10/2018 | 31/10/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0030 | red | RW Collection Pump Rm - Install waterproofing [confirmed not required] | TT_Task | 26/11/2018 | 27/11/2018 | 31/10/2018 | 31/10/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0040 | red | RW Collection Pump Rm - Fix rebar for base slab and shallow pits | TT_Task | 28/11/2018 | 01/12/2018 | 01/11/2018 | 07/11/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0050 | red | RW Collection Pump Rm - Close formwork (if any) | TT_Task | 03/12/2018 | 03/12/2018 | 03/11/2018 | 07/11/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0060 | red | RW Collection Pump Rm - Pour base slab and shallow pit | TT_Task | 04/12/2018 | 04/12/2018 | 08/11/2018 | 08/11/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0070 | red | RW Collection Pump Rm - Prepare CJ | TT_Task | 28/11/2018 | 28/11/2018 | 09/11/2018 | 09/11/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0080 | red | RW Collection Pump Rm - Erect formwork for basement wall and staircase (Part 1 of 2) | TT_Task | 29/11/2018 | 03/12/2018 | 14/11/2018 | 16/11/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0090 | red | RW Collection Pump Rm - Fix rebar for basement wall and staircase (Part 1 of 2) | TT_Task | 01/12/2018 | 05/12/2018 | 16/11/2018 | 22/11/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0100 | red | RW Collection Pump Rm - Close wall formwork (Part 1 of 2) | TT_Task | 26/11/2018 | 26/11/2018 | 23/11/2018 | 28/11/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0110 | red | RW Collection Pump Rm - Pour basement wall and staircase (Part 1 of 2) | TT_Task | 28/01/2019 | 28/01/2019 | 29/11/2018 | 29/11/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0120 | red | RW Collection Pump Rm - Erect formwork for basement wall and staircase (Part 2 of 2) | TT_Task | 15/02/2019 | 19/02/2019 | 16/12/2018 | 23/12/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0130 | red | RW Collection Pump Rm - Fix rebar for basement wall and staircase (Part 2 of 2) | TT_Task | 18/02/2019 | 21/02/2019 | 21/12/2018 | 05/01/2019 | 0 | TK_Complete | CCGTD1_IPS
RWPR0140 | red | RW Collection Pump Rm - Close wall formwork (Part 2 of 2) | TT_Task | 21/02/2019 | 22/02/2019 | 04/01/2019 | 06/01/2019 | 0 | TK_Complete | CCGTD1_IPS
RWPR0150 | red | RW Collection Pump Rm - Pour basement wall and staircase (Part 2 of 2) | TT_Task | 23/02/2019 | 23/02/2019 | 07/01/2019 | 07/01/2019 | 0 | TK_Complete | CCGTD1_IPS
RWPR0160 | red | RW Collection Pump Rm - Curing | TT_Task | 26/01/2019 | 01/02/2019 | 08/01/2019 | 14/01/2019 | 0 | TK_Complete | CCGTD1_IPS
RWPR0170 | red | RW Collection Pump Rm - Apply waterproofing to the external face of basement wall [confirmed not required] | TT_Task | 01/04/2019 | 02/04/2019 | 29/11/2018 | 29/11/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0180 | red | RW Collection Pump Rm - Backfill againt basement wall | TT_Task | 04/02/2019 | 14/02/2019 | 17/12/2018 | 22/12/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0185 | red | RW Collection Pump Rm - Construct Irrigation Tank and Rainwater Collection Tank structure | TT_Task | 01/04/2019 | 27/05/2019 | 09/03/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
RWPR0190 | red | RW Collection Pump Rm - Falsework and formwork to top slab | TT_Task | 16/03/2019 | 18/03/2019 | 16/12/2018 | 23/12/2018 | 0 | TK_Complete | CCGTD1_IPS
RWPR0200 | red | RW Collection Pump Rm - Fix rebar | TT_Task | 19/03/2019 | 21/03/2019 | 21/12/2018 | 05/01/2019 | 0 | TK_Complete | CCGTD1_IPS
RWPR0210 | red | RW Collection Pump Rm - Pour top slab | TT_Task | 22/03/2019 | 22/03/2019 | 07/01/2019 | 07/01/2019 | 0 | TK_Complete | CCGTD1_IPS
RWPR0220 | red | RW Collection Pump Rm - Construct remaining staircase structure abovehground | TT_Task | 16/09/2019 | 14/10/2019 | 19/08/2019 | 24/09/2019 | 0 | TK_Complete | CCGTD1_IPS
RWPR0230 | red | RW Collection Pump Rm - Construct footing for Emergency Power Generator on top slab (relocated to adj. Shaft F) | TT_Task | 01/04/2019 | 18/04/2019 | 18/03/2019 | 02/07/2019 | 0 | TK_Complete | CCGTD1_IPS
RWPR0240 | red | RW Collection Pump Rm - ABWF works to pump room and water tanks | TT_Task | 02/01/2020 | 17/02/2020 | 25/09/2019 | 31/12/2019 | 0 | TK_Complete | CCGTD1_IPS
RWPR0250 | red | RW Collection Pump Rm - Building Services installation | TT_Task | 02/01/2020 | 17/02/2020 | 22/08/2019 | 24/01/2020 | 0 | TK_Complete | CCGTD1_IPS
IRRI0010 | red | Irrigation System - Plant room installation inside RW Collection Pump Rm | TT_Task | 04/02/2020 | 12/03/2020 | 20/10/2019 | 24/01/2020 | 0 | TK_Complete | CCGTD1_IPS
IRRI0015 | red | Irrigation System - Water supply pipeline from the water cabinet | TT_Task | 09/08/2019 | 05/09/2019 | 29/04/2019 | 30/09/2019 | 0 | TK_Complete | CCGTD1_IPS
IRRI0020 | red | Irrigation System - Distribution pipeline installation along the east perimeter of HRSG Area | TT_Task | 02/01/2020 | 15/01/2020 | 19/12/2019 | 17/01/2020 | 0 | TK_Complete | CCGTD1_IPS
IRRI0030 | red | Irrigation System - Distribution pipeline installation along the perimeter of Turbine Hall | TT_Task | 19/02/2020 | 03/03/2020 | 22/07/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS
IRRI0040 | red | Irrigation System - Distribution pipeline installation to the northern side of HRSG Area | TT_Task | 15/01/2020 | 24/01/2020 | 15/01/2020 | 24/01/2020 | 0 | TK_Complete | CCGTD1_IPS
EV041010 | red | Event 041 - Crane access for KSS (original thought was three months) | TT_Task | 26/11/2018 | 23/02/2019 | 07/09/2018 | 15/04/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 07/09/2018
GFFE0010 | red | Gas Final Filter Equip - Construct 1.1m deep foundation | TT_Task | 02/05/2019 | 27/05/2019 | 18/04/2019 | 04/05/2019 | 0 | TK_Complete | CCGTD1_IPS
GFFE0020 | red | Gas Final Filter Equip - Construct 1m high bund wall all around | TT_Task | 05/06/2019 | 20/06/2019 | 06/05/2019 | 02/09/2019 | 0 | TK_Complete | CCGTD1_IPS
GFFE0030 | red | Gas Final Filter Equip - Erect wire mesh security fence after filter install | TT_Task | 02/01/2020 | 15/01/2020 | 12/10/2019 | 18/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCWS0010 | red | Close Cooling Water Structure - Construct foundation and plinths | TT_Task | 09/04/2019 | 29/04/2019 | 25/02/2019 | 04/03/2019 | 0 | TK_Complete | CCGTD1_IPS
EV051010 | blue | Event 051 / Utilities Trench / KSS hand back over the area | TT_FinMile | 26/01/2019 | 26/01/2019 | 04/01/2019 | 04/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 11/12/2018
ODPT0010 | red | Outdoor Pipe Trench - Construct pipe trench | TT_Task | 01/04/2019 | 13/04/2019 | 02/02/2019 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS
EV052010 | blue | Event 052 / Foundation to the South of HRSG / KSS hand back over the area | TT_FinMile | 31/03/2019 | 31/03/2019 | 19/03/2019 | 19/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 14/03/2019
EV053010 | blue | Event 053 / Foundation to the East of HRSG / KSS hand back over the area | TT_FinMile | 31/03/2019 | 31/03/2019 | 19/03/2019 | 19/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 14/03/2019
FTP10005 | red | Construct footings of False Start &amp; GT Water Tank to the South of HRSG | TT_Task | 01/04/2019 | 18/05/2019 | 20/03/2019 | 12/04/2019 | 0 | TK_Complete | CCGTD1_IPS
FTP10010 | red | Construct footings of Urea Decomposition Chamber to the East of HRSG | TT_Task | 01/08/2019 | 26/08/2019 | 03/06/2019 | 29/06/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 03/06/2019
EV050010 | blue | Event 050 / Gas Blending / KSS hand back over the area | TT_FinMile | 26/01/2019 | 26/01/2019 | 04/01/2019 | 04/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 11/12/2018
FTP20005 | red | Fuel Gas Purger Air, GRS &amp; Fuel Gas Blending - Underground drainage | TT_Task | 26/01/2019 | 15/02/2019 | 05/01/2019 | 16/01/2019 | 0 | TK_Complete | CCGTD1_IPS
FTP20010 | red | Fuel Gas Purge Air System - Construct foundation | TT_Task | 16/02/2019 | 01/03/2019 | 17/01/2019 | 29/01/2019 | 0 | TK_Complete | CCGTD1_IPS
FTP20020 | red | Gas Receiving &amp; Fuel Gas Blending Station - Construct foundation | TT_Task | 28/01/2019 | 09/02/2019 | 17/01/2019 | 29/01/2019 | 0 | TK_Complete | CCGTD1_IPS
FTP20030 | red | Gas Receiving &amp; Fuel Gas Blending Station - Construct fire wall | TT_Task | 26/01/2019 | 08/02/2019 | 17/01/2019 | 29/01/2019 | 0 | TK_Complete | CCGTD1_IPS
FTP20040 | red | Gas Receiving &amp; Fuel Gas Blending Station - Erect wire mech fence | TT_Task | 02/01/2020 | 11/01/2020 | 28/10/2019 | 30/10/2019 | 0 | TK_Complete | CCGTD1_IPS
EV049010 | blue | Event 049 / Urea Facilities / KSS hand back over the area | TT_FinMile | 26/01/2019 | 26/01/2019 | 08/12/2018 | 08/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_EARLIER_THAN | 01/12/2018
EV049020 | red | Event 049 / Urea Facilities / Set up and conduct plate load test no. PL1 | TT_Task | 26/01/2019 | 26/01/2019 | 09/12/2018 | 13/12/2018 | 0 | TK_Complete | CCGTD1_IPS
FTP30010 | red | Construct footings for Chemical Unloading Bay and Urea Factilities | TT_Task | 26/01/2019 | 22/02/2019 | 14/12/2018 | 11/01/2019 | 0 | TK_Complete | CCGTD1_IPS
CLPCCR10 | red | Works in Existing Central Control Room in Control Block Building and Associated Works (indicative only, TBC) | TT_Task | 03/02/2020 | 22/02/2020 | 03/02/2020 | 22/02/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 03/02/2020
DEF_WK09 | red | DW09 - Construct UG Neutralization Tank | TT_Task | 26/11/2018 | 31/12/2018 | 15/11/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS
DEF_WK10 | red | DW10 - Final Reinstatement of Access Roads and Pavement at Turbine Hall and HRSG Area (i.e. wearing course) | TT_Task | 23/05/2020 | 28/05/2020 | 23/05/2020 | 28/05/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 17/02/2020
13584 | red | Provide/Extend/Relocate Sitewide Drainage System | TT_Task | 01/04/2019 | 13/08/2019 | 16/07/2018 | 24/01/2020 | 0 | TK_Complete | CCGTD1_IPS
EXCL0020 | red | Roadworks - Concrete Pavements | TT_Task | 01/08/2019 | 20/09/2019 | 22/07/2019 | 09/09/2019 | 0 | TK_Complete | CCGTD1_IPS
EXCL0030 | red | Roadworks - Road Marking and signs | TT_Task | 04/06/2020 | 11/06/2020 | 04/06/2020 | 11/06/2020 | 0 | TK_Complete | CCGTD1_IPS
EXCL0040 | red | Roadworks - Install Directonal Signage | TT_Task | 12/06/2020 | 30/06/2020 | 12/06/2020 | 30/06/2020 | 0 | TK_Complete | CCGTD1_IPS
EXCL0050 | red | Roadworks - Install Street Furniture | TT_Task | 12/06/2020 | 30/06/2020 | 12/06/2020 | 30/06/2020 | 0 | TK_Complete | CCGTD1_IPS
LAND0010 | red | Irrigation Points | TT_Task | 01/02/2020 | 14/02/2020 | 01/02/2020 | 14/02/2020 | 0 | TK_Complete | CCGTD1_IPS
LAND0020XX | red | Grasscrete Around Building | TT_Task | 02/01/2020 | 12/02/2020 | 22/07/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS
EV057010 | blue | Event 057 /Utility and Gas Trenches - Chimney Road closed with TTM implemented | TT_FinMile | 26/01/2019 | 26/01/2019 | 08/12/2018 | 08/12/2018 | 0 | TK_Complete | CCGTD1_IPS
EV057020 | black | Event 057 /Utility and Gas Trenches - Excavation permit issued | TT_Mile | 26/01/2019 | 26/01/2019 | 12/12/2018 | 12/12/2018 | 0 | TK_Complete | CCGTD1_IPS
PTA10010 | red | Utility and Gas Trenches (as per drawing ref. BPB /OARU /GA /1 /VAA /D1 /161 Rev.4) | TT_Task | 26/01/2019 | 13/04/2019 | 12/12/2018 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS
PTA10020 | red | Sleeperways (as per drawing ref. BPB /OARU /GA /1 /VAA /D1 /161 Rev.4) | TT_Task | 01/08/2019 | 20/08/2019 | 06/07/2019 | 22/08/2019 | 0 | TK_Complete | CCGTD1_IPS
A1010 | black | Date for Commencement of the Works | TT_Mile | 30/11/2017 | 30/11/2017 | 22/09/2017 | 22/09/2017 | 0 | TK_Complete | CCGTD1_IPS
SC1040 | blue | Section 04 - Completion of grouting required for the foundations and support for shaftline equipment | TT_FinMile | 09/05/2019 | 09/05/2019 | 07/03/2019 | 07/03/2019 | 0 | TK_Complete | CCGTD1_IPS
SC1060-1 | blue | Section 06.1 - Completion of TOP'S and successfully pass TOP Tests for Generator &amp; Auxiliaries Systems | TT_FinMile | 31/12/2019 | 31/12/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SC1060-2 | blue | Section 06.2 - Completion of TOP'S and successfully pass TOP Tests for Gas Turbine &amp; Auxiliaries | TT_FinMile | 17/12/2019 | 17/12/2019 | 21/11/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SC1070 | blue | Section 07 - Completion of TOP'S and successfully pass TOP Tests for Steam Turbine &amp; Auxiliaries | TT_FinMile | 28/03/2020 | 28/03/2020 | 28/03/2020 | 28/03/2020 | 0 | TK_Complete | CCGTD1_IPS
SC1080 | blue | Section 08 - Completion of TOP'S and successfully pass TOP Tests for Circulating Water Area | TT_FinMile | 08/04/2020 | 08/04/2020 | 17/12/2019 | 17/12/2019 | 0 | TK_Complete | CCGTD1_IPS
SC1110 | blue | Section 11 - Mechanical Completion 100% of TOP and pass TOP tests, for piping systems to allow chemical clean of HRSG | TT_FinMile | 11/12/2019 | 11/12/2019 | 30/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SC1120 | blue | Section 12 - Completion of the HRSG systems, incl. all tests to prove integrity of the HRSG | TT_FinMile | 30/11/2019 | 30/11/2019 | 30/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SC1160 | blue | Section 16 - Mechanical Completion of gas supply pipework with the issuance of the User App. from GSO | TT_FinMile | 28/03/2020 | 28/03/2020 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SC1170 | blue | Section 17 - Mechanical Completion of 100% of TOP and successfully pass TOP Tests for all piping systems and Module Skid | TT_FinMile | 28/03/2020 | 28/03/2020 | 15/02/2020 | 15/02/2020 | 0 | TK_Complete | CCGTD1_IPS
SC1180 | blue | Section 18 - Completion of the following TOP's and pass TOP test (refer to list) | TT_FinMile | 02/12/2019 | 02/12/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SC1190 | blue | Section 19 - Completion of Installation of 100% of TOP and successfully pass TOP Tests for EC&amp;I systems | TT_FinMile | 28/03/2020 | 28/03/2020 | 15/02/2020 | 15/02/2020 | 0 | TK_Complete | CCGTD1_IPS
SC1200 | blue | Section 20 - Completion of all terminations of 6.6kV system and construction completion of the generator isolated ph.BD | TT_FinMile | 28/03/2020 | 28/03/2020 | 27/11/2019 | 27/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SC1210 | blue | Section 21 - Completion of all works and TOP's to enable back-energization from CLP 400kV System | TT_FinMile | 06/12/2019 | 06/12/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SC1220 | blue | Section 22 - Construction Completion of CO2 systems including completion of NFPA leakage test | TT_FinMile | 14/04/2020 | 14/04/2020 | 06/01/2020 | 06/01/2020 | 0 | TK_Complete | CCGTD1_IPS
SC1230 | blue | Section 23 - Completion of all TOP's associated with works and successfully pass TOP tests | TT_FinMile | 14/04/2020 | 14/04/2020 | 20/01/2020 | 20/01/2020 | 0 | TK_Complete | CCGTD1_IPS
SC1240 | blue | Section 24 - Completion of all completion documentation | TT_FinMile | 14/04/2020 | 14/04/2020 | 15/06/2020 | 15/06/2020 | 0 | TK_Complete | CCGTD1_IPS
SC1250 | blue | Section 25 - Completion of all support to OEM during cold commissioning to allow first fire and first steam blow | TT_FinMile | 14/04/2020 | 14/04/2020 | 20/01/2020 | 20/01/2020 | 0 | TK_Complete | CCGTD1_IPS
SC1260 | blue | Section 26 - Completion of all support to the OEM during hot commissioning and testing to allow commencement of operate | TT_FinMile | 24/06/2020 | 24/06/2020 | 30/06/2020 | 30/06/2020 | 0 | TK_Complete | CCGTD1_IPS
SC1350 | blue | Section 20 - Partial 6.6Kv Ready for Station Feed | TT_FinMile | 31/08/2019 | 31/08/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
SC1010-1 | blue | Section 01.1 - Completion of the submission of unpriced PO to confirm the placement of Crane barge(s) &gt; 300t | TT_FinMile | 12/02/2018 | 12/02/2018 | 12/01/2018 | 12/01/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 16/10/2017
SC1010-2 | blue | Section 01.2 - Completion of the submission of unpriced PO to confirm the placement of Land based cranes (50-300T) | TT_FinMile | 12/02/2018 | 12/02/2018 | 15/01/2018 | 15/01/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 16/10/2017
SC1020-1 | blue | Section 02.1 - Completion of submission of Insurance certificates and policy documentation | TT_FinMile | 15/02/2018 | 15/02/2018 | 17/11/2017 | 17/11/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/02/2018
SC1020-2 | blue | Section 02.2 - Completion of submission of Construction Execution Plan | TT_FinMile | 15/02/2018 | 15/02/2018 | 17/11/2017 | 17/11/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 11/03/2017
SC1020-3 | blue | Section 02.3 - Completion of submission of SHE Plans | TT_FinMile | 15/02/2018 | 15/02/2018 | 17/11/2017 | 17/11/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/10/2017
SC1020-4 | blue | Section 02.4 - Completion of submission of Material Management Plan | TT_FinMile | 15/02/2018 | 15/02/2018 | 11/01/2018 | 11/01/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/10/2017
SC1020-5 | blue | Section 02.5 - Completion of submission of Project Quality Plan, Quality Assurance System Manual, etc | TT_FinMile | 15/02/2018 | 15/02/2018 | 08/01/2018 | 08/01/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 31/10/2017
SC1030 | blue | Section 03 - Completion of Mobilization of the crane barge to site, necessary to commence lifting | TT_FinMile | 01/03/2018 | 01/03/2018 | 15/03/2018 | 15/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 15/03/2018
SC1050 | blue | Section 05 - Completion of alignment checks of Steam Turbines, Generator, Compressor/ Gas Turbine | TT_FinMile | 09/05/2019 | 09/05/2019 | 12/04/2019 | 12/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 12/04/2019
SC1090 | blue | Section 09 - Mechanical Completion of the HRSG Supporting frames: Structure Ready for loading of Module HRSG | TT_FinMile | 26/07/2018 | 26/07/2018 | 26/07/2018 | 26/07/2018 | 0 | TK_Complete | CCGTD1_IPS
SC1100 | blue | Section 10 - Mech. Compl. of all PP incl. Heating Modules, drums, evaporators. - HRSG Ready for HP Piping | TT_FinMile | 31/10/2018 | 31/10/2018 | 24/10/2018 | 24/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SC1130 | blue | Section 13 - Construction Completion of the Steam Turbine Drain Skid MAL00Y | TT_FinMile | 29/09/2018 | 29/09/2018 | 22/09/2018 | 22/09/2018 | 0 | TK_Complete | CCGTD1_IPS
SC1140 | blue | Section 14 - Construction completion of the Module Pipe Racks UMCM1Y &amp; UMCL1Y | TT_FinMile | 12/04/2019 | 12/04/2019 | 30/03/2019 | 30/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 30/03/2019
SC1150 | blue | Section 15 A - Construction completion of the condenser and cooling water connection to the Bonna cooling water pipes | TT_FinMile | 02/12/2019 | 02/12/2019 | 14/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SC1270 | blue | New Section A (Formerly Sec. 20) 6.6Kv Completion | TT_FinMile | 09/09/2019 | 09/09/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 20/08/2019
SC1280 | blue | New Section B (Formerly Sec. 11 &amp; 12) Chemical Cleaning | TT_FinMile | 30/11/2019 | 30/11/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SC1290 | blue | New Section C (Formerly Sec. 18 &amp; 21) Back Energization | TT_FinMile | 06/12/2019 | 06/12/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete | CCGTD1_IPS
SC1300 | blue | New Section D (Formerly Sec. 6A, 6B, 7, 8, 16, 17,19, 22 &amp; 23) Pre-mechanical completion (Initial fire) | TT_FinMile | 14/04/2020 | 14/04/2020 | 29/03/2020 | 29/03/2020 | 0 | TK_Complete | CCGTD1_IPS
SC1310 | blue | New Section E (Formerly Sec. 24) Documentation complete | TT_FinMile | 14/04/2020 | 14/04/2020 | 16/06/2020 | 16/06/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 13/11/2019
SC1320 | blue | New Section F (Formerly Sec. 25) Mechanical Completion (Cold commissioning) | TT_FinMile | 14/04/2020 | 14/04/2020 | 21/01/2020 | 21/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 30/10/2019
SC1330 | blue | New Section G (Formerly Sec. 26) Commercial operation (Hot Commissioning) | TT_FinMile | 14/04/2020 | 14/04/2020 | 01/07/2020 | 01/07/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 28/02/2020
SC1340 | blue | Section 15 B - Demin Water Available | TT_FinMile | 10/07/2019 | 10/07/2019 | 22/05/2019 | 22/05/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_NO_LATER_THAN | 20/05/2019
TOP1030 | blue | (TOP-10BZL-03) L&amp;SP Incl. BMZ in UBA and UBF and UBE | TT_FinMile | 17/12/2019 | 17/12/2019 | 05/02/2020 | 05/02/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP1040 | blue | (TOP-10CY) Communication / Security Systems 10 (Is it same as TOP-00CY-02 and TOP-00CY-01) | TT_FinMile | 31/12/2019 | 31/12/2019 | 19/01/2020 | 19/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/11/2019
TOP1060 | blue | (TOP-10GM-03) Plant Drainage System Pump for UGD (incl. UGU) | TT_FinMile | 03/04/2020 | 03/04/2020 | 20/12/2019 | 20/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/11/2019
TOP1070 | blue | (TOP-10GHD-02) Service Water Distribution Inside Power Block | TT_FinMile | 30/03/2020 | 30/03/2020 | 21/02/2020 | 21/02/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/11/2019
TOP1080 | blue | (TOP-10GKB-02) Drinking Water Distribution Inside Power Block | TT_FinMile | 30/03/2020 | 30/03/2020 | 21/02/2020 | 21/02/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/11/2019
TOP1090 | blue | (TOP-10GM-02) Plant Drainage System for 10U MC *LCAL | TT_FinMile | 17/12/2019 | 17/12/2019 | 20/12/2019 | 20/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1100 | blue | (TOP-10MA-01) HP / IP / LP Turbine 10MAA/MAB/MAC | TT_FinMile | 17/12/2019 | 17/12/2019 | 16/11/2019 | 16/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP1110 | blue | (TOP-10MAD) ST Bearing System | TT_FinMile | 18/09/2019 | 18/09/2019 | 06/09/2019 | 06/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 07/09/2019
TOP1120 | blue | (TOP-10MAL) ST Drain System | TT_FinMile | 11/11/2019 | 11/11/2019 | 11/11/2019 | 11/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1130 | blue | (TOP-10MAN) ST Bypass System | TT_FinMile | 21/10/2019 | 21/10/2019 | 26/10/2019 | 26/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 26/10/2019
TOP1140 | blue | (TOP-10MA-02) HP / IP / LP Steam Turbine Emergency Stop Valves and Control Valves | TT_FinMile | 04/11/2019 | 04/11/2019 | 09/11/2019 | 09/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP1150 | blue | (TOP-10MAG) Condensing System | TT_FinMile | 11/11/2019 | 11/11/2019 | 14/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1160 | blue | (TOP-10MAV) Lube and Lifting Oil system Incl. Generator and GT(10MAV01_16Aug19 / 10MAV02_05Sep19 / 10MAV03_27Mar20) | TT_FinMile | 05/09/2019 | 05/09/2019 | 27/03/2020 | 27/03/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 05/09/2019
TOP1170 | blue | (TOP-10MAW) Gland / Leakage Steam System | TT_FinMile | 21/10/2019 | 21/10/2019 | 26/10/2019 | 26/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 26/10/2019
TOP1180 | blue | (TOP-10MAX) ST Hydraulic System | TT_FinMile | 21/10/2019 | 21/10/2019 | 12/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 12/10/2019
TOP1190 | blue | (TOP-10QFB) Control Air System for ST (10QFB01_11Nov19 / 10QFB02_05Dec19 / 10QFB03_12Feb20) | TT_FinMile | 11/11/2019 | 11/11/2019 | 12/02/2020 | 12/02/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1200 | blue | (TOP-10MKA) Generator Incl. Bearing System 10MKD | TT_FinMile | 11/11/2019 | 11/11/2019 | 18/11/2019 | 18/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1210 | blue | (TOP-10MKF) Generator Primary Water Cooling System | TT_FinMile | 28/10/2019 | 28/10/2019 | 25/10/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 26/10/2019
TOP1220 | blue | (TOP-10MKG) Hydrogen Gas Supply System | TT_FinMile | 08/11/2019 | 08/11/2019 | 01/11/2019 | 01/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP1230 | blue | (TOP-10MKQ) Waste Gas System | TT_FinMile | 14/10/2019 | 14/10/2019 | 03/10/2019 | 03/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/10/2019
TOP1240 | blue | (TOP-10MKW) Seal Oil Supply System | TT_FinMile | 24/09/2019 | 24/09/2019 | 26/08/2019 | 26/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 01/09/2019
TOP1250 | blue | (TOP-10MBV) GT Lube Oil / Lifting Oil System | TT_FinMile | 17/09/2019 | 17/09/2019 | 06/09/2019 | 06/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 06/09/2019
TOP1260 | blue | (TOP-10MBA) GT Including Combustion Chamber | TT_FinMile | 21/11/2019 | 21/11/2019 | 21/11/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1270 | blue | (TOP-10MBX) GT Hydraulic Oil | TT_FinMile | 14/10/2019 | 14/10/2019 | 28/10/2019 | 28/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 26/10/2019
TOP1280 | blue | (TOP-10MBP) GT Natural Gas incl. Draining System MBP40 | TT_FinMile | 05/11/2019 | 05/11/2019 | 21/11/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP1290 | blue | (TOP-10MBN) GT Fuel Oil Injection System | TT_FinMile | 11/11/2019 | 11/11/2019 | 05/11/2019 | 05/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1300 | blue | (TOP-10MBH) GT Cooling Air System | TT_FinMile | 23/09/2019 | 23/09/2019 | 23/09/2019 | 23/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/09/2019
TOP1310 | blue | (TOP-10MBA18) Compressor Cleaning Package | TT_FinMile | 23/09/2019 | 23/09/2019 | 13/09/2019 | 13/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 22/09/2019
TOP1320 | blue | (TOP-10MBA5x) GT Hydraulic Clearance Optimization Supply System | TT_FinMile | 16/10/2019 | 16/10/2019 | 23/08/2019 | 23/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 20/10/2019
TOP1330 | blue | (TOP-10MBX2x) GT Pneumatic System | TT_FinMile | 14/10/2019 | 14/10/2019 | 29/09/2019 | 29/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 29/09/2019
TOP1340 | blue | (TOP-10MBA4X) Blow Off System | TT_FinMile | 14/10/2019 | 14/10/2019 | 12/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 12/10/2019
TOP1350 | blue | (TOP-00QFB) Instrument Air Distribution system | TT_FinMile | 11/11/2019 | 11/11/2019 | 29/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1360 | blue | (TOP-10MBL) Air Intake System | TT_FinMile | 21/10/2019 | 21/10/2019 | 10/10/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/10/2019
TOP1370 | blue | (TOP-10MBU) GT NOX Water Injection System (10MBU01_12Oct19 /10MBU02_17Oct19) | TT_FinMile | 14/10/2019 | 14/10/2019 | 17/10/2019 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/10/2019
TOP1380 | blue | (TOP-10SAM30) Ventilation System for GT Enclosure and Skid Enclosures | TT_FinMile | 15/11/2019 | 15/11/2019 | 02/11/2019 | 02/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP1390 | blue | (TOP-10SGJ-02) FF CO2 System CYE/SGJ for GT Noise Enclosure and Gas Skid | TT_FinMile | 07/04/2020 | 07/04/2020 | 06/01/2020 | 06/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1400 | blue | (TOP-10CYQ) Gas Detection System | TT_FinMile | 15/04/2020 | 15/04/2020 | 09/01/2020 | 09/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP1410 | blue | (TOP-10LCA) Main Condensate Pumps and Supply system for Min. Flow Operation | TT_FinMile | 30/03/2020 | 30/03/2020 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1420 | blue | (TOP-10PGB) CCW System | TT_FinMile | 21/10/2019 | 21/10/2019 | 30/09/2019 | 30/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 29/09/2019
TOP1430 | blue | (TOP-10PCB) Service Cooling Water System Incl. 10PDB | TT_FinMile | 30/03/2020 | 30/03/2020 | 02/01/2020 | 02/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/11/2019
TOP1440 | blue | (TOP-10PAB-02) Circulating Water System - Power Island Part | TT_FinMile | 30/03/2020 | 30/03/2020 | 21/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP1460 | blue | (TOP-00SCA) Compressed Air Station | TT_FinMile | 01/11/2019 | 01/11/2019 | 11/10/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 19/10/2019
TOP1470 | blue | (TOP-10SGA) FF Indoor Hydrants 10SGA Inside 10ULA, 10UHA, 10UMC | TT_FinMile | 09/04/2020 | 09/04/2020 | 18/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP1480 | blue | (TOP-10SGC-02) FF Spray Deluge System 10SGC for Lube Oil / Seal Oil System | TT_FinMile | 09/04/2020 | 09/04/2020 | 15/01/2020 | 15/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP1490 | blue | (TOP-10BBA) MV Switchgear 10BBA | TT_FinMile | 31/07/2019 | 31/07/2019 | 19/07/2019 | 19/07/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 12/07/2019
TOP1500 | blue | (TOP-10BF) LV Switchgear 10BFE/10BMA | TT_FinMile | 03/06/2019 | 03/06/2019 | 29/07/2019 | 29/07/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 31/05/2019
TOP1520 | blue | (TOP-10BT) DC-SWITCHGEAR 10BU | TT_FinMile | 29/07/2019 | 29/07/2019 | 29/07/2019 | 29/07/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 29/07/2019
TOP1530 | blue | (TOP-10CHA) Generator Protection 10CHA | TT_FinMile | 16/09/2019 | 16/09/2019 | 12/08/2019 | 12/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 12/08/2019
TOP1560 | blue | (TOP-10CJ) Automation System 10CJ | TT_FinMile | 17/10/2019 | 17/10/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 19/08/2019
TOP1570 | blue | (TOP-10CP-AA) ET200 Stations in Function Area 10 Auxiliary and Ancillary | TT_FinMile | 11/11/2019 | 11/11/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1580 | blue | (TOP-10CP-HR) ET200 Stations in Function Area 10 HRSG | TT_FinMile | 04/09/2019 | 04/09/2019 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 04/09/2019
TOP1590 | blue | (TOP-10CP-WS) ET200 Stations in Function Area 10 Water / Steam Cycle | TT_FinMile | 02/09/2019 | 02/09/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/08/2019
TOP1620 | blue | (TOP-10CP-ST) ET200 Stations in Function Area 10ST | TT_FinMile | 06/09/2019 | 06/09/2019 | 15/08/2019 | 15/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/08/2019
TOP1640 | blue | (TOP-10CP-GT) ET200 Stations in Function Area 10GT | TT_FinMile | 12/09/2019 | 12/09/2019 | 08/08/2019 | 08/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 08/08/2019
TOP1650 | blue | (TOP-10SGJ-01) FF CO2 System for PCC 10SGJ | TT_FinMile | 15/04/2020 | 15/04/2020 | 06/01/2020 | 06/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1660 | blue | (TOP-10BAT) Main Transformer 10BAT01/10BBT01 | TT_FinMile | 16/09/2019 | 16/09/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 19/08/2019
TOP1670 | blue | (TOP-10GM-01) Plant Drainage System for 10UBE/10UBF | TT_FinMile | 04/11/2019 | 04/11/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP1680 | blue | (TOP-10MKC) SEE/SFC Equipment, Excitation Transformer MKC; SFC Transformer MBJ | TT_FinMile | 28/10/2019 | 28/10/2019 | 25/10/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 27/10/2019
TOP1690 | blue | (TOP-10SGC-01) FF Spray Deluge System for BAT/ BBT SGC | TT_FinMile | 14/04/2020 | 14/04/2020 | 18/03/2020 | 18/03/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP1700 | blue | (TOP-10LD) Condensate Polishing Plant | TT_FinMile | 30/03/2020 | 30/03/2020 | 15/02/2020 | 15/02/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP1710 | blue | (TOP-10LDK) Condensate Polishing System | TT_FinMile | 11/11/2019 | 11/11/2019 | 26/11/2019 | 26/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1720 | blue | (TOP-10BA) Isolated Generator Busduct 10BAA Incl. 10BAB, BAC | TT_FinMile | 13/11/2019 | 13/11/2019 | 05/11/2019 | 05/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1730 | blue | (TOP-00XKA) Emergency Diesel Generator Set | TT_FinMile | 07/11/2019 | 07/11/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP1740 | blue | (TOP-00SGM) FF Protection System for UBN | TT_FinMile | 02/04/2020 | 02/04/2020 | 13/03/2020 | 13/03/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1750 | blue | (TOP-10BFT01) LV Transformer BFT01 (BHT) | TT_FinMile | 16/09/2019 | 16/09/2019 | 18/09/2019 | 18/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/09/2019
TOP1760 | blue | (TOP-10BFT02) LV Transformer BFT02 (BHT) | TT_FinMile | 09/09/2019 | 09/09/2019 | 29/08/2019 | 29/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 01/09/2019
TOP1770 | blue | (TOP-10BBT) MV Transformer BBT01 | TT_FinMile | 13/09/2019 | 13/09/2019 | 07/09/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 07/09/2019
TOP1790 | blue | (TOP-10MBR) GT Exhaust Gas System | TT_FinMile | 18/11/2019 | 18/11/2019 | 01/11/2019 | 01/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP1800 | blue | (TOP-10EK) FUEL GAS SUPPLY SYSTEM FOR GT10 | TT_FinMile | 30/03/2020 | 30/03/2020 | 09/01/2020 | 09/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1810 | blue | (TOP-10BZL-02) L&amp;SP incl. BMZ at 10UHA Area | TT_FinMile | 30/03/2020 | 30/03/2020 | 05/02/2020 | 05/02/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP1820 | blue | (TOP-10CFE) CEMS | TT_FinMile | 31/03/2020 | 31/03/2020 | 06/01/2020 | 06/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1830 | blue | (TOP-10HAD10) HRSG HP Steam | TT_FinMile | 18/11/2019 | 18/11/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1840 | blue | (TOP-10HAD50) HRSG IP Steam | TT_FinMile | 07/11/2019 | 07/11/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP1850 | blue | (TOP-10HAD80) HRSG LP Steam | TT_FinMile | 18/11/2019 | 18/11/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP1860 | blue | (TOP-10HAA) HRSG Condensate Preheating System | TT_FinMile | 11/11/2019 | 11/11/2019 | 11/11/2019 | 11/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1870 | blue | (TOP-10HBK) HRSG Exhaust Gas System | TT_FinMile | 08/11/2019 | 08/11/2019 | 21/11/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP1880 | blue | (TOP-00LBG) Auxiliary Steam System Common Area | TT_FinMile | 06/11/2019 | 06/11/2019 | 26/11/2019 | 26/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP1890 | blue | (TOP-10GM-02) Plant Drainage System for 10U HW | TT_FinMile | 07/04/2020 | 07/04/2020 | 20/12/2019 | 20/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1900 | blue | (TOP-10LBH) Start-up and Shutdown Steam System incl. Drains System | TT_FinMile | 04/11/2019 | 04/11/2019 | 19/11/2019 | 19/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP1910 | blue | (TOP-10LCL) HRSG Drains System | TT_FinMile | 07/11/2019 | 07/11/2019 | 15/11/2019 | 15/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP1920 | blue | (TOP-10LCA-02) Condensate Supply System incl. Preheater 10HAA10 | TT_FinMile | 11/11/2019 | 11/11/2019 | 11/11/2019 | 11/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1930 | blue | (TOP-10LAB) HP/IP Feedwater Supply System | TT_FinMile | 11/11/2019 | 11/11/2019 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP1940 | blue | (TOP-10LAC) Feedwater Pump | TT_FinMile | 11/11/2019 | 11/11/2019 | 14/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1950 | blue | (TOP-10QCB) Hydrazine Dosing QC | TT_FinMile | 11/11/2019 | 11/11/2019 | 26/11/2019 | 26/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1960 | blue | (TOP-10QCC) Trisodiumphosphate Dosing QC | TT_FinMile | 07/04/2020 | 07/04/2020 | 03/12/2019 | 03/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1970 | blue | (TOP-10QCD) Ammonia Dosing QC | TT_FinMile | 07/04/2020 | 07/04/2020 | 03/12/2019 | 03/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP1980 | blue | (TOP-10QU) Sampling Container QU | TT_FinMile | 07/04/2020 | 07/04/2020 | 20/01/2020 | 20/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/11/2019
TOP2000 | blue | (TOP-10HSJ) Reduction Agent Supply System for SCR | TT_FinMile | 13/04/2020 | 13/04/2020 | 19/01/2020 | 19/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2010 | blue | (TOP-10EKT20) Fuel Gas Preheating System 10EKT20 | TT_FinMile | 11/11/2019 | 11/11/2019 | 27/11/2019 | 27/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP2020 | blue | (TOP-10GHC) Demineralised Water Distribution System Inside 10UMC | TT_FinMile | 30/09/2019 | 30/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/09/2019
TOP2050 | blue | (TOP-10LBA10) HP Main Steam System | TT_FinMile | 05/11/2019 | 05/11/2019 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP2060 | blue | (TOP-10LBA80) LP Main Steam System | TT_FinMile | 11/11/2019 | 11/11/2019 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP2070 | blue | (TOP-10LBB) Cold and Hot Reheat System 10LBB / 10LBC | TT_FinMile | 15/11/2019 | 15/11/2019 | 29/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP2080 | blue | (TOP-00LBG) Auxiliary Steam System | TT_FinMile | 08/11/2019 | 08/11/2019 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP2090 | blue | (TOP-10MAJ) ST Evacuation System | TT_FinMile | 04/11/2019 | 04/11/2019 | 22/10/2019 | 22/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 23/10/2019
TOP2100 | blue | (TOP-10PAH) Condenser Tube Cleaning System | TT_FinMile | 09/04/2020 | 09/04/2020 | 18/12/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/11/2019
TOP2110 | blue | (TOP-00BZL-01) L&amp;SP Iincl. BMZ 00 IN UBA 81 Area (Civil Contractor) | TT_FinMile | 30/03/2020 | 30/03/2020 | 05/02/2020 | 05/02/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2120 | blue | (TOP-10PAB-01) Circulating Water System incl. Cooling Water Pumps | TT_FinMile | 08/04/2020 | 08/04/2020 | 13/12/2019 | 13/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2130 | blue | (TOP-00PAA) Cooling Water Screening Plant | TT_FinMile | 30/03/2020 | 30/03/2020 | 05/12/2019 | 05/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2140 | blue | (TOP-00PUR) Cathodic Protection System for Cooling Water Inlet | TT_FinMile | 30/03/2020 | 30/03/2020 | 16/12/2019 | 16/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2160 | blue | (TOP-10PUR) Cathodic Protection System for Cooling Water Side of Condenser | TT_FinMile | 30/03/2020 | 30/03/2020 | 09/12/2019 | 09/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2190 | blue | (TOP-00GHC-02) Demineralised Water Supply System up to UMC | TT_FinMile | 30/09/2019 | 30/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/09/2019
TOP2250 | blue | (TOP-00SGA-01) Fire Pump Station, Ring Main, Outdoor Hydrants TEMP FIRE SUPPLY (REQUIRED DATE TO BE CLARIFIED) | TT_FinMile | 14/04/2020 | 14/04/2020 | 18/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2260 | blue | (TOP-00STG) Laboratory Container STG | TT_FinMile | 07/04/2020 | 07/04/2020 | 11/12/2019 | 11/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2270 | blue | (TOP-00EK) Fuel Gas Conditioning System EKD (incl. Fuel Gas Supply for QHA) | TT_FinMile | 30/03/2020 | 30/03/2020 | 28/12/2019 | 28/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 27/10/2019
TOP2280 | blue | (TOP-10SGC-02) FF Spray Deluge System for BOP Systems | TT_FinMile | 09/04/2020 | 09/04/2020 | 15/01/2020 | 15/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2290 | blue | (TOP-00SCB) Compressed air Distribution System Overall Plant | TT_FinMile | 31/10/2019 | 31/10/2019 | 04/10/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 19/10/2019
TOP2300 | blue | (TOP-00EG-01) Fuel Oil Forwarding Station and Storage Tank | TT_FinMile | 11/11/2019 | 11/11/2019 | 26/10/2019 | 26/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 26/10/2019
TOP2310 | blue | (TOP-00EG-02) Fuel Oil Forwarding System incl. Supply Lines up to Fuel Oil | TT_FinMile | 30/03/2020 | 30/03/2020 | 27/03/2020 | 27/03/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP2330 | blue | (TOP-00CR) Control Room Equipment | TT_FinMile | 31/07/2019 | 31/07/2019 | 16/07/2019 | 16/07/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 16/07/2019
TOP2350 | blue | (TOP-00CY) Communication System in 00UCA (00CY-01_19Jan20 / 00CY-02_27Feb20) | TT_FinMile | 30/03/2020 | 30/03/2020 | 27/02/2020 | 27/02/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/11/2019
TOP2360 | blue | (TOP-10AC) HV Switchgear Including Cable Connection and Lighting and Small | TT_FinMile | 02/09/2019 | 02/09/2019 | 07/08/2019 | 07/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 09/08/2019
TOP2370 | blue | (TOP-10CYE) Fire Detection System for GT Noise Enclosure MPB | TT_FinMile | 13/04/2020 | 13/04/2020 | 09/01/2020 | 09/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2340 | blue | (TOP-10CJ-ST) Automation Panel in Function Area Steam Turbine | TT_FinMile | 05/09/2019 | 05/09/2019 | 15/08/2019 | 15/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/08/2019
TOP2390 | blue | (TOP-10CJ-GT) Automation Panel in Function Area Gas Turbine | TT_FinMile | 31/08/2019 | 31/08/2019 | 06/08/2019 | 06/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/08/2019
TOP2400 | blue | (TOP-10BA-03) Generator Circuit Breaker | TT_FinMile | 17/09/2019 | 17/09/2019 | 01/08/2019 | 01/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/08/2019
TOP2410 | blue | (TOP-10BFT-03) LV-Transformer BFT03 | TT_FinMile | 06/09/2019 | 06/09/2019 | 28/08/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 01/09/2019
TOP2420 | blue | (TOP-10BFT-02) LV-Transformer BFT02 | TT_FinMile | 06/09/2019 | 06/09/2019 | 29/08/2019 | 29/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 01/09/2019
TOP2430 | blue | (TOP-10CJ-BOP) Automation Panel in Function Area BOP | TT_FinMile | 16/09/2019 | 16/09/2019 | 19/08/2019 | 19/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 19/08/2019
TOP2440 | blue | (TOP-10CJ-HR) Automation Panel in Function Area HRSG | TT_FinMile | 04/09/2019 | 04/09/2019 | 03/09/2019 | 03/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 04/09/2019
TOP2450 | blue | (TOP-10CP-BOP-01) CPC Interface Panels ET200 in Function Area BOP (UBA area) | TT_FinMile | 10/09/2019 | 10/09/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 19/08/2019
TOP2460 | blue | (TOP-10CP-BOP-02) CPD Interface Panels ET200 in Function Area BOP | TT_FinMile | 10/09/2019 | 10/09/2019 | 19/08/2019 | 19/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 19/08/2019
TOP2470 | blue | (TOP-10BT-03) DC-Switchgear BUC/BUD | TT_FinMile | 11/11/2019 | 11/11/2019 | 18/11/2019 | 18/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP2480 | blue | (TOP-10BF-03) LV Switchgear BFD | TT_FinMile | 11/11/2019 | 11/11/2019 | 20/11/2019 | 20/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP2490 | blue | (TOP-10BF-02) LV Switchgear BFB/ BFC | TT_FinMile | 05/09/2019 | 05/09/2019 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 04/09/2019
TOP2500 | blue | (TOP-10BMT-01) LV-Transformer BMT01 | TT_FinMile | 06/09/2019 | 06/09/2019 | 16/08/2019 | 16/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 01/09/2019
TOP2520 | blue | (TOP-10CP-BOP-03) CPC Interface Panels ET200 in Function Area BOP (UQA area) | TT_FinMile | 30/11/2019 | 30/11/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP2530 | blue | (TOP-10CP-BOP-04) CPC Interface Panels ET200 in Function Area BOP (UTR0500 CPC91) | TT_FinMile | 11/09/2019 | 11/09/2019 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 04/09/2019
TOP2540 | blue | (TOP-10CP-BOP-05) CPC Interface Panels ET200 in Function Area BOP (UTR0500 CPC92) | TT_FinMile | 30/09/2019 | 30/09/2019 | 25/09/2019 | 25/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 29/09/2019
TOP2550 | blue | (TOP-10BT-01) 220 V Batteries | TT_FinMile | 31/08/2019 | 31/08/2019 | 16/08/2019 | 16/08/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 16/08/2019
TOP2560 | blue | (TOP-10MBU-01) Reserve feedwater pumps and distribution system | TT_FinMile | 21/10/2019 | 21/10/2019 | 10/10/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 12/10/2019
TOP2570 | blue | (TOP-10CKA) Partial Discharge &amp; Shaft voltage/current Monitoring System | TT_FinMile | 21/10/2019 | 21/10/2019 | 20/10/2019 | 20/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 20/10/2019
TOP2580 | blue | (TOP-10CJT) SEE / SFC Equipment | TT_FinMile | 21/10/2019 | 21/10/2019 | 24/10/2019 | 24/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/10/2019
TOP2590 | blue | (TOP-10BAB) Generator Neutral point and auxilaries | TT_FinMile | 12/11/2019 | 12/11/2019 | 14/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP2600 | blue | (TOP-01AC) HV Switchgear interface | TT_FinMile | 16/09/2019 | 16/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/09/2019
TOP2610 | blue | (TOP-10BA-01) Isolated Phase Busduct Section BAT-BAC | TT_FinMile | 05/10/2019 | 05/10/2019 | 29/09/2019 | 29/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 29/09/2019
TOP2620 | blue | (TOP-10BA-02) Isolated Phase Busduct Section BAC-MKA | TT_FinMile | 12/11/2019 | 12/11/2019 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP2630 | blue | (TOP-00CY-01) CCTV | TT_FinMile | 08/04/2020 | 08/04/2020 | 19/01/2020 | 19/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/11/2019
TOP2640 | blue | (TOP-00CY-02) Telephone System | TT_FinMile | 28/03/2020 | 28/03/2020 | 27/02/2020 | 27/02/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/11/2019
TOP2650 | blue | (TOP-10CR-01) Central Control Room Equipment | TT_FinMile | 31/07/2019 | 31/07/2019 | 15/07/2019 | 15/07/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 16/07/2019
TOP2660 | blue | (TOP-10CR-02) Central Control Room Equipment | TT_FinMile | 31/07/2019 | 31/07/2019 | 04/07/2019 | 04/07/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 04/07/2019
TOP2670 | blue | (TOP-10BF-01) LV Switchgear BFA/ BMA/BLA | TT_FinMile | 31/07/2019 | 31/07/2019 | 29/07/2019 | 29/07/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 27/07/2019
TOP2680 | blue | (TOP-10AC) GIL | TT_FinMile | 31/07/2019 | 31/07/2019 | 24/07/2019 | 24/07/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/07/2019
TOP2690 | blue | (TOP-10SMQ) 18t Gantry Crane at CWPS | TT_FinMile | 31/07/2019 | 31/07/2019 | 28/07/2019 | 28/07/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 28/07/2019
TOP2700 | blue | (TOP-10PUS) Electro Chlorination System | TT_FinMile | 28/03/2020 | 28/03/2020 | 15/02/2020 | 15/02/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2710 | blue | (TOP-10MBU-02) GT De-NOx-Water Forwarding and Injection System | TT_FinMile | 14/10/2019 | 14/10/2019 | 12/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/10/2019
TOP2720 | blue | (TOP-10PUR-20) Cathodic Protection System for Condenser | TT_FinMile | 28/03/2020 | 28/03/2020 | 09/12/2019 | 09/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2730 | blue | (TOP-10PUR-50) Cathodic Protection System for Fuel Gas System (EKG) | TT_FinMile | 28/03/2020 | 28/03/2020 | 04/12/2019 | 04/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2740 | blue | (TOP-10SGA-10) FF Outdoor Hydrants indluding Ring Main Line (10sga-10-01_18Jan20 / 10sga10-02_18Jan20) | TT_FinMile | 02/04/2020 | 02/04/2020 | 18/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2750 | blue | (TOP-10SGA-20) FF Indoor Hydrants indluding Ring Main Line (10sga-20-01_18Nov19 / 10sga20-02_18Jan20) | TT_FinMile | 02/04/2020 | 02/04/2020 | 18/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2760 | blue | (TOP-10LBG) Auxiliary Steam System for Power Island | TT_FinMile | 08/11/2019 | 08/11/2019 | 29/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/11/2019
TOP2770 | blue | (TOP-10SGM-01) Inert gas system inside UBA | TT_FinMile | 01/04/2020 | 01/04/2020 | 13/03/2020 | 13/03/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP2780 | blue | (TOP-10SGM-02) Inert gas system inside UBN container | TT_FinMile | 01/04/2020 | 01/04/2020 | 13/03/2020 | 13/03/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP2790 | blue | (TOP-10SGM-03) Inert gas system inside CPP Control room | TT_FinMile | 01/04/2020 | 01/04/2020 | 13/03/2020 | 13/03/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2800 | blue | (TOP-10GM-05) Plant Drainage System for UGH Area | TT_FinMile | 02/04/2020 | 02/04/2020 | 20/12/2019 | 20/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP2810 | blue | (TOP-10GM-04) Plant Drainage System for UGU/UTS/UVM Area | TT_FinMile | 02/04/2020 | 02/04/2020 | 27/03/2020 | 27/03/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2820 | blue | (TOP-10GM-06) Plant Drainage System from UGH to Seal Pit Area | TT_FinMile | 02/04/2020 | 02/04/2020 | 20/12/2019 | 20/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2830 | blue | (TOP-10GNR) Centralized Chemical Drain System | TT_FinMile | 28/03/2020 | 28/03/2020 | 15/01/2020 | 15/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP2840 | blue | (TOP-10QJA10) Carbon Dioxide Distribution System | TT_FinMile | 08/04/2020 | 08/04/2020 | 24/12/2019 | 24/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2850 | blue | (TOP-10QJA20) Hydrogen Distribution System | TT_FinMile | 01/04/2020 | 01/04/2020 | 07/01/2020 | 07/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2860 | blue | (TOP-10GHC-01) Demin water supply system - Pump skid | TT_FinMile | 16/09/2019 | 16/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/09/2019
TOP2870 | blue | (TOP-10GHC-02) Demineralized Water Distribution Pump skid - D5 terminal point | TT_FinMile | 16/09/2019 | 16/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/09/2019
TOP2880 | blue | (TOP-10GHC-03) Demineralized Water Distribution System Power Island | TT_FinMile | 16/09/2019 | 16/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/09/2019
TOP2890 | blue | (TOP-10CX) Weather Station and other minor auxiliaries | TT_FinMile | 14/04/2020 | 14/04/2020 | 09/12/2019 | 09/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 10/11/2019
TOP2910 | blue | (TOP-10GM-03) Plant Drainage System for UBH Area | TT_FinMile | 02/04/2020 | 02/04/2020 | 20/12/2019 | 20/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/11/2019
TOP2920 | blue | TOP-10BT-02 DC-Switchgear BUA/BUB, Chargers and DC-DC converters | TT_FinMile | 31/07/2019 | 31/07/2019 | 29/07/2019 | 29/07/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 29/07/2019
MWS01.1000 | red | Submission and Approval - Purchase Orders to Sub-contractors of Crane Barges (e.g. for lifts greater than 300t) | TT_Task | 01/03/2018 | 16/03/2018 | 30/01/2018 | 14/02/2018 | 0 | TK_Complete | CCGTD1_IPS
MWS01.1010 | red | Submission and Approval - Purchase Orders to Sub-contractors of Land based cranes (e.g. for large lifts between 50-300t) | TT_Task | 01/03/2018 | 16/03/2018 | 30/01/2018 | 09/02/2018 | 0 | TK_Complete | CCGTD1_IPS
MWS02.1010 | red | Submission and Approval - Insurance certificates and policy documentation | TT_Task | 01/02/2018 | 21/02/2018 | 01/11/2017 | 17/11/2017 | 0 | TK_Complete | CCGTD1_IPS
MWS02.1020 | red | Submission and Approval - Construction Execution Plan | TT_Task | 01/02/2018 | 21/02/2018 | 17/11/2017 | 26/02/2018 | 0 | TK_Complete | CCGTD1_IPS
MWS02.1030 | red | Submission and Approval - SHHE Plans | TT_Task | 01/02/2018 | 21/02/2018 | 17/11/2017 | 26/02/2018 | 0 | TK_Complete | CCGTD1_IPS
MWS02.1040 | red | Submission and Approval - Material Management Plan | TT_Task | 01/02/2018 | 21/02/2018 | 17/12/2017 | 17/12/2017 | 0 | TK_Complete | CCGTD1_IPS
MWS02.1050 | red | Submission and Approval - Project Quality Plan | TT_Task | 01/02/2018 | 21/02/2018 | 08/01/2018 | 08/01/2018 | 0 | TK_Complete | CCGTD1_IPS
MWS02.1060 | red | Submission and Approval - Quality Assurance System Manual | TT_Task | 01/02/2018 | 21/02/2018 | 08/01/2018 | 08/01/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG0000 | blue | Engineering complete - Start delivering engineering systems | TT_FinMile | 01/03/2018 | 01/03/2018 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 04/11/2017
ENG1000 | blue | Engineering complete - (00BAW-01) Earthing Grid for back-energizing | TT_FinMile | 01/03/2018 | 01/03/2018 | 22/01/2018 | 22/01/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1010 | blue | Engineering complete - (00BAW-02) Earthing Grid Complete | TT_FinMile | 01/03/2018 | 01/03/2018 | 05/02/2018 | 05/02/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1020 | blue | Engineering complete - (00BAW-03) Lightening Protection | TT_FinMile | 01/03/2018 | 01/03/2018 | 22/01/2018 | 22/01/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1030 | blue | Engineering complete - (10MA-01) HP / IP / LP Turbine 10MAA/MAB/MAC | TT_FinMile | 01/03/2018 | 01/03/2018 | 23/02/2018 | 23/02/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1040 | blue | Engineering complete - (10MAL) ST Drain System | TT_FinMile | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1060 | blue | Engineering complete - (10MA-02) HP / IP / LP Steam Turbine Emergency Stop Valves and Control Valves | TT_FinMile | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1070 | blue | Engineering complete - (10MAG) Condensing System | TT_FinMile | 01/03/2018 | 01/03/2018 | 23/01/2018 | 23/01/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1080 | blue | Engineering complete - (10MAV) Lube and Lifting Oil System Incl. Generator and GT | TT_FinMile | 19/03/2018 | 19/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1090 | blue | Engineering complete - (10MAW) Gland / Leakage Steam System | TT_FinMile | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1100 | blue | Engineering complete - (10MAX) ST Hydraulic System | TT_FinMile | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1120 | blue | Engineering complete - (10MKA) Generator Incl. Bearing System 10 MKD | TT_FinMile | 01/03/2018 | 01/03/2018 | 30/11/2017 | 30/11/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG1170 | blue | Engineering complete - (10MBV) GT Lube Oil / Lifting Oil System | TT_FinMile | 01/03/2018 | 01/03/2018 | 16/03/2018 | 16/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1180 | blue | Engineering complete - (10MBA) GT Including Combustion Chamber | TT_FinMile | 01/03/2018 | 01/03/2018 | 12/02/2018 | 12/02/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1190 | blue | Engineering complete - (10MBX) GT Hydraulic Oil | TT_FinMile | 01/03/2018 | 01/03/2018 | 16/02/2018 | 16/02/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1200 | blue | Engineering complete - (10MBP) GT Natural Gas Incl. Draining System MBP40 | TT_FinMile | 01/03/2018 | 01/03/2018 | 16/03/2018 | 16/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1210 | blue | Engineering complete - (10MBN) GT Fuel Oil Injection System | TT_FinMile | 01/03/2018 | 01/03/2018 | 16/03/2018 | 16/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1220 | blue | Engineering complete - (10MBH) GT Cooling Air System | TT_FinMile | 01/03/2018 | 01/03/2018 | 12/02/2018 | 12/02/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1250 | blue | Engineering complete - (10MBX2x) GT Pneumatic System | TT_FinMile | 01/03/2018 | 01/03/2018 | 12/02/2018 | 12/02/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1280 | blue | Engineering complete - (10MBL) Air Intake System | TT_FinMile | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1290 | blue | Engineering complete - (10MBU) GT NOX Water Injection System | TT_FinMile | 01/03/2018 | 01/03/2018 | 16/03/2018 | 16/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1300 | blue | Engineering complete - (10SAM30) Ventilation System For GT Enclosure and Skid Enclosures | TT_FinMile | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1330 | blue | Engineering complete - (10LCA) Main Condensate Pumps and Supply System for Min. Flow Operation Incl. | TT_FinMile | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1340 | blue | Engineering complete - (10PGB) Closed Cooling Water System | TT_FinMile | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1350 | blue | Engineering complete - (10PCB) Service Cooling Water System Incl. 10PDB | TT_FinMile | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1390 | blue | Engineering complete - (10SGA) FF Indoor Hydrants 10SGA Inside 10ULA, 10UHA, 10UMC | TT_FinMile | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1600 | blue | Engineering complete - (10MKC) SEE/SFC Equipment Excitation Transformer MKC; SFC Transformer MBJ | TT_FinMile | 01/03/2018 | 01/03/2018 | 07/03/2018 | 07/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1610 | blue | Engineering complete - (10SGC-01) FF Spary Deluge System for BAT/ BBT SGC | TT_FinMile | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1620 | blue | Engineering complete - (10LD) Condensate Polishing Plant | TT_FinMile | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1630 | blue | Engineering complete - (10LDK) Condensate Polishing System | TT_FinMile | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1710 | blue | Engineering complete - (10MBR) Exhaust Gas System | TT_FinMile | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1720 | blue | Engineering complete - (10EK) Fuel Gas Supply System for GT10 | TT_FinMile | 28/05/2018 | 28/05/2018 | 31/05/2018 | 31/05/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1750 | blue | Engineering complete - (10HAD10) HRSG HP Steam | TT_FinMile | 01/03/2018 | 01/03/2018 | 22/01/2018 | 22/01/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1760 | blue | Engineering complete - (10HAD50) HRSG IP Steam | TT_FinMile | 01/03/2018 | 01/03/2018 | 22/01/2018 | 22/01/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1770 | blue | Engineering complete - (10HAD80) HRSG LP Steam | TT_FinMile | 01/03/2018 | 01/03/2018 | 22/01/2018 | 22/01/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1780 | blue | Engineering complete - (10HAA) HRSG Condensate Preheating System | TT_FinMile | 01/03/2018 | 01/03/2018 | 22/01/2018 | 22/01/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1790 | blue | Engineering complete - (10HBK) HRSG Exhaust Gas System | TT_FinMile | 01/03/2018 | 01/03/2018 | 05/02/2018 | 05/02/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1800 | blue | Engineering complete - (00LBG) Auxiliary Steam System Common Area | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG1810 | blue | Engineering complete - (10GM-02) Plant Drainage System for 10U HW | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG1820 | blue | Engineering complete - (10LBH) Start-up and Shutdown Steam System incl Drains System | TT_FinMile | 01/03/2018 | 01/03/2018 | 05/02/2018 | 05/02/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1830 | blue | Engineering complete - (10LCL) HRSG Drains System | TT_FinMile | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1840 | blue | Engineering complete - (10LCA-02) Condensate Supply System incl. Preheater 10HAA10 | TT_FinMile | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1850 | blue | Engineering complete - (10LAB) HP/IP Feedwater Supply System | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG1860 | blue | Engineering complete - (10LAC) Feedwater Pump | TT_FinMile | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1870 | blue | Engineering complete - (10QCB) Hydrazine Dosing QC | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG1880 | blue | Engineering complete - (10QCC) Trisodium Phosphate Dosing QC | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG1890 | blue | Engineering complete - (10QCD) Ammonia Dosing QC | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG1900 | blue | Engineering complete - (10QU) Sampling Container QC | TT_FinMile | 01/03/2018 | 01/03/2018 | 02/03/2018 | 02/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG1920 | blue | Engineering complete - (10HSJ) Reduction Agent Supply System for SCR | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG1930 | blue | Engineering complete - (10EKT20) Fuel Gas Preheating System 10EKT20 | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG1940 | blue | Engineering complete - (10GHC) Demineralised Water Distribution System inside 10 UMC | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG1950 | blue | Engineering complete - (00GHD-01) Service Water Distribution System | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG1960 | blue | Engineering complete - (00GKB-01) Drinking Water Distribution System | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG1970 | blue | Engineering complete - (10LBA10) HP Main Steam System | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG1980 | blue | Engineering complete - (10LBA80) LP Main Steam System | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG1990 | blue | Engineering complete - (10LBB) Cold and Hot Reheat System 10LBB / 10LBC | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2000 | blue | Engineering complete - (00LBG) Auxiliary Steam System | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2010 | blue | Engineering complete - (10MAJ) ST Evacuation System | TT_FinMile | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG2020 | blue | Engineering complete - (10PAH) Condenser Tube Cleaning System | TT_FinMile | 01/03/2018 | 01/03/2018 | 23/01/2018 | 23/01/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG2030 | blue | Engineering complete - (00BZL-01) L&amp;SP incl BMZ 00 IN UBA 81 Area | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2040 | blue | Engineering complete - (10PAB-01) Circulating Water System incl. Cooling Water Pumps | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2050 | blue | Engineering complete - (00PAA) Cooling Water Screening Plant | TT_FinMile | 01/03/2018 | 01/03/2018 | 02/03/2018 | 02/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG2060 | blue | Engineering complete - (00PUR) Cathodic Protection System for Cooling Water Inlet | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2070 | blue | Engineering complete - (00PUN) Biocide Dosing System for Cooling Water | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2080 | blue | Engineering complete - (10PUR) Cathodic Protection System for Cooling Water Side of Condenser | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2100 | blue | Engineering complete - (00GM-02) Plant Drainage System for Surface Water | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2110 | blue | Engineering complete - (00GHC-02) Demineralised Water Supply System up to UMC | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2130 | blue | Engineering complete - (00MBU) NOX Water Forwarding System incl. Supply Lines to GT Skid | TT_FinMile | 01/03/2018 | 01/03/2018 | 16/03/2018 | 16/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG2140 | blue | Engineering complete - (00GHC-01) Demineralised Water Storage System | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2150 | blue | Engineering complete - (00GA) Raw Water Supply and Storage Tank 00GAC/GAD | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2160 | blue | Engineering complete - (00BZL-03) L&amp;SP incl. BMZ 00 IN USG Area | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2170 | blue | Engineering complete - (00SGA-01) Fire Pump Station, Ring Main, Outdoors Hydrants | TT_FinMile | 01/03/2018 | 01/03/2018 | 19/03/2018 | 19/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG2180 | blue | Engineering complete - (00STG) Laboratory Container STG | TT_FinMile | 01/03/2018 | 01/03/2018 | 12/03/2018 | 12/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ENG2190 | blue | Engineering complete - (00EK) Fuel Gas Conditioning System EKD (incl. Fuel Gas Supply for QHA) | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2200 | blue | Engineering complete - (10SGC-02) FF Spray Deluge Systems for 00UEH/UEJ/UEK Area | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2210 | blue | Engineering complete - (00SCB) Comprssed Air Distribution System Overall Plant | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2220 | blue | Engineering complete - (00EG-01) Fuel Oil Forwarding Station and Storage Tank | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2230 | blue | Engineering complete - (00EG-02) Fuel Oil Forwarding System incl. Supply Lines up to Fuel Oil | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2240 | blue | Engineering complete - (00BZL-02) L&amp;SP in UCA | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2250 | blue | Engineering complete - (00CR) Control Room Equipment | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2270 | blue | Engineering complete - (00CY) Communication System in 00UCA | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2280 | blue | Engineering complete - (10AC) HV Swictchgear Including Cable Connection and Lighting and Small Power | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2290 | blue | Engineering complete - (10CYE) Fire Detection System for GT Noise Enlcosure MPB | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2300 | blue | Engineering complete - (00PUS) Electro Chlorination System | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2310 | blue | Engineering complete - (10BZL-03) L&amp;SP incl. BMZ in UBA and UBF and UBE | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2320 | blue | Engineering complete - (10BZL-01) L&amp;SP incl BMZ inside 10UMC | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2330 | blue | Engineering complete - (00GM-03) Plant Drainage System Pump for UGD (incl. UGU) | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2340 | blue | Engineering complete - (00GHD-02) Service Water Distribution Inside Power Block | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2350 | blue | Engineering complete - (00GKB-02) Drinking Water Distribution Inside Power Block | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2360 | blue | Engineering complete - (10MAD) ST Bearing System | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2370 | blue | Engineering complete - (10CY) Communication / Security Systems 10 | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
ENG2380 | blue | Engineering complete - (10GM-02) Plant Drainage System for 10U MC | TT_FinMile | 02/12/2019 | 02/12/2019 | 31/10/2017 | 31/10/2017 | 0 | TK_Complete | CCGTD1_IPS
Sub-GTST-100 | red | Prepare RFQ Documentation | TT_Task | 28/02/2018 | 28/02/2018 | 28/02/2018 | 20/03/2018 | 0 | TK_Complete | CCGTD1_IPS
Sub-GTST-110 | blue | Issue RFQ Documentation | TT_FinMile | 01/03/2018 | 01/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete | CCGTD1_IPS
Sub-GTST-120 | red | RFQ Process | TT_Task | 01/03/2018 | 01/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete | CCGTD1_IPS
Sub-GTST-130 | red | Bid Technical Evaluation/Review Process | TT_Task | 01/03/2018 | 01/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete | CCGTD1_IPS
Sub-GTST-140 | red | Negoitiations with Selected Sub-Contractor | TT_Task | 15/03/2018 | 15/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete | CCGTD1_IPS
Sub-GTST-150 | blue | Award Sub-Contract Package | TT_FinMile | 28/03/2018 | 28/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete | CCGTD1_IPS
Sub-GTST-160 | red | Subcontractor Site Mobilization | TT_Task | 29/03/2018 | 29/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete | CCGTD1_IPS
Sub-GTST-170 | red | Subcontractor Submittal/Approval of Required Documentation (QA/QC, Weld Procedures, HSE, Schedules) | TT_Task | 29/03/2018 | 29/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete | CCGTD1_IPS
Sub-GTST-180 | black | GT/ST/Generator Mobilized @ Site - Commencement of Work | TT_Mile | 26/06/2018 | 26/06/2018 | 04/06/2018 | 04/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-CON-100 | red | Prepare RFQ Documentation | TT_Task | 01/03/2018 | 21/03/2018 | 24/01/2018 | 13/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-CON-110 | blue | Issue RFQ Documentation | TT_FinMile | 21/03/2018 | 21/03/2018 | 14/02/2018 | 14/02/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-CON-120 | red | RFQ Process | TT_Task | 01/03/2018 | 21/03/2018 | 15/02/2018 | 01/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-CON-130 | red | Bid Technical Evaluation/Review Process | TT_Task | 22/03/2018 | 09/04/2018 | 02/03/2018 | 07/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-CON-140 | red | Negoitiations with Selected Sub-Contractor | TT_Task | 10/04/2018 | 20/04/2018 | 08/03/2018 | 12/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-CON-150 | blue | Award Sub-Contract Package | TT_FinMile | 13/04/2018 | 13/04/2018 | 13/03/2018 | 13/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-CON-160 | red | Subcontractor Site Mobilization | TT_Task | 24/04/2018 | 30/05/2018 | 14/03/2018 | 31/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-CON-170 | red | Subcontractor Submittal/Approval of Required Documentation (QA/QC, Weld Procedures, HSE, Schedules) | TT_Task | 01/03/2018 | 28/03/2018 | 14/03/2018 | 28/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-CON-180 | black | Condenser Contractor Mobilized @ Site - Commencement of Work | TT_Mile | 02/05/2018 | 02/05/2018 | 29/03/2018 | 29/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-HRSG-100 | red | Prepare RFQ Documentation | TT_Task | 01/02/2018 | 24/02/2018 | 06/11/2017 | 24/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SUB-HRSG-110 | blue | Issue RFQ Documentation | TT_FinMile | 24/02/2018 | 24/02/2018 | 27/11/2017 | 27/11/2017 | 0 | TK_Complete | CCGTD1_IPS
SUB-HRSG-120 | red | RFQ Process | TT_Task | 26/02/2018 | 17/03/2018 | 28/11/2017 | 15/12/2017 | 0 | TK_Complete | CCGTD1_IPS
SUB-HRSG-130 | red | Bid Technical Evaluation/Review Process | TT_Task | 13/02/2018 | 01/03/2018 | 18/12/2017 | 03/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-HRSG-140 | red | Negoitiations with Selected Sub-Contractor | TT_Task | 02/03/2018 | 15/03/2018 | 04/01/2018 | 17/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-HRSG-150 | blue | Award Sub-Contract Package | TT_FinMile | 01/02/2018 | 01/02/2018 | 18/01/2018 | 18/01/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-HRSG-160 | red | HRSG Subcontractor Site Mobilization | TT_Task | 16/03/2018 | 21/03/2018 | 19/02/2018 | 07/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-HRSG-170 | red | HRSG Subcontractor Submittal/Approval of Required Documentation (QA/QC, Weld Procedures, HSE, Schedules) | TT_Task | 01/02/2018 | 10/03/2018 | 18/01/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-HRSG-180 | black | HSRG Contractor Mobilized @ Site - Commencement of Work | TT_Mile | 02/03/2018 | 02/03/2018 | 08/03/2018 | 08/03/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-BOP-160 | red | Site Mobilization (Pipe Fitter + Welder) | TT_Task | 05/09/2018 | 11/10/2018 | 28/06/2018 | 28/06/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-EIC-100 | red | Prepare RFQ Documentation | TT_Task | 26/06/2018 | 17/07/2018 | 16/04/2018 | 21/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-EIC-110 | blue | Issue RFQ Documentation | TT_FinMile | 17/07/2018 | 17/07/2018 | 23/04/2018 | 23/04/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-EIC-120 | red | RFQ Process | TT_Task | 18/07/2018 | 07/08/2018 | 23/04/2018 | 26/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-EIC-130 | red | Bid Technical Evaluation/Review Process | TT_Task | 08/08/2018 | 21/08/2018 | 07/05/2018 | 16/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-EIC-140 | red | Negotiations with Selected Sub-Contractor | TT_Task | 22/08/2018 | 04/09/2018 | 16/05/2018 | 26/05/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-EIC-150 | blue | Award Sub-Contract Package | TT_FinMile | 30/08/2018 | 30/08/2018 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-EIC-160 | red | Subcontractor Site Mobilization | TT_Task | 02/10/2018 | 05/11/2018 | 26/09/2018 | 10/10/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-EIC-170 | red | Subcontractor Submittal/Approval of Required Documentation (QA/QC, Weld Procedures, HSE, Schedules) | TT_Task | 06/09/2018 | 13/10/2018 | 05/09/2018 | 05/12/2018 | 0 | TK_Complete | CCGTD1_IPS
SUB-EIC-180 | black | EI&amp;C Contractor Mobilized @ Site - Commencement of Work | TT_Mile | 29/09/2018 | 29/09/2018 | 29/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
ECS18.1130 | red | Delivery of LV Transformer BFT01 (BHT) | TT_Task | 02/12/2019 | 03/12/2019 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 26/03/2018
ECS18.1170 | red | Delivery of LV Transformer BFT02 (BHT) | TT_Task | 02/12/2019 | 03/12/2019 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete | CCGTD1_IPS
ECS18.1210 | red | Delivery of LV Transformer BFT03 | TT_Task | 02/12/2019 | 03/12/2019 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete | CCGTD1_IPS
ECS18.1330 | red | Delivery of LV Switchgear 10BFE/10BMA | TT_Task | 02/12/2019 | 09/12/2019 | 05/04/2019 | 10/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/05/2018
ECS18.1370 | red | Delivery of PCC UBA81 &amp; Cabinet 10UBA Building | TT_Task | 30/03/2020 | 06/04/2020 | 28/03/2020 | 28/03/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 06/07/2018
ECS21.1010 | red | Delivery of SEE/ SFC Transformer | TT_Task | 26/04/2018 | 03/05/2018 | 26/04/2018 | 02/05/2018 | 0 | TK_Complete | CCGTD1_IPS
EDKS.1000 | black | Equipment Purchasing - Switchboard of fuel oil system | TT_Mile | 30/11/2019 | 30/11/2019 | 08/06/2019 | 08/06/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 23/08/2018
EDKS.1010 | black | Equipment Purchasing - Switchboard of reserved feed water system | TT_Mile | 30/11/2019 | 30/11/2019 | 08/06/2019 | 08/06/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 23/08/2018
EDS.1000 | black | Equipment Delivery by Siemens - Lighting Fixture | TT_Mile | 30/11/2019 | 30/11/2019 | 31/05/2019 | 31/05/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 18/06/2018
EDS.1010 | black | Equipment Delivery by Siemens - Batteries, Battery Charger, Converter &amp; Inverter and UPS System | TT_Mile | 26/04/2018 | 26/04/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 26/03/2018
EDS.1020 | black | Equipment Delivery by Siemens - Filter House System | TT_Mile | 30/11/2019 | 30/11/2019 | 20/04/2019 | 20/04/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 03/07/2018
EDS.1030 | black | Equipment Delivery by Siemens - Cathodic Corrosion Protection System | TT_Mile | 30/11/2019 | 30/11/2019 | 19/09/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 22/10/2018
EDS.1040 | black | Equipment Delivery by Siemens - Central Control Room Furniture and Equipment | TT_Mile | 30/11/2019 | 30/11/2019 | 15/03/2019 | 15/03/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 29/06/2018
EDS.1050 | black | Equipment Delivery by Siemens - Continuous Emission Monitoring System Equipment | TT_Mile | 30/11/2019 | 30/11/2019 | 20/05/2019 | 20/05/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 30/10/2018
EDS.1060 | black | Equipment Delivery by Siemens - Electrical, Control &amp; Instrumentation (for Gas Turbine &amp; Auxiliaries) | TT_Mile | 30/11/2019 | 30/11/2019 | 22/03/2019 | 22/03/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 07/05/2018
EDS.1070 | black | Equipment Delivery by Siemens - Electrical, Control &amp; Instrumentation (for HRSG) | TT_Mile | 30/11/2019 | 30/11/2019 | 15/05/2019 | 15/05/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 20/08/2018
EDS.1080 | black | Equipment Delivery by Siemens - Electrical, Control &amp; Instrumentation (for Generator Steam Turbine) | TT_Mile | 30/11/2019 | 30/11/2019 | 13/04/2019 | 13/04/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 17/09/2018
EDS.1090 | black | Equipment Delivery by Siemens - Electrical, Control &amp; Instrumentation (for BOP) | TT_Mile | 30/11/2019 | 30/11/2019 | 24/04/2019 | 24/04/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 03/07/2018
P1010 | blue | ST LP Outer Casing on-site | TT_FinMile | 26/04/2018 | 26/04/2018 | 02/04/2018 | 02/04/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 29/03/2018
SI---P4I40 | blue | BOP Valves on-site | TT_FinMile | 23/04/2018 | 23/04/2018 | 23/02/2018 | 23/02/2018 | 0 | TK_Complete | CCGTD1_IPS | MUST_FINISH_ON | 23/04/2018
SI-BZK4-25 | blue | MV/LV Cables (BZK) (1ST SET 30%) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 20/02/2019 | 20/02/2019 | 0 | TK_Complete | CCGTD1_IPS | MUST_FINISH_ON | 29/03/2018
SI-BZK4-52 | blue | MV Cables (BZK) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 20/02/2019 | 20/02/2019 | 0 | TK_Complete | CCGTD1_IPS | MUST_FINISH_ON | 24/07/2018
SI-BZK4-58 | blue | MV / LV Cables (BZK) (2ND SET 80%) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 11/03/2019 | 11/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 16/07/2018
SI-BZK4-60 | blue | MV/LV Cables (BZK) (3RD SET 100%) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/09/2018
SI-BZP4-25 | blue | First Cables Support System (BZP) (for Pre-Fab Modules) on-site | TT_FinMile | 14/05/2018 | 14/05/2018 | 29/12/2017 | 29/12/2017 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 14/05/2018
SI-BZP4-27 | blue | First Cables Support System (BZP) (Main) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 22/10/2018 | 22/10/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 07/06/2018
SI-BZP4B25 | blue | Second Cable Support System (BZP) (Main) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 22/10/2018 | 22/10/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 22/06/2018
SI-C--4B40 | blue | BOP I&amp;C Field Devices and Erection Material on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 10/05/2019 | 10/05/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 18/08/2018
SI-C-4C40 | blue | BOP I&amp;C Cables on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 24/04/2019 | 24/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 18/08/2018
SI-CFE4-40 | blue | CEMS on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 20/05/2019 | 20/05/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 29/08/2018
SI-CP-4-40 | blue | BOP I&amp;C Field Cabinets on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 10/10/2018 | 10/10/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 18/08/2018
SI-CR-4-40 | blue | CCR Furniture and HMI Equipment on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 10/10/2018 | 10/10/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 18/08/2018
SI-CYA4-25 | black | Equipment Delivery by Siemens - TELECOMMUNICATION CYA | TT_Mile | 30/11/2019 | 30/11/2019 | 16/04/2019 | 16/04/2019 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 06/07/2018
SI-CYE4-58 | blue | Fire Alarm System (CYE) on-site | TT_FinMile | 01/03/2018 | 01/03/2018 | 28/02/2018 | 28/02/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 28/02/2018
SI-CYP4-25 | blue | Security System (CYP) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 16/04/2019 | 16/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 06/07/2018
SI-EK-4-40 | blue | Fuel Gas Supply System (EK/EKC) on-site | TT_FinMile | 28/05/2018 | 28/05/2018 | 26/05/2018 | 26/05/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 28/05/2018
SI-EK-4-44 | blue | Fuel Gas Supply System EK (Add. Isolating Valves Only) | TT_FinMile | 30/11/2019 | 30/11/2019 | 10/06/2019 | 10/06/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 28/05/2018
SI-GHD4-62 | blue | Water Pipework System on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 31/10/2018 | 31/10/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 06/08/2018
SI-GM-4B40 | blue | Sump Pump (GM/GKB/GHD/UGU) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 14/08/2018
SI-MBH4-58 | blue | Hydrogen Supply Sytsem on site | TT_FinMile | 30/11/2019 | 30/11/2019 | 17/10/2018 | 17/10/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 31/07/2018
SI-MKG4-60 | blue | CO2 Supply System on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete | CCGTD1_IPS | MUST_FINISH_ON | 31/07/2018
SI-PAS4-66 | blue | Make-up Water Pumps (PAS) / NOX Control Water Pump on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 15/12/2018 | 15/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 30/08/2018
SI-SCB4-64 | blue | Compressed Air Interconnection system on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 02/01/2019 | 02/01/2019 | 0 | TK_Complete | CCGTD1_IPS | MUST_FINISH_ON | 27/08/2018
SI-SG-4-56 | blue | Fire Fighting Systems (SG) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 15/02/2019 | 15/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/07/2018
SI-SGA4A25 | blue | Fire Fighting Ring Main (SGA) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 23/05/2019 | 23/05/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/07/2018
SI-ZTB4A25 | blue | Steam Blow pipework (ZTB) on-site | TT_FinMile | 28/03/2020 | 28/03/2020 | 15/06/2018 | 15/06/2018 | 0 | TK_Complete | CCGTD1_IPS | MUST_FINISH_ON | 15/06/2018
SI0ACA4-25 | blue | HV Switchgear (GIL) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 10/04/2019 | 10/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 06/07/2018
SI0ACA4-45 | black | Equipment Delivery by Siemens - HV Switchgear GIL | TT_Mile | 30/11/2019 | 30/11/2019 | 10/04/2019 | 10/04/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 07/06/2018
SI0ACA4-55 | black | Equip Delivery - Feedwater Pumps LAC | TT_Mile | 30/11/2019 | 30/11/2019 | 15/02/2019 | 15/02/2019 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 31/05/2018
SI0EG-4-44 | blue | Fuel Oil Forwarding System (EG) (incl. Pumps) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 15/09/2018 | 15/09/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 25/07/2018
SI0GN-4B44 | blue | Process Drains Treatment (GN) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/06/2018
SI0PUN4-60 | blue | Electrochlorination System on-site | TT_FinMile | 28/03/2020 | 28/03/2020 | 30/08/2018 | 30/08/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 30/08/2018
SI0XKA4-25 | black | Equipment Delivery by Siemens - EMERGENCY DIESEL GENERATOR SET XKA | TT_Mile | 30/11/2019 | 30/11/2019 | 22/07/2019 | 22/07/2019 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 15/06/2018
SI1--P4A40 | black | Equipment Delivery by Siemens - Supply Piping DN &gt;=80 | TT_Mile | 30/11/2019 | 30/11/2019 | 15/09/2018 | 15/09/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 06/04/2018
SI1--P4H40 | black | Equipment Delivery by Siemens - Supply Piping DN &lt;80 | TT_Mile | 30/11/2019 | 30/11/2019 | 15/09/2018 | 15/09/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 06/04/2018
SI1BAA4-25 | black | Equipment Delivery by Siemens - Isolated Generator Busduct 10BAA | TT_Mile | 30/11/2019 | 30/11/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 08/06/2018
SI1BAC4-25 | blue | Generator Circuit Breaker (BAC) on-site | TT_FinMile | 16/03/2018 | 16/03/2018 | 15/03/2018 | 15/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 16/03/2018
SI1BAT4-25 | black | Equipment Delivery by Siemens - Main Transformer BAT | TT_Mile | 15/05/2018 | 15/05/2018 | 05/05/2018 | 05/05/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 15/05/2018
SI1BBA4-10 | black | Equipment Delivery by Siemens - MV Switchgear BBA | TT_Mile | 30/11/2019 | 30/11/2019 | 10/03/2019 | 10/03/2019 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 23/07/2018
SI1BBT4-25 | black | Equipment Delivery by Siemens - Main Transformer BBT | TT_Mile | 21/03/2018 | 21/03/2018 | 03/02/2018 | 03/02/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 21/03/2018
SI1BFA4-10 | black | Equipment Delivery by Siemens - LV/DC Switchgear BFA | TT_Mile | 30/11/2019 | 30/11/2019 | 09/04/2019 | 09/04/2019 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 16/07/2018
SI1BFT4-25 | black | Equipment Delivery by Siemens - LV Transformer BFT | TT_Mile | 26/05/2018 | 26/05/2018 | 15/05/2018 | 15/05/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 29/04/2018
SI1C--4-25 | blue | ST I&amp;C Field Instrumentation on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 15/04/2019 | 15/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 08/05/2018
SI1CHA4-10 | blue | Protection., Synchronising., Metering (CHA) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 30/04/2019 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 07/06/2018
SI1CJF4-25 | blue | HRSG Electrical &amp; I&amp;C Equipment on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 14/01/2019 | 14/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/07/2018
SI1CJT4-25 | blue | SFC/SEE Cubicle (CJT) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 27/03/2019 | 27/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 08/05/2018
SI1HA-4C25 | blue | HRSG Modules on-site | TT_FinMile | 26/04/2018 | 26/04/2018 | 30/03/2018 | 30/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 30/03/2018
SI1HA-4C40 | black | Equipment Delivery by Siemens - HRSG Modules | TT_Mile | 26/04/2018 | 26/04/2018 | 30/03/2018 | 30/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 23/03/2018
SI1HA-4D25 | blue | HRSG Drums on-site | TT_FinMile | 26/04/2018 | 26/04/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 20/04/2018
SI1HA-4D40 | black | Equipment Delivery by Siemens - Drums of HRSG | TT_Mile | 26/04/2018 | 26/04/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 23/03/2018
SI1HAD4E25 | blue | HRSG Piping Material on-site | TT_FinMile | 06/11/2018 | 06/11/2018 | 01/11/2018 | 01/11/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 18/06/2018
SI1HAD4E40 | black | Equipment Delivery by Siemens - Piping Material HRSG | TT_Mile | 06/11/2018 | 06/11/2018 | 01/10/2018 | 01/10/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 19/04/2018
SI1HB-4A25 | blue | HRSG Main Steel Structure (Main Frame/Casing) on-site | TT_FinMile | 03/03/2018 | 03/03/2018 | 08/03/2018 | 08/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/03/2018
SI1HB-4A40 | black | Equipment Delivery by Siemens - Main Steel Structure HRSG | TT_Mile | 05/03/2018 | 05/03/2018 | 03/03/2018 | 03/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 05/03/2018
SI1HB-4C25 | blue | HRSG Steel Structure - Secondary Steel on-site | TT_FinMile | 18/05/2018 | 18/05/2018 | 19/05/2018 | 19/05/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 18/05/2018
SI1HB-4D25 | blue | HRSG Steel Structure - Stack on-site | TT_FinMile | 30/08/2018 | 30/08/2018 | 29/08/2018 | 29/08/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 18/07/2018
SI1HB-4E25 | blue | HRSG Inlet Duct on-site | TT_FinMile | 01/03/2018 | 01/03/2018 | 03/03/2018 | 03/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 05/03/2018
SI1HSJ4-25 | blue | SCR Unit on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 28/06/2018
SI1HSJ4-42 | blue | SCR Catalyst on-site | TT_FinMile | 28/03/2020 | 28/03/2020 | 20/01/2020 | 20/01/2020 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 28/08/2018
SI1LAC4-40 | blue | LAC10Y Module on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 15/02/2019 | 15/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 30/05/2018
SI1LBG4C40 | blue | Electrical Superheater LBG on-site | TT_FinMile | 16/03/2018 | 16/03/2018 | 15/03/2018 | 15/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 16/03/2018
SI1LBH4D25 | blue | Clean Drain Flush Tank (LBH) on-site | TT_FinMile | 28/03/2020 | 28/03/2020 | 15/06/2018 | 15/06/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/06/2018
SI1LCA4-40 | blue | LCA50Y Module on-site | TT_FinMile | 28/03/2020 | 28/03/2020 | 27/02/2019 | 27/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 30/05/2018
SI1LCA4B25 | blue | Condensate Recirculating Pump (LCA51) on-site | TT_FinMile | 01/03/2018 | 01/03/2018 | 10/02/2018 | 10/02/2018 | 0 | TK_Complete | CCGTD1_IPS | MUST_FINISH_ON | 09/02/2018
SI1LCB4B40 | blue | Condensate Extraction Pump (LCB) on-site (arrived on June 1) | TT_FinMile | 30/11/2019 | 30/11/2019 | 10/01/2019 | 10/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 08/06/2018
SI1LCL4B40 | blue | Steam Generator Drain Pump (LCL) on-site | TT_FinMile | 16/03/2018 | 16/03/2018 | 15/03/2018 | 15/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 16/03/2018
SI1LD-4-40 | blue | Condensate Polishing Plant (LD) on-site | TT_FinMile | 28/03/2020 | 28/03/2020 | 30/04/2018 | 30/04/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 18/06/2018
SI1LDK4B40 | blue | Condensate Polishing Pump (LDK) on-site | TT_FinMile | 26/04/2018 | 26/04/2018 | 30/04/2018 | 30/04/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/04/2018
SI1MA-4-25 | black | Equipment Delivery by Siemens - STEAM TURBINE MA- (HP/IP) (incl. FCA) | TT_Mile | 26/04/2018 | 26/04/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 23/03/2018
SI1MA-4-45 | black | Equipment Delivery by Siemens - ST MA- (LP OUTER CASING) | TT_Mile | 26/04/2018 | 26/04/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 29/03/2018
SI1MA-4-55 | black | Equipment Delivery by Siemens - ST MA- (LP-ROTOR, INNERCASING) | TT_Mile | 26/04/2018 | 26/04/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 28/03/2018
SI1MA-4-59 | black | Equipment Delivery by Siemens - Steam Turbine MA- (HP/IP) AUX. (Incl. FCA) | TT_Mile | 30/08/2018 | 30/08/2018 | 31/07/2018 | 31/07/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 23/03/2018
SI1MAD4-25 | black | Equipment Delivery by Siemens - Steam Turbine Bearings MAD | TT_Mile | 01/03/2018 | 01/03/2018 | 09/01/2018 | 09/01/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 14/12/2017
SI1MAG4-40 | black | Equipment Delivery by Siemens - Steam Condenser MAG | TT_Mile | 02/04/2018 | 02/04/2018 | 02/04/2018 | 02/04/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 24/03/2018
SI1MAJ4-44 | blue | Removal System (MAJ) on-site | TT_FinMile | 02/04/2018 | 02/04/2018 | 23/03/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 18/03/2018
SI1MAL4-25 | blue | MAL00Y Module on-site | TT_FinMile | 27/04/2018 | 27/04/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 27/04/2018
SI1MAL4-40 | black | Equipment Delivery by Siemens - Steam Turbine Drain Skid MAL00Y Module | TT_Mile | 26/04/2018 | 26/04/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 14/03/2018
SI1MAV4-40 | black | Equipment Delivery by Siemens - ST Lube oil Module MAV | TT_Mile | 26/04/2018 | 26/04/2018 | 31/03/2018 | 31/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 28/03/2018
SI1MAW4-40 | black | Equipment Delivery by Siemens - ST GLAND STEAM CONDENSER MAW | TT_Mile | 26/04/2018 | 26/04/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 31/03/2018
SI1MAX4-40 | black | Equipment Delivery by Siemens - ST Hydraulic System MAX | TT_Mile | 26/04/2018 | 26/04/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 31/03/2018
SI1MB-4E25 | black | Equipment Delivery by Siemens - Gas Turbine Auxiliaries MB | TT_Mile | 30/08/2018 | 30/08/2018 | 31/07/2018 | 31/07/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 08/05/2018
SI1MB-4E27 | blue | GT Interconnection Piping (MB) on-site | TT_FinMile | 02/04/2018 | 02/04/2018 | 24/03/2018 | 24/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 21/03/2018
SI1MBA4-25 | black | Equipment Delivery by Siemens - Gas Turbine MB | TT_Mile | 26/04/2018 | 26/04/2018 | 27/03/2018 | 27/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 31/03/2018
SI1MBL4-40 | black | Equipment Delivery by Siemens - GT Air Intake System MBL | TT_Mile | 23/03/2018 | 23/03/2018 | 31/03/2018 | 31/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 31/03/2018
SI1MBR4-40 | blue | Exhaust Gas Diffuser (MBR) on-site | TT_FinMile | 01/03/2018 | 01/03/2018 | 02/03/2018 | 02/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 01/03/2018
SI1MBR4-42 | blue | Exhaust Gas Manifold (MBR) on-site | TT_FinMile | 07/03/2018 | 07/03/2018 | 10/03/2018 | 10/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 07/03/2018
SI1MKA4-25 | black | Equipment Delivery by Siemens - Generator MK | TT_Mile | 26/04/2018 | 26/04/2018 | 28/03/2018 | 28/03/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 28/03/2018
SI1MKA4E25 | black | Equipment Delivery by Siemens - Generator Skids MKA | TT_Mile | 29/09/2018 | 29/09/2018 | 01/08/2018 | 01/08/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 08/05/2018
SI1MKC4-25 | black | Equipment Delivery by Siemens - SEE TRANSFORMER MKC / SFC TRANSFORMER MBJ | TT_Mile | 26/04/2018 | 26/04/2018 | 02/05/2018 | 02/05/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 18/04/2018
SI1MPB4-25 | blue | Noise Protection System (MPB20) on-site | TT_FinMile | 30/04/2018 | 30/04/2018 | 21/03/2018 | 21/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 29/04/2018
SI1MPB4E25 | black | Equipment Delivery by Siemens - GT Enclosure Incl. Ventilation MPB/SAM | TT_Mile | 01/03/2018 | 01/03/2018 | 22/02/2018 | 22/02/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 23/02/2018
SI1PAA4-25 | blue | CW Bar Screen for (PAB) on-site | TT_FinMile | 26/05/2018 | 26/05/2018 | 29/05/2018 | 29/05/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/05/2018
SI1PAA4-40 | black | Equipment Delivery by Siemens - Cooling Water Bar Screen for PAB System | TT_Mile | 26/05/2018 | 26/05/2018 | 29/05/2018 | 29/05/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 03/05/2018
SI1PAA4-50 | black | Equipment Delivery UMC Crane | TT_Mile | 26/04/2018 | 26/04/2018 | 01/01/2018 | 01/01/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 01/03/2018
SI1PAC4B40 | blue | Circ CW Pump (PAC) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 06/07/2019 | 06/07/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 12/07/2018
SI1PAC4E40 | blue | Embedded Parts Pump (PAC) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 06/07/2019 | 06/07/2019 | 0 | TK_Complete | CCGTD1_IPS | MUST_FINISH_ON | 13/07/2018
SI1PAH4-25 | black | Equipment Delivery by Siemens - Condenser Tube Cleaning System PAH/PCH | TT_Mile | 01/03/2018 | 01/03/2018 | 17/01/2018 | 17/01/2018 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 10/02/2018
SI1PBB4B45 | blue | Debris Filter (PBB) on-site | TT_FinMile | 01/03/2018 | 01/03/2018 | 17/01/2018 | 17/01/2018 | 0 | TK_Complete | CCGTD1_IPS | MUST_FINISH_ON | 24/02/2018
SI1PCB4B25 | blue | Service Cooling Water Pump (PCB) on-site | TT_FinMile | 12/03/2018 | 12/03/2018 | 14/03/2018 | 14/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 12/03/2018
SI1PDB4-25 | blue | Debris Filer (PDB) on-site | TT_FinMile | 02/04/2018 | 02/04/2018 | 20/03/2018 | 20/03/2018 | 0 | TK_Complete | CCGTD1_IPS | MUST_FINISH_ON | 19/03/2018
SI1PGB4B25 | blue | CCW Pumps (PGB) on-site | TT_FinMile | 02/04/2018 | 02/04/2018 | 13/03/2018 | 13/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 02/03/2018
SI1PGB4C25 | blue | Heat Exchanger (PGB) on-site | TT_FinMile | 02/04/2018 | 02/04/2018 | 13/03/2018 | 13/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 12/03/2018
SI1PGB4D25 | blue | Expansion Tank (PGB) on-site | TT_FinMile | 02/04/2018 | 02/04/2018 | 20/03/2018 | 20/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 19/03/2018
SI1PXB4-40 | blue | PXB00Y Module on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 30/05/2018
SI1QC-4-40 | blue | Dosing Container (QC) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 26/02/2019 | 26/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 06/06/2018
SI1QU-4-40 | blue | Sampling Container (QU) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 26/02/2019 | 26/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 17/07/2018
SI1SCA4-40 | blue | Compressed Air System (SCA) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 02/01/2019 | 02/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 11/09/2018
SI1SGJ4-25 | black | Equipment Delivery by Siemens - Econopac fire Protection System CYE/ SGJ | TT_Mile | 30/11/2019 | 30/11/2019 | 07/03/2019 | 07/03/2019 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 08/05/2018
SI1SMM4-25 | blue | Cranes SMM01/ 02 for (UMC) on-site | TT_FinMile | 01/03/2018 | 01/03/2018 | 01/01/2018 | 01/01/2018 | 0 | TK_Complete | CCGTD1_IPS | MUST_FINISH_ON | 30/12/2017
SI1SMM4A25 | blue | Cranes SMM03 for (UMC) on-site | TT_FinMile | 01/03/2018 | 01/03/2018 | 15/01/2018 | 15/01/2018 | 0 | TK_Complete | CCGTD1_IPS | MUST_FINISH_ON | 29/01/2018
SI1SMQ4A45 | blue | Crane SMQ for UQA on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 18/05/2019 | 18/05/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 18/04/2018
SI1STG-4-44 | blue | Laboratory Container on-site STG | TT_FinMile | 30/11/2019 | 30/11/2019 | 30/04/2019 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 13/07/2018
SI1UBA4G25 | black | Equipment Delivery by Siemens - Cabinets for I&amp;C 10UBA Building | TT_Mile | 28/03/2020 | 28/03/2020 | 20/02/2019 | 20/02/2019 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 04/08/2018
SI1UHW3B25 | blue | Steel Structure (UHW) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 05/10/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 29/04/2018
SI1ULA3B25 | blue | Steel Structure (ULA) on-site | TT_FinMile | 30/11/2019 | 30/11/2019 | 15/02/2019 | 15/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 01/06/2018
SI1UMC4X40 | black | Equipment Delivery by Siemens - Module Pipe Rack UMCM1Y | TT_Mile | 26/05/2018 | 26/05/2018 | 28/05/2018 | 28/05/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 25/05/2018
SI1UMC4Y40 | black | Equipment Delivery by Siemens - Module Pipe Rack UMCL1Y | TT_Mile | 27/04/2018 | 27/04/2018 | 27/04/2018 | 27/04/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 27/04/2018
SI1UMY4-42 | blue | UMY00Y Module on-site | TT_FinMile | 29/09/2018 | 29/09/2018 | 06/09/2018 | 06/09/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 30/06/2018
SI1UPY4-40 | black | Equipment Delivery by Siemens - Condenser Tube Cleaning System PAH - Module UPY00Y | TT_Mile | 30/11/2019 | 30/11/2019 | 15/11/2018 | 15/11/2018 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 30/06/2018
SP1MA-3-80 | black | Equipment Delivery by Siemens - STEAM TURBINE MA- (HP/IP) EX WORKS | TT_Mile | 19/03/2018 | 19/03/2018 | 12/12/2017 | 12/12/2017 | 0 | TK_Complete | CCGTD1_IPS | START_ON | 19/03/2018
MWS03.1010 | red | Mobilisation of the Crane Barge to Site | TT_Task | 13/03/2018 | 10/07/2018 | 14/02/2018 | 15/03/2018 | 0 | TK_Complete | CCGTD1_IPS
MWS03.1020 | red | Mobilisation of the Land based cranes to Site | TT_Task | 01/03/2018 | 08/03/2018 | 19/03/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1000 | red | ITP for - (00BAW-01) Earthing Grid for back-energizing | TT_Task | 30/08/2018 | 24/09/2018 | 23/08/2018 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
ITP1010 | red | ITP for - (00BAW-02) Earthing Grid Complete | TT_Task | 30/08/2018 | 24/09/2018 | 23/08/2018 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
ITP1020 | red | ITP for - (00BAW-03) Lightening Protection | TT_Task | 30/08/2018 | 24/09/2018 | 23/08/2018 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
ITP1030 | red | ITP for - (10MA-01) HP-/ IP-/ LP-Turbine 10MAA/MAB/MAC | TT_Task | 02/12/2019 | 25/12/2019 | 07/05/2019 | 14/06/2019 | 0 | TK_Complete | CCGTD1_IPS
ITP1050 | red | ITP for - (10MAN) ST Bypass System | TT_Task | 30/08/2018 | 24/09/2018 | 07/06/2018 | 29/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1070 | red | ITP for - (10MAG) Condensing System | TT_Task | 10/04/2018 | 04/05/2018 | 28/02/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1080 | red | ITP for - (10MAV) Lube and Lifting Oil System Incl. Generator and GT | TT_Task | 05/07/2018 | 31/07/2018 | 09/05/2018 | 30/05/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1090 | red | ITP for - (10MAW) Gland / Leakage Steam System | TT_Task | 03/09/2018 | 26/09/2018 | 25/06/2018 | 17/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1100 | red | ITP for - (10MAX) ST Hydraulic System | TT_Task | 03/09/2018 | 26/09/2018 | 25/06/2018 | 17/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1120 | red | ITP for - (10MKA) Generator Incl. Bearing System 10 MKD | TT_Task | 02/12/2019 | 25/12/2019 | 08/05/2018 | 05/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1130 | red | ITP for - (10MKF) Generator Primary Water Cooling System | TT_Task | 03/07/2019 | 29/07/2019 | 12/05/2018 | 05/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1140 | red | ITP for - (10MKG) Gas Supply System | TT_Task | 01/08/2018 | 27/08/2018 | 12/05/2018 | 05/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1150 | red | ITP for - (10MKQ) Waste Gas System | TT_Task | 03/07/2019 | 29/07/2019 | 31/05/2018 | 14/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1160 | red | ITP for - (10MKW) Seal Oil Supply System | TT_Task | 02/07/2018 | 26/07/2018 | 11/05/2018 | 30/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1180 | red | ITP for - (10MBA) GT Including Combustion Chamber | TT_Task | 02/12/2019 | 25/12/2019 | 08/05/2018 | 14/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1190 | red | ITP for - (10MBX) GT Hydraulic Oil | TT_Task | 11/07/2018 | 03/08/2018 | 19/05/2018 | 28/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1200 | red | ITP for - (10MBP) GT Natural Gas Incl. Draining System MBP40 | TT_Task | 03/07/2019 | 29/07/2019 | 01/06/2018 | 13/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1210 | red | ITP for - (10MBN) GT Fuel Oil Injection System | TT_Task | 03/07/2019 | 29/07/2019 | 19/05/2018 | 16/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1220 | red | ITP for - (10MBH) GT Cooling Air System | TT_Task | 05/07/2018 | 31/07/2018 | 19/05/2018 | 15/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1230 | red | ITP for - (10MBA18) Compressor Cleaning Package | TT_Task | 02/12/2019 | 25/12/2019 | 13/06/2018 | 21/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1240 | red | ITP for - (10MBA5x) GT Hydraulic Clearance Optimization Supply System | TT_Task | 02/12/2019 | 25/12/2019 | 02/06/2018 | 12/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1250 | red | ITP for - (10MBX2x) GT Pneumatic System | TT_Task | 26/06/2018 | 19/07/2018 | 19/05/2018 | 28/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1280 | red | ITP for - (10MBL) Air Intake System | TT_Task | 02/12/2019 | 25/12/2019 | 07/05/2018 | 14/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1290 | red | ITP for - (10MBU) GT NOX Water Injection System | TT_Task | 02/12/2019 | 25/12/2019 | 19/05/2018 | 15/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1330 | red | ITP for - (10LCA) Main Condensate Pumps and Supply System for Min. Flow Operation Incl. | TT_Task | 17/09/2018 | 10/10/2018 | 04/06/2018 | 16/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1340 | red | ITP for - (10PGB) Closed Cooling Water System | TT_Task | 02/12/2019 | 25/12/2019 | 04/06/2018 | 09/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1350 | red | ITP for - (10PCB) Service Cooling Water System Incl. 10PDB | TT_Task | 12/11/2018 | 06/12/2018 | 04/06/2018 | 06/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1390 | red | ITP for - (10SGA) FF Indoor Hydrants 10SGA Inside 10ULA, 10UHA, 10UMC | TT_Task | 22/11/2018 | 18/12/2018 | 09/07/2018 | 27/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1400 | red | ITP for - (10SGC-02) FF Spray Deluge System 10SGC for Lube Oil / Seal Oil System | TT_Task | 13/11/2018 | 07/12/2018 | 19/07/2018 | 03/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1580 | red | ITP for - (10BAT) Main Transformer 10BAT01/10BBT01 | TT_Task | 30/08/2018 | 24/09/2018 | 16/08/2018 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
ITP1600 | red | ITP for - (10MKC) SEE/SFC Equipment Excitation Transformer MKC; SFC Transformer MBJ | TT_Task | 13/11/2018 | 06/12/2018 | 17/08/2018 | 28/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1610 | red | ITP for - (10SGC-01) FF Spary Deluge System for BAT/ BBT SGC | TT_Task | 20/03/2019 | 12/04/2019 | 19/07/2018 | 03/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1620 | red | ITP for - (10LD) Condensate Polishing Plant | TT_Task | 30/08/2018 | 24/09/2018 | 04/06/2018 | 16/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1630 | red | ITP for - (10LDK) Condensate Polishing System | TT_Task | 01/08/2018 | 27/08/2018 | 04/06/2018 | 16/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1660 | red | ITP for - (00SGM) FF Protection System for UBN | TT_Task | 28/11/2018 | 21/12/2018 | 19/07/2018 | 01/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1670 | red | ITP for - (10BFT01) LV-Transformer BFT01 (BHT) | TT_Task | 06/07/2018 | 31/07/2018 | 06/07/2018 | 18/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1680 | red | ITP for - (10BFT02) LV-Transformer BFT02 (BHT) | TT_Task | 27/11/2018 | 20/12/2018 | 03/08/2018 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
ITP1690 | red | ITP for - (00BBT) MV Transformer BBT01 | TT_Task | 27/11/2018 | 20/12/2018 | 29/08/2018 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
ITP1710 | red | ITP for - (10MBR) Exhaust Gas System | TT_Task | 10/08/2018 | 04/09/2018 | 11/05/2018 | 05/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1720 | red | ITP for - (10EK) Fuel Gas Supply System for GT10 | TT_Task | 11/07/2018 | 03/08/2018 | 22/06/2018 | 31/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1750 | red | ITP for - (10HAD10) HRSG HP Steam | TT_Task | 17/10/2018 | 09/11/2018 | 23/02/2018 | 28/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1760 | red | ITP for - (10HAD50) HRSG IP Steam | TT_Task | 17/10/2018 | 09/11/2018 | 23/02/2018 | 28/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1770 | red | ITP for - (10HAD80) HRSG LP Steam | TT_Task | 17/10/2018 | 09/11/2018 | 23/02/2018 | 28/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1790 | red | ITP for - (10HBK) HRSG Exhaust Gas System | TT_Task | 30/08/2018 | 24/09/2018 | 12/03/2018 | 28/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1830 | red | ITP for - (10LCL) HRSG Drains System | TT_Task | 15/08/2018 | 07/09/2018 | 04/06/2018 | 28/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1840 | red | ITP for - (10LCA-02) Condensate Supply System incl. Preheater 10HAA10 | TT_Task | 01/08/2018 | 27/08/2018 | 02/06/2018 | 16/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1860 | red | ITP for - (10LAC) Feedwater Pump | TT_Task | 03/07/2019 | 29/07/2019 | 02/06/2018 | 30/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1870 | red | ITP for - (10QCB) Hydrazine Dosing QC | TT_Task | 19/09/2018 | 12/10/2018 | 29/06/2018 | 07/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1880 | red | ITP for - (10QCC) Trisodium Phosphate Dosing QC | TT_Task | 19/09/2018 | 12/10/2018 | 29/06/2018 | 07/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1890 | red | ITP for - (10QCD) Ammonia Dosing QC | TT_Task | 11/10/2018 | 05/11/2018 | 29/06/2018 | 07/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP1900 | red | ITP for - (10QU) Sampling Container QC | TT_Task | 19/09/2018 | 12/10/2018 | 20/08/2018 | 11/09/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP2000 | red | ITP for - (00LBG) Auxiliary Steam System | TT_Task | 30/08/2018 | 24/09/2018 | 03/07/2018 | 08/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP2020 | red | ITP for - (10PAH) Condenser Tube Cleaning System | TT_Task | 01/08/2018 | 27/08/2018 | 12/05/2018 | 06/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP2040 | red | ITP for - (10PAB-01) Circulating Water System incl. Cooling Water Pumps | TT_Task | 26/06/2018 | 19/07/2018 | 04/06/2018 | 17/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP2050 | red | ITP for - (00PAA) Cooling Water Screening Plant | TT_Task | 30/08/2018 | 24/09/2018 | 03/08/2018 | 10/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP2060 | red | ITP for - (00PUR) Cathodic Protection System for Cooling Water Inlet | TT_Task | 12/09/2018 | 05/10/2018 | 01/06/2018 | 13/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP2080 | red | ITP for - (10PUR) Cathodic Protection System for Cooling Water Side of Condenser | TT_Task | 12/09/2018 | 05/10/2018 | 01/06/2018 | 13/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP2130 | red | ITP for - (00MBU) NOX Water Forwarding System incl. Supply Lines to GT Skid | TT_Task | 06/08/2018 | 29/08/2018 | 19/05/2018 | 15/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP2180 | red | ITP for - (00STG) Laboratory Container STG | TT_Task | 01/08/2018 | 27/08/2018 | 04/06/2018 | 17/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP2200 | red | ITP for - (10SGC-02) FF Spray Deluge Systems for 00UEH/UEJ/UEK Area | TT_Task | 13/11/2018 | 07/12/2018 | 19/07/2018 | 03/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP2220 | red | ITP for - (00EG-01) Fuel Oil Forwarding Station and Storage Tank | TT_Task | 12/09/2018 | 05/10/2018 | 25/05/2018 | 14/06/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP2230 | red | ITP for - (00EG-02) Fuel Oil Forwarding System incl. Supply Lines up to Fuel Oil | TT_Task | 26/06/2018 | 19/07/2018 | 25/05/2018 | 25/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP2360 | red | ITP for - (10MAD) ST Bearing System | TT_Task | 30/08/2018 | 24/09/2018 | 07/05/2018 | 29/08/2018 | 0 | TK_Complete | CCGTD1_IPS
ITP2390 | red | ITP for - (10HAA) HRSG | TT_Task | 09/02/2018 | 06/03/2018 | 10/01/2018 | 23/03/2018 | 0 | TK_Complete | CCGTD1_IPS
MS1050 | red | Method Statement - (10MAN) ST Bypass System | TT_Task | 30/08/2018 | 24/09/2018 | 08/06/2018 | 06/08/2018 | 0 | TK_Complete | CCGTD1_IPS
MS1070 | red | Method Statement - (10MAG) Condensing System | TT_Task | 10/04/2018 | 04/05/2018 | 02/03/2018 | 30/03/2018 | 0 | TK_Complete | CCGTD1_IPS
MS1120 | red | Method Statement - (10MKA) Generator Incl. Bearing System 10 MKD | TT_Task | 26/07/2018 | 20/08/2018 | 11/06/2018 | 26/06/2018 | 0 | TK_Complete | CCGTD1_IPS
MS1790 | red | Method Statement - (10HBK) HRSG Exhaust Gas System | TT_Task | 30/08/2018 | 24/09/2018 | 02/07/2018 | 14/07/2018 | 0 | TK_Complete | CCGTD1_IPS
MS2390 | red | Method Statement - (10HAA) HRSG | TT_Task | 09/02/2018 | 22/02/2018 | 10/01/2018 | 07/03/2018 | 0 | TK_Complete | CCGTD1_IPS
10MKB90 | red | Erect Annex Hall D5/D9/D12 Secondary Steel Structure | TT_Task | 21/01/2019 | 22/03/2019 | 21/01/2019 | 15/05/2019 | 0 | TK_Complete | CCGTD1_IPS
CP1HB-6A25 | blue | Foundations for HRSG | TT_FinMile | 01/03/2018 | 01/03/2018 | 08/03/2018 | 08/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/02/2018
CP1UMC5A45 | blue | Turboset Foundation (UMC) (Completion of Foundatio Repair) | TT_FinMile | 26/06/2018 | 26/06/2018 | 14/06/2018 | 14/06/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 01/06/2018
KD_B01 | blue | B1 - Complete Foundation Structures and Pile Caps for Stack, Diffuser and HRSG Main Plant with Lift and Staircase | TT_FinMile | 05/03/2018 | 05/03/2018 | 08/03/2018 | 08/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 05/03/2018
KD_B02 | blue | B2 - Construct Duct Bank Underneath the Diffuser | TT_FinMile | 02/04/2018 | 02/04/2018 | 07/02/2018 | 07/02/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 05/03/2018
KD_B03 | blue | B3 - Construct temp.pad foundation for heavy lift crane &amp; temp.H/O Area1a for M&amp;E Contractor (Test Complete by KSS) | TT_FinMile | 26/06/2018 | 26/06/2018 | 07/06/2018 | 07/06/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 08/06/2018
KD_B05 | blue | B5 - Construct Condensate Pit | TT_FinMile | 31/12/2018 | 31/12/2018 | 28/12/2018 | 28/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/12/2018
KD_B06 | blue | B6 - Construct Turboset foundation and supporting pile cap (Completion of Foundation Repair by Civil Contractor) | TT_FinMile | 01/06/2018 | 01/06/2018 | 14/06/2018 | 14/06/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 01/06/2018
KD_B07 | blue | B7 - Construct Pile Caps, Tie Beams&amp; GF Slab of Turbine Hall Building | TT_FinMile | 31/10/2018 | 31/10/2018 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 28/09/2018
KD_B12 | blue | HRSG East Side Urea Decomposition Chamber Foundation | TT_FinMile | 02/07/2020 | 02/07/2020 | 28/10/2019 | 28/10/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 30/03/2019
KD_C02 | blue | C2 - Complete ALL building works incl. roof &amp; cladding surrounding &amp; above Turboset main equipment area | TT_FinMile | 02/07/2020 | 02/07/2020 | 30/04/2019 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 30/04/2019
KD_C03 | blue | C3 - Construct Polishing Pit, G/F Slab for Condensate Polishing Plant area of T/H | TT_FinMile | 02/07/2020 | 02/07/2020 | 30/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 31/01/2019
KD_C04 | blue | C4 - Install and T&amp;C two 250t O/H cranes within Turbine Hall and H/O to M&amp;E Contractor | TT_FinMile | 31/08/2018 | 31/08/2018 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 31/08/2018
KD_C06 | blue | C6 - Construct Foundations &amp; Plinths for Support Steel for A/G Sections of CWP South of T/H | TT_FinMile | 02/07/2020 | 02/07/2020 | 07/03/2019 | 07/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 01/03/2019
KD_C07 | blue | C7 - Complete ALL civil works incl. foundations, pile cap, blast walls &amp; hard standings for Generator Transformer Area | TT_FinMile | 01/04/2019 | 01/04/2019 | 16/02/2019 | 16/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 14/02/2019
KD_C17 | blue | Turbine Bldg. GL 5-7 Mechanical Annex | TT_FinMile | 31/12/2018 | 31/12/2018 | 28/12/2018 | 28/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 18/12/2018
KD_C27 | blue | Turbine Bldg. GL 7-10 Condensate Polishing Plant | TT_FinMile | 02/07/2020 | 02/07/2020 | 15/02/2019 | 15/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/02/2019
KD_D01 | blue | D1 - Complete ALL remaining platforms within Turbine Hall Building (civil scope) | TT_FinMile | 31/12/2018 | 31/12/2018 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/12/2018
KD_D02 | blue | D2 - Complete ALL building works for Switchgear Block | TT_FinMile | 02/07/2020 | 02/07/2020 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 14/02/2019
KD_D04 | blue | D4 - Construct Duct Bank between Switchgear Building and Generator Transformer Area | TT_FinMile | 02/07/2020 | 02/07/2020 | 12/02/2019 | 12/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 31/01/2019
KD_D05 | blue | D5 - Construct Boiler Blow Down Pit | TT_FinMile | 31/12/2018 | 31/12/2018 | 10/11/2018 | 10/11/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 06/11/2018
KD_D06 | blue | D6 - Complete foundations and plinths for ALL equipment, pipe bridge and sleeper way to the west of HRSG Area | TT_FinMile | 31/10/2018 | 31/10/2018 | 31/10/2018 | 31/10/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 06/11/2018
KD_D07 | blue | D7 - Complete foundations and bund walls for Outdoor Dirty and Clean Oil Tanks | TT_FinMile | 02/07/2020 | 02/07/2020 | 25/04/2019 | 25/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 25/04/2019
KD_D08 | blue | D8 - Complete foundations and plinths for LV Auxiliary Power Transformers | TT_FinMile | 02/07/2020 | 02/07/2020 | 04/02/2019 | 04/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 14/02/2019
KD_D09 | blue | D9 - Complete foundation and plinths for Emergency Power Generator | TT_FinMile | 02/07/2020 | 02/07/2020 | 16/07/2019 | 16/07/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 16/07/2019
KD_D10 | blue | D10 - Complete foundation and plinths for Gas Final Filter Equipment | TT_FinMile | 02/07/2020 | 02/07/2020 | 30/04/2019 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 30/04/2019
KD_D11 | blue | D11 - Complete foundations and plinths for Close Cooling Water Structure | TT_FinMile | 02/07/2020 | 02/07/2020 | 04/03/2019 | 04/03/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 01/03/2019
KD_E01 | blue | E1 - Complete foundations and plinths for Effluent Storage Tanks | TT_FinMile | 02/07/2020 | 02/07/2020 | 25/04/2019 | 25/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 25/04/2019
KD_E02 | blue | E2 - Complete ALL outdoor pipe trenches including 10UEZ01, 10UEZ02 and 10UGZ | TT_FinMile | 02/07/2020 | 02/07/2020 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 14/02/2019
KD_E03 | blue | E3 - Complete foundation &amp; plinths for CEMS Panels, Compressed Air Sys, N2 Blanket Sys, struc.for emerg.CO2 &amp; | TT_FinMile | 31/12/2018 | 31/12/2018 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 24/12/2018
KD_E04 | blue | E4 - Complete foundation &amp; plinths for Fuel Gas Purge Air, Gas Receiving Station, Fuel Gas Blending System | TT_FinMile | 02/07/2020 | 02/07/2020 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 14/02/2019
KD_E05 | blue | E5 - Complete Foundations &amp; Plinths for Chemical Unloading Bay, Urea StorageTank, Ammonia, | TT_FinMile | 31/12/2018 | 31/12/2018 | 21/01/2019 | 21/01/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 31/12/2018
KD_E07 | blue | E7 - Complete ALL building services for Switchgear Block incl' T&amp;C | TT_FinMile | 02/07/2020 | 02/07/2020 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 14/02/2019
KD_F01 | blue | F1 - Complete Chem.Contaminated Drainage Sys incl. pipe trenches, Effluent Disposal U/G struc, Neutralization Sys | TT_FinMile | 02/07/2020 | 02/07/2020 | 25/04/2019 | 25/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 25/04/2019
KD_F02 | blue | F2 - Complete Oil Contaminated Drainage System incl' external drainage, oil interceptor and pipe trecnhes | TT_FinMile | 02/07/2020 | 02/07/2020 | 14/02/2019 | 14/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/02/2019
KD_F07 | blue | F6 - Complete Cooling Water Pumping Station and Diversion Culvert (temp access available per CLP 27 Apr 18) | TT_FinMile | 02/07/2020 | 02/07/2020 | 15/04/2019 | 15/04/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/04/2019
KD_F7 | blue | F5-Install North Section of UGP Large Dia. Intake&amp;Discharge CWP &amp; Finish Grid. for Machinery | TT_FinMile | 02/07/2020 | 02/07/2020 | 07/06/2019 | 07/06/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 15/06/2019
KD_G01 | blue | G1 - Complete Existing Supplementary Cooling Water (SCW) Intake Culvert Modification | TT_FinMile | 02/07/2020 | 02/07/2020 | 26/12/2019 | 26/12/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 03/08/2019
KD_H01 | blue | Completion of West of HRSG Foundations (incl. Condenstae Recirc Pumps) | TT_FinMile | 31/12/2018 | 31/12/2018 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 31/12/2018
KD_H02 | blue | Complete GT Diffuser Area Foundations | TT_FinMile | 02/07/2020 | 02/07/2020 | 28/02/2019 | 28/02/2019 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 28/02/2019
KD_H03 | blue | Completion of Neutralization Tank | TT_FinMile | 02/07/2020 | 02/07/2020 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 14/02/2019
TPAD0010 | blue | Temp Pad Foundation - Construct pad foundation for HRSG Heavy lift crane | TT_FinMile | 01/03/2018 | 01/03/2018 | 16/03/2018 | 16/03/2018 | 0 | TK_Complete | CCGTD1_IPS | FINISH_ON | 25/01/2018
10MAA-1000 | red | HP/IP - Clean HP Turbine and Prepare for Assembly | TT_Task | 04/10/2018 | 09/10/2018 | 12/09/2018 | 18/09/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAA-1010 | red | HP/IP - Set Down Turbine on Bearing Pedestals &amp; Provisionaly Align | TT_Task | 10/10/2018 | 18/10/2018 | 18/09/2018 | 12/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAA-1020 | red | HP/IP - Establish the Radial &amp; Axial Check Dimensions for the Shaft in Bearing Pedestals | TT_Task | 09/10/2018 | 09/10/2018 | 29/09/2018 | 12/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAA-1040 | red | HP/IP - Clean Main &amp; Auxiliary Bearings, Prepare for Assembly &amp; Install | TT_Task | 11/12/2018 | 13/12/2018 | 26/11/2018 | 07/12/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAA-1050 | red | HP/IP - Set Down Shaft in Bearings &amp; Align Shaft | TT_Task | 03/12/2018 | 11/12/2018 | 08/12/2018 | 17/12/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAA-1060 | red | HP/IP Perform Radial &amp; Axial Clearance Checks on Turbine | TT_Task | 12/12/2018 | 13/12/2018 | 22/12/2018 | 15/01/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1110 | red | Clean Turbine &amp; Generator Foundations &amp; Confirm Survey Acceptance | TT_Task | 08/08/2018 | 10/08/2018 | 23/07/2018 | 26/07/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1130 | red | Markout Reference Points for Turbine Floor Elev., Longitudinal &amp; Transverse Axis | TT_Task | 14/08/2018 | 16/08/2018 | 16/07/2018 | 26/07/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1140 | red | Install Anchor Bolts - Front HP Bearing Pedestal | TT_Task | 17/08/2018 | 17/08/2018 | 23/07/2018 | 25/07/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1150 | red | Clean Front HP Bearing Pedestal, Prepare for Assembly and Set Down on Adjusting Screws | TT_Task | 17/08/2018 | 20/08/2018 | 23/07/2018 | 26/07/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1170 | red | Install Anchor Bolts - Rear HP Bearing Pedestal | TT_Task | 17/08/2018 | 17/08/2018 | 23/07/2018 | 25/07/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1180 | red | Clean Rear HP Bearing Pedestal, Prepare for Assembly and Set Down on Adjusting Screws | TT_Task | 17/08/2018 | 24/08/2018 | 23/07/2018 | 26/07/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1200 | red | Install Anchor Bolts - Rear LP-1 Bearing Pedestal | TT_Task | 17/08/2018 | 17/08/2018 | 23/07/2018 | 26/07/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1210 | red | Clean Rear LP-1 Bearing Pedestal, Prepare for Assembly and Set Down on Adjusting Screws | TT_Task | 26/07/2018 | 01/08/2018 | 23/07/2018 | 24/08/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1220 | red | Align Front &amp; Rear HP Bearing Pedestals | TT_Task | 01/08/2018 | 06/08/2018 | 01/08/2018 | 06/08/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1230 | red | Align Rear LP-1 Bearing Pedestals | TT_Task | 30/08/2018 | 04/09/2018 | 10/08/2018 | 24/08/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1240 | red | Set-up Formwork for Grouting Front &amp; Rear HP Bearing Pedestals | TT_Task | 06/08/2018 | 08/08/2018 | 06/08/2018 | 08/08/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1250 | red | Set-up Formwork for Grouting Rear LP-1 Bearing Pedestal | TT_Task | 04/09/2018 | 07/09/2018 | 17/08/2018 | 24/08/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1260 | red | Align Check of Pedestals before Grouting | TT_Task | 25/08/2018 | 28/08/2018 | 25/08/2018 | 27/08/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1270 | red | Grout Pedestals | TT_Task | 12/09/2018 | 14/09/2018 | 25/08/2018 | 30/08/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1280 | red | Align Check of Bearing Casings &amp; Baseplates After Grouting | TT_Task | 23/08/2018 | 25/08/2018 | 23/08/2018 | 24/08/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1290 | red | Install &amp; Prealign Steel Bars for LP-1 Casing Centering Guiders in Foundation | TT_Task | 29/09/2018 | 08/10/2018 | 08/09/2018 | 19/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MA-1300 | red | Fill in Voids in Casing Centering Guides with Grout | TT_Task | 08/10/2018 | 10/10/2018 | 08/10/2018 | 19/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1000 | red | Install &amp; Prealign Steel Bar for LP-1 Casing Guider in Foundation | TT_Task | 10/10/2018 | 11/10/2018 | 08/09/2018 | 19/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1010 | red | LP-1 - Clean LP1 Side Casing &amp; End Walls, Prepare for Assembly | TT_Task | 12/10/2018 | 15/10/2018 | 06/10/2018 | 19/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1020 | red | LP-1 - LP1 Side End Walls on Supporting Arms, Align &amp; Secure, Prepare for Assembly | TT_Task | 15/10/2018 | 17/10/2018 | 22/10/2018 | 23/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1030 | red | LP-1 - Fit Bottom Plate, Align &amp; Tack Weld | TT_Task | 17/10/2018 | 22/10/2018 | 26/10/2018 | 30/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1040 | red | LP-1 - Prepare &amp; Install Side Wall | TT_Task | 31/10/2018 | 03/11/2018 | 22/10/2018 | 27/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1050 | red | LP-1 - Fit &amp; Weld Bracing Pipes for LP-1 Casing | TT_Task | 06/11/2018 | 13/11/2018 | 13/11/2018 | 26/11/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1070 | red | LP-1 - Align, Mount &amp; Bolt Down the LP-1 Casing | TT_Task | 10/11/2018 | 15/11/2018 | 24/11/2018 | 21/12/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1080 | red | LP-1 - Weld Entire LP-1 Outer Casing | TT_Task | 03/12/2018 | 12/12/2018 | 30/11/2018 | 12/12/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1090 | red | LP-1 - Remove Top Half Outer Casing, Clean, Weld &amp; Finish Joints on Joint Plane | TT_Task | 13/12/2018 | 31/12/2018 | 14/12/2018 | 14/12/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1100 | red | LP-1 - Align Bottom Half Outer Casing to Longitunal &amp; Transverse Axes &amp; Vertically | TT_Task | 14/12/2018 | 03/01/2019 | 05/11/2018 | 21/11/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1110 | red | LP-1 - Align Steel Bar for Outer Casing Guider &amp; Fill Voids w/ Grout | TT_Task | 03/01/2019 | 07/01/2019 | 24/11/2018 | 21/12/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1120 | red | LP-1 - Provisionally Mount Exp. Joints for Supporting Arm &amp; Centering Guide | TT_Task | 03/01/2019 | 09/01/2019 | 15/12/2018 | 29/12/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1130 | red | LP-1 - Set Down Bottom Half Inner Casing in Bottom Outer Casing | TT_Task | 09/01/2019 | 14/01/2019 | 21/12/2018 | 21/12/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1140 | red | LP-1 - Align Elevation &amp; Centerline of Bottom Half of Inner Casing | TT_Task | 14/01/2019 | 18/01/2019 | 22/12/2018 | 28/12/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1150 | red | LP-1 - Fix the Inner Casing Radially &amp; Axially, Check Guide Rods | TT_Task | 02/01/2019 | 08/01/2019 | 26/12/2018 | 02/01/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1160 | red | LP-1 - Clean Botton Half Shaft Seal Casing &amp; Attach to Bearing Pedestal | TT_Task | 22/01/2019 | 23/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1170 | red | LP-1 - Clean LP-1 Shaft &amp; Prepare for Assembly | TT_Task | 18/01/2019 | 21/01/2019 | 29/12/2018 | 15/01/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1180 | red | LP-1 - Clean Main &amp; Auxiliary Bearing, Prepare for Assembly &amp; Install | TT_Task | 24/01/2019 | 25/01/2019 | 31/12/2018 | 31/12/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1190 | red | LP-1 - Slide Bellow Type Expansion Joints onto LP-1 Shaft | TT_Task | 02/01/2019 | 05/01/2019 | 29/12/2018 | 29/12/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1200 | red | LP-1 - Install Turbine Shaft in Main &amp; Auxiliary Bearings &amp; Align | TT_Task | 05/01/2019 | 08/01/2019 | 04/01/2019 | 05/01/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1210 | red | LP-1 - Take Actual Radial &amp; Axial Shaft Dimensions in the Bearing Pedestals | TT_Task | 08/01/2019 | 10/01/2019 | 08/01/2019 | 14/01/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1220 | red | LP-1 - Provisionally Align Lower Section of Shaft Seal Casing to Shaft | TT_Task | 10/01/2019 | 12/01/2019 | 14/01/2019 | 22/01/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1230 | red | LP-1 - Radially &amp; Axially Align Bottom Half Inner Casing to Turbine Shaft | TT_Task | 12/01/2019 | 18/01/2019 | 14/01/2019 | 21/01/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1240 | red | LP-1 - Perform Radially &amp; Axially Blading Clearance Checks | TT_Task | 19/01/2019 | 23/01/2019 | 14/01/2019 | 21/01/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1250 | red | LP-1 - Install Guide Blade Carrier &amp; Stationary Blade Ring Upper Part | TT_Task | 24/01/2019 | 26/01/2019 | 20/01/2019 | 21/01/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1260 | red | LP-1 - Mount Outer Shell of Inner Casing &amp; Tighten Casing Joint Bolts | TT_Task | 21/01/2019 | 24/01/2019 | 15/02/2019 | 17/03/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1270 | red | LP-1 - Check Axial Displacement of Inner Casing | TT_Task | 01/04/2019 | 01/04/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1290 | red | LP-1 - Drill &amp; Ream Holes for Fitting Bolts in Joint Plane of Outer Casing | TT_Task | 01/04/2019 | 03/04/2019 | 09/03/2019 | 17/03/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1300 | red | LP-1 - Install Atmospheric Relief Diaphragm into Top Half Outer Casing | TT_Task | 18/02/2019 | 22/02/2019 | 13/12/2018 | 14/12/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1320 | red | LP-1 - Mount Top Half Cover &amp; Tighten Casing Joint Bolts | TT_Task | 04/04/2019 | 09/04/2019 | 20/03/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1330 | red | LP-1 - Pre-assemble Cross Over Pipe | TT_Task | 01/04/2019 | 29/04/2019 | 01/04/2019 | 02/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1340 | red | LP-1 - Assemble Cross Over Pipe | TT_Task | 20/06/2019 | 24/06/2019 | 20/06/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAC-1350 | red | LP-1 - Insulate Cross Over Pipe &amp; Turbine | TT_Task | 31/08/2019 | 20/09/2019 | 17/08/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1410 | red | Perform Preliminary Alignment of Shaft Assembly in Operating Position | TT_Task | 28/01/2019 | 31/01/2019 | 09/01/2019 | 12/01/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1420 | red | Alignment - Generator to Steam Turbine/Gas Turbine to Generator | TT_Task | 01/02/2019 | 08/02/2019 | 14/01/2019 | 12/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1430 | red | Assembly of Shifting Clutch | TT_Task | 26/01/2019 | 30/01/2019 | 30/01/2019 | 01/02/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1440 | red | Common Coupling Alignment at Steam Turbine/Generator/Gas Turbine | TT_Task | 30/01/2019 | 08/02/2019 | 11/02/2019 | 03/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1450 | red | Draw Together HP/LP Coupling, Ream &amp; Hone Coupling Holes, Finish Grind Coupling Holes | TT_Task | 08/02/2019 | 14/02/2019 | 18/02/2019 | 02/03/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1460 | red | Couple HP &amp; LP1 Shafts Checking Radial Run-Out of Coupling Flanges | TT_Task | 14/02/2019 | 16/02/2019 | 02/03/2019 | 07/03/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1470 | red | Check The Radial Clearance of the LP1 Inner Casing by Means of Adjusting Screws | TT_Task | 30/01/2019 | 01/02/2019 | 30/01/2019 | 04/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1480 | red | Check Radial Run-Out of FInal Stage of Outer Shell of LP Casing | TT_Task | 01/02/2019 | 02/02/2019 | 09/03/2019 | 11/03/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1490 | red | Correct the Alignment of LP Inner Casing if Necessary &amp; Mount Fitted Keys for Casing Support | TT_Task | 01/02/2019 | 09/02/2019 | 01/02/2019 | 09/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1500 | red | Align LP1 Bottom Half Shaft Seal Casing to Coupled Shaft Assembly | TT_Task | 09/02/2019 | 12/02/2019 | 20/03/2019 | 11/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1510 | red | Check Radial Clearance of LP1 Shaft Seal | TT_Task | 30/04/2019 | 30/04/2019 | 10/04/2019 | 24/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1520 | red | Place Cover on LP Shaft Seal Casing Ready for Operations - Fabricate to Size &amp; Insert Fitted Keys | TT_Task | 02/05/2019 | 06/05/2019 | 20/05/2019 | 21/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1530 | red | If Necessary - Realign HP Casing to Coupled Shaft Assembly, Level off Brack Supports | TT_Task | 17/04/2019 | 20/04/2019 | 17/04/2019 | 24/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1540 | red | Install &amp; Align Shaft Turning Gear (Electric Motor) | TT_Task | 07/05/2019 | 08/05/2019 | 29/04/2019 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1550 | red | Machine to Size &amp; Install Fitted Keys for HP Casing Guide | TT_Task | 07/05/2019 | 09/05/2019 | 20/05/2019 | 28/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1560 | red | Machine to Size &amp; Install Shim Plates for HP Turbine Bracket &amp; Support | TT_Task | 10/05/2019 | 11/05/2019 | 10/05/2019 | 31/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1570 | red | Establish Clearance @ Front HP Bearing Pedestal | TT_Task | 13/05/2019 | 14/05/2019 | 13/05/2019 | 14/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1580 | red | Install Vibration Sensors in Bearing Pedestals | TT_Task | 01/08/2019 | 16/08/2019 | 19/07/2019 | 27/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1590 | red | Install Sealing Rings in Front/Rear HP &amp; Rear LP1 Bearing Pedestals | TT_Task | 20/05/2019 | 23/05/2019 | 30/04/2019 | 02/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1600 | red | Prepare Front/Rear HP &amp; Rear LP1 Bearing Pedestals for Flushing | TT_Task | 25/04/2019 | 03/05/2019 | 25/04/2019 | 07/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1605 | blue | Power Available for Oil Flushing | TT_FinMile | 30/04/2019 | 30/04/2019 | 30/04/2019 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1610 | red | Steam Turbine Ready for Oil FLushing | TT_Task | 07/06/2019 | 07/06/2019 | 20/05/2019 | 20/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1620 | red | Steam Turbine Lube Oil Flushing | TT_Task | 08/06/2019 | 02/07/2019 | 29/05/2019 | 21/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1630 | red | Re-assembly after Lube Oil Flush | TT_Task | 17/06/2019 | 26/06/2019 | 22/06/2019 | 06/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1650 | red | Closing of Bearing Pedestals | TT_Task | 09/07/2019 | 19/07/2019 | 13/07/2019 | 27/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1660 | red | E &amp; IC Installation | TT_Task | 03/06/2019 | 13/07/2019 | 13/05/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA-1670 | red | Pre-Commissioning - (10MA-01) HP/IP/LP Turbine | TT_Task | 09/09/2019 | 17/09/2019 | 06/09/2019 | 16/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAV10 | red | Install Equipment/Skids/Pumps | TT_Task | 29/09/2018 | 11/10/2018 | 14/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAV1001 | red | Set Lube Oil Module into Position - Skid | TT_Task | 29/09/2018 | 05/10/2018 | 14/09/2018 | 30/09/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAV20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 12/01/2019 | 08/03/2019 | 07/01/2019 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAV30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 08/02/2019 | 01/04/2019 | 08/02/2019 | 23/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAV40 | red | NDE | TT_Task | 01/03/2019 | 10/04/2019 | 01/03/2019 | 28/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAV50 | red | EC+I | TT_Task | 05/06/2019 | 02/07/2019 | 21/05/2019 | 06/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAV60 | red | Line Inspection | TT_Task | 31/05/2019 | 04/06/2019 | 12/06/2019 | 15/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAV70 | red | Hydro Test | TT_Task | 29/06/2019 | 02/07/2019 | 20/07/2019 | 19/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAV75 | blue | Lube Oil System Ready for Flushing | TT_FinMile | 06/06/2019 | 06/06/2019 | 27/05/2019 | 27/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAV80 | red | Painting/Insulation | TT_Task | 08/06/2019 | 18/06/2019 | 08/05/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAV90 | red | Pre-Commissioning | TT_Task | 31/08/2019 | 12/09/2019 | 20/08/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAX10 | red | Install Equipment/Skids/Pumps | TT_Task | 31/10/2018 | 05/11/2018 | 03/10/2018 | 05/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAX100 | red | Flush ST Hydraulic Piping | TT_Task | 09/09/2019 | 16/09/2019 | 09/09/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAX110 | red | Reconfigure ST Hydraulic Piping after Flushing] | TT_Task | 30/09/2019 | 08/10/2019 | 05/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAX20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 08/02/2019 | 15/03/2019 | 15/12/2018 | 25/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAX30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 08/04/2019 | 17/05/2019 | 08/04/2019 | 04/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAX40 | red | NDE | TT_Task | 08/04/2019 | 17/05/2019 | 17/04/2019 | 16/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAX50 | red | EC+I | TT_Task | 30/04/2019 | 08/06/2019 | 07/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAX60 | red | Line Inspection | TT_Task | 31/07/2019 | 05/08/2019 | 26/08/2019 | 29/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAX70 | red | Hydro Test | TT_Task | 04/09/2019 | 07/09/2019 | 04/09/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAX80 | red | Painting/Insulation | TT_Task | 11/06/2019 | 29/06/2019 | 07/05/2019 | 09/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAX90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 24/09/2019 | 28/09/2019 | 24/09/2019 | 09/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA1400 | red | Install &amp; Align Main Stop &amp; Control Valves | TT_Task | 04/04/2019 | 24/04/2019 | 09/04/2019 | 17/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA1410 | red | Install &amp; Align RH Stop &amp; Control Valves | TT_Task | 13/04/2019 | 04/05/2019 | 13/04/2019 | 21/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA1420 | red | Install &amp; Align Steam Supply Valves &amp; Bolt | TT_Task | 10/06/2019 | 28/06/2019 | 15/06/2019 | 22/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA1430 | red | Installation of all Actuators for MS, RH, LP | TT_Task | 18/06/2019 | 15/07/2019 | 11/06/2019 | 22/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA1450 | red | E&amp;IC Installation ST Stop and Control Valves | TT_Task | 26/06/2019 | 05/08/2019 | 21/06/2019 | 31/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MA1460 | red | Pre-Commissioning | TT_Task | 31/08/2019 | 11/09/2019 | 02/09/2019 | 11/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAN1000 | red | Attach Spring Supports for By Pass Valve | TT_Task | 31/05/2019 | 05/06/2019 | 10/06/2019 | 21/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAN1010 | red | Install By Pass Valves | TT_Task | 06/06/2019 | 14/06/2019 | 21/06/2019 | 31/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAN1020 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 25/04/2019 | 24/05/2019 | 25/04/2019 | 31/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAN1050 | red | NDE | TT_Task | 30/04/2019 | 29/05/2019 | 15/05/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAN1060 | red | EC+I | TT_Task | 07/06/2019 | 06/07/2019 | 24/05/2019 | 25/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAN1070 | red | Line Inspection &amp; Preparation for Neutral Float Welds | TT_Task | 02/08/2019 | 09/08/2019 | 10/08/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAN1075 | red | Neutral Float &amp; Final Weld Connections to Bypass Control Valves | TT_Task | 11/07/2019 | 24/07/2019 | 22/07/2019 | 31/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAN1080 | red | Hydro Test | TT_Task | 21/08/2019 | 02/09/2019 | 31/08/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAN1085 | red | Close-out Insulation after Neutral Float Welds | TT_Task | 07/09/2019 | 18/09/2019 | 07/09/2019 | 07/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAN1090 | red | Painting/Insulation | TT_Task | 29/06/2019 | 20/07/2019 | 25/06/2019 | 26/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAN110 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 18/09/2019 | 30/09/2019 | 07/09/2019 | 26/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAW10 | red | Install Gland Steam Condenser (MAW) | TT_Task | 01/04/2019 | 04/04/2019 | 12/04/2019 | 15/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAW100 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 11/09/2019 | 19/09/2019 | 11/09/2019 | 12/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAW30 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 30/04/2019 | 11/05/2019 | 10/05/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAW40 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 18/04/2019 | 23/05/2019 | 18/04/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAW50 | red | NDE | TT_Task | 25/05/2019 | 18/06/2019 | 14/05/2019 | 24/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAW60 | red | EC+I | TT_Task | 05/06/2019 | 11/07/2019 | 27/06/2019 | 24/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAW70 | red | Line Inpsection | TT_Task | 14/08/2019 | 21/08/2019 | 23/08/2019 | 30/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAW80 | red | Hydro Test | TT_Task | 22/08/2019 | 29/08/2019 | 24/08/2019 | 31/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAW90 | red | Painting/Insulation | TT_Task | 05/06/2019 | 22/06/2019 | 18/06/2019 | 12/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAL10 | red | Install Steam Turbine Drain Module (MAL00Y) | TT_Task | 24/10/2018 | 29/10/2018 | 01/08/2018 | 22/09/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAL10a | red | Resolution of Foundation Embedment problem (Civil Issue) | TT_Task | 29/09/2018 | 23/10/2018 | 29/09/2018 | 20/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MAL20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 06/04/2019 | 11/05/2019 | 09/04/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAL30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 27/04/2019 | 01/06/2019 | 27/04/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAL40 | red | NDE | TT_Task | 28/05/2019 | 26/06/2019 | 21/05/2019 | 25/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAL50 | red | EC+I | TT_Task | 12/06/2019 | 03/07/2019 | 12/06/2019 | 27/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAL60 | red | Line Inspection | TT_Task | 31/08/2019 | 04/09/2019 | 10/09/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAL70 | red | Hydro Test | TT_Task | 30/09/2019 | 04/10/2019 | 05/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAL80 | red | Painting/Insulation | TT_Task | 05/06/2019 | 19/07/2019 | 23/05/2019 | 12/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAL90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 10/09/2019 | 19/09/2019 | 10/09/2019 | 12/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAJ10 | red | Install Equipment/Skids/Pumps | TT_Task | 06/04/2019 | 13/04/2019 | 08/04/2019 | 07/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAJ20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 13/04/2019 | 08/05/2019 | 15/04/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAJ30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 23/04/2019 | 17/05/2019 | 23/04/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAJ40 | red | NDE | TT_Task | 11/05/2019 | 07/06/2019 | 11/05/2019 | 25/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAJ50 | red | EC+I | TT_Task | 28/05/2019 | 19/06/2019 | 15/05/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAJ60 | red | Line Inspection | TT_Task | 14/08/2019 | 20/08/2019 | 21/08/2019 | 31/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAJ70 | red | Hydro Test | TT_Task | 30/09/2019 | 08/10/2019 | 05/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAJ80 | red | Painting/Insulation | TT_Task | 14/06/2019 | 28/06/2019 | 17/06/2019 | 07/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MAJ90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 11/09/2019 | 19/09/2019 | 11/09/2019 | 07/11/2019 | 0 | TK_Complete | CCGTD1_IPS
A1620 | red | Set up and Check Condenser Foundations | TT_Task | 18/04/2018 | 21/04/2018 | 16/04/2018 | 18/04/2018 | 0 | TK_Complete | CCGTD1_IPS
A1630 | red | Placing and Alignment of Support Plates | TT_Task | 02/04/2019 | 04/04/2019 | 02/04/2019 | 04/04/2019 | 0 | TK_Complete | CCGTD1_IPS
A1640 | red | Fitting and Welding of Fixing and Guide Points | TT_Task | 07/05/2018 | 09/05/2018 | 28/04/2018 | 04/05/2018 | 0 | TK_Complete | CCGTD1_IPS
A1650 | red | Placing Hotwell | TT_Task | 07/05/2018 | 07/05/2018 | 05/05/2018 | 19/05/2018 | 0 | TK_Complete | CCGTD1_IPS
A1660 | red | Assembly and Welding of Condensate Drain Tank | TT_Task | 04/06/2018 | 08/06/2018 | 02/06/2018 | 05/06/2018 | 0 | TK_Complete | CCGTD1_IPS
A1670 | red | Placing Steam Shell (lower part) and Connection Weld | TT_Task | 23/05/2018 | 02/06/2018 | 22/05/2018 | 23/05/2018 | 0 | TK_Complete | CCGTD1_IPS
A1680 | red | Placing, Aligning and Grouting of Vacuum Pumps | TT_Task | 01/04/2019 | 12/04/2019 | 04/04/2019 | 07/06/2019 | 0 | TK_Complete | CCGTD1_IPS
A1690 | red | Installing Protective Covers for Cooling Tubes | TT_Task | 26/07/2018 | 28/07/2018 | 11/06/2018 | 13/06/2018 | 0 | TK_Complete | CCGTD1_IPS
A1700 | red | Alignment of Condenser Steam Shell | TT_Task | 16/08/2018 | 17/08/2018 | 22/05/2018 | 25/05/2018 | 0 | TK_Complete | CCGTD1_IPS
A1710 | black | Condenser Ready for Preassembling Piping | TT_Mile | 29/09/2018 | 29/09/2018 | 31/08/2018 | 31/08/2018 | 0 | TK_Complete | CCGTD1_IPS
A1720 | red | Assembly and Welding of Condenser Neck | TT_Task | 17/08/2018 | 13/09/2018 | 15/06/2018 | 31/08/2018 | 0 | TK_Complete | CCGTD1_IPS
A1730 | red | Fitting and Welding of Guide Bolts and Stiffening Plates | TT_Task | 13/09/2018 | 26/09/2018 | 17/06/2018 | 21/01/2019 | 0 | TK_Complete | CCGTD1_IPS
A1740 | red | Installing and Wedling of Seismic Tie Down | TT_Task | 04/04/2019 | 09/04/2019 | 04/04/2019 | 10/04/2019 | 0 | TK_Complete | CCGTD1_IPS
A1750 | red | Assemble and Weld Nozzles into Steam Dome | TT_Task | 29/09/2018 | 13/10/2018 | 03/09/2018 | 15/10/2018 | 0 | TK_Complete | CCGTD1_IPS
A1760 | red | Vacuum Test Water Side | TT_Task | 31/12/2018 | 02/01/2019 | 11/12/2018 | 09/01/2019 | 0 | TK_Complete | CCGTD1_IPS
A1770 | red | Check Corrosion Protection on CW Side | TT_Task | 02/01/2019 | 19/01/2019 | 14/01/2019 | 21/01/2019 | 0 | TK_Complete | CCGTD1_IPS
A1780 | red | Fitting and Bolting of Front and Rear Coverwith Seal | TT_Task | 12/10/2018 | 20/10/2018 | 03/06/2018 | 13/06/2018 | 0 | TK_Complete | CCGTD1_IPS
A1790 | red | Connection and Welding of Rear Cover | TT_Task | 01/04/2019 | 09/04/2019 | 03/04/2019 | 11/04/2019 | 0 | TK_Complete | CCGTD1_IPS
A1800 | black | Condenser Ready for PAB Piping | TT_Mile | 04/05/2019 | 04/05/2019 | 04/05/2019 | 04/05/2019 | 0 | TK_Complete | CCGTD1_IPS
A1810 | red | Fitting of Condenser to LP Turbine | TT_Task | 30/01/2019 | 18/02/2019 | 30/01/2019 | 04/05/2019 | 0 | TK_Complete | CCGTD1_IPS
A1820 | red | Welding of Condenser to LP Turbine | TT_Task | 19/02/2019 | 22/02/2019 | 19/02/2019 | 22/02/2019 | 0 | TK_Complete | CCGTD1_IPS
A1830 | red | Floating of Bypass Station | TT_Task | 31/05/2019 | 11/06/2019 | 22/06/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
A1840 | red | Assembly and Welding of Condenser Neck Structure | TT_Task | 03/09/2018 | 13/09/2018 | 15/06/2018 | 30/07/2018 | 0 | TK_Complete | CCGTD1_IPS
A1850 | red | Grouting of Condenser Shell Support Structure Seismic Tie | TT_Task | 02/02/2019 | 12/02/2019 | 26/03/2019 | 11/04/2019 | 0 | TK_Complete | CCGTD1_IPS
A1860 | red | Final Works and Cleaning | TT_Task | 11/04/2019 | 16/04/2019 | 11/04/2019 | 29/06/2019 | 0 | TK_Complete | CCGTD1_IPS
A1870 | red | Final Inspection | TT_Task | 12/07/2019 | 15/07/2019 | 20/07/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
A1880 | red | Insulation Condenser | TT_Task | 15/07/2019 | 24/08/2019 | 13/07/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
A1890 | red | Placing and Alignment of Sliding Supports | TT_Task | 26/01/2019 | 29/01/2019 | 15/03/2019 | 03/05/2019 | 0 | TK_Complete | CCGTD1_IPS
A2590 | red | Piping Installation MAG | TT_Task | 04/05/2019 | 08/06/2019 | 04/05/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
A3350 | red | Prepare ground to South of Condenser for 750T crane | TT_Task | 25/04/2018 | 03/05/2018 | 26/04/2018 | 03/05/2018 | 0 | TK_Complete | CCGTD1_IPS
A3360 | black | Hand back area South of Condenser to Civil Contractor | TT_Mile | 15/06/2018 | 15/06/2018 | 25/06/2018 | 25/06/2018 | 0 | TK_Complete | CCGTD1_IPS
A3370 | blue | Turbine Hall Grid Line 8-10 made available by Civil Contractor | TT_FinMile | 30/04/2019 | 30/04/2019 | 03/05/2019 | 03/05/2019 | 0 | TK_Complete | CCGTD1_IPS
A3380 | red | Pressure Test Condenser | TT_Task | 18/10/2019 | 29/10/2019 | 18/10/2019 | 29/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA10 | red | Installation of Condensate Extraction Pump - Skid | TT_Task | 02/01/2019 | 12/01/2019 | 10/01/2019 | 06/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA100 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 31/08/2019 | 11/09/2019 | 07/09/2019 | 05/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA20 | red | Install Condensate Recirculation Pump Skid (LCA50Y Module) | TT_Task | 28/02/2019 | 13/03/2019 | 27/02/2019 | 28/02/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA30 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 12/01/2019 | 03/04/2019 | 12/01/2019 | 17/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA40 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 30/04/2019 | 05/06/2019 | 06/05/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA50 | red | NDE | TT_Task | 30/04/2019 | 05/06/2019 | 08/04/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA60 | red | E &amp;IC Erection Cond Recirc Pump | TT_Task | 01/04/2019 | 17/05/2019 | 15/04/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA70 | red | Line Inspection | TT_Task | 03/08/2019 | 13/08/2019 | 05/08/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA80 | red | Hydro Test | TT_Task | 13/08/2019 | 23/08/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA90 | red | Painting/Insulation | TT_Task | 19/06/2019 | 08/07/2019 | 07/06/2019 | 05/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA-02-10 | red | Install Equipment/Skids/Pumps | TT_Task | 01/04/2019 | 08/05/2019 | 02/04/2019 | 10/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA-02-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 22/03/2019 | 29/06/2019 | 07/01/2019 | 24/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA-02-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 21/06/2019 | 16/07/2019 | 07/05/2019 | 25/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA-02-40 | red | NDE | TT_Task | 08/07/2019 | 16/07/2019 | 13/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA-02-50 | red | EC+I | TT_Task | 27/05/2019 | 06/06/2019 | 26/04/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA-02-60 | red | Line Inspection | TT_Task | 31/07/2019 | 10/08/2019 | 05/07/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA-02-70 | red | Hydro Test | TT_Task | 12/08/2019 | 22/08/2019 | 15/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA-02-80 | red | Painting/Insulation | TT_Task | 31/05/2019 | 29/06/2019 | 18/06/2019 | 11/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCA-02-90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 07/09/2019 | 20/09/2019 | 07/09/2019 | 11/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LD-10 | red | Install Equipment/Skids/Pumps | TT_Task | 16/02/2019 | 22/03/2019 | 25/03/2019 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10LD-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 16/04/2019 | 06/06/2019 | 16/04/2019 | 24/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LD-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 15/05/2019 | 29/06/2019 | 26/04/2019 | 24/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LD-40 | red | NDE | TT_Task | 10/05/2019 | 26/06/2019 | 10/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LD-50 | red | EC+I | TT_Task | 03/07/2019 | 25/07/2019 | 30/04/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LD-60 | red | Line Inspection | TT_Task | 14/08/2019 | 22/08/2019 | 24/08/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LD-70 | red | Hydro Test | TT_Task | 30/09/2019 | 04/10/2019 | 19/10/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10LD-80 | red | Painting/Insulation | TT_Task | 10/07/2019 | 07/08/2019 | 20/07/2019 | 09/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10LD-90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 12/09/2019 | 21/09/2019 | 12/09/2019 | 09/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10LDK-10 | red | Install Equipment/Skids/Pumps | TT_Task | 16/02/2019 | 04/03/2019 | 25/03/2019 | 15/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10LDK-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 15/04/2019 | 31/05/2019 | 15/04/2019 | 22/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LDK-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 29/05/2019 | 28/06/2019 | 14/05/2019 | 22/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LDK-40 | red | NDE | TT_Task | 30/05/2019 | 06/07/2019 | 16/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LDK-50 | red | EC+I | TT_Task | 21/06/2019 | 02/08/2019 | 14/06/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LDK-60 | red | Line Inspection | TT_Task | 05/08/2019 | 13/08/2019 | 24/08/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LDK-70 | red | Hydro Test | TT_Task | 30/09/2019 | 04/10/2019 | 25/10/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LDK-80 | red | Painting/Insulation | TT_Task | 18/07/2019 | 05/08/2019 | 20/07/2019 | 26/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LDK-90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 21/09/2019 | 30/09/2019 | 14/09/2019 | 26/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBL1000 | red | Pre-assemble of Air Intake System | TT_Task | 15/02/2019 | 04/03/2019 | 25/03/2019 | 26/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBL1010 | red | Installation of Air Inlet Duct (Inlet Plenum Damper and Transition piece) | TT_Task | 15/05/2019 | 06/06/2019 | 13/05/2019 | 22/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBL1020 | red | Set Air Inlet Duct Lower Plenum on Foundation MBL | TT_Task | 15/04/2019 | 27/04/2019 | 15/04/2019 | 03/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBL1030 | red | Installation of Air Inlet Duct (Remaining) | TT_Task | 06/06/2019 | 02/07/2019 | 15/05/2019 | 31/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBL1040 | red | Installation of Air Intake Cone and Filters | TT_Task | 01/06/2019 | 26/06/2019 | 20/04/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBL1050 | red | Insulation Anti Icing MBL | TT_Task | 12/07/2019 | 06/08/2019 | 03/06/2019 | 24/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBL1060 | red | E&amp;IC MBL | TT_Task | 29/04/2019 | 14/06/2019 | 29/04/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBL1070 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 31/08/2019 | 19/09/2019 | 07/09/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBL1080 | red | Install Filter House Support Steel | TT_Task | 01/04/2019 | 10/05/2019 | 23/01/2019 | 28/02/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBL1090 | red | Install Filter House | TT_Task | 01/04/2019 | 10/05/2019 | 01/04/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBL1100 | red | Installation of Inlet Air Duct Support Platform | TT_Task | 01/04/2019 | 18/04/2019 | 01/04/2019 | 11/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBL1110 | red | Lower Half Secondary Air Piping | TT_Task | 27/04/2019 | 04/05/2019 | 27/04/2019 | 06/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBL1120 | red | Set Exhaust Manifold | TT_Task | 26/10/2018 | 31/10/2018 | 05/09/2018 | 27/09/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBL1130 | red | Complete Steel Work for Inlet Air System | TT_Task | 01/04/2019 | 27/04/2019 | 01/03/2019 | 06/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1000 | red | Check Foundation | TT_Task | 30/08/2018 | 03/09/2018 | 08/08/2018 | 08/09/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1020 | red | Lower Support Block Centering Guide to Foundation Pit | TT_Task | 11/10/2018 | 15/10/2018 | 15/09/2018 | 15/09/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1030 | red | Install &amp; Grout Compressor Supports | TT_Task | 16/10/2018 | 20/10/2018 | 13/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1035 | red | Position Support Bridge | TT_Task | 17/10/2018 | 17/10/2018 | 17/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1040 | red | Install &amp; Grout Turbine Supports Blocks | TT_Task | 22/10/2018 | 26/10/2018 | 17/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1050 | red | Install Turbine Supports | TT_Task | 23/10/2018 | 24/10/2018 | 17/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1060 | red | Set Combustion Turbine | TT_Task | 03/11/2018 | 07/11/2018 | 03/10/2018 | 06/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1067 | red | GT Enclosure Installation | TT_Task | 21/01/2019 | 16/04/2019 | 21/01/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1070 | red | Align Support Block Centering Guide | TT_Task | 07/11/2018 | 09/11/2018 | 14/09/2018 | 15/09/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1080 | red | Grout Support Block Centering Guide | TT_Task | 09/11/2018 | 12/11/2018 | 09/10/2018 | 10/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1090 | red | Align Combustion Turbine to Foundation Axis | TT_Task | 12/11/2018 | 15/11/2018 | 06/10/2018 | 10/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1100 | blue | Generator in Position - Interface Date | TT_FinMile | 08/10/2018 | 08/10/2018 | 04/10/2018 | 04/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1110 | red | Install Weld Support Bridge &amp; Clamps for Fuel Gas Manifolds | TT_Task | 27/04/2019 | 03/05/2019 | 20/04/2019 | 26/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1120 | red | Install Intermediate Shaft &amp; Center to Combustion Turbine | TT_Task | 28/12/2018 | 31/12/2018 | 16/11/2018 | 21/11/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1130 | red | Install Clamps for Fuel Gas Manifolds | TT_Task | 28/12/2018 | 04/01/2019 | 26/10/2018 | 15/11/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1140 | red | Install Secondary Air Piping System | TT_Task | 18/04/2019 | 27/04/2019 | 30/11/2018 | 12/01/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1150 | red | Install Fuel Gas Manifold Pilot Gas | TT_Task | 04/01/2019 | 09/01/2019 | 06/11/2018 | 16/11/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1160 | black | Ready for Pre-assembling Pipework MBA/MBP/ MBX/ EKG Piping | TT_Mile | 25/03/2019 | 25/03/2019 | 01/01/2019 | 01/01/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1170 | red | Install Fuel Gas Manifold Stages A/B/C/D | TT_Task | 09/01/2019 | 15/01/2019 | 06/11/2018 | 16/11/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1180 | red | E &amp; IC Erection of GT | TT_Task | 02/04/2019 | 06/06/2019 | 22/03/2019 | 11/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1190 | red | Common Coupling Alignment GT/GEN/ST | TT_Task | 27/04/2019 | 10/05/2019 | 05/03/2019 | 12/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1200 | red | Align &amp; Welding Spur of the Support Block of Centering Guide | TT_Task | 30/01/2019 | 01/02/2019 | 10/10/2018 | 11/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA1210 | red | Insulate Compressor Vane Carrier | TT_Task | 31/07/2019 | 06/08/2019 | 24/08/2019 | 03/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1220 | red | Weld Lugs of Compressor Supports | TT_Task | 01/04/2019 | 08/04/2019 | 26/03/2019 | 08/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1230 | red | Weld &amp; Pretension Turbine Supports | TT_Task | 08/04/2019 | 11/04/2019 | 08/04/2019 | 11/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1260 | red | Connect Exhaust Gas Line to Exhaust Gas Diffuser | TT_Task | 11/04/2019 | 16/04/2019 | 15/03/2019 | 23/03/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1270 | red | Install Actuators for Vane Pitch Controllers (IGV/VGv1/2/3) | TT_Task | 07/06/2019 | 14/06/2019 | 12/06/2019 | 25/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1280 | red | Check Alignment of Shaft Assembly | TT_Task | 11/04/2019 | 15/04/2019 | 25/03/2019 | 11/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1290 | red | Complete Insulation Installation | TT_Task | 30/04/2019 | 23/07/2019 | 24/05/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1300 | red | Position &amp; Align Coupling Flanges, Bore Out &amp; Hone Bolt Holes | TT_Task | 12/04/2019 | 23/04/2019 | 12/04/2019 | 26/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1310 | red | Install Compressor Bearing Cover &amp; Shaft Turning Gear Unit | TT_Task | 27/04/2019 | 30/04/2019 | 26/03/2019 | 31/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1320 | red | Install Shaft Position Sensors for HCO System | TT_Task | 31/07/2019 | 01/08/2019 | 24/08/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1330 | red | Install Speed Measuring Facilities | TT_Task | 01/08/2019 | 02/08/2019 | 28/08/2019 | 31/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1340 | red | Install Vibration Sensors | TT_Task | 02/08/2019 | 05/08/2019 | 28/08/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1350 | red | GT Encl E&amp;IC Installation Incl Lighting | TT_Task | 20/05/2019 | 06/06/2019 | 20/05/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1360 | red | Gas Turbine FInal Check | TT_Task | 03/10/2019 | 12/10/2019 | 14/09/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA1370 | red | Completion of Gas Turbine | TT_Task | 26/10/2019 | 04/11/2019 | 28/09/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBR1000 | red | Installation of Exhaust Gas Support /Steelwork | TT_Task | 01/03/2019 | 23/03/2019 | 01/03/2019 | 23/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBR1010 | red | Installation of Exhaust Gas System Diffuser Casing &amp; Transition Piece | TT_Task | 06/05/2019 | 30/05/2019 | 16/05/2019 | 23/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBR1020 | red | Final Installation of Exhaust Gas Diffuser Expansion Jt (After Final Train Alignment) | TT_Task | 18/04/2019 | 28/05/2019 | 18/03/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBR1030 | red | Grout Exhaust Gas Diffuser Supports | TT_Task | 31/08/2019 | 04/09/2019 | 24/09/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBH10 | red | Install Equipment/Skids/Pumps | TT_Task | 01/04/2019 | 09/04/2019 | 08/04/2019 | 10/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBH20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 01/04/2019 | 06/05/2019 | 01/04/2019 | 06/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBH30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 09/05/2019 | 01/06/2019 | 09/05/2019 | 06/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBH40 | red | NDE | TT_Task | 15/05/2019 | 13/06/2019 | 15/05/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBH50 | red | EC+I | TT_Task | 24/06/2019 | 15/07/2019 | 01/06/2019 | 13/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBH60 | red | Line Inspection | TT_Task | 06/09/2019 | 11/09/2019 | 16/09/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBH70 | red | Hydro Test | TT_Task | 30/09/2019 | 04/10/2019 | 21/09/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBH80 | red | Painting/Insulation | TT_Task | 16/08/2019 | 21/08/2019 | 10/08/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBH90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 17/09/2019 | 23/09/2019 | 07/09/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBN10 | red | Install Equipment/Skids/Pumps | TT_Task | 08/04/2019 | 25/04/2019 | 06/04/2019 | 07/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBN20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 21/01/2019 | 11/03/2019 | 21/01/2019 | 22/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBN30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 01/04/2019 | 06/05/2019 | 04/04/2019 | 03/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBN40 | red | NDE | TT_Task | 23/04/2019 | 22/05/2019 | 23/04/2019 | 17/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBN50 | red | EC+I | TT_Task | 30/04/2019 | 04/06/2019 | 08/05/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBN60 | red | Line Inspection | TT_Task | 04/09/2019 | 07/09/2019 | 14/09/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBN70 | red | Hydro Test | TT_Task | 30/09/2019 | 04/10/2019 | 26/10/2019 | 26/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBN80 | red | Painting/Insulation | TT_Task | 21/06/2019 | 10/07/2019 | 13/06/2019 | 06/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBN90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 17/09/2019 | 24/09/2019 | 07/09/2019 | 06/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBP10 | red | Install Fuel Gas Equipment/Skids | TT_Task | 06/04/2019 | 25/04/2019 | 09/04/2019 | 23/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBP20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 23/05/2019 | 19/06/2019 | 15/05/2019 | 25/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBP30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 07/06/2019 | 26/06/2019 | 24/05/2019 | 25/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBP40 | red | NDE | TT_Task | 22/05/2019 | 26/06/2019 | 22/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBP50 | red | EC+I | TT_Task | 25/06/2019 | 19/07/2019 | 24/06/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBP60 | red | Line Inspection | TT_Task | 07/09/2019 | 12/09/2019 | 17/09/2019 | 20/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBP70 | red | Hydro Test | TT_Task | 30/09/2019 | 04/10/2019 | 22/10/2019 | 24/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBP80 | red | Painting/Insulation | TT_Task | 25/06/2019 | 13/07/2019 | 13/06/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBP90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 18/09/2019 | 24/09/2019 | 14/09/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX05 | red | Set Equipment/Skids/Pumps | TT_Task | 08/04/2019 | 09/04/2019 | 06/04/2019 | 05/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX10 | red | Final nstall Equipment/Skids/Pumps | TT_Task | 14/06/2019 | 18/06/2019 | 01/06/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX100 | red | Final Pipe Connections to Skid | TT_Task | 17/06/2019 | 19/06/2019 | 17/06/2019 | 03/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 01/04/2019 | 27/04/2019 | 02/04/2019 | 04/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 23/04/2019 | 17/05/2019 | 23/04/2019 | 06/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX40 | red | NDE | TT_Task | 16/04/2019 | 13/05/2019 | 16/04/2019 | 10/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX50 | red | EC+I | TT_Task | 31/05/2019 | 26/06/2019 | 01/06/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX60 | red | Line Inspection | TT_Task | 12/08/2019 | 16/08/2019 | 27/08/2019 | 04/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX70 | red | Hydro Test | TT_Task | 16/08/2019 | 28/08/2019 | 29/08/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX80 | red | Painting/Insulation | TT_Task | 30/04/2019 | 24/05/2019 | 06/05/2019 | 13/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 28/08/2019 | 11/09/2019 | 31/08/2019 | 13/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBV1000 | red | Set GT Lube Oil Package into Position - Skid | TT_Task | 29/09/2018 | 29/09/2018 | 14/09/2018 | 29/09/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBV1010 | red | Install Equipment/Skids/Pumps | TT_Task | 30/11/2018 | 07/12/2018 | 10/10/2018 | 11/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBV1020 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 19/02/2019 | 08/05/2019 | 07/01/2019 | 20/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBV1030 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 08/02/2019 | 26/03/2019 | 18/03/2019 | 25/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBV1040 | red | NDE | TT_Task | 03/04/2019 | 25/04/2019 | 03/04/2019 | 25/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBV1050 | red | EC+I | TT_Task | 27/05/2019 | 18/06/2019 | 27/05/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBV1060 | red | Line Inspection | TT_Task | 10/06/2019 | 13/06/2019 | 04/06/2019 | 08/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBV1080 | red | Painting/Insulation | TT_Task | 31/05/2019 | 18/06/2019 | 21/05/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBV1083 | black | Temporary Power Available for GT Lube Oil Flush &amp; Restore | TT_Mile | 31/05/2019 | 31/05/2019 | 24/05/2019 | 24/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBV1085 | red | GT Lube Oil/Lifting Flush &amp; Restore | TT_Task | 31/05/2019 | 22/06/2019 | 20/06/2019 | 13/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBV1090 | red | Pre-Commissioning/Cleaning | TT_Task | 06/09/2019 | 17/09/2019 | 06/09/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX2x05 | red | Set Pneumatic Skid Package into Position | TT_Task | 01/04/2019 | 02/04/2019 | 03/04/2019 | 11/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX2x10 | red | Install Equipment/Skids/Pumps | TT_Task | 03/06/2019 | 11/06/2019 | 15/05/2019 | 25/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX2x20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 02/04/2019 | 30/04/2019 | 02/04/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX2x30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 09/04/2019 | 08/05/2019 | 09/04/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX2x40 | red | NDE | TT_Task | 25/05/2019 | 12/06/2019 | 25/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX2x50 | red | EC+I | TT_Task | 24/06/2019 | 24/07/2019 | 01/06/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX2x60 | red | Line Inspection | TT_Task | 04/09/2019 | 09/09/2019 | 04/09/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX2x70 | red | Hydro Test | TT_Task | 09/09/2019 | 17/09/2019 | 21/09/2019 | 27/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX2x80 | red | Painting/Insulation | TT_Task | 16/07/2019 | 08/08/2019 | 26/07/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBX2x90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 17/09/2019 | 24/09/2019 | 14/09/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA5x05 | red | Set Hydraulic Clearance Optimization Package into Position | TT_Task | 08/04/2019 | 09/04/2019 | 06/04/2019 | 06/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA5x10 | red | Install Equipment/Skids/Pumps | TT_Task | 08/04/2019 | 16/04/2019 | 08/04/2019 | 04/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA5x20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 13/04/2019 | 07/05/2019 | 13/04/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA5x30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 13/04/2019 | 07/05/2019 | 13/04/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA5x40 | red | NDE | TT_Task | 10/05/2019 | 28/05/2019 | 10/05/2019 | 27/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA5x50 | red | EC+I | TT_Task | 21/05/2019 | 13/06/2019 | 21/05/2019 | 13/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA5x60 | red | Line Inspection | TT_Task | 31/08/2019 | 04/09/2019 | 07/09/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA5x70 | red | Hydro Test | TT_Task | 30/09/2019 | 15/10/2019 | 30/09/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA5x80 | red | Painting/Insulation | TT_Task | 01/06/2019 | 26/06/2019 | 20/05/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA5x90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 19/09/2019 | 09/10/2019 | 07/09/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA4x10 | red | Install Equipment/Skids/Pumps | TT_Task | 31/12/2018 | 15/01/2019 | 31/12/2018 | 11/01/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA4x20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 01/04/2019 | 23/04/2019 | 01/04/2019 | 10/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA4x30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 15/05/2019 | 25/05/2019 | 15/05/2019 | 10/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA4x40 | red | NDE | TT_Task | 21/05/2019 | 31/05/2019 | 21/05/2019 | 13/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA4x50 | red | EC+I | TT_Task | 10/07/2019 | 20/07/2019 | 10/07/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA4x60 | red | Line Inspection | TT_Task | 22/07/2019 | 31/07/2019 | 22/07/2019 | 31/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA4x70 | red | Hydro Test | TT_Task | 31/07/2019 | 09/08/2019 | 01/06/2019 | 15/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA4x80 | red | Painting/Insulation | TT_Task | 10/07/2019 | 30/07/2019 | 11/05/2019 | 23/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA4x90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 10/08/2019 | 20/08/2019 | 15/06/2019 | 22/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBU10 | red | Install Equipment/Skids/Pumps | TT_Task | 24/01/2019 | 08/02/2019 | 15/12/2018 | 20/12/2018 | 0 | TK_Complete | CCGTD1_IPS
00MBU20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 18/02/2019 | 12/04/2019 | 12/02/2019 | 06/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBU30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 27/05/2019 | 21/06/2019 | 27/05/2019 | 08/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBU40 | red | NDE | TT_Task | 10/06/2019 | 21/06/2019 | 28/05/2019 | 13/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBU50 | red | E&amp;IC Installation MBU | TT_Task | 08/07/2019 | 18/07/2019 | 08/07/2019 | 18/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBU60 | red | Line Inspection | TT_Task | 31/07/2019 | 08/08/2019 | 01/06/2019 | 08/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBU70 | red | Hydro Test | TT_Task | 09/08/2019 | 19/08/2019 | 15/06/2019 | 22/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBU80 | red | Painting/Insulation | TT_Task | 31/07/2019 | 08/08/2019 | 01/06/2019 | 08/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBU90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 20/08/2019 | 30/08/2019 | 22/06/2019 | 13/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBU10 | red | Install Equipment/Skids/Pumps | TT_Task | 01/03/2019 | 02/04/2019 | 15/12/2018 | 23/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBU20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 24/04/2019 | 14/05/2019 | 24/04/2019 | 06/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBU30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 25/04/2019 | 16/05/2019 | 25/04/2019 | 08/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBU40 | red | NDE | TT_Task | 10/05/2019 | 15/05/2019 | 10/05/2019 | 10/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBU50 | red | EC+I | TT_Task | 08/07/2019 | 24/07/2019 | 08/07/2019 | 24/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBU60 | red | Line Inspection | TT_Task | 10/07/2019 | 20/07/2019 | 10/07/2019 | 12/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBU70 | red | Hydro Test | TT_Task | 20/07/2019 | 02/08/2019 | 13/07/2019 | 17/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBU80 | red | Painting/Insulation | TT_Task | 05/07/2019 | 13/07/2019 | 05/07/2019 | 24/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBU90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 31/07/2019 | 13/08/2019 | 08/06/2019 | 15/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA18-100 | red | Set Compressor Cleaning Package into Position -Skid | TT_Task | 31/10/2018 | 05/11/2018 | 26/10/2018 | 30/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MBA18-110 | red | Final Align Compressor Cleaning Package and final pipe connections | TT_Task | 18/06/2019 | 26/06/2019 | 08/06/2019 | 03/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA18-120 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 01/04/2019 | 06/05/2019 | 01/04/2019 | 05/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA18-130 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 23/04/2019 | 22/05/2019 | 23/04/2019 | 05/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA18-140 | red | NDE | TT_Task | 06/05/2019 | 29/05/2019 | 06/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA18-150 | red | EC+I | TT_Task | 29/05/2019 | 12/06/2019 | 23/05/2019 | 11/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA18-160 | red | Line Inspection | TT_Task | 04/09/2019 | 05/09/2019 | 16/09/2019 | 18/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA18-170 | red | Hydro Test | TT_Task | 06/09/2019 | 09/09/2019 | 19/09/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA18-180 | red | Painting/Insulation | TT_Task | 29/05/2019 | 03/06/2019 | 23/05/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MBA18-190 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 10/09/2019 | 12/09/2019 | 21/09/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10QFB10 | red | Install Equipment/Skids/Pumps | TT_Task | 29/06/2019 | 05/07/2019 | 29/06/2019 | 05/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10QFB20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 04/05/2019 | 22/06/2019 | 02/01/2019 | 06/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10QFB30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 04/07/2019 | 17/07/2019 | 04/07/2019 | 17/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10QFB40 | red | NDE | TT_Task | 10/07/2019 | 17/07/2019 | 10/07/2019 | 19/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10QFB50 | red | EC+I | TT_Task | 18/07/2019 | 09/08/2019 | 10/07/2019 | 27/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10QFB60 | red | Line Inspection | TT_Task | 10/07/2019 | 17/07/2019 | 10/07/2019 | 17/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10QFB70 | red | Hydro Test | TT_Task | 31/07/2019 | 03/08/2019 | 22/06/2019 | 29/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10QFB80 | red | Painting/Insulation | TT_Task | 13/07/2019 | 26/07/2019 | 13/07/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10QFB90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 05/08/2019 | 12/08/2019 | 29/06/2019 | 12/11/2019 | 0 | TK_Complete | CCGTD1_IPS
TWS06.2520 | red | Installation of Ventilation System for Gas Turbine Enclosure and Skid Enclosures | TT_Task | 30/04/2019 | 28/06/2019 | 09/05/2019 | 26/09/2019 | 0 | TK_Complete | CCGTD1_IPS
FSS22.1180 | red | Installation of Fire Detection System for GT Noise Enclosure MPB | TT_Task | 01/07/2019 | 11/09/2019 | 13/07/2019 | 08/01/2020 | 0 | TK_Complete | CCGTD1_IPS
A1900 | red | Set on Base Boiler Blowdown Vessel | TT_Task | 13/11/2018 | 13/11/2018 | 06/11/2018 | 08/11/2018 | 0 | TK_Complete | CCGTD1_IPS
A1910 | red | Tie In Works to BD Vessel | TT_Task | 06/05/2019 | 28/05/2019 | 06/05/2019 | 13/06/2019 | 0 | TK_Complete | CCGTD1_IPS
A2380 | red | Erection Main Piperack Structure (UMY00Y Modules) | TT_Task | 20/11/2018 | 07/12/2018 | 07/11/2018 | 30/11/2018 | 0 | TK_Complete | CCGTD1_IPS
ECS20.1100 | red | Erection of Boiler Platforms and Ladders | TT_Task | 17/10/2018 | 28/12/2018 | 15/09/2018 | 25/03/2019 | 0 | TK_Complete | CCGTD1_IPS
ECS20.1180 | red | Erection of Inlet Duct | TT_Task | 11/10/2018 | 09/01/2019 | 16/10/2018 | 29/03/2019 | 0 | TK_Complete | CCGTD1_IPS
ECS20.1200 | red | Pressure Test Walkdowns and Prep | TT_Task | 14/06/2019 | 27/06/2019 | 14/05/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
ECS20.1220 | red | PWHT HRSG Casing roof beams | TT_Task | 26/06/2018 | 12/07/2018 | 23/06/2018 | 14/07/2018 | 0 | TK_Complete | CCGTD1_IPS
ECS20.1230 | red | Completion Works at Roof Beams - NDE, Roof Beam Seam Welds, Painting, Insulation + Liner Plates, Modify | TT_Task | 09/07/2018 | 19/07/2018 | 15/07/2018 | 26/07/2018 | 0 | TK_Complete | CCGTD1_IPS
HRS09.1020 | red | Installation of Main Steel Structure HRSG (Main Frame / Casing) without PWHT of roof beams | TT_Task | 03/04/2018 | 13/06/2018 | 06/04/2018 | 22/06/2018 | 0 | TK_Complete | CCGTD1_IPS
HRS09.1030 | red | Preparation of Foundations and installation of Sole Plates | TT_Task | 06/03/2018 | 15/03/2018 | 12/03/2018 | 23/04/2018 | 0 | TK_Complete | CCGTD1_IPS
HRS10.1010 | black | First Del to pad of Modules (Heating Surfaces) | TT_Mile | 20/07/2018 | 20/07/2018 | 24/07/2018 | 24/07/2018 | 0 | TK_Complete | CCGTD1_IPS
HRS10.1020 | red | Alignment and Installation of Modules (Heating Surfaces) | TT_Task | 20/07/2018 | 20/08/2018 | 27/07/2018 | 08/09/2018 | 0 | TK_Complete | CCGTD1_IPS
HRS10.1020a | red | Resolve Row 2 Support Beam Issue / SPMT Working on Stack Delivery | TT_Task | 30/08/2018 | 15/09/2018 | 18/08/2018 | 31/08/2018 | 0 | TK_Complete | CCGTD1_IPS
HRS10.1050 | red | Installation of Supports &amp; Drums of HRSG | TT_Task | 15/10/2018 | 25/10/2018 | 20/09/2018 | 27/10/2018 | 0 | TK_Complete | CCGTD1_IPS
HRS10.1060 | black | HRSG Structure Ready for Modules &amp; Drums | TT_Mile | 26/06/2018 | 26/06/2018 | 26/06/2018 | 26/06/2018 | 0 | TK_Complete | CCGTD1_IPS
HRS10.1070 | red | Modules Welding | TT_Task | 06/11/2018 | 28/11/2018 | 01/11/2018 | 30/11/2018 | 0 | TK_Complete | CCGTD1_IPS
HRS10.1080 | blue | Civil Contractor H/O West Side of HRSG back | TT_FinMile | 06/11/2018 | 06/11/2018 | 06/11/2018 | 06/11/2018 | 0 | TK_Complete | CCGTD1_IPS
HRS10.1090 | blue | Punchlist &amp; Final Completion of HRSG Foundation Works - Prepare Pockets for GL11 Sole Plates | TT_FinMile | 24/07/2018 | 24/07/2018 | 18/04/2018 | 18/04/2018 | 0 | TK_Complete | CCGTD1_IPS
HRS10.1100 | red | Erect Stair Towers | TT_Task | 26/05/2018 | 19/07/2018 | 11/06/2018 | 29/10/2018 | 0 | TK_Complete | CCGTD1_IPS
HRS10.1110 | blue | Civil Contractor H/O Inlet Duct Foundation | TT_FinMile | 06/11/2018 | 06/11/2018 | 15/10/2018 | 15/10/2018 | 0 | TK_Complete | CCGTD1_IPS
HRS11.1170 | red | Installation of HRSG Piping | TT_Task | 06/11/2018 | 13/05/2019 | 07/11/2018 | 28/05/2019 | 0 | TK_Complete | CCGTD1_IPS
HRS11.1200 | red | Reconfigure Post Hydro Test | TT_Task | 02/10/2019 | 24/10/2019 | 19/10/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS
HRS12.1000 | red | Completion of the HRSG ready to start Piping | TT_Task | 19/10/2018 | 24/10/2018 | 12/10/2018 | 24/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10HAD80-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 10/12/2018 | 05/04/2019 | 23/11/2018 | 25/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD80-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 21/02/2019 | 07/05/2019 | 21/02/2019 | 14/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD80-40 | red | NDE | TT_Task | 25/01/2019 | 07/05/2019 | 23/11/2018 | 18/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD80-50 | red | EC+I | TT_Task | 15/06/2019 | 22/07/2019 | 18/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD80-60 | red | Line Inspection | TT_Task | 07/06/2019 | 12/06/2019 | 13/05/2019 | 17/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD80-70 | red | Hydro Test with HRSG | TT_Task | 27/06/2019 | 04/07/2019 | 18/05/2019 | 25/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD80-80 | red | Painting/Insulation | TT_Task | 15/06/2019 | 17/07/2019 | 18/05/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD80-90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 25/09/2019 | 09/10/2019 | 07/09/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD50-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 10/12/2018 | 05/04/2019 | 09/11/2018 | 22/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD50-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 12/02/2019 | 26/04/2019 | 09/11/2018 | 14/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD50-40 | red | NDE | TT_Task | 05/03/2019 | 24/04/2019 | 09/11/2018 | 18/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD50-50 | red | EC+I | TT_Task | 15/06/2019 | 27/07/2019 | 15/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD50-60 | red | Line Inspection | TT_Task | 15/06/2019 | 25/06/2019 | 15/06/2019 | 25/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD50-70 | red | Hydro Test with HRSG | TT_Task | 28/06/2019 | 13/07/2019 | 21/06/2019 | 13/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD50-80 | red | Painting/Insulation | TT_Task | 15/06/2019 | 17/07/2019 | 13/05/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD50-90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 06/09/2019 | 21/09/2019 | 07/09/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD10-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 10/12/2018 | 30/04/2019 | 08/11/2018 | 17/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD10-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 23/02/2019 | 26/04/2019 | 08/11/2018 | 14/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD10-40 | red | NDE | TT_Task | 01/02/2019 | 22/03/2019 | 30/04/2019 | 20/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD10-50 | red | EC+I | TT_Task | 15/06/2019 | 20/07/2019 | 20/05/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD10-60 | red | Line Inspection | TT_Task | 27/06/2019 | 16/07/2019 | 27/06/2019 | 06/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD10-70 | red | Hydro Test with HRSG | TT_Task | 02/09/2019 | 12/09/2019 | 30/08/2019 | 26/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD10-80 | red | Painting/Insulation | TT_Task | 31/05/2019 | 29/06/2019 | 31/05/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAD10-90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 24/10/2019 | 05/11/2019 | 05/10/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAA10 | red | Install Equipment/Skids/Pumps | TT_Task | 24/05/2019 | 04/06/2019 | 23/05/2019 | 10/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAA20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 10/12/2018 | 02/02/2019 | 10/12/2018 | 21/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAA30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 17/04/2019 | 28/05/2019 | 17/01/2019 | 25/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAA40 | red | NDE | TT_Task | 17/04/2019 | 28/05/2019 | 10/12/2018 | 27/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAA50 | red | EC+I | TT_Task | 28/06/2019 | 22/07/2019 | 15/05/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAA60 | red | Line Inspection | TT_Task | 25/06/2019 | 08/07/2019 | 25/06/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAA70 | red | Hydro Test | TT_Task | 11/07/2019 | 24/07/2019 | 13/07/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAA80 | red | Painting/Insulation | TT_Task | 28/06/2019 | 23/07/2019 | 17/05/2019 | 11/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10HAA90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 17/09/2019 | 30/09/2019 | 09/09/2019 | 11/11/2019 | 0 | TK_Complete | CCGTD1_IPS
ADD_BY_CLP_01 | red | Insulation of Stack + Complete Outlet Duct | TT_Task | 30/04/2019 | 06/08/2019 | 13/05/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
ECS20.1190 | red | Erection of Stack | TT_Task | 15/10/2018 | 15/04/2019 | 31/08/2018 | 20/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCL20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 08/02/2019 | 06/05/2019 | 08/02/2019 | 27/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCL30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 04/03/2019 | 30/05/2019 | 04/03/2019 | 25/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCL40 | red | NDE | TT_Task | 25/03/2019 | 11/06/2019 | 25/03/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCL50 | red | EC+I | TT_Task | 18/06/2019 | 23/07/2019 | 08/06/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCL60 | red | Line Inspection | TT_Task | 08/07/2019 | 17/07/2019 | 03/08/2019 | 07/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCL70 | red | Hydro Test | TT_Task | 05/08/2019 | 15/08/2019 | 05/08/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCL80 | red | Painting/Insulation | TT_Task | 21/05/2019 | 22/06/2019 | 21/05/2019 | 15/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LCL90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 05/09/2019 | 18/09/2019 | 07/09/2019 | 15/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10CFE10 | red | Skid/Panels/Cabinets Installation | TT_Task | 18/06/2019 | 05/07/2019 | 20/05/2019 | 14/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10CFE100 | red | Cable Raceway | TT_Task | 28/03/2019 | 18/04/2019 | 15/03/2019 | 20/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10CFE110 | red | Cable | TT_Task | 20/06/2019 | 09/07/2019 | 01/06/2019 | 10/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10CFE120 | red | Tubing | TT_Task | 14/06/2019 | 06/07/2019 | 14/06/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CFE130 | red | Instrumentation | TT_Task | 31/07/2019 | 19/08/2019 | 20/07/2019 | 20/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10CFE150 | red | Installation CEMS equiptment on Stack | TT_Task | 14/06/2019 | 26/07/2019 | 14/06/2019 | 06/09/2019 | 0 | TK_Complete | CCGTD1_IPS
ECS20.1050 | red | Installation of Cable Support Structure for HRSG | TT_Task | 24/04/2019 | 20/07/2019 | 24/04/2019 | 29/06/2019 | 0 | TK_Complete | CCGTD1_IPS
ECS20.1060 | red | Installation &amp; Termination of Power &amp; Control Cable for HRSG | TT_Task | 24/05/2019 | 12/08/2019 | 24/05/2019 | 26/06/2019 | 0 | TK_Complete | CCGTD1_IPS
ECS20.1070 | red | Installation of Distribution Panel &amp; Control Panel and Racks for HRSG | TT_Task | 24/04/2019 | 10/06/2019 | 24/04/2019 | 22/06/2019 | 0 | TK_Complete | CCGTD1_IPS
ECS20.1080 | red | Installation of Instrumentation for HRSG | TT_Task | 01/04/2019 | 10/06/2019 | 22/04/2019 | 28/06/2019 | 0 | TK_Complete | CCGTD1_IPS
ECS20.1110 | red | Installation &amp; Termination of Cable for Lighting Fittings for HRSG | TT_Task | 25/02/2019 | 24/04/2019 | 14/01/2019 | 27/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1000 | red | Set Up Equipment on Site | TT_Task | 29/09/2018 | 08/10/2018 | 20/08/2018 | 22/08/2018 | 0 | TK_Complete | CCGTD1_IPS
10MKA1010 | red | Check and Prep of Foundation | TT_Task | 30/08/2018 | 12/09/2018 | 22/08/2018 | 23/08/2018 | 0 | TK_Complete | CCGTD1_IPS
10MKA1020 | red | Prepare Generator and Lower onto Foundation | TT_Task | 23/10/2018 | 29/10/2018 | 22/09/2018 | 24/09/2018 | 0 | TK_Complete | CCGTD1_IPS
10MKA1030 | black | Commence Weekly Winding Insulation Resistance Checks | TT_Mile | 31/10/2018 | 31/10/2018 | 25/10/2018 | 25/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MKA1050 | red | Shift Generator into Position | TT_Task | 23/10/2018 | 24/10/2018 | 26/09/2018 | 04/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MKA1070 | red | Recording the Axial Adjustment of the Shaft System | TT_Task | 31/12/2018 | 17/01/2019 | 14/01/2019 | 28/02/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1080 | red | Installation and Coupling of Collector Rotor, Swing Check, Decoupling | TT_Task | 01/04/2019 | 12/04/2019 | 05/04/2019 | 27/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1090 | blue | Inspections, Electrical Installations &amp; Tests Begin | TT_FinMile | 12/04/2019 | 12/04/2019 | 12/04/2019 | 12/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1095 | red | EC&amp;I | TT_Task | 13/04/2019 | 25/05/2019 | 15/04/2019 | 04/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1100 | blue | Checking Instrumentaion and Commissioning Seal Oil System Begin | TT_FinMile | 12/04/2019 | 12/04/2019 | 12/04/2019 | 12/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1105 | blue | Release for Connection of Piping to The Generator | TT_FinMile | 10/04/2019 | 10/04/2019 | 10/04/2019 | 10/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1120 | red | Install Isophase Supports | TT_Task | 31/12/2018 | 08/01/2019 | 03/01/2019 | 08/01/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1130 | red | Install Bushings | TT_Task | 09/01/2019 | 19/01/2019 | 21/01/2019 | 01/02/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1140 | blue | Release for Bus Bar Interface at the Terminal Bushing | TT_FinMile | 01/04/2019 | 01/04/2019 | 01/04/2019 | 01/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1150 | red | Removal of Transport Covers, Installation of Frame Covers | TT_Task | 16/03/2019 | 19/03/2019 | 20/10/2018 | 25/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MKA1160 | red | Install H2 Shaft Seals | TT_Task | 07/11/2018 | 24/11/2018 | 19/11/2018 | 20/12/2018 | 0 | TK_Complete | CCGTD1_IPS
10MKA1170 | red | Common Coupling Alignment GT/Gen/ST (with Installed Clutch) | TT_Task | 02/02/2019 | 13/03/2019 | 14/01/2019 | 12/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1190 | red | Fix Generator into Position | TT_Task | 11/02/2019 | 21/02/2019 | 11/02/2019 | 21/02/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1200 | red | Grouting the Generator Foundation Beams | TT_Task | 25/02/2019 | 06/03/2019 | 07/03/2019 | 07/03/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1210 | red | Coupling of Collector Rotor | TT_Task | 22/02/2019 | 25/02/2019 | 15/02/2019 | 09/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1220 | blue | Release for Coupling of the Gas Turbine | TT_FinMile | 11/04/2019 | 11/04/2019 | 11/04/2019 | 11/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1230 | red | Assembling of Collector | TT_Task | 10/04/2019 | 26/04/2019 | 10/04/2019 | 12/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1240 | red | Removal of Dessicant Bags (Timing to Start - TBE) | TT_Task | 31/08/2019 | 02/09/2019 | 15/06/2019 | 15/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1250 | red | Generator Leak Test | TT_Task | 04/10/2019 | 08/10/2019 | 07/09/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1260 | red | Install Bearing Bracket Oil Seals TE/EE | TT_Task | 03/05/2019 | 06/05/2019 | 03/05/2019 | 06/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1270 | red | Install Grounding Brushes | TT_Task | 07/05/2019 | 07/05/2019 | 10/08/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1280 | red | Install Coupling Cover | TT_Task | 03/06/2019 | 04/06/2019 | 25/06/2019 | 08/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKA1290 | red | Pre-Commissioning/Cleaning | TT_Task | 09/10/2019 | 16/10/2019 | 14/09/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKW10 | red | Install Equipment/Skids/Pumps | TT_Task | 15/12/2018 | 24/12/2018 | 19/10/2018 | 26/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MKW20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 06/03/2019 | 28/03/2019 | 15/10/2018 | 23/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKW30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 16/04/2019 | 10/05/2019 | 20/03/2019 | 13/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKW40 | red | NDE | TT_Task | 30/04/2019 | 14/05/2019 | 11/04/2019 | 23/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKW50 | red | EC+I | TT_Task | 13/04/2019 | 26/04/2019 | 13/04/2019 | 07/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKW60 | red | Line Inspection | TT_Task | 31/05/2019 | 03/06/2019 | 03/06/2019 | 29/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKW70 | red | Hydro Test | TT_Task | 31/07/2019 | 05/08/2019 | 03/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKW80 | red | Painting/Insulation | TT_Task | 12/06/2019 | 21/06/2019 | 13/05/2019 | 26/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKW90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 30/09/2019 | 16/10/2019 | 30/09/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKF10 | red | Install Equipment/Skids/Pumps | TT_Task | 31/10/2018 | 07/11/2018 | 02/10/2018 | 10/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MKF20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 31/01/2019 | 16/03/2019 | 15/10/2018 | 26/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKF30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 07/05/2019 | 06/06/2019 | 20/03/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKF40 | red | NDE | TT_Task | 01/06/2019 | 06/07/2019 | 22/05/2019 | 20/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKF50 | red | EC+I | TT_Task | 25/06/2019 | 23/07/2019 | 17/05/2019 | 18/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKF60 | red | Line Inspection | TT_Task | 19/08/2019 | 24/08/2019 | 10/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKF70 | red | Hydro Test | TT_Task | 15/10/2019 | 18/10/2019 | 05/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKF80 | red | Painting/Insulation | TT_Task | 13/06/2019 | 03/07/2019 | 27/06/2019 | 28/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKF90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 22/10/2019 | 25/10/2019 | 28/10/2019 | 20/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKQ10 | red | Install Equipment/Skids/Pumps | TT_Task | 01/04/2019 | 09/04/2019 | 08/04/2019 | 11/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKQ20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 14/03/2019 | 06/04/2019 | 07/01/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKQ30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 25/04/2019 | 20/05/2019 | 20/03/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKQ40 | red | NDE | TT_Task | 09/04/2019 | 20/04/2019 | 09/04/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKQ50 | red | EC+I | TT_Task | 24/04/2019 | 08/05/2019 | 24/04/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKQ60 | red | Line Inspection | TT_Task | 31/08/2019 | 09/09/2019 | 07/09/2019 | 17/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKQ70 | red | Hydro Test | TT_Task | 30/09/2019 | 05/10/2019 | 05/10/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKQ90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 08/10/2019 | 12/10/2019 | 07/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKG10 | red | Install Equipment/Skids/Pumps | TT_Task | 01/11/2018 | 12/11/2018 | 17/10/2018 | 27/10/2018 | 0 | TK_Complete | CCGTD1_IPS
10MKG20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 01/04/2019 | 07/05/2019 | 01/11/2018 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKG30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 08/05/2019 | 04/06/2019 | 05/11/2018 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKG40 | red | NDE | TT_Task | 30/04/2019 | 24/05/2019 | 17/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKG50 | red | EC+I | TT_Task | 30/04/2019 | 23/05/2019 | 17/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKG60 | red | Line Inspection | TT_Task | 07/08/2019 | 12/08/2019 | 05/08/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKG70 | red | Hydro Test | TT_Task | 30/09/2019 | 09/10/2019 | 12/10/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKG80 | red | Painting/Insulation | TT_Task | 04/07/2019 | 27/07/2019 | 24/07/2019 | 01/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKG90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 10/10/2019 | 18/10/2019 | 14/10/2019 | 01/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAC05 | red | Preparation of Feed Water Pump Foundations | TT_Task | 11/02/2019 | 14/02/2019 | 29/01/2019 | 07/02/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAC10 | red | Install Feedwater Pump Skid (LAC10Y) | TT_Task | 15/02/2019 | 28/02/2019 | 15/02/2019 | 08/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAC20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 13/04/2019 | 04/06/2019 | 13/04/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAC30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 23/05/2019 | 05/07/2019 | 20/05/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAC40 | red | NDE | TT_Task | 16/05/2019 | 05/07/2019 | 16/05/2019 | 20/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAC50 | red | EC+I | TT_Task | 10/06/2019 | 16/07/2019 | 22/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAC60 | red | Line Inspection | TT_Task | 04/07/2019 | 12/07/2019 | 27/07/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAC70 | red | Hydro Test | TT_Task | 31/08/2019 | 07/09/2019 | 14/09/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAC80 | red | Painting/Insulation | TT_Task | 27/06/2019 | 16/07/2019 | 21/06/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAC90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 30/09/2019 | 17/10/2019 | 03/10/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAB10 | red | Install Equipment/Skids/Pumps/ | TT_Task | 01/04/2019 | 08/05/2019 | 01/03/2019 | 18/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAB100 | red | Insulation of FInal Weld Connections | TT_Task | 31/08/2019 | 17/09/2019 | 21/09/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAB20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 28/02/2019 | 10/05/2019 | 28/02/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAB30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 14/05/2019 | 22/06/2019 | 14/05/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAB40 | red | NDE | TT_Task | 04/05/2019 | 22/06/2019 | 04/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAB50 | red | EC+I | TT_Task | 31/05/2019 | 06/07/2019 | 24/05/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAB60 | red | Line Inspection &amp; Preparation for Neutral Float Welds | TT_Task | 10/06/2019 | 21/06/2019 | 18/06/2019 | 27/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAB65 | red | Neural Float &amp; Final Weld Connections to FW Pump | TT_Task | 29/06/2019 | 11/07/2019 | 27/07/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAB70 | red | Hydro Test | TT_Task | 30/09/2019 | 12/10/2019 | 02/10/2019 | 08/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAB80 | red | Insulation of Pipework Prior to Neutral Float | TT_Task | 07/06/2019 | 02/07/2019 | 14/06/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LAB90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 14/10/2019 | 24/10/2019 | 03/10/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00LAB10 | red | Install Make-up Water/NOx Pumps &amp; Pressure System (Tank/Controls) | TT_Task | 21/01/2019 | 21/02/2019 | 15/01/2019 | 07/05/2019 | 0 | TK_Complete | CCGTD1_IPS
00LAB20 | red | Install NOx Piping from Existing Demin Tank to GT NOx Control Pump including Recir Line | TT_Task | 24/04/2019 | 16/07/2019 | 24/04/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00LAB30 | red | Install Make-up Water Piping from Existing Demin Tank to Connection Points of New CCGT | TT_Task | 30/04/2019 | 22/07/2019 | 15/05/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00LAB40 | red | NDE | TT_Task | 22/06/2019 | 29/07/2019 | 14/05/2019 | 20/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00LAB50 | red | EC+I | TT_Task | 23/07/2019 | 06/09/2019 | 23/05/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00LAB60 | red | Line Inspection | TT_Task | 20/07/2019 | 29/07/2019 | 11/07/2019 | 13/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00LAB70 | red | Hydro Test | TT_Task | 30/09/2019 | 09/10/2019 | 11/10/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00LAB80 | red | Painting/Insulation | TT_Task | 13/08/2019 | 20/09/2019 | 10/08/2019 | 15/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00LAB90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 15/10/2019 | 23/10/2019 | 15/10/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00EG-01-10 | red | Install Equipment/Skids/Pumps | TT_Task | 18/02/2019 | 06/03/2019 | 15/09/2018 | 25/09/2018 | 0 | TK_Complete | CCGTD1_IPS
00EG-01-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 06/03/2019 | 03/05/2019 | 15/09/2018 | 27/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00EG-01-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 03/04/2019 | 03/05/2019 | 05/04/2019 | 27/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00EG-01-50 | red | EC+I | TT_Task | 10/06/2019 | 04/07/2019 | 10/05/2019 | 27/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00EG-01-60 | red | Line Inspection | TT_Task | 23/07/2019 | 05/08/2019 | 24/07/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00EG-01-70 | red | Hydro Test | TT_Task | 07/08/2019 | 21/08/2019 | 10/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00EG-01-80 | red | Painting/Insulation | TT_Task | 03/05/2019 | 15/06/2019 | 03/05/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00EG-01-90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 16/09/2019 | 30/09/2019 | 28/09/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00EG-02-10 | red | Install Equipment/Skids/Pumps | TT_Task | 15/02/2019 | 01/03/2019 | 15/09/2018 | 25/09/2018 | 0 | TK_Complete | CCGTD1_IPS
00EG-02-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 16/11/2018 | 28/01/2019 | 01/09/2018 | 21/05/2019 | 0 | TK_Complete | CCGTD1_IPS
00EG-02-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 10/06/2019 | 08/07/2019 | 10/05/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00EG-02-40 | red | EC+I | TT_Task | 04/07/2019 | 17/07/2019 | 08/06/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00EG-02-50 | red | Line Inspection | TT_Task | 02/07/2019 | 15/07/2019 | 20/07/2019 | 27/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00EG-02-60 | red | Hydro Test | TT_Task | 31/07/2019 | 14/08/2019 | 10/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00EG-02-70 | red | Painting/Insulation | TT_Task | 04/07/2019 | 26/07/2019 | 04/06/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00EG-02-80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 31/08/2019 | 13/09/2019 | 28/09/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10EK10 | red | Install Equipment/Skids/Pumps | TT_Task | 31/05/2019 | 18/06/2019 | 10/06/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10EK30 | red | Install Pipe/Valves/Supports (Inside+Outside) | TT_Task | 06/04/2019 | 13/05/2019 | 06/04/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10EK40 | red | EC+I | TT_Task | 03/07/2019 | 25/07/2019 | 22/05/2019 | 25/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10EK50 | red | Line Inspection | TT_Task | 30/09/2019 | 18/10/2019 | 03/10/2019 | 18/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10EK60 | red | Hydro Test | TT_Task | 19/10/2019 | 30/10/2019 | 19/10/2019 | 21/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10EK70 | red | Painting/Insulation | TT_Task | 08/06/2019 | 04/07/2019 | 16/05/2019 | 10/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10EK80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 31/10/2019 | 11/11/2019 | 08/10/2019 | 10/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10EK90 | red | Install Fuel Gas Piping from Plant to Tie-in to Existing Line | TT_Task | 30/08/2018 | 17/10/2018 | 13/08/2018 | 06/05/2019 | 0 | TK_Complete | CCGTD1_IPS
00EK09 | red | Erection of Blending Station | TT_Task | 30/04/2019 | 22/05/2019 | 25/05/2019 | 27/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00EK10 | red | Install Equipment/Skids/Pumps | TT_Task | 30/04/2019 | 05/06/2019 | 07/05/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00EK20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 03/04/2019 | 06/06/2019 | 01/03/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00EK30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 06/04/2019 | 16/05/2019 | 10/04/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00EK35 | red | NDE | TT_Task | 08/05/2019 | 15/06/2019 | 08/05/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00EK40 | red | EC+I | TT_Task | 23/05/2019 | 05/07/2019 | 23/05/2019 | 26/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00EK50 | red | Line Inspection | TT_Task | 02/09/2019 | 11/09/2019 | 28/09/2019 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00EK60 | red | Hydro Test | TT_Task | 10/10/2019 | 19/10/2019 | 21/10/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00EK70 | red | Painting/Insulation | TT_Task | 26/07/2019 | 06/08/2019 | 15/06/2019 | 16/12/2019 | 0 | TK_Complete | CCGTD1_IPS
00EK80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 19/10/2019 | 31/10/2019 | 07/10/2019 | 16/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10EKT20-10 | red | Install Equipment/Skids/Pumps | TT_Task | 30/04/2019 | 05/06/2019 | 08/05/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10EKT20-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 30/04/2019 | 05/06/2019 | 06/05/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10EKT20-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 13/05/2019 | 07/06/2019 | 13/05/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10EKT20-40 | red | EC+I | TT_Task | 30/04/2019 | 05/06/2019 | 15/05/2019 | 27/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10EKT20-50 | red | Line Inspection | TT_Task | 09/09/2019 | 16/09/2019 | 28/09/2019 | 16/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10EKT20-60 | red | Hydro Test | TT_Task | 05/10/2019 | 15/10/2019 | 11/10/2019 | 16/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10EKT20-70 | red | Painting/Insulation | TT_Task | 25/06/2019 | 17/07/2019 | 14/06/2019 | 27/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10EKT20-80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 15/10/2019 | 23/10/2019 | 05/10/2019 | 27/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10EKT20-90 | red | NDE | TT_Task | 08/05/2019 | 13/06/2019 | 08/05/2019 | 02/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00PAA10 | red | Install Equipment - Skid | TT_Task | 22/06/2019 | 06/07/2019 | 18/05/2019 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00PAA11 | red | Installation of Bar Screen - Skid | TT_Task | 31/07/2019 | 22/08/2019 | 03/08/2019 | 15/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00PAA20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 22/07/2019 | 09/08/2019 | 13/07/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00PAA30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 10/08/2019 | 29/08/2019 | 13/07/2019 | 23/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00PAA40 | red | NDE | TT_Task | 15/08/2019 | 31/08/2019 | 24/08/2019 | 26/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00PAA50 | red | EC+I | TT_Task | 02/09/2019 | 17/09/2019 | 24/08/2019 | 20/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00PAA60 | red | Line Inspection | TT_Task | 30/10/2019 | 04/11/2019 | 30/10/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00PAA70 | red | Hydro Test | TT_Task | 05/11/2019 | 08/11/2019 | 05/11/2019 | 15/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00PAA80 | red | Painting/Insulation | TT_Task | 21/09/2019 | 30/09/2019 | 28/09/2019 | 10/12/2019 | 0 | TK_Complete | CCGTD1_IPS
00PAA90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 30/11/2019 | 07/12/2019 | 30/11/2019 | 10/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-02-10 | red | Install Cooling Water Piperack (UPY00Y Module) | TT_Task | 01/04/2019 | 15/04/2019 | 01/04/2019 | 23/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-02-20 | red | Install Large Bore Pipe/Valves/Supports from Civil U/G TP to Condenser | TT_Task | 09/05/2019 | 06/06/2019 | 09/05/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-02-30 | red | Install Small Bore Pipe/Valves/Supports from Civil U/G TP to Condenser | TT_Task | 01/04/2019 | 04/06/2019 | 09/04/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-02-40 | red | NDE | TT_Task | 24/06/2019 | 02/07/2019 | 04/06/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-02-50 | red | EC+I | TT_Task | 28/06/2019 | 30/07/2019 | 13/06/2019 | 05/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-02-60 | red | Line Inspection | TT_Task | 26/10/2019 | 31/10/2019 | 04/10/2019 | 22/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-02-70 | red | Hydro Test | TT_Task | 04/11/2019 | 13/11/2019 | 04/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-02-80 | red | Painting/Insulation | TT_Task | 15/10/2019 | 29/10/2019 | 25/09/2019 | 16/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-02-90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 04/12/2019 | 10/12/2019 | 04/12/2019 | 16/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-01-10 | red | Install Circulating Water Pumps | TT_Task | 08/07/2019 | 22/07/2019 | 06/07/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-01-110 | red | Prepare Circulating Water Pumps Foundations | TT_Task | 31/05/2019 | 14/06/2019 | 29/06/2019 | 19/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-01-20 | red | Install Large Bore Pipe/Valves/Supports from CW Pumps to U/G Piping Terminal Point | TT_Task | 11/07/2019 | 05/08/2019 | 13/07/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-01-30 | red | Install Small Bore Pipe/Valves/Supports from CW Pump to U/G Piping Terminal Point | TT_Task | 15/07/2019 | 07/08/2019 | 13/07/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-01-40 | red | NDE | TT_Task | 09/08/2019 | 20/08/2019 | 24/08/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-01-50 | red | EC+I | TT_Task | 02/09/2019 | 03/10/2019 | 02/09/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-01-60 | red | Line Inspection | TT_Task | 30/11/2019 | 04/12/2019 | 30/11/2019 | 01/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-01-70 | red | Hydro Test | TT_Task | 30/03/2020 | 02/04/2020 | 02/12/2019 | 06/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-01-80 | red | Painting/Insulation | TT_Task | 26/09/2019 | 05/10/2019 | 26/09/2019 | 12/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAB-01-90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 03/04/2020 | 08/04/2020 | 07/12/2019 | 12/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10PGB1010 | red | Install Closed Cooling/Service Water Pump Module (PXB00Y) | TT_Task | 30/04/2019 | 06/06/2019 | 03/05/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10PGB1020 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 03/04/2019 | 27/06/2019 | 18/10/2018 | 02/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10PGB1030 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 16/04/2019 | 25/05/2019 | 08/03/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10PGB1040 | red | NDE | TT_Task | 15/05/2019 | 06/07/2019 | 15/05/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10PGB1050 | red | EC+I | TT_Task | 13/07/2019 | 12/08/2019 | 06/06/2019 | 26/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10PGB1060 | red | Line Inspection | TT_Task | 08/08/2019 | 16/08/2019 | 29/06/2019 | 13/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10PGB1070 | red | Hydro Test | TT_Task | 22/08/2019 | 30/08/2019 | 10/07/2019 | 13/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10PGB1080 | red | Painting/Insulation | TT_Task | 13/07/2019 | 06/08/2019 | 08/06/2019 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PGB1090 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 11/10/2019 | 18/10/2019 | 05/10/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PCB10 | blue | Service Cooling Water Pumps Installed w/PXB00Y Module (See Activity 10PGB1010) | TT_FinMile | 02/09/2019 | 02/09/2019 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10PCB20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 26/07/2019 | 28/08/2019 | 12/07/2019 | 04/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10PCB30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 24/07/2019 | 19/08/2019 | 11/07/2019 | 03/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10PCB40 | red | NDE | TT_Task | 06/08/2019 | 12/08/2019 | 10/08/2019 | 03/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PCB50 | red | EC+I | TT_Task | 10/08/2019 | 20/08/2019 | 15/07/2019 | 25/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10PCB60 | red | Line Inspection | TT_Task | 30/09/2019 | 08/10/2019 | 10/10/2019 | 09/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10PCB70 | red | Hydro Test | TT_Task | 01/11/2019 | 08/11/2019 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10PCB80 | red | Painting/Insulation | TT_Task | 20/08/2019 | 02/09/2019 | 24/08/2019 | 15/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10PCB90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 09/11/2019 | 15/11/2019 | 09/11/2019 | 15/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAH10 | red | Install Equipment/Skids/Pumps | TT_Task | 19/02/2019 | 25/02/2019 | 15/11/2018 | 20/11/2018 | 0 | TK_Complete | CCGTD1_IPS
10PAH15 | red | Install Control Cabinet &amp; Junction Box for Tube Cleaning Systen | TT_Task | 31/05/2019 | 03/06/2019 | 25/06/2019 | 17/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAH20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 06/04/2019 | 09/05/2019 | 06/04/2019 | 03/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAH30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 26/04/2019 | 14/05/2019 | 26/04/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAH40 | red | NDE | TT_Task | 23/05/2019 | 05/06/2019 | 23/05/2019 | 27/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAH50 | red | EC+I | TT_Task | 30/05/2019 | 29/06/2019 | 21/05/2019 | 26/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAH60 | red | Line Inspection | TT_Task | 04/09/2019 | 17/09/2019 | 28/09/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAH70 | red | Hydro Test | TT_Task | 28/03/2020 | 02/04/2020 | 04/12/2019 | 09/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAH80 | red | Painting/Insulation | TT_Task | 23/09/2019 | 10/10/2019 | 23/09/2019 | 17/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10PAH90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 01/04/2020 | 08/04/2020 | 10/12/2019 | 17/12/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUN10 | red | Install Equipment/Skids/Pumps - Skid | TT_Task | 22/05/2019 | 01/06/2019 | 23/04/2019 | 10/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUN11 | red | Install Containers - Skid | TT_Task | 08/06/2019 | 13/06/2019 | 27/06/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUN12 | red | Install Interconnection Lines to Process | TT_Task | 02/08/2019 | 07/08/2019 | 17/08/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUN20 | red | Install Pipe/Valves/Supports - Skid | TT_Task | 08/06/2019 | 06/07/2019 | 14/06/2019 | 02/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUN40 | red | EC+I | TT_Task | 20/08/2019 | 29/08/2019 | 17/08/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUN50 | red | Line Inspection | TT_Task | 30/10/2019 | 08/11/2019 | 30/10/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUN60 | red | Hydro Test/Leak Test | TT_Task | 01/11/2019 | 11/11/2019 | 01/11/2019 | 11/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUN80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 11/11/2019 | 20/11/2019 | 11/11/2019 | 20/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUN90 | red | NDE | TT_Task | 16/07/2019 | 29/07/2019 | 16/07/2019 | 03/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PUR10 | red | Anode Installation | TT_Task | 02/09/2019 | 11/09/2019 | 19/09/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PUR20 | red | Rectifier Installation | TT_Task | 07/09/2019 | 18/09/2019 | 21/09/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PUR30 | red | Junction Box Installion | TT_Task | 13/09/2019 | 24/09/2019 | 21/09/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PUR40 | red | Test Station | TT_Task | 20/09/2019 | 30/09/2019 | 20/09/2019 | 30/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PUR50 | red | Cable Pulling/Termination | TT_Task | 02/10/2019 | 12/10/2019 | 20/09/2019 | 30/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10PUR60 | red | Precommissioning | TT_Task | 30/10/2019 | 09/11/2019 | 30/10/2019 | 09/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00UPR10 | red | Anode Installation | TT_Task | 02/09/2019 | 10/09/2019 | 20/09/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00UPR20 | red | Rectifier Installation | TT_Task | 11/09/2019 | 21/09/2019 | 19/09/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00UPR30 | red | Junction Box Installion | TT_Task | 23/09/2019 | 02/10/2019 | 19/09/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00UPR40 | red | Test Station | TT_Task | 03/10/2019 | 12/10/2019 | 21/09/2019 | 30/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00UPR50 | red | Cable Pulling/Termination | TT_Task | 14/10/2019 | 22/10/2019 | 18/09/2019 | 30/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00UPR60 | red | Precommissioning | TT_Task | 30/10/2019 | 08/11/2019 | 30/10/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA10 | red | Install Equipment/Skids/Pumps | TT_Task | 15/03/2019 | 17/04/2019 | 15/03/2019 | 22/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 01/04/2019 | 10/05/2019 | 03/04/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 13/04/2019 | 23/05/2019 | 13/04/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA40 | red | NDE | TT_Task | 29/05/2019 | 17/06/2019 | 07/05/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA50 | red | EC+I | TT_Task | 05/06/2019 | 28/06/2019 | 17/05/2019 | 26/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA60 | red | Line Inspection | TT_Task | 01/08/2019 | 05/08/2019 | 28/08/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA70 | red | Hydro Test | TT_Task | 30/09/2019 | 03/10/2019 | 05/10/2019 | 09/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA80 | red | Painting/Insulation | TT_Task | 24/06/2019 | 03/07/2019 | 03/06/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 04/10/2019 | 08/10/2019 | 12/10/2019 | 30/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCB20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 17/04/2019 | 10/06/2019 | 15/03/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCB30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 24/04/2019 | 06/06/2019 | 24/04/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCB40 | red | NDE | TT_Task | 31/05/2019 | 08/06/2019 | 05/06/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCB50 | red | EC+I | TT_Task | 30/04/2019 | 10/06/2019 | 08/05/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCB60 | red | Line Inspection | TT_Task | 02/08/2019 | 10/08/2019 | 28/08/2019 | 18/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCB70 | red | Hydro Test | TT_Task | 30/09/2019 | 04/10/2019 | 05/10/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCB80 | red | Painting | TT_Task | 21/06/2019 | 20/07/2019 | 03/06/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCB90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 05/10/2019 | 11/10/2019 | 05/10/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA110 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 18/02/2019 | 14/05/2019 | 02/01/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA120 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 08/05/2019 | 14/06/2019 | 08/05/2019 | 20/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA130 | red | NDE | TT_Task | 01/04/2019 | 17/06/2019 | 01/04/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA140 | red | EC+I | TT_Task | 29/06/2019 | 24/07/2019 | 03/06/2019 | 26/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA150 | red | Line Inspection | TT_Task | 12/08/2019 | 20/08/2019 | 28/08/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA160 | red | Hydro Test | TT_Task | 30/09/2019 | 04/10/2019 | 11/10/2019 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA170 | red | Painting/Insulation | TT_Task | 29/06/2019 | 24/07/2019 | 04/06/2019 | 15/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00SCA180 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 05/10/2019 | 14/10/2019 | 12/10/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
GKB10 | red | Install Equipment/Skids/Pumps | TT_Task | 01/04/2019 | 15/04/2019 | 01/04/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
GKB20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 15/04/2019 | 25/05/2019 | 15/04/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
GKB30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 18/06/2019 | 08/07/2019 | 05/06/2019 | 09/10/2019 | 0 | TK_Complete | CCGTD1_IPS
GKB40 | red | EC+I | TT_Task | 08/07/2019 | 19/07/2019 | 06/06/2019 | 08/10/2019 | 0 | TK_Complete | CCGTD1_IPS
GKB50 | red | Line Inspection | TT_Task | 30/09/2019 | 09/10/2019 | 10/10/2019 | 07/11/2019 | 0 | TK_Complete | CCGTD1_IPS
GKB60 | red | Hydro Test | TT_Task | 05/12/2019 | 17/12/2019 | 08/11/2019 | 19/11/2019 | 0 | TK_Complete | CCGTD1_IPS
GKB70 | red | Painting/Insulation | TT_Task | 03/07/2019 | 20/07/2019 | 07/06/2019 | 19/11/2019 | 0 | TK_Complete | CCGTD1_IPS
GKB80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 23/10/2019 | 29/10/2019 | 12/10/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GKB-02-10 | red | Install Equipment/Skids/Pumps | TT_Task | 01/04/2019 | 15/04/2019 | 01/04/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00GKB-02-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 15/04/2019 | 25/05/2019 | 15/04/2019 | 08/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GKB-02-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 24/06/2019 | 12/07/2019 | 01/06/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GKB-02-40 | red | EC+I | TT_Task | 05/06/2019 | 05/07/2019 | 07/06/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GKB-02-50 | red | Line Inspection | TT_Task | 30/09/2019 | 11/10/2019 | 08/10/2019 | 31/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GKB-02-60 | red | Hydro Test | TT_Task | 06/12/2019 | 13/12/2019 | 01/11/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GKB-02-70 | red | Painting/Insulation | TT_Task | 06/07/2019 | 24/07/2019 | 14/06/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GKB-02-80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 10/12/2019 | 13/12/2019 | 20/11/2019 | 25/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-02-10 | red | Install Equipment/Skids/Pumps | TT_Task | 01/04/2019 | 12/04/2019 | 01/04/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-02-20 | red | Install Large Bore Pipe/Valves/Supports (Inside+Outside) | TT_Task | 11/03/2019 | 30/04/2019 | 22/03/2019 | 08/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-02-30 | red | Install Small Bore Pipe/Valves/Supports (Inside+Outside) | TT_Task | 17/05/2019 | 11/06/2019 | 17/05/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-02-40 | red | EC+I | TT_Task | 12/06/2019 | 08/07/2019 | 12/06/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-02-50 | red | Line Inspection | TT_Task | 30/09/2019 | 04/10/2019 | 19/10/2019 | 30/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-02-60 | red | Hydro Test | TT_Task | 06/12/2019 | 10/12/2019 | 01/11/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-02-70 | red | Painting/Insulation | TT_Task | 10/06/2019 | 05/07/2019 | 03/06/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-02-80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 06/12/2019 | 10/12/2019 | 20/11/2019 | 25/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-02-90 | red | NDE | TT_Task | 24/05/2019 | 18/06/2019 | 24/05/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-110 | red | Install Equipment/Skids/Pumps | TT_Task | 01/04/2019 | 12/04/2019 | 01/04/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-120 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 26/02/2019 | 24/04/2019 | 22/02/2019 | 09/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-130 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 07/05/2019 | 12/06/2019 | 07/05/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-140 | red | EC+I | TT_Task | 10/07/2019 | 22/07/2019 | 12/06/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-150 | red | Line Inspection | TT_Task | 04/10/2019 | 10/10/2019 | 18/10/2019 | 22/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-160 | red | Hydro Test | TT_Task | 30/11/2019 | 03/12/2019 | 01/11/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-170 | red | Painting/Insulation | TT_Task | 29/06/2019 | 24/07/2019 | 14/06/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-180 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 14/10/2019 | 18/10/2019 | 10/10/2019 | 25/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHD-190 | red | NDE | TT_Task | 30/04/2019 | 12/06/2019 | 22/05/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-02-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 21/02/2019 | 06/04/2019 | 31/10/2018 | 07/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-02-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 17/06/2019 | 24/06/2019 | 08/05/2019 | 08/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-02-40 | red | EC+I | TT_Task | 22/06/2019 | 23/07/2019 | 15/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-02-50 | red | Line Inspection | TT_Task | 31/05/2019 | 11/06/2019 | 01/06/2019 | 17/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-02-60 | red | Hydro Test | TT_Task | 20/06/2019 | 25/06/2019 | 22/06/2019 | 05/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-02-70 | red | Painting/Insulation | TT_Task | 24/06/2019 | 12/07/2019 | 16/05/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-02-80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 02/09/2019 | 06/09/2019 | 02/09/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-01-10 | red | Install Equipment/Skids/Pumps | TT_Task | 01/04/2019 | 10/05/2019 | 17/02/2019 | 28/02/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-01-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 01/04/2019 | 10/05/2019 | 16/02/2019 | 15/05/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-01-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 08/04/2019 | 23/04/2019 | 08/04/2019 | 08/05/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-01-40 | red | EC+I | TT_Task | 15/05/2019 | 08/06/2019 | 15/05/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-01-50 | red | Line Inspection | TT_Task | 08/05/2019 | 13/05/2019 | 08/05/2019 | 13/05/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-01-60 | red | Hydro Test | TT_Task | 13/05/2019 | 17/05/2019 | 13/05/2019 | 23/05/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-01-70 | red | Painting/Insulation | TT_Task | 15/05/2019 | 01/06/2019 | 15/05/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00GHC-01-80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 31/08/2019 | 04/09/2019 | 07/09/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10GHC10 | red | Install Equipment/Skids/Pumps | TT_Task | 01/04/2019 | 12/04/2019 | 01/04/2019 | 10/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10GHC20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 22/02/2019 | 29/03/2019 | 31/10/2018 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10GHC30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 27/04/2019 | 07/06/2019 | 27/04/2019 | 15/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10GHC40 | red | EC+I | TT_Task | 05/06/2019 | 22/06/2019 | 07/06/2019 | 20/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10GHC50 | red | Line Inspection | TT_Task | 13/06/2019 | 25/06/2019 | 22/06/2019 | 10/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10GHC60 | red | Hydro Test | TT_Task | 11/07/2019 | 22/07/2019 | 24/07/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10GHC70 | red | Painting/Insulation | TT_Task | 13/06/2019 | 02/07/2019 | 13/06/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10GHC80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 12/08/2019 | 21/08/2019 | 17/08/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10QU20 | red | Install Containers | TT_Task | 01/04/2019 | 08/04/2019 | 01/04/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10QU30 | red | Install Interconnecting Lines To Process | TT_Task | 09/04/2019 | 27/06/2019 | 09/04/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10QU40 | red | Hydro/Leak Test | TT_Task | 13/09/2019 | 10/10/2019 | 28/09/2019 | 08/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10QU50 | red | EC+I | TT_Task | 08/07/2019 | 07/08/2019 | 04/06/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10QU60 | red | Precommissioning | TT_Task | 21/10/2019 | 07/11/2019 | 18/10/2019 | 19/01/2020 | 0 | TK_Complete | CCGTD1_IPS
10QCD20 | red | Install Containers | TT_Task | 13/02/2019 | 20/02/2019 | 26/02/2019 | 03/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10QCD30 | red | Install Interconnecting Lines To Process | TT_Task | 07/06/2019 | 09/07/2019 | 01/06/2019 | 09/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10QCD40 | red | Hydro/Leak Test | TT_Task | 05/09/2019 | 30/09/2019 | 28/09/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10QCD50 | red | EC+I | TT_Task | 09/07/2019 | 01/08/2019 | 08/06/2019 | 08/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10QCD60 | red | Precommissioning | TT_Task | 05/10/2019 | 26/10/2019 | 19/10/2019 | 02/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10QCC20 | red | Install Containers | TT_Task | 11/03/2019 | 16/03/2019 | 26/03/2019 | 03/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10QCC30 | red | Install Interconnecting Lines To Process | TT_Task | 20/06/2019 | 20/07/2019 | 10/05/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10QCC40 | red | Hydro/Leak Test | TT_Task | 05/09/2019 | 30/09/2019 | 28/09/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10QCC50 | red | EC+I | TT_Task | 27/06/2019 | 26/07/2019 | 22/06/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10QCC60 | red | Precommissioning | TT_Task | 11/10/2019 | 04/11/2019 | 18/10/2019 | 02/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10QCB20 | red | Install Containers | TT_Task | 01/04/2019 | 18/04/2019 | 26/03/2019 | 07/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10QCB30 | red | Install Interconnecting Lines To Process | TT_Task | 31/05/2019 | 23/07/2019 | 01/06/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10QCB40 | red | Hydro/Leak Test | TT_Task | 11/09/2019 | 24/09/2019 | 28/09/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10QCB50 | red | EC+I | TT_Task | 30/04/2019 | 08/06/2019 | 09/05/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10QCB60 | red | Precommissioning | TT_Task | 04/10/2019 | 21/10/2019 | 19/10/2019 | 26/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00STG20 | red | Install Containers | TT_Task | 11/03/2019 | 16/03/2019 | 30/04/2019 | 24/05/2019 | 0 | TK_Complete | CCGTD1_IPS
00STG30 | red | Install Interconnecting Lines To Process | TT_Task | 31/05/2019 | 06/07/2019 | 03/06/2019 | 08/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00STG40 | red | Hydro/Leak Test | TT_Task | 10/09/2019 | 16/09/2019 | 28/09/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00STG50 | red | EC+I | TT_Task | 08/07/2019 | 13/08/2019 | 04/06/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00STG60 | red | Precommissioning | TT_Task | 03/10/2019 | 22/10/2019 | 17/10/2019 | 10/12/2019 | 0 | TK_Complete | CCGTD1_IPS
PMS14.1020 | red | Installation Aux. System Pipe Racks (UMCM1Y Modules) | TT_Task | 06/11/2018 | 07/12/2018 | 18/10/2018 | 20/11/2018 | 0 | TK_Complete | CCGTD1_IPS
PMS14.1050 | red | Installation Water System Pipe Racks (UMCL1Y Modules) | TT_Task | 12/02/2019 | 22/02/2019 | 21/01/2019 | 11/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA80-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 11/03/2019 | 30/04/2019 | 11/03/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA80-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 16/04/2019 | 03/06/2019 | 16/04/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA80-40 | red | NDE | TT_Task | 16/04/2019 | 08/06/2019 | 16/04/2019 | 27/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA80-50 | red | EC+I | TT_Task | 20/05/2019 | 18/06/2019 | 20/05/2019 | 26/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA80-60 | red | Line Inspection | TT_Task | 04/09/2019 | 17/09/2019 | 28/09/2019 | 21/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA80-70 | red | Hydro Test | TT_Task | 22/10/2019 | 26/10/2019 | 22/10/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA80-80 | red | Painting/Insulation of Pipework | TT_Task | 20/05/2019 | 25/06/2019 | 20/05/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA80-90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 17/10/2019 | 22/10/2019 | 26/10/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA10-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 28/02/2019 | 09/05/2019 | 11/03/2019 | 05/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA10-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 09/05/2019 | 17/06/2019 | 09/05/2019 | 03/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA10-40 | red | NDE | TT_Task | 04/04/2019 | 10/06/2019 | 04/04/2019 | 26/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA10-50 | red | EC+I | TT_Task | 27/05/2019 | 02/07/2019 | 14/05/2019 | 24/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA10-55 | red | Insulation of Pipework Prior to Neutral Float | TT_Task | 17/06/2019 | 11/07/2019 | 17/06/2019 | 25/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA10-60 | red | Line Inspection &amp; Preparation for Neutral Float | TT_Task | 01/08/2019 | 13/08/2019 | 10/08/2019 | 26/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA10-65 | red | Neutral Float of LBA and FInal Weld to Turbine Stop Valve | TT_Task | 26/07/2019 | 07/08/2019 | 17/07/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA10-70 | red | Hydro Test | TT_Task | 30/09/2019 | 04/10/2019 | 23/10/2019 | 26/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA10-80 | red | Insulation of Neutral Float Weld | TT_Task | 05/10/2019 | 11/10/2019 | 05/10/2019 | 30/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBA10-90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 12/10/2019 | 17/10/2019 | 26/10/2019 | 05/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBB20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 11/03/2019 | 07/05/2019 | 11/03/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBB30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 08/05/2019 | 15/06/2019 | 08/05/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBB40 | red | NDE | TT_Task | 09/05/2019 | 15/06/2019 | 09/05/2019 | 26/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBB50 | red | EC+I | TT_Task | 25/05/2019 | 12/07/2019 | 25/05/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBB55 | red | Insulation of Pipework Prior to Neutral Float | TT_Task | 20/06/2019 | 03/07/2019 | 20/06/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBB60 | red | Line Inspection &amp; Preparation for Neutral Float | TT_Task | 03/08/2019 | 15/08/2019 | 03/08/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBB65 | red | Neutral Float of LBB and FInal Weld to Turbine Stop Valve | TT_Task | 19/07/2019 | 01/08/2019 | 18/07/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBB70 | red | Hydro Test | TT_Task | 30/09/2019 | 16/10/2019 | 24/09/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBB80 | red | Insulation of Neutral Float Weld | TT_Task | 30/09/2019 | 12/10/2019 | 04/10/2019 | 02/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBB90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 16/10/2019 | 30/10/2019 | 26/10/2019 | 15/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBC20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 18/02/2019 | 27/04/2019 | 14/01/2019 | 05/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBC30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 30/04/2019 | 10/06/2019 | 15/05/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBC40 | red | NDE | TT_Task | 03/05/2019 | 10/06/2019 | 03/05/2019 | 25/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBC50 | red | EC+I | TT_Task | 18/05/2019 | 22/06/2019 | 18/05/2019 | 25/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBC55 | red | Insulation of Pipework Prior to Neutral Float | TT_Task | 17/06/2019 | 28/06/2019 | 17/06/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBC60 | red | Line Inspection &amp; Preparation for Neutral Float | TT_Task | 05/08/2019 | 09/08/2019 | 03/08/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBC65 | red | Neutral Float of LBC and FInal Weld to Turbine Stop Valve | TT_Task | 09/08/2019 | 15/08/2019 | 24/08/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBC70 | red | Hydro Test | TT_Task | 30/09/2019 | 04/10/2019 | 18/10/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBC80 | red | Insulation of Neutral Float Weld | TT_Task | 05/10/2019 | 11/10/2019 | 05/10/2019 | 31/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBC90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 05/10/2019 | 11/10/2019 | 26/10/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBG20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 01/04/2019 | 04/05/2019 | 04/04/2019 | 25/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBG30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 24/05/2019 | 19/06/2019 | 24/05/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBG40 | red | NDE | TT_Task | 08/06/2019 | 26/06/2019 | 09/05/2019 | 20/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBG50 | red | EC+I | TT_Task | 24/05/2019 | 21/06/2019 | 24/05/2019 | 26/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBG60 | red | Line Inspection | TT_Task | 31/07/2019 | 10/08/2019 | 10/08/2019 | 31/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBG70 | red | Hydro Test | TT_Task | 30/09/2019 | 12/10/2019 | 07/10/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBG80 | red | Insulation | TT_Task | 24/06/2019 | 12/07/2019 | 14/06/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10LBG90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 14/10/2019 | 24/10/2019 | 12/10/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00LBG10 | red | Install Equipment/Skids/Pumps | TT_Task | 01/04/2019 | 04/04/2019 | 08/04/2019 | 11/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00LBG20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 15/04/2019 | 12/06/2019 | 15/04/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00LBG30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 31/05/2019 | 29/06/2019 | 15/05/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00LBG40 | red | NDE | TT_Task | 22/06/2019 | 11/07/2019 | 08/06/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00LBG50 | red | EC+I | TT_Task | 18/06/2019 | 18/07/2019 | 17/05/2019 | 26/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00LBG60 | red | Line Inspection | TT_Task | 31/07/2019 | 10/08/2019 | 10/08/2019 | 02/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00LBG70 | red | Hydro Test | TT_Task | 30/09/2019 | 12/10/2019 | 07/10/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00LBG80 | red | Insulation | TT_Task | 09/07/2019 | 01/08/2019 | 15/06/2019 | 06/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00LBG90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 14/10/2019 | 25/10/2019 | 12/10/2019 | 06/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-10 | red | Install Equipment/Skids/Pumps | TT_Task | 01/04/2019 | 15/04/2019 | 10/04/2019 | 17/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-20 | red | Erection of Oil Separator Pumps GM - Skid | TT_Task | 07/06/2019 | 17/06/2019 | 07/06/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-30 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 15/04/2019 | 25/05/2019 | 15/04/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-40 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 30/04/2019 | 24/05/2019 | 08/05/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-50 | red | E&amp;IC of Oil Separator Pumps GM | TT_Task | 25/05/2019 | 13/06/2019 | 25/05/2019 | 07/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-60 | red | Line Inspection | TT_Task | 01/08/2019 | 06/08/2019 | 24/08/2019 | 03/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-70 | red | Hydro Test | TT_Task | 03/09/2019 | 10/09/2019 | 25/09/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-80 | red | Painting/Insulation | TT_Task | 25/05/2019 | 04/06/2019 | 15/05/2019 | 31/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 31/10/2019 | 07/11/2019 | 10/10/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-03-10 | red | Install Equipment/Skids/Pumps | TT_Task | 17/04/2019 | 02/05/2019 | 19/04/2019 | 10/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-03-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 14/05/2019 | 07/06/2019 | 14/05/2019 | 23/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-03-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 07/06/2019 | 19/06/2019 | 21/05/2019 | 25/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-03-40 | red | EC+I | TT_Task | 14/05/2019 | 01/06/2019 | 14/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-03-50 | red | Line Inspection | TT_Task | 31/07/2019 | 07/08/2019 | 10/07/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-03-60 | red | Hydro Test | TT_Task | 02/09/2019 | 12/09/2019 | 28/09/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-03-70 | red | Painting/Insulation | TT_Task | 08/06/2019 | 20/06/2019 | 21/05/2019 | 26/03/2020 | 0 | TK_Complete | CCGTD1_IPS
00GM-03-80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 05/10/2019 | 15/10/2019 | 12/10/2019 | 26/03/2020 | 0 | TK_Complete | CCGTD1_IPS
00GM-03-90 | blue | Assumption Underground System Available | TT_FinMile | 21/12/2019 | 21/12/2019 | 22/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-02-10 | red | Install Equipment/Skids/Pumps | TT_Task | 15/04/2019 | 11/05/2019 | 15/04/2019 | 09/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-02-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 30/04/2019 | 24/05/2019 | 09/05/2019 | 23/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-02-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 14/05/2019 | 05/06/2019 | 14/05/2019 | 24/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-02-40 | red | EC+I | TT_Task | 24/05/2019 | 17/06/2019 | 24/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-02-50 | red | Line Inspection | TT_Task | 02/08/2019 | 06/08/2019 | 10/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-02-60 | red | Hydro Test | TT_Task | 31/08/2019 | 09/09/2019 | 28/09/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-02-70 | red | Painting/Insulation | TT_Task | 13/05/2019 | 11/06/2019 | 13/05/2019 | 05/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-02-80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 04/10/2019 | 14/10/2019 | 09/10/2019 | 05/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-100 | red | Install Effluent Transfer Pump Station incl Canopy | TT_Task | 17/06/2019 | 27/06/2019 | 14/06/2019 | 11/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-120 | red | Install Large Bore Pipe/Valves on Sleepers | TT_Task | 07/06/2019 | 03/07/2019 | 19/06/2019 | 08/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-130 | red | Install Small Bore Pipe/Valves on Sleepers | TT_Task | 20/06/2019 | 15/07/2019 | 05/06/2019 | 10/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-140 | red | EC+I | TT_Task | 12/06/2019 | 02/07/2019 | 21/05/2019 | 12/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-150 | red | Line Inspection | TT_Task | 31/07/2019 | 08/08/2019 | 17/08/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-160 | red | Hydro Test | TT_Task | 31/08/2019 | 06/09/2019 | 28/09/2019 | 03/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-170 | red | Painting/Insulation | TT_Task | 15/06/2019 | 05/07/2019 | 20/05/2019 | 11/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-180 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 03/10/2019 | 12/10/2019 | 09/10/2019 | 10/02/2020 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-190 | red | Install Effluent Tanks incl Stairs/Platforms - Skid | TT_Task | 30/04/2019 | 18/05/2019 | 13/05/2019 | 26/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-200 | red | Install Effluent Treatment Dispossal to Existing Station | TT_Task | 30/10/2019 | 09/12/2019 | 14/10/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-210 | red | Install Sump Pumps | TT_Task | 01/04/2019 | 23/05/2019 | 01/04/2019 | 28/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-220 | red | Install Piping Support Steelwork at Effluent Plant | TT_Task | 13/04/2019 | 25/04/2019 | 13/04/2019 | 10/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-240 | red | Install Effluent Chemical (Caustic/Sulfuric Acid) Equipment | TT_Task | 30/04/2019 | 17/05/2019 | 20/05/2019 | 27/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-250 | red | Install Large Bore Pipe/Valves - Remaining Sections to Pumps &amp; U/G TP | TT_Task | 25/05/2019 | 19/06/2019 | 25/05/2019 | 27/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00GM-01-260 | red | Install Small Bore Pipe/Valves - Remaining Sections to Pumps &amp; U/G TP | TT_Task | 25/05/2019 | 19/06/2019 | 25/05/2019 | 12/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-01-10 | red | Install Equipment/Skids/Pumps | TT_Task | 15/04/2019 | 06/05/2019 | 15/04/2019 | 17/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-01-20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 02/04/2019 | 06/05/2019 | 02/04/2019 | 24/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-01-30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 27/05/2019 | 05/06/2019 | 16/05/2019 | 23/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-01-50 | red | Line Inspection | TT_Task | 31/07/2019 | 07/08/2019 | 10/08/2019 | 02/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-01-60 | red | Hydro Test | TT_Task | 02/09/2019 | 10/09/2019 | 28/09/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-01-80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 04/10/2019 | 10/10/2019 | 08/10/2019 | 31/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-01-90 | blue | Assumption Underground System Available | TT_FinMile | 28/03/2020 | 28/03/2020 | 21/11/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-100 | red | Install Equipment/Skids/Pumps | TT_Task | 15/04/2019 | 06/05/2019 | 17/04/2019 | 09/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-110 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 30/04/2019 | 23/05/2019 | 15/05/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-120 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 13/05/2019 | 21/05/2019 | 13/05/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-130 | red | EC+I | TT_Task | 21/05/2019 | 04/06/2019 | 21/05/2019 | 27/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-140 | red | Line Inspection | TT_Task | 31/07/2019 | 08/08/2019 | 10/08/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-150 | red | Hydro Test | TT_Task | 31/08/2019 | 09/09/2019 | 28/09/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-160 | red | Painting/Insulation | TT_Task | 04/07/2019 | 12/07/2019 | 25/07/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10GM-02-170 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 04/10/2019 | 14/10/2019 | 09/10/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS
00GA10 | red | Install Equipment/Skids/Pumps | TT_Task | 16/04/2019 | 30/04/2019 | 18/04/2019 | 10/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00GA20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 30/04/2019 | 21/05/2019 | 14/05/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00GA30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 10/05/2019 | 31/05/2019 | 10/05/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00GA40 | red | EC+I | TT_Task | 22/05/2019 | 01/06/2019 | 22/05/2019 | 27/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00GA60 | red | Hydro Test | TT_Task | 28/03/2020 | 02/04/2020 | 04/08/2019 | 09/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00GA70 | red | Painting/Insulation | TT_Task | 22/05/2019 | 01/06/2019 | 22/05/2019 | 03/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00GA80 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 03/04/2020 | 08/04/2020 | 10/08/2019 | 15/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBH20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 01/04/2019 | 27/04/2019 | 01/04/2019 | 03/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBH30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 13/04/2019 | 07/05/2019 | 13/04/2019 | 03/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBH40 | red | NDE | TT_Task | 13/04/2019 | 10/05/2019 | 13/04/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBH50 | red | EC+I | TT_Task | 22/05/2019 | 14/06/2019 | 22/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBH60 | red | Line Inspection | TT_Task | 03/09/2019 | 09/09/2019 | 26/09/2019 | 08/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBH70 | red | Hydro Test | TT_Task | 04/10/2019 | 12/10/2019 | 30/09/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBH80 | red | Painting/Insulation | TT_Task | 29/07/2019 | 14/08/2019 | 26/07/2019 | 12/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00MBH90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 21/10/2019 | 29/10/2019 | 05/10/2019 | 14/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00MKG20 | red | Install Large Bore Pipe/Valves/Supports | TT_Task | 01/04/2019 | 02/05/2019 | 01/04/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00MKG30 | red | Install Small Bore Pipe/Valves/Supports | TT_Task | 13/03/2019 | 06/04/2019 | 01/03/2019 | 25/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00MKG40 | red | NDE | TT_Task | 02/04/2019 | 07/05/2019 | 02/04/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00MKG50 | red | EC+I | TT_Task | 14/05/2019 | 06/06/2019 | 14/05/2019 | 25/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00MKG60 | red | Line Inspection | TT_Task | 03/08/2019 | 12/08/2019 | 22/08/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00MKG70 | red | Hydro Test | TT_Task | 30/09/2019 | 09/10/2019 | 18/10/2019 | 22/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00MKG80 | red | Painting/Insulation | TT_Task | 14/05/2019 | 06/06/2019 | 14/05/2019 | 23/12/2019 | 0 | TK_Complete | CCGTD1_IPS
00MKG90 | red | Pre-Commissioning/Flushing/Cleaning | TT_Task | 03/10/2019 | 12/10/2019 | 25/10/2019 | 23/12/2019 | 0 | TK_Complete | CCGTD1_IPS
10BAT10 | red | Cable Raceway | TT_Task | 01/04/2019 | 25/04/2019 | 03/04/2019 | 02/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BAT120 | red | Precommissioning | TT_Task | 02/08/2019 | 14/08/2019 | 12/08/2019 | 19/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10BAT20 | red | BAT Transformer Installation Programme | TT_Task | 21/02/2019 | 20/05/2019 | 06/02/2019 | 26/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10BAT30 | red | Install, grout 30 Support Plates in Foundation | TT_Task | 30/04/2019 | 06/05/2019 | 30/04/2019 | 07/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BAT50 | red | Cable Pulling | TT_Task | 02/05/2019 | 06/06/2019 | 02/05/2019 | 26/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10BAT90 | red | Cable Termination | TT_Task | 25/05/2019 | 06/06/2019 | 14/05/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10BFT100 | red | Hi Pot Testing | TT_Task | 26/06/2019 | 06/07/2019 | 29/06/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10SFC-10 | red | Cable Raceway | TT_Task | 02/04/2019 | 16/04/2019 | 02/04/2019 | 16/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10SFC-20 | red | SFC Transformer Installation Programme | TT_Task | 25/03/2019 | 11/04/2019 | 27/03/2019 | 04/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10SFC-40 | red | Cable Pulling | TT_Task | 11/04/2019 | 15/05/2019 | 11/03/2019 | 17/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10SFC-50 | red | Cable Termination | TT_Task | 05/06/2019 | 17/06/2019 | 25/05/2019 | 20/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10SFC-70 | red | Hi Pot Testing | TT_Task | 28/06/2019 | 04/07/2019 | 25/06/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10SFC-80 | red | Precommissioning | TT_Task | 03/08/2019 | 15/08/2019 | 24/08/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
101BBT20 | red | BBT Transformer Installation Programme | TT_Task | 11/03/2019 | 30/04/2019 | 20/03/2019 | 03/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10BBT10 | red | Cable Raceway | TT_Task | 02/04/2019 | 16/04/2019 | 02/04/2019 | 03/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BBT50 | red | Cable Termination | TT_Task | 07/05/2019 | 24/05/2019 | 07/05/2019 | 20/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10BBT60 | red | Cable Pulling | TT_Task | 25/03/2019 | 26/04/2019 | 11/03/2019 | 07/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10BBT70 | red | Hi Pot Testing | TT_Task | 06/06/2019 | 20/06/2019 | 28/06/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10BBT90 | red | Precommissioning | TT_Task | 12/08/2019 | 26/08/2019 | 28/08/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SEE-10 | red | Cable Raceway | TT_Task | 02/04/2019 | 16/04/2019 | 02/04/2019 | 14/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10SEE-20 | red | SEE Transformer Installation Programme | TT_Task | 25/03/2019 | 11/04/2019 | 27/03/2019 | 04/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10SEE-40 | red | Cable Pulling | TT_Task | 11/04/2019 | 25/05/2019 | 11/03/2019 | 27/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10SEE-50 | red | Cable Termination | TT_Task | 25/06/2019 | 11/07/2019 | 10/05/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10SEE-70 | red | Hi Pot Testing | TT_Task | 08/07/2019 | 17/07/2019 | 16/07/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10SEE2-80 | red | Precommissioning | TT_Task | 02/09/2019 | 13/09/2019 | 02/09/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10BHT-10 | red | Cable Raceway | TT_Task | 22/02/2019 | 15/03/2019 | 01/03/2019 | 13/03/2019 | 0 | TK_Complete | CCGTD1_IPS
10BHT-20 | red | LV Transformer Installation Programme (7 days x 4 transformers) | TT_Task | 11/03/2019 | 03/04/2019 | 27/03/2019 | 12/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10BHT-40 | red | Cable Pulling | TT_Task | 18/04/2019 | 16/05/2019 | 13/03/2019 | 20/03/2019 | 0 | TK_Complete | CCGTD1_IPS
10BHT-50 | red | Cable Termination | TT_Task | 03/05/2019 | 13/05/2019 | 03/05/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10BHT-70 | red | Hi Pot Testing | TT_Task | 15/06/2019 | 27/06/2019 | 15/06/2019 | 23/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10BHT-80 | red | Precommissioning | TT_Task | 31/07/2019 | 12/08/2019 | 24/07/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10BAC10 | red | Install Generator Circuit Breaker (GCB) onto Support Steel | TT_Task | 18/06/2019 | 04/07/2019 | 14/05/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10BAC20 | red | Install Control Panel | TT_Task | 05/07/2019 | 11/07/2019 | 06/05/2019 | 27/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10BAC30 | red | Precommissioning | TT_Task | 31/07/2019 | 10/08/2019 | 27/07/2019 | 01/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10BAC40 | red | Test | TT_Task | 12/08/2019 | 22/08/2019 | 02/08/2019 | 03/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA10 | red | Installation of IPB Cabinet (Neut. Grd, Sec CT, Earthing, Pressure Red., H2 Purge) | TT_Task | 13/05/2019 | 29/05/2019 | 13/05/2019 | 06/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA100 | red | IPB Connection to Generator &amp; Generator Breaker after HI Voltage Test | TT_Task | 12/07/2019 | 16/07/2019 | 13/05/2019 | 07/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA110 | red | IPB Connection at Main Transformer &amp; Auxiliary Transformers after HI Voltage Test | TT_Task | 29/08/2019 | 31/08/2019 | 13/07/2019 | 24/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA120 | red | Installation of Surge Arrestor | TT_Task | 18/07/2019 | 23/07/2019 | 06/07/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA130 | red | IPB Connection at ExcitationTransformer &amp; SFC Transformer after HI Voltage Test | TT_Task | 02/09/2019 | 04/09/2019 | 17/08/2019 | 07/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA140 | red | IPB Connection at Main Transformer &amp; Auxiliary Transformers after HI Voltage Test | TT_Task | 02/09/2019 | 04/09/2019 | 15/08/2019 | 07/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA150 | red | Close Inspection Cover | TT_Task | 08/11/2019 | 08/11/2019 | 08/11/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA160 | red | Air Leakage Test | TT_Task | 10/09/2019 | 13/09/2019 | 21/09/2019 | 25/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA170 | red | Precommissioning | TT_Task | 09/11/2019 | 12/11/2019 | 09/11/2019 | 12/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA20 | red | Install Steel Structure @ Generator Area | TT_Task | 01/04/2019 | 23/05/2019 | 01/04/2019 | 23/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA30 | red | Install/Align/Weld IPB | TT_Task | 01/06/2019 | 03/07/2019 | 16/05/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA40 | red | NDE | TT_Task | 04/06/2019 | 10/07/2019 | 20/05/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA50 | red | Install Support Steel Transformer Area | TT_Task | 26/04/2019 | 10/05/2019 | 26/04/2019 | 24/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA60 | red | Install Air Piping from Pressure Reducing Cubicle to Taps @ IPB Enclosure | TT_Task | 14/05/2019 | 22/05/2019 | 14/05/2019 | 07/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA70 | red | Install Air Piping from Pressure Reducing Cubicle to Taps @ IPB Enclosure | TT_Task | 18/07/2019 | 22/07/2019 | 27/07/2019 | 07/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA80 | red | Installation of Short Circuit Devise | TT_Task | 26/06/2019 | 03/07/2019 | 15/06/2019 | 20/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10BA90 | red | Hi Potential Test | TT_Task | 02/09/2019 | 07/09/2019 | 02/09/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10CHA30 | red | Set Generator Protection Panel, Align &amp; Bolt | TT_Task | 30/04/2019 | 08/05/2019 | 30/04/2019 | 06/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10CHA40 | red | Install Generator Protection Panel Relays | TT_Task | 04/06/2019 | 11/06/2019 | 07/05/2019 | 24/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10CHA50 | red | Install Cable Tray | TT_Task | 30/04/2019 | 25/05/2019 | 30/04/2019 | 13/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10CHA60 | red | Cable Pulling &amp; Terminations | TT_Task | 25/05/2019 | 15/06/2019 | 15/05/2019 | 02/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CHA70 | red | Hi Pot | TT_Task | 13/06/2019 | 20/06/2019 | 26/06/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CHA80 | red | Precommissioning | TT_Task | 02/08/2019 | 12/08/2019 | 24/08/2019 | 30/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKB30 | red | Set Excitation Control &amp; Circuit Breaker Panels, Align &amp; Bolt | TT_Task | 04/06/2019 | 12/06/2019 | 20/05/2019 | 17/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKB40 | red | Install Relays | TT_Task | 12/06/2019 | 19/06/2019 | 21/05/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKB50 | red | Install Cable Tray | TT_Task | 04/06/2019 | 22/06/2019 | 07/05/2019 | 21/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKB60 | red | Cable Puling &amp; Terminations | TT_Task | 22/06/2019 | 17/07/2019 | 22/05/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKB70 | red | Hi Pot | TT_Task | 18/06/2019 | 24/06/2019 | 27/06/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKB80 | red | Precommissioning | TT_Task | 03/08/2019 | 08/08/2019 | 28/08/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKB200 | red | Set Static Start-up Panel &amp; Switichgear, Align &amp; Bolt | TT_Task | 15/04/2019 | 25/04/2019 | 27/03/2019 | 23/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKB210 | red | Install Relays | TT_Task | 17/06/2019 | 24/06/2019 | 14/05/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKB220 | red | Install Cable Tray | TT_Task | 03/05/2019 | 25/05/2019 | 11/03/2019 | 08/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKB230 | red | Cable Puling &amp; Terminations | TT_Task | 25/05/2019 | 17/06/2019 | 11/03/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKB240 | red | Hi Pot | TT_Task | 10/07/2019 | 17/07/2019 | 17/07/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10MKB250 | red | Precommissioning | TT_Task | 06/08/2019 | 10/08/2019 | 06/08/2019 | 08/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10BH10 | red | Switchgear Cubicles Installation/ Bolting | TT_Task | 08/04/2019 | 16/05/2019 | 10/04/2019 | 09/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BH20 | red | Cable Raceway | TT_Task | 02/04/2019 | 16/04/2019 | 01/03/2019 | 30/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10BH30 | red | Protection Panel | TT_Task | 09/05/2019 | 24/05/2019 | 09/05/2019 | 24/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BH40 | red | UPS/DC Cable Pulling | TT_Task | 24/05/2019 | 10/06/2019 | 20/05/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10BH41 | red | Distribution Panel | TT_Task | 10/06/2019 | 25/06/2019 | 14/05/2019 | 16/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BH50 | red | Bus Torquing/Connection | TT_Task | 25/06/2019 | 09/07/2019 | 20/05/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10BH60 | red | Hi Pot Testing | TT_Task | 16/07/2019 | 31/07/2019 | 16/07/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00BHV10 | red | Switchgear Cubicles Installation/ Bolting | TT_Task | 08/04/2019 | 03/05/2019 | 10/04/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00BHV20 | red | Cable Raceway | TT_Task | 27/02/2019 | 21/03/2019 | 11/02/2019 | 27/04/2019 | 0 | TK_Complete | CCGTD1_IPS
00BHV30 | red | Protection Panel | TT_Task | 11/05/2019 | 15/05/2019 | 11/05/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00BHV40 | red | UPS/DC Cable Pulling | TT_Task | 16/05/2019 | 01/06/2019 | 16/05/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00BHV50 | red | Distribution Panel | TT_Task | 03/06/2019 | 06/06/2019 | 12/05/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00BHV60 | red | Bus Torquing/Connection | TT_Task | 06/06/2019 | 11/06/2019 | 17/05/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00BHV70 | red | Hi Pot Testing | TT_Task | 22/07/2019 | 26/07/2019 | 15/06/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10BF10 | red | Switchgear Cubicles Installation/ Bolting | TT_Task | 02/04/2019 | 24/05/2019 | 10/03/2019 | 03/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BF20 | red | Cable Raceway | TT_Task | 02/04/2019 | 06/04/2019 | 01/03/2019 | 17/04/2019 | 0 | TK_Complete | CCGTD1_IPS
10BF30 | red | Protection Panel | TT_Task | 16/04/2019 | 20/04/2019 | 16/04/2019 | 04/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BF40 | red | UPS/DC Cable Pulling | TT_Task | 04/05/2019 | 09/05/2019 | 04/05/2019 | 17/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BF50 | red | Distribution Panel | TT_Task | 09/05/2019 | 14/05/2019 | 09/05/2019 | 14/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BF60 | red | Bus Torquing/Connection | TT_Task | 14/05/2019 | 18/05/2019 | 14/05/2019 | 18/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BF70 | red | Hi Pot Testing | TT_Task | 18/05/2019 | 23/05/2019 | 18/05/2019 | 25/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BBE10 | red | Switchgear Cubicles Installation/ Bolting | TT_Task | 01/04/2019 | 26/04/2019 | 10/03/2019 | 02/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BBE20 | red | Cable Raceway | TT_Task | 01/04/2019 | 18/04/2019 | 01/03/2019 | 14/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BBE30 | red | Protection Panel | TT_Task | 15/04/2019 | 02/05/2019 | 15/04/2019 | 09/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BBE40 | red | UPS/DC Cable Pulling | TT_Task | 13/04/2019 | 03/05/2019 | 13/04/2019 | 27/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10BBE50 | red | Bus Torquing | TT_Task | 29/04/2019 | 08/05/2019 | 29/04/2019 | 20/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BBE60 | red | Hi Pot Testing | TT_Task | 18/06/2019 | 03/07/2019 | 04/06/2019 | 13/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10BBE70 | red | Install &amp; Test 6.6kV Switchgear Panel x 2 | TT_Task | 01/03/2018 | 06/03/2018 | 22/02/2018 | 26/02/2018 | 0 | TK_Complete | CCGTD1_IPS
10BBE80 | blue | Ready for Energization from Temp. Feed | TT_FinMile | 09/09/2019 | 09/09/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10BBE90 | red | Pull Temp. MV Cable from Existing Station MV | TT_Task | 31/07/2019 | 20/08/2019 | 03/06/2019 | 20/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10AC10 | red | Installation of Gas Insulated Line - GIL | TT_Task | 08/04/2019 | 03/05/2019 | 10/04/2019 | 20/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10AC20 | red | Cable Raceway | TT_Task | 21/05/2019 | 24/05/2019 | 14/05/2019 | 20/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10AC30 | red | Protection Panel | TT_Task | 18/06/2019 | 22/06/2019 | 17/05/2019 | 24/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10AC40 | red | UPS/DC Cable Pulling | TT_Task | 22/06/2019 | 27/06/2019 | 22/05/2019 | 31/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10AC50 | red | Bus Torquing | TT_Task | 27/06/2019 | 03/07/2019 | 23/05/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10AC60 | red | Hi Pot Testing | TT_Task | 27/06/2019 | 03/07/2019 | 27/06/2019 | 02/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10AC70 | red | Connection of HV Cable to 400Kv Building | TT_Task | 20/06/2019 | 29/06/2019 | 20/06/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10BT10 | red | Switchgear Cubicles Installation/ Bolting | TT_Task | 01/04/2019 | 17/04/2019 | 09/04/2019 | 08/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BT20 | red | Cable Raceway | TT_Task | 30/04/2019 | 13/05/2019 | 30/04/2019 | 13/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BT30 | red | Protection Panel | TT_Task | 13/04/2019 | 17/04/2019 | 13/04/2019 | 17/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BT40 | red | UPS/DC Cable Pulling | TT_Task | 14/05/2019 | 30/05/2019 | 14/05/2019 | 24/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10BT50 | red | Distribution Panel | TT_Task | 31/05/2019 | 04/06/2019 | 21/05/2019 | 24/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10BT60 | red | Bus Torquing/Connection | TT_Task | 05/06/2019 | 12/06/2019 | 21/05/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10BT70 | red | Hi Pot Testing | TT_Task | 12/06/2019 | 15/06/2019 | 23/05/2019 | 25/07/2019 | 0 | TK_Complete | CCGTD1_IPS
ECS19.1210 | red | Installation of Batteries, Battery Charger, Converter &amp; Inverter and UPS System | TT_Task | 09/05/2019 | 05/06/2019 | 09/05/2019 | 18/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-01-10 | red | Install Cabling | TT_Task | 18/06/2019 | 13/07/2019 | 24/05/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-01-20 | red | Install Accessories/Supports | TT_Task | 01/04/2019 | 23/04/2019 | 01/04/2019 | 18/05/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-01-30 | red | Install equipment | TT_Task | 20/05/2019 | 08/06/2019 | 13/05/2019 | 29/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-01-40 | red | Install Primary Containment | TT_Task | 10/06/2019 | 13/06/2019 | 15/05/2019 | 16/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-01-50 | red | Install Secondary Containment | TT_Task | 13/06/2019 | 18/06/2019 | 24/05/2019 | 17/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-01-60 | red | Test | TT_Task | 02/08/2019 | 07/08/2019 | 17/08/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-02-10 | red | Lay the Earthing Conductors from the Equipment to Designated Earth Pit | TT_Task | 17/06/2019 | 23/07/2019 | 21/05/2019 | 23/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-02-20 | red | Install Accessories/Supports/Mounting Fitting | TT_Task | 01/04/2019 | 12/04/2019 | 10/04/2019 | 10/05/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-02-30 | red | Install equipment | TT_Task | 12/04/2019 | 27/04/2019 | 12/04/2019 | 19/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-02-40 | red | Install Secondary Containment | TT_Task | 31/05/2019 | 05/07/2019 | 22/05/2019 | 18/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-02-50 | red | Install Primary Containment | TT_Task | 23/05/2019 | 27/06/2019 | 20/05/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-02-60 | red | Test | TT_Task | 10/09/2019 | 16/09/2019 | 07/09/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-02-80 | red | Complete all Terminations | TT_Task | 06/06/2019 | 29/06/2019 | 15/06/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-03-10 | red | Install Cabling | TT_Task | 31/05/2019 | 24/06/2019 | 22/06/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-03-20 | red | Install Accessories/Supports/Mounting/Fittings | TT_Task | 01/04/2019 | 06/05/2019 | 08/04/2019 | 17/05/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-03-30 | red | Install Equipment | TT_Task | 15/05/2019 | 15/06/2019 | 15/05/2019 | 03/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-03-40 | red | Install Primary Containment | TT_Task | 29/05/2019 | 27/06/2019 | 20/05/2019 | 16/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-03-50 | red | Install Secondary Containment | TT_Task | 15/06/2019 | 10/07/2019 | 20/05/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-03-60 | red | Test | TT_Task | 09/08/2019 | 14/08/2019 | 28/08/2019 | 08/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-03-70 | red | Install All Termination Rods | TT_Task | 21/06/2019 | 06/07/2019 | 23/05/2019 | 31/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-03-80 | red | Install Downcomers | TT_Task | 31/05/2019 | 27/06/2019 | 22/06/2019 | 22/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00BAW-03-90 | blue | Assumption Underground Grid Complete | TT_FinMile | 17/12/2019 | 17/12/2019 | 28/08/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
A2220 | red | Installation of Gas Detection and System | TT_Task | 30/04/2019 | 03/06/2019 | 07/05/2019 | 22/05/2019 | 0 | TK_Complete | CCGTD1_IPS
ECS20.1030 | red | Installation of instrument, equipment and cable for gas detection system for Gas Turbine &amp; Auxiliaries | TT_Task | 23/05/2019 | 15/06/2019 | 23/05/2019 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS
FSS22.1140 | red | Installation of Gas Detection System for BOP | TT_Task | 30/04/2019 | 01/08/2019 | 07/03/2019 | 08/01/2020 | 0 | TK_Complete | CCGTD1_IPS
A2330 | red | Lighting and Small Power Installation &amp; Commissioning FW Area | TT_Task | 31/05/2019 | 12/06/2019 | 31/05/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
A3320 | red | Installation Lighting and Small Power | TT_Task | 01/04/2019 | 04/05/2019 | 01/04/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CP-BZL7-60 | red | Remaining Lighting and Small Power Finished | TT_Task | 30/09/2019 | 30/09/2019 | 11/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CP1BZL7A15 | red | Lighting and Small Power Installation (10UBA) | TT_Task | 22/06/2019 | 10/07/2019 | 22/05/2019 | 24/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10BZL-03-10 | red | Install Accessories/Supports | TT_Task | 22/08/2019 | 07/09/2019 | 01/06/2019 | 03/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10BZL-03-20 | red | Install Primary Containment | TT_Task | 09/09/2019 | 03/10/2019 | 03/07/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10BZL-03-30 | red | Install Secondary Containment | TT_Task | 04/10/2019 | 25/10/2019 | 20/07/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10BZL-03-40 | red | Install Cabling | TT_Task | 04/10/2019 | 01/11/2019 | 14/08/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10BZL-03-50 | blue | Assumption Civil Contractor L&amp;SP Complete | TT_FinMile | 28/03/2020 | 28/03/2020 | 05/02/2020 | 05/02/2020 | 0 | TK_Complete | CCGTD1_IPS
10BZL-01-10 | red | Install Accessories/Supports | TT_Task | 30/09/2019 | 16/10/2019 | 07/10/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10BZL-01-20 | red | Install Primary Containment | TT_Task | 08/10/2019 | 22/10/2019 | 12/10/2019 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10BZL-01-30 | red | Install Secondary Containment | TT_Task | 11/10/2019 | 22/10/2019 | 11/10/2019 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10BZL-01-40 | red | Install Cabling | TT_Task | 17/10/2019 | 28/10/2019 | 11/10/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10BZL-02-10 | red | Install Accessories/Supports | TT_Task | 30/09/2019 | 18/10/2019 | 02/07/2019 | 30/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10BZL-02-20 | red | Install Primary Containment | TT_Task | 11/10/2019 | 28/10/2019 | 02/07/2019 | 30/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10BZL-02-30 | red | Install Secondary Containment | TT_Task | 21/10/2019 | 09/11/2019 | 23/09/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10BZL-02-40 | red | Install Cabling | TT_Task | 05/11/2019 | 25/11/2019 | 03/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00BZL-01-10 | red | Install Accessories/Supports | TT_Task | 15/10/2019 | 26/10/2019 | 05/10/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00BZL-01-30 | red | Install Secondary Containment | TT_Task | 26/10/2019 | 09/11/2019 | 05/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00BZL-01-40 | red | Install Cabling | TT_Task | 09/11/2019 | 23/11/2019 | 05/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00BZL-03-10 | red | Install Accessories/Supports | TT_Task | 30/09/2019 | 14/10/2019 | 04/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00BZL-03-20 | red | Install Primary Containment | TT_Task | 09/10/2019 | 25/10/2019 | 04/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00BZL-03-30 | red | Install Secondary Containment | TT_Task | 21/10/2019 | 06/11/2019 | 04/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00BZL-03-40 | red | Install Cabling | TT_Task | 07/11/2019 | 26/11/2019 | 04/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00BZL-02-10 | red | Install Accessories/Supports | TT_Task | 30/09/2019 | 12/10/2019 | 02/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00BZL-02-30 | red | Install Secondary Containment | TT_Task | 03/10/2019 | 12/10/2019 | 02/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00BZL-02-40 | red | Install Cabling | TT_Task | 05/10/2019 | 15/10/2019 | 02/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00XKA10 | red | Installation of Emergency Diesel Generator Set ( XKA) | TT_Task | 16/07/2019 | 01/08/2019 | 22/07/2019 | 02/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00XKA30 | red | Install Pipework | TT_Task | 26/06/2019 | 17/07/2019 | 01/06/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00XKA40 | red | Cable Raceway | TT_Task | 12/07/2019 | 29/07/2019 | 04/06/2019 | 22/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00XKA50 | red | Pull Cables &amp; Terminate | TT_Task | 18/07/2019 | 03/08/2019 | 06/06/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00XKA60 | red | Precommissioning | TT_Task | 05/10/2019 | 18/10/2019 | 15/10/2019 | 26/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-ST-10 | red | ET200 Cabinet Installation including Supports | TT_Task | 13/04/2019 | 25/04/2019 | 13/04/2019 | 10/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-ST-20 | red | Grounding Supports | TT_Task | 01/04/2019 | 11/04/2019 | 01/04/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-ST-30 | red | AC/DC Installation | TT_Task | 07/06/2019 | 24/06/2019 | 15/06/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-ST-40 | red | Cable Installation | TT_Task | 28/05/2019 | 11/06/2019 | 28/05/2019 | 07/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-ST-50 | red | Communication Cable Installation | TT_Task | 28/05/2019 | 07/06/2019 | 28/05/2019 | 07/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-ST-60 | red | Primary and Secondary Containment Installation | TT_Task | 10/05/2019 | 27/05/2019 | 10/05/2019 | 10/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-ST-70 | red | Test System | TT_Task | 02/08/2019 | 16/08/2019 | 12/08/2019 | 14/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-GT10 | red | ET200 Cabinet Installation including Supports | TT_Task | 01/04/2019 | 11/04/2019 | 05/04/2019 | 15/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-GT20 | red | Grounding Supports | TT_Task | 13/04/2019 | 24/04/2019 | 13/04/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-GT30 | red | AC/DC Installation | TT_Task | 16/05/2019 | 27/05/2019 | 16/05/2019 | 07/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-GT40 | red | Cable Installation | TT_Task | 16/05/2019 | 27/05/2019 | 16/05/2019 | 08/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-GT50 | red | Communication Cable Installation | TT_Task | 28/05/2019 | 07/06/2019 | 28/05/2019 | 08/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-GT60 | red | Primary and Secondary Containment Installation | TT_Task | 13/04/2019 | 24/04/2019 | 13/04/2019 | 10/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-GT70 | red | Test System | TT_Task | 05/08/2019 | 15/08/2019 | 09/08/2019 | 13/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-WS10 | red | ET200 Cabinet Installation including Supports | TT_Task | 17/04/2019 | 27/04/2019 | 17/04/2019 | 15/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-WS20 | red | Grounding Supports | TT_Task | 26/04/2019 | 02/05/2019 | 26/04/2019 | 09/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-WS30 | red | AC/DC Installation | TT_Task | 11/05/2019 | 22/05/2019 | 11/05/2019 | 23/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-WS40 | red | Cable Installation | TT_Task | 23/05/2019 | 03/06/2019 | 23/05/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-WS50 | red | Communication Cable Installation | TT_Task | 23/05/2019 | 03/06/2019 | 23/05/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-WS60 | red | Primary and Secondary Containment Installation | TT_Task | 06/05/2019 | 16/05/2019 | 06/05/2019 | 10/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-WS70 | red | Test System | TT_Task | 05/08/2019 | 16/08/2019 | 06/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-HR10 | red | ET200 Cabinet Installation including Supports | TT_Task | 31/08/2019 | 07/09/2019 | 06/08/2019 | 13/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-HR20 | red | Grounding Supports | TT_Task | 31/05/2019 | 11/06/2019 | 20/05/2019 | 30/05/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-HR30 | red | AC/DC Installation | TT_Task | 04/09/2019 | 10/09/2019 | 14/08/2019 | 20/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-HR40 | red | Cable Installation | TT_Task | 31/08/2019 | 06/09/2019 | 22/08/2019 | 23/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-HR50 | red | Communication Cable Installation | TT_Task | 31/08/2019 | 06/09/2019 | 22/08/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-HR60 | red | Primary and Secondary Containment Installation | TT_Task | 31/08/2019 | 06/09/2019 | 06/08/2019 | 13/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-HR70 | red | Test System | TT_Task | 31/08/2019 | 03/09/2019 | 26/08/2019 | 26/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-AA10 | red | ET200 Cabinet Installation including Supports | TT_Task | 30/09/2019 | 10/10/2019 | 25/07/2019 | 31/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-AA20 | red | Grounding Supports | TT_Task | 30/09/2019 | 10/10/2019 | 25/07/2019 | 31/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-AA30 | red | AC/DC Installation | TT_Task | 03/10/2019 | 09/10/2019 | 31/07/2019 | 07/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-AA40 | red | Cable Installation | TT_Task | 30/09/2019 | 09/10/2019 | 01/08/2019 | 09/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-AA50 | red | Communication Cable Installation | TT_Task | 30/09/2019 | 11/10/2019 | 01/08/2019 | 09/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-AA60 | red | Primary and Secondary Containment Installation | TT_Task | 30/09/2019 | 11/10/2019 | 25/07/2019 | 31/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10CP-AA70 | red | Test System | TT_Task | 30/09/2019 | 08/10/2019 | 10/08/2019 | 13/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CP-BZP7A15 | red | Erection Cable Trays Between UEY/UGY01 to UGD/USG/UGA/UGC/UEN | TT_Task | 01/04/2019 | 23/05/2019 | 01/04/2019 | 05/06/2019 | 0 | TK_Complete | CCGTD1_IPS
CP-BZP7B15 | red | Erection Cable Trays Between 10UBA Building to UEY/10UEN | TT_Task | 21/01/2019 | 27/02/2019 | 21/01/2019 | 08/05/2019 | 0 | TK_Complete | CCGTD1_IPS
CP1BZP7A15 | red | Erection Cable Trays UMC to Generator (1f) | TT_Task | 02/01/2019 | 22/02/2019 | 13/11/2018 | 15/05/2019 | 0 | TK_Complete | CCGTD1_IPS
CP1BZP7C15 | red | Erection Cable Trays 10UBA Building to UBX/UBE/UBF | TT_Task | 02/01/2019 | 20/02/2019 | 22/10/2018 | 15/05/2019 | 0 | TK_Complete | CCGTD1_IPS
CP1BZP7C25 | red | Cable Support Installation | TT_Task | 01/04/2019 | 27/06/2019 | 01/04/2019 | 19/06/2019 | 0 | TK_Complete | CCGTD1_IPS
CP1BZP7D15 | red | Erection Cable Trays 10UBA Building to USA01-03 | TT_Task | 01/04/2019 | 23/05/2019 | 01/04/2019 | 14/06/2019 | 0 | TK_Complete | CCGTD1_IPS
CP1BZP7F15 | red | Erection Cable Trays UMC to ST AND PUMPS (1d) | TT_Task | 01/04/2019 | 17/05/2019 | 01/04/2019 | 15/06/2019 | 0 | TK_Complete | CCGTD1_IPS
CP1BZP7G15 | red | Erection Cable Trays UMC to GT (1e) | TT_Task | 12/02/2019 | 25/03/2019 | 15/01/2019 | 21/05/2019 | 0 | TK_Complete | CCGTD1_IPS
CP-BZK7A25 | red | Cabling From 10UBA Building to UCA / UYC | TT_Task | 03/06/2019 | 02/07/2019 | 03/05/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CP-BZK7B2 | red | Cabling From 10UBA Building to UAA | TT_Task | 30/04/2019 | 04/06/2019 | 06/05/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CP-BZK7C25 | red | Cabling 10UBA Building to 00UGD/UGA/UGC | TT_Task | 27/05/2019 | 02/07/2019 | 02/05/2019 | 31/05/2019 | 0 | TK_Complete | CCGTD1_IPS
CP-BZK7E25 | red | Cabling 10UBA Building to USG | TT_Task | 30/04/2019 | 04/06/2019 | 08/05/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CP-BZK7F25 | red | Cabling 10UBA Building to UEL/UEH/UEJ | TT_Task | 30/04/2019 | 10/06/2019 | 03/05/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CP-BZK7G25 | red | Cabling From 10UBA (Switchgear) Building to 10UBN Diesel Generator | TT_Task | 18/07/2019 | 21/08/2019 | 01/06/2019 | 06/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CP-BZK7H25 | red | Cabling From 10UBA Building to ULA (FW Pumps)/UHA (HRSG) AND UHW (Blow Down Tank) | TT_Task | 24/05/2019 | 10/07/2019 | 24/05/2019 | 06/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CP-BZK7I25 | red | Cabling From 10UBA Building to UST | TT_Task | 01/04/2019 | 06/05/2019 | 08/04/2019 | 05/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CP1BZK7A25 | red | Cabling From 10UBA (Switchgear) Building to UBX/UBE/UBF (Transformers) | TT_Task | 16/04/2019 | 27/05/2019 | 16/04/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CP1BZK7B25 | red | Cabling Between 10UBA Building | TT_Task | 14/02/2019 | 18/03/2019 | 20/02/2019 | 31/05/2019 | 0 | TK_Complete | CCGTD1_IPS
CP1BZK7B35 | red | MV and LV Cable Pulling | TT_Task | 30/04/2019 | 21/09/2019 | 10/05/2019 | 09/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CP1BZK7D25 | red | Cabling 10UBA (Switchgear) Building to 10UEN (Gas Filter/Preheating) | TT_Task | 17/06/2019 | 12/07/2019 | 17/05/2019 | 02/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CP1BZK7J25 | red | Cabling From 10UBA Building to USA01-03 | TT_Task | 05/06/2019 | 11/07/2019 | 14/06/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CP-CYP7A15 | red | Erection Security Other Buildings (Except UCA) | TT_Task | 30/11/2019 | 28/12/2019 | 04/11/2019 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CP-CYP7A25 | red | Install Equipment | TT_Task | 31/08/2019 | 30/09/2019 | 20/08/2019 | 13/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CP-CYP7A35 | red | EC+I | TT_Task | 25/09/2019 | 19/10/2019 | 20/08/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CP-CYP7A45 | red | Precommissioning | TT_Task | 04/04/2020 | 08/04/2020 | 14/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
00SGA-01-10 | red | Install Skids/Euipment (Firehouse) | TT_Task | 30/09/2019 | 17/10/2019 | 12/10/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00SGA-01-20 | red | Install LB Pipework/Valves/Supports (Firehouse) | TT_Task | 18/10/2019 | 29/10/2019 | 09/10/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00SGA-01-30 | red | Install SB Pipework/Valves/Supports (Firehouse) | TT_Task | 24/10/2019 | 04/11/2019 | 11/10/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00SGA-01-40 | red | Install Ring Main | TT_Task | 09/02/2019 | 13/06/2019 | 15/01/2019 | 17/01/2020 | 0 | TK_Complete | CCGTD1_IPS
00SGA-01-50 | red | Install all Hydrants/Supports | TT_Task | 14/10/2019 | 30/10/2019 | 14/10/2019 | 06/01/2020 | 0 | TK_Complete | CCGTD1_IPS
00SGA-01-60 | red | EC+I | TT_Task | 12/10/2019 | 06/11/2019 | 09/10/2019 | 18/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00SGA-01-70 | red | Hydro Test | TT_Task | 02/04/2020 | 14/04/2020 | 07/01/2020 | 17/01/2020 | 0 | TK_Complete | CCGTD1_IPS
00SGA-01-80 | red | Precommissioning/Flush/Clean | TT_Task | 08/04/2020 | 14/04/2020 | 12/01/2020 | 17/01/2020 | 0 | TK_Complete | CCGTD1_IPS
00SGA-01-90 | red | Paint | TT_Task | 05/11/2019 | 15/11/2019 | 12/10/2019 | 17/01/2020 | 0 | TK_Complete | CCGTD1_IPS
10SGC-02-10 | red | Install Deluge Pipework/Valves/Sprinklers | TT_Task | 31/07/2019 | 28/08/2019 | 05/08/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGC-02-20 | red | Install Supports | TT_Task | 29/08/2019 | 09/09/2019 | 07/08/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGC-02-30 | red | Hydro Test | TT_Task | 25/10/2019 | 30/10/2019 | 10/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGC-02-40 | red | Precommissioning/Flush/Clean | TT_Task | 30/10/2019 | 04/11/2019 | 10/10/2019 | 14/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGC-02-50 | red | Spray Test | TT_Task | 04/11/2019 | 08/11/2019 | 12/10/2019 | 14/01/2020 | 0 | TK_Complete | CCGTD1_IPS
10SGA-02-10 | red | Install Deluge Pipework/Valves/Sprinklers | TT_Task | 08/08/2019 | 28/08/2019 | 08/08/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGA-02-20 | red | Install Supports | TT_Task | 31/07/2019 | 20/08/2019 | 05/08/2019 | 09/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGA-02-30 | red | Hydro Test | TT_Task | 17/10/2019 | 26/10/2019 | 08/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGA-02-40 | red | Precommissioning/Flush/Clean | TT_Task | 26/10/2019 | 05/11/2019 | 11/10/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGA-02-50 | red | Spray Test | TT_Task | 31/03/2020 | 08/04/2020 | 04/01/2020 | 14/01/2020 | 0 | TK_Complete | CCGTD1_IPS
10SGA-02-60 | red | Provide TEMP Fire Water Supply | TT_Task | 30/11/2019 | 20/12/2019 | 20/11/2019 | 03/01/2020 | 0 | TK_Complete | CCGTD1_IPS
10SGA10 | red | Install LB Pipework/Valves/Supports | TT_Task | 30/09/2019 | 24/10/2019 | 17/09/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGA20 | red | Install SB Pipework/Valves/Supports | TT_Task | 30/09/2019 | 18/10/2019 | 17/09/2019 | 14/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGA30 | red | Install all Hydrants/Supports | TT_Task | 30/09/2019 | 12/10/2019 | 17/09/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGA40 | red | Hydro Test | TT_Task | 14/10/2019 | 18/10/2019 | 14/10/2019 | 18/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGA50 | red | Precommissioning/Flush/Clean | TT_Task | 18/10/2019 | 23/10/2019 | 19/10/2019 | 17/01/2020 | 0 | TK_Complete | CCGTD1_IPS
10SGA60 | red | Provide TEMP Fire Water Supply | TT_Task | 30/11/2019 | 11/12/2019 | 20/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
00SGM-01-10 | red | Install Pipework/Valves/Sprinklers | TT_Task | 08/10/2019 | 05/11/2019 | 23/05/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00SGM-01-20 | red | Install Supports | TT_Task | 19/10/2019 | 11/11/2019 | 23/05/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00SGM-01-30 | red | Hydro Test | TT_Task | 11/10/2019 | 15/10/2019 | 11/10/2019 | 15/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00SGM-01-40 | red | Precommissioning/Flush/Clean | TT_Task | 16/10/2019 | 19/10/2019 | 16/10/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
00SGM-01-50 | red | Spray Test | TT_Task | 28/03/2020 | 01/04/2020 | 07/03/2020 | 12/03/2020 | 0 | TK_Complete | CCGTD1_IPS
10SGC-01-10 | red | Install Deluge Pipework/Valves/Sprinklers | TT_Task | 25/10/2019 | 16/11/2019 | 19/08/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGC-01-20 | red | Install Supports | TT_Task | 30/09/2019 | 24/10/2019 | 27/05/2019 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGC-01-30 | red | Hydro Test | TT_Task | 01/11/2019 | 05/11/2019 | 09/10/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGC-01-40 | red | Precommissioning/Flush/Clean | TT_Task | 06/11/2019 | 09/11/2019 | 12/10/2019 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGC-01-50 | red | Spray Test | TT_Task | 09/04/2020 | 13/04/2020 | 14/03/2020 | 17/03/2020 | 0 | TK_Complete | CCGTD1_IPS
10SGJ-02-10 | red | Install Skid+Auxiliaries | TT_Task | 30/09/2019 | 15/10/2019 | 08/10/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGJ-02-20 | red | Install all pipepwork and Supports | TT_Task | 31/07/2019 | 12/09/2019 | 05/07/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGJ-02-30 | red | EC+I | TT_Task | 16/10/2019 | 12/11/2019 | 14/10/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10SGJ-02-40 | red | Hydro Test | TT_Task | 28/03/2020 | 06/04/2020 | 26/12/2019 | 04/01/2020 | 0 | TK_Complete | CCGTD1_IPS
10SGJ-02-50 | red | Precommissioning/Flush/Clean | TT_Task | 28/03/2020 | 06/04/2020 | 26/12/2019 | 04/01/2020 | 0 | TK_Complete | CCGTD1_IPS
FSS22.1060 | red | Installation of Fire Fighting CO2 System for PCC 10SGJ | TT_Task | 11/10/2019 | 27/11/2019 | 05/07/2019 | 05/01/2020 | 0 | TK_Complete | CCGTD1_IPS
A3220 | red | Installation Fire Detection System (SGY) | TT_Task | 15/02/2019 | 19/06/2019 | 15/02/2019 | 20/01/2020 | 0 | TK_Complete | CCGTD1_IPS
00CY10 | red | Equipment Installation | TT_Task | 01/04/2019 | 17/04/2019 | 16/04/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00CY20 | red | Cable Raceways | TT_Task | 23/04/2019 | 18/05/2019 | 23/04/2019 | 27/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00CY30 | red | Cable Pulling | TT_Task | 07/06/2019 | 03/07/2019 | 30/05/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
00CY40 | red | Cable Termination | TT_Task | 12/07/2019 | 05/08/2019 | 12/06/2019 | 02/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00CY50 | red | Precommissioning | TT_Task | 03/09/2019 | 13/09/2019 | 03/09/2019 | 20/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10CY10 | red | Erection Telecommunication Other Buildings (Except UCA) | TT_Task | 24/04/2019 | 30/05/2019 | 24/04/2019 | 03/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CY20 | red | Cable Raceways | TT_Task | 06/06/2019 | 08/07/2019 | 25/05/2019 | 26/06/2019 | 0 | TK_Complete | CCGTD1_IPS
10CY30 | red | Cable Pulling | TT_Task | 18/06/2019 | 12/07/2019 | 13/06/2019 | 10/08/2019 | 0 | TK_Complete | CCGTD1_IPS
10CY40 | red | Cable Termination | TT_Task | 29/06/2019 | 24/07/2019 | 29/06/2019 | 05/09/2019 | 0 | TK_Complete | CCGTD1_IPS
10CY50 | red | Precommissioning | TT_Task | 31/08/2019 | 12/09/2019 | 06/09/2019 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
00CR10 | red | Cable Tray Installation (Under Floor) | TT_Task | 06/11/2018 | 04/12/2018 | 20/11/2018 | 31/01/2019 | 0 | TK_Complete | CCGTD1_IPS
00CR100 | red | Printer Installation | TT_Task | 01/06/2019 | 04/06/2019 | 22/06/2019 | 20/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00CR15 | red | Install Floor | TT_Task | 01/04/2019 | 13/04/2019 | 03/04/2019 | 07/05/2019 | 0 | TK_Complete | CCGTD1_IPS
00CR20 | red | I/O Cabinet Installation | TT_Task | 29/01/2019 | 01/03/2019 | 10/10/2018 | 04/03/2019 | 0 | TK_Complete | CCGTD1_IPS
00CR30 | red | Control Cabinet Installation | TT_Task | 27/02/2019 | 15/03/2019 | 10/10/2018 | 12/03/2019 | 0 | TK_Complete | CCGTD1_IPS
00CR40 | red | Engineer Work Station Installation | TT_Task | 12/03/2019 | 26/03/2019 | 15/03/2019 | 21/05/2019 | 0 | TK_Complete | CCGTD1_IPS
00CR50 | red | Operator Work Station Installation | TT_Task | 29/06/2019 | 04/07/2019 | 04/07/2019 | 25/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00CR60 | red | Network/Cabinet Installation | TT_Task | 18/06/2019 | 21/06/2019 | 10/05/2019 | 25/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00CR70 | red | AC/DC System Installation | TT_Task | 18/06/2019 | 20/06/2019 | 14/05/2019 | 28/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00CR80 | red | Hardwire Switches Installation | TT_Task | 07/06/2019 | 13/06/2019 | 22/06/2019 | 27/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00CR90 | red | Furniture Installation | TT_Task | 09/03/2019 | 14/03/2019 | 15/03/2019 | 29/04/2019 | 0 | TK_Complete | CCGTD1_IPS
A3300 | red | Control Room Equipment Installation | TT_Task | 14/06/2019 | 26/06/2019 | 07/05/2019 | 06/07/2019 | 0 | TK_Complete | CCGTD1_IPS
A3310 | red | Installation of Telecommunication System | TT_Task | 22/06/2019 | 02/07/2019 | 13/05/2019 | 06/07/2019 | 0 | TK_Complete | CCGTD1_IPS
ECS19.1420 | red | Cable Laying of Local Control Room | TT_Task | 18/04/2019 | 14/05/2019 | 18/04/2019 | 26/06/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUS10 | red | Equipment Installation | TT_Task | 16/04/2019 | 27/04/2019 | 17/04/2019 | 24/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUS100 | red | EC+I | TT_Task | 16/07/2019 | 25/07/2019 | 13/06/2019 | 27/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUS110 | red | Precommissioning | TT_Task | 31/07/2019 | 09/08/2019 | 15/06/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUS20 | red | Booster Pump Install | TT_Task | 11/06/2019 | 20/06/2019 | 11/06/2019 | 23/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUS30 | red | Auto Wash Strainer Install | TT_Task | 15/06/2019 | 26/06/2019 | 15/06/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUS40 | red | Chlorinated Cell Module Install | TT_Task | 20/06/2019 | 02/07/2019 | 15/06/2019 | 27/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUS50 | red | Fresh Air Blower Install | TT_Task | 26/06/2019 | 06/07/2019 | 12/06/2019 | 23/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUS60 | red | XXX and Contineous Dosing Install | TT_Task | 02/07/2019 | 12/07/2019 | 11/06/2019 | 24/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUS70 | red | Fume Scrubber Install | TT_Task | 08/07/2019 | 17/07/2019 | 15/06/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUS80 | red | Acid Tank and Acid Cleaning Install | TT_Task | 15/07/2019 | 25/07/2019 | 15/06/2019 | 26/07/2019 | 0 | TK_Complete | CCGTD1_IPS
00PUS90 | red | Sump Pump Install | TT_Task | 10/07/2019 | 20/07/2019 | 13/06/2019 | 25/07/2019 | 0 | TK_Complete | CCGTD1_IPS
10HSJ100 | red | Equipment Installation | TT_Task | 06/12/2019 | 13/12/2019 | 04/11/2019 | 19/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10HSJ110 | red | EC+I | TT_Task | 09/12/2019 | 16/12/2019 | 04/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
10HSJ120 | red | Precommissioning | TT_Task | 06/12/2019 | 14/12/2019 | 25/11/2019 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
10HSJ130 | red | Function Test | TT_Task | 03/04/2020 | 11/04/2020 | 11/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM1000 | black | Demin Water available for Construction | TT_Mile | 23/05/2019 | 23/05/2019 | 22/05/2019 | 22/05/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1310 | red | LUN to CLP for Energisation of Electrical cabinet 10GHC10GH001/2 on 30-Aug | TT_Task | 28/08/2019 | 02/09/2019 | 28/08/2019 | 29/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1350 | red | Energisation of Electrical Cabinet 10GHC10GH001/2 | TT_Task | 31/08/2019 | 05/09/2019 | 03/09/2019 | 03/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1400 | red | Cold Commissioning of Electrical Cabinet and Pump Motors | TT_Task | 31/08/2019 | 05/09/2019 | 04/09/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1420 | red | Preparation for System Flushing | TT_Task | 04/09/2019 | 09/09/2019 | 04/09/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1520 | red | System flushing | TT_Task | 31/08/2019 | 05/09/2019 | 09/09/2019 | 09/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1560 | red | System restoration post flush | TT_Task | 31/08/2019 | 05/09/2019 | 10/09/2019 | 14/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1590 | blue | Handover of TOP-10GHC-01 | TT_FinMile | 12/09/2019 | 12/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1600 | blue | Handover of TOP-10GHC-02 | TT_FinMile | 12/09/2019 | 12/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1610 | blue | Handover of TOP-10GHC-03 | TT_FinMile | 12/09/2019 | 12/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1630 | red | System Commissioning | TT_Task | 31/08/2019 | 05/09/2019 | 16/09/2019 | 16/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3020 | red | Draining of system for finalising the tie-in works for dosing system | TT_Task | 31/08/2019 | 05/09/2019 | 13/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1830 | blue | Handover of TOP 10PGB | TT_FinMile | 31/08/2019 | 31/08/2019 | 30/09/2019 | 30/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1840 | red | Rotation checks and motor solo runs incl re-coupling in preparation for flushing | TT_Task | 31/08/2019 | 05/09/2019 | 30/09/2019 | 30/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1880 | red | Investigation works on elevated vibrations during motor solo runs for PGB11&amp;12AP001 | TT_Task | 31/08/2019 | 05/09/2019 | 02/10/2019 | 02/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1910 | red | Prep for additional grouting works for baseframe of PGB11&amp;12AP001 | TT_Task | 31/08/2019 | 05/09/2019 | 03/10/2019 | 03/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1930 | red | Additional grouting works for baseframe of PGB11&amp;12AP001 | TT_Task | 31/08/2019 | 05/09/2019 | 04/10/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1990 | red | Re-testing of motor solo run after grouting | TT_Task | 31/08/2019 | 05/09/2019 | 09/10/2019 | 09/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2050 | red | Coupling of pump &amp; setup for initial pump operation | TT_Task | 31/08/2019 | 05/09/2019 | 10/10/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2100 | red | Filling of baseframe with concrete and preparation for final grouting | TT_Task | 31/08/2019 | 05/09/2019 | 11/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2170 | red | Curing time for concrete grouting ongoing | TT_Task | 31/08/2019 | 05/09/2019 | 14/10/2019 | 14/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2210 | red | Motor solo run and coupling / fist flushing operation | TT_Task | 31/08/2019 | 05/09/2019 | 15/10/2019 | 15/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2260 | red | System flushing | TT_Task | 31/08/2019 | 05/09/2019 | 16/10/2019 | 24/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2440 | red | Oil draining | TT_Task | 31/08/2019 | 05/09/2019 | 24/10/2019 | 28/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2590 | red | Restoration ongoing, prepare for filling | TT_Task | 31/08/2019 | 05/09/2019 | 29/10/2019 | 13/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3480 | red | Refilling System, adjusting flowrates (pending finalization of reinstatements) | TT_Task | 02/07/2020 | 07/07/2020 | 12/11/2019 | 16/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3490 | red | Refilling System, adjusting flowrates (pending finalization of reinstatements) | TT_Task | 02/07/2020 | 07/07/2020 | 19/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3500 | red | System in operation, adjusting flowrates | TT_Task | 02/07/2020 | 07/07/2020 | 27/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3510 | red | System in service for flushing | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1110 | blue | Handover of TOP 10-CP-ST | TT_FinMile | 15/08/2019 | 15/08/2019 | 15/08/2019 | 15/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1200 | red | Loading of APs for ST | TT_Task | 20/08/2019 | 20/08/2019 | 20/08/2019 | 20/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1390 | red | Cold Commissioning | TT_Task | 03/09/2019 | 07/09/2019 | 03/09/2019 | 09/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3300 | red | cold commissioning MA-01 | TT_Task | 02/07/2020 | 07/07/2020 | 21/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1130 | blue | Handover of TOP 10MAV-01 | TT_FinMile | 16/08/2019 | 16/08/2019 | 16/08/2019 | 16/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1240 | red | Preparation for Loop checking | TT_Task | 21/08/2019 | 26/08/2019 | 21/08/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1270 | red | Loop Checking | TT_Task | 26/08/2019 | 30/08/2019 | 26/08/2019 | 05/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1380 | red | Preparation for flushing | TT_Task | 03/09/2019 | 07/09/2019 | 03/09/2019 | 05/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1450 | blue | Handover of TOP 10MAV-02 | TT_FinMile | 05/09/2019 | 05/09/2019 | 05/09/2019 | 05/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1455 | blue | Handover of TOP 10MAV-03 | TT_FinMile | 05/09/2019 | 05/09/2019 | 27/03/2020 | 27/03/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM1465 | red | Turning gear operation &amp; adjustment of oil system tosupport GT turning gear | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1475 | red | Topping up of main oil tank to normal operation Level | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1485 | red | System offline for HCO inspection | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 06/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM1490 | red | Setup for Commissioning Oil Flushing | TT_Task | 31/08/2019 | 05/09/2019 | 06/09/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1530 | red | Commissioning Oil flushing | TT_Task | 31/08/2019 | 05/09/2019 | 10/09/2019 | 13/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1580 | red | Connection of DC Lube Oil Pump for flushing | TT_Task | 31/08/2019 | 05/09/2019 | 12/09/2019 | 12/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1620 | red | Electrical commissioning of DC oil pump | TT_Task | 31/08/2019 | 05/09/2019 | 13/09/2019 | 17/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1820 | red | Preparation for installation of new feeder for MAV24AP001 | TT_Task | 31/08/2019 | 05/09/2019 | 30/09/2019 | 30/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1870 | red | Removal of current feeder &amp; Preparation for installation of new feeder MAV24AP001 | TT_Task | 31/08/2019 | 05/09/2019 | 02/10/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1980 | red | Finalisation of Cabling Works for new feeder for DC Pump | TT_Task | 31/08/2019 | 05/09/2019 | 09/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2160 | red | Test Run of MAV24AP001 after feeder exchange | TT_Task | 31/08/2019 | 05/09/2019 | 14/10/2019 | 14/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2200 | red | Preparation works for draining oil from main lube oil tank (construction activity) | TT_Task | 31/08/2019 | 05/09/2019 | 15/10/2019 | 15/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2250 | red | Continuation of oil draining from tank (construction) | TT_Task | 31/08/2019 | 05/09/2019 | 16/10/2019 | 18/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2370 | red | Preparation for inspection/cleaning works (Construction) | TT_Task | 21/10/2019 | 25/10/2019 | 21/10/2019 | 22/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2400 | red | Inspection of Oil tank | TT_Task | 31/08/2019 | 05/09/2019 | 23/10/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2510 | red | Oil Tank refilling, pending cleanliness inspection | TT_Task | 31/08/2019 | 05/09/2019 | 28/10/2019 | 28/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2580 | red | Oil Tank cleanliness inspection | TT_Task | 31/08/2019 | 05/09/2019 | 29/10/2019 | 29/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2610 | red | Oil Tank refilling ongoing | TT_Task | 31/08/2019 | 05/09/2019 | 30/10/2019 | 31/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2670 | red | Normalization of system | TT_Task | 31/08/2019 | 05/09/2019 | 02/11/2019 | 02/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2730 | red | lube oil flushing ongoing | TT_Task | 31/08/2019 | 05/09/2019 | 04/11/2019 | 13/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2990 | red | Restoration ongoing | TT_Task | 31/08/2019 | 05/09/2019 | 13/11/2019 | 16/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4970 | red | System operation | TT_Task | 02/07/2020 | 07/07/2020 | 13/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM1430 | red | System setup for lube oil flushing | TT_Task | 31/08/2019 | 05/09/2019 | 05/09/2019 | 10/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1460 | blue | Handover of TOP 10MAD | TT_FinMile | 31/08/2019 | 31/08/2019 | 06/09/2019 | 06/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2480 | blue | Handover of TOP 10MAW | TT_FinMile | 31/08/2019 | 31/08/2019 | 26/10/2019 | 26/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3030 | red | Pneumatic valve commissioning | TT_Task | 31/08/2019 | 05/09/2019 | 14/11/2019 | 18/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3360 | red | Valve commissioning | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4980 | red | Seal steam commissioning | TT_Task | 02/07/2020 | 07/07/2020 | 16/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM1090 | blue | Handover of TOP 10CP-GT | TT_FinMile | 08/08/2019 | 08/08/2019 | 08/08/2019 | 08/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1210 | red | Loading of APs for GT | TT_Task | 20/08/2019 | 24/08/2019 | 20/08/2019 | 22/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1340 | red | Cold Commissioning | TT_Task | 31/08/2019 | 05/09/2019 | 03/09/2019 | 02/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1920 | red | Engineering updates for GT system | TT_Task | 31/08/2019 | 05/09/2019 | 03/10/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3290 | red | cold commissioning (MBP/MBA) | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3310 | red | cold commissioning (VGV/IGV) | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3320 | red | cold commissioning MBA50 | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1260 | red | Energisation of motor &amp; loop checks to support construction flushing | TT_Task | 26/08/2019 | 30/08/2019 | 26/08/2019 | 27/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2360 | red | Cold commissioning in preparation for first pressurization | TT_Task | 31/08/2019 | 05/09/2019 | 21/10/2019 | 29/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2560 | blue | Handover of TOP 10MBX | TT_FinMile | 28/10/2019 | 28/10/2019 | 28/10/2019 | 28/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2790 | red | Initial pressurization of system, valve commissioning | TT_Task | 31/08/2019 | 05/09/2019 | 05/11/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1440 | red | System setup for lube oil flushing | TT_Task | 31/08/2019 | 05/09/2019 | 05/09/2019 | 09/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1470 | blue | Handover of TOP 10MBV | TT_FinMile | 31/08/2019 | 31/08/2019 | 06/09/2019 | 06/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1640 | red | Operation of lifting oil system to support construction works | TT_Task | 31/08/2019 | 05/09/2019 | 16/09/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3410 | red | Commissioning of turning gear system | TT_Task | 02/07/2020 | 07/07/2020 | 21/11/2019 | 14/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3420 | red | First GT turning Gear | TT_Task | 02/07/2020 | 07/07/2020 | 23/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3430 | red | System in operation for air leak test ( if required) | TT_Task | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2780 | red | IGV/VGV comissioning | TT_Task | 31/08/2019 | 05/09/2019 | 05/11/2019 | 08/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3100 | blue | Handover of TOP 10MBA | TT_FinMile | 31/08/2019 | 31/08/2019 | 21/11/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3380 | red | IGV/VGV | TT_Task | 02/07/2020 | 07/07/2020 | 13/11/2019 | 16/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3390 | red | IGV/VGV | TT_Task | 02/07/2020 | 07/07/2020 | 20/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3400 | red | Commissioning of HCO system | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4710 | red | Commissioning of HCO system - system restored | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 09/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4720 | red | GT protection testing | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 08/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM1780 | blue | Handover of 10MBX2x | TT_FinMile | 31/08/2019 | 31/08/2019 | 29/09/2019 | 29/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3040 | red | Pneumatic valve commisioning | TT_Task | 31/08/2019 | 05/09/2019 | 14/11/2019 | 19/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2300 | red | Motor rotation checks | TT_Task | 31/08/2019 | 05/09/2019 | 17/10/2019 | 18/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2460 | blue | Handover of TOP 10MKF | TT_FinMile | 31/08/2019 | 31/08/2019 | 25/10/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2530 | red | Initial filling &amp; flushing of system | TT_Task | 31/08/2019 | 05/09/2019 | 28/10/2019 | 07/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2860 | red | Flushing on HOLD | TT_Task | 31/08/2019 | 05/09/2019 | 08/11/2019 | 13/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3440 | red | System flushing | TT_Task | 02/07/2020 | 07/07/2020 | 11/11/2019 | 13/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3450 | red | System flushing pending filter delivery | TT_Task | 02/07/2020 | 07/07/2020 | 20/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3460 | red | System flushing pending filter delivery | TT_Task | 02/07/2020 | 07/07/2020 | 27/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3470 | red | System restoration | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 11/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1700 | red | Prep of Pumps for Construction oil flushing | TT_Task | 31/08/2019 | 05/09/2019 | 20/09/2019 | 20/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1730 | red | Support prep for Construction oil flushing | TT_Task | 31/08/2019 | 05/09/2019 | 23/09/2019 | 26/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1760 | red | Restoration Works after Construction Flushing completion | TT_Task | 31/08/2019 | 05/09/2019 | 27/09/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2110 | blue | Handover of TOP 10MAX | TT_FinMile | 31/08/2019 | 31/08/2019 | 12/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1940 | blue | Handover of TOP 00SCB | TT_FinMile | 31/08/2019 | 31/08/2019 | 04/10/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2000 | red | Initial pressurizing of compressed air skid | TT_Task | 31/08/2019 | 05/09/2019 | 09/10/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2060 | red | Preparation for piping service test and air blow | TT_Task | 31/08/2019 | 05/09/2019 | 10/10/2019 | 11/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2180 | red | System operation and preparation for air blow of system piping | TT_Task | 31/08/2019 | 05/09/2019 | 14/10/2019 | 14/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2310 | blue | Handover of TOP 10SCB | TT_FinMile | 31/08/2019 | 31/08/2019 | 19/10/2019 | 19/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2380 | red | Preparation for air blow out | TT_Task | 31/08/2019 | 05/09/2019 | 22/10/2019 | 23/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2430 | red | Initial air blow out @12.00 | TT_Task | 31/08/2019 | 05/09/2019 | 24/10/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2550 | red | Service test completed, system normalised | TT_Task | 31/08/2019 | 05/09/2019 | 28/10/2019 | 31/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2220 | red | Rotation check and motor solo run for vibration check (LCA51/52AP001) | TT_Task | 31/08/2019 | 05/09/2019 | 15/10/2019 | 18/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3110 | blue | Handover of TOP 10LCA | TT_FinMile | 31/08/2019 | 31/08/2019 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3330 | red | cold commissioning, preparation for oil flushing (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 20/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3340 | red | cold commissioning, preparation for oil flushing (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 27/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3350 | red | System in service for flushing | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 13/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2740 | blue | Handover of TOP 10LAB | TT_FinMile | 31/08/2019 | 31/08/2019 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2800 | red | Cold commissioning | TT_Task | 31/08/2019 | 05/09/2019 | 05/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2840 | red | Check of interlocks, commissioning of components | TT_Task | 31/08/2019 | 05/09/2019 | 07/11/2019 | 11/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2920 | red | Blow out of sysem branch lines, service test | TT_Task | 31/08/2019 | 05/09/2019 | 12/11/2019 | 13/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3050 | black | System in service | TT_Mile | 31/08/2019 | 31/08/2019 | 14/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2910 | blue | Handover of TOP 10QFB-01 | TT_FinMile | 31/08/2019 | 31/08/2019 | 11/11/2019 | 11/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3520 | red | system commissioning, leakage check and air blow | TT_Task | 02/07/2020 | 07/07/2020 | 31/10/2019 | 02/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3530 | red | system commissioning, leakage check and air blow | TT_Task | 02/07/2020 | 07/07/2020 | 12/11/2019 | 16/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3120 | blue | Handover of TOP 10QFB-02 | TT_FinMile | 02/09/2019 | 02/09/2019 | 05/12/2019 | 05/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3540 | red | system commissioning, leakage check and air blow (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 11/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3550 | red | system commissioning, leakage check and air blow (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 26/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3560 | red | System blow out | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 10/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3130 | blue | Handover of TOP 10QFB-03 | TT_FinMile | 02/07/2020 | 02/07/2020 | 12/02/2020 | 12/02/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM1120 | blue | Handover of TOP 10BT-01 | TT_FinMile | 16/08/2019 | 16/08/2019 | 16/08/2019 | 16/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1160 | red | Acid Filling UBA-0104 | TT_Task | 20/08/2019 | 20/08/2019 | 20/08/2019 | 20/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1230 | red | Battery charging (First Bank) | TT_Task | 21/08/2019 | 26/08/2019 | 21/08/2019 | 22/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1250 | red | Preparation for Battery charging (Second Bank) | TT_Task | 26/08/2019 | 30/08/2019 | 26/08/2019 | 26/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1290 | red | Battery charging (Second Bank) | TT_Task | 27/08/2019 | 28/08/2019 | 27/08/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1950 | red | Discharge test from 1st Bank | TT_Task | 31/08/2019 | 05/09/2019 | 09/10/2019 | 09/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2020 | red | Preparation for 2nd Discharge test | TT_Task | 31/08/2019 | 05/09/2019 | 10/10/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2080 | red | 2nd Discharge test | TT_Task | 31/08/2019 | 05/09/2019 | 11/10/2019 | 16/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1050 | blue | Handover of TOP 10BBA | TT_FinMile | 19/07/2019 | 19/07/2019 | 19/07/2019 | 19/07/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1060 | red | Cold Commissioning | TT_Task | 29/07/2019 | 02/08/2019 | 29/07/2019 | 24/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1280 | red | Initial Interlock testing | TT_Task | 26/08/2019 | 30/08/2019 | 26/08/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1330 | red | Interlock testing with CLP | TT_Task | 31/08/2019 | 05/09/2019 | 30/08/2019 | 30/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1360 | red | Feeder commissioning | TT_Task | 03/09/2019 | 07/09/2019 | 03/09/2019 | 10/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1510 | blue | Energisation of BMT01 | TT_FinMile | 31/08/2019 | 31/08/2019 | 09/09/2019 | 09/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2340 | red | Feeder commissioning - 10MBU25AP001 | TT_Task | 31/08/2019 | 05/09/2019 | 21/10/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2500 | red | Feeder commissioning - 10LCB11/12AP001 | TT_Task | 31/08/2019 | 05/09/2019 | 28/10/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2640 | red | Rotation check - 10MBU25AP001 | TT_Task | 31/08/2019 | 05/09/2019 | 31/10/2019 | 31/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2770 | red | De-energization of BBA for LCAL works inside MV room | TT_Task | 31/08/2019 | 05/09/2019 | 05/11/2019 | 12/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2970 | red | Primary injection start planned at 9am | TT_Task | 31/08/2019 | 05/09/2019 | 13/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3070 | red | MV feeder commissioning | TT_Task | 31/08/2019 | 05/09/2019 | 15/11/2019 | 20/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3210 | red | Feeder commissioning 10LAC11/12AP001,10PAC11/12AP001 | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3240 | red | Supporting MV motor test runs | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 14/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4570 | red | De-energization of BBB for civil completion works inside room 206 | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 07/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4580 | red | Re-energization of BBB busbar | TT_Task | 02/07/2020 | 07/07/2020 | 08/01/2020 | 08/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM1150 | blue | Handover of TOP 10CP-BOP-01 | TT_FinMile | 17/08/2019 | 17/08/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1550 | red | Cold Commissioning | TT_Task | 31/08/2019 | 05/09/2019 | 10/09/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1850 | red | Cold Commissioning - PGB Signal checks | TT_Task | 31/08/2019 | 05/09/2019 | 30/09/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3570 | red | I&amp;C Commissioning EK,EG and PA System | TT_Task | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4600 | red | I&amp;C Commissioning EK,EG and PA System | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4850 | red | I&amp;C Commissioning EK,EG and PA System | TT_Task | 02/07/2020 | 07/07/2020 | 13/01/2020 | 16/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM1650 | blue | Handover of TOP 10BFT-01 | TT_FinMile | 31/08/2019 | 31/08/2019 | 18/09/2019 | 18/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1660 | red | Commissioning Works | TT_Task | 31/08/2019 | 05/09/2019 | 18/09/2019 | 23/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1680 | red | Energization | TT_Task | 31/08/2019 | 05/09/2019 | 19/09/2019 | 24/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1300 | blue | Handover of TOP 10BFT-03 | TT_FinMile | 31/08/2019 | 31/08/2019 | 28/08/2019 | 28/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1810 | red | Prep for Energisation (Final checks) | TT_Task | 31/08/2019 | 05/09/2019 | 30/09/2019 | 30/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1860 | red | Energisation | TT_Task | 31/08/2019 | 05/09/2019 | 02/10/2019 | 05/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1320 | blue | Handover of TOP 10BFT-02 | TT_FinMile | 31/08/2019 | 31/08/2019 | 29/08/2019 | 29/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2030 | red | Preparation for Energization | TT_Task | 31/08/2019 | 05/09/2019 | 10/10/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2090 | red | Energization | TT_Task | 31/08/2019 | 05/09/2019 | 11/10/2019 | 16/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2150 | red | Review of Interlcok with CLP / ARUP | TT_Task | 31/08/2019 | 05/09/2019 | 14/10/2019 | 14/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2190 | red | Energization of BFT04 &amp; BFT05 | TT_Task | 31/08/2019 | 05/09/2019 | 15/10/2019 | 15/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2240 | red | De-Energization of BFT04 &amp; BFT05 for completion of | TT_Task | 31/08/2019 | 05/09/2019 | 16/10/2019 | 16/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2280 | red | BFT04 / BFT05 Energized | TT_Task | 31/08/2019 | 05/09/2019 | 17/10/2019 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2820 | blue | Handover of TOP 10BHV-01 | TT_FinMile | 31/08/2019 | 31/08/2019 | 07/11/2019 | 07/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1070 | blue | Handover of TOP 10BF-01 | TT_FinMile | 29/07/2019 | 29/07/2019 | 29/07/2019 | 29/07/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1080 | blue | Handover of TOP-10BF-01 | TT_FinMile | 29/07/2019 | 29/07/2019 | 29/07/2019 | 29/07/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1190 | red | System Commissioning &amp; Energisation of Components (UBA-0204,0205) | TT_Task | 20/08/2019 | 24/08/2019 | 20/08/2019 | 23/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1370 | red | Prep work for LV Board Energization via BMT01 | TT_Task | 03/09/2019 | 07/09/2019 | 03/09/2019 | 05/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1480 | blue | LV Board ready for energisation via BMT01 | TT_FinMile | 31/08/2019 | 31/08/2019 | 06/09/2019 | 06/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1540 | blue | BMT01 Energized | TT_FinMile | 31/08/2019 | 31/08/2019 | 10/09/2019 | 10/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3250 | red | Energisation of first components upon requirements | TT_Task | 18/11/2019 | 21/12/2019 | 18/11/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4590 | red | Energisation of first components upon requirements | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM1140 | blue | Handover of TOP 10BAT | TT_FinMile | 31/08/2019 | 31/08/2019 | 17/08/2019 | 17/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1670 | red | Partial draining of oil for inspection at bushings | TT_Task | 31/08/2019 | 05/09/2019 | 19/09/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1690 | red | Inspection of Internal bushing connection to Phase B | TT_Task | 31/08/2019 | 05/09/2019 | 20/09/2019 | 21/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1710 | red | Preparation for rectification works | TT_Task | 31/08/2019 | 05/09/2019 | 23/09/2019 | 27/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1740 | red | Inspection with Client Consultant Engineer | TT_Task | 31/08/2019 | 05/09/2019 | 25/09/2019 | 28/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1790 | red | FRA Test with STGZ | TT_Task | 31/08/2019 | 05/09/2019 | 30/09/2019 | 30/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1890 | red | Prep Work - awaiting material delivery confirmation) | TT_Task | 31/08/2019 | 05/09/2019 | 02/10/2019 | 09/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2010 | red | Start Rectification Works - exchange of insulation boards and installaiton of spacer | TT_Task | 31/08/2019 | 05/09/2019 | 10/10/2019 | 10/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2070 | red | Exchange of flange on neutral bushing &amp; preparation for transformer testing prior to final close up | TT_Task | 31/08/2019 | 05/09/2019 | 11/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2130 | red | Vacuum pulling ongoing in preparation for oil filling | TT_Task | 31/08/2019 | 05/09/2019 | 14/10/2019 | 16/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2270 | red | 24hr vacuum hold prior to oil filling | TT_Task | 31/08/2019 | 05/09/2019 | 17/10/2019 | 18/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2330 | red | Oil Circulation and sampling | TT_Task | 31/08/2019 | 05/09/2019 | 21/10/2019 | 23/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2410 | red | Cool down of oil in preparation for testing - Dirana test scheduled | TT_Task | 31/08/2019 | 05/09/2019 | 24/10/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2490 | red | Continuation of transformer testing - Winding resistance test | TT_Task | 31/08/2019 | 05/09/2019 | 28/10/2019 | 28/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2570 | red | Dirana Test | TT_Task | 31/08/2019 | 05/09/2019 | 29/10/2019 | 30/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2630 | red | Signal checks | TT_Task | 31/08/2019 | 05/09/2019 | 30/10/2019 | 02/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2700 | red | Finalization of commissioning | TT_Task | 31/08/2019 | 05/09/2019 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2750 | red | Preparation for primary injection test | TT_Task | 31/08/2019 | 05/09/2019 | 05/11/2019 | 09/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2870 | red | Final check for readiness | TT_Task | 31/08/2019 | 05/09/2019 | 11/11/2019 | 11/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2930 | red | Ready for Primary injection test | TT_Task | 31/08/2019 | 05/09/2019 | 12/11/2019 | 12/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2950 | red | Primary injection planned at 9am | TT_Task | 31/08/2019 | 05/09/2019 | 13/11/2019 | 13/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3060 | red | Signal checks oil analyzer (DGA) | TT_Task | 31/08/2019 | 05/09/2019 | 15/11/2019 | 19/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3065 | red | 400V Injection from GIS side (pending release from CLP) | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 19/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3075 | red | final check for readiness for BE / walkdown | TT_Task | 02/07/2020 | 07/07/2020 | 28/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3085 | red | Outage works | TT_Task | 02/07/2020 | 07/07/2020 | 11/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3140 | red | DGA Signal exchange CCR-LDC | TT_Task | 02/07/2020 | 07/07/2020 | 19/11/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3150 | red | Interlock/Intertrip for BE | TT_Task | 19/11/2019 | 23/11/2019 | 20/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3160 | red | Re-Energization | TT_Task | 02/07/2020 | 07/07/2020 | 14/12/2019 | 15/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3170 | red | Re-Energization | TT_Task | 02/07/2020 | 07/07/2020 | 21/12/2019 | 22/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3190 | red | final check for readiness for BE | TT_Task | 02/07/2020 | 07/07/2020 | 21/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1100 | blue | Handover of TOP 10CHA | TT_FinMile | 31/08/2019 | 31/08/2019 | 12/08/2019 | 12/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1750 | red | Cold Commissioning (Software loading) | TT_Task | 26/09/2019 | 02/10/2019 | 26/09/2019 | 30/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1800 | red | Preparation for Interlock testing | TT_Task | 31/08/2019 | 05/09/2019 | 30/09/2019 | 02/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1900 | red | Interlock testing &amp; prep for sec injection | TT_Task | 31/08/2019 | 05/09/2019 | 03/10/2019 | 04/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1960 | red | Interlock testing &amp; sec injection | TT_Task | 31/08/2019 | 05/09/2019 | 09/10/2019 | 18/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2350 | red | Signal exchange SCB | TT_Task | 31/08/2019 | 05/09/2019 | 21/10/2019 | 21/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2890 | red | Preparation for primary injection test | TT_Task | 31/08/2019 | 05/09/2019 | 11/11/2019 | 12/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3000 | red | Primary injection test | TT_Task | 31/08/2019 | 05/09/2019 | 13/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3080 | red | Implementing requested changes from CLP | TT_Task | 31/08/2019 | 05/09/2019 | 15/11/2019 | 19/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3270 | red | Interlock/Intertrip for BE | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1770 | blue | Handover of TOP 10BA-01 | TT_FinMile | 31/08/2019 | 31/08/2019 | 29/09/2019 | 29/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2690 | blue | Handover of TOP 10BA-02 | TT_FinMile | 31/08/2019 | 31/08/2019 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1500 | blue | Handover of TOP 10BBT | TT_FinMile | 31/08/2019 | 31/08/2019 | 07/09/2019 | 07/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2390 | red | Fans/Pumps cold commissioning | TT_Task | 31/08/2019 | 05/09/2019 | 23/10/2019 | 23/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2420 | red | Signal checks | TT_Task | 31/08/2019 | 05/09/2019 | 24/10/2019 | 31/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2650 | red | Commissioning test | TT_Task | 31/08/2019 | 05/09/2019 | 01/11/2019 | 02/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2710 | red | Finalization of Commissioning | TT_Task | 31/08/2019 | 05/09/2019 | 04/11/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2760 | red | Preparation for primary injection test | TT_Task | 31/08/2019 | 05/09/2019 | 05/11/2019 | 09/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2880 | red | Final check for readiness | TT_Task | 31/08/2019 | 05/09/2019 | 11/11/2019 | 11/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2940 | red | Ready for Primary injection test | TT_Task | 31/08/2019 | 05/09/2019 | 12/11/2019 | 12/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2960 | red | Primary injection test planned at 9am | TT_Task | 31/08/2019 | 05/09/2019 | 13/11/2019 | 13/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3180 | red | 400V Injection from GIS side (pending release from CLP) | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 19/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3200 | red | final check for readiness for BE | TT_Task | 02/07/2020 | 07/07/2020 | 21/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3220 | red | final check for readiness for BE / walkdown | TT_Task | 02/07/2020 | 07/07/2020 | 28/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3230 | red | Outage works | TT_Task | 02/07/2020 | 07/07/2020 | 11/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2450 | blue | Handover of TOP 10CJT | TT_FinMile | 31/08/2019 | 31/08/2019 | 24/10/2019 | 24/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2520 | red | Cold commissioning | TT_Task | 31/08/2019 | 05/09/2019 | 28/10/2019 | 31/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3010 | red | Cold commissioning - primary injection test | TT_Task | 31/08/2019 | 05/09/2019 | 13/11/2019 | 16/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4860 | red | First SFC test runs | TT_Task | 02/07/2020 | 07/07/2020 | 15/01/2020 | 16/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM2470 | blue | Handover of TOP 10MKC | TT_FinMile | 31/08/2019 | 31/08/2019 | 25/10/2019 | 25/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2600 | red | Cold comm - energization of cabinet | TT_Task | 31/08/2019 | 05/09/2019 | 30/10/2019 | 01/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2660 | red | Cold comm - isolation test, ratio test | TT_Task | 31/08/2019 | 05/09/2019 | 02/11/2019 | 02/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2720 | red | Cold comm - current trafo test, voltage trafo test | TT_Task | 31/08/2019 | 05/09/2019 | 04/11/2019 | 06/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2830 | red | Finalizing cold comm - torquing of connections | TT_Task | 31/08/2019 | 05/09/2019 | 07/11/2019 | 07/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2850 | red | Ready for primary injection test | TT_Task | 31/08/2019 | 05/09/2019 | 08/11/2019 | 12/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2980 | red | Primary injection test planned at 9am | TT_Task | 31/08/2019 | 05/09/2019 | 13/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2320 | blue | Handover of TOP 10CKA | TT_FinMile | 31/08/2019 | 31/08/2019 | 20/10/2019 | 20/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3280 | red | CLP Training on the job &amp; commissioning of CKA-03 | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 18/11/2019 | 0 | TK_Complete | CCGTD1_IPS
A4270 | red | Back Engergization | TT_Task | 01/06/2021 | 07/06/2021 | 01/12/2019 | 01/12/2019 | 0 | TK_Complete | CCGTD1_IPS
A4280 | blue | Back Engergization Achieved | TT_FinMile | 01/06/2021 | 01/06/2021 | 01/12/2019 | 01/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2680 | blue | Handover of TOP 10SAM30 | TT_FinMile | 31/08/2019 | 31/08/2019 | 02/11/2019 | 02/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2900 | red | Cold commissioning, rotation checks, commossioning of components | TT_Task | 31/08/2019 | 05/09/2019 | 11/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1010 | blue | Handover of TOP 10CR-02 | TT_FinMile | 04/07/2019 | 04/07/2019 | 04/07/2019 | 04/07/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1020 | blue | Handover of TOP-10CR-02 | TT_FinMile | 04/07/2019 | 04/07/2019 | 04/07/2019 | 04/07/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1030 | blue | Handover of TOP 10CR-01 | TT_FinMile | 15/07/2019 | 15/07/2019 | 15/07/2019 | 15/07/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1040 | blue | Handover of TOP-10CR-01 | TT_FinMile | 15/07/2019 | 15/07/2019 | 15/07/2019 | 15/07/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1170 | red | Server Commissioning CCR (CRY-01) | TT_Task | 20/08/2019 | 24/08/2019 | 20/08/2019 | 23/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1180 | red | Server Commissioning LCR UBA-0202 (CRY-02) | TT_Task | 20/08/2019 | 24/08/2019 | 20/08/2019 | 23/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1220 | red | Simulator Commissioning (CRQ) | TT_Task | 20/08/2019 | 24/08/2019 | 20/08/2019 | 23/08/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1410 | blue | Handover of TOP 10BF-02 | TT_FinMile | 31/08/2019 | 31/08/2019 | 04/09/2019 | 04/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1570 | red | Initial commissioning of LV Busbars | TT_Task | 31/08/2019 | 05/09/2019 | 12/09/2019 | 19/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1720 | red | Commissioning of LV Busbars | TT_Task | 31/08/2019 | 05/09/2019 | 23/09/2019 | 27/09/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM1970 | red | Feeder commissioning - BFTGT002 | TT_Task | 31/08/2019 | 05/09/2019 | 09/10/2019 | 14/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2140 | red | Testing of automatic transfer system (ATS) | TT_Task | 31/08/2019 | 05/09/2019 | 14/10/2019 | 17/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3260 | red | Energisation of first components upon requirements | TT_Task | 18/11/2019 | 21/12/2019 | 18/11/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2040 | red | Preparation for system flushing, rotation check of water transfer pumps | TT_Task | 31/08/2019 | 05/09/2019 | 10/10/2019 | 14/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2120 | blue | Handover of TOP 10MBU-01 | TT_FinMile | 31/08/2019 | 31/08/2019 | 12/10/2019 | 12/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2230 | red | Finalisation of piping by Wai Leun to complete last flushing step | TT_Task | 31/08/2019 | 05/09/2019 | 16/10/2019 | 16/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2290 | red | System flushing (discharge piping) | TT_Task | 31/08/2019 | 05/09/2019 | 17/10/2019 | 18/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2540 | red | Borescope inspection of piping system | TT_Task | 31/08/2019 | 05/09/2019 | 28/10/2019 | 29/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2620 | red | Blow out of gas ring lines | TT_Task | 31/08/2019 | 05/09/2019 | 30/10/2019 | 04/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM2810 | red | Valve commissioning | TT_Task | 31/08/2019 | 05/09/2019 | 06/11/2019 | 11/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3090 | blue | Handover of TOP 10MBP | TT_FinMile | 31/08/2019 | 31/08/2019 | 21/11/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3370 | red | Valve commissioning | TT_Task | 02/07/2020 | 07/07/2020 | 13/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4940 | red | System line up | TT_Task | 02/07/2020 | 07/07/2020 | 15/01/2020 | 17/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4930 | red | Ammonia dosing system line up and chemical filling | TT_Task | 02/07/2020 | 07/07/2020 | 13/01/2020 | 15/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4470 | red | Outage initiation post chem clean, setup of all system isolations | TT_Task | 02/07/2020 | 07/07/2020 | 19/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM5100 | red | Preparation and line up of all systems for first fire | TT_Task | 02/07/2020 | 07/07/2020 | 17/01/2020 | 19/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4440 | red | cold commissioning of hydraulic flaps incl system flushing | TT_Task | 02/07/2020 | 07/07/2020 | 17/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4450 | red | preparation for filling of PAB system | TT_Task | 02/07/2020 | 07/07/2020 | 19/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4790 | red | preparation for filling of PAB system at condenser | TT_Task | 02/07/2020 | 07/07/2020 | 07/01/2020 | 08/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4800 | red | system final line up &amp; first pump operation | TT_Task | 02/07/2020 | 07/07/2020 | 09/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM5080 | red | PAB System commissioning | TT_Task | 02/07/2020 | 07/07/2020 | 14/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM5090 | red | PAB System - First 2 pump operation | TT_Task | 02/07/2020 | 07/07/2020 | 16/01/2020 | 16/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4250 | red | Energization of cabinets/components and I&amp;C checks | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 14/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4420 | red | cold commissioning of intake system | TT_Task | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4430 | red | testing of PAC chamber stoplog - dry and wet testing | TT_Task | 02/07/2020 | 07/07/2020 | 18/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4760 | red | cold commissioning of intake system | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4770 | red | flooding of cooling water intake structure and removal of stoplogs | TT_Task | 02/07/2020 | 07/07/2020 | 07/01/2020 | 08/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4780 | red | wet commissioning of intake systems | TT_Task | 02/07/2020 | 07/07/2020 | 08/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM5070 | red | wet commissioning of intake systems | TT_Task | 02/07/2020 | 07/07/2020 | 15/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4320 | red | Support motor solo runs in fuel oil pumphouse | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 12/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4410 | red | Finalisation of temporary piping works and system line up for flushing | TT_Task | 02/07/2020 | 07/07/2020 | 18/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4750 | red | Finalisation of temporary piping works and system line up for flushing (after FSD inspection) | TT_Task | 02/07/2020 | 07/07/2020 | 09/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM5060 | red | Finalisation of temporary piping works and system line up for flushing (after FSD inspection) | TT_Task | 02/07/2020 | 07/07/2020 | 16/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM3710 | red | Filling, Service test | TT_Task | 02/07/2020 | 07/07/2020 | 29/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4270 | red | Flushing/Chem clean as per schedule | TT_Task | 02/07/2020 | 07/07/2020 | 10/12/2019 | 12/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4480 | red | Chem clean as per schedule | TT_Task | 02/07/2020 | 07/07/2020 | 17/12/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4490 | red | Steam rinsing | TT_Task | 02/07/2020 | 07/07/2020 | 17/12/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4500 | red | initial inspections post chem clean | TT_Task | 02/07/2020 | 07/07/2020 | 19/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3700 | red | Spray deluge test for UBE/UBF/UBG | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 18/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4080 | red | final paint check and touch up where required | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 26/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3690 | red | Hot commissioning of Aux Boilers and safety valve testing | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4070 | red | ready for operation, pending operational licence | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4260 | red | Operation for heating up during chemical clean | TT_Task | 02/07/2020 | 07/07/2020 | 12/12/2019 | 14/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4460 | red | Operation for heating up during chemical clean | TT_Task | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4170 | red | High velocity flushing as per schedule incl heat up and Chem Clean | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4340 | red | Chemical cleaning as per schedule | TT_Task | 02/07/2020 | 07/07/2020 | 16/12/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4620 | red | Inspections post chem clean | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 09/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4640 | red | I&amp;C commissionin of components restored after chem clean | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4670 | red | System line up for filling | TT_Task | 02/07/2020 | 07/07/2020 | 09/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4880 | red | System line up for filling (with QCD) | TT_Task | 02/07/2020 | 07/07/2020 | 13/01/2020 | 15/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4900 | red | Re-filling of HRSG/Water steam | TT_Task | 02/07/2020 | 07/07/2020 | 16/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4920 | red | I&amp;C commissionin of components restored after chem clean | TT_Task | 02/07/2020 | 07/07/2020 | 13/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM3680 | red | cold commissioning/system line up for chemical cleaning | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3930 | red | initial I&amp;C commissioning | TT_Task | 02/07/2020 | 07/07/2020 | 20/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4050 | red | initial I&amp;C commissioning | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4060 | red | cold commissioning/system line up for chemical cleaning | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4160 | red | High velocity flushing as per schedule incl heat up and Chem Clean | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 15/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4330 | red | Chemical cleaning as per schedule | TT_Task | 02/07/2020 | 07/07/2020 | 16/12/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4610 | red | Inspections post chem clean | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 09/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4630 | red | I&amp;C commissionin of components restored after chem clean | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4650 | red | HRSG protection testing | TT_Task | 02/07/2020 | 07/07/2020 | 09/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4660 | red | System line up for filling | TT_Task | 02/07/2020 | 07/07/2020 | 09/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4870 | red | System line up for filling (with QCD) | TT_Task | 02/07/2020 | 07/07/2020 | 13/01/2020 | 15/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4890 | red | Re-filling of HRSG/Water steam | TT_Task | 02/07/2020 | 07/07/2020 | 16/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4910 | red | I&amp;C commissionin of components restored after chem clean | TT_Task | 02/07/2020 | 07/07/2020 | 13/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4400 | red | Cold commissioning, I&amp;C checks with vendor TFA | TT_Task | 02/07/2020 | 07/07/2020 | 17/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4740 | red | Cold commissioning, I&amp;C checks with vendor TFA | TT_Task | 02/07/2020 | 07/07/2020 | 07/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM5040 | red | Cold commissioning, I&amp;C checks with vendor TFA | TT_Task | 02/07/2020 | 07/07/2020 | 13/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM5050 | red | System line up for purging/gas charging | TT_Task | 02/07/2020 | 07/07/2020 | 16/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM3670 | red | TOP Walkdowns as per IFIs | TT_Task | 02/07/2020 | 07/07/2020 | 19/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4040 | red | TOP Walkdowns as per IFIs | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4230 | red | TOP Walkdowns as per IFIs | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 14/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4390 | red | TOP Walkdowns as per IFIs | TT_Task | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4730 | red | TOP Walkdowns as per IFIs | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM5030 | red | TOP Walkdowns as per IFIs | TT_Task | 02/07/2020 | 07/07/2020 | 13/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4380 | red | Continuatuion of air leak testing | TT_Task | 02/07/2020 | 07/07/2020 | 17/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3650 | red | System operation to support GT turning gear | TT_Task | 02/07/2020 | 07/07/2020 | 20/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4030 | red | System operation to support GT turning gear | TT_Task | 02/07/2020 | 07/07/2020 | 27/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4220 | red | System operation to support GT turning gear and fact finding on MKW12AP001 | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 14/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4370 | red | System operation to support GT turning gear and fact finding on MKW12AP001 | TT_Task | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3660 | red | Preparation and system line up for CO2 purging | TT_Task | 02/07/2020 | 07/07/2020 | 09/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM5010 | red | Preparation and system line up for CO2 purging | TT_Task | 02/07/2020 | 07/07/2020 | 13/01/2020 | 14/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM5020 | red | H2 Charging (Date TBC) | TT_Task | 02/07/2020 | 07/07/2020 | 18/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM3640 | red | cold commissioning and first filling | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4020 | red | cold commissioning and first filling | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4690 | red | Condenser cleaning | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 08/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4700 | red | Condenser protection testing | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 07/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4990 | red | Condenser filling | TT_Task | 02/07/2020 | 07/07/2020 | 15/01/2020 | 15/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM5000 | red | First vacuum pulling | TT_Task | 02/07/2020 | 07/07/2020 | 16/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM3630 | red | Initial cold commissioning - signal checks | TT_Task | 02/07/2020 | 07/07/2020 | 20/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4000 | red | Initial cold commissioning, signal checks, system line up for aux. Steam blow (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 27/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4010 | red | Aux. Steam Blow | TT_Task | 02/07/2020 | 07/07/2020 | 30/11/2019 | 01/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4200 | red | System restoration after steam blow | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 11/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4210 | red | System operation for heat up prior to chemical cleaning | TT_Task | 02/07/2020 | 07/07/2020 | 12/12/2019 | 14/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4360 | red | System restoration after steam blow | TT_Task | 02/07/2020 | 07/07/2020 | 16/12/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4680 | red | System restoration | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 08/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4960 | red | System operation with Aux Boiler for seal steam comm | TT_Task | 02/07/2020 | 07/07/2020 | 16/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM3620 | red | cold commissioning and system setup for filling of condenser | TT_Task | 02/07/2020 | 07/07/2020 | 20/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3990 | red | cold commissioning and system setup for filling of condenser (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 27/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3900 | red | TOP pending - cold commissioning | TT_Task | 02/07/2020 | 07/07/2020 | 30/10/2019 | 31/10/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3910 | red | cold commissioning (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 11/11/2019 | 16/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3920 | red | cold commissioning incl motor solo runs incl first pump operation | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3980 | red | cold commissioning incl motor solo runs incl first pump operation | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4190 | red | System in service for flushing | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 14/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4350 | red | System in service | TT_Task | 02/07/2020 | 07/07/2020 | 17/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3610 | red | min flow run (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 15/11/2019 | 16/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3870 | red | min flow run (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 22/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3880 | red | preparation for min flow run, cold comissioning (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 11/11/2019 | 14/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3890 | red | preparation for min flow run, cold comissioning (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3960 | red | preparation for min flow run, cold comissioning (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 28/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3970 | red | min flow run (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 28/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4180 | red | Pump operation for high velocity flushing | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 14/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3600 | red | cold commissioning, preparation for oil flushing (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 12/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3950 | red | cold commissioning, oil flushing, motor rotation checks, motor solo run | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4950 | red | First FWP operation | TT_Task | 02/07/2020 | 07/07/2020 | 17/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM3590 | red | Commissioning of GM-01 system (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 14/11/2019 | 16/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3860 | red | Commissioning of GM-01 system (pending TOP) | TT_Task | 02/07/2020 | 07/07/2020 | 19/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4150 | red | Commissioning of GM-01 system | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 10/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3800 | red | Initial electrical cold commissioning | TT_Task | 02/07/2020 | 07/07/2020 | 19/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3810 | red | Synchronization tests | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 12/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3820 | red | Synchronization tests | TT_Task | 02/07/2020 | 07/07/2020 | 16/12/2019 | 19/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3830 | red | UVTS internal testing/logic checks | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 14/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM3840 | red | Initial ATS internal testing | TT_Task | 02/07/2020 | 07/07/2020 | 11/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM3850 | red | ATS official testing | TT_Task | 02/07/2020 | 07/07/2020 | 14/01/2020 | 15/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM5150 | red | ATS Test | TT_Task | 02/07/2020 | 07/07/2020 | 14/01/2020 | 14/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM3580 | red | pressurisation of bus duct (pressure test for constrcution) | TT_Task | 02/07/2020 | 07/07/2020 | 19/11/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3940 | red | pressurisation of bus duct (pressure test for constrcution) | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 27/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3575 | red | End- to End test: D1 - LDC | TT_Task | 02/07/2020 | 07/07/2020 | 20/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3770 | red | 400V Injection from GIS side (pending release from CLP) | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 19/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3780 | red | Exchange of gasket on GIL &amp; refilling of SF6 | TT_Task | 02/07/2020 | 07/07/2020 | 19/11/2019 | 20/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3790 | red | Exchange of gasket on GIL &amp; refilling of SF6 | TT_Task | 02/07/2020 | 07/07/2020 | 26/11/2019 | 27/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3720 | red | MEP System Commissioining | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 23/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4090 | red | MEP System Commissioining | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4280 | red | MEP System Commissioining | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 14/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4510 | red | MEP System Commissioining | TT_Task | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4810 | red | MEP System Commissioining | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 11/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM5110 | red | MEP System Commissioining | TT_Task | 02/07/2020 | 07/07/2020 | 13/01/2020 | 19/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM3730 | red | Station interface walkdowns for all upcoming terminal points (flushing/cleaning preparation) | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4110 | red | 400kV Backfeed @ 1/12 02:00 | TT_Task | 02/07/2020 | 07/07/2020 | 01/12/2019 | 01/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3740 | red | Backfeed Coordination (HV injection &amp; interlock/intertrip tests) | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 21/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4100 | red | Backfeed Coordination (Document review) | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4310 | red | Issue for BAT re-energization after outage | TT_Task | 09/12/2019 | 13/12/2019 | 10/12/2019 | 13/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4540 | red | Issue for BAT re-energization after outage | TT_Task | 02/07/2020 | 07/07/2020 | 17/12/2019 | 20/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4550 | red | Transformer re-energization work | TT_Task | 02/07/2020 | 07/07/2020 | 22/12/2019 | 22/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM3750 | red | Fresh water fire fight system preparation and spray test | TT_Task | 02/07/2020 | 07/07/2020 | 18/11/2019 | 18/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM5140 | red | Fire Fighting System flushing coordination | TT_Task | 02/07/2020 | 07/07/2020 | 13/01/2020 | 17/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM3760 | red | GHD Tie-in work coordination | TT_Task | 02/07/2020 | 07/07/2020 | 19/11/2019 | 22/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4120 | red | GHD Tie-in work coordination | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 26/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4130 | red | QJA10 / QJA20 Tie-in work coordination | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4290 | red | QJA10 / QJA20 Tie-in work coordination | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 13/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4520 | red | QJA10 / QJA20 Tie-in work coordination | TT_Task | 02/07/2020 | 07/07/2020 | 16/12/2019 | 20/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4140 | red | EG Tie-in work coordination | TT_Task | 02/07/2020 | 07/07/2020 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4300 | red | EG Tie-in work coordination | TT_Task | 02/07/2020 | 07/07/2020 | 09/12/2019 | 13/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4530 | red | EG Tie-in work coordination | TT_Task | 02/07/2020 | 07/07/2020 | 16/12/2019 | 20/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4820 | red | EG Tie-in work coordination | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 10/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM5120 | red | EG Tie-in work coordination | TT_Task | 02/07/2020 | 07/07/2020 | 13/01/2020 | 17/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4240 | red | Rotation checks &amp; motor solo runs for Fuel oil forwarding pumps | TT_Task | 02/07/2020 | 07/07/2020 | 11/12/2019 | 12/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4560 | red | Chemical clean effluent coordination | TT_Task | 02/07/2020 | 07/07/2020 | 16/12/2019 | 21/12/2019 | 0 | TK_Complete | CCGTD1_IPS
CCOM4830 | red | EK purging procedure review | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 10/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM5130 | red | EK purging procedure review | TT_Task | 02/07/2020 | 07/07/2020 | 13/01/2020 | 17/01/2020 | 0 | TK_Complete | CCGTD1_IPS
CCOM4840 | red | Primary protection test discussion | TT_Task | 02/07/2020 | 07/07/2020 | 06/01/2020 | 06/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1360 | black | YOC &amp; PCI Gas Outage [No Gas Available] | TT_Rsrc | 05/02/2020 | 12/02/2020 | 05/02/2020 | 10/02/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 05/02/2020
HCOM1370 | black | BPPS Station Outage | TT_Rsrc | 05/02/2020 | 10/02/2020 | 05/02/2020 | 08/02/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 05/02/2020
HCOM1420 | black | Oil Available | TT_Rsrc | 10/02/2020 | 14/02/2020 | 09/02/2020 | 13/02/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 09/02/2020
HCOM1450 | black | YOC Gas Available | TT_Rsrc | 11/02/2020 | 13/02/2020 | 11/02/2020 | 13/02/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 11/02/2020
HCOM1460 | black | PCI Gas Available | TT_Rsrc | 13/02/2020 | 13/02/2020 | 13/02/2020 | 13/02/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 13/02/2020
HCOM1000 | black | Final Boxing up of HRSG and removal of SCR scaffolding | TT_Rsrc | 25/11/2019 | 29/11/2019 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 25/11/2019
HCOM1010 | black | Scaffolding Dismantling | TT_Rsrc | 25/11/2019 | 29/11/2019 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 25/11/2019
HCOM1020 | black | All Remaining TOPs for Chemical Clean Handed Over | TT_Rsrc | 25/11/2019 | 29/11/2019 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS
HCOM1030 | black | ZTB across road to be in place | TT_Rsrc | 25/11/2019 | 29/11/2019 | 25/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS
HCOM1060 | black | ZXB pressure test | TT_Rsrc | 27/11/2019 | 27/11/2019 | 27/11/2019 | 27/11/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 27/11/2019
HCOM1080 | black | ZTA Leak check | TT_Rsrc | 29/11/2019 | 29/11/2019 | 29/11/2019 | 29/11/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 29/11/2019
HCOM1070 | black | MAG / LCA condensate system recirculation run | TT_Rsrc | 28/11/2019 | 28/11/2019 | 28/11/2019 | 28/11/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 28/11/2019
HCOM1090 | black | Auxiliary Boiler Steam Blow | TT_Rsrc | 02/12/2019 | 02/12/2019 | 30/11/2019 | 30/11/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 29/11/2019
HCOM1100 | black | Commissioning of Systems to Support Chemical Clean | TT_Rsrc | 02/12/2019 | 06/12/2019 | 01/12/2019 | 05/12/2019 | 0 | TK_Complete | CCGTD1_IPS
HCOM1120 | black | High Velocity Flushing | TT_Rsrc | 06/12/2019 | 12/12/2019 | 06/12/2019 | 10/12/2019 | 0 | TK_Complete | CCGTD1_IPS
HCOM1130 | black | Heating Phase &amp; Other Remaining Commissioning | TT_Rsrc | 11/12/2019 | 16/12/2019 | 11/12/2019 | 14/12/2019 | 0 | TK_Complete | CCGTD1_IPS
HCOM1140 | black | Chemical Cleaning | TT_Rsrc | 16/12/2019 | 18/12/2019 | 14/12/2019 | 16/12/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 30/11/2019
HCOM1150 | black | Cooldown, Draining &amp; Rinsing | TT_Rsrc | 16/12/2019 | 18/12/2019 | 16/12/2019 | 18/12/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 30/11/2019
HCOM1160 | black | Work on affected component list | TT_Rsrc | 19/12/2019 | 08/01/2020 | 19/12/2019 | 03/01/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 01/12/2018
HCOM1180 | black | Dosing Commissioning (automatic Operation) | TT_Rsrc | 03/01/2020 | 07/01/2020 | 03/01/2020 | 05/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1190 | black | Commissioning MOVs | TT_Rsrc | 06/01/2020 | 24/01/2020 | 04/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1210 | black | Sampling System Commissioning (automatic operation) | TT_Rsrc | 06/01/2020 | 08/01/2020 | 06/01/2020 | 08/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1220 | black | Commissioning LAB | TT_Rsrc | 10/01/2020 | 20/01/2020 | 10/01/2020 | 16/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1230 | black | Filling HRSG | TT_Rsrc | 17/01/2020 | 20/01/2020 | 17/01/2020 | 18/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1170 | black | Dismantle ZTA &amp; all temporary equipment | TT_Rsrc | 19/12/2019 | 16/01/2020 | 19/12/2019 | 09/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1200 | black | Reinstatement LAB System &amp; Issue ECC | TT_Rsrc | 06/01/2020 | 10/01/2020 | 05/01/2020 | 09/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1040 | black | Cold Commissioning Activites for First Fire | TT_Rsrc | 25/11/2019 | 13/02/2020 | 25/11/2019 | 23/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1050 | black | All Construction Activities Required for FF (inc. TOPS &amp; P/Ls) | TT_Rsrc | 25/11/2019 | 10/02/2020 | 25/11/2019 | 20/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1240 | black | Construction Completion / PL 'B's Cleared and handover of all TOPs required for FF | TT_Rsrc | 21/01/2020 | 21/01/2020 | 20/01/2020 | 20/01/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 14/01/2020
HCOM1270 | black | Required Dangerous Good Licenses in Place | TT_Rsrc | 23/01/2020 | 23/01/2020 | 23/01/2020 | 23/01/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 18/01/2020
HCOM1280 | black | Completion of all Cold Commissioning required for FF | TT_Rsrc | 24/01/2020 | 24/01/2020 | 23/01/2020 | 23/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1110 | black | CLP First Fire Review &amp; Green Light to Proceed | TT_Rsrc | 02/12/2019 | 06/12/2019 | 02/12/2019 | 06/12/2019 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 02/12/2019
HCOM1250 | black | Siemens First Fire Readiness Review &amp; Green Light to Proceed | TT_Rsrc | 22/01/2020 | 23/01/2020 | 22/01/2020 | 23/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1260 | black | CLP Green Light of Start Up review to proceed to First Fire | TT_Rsrc | 22/01/2020 | 23/01/2020 | 22/01/2020 | 23/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1290 | black | First Fire | TT_Rsrc | 27/01/2020 | 27/01/2020 | 24/01/2020 | 24/01/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 25/09/2019
HCOM1300 | black | GT FSNL Testing | TT_Rsrc | 27/01/2020 | 27/01/2020 | 25/01/2020 | 25/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1310 | black | Generator Protection | TT_Rsrc | 27/01/2020 | 28/01/2020 | 26/01/2020 | 27/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1320 | black | Generator Syncronisation | TT_Rsrc | 27/01/2020 | 27/01/2020 | 27/01/2020 | 27/01/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1330 | black | Steam Blow | TT_Rsrc | 28/01/2020 | 06/02/2020 | 28/01/2020 | 04/02/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1340 | black | Reinstatement of ZTB | TT_Rsrc | 05/02/2020 | 06/02/2020 | 05/02/2020 | 06/02/2020 | 0 | TK_Complete | CCGTD1_IPS | START_NO_EARLIER_THAN | 05/02/2020
HCOM1350 | black | Reinstatement of LBC40 | TT_Rsrc | 05/02/2020 | 06/02/2020 | 05/02/2020 | 06/02/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1390 | black | Reinstatement of MAX System | TT_Rsrc | 07/02/2020 | 07/02/2020 | 07/02/2020 | 07/02/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1410 | black | Valve Commissioing LBC412, LBC40, MAA, MAB MAC | TT_Rsrc | 10/02/2020 | 12/02/2020 | 08/02/2020 | 10/02/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1430 | black | SIL Test HP, LP, CRH | TT_Rsrc | 10/02/2020 | 11/02/2020 | 10/02/2020 | 11/02/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1440 | black | ATT Standsill / TGO | TT_Rsrc | 11/02/2020 | 11/02/2020 | 11/02/2020 | 11/02/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1470 | black | Preparation for unit start and Close all Construction Permits | TT_Rsrc | 02/03/2020 | 02/03/2020 | 02/03/2020 | 02/03/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1380 | black | Unit cooldown | TT_Rsrc | 05/02/2020 | 06/02/2020 | 05/02/2020 | 06/02/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1400 | black | Installation of SCR | TT_Rsrc | 07/02/2020 | 11/03/2020 | 07/02/2020 | 01/03/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1480 | black | Bypass operation &amp; Trevi Tests | TT_Rsrc | 03/03/2020 | 05/03/2020 | 03/03/2020 | 05/03/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1490 | black | Event: Unit S/D due to bearing 1 lift oil leak | TT_Rsrc | 05/03/2020 | 09/03/2020 | 05/03/2020 | 07/03/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1500 | black | Unit Startup | TT_Rsrc | 09/03/2020 | 09/03/2020 | 08/03/2020 | 08/03/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1510 | black | Event: Unit Trip: Unit Trip - HP Bypass failed to full open | TT_Rsrc | 09/03/2020 | 09/03/2020 | 09/03/2020 | 09/03/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1520 | black | Event: Forced Outage for HP Bypass Valve Damage Repair | TT_Rsrc | 10/03/2020 | 27/04/2020 | 10/03/2020 | 13/04/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1530 | black | Unit Restart - Bypass Operation | TT_Rsrc | 14/04/2020 | 15/04/2020 | 14/04/2020 | 15/04/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1540 | black | First Steam to ST &amp; ramp up to warm up speed | TT_Rsrc | 16/04/2020 | 16/04/2020 | 16/04/2020 | 16/04/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1550 | black | Steam Turbine ramp up to nominal speed &amp; initial loading | TT_Rsrc | 17/04/2020 | 20/04/2020 | 17/04/2020 | 18/04/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1560 | black | First CC Baseload operation | TT_Rsrc | 20/04/2020 | 20/04/2020 | 18/04/2020 | 18/04/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1570 | black | Outage - Combustor cold spot | TT_Rsrc | 20/04/2020 | 21/04/2020 | 19/04/2020 | 26/04/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1580 | red | Unit on Load | TT_Task | 01/06/2021 | 07/06/2021 | 27/04/2020 | 30/04/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1590 | red | Vibration trip test | TT_Task | 01/06/2021 | 07/06/2021 | 01/05/2020 | 01/05/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1600 | red | Unit Shutdown | TT_Task | 01/06/2021 | 07/06/2021 | 02/05/2020 | 03/05/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1610 | red | Unit on Load | TT_Task | 01/06/2021 | 07/06/2021 | 04/05/2020 | 04/05/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1620 | red | Unit CC Base Load | TT_Task | 01/06/2021 | 07/06/2021 | 05/05/2020 | 10/05/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1630 | red | Unit Trip @ 16 MW | TT_Task | 01/06/2021 | 07/06/2021 | 11/05/2020 | 11/05/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1640 | red | Unit CC Base Load | TT_Task | 01/06/2021 | 07/06/2021 | 11/05/2020 | 12/05/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1650 | red | Shut down outage for FSD Inspection | TT_Task | 01/06/2021 | 07/06/2021 | 13/05/2020 | 04/06/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1660 | red | Fuel Gas Line flushing Outage (Flushing cleaning I/P) | TT_Task | 01/06/2021 | 07/06/2021 | 05/06/2020 | 14/06/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1670 | red | Cold start / Load / shutdown | TT_Task | 01/06/2021 | 07/06/2021 | 15/06/2020 | 15/06/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1680 | red | Hot start / Load / SCR system testing / shutdown | TT_Task | 01/06/2021 | 07/06/2021 | 16/06/2020 | 17/06/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1690 | red | Shutdown (GT Offline Washing ) | TT_Task | 01/06/2021 | 07/06/2021 | 18/06/2020 | 18/06/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1700 | red | Offline washing / Warm start / Trip test/ Hot start/ Shutdown | TT_Task | 27/09/2021 | 01/10/2021 | 19/06/2020 | 19/06/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1710 | red | Hot start / shutdown / Hot start on the fly | TT_Task | 27/09/2021 | 01/10/2021 | 20/06/2020 | 20/06/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1720 | red | Unit on Load / shutdown | TT_Task | 27/09/2021 | 01/10/2021 | 21/06/2020 | 21/06/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1730 | red | Hot start/ Unit on Load | TT_Task | 27/09/2021 | 01/10/2021 | 22/06/2020 | 22/06/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1740 | red | Unit Minimum Load Operation | TT_Task | 27/09/2021 | 01/10/2021 | 23/06/2020 | 23/06/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1750 | red | Unit on Load / Excitation Test | TT_Task | 27/09/2021 | 01/10/2021 | 24/06/2020 | 24/06/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1760 | red | Unit on Load / Emergency Shutdown (FF Ring main water leak inside turbine hall) | TT_Task | 27/09/2021 | 01/10/2021 | 25/06/2020 | 26/06/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1770 | red | Warm Test / Excitation Test | TT_Task | 27/09/2021 | 01/10/2021 | 27/06/2020 | 27/06/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1780 | red | Unit on Load / Excitation test/ SCR Load Testing | TT_Task | 27/09/2021 | 01/10/2021 | 28/06/2020 | 28/06/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1790 | red | Load / SCR Load Testing | TT_Task | 27/09/2021 | 01/10/2021 | 29/06/2020 | 01/07/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1800 | red | SCR Load Testing | TT_Task | 27/09/2021 | 01/10/2021 | 02/07/2020 | 02/07/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1810 | red | Shutdown | TT_Task | 27/09/2021 | 01/10/2021 | 02/07/2020 | 02/07/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1820 | red | Automatic Hot Start on the Fly and verification of SCR system | TT_Task | 27/09/2021 | 01/10/2021 | 03/07/2020 | 03/07/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1830 | red | Unit on Load / Emissiong QAL2 Test | TT_Task | 27/09/2021 | 01/10/2021 | 04/07/2020 | 04/07/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1840 | red | Unit on Load / Emissiong QAL2 Test / Operational Reliability test Running | TT_Task | 27/09/2021 | 01/10/2021 | 05/07/2020 | 07/07/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1850 | red | shutdown for defect clearance before contractual RTR | TT_Task | 27/09/2021 | 01/10/2021 | 08/07/2020 | 10/07/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1860 | red | Cold Start / Load | TT_Task | 27/09/2021 | 01/10/2021 | 11/07/2020 | 11/07/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1870 | red | Unit on Load | TT_Task | 27/09/2021 | 01/10/2021 | 12/07/2020 | 12/07/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1880 | red | Contractual Reliability test Running | TT_Task | 27/09/2021 | 01/10/2021 | 13/07/2020 | 23/07/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1890 | red | Forced Outage - SCR Blower failure | TT_Task | 27/09/2021 | 01/10/2021 | 24/07/2020 | 25/07/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1900 | red | Phase 1 - Cold Start / Contractual Reliability test Running - (Start) | TT_Task | 27/09/2021 | 01/10/2021 | 26/07/2020 | 26/07/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1905 | red | Phase 1 - Contractual Reliability test Running | TT_Task | 27/09/2021 | 01/10/2021 | 27/07/2020 | 28/07/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1910 | red | Phase 1 - Contractual Reliability test Running / AGC test | TT_Task | 27/09/2021 | 01/10/2021 | 29/07/2020 | 30/07/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1920 | red | Phase 1 - Contractual Reliability test Running - (Complete) | TT_Task | 27/09/2021 | 01/10/2021 | 31/07/2020 | 05/08/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1930 | red | Phase 2 - Contractual Reliability test Running - (Start) | TT_Task | 27/09/2021 | 01/10/2021 | 06/08/2020 | 12/08/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1940 | red | Phase 2 - Contractual Reliability test Running / shutdown - (Complete) | TT_Task | 27/09/2021 | 01/10/2021 | 13/08/2020 | 13/08/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1950 | red | Shutdown - defect clearance | TT_Task | 01/06/2021 | 07/06/2021 | 14/08/2020 | 15/08/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1960 | red | Shutdown - IGV cleaning / calibration | TT_Task | 01/06/2021 | 07/06/2021 | 16/08/2020 | 16/08/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1970 | red | Shutdown - defect clearance | TT_Task | 01/06/2021 | 07/06/2021 | 17/08/2020 | 17/08/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1980 | red | Phase 3 - Cold Start / Contractual Reliability test Running (Start) | TT_Task | 01/06/2021 | 07/06/2021 | 18/08/2020 | 18/08/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM1990 | red | Phase 3 - Contractual Reliability test Running / internal Performance Test | TT_Task | 01/06/2021 | 07/06/2021 | 19/08/2020 | 20/08/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2000 | red | Phase 3 - Contractual Reliability test Running / Contracual Performance Test | TT_Task | 01/06/2021 | 07/06/2021 | 21/08/2020 | 22/08/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2010 | red | Phase 3 - Contractual Reliability test Running | TT_Task | 01/06/2021 | 07/06/2021 | 23/08/2020 | 27/06/2021 | 0 | TK_Complete | CCGTD1_IPS
HCOM2020 | red | Phase 3 - Contractual Reliability test Running / shutdown (complete) | TT_Task | 01/06/2021 | 07/06/2021 | 28/08/2020 | 28/08/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2030 | red | Shutdown - defect clearance | TT_Task | 01/06/2021 | 07/06/2021 | 29/08/2020 | 31/08/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2040 | red | Cold start test, internal Pefromance Test @ 50%CC | TT_Task | 01/06/2021 | 07/06/2021 | 01/09/2020 | 01/09/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2050 | red | Hot start on YOC Gas / shutdown | TT_Task | 01/06/2021 | 07/06/2021 | 02/09/2020 | 04/09/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2060 | red | Shutdown | TT_Task | 01/06/2021 | 07/06/2021 | 05/09/2020 | 05/09/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2070 | red | Shutdown / Preparation for Performance Test | TT_Task | 01/06/2021 | 07/06/2021 | 06/09/2020 | 09/09/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2080 | red | Shutdown | TT_Task | 08/06/2021 | 14/06/2021 | 10/09/2020 | 11/09/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2090 | red | Offline washing / cold start | TT_Task | 15/06/2021 | 21/06/2021 | 12/09/2020 | 12/09/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2100 | red | Unit on Load / internal Performance Test | TT_Task | 22/06/2021 | 28/06/2021 | 13/09/2020 | 14/09/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2110 | red | Unit on Load / Contractual Performance Test | TT_Task | 29/06/2021 | 05/07/2021 | 15/09/2020 | 16/09/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2120 | red | Shutdown / hot start / Contractual Performance Test | TT_Task | 06/07/2021 | 12/07/2021 | 17/09/2020 | 17/09/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2130 | red | Unit on Load / Contractual Performance Test | TT_Task | 13/07/2021 | 19/07/2021 | 18/09/2020 | 18/09/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2140 | red | Unit Load / Contractual Performance Test / shutdown | TT_Task | 20/07/2021 | 26/07/2021 | 19/09/2020 | 19/09/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2150 | red | Shutdown | TT_Task | 27/07/2021 | 02/08/2021 | 20/09/2020 | 20/09/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2160 | red | Cold Start / YOC gas commissioning | TT_Task | 03/08/2021 | 09/08/2021 | 21/09/2020 | 21/09/2020 | 0 | TK_Complete | CCGTD1_IPS
HCOM2170 | red | YOC gas commissioning | TT_Task | 10/08/2021 | 16/08/2021 | 22/09/2020 | 24/09/2020 | 0 | TK_Complete | CCGTD1_IPS
A3900 | red | Unit under Operation Control | TT_Task | 01/06/2021 | 07/06/2021 | 28/09/2020 | 18/02/2021 | 0 | TK_Complete | CCGTD1_IPS
A3500 | red | Unit Cool down | TT_Task | 01/06/2021 | 07/06/2021 | 19/02/2021 | 20/02/2021 | 0 | TK_Complete | CCGTD1_IPS
A3510 | red | Unit offline and Issue PTW's | TT_Task | 01/06/2021 | 07/06/2021 | 21/02/2021 | 21/02/2021 | 0 | TK_Complete | CCGTD1_IPS
A3520 | red | TB2 Handover to Siemens | TT_Task | 01/06/2021 | 07/06/2021 | 22/02/2021 | 22/02/2021 | 0 | TK_Complete | CCGTD1_IPS
A3530 | red | TB2 Blade Rectification Works outage | TT_Task | 01/06/2021 | 07/06/2021 | 22/02/2021 | 23/03/2021 | 0 | TK_Complete | CCGTD1_IPS
A3540 | red | GT Fuel Oil Barrel / Bucket testing | TT_Task | 01/06/2021 | 07/06/2021 | 14/03/2021 | 23/03/2021 | 0 | TK_Complete | CCGTD1_IPS
A3550 | red | H/O to Commissioning Team - GT TGO | TT_Task | 01/06/2021 | 07/06/2021 | 23/03/2021 | 23/03/2021 | 0 | TK_Complete | CCGTD1_IPS
A3560 | red | Unit Start -up Verification on fuel gas operation incl initial testing of SCR System | TT_Task | 01/06/2021 | 07/06/2021 | 24/03/2021 | 24/03/2021 | 0 | TK_Complete | CCGTD1_IPS
A3570 | red | SCR Testing | TT_Task | 01/06/2021 | 07/06/2021 | 25/03/2021 | 29/03/2021 | 0 | TK_Complete | CCGTD1_IPS
A3580 | red | SCR Testing -RTR Phase 1- Fuel Gas emissions (Nox &amp; NH3) and noise testing @ HRSG (with plant instrumentation) | TT_Task | 01/06/2021 | 07/06/2021 | 30/03/2021 | 30/03/2021 | 0 | TK_Complete | CCGTD1_IPS
A3590 | red | SCR Testing - RTR Phase 1 | TT_Task | 01/06/2021 | 07/06/2021 | 31/03/2021 | 06/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3600 | red | Fuel oil commissioning - Water purge testing | TT_Task | 01/06/2021 | 07/06/2021 | 07/04/2021 | 08/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3610 | red | Fuel oil commissioning - Start up Testing &amp; Initial Change over testing @20% | TT_Task | 01/06/2021 | 07/06/2021 | 09/04/2021 | 09/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3620 | red | Fuel oil commissioning - Partload combustion tuning (incl NoX Water Tuning) | TT_Task | 01/06/2021 | 07/06/2021 | 10/04/2021 | 11/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3630 | red | Fuel oil commissioning - Baseload combustion tuning (incl NoX Water Tuning) | TT_Task | 01/06/2021 | 07/06/2021 | 12/04/2021 | 12/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3640 | red | Fuel oil commissioning - inspection after initial Fuel Oil preparation (burner filters, MBN,MBU,EG) | TT_Task | 01/06/2021 | 07/06/2021 | 13/04/2021 | 13/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3650 | red | Fuel oil commissioning - Start up testing &amp; Initial Change over testing @ 20% | TT_Task | 01/06/2021 | 07/06/2021 | 14/04/2021 | 14/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3660 | red | Fuel oil commissioning - Start up testing &amp; Initial Change over testing @ 30% | TT_Task | 01/06/2021 | 07/06/2021 | 15/04/2021 | 15/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3670 | red | Fuel oil commissioning - Change over testing @ 40% | TT_Task | 01/06/2021 | 07/06/2021 | 16/04/2021 | 16/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3680 | red | Fuel oil commissioning - Change over testing @ 50% | TT_Task | 01/06/2021 | 07/06/2021 | 17/04/2021 | 17/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3690 | red | Fuel oil commissioning - Change over testing @ 60% | TT_Task | 01/06/2021 | 07/06/2021 | 18/04/2021 | 18/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3700 | red | Fuel oil commissioning - Change over testing @ 70% | TT_Task | 01/06/2021 | 07/06/2021 | 19/04/2021 | 19/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3710 | red | Fuel oil commissioning - Change over testing @ 70% | TT_Task | 01/06/2021 | 07/06/2021 | 20/04/2021 | 20/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3720 | red | Fuel oil commissioning - Inspection of Fuel oil System | TT_Task | 01/06/2021 | 07/06/2021 | 21/04/2021 | 21/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3730 | red | Fuel oil commissioning - Start-up optimisation - high load transfer testing | TT_Task | 01/06/2021 | 07/06/2021 | 22/04/2021 | 23/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3740 | red | Fuel oil commissioning - GT Fuel Gas Baseload operation and automatic changeover to fuel oil operation | TT_Task | 01/06/2021 | 07/06/2021 | 24/04/2021 | 26/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3750 | red | Fuel oil commissioning - Unit Start up and loading to baseload | TT_Task | 01/06/2021 | 07/06/2021 | 27/04/2021 | 27/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3760 | red | Fuel oil commissioning - Phase - C 910 Automatic Start-up of the unit with secondary fuel | TT_Task | 01/06/2021 | 07/06/2021 | 28/04/2021 | 28/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3770 | red | Fuel oil commissioning - Phase - C 932 Load change rates of unit with secondary fuel | TT_Task | 01/06/2021 | 07/06/2021 | 29/04/2021 | 29/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3780 | red | Fuel oil commissioning - Phase - C 966 Fuel changeover in combined cycle mode | TT_Task | 01/06/2021 | 07/06/2021 | 30/04/2021 | 30/04/2021 | 0 | TK_Complete | CCGTD1_IPS
A3790 | red | Fuel oil commissioning - Unit Shutdown | TT_Task | 01/06/2021 | 07/06/2021 | 01/05/2021 | 01/05/2021 | 0 | TK_Complete | CCGTD1_IPS
A3800 | red | Fuel oil commissioning - Phase - C 910 Automatic Start-up of the unit with secondary fuel | TT_Task | 01/06/2021 | 07/06/2021 | 02/05/2021 | 02/05/2021 | 0 | TK_Complete | CCGTD1_IPS
A3810 | red | Fuel oil commissioning - Phase - C 932 Load change rates of unit with secondary fuel | TT_Task | 01/06/2021 | 07/06/2021 | 03/05/2021 | 03/05/2021 | 0 | TK_Complete | CCGTD1_IPS
A3820 | red | Fuel oil commissioning - Phase - C 966 Fuel changeover in combined cycle mode | TT_Task | 01/06/2021 | 07/06/2021 | 04/05/2021 | 04/05/2021 | 0 | TK_Complete | CCGTD1_IPS
A3830 | red | Performance Test on Oil - Phase - C 956 maximum caoacity of the unit with secondary fuel | TT_Task | 01/06/2021 | 07/06/2021 | 05/05/2021 | 06/05/2021 | 0 | TK_Complete | CCGTD1_IPS
A3840 | red | S/D outage - PT and FO Burner Removal | TT_Task | 01/06/2021 | 07/06/2021 | 07/05/2021 | 10/05/2021 | 0 | TK_Complete | CCGTD1_IPS
A3850 | red | S/U for PT - Fuel Oil Performance Testing (@100%) | TT_Task | 01/06/2021 | 07/06/2021 | 11/05/2021 | 11/05/2021 | 0 | TK_Complete | CCGTD1_IPS
A3860 | red | Restart of Unit - Start SCR RTR - Phase 2 | TT_Task | 01/06/2021 | 07/06/2021 | 12/05/2021 | 12/05/2021 | 0 | TK_Complete | CCGTD1_IPS
A3870 | red | SCR RTR Phase 2 | TT_Task | 01/06/2021 | 07/06/2021 | 13/05/2021 | 22/05/2021 | 0 | TK_Complete | CCGTD1_IPS
A3880 | red | SCR RTR Phase 3 | TT_Task | 01/06/2021 | 07/06/2021 | 23/05/2021 | 30/05/2021 | 0 | TK_Complete | CCGTD1_IPS
A3890 | red | SCR RTR Phase 3 - Handover tp CPL - Section 6 part 2 | TT_Task | 01/06/2021 | 07/06/2021 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete | CCGTD1_IPS
SI1---2-40 | blue | (6c) COMPLETION AND SIGN OFF OF ALL CHECK SHEET TO CONFIRM COMPLETION OF HOT COMMISSIONING | TT_FinMile | 31/05/2021 | 31/05/2021 | 31/05/2021 | 31/05/2021 | 0 | TK_Complete | CCGTD1_IPS
SI1---2-45 | blue | (6d) COMPLETION OF O&amp;M MANUALS | TT_FinMile | 16/07/2021 | 16/07/2021 |  |  | 0 | TK_NotStart | CCGTD1_IPS | MUST_FINISH_ON | 16/07/2021
SI1---2-50 | blue | (6e) COMPLETION OF AS-BUILT DRAWINGS AND OTHER COMPLETION DOCUMENTS | TT_FinMile | 16/07/2021 | 16/07/2021 |  |  | 0 | TK_NotStart | CCGTD1_IPS | MUST_FINISH_ON | 16/07/2021
SI1---3-53 | blue | (BOP6) COMPLETION AND SIGN OFF OF ALL CHECK SHEET TO CONFIRM COMPLETION OF HOT COMMISSIONING | TT_FinMile | 16/07/2021 | 16/07/2021 |  |  | 0 | TK_NotStart | CCGTD1_IPS | MUST_FINISH_ON | 16/07/2021
SI-1102-40 | blue | FINAL OPERATING AND MAINTENANCE DOCUMENTATION (O&amp;M) | TT_FinMile | 16/07/2021 | 16/07/2021 |  |  | 0 | TK_NotStart | CCGTD1_IPS | MUST_FINISH_ON | 16/07/2021
SI-92-2-96 | blue | MARK-UPS FROM SITE AVAILABLE | TT_FinMile | 16/07/2021 | 16/07/2021 |  |  | 0 | TK_NotStart | CCGTD1_IPS | MUST_FINISH_ON | 16/07/2021
SP-92-2-45 | black | AS BUILT DOCUMENTATION [submittal to customer] | TT_Mile | 16/07/2021 | 16/07/2021 |  |  | 8 | TK_NotStart | CCGTD1_IPS | START_NO_EARLIER_THAN | 16/07/2021
PCS00010 | blue | Post TB2 P/L | TT_FinMile | 31/05/2022 | 31/05/2022 |  |  | 0 | TK_NotStart | CCGTD1_IPS | FINISH_ON | 31/05/2022